## Sheet1
Distrito Geografico | Nombre Escuela | Tipo de Proyecto | Descripción del Proyecto | Fase del Proyecto | Estado del Proyecto | Fecha de Inicio | Fecha de Fin Proyectada | Fecha de Fin Real | Presupuesto del Proyecto | Presupuesto Final Estimado | Cantidad Real Gastada
1 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2021-04-13 | 2021-09-13 | 2021-07-01 | 68660 | 70899 | 70899
1 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2021-07-06 | 2021-12-07 | 2021-11-29 | 343300 | 362786 | 298189
1 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-07-18 | 2024-07-16 |  | 7724250 | 7114234 | 4049545
1 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-07-18 | 2024-07-16 |  | 480620 | 152212 | 151513
1 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-06-22 | 2023-10-23 | 2023-07-06 | 4240 | 1518 | 1518
1 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-06 | 2024-01-03 | 2023-12-13 | 19080 | 6074 | 6074
1 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-05-27 | 2025-05-26 |  | 245920 | 224898 | 4211
1 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-05-27 | 2025-05-26 |  | 49844 | 31896 | 9000
1 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2021-05-26 | 2021-10-12 | 2022-01-21 | 124674 | 160738 | 160738
1 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2022-01-21 | 2022-06-22 | 2022-05-10 | 613841 | 521613 | 513485
1 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 2022-09-19 | 2024-06-09 |  | 12987707 | 12184833 | 11331962
1 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 2022-09-19 | 2024-06-09 |  | 944133 | 297273 | 268223
1 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2021-04-22 | 2021-09-07 | 2021-12-21 | 195550 | 193921 | 191326
1 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2021-12-22 | 2022-06-10 | 2022-09-16 | 977750 | 605106 | 444554
1 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 2023-08-07 | 2025-08-05 |  | 21999375 | 19954646 | 5905863
1 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2023-08-07 | 2025-08-05 |  | 1369882 | 204592 | 146352
1 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | Scope | Complete | 2018-10-23 | 2019-03-13 | 2020-01-24 | 118770 | 254063 | 253255
1 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | Design | Complete | 2020-01-24 | 2020-06-24 | 2021-05-05 | 586080 | 582536 | 525486
1 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | Construction | Complete | 2021-08-13 | 2024-08-11 | 2024-08-14 | 12514695 | 12763307 | 11212816
1 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | CM,F&E | Complete | 2021-08-13 | 2024-08-11 | 2024-08-14 | 889665 | 1281548 | 1217784
1 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-06-25 | 2020-10-26 | 2020-07-21 | 3482 | 4450 | 4450
1 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-21 | 2021-01-15 | 2021-03-30 | 15667 | 17800 | 17800
1 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-24 | 2023-03-19 |  | 201929 | 188076 | 169532
1 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-24 | 2023-03-19 |  | 234839 | 261400 | 256059
1 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | Scope | Complete | 2018-10-19 | 2019-12-30 | 2020-03-31 | 294023 | 340316 | 330125
1 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | Design | Complete | 2020-12-07 | 2021-05-10 | 2021-05-18 | 1450039 | 1134398 | 1038316
1 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | Construction | In-Progress | 2022-07-05 | 2024-12-20 |  | 31392155 | 29698478 | 26293299
1 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | CM,F&E | In-Progress | 2022-07-05 | 2024-12-20 |  | 2211023 | 650299 | 599535
1 | J.H.S. 292 - MANHATTAN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2021-04-30 | 2021-07-30 | 2021-07-22 | 27380 | 42814 | 42814
1 | J.H.S. 292 - MANHATTAN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2021-08-02 | 2022-02-07 | 2022-02-01 | 136900 | 171027 | 154403
1 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2022-05-16 | 2022-09-16 | 2022-08-02 | 53927 | 78550 | 78550
1 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-08-08 | 2023-02-13 | 2023-05-08 | 259893 | 201922 | 184167
1 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | Scope | Complete | 2019-04-09 | 2019-08-22 | 2019-09-20 | 22622 | 11835 | 11835
1 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | Design | Complete | 2019-10-23 | 2020-03-27 | 2020-06-08 | 113110 | 118178 | 114874
1 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | Construction | In-Progress | 2021-10-18 | 2023-04-10 |  | 2544967 | 2359829 | 1955510
1 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | CM,F&E | In-Progress | 2021-10-18 | 2023-04-10 |  | 158354 | 580740 | 498649
1 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-07 | 2022-11-04 | 2022-07-27 | 3838 | 2363 | 2363
1 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-07-27 | 2023-01-25 | 2022-09-21 | 17271 | 9450 | 9450
1 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-04-29 |  | 222607 | 204544 | 175427
1 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-04-29 |  | 117815 | 102920 | 71112
1 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2019-06-20 | 2019-11-05 | 2019-12-23 | 111561 | 221145 | 217082
1 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2020-01-08 | 2020-06-09 | 2020-06-30 | 551747 | 733548 | 663725
1 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2021-05-24 | 2023-05-23 |  | 11889967 | 11695625 | 9428092
1 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-05-24 | 2023-05-23 |  | 826395 | 882597 | 780943
1 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 2020-02-11 | 2020-06-25 | 2024-01-02 | 74829 | 139951 | 78818
1 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 2020-12-04 | 2021-05-24 | 2024-01-02 | 2354 | 22197 | 15280
1 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-01-07 | 2021-05-07 | 2021-06-15 | 39541 | 50839 | 50800
1 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2021-07-15 | 2021-12-16 | 2022-04-21 | 186049 | 145846 | 106797
1 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-01-15 | 2026-01-03 |  | 3178051 | 2811396 | 65435
1 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-01-15 | 2026-01-03 |  | 364189 | 62879 | 62879
1 | P.S. 110 - MANHATTAN | SCA CIP | FACADE REMEDIATION @M110 / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2021-08-04 | 2021-12-21 | 2022-02-02 | 73176 | 195932 | 177643
1 | P.S. 110 - MANHATTAN | SCA CIP | FACADE REMEDIATION @M110 / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 2022-06-01 | 2022-11-22 | 2023-05-12 | 355589 | 310017 | 290581
1 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2018-10-23 | 2019-03-13 | 2019-01-18 | 371656 | 171214 | 171214
1 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2019-01-22 | 2019-06-21 | 2019-05-17 | 1486620 | 826156 | 771304
1 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2019-10-21 | 2022-08-15 |  | 27874124 | 27152807 | 21280871
1 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2019-10-21 | 2022-08-15 |  | 1734390 | 717658 | 663851
1 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Scope | Complete | 2018-01-24 | 2021-01-20 | 2021-05-19 | 15710 | 29475 | 29475
1 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Design | Complete | 2021-07-07 | 2021-12-10 | 2022-03-03 | 62520 | 98375 | 74465
1 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Construction | In-Progress | 2023-05-17 | 2024-05-15 |  | 723155 | 753545 | 505835
1 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 2023-05-17 | 2024-05-15 |  | 151715 | 149779 | 73298
1 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-11 | 2022-11-08 | 2022-07-28 | 5326 | 2660 | 2660
1 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-07-28 | 2023-01-26 | 2022-09-21 | 23966 | 10640 | 10640
1 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-04-29 |  | 308893 | 280585 | 243384
1 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-04-29 |  | 165385 | 134685 | 102877
1 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2018-10-24 | 2019-03-14 | 2019-01-18 | 504775 | 543899 | 505763
1 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2019-01-22 | 2019-06-21 | 2022-09-16 | 2518835 | 2354532 | 1756812
1 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2023-06-05 | 2026-06-03 |  | 56237200 | 51029130 | 4601408
1 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2023-06-05 | 2026-06-03 |  | 3571289 | 1036553 | 1031764
1 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-06 | 2022-11-03 | 2022-07-22 | 4336 | 4223 | 4223
1 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-07-22 | 2023-01-20 | 2022-09-21 | 19513 | 17729 | 17729
1 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-04-29 |  | 251500 | 232972 | 197652
1 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-04-29 |  | 149910 | 133293 | 101485
1 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2020-05-22 | 2020-11-19 | 2020-08-19 | 86400 | 152029 | 152029
1 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2020-09-01 | 2021-06-15 | 2021-04-06 | 432000 | 390753 | 347885
1 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2021-09-13 | 2023-06-04 |  | 9720000 | 10321594 | 7138602
1 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-09-13 | 2023-06-04 |  | 604800 | 494522 | 449493
1 | UNIVERSITY NEIGHBORHOOD HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / PARAPETS / ROOFS | Scope | Complete | 2023-06-22 | 2023-11-07 | 2024-03-26 | 154686 | 233284 | 88837
1 | UNIVERSITY NEIGHBORHOOD HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / PARAPETS / ROOFS | Design | In-Progress | 2024-04-17 | 2024-09-18 |  | 720869 | 720869 | 28699
2 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | Scope | Complete | 2018-10-12 | 2019-03-04 | 2019-01-03 | 373649 | 159135 | 159120
2 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | Design | Complete | 2019-01-03 | 2019-06-05 | 2019-05-14 | 1494600 | 1080167 | 939756
2 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | Construction | In-Progress | 2019-10-09 | 2021-10-07 |  | 28023750 | 32377844 | 25501579
2 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | CM,F&E | In-Progress | 2019-10-09 | 2021-10-07 |  | 1743699 | 2256085 | 2133432
2 | P.S. 1 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-22 | 2024-05-20 | 2024-01-22 | 5982 | 1725 | 1725
2 | P.S. 1 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-21 | 2024-09-16 | 2024-08-13 | 26919 | 6899 | 6899
2 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | Scope | Complete | 2019-02-14 | 2019-06-17 | 2019-10-29 | 113406 | 3077 | 3077
2 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | Design | Complete | 2019-11-25 | 2020-04-28 | 2022-03-22 | 559432 | 344697 | 333251
2 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | Construction | In-Progress | 2022-08-15 | 2024-08-13 |  | 11930288 | 10665990 | 6430896
2 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | CM,F&E | In-Progress | 2022-08-15 | 2024-08-13 |  | 850799 | 55085 | 54870
2 | P.S. 2 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-02-26 | 2024-06-25 | 2024-03-20 | 3740 | 945 | 945
2 | P.S. 2 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-20 | 2024-09-13 | 2024-08-13 | 16830 | 3780 | 3780
2 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-06-26 | 2023-10-25 | 2023-07-06 | 4065 | 1585 | 1585
2 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-06 | 2024-01-03 | 2023-10-18 | 18290 | 6342 | 6342
2 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-28 | 2024-12-23 |  | 235742 | 221652 | 8443
2 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-28 | 2024-12-23 |  | 72482 | 54237 | 32288
2 | P.S. 6 - MANHATTAN | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2022-01-31 | 2022-03-28 | 2022-04-04 | 60518 | 89611 | 80611
2 | P.S. 6 - MANHATTAN | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 2023-06-15 | 2024-03-15 |  | 887607 | 549068 | 460949
2 | P.S. 6 - MANHATTAN | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2023-06-15 | 2024-03-15 |  | 201380 | 225541 | 142394
2 | P.P.A.S. - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-03-28 | 2024-07-29 | 2024-04-16 | 5043 | 1294 | 1294
2 | P.P.A.S. - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-16 | 2024-10-10 | 2024-09-25 | 22694 | 5176 | 5176
2 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | Scope | Complete | 2019-02-28 | 2019-07-29 | 2019-10-03 | 39007 | 69397 | 69397
2 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | Design | Complete | 2019-11-13 | 2020-04-16 | 2021-09-01 | 192928 | 234471 | 226749
2 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | Construction | In-Progress | 2022-08-15 | 2024-08-13 |  | 4158625 | 3864692 | 3185214
2 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | CM,F&E | In-Progress | 2022-08-15 | 2024-08-13 |  | 288851 | 662021 | 644892
2 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-06-06 | 2022-10-04 | 2022-09-07 | 6015 | 5355 | 5355
2 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-09-07 | 2023-03-08 | 2023-03-08 | 27067 | 21421 | 21421
2 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-03 | 2024-08-28 |  | 348863 | 311134 | 2283
2 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-03 | 2024-08-28 |  | 102777 | 79102 | 13121
2 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 2021-03-03 | 2021-07-16 | 2022-01-25 | 319430 | 368295 | 365506
2 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 2022-01-25 | 2022-06-24 | 2022-05-10 | 1597150 | 1149263 | 974622
2 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | In-Progress | 2023-08-10 | 2026-02-04 |  | 35935875 | 32552762 | 7105683
2 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | In-Progress | 2023-08-10 | 2026-02-04 |  | 2237013 | 211198 | 211198
2 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Design | Complete | 2021-06-15 | 2021-12-02 | 2022-01-12 | 43862 | 72006 | 70456
2 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Construction | In-Progress | 2022-07-22 | 2023-07-21 |  | 643305 | 595403 | 327835
2 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | CM,F&E | In-Progress | 2022-07-22 | 2023-07-21 |  | 43862 | 64832 | 56273
2 | P.S. 40 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Design | Complete | 2022-11-02 | 2023-03-02 | 2023-01-20 | 56890 | 79380 | 70380
2 | P.S. 40 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 2023-06-13 | 2024-03-13 |  | 834386 | 713992 | 310616
2 | P.S. 40 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2023-06-13 | 2024-03-13 |  | 147027 | 182675 | 113611
2 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2019-06-27 | 2019-11-13 | 2020-02-11 | 172368 | 155663 | 153802
2 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2020-02-11 | 2020-07-13 | 2021-05-14 | 860032 | 584811 | 513457
2 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-09-05 | 2026-01-01 |  | 19194327 | 17257355 | 5604861
2 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-09-05 | 2026-01-01 |  | 1221137 | 113881 | 113485
2 | P.S. 41 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-03-27 | 2024-07-26 | 2024-04-16 | 4394 | 1614 | 1614
2 | P.S. 41 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-16 | 2024-10-10 | 2024-09-25 | 19773 | 6457 | 6457
2 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2019-07-17 | 2019-12-03 | 2020-01-23 | 129854 | 175514 | 169963
2 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2020-01-23 | 2020-06-23 | 2020-06-30 | 643030 | 611673 | 556378
2 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2022-02-28 | 2024-03-28 |  | 13927885 | 13316419 | 10517795
2 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-02-28 | 2024-03-28 |  | 955827 | 369685 | 337723
2 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-03 | 2023-11-01 | 2023-07-12 | 4335 | 1674 | 1674
2 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-12 | 2024-01-09 | 2023-10-18 | 19510 | 6698 | 6698
2 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-28 | 2024-12-23 |  | 251458 | 227745 | 853
2 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-28 | 2024-12-23 |  | 74914 | 55031 | 31619
2 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2019-12-18 | 2020-03-20 | 2020-03-16 | 27730 | 54369 | 54369
2 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2021-04-20 | 2021-10-21 | 2022-08-03 | 138650 | 355523 | 224041
2 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2023-05-01 | 2024-10-21 |  | 3119625 | 3000612 | 2339451
2 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2023-05-01 | 2024-10-21 |  | 194110 | 314895 | 193770
2 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | Scope | Complete | 2022-04-29 | 2022-09-14 | 2022-12-07 | 247331 | 323214 | 323204
2 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | Design | Complete | 2022-12-22 | 2023-05-25 | 2023-04-28 | 1236651 | 935117 | 761396
2 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | Construction | In-Progress | 2023-08-21 | 2026-02-15 |  | 27824626 | 24876373 | 4835599
2 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | CM,F&E | In-Progress | 2023-08-21 | 2026-02-15 |  | 1731310 | 230056 | 229809
2 | P.S. 151 - MANHATTAN | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2023-12-12 | 2024-04-29 | 2024-07-19 | 54409 | 139006 | 65071
2 | P.S. 151 - MANHATTAN | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | In-Progress | 2024-07-30 | 2025-01-02 |  | 254254 | 254254 | 5943
2 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-06-30 | 2020-10-29 | 2020-07-13 | 2081 | 6193 | 6193
2 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-13 | 2021-01-07 | 2021-03-30 | 9363 | 24772 | 24772
2 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-24 | 2023-03-19 |  | 120678 | 116860 | 102313
2 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-24 | 2023-03-19 |  | 118762 | 153437 | 149011
2 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | RESO A LOCKER ROOM UPGRADE | Design | Complete | 2024-01-16 | 2024-05-30 | 2024-05-22 | 195787 | 126845 | 119106
2 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 2023-10-18 | 2024-01-22 | 2024-01-09 | 5615 | 5615 | 130
2 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | Complete | 2024-01-12 | 2024-05-15 | 2024-05-22 | 521 | 521 | 521
2 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-20 | 2023-11-20 | 2023-08-10 | 4160 | 4833 | 4833
2 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-10 | 2024-02-08 | 2023-12-13 | 18720 | 19334 | 19334
2 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-05-27 | 2025-05-26 |  | 241280 | 220457 | 0
2 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-05-27 | 2025-05-26 |  | 75672 | 59055 | 9635
2 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY 21 RESO A (MA) FITNESS ROOM / PATH OF TRAVEL RESO A FITNESS ROOM | Design | Complete | 2021-11-04 | 2022-03-10 | 2022-04-14 | 90524 | 94457 | 79543
2 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY 21 RESO A (MA) FITNESS ROOM / PATH OF TRAVEL RESO A FITNESS ROOM | Construction | In-Progress | 2024-08-07 | 2025-07-02 |  | 1327691 | 1269565 | 63185
2 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY 21 RESO A (MA) FITNESS ROOM / PATH OF TRAVEL RESO A FITNESS ROOM | CM,F&E | In-Progress | 2024-08-07 | 2025-07-02 |  | 90524 | 131835 | 39472
2 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-08-10 | 2023-12-12 | 2023-08-22 | 4480 | 3704 | 3704
2 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-22 | 2024-02-21 | 2023-12-13 | 20160 | 14814 | 14814
2 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-05-27 | 2025-05-26 |  | 259840 | 237982 | 975
2 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-05-27 | 2025-05-26 |  | 52424 | 33093 | 8901
2 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY16 RESO A GREEN ROOF | Design | Complete | 2016-05-18 | 2016-10-19 | 2019-05-17 | 39714 | 183531 | 183531
2 | I.S. 114 - MANHATTAN | SCA CIP RESOA | RESO A- DANCE STUDIO | Design | Complete | 2021-08-09 | 2022-01-12 | 2022-08-08 | 45750 | 111363 | 80911
2 | I.S. 114 - MANHATTAN | SCA CIP RESOA | RESO A- DANCE STUDIO | Construction | In-Progress | 2024-09-16 | 2025-06-12 |  | 671000 | 472674 | 0
2 | I.S. 114 - MANHATTAN | SCA CIP RESOA | RESO A- DANCE STUDIO | CM,F&E | In-Progress | 2024-09-16 | 2025-06-12 |  | 45750 | 51899 | 7277
2 | P.S. 116 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | In-Progress | 2024-06-14 | 2024-10-31 |  | 151387 | 170760 | 34364
2 | P.S. 116 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2023-11-17 | 2024-04-05 |  | 57000 | 54853 | 34032
2 | P.S. 116 - MANHATTAN | SCA CIP RESOA | RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Design | In-Progress | 2024-08-19 | 2024-12-19 |  | 7724 | 3744 | 3744
2 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2020-05-15 | 2020-11-12 | 2020-10-23 | 154300 | 247640 | 247640
2 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2020-10-29 | 2021-06-15 | 2021-07-01 | 771500 | 449392 | 449392
2 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2022-09-06 | 2024-08-05 |  | 17358751 | 15759814 | 12447762
2 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-09-06 | 2024-08-05 |  | 1080100 | 249881 | 247568
2 | P.S. 124 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-08-07 | 2023-12-22 | 2023-12-26 | 42000 | 53366 | 11831
2 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2018-10-23 | 2019-03-13 | 2019-01-10 | 279097 | 290155 | 290155
2 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2019-01-16 | 2019-06-17 | 2020-05-29 | 1385660 | 859901 | 842340
2 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2021-07-15 | 2024-07-13 |  | 30327154 | 28152186 | 16661742
2 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-07-15 | 2024-07-13 |  | 2027404 | 565468 | 547075
2 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-17 | 2023-07-18 | 2023-03-24 | 5645 | 2617 | 2617
2 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-24 | 2023-09-19 | 2023-05-08 | 25403 | 10465 | 10465
2 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-03 | 2024-08-28 |  | 327417 | 294319 | 1441
2 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-03 | 2024-08-28 |  | 64949 | 37932 | 7448
2 | P.S. 130 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-06-12 | 2024-10-11 | 2024-06-13 | 3380 | 2286 | 2286
2 | P.S. 130 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-06-13 | 2024-12-11 |  | 15208 | 15208 | 9143
2 | P.S. 130 - MANHATTAN | SCA CIP | ROOFS | Scope | Complete | 2024-09-17 | 2024-09-17 | 2024-09-17 | 3000 | 0 | 0
2 | P.S. 130 - MANHATTAN | SCA CIP | ROOFS | Design | In-Progress | 2024-09-17 | 2025-01-17 |  | 12000 | 12000 | 0
2 | P.S. 130 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-08-15 | 2023-01-03 | 2022-12-08 | 36000 | 52960 | 51692
2 | P.S. 130 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-11-07 | 2024-08-02 |  | 528000 | 489278 | 10914
2 | P.S. 130 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-11-07 | 2024-08-02 |  | 36000 | 56007 | 18860
2 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Scope | Complete | 2020-09-09 | 2021-01-20 | 2021-10-01 | 30137 | 38340 | 38340
2 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Design | Complete | 2021-10-13 | 2022-04-19 | 2022-07-12 | 145516 | 225920 | 189181
2 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Construction | In-Progress | 2023-05-03 | 2025-05-01 |  | 2827207 | 2755476 | 2098615
2 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | CM,F&E | In-Progress | 2023-05-03 | 2025-05-01 |  | 249701 | 297198 | 263262
2 | I.S. 167 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 2024-01-08 | 2024-05-31 | 2024-08-20 | 31610 | 51774 | 31855
2 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | Scope | Complete | 2018-10-12 | 2020-06-12 | 2020-05-26 | 61639 | 88445 | 88445
2 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | Design | Complete | 2020-05-26 | 2020-09-18 | 2020-12-30 | 301587 | 179754 | 150125
2 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | Construction | In-Progress | 2023-07-10 | 2025-01-07 |  | 6214007 | 5718517 | 1539771
2 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | CM,F&E | In-Progress | 2023-07-10 | 2025-01-07 |  | 481042 | 321734 | 311527
2 | P.S. 183 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Design | Complete | 2018-12-03 | 2019-04-29 | 2019-04-01 | 36000 | 58475 | 49903
2 | P.S. 183 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 2019-06-14 | 2020-03-09 |  | 528000 | 365454 | 352053
2 | P.S. 183 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | CM,F&E | In-Progress | 2019-06-14 | 2020-03-09 |  | 36000 | 70206 | 69536
2 | P.S. 183 - MANHATTAN | SCA CIP RESOA | NYS IPDVS NEW INSTALLATION | Design | Complete | 2023-05-26 | 2023-11-24 | 2023-08-30 | 30000 | 2836 | 2836
2 | P.S. 183 - MANHATTAN | SCA CIP RESOA | NYS IPDVS NEW INSTALLATION | Construction | In-Progress | 2024-02-09 | 2025-01-03 |  | 440000 | 199047 | 4124
2 | P.S. 183 - MANHATTAN | SCA CIP RESOA | NYS IPDVS NEW INSTALLATION | CM,F&E | In-Progress | 2024-02-09 | 2025-01-03 |  | 63657 | 147971 | 115170
2 | P.S. 290 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2015-12-02 | 2018-05-04 | 2018-02-21 | 76099 | 83507 | 83507
2 | P.S. 290 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2018-02-28 | 2018-07-30 | 2018-05-04 | 291517 | 386048 | 366697
2 | P.S. 290 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | Complete | 2022-08-08 | 2024-10-05 | 2024-04-30 | 4310303 | 4022455 | 3437934
2 | P.S. 290 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 2022-08-08 | 2024-10-05 | 2024-04-30 | 522514 | 533996 | 529604
2 | P.S. 290 - MANHATTAN | SCA CIP RESOA | RESO A ROOFTOP PLAYGROUND | Design | Complete | 2023-02-06 | 2023-07-10 | 2023-12-26 | 643687 | 234030 | 15990
2 | P.S. 290 - MANHATTAN | SCA CIP RESOA | RESO A ROOFTOP PLAYGROUND | Construction | In-Progress | 2024-08-02 | 2026-08-01 |  | 9440749 | 8854882 | 144772
2 | P.S. 290 - MANHATTAN | SCA CIP RESOA | RESO A ROOFTOP PLAYGROUND | CM,F&E | In-Progress | 2024-08-02 | 2026-08-01 |  | 643687 | 86230 | 32893
2 | P.S. 77 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-11-14 | 2024-05-10 | 2024-03-05 | 27000 | 19762 | 19762
2 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2018-03-12 | 2018-07-25 | 2019-12-16 | 28750 | 95254 | 93861
2 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2020-01-08 | 2020-06-09 | 2020-06-26 | 143751 | 187935 | 120611
2 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2021-07-22 | 2023-04-12 |  | 3234403 | 3144565 | 2276635
2 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-07-22 | 2023-04-12 |  | 201252 | 396495 | 380792
2 | P.S. 234 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-06-10 | 2024-10-09 | 2024-06-14 | 3954 | 911 | 911
2 | P.S. 234 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-06-14 | 2024-12-12 |  | 17792 | 17792 | 3646
2 | P.S. 234 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2024-07-01 | 2024-09-30 | 2024-08-21 | 30637 | 756 | 756
2 | P.S. 234 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | In-Progress | 2024-08-22 | 2025-02-28 |  | 142975 | 142975 | 3024
2 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 2022-03-21 | 2022-07-19 | 2022-04-12 | 3341 | 5686 | 5686
2 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 2022-04-12 | 2022-10-05 | 2022-07-19 | 15033 | 22743 | 22743
2 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 2023-03-09 | 2024-02-01 |  | 193762 | 178974 | 165938
2 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 2023-03-09 | 2024-02-01 |  | 166229 | 159600 | 115450
2 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-23 | 2023-07-24 | 2023-03-28 | 4130 | 2003 | 2003
2 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-28 | 2023-09-21 | 2023-05-05 | 18586 | 8012 | 8012
2 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2024-02-09 | 2025-01-03 |  | 239549 | 209434 | 160
2 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2024-02-09 | 2025-01-03 |  | 44399 | 112838 | 112838
2 | P.S./I.S. 276 - MANHATTAN | SCA CIP | IDA INTERIOR SPACES / IDA FLOOD ELIMINATION | Scope | Complete | 2022-01-19 | 2022-05-19 | 2023-04-06 | 18284 | 40499 | 39644
2 | P.S./I.S. 276 - MANHATTAN | SCA CIP | IDA INTERIOR SPACES / IDA FLOOD ELIMINATION | Design | Complete | 2023-04-24 | 2023-10-24 | 2024-02-21 | 82275 | 61758 | 55851
2 | I.S. 896 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2023-09-28 | 2024-02-05 | 2024-07-22 | 30000 | 43563 | 41415
2 | M.S. 297 | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-07-05 | 2024-11-20 |  | 6000 | 5013 | 5013
2 | P.S. 51 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Design | Complete | 2021-10-01 | 2022-03-24 | 2022-07-15 | 15052 | 29640 | 29640
2 | P.S. 51 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Construction | In-Progress | 2023-04-17 | 2024-01-11 |  | 220759 | 201665 | 0
2 | P.S. 51 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | CM,F&E | In-Progress | 2023-04-17 | 2024-01-11 |  | 15052 | 37912 | 36040
2 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | DEFECTIVE POOL FOUNDATION WALLS | Scope | Complete | 2015-06-17 | 2015-11-17 | 2016-06-22 | 176680 | 154529 | 154529
2 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | DEFECTIVE POOL FOUNDATION WALLS | Design | Complete | 2019-04-16 | 2019-10-18 | 2020-06-30 | 883400 | 521017 | 480422
2 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Scope | Complete | 2018-08-01 | 2018-12-18 | 2018-11-21 | 98775 | 132497 | 132497
2 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Design | Complete | 2019-02-06 | 2019-07-09 | 2019-09-18 | 492101 | 415286 | 345032
2 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Construction | In-Progress | 2020-11-16 | 2022-11-15 |  | 10918714 | 12766835 | 11383990
2 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | CM,F&E | In-Progress | 2020-11-16 | 2022-11-15 |  | 704739 | 1122809 | 1088010
2 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-06-16 | 2020-10-15 | 2020-06-22 | 3418 | 6911 | 6911
2 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-06-22 | 2020-12-17 | 2020-12-23 | 15380 | 27643 | 27643
2 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-24 | 2023-03-19 |  | 198231 | 190677 | 166368
2 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-24 | 2023-03-19 |  | 206690 | 225653 | 220817
2 | LOWER MANHATTAN ARTS - MANHATTAN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2022-07-05 | 2022-11-02 | 2022-11-02 | 125400 | 121298 | 92493
2 | LOWER MANHATTAN ARTS - MANHATTAN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2024-01-16 | 2025-01-14 |  | 1839200 | 1744481 | 1501622
2 | LOWER MANHATTAN ARTS - MANHATTAN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2024-01-16 | 2025-01-14 |  | 125400 | 65402 | 60084
2 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2020-08-20 | 2020-12-18 | 2021-06-18 | 198200 | 239364 | 190528
2 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2021-06-30 | 2021-11-30 | 2021-12-20 | 991001 | 896859 | 616499
2 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2023-07-17 | 2025-07-15 |  | 22297501 | 21214727 | 3024154
2 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2023-07-17 | 2025-07-15 |  | 1387695 | 288485 | 286443
2 | INT'L HS AT UNION SQUARE - MANHATTAN | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 2024-06-11 |  |  | 50000 | 50000 | 37386
2 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2020-05-21 | 2021-01-29 | 2020-10-27 | 37305 | 99671 | 99671
2 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2020-11-24 | 2021-07-28 | 2021-12-13 | 180483 | 354828 | 354828
2 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2022-08-15 | 2023-12-14 |  | 3537910 | 3670397 | 3517034
2 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2022-08-15 | 2023-12-14 |  | 306482 | 214151 | 214151
2 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2020-01-27 | 2021-12-13 | 2021-11-09 | 277969 | 185667 | 185667
2 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2021-11-09 | 2022-01-20 | 2023-05-12 | 1388986 | 712795 | 596637
2 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-08-07 | 2026-02-01 |  | 31177883 | 28109430 | 2192068
2 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-08-07 | 2026-02-01 |  | 1952963 | 161120 | 160217
2 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | Scope | Complete | 2018-06-28 | 2019-08-02 | 2021-03-02 | 111561 | 296841 | 296841
32 | BUSHWICK LEADERS - K | SCA CIP | ROOM CONVERSION | Scope | Complete | 2022-04-11 | 2022-08-10 | 2022-04-11 | 10612 | 317 | 317
2 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | Design | Complete | 2021-03-02 | 2021-08-31 | 2021-06-08 | 557801 | 933124 | 627031
2 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | Construction | In-Progress | 2023-03-10 | 2026-03-08 |  | 12550500 | 11267633 | 5261932
2 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | CM,F&E | In-Progress | 2023-03-10 | 2026-03-08 |  | 780920 | 94213 | 93438
2 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | Scope | Complete | 2021-03-05 | 2021-07-20 | 2022-01-25 | 198437 | 442128 | 421448
2 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | Design | Complete | 2022-01-25 | 2022-06-24 | 2022-05-12 | 982629 | 844302 | 841135
2 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | Construction | In-Progress | 2022-08-15 | 2024-08-13 |  | 21282452 | 20025738 | 15058766
2 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | CM,F&E | In-Progress | 2022-08-15 | 2024-08-13 |  | 1460742 | 739489 | 733982
2 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | Scope | Complete | 2020-09-11 | 2021-01-20 | 2021-12-15 | 32665 | 47985 | 47985
2 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | Design | Complete | 2021-12-15 | 2022-05-18 | 2022-09-30 | 159563 | 219339 | 183527
2 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | Construction | In-Progress | 2023-08-04 | 2025-02-01 |  | 3264430 | 3890512 | 1376112
2 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | CM,F&E | In-Progress | 2023-08-04 | 2025-02-01 |  | 256902 | 298301 | 294667
2 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2024-04-05 | 2024-08-21 |  | 72000 | 59248 | 16549
2 | P.S. 225 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2024-06-28 | 2024-10-31 |  | 10326 | 1017 | 1017
2 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | Complete | 2023-06-15 | 2023-11-02 | 2024-01-24 | 234785 | 93740 | 89548
2 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | In-Progress | 2024-07-18 | 2026-01-08 |  | 3443514 | 2483807 | 3107
2 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | In-Progress | 2024-07-18 | 2026-01-08 |  | 234785 | 20331 | 20331
2 | J. K. ONASSIS HS FOR INT CAREERS-M | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS / WINDOWS | Scope | Complete | 2018-10-15 | 2019-03-05 | 2019-04-12 | 90044 | 180570 | 180570
2 | J. K. ONASSIS HS FOR INT CAREERS-M | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS / WINDOWS | Design | Complete | 2019-04-12 | 2019-09-12 | 2020-06-30 | 437233 | 342685 | 324197
2 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY20 RESO A GREENROOF | Design | Complete | 2020-03-11 | 2020-08-10 | 2022-08-23 | 194775 | 127213 | 111464
2 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY20 RESO A GREENROOF | Construction | In-Progress | 2023-03-20 | 2024-09-09 |  | 2856700 | 2702316 | 373475
2 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY20 RESO A GREENROOF | CM,F&E | In-Progress | 2023-03-20 | 2024-09-09 |  | 194775 | 212285 | 207894
2 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-09-26 | 2025-02-14 |  | 30000 | 23847 | 1550
2 | P.S. @ 2 HUDSON SQUARE - MANHATTAN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2018-04-19 | 2018-10-09 | 2021-01-25 | 661838 | 836785 | 834689
2 | P.S. @ 2 HUDSON SQUARE - MANHATTAN | SCA Capacity | NEW SCHOOL | Design | Complete | 2021-01-26 | 2019-04-10 | 2023-04-04 | 2647352 | 1457207 | 1366481
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | Scope | Complete | 2020-11-18 | 2021-02-16 | 2021-05-07 | 71190 | 119477 | 119477
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | Design | Complete | 2021-05-18 | 2021-10-19 | 2021-12-17 | 355950 | 354107 | 317163
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | Construction | In-Progress | 2022-09-05 | 2024-09-03 |  | 8008876 | 8691756 | 6754474
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | CM,F&E | In-Progress | 2022-09-05 | 2024-09-03 |  | 498330 | 310620 | 283665
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | GENERATOR REPLACEMENT / NEW GAS METER ROOM | Scope | Complete | 2021-03-05 | 2021-07-06 | 2021-03-05 | 18902 | 2734 | 2734
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | GENERATOR REPLACEMENT / NEW GAS METER ROOM | Design | Complete | 2021-03-05 | 2021-08-04 | 2023-02-23 | 85062 | 10932 | 10932
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | Scope | Complete | 2021-07-06 | 2021-11-19 | 2021-10-25 | 151512 | 92010 | 92010
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | Design | Complete | 2021-11-24 | 2022-04-28 | 2022-05-11 | 754168 | 431668 | 364624
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | Construction | In-Progress | 2024-01-04 | 2026-01-02 |  | 16675372 | 15050776 | 1777287
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | CM,F&E | In-Progress | 2024-01-04 | 2026-01-02 |  | 1086024 | 66740 | 66740
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | Scope | Complete | 2022-03-09 | 2022-05-13 | 2022-09-12 | 20950 | 7327 | 7327
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | Design | Complete | 2022-09-13 | 2023-01-13 | 2023-01-27 | 104750 | 164762 | 132899
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | Construction | In-Progress | 2023-06-05 | 2024-10-01 |  | 2356875 | 2160426 | 1403101
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | CM,F&E | In-Progress | 2023-06-05 | 2024-10-01 |  | 146650 | 52740 | 52740
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | ATHLETIC FIELD UPGRADE | Scope | Complete | 2019-08-15 | 2020-02-03 | 2020-01-24 | 83930 | 143676 | 143676
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | ATHLETIC FIELD UPGRADE | Design | In-Progress | 2022-04-18 | 2022-10-11 |  | 419648 | 419648 | 175727
2 | BERGTRAUM HS - MANHATTAN | SCA CIP | FIELD HOUSE | Scope | In-Progress | 2024-06-18 | 2024-10-18 |  | 75249 | 75249 | 1808
2 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | Scope | Complete | 2021-11-01 | 2021-12-21 | 2022-01-31 | 216951 | 326093 | 201529
2 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | Design | Complete | 2022-02-01 | 2022-02-18 | 2023-04-05 | 976282 | 683347 | 541090
2 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | Construction | In-Progress | 2023-10-18 | 2024-09-03 |  | 12311996 | 13031051 | 12326037
2 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | CM,F&E | In-Progress | 2023-10-18 | 2024-09-03 |  | 1887927 | 574921 | 1167229
2 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | Scope | Complete | 2022-02-04 | 2022-03-04 | 2022-03-11 | 268658 | 265086 | 247062
2 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | Design | Complete | 2022-03-14 | 2022-06-10 | 2023-02-06 | 1208963 | 1269243 | 1043987
2 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | Construction | In-Progress | 2023-02-27 | 2023-09-03 |  | 15246363 | 15772302 | 15068740
2 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | CM,F&E | In-Progress | 2023-02-27 | 2023-09-03 |  | 2149267 | 711945 | 1454152
2 | HARBOR HIGH SCHOOL ATHLETIC COMPLEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Scope | Complete | 2022-10-04 | 2023-02-01 | 2023-02-01 | 2396800 | 1313333 | 1106310
2 | HARBOR HIGH SCHOOL ATHLETIC COMPLEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Design | Complete | 2023-02-02 | 2023-10-04 | 2024-05-09 | 10785600 | 4346491 | 4195522
2 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 2021-11-10 | 2022-03-31 | 2022-01-25 | 160567 | 133507 | 133507
2 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 2022-02-01 | 2022-07-01 | 2022-05-12 | 793146 | 547862 | 517894
2 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 2022-07-18 | 2024-07-16 |  | 17007903 | 15451512 | 12647311
2 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 2022-07-18 | 2024-07-16 |  | 1196615 | 917447 | 900687
32 | BUSHWICK LEADERS - K | SCA CIP | ROOM CONVERSION | Design | Complete | 2022-04-11 | 2022-12-30 | 2023-03-07 | 53059 | 1269 | 1269
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 2015-10-02 | 2016-02-23 | 2016-04-25 | 176283 | 197110 | 197110
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS | Design | Complete | 2018-10-10 | 2019-03-15 | 2019-05-02 | 865743 | 507479 | 487077
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | Scope | Complete | 2016-11-23 | 2017-03-29 | 2017-04-20 | 258990 | 138919 | 138919
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | Design | Complete | 2018-10-10 | 2019-03-15 | 2019-05-10 | 1035960 | 812704 | 676177
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | Construction | In-Progress | 2021-05-21 | 2024-05-19 |  | 19424250 | 18214090 | 16938837
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | CM,F&E | In-Progress | 2021-05-21 | 2024-05-19 |  | 1208621 | 1065739 | 1043144
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | Scope | Complete | 2019-09-11 | 2020-01-13 | 2019-12-18 | 8140 | 11138 | 11138
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | Design | Complete | 2020-01-08 | 2020-06-15 | 2020-06-30 | 36630 | 40339 | 36594
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | Construction | In-Progress | 2022-03-30 | 2022-12-24 |  | 472120 | 483127 | 378000
2 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | CM,F&E | In-Progress | 2022-03-30 | 2022-12-24 |  | 205263 | 180212 | 175493
2 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Scope | Complete | 2014-09-16 | 2014-10-31 | 2014-10-27 | 716528 | 902217 | 895328
2 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Design | Complete | 2014-10-28 | 2015-04-15 | 2019-04-19 | 3224378 | 3581095 | 3250771
2 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 2024-08-19 | 2026-09-03 |  | 40662990 | 37774151 | 974325
2 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 2024-08-19 | 2026-09-03 |  | 5732228 | 2842105 | 243424
2 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | Scope | Complete | 2019-06-19 | 2019-11-04 | 2020-01-30 | 266212 | 259278 | 257923
2 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | Design | Complete | 2020-02-05 | 2020-07-07 | 2021-10-28 | 1321071 | 909569 | 651083
2 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | Construction | In-Progress | 2023-08-15 | 2026-02-09 |  | 28859726 | 25893674 | 3804601
2 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | CM,F&E | In-Progress | 2023-08-15 | 2026-02-09 |  | 1938432 | 649984 | 637185
2 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-17 | 2023-07-18 | 2023-03-21 | 4200 | 2783 | 2783
2 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-21 | 2023-09-14 | 2023-05-04 | 18900 | 11134 | 11134
2 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2024-03-13 | 2025-01-06 |  | 243600 | 220260 | 3760
2 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2024-03-13 | 2025-01-06 |  | 45150 | 24168 | 1488
2 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | Scope | Complete | 2021-05-18 | 2021-08-17 | 2022-06-15 | 75078 | 92585 | 92585
2 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | Design | Complete | 2022-06-16 | 2022-12-20 | 2023-05-05 | 375390 | 367778 | 298012
2 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | Construction | In-Progress | 2023-08-07 | 2025-08-05 |  | 8446279 | 8064547 | 2737466
2 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | CM,F&E | In-Progress | 2023-08-07 | 2025-08-05 |  | 525546 | 215762 | 215626
2 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2021-02-24 | 2021-07-09 | 2021-12-07 | 38648 | 135138 | 127579
2 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2021-12-15 | 2022-05-18 | 2022-05-10 | 180499 | 136798 | 111323
2 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-09-02 | 2023-01-06 | 2022-10-28 | 6200 | 11767 | 11767
2 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-10-28 | 2023-04-27 | 2023-03-08 | 27900 | 47071 | 47071
2 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-08 | 2024-07-03 |  | 359600 | 325817 | 225857
2 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-08 | 2024-07-03 |  | 189922 | 175067 | 121692
2 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Design | In-Progress | 2024-05-21 | 2024-10-07 |  | 30000 | 39276 | 11702
2 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | In-Progress | 2024-05-21 | 2024-09-24 |  | 2846 | 2846 | 0
2 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | Scope | Complete | 2019-03-07 | 2020-07-08 | 2020-06-22 | 61612 | 162213 | 151739
2 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | Design | Complete | 2020-06-22 | 2020-08-03 | 2020-06-30 | 288665 | 254059 | 232118
2 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | Construction | In-Progress | 2022-01-03 | 2023-08-25 |  | 4817622 | 4606043 | 4035019
2 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | CM,F&E | In-Progress | 2022-01-03 | 2023-08-25 |  | 576714 | 561181 | 551930
2 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | Scope | Complete | 2019-05-20 | 2019-09-23 | 2019-07-18 | 140676 | 220325 | 220325
2 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | Design | Complete | 2019-07-24 | 2019-12-26 | 2019-12-05 | 696032 | 1264577 | 967967
2 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2023-06-14 | 2025-02-02 |  | 15025246 | 13564352 | 6880311
2 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2023-06-14 | 2025-02-02 |  | 1044922 | 649943 | 253109
2 | HS FOR ECONOMICS & FINANCE - M | SCA CIP | ABSORBER REPLACEMENT | Scope | Complete | 2019-08-12 | 2019-12-13 | 2020-03-30 | 43701 | 48744 | 48744
2 | HS FOR ECONOMICS & FINANCE - M | SCA CIP | ABSORBER REPLACEMENT | Design | Complete | 2020-03-31 | 2020-07-17 | 2020-06-19 | 218503 | 200082 | 176926
2 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | Scope | Complete | 2019-01-30 | 2019-06-14 | 2022-01-10 | 25250 | 52209 | 40697
2 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | Design | Complete | 2022-01-13 | 2022-06-15 | 2022-04-22 | 126250 | 327056 | 170965
2 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | Construction | In-Progress | 2022-09-12 | 2024-03-12 |  | 2840625 | 2714609 | 2379171
2 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | CM,F&E | In-Progress | 2022-09-12 | 2024-03-12 |  | 176750 | 442113 | 314340
2 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | HEATING PLANT UPGRADE | Scope | Complete | 2021-06-24 | 2021-11-26 | 2022-01-19 | 34972 | 60798 | 60798
2 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | HEATING PLANT UPGRADE | Design | Complete | 2022-01-20 | 2022-06-21 | 2022-10-27 | 174858 | 193384 | 169529
2 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | FY24 RESO A CULINARY KITCHEN | Design | In-Progress | 2024-07-30 | 2025-01-02 |  | 42000 | 37669 | 37669
2 | M721 SPED - MANHATTAN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 2023-12-12 | 2024-04-29 | 2024-07-09 | 45876 | 58647 | 36183
2 | M721 SPED - MANHATTAN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | In-Progress | 2024-07-24 | 2024-12-26 |  | 208429 | 208429 | 6927
2 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP | STRUCTURAL ISSUES | Scope | Complete | 2019-02-28 | 2019-07-15 | 2019-09-17 | 61083 | 77115 | 76275
2 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP | STRUCTURAL ISSUES | Design | Complete | 2019-10-23 | 2020-03-27 | 2022-04-08 | 305417 | 329104 | 280163
2 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-05-24 | 2023-09-25 | 2023-06-15 | 3327 | 359 | 359
2 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-15 | 2023-12-13 | 2023-08-30 | 14970 | 1437 | 1437
2 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-09 | 2025-01-03 |  | 192950 | 173804 | 4702
2 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-09 | 2025-01-03 |  | 40026 | 122415 | 122415
2 | HS FOR LEADERSHIP & PUBLIC SERV-M | SCA CIP | EMERGENCY GENERATOR REPLACEMENT | Scope | Complete | 2019-07-17 | 2019-11-18 | 2021-03-11 | 5770 | 11587 | 11587
2 | HS FOR LEADERSHIP & PUBLIC SERV-M | SCA CIP | EMERGENCY GENERATOR REPLACEMENT | Design | In-Progress | 2021-04-09 | 2021-09-09 |  | 25963 | 82084 | 56465
2 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-10-13 | 2023-02-15 | 2022-10-28 | 4780 | 6694 | 6694
2 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-10-28 | 2023-04-27 | 2023-03-08 | 21510 | 26777 | 26777
2 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-08 | 2024-07-03 |  | 277240 | 262618 | 153824
2 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-08 | 2024-07-03 |  | 153291 | 140567 | 51208
3 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-06-26 | 2019-11-27 | 2019-09-17 | 73499 | 83034 | 83034
3 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-09-26 | 2020-03-03 | 2020-02-11 | 354838 | 361717 | 342794
3 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-08-16 | 2023-08-15 |  | 7569284 | 7003469 | 4828672
3 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-08-16 | 2023-08-15 |  | 533487 | 448409 | 444198
3 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2021-06-14 | 2021-12-13 | 2021-09-16 | 192000 | 171540 | 162266
3 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2021-10-20 | 2022-06-30 | 2022-04-25 | 960000 | 347483 | 347483
3 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-09-05 | 2025-09-03 |  | 21600000 | 19625837 | 1419959
3 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-09-05 | 2025-09-03 |  | 1345280 | 107417 | 106288
3 | P.S. 334 - MANHATTAN | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 2023-08-08 |  |  | 135342 | 135342 | 923
3 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2018-10-05 | 2019-03-13 | 2018-12-03 | 100920 | 89740 | 89740
3 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2018-12-12 | 2019-05-15 | 2019-05-13 | 403680 | 412526 | 396123
3 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2019-10-03 | 2021-10-01 |  | 7569000 | 7727869 | 7141575
3 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2019-10-03 | 2021-10-01 |  | 470960 | 1111635 | 1102602
3 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2023-06-05 | 2023-12-04 | 2023-10-12 | 142980 | 138134 | 137523
3 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-10-18 | 2024-06-11 | 2024-04-10 | 714900 | 264171 | 259655
3 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2024-08-15 | 2026-08-14 |  | 16085250 | 14423882 | 80684
3 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2024-08-15 | 2026-08-14 |  | 1000860 | 39288 | 39288
3 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2019-10-30 | 2020-04-29 | 2020-02-13 | 14136 | 28081 | 28081
3 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-02-25 | 2020-08-18 | 2020-04-08 | 63611 | 129418 | 119755
3 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2021-08-16 | 2022-11-08 |  | 819872 | 1022921 | 788260
3 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2021-08-16 | 2022-11-08 |  | 151959 | 254421 | 240693
3 | P.S. 75 - MANHATTAN | SCA CIP | ROOFS / STAIRWELL WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 2023-08-03 | 2023-12-20 | 2023-12-29 | 136647 | 236064 | 202825
3 | P.S. 75 - MANHATTAN | SCA CIP | ROOFS / STAIRWELL WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 2024-01-12 | 2024-06-13 | 2024-05-14 | 672871 | 560119 | 560119
3 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-19 | 2023-11-17 | 2023-07-26 | 4800 | 2655 | 2655
3 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-26 | 2024-01-24 | 2023-11-01 | 21600 | 10624 | 10624
3 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-28 | 2024-12-23 |  | 278400 | 247110 | 1810
3 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-28 | 2024-12-23 |  | 55864 | 34398 | 8478
3 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-09-30 | 2023-02-21 | 2023-01-11 | 142110 | 146477 | 120467
3 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-01-24 | 2023-06-26 | 2023-05-04 | 710551 | 397823 | 397823
3 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-07-25 | 2026-01-19 |  | 15987375 | 14657868 | 3161368
3 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-07-25 | 2026-01-19 |  | 994770 | 575810 | 556904
3 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-07 | 2023-07-06 | 2023-03-08 | 4980 | 1868 | 1868
3 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-08 | 2023-08-31 | 2023-05-03 | 22410 | 7474 | 7474
3 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-08 | 2024-12-06 |  | 288840 | 260132 | 24948
3 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-08 | 2024-12-06 |  | 134058 | 110036 | 66512
3 | P.S. 84 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUND UPGRADE | Design | Complete | 2018-10-29 | 2019-03-19 | 2019-05-20 | 51674 | 66374 | 64914
3 | P.S. 84 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2019-09-10 | 2020-09-08 |  | 757879 | 749781 | 709122
3 | P.S. 84 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2019-09-10 | 2020-09-08 |  | 51674 | 102300 | 71789
3 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | Scope | Complete | 2018-06-19 | 2019-03-06 | 2018-11-30 | 387378 | 225299 | 225299
3 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | Design | Complete | 2018-12-05 | 2019-05-16 | 2019-04-18 | 1528452 | 898292 | 866393
3 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | Construction | In-Progress | 2019-12-16 | 2022-06-02 |  | 26768125 | 25560920 | 19929780
3 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | CM,F&E | In-Progress | 2019-12-16 | 2022-06-02 |  | 2081581 | 1550515 | 1497922
3 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | Scope | Complete | 2021-08-04 | 2021-11-03 | 2021-12-08 | 157660 | 186014 | 186014
3 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | Design | Complete | 2021-12-08 | 2022-06-13 | 2023-05-08 | 788300 | 698937 | 448002
3 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | Construction | In-Progress | 2023-07-10 | 2025-07-08 |  | 17736750 | 15864981 | 2167382
3 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | CM,F&E | In-Progress | 2023-07-10 | 2025-07-08 |  | 1104652 | 252503 | 250052
3 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2023-01-20 | 2023-06-06 | 2023-08-10 | 29051 | 60363 | 60199
3 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2023-08-25 | 2024-01-31 | 2024-02-05 | 145255 | 112205 | 59766
3 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2023-06-21 | 2023-11-06 | 2023-11-01 | 70724 | 90211 | 88954
3 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2023-11-08 | 2024-04-12 | 2024-04-22 | 353618 | 236120 | 121115
3 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | Scope | Complete | 2021-06-02 | 2021-10-18 | 2021-11-09 | 68681 | 65581 | 65581
3 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | Design | Complete | 2021-11-19 | 2022-04-25 | 2022-05-05 | 335836 | 270171 | 249355
3 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | Construction | In-Progress | 2023-06-12 | 2024-12-02 |  | 6901376 | 6467784 | 3619560
3 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | CM,F&E | In-Progress | 2023-06-12 | 2024-12-02 |  | 538335 | 365889 | 357163
3 | P.S. 333 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2019-09-13 | 2020-03-16 | 2019-10-11 | 26620 | 11580 | 11580
3 | P.S. 333 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2019-11-21 | 2020-05-19 | 2020-02-24 | 119790 | 54816 | 54816
3 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-08-02 | 2023-12-01 | 2023-11-16 | 10874 | 15970 | 15970
3 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-12-04 | 2024-05-06 | 2024-05-03 | 48933 | 51695 | 40612
3 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-09 | 2025-09-08 |  | 630692 | 567160 | 3368
3 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-09 | 2025-09-08 |  | 116896 | 81748 | 12071
3 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2018-11-15 | 2019-04-04 | 2019-03-06 | 49435 | 50347 | 50347
3 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2019-03-06 | 2019-08-05 | 2021-11-18 | 197741 | 116925 | 110115
3 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2022-07-11 | 2024-07-09 |  | 3707639 | 3385667 | 3259321
3 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-07-11 | 2024-07-09 |  | 230698 | 187606 | 181719
3 | WEST PREP ACADEMY - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2023-06-15 | 2023-11-01 | 2023-11-20 | 111046 | 121472 | 121472
3 | WEST PREP ACADEMY - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2024-02-28 | 2024-07-30 | 2024-05-03 | 555232 | 381748 | 16757
3 | M811 SPED - MANHATTAN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2023-06-09 | 2023-12-08 | 2023-09-22 | 104451 | 129366 | 129360
3 | M811 SPED - MANHATTAN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2023-10-25 | 2024-06-10 | 2024-04-03 | 522249 | 311801 | 311801
3 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 2021-06-21 | 2021-12-20 | 2021-10-14 | 203462 | 182193 | 171298
3 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Design | Complete | 2021-10-26 | 2022-06-30 | 2022-04-22 | 1012328 | 386014 | 386014
3 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 2022-07-18 | 2024-07-16 |  | 22346452 | 20392184 | 16113686
3 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 2022-07-18 | 2024-07-16 |  | 1461598 | 424132 | 419124
3 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2020-05-15 | 2021-01-29 | 2020-10-19 | 11777 | 34259 | 34259
3 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-10-27 | 2021-07-28 | 2021-07-28 | 52996 | 137044 | 137044
3 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2022-06-28 | 2023-06-27 |  | 683061 | 620702 | 7968
3 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2022-06-28 | 2023-06-27 |  | 126602 | 92639 | 88382
3 | P.S. 165 - MANHATTAN | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 2023-10-17 | 2024-03-06 | 2024-04-22 | 82500 | 87854 | 83946
3 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 2023-11-07 | 2024-03-14 | 2024-04-22 | 9483 | 1171 | 1171
3 | P.S. 165 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-01-10 | 2024-05-13 |  | 3021 | 29323 | 1862
3 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 2017-09-29 | 2018-02-20 | 2018-03-29 | 195014 | 274856 | 274856
3 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | Design | Complete | 2019-03-04 | 2019-08-01 | 2019-09-13 | 973425 | 678209 | 591300
3 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | Construction | In-Progress | 2021-04-05 | 2023-05-24 |  | 21759878 | 21930678 | 18341194
3 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | CM,F&E | In-Progress | 2021-04-05 | 2023-05-24 |  | 1377423 | 1100910 | 1059365
3 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | Scope | Complete | 2019-03-01 | 2019-05-30 | 2019-12-13 | 13750 | 70483 | 70483
3 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | Design | Complete | 2020-01-15 | 2020-07-17 | 2020-06-29 | 68750 | 159947 | 97702
3 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | Construction | In-Progress | 2021-07-22 | 2022-07-21 |  | 1546875 | 1482290 | 1344487
3 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | CM,F&E | In-Progress | 2021-07-22 | 2022-07-21 |  | 96250 | 198025 | 197035
3 | P.S. 166 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADES | Design | Complete | 2019-09-03 | 2019-11-05 | 2020-01-31 | 2100 | 1819 | 1819
3 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2022-03-16 | 2022-07-14 | 2022-04-12 | 5962 | 3389 | 3389
3 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2022-04-12 | 2022-10-05 | 2022-07-19 | 26831 | 13554 | 13554
3 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2023-03-09 | 2024-02-01 |  | 345820 | 310900 | 289277
3 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2023-03-09 | 2024-02-01 |  | 234789 | 202681 | 197623
3 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-08-13 | 2022-01-03 | 2022-07-29 | 124270 | 127442 | 127433
3 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2022-09-02 | 2023-02-24 | 2023-05-03 | 621350 | 356366 | 292955
3 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-08-07 | 2025-08-05 |  | 13980375 | 12695031 | 2620640
3 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-08-07 | 2025-08-05 |  | 869890 | 282711 | 267559
3 | P.S. 452 - MANHATTAN | SCA CIP | GYM CEILING RESTORATION- PERMANENT FIX | Scope | Complete | 2023-05-17 | 2023-09-19 | 2023-08-23 | 12427 | 12899 | 12899
3 | P.S. 452 - MANHATTAN | SCA CIP | GYM CEILING RESTORATION- PERMANENT FIX | Design | Complete | 2023-08-30 | 2024-01-19 | 2023-12-12 | 55919 | 30720 | 26998
3 | P.S. 452 - MANHATTAN | SCA CIP RESOA | FY19 RESO A PLAYGROUND | Design | Complete | 2021-08-10 | 2021-12-28 | 2022-01-18 | 84113 | 78796 | 78796
3 | P.S. 452 - MANHATTAN | SCA CIP RESOA | FY19 RESO A PLAYGROUND | Construction | In-Progress | 2022-10-31 | 2023-07-27 |  | 1233650 | 1170177 | 1050727
3 | P.S. 452 - MANHATTAN | SCA CIP RESOA | FY19 RESO A PLAYGROUND | CM,F&E | In-Progress | 2022-10-31 | 2023-07-27 |  | 84113 | 105490 | 79517
3 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-18 | 2023-11-16 | 2023-07-26 | 4400 | 2480 | 2480
3 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-26 | 2024-01-24 | 2023-11-01 | 19800 | 9922 | 9922
3 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-28 | 2024-12-23 |  | 255200 | 227463 | 2163
3 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-28 | 2024-12-23 |  | 51564 | 32635 | 8875
3 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | Scope | Complete | 2013-05-20 | 2013-09-20 | 2013-11-04 | 49058 | 58427 | 48452
3 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | Design | Complete | 2013-11-13 | 2014-05-15 | 2014-10-27 | 189433 | 210497 | 207760
3 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | Construction | In-Progress | 2018-08-14 | 2019-10-07 |  | 2941946 | 3534155 | 3439749
3 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | CM,F&E | In-Progress | 2018-08-14 | 2019-10-07 |  | 317281 | 712592 | 710274
3 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | Scope | Complete | 2020-02-14 | 2020-05-14 | 2021-09-23 | 112212 | 104405 | 99517
3 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | Design | Complete | 2021-10-13 | 2022-04-19 | 2022-07-11 | 561061 | 598978 | 346524
3 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | Construction | In-Progress | 2023-05-15 | 2025-05-13 |  | 12623864 | 11522246 | 4802061
3 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | CM,F&E | In-Progress | 2023-05-15 | 2025-05-13 |  | 786541 | 202184 | 190431
3 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Design | Complete | 2018-01-31 | 2018-06-18 | 2018-05-21 | 41220 | 49682 | 39615
3 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 2018-07-09 | 2019-04-04 |  | 604563 | 613632 | 546151
3 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | CM,F&E | In-Progress | 2018-07-09 | 2019-04-04 |  | 41763 | 91034 | 89061
3 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | STAIRWELL WALLS | Scope | Complete | 2023-05-25 | 2023-09-25 | 2023-09-21 | 31036 | 36239 | 36239
3 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | STAIRWELL WALLS | Design | Complete | 2023-10-02 | 2024-03-07 | 2024-05-10 | 155181 | 114174 | 107469
3 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | Scope | Complete | 2020-05-18 | 2021-01-29 | 2020-08-11 | 29299 | 57257 | 57257
3 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | Design | Complete | 2020-08-19 | 2021-07-28 | 2021-07-28 | 137177 | 219540 | 219540
3 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | Construction | In-Progress | 2022-07-21 | 2024-01-11 |  | 2280149 | 2145863 | 1955376
3 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | CM,F&E | In-Progress | 2022-07-21 | 2024-01-11 |  | 275011 | 335213 | 335213
3 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | FY15 RESO A TECHNICAL THEATER SHOP | Design | Complete | 2016-07-28 | 2017-03-28 | 2018-09-19 | 285834 | 791554 | 673985
3 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | FY15 RESO A TECHNICAL THEATER SHOP | Construction | In-Progress | 2022-06-10 | 2023-12-01 |  | 4192225 | 2598515 | 2564537
3 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | FY15 RESO A TECHNICAL THEATER SHOP | CM,F&E | In-Progress | 2022-06-10 | 2023-12-01 |  | 472534 | 702428 | 547063
3 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | Scope | Complete | 2021-05-04 | 2021-09-02 | 2021-11-16 | 89950 | 69953 | 69953
3 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | Design | Complete | 2021-12-01 | 2022-04-19 | 2022-10-07 | 449750 | 397948 | 316568
3 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | Construction | In-Progress | 2023-08-07 | 2026-02-06 |  | 10119375 | 9145812 | 2222462
3 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | CM,F&E | In-Progress | 2023-08-07 | 2026-02-06 |  | 629650 | 157608 | 152702
3 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | Scope | Complete | 2022-06-08 | 2022-09-07 | 2022-08-30 | 14950 | 22221 | 22221
3 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | Design | Complete | 2022-09-12 | 2023-03-20 | 2023-04-21 | 74750 | 114575 | 12711
3 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | Construction | In-Progress | 2024-04-18 | 2025-10-09 |  | 1681875 | 1696592 | 133147
3 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | CM,F&E | In-Progress | 2024-04-18 | 2025-10-09 |  | 104650 | 87319 | 64281
3 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | SWIMMING POOL | Scope | Complete | 2023-06-14 | 2023-12-12 | 2023-12-06 | 73230 | 75789 | 75789
3 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | SWIMMING POOL | Design | Complete | 2023-12-26 | 2024-07-01 | 2024-08-13 | 341739 | 238794 | 216085
3 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | PATH OF TRAVEL SWIMMING POOL | Scope | Complete | 2023-12-05 | 2024-03-08 | 2024-03-15 | 698 | 620 | 620
3 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | PATH OF TRAVEL SWIMMING POOL | Design | Complete | 2024-04-03 | 2024-08-06 | 2024-08-13 | 3139 | 2478 | 2478
3 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | Scope | Complete | 2021-07-29 | 2021-09-16 | 2021-09-16 | 331100 | 221828 | 221828
3 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | Design | Complete | 2021-09-17 | 2021-12-20 | 2022-05-04 | 1489950 | 700147 | 669519
3 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | Construction | In-Progress | 2022-06-13 | 2023-09-03 |  | 18789925 | 19138493 | 18018405
3 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | CM,F&E | In-Progress | 2022-06-13 | 2023-09-03 |  | 2648800 | 877415 | 1724821
3 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-02-06 | 2023-08-02 | 2023-05-03 | 20138 | 10409 | 10409
3 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2023-12-08 | 2024-12-06 |  | 295351 | 208878 | 21745
3 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2023-12-08 | 2024-12-06 |  | 49925 | 54520 | 34760
3 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | Scope | Complete | 2021-04-27 | 2021-09-10 | 2021-09-08 | 56358 | 68816 | 68816
3 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | Design | Complete | 2021-09-09 | 2022-02-14 | 2022-05-06 | 281792 | 251114 | 238910
3 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | Construction | In-Progress | 2023-06-12 | 2024-12-02 |  | 6340318 | 5755968 | 1864098
3 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | CM,F&E | In-Progress | 2023-06-12 | 2024-12-02 |  | 394509 | 147849 | 143296
3 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-09 | 2023-07-10 | 2023-03-21 | 4500 | 1843 | 1843
3 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-21 | 2023-09-14 | 2023-05-03 | 20250 | 7371 | 7371
3 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-08 | 2024-12-06 |  | 261000 | 233371 | 54487
3 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-08 | 2024-12-06 |  | 85737 | 63686 | 40891
4 | P.S. 7 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2023-12-14 | 2024-05-01 | 2024-05-10 | 96443 | 90594 | 90531
4 | P.S. 7 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 2024-05-28 | 2024-10-29 |  | 437829 | 437829 | 4381
4 | P.S. 497 - MANHATTAN | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA ROOFS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES / NON-IDA PLAYGROUND UPGRADE | Scope | Complete | 2022-01-21 | 2022-06-07 | 2022-12-21 | 121867 | 246608 | 111046
4 | P.S. 497 - MANHATTAN | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA ROOFS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES / NON-IDA PLAYGROUND UPGRADE | Design | In-Progress | 2022-12-23 | 2023-05-26 |  | 607409 | 703376 | 426526
4 | P.S. 497 - MANHATTAN | SCA CIP | PATH OF TRAVEL IDA FLOOD ELIMINATION | Scope | Complete | 2023-01-25 | 2023-04-26 | 2023-03-27 | 9146 | 0 | 0
4 | P.S. 497 - MANHATTAN | SCA CIP | PATH OF TRAVEL IDA FLOOD ELIMINATION | Design | In-Progress | 2023-03-28 | 2023-07-27 |  | 41157 | 41157 | 0
4 | P.S. 37 - MANHATTAN | SCA CIP | SIDEWALK REPAIR / ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 2023-01-17 | 2024-02-06 | 2023-12-05 | 173001 | 254581 | 213934
4 | P.S. 37 - MANHATTAN | SCA CIP | SIDEWALK REPAIR / ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | Complete | 2023-12-21 | 2024-05-23 | 2024-04-26 | 865002 | 456687 | 374582
4 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2018-07-27 | 2018-12-13 | 2019-03-21 | 124610 | 153729 | 146079
4 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2019-11-06 | 2020-04-27 | 2021-05-14 | 623050 | 447813 | 426824
4 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2022-07-20 | 2024-07-18 |  | 14018625 | 14434026 | 4677993
4 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2022-07-20 | 2024-07-18 |  | 906164 | 1115823 | 1084109
4 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-06-02 | 2022-09-30 | 2022-06-09 | 3426 | 2739 | 2739
4 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-09 | 2022-12-06 | 2022-10-25 | 15415 | 10955 | 10955
4 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-04-17 | 2024-03-11 |  | 198679 | 186643 | 158604
4 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-04-17 | 2024-03-11 |  | 142519 | 138055 | 124065
4 | P.S. 72 - MANHATTAN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY | Scope | Complete | 2023-07-13 | 2023-11-29 | 2023-11-07 | 34411 | 55331 | 46977
4 | P.S. 72 - MANHATTAN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY | Design | Complete | 2023-11-17 | 2024-04-22 | 2024-04-24 | 172055 | 127629 | 115147
4 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-06-14 | 2022-10-13 | 2022-06-28 | 4689 | 4028 | 4028
4 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-28 | 2022-12-23 | 2022-10-25 | 21099 | 16109 | 16109
4 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-04-17 | 2024-03-11 |  | 271948 | 248967 | 215141
4 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-04-17 | 2024-03-11 |  | 155435 | 130930 | 116928
4 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2020-02-04 | 2020-07-06 | 2020-04-02 | 59840 | 84240 | 84240
4 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2020-04-03 | 2020-09-02 | 2020-07-16 | 299201 | 433268 | 365062
4 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-09-20 | 2023-09-19 |  | 6732000 | 6394375 | 5171546
4 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-09-20 | 2023-09-19 |  | 420477 | 951083 | 933668
4 | P.S. 83 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-09-29 | 2024-02-20 | 2023-11-09 | 173903 | 127284 | 112639
4 | P.S. 83 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-12-20 | 2024-05-22 | 2024-05-07 | 869516 | 322595 | 322475
4 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2020-02-18 | 2020-07-17 | 2020-04-27 | 96801 | 170994 | 143896
4 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2020-04-28 | 2020-09-28 | 2020-10-29 | 484003 | 597277 | 531987
4 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2022-08-04 | 2024-08-02 |  | 10890057 | 9985016 | 8074938
4 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2022-08-04 | 2024-08-02 |  | 677603 | 422270 | 419426
4 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-11 | 2022-11-08 | 2022-08-18 | 3986 | 3990 | 3990
4 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-08-18 | 2023-02-16 | 2022-10-25 | 17936 | 15959 | 15959
4 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-04-17 | 2024-03-11 |  | 231173 | 215491 | 187140
4 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-04-17 | 2024-03-11 |  | 141724 | 124797 | 113580
4 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2020-05-21 | 2021-01-29 | 2020-09-24 | 14880 | 29636 | 29636
4 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-10-14 | 2021-07-28 | 2021-08-18 | 66960 | 110264 | 110264
4 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2022-07-01 | 2023-06-30 |  | 863040 | 812105 | 425015
4 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2022-07-01 | 2023-06-30 |  | 159960 | 144388 | 112313
4 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2020-05-26 | 2021-02-02 | 2020-10-15 | 15640 | 21103 | 21103
4 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-11-03 | 2021-07-28 | 2021-07-28 | 70380 | 84453 | 84453
4 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2022-06-24 | 2023-06-23 |  | 907120 | 841057 | 718363
4 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2022-06-24 | 2023-06-23 |  | 168130 | 137044 | 120213
4 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2021-04-09 | 2021-09-09 | 2021-06-14 | 75000 | 102475 | 102475
4 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2021-06-16 | 2021-11-17 | 2021-11-04 | 375000 | 489081 | 427297
4 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-08-08 | 2024-08-06 |  | 8437501 | 7695199 | 5984587
4 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-08-08 | 2024-08-06 |  | 525000 | 929620 | 922443
4 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-11 | 2023-05-11 | 2023-01-24 | 2412 | 2397 | 2397
4 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-24 | 2023-07-20 | 2023-04-11 | 10852 | 9588 | 9588
4 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-03 | 2024-10-01 |  | 139875 | 134291 | 2993
4 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-03 | 2024-10-01 |  | 30189 | 20365 | 20365
4 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-29 | 2023-10-30 | 2023-10-13 | 8560 | 15547 | 15547
4 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-25 | 2024-03-26 | 2024-03-20 | 38520 | 79541 | 40820
4 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-26 | 2025-09-25 |  | 496480 | 489221 | 11340
4 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-26 | 2025-09-25 |  | 92020 | 98417 | 13472
4 | P.S. 108 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2018-10-25 | 2019-11-01 | 2019-11-22 | 128458 | 220500 | 217803
4 | P.S. 108 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2019-12-03 | 2020-05-05 | 2020-06-29 | 634424 | 545173 | 512692
4 | P.S. 108 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | Complete | 2021-08-23 | 2023-10-01 | 2024-05-22 | 13593915 | 12773505 | 11932260
4 | P.S. 108 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | Complete | 2021-08-23 | 2023-10-01 | 2024-05-22 | 958221 | 880628 | 871447
4 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-24 | 2023-05-23 | 2023-02-13 | 4119 | 3376 | 3376
4 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-13 | 2023-08-09 | 2023-04-11 | 18537 | 13506 | 13506
4 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-03 | 2024-10-01 |  | 238925 | 215873 | 4137
4 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-03 | 2024-10-01 |  | 48548 | 31695 | 31695
4 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2019-07-08 | 2019-11-21 | 2019-10-03 | 173003 | 185064 | 129564
4 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2021-03-03 | 2021-08-17 | 2023-03-27 | 865016 | 1040023 | 519299
4 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-07-17 | 2026-01-01 |  | 19462868 | 18138372 | 2506345
4 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-07-17 | 2026-01-01 |  | 1211023 | 729221 | 290993
4 | I.S. 12 - MANHATTAN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | In-Progress | 2024-06-22 |  |  | 75000 | 75000 | 74839
4 | P.S. 38 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 2023-05-04 | 2023-09-20 | 2023-11-07 | 58698 | 97931 | 93881
4 | P.S. 38 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | Complete | 2023-11-27 | 2024-04-29 | 2024-04-29 | 285575 | 177823 | 157604
4 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2019-11-05 | 2020-05-05 | 2019-12-18 | 16980 | 19525 | 19525
4 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-01-08 | 2020-07-02 | 2020-03-30 | 76410 | 59341 | 59341
4 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2022-10-21 | 2023-10-20 |  | 984840 | 917404 | 434121
4 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2022-10-21 | 2023-10-20 |  | 182535 | 136560 | 113912
4 | P.S. 146 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-07-12 | 2022-11-28 | 2023-01-31 | 211757 | 218337 | 217967
4 | P.S. 146 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2023-02-03 | 2023-07-07 | 2023-11-01 | 1058784 | 571772 | 548330
4 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-08 | 2023-06-08 | 2023-03-02 | 3369 | 3180 | 3180
4 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-02 | 2023-08-25 | 2023-04-11 | 15160 | 12720 | 12720
4 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-03 | 2024-10-01 |  | 195400 | 182191 | 3026
4 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-03 | 2024-10-01 |  | 40480 | 19948 | 19948
4 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | Scope | Complete | 2021-09-08 | 2022-01-27 | 2021-12-28 | 136319 | 186538 | 185858
4 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | Design | Complete | 2022-02-02 | 2022-07-20 | 2022-11-10 | 681596 | 540488 | 479716
4 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | Construction | In-Progress | 2023-08-03 | 2025-08-01 |  | 15335909 | 14067682 | 3707453
4 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | CM,F&E | In-Progress | 2023-08-03 | 2025-08-01 |  | 955236 | 541742 | 531189
4 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | Scope | Complete | 2022-12-22 | 2023-06-22 | 2023-12-13 | 273180 | 308703 | 300356
4 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | Design | Complete | 2023-12-20 | 2024-09-12 | 2024-05-08 | 1365900 | 1099882 | 1057481
4 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | Construction | In-Progress | 2024-09-27 | 2027-09-11 |  | 30732750 | 27472504 | 123939
4 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | CM,F&E | In-Progress | 2024-09-27 | 2027-09-11 |  | 1912260 | 123869 | 123869
4 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-05-22 | 2023-09-21 | 2023-06-13 | 3810 | 947 | 947
4 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-13 | 2023-12-11 | 2023-08-16 | 17145 | 3788 | 3788
4 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-26 | 2024-12-21 |  | 220980 | 205904 | 2999
4 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-26 | 2024-12-21 |  | 115677 | 99210 | 40439
4 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-01 | 2023-06-29 | 2023-03-09 | 5310 | 1200 | 1200
4 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-09 | 2023-09-01 | 2023-05-03 | 23895 | 4799 | 4799
4 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-06 | 2024-09-30 |  | 307980 | 279393 | 170357
4 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-06 | 2024-09-30 |  | 158095 | 132236 | 75324
4 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2019-07-08 | 2019-11-21 | 2019-10-03 | 136097 | 217460 | 161921
4 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2021-03-03 | 2021-08-17 | 2023-03-27 | 680484 | 798161 | 396480
4 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-07-17 | 2026-01-01 |  | 15310882 | 14310666 | 3105972
4 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-07-17 | 2026-01-01 |  | 953709 | 932203 | 591331
4 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-03 | 2023-07-03 | 2023-03-09 | 6490 | 2057 | 2057
4 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-09 | 2023-09-01 | 2023-05-03 | 29205 | 8225 | 8225
4 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-06 | 2024-09-30 |  | 376420 | 339582 | 56552
4 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-06 | 2024-09-30 |  | 110942 | 78812 | 43766
4 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2020-05-20 | 2021-01-29 | 2020-08-07 | 14940 | 40527 | 40527
4 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-08-19 | 2021-07-28 | 2021-12-15 | 67230 | 153258 | 153258
4 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2022-07-11 | 2023-07-10 |  | 866520 | 805383 | 572784
4 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2022-07-11 | 2023-07-10 |  | 160605 | 128560 | 118800
4 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-06-02 | 2020-09-30 | 2020-06-26 | 4926 | 3868 | 3868
4 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-06-26 | 2020-12-23 | 2020-12-22 | 22168 | 15470 | 15470
4 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-11-17 | 2023-09-12 |  | 285722 | 251947 | 238122
4 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-11-17 | 2023-09-12 |  | 181104 | 182752 | 177802
4 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2020-05-18 | 2021-01-29 | 2020-09-03 | 10937 | 27807 | 27807
4 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-10-14 | 2021-07-28 | 2021-07-28 | 49214 | 111226 | 111226
4 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2023-06-12 | 2024-06-10 |  | 634317 | 593650 | 112653
4 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2023-06-12 | 2024-06-10 |  | 117567 | 93944 | 58599
4 | PARK EAST HS - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-12-18 | 2024-05-03 | 2024-06-26 | 35050 | 66784 | 33792
4 | PARK EAST HS - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 2024-07-08 | 2024-12-09 |  | 167921 | 167921 | 7330
4 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 208 | 208
4 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2003-09-15 | 2003-10-30 | 2003-10-30 | 2600 | 19743 | 17929
4 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2004-05-10 | 2006-03-15 |  | 77000 | 78318 | 73504
4 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2004-05-10 | 2006-03-15 |  | 12240 | 160745 | 160725
4 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | EXTERIOR MASONRY- PERMANENT FIX / PARAPETS | Scope | Complete | 2023-05-31 | 2023-10-17 | 2023-10-25 | 73701 | 83903 | 83903
4 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | EXTERIOR MASONRY- PERMANENT FIX / PARAPETS | Design | In-Progress | 2023-12-20 | 2024-05-22 |  | 330731 | 330731 | 89771
4 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-05-22 | 2023-09-21 | 2023-06-06 | 4010 | 611 | 611
4 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-06 | 2023-12-04 | 2023-08-16 | 18045 | 2446 | 2446
4 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-26 | 2024-12-21 |  | 232580 | 221944 | 4744
4 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-26 | 2024-12-21 |  | 47372 | 31325 | 9285
5 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | ROOF LEAK / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-10-07 | 2023-01-11 | 2023-01-27 | 218792 | 265146 | 257888
5 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | ROOF LEAK / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-02-09 | 2023-07-13 | 2023-11-29 | 1093958 | 507907 | 485684
5 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2021-07-28 | 2021-11-29 | 2021-08-18 | 6205 | 8646 | 8646
5 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-08-18 | 2022-02-16 | 2021-12-22 | 27922 | 34582 | 34582
5 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-11-17 | 2023-09-12 |  | 359888 | 317851 | 300987
5 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-11-17 | 2023-09-12 |  | 252923 | 241055 | 235939
5 | P.S. 30 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 2023-05-10 | 2023-11-07 | 2023-10-25 | 175442 | 162357 | 162357
5 | P.S. 30 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 2023-11-09 | 2024-06-28 | 2024-05-15 | 877211 | 666392 | 634450
5 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-03-03 | 2021-07-16 | 2021-09-13 | 119974 | 167634 | 167634
5 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2021-09-28 | 2022-03-21 | 2023-01-10 | 599870 | 469968 | 354780
5 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-08-03 | 2025-08-01 |  | 13497075 | 12251980 | 3953288
5 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-08-03 | 2025-08-01 |  | 840789 | 344558 | 343638
5 | P.S. 46 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PAVED AREA-CONCRETE | Scope | Complete | 2023-03-14 | 2023-06-12 | 2023-06-20 | 22522 | 65524 | 65524
5 | P.S. 46 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PAVED AREA-CONCRETE | Design | Complete | 2023-07-14 | 2023-11-30 | 2024-05-14 | 112609 | 173291 | 90405
5 | P.S. 46 - MANHATTAN | SCA CIP | PERMANENT FIX- PIPING REPLACEMENT @ M046 / VENTILATION | Scope | Complete | 2024-03-01 | 2024-06-17 | 2024-07-01 | 51955 | 70119 | 5163
5 | P.S. 46 - MANHATTAN | SCA CIP | PERMANENT FIX- PIPING REPLACEMENT @ M046 / VENTILATION | Design | In-Progress | 2024-07-22 | 2024-12-23 |  | 250193 | 250193 | 8251
5 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2021-04-20 | 2021-09-20 | 2021-08-03 | 83510 | 171703 | 116303
5 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2021-08-05 | 2022-01-10 | 2022-04-06 | 417550 | 561718 | 500521
5 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-07-18 | 2024-07-16 |  | 9394875 | 8645800 | 7128731
5 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-07-18 | 2024-07-16 |  | 584570 | 1046921 | 1036398
5 | M079 SPED - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | Complete | 2021-06-30 | 2021-09-29 | 2022-01-10 | 17302 | 17302 | 17302
5 | M079 SPED - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2022-01-14 | 2022-06-01 |  | 23430 | 23430 | 14461
5 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2020-05-22 | 2021-02-01 | 2020-10-27 | 13482 | 29380 | 29380
5 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-11-16 | 2021-07-28 | 2021-07-28 | 60669 | 117613 | 117613
5 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2022-07-08 | 2023-07-07 |  | 781957 | 706153 | 221632
5 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2022-07-08 | 2023-07-07 |  | 144932 | 98358 | 70665
5 | P.S. 123 - MANHATTAN | SCA CIP | WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2023-06-07 | 2023-12-06 | 2023-10-04 | 88046 | 78431 | 78431
5 | P.S. 123 - MANHATTAN | SCA CIP | WINDOWS / EXTERIOR MASONRY | Design | Complete | 2023-10-30 | 2024-06-28 | 2024-04-22 | 431183 | 172559 | 172559
5 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-21 | 2022-11-21 | 2022-08-10 | 5368 | 3664 | 3664
5 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-08-10 | 2023-02-08 | 2023-01-18 | 24157 | 14656 | 14656
5 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-20 | 2024-06-18 |  | 311361 | 277036 | 246081
5 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-20 | 2024-06-18 |  | 182785 | 185679 | 154358
5 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2020-02-12 | 2020-07-14 | 2022-04-11 | 217910 | 245305 | 234280
5 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-04-11 | 2022-10-12 | 2023-03-24 | 1089550 | 844608 | 549229
5 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2023-08-07 | 2026-02-01 |  | 24514875 | 22537404 | 8157069
5 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-08-07 | 2026-02-01 |  | 1525665 | 505231 | 502978
5 | I.S. 362 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-08 | 2024-11-05 | 2024-07-12 | 3557 | 1229 | 1229
5 | I.S. 362 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-12 | 2025-01-09 |  | 16006 | 16006 | 4915
5 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Design | Complete | 2019-08-28 | 2020-01-16 | 2020-06-15 | 210000 | 201151 | 197604
5 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Construction | Complete | 2022-04-20 | 2023-06-13 | 2023-06-13 | 3080000 | 2486645 | 2167343
5 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | CM,F&E | Complete | 2022-04-20 | 2023-06-13 | 2023-06-13 | 210000 | 427839 | 424558
5 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | Complete | 2023-07-14 | 2023-11-30 | 2024-02-13 | 32379 | 33860 | 31991
5 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A POOL UPGRADE | Design | In-Progress | 2023-11-01 | 2024-03-08 |  | 464122 | 328979 | 20344
5 | P.S. 125 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A POOL UPGRADE | Scope | Complete | 2023-03-01 | 2023-05-31 | 2023-10-06 | 504 | 504 | 504
5 | P.S. 125 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A POOL UPGRADE | Design | In-Progress | 2023-10-17 | 2024-02-22 |  | 2115 | 2115 | 2115
5 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2018-10-31 | 2019-03-21 | 2019-01-10 | 297170 | 319630 | 319592
5 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2019-01-16 | 2019-06-17 | 2021-03-30 | 1485850 | 987782 | 865879
5 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2022-02-03 | 2025-02-01 |  | 33431626 | 31178199 | 5039641
5 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-02-03 | 2025-02-01 |  | 2080190 | 953023 | 930803
5 | P.S. 129 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2023-04-24 | 2023-09-21 | 2023-12-14 | 302501 | 213901 | 198364
5 | P.S. 129 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2023-12-26 | 2024-07-22 | 2024-05-15 | 1512501 | 680747 | 549024
5 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-05-25 | 2021-11-23 | 2021-10-14 | 119803 | 137290 | 137290
5 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2021-11-10 | 2022-06-30 | 2022-04-20 | 599020 | 583876 | 567157
5 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2022-08-08 | 2024-08-06 |  | 13477951 | 12345648 | 11526579
5 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-08-08 | 2024-08-06 |  | 838628 | 672454 | 669551
5 | MOTT HALL HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2020-05-18 | 2021-01-29 | 2020-07-09 | 9700 | 25020 | 25020
5 | MOTT HALL HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-10-27 | 2021-07-28 | 2021-07-28 | 43650 | 92780 | 92780
5 | MOTT HALL HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | Complete | 2022-07-06 | 2023-07-05 | 2024-04-04 | 562600 | 513460 | 470616
5 | MOTT HALL HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | Complete | 2022-07-06 | 2023-07-05 | 2024-04-04 | 104275 | 80959 | 79546
5 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-05-27 | 2020-09-24 | 2020-06-19 | 3269 | 4468 | 4468
5 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-06-19 | 2020-12-16 | 2020-12-16 | 14710 | 17872 | 17872
5 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-11-17 | 2023-09-12 |  | 189590 | 170244 | 155302
5 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-11-17 | 2023-09-12 |  | 132665 | 160821 | 156270
5 | P.S. 154 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2022-09-13 | 2023-02-01 | 2022-12-19 | 16053 | 11876 | 11876
5 | P.S. 154 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-12-21 | 2023-06-27 | 2023-07-11 | 72239 | 47500 | 47500
5 | P.S. 154 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-25 | 2024-11-25 | 2024-07-29 | 4105 | 780 | 780
5 | P.S. 154 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-29 | 2025-01-27 |  | 18471 | 18471 | 3118
5 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-10-06 | 2023-02-09 | 2022-10-20 | 4900 | 3119 | 3119
5 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-10-20 | 2023-04-19 | 2023-01-18 | 22050 | 12473 | 12473
5 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-20 | 2024-06-18 |  | 284194 | 256196 | 227779
5 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-20 | 2024-06-18 |  | 170421 | 186124 | 138024
5 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Scope | Complete | 2021-03-02 | 2021-11-10 | 2021-11-05 | 23406 | 27334 | 27334
5 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Design | Complete | 2021-11-09 | 2022-04-05 | 2022-05-09 | 116471 | 119350 | 96158
5 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Construction | In-Progress | 2023-05-15 | 2024-08-11 |  | 2572569 | 2080139 | 658862
5 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-05-15 | 2024-08-11 |  | 168001 | 271407 | 269195
5 | P.S. 194 - MANHATTAN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | In-Progress | 2024-07-15 |  |  | 50000 | 50000 | 49774
5 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-01-27 | 2023-05-26 | 2023-04-19 | 8380 | 15725 | 15725
5 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-04-24 | 2023-10-24 | 2023-08-28 | 37710 | 48107 | 41712
5 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-03-05 | 2025-03-04 |  | 486040 | 489340 | 60150
5 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-03-05 | 2025-03-04 |  | 90085 | 61102 | 15850
5 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2021-04-29 | 2021-09-14 | 2021-11-17 | 210430 | 165632 | 147935
5 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2021-11-17 | 2022-05-06 | 2022-10-21 | 1052150 | 438769 | 384969
5 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 2023-08-03 | 2025-08-01 |  | 23673375 | 21299502 | 961823
5 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2023-08-03 | 2025-08-01 |  | 1473010 | 343973 | 339674
5 | P.S. 197 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-26 | 2024-11-26 | 2024-07-29 | 3126 | 602 | 602
5 | P.S. 197 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-29 | 2025-01-27 |  | 14066 | 14066 | 2407
5 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2023-02-27 | 2023-07-27 | 2023-12-14 | 658414 | 42093 | 29231
5 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2024-01-10 | 2024-08-12 | 2024-08-23 | 3072595 | 1015773 | 38003
5 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-05-18 | 2021-10-01 | 2022-01-14 | 80048 | 192462 | 189360
5 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2022-02-02 | 2022-07-05 | 2022-05-09 | 395977 | 291360 | 253117
5 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2023-07-18 | 2025-07-16 |  | 8541042 | 7897730 | 1736024
5 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-07-18 | 2025-07-16 |  | 592275 | 422121 | 409112
5 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-10-17 | 2023-02-17 | 2022-11-10 | 3672 | 2315 | 2315
5 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-11-10 | 2023-05-10 | 2023-01-18 | 16523 | 9259 | 9259
5 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-20 | 2024-06-18 |  | 212964 | 194780 | 167440
5 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-20 | 2024-06-18 |  | 161284 | 218278 | 170177
6 | P.S. 4 - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-09-09 | 2025-01-28 |  | 32829 | 29405 | 29405
6 | P.S. 5 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-04 | 2024-08-05 | 2024-04-16 | 4635 | 2671 | 2671
6 | P.S. 5 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-16 | 2024-10-10 | 2024-09-24 | 20855 | 10684 | 10684
6 | P.S. 8 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2024-01-09 | 2024-05-23 | 2024-06-12 | 18414 | 20374 | 2452
6 | P.S. 8 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 2024-06-24 | 2024-11-25 |  | 77468 | 77468 | 3758
6 | P.S. 28 - MANHATTAN | SCA CIP | WATER INFILTRATION INTO ELECTRCIAL EQUIPMENT / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2023-03-07 | 2023-07-21 | 2023-06-26 | 20595 | 14061 | 14061
6 | P.S. 28 - MANHATTAN | SCA CIP | WATER INFILTRATION INTO ELECTRCIAL EQUIPMENT / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2023-07-17 | 2023-12-18 | 2023-12-15 | 97886 | 82623 | 80579
6 | P.S. 48 - MANHATTAN | SCA CIP | CERTIFICATE OF OCCUPANCY | Scope | Complete | 2016-09-07 | 2016-12-08 | 2017-10-27 | 18951 | 131283 | 131283
6 | P.S. 48 - MANHATTAN | SCA CIP | CERTIFICATE OF OCCUPANCY | Design | Complete | 2017-11-07 | 2018-05-14 | 2018-05-22 | 75804 | 106822 | 105493
6 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 2023-01-17 | 2023-05-16 | 2023-09-26 | 457850 | 303629 | 31818
6 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 2023-10-04 | 2024-05-06 | 2024-05-08 | 2289250 | 1277743 | 524211
6 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Construction | In-Progress | 2024-07-17 | 2027-07-16 |  | 51508124 | 46280839 | 287839
6 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | CM,F&E | In-Progress | 2024-07-17 | 2027-07-16 |  | 3204950 | 256101 | 246815
6 | P.S. 48 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-17 | 2024-08-16 | 2024-04-30 | 4907 | 3287 | 3287
6 | P.S. 48 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-04-30 | 2024-10-25 |  | 22082 | 22082 | 13151
6 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2021-06-29 | 2021-10-28 | 2021-07-27 | 2596 | 12332 | 12332
6 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-07-27 | 2022-01-25 | 2021-12-15 | 11682 | 49340 | 49340
6 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-07-15 | 2023-04-10 |  | 150568 | 140015 | 113142
6 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-07-15 | 2023-04-10 |  | 189179 | 188767 | 184048
6 | J.H.S. 52 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 2023-01-20 | 2023-06-06 | 2023-11-01 | 236686 | 237547 | 165367
6 | J.H.S. 52 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Design | In-Progress | 2023-11-20 | 2024-04-23 |  | 1176020 | 1176020 | 205042
6 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-02-16 | 2023-06-16 | 2023-04-25 | 12972 | 19332 | 19332
6 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-04-25 | 2023-10-25 | 2023-08-25 | 58374 | 67674 | 51390
6 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-03-04 | 2025-03-03 |  | 752371 | 15087 | 53
6 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-03-04 | 2025-03-03 |  | 139448 | 22790 | 7756
6 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | Scope | Complete | 2020-08-20 | 2022-11-10 | 2022-09-09 | 338022 | 430382 | 402001
6 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | Design | Complete | 2022-09-27 | 2023-06-12 | 2023-05-05 | 1684198 | 1124880 | 881852
6 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | Construction | In-Progress | 2023-08-14 | 2026-08-07 |  | 37383068 | 33416039 | 9151808
6 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | CM,F&E | In-Progress | 2023-08-14 | 2026-08-07 |  | 2410487 | 233377 | 207870
6 | P.S. 210 - MANHATTAN | SCA CIP | ROOFS | Scope | Complete | 2021-03-10 | 2021-07-23 | 2021-11-01 | 22378 | 55044 | 52372
6 | P.S. 210 - MANHATTAN | SCA CIP | ROOFS | Design | Complete | 2021-11-01 | 2022-04-06 | 2022-03-29 | 111889 | 107390 | 74180
6 | P.S. 98 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-01-25 | 2023-04-25 | 2023-04-20 | 21522 | 84678 | 84596
6 | P.S. 98 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | In-Progress | 2023-05-01 | 2023-09-15 |  | 107608 | 116558 | 66267
6 | P.S. 98 - MANHATTAN | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Scope | Complete | 2023-03-28 | 2023-06-28 | 2023-07-13 | 3784 | 1335 | 1335
6 | P.S. 98 - MANHATTAN | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Design | In-Progress | 2023-07-17 | 2023-12-04 |  | 17029 | 17029 | 5338
6 | P.S. 98 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-06-28 | 2024-10-29 | 2024-07-09 | 3824 | 0 | 0
6 | P.S. 98 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-09 | 2025-01-06 |  | 17206 | 17206 | 0
6 | P.S. 115 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL UPGRADE | Scope | Complete | 2021-06-22 | 2021-11-05 | 2022-01-07 | 93227 | 167844 | 151172
6 | P.S. 115 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL UPGRADE | Design | Complete | 2022-01-12 | 2022-06-14 | 2022-05-11 | 466141 | 340471 | 313762
6 | P.S. 115 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2020-08-18 | 2021-01-20 | 2021-12-16 | 71574 | 88916 | 88916
6 | P.S. 115 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2021-12-16 | 2022-06-21 | 2022-08-15 | 357872 | 267873 | 238537
6 | P.S. 513 - MANHATTAN | SCA Furniture & Equipment | FY24 RESO A MOBILE STEM CARTS | F&E | Complete | 2024-07-11 |  | 2024-08-29 | 49930 | 49930 | 49930
6 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2020-12-15 | 2021-04-05 | 2021-11-16 | 120420 | 129719 | 129719
6 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2021-11-29 | 2022-05-23 | 2022-08-30 | 595229 | 426281 | 320906
6 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2023-08-07 | 2025-08-05 |  | 12798419 | 12698768 | 2469412
6 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-08-07 | 2025-08-05 |  | 894461 | 458635 | 386248
6 | P.S. 132 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-03 | 2024-11-01 | 2024-07-09 | 3589 | 28 | 28
6 | P.S. 132 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-09 | 2025-01-06 |  | 16152 | 16152 | 112
6 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2015-04-06 | 2018-02-01 | 2017-12-18 | 157058 | 158822 | 158822
6 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2018-01-26 | 2018-06-27 | 2018-05-09 | 635343 | 1229645 | 1100297
6 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2018-07-16 | 2020-11-01 |  | 11140918 | 13250059 | 10471864
6 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2018-07-16 | 2020-11-01 |  | 889516 | 1838131 | 1721515
6 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | Scope | Complete | 2021-07-08 | 2021-11-23 | 2021-11-15 | 256450 | 149324 | 149324
6 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | Design | Complete | 2021-12-01 | 2022-05-19 | 2022-05-11 | 1282250 | 1040643 | 615253
6 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | Construction | In-Progress | 2022-07-18 | 2024-07-16 |  | 28850625 | 26578168 | 3062009
6 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | CM,F&E | In-Progress | 2022-07-18 | 2024-07-16 |  | 1795150 | 736254 | 309303
6 | I.S. 143 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LIGHTING UPGRADE | Scope | Complete | 2023-08-31 | 2024-01-30 | 2024-02-26 | 371903 | 251567 | 251567
6 | I.S. 143 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LIGHTING UPGRADE | Design | In-Progress | 2024-07-02 | 2025-01-29 |  | 1838016 | 1838016 | 32540
6 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2018-10-10 | 2019-04-10 | 2019-09-06 | 31096 | 34530 | 34530
6 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2019-09-11 | 2020-05-20 | 2020-04-15 | 147389 | 140228 | 140228
6 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2021-09-15 | 2023-01-17 |  | 2616721 | 2390218 | 2135946
6 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2021-09-15 | 2023-01-17 |  | 278322 | 43434 | 43434
6 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Scope | Complete | 2018-06-25 | 2018-09-24 | 2018-10-09 | 84575 | 79488 | 79488
6 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Design | Complete | 2018-10-16 | 2019-03-06 | 2019-04-29 | 342970 | 342970 | 318240
6 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2019-07-31 | 2021-01-20 |  | 5596579 | 5585850 | 4723601
6 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2019-07-31 | 2021-01-20 |  | 878417 | 878417 | 849009
6 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | Scope | Complete | 2019-09-10 | 2020-01-14 | 2021-08-16 | 14579 | 22049 | 22049
6 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | Design | Complete | 2021-08-31 | 2022-02-04 | 2022-05-11 | 72894 | 85968 | 79267
6 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | Construction | In-Progress | 2022-11-14 | 2024-05-06 |  | 1640115 | 1487768 | 1199666
6 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2022-11-14 | 2024-05-06 |  | 102052 | 160658 | 159928
6 | P.S. 152 - MANHATTAN | SCA CIP | PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Scope | Complete | 2021-08-31 | 2021-12-03 | 2022-03-25 | 18526 | 18526 | 18526
6 | P.S. 152 - MANHATTAN | SCA CIP | PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Design | Complete | 2022-03-25 | 2022-07-25 | 2024-01-03 | 5436 | 5436 | 5436
6 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | Scope | Complete | 2023-05-30 | 2023-10-16 | 2023-09-25 | 229330 | 246882 | 240247
6 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | Design | Complete | 2023-10-25 | 2024-06-10 | 2024-04-25 | 1131307 | 404092 | 395914
6 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | Construction | In-Progress | 2024-08-15 | 2027-02-10 |  | 24127238 | 21671691 | 213891
6 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | CM,F&E | In-Progress | 2024-08-15 | 2027-02-10 |  | 1720382 | 63720 | 63720
6 | P.S. 152 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-27 | 2023-10-27 | 2023-10-05 | 10634 | 17749 | 17686
6 | P.S. 152 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-17 | 2024-03-18 | 2024-04-10 | 47852 | 44868 | 44868
6 | P.S. 152 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-11-17 | 2024-05-15 | 2024-04-02 | 27000 | 18005 | 18005
6 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-20 | 2022-12-06 | 2023-05-04 | 77350 | 143338 | 143338
6 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-06-14 | 2023-11-16 | 2023-10-27 | 386750 | 346454 | 305705
6 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-08-15 | 2027-02-10 |  | 8701876 | 7853254 | 112254
6 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-08-15 | 2027-02-10 |  | 541450 | 46132 | 46132
6 | I.S. 328 - MANHATTAN | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Scope | Complete | 2022-10-12 | 2023-07-14 | 2023-09-28 | 15192 | 48889 | 48889
6 | I.S. 328 - MANHATTAN | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Design | Complete | 2023-10-11 | 2024-02-15 | 2024-04-19 | 74053 | 64103 | 56250
6 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | Scope | Complete | 2017-12-18 | 2018-05-04 | 2018-03-23 | 165873 | 150089 | 150087
6 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | Design | Complete | 2018-03-23 | 2018-08-22 | 2018-05-18 | 652179 | 584627 | 529862
6 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | Construction | In-Progress | 2018-08-13 | 2020-08-11 |  | 11212637 | 12719807 | 8991567
6 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | CM,F&E | In-Progress | 2018-08-13 | 2020-08-11 |  | 921201 | 1980326 | 1925130
6 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-27 | 2023-10-27 | 2023-10-13 | 10620 | 16346 | 13367
6 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-16 | 2024-03-15 | 2024-04-10 | 47790 | 64196 | 54116
6 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-12 | 2025-09-11 |  | 615960 | 541080 | 0
6 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-12 | 2025-09-11 |  | 114165 | 75518 | 8090
6 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | Scope | Complete | 2019-06-27 | 2021-07-13 | 2021-09-23 | 68580 | 95630 | 95630
6 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | Design | Complete | 2022-01-11 | 2022-05-26 | 2022-07-19 | 326100 | 298937 | 276308
6 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | Construction | In-Progress | 2023-05-03 | 2025-05-01 |  | 7085251 | 6750375 | 1214735
6 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-05-03 | 2025-05-01 |  | 442390 | 500941 | 486115
6 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-06-28 | 2022-10-27 | 2022-07-06 | 3660 | 5349 | 5349
6 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-07-06 | 2023-01-03 | 2023-01-04 | 16470 | 21397 | 21397
6 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-21 | 2024-04-15 |  | 212280 | 189728 | 149015
6 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-21 | 2024-04-15 |  | 176297 | 166968 | 155035
6 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2020-01-16 | 2021-05-24 | 2022-02-15 | 104838 | 104838 | 99073
6 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-02-16 | 2022-04-18 | 2022-11-01 | 142866 | 142866 | 79738
6 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-06-12 | 2024-05-06 |  | 808674 | 766843 | 286485
6 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-06-12 | 2024-05-06 |  | 156216 | 156216 | 43237
6 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-08-09 | 2023-12-13 | 2023-11-01 | 113541 | 57591 | 52776
6 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | Scope | Complete | 2017-12-18 | 2018-05-04 | 2018-02-28 | 185319 | 256806 | 256760
6 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | Design | Complete | 2018-02-28 | 2018-07-30 | 2018-05-17 | 735179 | 1185363 | 933574
6 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | Construction | In-Progress | 2018-08-13 | 2020-08-11 |  | 13237508 | 21288762 | 16287075
6 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | CM,F&E | In-Progress | 2018-08-13 | 2020-08-11 |  | 944063 | 1713359 | 1509888
6 | P.S. 192 - MANHATTAN | SCA CIP | EXTERIOR STAIRS / PAVED AREAS - CONCRETE / NON-TCU TEMPORARY REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2020-10-22 | 2023-05-17 | 2023-06-05 | 37500 | 133176 | 118997
6 | P.S. 192 - MANHATTAN | SCA CIP | EXTERIOR STAIRS / PAVED AREAS - CONCRETE / NON-TCU TEMPORARY REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-06-06 | 2023-10-23 | 2023-12-29 | 186383 | 289250 | 197228
6 | HAMILTON GRANGE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-08-08 | 2024-01-11 | 2024-01-05 | 14461 | 54518 | 48571
6 | I.S. 293 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ELECTRIFICATION/HEAT PUMP SYSTEMS / EXTERIOR MASONRY / PARAPETS / ROOFS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SERVICE UPGRADE / WINDOWS / LIGHTING UPGRADE | Scope | Complete | 2022-07-08 | 2023-11-22 | 2024-03-01 | 673976 | 953582 | 669935
6 | I.S. 293 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ELECTRIFICATION/HEAT PUMP SYSTEMS / EXTERIOR MASONRY / PARAPETS / ROOFS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SERVICE UPGRADE / WINDOWS / LIGHTING UPGRADE | Design | Complete | 2024-03-01 | 2024-08-01 | 2024-05-15 | 3365191 | 1695891 | 1679351
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | Scope | Complete | 2017-09-11 | 2017-09-14 | 2017-09-21 | 26700 | 70204 | 70204
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | Design | Complete | 2017-09-21 | 2018-06-29 | 2018-08-08 | 97900 | 132798 | 124219
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | Construction | In-Progress | 2019-04-03 | 2020-04-01 |  | 1036850 | 1151245 | 911896
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | CM,F&E | In-Progress | 2019-04-03 | 2020-04-01 |  | 240300 | 293066 | 284487
6 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | Scope | Complete | 2018-04-02 | 2018-07-31 | 2018-08-06 | 27662 | 126860 | 126860
6 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | Design | Complete | 2021-12-01 | 2022-05-04 | 2023-05-12 | 138310 | 310782 | 24743
6 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | Construction | In-Progress | 2023-08-14 | 2025-02-03 |  | 3111982 | 2832214 | 1501581
6 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | CM,F&E | In-Progress | 2023-08-14 | 2025-02-03 |  | 193634 | 130564 | 124878
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2018-11-15 | 2019-04-04 | 2019-04-04 | 564406 | 471256 | 471256
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2019-04-05 | 2019-09-05 | 2019-05-16 | 2257620 | 1196023 | 1024916
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2019-07-22 | 2022-06-15 |  | 42330374 | 42706997 | 36599952
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2019-07-22 | 2022-06-15 |  | 2633889 | 2611828 | 2414706
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | Scope | Complete | 2020-01-03 | 2020-05-19 | 2021-10-14 | 57240 | 124249 | 106234
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | Design | Complete | 2021-10-18 | 2022-04-22 | 2022-09-26 | 286200 | 464066 | 412376
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | Construction | In-Progress | 2023-05-08 | 2025-05-06 |  | 6439500 | 5924108 | 3104031
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | CM,F&E | In-Progress | 2023-05-08 | 2025-05-06 |  | 400680 | 216186 | 209022
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2013-09-18 | 2019-10-04 | 2019-10-01 | 216730 | 202664 | 202664
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2019-10-01 | 2020-03-06 | 2021-05-12 | 1083650 | 1126786 | 1033140
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2022-07-11 | 2025-01-07 |  | 24382125 | 22414923 | 16659373
6 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2022-07-11 | 2025-01-07 |  | 1517110 | 825162 | 808888
6 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2020-10-26 | 2021-03-23 | 2021-03-23 | 2036860 | 1480120 | 1444512
6 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | Design | Complete | 2021-03-24 | 2021-10-25 | 2021-11-03 | 9165870 | 5472738 | 5142063
6 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2022-09-15 | 2024-09-03 |  | 115591805 | 105690237 | 100901655
6 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2022-09-15 | 2024-09-03 |  | 16294880 | 9496489 | 6608399
6 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | Scope | Complete | 2021-01-20 | 2021-01-20 | 2021-01-20 | 17304 | 35264 | 35264
6 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | Design | Complete | 2021-01-20 | 2021-10-25 | 2021-12-01 | 86520 | 141063 | 141063
6 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | Construction | In-Progress | 2022-01-03 | 2022-07-01 |  | 1946700 | 2840866 | 2647621
6 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2022-01-03 | 2022-07-01 |  | 121128 | 832812 | 293321
6 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-06 | 2022-11-03 | 2022-07-19 | 5800 | 7547 | 7547
6 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-07-19 | 2023-01-17 | 2023-01-04 | 26100 | 30192 | 30192
6 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-21 | 2024-04-15 |  | 336400 | 299652 | 206868
6 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-21 | 2024-04-15 |  | 114284 | 105830 | 74080
6 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-12-21 | 2023-05-09 | 2023-07-05 | 83526 | 66393 | 65113
6 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | Scope | Complete | 2018-06-25 | 2018-09-24 | 2018-10-09 | 76528 | 76528 | 76528
6 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | Design | Complete | 2018-10-16 | 2019-03-06 | 2019-04-29 | 208701 | 208701 | 208701
6 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | Construction | In-Progress | 2019-07-31 | 2021-01-20 |  | 1520197 | 1398265 | 1277223
6 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | CM,F&E | In-Progress | 2019-07-31 | 2021-01-20 |  | 94590 | 71176 | 71176
6 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | Scope | Complete | 2021-01-11 | 2021-04-12 | 2021-01-19 | 1584 | 1037 | 1037
6 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | Design | Complete | 2021-01-20 | 2021-06-21 | 2021-04-12 | 7127 | 4772 | 4147
6 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | Construction | In-Progress | 2021-09-15 | 2023-01-17 |  | 91856 | 138821 | 76663
6 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | CM,F&E | In-Progress | 2021-09-15 | 2023-01-17 |  | 17025 | 213249 | 212624
6 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 2022-03-28 | 2022-07-26 | 2022-04-14 | 1477 | 2955 | 2955
6 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 2022-04-14 | 2022-10-07 | 2022-07-19 | 6646 | 11817 | 11817
6 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 2023-03-09 | 2024-02-01 |  | 85658 | 83295 | 72203
6 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 2023-03-09 | 2024-02-01 |  | 123026 | 136131 | 96735
6 | U.F.B.C.O. | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 2021-04-07 | 2021-07-07 | 2021-08-06 | 780 | 35150 | 35150
7 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 2019-06-26 | 2019-11-12 | 2019-12-03 | 57964 | 82112 | 82112
7 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 2019-12-18 | 2020-05-20 | 2022-02-28 | 285806 | 233037 | 233037
7 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 2022-07-11 | 2024-01-01 |  | 6083424 | 6137210 | 5667959
7 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 2022-07-11 | 2024-01-01 |  | 435851 | 312897 | 309861
7 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-28 | 2022-11-29 | 2022-11-15 | 3721 | 9128 | 9128
7 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-11-15 | 2023-05-12 | 2023-02-15 | 16744 | 36511 | 36511
7 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-06-03 |  | 215817 | 199168 | 182941
7 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-06-03 |  | 129296 | 118045 | 91553
7 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2018-09-25 | 2019-08-29 | 2019-05-01 | 25281 | 17964 | 17964
7 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2019-05-01 | 2019-10-01 | 2019-05-16 | 93087 | 75917 | 71980
7 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2019-07-22 | 2020-04-16 |  | 990715 | 2011186 | 1287255
7 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2019-07-22 | 2020-04-16 |  | 228349 | 477117 | 416396
7 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-08-08 | 2023-12-08 | 2023-08-22 | 4690 | 1648 | 1648
7 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-22 | 2024-02-21 | 2023-11-29 | 21105 | 6593 | 6593
7 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-04-12 | 2025-02-05 |  | 272020 | 248850 | 1810
7 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-04-12 | 2025-02-05 |  | 50418 | 30654 | 5328
7 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2018-11-06 | 2019-03-27 | 2019-02-26 | 115360 | 98171 | 98171
7 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 2019-02-27 | 2019-07-29 | 2019-05-17 | 454495 | 499266 | 408517
7 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2019-07-22 | 2021-01-11 |  | 7898289 | 8227320 | 7313883
7 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2019-07-22 | 2021-01-11 |  | 628661 | 998864 | 978247
7 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 2020-12-22 | 2021-04-22 | 2021-11-23 | 76950 | 105699 | 105699
7 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 2021-11-29 | 2022-05-23 | 2022-08-16 | 384750 | 375001 | 310720
7 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2023-04-10 | 2025-03-09 |  | 8656875 | 8898335 | 3502505
7 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2023-04-10 | 2025-03-09 |  | 538650 | 355044 | 352609
7 | P.S. 277 - BRONX | SCA CIP | RETAINING WALL | Scope | Complete | 2022-02-23 | 2022-05-23 | 2022-03-29 | 8577 | 0 | 0
7 | P.S. 277 - BRONX | SCA CIP | RETAINING WALL | Design | Complete | 2022-03-29 | 2022-03-29 | 2022-03-29 | 38597 | 0 | 0
7 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-08-18 | 2020-12-18 | 2020-08-21 | 5200 | 3620 | 3620
7 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-08-21 | 2021-02-17 | 2021-05-26 | 23400 | 14481 | 14481
7 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-06-29 | 2023-04-24 |  | 301600 | 272834 | 240608
7 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-06-29 | 2023-04-24 |  | 187128 | 177616 | 176048
7 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 2021-06-04 | 2021-10-20 | 2021-12-07 | 96300 | 137083 | 137083
7 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 2021-12-08 | 2022-05-11 | 2022-05-12 | 481500 | 421066 | 421066
7 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 2022-08-15 | 2024-08-13 |  | 10833750 | 9975380 | 6158212
7 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 2022-08-15 | 2024-08-13 |  | 675329 | 411245 | 410592
7 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | Scope | Complete | 2015-10-27 | 2017-02-16 | 2017-02-27 | 331508 | 452076 | 452076
7 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | Design | Complete | 2017-04-26 | 2017-09-26 | 2018-04-20 | 1318825 | 1464844 | 1079218
7 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | Construction | In-Progress | 2018-07-09 | 2020-09-05 |  | 24081321 | 30123194 | 22853588
7 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | CM,F&E | In-Progress | 2018-07-09 | 2020-09-05 |  | 1682970 | 3425395 | 3154387
7 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-04-29 | 2022-08-29 | 2022-08-25 | 4663 | 7401 | 7401
7 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-08-25 | 2023-02-24 | 2023-02-15 | 20982 | 29602 | 29602
7 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-06-03 |  | 270432 | 247372 | 228695
7 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-06-03 |  | 174742 | 154792 | 117439
7 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | Scope | Complete | 2019-05-29 | 2021-08-19 | 2021-07-12 | 170880 | 149317 | 139319
7 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | Design | Complete | 2021-10-20 | 2022-04-11 | 2023-03-20 | 854400 | 545180 | 436140
7 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | Construction | In-Progress | 2023-08-14 | 2025-08-02 |  | 19224000 | 17857289 | 2668106
7 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | CM,F&E | In-Progress | 2023-08-14 | 2025-08-02 |  | 1196160 | 286857 | 275407
7 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2021-03-23 | 2021-08-05 | 2022-01-27 | 161224 | 146826 | 146826
7 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2022-05-27 | 2022-12-01 | 2023-05-12 | 801894 | 674151 | 596966
7 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2023-07-10 | 2025-08-07 |  | 17677282 | 16071205 | 1813646
7 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2023-07-10 | 2025-08-07 |  | 1160238 | 401860 | 396310
7 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 2020-08-05 | 2020-12-04 | 2021-07-02 | 44200 | 22516 | 20065
7 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 2021-07-07 | 2021-12-08 | 2021-12-22 | 221000 | 155225 | 56256
7 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2024-07-15 | 2026-05-15 |  | 4972500 | 4834908 | 403633
7 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2024-07-15 | 2026-05-15 |  | 309400 | 44844 | 44844
7 | P.S. 65 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-09-11 | 2025-01-14 | 2024-09-18 | 4093 | 1073 | 1073
7 | P.S. 65 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-09-18 | 2025-03-19 |  | 18417 | 18417 | 4291
7 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | Scope | Complete | 2020-08-12 | 2021-01-15 | 2020-12-04 | 75640 | 99774 | 99774
7 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | Design | Complete | 2020-12-07 | 2021-05-10 | 2021-03-17 | 378200 | 402471 | 379743
7 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | Construction | In-Progress | 2022-05-23 | 2024-05-21 |  | 8509501 | 7767721 | 6635795
7 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | CM,F&E | In-Progress | 2022-05-23 | 2024-05-21 |  | 529480 | 340520 | 327876
7 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2021-03-12 | 2021-07-12 | 2021-03-25 | 4700 | 6783 | 6783
7 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-03-25 | 2021-08-17 | 2021-08-25 | 21150 | 27203 | 27203
7 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-06-29 | 2023-04-24 |  | 272600 | 248269 | 218053
7 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-06-29 | 2023-04-24 |  | 265097 | 255831 | 178334
7 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 2018-07-25 | 2018-12-11 | 2019-09-23 | 97962 | 137543 | 137543
7 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 2019-11-06 | 2020-04-27 | 2020-06-30 | 481290 | 475221 | 404814
7 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | In-Progress | 2021-08-16 | 2023-05-17 |  | 10091829 | 10016192 | 8875441
7 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 2021-08-16 | 2023-05-17 |  | 749657 | 903423 | 863768
7 | P.S. 154 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | In-Progress | 2024-09-24 | 2025-01-28 |  | 5611 | 5611 | 597
7 | P.S. 154 - BRONX | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-07-19 | 2023-12-20 | 2024-01-22 | 56764 | 109929 | 34614
7 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2023-06-15 | 2023-12-14 | 2023-10-25 | 135892 | 95148 | 93939
7 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2023-11-06 | 2024-06-28 | 2024-04-04 | 679460 | 224545 | 224545
7 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 2024-09-16 | 2026-11-04 |  | 15287850 | 13713741 | 109535
7 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 2024-09-16 | 2026-11-04 |  | 951243 | 36547 | 36547
7 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-03 | 2024-09-04 | 2024-05-13 | 5477 | 665 | 665
7 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-05-13 | 2025-03-12 | 2024-09-17 | 24648 | 2661 | 2661
7 | P.S. 157 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-19 | 2024-08-20 | 2024-04-23 | 4663 | 386 | 386
7 | P.S. 157 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-23 | 2024-10-18 | 2024-09-17 | 20982 | 1546 | 1546
7 | P.S. 161 - BRONX | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-01-12 | 2023-05-30 | 2023-12-06 | 41773 | 173121 | 173082
7 | P.S. 161 - BRONX | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-12-08 | 2024-05-10 | 2024-05-14 | 203358 | 193070 | 184110
7 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-08-31 | 2023-01-04 | 2022-11-15 | 3596 | 9200 | 9200
7 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-11-15 | 2023-05-12 | 2023-02-15 | 16184 | 36798 | 36798
7 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-06-03 |  | 208591 | 192224 | 177327
7 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-06-03 |  | 149998 | 149204 | 107758
7 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-11 | 2022-11-25 | 2023-11-22 | 52640 | 215935 | 209457
7 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-11-28 | 2024-04-30 | 2024-05-02 | 263200 | 411674 | 312034
7 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-09-09 | 2026-08-09 |  | 5922000 | 5473979 | 110058
7 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-09-09 | 2026-08-09 |  | 368480 | 132584 | 37446
7 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-07-06 | 2023-11-06 | 2023-10-25 | 11900 | 16395 | 16395
7 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-11-01 | 2024-04-01 | 2024-04-12 | 53550 | 103603 | 48914
7 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-12 | 2025-09-11 |  | 690200 | 668899 | 14808
7 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-12 | 2025-09-11 |  | 127925 | 130040 | 12689
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-04-07 | 2021-08-20 | 2021-09-02 | 44214 | 177726 | 174955
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2021-09-15 | 2022-02-18 | 2022-05-05 | 216529 | 257503 | 252226
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2022-07-11 | 2024-01-01 |  | 4479323 | 4297283 | 3976786
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-07-11 | 2024-01-01 |  | 343538 | 381367 | 377337
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | SCIENCE LAB UPGRADE | Scope | Complete | 2024-03-05 | 2024-06-18 | 2024-06-03 | 15652 | 20939 | 2039
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | SCIENCE LAB UPGRADE | Design | In-Progress | 2024-06-06 | 2024-11-07 |  | 78262 | 78262 | 8153
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | PATH OF TRAVEL SCIENCE LAB UPGRADE | Scope | Complete | 2024-06-04 | 2024-09-05 | 2024-07-02 | 2926 | 267 | 267
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | PATH OF TRAVEL SCIENCE LAB UPGRADE | Design | In-Progress | 2024-08-05 | 2024-12-04 |  | 11705 | 11705 | 1067
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-03-11 | 2020-07-09 | 2020-06-04 | 3546 | 3557 | 3557
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-06-04 | 2020-12-01 | 2020-12-01 | 15956 | 14226 | 14226
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-07-18 | 2023-05-13 |  | 205654 | 189589 | 178283
7 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-07-18 | 2023-05-13 |  | 194321 | 221837 | 216934
7 | LEARNING THROUGH PLAY PRE-K CENTER | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LABS | F&E | Complete | 2024-05-30 |  | 2024-07-10 | 65000 | 65000 | 65000
7 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2018-11-07 | 2021-09-09 | 2021-12-15 | 89549 | 241244 | 241244
7 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | Design | Complete | 2021-12-17 | 2022-05-20 | 2023-02-15 | 409361 | 584037 | 535067
7 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2023-06-20 | 2025-05-19 |  | 8279391 | 7886207 | 3555241
7 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-06-20 | 2025-05-19 |  | 586171 | 376337 | 320168
7 | P.S. @ 639 ST ANN'S AVENUE - BRONX | SCA Capacity | NEW SCHOOL | Scope | Complete | 2019-04-01 | 2019-09-06 | 2019-08-28 | 1335780 | 1405829 | 1385877
7 | P.S. @ 639 ST ANN'S AVENUE - BRONX | SCA Capacity | NEW SCHOOL | Design | Complete | 2019-08-29 | 2020-04-01 | 2020-04-01 | 6011010 | 4958965 | 4762051
7 | P.S. @ 639 ST ANN'S AVENUE - BRONX | SCA Capacity | NEW SCHOOL | Construction | Complete | 2021-08-02 | 2024-09-03 | 2024-05-13 | 75805515 | 69156272 | 65374035
7 | P.S. @ 639 ST ANN'S AVENUE - BRONX | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 2021-08-02 | 2024-09-03 | 2024-05-13 | 10686240 | 8001439 | 6579352
7 | ALFRED E. SMITH HS - X | SCA CIP | STRUCTURAL CONCRETE FAILURE @ X600 | Scope | Complete | 2022-08-05 | 2022-12-22 | 2022-12-14 | 19525 | 12861 | 12861
7 | ALFRED E. SMITH HS - X | SCA CIP | STRUCTURAL CONCRETE FAILURE @ X600 | Design | Complete | 2022-12-23 | 2023-05-26 | 2023-08-02 | 87863 | 37377 | 3524
7 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-03-09 | 2020-07-07 | 2020-06-04 | 3806 | 3584 | 3584
7 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-06-04 | 2020-12-01 | 2020-12-01 | 17128 | 14336 | 14336
7 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-07-18 | 2023-05-13 |  | 220758 | 203918 | 185723
7 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-07-18 | 2023-05-13 |  | 223156 | 251993 | 242634
7 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | Scope | Complete | 2018-09-07 | 2019-02-06 | 2018-11-26 | 43770 | 25975 | 25975
7 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | Design | Complete | 2018-12-05 | 2019-05-29 | 2019-05-17 | 175080 | 262283 | 122751
7 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | Construction | In-Progress | 2019-08-05 | 2020-08-03 |  | 3282750 | 3199145 | 2894174
7 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | CM,F&E | In-Progress | 2019-08-05 | 2020-08-03 |  | 289590 | 1131670 | 1120714
7 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | Scope | Complete | 2020-02-10 | 2020-07-07 | 2021-05-03 | 37750 | 60357 | 60357
7 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | Design | Complete | 2021-05-10 | 2021-10-26 | 2022-05-13 | 188750 | 254143 | 246758
7 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | Construction | In-Progress | 2022-08-11 | 2024-02-01 |  | 4246876 | 3928269 | 1981789
7 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | CM,F&E | In-Progress | 2022-08-11 | 2024-02-01 |  | 264250 | 341074 | 328788
7 | X188 SPED - BRONX | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 2021-10-08 | 2022-02-14 | 2022-02-03 | 26831 | 19849 | 19849
7 | X188 SPED - BRONX | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 2022-12-20 | 2023-05-08 | 2023-06-15 | 129250 | 102038 | 90493
7 | DOE ADMINISTRATIVE OFFICE - BRONX | SCA CIP | SITE WALLS | Scope | In-Progress | 2024-05-07 | 2024-09-23 |  | 15000 | 15000 | 542
8 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2017-09-21 | 2018-02-09 | 2017-12-19 | 23694 | 29336 | 29144
8 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2018-08-01 | 2019-01-04 | 2019-04-23 | 94776 | 159173 | 139135
8 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 2019-07-15 | 2020-10-06 |  | 1777049 | 1910651 | 1131729
8 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 2019-07-15 | 2020-10-06 |  | 110572 | 338201 | 327362
8 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | COVID VENTILATION | Scope | Complete | 2021-01-05 | 2021-05-05 | 2021-09-15 | 57262 | 107560 | 96635
8 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | COVID VENTILATION | Design | Complete | 2021-09-24 | 2022-02-24 | 2022-03-01 | 286311 | 188101 | 177977
8 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 2022-06-21 | 2022-11-17 | 2022-11-23 | 290421 | 290421 | 288724
8 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SERVICE UPGRADE | Design | Complete | 2022-11-30 | 2023-05-26 | 2024-05-21 | 1006108 | 1006108 | 970753
8 | HOLCOMBE L. RUCKER SCHOOLOF COMMUNITY RESEARCH - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE | Design | Complete | 2016-09-15 | 2017-03-09 | 2017-03-08 | 36870 | 299175 | 298514
8 | HOLCOMBE L. RUCKER SCHOOLOF COMMUNITY RESEARCH - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2018-06-21 | 2018-12-17 |  | 540766 | 587759 | 538239
8 | HOLCOMBE L. RUCKER SCHOOLOF COMMUNITY RESEARCH - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2018-06-21 | 2018-12-17 |  | 36870 | 106605 | 104747
8 | I.S. 302 - BRONX | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 2022-11-29 | 2023-04-17 | 2023-05-03 | 90954 | 41149 | 36085
8 | I.S. 302 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2020-02-05 | 2020-07-30 | 2020-05-14 | 27000 | 32440 | 32195
8 | I.S. 302 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2021-06-09 | 2022-04-04 |  | 396000 | 180665 | 159599
8 | I.S. 302 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2021-06-09 | 2022-04-04 |  | 186857 | 216102 | 189749
8 | I.S. 302 - BRONX | SCA CIP RESOA | FY21 RESO A STEM LAB / PATH OF TRAVEL RESO A STEM LAB | Design | Complete | 2023-03-22 | 2023-07-25 | 2023-05-02 | 47934 | 85324 | 68437
8 | I.S. 302 - BRONX | SCA CIP RESOA | FY21 RESO A STEM LAB / PATH OF TRAVEL RESO A STEM LAB | Construction | In-Progress | 2023-12-22 | 2024-12-20 |  | 703036 | 644813 | 3583
8 | I.S. 302 - BRONX | SCA CIP RESOA | FY21 RESO A STEM LAB / PATH OF TRAVEL RESO A STEM LAB | CM,F&E | In-Progress | 2023-12-22 | 2024-12-20 |  | 47934 | 68841 | 20870
8 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | FLOOD ELIMINATION / ROOFS | Scope | Complete | 2024-01-09 | 2024-05-23 | 2024-08-13 | 26981 | 84061 | 50590
8 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | FLOOD ELIMINATION / ROOFS | Design | In-Progress | 2024-09-06 | 2025-02-11 |  | 121397 | 121397 | 4254
8 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-06-20 | 2024-10-21 | 2024-07-01 | 4906 | 1542 | 1542
8 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-01 | 2024-12-27 |  | 22077 | 22077 | 6167
8 | P.S. 62 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-18 | 2024-11-18 | 2024-07-23 | 4708 | 1253 | 1253
8 | P.S. 62 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-23 | 2025-01-21 |  | 21187 | 21187 | 5011
8 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-04-01 | 2021-09-22 | 2021-11-03 | 185950 | 202706 | 202706
8 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | Design | Complete | 2021-11-10 | 2022-05-02 | 2022-08-09 | 929750 | 715665 | 678744
8 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-03-15 | 2025-03-13 |  | 20919375 | 19266787 | 3579221
8 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-03-15 | 2025-03-13 |  | 1301650 | 140133 | 140133
8 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2019-06-19 | 2019-11-04 | 2019-11-01 | 59740 | 140291 | 140017
8 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | Design | Complete | 2020-02-19 | 2020-07-20 | 2022-04-29 | 298700 | 290665 | 289542
8 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2022-10-12 | 2024-07-02 |  | 6720750 | 6088556 | 3259144
8 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-10-12 | 2024-07-02 |  | 425671 | 384956 | 368949
8 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2019-07-29 | 2021-07-09 | 2021-11-24 | 409144 | 531249 | 515060
8 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 2021-12-07 | 2022-05-10 | 2022-10-11 | 2032006 | 1817358 | 1448093
8 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 2023-08-03 | 2026-08-02 |  | 44534318 | 40603122 | 5796974
8 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-08-03 | 2026-08-02 |  | 2966811 | 487435 | 471768
8 | P.S. 72 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 2022-03-17 | 2022-08-01 | 2023-02-07 | 92868 | 174901 | 164656
8 | P.S. 72 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 2023-05-17 | 2023-10-19 | 2024-05-13 | 460223 | 341490 | 239495
8 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2018-10-19 | 2019-03-11 | 2019-10-03 | 89717 | 163059 | 163058
8 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2019-12-04 | 2020-05-06 | 2021-04-13 | 433912 | 903723 | 711292
8 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2021-07-13 | 2023-04-03 |  | 8493945 | 14861269 | 9450821
8 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-07-13 | 2023-04-03 |  | 738053 | 771432 | 599331
8 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-10-16 | 2021-02-19 | 2021-02-12 | 3944 | 3962 | 3962
8 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-02-12 | 2021-08-09 | 2021-07-14 | 17748 | 15849 | 15849
8 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-07-29 | 2023-05-24 |  | 228752 | 208950 | 180509
8 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-07-29 | 2023-05-24 |  | 243606 | 239926 | 159635
8 | I.S. 424 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-01-10 | 2022-05-25 | 2024-05-10 | 97500 | 69355 | 65747
8 | I.S. 424 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-03-22 | 2022-07-25 | 2024-05-10 | 1960 | 22895 | 8706
8 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 2018-10-24 | 2019-02-22 | 2019-04-08 | 358164 | 319216 | 319216
8 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | Complete | 2019-08-07 | 2020-01-15 | 2020-06-30 | 1790823 | 1107674 | 1059170
8 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Construction | In-Progress | 2021-08-02 | 2024-07-16 |  | 40293507 | 37178902 | 19978598
8 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | CM,F&E | In-Progress | 2021-08-02 | 2024-07-16 |  | 2507152 | 682573 | 627630
8 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 2020-08-03 | 2020-12-03 | 2021-06-30 | 34550 | 23504 | 16973
8 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 2021-07-07 | 2021-12-08 | 2021-11-22 | 172750 | 113954 | 96559
8 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2023-07-10 | 2024-10-01 |  | 3886875 | 3932688 | 522780
8 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2023-07-10 | 2024-10-01 |  | 241850 | 96266 | 78871
8 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-11-16 | 2023-03-21 | 2022-12-13 | 4672 | 5811 | 5811
8 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-13 | 2023-06-09 | 2023-02-08 | 21026 | 23245 | 23245
8 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-10 | 2024-06-04 |  | 270999 | 241552 | 167912
8 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-10 | 2024-06-04 |  | 166957 | 155243 | 99899
8 | P.S. 75 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-03-14 | 2022-07-15 | 2022-05-11 | 77520 | 71543 | 53103
8 | P.S. 75 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-08-11 | 2024-05-06 |  | 1136960 | 989068 | 7018
8 | P.S. 75 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-08-11 | 2024-05-06 |  | 77520 | 84287 | 9520
8 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2017-05-15 | 2017-10-16 | 2017-07-07 | 99450 | 120648 | 120648
8 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2017-07-14 | 2017-12-15 | 2018-01-12 | 397800 | 418734 | 408132
8 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2018-07-09 | 2020-07-07 |  | 7458750 | 7052282 | 6543372
8 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2018-07-09 | 2020-07-07 |  | 464100 | 995394 | 987908
8 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-11-28 | 2023-03-30 | 2022-12-13 | 5300 | 6356 | 6356
8 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-13 | 2023-06-09 | 2023-02-08 | 23850 | 25424 | 25424
8 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-10 | 2024-06-04 |  | 307400 | 274511 | 198279
8 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-10 | 2024-06-04 |  | 191294 | 176957 | 121671
8 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2022-06-28 | 2022-11-14 | 2022-10-26 | 71874 | 81842 | 81432
8 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 2022-11-30 | 2023-05-03 | 2023-11-15 | 347396 | 225567 | 157040
8 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 2024-04-26 | 2026-04-15 |  | 6780659 | 6255154 | 654070
8 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2024-04-26 | 2026-04-15 |  | 592923 | 113363 | 113094
8 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | Scope | Complete | 2017-09-15 | 2018-02-05 | 2018-02-02 | 16049 | 17430 | 17430
8 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | Design | Complete | 2018-03-16 | 2018-08-15 | 2018-10-17 | 58847 | 63875 | 63875
8 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 2019-02-21 | 2019-11-17 |  | 623246 | 449483 | 361692
8 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 2019-02-21 | 2019-11-17 |  | 144443 | 205046 | 197438
8 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | Scope | Complete | 2023-06-05 | 2023-12-04 | 2023-10-30 | 124676 | 142776 | 123868
8 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | Design | Complete | 2023-11-14 | 2024-04-17 | 2024-04-16 | 623380 | 325614 | 325614
8 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | Construction | In-Progress | 2024-08-02 | 2026-08-01 |  | 14026051 | 12803190 | 295098
8 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | CM,F&E | In-Progress | 2024-08-02 | 2026-08-01 |  | 872733 | 88083 | 88083
8 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2020-07-09 | 2020-12-10 | 2020-09-15 | 88770 | 68219 | 68219
8 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2020-09-18 | 2021-02-24 | 2021-01-08 | 443850 | 287980 | 259780
8 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2023-07-05 | 2025-07-03 |  | 9986625 | 9128553 | 2606562
8 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2023-07-05 | 2025-07-03 |  | 622422 | 352747 | 348084
8 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-17 | 2023-05-16 | 2023-02-02 | 2960 | 2598 | 2598
8 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-02 | 2023-07-31 | 2023-04-12 | 13320 | 10390 | 10390
8 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-06 | 2024-09-30 |  | 171680 | 159324 | 2094
8 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-06 | 2024-09-30 |  | 31820 | 20320 | 4227
8 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2017-09-01 | 2018-01-23 | 2018-01-30 | 68640 | 120343 | 120343
8 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2020-01-08 | 2020-06-09 | 2020-05-07 | 343200 | 529193 | 495214
8 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-07-06 | 2023-07-05 |  | 7722000 | 8657841 | 7412268
8 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-07-06 | 2023-07-05 |  | 480479 | 742802 | 689073
8 | I.S. 123 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2023-12-11 | 2024-04-26 | 2024-07-31 | 190360 | 175422 | 115751
8 | I.S. 123 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | In-Progress | 2024-08-27 | 2025-01-31 |  | 881723 | 881723 | 9772
8 | P.S. 119 - BRONX | SCA CIP | SEWAGE TANK REPLACEMENT- PERM FIX @ X125 | Scope | Complete | 2023-10-04 | 2024-02-08 | 2024-01-05 | 7019 | 11672 | 11672
8 | P.S. 119 - BRONX | SCA CIP | SEWAGE TANK REPLACEMENT- PERM FIX @ X125 | Design | Complete | 2024-01-22 | 2024-05-15 | 2024-04-25 | 31586 | 28596 | 27063
8 | I.S. 562 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-05-18 | 2023-10-20 | 2023-12-18 | 45000 | 49395 | 46894
8 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-06-21 | 2019-11-22 | 2019-09-25 | 60358 | 62272 | 62272
8 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-10-04 | 2020-03-11 | 2020-02-11 | 294168 | 282565 | 263071
8 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-07-12 | 2023-07-11 |  | 5959342 | 5907648 | 5524621
8 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-07-12 | 2023-07-11 |  | 479686 | 469661 | 468786
8 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | Scope | Complete | 2020-01-15 | 2022-06-03 | 2022-11-15 | 11900 | 31873 | 31873
8 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | Design | Complete | 2022-11-25 | 2023-04-07 | 2023-04-17 | 53550 | 118629 | 49832
8 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | Construction | In-Progress | 2023-08-16 | 2024-06-10 |  | 690200 | 713225 | 191828
8 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 2023-08-16 | 2024-06-10 |  | 128883 | 126879 | 76102
8 | I.S. 131 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 2019-04-03 | 2019-09-03 | 2022-03-25 | 49500 | 63829 | 37502
8 | I.S. 131 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2023-02-10 | 2023-11-06 |  | 726000 | 420982 | 363415
8 | I.S. 131 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-02-10 | 2023-11-06 |  | 49500 | 54369 | 41605
8 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-07-01 | 2024-12-03 |  | 57000 | 42889 | 2470
8 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 2024-09-30 | 2025-03-06 |  | 59627 | 43549 | 2325
8 | P.S. 138 - BRONX | SCA Capacity | ADDITION | Scope | Complete | 2019-09-06 | 2020-03-12 | 2020-10-23 | 1155980 | 733168 | 732146
8 | P.S. 138 - BRONX | SCA Capacity | ADDITION | Design | Complete | 2020-10-26 | 2020-09-14 | 2021-08-12 | 5201910 | 2946193 | 2434885
8 | P.S. 138 - BRONX | SCA Capacity | ADDITION | Construction | Complete | 2022-01-19 | 2024-09-03 | 2024-09-01 | 65601865 | 65368873 | 46926835
8 | P.S. 138 - BRONX | SCA Capacity | ADDITION | CM,Art,F&E | Complete | 2022-01-19 | 2024-09-03 | 2024-09-01 | 9247840 | 8320544 | 5474140
8 | P.S. 138 - BRONX | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS | Scope | Complete | 2023-02-07 | 2023-06-07 | 2023-12-14 | 14596 | 62015 | 41450
8 | P.S. 138 - BRONX | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS | Design | In-Progress | 2023-12-19 | 2024-05-21 |  | 72981 | 120772 | 66359
8 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 2022-05-12 | 2022-09-27 | 2022-08-31 | 46285 | 42360 | 42360
8 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | Design | Complete | 2022-09-02 | 2023-02-08 | 2023-02-08 | 224497 | 186291 | 169881
8 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 2023-06-16 | 2025-06-14 |  | 4451993 | 4095072 | 2493824
8 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 2023-06-16 | 2025-06-14 |  | 375946 | 331054 | 324576
8 | P.S. 140 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-04-05 | 2023-07-06 | 2023-08-02 | 24894 | 61170 | 61170
8 | P.S. 140 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-08-07 | 2023-12-22 | 2024-04-30 | 124469 | 133611 | 122383
8 | P.S. 140 - BRONX | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-06-29 | 2023-10-31 | 2023-10-02 | 7313 | 14418 | 592
8 | P.S. 140 - BRONX | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-10-13 | 2024-02-20 | 2024-04-30 | 32908 | 32716 | 2368
8 | P.S. 140 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-08 | 2024-09-09 | 2024-05-17 | 5638 | 1955 | 1955
8 | P.S. 140 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-05-17 | 2024-11-14 |  | 25372 | 25372 | 7822
8 | P.S. 140 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2024-06-11 | 2024-10-15 | 2024-08-13 | 30000 | 34313 | 32546
8 | P.S. 146 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2018-11-19 | 2019-04-08 | 2019-03-06 | 170028 | 184128 | 126385
8 | P.S. 146 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | In-Progress | 2024-07-17 | 2024-12-18 |  | 744831 | 744831 | 5948
8 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2019-08-01 | 2019-12-18 | 2019-12-03 | 89740 | 113807 | 113807
8 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2020-01-22 | 2020-07-08 | 2022-01-12 | 448700 | 558155 | 527801
8 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2022-07-11 | 2024-07-09 |  | 10095750 | 9601325 | 7835375
8 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2022-07-11 | 2024-07-09 |  | 629386 | 1229588 | 1229059
8 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-21 | 2023-04-24 | 2023-01-26 | 5000 | 3925 | 3925
8 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-26 | 2023-07-24 | 2023-04-12 | 22500 | 15697 | 15697
8 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-06 | 2024-09-30 |  | 290000 | 262060 | 1810
8 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-06 | 2024-09-30 |  | 90116 | 68990 | 5515
8 | P.S. 152 - BRONX | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / CHILLER PLANT UPGRADE / FLOOD ELIMINATION | Scope | Complete | 2019-06-05 | 2019-10-21 | 2019-10-10 | 128000 | 189649 | 166630
8 | P.S. 152 - BRONX | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / CHILLER PLANT UPGRADE / FLOOD ELIMINATION | Design | Complete | 2019-11-20 | 2020-04-23 | 2020-06-15 | 603485 | 482898 | 437950
8 | P.S. 152 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-15 | 2024-09-16 | 2024-05-21 | 5079 | 592 | 592
8 | P.S. 152 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-05-21 | 2024-11-18 |  | 22857 | 22857 | 2368
8 | P.S. 182 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-29 | 2024-09-27 | 2024-06-05 | 4749 | 1804 | 1804
8 | P.S. 182 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-06-05 | 2024-12-03 |  | 21368 | 21368 | 7216
8 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | Scope | Complete | 2020-11-20 | 2021-02-16 | 2021-12-15 | 164800 | 99880 | 96998
8 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | Design | Complete | 2022-01-13 | 2022-06-20 | 2022-09-28 | 824000 | 748032 | 409377
8 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | Construction | In-Progress | 2024-03-06 | 2026-03-05 |  | 18540000 | 16800772 | 75805
8 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | CM,F&E | In-Progress | 2024-03-06 | 2026-03-05 |  | 1153600 | 168201 | 87094
8 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | Scope | Complete | 2021-11-10 | 2022-01-13 | 2022-01-12 | 10500 | 19205 | 19205
8 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | Design | Complete | 2022-01-31 | 2022-06-03 | 2022-05-10 | 52500 | 110563 | 36644
8 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | Construction | In-Progress | 2023-04-04 | 2024-04-02 |  | 1181250 | 1256275 | 1052032
8 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | CM,F&E | In-Progress | 2023-04-04 | 2024-04-02 |  | 73500 | 165531 | 157821
8 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | Scope | Complete | 2019-03-22 | 2021-11-01 | 2021-11-24 | 264990 | 382373 | 382373
8 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | Design | Complete | 2021-11-29 | 2022-04-28 | 2022-09-30 | 1324948 | 1581837 | 1255058
8 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 2023-07-07 | 2025-01-01 |  | 29811319 | 32382156 | 1311448
8 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | CM,F&E | In-Progress | 2023-07-07 | 2025-01-01 |  | 1855517 | 206407 | 206407
8 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2018-09-21 | 2018-12-24 | 2019-01-10 | 59010 | 87548 | 87548
8 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2019-01-16 | 2019-06-03 | 2019-05-16 | 236040 | 432892 | 422707
8 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2021-07-13 | 2023-01-03 |  | 4425750 | 1829974 | 2774789
8 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2021-07-13 | 2023-01-03 |  | 275380 | 191128 | 190227
8 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2021-09-15 | 2022-01-19 | 2021-09-30 | 4600 | 3095 | 3095
8 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-09-30 | 2022-03-31 | 2022-01-11 | 20700 | 12378 | 12378
8 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-07-25 | 2023-04-19 |  | 266800 | 237136 | 181490
8 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-07-25 | 2023-04-19 |  | 219927 | 208001 | 201746
9 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-14 | 2023-10-13 | 2023-10-17 | 8800 | 16275 | 16275
9 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-24 | 2024-03-25 | 2024-03-27 | 39600 | 51616 | 41175
9 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-16 | 2025-09-15 |  | 510400 | 530372 | 71786
9 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-16 | 2025-09-15 |  | 94600 | 71773 | 14902
9 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-25 | 2023-05-24 | 2023-02-24 | 4080 | 4526 | 4526
9 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-24 | 2023-08-21 | 2023-05-03 | 18360 | 18106 | 18106
9 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-12 | 2024-12-10 |  | 236640 | 213929 | 102696
9 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-12 | 2024-12-10 |  | 78489 | 60696 | 38664
9 | P.S. 4 - BRONX | SCA CIP | SWIMMING POOLS | Scope | Complete | 2023-11-22 | 2024-05-17 | 2024-07-22 | 89722 | 116490 | 5490
9 | P.S. 4 - BRONX | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | In-Progress | 2024-06-10 | 2024-10-25 |  | 270318 | 280537 | 37723
9 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | Scope | Complete | 2016-02-11 | 2021-09-17 | 2021-10-05 | 62480 | 72320 | 72320
9 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | Design | Complete | 2021-10-06 | 2022-03-03 | 2022-05-11 | 312400 | 422837 | 326544
9 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | Construction | In-Progress | 2022-08-08 | 2024-08-06 |  | 7029000 | 6632971 | 3479296
9 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | CM,F&E | In-Progress | 2022-08-08 | 2024-08-06 |  | 444685 | 292850 | 183744
9 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | Scope | Complete | 2021-02-24 | 2021-06-08 | 2022-01-18 | 144418 | 486036 | 463729
31 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | Scope | Complete | 2019-02-14 | 2019-07-01 | 2021-07-07 | 30869 | 173897 | 169991
9 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | Design | Complete | 2022-01-26 | 2022-06-27 | 2022-05-11 | 705001 | 610416 | 599177
9 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | Construction | Complete | 2022-07-18 | 2024-07-16 | 2024-07-22 | 14384433 | 13560587 | 12856267
9 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | CM,F&E | Complete | 2022-07-18 | 2024-07-16 | 2024-07-22 | 1168540 | 776803 | 770832
9 | P.S. 11 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-16 | 2023-10-16 | 2023-10-16 | 9700 | 12384 | 12384
9 | P.S. 11 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-24 | 2024-03-25 | 2024-04-05 | 43650 | 40969 | 39829
9 | I.S. 22 - BRONX | SCA CIP | ROOFS / GYMNASIUM FLOORING / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 2023-06-05 | 2023-12-04 | 2023-10-02 | 182777 | 203386 | 203386
9 | I.S. 22 - BRONX | SCA CIP | ROOFS / GYMNASIUM FLOORING / EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 2023-10-18 | 2024-06-11 | 2024-04-19 | 910109 | 352567 | 352567
9 | I.S. 22 - BRONX | SCA CIP RESOA | FY21 RESO A (MA) AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-02-01 | 2023-06-02 | 2023-10-13 | 90000 | 105109 | 101087
9 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2017-09-19 | 2021-11-15 | 2022-03-04 | 383131 | 385894 | 385894
9 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2022-03-04 | 2022-08-03 | 2022-05-16 | 1905372 | 1818432 | 1643053
9 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2022-09-05 | 2026-03-04 |  | 42534156 | 38503672 | 8045568
9 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2022-09-05 | 2026-03-04 |  | 2697337 | 958531 | 951477
9 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-03-13 | 2023-07-12 | 2023-03-21 | 3320 | 2744 | 2744
9 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-03-21 | 2023-09-14 | 2023-05-03 | 14940 | 10976 | 10976
9 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2023-12-12 | 2024-12-10 |  | 192560 | 174870 | 115054
9 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2023-12-12 | 2024-12-10 |  | 60520 | 46752 | 28824
9 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | Scope | Complete | 2022-03-14 | 2022-07-12 | 2022-07-20 | 29950 | 29110 | 29110
9 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | Design | Complete | 2022-08-04 | 2023-01-19 | 2023-05-11 | 149750 | 130820 | 103916
9 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | Construction | In-Progress | 2024-01-17 | 2025-07-09 |  | 3369375 | 3061869 | 563550
9 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | CM,F&E | In-Progress | 2024-01-17 | 2025-07-09 |  | 209650 | 89729 | 89512
9 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Scope | Complete | 2021-08-06 | 2022-06-03 | 2022-11-15 | 22639 | 38939 | 38939
9 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Design | Complete | 2022-11-25 | 2023-04-07 | 2023-04-17 | 112861 | 158408 | 121247
9 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Construction | In-Progress | 2023-08-24 | 2024-11-20 |  | 2510442 | 2412244 | 1626808
9 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-08-24 | 2024-11-20 |  | 160983 | 100669 | 76977
9 | P.S. 58 - BRONX | SCA CIP | SITE DRAINAGE | Scope | Complete | 2024-03-18 | 2024-03-18 | 2024-03-18 | 17000 | 6108 | 343
9 | P.S. 58 - BRONX | SCA CIP | SITE DRAINAGE | Design | Complete | 2024-03-18 | 2024-06-28 | 2024-06-26 | 76500 | 1371 | 1371
9 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | Scope | Complete | 2017-11-28 | 2018-12-11 | 2018-12-12 | 283697 | 209902 | 209853
9 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | Design | Complete | 2019-01-03 | 2019-06-20 | 2019-05-17 | 1120106 | 579719 | 516897
9 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | Construction | In-Progress | 2020-03-09 | 2023-03-08 |  | 19683701 | 19545874 | 17707821
9 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | CM,F&E | In-Progress | 2020-03-09 | 2023-03-08 |  | 1514872 | 1148266 | 1105745
9 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2021-03-11 | 2021-07-26 | 2021-08-23 | 208115 | 236644 | 236644
9 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 2021-09-29 | 2022-03-07 | 2022-03-02 | 1035400 | 814709 | 651446
9 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2023-10-13 | 2026-10-11 |  | 22848863 | 20770898 | 1456445
9 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-10-13 | 2026-10-11 |  | 1495617 | 61710 | 61156
9 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-10-20 | 2021-02-23 | 2020-10-23 | 5772 | 5570 | 5570
9 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-10-23 | 2021-04-22 | 2021-06-09 | 25974 | 22280 | 22280
9 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-11-30 | 2023-09-25 |  | 334776 | 295260 | 273780
9 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-11-30 | 2023-09-25 |  | 203376 | 184274 | 147975
9 | P.S. 63 - BRONX | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 2024-05-14 | 2024-10-16 |  | 49071 | 44414 | 26549
9 | P.S. 63 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 2024-03-18 | 2024-06-17 | 2024-07-12 | 265 | 265 | 265
9 | P.S. 63 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | In-Progress | 2024-07-12 | 2024-10-31 |  | 1061 | 1061 | 1061
9 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2020-05-18 | 2020-11-13 | 2020-11-03 | 205690 | 351001 | 324001
9 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2020-11-19 | 2021-06-15 | 2021-07-01 | 1028450 | 676450 | 674513
9 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2021-12-13 | 2023-09-03 |  | 23140125 | 21934136 | 16870374
9 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2021-12-13 | 2023-09-03 |  | 1439830 | 916237 | 832660
9 | THE WALTON AVENUE SCHOOL | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-05-24 | 2023-08-24 | 2023-11-16 | 20798 | 34525 | 28690
9 | THE WALTON AVENUE SCHOOL | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-11-27 | 2024-04-12 | 2024-05-17 | 103990 | 119636 | 113945
9 | THE WALTON AVENUE SCHOOL | SCA CIP | PATH OF TRAVEL- TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2024-03-15 | 2024-06-13 | 2024-05-08 | 4073 | 673 | 673
9 | THE WALTON AVENUE SCHOOL | SCA CIP | PATH OF TRAVEL- TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2024-05-13 | 2024-09-16 | 2024-05-17 | 16291 | 2690 | 2690
9 | P.S. 70 - BRONX | SCA CIP | STH SBHC | Scope | Complete | 2022-03-07 | 2022-07-05 | 2022-08-10 | 32500 | 25290 | 25290
9 | P.S. 70 - BRONX | SCA CIP | STH SBHC | Design | Complete | 2022-08-12 | 2023-01-26 | 2023-03-17 | 162500 | 115123 | 81721
9 | P.S. 70 - BRONX | SCA CIP | STH SBHC | Construction | In-Progress | 2023-11-06 | 2025-11-04 |  | 3656250 | 3333159 | 468209
9 | P.S. 70 - BRONX | SCA CIP | STH SBHC | CM,F&E | In-Progress | 2023-11-06 | 2025-11-04 |  | 227500 | 65156 | 65156
9 | P.S. 70 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Scope | Complete | 2022-09-30 | 2023-01-04 | 2022-12-30 | 36545 | 118527 | 111768
9 | P.S. 70 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Design | Complete | 2023-09-05 | 2024-04-02 | 2024-05-07 | 178968 | 373279 | 367856
9 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-07-06 | 2023-11-06 | 2023-10-25 | 9680 | 16580 | 16580
9 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-11-01 | 2024-04-01 | 2024-04-09 | 43560 | 97429 | 43208
9 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-20 | 2025-09-19 |  | 561440 | 558282 | 2823
9 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-20 | 2025-09-19 |  | 104060 | 117421 | 12124
9 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2021-03-15 | 2021-07-28 | 2021-11-24 | 157770 | 183993 | 183993
9 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2021-12-08 | 2022-05-26 | 2022-08-26 | 788850 | 466404 | 383894
9 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 2023-08-07 | 2026-02-01 |  | 17749125 | 16430557 | 5147444
9 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2023-08-07 | 2026-02-01 |  | 1105446 | 465093 | 457969
9 | P.S. 73 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-06-14 | 2023-09-14 | 2023-11-21 | 29151 | 46114 | 45764
9 | P.S. 73 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | In-Progress | 2024-01-10 | 2024-05-24 |  | 145755 | 145755 | 19501
9 | P.S. 73 - BRONX | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | Complete | 2023-10-02 | 2023-10-02 | 2023-10-02 | 45000 | 18027 | 0
9 | I.S. 303 - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 2023-05-18 | 2023-10-04 | 2023-10-03 | 31200 | 44007 | 31642
9 | I.S. 303 - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | In-Progress | 2024-05-15 | 2025-02-13 |  | 457600 | 236513 | 3358
9 | I.S. 303 - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2024-05-15 | 2025-02-13 |  | 31200 | 38970 | 10985
9 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2021-04-16 | 2021-09-16 | 2021-08-05 | 51235 | 85011 | 85011
9 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2021-08-09 | 2022-01-12 | 2022-01-13 | 252730 | 359260 | 340754
9 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-07-05 | 2024-07-03 |  | 5388433 | 5210480 | 5077934
9 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-07-05 | 2024-07-03 |  | 384483 | 788661 | 736729
9 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2019-08-06 | 2020-01-06 | 2019-09-03 | 2901 | 2074 | 2074
9 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2019-09-03 | 2020-02-06 | 2020-01-31 | 13056 | 8340 | 8340
9 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2020-10-05 | 2021-07-01 |  | 168282 | 225463 | 211956
9 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2020-10-05 | 2021-07-01 |  | 31190 | 41671 | 41671
9 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 2019-07-02 | 2019-11-01 | 2019-07-24 | 2537 | 1166 | 1166
9 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 2019-07-24 | 2019-12-26 | 2019-12-30 | 11418 | 4719 | 4719
9 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 2020-10-05 | 2021-07-01 |  | 147165 | 154131 | 145191
9 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 2020-10-05 | 2021-07-01 |  | 27276 | 34164 | 34164
9 | P.S. 199 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-11-05 | 2022-03-28 | 2023-01-30 | 133261 | 144023 | 142749
9 | P.S. 199 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | In-Progress | 2023-02-06 | 2023-07-25 |  | 621884 | 621884 | 204677
9 | P.S. 199 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-07-12 | 2022-11-28 | 2023-09-20 | 227002 | 351262 | 221575
9 | P.S. 199 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | In-Progress | 2023-09-26 | 2024-03-01 |  | 1135010 | 1135010 | 327022
9 | P.S. 109 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS UPGRADE / WINDOWS / ROOFS / PARAPETS | Scope | Complete | 2023-10-05 | 2024-03-05 | 2024-03-13 | 457765 | 439412 | 330692
9 | P.S. 109 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS UPGRADE / WINDOWS / ROOFS / PARAPETS | Design | In-Progress | 2024-08-12 | 2025-03-11 |  | 2204122 | 2204122 | 24194
9 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 2019-06-03 | 2019-10-02 | 2019-06-24 | 12141 | 4568 | 4568
9 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 2019-06-24 | 2019-11-25 | 2019-12-03 | 54636 | 18313 | 18313
9 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 2020-10-05 | 2021-07-01 |  | 704194 | 562576 | 403252
9 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 2020-10-05 | 2021-07-01 |  | 130519 | 79553 | 79553
9 | P.S. 110 - BRONX | SCA CIP | REPAIR RETAINING WALLS | Scope | Complete | 2018-08-02 | 2018-12-19 | 2018-12-03 | 15503 | 148516 | 141215
9 | P.S. 110 - BRONX | SCA CIP | REPAIR RETAINING WALLS | Design | Complete | 2022-05-03 | 2023-05-12 | 2023-05-10 | 77514 | 76356 | 69847
9 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2019-05-28 | 2022-11-16 | 2023-02-08 | 150499 | 178247 | 175590
9 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-02-09 | 2023-07-13 | 2023-05-11 | 748896 | 684258 | 510906
9 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-02-05 | 2026-08-02 |  | 16538847 | 15222389 | 654366
9 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-02-05 | 2026-08-02 |  | 1080486 | 122814 | 120612
9 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-06 | 2023-11-03 | 2023-07-18 | 5400 | 1081 | 1081
9 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-18 | 2024-01-16 | 2023-10-11 | 24300 | 4324 | 4324
9 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-02 | 2024-11-27 |  | 313200 | 281947 | 2747
9 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-02 | 2024-11-27 |  | 124179 | 98818 | 43404
9 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2018-09-28 | 2019-03-06 | 2018-11-15 | 99750 | 93285 | 93285
9 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2018-11-30 | 2019-05-03 | 2019-04-12 | 399000 | 411435 | 399792
9 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2019-07-22 | 2021-07-20 |  | 7481250 | 7471337 | 6176779
9 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2019-07-22 | 2021-07-20 |  | 465500 | 1343596 | 1273119
9 | P.S. 114 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2020-05-26 | 2020-11-20 | 2020-09-25 | 89701 | 236653 | 227811
9 | P.S. 114 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2020-10-08 | 2021-12-15 | 2021-07-01 | 444984 | 510819 | 508320
9 | P.S. 114 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / WINDOWS | Construction | Complete | 2022-01-24 | 2023-10-15 | 2024-05-15 | 9708168 | 9005894 | 8432953
9 | P.S. 114 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / WINDOWS | CM,F&E | Complete | 2022-01-24 | 2023-10-15 | 2024-05-15 | 654256 | 851417 | 831109
9 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-06 | 2023-11-03 | 2023-07-18 | 4136 | 1061 | 1061
9 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-18 | 2024-01-16 | 2023-10-11 | 18612 | 4243 | 4243
9 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-02 | 2024-11-27 |  | 239888 | 218456 | 3088
9 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-02 | 2024-11-27 |  | 77640 | 58191 | 35856
9 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2020-08-17 | 2021-01-21 | 2021-01-04 | 74140 | 85591 | 85591
9 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2021-01-05 | 2021-07-30 | 2021-07-28 | 370700 | 353261 | 332901
9 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-06-15 | 2024-06-13 |  | 8340750 | 7499783 | 3436619
9 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-06-15 | 2024-06-13 |  | 518980 | 396680 | 373891
9 | P.S. 126 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2021-11-10 | 2022-03-31 | 2023-01-19 | 118408 | 201403 | 186209
9 | P.S. 126 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2023-01-20 | 2023-07-10 | 2024-09-12 | 592044 | 395447 | 370144
9 | P.S. 126 - BRONX | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 2023-12-12 | 2024-04-29 | 2024-09-25 | 27014 | 0 | 0
9 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-15 | 2023-10-16 | 2023-09-22 | 9899 | 16018 | 12505
9 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-04 | 2024-03-05 | 2024-04-04 | 44546 | 62362 | 47196
9 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-25 | 2025-09-24 |  | 574142 | 551412 | 35912
9 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-25 | 2025-09-24 |  | 106414 | 88839 | 21379
9 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2018-11-21 | 2019-04-10 | 2020-02-11 | 15826 | 64028 | 46404
9 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2020-02-11 | 2020-07-13 | 2021-05-14 | 71215 | 120171 | 89178
9 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 2022-01-25 | 2023-01-24 |  | 917879 | 824587 | 214827
9 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 2022-01-25 | 2023-01-24 |  | 170124 | 121764 | 102240
9 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | ROOFS | Scope | In-Progress | 2024-06-10 | 2024-10-25 |  | 81830 | 81830 | 22257
9 | I.S. 219 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-08-17 | 2022-01-21 | 2022-02-10 | 67074 | 73513 | 71958
9 | I.S. 219 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2022-09-13 | 2023-09-12 |  | 983748 | 966225 | 743805
9 | I.S. 219 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2022-09-13 | 2023-09-12 |  | 67074 | 98036 | 58344
9 | I.S. 215 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-08-07 | 2024-12-24 |  | 143830 | 164025 | 9307
9 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-12-03 | 2022-01-18 | 2022-01-13 | 111956 | 159049 | 142435
9 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2022-07-06 | 2023-07-05 |  | 1642030 | 1674385 | 1540975
9 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2022-07-06 | 2023-07-05 |  | 111956 | 177237 | 174679
9 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2019-02-01 | 2019-06-18 | 2022-01-21 | 60992 | 67606 | 67606
9 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Design | Complete | 2022-02-02 | 2022-07-05 | 2022-05-11 | 299610 | 282278 | 274885
9 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 2022-09-21 | 2024-03-13 |  | 6278234 | 5759606 | 5463751
9 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2022-09-21 | 2024-03-13 |  | 467092 | 181570 | 180513
9 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-09 | 2023-06-09 | 2023-03-15 | 4440 | 5165 | 5165
9 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-15 | 2023-09-08 | 2023-05-03 | 19980 | 20659 | 20659
9 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-12 | 2024-12-10 |  | 257520 | 229765 | 2297
9 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-12 | 2024-12-10 |  | 83489 | 61444 | 37468
9 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | SCA CIP | PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2022-07-08 | 2022-11-23 | 2023-07-25 | 32629 | 70153 | 39666
9 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | SCA CIP | PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2023-09-07 | 2024-02-12 | 2024-04-10 | 146829 | 90327 | 81818
9 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | Scope | Complete | 2014-09-18 | 2015-02-06 | 2015-02-06 | 586154 | 423577 | 407985
9 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | Design | Complete | 2016-07-29 | 2017-01-03 | 2017-05-15 | 2327215 | 1999734 | 1700302
9 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | Construction | In-Progress | 2017-07-24 | 2021-12-09 |  | 42073721 | 43285543 | 38685933
9 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | CM,F&E | In-Progress | 2017-07-24 | 2021-12-09 |  | 2961572 | 3244379 | 3143920
9 | MORRIS COLLAB HS TECH & HUMAN - X | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADES | Scope | Complete | 2021-11-24 | 2023-08-15 | 2023-09-08 | 20763 | 41886 | 39819
9 | MORRIS COLLAB HS TECH & HUMAN - X | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADES | Design | Complete | 2023-09-11 | 2024-01-11 | 2023-12-15 | 102871 | 114973 | 98370
9 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2021-10-29 | 2022-09-06 | 2022-10-11 | 35710 | 198939 | 198939
9 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2022-10-12 | 2023-02-13 | 2023-12-22 | 177477 | 383958 | 341852
9 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2024-08-22 | 2026-08-11 |  | 3900656 | 3575696 | 65158
9 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2024-08-22 | 2026-08-11 |  | 257995 | 117396 | 75290
9 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-01-23 | 2023-05-23 | 2023-03-28 | 11680 | 16689 | 16689
9 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-03-31 | 2023-09-29 | 2023-08-02 | 52560 | 51366 | 36984
9 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-03-29 | 2025-03-28 |  | 677440 | 608512 | 5609
9 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-03-29 | 2025-03-28 |  | 125560 | 86900 | 12765
9 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-06-30 | 2022-11-16 | 2024-04-03 | 133228 | 189786 | 84577
9 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | In-Progress | 2024-08-02 | 2025-01-07 |  | 653250 | 653250 | 14788
9 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 2023-07-05 | 2023-11-20 | 2023-11-21 | 30000 | 34155 | 659
9 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | Scope | Complete | 2019-08-20 | 2020-01-14 | 2020-01-15 | 1150660 | 840988 | 840574
9 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | Design | Complete | 2020-01-16 | 2020-08-31 | 2021-05-04 | 5177970 | 3131749 | 2519526
9 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | Construction | Complete | 2021-12-20 | 2024-09-03 | 2024-07-03 | 65299955 | 61772471 | 59258093
9 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 2021-12-20 | 2024-09-03 | 2024-07-03 | 9205280 | 6659106 | 5026105
9 | 3K CENTER @ 1450 PLIMPTON AVENUE - BRONX | 3K | LEASE | Scope | Complete | 2018-11-15 | 2018-12-03 | 2018-12-03 | 250680 | 214584 | 214584
9 | 3K CENTER @ 1450 PLIMPTON AVENUE - BRONX | 3K | LEASE | Design | Complete | 2018-12-04 | 2019-03-15 | 2019-03-21 | 1128060 | 1142285 | 962882
9 | 3K CENTER @ 1450 PLIMPTON AVENUE - BRONX | 3K | LEASE | Construction | Complete | 2023-02-20 | 2023-09-03 | 2024-08-14 | 14226090 | 14046262 | 13493977
9 | 3K CENTER @ 1450 PLIMPTON AVENUE - BRONX | 3K | LEASE | CM,F&E | Complete | 2023-02-20 | 2023-09-03 | 2024-08-14 | 2005440 | 664302 | 1241621
9 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | Scope | Complete | 2019-06-13 | 2019-11-29 | 2019-12-05 | 1595980 | 1094470 | 1091253
9 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | Design | Complete | 2019-12-06 | 2020-06-15 | 2021-10-28 | 7181910 | 5404130 | 3817046
9 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | Construction | In-Progress | 2022-05-18 | 2024-09-03 |  | 90571865 | 87112858 | 70923970
9 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | CM,Art,F&E | In-Progress | 2022-05-18 | 2024-09-03 |  | 12767840 | 8631632 | 6210971
9 | P.S. 53 - BRONX | SCA CIP | PS53X @ X851/X874 OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 2024-07-24 | 2024-10-23 |  | 57006 | 57006 | 11347
9 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 2020-02-24 | 2020-07-08 | 2021-11-29 | 90790 | 81337 | 79684
9 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | Design | Complete | 2021-12-08 | 2022-05-11 | 2022-05-10 | 453950 | 369014 | 334825
9 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | Construction | In-Progress | 2022-09-01 | 2025-08-15 |  | 10213875 | 9267117 | 6327494
9 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | CM,F&E | In-Progress | 2022-09-01 | 2025-08-15 |  | 636178 | 188603 | 163922
9 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2022-03-22 | 2022-07-20 | 2022-04-12 | 3732 | 3456 | 3456
9 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2022-04-12 | 2022-10-05 | 2022-07-27 | 16793 | 13824 | 13824
9 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2023-04-14 | 2024-02-07 |  | 216439 | 191206 | 110987
9 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2023-04-14 | 2024-02-07 |  | 134916 | 124849 | 104538
9 | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | Scope | Complete | 2021-03-10 | 2022-01-13 | 2022-04-11 | 23164 | 87958 | 57331
9 | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | Design | Complete | 2022-04-11 | 2022-08-10 | 2022-05-11 | 114030 | 114612 | 24207
9 | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | Construction | In-Progress | 2024-03-05 | 2025-09-02 |  | 2410555 | 2327651 | 221797
9 | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | CM,F&E | In-Progress | 2024-03-05 | 2025-09-02 |  | 175599 | 255150 | 136902
10 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-10-06 | 2023-02-09 | 2022-10-18 | 4464 | 8700 | 8700
10 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-10-18 | 2023-04-17 | 2023-02-15 | 20088 | 34800 | 34800
10 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-23 | 2024-06-17 |  | 258910 | 225430 | 166694
10 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-23 | 2024-06-17 |  | 177762 | 158411 | 100970
10 | P.S. 8 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-08-07 | 2024-12-09 | 2024-08-15 | 4041 | 514 | 514
10 | P.S. 8 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-08-15 | 2025-02-13 |  | 18183 | 18183 | 2058
10 | P.S. 8 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 2024-03-04 | 2024-08-02 | 2024-07-16 | 33000 | 37282 | 7213
10 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | Scope | Complete | 2018-01-12 | 2018-05-30 | 2018-06-05 | 233995 | 175679 | 175679
10 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | Design | Complete | 2018-11-28 | 2019-05-01 | 2019-04-30 | 935980 | 777989 | 720706
10 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 2019-08-13 | 2021-08-01 |  | 17549627 | 16263798 | 13910570
10 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 2019-08-13 | 2021-08-01 |  | 1091977 | 728665 | 726094
10 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | Scope | Complete | 2022-04-12 | 2022-08-10 | 2022-09-12 | 62504 | 66335 | 2315
10 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | Design | Complete | 2022-09-26 | 2023-03-13 | 2023-03-31 | 308752 | 599947 | 277314
10 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | Construction | In-Progress | 2023-09-15 | 2025-09-13 |  | 6620774 | 6245447 | 1602800
10 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | CM,F&E | In-Progress | 2023-09-15 | 2025-09-13 |  | 465813 | 339037 | 83208
10 | P.S. 9 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 2024-05-31 | 2024-08-30 |  | 28215 | 42934 | 3727
10 | P.S. 9 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 2024-03-25 | 2024-08-23 | 2024-08-19 | 60000 | 49909 | 3606
10 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2021-03-11 | 2021-07-26 | 2021-10-04 | 48803 | 53202 | 51935
10 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2021-11-10 | 2022-04-15 | 2022-05-03 | 237462 | 223739 | 220329
10 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2022-12-15 | 2024-06-06 |  | 4776062 | 4323378 | 4113218
10 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-12-15 | 2024-06-06 |  | 390768 | 851562 | 842238
10 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-10-06 | 2023-02-09 | 2022-10-18 | 5456 | 9058 | 9058
10 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-10-18 | 2023-04-17 | 2023-02-15 | 24552 | 36231 | 36231
10 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-23 | 2024-06-17 |  | 316445 | 275525 | 201432
10 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-23 | 2024-06-17 |  | 146983 | 127601 | 29843
10 | P.S. 15 - BRONX | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 2023-11-20 | 2024-04-08 | 2024-03-18 | 58500 | 39441 | 6869
10 | P.S. 20 - BRONX | SCA CIP | HVAC AND BMS UPGRADE / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2022-05-26 | 2022-10-27 | 2023-01-03 | 310975 | 154253 | 154210
10 | P.S. 20 - BRONX | SCA CIP | HVAC AND BMS UPGRADE / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2023-01-13 | 2023-06-15 | 2023-05-12 | 1554876 | 920945 | 795336
10 | P.S. 20 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2021-11-30 | 2022-04-18 | 2022-05-12 | 90000 | 85736 | 79051
10 | X168 SPED - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION / FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2021-12-06 | 2022-06-02 | 2022-02-23 | 37500 | 40131 | 22131
10 | X168 SPED - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION / FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-11-30 | 2023-09-25 |  | 550000 | 445318 | 112693
10 | X168 SPED - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION / FY24 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-11-30 | 2023-09-25 |  | 141926 | 158470 | 138045
10 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-05-25 | 2023-09-26 | 2023-06-06 | 3690 | 2125 | 2125
10 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-06 | 2023-12-04 | 2023-10-03 | 16605 | 8500 | 8500
10 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-12 | 2024-12-07 |  | 214020 | 186345 | 498
10 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-12 | 2024-12-07 |  | 39668 | 31739 | 14696
10 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | Scope | Complete | 2021-04-19 | 2021-09-01 | 2021-11-24 | 43398 | 30858 | 30858
10 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | Design | Complete | 2021-11-29 | 2022-05-02 | 2022-12-27 | 216989 | 225406 | 164286
10 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | Construction | In-Progress | 2023-09-15 | 2025-09-13 |  | 4882259 | 4442414 | 1076672
10 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | CM,F&E | In-Progress | 2023-09-15 | 2025-09-13 |  | 303785 | 387565 | 362516
10 | I.S. 390 - BRONX | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2023-03-07 | 2023-06-05 | 2023-08-09 | 29787 | 45260 | 45260
10 | I.S. 390 - BRONX | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | In-Progress | 2023-09-08 | 2024-03-15 |  | 148934 | 148934 | 79093
10 | I.S. 390 - BRONX | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Design | In-Progress | 2024-03-07 | 2024-08-07 |  | 119124 | 206041 | 105950
10 | P.S. 32 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT: | Scope | Complete | 2023-09-06 | 2023-12-07 | 2023-11-27 | 39758 | 77317 | 942
10 | P.S. 32 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT: | Design | In-Progress | 2024-06-04 | 2024-10-21 |  | 185539 | 185539 | 3769
10 | P.S. 32 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 2023-12-20 | 2024-03-22 |  | 647 | 647 | 0
10 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-09-28 | 2023-02-01 | 2022-10-03 | 5181 | 3391 | 3391
10 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-10-03 | 2023-04-03 | 2023-01-11 | 23314 | 13564 | 13564
10 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-06-03 |  | 300491 | 276019 | 238398
10 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-06-03 |  | 192788 | 164247 | 132439
10 | P.S. 37 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2022-04-05 | 2022-09-28 | 2022-07-19 | 24000 | 17454 | 17454
10 | P.S. 37 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2023-06-14 | 2024-04-08 |  | 352000 | 238328 | 192409
10 | P.S. 37 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2023-06-14 | 2024-04-08 |  | 144549 | 155560 | 94835
10 | P.S. 37 - BRONX | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 2022-06-07 |  |  | 100000 | 100000 | 0
10 | I.S. 45 - BRONX | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-05-17 | 2022-09-30 | 2023-01-27 | 363000 | 278276 | 278276
10 | I.S. 45 - BRONX | SCA Furniture & Equipment | FY22 RESO A MOBILE STEM LAB | F&E | Complete | 2024-07-15 |  | 2024-09-16 | 50000 | 50000 | 50000
10 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Scope | Complete | 2014-08-04 | 2014-12-19 | 2014-12-19 | 112122 | 240930 | 240930
10 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Design | Complete | 2015-07-13 | 2015-12-14 | 2016-06-28 | 558225 | 645125 | 591822
10 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Construction | In-Progress | 2022-06-13 | 2024-06-11 |  | 12354085 | 13387344 | 11913965
10 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | CM,F&E | In-Progress | 2022-06-13 | 2024-06-11 |  | 802709 | 965059 | 940622
10 | P.S. 54 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2022-07-14 | 2022-11-30 | 2023-07-25 | 37560 | 52316 | 50554
10 | P.S. 54 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2023-08-23 | 2024-01-29 | 2024-03-21 | 187049 | 194311 | 186977
10 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-08-01 | 2024-12-18 |  | 18000 | 67102 | 4698
10 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-06 | 2023-12-04 | 2023-10-03 | 24000 | 3772 | 3772
10 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-12 | 2024-12-07 |  | 352000 | 189375 | 498
10 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-12 | 2024-12-07 |  | 24000 | 29355 | 12034
10 | P.S. 54 - BRONX | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 2023-03-31 |  |  | 100000 | 100000 | 15744
10 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | Scope | Complete | 2021-04-30 | 2021-08-30 | 2021-07-28 | 13940 | 44784 | 44784
10 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | Design | Complete | 2021-08-05 | 2022-02-03 | 2021-11-17 | 62730 | 179139 | 179139
10 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | Construction | In-Progress | 2023-04-27 | 2024-10-17 |  | 808520 | 754850 | 268685
10 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | CM,F&E | In-Progress | 2023-04-27 | 2024-10-17 |  | 149855 | 103314 | 80361
10 | I.S. 447 - BRONX | SCA CIP RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2019-09-05 | 2020-03-05 | 2020-03-10 | 28617 | 25075 | 19131
10 | I.S. 447 - BRONX | SCA CIP RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2021-08-05 | 2022-05-01 |  | 419720 | 347301 | 198085
10 | I.S. 447 - BRONX | SCA CIP RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2021-08-05 | 2022-05-01 |  | 175088 | 175477 | 163300
10 | SCHOOL FOR ENVIR CITIZEN - BRONX | SCA CIP RESOA | FY21 RESO A SUPPLEMENTAL COOLING / FY21 RESO A ROOM CONVERSION | Design | Complete | 2022-01-20 | 2022-06-20 | 2022-07-22 | 82267 | 92328 | 87759
10 | SCHOOL FOR ENVIR CITIZEN - BRONX | SCA CIP RESOA | FY21 RESO A SUPPLEMENTAL COOLING / FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 2023-10-25 | 2024-10-23 |  | 1206575 | 1123828 | 21111
10 | SCHOOL FOR ENVIR CITIZEN - BRONX | SCA CIP RESOA | FY21 RESO A SUPPLEMENTAL COOLING / FY21 RESO A ROOM CONVERSION | CM,F&E | In-Progress | 2023-10-25 | 2024-10-23 |  | 82267 | 123803 | 41182
10 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-06-28 | 2022-11-14 | 2023-02-02 | 88790 | 175531 | 174375
10 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-02-13 | 2023-07-17 | 2023-05-10 | 443950 | 489367 | 404423
10 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2023-08-15 | 2025-10-14 |  | 9988876 | 9067854 | 4118332
10 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-08-15 | 2025-10-14 |  | 623060 | 125362 | 118236
10 | I.S. 80 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2024-06-28 | 2024-10-31 | 2024-09-06 | 56339 | 72167 | 46597
10 | P.S. 81 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2020-02-05 | 2020-07-30 | 2020-05-14 | 27818 | 38788 | 38788
10 | P.S. 81 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2021-06-09 | 2022-04-04 |  | 407999 | 345556 | 329511
10 | P.S. 81 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2021-06-09 | 2022-04-04 |  | 135535 | 178036 | 173644
10 | P.S. 85 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-03-02 | 2023-05-31 | 2023-08-18 | 51736 | 85619 | 85619
10 | P.S. 85 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-08-18 | 2024-01-08 | 2024-05-14 | 258680 | 177415 | 150076
10 | P.S. 85 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDELOPMENT | Scope | Complete | 2023-08-04 | 2023-12-06 | 2023-09-01 | 2915 | 5866 | 5866
10 | P.S. 85 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDELOPMENT | Design | Complete | 2023-09-06 | 2024-01-05 | 2024-05-14 | 13119 | 17666 | 17666
10 | P.S. 85 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-06-28 | 2024-10-29 | 2024-07-08 | 3412 | 1029 | 1029
10 | P.S. 85 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-08 | 2025-01-03 |  | 15352 | 15352 | 4116
10 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | Complete | 2024-05-01 | 2024-09-17 | 2024-09-24 | 23061 | 35670 | 5085
10 | P.S. 85 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2024-03-12 | 2024-06-11 | 2024-06-20 | 5540 | 5540 | 74
10 | P.S. 85 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2024-06-25 | 2024-10-28 | 2024-09-24 | 10473 | 10473 | 296
10 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2024-06-25 | 2024-10-28 | 2024-09-17 | 60000 | 64133 | 4126
10 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | Scope | Complete | 2022-03-17 | 2022-08-01 | 2023-01-13 | 108367 | 167122 | 162169
10 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | Design | Complete | 2023-01-18 | 2023-06-20 | 2023-05-09 | 534877 | 452586 | 381514
10 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | Construction | In-Progress | 2023-08-21 | 2025-08-19 |  | 11432973 | 10617323 | 1829699
10 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | CM,F&E | In-Progress | 2023-08-21 | 2025-08-19 |  | 810742 | 273738 | 250222
10 | P.S. 86 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2024-01-08 | 2024-04-08 | 2024-09-26 | 28422 | 41564 | 8805
10 | P.S. 86 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-03 | 2024-11-01 | 2024-07-09 | 3526 | 1115 | 1115
10 | P.S. 86 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-09 | 2025-01-06 |  | 15865 | 15865 | 4459
10 | P.S. 86 - BRONX | SCA CIP | PATH OF TRAVEL OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 2024-04-01 | 2024-07-01 |  | 647 | 690 | 690
10 | P.S. 91 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2023-05-18 | 2023-10-04 | 2023-11-01 | 325236 | 248858 | 247293
10 | P.S. 91 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-11-08 | 2024-04-12 | 2024-09-18 | 1517765 | 670278 | 342768
10 | P.S. 91 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2023-08-02 | 2023-12-19 |  | 422700 | 338104 | 81227
10 | P.S. 91 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2023-12-05 | 2024-03-08 | 2024-04-09 | 889 | 889 | 889
10 | P.S. 91 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-04-16 | 2024-08-19 |  | 3555 | 3555 | 3555
10 | P.S. 94 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-17 | 2024-11-15 | 2024-07-23 | 3536 | 626 | 626
10 | P.S. 94 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-23 | 2025-01-21 |  | 15912 | 15912 | 2506
10 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | Scope | Complete | 2021-07-28 | 2023-08-25 | 2023-08-02 | 78240 | 79916 | 79916
10 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | Design | Complete | 2023-08-08 | 2023-12-26 | 2024-01-31 | 391201 | 336675 | 244504
31 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | Design | Complete | 2021-08-05 | 2022-01-10 | 2022-05-09 | 154346 | 178140 | 159024
10 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | Construction | In-Progress | 2024-09-20 | 2026-09-19 |  | 8802000 | 7966622 | 75911
10 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | CM,F&E | In-Progress | 2024-09-20 | 2026-09-19 |  | 547679 | 101893 | 41807
10 | I.S. 118 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-08-04 | 2023-11-03 | 2023-10-23 | 27634 | 48234 | 48234
10 | I.S. 118 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-11-01 | 2024-03-21 | 2024-03-26 | 138170 | 109769 | 96857
10 | I.S. 118 - BRONX | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Design | Complete | 2021-12-09 | 2022-05-11 | 2022-07-21 | 122580 | 77550 | 75482
10 | I.S. 118 - BRONX | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 2023-04-20 | 2024-02-13 |  | 1797840 | 724556 | 513035
10 | I.S. 118 - BRONX | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | CM,F&E | In-Progress | 2023-04-20 | 2024-02-13 |  | 140624 | 84439 | 56061
10 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2019-03-14 | 2019-06-12 | 2020-03-10 | 22890 | 114350 | 97173
10 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2020-03-11 | 2020-09-10 | 2020-06-30 | 114450 | 180609 | 154539
10 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 2023-10-20 | 2025-10-18 |  | 2575125 | 2507766 | 414643
10 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2023-10-20 | 2025-10-18 |  | 160230 | 55636 | 54650
10 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Design | Complete | 2023-07-05 | 2023-12-06 | 2024-04-15 | 154815 | 87611 | 72999
10 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-06-26 | 2023-11-09 | 2024-05-15 | 380596 | 272198 | 216286
10 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2023-02-27 | 2023-05-26 | 2023-11-20 | 2220 | 2220 | 2220
10 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-11-30 | 2024-04-01 | 2024-05-15 | 8881 | 8881 | 8881
10 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 2023-08-28 | 2023-11-30 | 2023-10-13 | 8070 | 8070 | 0
10 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 2023-10-20 | 2024-03-05 | 2024-04-15 | 585 | 585 | 0
10 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-31 | 2024-01-29 | 2023-10-18 | 24000 | 9267 | 9267
10 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-03-15 | 2025-01-08 |  | 352000 | 223276 | 2776
10 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-03-15 | 2025-01-08 |  | 45913 | 43866 | 24366
10 | I.S. 244 - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2022-12-16 | 2023-04-21 | 2023-05-12 | 98731 | 57501 | 53545
10 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-09-19 | 2023-01-23 | 2022-09-27 | 2847 | 3373 | 3373
10 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-09-27 | 2023-07-20 | 2023-01-11 | 12812 | 13491 | 13491
10 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-06-03 |  | 165134 | 161195 | 134857
10 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-06-03 |  | 129628 | 129545 | 98311
10 | I.S. 206B - BRONX | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2022-02-15 | 2022-05-13 | 2022-08-16 | 66110 | 70319 | 70319
10 | I.S. 206B - BRONX | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | Complete | 2023-04-14 | 2024-04-12 | 2024-04-11 | 969601 | 706052 | 577122
10 | I.S. 206B - BRONX | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | Complete | 2023-04-14 | 2024-04-12 | 2024-04-11 | 269594 | 304822 | 147279
10 | P.S. 209 - BRONX | SCA CIP | PLAYGROUND SAFETY SURFACE | Scope | Complete | 2023-04-13 | 2023-07-14 | 2023-04-13 | 3336 | 5765 | 0
10 | P.S. 209 - BRONX | SCA CIP | PLAYGROUND SAFETY SURFACE | Design | Complete | 2023-04-13 | 2023-08-29 | 2023-05-24 | 15010 | 0 | 0
10 | P.S. 279 - BRONX | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 2021-12-06 | 2022-04-08 | 2022-09-21 | 72203 | 236793 | 233955
10 | P.S. 279 - BRONX | SCA CIP | PLAYGROUND UPGRADE | Design | In-Progress | 2023-08-14 | 2024-01-02 |  | 361013 | 361013 | 129480
10 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2018-10-17 | 2019-03-07 | 2019-09-03 | 172980 | 232592 | 232592
10 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2019-09-04 | 2020-02-07 | 2021-05-14 | 864901 | 944641 | 912029
10 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2021-07-19 | 2023-10-06 |  | 19460250 | 18812778 | 17374108
10 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-07-19 | 2023-10-06 |  | 1210860 | 716565 | 711704
10 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-09-20 | 2023-01-24 | 2022-09-29 | 6272 | 3036 | 3036
10 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-09-29 | 2023-03-30 | 2023-01-11 | 28224 | 12143 | 12143
10 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-06-03 |  | 363775 | 335598 | 295798
10 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-06-03 |  | 260621 | 222011 | 187671
10 | P.S. 306 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | Complete | 2024-02-29 | 2024-07-16 | 2024-05-01 | 30000 | 32039 | 31337
10 | M.S./H.S. 368 - BRONX | SCA CIP | ASPHALT PAVEMENT AT TIBBETT AVE | Scope | Complete | 2023-03-14 | 2023-06-12 | 2024-02-05 | 108500 | 306093 | 306093
10 | M.S./H.S. 368 - BRONX | SCA CIP | ASPHALT PAVEMENT AT TIBBETT AVE | Design | Complete | 2024-02-20 | 2024-07-05 | 2024-05-16 | 542500 | 180886 | 20292
10 | M.S./H.S. 368 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2024-06-14 | 2024-10-31 | 2024-09-16 | 130463 | 57698 | 37263
10 | M.S./H.S. 368 - BRONX | SCA CIP RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | Scope | Complete | 2022-04-28 | 2022-07-29 | 2022-07-20 | 83824 | 83824 | 83824
10 | M.S./H.S. 368 - BRONX | SCA CIP RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | Design | In-Progress | 2022-08-09 | 2023-01-12 |  | 86105 | 86105 | 47635
10 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | Scope | Complete | 2019-06-18 | 2019-12-16 | 2019-11-20 | 403971 | 363933 | 360892
10 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | Design | Complete | 2019-12-18 | 2020-06-15 | 2020-05-15 | 2007396 | 744547 | 740398
10 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | Construction | In-Progress | 2021-05-17 | 2024-05-15 |  | 44088491 | 41660369 | 39013312
10 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2021-05-17 | 2024-05-15 |  | 2954624 | 1023596 | 1011851
10 | M.S./H.S. 342 - BRONX | SCA CIP | FIRE SPRINKLER SYSTEM | Scope | Complete | 2023-08-10 | 2023-11-09 | 2023-11-08 | 19190 | 49366 | 49366
10 | M.S./H.S. 342 - BRONX | SCA CIP | FIRE SPRINKLER SYSTEM | Design | Complete | 2023-11-20 | 2024-05-23 | 2024-08-05 | 76759 | 70547 | 63080
10 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | Scope | Complete | 2020-02-07 | 2023-07-21 | 2023-08-04 | 223330 | 134168 | 134168
10 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | Design | Complete | 2023-08-30 | 2024-01-05 | 2024-04-11 | 1116650 | 542016 | 364209
10 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | Construction | In-Progress | 2024-09-16 | 2027-09-15 |  | 25124625 | 22563117 | 85524
10 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | CM,F&E | In-Progress | 2024-09-16 | 2027-09-15 |  | 1563310 | 183641 | 57049
10 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | Scope | Complete | 2019-09-24 | 2020-03-05 | 2020-03-12 | 1153240 | 899738 | 898881
10 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | Design | Complete | 2020-03-13 | 2020-09-23 | 2021-05-14 | 5189580 | 3233984 | 2894021
10 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2021-12-20 | 2024-09-03 |  | 65446370 | 62764232 | 52006177
10 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | CM,Art,F&E | In-Progress | 2021-12-20 | 2024-09-03 |  | 9225920 | 6616953 | 4985924
10 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | Scope | Complete | 2021-04-14 | 2021-08-13 | 2022-01-21 | 36500 | 111873 | 107021
10 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | Design | Complete | 2022-01-21 | 2022-06-13 | 2022-05-10 | 182499 | 272012 | 203468
10 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | Construction | Complete | 2022-08-15 | 2024-02-05 | 2024-07-24 | 4106226 | 3774362 | 3665006
10 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | CM,F&E | Complete | 2022-08-15 | 2024-02-05 | 2024-07-24 | 255499 | 327202 | 321131
10 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA Capacity | NEW SCHOOL | Scope | Complete | 2022-07-19 | 2022-12-30 | 2023-01-20 | 1788220 | 903503 | 876551
10 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA Capacity | NEW SCHOOL | Design | Complete | 2023-01-23 | 2023-08-18 | 2024-05-14 | 8046990 | 1702364 | 1466967
10 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | Scope | Complete | 2023-01-26 | 2023-01-26 | 2023-01-26 | 42240 | 3480 | 3480
10 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | Design | Complete | 2023-01-26 | 2023-05-25 | 2023-12-08 | 211200 | 239940 | 157605
10 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | Construction | In-Progress | 2024-07-22 | 2025-04-17 |  | 4752000 | 4330151 | 72674
10 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2024-07-22 | 2025-04-17 |  | 295680 | 62444 | 62444
10 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-08-16 | 2024-01-04 | 2024-04-09 | 225570 | 106066 | 103164
10 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2023-04-06 | 2023-07-06 | 2023-11-20 | 1354 | 1354 | 1354
10 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2023-11-30 | 2024-04-01 |  | 5414 | 5414 | 5414
10 | P.S. 315 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 2023-01-18 | 2023-05-11 | 2023-05-05 | 72000 | 57871 | 9307
10 | P.S. 315 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2023-11-29 | 2024-09-23 |  | 1056000 | 613872 | 4995
10 | P.S. 315 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY22 RESO A GYMNASIUM UPGRADE | CM,F&E | In-Progress | 2023-11-29 | 2024-09-23 |  | 72000 | 69897 | 34781
10 | P.S. 226 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-16 | 2024-11-14 | 2024-07-23 | 3305 | 564 | 564
10 | P.S. 226 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-23 | 2025-01-21 |  | 14872 | 14872 | 2257
10 | P.S. 59 - BRONX | SCA CIP | ROOFS | Scope | Complete | 2019-07-19 | 2019-12-05 | 2019-11-06 | 21987 | 21606 | 21606
10 | P.S. 59 - BRONX | SCA CIP | ROOFS | Design | Complete | 2019-11-13 | 2020-04-16 | 2021-05-12 | 109937 | 111763 | 111696
10 | P.S. 59 - BRONX | SCA CIP | ROOFS | Construction | In-Progress | 2023-04-17 | 2024-07-09 |  | 2473592 | 2543682 | 891586
10 | P.S. 59 - BRONX | SCA CIP | ROOFS | CM,F&E | In-Progress | 2023-04-17 | 2024-07-09 |  | 153912 | 936269 | 870446
10 | GIRLS PREPARATORY CHARTER SCHOOL OF THE BRONX II | SCA CIP | HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2023-12-15 | 2024-05-17 | 2024-05-24 | 72617 | 123897 | 123835
10 | GIRLS PREPARATORY CHARTER SCHOOL OF THE BRONX II | SCA CIP | HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM | Design | In-Progress | 2024-06-11 | 2024-12-16 |  | 355133 | 355133 | 6545
10 | P.S. 9 - BRONX | SCA CIP | ROOF | Scope | Complete | 2018-01-12 | 2018-05-30 | 2018-06-05 | 18067 | 33365 | 33365
10 | P.S. 9 - BRONX | SCA CIP | ROOF | Design | Complete | 2018-11-28 | 2019-05-01 | 2019-04-30 | 90336 | 132795 | 98771
10 | P.S. 9 - BRONX | SCA CIP | ROOF | Construction | In-Progress | 2019-08-13 | 2021-08-01 |  | 2032570 | 888104 | 864361
10 | P.S. 9 - BRONX | SCA CIP | ROOF | CM,F&E | In-Progress | 2019-08-13 | 2021-08-01 |  | 126471 | 23057 | 22589
11 | X012 SPED - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-02-27 | 2024-07-12 |  | 40860 | 36450 | 10617
11 | X012 SPED - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-04-25 | 2024-08-26 |  | 5787 | 1572 | 1572
11 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | Scope | Complete | 2020-01-17 | 2020-06-03 | 2021-10-19 | 58202 | 113247 | 113247
11 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | Design | Complete | 2021-10-22 | 2022-03-29 | 2022-03-09 | 281335 | 345203 | 345203
11 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | Construction | In-Progress | 2022-06-20 | 2024-03-10 |  | 5493262 | 5097047 | 4195695
11 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | CM,F&E | In-Progress | 2022-06-20 | 2024-03-10 |  | 479968 | 440052 | 439560
11 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 2023-06-14 | 2023-10-31 | 2023-11-09 | 71503 | 115650 | 115588
11 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | Complete | 2023-11-20 | 2024-04-23 | 2024-05-15 | 348241 | 320416 | 270250
11 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Construction | In-Progress | 2024-08-19 | 2026-05-10 |  | 7033353 | 6433985 | 112056
11 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2024-08-19 | 2026-05-10 |  | 570060 | 88936 | 42267
11 | P.S. 19 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2024-05-10 |  | 2024-08-16 | 280000 | 280000 | 279979
11 | P.S. 41 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2020-01-29 | 2020-07-23 | 2020-05-06 | 30000 | 27384 | 27384
11 | P.S. 41 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2021-06-09 | 2022-04-04 |  | 440000 | 220890 | 204028
11 | P.S. 41 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2021-06-09 | 2022-04-04 |  | 127480 | 155075 | 151569
11 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-05-25 | 2023-09-26 | 2023-06-07 | 3490 | 1618 | 1618
11 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-07 | 2023-12-05 | 2023-10-18 | 15705 | 6474 | 6474
11 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-03-15 | 2025-01-08 |  | 202420 | 183350 | 2850
11 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-03-15 | 2025-01-08 |  | 66758 | 57131 | 41267
11 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 2022-10-17 | 2023-05-26 | 2023-04-19 | 15993 | 40243 | 15730
11 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 2023-04-19 | 2023-08-22 | 2023-05-12 | 71969 | 85738 | 51788
11 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Construction | In-Progress | 2024-02-05 | 2024-10-31 |  | 927594 | 911219 | 79411
11 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2024-02-05 | 2024-10-31 |  | 171924 | 125878 | 33402
11 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-05-12 | 2022-09-12 | 2022-06-13 | 5500 | 5541 | 5541
11 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-13 | 2022-12-08 | 2022-12-07 | 24750 | 22162 | 22162
11 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-21 | 2024-04-15 |  | 319000 | 288345 | 155760
11 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-21 | 2024-04-15 |  | 201639 | 181254 | 147569
11 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 2022-06-17 | 2022-11-02 | 2023-03-09 | 120306 | 125177 | 110918
11 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 2023-03-10 | 2023-08-10 | 2023-05-12 | 601528 | 403203 | 351513
11 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 2023-08-07 | 2025-11-03 |  | 13534365 | 12495996 | 3744145
11 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 2023-08-07 | 2025-11-03 |  | 842138 | 464383 | 463953
11 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | Scope | Complete | 2019-04-30 | 2019-09-20 | 2019-09-20 | 1096620 | 847375 | 845153
11 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | Design | Complete | 2019-09-23 | 2020-03-30 | 2020-06-30 | 4934790 | 3182903 | 2489607
11 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | Construction | Complete | 2021-08-23 | 2024-09-03 | 2024-07-05 | 62233185 | 57999974 | 53221677
11 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | CM,Art,F&E | Complete | 2021-08-23 | 2024-09-03 | 2024-07-05 | 8772960 | 7031912 | 5214749
11 | P.S. 96 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-08-09 | 2022-12-27 | 2022-12-27 | 21983 | 34555 | 27945
11 | P.S. 96 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-12-29 | 2024-12-27 |  | 322417 | 293994 | 62588
11 | P.S. 96 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-12-29 | 2024-12-27 |  | 21983 | 45486 | 29162
11 | P.S. 97 - BRONX | SCA CIP | ROOM CONVERSION AND ADA WORK IN EXISTING BUILDING (PHASE 3) | Scope | Complete | 2018-06-01 | 2018-11-02 | 2022-05-02 | 17296 | 4607 | 4607
11 | P.S. 97 - BRONX | SCA CIP | ROOM CONVERSION AND ADA WORK IN EXISTING BUILDING (PHASE 3) | Design | Complete | 2022-05-02 | 2022-05-02 | 2022-05-02 | 63419 | 18426 | 18426
11 | P.S. 97 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-08-28 | 2025-01-16 |  | 39000 | 1155 | 1155
11 | P.S. 103 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2023-06-06 |  | 2023-08-21 | 80000 | 80000 | 75932
11 | P.S. 105 - BRONX | SCA Capacity | ADDITION | Scope | Complete | 2020-10-19 | 2021-04-06 | 2021-04-14 | 1067475 | 717767 | 715502
11 | P.S. 105 - BRONX | SCA Capacity | ADDITION | Design | Complete | 2021-04-15 | 2021-11-09 | 2022-09-16 | 4803640 | 2731631 | 1729503
11 | P.S. 105 - BRONX | SCA Capacity | ADDITION | Construction | In-Progress | 2023-04-06 | 2025-09-03 |  | 60579232 | 54436330 | 27190184
11 | P.S. 105 - BRONX | SCA Capacity | ADDITION | CM,Art,F&E | In-Progress | 2023-04-06 | 2025-09-03 |  | 8539804 | 6040266 | 2811355
11 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-IPDVS WORK / EXISTING BUILDING-FIRE ALARM WORK / EXISTING BUILDING-ELECTRICAL SYSTEMS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-10-14 | 2023-01-31 | 2023-10-23 | 149604 | 171157 | 171135
11 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-IPDVS WORK / EXISTING BUILDING-FIRE ALARM WORK / EXISTING BUILDING-ELECTRICAL SYSTEMS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 2023-10-25 | 2024-04-15 |  | 695712 | 695712 | 206718
11 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-GYMNASIUM | Scope | Complete | 2022-10-14 | 2023-01-31 | 2023-03-10 | 18206 | 12613 | 12613
11 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-GYMNASIUM | Design | Complete | 2023-03-15 | 2023-08-30 | 2023-11-21 | 81926 | 54764 | 52258
11 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2023-04-11 | 2023-08-25 | 2023-12-20 | 19293 | 57816 | 57816
11 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2024-01-02 | 2024-06-03 | 2024-05-07 | 96467 | 170017 | 130016
11 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2024-08-12 | 2026-04-03 |  | 2170514 | 1985880 | 5365
11 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-08-12 | 2026-04-03 |  | 135054 | 60336 | 23697
11 | P.S. 108 - BRONX | SCA Capacity | ADDITION | Scope | Complete | 2019-07-01 | 2019-12-02 | 2020-01-16 | 1237400 | 877808 | 849083
11 | P.S. 108 - BRONX | SCA Capacity | ADDITION | Design | Complete | 2020-01-17 | 2020-06-16 | 2021-05-14 | 5568300 | 2996965 | 2322579
11 | P.S. 108 - BRONX | SCA Capacity | ADDITION | Construction | In-Progress | 2021-10-04 | 2024-09-03 |  | 70222450 | 64773226 | 60051713
11 | P.S. 108 - BRONX | SCA Capacity | ADDITION | CM,Art,F&E | In-Progress | 2021-10-04 | 2024-09-03 |  | 9899200 | 7036993 | 4931754
11 | P.S. 108 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2024-03-04 |  | 2024-09-05 | 200000 | 200000 | 199728
11 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2020-02-11 | 2020-07-13 | 2020-03-25 | 59720 | 84751 | 84751
11 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2020-04-02 | 2020-09-01 | 2020-08-12 | 298600 | 397466 | 337733
11 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-05-10 | 2024-05-08 |  | 6718500 | 6185974 | 5824129
11 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-05-10 | 2024-05-08 |  | 418040 | 477671 | 458635
11 | P.S. 111 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2024-04-03 | 2024-08-19 | 2024-09-11 | 114324 | 38122 | 19222
11 | P.S. 111 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Design | In-Progress | 2024-09-17 | 2025-02-21 |  | 530877 | 530877 | 5307
11 | P.S. 112 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 2024-01-23 | 2024-06-06 | 2024-07-12 | 122210 | 615 | 615
11 | P.S. 112 - BRONX | SCA CIP | ROOFS | Scope | Complete | 2024-01-23 | 2024-06-06 | 2024-07-12 | 107301 | 107301 | 44173
11 | P.S. 112 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 2024-01-17 | 2024-05-31 | 2024-05-06 | 45000 | 35343 | 14564
11 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2020-05-22 | 2020-11-19 | 2020-10-21 | 273270 | 289029 | 289029
11 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2020-10-27 | 2021-06-15 | 2021-07-01 | 1366350 | 638855 | 620118
11 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2022-02-22 | 2024-05-11 |  | 30742876 | 27930574 | 21352100
11 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-02-22 | 2024-05-11 |  | 1912890 | 638443 | 632289
11 | SCHOOL OF DIPLOMACY | SCA CIP | AUDITORIUM UPGRADE | Scope | Complete | 2022-10-17 | 2023-02-21 | 2023-02-09 | 15645 | 52390 | 40709
11 | SCHOOL OF DIPLOMACY | SCA CIP | AUDITORIUM UPGRADE | Design | Complete | 2023-03-02 | 2023-08-02 | 2023-12-07 | 78227 | 173574 | 166043
11 | SCHOOL OF DIPLOMACY | SCA CIP | PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 2023-03-22 | 2023-06-22 | 2023-06-01 | 7065 | 9821 | 9821
11 | SCHOOL OF DIPLOMACY | SCA CIP | PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 2023-06-01 | 2023-10-04 | 2023-12-07 | 31792 | 36745 | 32051
11 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | FY22 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 2023-04-20 | 2023-08-21 | 2023-05-12 | 182944 | 113519 | 75473
11 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | FY22 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 2024-06-17 | 2026-01-07 |  | 2683165 | 2598180 | 48725
11 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | FY22 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 2024-06-17 | 2026-01-07 |  | 182944 | 39947 | 20137
11 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-06-25 | 2019-11-26 | 2019-09-25 | 65450 | 95684 | 95684
11 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-10-02 | 2020-03-09 | 2020-03-06 | 327250 | 467096 | 444956
11 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-06-14 | 2023-06-13 |  | 7363125 | 7145885 | 6707182
11 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-06-14 | 2023-06-13 |  | 458150 | 904710 | 898821
11 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2020-08-18 | 2021-01-22 | 2020-11-16 | 96030 | 111571 | 111571
11 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2020-11-18 | 2021-04-22 | 2021-02-03 | 480151 | 462070 | 430842
11 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-06-14 | 2024-06-12 |  | 10803375 | 10296205 | 8446524
11 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-06-14 | 2024-06-12 |  | 672210 | 402103 | 390613
11 | I.S. 127 - BRONX | SCA CIP | FLOOD ELIMINATION | Scope | In-Progress | 2024-08-21 | 2025-01-09 |  | 20000 | 20000 | 252
11 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-07-08 | 2021-11-23 | 2021-11-05 | 71743 | 84165 | 84165
11 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 2021-12-01 | 2022-05-04 | 2022-05-12 | 351722 | 297023 | 297023
11 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2022-08-15 | 2024-05-05 |  | 7308851 | 6785839 | 5693799
11 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-08-15 | 2024-05-05 |  | 555705 | 320158 | 319395
11 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | Scope | Complete | 2021-07-22 | 2021-12-23 | 2022-01-14 | 95580 | 103292 | 103292
11 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | Design | Complete | 2022-01-14 | 2022-06-16 | 2022-07-12 | 477900 | 840392 | 448464
11 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | Construction | In-Progress | 2023-04-13 | 2024-10-03 |  | 10752750 | 10211744 | 4655279
11 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | CM,F&E | In-Progress | 2023-04-13 | 2024-10-03 |  | 669060 | 512904 | 510518
11 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 2021-07-26 | 2021-12-10 | 2021-11-18 | 269000 | 312694 | 312694
11 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 2021-12-01 | 2022-05-04 | 2022-05-10 | 1345001 | 828741 | 756023
11 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Construction | In-Progress | 2023-04-10 | 2025-04-08 |  | 30262501 | 27491432 | 5663182
11 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | CM,F&E | In-Progress | 2023-04-10 | 2025-04-08 |  | 1884057 | 514753 | 513176
11 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2024-04-16 | 2024-08-30 |  | 112526 | 85650 | 35149
11 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 2024-03-28 | 2024-06-28 | 2024-09-16 | 419 | 419 | 419
11 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2024-09-16 | 2025-01-22 |  | 1676 | 1676 | 1676
11 | I.S. 144 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 2023-12-05 | 2024-04-22 | 2024-03-13 | 17928 | 35046 | 19323
11 | I.S. 144 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 2024-03-15 | 2024-08-15 | 2024-09-06 | 71711 | 57085 | 12058
11 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2021-03-08 | 2021-07-21 | 2021-11-12 | 255795 | 281991 | 281991
11 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2021-12-02 | 2022-05-05 | 2022-09-22 | 1265251 | 953177 | 796032
11 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2023-07-24 | 2025-10-20 |  | 27280913 | 24566832 | 6293726
11 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-07-24 | 2025-10-20 |  | 1894858 | 463590 | 459555
11 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-05-04 | 2022-09-01 | 2022-06-06 | 4200 | 2936 | 2936
11 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-06 | 2022-12-01 | 2022-11-30 | 18900 | 11745 | 11745
11 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-21 | 2024-04-15 |  | 243600 | 226960 | 121947
11 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-21 | 2024-04-15 |  | 187419 | 173893 | 136384
11 | P.S. 160 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-06-15 | 2021-11-16 | 2021-11-01 | 20657 | 60318 | 60318
11 | P.S. 160 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2022-11-28 | 2023-08-24 |  | 302971 | 111693 | 61457
11 | P.S. 160 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2022-11-28 | 2023-08-24 |  | 20657 | 45566 | 43846
11 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-05-27 | 2022-09-27 | 2022-06-15 | 3950 | 5401 | 5401
11 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-15 | 2022-12-12 | 2022-12-07 | 17775 | 21602 | 21602
11 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-16 | 2024-04-10 |  | 229100 | 206572 | 121984
11 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-16 | 2024-04-10 |  | 127985 | 118338 | 99784
11 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2022-01-19 | 2023-06-02 | 2023-03-14 | 32289 | 131461 | 127626
11 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-03-15 | 2023-12-04 | 2023-04-26 | 158330 | 165443 | 148157
11 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2023-11-09 | 2025-05-01 |  | 3292915 | 3113349 | 393080
11 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2023-11-09 | 2025-05-01 |  | 249392 | 144472 | 140705
11 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2022-01-24 | 2022-06-08 | 2022-08-12 | 68310 | 63318 | 63318
11 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-08-24 | 2023-02-14 | 2023-05-12 | 341550 | 266248 | 248470
11 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2023-07-24 | 2025-02-02 |  | 7684875 | 7030664 | 1825227
11 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-07-24 | 2025-02-02 |  | 478170 | 182214 | 177207
11 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Design | Complete | 2022-08-17 | 2023-02-02 | 2023-03-31 | 36000 | 48749 | 16432
11 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 2023-12-18 | 2024-09-12 |  | 528000 | 285830 | 1729
11 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | CM,F&E | In-Progress | 2023-12-18 | 2024-09-12 |  | 128751 | 124590 | 27420
11 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 2022-03-24 | 2022-07-22 | 2022-04-12 | 3008 | 3604 | 3604
11 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 2022-04-12 | 2022-10-05 | 2022-07-27 | 13537 | 14414 | 14414
11 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 2023-04-14 | 2024-02-07 |  | 174481 | 152864 | 62703
11 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 2023-04-14 | 2024-02-07 |  | 197884 | 189851 | 130244
11 | BRONXDALE HIGH SCHOOL - BRONX | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE / PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | Complete | 2024-05-14 | 2024-09-12 | 2024-07-26 | 28157 | 41888 | 11584
11 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 2020-08-05 | 2020-12-04 | 2021-05-28 | 64200 | 92974 | 84452
11 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 2021-06-08 | 2021-11-15 | 2021-11-23 | 321000 | 324155 | 318758
11 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2022-06-21 | 2024-06-19 |  | 7222500 | 7661359 | 4776379
11 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2022-06-21 | 2024-06-19 |  | 449400 | 263376 | 260858
11 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2022-06-09 | 2022-12-05 | 2022-10-25 | 499900 | 349714 | 349635
11 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | Design | Complete | 2022-11-08 | 2023-06-12 | 2023-05-08 | 2499499 | 654625 | 654625
11 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 2023-07-17 | 2026-01-01 |  | 56238751 | 50862291 | 16748400
11 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-07-17 | 2026-01-01 |  | 3499300 | 422187 | 418575
11 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | FY22 RESO A LOCKER ROOM UPGRADE / REINFORCING SUPPORT ELEMENTS / SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Scope | Complete | 2022-05-27 | 2024-01-25 | 2023-12-05 | 283042 | 257302 | 257302
11 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | FY22 RESO A LOCKER ROOM UPGRADE / REINFORCING SUPPORT ELEMENTS / SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Design | Complete | 2023-12-20 | 2024-05-01 | 2024-05-13 | 1406413 | 633418 | 576326
11 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | Scope | Complete | 2018-06-29 | 2018-12-28 | 2018-12-11 | 174630 | 478710 | 478710
11 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | Design | Complete | 2019-09-17 | 2020-10-02 | 2020-10-05 | 873151 | 1650225 | 1489280
11 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | Construction | In-Progress | 2022-08-15 | 2024-09-02 |  | 19645875 | 18523460 | 8919687
11 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | CM,F&E | In-Progress | 2022-08-15 | 2024-09-02 |  | 1223173 | 609190 | 602763
11 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | Scope | Complete | 2021-03-18 | 2021-08-02 | 2022-01-14 | 195096 | 180335 | 180335
11 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | Design | Complete | 2022-01-18 | 2022-06-17 | 2022-05-11 | 966382 | 590706 | 554000
11 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | Construction | In-Progress | 2022-07-18 | 2024-08-05 |  | 20956834 | 21379161 | 7834396
11 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | CM,F&E | In-Progress | 2022-07-18 | 2024-08-05 |  | 1433884 | 376114 | 370981
11 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2022-03-10 | 2022-07-25 | 2022-08-30 | 117480 | 103650 | 103650
11 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2022-09-06 | 2023-02-27 | 2023-05-09 | 587400 | 421689 | 371688
11 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-07-10 | 2025-10-06 |  | 13216500 | 12097154 | 1114740
11 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-07-10 | 2025-10-06 |  | 822360 | 185514 | 183281
11 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | In-Progress | 2023-08-03 | 2023-12-20 |  | 4730 | 30750 | 21465
11 | HARRY S. TRUMAN HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD / FY22 RESO A ATHLETIC FIELD UPGRADE | Design | Complete | 2023-08-21 | 2024-02-20 | 2024-05-08 | 732000 | 310302 | 310302
11 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | STANDALONE GYM ANNEX | Scope | Complete | 2018-11-08 | 2019-03-29 | 2019-04-29 | 218660 | 367784 | 367779
11 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | STANDALONE GYM ANNEX | Design | Complete | 2019-05-01 | 2019-11-25 | 2020-04-21 | 1093300 | 1663437 | 1270816
11 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | STANDALONE GYM ANNEX | Construction | Complete | 2021-07-06 | 2022-09-28 | 2024-04-18 | 24599250 | 22546579 | 21265504
11 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | STANDALONE GYM ANNEX | CM,F&E | Complete | 2021-07-06 | 2022-09-28 | 2024-04-18 | 1574072 | 1303654 | 1288710
11 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2021-05-03 | 2021-09-16 | 2021-07-20 | 28224 | 36508 | 36508
11 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | Complete | 2021-08-04 | 2022-01-07 | 2021-12-20 | 137389 | 165125 | 149780
11 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 2022-06-01 | 2023-11-22 |  | 2768198 | 2507695 | 2387388
11 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 2022-06-01 | 2023-11-22 |  | 225584 | 269473 | 261419
11 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 2012-11-13 | 2013-04-02 | 2013-03-25 | 162009 | 150673 | 150673
11 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | Design | Complete | 2013-05-06 | 2013-10-04 | 2014-02-28 | 633969 | 698888 | 629096
11 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 2018-02-12 | 2019-11-03 |  | 10624754 | 11526400 | 9664829
11 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 2018-02-12 | 2019-11-03 |  | 938858 | 1613382 | 1583094
11 | X721 SPED - BRONX | SCA CIP | ROOF REPLACEMENT | Scope | In-Progress | 2023-01-18 | 2023-06-02 |  | 18000 | 31313 | 2478
11 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-06-03 | 2022-10-03 | 2022-06-16 | 4490 | 3796 | 3796
11 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-16 | 2022-12-13 | 2022-12-07 | 20205 | 15186 | 15186
11 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-16 | 2024-04-10 |  | 260420 | 234990 | 149353
11 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-16 | 2024-04-10 |  | 164056 | 165980 | 116906
11 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | Scope | Complete | 2021-06-08 | 2021-10-22 | 2022-01-25 | 94105 | 37807 | 37807
11 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | Design | Complete | 2022-02-02 | 2022-07-05 | 2023-01-27 | 470523 | 403996 | 302132
11 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | Construction | In-Progress | 2023-08-07 | 2025-11-03 |  | 10586761 | 9646745 | 1131156
11 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | CM,F&E | In-Progress | 2023-08-07 | 2025-11-03 |  | 658732 | 66132 | 64991
11 | X000 - BRONX | SCA Furniture & Equipment | FY16 RESO A TECHNOLOGY | F&E | In-Progress | 2016-12-20 |  |  | 35000 | 35000 | 0
11 | WILLIAMSBRIDGE NAACP EARLY CHILDHOOD EDUCATION CEN - BRONX | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | Scope | Complete | 2023-11-08 | 2024-03-15 | 2024-06-13 | 712 | 18548 | 18548
12 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2019-07-11 | 2019-11-26 | 2020-01-31 | 112064 | 214153 | 208232
12 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2020-02-03 | 2020-07-02 | 2022-03-02 | 551088 | 653391 | 640694
12 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2022-06-21 | 2024-06-19 |  | 11600694 | 10659386 | 10222306
12 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2022-06-21 | 2024-06-19 |  | 853705 | 984546 | 944513
12 | P.S. 6 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SICENCE LAB | F&E | Complete | 2024-07-15 |  | 2024-07-26 | 200000 | 200000 | 199814
12 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | Scope | Complete | 2021-09-30 | 2022-02-18 | 2022-01-24 | 15435 | 97452 | 97452
12 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | Design | Complete | 2022-02-02 | 2022-06-10 | 2022-05-11 | 77175 | 80076 | 80076
12 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | Construction | In-Progress | 2022-08-10 | 2023-11-02 |  | 1736438 | 1603267 | 516415
12 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | CM,F&E | In-Progress | 2022-08-10 | 2023-11-02 |  | 108045 | 116326 | 116326
12 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2019-04-17 | 2019-08-30 | 2019-08-30 | 127200 | 158392 | 158392
12 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2019-10-04 | 2020-03-26 | 2020-06-30 | 636000 | 556622 | 543890
12 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2022-07-11 | 2024-07-09 |  | 14310000 | 13051229 | 11711783
12 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2022-07-11 | 2024-07-09 |  | 944363 | 577345 | 542006
12 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-01-23 | 2023-05-23 | 2023-03-30 | 7040 | 14844 | 2030
12 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-04-10 | 2023-10-11 | 2023-08-02 | 31680 | 38449 | 32674
12 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-02-01 | 2025-01-30 |  | 408320 | 370258 | 2818
12 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-02-01 | 2025-01-30 |  | 75680 | 47590 | 9574
12 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2022-06-14 | 2022-10-28 | 2023-01-09 | 58592 | 162079 | 141548
12 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Design | Complete | 2023-01-18 | 2023-06-20 | 2023-05-12 | 289823 | 220610 | 210313
12 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-08-12 | 2020-12-14 | 2020-08-21 | 4730 | 2851 | 2851
12 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-08-21 | 2021-02-17 | 2021-03-31 | 21284 | 11405 | 11405
12 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-16 | 2023-03-11 |  | 274326 | 248993 | 195789
12 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-16 | 2023-03-11 |  | 176996 | 168932 | 168772
12 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-08-08 | 2023-12-08 | 2023-08-22 | 4300 | 1863 | 1863
12 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-22 | 2024-02-21 | 2023-11-29 | 19350 | 7453 | 7453
12 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-04-12 | 2025-02-05 |  | 249400 | 230180 | 2830
12 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-04-12 | 2025-02-05 |  | 46225 | 30936 | 7716
12 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 2021-01-07 | 2021-05-07 | 2021-12-22 | 41250 | 95843 | 95843
12 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 2021-12-23 | 2022-05-26 | 2022-08-24 | 206250 | 314354 | 258150
12 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2023-06-21 | 2025-06-19 |  | 4640625 | 4857487 | 1754025
12 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2023-06-21 | 2025-06-19 |  | 288750 | 204914 | 201655
12 | P.S. 66 - BRONX | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2022-11-07 | 2023-03-07 | 2022-12-28 | 41808 | 87166 | 78166
12 | P.S. 66 - BRONX | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 2023-06-15 | 2024-03-15 |  | 613177 | 863498 | 83848
12 | P.S. 66 - BRONX | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2023-06-15 | 2024-03-15 |  | 117486 | 205884 | 140044
12 | P.S. 67 - BRONX | SCA CIP | KITCHEN ANSUL SYSTEM | Scope | Complete | 2020-02-03 | 2020-06-11 | 2021-10-08 | 12477 | 24972 | 24972
12 | P.S. 67 - BRONX | SCA CIP | KITCHEN ANSUL SYSTEM | Design | Complete | 2021-10-26 | 2022-05-13 | 2022-10-25 | 56144 | 66926 | 24284
12 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | Scope | Complete | 2018-10-10 | 2019-05-13 | 2019-03-28 | 319702 | 240815 | 240815
12 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | Design | Complete | 2019-03-28 | 2019-08-12 | 2019-05-17 | 1275345 | 707807 | 594968
12 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | Construction | In-Progress | 2019-08-05 | 2021-08-03 |  | 23602220 | 22599759 | 14400740
12 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | CM,F&E | In-Progress | 2019-08-05 | 2021-08-03 |  | 1536914 | 1591644 | 1566478
12 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | Scope | Complete | 2019-02-15 | 2020-03-27 | 2021-03-25 | 13687 | 33188 | 27423
12 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | Design | Complete | 2021-04-05 | 2021-08-24 | 2022-01-07 | 61592 | 113028 | 86722
12 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | Construction | In-Progress | 2022-07-20 | 2023-04-14 |  | 793858 | 842192 | 247820
12 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | CM,F&E | In-Progress | 2022-07-20 | 2023-04-14 |  | 147137 | 146739 | 106756
12 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | Scope | Complete | 2019-04-25 | 2020-02-05 | 2020-02-05 | 1385261 | 1374109 | 1340771
12 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | Design | Complete | 2020-02-05 | 2020-05-15 | 2020-08-17 | 6233670 | 4290997 | 3758188
12 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | Construction | Complete | 2021-08-02 | 2024-09-03 | 2024-07-01 | 78613505 | 72497377 | 65905826
12 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | CM,Art,F&E | Complete | 2021-08-02 | 2024-09-03 | 2024-07-01 | 11082080 | 9101427 | 7662178
12 | P.S. 195 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-01-13 | 2023-04-14 | 2023-05-31 | 21800 | 64050 | 63968
12 | P.S. 195 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-06-06 | 2023-10-23 | 2024-05-01 | 109001 | 121822 | 118685
12 | P.S. 195 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-10-04 | 2024-01-09 | 2023-12-21 | 708 | 1412 | 1412
12 | P.S. 195 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-12-28 | 2024-05-30 | 2024-05-01 | 3187 | 5772 | 5647
12 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-09 | 2023-07-10 | 2023-03-16 | 7180 | 2108 | 2108
12 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-16 | 2023-09-11 | 2023-05-02 | 32310 | 8430 | 8430
12 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-01 | 2024-08-26 |  | 416440 | 371443 | 2353
12 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-01 | 2024-08-26 |  | 77185 | 39736 | 854
12 | X352 SPED - BRONX | SCA CIP | EXTERIOR MASONRY @ X092- PERMANENT FIX | Scope | In-Progress | 2024-05-24 | 2024-10-10 |  | 20000 | 38323 | 3923
12 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-09 | 2023-07-24 | 2023-03-14 | 4880 | 1791 | 1791
12 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-14 | 2023-09-07 | 2023-05-02 | 21960 | 7161 | 7161
12 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-01 | 2024-08-26 |  | 283040 | 253813 | 873
12 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-01 | 2024-08-26 |  | 52460 | 28525 | 2063
12 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Scope | Complete | 2019-02-13 | 2019-06-28 | 2020-02-19 | 89700 | 256871 | 256825
12 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Design | Complete | 2021-04-12 | 2021-09-10 | 2022-02-03 | 442641 | 528430 | 506486
12 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Construction | In-Progress | 2022-10-03 | 2024-10-01 |  | 9452510 | 8608396 | 121021
12 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | CM,F&E | In-Progress | 2022-10-03 | 2024-10-01 |  | 679175 | 323508 | 258584
12 | METROPOLITAN HS - BRONX | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2019-06-14 | 2019-10-30 | 2019-11-20 | 35134 | 79410 | 77145
12 | METROPOLITAN HS - BRONX | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2021-02-16 | 2021-07-16 | 2021-05-14 | 172766 | 181079 | 137187
12 | METROPOLITAN HS - BRONX | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / PARAPETS | Construction | Complete | 2021-07-12 | 2023-01-02 | 2024-05-09 | 3636326 | 3371254 | 3184080
12 | METROPOLITAN HS - BRONX | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / PARAPETS | CM,F&E | Complete | 2021-07-12 | 2023-01-02 | 2024-05-09 | 267692 | 529241 | 522888
12 | METROPOLITAN HS - BRONX | SCA CIP | ROOFS / WINDOWS | Scope | In-Progress | 2024-06-20 | 2024-11-05 |  | 93943 | 93943 | 41599
12 | I.S. 217 - BRONX | SCA CIP | ROOFS | Scope | In-Progress | 2024-06-14 | 2024-10-31 |  | 71439 | 71439 | 25636
12 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2020-09-24 | 2021-03-02 | 2021-01-12 | 92200 | 87407 | 87407
12 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2021-01-14 | 2021-08-02 | 2021-12-07 | 461000 | 338707 | 314286
12 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-08-04 | 2024-08-02 |  | 10372501 | 9309887 | 4586111
12 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-08-04 | 2024-08-02 |  | 645695 | 208356 | 208356
12 | P.S. 134 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-08-07 | 2024-12-09 | 2024-09-05 | 4928 | 271 | 271
12 | P.S. 134 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-09-05 | 2025-03-06 |  | 22176 | 22176 | 1085
12 | P.S. 134 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 2024-07-23 | 2025-01-22 | 2024-09-26 | 240013 | 45718 | 20219
12 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | Scope | Complete | 2016-08-30 | 2017-02-03 | 2016-10-13 | 134195 | 141969 | 141969
12 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | Design | Complete | 2016-10-26 | 2017-03-31 | 2017-04-26 | 530645 | 521249 | 499912
12 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | Construction | In-Progress | 2018-04-16 | 2020-04-14 |  | 9399158 | 9099556 | 8657473
12 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | CM,F&E | In-Progress | 2018-04-16 | 2020-04-14 |  | 705971 | 1319187 | 1311342
12 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-08-10 | 2021-12-28 | 2021-11-30 | 72720 | 101652 | 101652
12 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2021-12-15 | 2022-06-03 | 2022-07-01 | 363600 | 730337 | 335438
12 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-09-18 | 2025-09-16 |  | 8181000 | 7827173 | 2220343
12 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-09-18 | 2025-09-16 |  | 647774 | 612453 | 188195
12 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-20 | 2023-04-21 | 2023-01-25 | 7315 | 4102 | 4102
12 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-25 | 2023-07-21 | 2023-04-19 | 32918 | 16407 | 16407
12 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-27 | 2024-08-21 |  | 424270 | 377668 | 1810
12 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-27 | 2024-08-21 |  | 122179 | 88379 | 5226
12 | P.S. 150 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-09-06 | 2025-01-09 | 2024-09-12 | 4788 | 186 | 186
12 | P.S. 150 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-09-12 | 2025-03-13 |  | 21545 | 21545 | 746
12 | P.S. 150 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-12-07 | 2022-05-10 | 2022-09-14 | 59731 | 69247 | 66617
12 | P.S. 150 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-07-20 | 2022-12-06 | 2023-02-23 | 56743 | 79569 | 79569
12 | P.S. 150 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-08-21 | 2024-05-16 |  | 832230 | 788047 | 209662
12 | P.S. 150 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-08-21 | 2024-05-16 |  | 56743 | 76974 | 17761
12 | DR. IZQUIERDO HEALTH CHARTER SCHL - X | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | In-Progress | 2024-05-29 |  |  | 250000 | 250000 | 38806
12 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-12 | 2023-10-12 | 2023-09-22 | 12387 | 15695 | 15695
12 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-04 | 2024-03-05 | 2024-04-04 | 55743 | 58478 | 43333
12 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-16 | 2025-09-15 |  | 718463 | 660247 | 17286
12 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-16 | 2025-09-15 |  | 133163 | 98154 | 17258
12 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-07-22 | 2020-11-20 | 2020-07-27 | 5317 | 3872 | 3872
12 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-27 | 2021-01-21 | 2021-03-30 | 23925 | 15488 | 15488
12 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-16 | 2023-03-11 |  | 308370 | 280609 | 222231
12 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-16 | 2023-03-11 |  | 199976 | 187766 | 184660
12 | P.S. 214 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LAB | F&E | In-Progress | 2024-08-16 |  |  | 200000 | 200000 | 923
12 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-07-22 | 2020-11-20 | 2020-07-27 | 5214 | 4128 | 4128
12 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-27 | 2021-01-21 | 2021-05-05 | 23461 | 16512 | 16512
12 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-16 | 2023-03-11 |  | 302384 | 283647 | 223488
12 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-16 | 2023-03-11 |  | 203875 | 195744 | 184377
12 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | Scope | Complete | 2022-06-16 | 2023-05-05 | 2023-05-05 | 31639 | 46774 | 41009
12 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | Design | Complete | 2023-05-08 | 2023-09-11 | 2023-05-12 | 157666 | 137428 | 93048
12 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | Construction | In-Progress | 2024-04-08 | 2025-10-04 |  | 3501726 | 3242312 | 56442
12 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | CM,F&E | In-Progress | 2024-04-08 | 2025-10-04 |  | 225439 | 61492 | 48269
12 | P.S. 211 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2023-10-02 |  | 2024-05-31 | 260007 | 260007 | 259618
12 | P.S. 212 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND REDEVELOPMENT | Scope | Complete | 2019-06-19 | 2019-12-17 | 2019-11-06 | 184250 | 278645 | 278392
12 | P.S. 212 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND REDEVELOPMENT | Design | Complete | 2019-11-19 | 2020-06-15 | 2020-04-28 | 921250 | 705351 | 703354
12 | P.S. 212 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND REDEVELOPMENT | Construction | Complete | 2021-06-03 | 2024-05-17 | 2023-12-11 | 20728125 | 18318296 | 18066843
12 | P.S. 212 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND REDEVELOPMENT | CM,F&E | Complete | 2021-06-03 | 2024-05-17 | 2023-12-11 | 1289749 | 497834 | 497677
12 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-17 | 2023-05-16 | 2023-02-02 | 4985 | 2362 | 2362
12 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-02 | 2023-07-31 | 2023-04-19 | 22433 | 9447 | 9447
12 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-27 | 2024-08-21 |  | 289130 | 260392 | 2200
12 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-27 | 2024-08-21 |  | 53589 | 29513 | 2484
12 | P.S. 300 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 2024-08-06 | 2024-11-05 |  | 28215 | 28215 | 4628
12 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | Scope | Complete | 2014-03-05 | 2014-07-18 | 2015-02-12 | 247379 | 200847 | 189919
12 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | Design | Complete | 2016-08-15 | 2017-01-19 | 2017-04-21 | 982671 | 818508 | 731310
12 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | Construction | In-Progress | 2018-08-06 | 2020-08-04 |  | 17810761 | 18183554 | 16392182
12 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | CM,F&E | In-Progress | 2018-08-06 | 2020-08-04 |  | 1243414 | 2372966 | 2306947
12 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Scope | Complete | 2021-04-13 | 2022-09-26 | 2022-07-29 | 101545 | 113778 | 102202
12 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Design | Complete | 2022-08-09 | 2022-12-09 | 2022-10-05 | 507289 | 401533 | 339070
12 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Construction | In-Progress | 2023-06-12 | 2025-06-10 |  | 11376396 | 10343333 | 734480
12 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | CM,F&E | In-Progress | 2023-06-12 | 2025-06-10 |  | 714075 | 154742 | 149816
13 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2021-12-17 | 2022-05-05 | 2022-02-25 | 104750 | 182119 | 147514
13 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2022-02-25 | 2022-07-27 | 2022-05-06 | 523751 | 189255 | 189255
13 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2022-07-18 | 2024-04-07 |  | 11784376 | 10729359 | 8992156
13 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2022-07-18 | 2024-04-07 |  | 733250 | 477980 | 473626
13 | P.S. 3 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-03-05 | 2024-07-03 | 2024-03-25 | 3222 | 1478 | 1478
13 | P.S. 3 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-25 | 2024-09-18 | 2024-08-13 | 14500 | 5910 | 5910
13 | P.S. 8 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-06-05 | 2023-10-20 | 2024-01-10 | 60000 | 69798 | 59384
13 | P.S. 8 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2024-07-15 | 2025-08-18 |  | 880000 | 599187 | 34662
13 | P.S. 8 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2024-07-15 | 2025-08-18 |  | 60000 | 74294 | 21368
13 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-31 | 2024-05-30 | 2024-03-25 | 4851 | 1387 | 1387
13 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-25 | 2024-09-18 | 2024-08-13 | 21827 | 5550 | 5550
13 | P.S. 20 - BROOKLYN | SCA CIP | PUBLIC ADDRESS SYSTEM | Scope | Complete | 2021-04-09 | 2021-07-09 | 2021-07-19 | 15958 | 17916 | 17916
13 | P.S. 20 - BROOKLYN | SCA CIP | PUBLIC ADDRESS SYSTEM | Design | Complete | 2021-08-10 | 2022-01-13 | 2022-02-11 | 71811 | 92025 | 90065
13 | P.S. 20 - BROOKLYN | SCA CIP | PUBLIC ADDRESS SYSTEM | Construction | Complete | 2022-07-11 | 2023-05-06 | 2023-05-05 | 925564 | 820348 | 813203
13 | P.S. 20 - BROOKLYN | SCA CIP | PUBLIC ADDRESS SYSTEM | CM,F&E | Complete | 2022-07-11 | 2023-05-06 | 2023-05-05 | 171549 | 83332 | 83332
13 | P.S. 20 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PLAYGROUND RENOVATION / FIRE ALARM SYSTEM | Scope | Complete | 2022-02-11 | 2022-06-28 | 2023-03-22 | 118587 | 215720 | 202065
13 | P.S. 20 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PLAYGROUND RENOVATION / FIRE ALARM SYSTEM | Design | Complete | 2023-04-19 | 2023-10-05 | 2024-07-05 | 580177 | 376642 | 339912
13 | P.S. 20 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-01 | 2022-11-17 | 2023-01-20 | 82243 | 122239 | 122239
13 | P.S. 20 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-01-31 | 2023-07-03 | 2023-11-16 | 411214 | 333761 | 292730
13 | P.S. 20 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-08-22 | 2024-12-24 | 2024-09-06 | 3959 | 0 | 0
13 | P.S. 20 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-09-06 | 2025-03-07 |  | 17816 | 17816 | 0
13 | P.S. 20 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GREEN ROOF | Design | Complete | 2024-02-16 | 2024-07-19 | 2024-09-18 | 423750 | 248025 | 21782
13 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Scope | Complete | 2022-05-20 | 2022-10-05 | 2022-11-30 | 136640 | 205561 | 179223
13 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Design | Complete | 2022-12-20 | 2023-06-08 | 2023-05-12 | 683200 | 514104 | 365323
13 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Construction | In-Progress | 2023-10-16 | 2026-03-03 |  | 15372000 | 14261625 | 2077351
13 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-10-16 | 2026-03-03 |  | 956480 | 166071 | 166071
13 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-06-14 | 2023-10-16 | 2023-06-29 | 4240 | 1319 | 1319
13 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-06-29 | 2023-12-27 | 2023-09-27 | 19080 | 5277 | 5277
13 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2024-03-29 | 2025-02-21 |  | 245920 | 225853 | 81651
13 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2024-03-29 | 2025-02-21 |  | 74471 | 56696 | 10184
13 | P.S. 54 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 2019-06-12 | 2019-10-28 | 2021-09-24 | 124280 | 132066 | 128688
13 | P.S. 54 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 2021-10-05 | 2022-04-12 | 2023-08-31 | 621399 | 343420 | 304285
13 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2019-09-09 | 2020-01-28 | 2020-01-23 | 12351 | 16570 | 16570
13 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2020-02-05 | 2020-07-07 | 2021-03-01 | 61755 | 156701 | 105355
13 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 2021-07-19 | 2022-10-11 |  | 1389488 | 1334838 | 900852
13 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 2021-07-19 | 2022-10-11 |  | 86457 | 43242 | 41019
13 | P.S. 54 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-08 | 2022-11-23 | 2023-10-20 | 104833 | 177201 | 176092
13 | P.S. 54 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-10-26 | 2024-04-01 | 2024-03-19 | 524168 | 369251 | 351106
13 | P.S. 54 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-09-18 | 2025-01-22 | 2024-09-25 | 3926 | 0 | 0
13 | P.S. 54 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-09-25 | 2025-03-26 |  | 17669 | 17669 | 0
13 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-06-15 | 2023-10-17 | 2023-06-29 | 4000 | 1700 | 1700
13 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-06-29 | 2023-12-27 | 2023-09-27 | 18000 | 6799 | 6799
13 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2024-03-29 | 2025-02-21 |  | 232000 | 218133 | 93744
13 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2024-03-29 | 2025-02-21 |  | 69388 | 50543 | 29863
13 | I.S. 351 - BROOKLYN | SCA CIP RESOA | FY18 RESO A COURTYARD GREENHOUSE | Design | Complete | 2018-10-31 | 2019-04-05 | 2019-12-13 | 195000 | 144963 | 141589
13 | P.S. 67 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Scope | Complete | 2022-06-03 | 2022-10-19 | 2022-12-06 | 132263 | 208408 | 164274
13 | P.S. 67 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Design | Complete | 2023-02-06 | 2023-07-25 | 2024-05-15 | 661316 | 474639 | 60074
13 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-09 | 2023-06-09 | 2023-02-10 | 4873 | 2099 | 2099
13 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-10 | 2023-08-08 | 2023-04-26 | 21929 | 8397 | 8397
13 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-16 | 2024-07-10 |  | 282634 | 259474 | 78692
13 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-16 | 2024-07-10 |  | 124094 | 101610 | 75567
13 | K753 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS | Scope | Complete | 2021-09-14 | 2022-11-21 | 2023-03-06 | 90069 | 151663 | 151663
13 | K753 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS | Design | Complete | 2023-03-15 | 2023-08-15 | 2023-09-13 | 450345 | 381235 | 351747
13 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | Scope | Complete | 2023-06-06 | 2023-10-05 | 2023-06-20 | 4580 | 176 | 176
13 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | Design | Complete | 2023-06-20 | 2023-12-15 | 2023-08-30 | 20610 | 705 | 705
13 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | Construction | In-Progress | 2024-02-16 | 2025-01-10 |  | 265640 | 249710 | 142908
13 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | CM,F&E | In-Progress | 2024-02-16 | 2025-01-10 |  | 77920 | 56705 | 37960
13 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | Scope | Complete | 2021-06-02 | 2021-12-01 | 2021-10-06 | 194245 | 154364 | 154364
13 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | Design | Complete | 2021-10-18 | 2022-06-30 | 2022-04-27 | 961994 | 526576 | 526576
13 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | Construction | In-Progress | 2022-07-18 | 2024-07-16 |  | 20846287 | 19050394 | 15291264
13 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | CM,F&E | In-Progress | 2022-07-18 | 2024-07-16 |  | 1428957 | 583924 | 576907
13 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2022-04-08 | 2022-10-04 | 2022-07-25 | 8980 | 12612 | 12612
13 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2022-07-26 | 2023-01-24 | 2022-12-21 | 40410 | 50447 | 50447
13 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2023-05-31 | 2024-04-24 |  | 520840 | 476661 | 300678
13 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2023-05-31 | 2024-04-24 |  | 96535 | 81922 | 71522
13 | P.S. 256 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2023-01-24 | 2023-06-08 | 2023-11-06 | 61430 | 167289 | 149608
13 | P.S. 256 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | In-Progress | 2023-12-13 | 2024-05-15 |  | 299444 | 299444 | 152015
13 | P.S. 256 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-08-13 | 2024-12-13 | 2024-08-13 | 4425 | 0 | 0
13 | P.S. 256 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-08-13 | 2025-02-11 |  | 19913 | 19913 | 0
13 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2023-06-22 | 2023-11-07 | 2023-12-05 | 95880 | 308735 | 261827
13 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2023-12-14 | 2024-05-16 | 2024-04-30 | 479400 | 777992 | 297209
13 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2024-07-18 | 2027-01-03 |  | 10786500 | 10407502 | 178590
13 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-07-18 | 2027-01-03 |  | 671160 | 553824 | 60665
13 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2019-07-22 | 2019-12-06 | 2019-12-19 | 103017 | 130059 | 130059
13 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2019-12-30 | 2020-06-01 | 2020-06-30 | 515089 | 362086 | 350973
13 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2021-07-21 | 2023-04-01 |  | 11589500 | 11331800 | 7169632
13 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-07-21 | 2023-04-01 |  | 721124 | 719157 | 704813
13 | P.S. 270 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-08-16 | 2024-12-18 | 2024-08-20 | 4221 | 0 | 0
13 | P.S. 270 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-08-20 | 2025-02-19 |  | 18996 | 18996 | 0
13 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-05-29 | 2019-10-29 | 2019-08-01 | 58280 | 81169 | 81169
13 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-08-01 | 2020-01-06 | 2020-02-03 | 291400 | 445239 | 380435
13 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-07-06 | 2023-07-05 |  | 6556500 | 7022643 | 5634384
13 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-07-06 | 2023-07-05 |  | 407960 | 625670 | 563727
13 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-15 | 2023-06-15 | 2023-02-17 | 5007 | 2398 | 2398
13 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-17 | 2023-08-15 | 2023-04-26 | 22532 | 9592 | 9592
13 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-16 | 2024-07-10 |  | 290406 | 257156 | 130285
13 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-16 | 2024-07-10 |  | 126373 | 101920 | 93093
13 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2020-01-17 | 2020-06-18 | 2020-04-14 | 71170 | 106445 | 106445
13 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2020-04-15 | 2020-09-15 | 2020-07-31 | 355850 | 392262 | 382491
13 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-03-28 | 2024-03-26 |  | 8006626 | 7334507 | 6809222
13 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-03-28 | 2024-03-26 |  | 498190 | 569149 | 563510
13 | P.S. 287 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-09-10 | 2025-01-13 | 2024-09-13 | 4287 | 0 | 0
13 | P.S. 287 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-09-13 | 2025-03-14 |  | 19292 | 19292 | 0
13 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-09-13 | 2023-03-13 | 2023-01-05 | 116173 | 244880 | 111302
13 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-01-11 | 2023-07-10 | 2023-05-02 | 580866 | 798016 | 304183
13 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-10-03 | 2025-10-01 |  | 13069464 | 12523532 | 2911089
13 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-10-03 | 2025-10-01 |  | 814213 | 818700 | 315197
13 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-06 | 2023-07-05 | 2023-03-09 | 4660 | 2529 | 2529
13 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-09 | 2023-09-01 | 2023-05-04 | 20970 | 10116 | 10116
13 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-20 | 2024-09-13 |  | 270280 | 249045 | 177250
13 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-20 | 2024-09-13 |  | 120700 | 102692 | 96620
13 | P.S. 307 - BROOKLYN | SCA CIP | NYS AUDITORIUM UPGRADE / PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Scope | Complete | 2019-07-30 | 2020-07-08 | 2020-07-22 | 17780 | 36710 | 24210
13 | P.S. 307 - BROOKLYN | SCA CIP | NYS AUDITORIUM UPGRADE / PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Design | Complete | 2020-07-22 | 2020-11-30 | 2021-05-14 | 80010 | 91769 | 80696
13 | P.S. 307 - BROOKLYN | SCA CIP | NYS AUDITORIUM UPGRADE / PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Construction | Complete | 2021-09-15 | 2022-09-14 | 2023-02-09 | 1031240 | 1023380 | 703664
13 | P.S. 307 - BROOKLYN | SCA CIP | NYS AUDITORIUM UPGRADE / PATH OF TRAVEL NYS AUDITORIUM UPGRADE | CM,F&E | Complete | 2021-09-15 | 2022-09-14 | 2023-02-09 | 191292 | 381477 | 379283
13 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-06-02 | 2023-10-03 | 2023-06-12 | 4860 | 176 | 176
13 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-12 | 2023-12-08 | 2023-08-30 | 21870 | 705 | 705
13 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-16 | 2025-01-10 |  | 281880 | 264671 | 139849
13 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-16 | 2025-01-10 |  | 86633 | 64359 | 52269
13 | P.S. 307 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-07-09 | 2024-11-22 |  | 81000 | 53263 | 9592
13 | P.S. 307 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-08-08 | 2024-12-12 |  | 4345 | 1338 | 1338
13 | I.S. 527 - BROOKLYN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 2022-03-17 | 2022-07-15 | 2022-04-13 | 3363 | 2268 | 2268
13 | I.S. 527 - BROOKLYN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 2022-04-13 | 2022-10-06 | 2022-07-19 | 15134 | 9072 | 9072
13 | I.S. 527 - BROOKLYN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | Complete | 2023-02-24 | 2023-12-20 | 2023-12-18 | 195054 | 169832 | 144828
13 | I.S. 527 - BROOKLYN | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | Complete | 2023-02-24 | 2023-12-20 | 2023-12-18 | 251328 | 252574 | 247772
13 | I.S. 527 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / ROOFS / FIRE ALARM | Scope | Complete | 2023-11-17 | 2024-04-17 | 2024-07-18 | 377571 | 121381 | 12661
13 | I.S. 527 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / ROOFS / FIRE ALARM | Design | In-Progress | 2024-08-15 | 2025-03-14 |  | 1753653 | 1753653 | 50636
13 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | Scope | Complete | 2013-02-28 | 2013-05-29 | 2013-07-24 | 77238 | 68602 | 68602
13 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | Design | Complete | 2013-08-21 | 2014-02-27 | 2014-09-04 | 300370 | 738707 | 690963
13 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | Construction | In-Progress | 2014-11-24 | 2016-02-16 |  | 4861703 | 6113070 | 5582552
13 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | CM,F&E | In-Progress | 2014-11-24 | 2016-02-16 |  | 472010 | 1155579 | 1148292
13 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | Scope | Complete | 2016-04-13 | 2016-08-26 | 2017-02-23 | 367911 | 214730 | 214730
13 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | Design | Complete | 2017-05-22 | 2017-10-23 | 2018-03-15 | 1463972 | 940079 | 824864
13 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | Construction | In-Progress | 2018-07-16 | 2021-01-14 |  | 26760698 | 28959956 | 20413342
13 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | CM,F&E | In-Progress | 2018-07-16 | 2021-01-14 |  | 1816689 | 1687162 | 1577160
13 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2017-08-01 | 2018-01-04 | 2018-12-11 | 362895 | 249954 | 249954
13 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2018-12-12 | 2019-05-15 | 2019-05-17 | 1451580 | 916008 | 857513
13 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2019-07-29 | 2022-07-12 |  | 27217125 | 38050514 | 32883720
13 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2019-07-29 | 2022-07-12 |  | 1693510 | 2013937 | 1881258
13 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY13 RESO A AUDITORIUM UPGRADE | Design | Complete | 2015-05-27 | 2015-10-27 | 2016-09-06 | 89709 | 258009 | 251587
13 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Design | Complete | 2019-07-09 | 2019-12-10 | 2020-05-28 | 106865 | 132270 | 125883
13 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 2022-08-08 | 2023-08-07 |  | 1567353 | 1415726 | 1257339
13 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 2022-08-08 | 2023-08-07 |  | 106865 | 383146 | 379206
13 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | Scope | Complete | 2013-03-18 | 2013-07-17 | 2013-08-23 | 141546 | 308168 | 308168
13 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | Design | Complete | 2015-06-05 | 2016-01-11 | 2016-10-28 | 566184 | 593499 | 561481
13 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | Construction | In-Progress | 2017-08-21 | 2019-08-20 |  | 10615950 | 10737510 | 9855180
13 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | CM,F&E | In-Progress | 2017-08-21 | 2019-08-20 |  | 660548 | 776959 | 744941
13 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-22 | 2023-10-20 | 2023-10-18 | 11111 | 19084 | 19084
13 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-20 | 2024-03-20 | 2024-04-29 | 49997 | 84130 | 61031
13 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-17 | 2025-10-21 |  | 644409 | 575716 | 4699
13 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-17 | 2025-10-21 |  | 119438 | 82905 | 8594
13 | I.S. 653 - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2015-05-27 | 2015-12-09 | 2016-06-06 | 836600 | 4265 | 4265
13 | I.S. 653 - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 2016-06-07 | 2016-07-20 | 2022-05-09 | 3764700 | 1099264 | 868719
13 | I.S. 653 - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | Complete | 2022-07-11 | 2025-09-03 | 2024-03-01 | 47477050 | 43585446 | 40663158
13 | I.S. 653 - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 2022-07-11 | 2025-09-03 | 2024-03-01 | 6692800 | 3404805 | 3041661
13 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | Scope | Complete | 2016-04-11 | 2016-07-07 | 2016-06-28 | 71100 | 219229 | 219229
13 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | Design | Complete | 2016-06-29 | 2016-12-30 | 2017-03-06 | 355500 | 1015792 | 475295
13 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | Construction | In-Progress | 2023-11-20 | 2024-09-03 |  | 7998750 | 7360534 | 6873730
13 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | CM,F&E | In-Progress | 2023-11-20 | 2024-09-03 |  | 1241006 | 1859745 | 1277518
13 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 2016-01-26 | 2016-06-09 | 2016-07-22 | 179797 | 97216 | 97216
13 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Design | Complete | 2017-03-13 | 2017-08-10 | 2018-05-18 | 698119 | 963788 | 763567
13 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Construction | In-Progress | 2018-08-27 | 2020-05-17 |  | 11199258 | 15565820 | 11532616
13 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2018-08-27 | 2020-05-17 |  | 1112884 | 1527301 | 1356817
13 | ALC - FUNDAMENTAL ACADEMY | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2023-12-22 | 2024-05-09 | 2024-03-13 | 13130 | 16519 | 16519
13 | ALC - FUNDAMENTAL ACADEMY | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2024-03-15 | 2024-08-15 | 2024-08-02 | 52522 | 47861 | 44012
13 | DIV. COMPUTER INFO-DATA CNTR - K | SCA CIP | DATA CENTER | Scope | Complete | 2015-01-20 | 2015-05-19 | 2015-06-03 | 407874 | 362965 | 362965
13 | DIV. COMPUTER INFO-DATA CNTR - K | SCA CIP | DATA CENTER | Design | In-Progress | 2016-12-21 | 2017-08-07 |  | 2039370 | 2039370 | 956411
13 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2019-06-05 | 2019-09-04 | 2019-08-15 | 10700 | 20719 | 20719
13 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2019-12-04 | 2020-06-08 | 2020-06-30 | 48150 | 85976 | 67443
13 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 2024-07-22 | 2025-06-16 |  | 620600 | 554086 | 5586
13 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2024-07-22 | 2025-06-16 |  | 115025 | 79628 | 21848
13 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-02 | 2023-06-30 | 2023-03-09 | 3140 | 2447 | 2447
13 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-09 | 2023-09-01 | 2023-05-04 | 14130 | 9789 | 9789
13 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-20 | 2024-09-13 |  | 182120 | 170777 | 108957
13 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-20 | 2024-09-13 |  | 112364 | 100181 | 92907
14 | P.S. 16 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-28 | 2024-09-26 | 2024-05-31 | 4830 | 2374 | 2374
14 | P.S. 16 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-05-31 | 2024-11-27 |  | 21733 | 21733 | 9494
14 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2017-04-06 | 2017-11-02 | 2017-12-19 | 183712 | 162802 | 162802
14 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2018-04-25 | 2018-10-25 | 2022-09-30 | 910025 | 549395 | 485039
14 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2023-08-28 | 2025-08-16 |  | 19737609 | 17864482 | 1766486
14 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-08-28 | 2025-08-16 |  | 1349963 | 177568 | 176061
14 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-07-27 | 2023-11-28 | 2023-08-02 | 3886 | 3429 | 3429
14 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-08-02 | 2024-01-31 | 2023-12-20 | 17487 | 13718 | 13718
14 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2024-04-16 | 2025-03-11 |  | 225388 | 201504 | 2704
14 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2024-04-16 | 2025-03-11 |  | 45515 | 29675 | 4841
14 | P.S. 18 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND UPGRADE | Scope | Complete | 2022-07-08 | 2022-11-23 | 2023-08-21 | 84605 | 158583 | 135690
14 | P.S. 18 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND UPGRADE | Design | Complete | 2023-08-31 | 2024-02-06 | 2024-01-30 | 417512 | 273743 | 260177
14 | P.S. 18 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 2023-12-13 | 2023-12-13 | 2023-12-13 | 1049 | 8420 | 108
14 | P.S. 18 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 2023-12-13 | 2024-04-12 | 2024-01-30 | 4722 | 432 | 432
14 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | Scope | Complete | 2022-06-06 | 2022-11-30 | 2022-10-04 | 284352 | 503815 | 465008
14 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | Design | Complete | 2022-10-24 | 2023-06-12 | 2023-04-28 | 1412403 | 809156 | 809156
14 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | Construction | In-Progress | 2023-09-04 | 2026-09-02 |  | 30970227 | 28906360 | 4742308
14 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-09-04 | 2026-09-02 |  | 2060577 | 344872 | 326374
14 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2020-08-18 | 2021-01-22 | 2021-01-06 | 71320 | 107204 | 107204
14 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2021-01-08 | 2021-09-30 | 2021-07-02 | 356600 | 402186 | 391997
14 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-04-04 | 2024-04-02 |  | 8023500 | 7507967 | 7048223
14 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-04-04 | 2024-04-02 |  | 499240 | 466305 | 465200
14 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-06-09 | 2022-12-05 | 2022-10-04 | 64303 | 228049 | 190965
14 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2022-10-21 | 2023-06-13 | 2023-04-25 | 316912 | 393636 | 386964
14 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 2023-07-17 | 2025-07-15 |  | 6732360 | 6252381 | 3274357
14 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-07-17 | 2025-07-15 |  | 484642 | 223439 | 209884
14 | P.S. 23 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-16 | 2024-09-17 | 2024-05-20 | 5190 | 2924 | 2924
14 | P.S. 23 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-05-20 | 2024-11-15 |  | 23355 | 23355 | 11695
14 | P.S. 31 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2019-05-13 | 2019-09-26 | 2019-10-01 | 137336 | 148157 | 148157
14 | P.S. 31 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2019-10-30 | 2020-04-20 | 2023-05-12 | 686680 | 363580 | 342826
14 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-05-26 | 2022-11-21 | 2022-09-26 | 203999 | 239838 | 206822
14 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2022-09-28 | 2023-06-12 | 2023-04-13 | 1020000 | 364971 | 364792
14 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-12-04 | 2027-04-06 |  | 22950000 | 21037150 | 3467592
14 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-12-04 | 2027-04-06 |  | 1428001 | 141361 | 130494
14 | K368 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 2022-10-17 | 2023-03-07 | 2023-03-20 | 44520 | 70446 | 58577
14 | K368 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2023-12-05 | 2024-10-29 |  | 652960 | 394270 | 115333
14 | K368 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | CM,F&E | In-Progress | 2023-12-05 | 2024-10-29 |  | 44520 | 66469 | 42698
14 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-07-14 | 2021-01-11 | 2020-09-17 | 4330 | 4718 | 4718
14 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-09-17 | 2021-03-15 | 2021-03-31 | 19483 | 18873 | 18873
14 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-26 | 2023-03-21 |  | 251117 | 225413 | 183519
14 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-26 | 2023-03-21 |  | 275558 | 267503 | 178580
14 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | Scope | Complete | 2020-02-04 | 2020-06-18 | 2021-06-08 | 5860 | 8707 | 8707
14 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | Design | Complete | 2021-06-11 | 2021-09-30 | 2021-11-17 | 26370 | 116972 | 90964
14 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | Construction | In-Progress | 2022-05-23 | 2023-02-16 |  | 339880 | 431435 | 219902
14 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | CM,F&E | In-Progress | 2022-05-23 | 2023-02-16 |  | 62995 | 96513 | 64815
14 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2020-08-13 | 2021-01-19 | 2020-10-16 | 79400 | 83494 | 83494
14 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2020-10-19 | 2021-03-24 | 2021-02-05 | 397000 | 334083 | 317342
14 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-05-16 | 2024-05-14 |  | 8932500 | 8239108 | 5012485
14 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-05-16 | 2024-05-14 |  | 555800 | 508311 | 503617
14 | J.H.S. 50 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 2023-01-10 | 2023-05-25 | 2023-06-14 | 26018 | 32023 | 32023
14 | J.H.S. 50 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 2023-06-23 | 2023-11-27 | 2023-12-05 | 130091 | 100824 | 88852
14 | P.S. 59 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2024-01-04 | 2024-05-20 | 2024-05-24 | 310813 | 97916 | 96324
14 | P.S. 59 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Design | In-Progress | 2024-06-20 | 2024-11-21 |  | 1476676 | 1476676 | 243068
14 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | Scope | Complete | 2018-06-25 | 2018-11-08 | 2018-12-18 | 14990 | 29962 | 29962
14 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | Design | Complete | 2018-12-18 | 2019-05-21 | 2021-05-14 | 74950 | 160986 | 147157
14 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | Construction | In-Progress | 2023-02-21 | 2024-02-20 |  | 1686375 | 1523840 | 452470
14 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | CM,F&E | In-Progress | 2023-02-21 | 2024-02-20 |  | 104930 | 254812 | 254159
14 | I.S. 71 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-30 | 2023-10-30 | 2023-10-31 | 18927 | 19535 | 18014
14 | I.S. 71 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-11-01 | 2024-04-01 | 2024-05-13 | 85170 | 72207 | 69272
14 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | Scope | Complete | 2019-06-28 | 2019-11-14 | 2019-12-06 | 50683 | 76515 | 74627
14 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | Design | Complete | 2020-02-28 | 2020-07-29 | 2022-03-01 | 251250 | 258761 | 258761
14 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | Construction | In-Progress | 2022-07-11 | 2024-01-01 |  | 5465528 | 4977368 | 4012010
14 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | CM,F&E | In-Progress | 2022-07-11 | 2024-01-01 |  | 371049 | 348881 | 344385
14 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2020-08-05 | 2021-01-08 | 2020-12-22 | 62300 | 93522 | 93522
14 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2020-12-22 | 2021-05-25 | 2021-07-08 | 311500 | 374669 | 360103
14 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-05-16 | 2024-05-14 |  | 7008751 | 6893027 | 6551439
14 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-05-16 | 2024-05-14 |  | 436100 | 595285 | 588509
14 | P.S. 84 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-03-09 | 2021-07-22 | 2021-11-18 | 76638 | 118049 | 116986
14 | P.S. 84 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2021-11-29 | 2022-05-17 | 2022-09-30 | 383191 | 290720 | 278115
14 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-10 | 2023-07-11 | 2023-03-20 | 4966 | 2058 | 2058
14 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-20 | 2023-09-13 | 2023-05-02 | 22347 | 8233 | 8233
14 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2024-01-11 | 2024-12-05 |  | 288028 | 260143 | 1810
14 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2024-01-11 | 2024-12-05 |  | 84793 | 62802 | 32245
14 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2020-01-09 | 2020-05-26 | 2021-09-14 | 12428 | 100898 | 100898
14 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2021-11-17 | 2022-04-21 | 2022-12-07 | 62138 | 169980 | 156340
14 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2023-09-11 | 2024-06-06 |  | 1398094 | 1294600 | 452622
14 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-09-11 | 2024-06-06 |  | 86993 | 197129 | 194259
14 | P.S. 110 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | In-Progress | 2024-05-24 | 2024-10-10 |  | 22452 | 46120 | 269
14 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-21 | 2023-07-20 | 2023-04-03 | 6424 | 2487 | 2487
14 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-04-03 | 2023-12-28 | 2023-05-02 | 28908 | 9947 | 9947
14 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2024-01-11 | 2024-12-05 |  | 372592 | 335725 | 3763
14 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2024-01-11 | 2024-12-05 |  | 94197 | 64201 | 29511
14 | P.S. 120 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-03-05 | 2022-11-22 | 2022-08-25 | 192109 | 351045 | 349531
14 | P.S. 120 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2022-09-21 | 2023-06-12 | 2023-11-14 | 960550 | 794303 | 737549
14 | J.H.S. 126 - BROOKLYN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 2023-06-28 | 2023-11-14 | 2023-12-15 | 54028 | 230630 | 203687
14 | J.H.S. 126 - BROOKLYN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 2023-12-19 | 2024-05-21 | 2024-05-09 | 267615 | 297835 | 264965
14 | P.S. 132 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-30 | 2024-11-29 | 2024-09-04 | 4333 | 992 | 992
14 | P.S. 132 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-09-04 | 2025-03-05 |  | 19497 | 19497 | 3969
14 | P.S. 147 - BROOKLYN | SCA CIP | ELECTRICAL SERVICE ROOM | Scope | Complete | 2019-05-30 | 2019-09-30 | 2020-02-05 | 10500 | 43113 | 43113
14 | P.S. 147 - BROOKLYN | SCA CIP | ELECTRICAL SERVICE ROOM | Design | Complete | 2020-02-06 | 2020-07-08 | 2021-10-27 | 52500 | 92379 | 91179
14 | P.S. 147 - BROOKLYN | SCA CIP | FLOOR REPLACEMENT | Scope | Complete | 2023-04-26 | 2023-09-27 | 2024-01-12 | 7115 | 17453 | 17453
14 | P.S. 147 - BROOKLYN | SCA CIP | FLOOR REPLACEMENT | Design | In-Progress | 2024-01-25 | 2024-06-10 |  | 32017 | 32017 | 9081
14 | P.S. 147 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-23 | 2024-11-21 | 2024-07-30 | 4171 | 1388 | 1388
14 | P.S. 147 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-30 | 2025-01-28 |  | 18769 | 18769 | 5554
14 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2021-02-24 | 2021-07-09 | 2021-07-13 | 150490 | 148286 | 148286
14 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2021-07-22 | 2022-01-11 | 2022-10-12 | 752450 | 702154 | 601028
14 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2023-11-15 | 2026-04-02 |  | 16930125 | 15522860 | 1651154
14 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-11-15 | 2026-04-02 |  | 1053430 | 418621 | 413508
14 | P.S. 157 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS | Scope | Complete | 2019-06-04 | 2019-10-03 | 2019-12-18 | 138929 | 156977 | 156961
14 | P.S. 157 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS | Design | Complete | 2020-01-14 | 2020-06-15 | 2021-03-30 | 694646 | 431559 | 420404
14 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-15 | 2023-10-16 | 2023-10-10 | 10583 | 19075 | 17554
14 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-12 | 2024-03-12 | 2024-04-29 | 47621 | 133465 | 65698
14 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-18 | 2025-10-22 |  | 613786 | 592957 | 7103
14 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-18 | 2025-10-22 |  | 113762 | 113209 | 14049
14 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-13 | 2023-07-12 | 2023-03-21 | 5508 | 1394 | 1394
14 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-21 | 2023-09-14 | 2023-05-02 | 24786 | 5577 | 5577
14 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-01 | 2024-09-25 |  | 319464 | 289149 | 204149
14 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-01 | 2024-09-25 |  | 81210 | 54708 | 43094
14 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Scope | Complete | 2020-08-12 | 2020-12-11 | 2021-02-18 | 35350 | 27177 | 12431
14 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Design | Complete | 2021-03-01 | 2021-08-06 | 2021-09-10 | 169952 | 162528 | 138852
14 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Construction | In-Progress | 2023-09-05 | 2024-09-03 |  | 3235677 | 3277117 | 1245134
14 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | CM,F&E | In-Progress | 2023-09-05 | 2024-09-03 |  | 298459 | 160306 | 155342
14 | I.S. 582 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-06-12 | 2024-11-14 |  | 105000 | 89558 | 3545
14 | P.S. 250 - BROOKLYN | SCA CIP | PARAPETS | Scope | Complete | 2023-12-19 | 2024-05-06 | 2024-04-22 | 3207 | 9797 | 5996
14 | P.S. 250 - BROOKLYN | SCA CIP | PARAPETS | Design | In-Progress | 2024-05-07 | 2024-10-08 |  | 12829 | 12829 | 7188
14 | P.S. 250 - BROOKLYN | SCA CIP RESOA | FY19 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Design | Complete | 2021-05-26 | 2021-10-01 | 2021-11-16 | 35239 | 50698 | 50698
14 | P.S. 250 - BROOKLYN | SCA CIP RESOA | FY19 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Construction | In-Progress | 2022-07-07 | 2023-05-02 |  | 516837 | 420912 | 360839
14 | P.S. 250 - BROOKLYN | SCA CIP RESOA | FY19 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | CM,F&E | In-Progress | 2022-07-07 | 2023-05-02 |  | 107875 | 131187 | 130110
14 | P.S. 257 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2023-02-07 | 2023-06-23 | 2023-07-31 | 58066 | 78795 | 67295
14 | P.S. 257 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | In-Progress | 2023-08-15 | 2024-02-21 |  | 283467 | 283467 | 98974
14 | P.S. 257 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2023-06-14 | 2023-12-13 | 2023-10-16 | 79440 | 96543 | 95930
14 | P.S. 257 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2023-10-20 | 2024-06-11 | 2024-04-05 | 397197 | 267755 | 264785
14 | P.S. 257 - BROOKLYN | SCA CIP | ANSUL/FIRE SUPPRESSION SYSTEM | Scope | Complete | 2024-09-05 | 2024-09-05 | 2024-09-05 | 22785 | 0 | 0
14 | P.S. 257 - BROOKLYN | SCA CIP | ANSUL/FIRE SUPPRESSION SYSTEM | Design | In-Progress | 2024-09-05 | 2025-02-10 |  | 106328 | 106328 | 0
14 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-08-28 | 2023-12-29 | 2023-08-30 | 4154 | 6008 | 6008
14 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-30 | 2024-02-29 | 2023-12-12 | 18693 | 24032 | 24032
14 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-05-09 | 2025-04-03 |  | 240932 | 214600 | 51720
14 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-05-09 | 2025-04-03 |  | 69649 | 50913 | 3524
14 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | Scope | Complete | 2022-06-09 | 2022-12-05 | 2022-09-28 | 155844 | 162964 | 126919
14 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | Design | Complete | 2022-10-19 | 2023-06-12 | 2023-04-04 | 775746 | 314872 | 314792
14 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | Construction | In-Progress | 2023-09-05 | 2025-09-03 |  | 17153786 | 15887872 | 6037364
14 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | CM,F&E | In-Progress | 2023-09-05 | 2025-09-03 |  | 1116963 | 295056 | 289006
14 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-09-27 | 2024-01-31 | 2023-10-10 | 4404 | 1263 | 1263
14 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-10-10 | 2024-04-08 | 2023-12-12 | 19818 | 5053 | 5053
14 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-05-09 | 2025-04-03 |  | 255432 | 228737 | 22577
14 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-05-09 | 2025-04-03 |  | 47343 | 29631 | 5453
14 | P.S. 297 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | Complete | 2024-05-08 | 2024-09-24 | 2024-09-13 | 54000 | 68172 | 15074
14 | P.S. 319 - BROOKLYN | SCA CIP | ROOFS / WINDOWS | Scope | Complete | 2019-08-09 | 2019-12-27 | 2020-03-13 | 33350 | 33064 | 33064
14 | P.S. 319 - BROOKLYN | SCA CIP | ROOFS / WINDOWS | Design | Complete | 2020-03-13 | 2020-08-12 | 2020-06-30 | 159981 | 167298 | 140636
14 | P.S. 319 - BROOKLYN | SCA CIP | ROOFS / WINDOWS | Construction | Complete | 2022-01-17 | 2023-07-10 | 2024-05-16 | 3013946 | 2979086 | 2736309
14 | P.S. 319 - BROOKLYN | SCA CIP | ROOFS / WINDOWS | CM,F&E | Complete | 2022-01-17 | 2023-07-10 | 2024-05-16 | 284228 | 597541 | 594482
14 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-06-04 | 2021-10-28 | 2022-01-26 | 113560 | 135065 | 135065
14 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2022-03-08 | 2022-08-22 | 2023-05-09 | 567800 | 431486 | 335384
14 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-09-05 | 2025-09-03 |  | 12775500 | 11674277 | 3677053
14 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-09-05 | 2025-09-03 |  | 796450 | 396674 | 385432
14 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-14 | 2023-07-13 | 2023-03-21 | 6092 | 1913 | 1913
14 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-21 | 2023-09-14 | 2023-05-02 | 27414 | 7651 | 7651
14 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-01 | 2024-09-25 |  | 353336 | 324341 | 154092
14 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-01 | 2024-09-25 |  | 170622 | 140484 | 86231
14 | WIILIAMSBURG PREP- BROOKLYN | SCA CIP | FIRE ALARM SYSTEM | Scope | Complete | 2021-07-22 | 2021-10-21 | 2022-10-04 | 21607 | 63822 | 63822
14 | WIILIAMSBURG PREP- BROOKLYN | SCA CIP | FIRE ALARM SYSTEM | Design | Complete | 2022-10-20 | 2023-04-26 | 2023-05-08 | 108034 | 159098 | 155868
14 | WIILIAMSBURG PREP- BROOKLYN | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 2021-12-21 |  |  | 425000 | 425000 | 401664
15 | P.S. 1 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2022-06-16 | 2022-11-01 | 2022-12-28 | 91123 | 141634 | 125354
15 | P.S. 1 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-12-28 | 2023-06-15 | 2023-06-15 | 455615 | 362699 | 312227
15 | P.S. 1 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-06-30 | 2022-11-16 | 2022-12-28 | 33712 | 48840 | 48840
15 | P.S. 1 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2022-12-29 | 2023-06-01 | 2023-06-15 | 164498 | 162269 | 133118
15 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2022-06-03 | 2022-09-15 | 2022-09-15 | 1333540 | 909819 | 907169
15 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 2022-09-16 | 2023-04-05 | 2023-04-28 | 6000930 | 3506239 | 1855029
15 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2023-09-11 | 2026-09-03 |  | 75678395 | 67054593 | 9063359
15 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2023-09-11 | 2026-09-03 |  | 10668320 | 4494008 | 677433
15 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2022-09-08 | 2022-09-08 | 2022-09-08 | 78880 | 64131 | 64131
15 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 2022-09-21 | 2023-02-14 | 2023-02-24 | 394400 | 194242 | 181509
15 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | Construction | In-Progress | 2023-03-06 | 2023-06-03 |  | 8874000 | 8319772 | 8310267
15 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2023-03-06 | 2023-06-03 |  | 552160 | 388062 | 302548
15 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2020-06-02 | 2020-11-30 | 2020-10-08 | 166640 | 300149 | 300149
15 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2020-10-16 | 2021-06-15 | 2021-04-23 | 833202 | 544558 | 543933
15 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2021-08-16 | 2023-08-15 |  | 18747001 | 17681728 | 16825995
15 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-08-16 | 2023-08-15 |  | 1166479 | 620968 | 613911
15 | P.S. 10 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-12 | 2024-05-13 | 2024-03-22 | 4439 | 179 | 179
15 | P.S. 10 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-22 | 2024-09-17 | 2024-07-16 | 19977 | 717 | 717
15 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2018-11-07 | 2019-11-06 | 2019-11-12 | 179240 | 149682 | 149681
15 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | Design | Complete | 2019-11-13 | 2020-05-01 | 2021-04-02 | 896202 | 736770 | 715975
15 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2021-08-16 | 2023-08-15 |  | 20164576 | 20755393 | 12782684
15 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2021-08-16 | 2023-08-15 |  | 1254685 | 911532 | 794193
15 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-13 | 2023-11-13 | 2023-08-02 | 3120 | 2241 | 2241
15 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-02 | 2024-01-31 | 2023-11-08 | 14040 | 8965 | 8965
15 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-06-12 | 2025-05-07 |  | 180960 | 164231 | 2681
15 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-06-12 | 2025-05-07 |  | 33540 | 22729 | 5502
15 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | Scope | Complete | 2018-10-16 | 2019-03-06 | 2019-01-22 | 29395 | 24677 | 24677
15 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | Design | Complete | 2019-01-30 | 2019-07-01 | 2020-05-06 | 132281 | 188960 | 187999
15 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | Construction | In-Progress | 2021-07-19 | 2022-10-11 |  | 1704952 | 1445928 | 840128
15 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | CM,F&E | In-Progress | 2021-07-19 | 2022-10-11 |  | 316004 | 160428 | 159467
15 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-18 | 2023-11-16 | 2023-08-02 | 3880 | 1908 | 1908
15 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-02 | 2024-01-31 | 2023-11-08 | 17460 | 7633 | 7633
15 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-06-12 | 2025-05-07 |  | 225040 | 199550 | 0
15 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-06-12 | 2025-05-07 |  | 41710 | 25775 | 4444
15 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2018-10-18 | 2019-04-18 | 2019-09-11 | 10680 | 18737 | 18737
15 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2019-09-25 | 2020-03-25 | 2020-04-13 | 48060 | 51290 | 51290
15 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2021-07-23 | 2022-07-22 |  | 619440 | 553810 | 326737
15 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2021-07-23 | 2022-07-22 |  | 114810 | 81199 | 68352
15 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-06-03 | 2022-11-29 | 2022-09-26 | 150072 | 116083 | 105480
15 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2022-09-30 | 2023-06-12 | 2023-04-14 | 750365 | 362850 | 356893
15 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-11-03 | 2025-11-01 |  | 16883213 | 15485554 | 3245300
15 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-11-03 | 2025-11-01 |  | 1057830 | 172991 | 141275
15 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2022-05-12 | 2022-09-27 | 2022-11-14 | 158750 | 195865 | 195865
15 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2022-12-07 | 2023-05-25 | 2023-05-12 | 793750 | 507101 | 452546
15 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 2024-08-05 | 2026-08-04 |  | 17859375 | 15981401 | 98895
15 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2024-08-05 | 2026-08-04 |  | 1111250 | 60342 | 60342
15 | P.S. 38 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-03-15 | 2024-07-16 | 2024-04-01 | 4691 | 502 | 502
15 | P.S. 38 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-01 | 2024-09-25 | 2024-07-16 | 21109 | 2008 | 2008
15 | P.S. 39 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Design | In-Progress | 2024-05-09 | 2024-11-13 |  | 18000 | 16691 | 5238
15 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-09-14 | 2023-01-18 | 2022-12-21 | 4120 | 2795 | 2795
15 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-21 | 2023-06-20 | 2023-02-22 | 18540 | 11183 | 11183
15 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 238960 | 215194 | 188773
15 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 119423 | 106877 | 105616
15 | P.S. 58 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-01-18 | 2022-04-22 | 2022-04-08 | 64281 | 94991 | 94991
15 | P.S. 58 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-03-31 | 2024-02-23 |  | 942777 | 891455 | 77575
15 | P.S. 58 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-03-31 | 2024-02-23 |  | 64281 | 84935 | 26368
15 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | Scope | Complete | 2021-06-14 | 2021-12-13 | 2021-10-20 | 232199 | 144500 | 144500
15 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | Design | Complete | 2021-11-03 | 2022-06-30 | 2022-04-22 | 1158195 | 465060 | 465060
15 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | Construction | In-Progress | 2022-07-18 | 2024-10-04 |  | 25817295 | 23317998 | 12521200
15 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | CM,F&E | In-Progress | 2022-07-18 | 2024-10-04 |  | 1646382 | 496576 | 471955
15 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | Scope | Complete | 2021-12-23 | 2022-04-22 | 2022-09-12 | 94564 | 85043 | 79908
15 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | Design | Complete | 2022-10-13 | 2023-04-13 | 2023-04-25 | 466664 | 328756 | 300490
15 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | Construction | In-Progress | 2024-09-09 | 2026-09-08 |  | 9967662 | 9266433 | 210200
15 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | CM,F&E | In-Progress | 2024-09-09 | 2026-09-08 |  | 708094 | 64668 | 51348
15 | P.S. 107 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-09-14 | 2024-02-02 | 2024-05-06 | 29520 | 44266 | 42236
15 | P.S. 107 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2023-09-14 | 2023-12-18 | 2024-02-07 | 465 | 465 | 465
15 | P.S. 107 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2024-02-09 | 2024-06-12 | 2024-05-06 | 1983 | 1983 | 1983
15 | P.S. 154 - BROOKLYN | SCA CIP | ROOFS | Scope | Complete | 2023-12-19 | 2024-05-06 | 2024-06-25 | 17385 | 38950 | 5475
15 | P.S. 154 - BROOKLYN | SCA CIP | ROOFS | Design | In-Progress | 2024-07-01 | 2024-12-03 |  | 86924 | 86924 | 4228
15 | P.S. 169 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2018-07-23 | 2018-12-07 | 2018-11-08 | 87734 | 164529 | 138929
15 | P.S. 169 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | In-Progress | 2018-11-28 | 2019-05-16 |  | 438667 | 438667 | 187722
15 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 2019-02-14 | 2019-07-01 | 2019-08-26 | 147899 | 186940 | 186940
15 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 2020-01-15 | 2020-06-16 | 2022-04-29 | 739501 | 488184 | 478997
15 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | Construction | In-Progress | 2022-09-12 | 2024-09-10 |  | 16638778 | 14996848 | 7957124
15 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | CM,F&E | In-Progress | 2022-09-12 | 2024-09-10 |  | 1035301 | 444828 | 438725
15 | P.S. 169 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2021-09-10 | 2022-01-31 |  | 45000 | 48381 | 28074
15 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | Scope | Complete | 2019-03-05 | 2019-07-18 | 2020-10-02 | 164813 | 255268 | 255268
15 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | Design | Complete | 2020-12-10 | 2021-05-13 | 2022-04-21 | 816891 | 633471 | 531136
15 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | Construction | In-Progress | 2022-09-19 | 2025-03-06 |  | 17759605 | 16202393 | 12353883
15 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | CM,F&E | In-Progress | 2022-09-19 | 2025-03-06 |  | 1208711 | 520461 | 505247
15 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2018-10-11 | 2019-03-01 | 2019-04-19 | 127484 | 136740 | 136740
15 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2019-04-19 | 2019-09-18 | 2019-05-15 | 637422 | 595541 | 546011
15 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 2021-08-16 | 2023-08-15 |  | 14342004 | 13455093 | 11472624
15 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 2021-08-16 | 2023-08-15 |  | 892391 | 659039 | 639707
15 | K721 SPED - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2024-01-05 | 2024-07-18 | 2024-07-12 | 15037 | 29264 | 5499
15 | K721 SPED - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | In-Progress | 2024-07-24 | 2024-12-26 |  | 75185 | 75185 | 6882
15 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | Scope | Complete | 2022-06-17 | 2023-04-25 | 2023-04-28 | 27880 | 39677 | 33678
15 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | Design | Complete | 2023-05-05 | 2023-09-08 | 2023-05-12 | 136639 | 102774 | 72249
15 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | Construction | In-Progress | 2024-01-04 | 2025-01-02 |  | 2835771 | 2570714 | 451267
15 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | CM,F&E | In-Progress | 2024-01-04 | 2025-01-02 |  | 215842 | 99309 | 91809
15 | P.S. 261 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / PLAYGROUND REDEVELOPMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2018-09-18 | 2023-04-25 | 2023-04-28 | 58991 | 111588 | 105723
15 | P.S. 261 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / PLAYGROUND REDEVELOPMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-05-01 | 2023-09-01 | 2024-02-07 | 294389 | 456098 | 401969
15 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | Scope | Complete | 2016-03-16 | 2016-03-16 | 2016-03-16 | 231000 | 718501 | 718501
15 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | Design | Complete | 2016-03-17 | 2016-08-29 | 2017-04-19 | 924000 | 2596298 | 2556089
15 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | Construction | In-Progress | 2017-08-07 | 2019-08-06 |  | 17325000 | 19796107 | 18240690
15 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | CM,F&E | In-Progress | 2017-08-07 | 2019-08-06 |  | 1584858 | 2334702 | 2028228
15 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Scope | Complete | 2023-02-06 | 2023-04-17 | 2023-04-10 | 202000 | 189062 | 189062
15 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Design | Complete | 2023-04-11 | 2023-09-19 | 2024-02-16 | 909000 | 490915 | 249171
15 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 2024-08-12 | 2026-09-03 |  | 11463500 | 10393614 | 233843
15 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 2024-08-12 | 2026-09-03 |  | 1616000 | 746707 | 137634
15 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2021-06-14 | 2021-12-13 | 2021-10-28 | 122827 | 240025 | 217028
15 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2021-12-01 | 2022-06-30 | 2022-04-19 | 614136 | 519175 | 516369
15 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2022-07-18 | 2025-01-02 |  | 13818037 | 12556279 | 11552592
15 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2022-07-18 | 2025-01-02 |  | 859789 | 502779 | 502229
15 | P.S. 321 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-10-18 | 2023-03-08 | 2023-02-14 | 46341 | 62948 | 59875
15 | P.S. 338 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE CARTS | F&E | In-Progress | 2024-08-19 |  |  | 150000 | 150000 | 14907
15 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Scope | Complete | 2021-01-21 | 2021-05-13 | 2021-05-11 | 423340 | 393953 | 393953
15 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Design | Complete | 2021-05-12 | 2021-11-12 | 2022-04-11 | 1905030 | 1249045 | 829867
15 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 2022-07-11 | 2024-09-03 |  | 24024545 | 24477814 | 21557346
15 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 2022-07-11 | 2024-09-03 |  | 3386720 | 2942947 | 2485789
15 | COY L. COX SCHOOL | SCA CIP | WINDOWS | Scope | Complete | 2021-05-21 | 2021-10-06 | 2021-08-18 | 37780 | 71336 | 71336
15 | COY L. COX SCHOOL | SCA CIP | WINDOWS | Design | Complete | 2021-09-15 | 2022-02-18 | 2022-01-12 | 188900 | 285346 | 285346
15 | COY L. COX SCHOOL | SCA CIP | WINDOWS | Construction | In-Progress | 2022-09-12 | 2024-03-04 |  | 4250250 | 3948375 | 658439
15 | COY L. COX SCHOOL | SCA CIP | WINDOWS | CM,F&E | In-Progress | 2022-09-12 | 2024-03-04 |  | 264460 | 114241 | 114044
15 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-16 | 2023-04-19 | 2022-12-27 | 4140 | 3836 | 3836
15 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-27 | 2023-06-23 | 2023-02-22 | 18630 | 15347 | 15347
15 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 240120 | 217574 | 183114
15 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 152433 | 138771 | 82282
15 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | Scope | Complete | 2021-05-28 | 2021-07-16 | 2021-07-15 | 283140 | 233231 | 233231
15 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | Design | Complete | 2021-07-16 | 2021-10-07 | 2022-06-07 | 1274130 | 1495093 | 1179675
15 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | Construction | In-Progress | 2022-08-15 | 2023-09-03 |  | 16068195 | 14504545 | 13776493
15 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | CM,F&E | In-Progress | 2022-08-15 | 2023-09-03 |  | 2265120 | 750321 | 1511241
15 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | Scope | Complete | 2018-12-21 | 2019-05-09 | 2019-09-24 | 29978 | 74130 | 74097
15 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | Design | Complete | 2019-10-28 | 2020-04-01 | 2020-05-18 | 149889 | 229906 | 149710
15 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | Construction | In-Progress | 2021-05-11 | 2022-11-01 |  | 3372509 | 2406900 | 1819225
15 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | CM,F&E | In-Progress | 2021-05-11 | 2022-11-01 |  | 209845 | 250437 | 247075
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-10-23 | 2021-02-26 | 2021-03-03 | 5800 | 5567 | 5567
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-03-03 | 2021-08-25 | 2021-07-14 | 26100 | 22269 | 22269
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-05 | 2023-02-28 |  | 336400 | 297211 | 250533
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-05 | 2023-02-28 |  | 352096 | 337752 | 235344
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2017-05-18 | 2017-10-19 | 2017-07-18 | 109022 | 165859 | 165859
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2017-07-20 | 2017-12-21 | 2018-01-19 | 426177 | 510233 | 491812
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2018-06-11 | 2020-03-01 |  | 7101271 | 6895054 | 5402010
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2018-06-11 | 2020-03-01 |  | 637617 | 950508 | 930867
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | Scope | Complete | 2021-01-26 | 2021-07-12 | 2021-11-03 | 129522 | 250049 | 241536
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | Design | Complete | 2021-11-10 | 2022-04-15 | 2022-05-11 | 639043 | 512647 | 465474
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | Construction | In-Progress | 2022-09-12 | 2024-09-10 |  | 13637703 | 12627103 | 6299713
15 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | CM,F&E | In-Progress | 2022-09-12 | 2024-09-10 |  | 970878 | 274649 | 246057
15 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2021-05-06 | 2021-09-30 | 2021-11-16 | 2016007 | 1150696 | 1148923
15 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | In-Progress | 2021-11-17 | 2022-05-05 |  | 9072032 | 9072032 | 1690205
15 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2022-09-13 | 2022-09-13 | 2022-09-13 | 68074 | 60578 | 60264
15 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 2022-09-13 | 2023-04-18 | 2023-07-14 | 340372 | 152065 | 134641
15 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2022-07-01 | 2022-08-29 | 2022-07-01 | 105550 | 60915 | 60915
15 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 2022-07-01 | 2022-11-30 | 2022-12-19 | 527750 | 119480 | 119480
15 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-06-28 | 2022-11-14 | 2022-11-16 | 100490 | 99568 | 99568
15 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2022-12-09 | 2023-05-12 | 2023-05-12 | 496499 | 311641 | 284259
15 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2022-03-22 | 2022-07-20 | 2022-03-28 | 4700 | 3389 | 3389
15 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2022-03-28 | 2022-09-20 | 2022-07-19 | 21150 | 13556 | 13556
15 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2023-02-08 | 2024-01-03 |  | 272600 | 243589 | 174214
15 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2023-02-08 | 2024-01-03 |  | 247639 | 234041 | 116653
15 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-10-26 | 2023-03-01 | 2022-12-23 | 4140 | 5027 | 5027
15 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-23 | 2023-06-22 | 2023-02-22 | 18630 | 20109 | 20109
15 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 240120 | 213785 | 180085
15 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 70527 | 54852 | 51621
15 | K372 SPED - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 2023-03-29 | 2024-04-03 | 2024-02-05 | 13581 | 47434 | 46376
15 | K372 SPED - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 2024-02-05 | 2024-07-23 | 2024-03-14 | 61114 | 42957 | 41876
15 | K372 SPED - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2021-11-15 | 2022-04-04 | 2022-10-31 | 49603 | 73118 | 73118
15 | K372 SPED - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-06-16 | 2024-07-19 |  | 727510 | 545573 | 296970
15 | K372 SPED - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-06-16 | 2024-07-19 |  | 49603 | 77942 | 51026
15 | P.S. 295 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 2020-12-17 | 2021-04-16 | 2021-06-29 | 21629 | 53170 | 53170
15 | P.S. 295 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 2021-06-30 | 2021-12-01 | 2021-11-05 | 108145 | 101835 | 92097
15 | I.S. 443 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2023-11-27 | 2024-04-12 | 2024-06-05 | 96022 | 109001 | 44664
15 | I.S. 443 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | In-Progress | 2024-06-14 | 2024-11-18 |  | 465518 | 465518 | 4459
15 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | Scope | Complete | 2012-11-28 | 2014-04-23 | 2014-06-23 | 176917 | 289253 | 254282
15 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | Design | Complete | 2014-12-10 | 2015-05-13 | 2015-08-24 | 672202 | 1193170 | 1121040
15 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | Construction | In-Progress | 2017-07-17 | 2019-01-07 |  | 10351810 | 10572103 | 9178519
15 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | CM,F&E | In-Progress | 2017-07-17 | 2019-01-07 |  | 1156748 | 1411309 | 1368090
15 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-05-22 | 2023-09-21 | 2023-06-07 | 4537 | 587 | 587
15 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-07 | 2023-12-05 | 2023-08-30 | 20417 | 2346 | 2346
15 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-23 | 2025-01-17 |  | 263158 | 249438 | 8228
15 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-23 | 2025-01-17 |  | 48775 | 29991 | 7839
15 | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Scope | Complete | 2021-03-02 | 2022-08-03 | 2023-02-22 | 23316 | 43607 | 43607
15 | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Design | Complete | 2023-02-28 | 2023-06-30 | 2023-03-31 | 115467 | 178296 | 115172
15 | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Construction | In-Progress | 2023-11-13 | 2025-05-05 |  | 2501588 | 2830835 | 1273118
15 | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | CM,F&E | In-Progress | 2023-11-13 | 2025-05-05 |  | 171572 | 249807 | 124247
16 | P.S. 5 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | Scope | Complete | 2020-09-17 | 2021-02-23 | 2020-12-09 | 167950 | 160789 | 146789
16 | P.S. 5 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | Design | Complete | 2020-12-10 | 2021-08-31 | 2021-08-09 | 839750 | 654065 | 595785
16 | P.S. 5 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | Construction | In-Progress | 2022-08-08 | 2024-08-06 |  | 18894375 | 17213876 | 14734456
16 | P.S. 5 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2022-08-08 | 2024-08-06 |  | 1175650 | 631827 | 625163
16 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-06-14 | 2022-10-13 | 2022-06-21 | 4999 | 6697 | 6697
16 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-21 | 2022-12-16 | 2022-12-07 | 22495 | 26788 | 26788
16 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-05-31 | 2024-04-24 |  | 289930 | 258751 | 217021
16 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-05-31 | 2024-04-24 |  | 180882 | 158412 | 96291
16 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2019-05-22 | 2019-10-07 | 2021-04-20 | 113330 | 123282 | 123282
16 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2021-07-21 | 2022-01-10 | 2022-10-31 | 566650 | 294218 | 250833
16 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-09-11 | 2025-07-01 |  | 12749625 | 11676666 | 4716043
16 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-09-11 | 2025-07-01 |  | 793310 | 358880 | 355552
16 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2020-01-31 | 2020-07-01 | 2020-04-30 | 68800 | 100167 | 100167
16 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2020-05-04 | 2020-10-02 | 2020-07-22 | 344000 | 404289 | 376518
16 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-02-07 | 2024-02-06 |  | 7740000 | 7494404 | 6457333
16 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-02-07 | 2024-02-06 |  | 481600 | 771393 | 756020
16 | P.S. 21 - BROOKLYN | SCA CIP | EXTERIOR MASONRY PERM FIX @ K021 / PARAPETS / ROOFS | Scope | Complete | 2024-05-22 | 2024-10-08 | 2024-09-20 | 127493 | 16591 | 16591
16 | P.S. 21 - BROOKLYN | SCA CIP | EXTERIOR MASONRY PERM FIX @ K021 / PARAPETS / ROOFS | Design | In-Progress | 2024-09-27 | 2025-03-05 |  | 614095 | 614095 | 4617
16 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-05-28 | 2020-09-25 | 2020-07-02 | 3070 | 7669 | 7669
16 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-02 | 2020-12-30 | 2021-03-30 | 13817 | 30679 | 30679
16 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-26 | 2023-03-21 |  | 178083 | 166715 | 132760
16 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-26 | 2023-03-21 |  | 218674 | 228954 | 141343
16 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-05-29 | 2020-09-28 | 2020-07-02 | 5300 | 5549 | 5549
16 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-02 | 2020-12-30 | 2021-03-31 | 23850 | 22197 | 22197
16 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-05 | 2023-02-28 |  | 307394 | 271523 | 219110
16 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-05 | 2023-02-28 |  | 244767 | 233641 | 155771
16 | P.S. 40 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-01 | 2024-10-30 | 2024-07-02 | 4457 | 979 | 979
16 | P.S. 40 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-02 | 2024-12-30 |  | 20058 | 20058 | 3915
16 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PAVED AREAS- CONCRETE | Scope | Complete | 2022-07-06 | 2022-11-21 | 2023-05-26 | 87871 | 128464 | 128464
16 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PAVED AREAS- CONCRETE | Design | Complete | 2023-07-26 | 2023-12-28 | 2024-02-13 | 428097 | 297610 | 283429
16 | P.S. 81 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-06-30 | 2022-11-16 | 2023-08-29 | 52171 | 124908 | 111939
16 | P.S. 81 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2023-09-18 | 2024-02-22 | 2024-02-15 | 258625 | 65782 | 35588
16 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2019-07-30 | 2019-12-16 | 2019-11-14 | 57772 | 106673 | 106673
16 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2019-12-02 | 2020-05-04 | 2021-05-11 | 285216 | 440733 | 427828
16 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2021-09-20 | 2023-12-08 |  | 6102371 | 7199125 | 6576060
16 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-09-20 | 2023-12-08 |  | 431713 | 764209 | 759690
16 | P.S. 243 - BROOKLYN | SCA CIP | TERRACOTTA PANEL REPLACEMENT | Scope | Complete | 2023-08-29 | 2024-01-18 | 2023-11-03 | 11067 | 17082 | 17082
16 | P.S. 243 - BROOKLYN | SCA CIP | TERRACOTTA PANEL REPLACEMENT | Design | Complete | 2023-11-15 | 2024-04-18 | 2024-03-26 | 55335 | 59284 | 48206
16 | P.S. 243 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-06-18 | 2024-10-18 | 2024-06-24 | 4416 | 746 | 746
16 | P.S. 243 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-06-24 | 2024-12-19 |  | 19871 | 19871 | 2985
16 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2021-04-06 | 2021-09-03 | 2021-06-21 | 89280 | 115764 | 115764
16 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2021-06-22 | 2021-11-23 | 2021-11-10 | 446400 | 535274 | 493194
16 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2022-07-05 | 2024-07-03 |  | 10044000 | 9522225 | 8450311
16 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2022-07-05 | 2024-07-03 |  | 624960 | 737895 | 737022
16 | P.S. 262 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-04-21 | 2023-09-07 | 2024-05-21 | 92168 | 74585 | 67647
16 | P.S. 262 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-12-28 | 2024-05-01 | 2024-05-21 | 952 | 9521 | 9521
16 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2019-07-17 | 2019-12-03 | 2022-08-08 | 147804 | 142251 | 142251
16 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-09-16 | 2023-03-24 | 2023-05-09 | 730453 | 500757 | 434193
16 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2023-09-18 | 2025-09-06 |  | 15694471 | 14490705 | 2935869
16 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-09-18 | 2025-09-06 |  | 1098847 | 308625 | 297942
16 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-06-14 | 2022-10-13 | 2022-06-22 | 4721 | 7425 | 7425
16 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-22 | 2022-12-19 | 2022-12-19 | 21245 | 32295 | 32295
16 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-05-31 | 2024-04-24 |  | 273824 | 241418 | 207093
16 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-05-31 | 2024-04-24 |  | 167085 | 156002 | 98872
16 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 2022-11-01 | 2023-02-03 | 2023-05-15 | 25491 | 98022 | 97422
16 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | Design | Complete | 2023-05-30 | 2023-10-16 | 2024-02-05 | 127455 | 257076 | 200644
16 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | Construction | In-Progress | 2024-09-16 | 2026-02-15 |  | 2867739 | 2658048 | 17211
16 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2024-09-16 | 2026-02-15 |  | 178437 | 88250 | 33455
16 | P.S. 308 - BROOKLYN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2024-01-05 | 2024-04-05 | 2024-06-05 | 36006 | 28486 | 28486
16 | P.S. 308 - BROOKLYN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEMS | Design | In-Progress | 2024-06-17 | 2024-12-20 |  | 168028 | 168028 | 7381
16 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2020-01-31 | 2020-07-01 | 2020-04-07 | 69310 | 76960 | 76960
16 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2020-04-08 | 2020-09-08 | 2020-08-12 | 346550 | 351398 | 324598
16 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2023-08-10 | 2025-08-08 |  | 7797375 | 7293302 | 4539134
16 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2023-08-10 | 2025-08-08 |  | 485170 | 219480 | 218192
16 | P.S. 309 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS | Scope | In-Progress | 2024-05-14 | 2024-09-30 |  | 49427 | 51995 | 3721
16 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | Scope | Complete | 2022-04-21 | 2022-08-05 | 2022-09-13 | 21510 | 30835 | 30835
16 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | Design | Complete | 2022-09-28 | 2023-03-06 | 2023-03-03 | 107550 | 136159 | 112065
16 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | Construction | In-Progress | 2023-10-04 | 2024-10-02 |  | 2419875 | 2205115 | 822917
16 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 2023-10-04 | 2024-10-02 |  | 150570 | 117187 | 115913
16 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-26 | 2023-10-26 | 2023-10-25 | 12302 | 18742 | 17221
16 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-26 | 2024-03-26 | 2024-04-10 | 55361 | 78276 | 63091
16 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-09-12 | 2025-10-16 |  | 713543 | 644356 | 8059
16 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-09-12 | 2025-10-16 |  | 132251 | 89271 | 10664
16 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2020-02-25 | 2020-07-09 | 2021-09-21 | 28730 | 36041 | 30294
16 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2021-11-10 | 2022-04-15 | 2022-05-04 | 143650 | 159924 | 159924
16 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2022-09-12 | 2024-03-04 |  | 3232125 | 2991567 | 2837558
16 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-09-12 | 2024-03-04 |  | 203546 | 453418 | 434993
16 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | GYM UPGRADE | Scope | Complete | 2023-01-25 | 2023-05-25 | 2023-05-24 | 32796 | 39707 | 39707
16 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | GYM UPGRADE | Design | Complete | 2023-07-10 | 2023-11-24 | 2024-02-13 | 163980 | 125662 | 111302
16 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM UPGRADE | Scope | Complete | 2023-01-25 | 2023-04-25 | 2023-06-28 | 5668 | 16383 | 658
16 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM UPGRADE | Design | Complete | 2023-07-10 | 2023-11-09 | 2024-02-13 | 25507 | 2632 | 2632
16 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2022-03-24 | 2022-07-22 | 2022-04-01 | 3510 | 2560 | 2560
16 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2022-04-01 | 2022-09-26 | 2022-07-19 | 15795 | 10239 | 10239
16 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2023-02-08 | 2024-01-03 |  | 203580 | 182984 | 147127
16 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2023-02-08 | 2024-01-03 |  | 168148 | 158976 | 111414
17 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2018-10-16 | 2019-03-06 | 2019-02-20 | 133778 | 215574 | 134593
17 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2019-02-20 | 2019-07-22 | 2020-06-30 | 660659 | 813498 | 691674
17 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2021-07-14 | 2023-10-01 |  | 14153170 | 14119377 | 12557690
17 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2021-07-14 | 2023-10-01 |  | 998143 | 1093210 | 1068942
17 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-05-27 | 2020-09-24 | 2020-06-19 | 2400 | 3747 | 3747
17 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-06-19 | 2020-12-16 | 2020-12-01 | 10800 | 14989 | 14989
17 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-07-07 | 2023-05-02 |  | 139200 | 122857 | 98061
17 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-07-07 | 2023-05-02 |  | 226903 | 230806 | 132872
17 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | Scope | Complete | 2022-10-12 | 2023-03-02 | 2023-01-20 | 22508 | 72272 | 71809
17 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | Design | Complete | 2023-02-01 | 2023-07-05 | 2023-05-09 | 112539 | 186794 | 165466
17 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | Construction | In-Progress | 2023-09-18 | 2025-03-10 |  | 2532134 | 2288025 | 1241562
17 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | CM,F&E | In-Progress | 2023-09-18 | 2025-03-10 |  | 157850 | 197437 | 194495
17 | P.S. 6 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-07-07 | 2023-12-08 | 2023-11-09 | 33000 | 56924 | 49172
17 | P.S. 6 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2024-04-01 | 2025-02-24 |  | 484000 | 334700 | 167147
17 | P.S. 6 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2024-04-01 | 2025-02-24 |  | 33000 | 32696 | 14231
17 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | Scope | Complete | 2019-07-18 | 2019-12-04 | 2019-12-24 | 53034 | 41789 | 41789
17 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | Design | Complete | 2019-12-24 | 2020-05-27 | 2020-06-30 | 265169 | 228772 | 228733
17 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | Construction | In-Progress | 2022-10-21 | 2024-04-12 |  | 5966302 | 6335137 | 6022440
17 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | CM,F&E | In-Progress | 2022-10-21 | 2024-04-12 |  | 371237 | 278969 | 272433
17 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-15 | 2023-10-16 | 2023-10-12 | 11100 | 18411 | 18411
17 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-12 | 2024-03-12 | 2024-03-19 | 49950 | 64077 | 46999
17 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-08-06 | 2025-09-09 |  | 643800 | 571712 | 4755
17 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-08-06 | 2025-09-09 |  | 119325 | 87966 | 16069
17 | I.S. 61 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / DOORS / SIDEWALK ELEVATOR / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / ELECTRICAL UPGRADE / HOT WATER HEATERS / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2018-10-19 | 2019-03-11 | 2019-01-31 | 762293 | 289920 | 279682
17 | I.S. 61 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / DOORS / SIDEWALK ELEVATOR / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / ELECTRICAL UPGRADE / HOT WATER HEATERS / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2019-02-06 | 2019-07-09 | 2024-05-08 | 3788468 | 3962337 | 2308102
31 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | Construction | In-Progress | 2022-07-18 | 2023-07-17 |  | 3472784 | 4257287 | 3806804
17 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 2021-12-01 | 2022-04-05 | 2023-01-19 | 139292 | 212612 | 210026
17 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 2023-01-20 | 2023-06-22 | 2023-05-12 | 691081 | 504817 | 429334
17 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 2023-09-18 | 2026-02-03 |  | 15083717 | 13773738 | 3370839
17 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 2023-09-18 | 2026-02-03 |  | 1015426 | 301236 | 294849
17 | P.S. 91 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-30 | 2024-05-29 | 2024-04-02 | 4403 | 4445 | 4445
17 | P.S. 91 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-02 | 2024-09-26 | 2024-09-25 | 19814 | 17780 | 17780
17 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2021-02-10 | 2021-07-20 | 2022-09-30 | 2062074 | 1786728 | 1757479
17 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | In-Progress | 2022-10-03 | 2022-03-08 |  | 8248296 | 8248296 | 1758799
17 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2021-02-08 | 2021-03-05 | 2021-03-05 | 18590 | 69518 | 69518
17 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 2021-03-08 | 2021-05-21 | 2022-07-21 | 92950 | 561279 | 313379
17 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Construction | In-Progress | 2022-10-31 | 2022-12-29 |  | 2091375 | 3023100 | 2661616
17 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2022-10-31 | 2022-12-29 |  | 130130 | 689377 | 394525
17 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2018-11-29 | 2019-04-17 | 2019-08-26 | 86270 | 119282 | 119232
17 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2019-08-28 | 2020-02-03 | 2020-04-28 | 422009 | 384671 | 368484
17 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2022-10-17 | 2024-07-07 |  | 8687347 | 8626321 | 7176910
17 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2022-10-17 | 2024-07-07 |  | 673931 | 358196 | 356856
17 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2021-06-10 | 2021-12-09 | 2021-10-22 | 170674 | 208878 | 208878
17 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2021-11-03 | 2022-06-30 | 2022-04-29 | 848576 | 448265 | 448265
17 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 2022-08-11 | 2024-08-09 |  | 18678278 | 17127742 | 14504747
17 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 2022-08-11 | 2024-08-09 |  | 1231358 | 462264 | 451874
17 | NEW BRIDGES | SCA CIP | COVID VENTILATION | Scope | Complete | 2020-08-28 | 2020-12-28 | 2021-01-25 | 50600 | 86110 | 86110
17 | NEW BRIDGES | SCA CIP | COVID VENTILATION | Design | Complete | 2021-02-03 | 2021-07-09 | 2021-12-22 | 253000 | 439906 | 313844
17 | NEW BRIDGES | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2022-07-05 | 2023-07-04 |  | 5692500 | 5828030 | 3000706
17 | NEW BRIDGES | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2022-07-05 | 2023-07-04 |  | 354200 | 648755 | 539473
17 | NEW BRIDGES | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 2024-06-04 | 2024-11-05 |  | 30000 | 12427 | 11986
17 | NEW BRIDGES | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | In-Progress | 2024-07-31 | 2024-12-02 |  | 3438 | 623 | 623
17 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 2021-03-11 | 2021-07-26 | 2021-11-19 | 84670 | 153567 | 153567
17 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 2021-12-22 | 2022-05-25 | 2022-05-11 | 423350 | 484818 | 484818
17 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 2022-11-14 | 2024-08-04 |  | 9525375 | 8917824 | 7623275
17 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 2022-11-14 | 2024-08-04 |  | 593843 | 448770 | 447686
17 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-05-20 | 2020-09-18 | 2020-06-19 | 3720 | 4446 | 4446
17 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-06-19 | 2020-12-16 | 2020-11-25 | 16740 | 17785 | 17785
17 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-07-07 | 2023-05-02 |  | 215760 | 192261 | 167993
17 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-07-07 | 2023-05-02 |  | 200835 | 198016 | 106326
17 | P.S. 191 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM | Scope | Complete | 2023-05-31 | 2023-11-29 | 2023-11-17 | 291793 | 156000 | 152161
17 | P.S. 191 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM | Design | Complete | 2023-11-22 | 2024-06-28 | 2024-05-06 | 1454172 | 570680 | 515301
17 | P.S. 191 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-02-14 | 2024-06-13 | 2024-04-19 | 4068 | 3631 | 3631
17 | P.S. 191 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-19 | 2024-10-16 | 2024-09-25 | 18305 | 14524 | 14524
17 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 2023-06-09 | 2023-12-08 | 2023-10-06 | 186305 | 235893 | 235620
17 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Design | Complete | 2023-10-20 | 2024-06-11 | 2024-04-19 | 919057 | 401967 | 399048
17 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 2024-07-22 | 2027-01-07 |  | 19600625 | 17727968 | 89825
17 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 2024-07-22 | 2027-01-07 |  | 1397612 | 110003 | 109392
17 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-05 | 2023-04-06 | 2022-12-09 | 4880 | 6355 | 6355
17 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-09 | 2023-06-07 | 2023-03-08 | 21960 | 25417 | 25417
17 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-04-29 |  | 283040 | 255930 | 146886
17 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-04-29 |  | 169567 | 155321 | 91578
17 | P.S. 221 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-07-06 | 2022-11-21 | 2023-08-18 | 55897 | 131961 | 128164
17 | P.S. 221 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2023-09-12 | 2024-02-15 | 2024-03-07 | 269329 | 187712 | 166234
17 | P.S. 221 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-31 | 2024-05-30 | 2024-04-03 | 3931 | 0 | 0
17 | P.S. 221 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-03 | 2024-09-27 | 2024-09-19 | 17689 | 0 | 0
17 | P.S. 241 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-31 | 2024-05-30 | 2024-04-03 | 4004 | 164 | 164
17 | P.S. 241 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-03 | 2024-09-27 | 2024-09-19 | 18019 | 656 | 656
17 | P.S. 241 - BROOKLYN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2024-07-18 |  | 2024-07-26 | 100000 | 100000 | 2768
17 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | Scope | Complete | 2023-06-14 | 2023-10-13 | 2024-01-09 | 149220 | 299877 | 143285
17 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | Design | Complete | 2024-01-16 | 2024-07-18 | 2024-05-10 | 746100 | 690298 | 320128
17 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | Construction | In-Progress | 2024-08-12 | 2026-08-11 |  | 16787250 | 15479425 | 0
17 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | CM,F&E | In-Progress | 2024-08-12 | 2026-08-11 |  | 1044540 | 432862 | 97464
17 | I.S. 246 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2023-05-19 | 2023-10-05 | 2023-10-20 | 60000 | 75383 | 62986
17 | I.S. 246 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 2024-04-25 | 2025-03-20 |  | 880000 | 502193 | 66870
17 | I.S. 246 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2024-04-25 | 2025-03-20 |  | 84226 | 82408 | 10698
17 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-06-24 | 2022-11-09 | 2022-12-16 | 93351 | 169409 | 163656
17 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-01-10 | 2023-06-12 | 2023-05-10 | 462806 | 389897 | 330488
17 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-08-21 | 2026-01-06 |  | 10071331 | 9254036 | 3116365
17 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-08-21 | 2026-01-06 |  | 683096 | 157633 | 150857
17 | P.S. 249 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-06-25 | 2024-10-24 | 2024-08-08 | 4706 | 867 | 867
17 | P.S. 249 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-08-08 | 2025-02-06 |  | 21178 | 21178 | 3469
17 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-08 | 2023-04-11 | 2022-12-20 | 5000 | 3930 | 3930
17 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-20 | 2023-06-16 | 2023-03-08 | 22500 | 15718 | 15718
17 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-05 | 2024-04-29 |  | 290000 | 259509 | 145901
17 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-05 | 2024-04-29 |  | 134871 | 114740 | 59725
17 | P.S. 316 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2023-07-05 | 2023-12-06 |  | 30000 | 24681 | 4492
17 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-06-15 | 2023-12-14 | 2023-11-02 | 129163 | 140229 | 140229
17 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-11-20 | 2024-04-23 | 2024-04-18 | 636400 | 328263 | 328263
17 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-09-16 | 2027-03-04 |  | 13504847 | 12344252 | 367226
17 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-09-16 | 2027-03-04 |  | 974731 | 50615 | 50615
17 | M.S. 352 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-07-09 | 2024-11-22 |  | 43800 | 30854 | 8075
17 | M.S. 352 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-09-19 | 2025-01-27 |  | 4673 | 4673 | 0
17 | M.S. 352 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE CARTS | F&E | Complete | 2024-03-21 |  | 2024-07-24 | 150606 | 150606 | 67550
17 | M.S. 354 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / SECURITY LIGHTING / EXTERIOR DOORS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 2023-07-13 | 2023-11-29 | 2024-01-11 | 274233 | 379221 | 115061
17 | M.S. 354 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / SECURITY LIGHTING / EXTERIOR DOORS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | In-Progress | 2024-06-12 | 2024-11-14 |  | 1339277 | 1339277 | 30132
17 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | Scope | Complete | 2023-06-15 | 2023-10-16 | 2023-10-02 | 67150 | 45066 | 45066
17 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | Design | Complete | 2023-10-17 | 2024-04-22 | 2024-04-25 | 335750 | 318158 | 264391
17 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | Construction | In-Progress | 2024-09-09 | 2026-09-08 |  | 7554375 | 6835251 | 12635
17 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | CM,F&E | In-Progress | 2024-09-09 | 2026-09-08 |  | 470050 | 83967 | 43501
17 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 2016-10-18 | 2017-04-18 | 2017-02-14 | 26400 | 93873 | 93834
17 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | Complete | 2019-07-11 | 2020-01-14 | 2019-12-31 | 132000 | 219425 | 219425
17 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2023-02-20 | 2024-02-19 |  | 2970000 | 2818969 | 2081081
17 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2023-02-20 | 2024-02-19 |  | 184800 | 334148 | 330361
17 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | Scope | Complete | 2022-01-27 | 2022-11-15 | 2022-11-16 | 96020 | 109410 | 109410
17 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | Design | Complete | 2022-11-30 | 2023-05-03 | 2023-05-08 | 465818 | 460738 | 340887
17 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | Construction | In-Progress | 2023-10-16 | 2026-03-03 |  | 9245730 | 8540265 | 1245674
17 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | CM,F&E | In-Progress | 2023-10-16 | 2026-03-03 |  | 779240 | 599762 | 587052
17 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Design | In-Progress | 2024-05-21 | 2024-10-07 |  | 90000 | 69904 | 9858
17 | BROOKLYN HS FOR MUSIC &THEATER - K | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2024-05-22 | 2024-10-08 |  | 87000 | 70792 | 9229
17 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | In-Progress | 2024-07-23 | 2024-11-25 |  | 11212 | 11212 | 0
17 | BROOKLYN HS FOR SCI & THE ENVI-K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2024-07-23 | 2024-11-25 |  | 7000 | 7000 | 0
17 | I.S. 382 - BROOKLYN | SCA CIP | PARAPET AND SIDE OF BUILDING DAMAGE @ K465 / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 2021-06-25 | 2021-11-24 | 2022-01-25 | 601037 | 414185 | 414185
17 | I.S. 382 - BROOKLYN | SCA CIP | PARAPET AND SIDE OF BUILDING DAMAGE @ K465 / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION / WINDOWS | Design | Complete | 2022-01-26 | 2022-06-27 | 2022-05-11 | 3005178 | 1578416 | 1518762
17 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 2021-06-03 | 2021-12-02 | 2021-10-27 | 382790 | 341612 | 341612
17 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Design | Complete | 2021-11-10 | 2022-06-30 | 2022-05-09 | 1913951 | 752498 | 752498
17 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Construction | In-Progress | 2022-09-19 | 2024-12-06 |  | 43063875 | 39403199 | 27088504
17 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | CM,F&E | In-Progress | 2022-09-19 | 2024-12-06 |  | 2679530 | 1227560 | 1211130
17 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | Scope | Complete | 2019-12-04 | 2020-04-07 | 2021-04-07 | 132420 | 169711 | 168334
17 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | Design | Complete | 2021-04-14 | 2021-09-14 | 2021-12-15 | 529680 | 1072099 | 784075
17 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | Construction | In-Progress | 2022-03-28 | 2023-08-19 |  | 9931500 | 9741750 | 8908132
17 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | CM,F&E | In-Progress | 2022-03-28 | 2023-08-19 |  | 635669 | 602445 | 558721
17 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LABS | F&E | Complete | 2024-01-08 |  | 2024-04-09 | 235000 | 235000 | 235000
17 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-05-13 | 2020-09-11 | 2020-06-19 | 4368 | 4197 | 4197
17 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-06-19 | 2020-12-16 | 2020-12-14 | 19657 | 16789 | 16789
17 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-06-09 | 2023-04-04 |  | 253356 | 228459 | 161471
17 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-06-09 | 2023-04-04 |  | 266617 | 265528 | 187730
17 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-10-28 | 2021-03-03 | 2021-03-03 | 3532 | 4279 | 4279
17 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-03-03 | 2021-08-25 | 2021-07-14 | 15893 | 17117 | 17117
17 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-06-09 | 2023-04-04 |  | 204844 | 184963 | 133196
17 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-06-09 | 2023-04-04 |  | 229756 | 228523 | 152059
17 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2019-08-05 | 2019-12-20 | 2020-02-19 | 57509 | 78920 | 76423
17 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2020-02-19 | 2020-07-20 | 2021-05-14 | 277627 | 329418 | 298959
17 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2021-07-14 | 2023-01-04 |  | 5388593 | 5284483 | 3999394
17 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-07-14 | 2023-01-04 |  | 476962 | 477786 | 455494
17 | MOSDOTH DAY CARE CENTER, INC. | SCA CIP | ACS EARLY LEARN RENEWAL | Scope | Complete | 2023-01-19 | 2023-04-20 | 2023-08-15 | 5065 | 59087 | 51485
17 | MOSDOTH DAY CARE CENTER, INC. | SCA CIP | ACS EARLY LEARN RENEWAL | Design | Complete | 2023-08-23 | 2024-02-29 | 2024-05-09 | 22793 | 38846 | 38846
17 | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 2021-03-02 | 2021-06-30 | 2021-07-02 | 25326 | 47409 | 47409
17 | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | Complete | 2021-10-01 | 2022-03-28 | 2022-08-09 | 126629 | 101650 | 20001
17 | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Construction | In-Progress | 2024-02-09 | 2025-08-01 |  | 2849162 | 2715131 | 236431
17 | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | CM,F&E | In-Progress | 2024-02-09 | 2025-08-01 |  | 177281 | 256454 | 102791
17 | CUNY @ MEDGAR EVERS HS ANNEX - BROOKLYN | SCA Capacity | NEW BUILDING/CUNY CORE & SHELL | Scope | Complete | 2022-07-15 | 2022-10-07 | 2022-09-30 | 879281 | 59966 | 9287
17 | CUNY @ MEDGAR EVERS HS ANNEX - BROOKLYN | SCA Capacity | NEW BUILDING/CUNY CORE & SHELL | Design | In-Progress | 2022-10-03 | 2023-04-20 |  | 3956763 | 3956763 | 606275
18 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-07 | 2023-04-10 | 2022-12-23 | 5000 | 4216 | 4216
18 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-23 | 2023-06-22 | 2023-04-04 | 22500 | 17060 | 17060
18 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 290000 | 264397 | 225347
18 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 120143 | 98791 | 92497
18 | I.S. 68 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2019-07-24 | 2019-12-10 | 2020-01-30 | 69590 | 155296 | 155296
18 | I.S. 68 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 2020-01-30 | 2020-06-30 | 2020-06-30 | 338340 | 329767 | 328633
18 | I.S. 68 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Construction | Complete | 2021-08-10 | 2023-05-01 | 2024-05-15 | 6781385 | 6066979 | 5708407
18 | I.S. 68 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | CM,F&E | Complete | 2021-08-10 | 2023-05-01 | 2024-05-15 | 559205 | 625382 | 623202
18 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2020-02-12 | 2020-07-14 | 2020-05-19 | 77950 | 142599 | 138089
18 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2020-05-19 | 2020-10-20 | 2020-11-05 | 389751 | 486280 | 470869
18 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-04-11 | 2024-05-09 |  | 8769375 | 8205679 | 7771168
18 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-04-11 | 2024-05-09 |  | 545650 | 918573 | 917799
18 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2021-03-08 | 2021-07-21 | 2021-08-11 | 59831 | 71708 | 71708
18 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 2021-09-07 | 2022-02-10 | 2022-04-25 | 287036 | 298790 | 290451
18 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 2022-09-12 | 2024-09-10 |  | 5409692 | 5171102 | 3733478
18 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2022-09-12 | 2024-09-10 |  | 509744 | 602874 | 598680
18 | P.S. 115 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-28 | 2024-09-26 | 2024-06-05 | 4077 | 732 | 732
18 | P.S. 115 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-06-05 | 2024-12-03 |  | 18346 | 18346 | 2926
18 | P.S. 115 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 2023-09-15 | 2024-02-05 | 2024-04-10 | 54000 | 58525 | 55863
18 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | Scope | Complete | 2020-08-21 | 2020-12-21 | 2021-01-27 | 55460 | 73551 | 76506
18 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | Design | Complete | 2021-02-02 | 2021-07-09 | 2021-06-29 | 277301 | 399912 | 311104
18 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | Construction | In-Progress | 2023-05-08 | 2024-08-04 |  | 6239250 | 5815925 | 1798793
18 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | CM,F&E | In-Progress | 2023-05-08 | 2024-08-04 |  | 388220 | 425059 | 422783
18 | P.S. 208 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-30 | 2024-09-30 | 2024-06-05 | 3791 | 768 | 768
18 | P.S. 208 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-06-05 | 2024-12-03 |  | 17061 | 17061 | 3069
18 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2022-06-29 | 2022-11-15 | 2023-03-01 | 108440 | 128569 | 128569
18 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2023-03-02 | 2023-08-17 | 2023-05-12 | 542200 | 446921 | 374863
18 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-10-16 | 2026-03-03 |  | 12199500 | 11171638 | 2680422
18 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-10-16 | 2026-03-03 |  | 766103 | 120637 | 118781
18 | P.S. 219 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE / FY21 RESO A SCIENCE LAB UPGRADE | Design | Complete | 2023-02-17 | 2023-06-22 | 2023-05-12 | 225000 | 155927 | 120349
18 | P.S. 219 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE / FY21 RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 2024-02-12 | 2025-08-04 |  | 3300000 | 3088532 | 106153
18 | P.S. 219 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE / FY21 RESO A SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 2024-02-12 | 2025-08-04 |  | 225000 | 84939 | 84939
18 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-09 | 2023-05-09 | 2023-01-25 | 4200 | 3500 | 3500
18 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-25 | 2023-07-21 | 2023-04-04 | 18900 | 14003 | 14003
18 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 243600 | 218361 | 191511
18 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 105649 | 89297 | 77295
18 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 2021-03-26 | 2021-08-10 | 2021-09-08 | 48428 | 122843 | 122843
18 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 2021-09-20 | 2022-02-24 | 2022-05-12 | 228254 | 274389 | 256317
18 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 2022-08-29 | 2024-02-19 |  | 3934577 | 3669518 | 3604817
18 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 2022-08-29 | 2024-02-19 |  | 443139 | 320390 | 320390
18 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-30 | 2023-05-30 | 2023-02-13 | 4200 | 2820 | 2820
18 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-13 | 2023-08-09 | 2023-04-04 | 18900 | 11279 | 11279
18 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 243600 | 217432 | 188207
18 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 96837 | 79281 | 75840
18 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2023-07-14 | 2023-11-30 |  | 73510 | 57327 | 4825
18 | P.S. 244 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-04-17 | 2024-09-18 |  | 57000 | 61714 | 34625
18 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-11-01 | 2024-04-30 | 2024-03-20 | 12000 | 11959 | 11959
18 | MIDDLE SCHOOL FOR ART & PHILOS - K | SCA CIP | FLOOD ELIMINATION | Scope | In-Progress | 2024-03-01 | 2024-07-17 |  | 15000 | 54675 | 4655
18 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2022-06-01 | 2022-11-25 | 2022-08-30 | 145999 | 168528 | 132008
18 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2022-09-29 | 2023-06-12 | 2023-03-15 | 730000 | 388117 | 388117
18 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2023-09-05 | 2025-09-03 |  | 16425001 | 15189232 | 6374171
18 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-09-05 | 2025-09-03 |  | 1023032 | 420336 | 381684
18 | P.S. 272 - BROOKLYN | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Design | Complete | 2023-05-19 | 2023-10-03 | 2023-10-16 | 69000 | 73566 | 58368
18 | P.S. 272 - BROOKLYN | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Construction | In-Progress | 2024-05-09 | 2025-04-03 |  | 1012000 | 555835 | 7532
18 | P.S. 272 - BROOKLYN | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | CM,F&E | In-Progress | 2024-05-09 | 2025-04-03 |  | 69000 | 61967 | 7606
18 | P.S. 276 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) CAFETERIA UPGRADE | Design | In-Progress | 2023-05-24 | 2023-10-11 |  | 44958 | 36429 | 1039
18 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | Scope | Complete | 2018-03-12 | 2018-07-10 | 2018-10-16 | 22500 | 24016 | 24016
18 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | Design | Complete | 2018-11-14 | 2019-05-13 | 2019-05-10 | 82500 | 102544 | 101605
18 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2019-07-22 | 2020-07-15 |  | 873750 | 790102 | 606624
18 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2019-07-22 | 2020-07-15 |  | 202500 | 119000 | 116689
18 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Design | In-Progress | 2023-08-01 | 2024-01-04 |  | 125658 | 102909 | 43425
18 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES | Scope | Complete | 2023-08-10 | 2023-11-09 | 2023-10-18 | 1784 | 1784 | 1784
18 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES | Design | In-Progress | 2023-10-18 | 2024-02-20 |  | 7137 | 7137 | 7137
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | Scope | Complete | 2019-06-11 | 2019-12-09 | 2019-11-27 | 235000 | 164153 | 164153
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | Design | Complete | 2021-03-04 | 2021-07-23 | 2022-05-06 | 1175000 | 825775 | 704084
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | Construction | In-Progress | 2022-09-12 | 2024-09-10 |  | 26437500 | 24462051 | 14368060
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | CM,F&E | In-Progress | 2022-09-12 | 2024-09-10 |  | 1645000 | 761125 | 746961
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | LIGHTING UPGRADE | Scope | Complete | 2022-02-22 | 2022-06-22 | 2022-03-28 | 12270 | 2692 | 2692
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | LIGHTING UPGRADE | Design | Complete | 2022-03-28 | 2022-08-25 | 2022-08-25 | 55215 | 10768 | 10768
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | LIGHTING UPGRADE | Construction | Complete | 2023-02-24 | 2023-12-20 | 2023-10-20 | 711654 | 797070 | 739320
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | LIGHTING UPGRADE | CM,F&E | Complete | 2023-02-24 | 2023-12-20 | 2023-10-20 | 131901 | 99314 | 98071
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | CAFETERIA UPGRADE / PATH OF TRAVEL CAFETERIA UPGRADE | Scope | Complete | 2022-01-05 | 2022-12-15 | 2023-01-19 | 22657 | 69755 | 69755
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | CAFETERIA UPGRADE / PATH OF TRAVEL CAFETERIA UPGRADE | Design | Complete | 2023-01-24 | 2023-05-24 | 2023-03-15 | 112151 | 285454 | 281195
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | RESO A- CULINARY ARTS KITCHEN / PATH OF TRAVEL RESO A KITCHEN UPGRADE / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2022-11-30 | 2023-11-13 | 2023-11-30 | 61605 | 76021 | 70256
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | RESO A- CULINARY ARTS KITCHEN / PATH OF TRAVEL RESO A KITCHEN UPGRADE / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2023-11-30 | 2024-02-15 | 2024-04-23 | 307087 | 296311 | 246516
18 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 2024-05-29 | 2024-10-30 |  | 29640 | 22865 | 3789
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 2024-05-29 | 2024-10-30 |  | 29640 | 23042 | 23042
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 2024-03-20 | 2024-06-20 | 2024-07-01 | 496 | 496 | 496
18 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | In-Progress | 2024-07-01 | 2024-11-01 |  | 1983 | 1983 | 1983
18 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 2024-03-19 | 2024-06-18 | 2024-07-01 | 229 | 229 | 229
18 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | In-Progress | 2024-07-01 | 2024-11-01 |  | 915 | 915 | 915
18 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2022-06-01 | 2022-11-25 | 2022-09-15 | 211895 | 145873 | 145841
18 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 2022-09-28 | 2023-06-12 | 2023-04-27 | 1059470 | 432824 | 432824
18 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2023-10-16 | 2026-04-02 |  | 23838075 | 22135306 | 8312787
18 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-10-16 | 2026-04-02 |  | 1483258 | 388925 | 362340
18 | HS FOR MEDICAL PROFESSIONS - K | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 2023-08-31 | 2024-01-02 | 2023-12-06 | 84000 | 68527 | 14287
18 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | Scope | Complete | 2019-05-23 | 2019-09-23 | 2019-11-27 | 59160 | 55023 | 55023
18 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | Design | Complete | 2020-01-03 | 2020-07-07 | 2022-09-26 | 295800 | 227454 | 207080
18 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | Construction | In-Progress | 2023-09-11 | 2025-03-03 |  | 6655500 | 5990442 | 1107360
18 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2023-09-11 | 2025-03-03 |  | 414120 | 154242 | 154053
18 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2024-01-10 | 2024-05-14 | 2024-07-12 | 90000 | 60930 | 52561
18 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | ROOFS | Scope | Complete | 2019-07-23 | 2019-12-09 | 2019-10-10 | 12790 | 17110 | 17110
18 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | ROOFS | Design | Complete | 2019-10-22 | 2020-03-26 | 2020-06-08 | 63950 | 80662 | 80614
18 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | Scope | Complete | 2020-02-25 | 2020-07-24 | 2021-03-25 | 50050 | 44825 | 44825
18 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | Design | Complete | 2021-06-07 | 2021-12-09 | 2021-12-07 | 234927 | 231062 | 181775
18 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | Construction | In-Progress | 2023-08-07 | 2025-08-05 |  | 3960743 | 3538066 | 2047176
18 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | CM,F&E | In-Progress | 2023-08-07 | 2025-08-05 |  | 465242 | 137277 | 136792
18 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | Scope | Complete | 2019-02-04 | 2019-07-05 | 2019-09-10 | 40883 | 24498 | 24498
18 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | Design | Complete | 2021-03-16 | 2021-08-13 | 2021-12-17 | 199691 | 209857 | 120144
18 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | Construction | In-Progress | 2024-08-19 | 2027-02-04 |  | 4084529 | 3931013 | 158074
18 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | CM,F&E | In-Progress | 2024-08-19 | 2027-02-04 |  | 321597 | 136764 | 72828
18 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | Scope | Complete | 2013-08-01 | 2014-01-06 | 2013-12-05 | 48840 | 25752 | 25752
18 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | Design | Complete | 2014-01-08 | 2014-06-10 | 2014-10-22 | 195360 | 281516 | 281516
18 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | Construction | In-Progress | 2019-08-19 | 2021-08-17 |  | 3663000 | 3384381 | 2594772
18 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | CM,F&E | In-Progress | 2019-08-19 | 2021-08-17 |  | 227920 | 1014568 | 1014568
18 | EAST BKLN COMMUNITY HS - K | SCA CIP | COVID VENTILATION | Scope | Complete | 2020-12-10 | 2021-04-09 | 2021-06-09 | 10487 | 43705 | 43705
18 | EAST BKLN COMMUNITY HS - K | SCA CIP | COVID VENTILATION | Design | Complete | 2021-06-14 | 2021-11-15 | 2021-10-27 | 52434 | 68933 | 67801
19 | K004 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-11 | 2024-05-10 | 2024-01-11 | 4063 | 1555 | 1555
19 | K004 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-20 | 2024-09-13 | 2024-07-16 | 18284 | 6224 | 6224
19 | P.S. 13 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-18 | 2024-05-16 | 2024-04-02 | 5365 | 1962 | 1962
19 | P.S. 13 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-02 | 2024-09-26 | 2024-07-16 | 24144 | 7851 | 7851
19 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | Scope | Complete | 2023-05-25 | 2023-10-12 | 2023-09-26 | 30980 | 99039 | 54259
19 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | Design | Complete | 2023-10-05 | 2024-03-12 | 2024-03-06 | 154902 | 153482 | 107601
19 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | Construction | In-Progress | 2024-07-15 | 2025-12-06 |  | 3485301 | 3512883 | 96259
19 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | CM,F&E | In-Progress | 2024-07-15 | 2025-12-06 |  | 216863 | 37880 | 37880
19 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-08-31 | 2024-01-04 | 2023-11-07 | 5690 | 2202 | 2202
19 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-11-07 | 2024-05-06 | 2024-01-24 | 25603 | 8811 | 8811
19 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2024-07-19 | 2025-06-13 |  | 329997 | 297143 | 2163
19 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2024-07-19 | 2025-06-13 |  | 61163 | 35609 | 4992
19 | P.S. 149 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-09 | 2024-05-08 | 2024-03-22 | 4062 | 1226 | 1226
19 | P.S. 149 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-22 | 2024-09-17 | 2024-08-13 | 18281 | 4908 | 4908
19 | P.S. 158 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-01-11 | 2024-05-10 | 2024-01-11 | 3924 | 1082 | 1082
19 | P.S. 158 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-21 | 2024-09-16 | 2024-08-13 | 17660 | 4329 | 4329
19 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2022-07-21 | 2022-12-07 | 2022-12-27 | 37670 | 29394 | 29394
19 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2023-01-04 | 2023-06-06 | 2023-05-03 | 188350 | 116837 | 101446
19 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2024-01-12 | 2025-11-01 |  | 4237875 | 3852823 | 871031
19 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-01-12 | 2025-11-01 |  | 263690 | 112544 | 112544
19 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-08-29 | 2024-01-02 | 2023-11-07 | 5170 | 1398 | 1398
19 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-11-07 | 2024-05-06 | 2024-01-24 | 23267 | 5591 | 5591
19 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2024-07-19 | 2025-06-13 |  | 299883 | 271155 | 2135
19 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2024-07-19 | 2025-06-13 |  | 55582 | 32596 | 4676
19 | P.S. 190 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-09-26 | 2024-01-30 | 2023-09-27 | 5166 | 1424 | 1424
19 | P.S. 190 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-09-27 | 2024-03-27 | 2024-03-20 | 23248 | 5696 | 5696
19 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 2022-06-27 | 2022-12-21 | 2022-10-06 | 257257 | 313904 | 304123
19 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | Complete | 2022-10-19 | 2023-06-26 | 2023-05-03 | 1286286 | 406613 | 406613
19 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Construction | In-Progress | 2023-10-16 | 2026-03-03 |  | 28941441 | 26440453 | 5757584
19 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | CM,F&E | In-Progress | 2023-10-16 | 2026-03-03 |  | 1800800 | 331262 | 307195
19 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2019-09-18 | 2020-02-06 | 2021-05-04 | 28328 | 94277 | 74538
19 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2021-05-13 | 2021-10-14 | 2022-02-07 | 141640 | 213461 | 193056
19 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2022-06-27 | 2023-12-18 |  | 3186910 | 3328908 | 2839594
19 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-06-27 | 2023-12-18 |  | 199103 | 586627 | 575615
19 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-05 | 2023-05-05 | 2023-01-13 | 4395 | 4630 | 4630
19 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-13 | 2023-07-12 | 2023-04-05 | 19776 | 18521 | 18521
19 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 254893 | 229895 | 149390
19 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 108028 | 90831 | 85855
19 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2019-02-06 | 2019-09-03 | 2019-11-15 | 154000 | 157200 | 157200
19 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2020-01-23 | 2020-07-09 | 2022-05-10 | 770000 | 721250 | 721070
19 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 2022-08-10 | 2023-11-02 |  | 17325001 | 16129091 | 11698822
19 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2022-08-10 | 2023-11-02 |  | 1199985 | 674799 | 666876
19 | I.S. 218 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2023-08-14 | 2024-01-02 | 2023-10-27 | 12668 | 25452 | 25061
19 | I.S. 218 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2023-10-30 | 2024-04-03 | 2024-03-13 | 57008 | 39295 | 36540
19 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | Scope | Complete | 2019-06-07 | 2019-10-23 | 2021-09-01 | 112240 | 261298 | 260119
19 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | Design | Complete | 2021-09-29 | 2022-03-07 | 2024-05-09 | 561200 | 686351 | 490688
19 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | Construction | In-Progress | 2024-07-22 | 2027-01-07 |  | 12627000 | 11303737 | 57537
19 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | CM,F&E | In-Progress | 2024-07-22 | 2027-01-07 |  | 785679 | 74474 | 72919
19 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-01 | 2023-06-01 | 2023-02-06 | 7639 | 4973 | 4973
19 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-06 | 2023-08-02 | 2023-05-03 | 34375 | 19894 | 19894
19 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-09 | 2024-10-03 |  | 443050 | 402836 | 258181
19 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-09 | 2024-10-03 |  | 116757 | 80528 | 63440
19 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-09-17 | 2022-02-07 | 2022-01-26 | 104244 | 170619 | 170619
19 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2022-02-23 | 2022-08-09 | 2022-12-07 | 521220 | 489955 | 395148
19 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-09-04 | 2025-09-02 |  | 11727450 | 10710992 | 262973
19 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-09-04 | 2025-09-02 |  | 767134 | 342108 | 320575
19 | P.S. 273 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-15 | 2024-08-14 | 2024-04-19 | 4155 | 1430 | 1430
19 | P.S. 273 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-19 | 2024-10-16 | 2024-09-11 | 18697 | 5719 | 5719
19 | I.S. 292 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2023-07-07 | 2023-11-22 | 2023-11-20 | 54000 | 146024 | 146024
19 | I.S. 292 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2023-11-21 | 2024-04-24 | 2024-05-06 | 270000 | 276921 | 271106
19 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2023-01-10 | 2023-05-25 | 2023-06-05 | 69582 | 92418 | 85060
19 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2023-06-21 | 2023-12-08 | 2024-08-29 | 347914 | 198282 | 102106
19 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-30 | 2023-10-30 | 2023-11-01 | 11700 | 19375 | 19375
19 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-11-02 | 2024-04-02 | 2024-04-30 | 52650 | 84361 | 68306
19 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-08-22 | 2025-09-25 |  | 678600 | 617416 | 2772
19 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-08-22 | 2025-09-25 |  | 125775 | 85060 | 8761
19 | VISTA ACADEMY - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES / FY20 RESO A SCIENCE LAB UPGRADES | Design | Complete | 2021-10-13 | 2021-12-30 | 2022-02-11 | 57000 | 89411 | 66471
19 | VISTA ACADEMY - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES / FY20 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 2022-05-19 | 2023-03-14 |  | 836000 | 661090 | 415043
19 | VISTA ACADEMY - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES / FY20 RESO A SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 2022-05-19 | 2023-03-14 |  | 93860 | 149664 | 141408
19 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | Scope | Complete | 2022-06-02 | 2022-11-28 | 2022-09-23 | 140809 | 214285 | 180017
19 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | Design | Complete | 2022-09-27 | 2023-06-12 | 2023-04-19 | 702158 | 474528 | 474528
19 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | Construction | In-Progress | 2023-09-05 | 2025-09-03 |  | 15635113 | 14238632 | 1747947
19 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | CM,F&E | In-Progress | 2023-09-05 | 2025-09-03 |  | 1001893 | 232705 | 219937
19 | P.S. 306 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-17 | 2024-08-16 | 2024-04-24 | 4992 | 1407 | 1407
19 | P.S. 306 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-24 | 2024-10-21 | 2024-09-11 | 22464 | 5626 | 5626
19 | P.S. 328 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-17 | 2024-08-16 | 2024-05-01 | 4249 | 1215 | 1215
19 | P.S. 328 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-05-01 | 2024-10-28 | 2024-09-11 | 19122 | 4859 | 4859
19 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2018-05-22 | 2018-09-20 | 2018-10-19 | 84019 | 104874 | 104874
19 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2018-12-18 | 2019-03-11 | 2019-09-10 | 380332 | 278763 | 278763
19 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2022-10-12 | 2024-04-03 |  | 7651235 | 7664287 | 6316247
19 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2022-10-12 | 2024-04-03 |  | 563015 | 495986 | 492961
19 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-03-02 | 2021-07-15 | 2021-11-08 | 128939 | 108064 | 108064
19 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 2021-11-09 | 2022-04-14 | 2022-05-13 | 635011 | 395830 | 395830
19 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2022-09-12 | 2024-06-02 |  | 13450108 | 13049900 | 9833177
19 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-09-12 | 2024-06-02 |  | 975198 | 775015 | 767575
19 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-09-22 | 2024-01-26 | 2023-10-24 | 5074 | 1371 | 1371
19 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-10-24 | 2024-04-22 | 2023-12-20 | 22833 | 5485 | 5485
19 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2024-04-16 | 2025-03-11 |  | 294292 | 261197 | 2997
19 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2024-04-16 | 2025-03-11 |  | 54546 | 32576 | 5067
19 | I.S. 452 | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2023-09-12 | 2024-01-18 | 2023-11-29 | 60000 | 71996 | 59451
19 | I.S. 452 | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 2024-04-30 | 2025-03-25 |  | 880000 | 569474 | 188760
19 | I.S. 452 | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2024-04-30 | 2025-03-25 |  | 60000 | 58981 | 22574
19 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | Scope | Complete | 2022-02-22 | 2022-06-21 | 2022-06-24 | 6362 | 30398 | 30398
19 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | Design | Complete | 2022-11-03 | 2023-05-03 | 2023-05-03 | 23326 | 17831 | 11739
19 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2023-11-09 | 2024-10-03 |  | 247044 | 239021 | 165449
19 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2023-11-09 | 2024-10-03 |  | 140642 | 138171 | 97728
19 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | SCA CIP | ACCESSIBLE RAMP / ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 2023-01-27 | 2023-06-23 | 2023-08-29 | 1229210 | 965934 | 940179
19 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | SCA CIP | ACCESSIBLE RAMP / ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 2023-10-05 | 2024-05-15 | 2024-05-13 | 6146050 | 408567 | 202852
19 | MULTICULTURAL HS - BROOKLYN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2024-06-18 |  | 2024-09-03 | 350000 | 350000 | 350000
19 | PERFORMING ARTS AND TECH. HS - K | SCA CIP | ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ANSUL SYSTEMS / FIRE ALARM SYSTEM | Scope | Complete | 2023-06-20 | 2023-12-18 | 2023-11-02 | 670392 | 389157 | 359636
19 | PERFORMING ARTS AND TECH. HS - K | SCA CIP | ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ANSUL SYSTEMS / FIRE ALARM SYSTEM | Design | Complete | 2023-12-27 | 2024-07-01 | 2024-05-13 | 3346390 | 828385 | 828301
19 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Scope | Complete | 2021-11-19 | 2022-06-30 | 2022-05-12 | 16893 | 338976 | 22217
19 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Design | Complete | 2022-05-13 | 2022-09-26 | 2022-10-07 | 83405 | 117015 | 72988
19 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Construction | In-Progress | 2023-10-23 | 2025-03-05 |  | 1784836 | 1710066 | 366832
19 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 2023-10-23 | 2025-03-05 |  | 126210 | 183686 | 155976
19 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | Scope | Complete | 2023-03-09 | 2023-10-06 | 2023-10-25 | 549000 | 703978 | 700626
19 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | Design | Complete | 2023-10-30 | 2024-05-15 | 2024-05-15 | 2745000 | 1708694 | 1154133
19 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | Construction | In-Progress | 2024-09-23 | 2026-06-14 |  | 61762500 | 55627913 | 304115
19 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | CM,F&E | In-Progress | 2024-09-23 | 2026-06-14 |  | 3843000 | 683246 | 281526
19 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | Scope | Complete | 2023-10-25 | 2023-10-25 | 2023-10-25 | 19252 | 21678 | 2626
19 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | Design | Complete | 2023-10-25 | 2024-02-29 | 2024-04-08 | 96262 | 86865 | 10658
19 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | Construction | In-Progress | 2024-07-08 | 2025-01-03 |  | 2165888 | 2566504 | 590956
19 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | CM,F&E | In-Progress | 2024-07-08 | 2025-01-03 |  | 135768 | 155109 | 145834
19 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2020-05-27 | 2020-11-23 | 2020-10-22 | 282728 | 351779 | 350973
19 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2020-11-03 | 2021-06-15 | 2021-07-01 | 1405112 | 743393 | 743393
19 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2022-06-13 | 2024-06-11 |  | 30877347 | 28106693 | 23014016
19 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2022-06-13 | 2024-06-11 |  | 2043050 | 627952 | 622495
19 | WILLIAM MAXWELL VOC HS - K | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-23 | 2023-10-23 | 2023-10-18 | 15100 | 21756 | 21756
19 | WILLIAM MAXWELL VOC HS - K | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-11-14 | 2024-04-15 | 2024-05-15 | 75500 | 81902 | 71393
19 | P.S. 65 - BROOKLYN | SCA CIP | ROOFS | Scope | In-Progress | 2024-08-20 | 2025-01-08 |  | 38191 | 48158 | 933
19 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2018-10-16 | 2019-03-06 | 2019-02-08 | 48184 | 44140 | 44140
19 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2019-02-08 | 2019-07-11 | 2019-05-08 | 183794 | 135312 | 135226
19 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2023-05-11 | 2024-08-02 |  | 2643522 | 2393976 | 1422917
19 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-05-11 | 2024-08-02 |  | 341117 | 134149 | 132486
19 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | Scope | Complete | 2022-10-25 | 2023-01-27 | 2023-07-20 | 53682 | 69479 | 69477
19 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | Design | Complete | 2023-08-02 | 2024-02-07 | 2024-04-17 | 250136 | 531157 | 171626
19 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | Construction | In-Progress | 2024-08-05 | 2026-08-04 |  | 4047144 | 3894593 | 6075
19 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2024-08-05 | 2026-08-04 |  | 512852 | 378970 | 31052
19 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-11-21 | 2023-03-24 | 2022-12-06 | 3697 | 3217 | 3217
19 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-06 | 2023-06-02 | 2023-04-05 | 16638 | 12866 | 12866
19 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 214442 | 193153 | 131314
19 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 90566 | 75437 | 71527
19 | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 2021-04-09 | 2021-07-09 | 2021-08-03 | 12644 | 25329 | 17555
19 | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | In-Progress | 2022-09-28 | 2023-02-01 |  | 56896 | 73599 | 25095
19 | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | PATH OF TRAVEL | Scope | Complete | 2023-05-26 | 2023-09-25 | 2023-09-01 | 1445 | 0 | 0
19 | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | PATH OF TRAVEL | Design | In-Progress | 2023-09-05 | 2024-01-10 |  | 6504 | 6504 | 0
20 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 2020-06-29 | 2020-09-28 | 2020-09-02 | 17354 | 80447 | 80447
20 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 2020-11-25 | 2021-04-14 | 2021-04-14 | 85416 | 169187 | 163817
20 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | In-Progress | 2021-09-20 | 2022-09-19 |  | 1804739 | 1774075 | 1513955
20 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2021-09-20 | 2022-09-19 |  | 131634 | 199463 | 194093
20 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2021-04-01 | 2021-10-12 | 2021-10-15 | 1189920 | 907422 | 788469
20 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 2021-10-18 | 2022-04-01 | 2022-05-11 | 5354640 | 2539707 | 1638277
20 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2022-12-22 | 2024-09-03 |  | 67527960 | 62035796 | 56122126
20 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2022-12-22 | 2024-09-03 |  | 9519360 | 5393640 | 3185800
20 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2017-12-13 | 2018-05-16 | 2018-03-20 | 111330 | 100483 | 100483
20 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2018-03-23 | 2018-08-22 | 2018-07-31 | 445320 | 464738 | 460208
20 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2018-12-03 | 2020-12-01 |  | 8349750 | 8117352 | 7822270
20 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2018-12-03 | 2020-12-01 |  | 519540 | 996910 | 991839
20 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-06-06 | 2022-11-30 | 2022-09-23 | 218830 | 250669 | 248988
20 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2022-09-27 | 2023-06-12 | 2023-04-27 | 1094151 | 491760 | 491760
20 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 2023-09-18 | 2026-02-03 |  | 24618375 | 22177623 | 5315838
20 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-09-18 | 2026-02-03 |  | 1531810 | 211562 | 207238
20 | P.S. 69 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-03-01 | 2024-07-01 | 2024-04-04 | 2934 | 2040 | 2040
20 | P.S. 69 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-04 | 2024-09-30 | 2024-09-25 | 13205 | 8158 | 8158
20 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-07-11 | 2022-11-25 | 2023-01-05 | 48384 | 56685 | 45874
20 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-09-25 | 2024-08-19 |  | 709639 | 645126 | 248995
20 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-09-25 | 2024-08-19 |  | 48384 | 62214 | 25730
20 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 2024-04-10 | 2024-09-11 | 2024-08-23 | 75000 | 34883 | 2337
20 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2022-11-01 | 2023-04-14 | 2023-04-13 | 1274220 | 720341 | 720280
20 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 2023-04-14 | 2023-11-30 | 2024-05-01 | 5733990 | 1074092 | 893559
20 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2023-01-26 | 2023-01-26 | 2023-01-26 | 72660 | 615 | 615
20 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 2023-01-26 | 2023-07-05 | 2023-10-17 | 363300 | 181747 | 177680
20 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Construction | In-Progress | 2023-12-18 | 2024-03-16 |  | 8174250 | 7327333 | 4614860
20 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2023-12-18 | 2024-03-16 |  | 508620 | 272136 | 169788
20 | P.S. 102 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2023-10-12 | 2024-03-01 | 2024-04-23 | 31559 | 128346 | 119366
20 | P.S. 102 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Design | In-Progress | 2024-05-06 | 2024-10-07 |  | 157794 | 157794 | 66891
20 | P.S. 102 - BROOKLYN | SCA CIP | PATH OF TRAVEL FLOOD ELIMINATION | Scope | In-Progress | 2024-02-15 | 2024-05-15 |  | 6164 | 6164 | 344
20 | P.S. 102 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-03-28 | 2024-07-29 | 2024-04-19 | 4429 | 3370 | 3370
20 | P.S. 102 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-19 | 2024-10-16 | 2024-09-25 | 19929 | 13481 | 13481
20 | P.S. 102 - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2020-02-12 | 2020-04-10 | 2020-03-26 | 41257 | 239176 | 236141
20 | P.S. 102 - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | Complete | 2021-06-21 | 2022-03-17 | 2024-06-12 | 605104 | 561212 | 401336
20 | P.S. 102 - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 2021-06-21 | 2022-03-17 | 2024-06-12 | 41257 | 96186 | 91804
20 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | Scope | Complete | 2016-09-22 | 2023-07-26 | 2023-04-19 | 239660 | 239958 | 239552
20 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | Design | Complete | 2023-04-20 | 2023-09-21 | 2023-05-09 | 1198300 | 853628 | 625470
20 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | Construction | In-Progress | 2023-09-18 | 2026-03-05 |  | 26961751 | 25076237 | 5515787
20 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-09-18 | 2026-03-05 |  | 1678591 | 384220 | 344945
20 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY23 RESO A OUTDOOR STEM CENTER | Design | In-Progress | 2024-02-21 | 2024-07-08 |  | 39000 | 42468 | 27860
20 | P.S. 104 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A OUTDOOR STEM CENTER | Design | In-Progress | 2024-04-12 | 2024-08-15 |  | 7089 | 4500 | 4500
20 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2019-06-18 | 2019-11-01 | 2019-12-31 | 105581 | 165197 | 163449
20 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2020-01-08 | 2020-06-09 | 2020-06-30 | 521856 | 418412 | 384584
20 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2023-02-06 | 2025-02-04 |  | 11218306 | 10286949 | 6541211
20 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2023-02-06 | 2025-02-04 |  | 785642 | 223790 | 218761
20 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | Scope | Complete | 2017-06-30 | 2021-12-06 | 2021-10-28 | 262426 | 409386 | 409386
20 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | Design | Complete | 2021-11-18 | 2022-06-30 | 2022-04-26 | 1293602 | 1484874 | 1266334
20 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | Construction | In-Progress | 2022-09-26 | 2024-12-13 |  | 28828128 | 27482387 | 13409589
20 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | CM,F&E | In-Progress | 2022-09-26 | 2024-12-13 |  | 1795257 | 1015450 | 992148
20 | P.S. 748 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2023-06-05 | 2023-10-20 | 2023-10-17 | 48516 | 65151 | 64117
20 | P.S. 748 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | Complete | 2023-10-24 | 2024-03-28 | 2024-08-13 | 222536 | 126267 | 119901
20 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | Scope | Complete | 2018-06-28 | 2019-11-26 | 2019-11-13 | 29171 | 115406 | 104262
20 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | Design | Complete | 2019-12-04 | 2020-05-21 | 2020-05-20 | 118252 | 403105 | 402855
20 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2021-08-16 | 2022-08-15 |  | 2134466 | 1924381 | 1829629
20 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2021-08-16 | 2022-08-15 |  | 155221 | 291246 | 290996
20 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-05-03 | 2021-07-02 | 2021-05-12 | 4680 | 154 | 154
20 | P.S. 748 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Design | Complete | 2023-10-16 | 2024-03-20 | 2024-02-28 | 30000 | 5476 | 5476
20 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Scope | Complete | 2021-01-27 | 2021-05-27 | 2021-12-01 | 67750 | 95933 | 95883
20 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Design | Complete | 2021-12-02 | 2022-05-02 | 2022-08-31 | 338750 | 354035 | 319053
20 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Construction | In-Progress | 2023-03-06 | 2024-06-02 |  | 7621875 | 8580211 | 6086051
20 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 2023-03-06 | 2024-06-02 |  | 481273 | 400310 | 379758
20 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-10-14 | 2023-02-16 | 2022-12-21 | 3769 | 6321 | 6321
20 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-21 | 2023-06-20 | 2023-04-04 | 16961 | 25284 | 25284
20 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 218602 | 201092 | 133478
20 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 93447 | 84284 | 76298
20 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2021-06-15 | 2021-12-14 | 2021-10-04 | 204217 | 260162 | 235144
20 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2021-10-12 | 2022-06-30 | 2022-04-06 | 1017869 | 489339 | 489339
20 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2022-08-15 | 2024-08-13 |  | 22623879 | 21011692 | 10891609
20 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2022-08-15 | 2024-08-13 |  | 1454854 | 348223 | 342121
20 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2020-02-06 | 2020-06-22 | 2021-11-03 | 23126 | 64572 | 64572
20 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2021-11-05 | 2022-04-12 | 2022-05-13 | 115630 | 146980 | 133464
20 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 2023-03-10 | 2024-06-01 |  | 2601675 | 2483576 | 2398720
20 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-03-10 | 2024-06-01 |  | 161882 | 264336 | 261626
20 | P.S. 179 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-15 | 2024-09-16 | 2024-05-21 | 4979 | 2455 | 2455
20 | P.S. 179 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-05-21 | 2024-11-18 |  | 22404 | 22404 | 9818
20 | P.S. 180 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | In-Progress | 2024-07-01 | 2024-11-15 |  | 333997 | 333997 | 78173
20 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | Scope | Complete | 2020-02-11 | 2021-09-13 | 2021-11-03 | 233776 | 239594 | 231377
20 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | Design | Complete | 2021-11-08 | 2022-04-28 | 2022-09-30 | 1164456 | 663960 | 575773
20 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | Construction | In-Progress | 2023-09-18 | 2025-12-05 |  | 25817368 | 24060933 | 1856373
20 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-09-18 | 2025-12-05 |  | 1669634 | 203202 | 202358
20 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2021-07-15 | 2021-12-01 | 2022-02-03 | 61398 | 123584 | 123584
20 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 2022-02-03 | 2022-07-06 | 2022-05-16 | 297421 | 322620 | 311323
20 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2022-11-14 | 2024-08-04 |  | 5864363 | 5422326 | 4242234
20 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-11-14 | 2024-08-04 |  | 502749 | 287231 | 285976
20 | P.S. 185 - BROOKLYN | SCA CIP | CLASSROOM FLOORING / PATH OF TRAVEL CLASSROOM FLOORING | Scope | Complete | 2023-03-21 | 2024-02-27 | 2023-12-12 | 23456 | 28112 | 18868
20 | P.S. 185 - BROOKLYN | SCA CIP | CLASSROOM FLOORING / PATH OF TRAVEL CLASSROOM FLOORING | Design | Complete | 2023-12-13 | 2024-04-12 | 2024-04-11 | 114871 | 60544 | 32308
20 | P.S. 185 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND | Scope | In-Progress | 2024-07-10 | 2024-10-08 |  | 6388 | 6388 | 623
20 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-06-02 | 2020-09-30 | 2020-07-10 | 2597 | 7310 | 7310
20 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-10 | 2021-01-06 | 2021-05-05 | 11687 | 29243 | 29243
20 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-04-28 | 2023-02-21 |  | 150626 | 137240 | 117140
20 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-04-28 | 2023-02-21 |  | 179038 | 181506 | 90932
20 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-09-02 | 2023-01-06 | 2022-10-04 | 3371 | 10076 | 10076
20 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-10-04 | 2023-04-04 | 2023-04-04 | 15170 | 40306 | 40306
20 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 195518 | 179644 | 110733
20 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 81696 | 78177 | 73593
20 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2017-02-01 | 2017-06-16 | 2017-09-08 | 119212 | 111733 | 111733
20 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 2017-10-11 | 2018-03-16 | 2018-01-31 | 476847 | 506066 | 467258
20 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2018-06-01 | 2020-02-20 |  | 8940881 | 8987472 | 7102139
20 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2018-06-01 | 2020-02-20 |  | 556322 | 1805136 | 1766187
20 | P.S. 200 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-23 | 2024-09-24 | 2024-05-29 | 4375 | 2509 | 2509
20 | P.S. 200 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-05-29 | 2024-11-25 |  | 19689 | 19689 | 10036
20 | I.S. 201 - BROOKLYN | SCA CIP | GYM FLOOR REPLACEMENT | Scope | Complete | 2023-06-29 | 2023-10-31 | 2023-11-15 | 18216 | 17588 | 2392
20 | I.S. 201 - BROOKLYN | SCA CIP | GYM FLOOR REPLACEMENT | Design | Complete | 2023-12-07 | 2024-04-24 | 2024-05-31 | 85010 | 57160 | 9568
20 | I.S. 201 - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM FLOOR REPLACEMENT | Scope | Complete | 2023-10-27 | 2024-02-01 | 2024-01-11 | 7615 | 7615 | 15
20 | I.S. 201 - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM FLOOR REPLACEMENT | Design | Complete | 2024-01-12 | 2024-05-15 | 2024-05-31 | 22709 | 22709 | 59
20 | I.S. 201 - BROOKLYN | SCA CIP RESOA | FY18 RESO A ROOM CONVERSION | Design | Complete | 2018-11-28 | 2019-04-29 | 2019-08-22 | 113900 | 199923 | 179697
20 | I.S. 201 - BROOKLYN | SCA CIP RESOA | FY18 RESO A ROOM CONVERSION | Construction | In-Progress | 2021-09-20 | 2022-09-19 |  | 1670533 | 1788533 | 1589941
20 | I.S. 201 - BROOKLYN | SCA CIP RESOA | FY18 RESO A ROOM CONVERSION | CM,F&E | In-Progress | 2021-09-20 | 2022-09-19 |  | 144945 | 270162 | 263726
20 | P.S. 205 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2024-01-19 | 2024-04-18 | 2024-03-25 | 22834 | 29001 | 28903
20 | P.S. 205 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | In-Progress | 2024-04-03 | 2024-10-04 |  | 106558 | 106558 | 44954
20 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-05-24 | 2023-09-25 | 2023-06-16 | 4223 | 630 | 630
20 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-16 | 2023-12-14 | 2023-08-30 | 19003 | 2519 | 2519
20 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-23 | 2025-01-17 |  | 244922 | 234471 | 9298
20 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-23 | 2025-01-17 |  | 47953 | 29229 | 17751
20 | I.S. 223 - BROOKLYN | SCA CIP | DAMAGED STEEL BEAM AT THE MAIN ENTRANCE #1 | Scope | Complete | 2015-05-28 | 2015-09-25 | 2015-10-15 | 8724 | 13816 | 13816
20 | I.S. 223 - BROOKLYN | SCA CIP | DAMAGED STEEL BEAM AT THE MAIN ENTRANCE #1 | Design | Complete | 2016-02-17 | 2016-05-31 | 2016-10-17 | 31989 | 97809 | 71791
20 | P.S. 229 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 2023-05-15 | 2023-09-29 | 2023-09-27 | 60000 | 54630 | 42135
20 | P.S. 229 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | In-Progress | 2024-05-01 | 2025-03-26 |  | 880000 | 505328 | 356130
20 | P.S. 229 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2024-05-01 | 2025-03-26 |  | 200891 | 197080 | 28253
20 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 2023-04-27 | 2023-09-27 | 2023-08-25 | 66000 | 91198 | 21036
20 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 2024-05-03 | 2025-03-28 |  | 968000 | 826928 | 143450
20 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 2024-05-03 | 2025-03-28 |  | 66000 | 88098 | 20225
20 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-07-17 | 2023-12-18 | 2024-02-16 | 30000 | 35395 | 8468
20 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2024-07-26 | 2025-05-21 |  | 440000 | 307506 | 0
20 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2024-07-26 | 2025-05-21 |  | 30000 | 38152 | 8700
20 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | Scope | Complete | 2023-01-10 | 2023-06-09 | 2023-04-25 | 102004 | 94780 | 93891
20 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | Design | Complete | 2023-05-15 | 2023-10-17 | 2023-11-07 | 501798 | 650002 | 351794
20 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | Construction | In-Progress | 2024-04-03 | 2026-04-02 |  | 10579036 | 9477291 | 84292
20 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | CM,F&E | In-Progress | 2024-04-03 | 2026-04-02 |  | 775715 | 67300 | 66095
20 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2020-01-06 | 2020-06-03 | 2020-06-03 | 1215600 | 1273535 | 1245759
20 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 2020-06-04 | 2021-01-07 | 2021-01-07 | 5470200 | 4719461 | 4276995
20 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2021-11-22 | 2024-09-03 |  | 68985300 | 70055618 | 56933044
20 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2021-11-22 | 2024-09-03 |  | 9724800 | 7834400 | 5680773
20 | I.S. 30 - BROOKLYN | SCA CIP RESOA | RESO A LIBRARY UPGRADE | Design | Complete | 2023-11-21 | 2024-04-09 | 2024-04-05 | 30000 | 34519 | 32626
20 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2023-06-06 | 2023-06-06 | 2023-06-06 | 40607 | 114398 | 45021
20 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 2023-06-13 | 2023-09-29 | 2023-11-08 | 203037 | 87519 | 70531
20 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2024-04-16 | 2024-09-10 | 2024-09-10 | 2139680 | 434939 | 373411
20 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | In-Progress | 2024-09-11 | 2025-04-14 |  | 8558721 | 8558721 | 837433
20 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | EARLY DEMO WORK-TANK REMOVAL | Scope | Complete | 2024-04-15 | 2024-04-15 | 2024-04-15 | 7427 | 284 | 284
20 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | EARLY DEMO WORK-TANK REMOVAL | Design | Complete | 2024-04-16 | 2024-05-20 | 2024-05-20 | 29708 | 1135 | 1135
20 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2024-04-15 | 2024-04-15 | 2024-04-15 | 127577 | 38225 | 38225
20 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Design | In-Progress | 2024-04-16 | 2024-08-30 |  | 595359 | 595359 | 162789
20 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | Scope | Complete | 2021-09-21 | 2022-04-04 | 2022-04-04 | 235540 | 284437 | 284437
20 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | Design | Complete | 2022-04-04 | 2022-05-31 | 2022-08-16 | 1059930 | 674759 | 533245
20 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | Construction | In-Progress | 2023-04-12 | 2024-09-03 |  | 13366895 | 12286355 | 10371483
20 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | CM,F&E | In-Progress | 2023-04-12 | 2024-09-03 |  | 1884320 | 1772240 | 1259247
20 | TELECOM. ARTS & TECH. HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 2019-05-31 | 2019-10-15 | 2019-12-13 | 54000 | 46070 | 46070
20 | TELECOM. ARTS & TECH. HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | Complete | 2020-01-14 | 2020-06-15 | 2021-05-11 | 270000 | 247422 | 247422
20 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2019-07-09 | 2019-10-07 | 2020-02-12 | 30510 | 61315 | 61315
20 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2020-02-12 | 2020-08-13 | 2021-06-03 | 152550 | 273584 | 271097
20 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2023-04-10 | 2024-04-08 |  | 3432375 | 3098181 | 1560949
20 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2023-04-10 | 2024-04-08 |  | 213570 | 170159 | 168384
20 | FORT HAMILTON HS - K | SCA CIP | REPLACE 6' FIRE DOMESTIC WATER MAIN VALVES | Scope | Complete | 2019-06-04 | 2019-08-05 | 2019-07-12 | 8314 | 2293 | 2293
20 | FORT HAMILTON HS - K | SCA CIP | REPLACE 6' FIRE DOMESTIC WATER MAIN VALVES | Design | Complete | 2019-07-12 | 2019-11-12 | 2021-08-27 | 37411 | 69871 | 68642
20 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | Scope | Complete | 2021-06-15 | 2021-10-15 | 2021-10-27 | 37080 | 142242 | 142242
20 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | Design | Complete | 2021-12-08 | 2022-05-02 | 2022-05-11 | 185400 | 293166 | 287635
20 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | Construction | In-Progress | 2022-07-11 | 2023-10-03 |  | 4171500 | 3845311 | 3283992
20 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | CM,F&E | In-Progress | 2022-07-11 | 2023-10-03 |  | 259560 | 288226 | 284586
20 | FORT HAMILTON HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / IDA CLIMATE CONTROL / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES / IDA POOL BOILER / IDA ELECTRICAL SYSTEMS | Scope | Complete | 2022-01-31 | 2022-05-31 | 2023-06-13 | 269669 | 303265 | 298564
20 | FORT HAMILTON HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / IDA CLIMATE CONTROL / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES / IDA POOL BOILER / IDA ELECTRICAL SYSTEMS | Design | Complete | 2023-06-14 | 2023-11-16 | 2024-04-09 | 1339243 | 655872 | 620027
20 | FORT HAMILTON HS - K | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Scope | Complete | 2023-12-11 | 2024-03-13 | 2024-03-08 | 10712 | 22492 | 22492
20 | FORT HAMILTON HS - K | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Design | In-Progress | 2024-03-12 | 2024-07-11 |  | 48205 | 48205 | 4471
20 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-06-30 | 2022-11-16 | 2023-06-01 | 296709 | 316715 | 312909
20 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-06-12 | 2023-11-14 | 2023-12-12 | 1477044 | 679169 | 651816
20 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | Scope | Complete | 2021-01-12 | 2022-09-22 | 2022-08-25 | 178605 | 241469 | 227495
20 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | Design | Complete | 2022-08-26 | 2022-12-28 | 2023-04-05 | 892900 | 779201 | 556697
20 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | Construction | In-Progress | 2023-09-18 | 2026-03-05 |  | 20079437 | 18742924 | 1194783
20 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | CM,F&E | In-Progress | 2023-09-18 | 2026-03-05 |  | 1256508 | 247082 | 239629
20 | PRE-K CENTER @ 412 63 STREET - BROOKLYN | PRE-K | LEASE | Scope | Complete | 2016-11-10 | 2017-02-22 | 2017-02-22 | 142794 | 67386 | 67386
20 | PRE-K CENTER @ 412 63 STREET - BROOKLYN | PRE-K | LEASE | Design | Complete | 2017-08-08 | 2017-11-22 | 2024-08-08 | 642574 | 655057 | 629396
20 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2020-03-19 | 2020-08-11 | 2020-08-11 | 1339880 | 1383637 | 1353330
20 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 2020-08-12 | 2021-03-19 | 2021-04-09 | 6029460 | 5418189 | 5074329
20 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2021-09-13 | 2024-09-03 |  | 76038190 | 72313539 | 64499132
20 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2021-09-13 | 2024-09-03 |  | 10719040 | 6357057 | 5405025
20 | P.S. 163 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2024-02-05 | 2024-06-20 | 2024-07-22 | 24271 | 32690 | 23790
20 | P.S. 163 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 2024-08-13 | 2025-01-16 |  | 109148 | 109148 | 7292
20 | P.S. 163 - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 2022-09-06 | 2023-01-25 | 2023-02-01 | 59301 | 59977 | 58416
20 | P.S. 163 - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2023-06-28 | 2024-05-22 |  | 869744 | 560493 | 504771
20 | P.S. 163 - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | CM,F&E | In-Progress | 2023-06-28 | 2024-05-22 |  | 88071 | 87792 | 82589
21 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | Scope | Complete | 2019-09-05 | 2020-01-24 | 2021-06-22 | 115935 | 142083 | 139366
21 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | Design | Complete | 2021-07-12 | 2021-12-13 | 2022-01-25 | 572050 | 334896 | 334896
21 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | Construction | In-Progress | 2022-06-13 | 2024-03-03 |  | 12211563 | 11343258 | 7866539
21 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | CM,F&E | In-Progress | 2022-06-13 | 2024-03-03 |  | 868733 | 583399 | 576842
21 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-19 | 2022-11-17 | 2022-08-04 | 5380 | 1486 | 1486
21 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-08-04 | 2023-02-02 | 2023-01-11 | 24210 | 5941 | 5941
21 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-27 | 2024-08-21 |  | 312040 | 277100 | 188425
21 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-27 | 2024-08-21 |  | 129400 | 108295 | 99353
21 | I.S. 98 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION | Design | In-Progress | 2024-07-17 | 2024-11-18 |  | 45000 | 29794 | 2601
21 | I.S. 98 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | In-Progress | 2024-09-12 | 2025-01-17 |  | 7515 | 1186 | 1186
21 | P.S. 90 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-05-20 | 2021-10-05 | 2022-12-16 | 55740 | 118880 | 106378
21 | P.S. 90 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 2023-01-25 | 2023-06-27 |  | 278019 | 278019 | 146809
21 | P.S. 90 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-03-18 | 2024-07-17 | 2024-04-10 | 4495 | 2543 | 2543
21 | P.S. 90 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-10 | 2024-10-04 | 2024-08-22 | 20228 | 10171 | 10171
21 | P.S. 90 - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | Design | In-Progress | 2023-02-03 | 2023-07-07 |  | 426000 | 279420 | 157112
21 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2020-02-03 | 2020-07-02 | 2020-05-19 | 125407 | 120818 | 120818
21 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2020-05-20 | 2020-10-21 | 2020-08-03 | 609827 | 437473 | 437473
21 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2022-04-25 | 2024-07-12 |  | 12232723 | 11381292 | 7259902
21 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2022-04-25 | 2024-07-12 |  | 1006895 | 970000 | 962405
21 | P.S. 95 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 2024-03-08 | 2024-07-24 | 2024-07-22 | 27996 | 65259 | 22104
21 | P.S. 95 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | In-Progress | 2024-07-24 | 2024-12-26 |  | 134901 | 134901 | 4967
21 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE / FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 2022-03-01 | 2022-06-01 | 2022-10-04 | 196467 | 103816 | 96698
21 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE / FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2023-11-06 | 2024-11-04 |  | 2881512 | 2681240 | 1110743
21 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE / FY21 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-11-06 | 2024-11-04 |  | 196467 | 216628 | 214587
21 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 2020-05-28 | 2020-11-24 | 2020-10-08 | 198872 | 272439 | 272439
21 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 2020-10-16 | 2021-06-15 | 2021-04-27 | 986690 | 505708 | 496677
21 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | Complete | 2021-08-03 | 2024-08-01 | 2024-08-01 | 21536856 | 19755955 | 18380793
21 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | Complete | 2021-08-03 | 2024-08-01 | 2024-08-01 | 1449656 | 1171266 | 1155469
21 | P.S. 97 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / EXISTING BUILDING WORK | Scope | Complete | 2017-05-09 | 2018-03-21 | 2018-02-21 | 129190 | 140729 | 140729
21 | P.S. 97 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / EXISTING BUILDING WORK | Design | Complete | 2018-02-21 | 2018-06-18 | 2020-02-04 | 602780 | 642668 | 620376
21 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2019-05-07 | 2019-09-20 | 2019-11-04 | 127710 | 137712 | 132120
21 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2019-11-13 | 2020-05-01 | 2021-11-19 | 638550 | 567046 | 566096
21 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2022-08-08 | 2024-08-06 |  | 14367375 | 14332099 | 10243899
21 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2022-08-08 | 2024-08-06 |  | 1119367 | 665089 | 553120
21 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-23 | 2023-05-22 | 2023-01-31 | 4120 | 2728 | 2728
21 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-31 | 2023-07-27 | 2023-04-04 | 18540 | 10914 | 10914
21 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-14 | 2024-06-07 |  | 238960 | 229347 | 173787
21 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-14 | 2024-06-07 |  | 157810 | 145572 | 86806
21 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2020-05-14 | 2020-11-16 | 2020-10-16 | 211376 | 379580 | 375299
21 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2020-10-29 | 2021-06-15 | 2021-07-01 | 1053403 | 645275 | 626976
21 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2022-04-11 | 2024-04-09 |  | 23400916 | 21549130 | 18281474
21 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2022-04-11 | 2024-04-09 |  | 1505699 | 657813 | 654951
21 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Scope | Complete | 2020-08-04 | 2020-12-04 | 2021-02-10 | 39980 | 52579 | 52579
21 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Design | Complete | 2021-02-17 | 2021-07-16 | 2021-08-31 | 199900 | 199966 | 138973
21 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Construction | In-Progress | 2024-05-02 | 2026-05-01 |  | 4497750 | 4384561 | 268011
21 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | CM,F&E | In-Progress | 2024-05-02 | 2026-05-01 |  | 279860 | 90015 | 89906
21 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-25 | 2023-05-24 | 2023-02-03 | 4000 | 2519 | 2519
21 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-03 | 2023-08-01 | 2023-04-04 | 18000 | 10077 | 10077
21 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-14 | 2024-06-07 |  | 232000 | 225456 | 176906
21 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-14 | 2024-06-07 |  | 101331 | 84899 | 80655
21 | P.S. 101 - BROOKLYN | SCA CIP RESOA | RESO A IPDVS SYSTEM | Design | Complete | 2023-05-16 | 2023-11-13 | 2023-10-18 | 14657 | 3638 | 3638
21 | P.S. 101 - BROOKLYN | SCA CIP RESOA | RESO A IPDVS SYSTEM | Construction | In-Progress | 2024-04-17 | 2025-03-12 |  | 214965 | 187841 | 7541
21 | P.S. 101 - BROOKLYN | SCA CIP RESOA | RESO A IPDVS SYSTEM | CM,F&E | In-Progress | 2024-04-17 | 2025-03-12 |  | 18921 | 21213 | 7815
21 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-20 | 2022-11-18 | 2022-08-04 | 4260 | 1263 | 1263
21 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-08-04 | 2023-02-02 | 2023-01-11 | 19170 | 5052 | 5052
21 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-27 | 2024-08-21 |  | 247080 | 221100 | 157218
21 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-27 | 2024-08-21 |  | 128517 | 112801 | 106788
21 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2022-04-08 | 2022-10-04 | 2022-08-25 | 11980 | 31424 | 31424
21 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2022-08-26 | 2023-02-27 | 2023-02-23 | 59900 | 125691 | 125691
21 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2023-12-14 | 2024-11-07 |  | 1347750 | 1266436 | 213105
21 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2023-12-14 | 2024-11-07 |  | 83860 | 161354 | 44590
21 | P.S. 128 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2022-05-26 | 2022-09-27 | 2023-02-22 | 44224 | 35644 | 35644
21 | P.S. 128 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2023-03-03 | 2023-08-03 | 2023-05-11 | 221120 | 125181 | 111956
21 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | Scope | Complete | 2021-01-26 | 2021-05-26 | 2022-01-05 | 69210 | 63370 | 63370
21 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | Design | Complete | 2022-01-06 | 2022-07-11 | 2023-04-04 | 346050 | 323682 | 253530
21 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | Construction | In-Progress | 2023-12-04 | 2025-12-02 |  | 7786124 | 7755251 | 2250566
21 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | CM,F&E | In-Progress | 2023-12-04 | 2025-12-02 |  | 486055 | 127070 | 126146
21 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 2021-01-18 | 2021-05-18 | 2021-05-12 | 38000 | 54826 | 54826
21 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 2021-05-18 | 2021-10-19 | 2021-10-07 | 190000 | 104229 | 94101
21 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2023-09-11 | 2025-03-03 |  | 4275000 | 4047185 | 2610353
21 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2023-09-11 | 2025-03-03 |  | 266000 | 143646 | 132059
21 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 2021-01-29 | 2021-05-28 | 2022-02-09 | 48200 | 130163 | 130163
21 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 2022-02-09 | 2022-07-08 | 2022-09-07 | 241000 | 241790 | 208542
21 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2023-09-05 | 2024-09-03 |  | 5422500 | 8612773 | 4257102
21 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2023-09-05 | 2024-09-03 |  | 337400 | 421540 | 374712
21 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2020-02-14 | 2022-11-22 | 2022-10-27 | 199005 | 237655 | 237655
21 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2022-11-02 | 2023-04-07 | 2023-03-10 | 990021 | 1135584 | 715937
21 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2023-09-11 | 2026-09-09 |  | 21842519 | 20504618 | 2270648
21 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-09-11 | 2026-09-09 |  | 1430576 | 890192 | 586566
21 | P.S. 188 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-19 | 2024-08-20 | 2024-04-25 | 5815 | 4145 | 4145
21 | P.S. 188 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-25 | 2024-10-22 | 2024-08-22 | 26166 | 16579 | 16579
21 | P.S. 188 - BROOKLYN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-10-26 | 2022-03-31 | 2022-07-13 | 86564 | 65511 | 65511
21 | P.S. 188 - BROOKLYN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2023-04-21 | 2024-04-19 |  | 1269601 | 749118 | 656991
21 | P.S. 188 - BROOKLYN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-04-21 | 2024-04-19 |  | 86564 | 119944 | 117864
21 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2023-06-14 | 2023-12-13 | 2023-10-06 | 135720 | 107428 | 107428
21 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-11-09 | 2024-06-28 | 2024-04-29 | 678600 | 228967 | 228481
21 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2024-07-22 | 2027-01-07 |  | 15268501 | 13926131 | 87131
21 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2024-07-22 | 2027-01-07 |  | 950040 | 63536 | 63536
21 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-06-15 | 2023-10-17 | 2023-07-03 | 3920 | 1790 | 1790
21 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-03 | 2023-12-29 | 2023-10-18 | 17640 | 7162 | 7162
21 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-04-17 | 2025-03-12 |  | 227360 | 205470 | 3170
21 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-04-17 | 2025-03-12 |  | 42140 | 26250 | 4740
21 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2021-06-15 | 2021-12-14 | 2021-10-28 | 241601 | 317367 | 316455
21 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2021-11-17 | 2022-06-30 | 2022-04-29 | 1208001 | 552352 | 552352
21 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2022-07-18 | 2024-07-16 |  | 27180000 | 24818831 | 18320549
21 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-07-18 | 2024-07-16 |  | 1691200 | 310766 | 310224
21 | P.S. 209 - BROOKLYN | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-01-17 | 2023-04-17 | 2023-04-24 | 21878 | 57514 | 57514
21 | P.S. 209 - BROOKLYN | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2023-04-25 | 2023-09-11 | 2023-10-31 | 109392 | 125351 | 119571
21 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-13 | 2023-04-14 | 2023-01-06 | 3400 | 4733 | 4733
21 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-06 | 2023-07-05 | 2023-04-04 | 15300 | 18933 | 18933
21 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 197200 | 194715 | 132701
21 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 78931 | 81891 | 76002
21 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | Scope | Complete | 2020-08-04 | 2020-12-04 | 2021-01-29 | 54940 | 85152 | 85152
21 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | Design | Complete | 2021-02-02 | 2021-07-09 | 2021-07-09 | 274700 | 326223 | 239166
21 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | Construction | In-Progress | 2024-08-02 | 2026-08-01 |  | 6180750 | 5935490 | 238257
21 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | CM,F&E | In-Progress | 2024-08-02 | 2026-08-01 |  | 384579 | 165938 | 90178
21 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-19 | 2023-04-20 | 2023-01-10 | 3940 | 5119 | 5119
21 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-10 | 2023-07-07 | 2023-04-04 | 17730 | 20479 | 20479
21 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-21 | 2024-06-14 |  | 228520 | 207372 | 128592
21 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-21 | 2024-06-14 |  | 87740 | 77280 | 71023
21 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 2023-06-06 | 2023-12-05 | 2023-10-10 | 240689 | 225611 | 222440
21 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | Complete | 2023-10-31 | 2024-06-28 | 2024-04-18 | 1195757 | 345413 | 345413
21 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Construction | In-Progress | 2024-07-22 | 2027-07-05 |  | 26239413 | 23748589 | 130614
21 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | CM,F&E | In-Progress | 2024-07-22 | 2027-07-05 |  | 1742491 | 84462 | 83958
21 | I.S. 228 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2021-07-13 | 2021-11-10 | 2021-07-19 | 4160 | 5651 | 5651
21 | I.S. 228 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-07-19 | 2022-01-14 | 2021-12-22 | 18720 | 22606 | 22606
21 | I.S. 228 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 2022-05-09 | 2023-02-02 | 2024-04-30 | 241280 | 204322 | 181856
21 | I.S. 228 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 2022-05-09 | 2023-02-02 | 2024-04-30 | 236304 | 227718 | 152607
21 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-02 | 2023-06-02 | 2023-02-03 | 4444 | 7306 | 7306
21 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-03 | 2023-08-01 | 2023-05-03 | 19997 | 29225 | 29225
21 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-16 | 2024-07-10 |  | 257733 | 235514 | 193460
21 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-16 | 2024-07-10 |  | 112345 | 95132 | 85423
21 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2022-05-31 | 2022-11-23 | 2022-09-26 | 270000 | 197865 | 185913
21 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 2022-09-28 | 2023-06-12 | 2023-04-26 | 1350000 | 386176 | 385788
21 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 2023-10-23 | 2026-05-09 |  | 30375002 | 27442768 | 2840608
21 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-10-23 | 2026-05-09 |  | 1891584 | 150065 | 135062
21 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-18 | 2023-05-17 | 2023-01-24 | 5467 | 7590 | 7590
21 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-24 | 2023-07-20 | 2023-05-03 | 24599 | 30359 | 30359
21 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-16 | 2024-07-10 |  | 317058 | 287168 | 233027
21 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-16 | 2024-07-10 |  | 134217 | 112872 | 109196
21 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | Scope | Complete | 2019-11-05 | 2020-03-06 | 2020-03-06 | 1078540 | 768510 | 768510
21 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | Design | Complete | 2020-03-09 | 2020-09-01 | 2021-05-11 | 4853430 | 2852384 | 2463512
21 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | Construction | In-Progress | 2021-12-20 | 2024-09-03 |  | 61207145 | 58974564 | 57672969
21 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | CM,Art,F&E | In-Progress | 2021-12-20 | 2024-09-03 |  | 8628320 | 7686312 | 5706303
21 | P.S. 253 - BROOKLYN | SCA CIP | EXISTING BUILDING RENOVATION WORK | Scope | Complete | 2021-06-03 | 2021-12-13 | 2022-02-09 | 33418 | 65914 | 65914
21 | P.S. 253 - BROOKLYN | SCA CIP | EXISTING BUILDING RENOVATION WORK | Design | Complete | 2022-02-15 | 2022-08-04 | 2024-03-26 | 167092 | 184442 | 168699
21 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 2022-07-08 | 2022-11-23 | 2023-08-08 | 148170 | 212313 | 212313
21 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 2023-08-16 | 2024-01-22 | 2024-04-01 | 740850 | 633306 | 473821
21 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | In-Progress | 2024-07-12 | 2026-07-01 |  | 16669126 | 15386142 | 197768
21 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | In-Progress | 2024-07-12 | 2026-07-01 |  | 1037190 | 222372 | 70543
21 | I.S. 281 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-09-14 | 2021-11-04 | 2022-01-14 | 60605 | 61677 | 60302
21 | I.S. 281 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2022-08-30 | 2023-07-25 |  | 888861 | 860069 | 656471
21 | I.S. 281 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2022-08-30 | 2023-07-25 |  | 60605 | 111174 | 102201
21 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-01 | 2023-06-29 | 2023-03-08 | 3793 | 1915 | 1915
21 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-08 | 2023-08-31 | 2023-04-26 | 17068 | 7659 | 7659
21 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-19 | 2024-09-12 |  | 219988 | 201053 | 52632
21 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-19 | 2024-09-12 |  | 118534 | 102232 | 92203
21 | P.S. 288 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 2022-10-11 | 2023-03-16 | 2023-03-21 | 97500 | 88374 | 83475
21 | P.S. 288 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2023-09-18 | 2025-01-09 |  | 1430000 | 1341596 | 619471
21 | P.S. 288 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-09-18 | 2025-01-09 |  | 97500 | 82028 | 82028
21 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-06-22 | 2022-11-07 | 2023-01-05 | 119977 | 249570 | 242172
21 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2023-01-18 | 2023-06-20 | 2023-05-09 | 589908 | 489475 | 411741
21 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 2023-09-18 | 2026-02-03 |  | 12409921 | 11291104 | 1338586
21 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-09-18 | 2026-02-03 |  | 916197 | 296840 | 281163
21 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-11-15 | 2024-05-13 | 2024-03-20 | 30000 | 11340 | 11340
21 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSIONS/PARTITIONING / PATH OF TRAVEL RESO A ROOM CONVERSIONS/PARTITIONING | Design | Complete | 2023-10-19 | 2024-02-26 | 2024-09-20 | 79218 | 56120 | 36764
21 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-07 | 2022-11-22 | 2023-06-29 | 73554 | 182895 | 182895
21 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-07-24 | 2023-12-26 | 2023-12-18 | 363605 | 357639 | 264311
21 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-08-02 | 2026-08-01 |  | 7820974 | 7382858 | 208851
21 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-08-02 | 2026-08-01 |  | 546101 | 141706 | 57103
21 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-01 | 2023-06-29 | 2023-03-08 | 3784 | 1633 | 1633
21 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-08 | 2023-08-31 | 2023-04-26 | 17028 | 6529 | 6529
21 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-19 | 2024-09-12 |  | 219478 | 198038 | 97842
21 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-19 | 2024-09-12 |  | 133287 | 123457 | 117302
21 | P.S. 329 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Design | Complete | 2021-09-17 | 2021-11-08 | 2021-11-22 | 62727 | 61457 | 61457
21 | P.S. 329 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Construction | Complete | 2022-08-26 | 2023-06-21 | 2023-06-21 | 920004 | 512716 | 442357
21 | P.S. 329 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | CM,F&E | Complete | 2022-08-26 | 2023-06-21 | 2023-06-21 | 62727 | 58557 | 57600
21 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2022-02-28 | 2022-07-18 | 2022-07-18 | 1554220 | 1292430 | 1222007
21 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 2022-07-19 | 2023-03-03 | 2023-03-03 | 6993990 | 4474860 | 4121562
21 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2023-09-01 | 2026-09-03 |  | 88201985 | 79067861 | 15305246
21 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2023-09-01 | 2026-09-03 |  | 12433760 | 5527804 | 1120715
21 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2022-05-03 | 2022-05-03 | 2022-05-03 | 21847 | 19313 | 19313
21 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 2022-05-04 | 2022-08-12 | 2022-10-18 | 109235 | 56691 | 56691
21 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Construction | In-Progress | 2022-12-08 | 2023-03-07 |  | 2457798 | 2333489 | 1179860
21 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2022-12-08 | 2023-03-07 |  | 152930 | 253634 | 221063
21 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2019-05-28 | 2019-08-26 | 2020-02-18 | 10270 | 37651 | 37651
21 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2020-02-18 | 2020-08-18 | 2022-07-08 | 51350 | 239766 | 102165
21 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2023-05-03 | 2024-05-01 |  | 1155375 | 1189388 | 886518
21 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2023-05-03 | 2024-05-01 |  | 71890 | 215659 | 78059
21 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2022-07-07 | 2022-11-22 | 2023-03-14 | 19702 | 56015 | 56015
21 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2023-03-23 | 2023-08-23 | 2023-10-18 | 98512 | 133249 | 44141
21 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2024-08-12 | 2026-02-02 |  | 2216530 | 2062846 | 5044
21 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-08-12 | 2026-02-02 |  | 137917 | 94146 | 9103
21 | INTERNATIONAL HIGH SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2021-04-08 | 2021-08-06 | 2021-04-26 | 5600 | 6499 | 6499
21 | INTERNATIONAL HIGH SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-04-26 | 2021-10-20 | 2021-09-29 | 25200 | 25997 | 25997
21 | INTERNATIONAL HIGH SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 2022-05-09 | 2023-02-02 | 2024-04-30 | 324800 | 307728 | 259689
21 | INTERNATIONAL HIGH SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 2022-05-09 | 2023-02-02 | 2024-04-30 | 341579 | 322590 | 215488
21 | LEADERS HIGH SCHOOL - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY21 RESO A LIBRARY UPGRADE | Design | Complete | 2022-02-11 | 2022-06-28 | 2022-05-09 | 104081 | 112966 | 112966
21 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | RESO A ATHLETIC FIELD | Design | In-Progress | 2024-08-13 | 2024-12-17 |  | 16199 | 30137 | 5947
21 | MIDWOOD HS - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / IDA PAVED AREAS- BLACKTOP / IDA HEATING PLANT UPGRADE | Scope | Complete | 2022-04-06 | 2022-07-06 | 2023-04-21 | 39483 | 81218 | 81218
21 | MIDWOOD HS - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / IDA PAVED AREAS- BLACKTOP / IDA HEATING PLANT UPGRADE | Design | Complete | 2023-04-24 | 2023-09-25 | 2023-11-01 | 193391 | 208442 | 165022
21 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Scope | Complete | 2023-09-01 | 2024-03-13 | 2024-02-16 | 162484 | 153330 | 153330
21 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Design | Complete | 2024-02-28 | 2024-07-01 | 2024-05-01 | 812422 | 441050 | 391368
21 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE / FY20 RESO A CAFETERIA UPGRADE | Design | Complete | 2021-11-17 | 2022-03-18 | 2022-10-12 | 60716 | 96000 | 61785
21 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE / FY20 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2023-10-05 | 2024-08-29 |  | 890495 | 575319 | 217539
21 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE / FY20 RESO A CAFETERIA UPGRADE | CM,F&E | In-Progress | 2023-10-05 | 2024-08-29 |  | 314181 | 332901 | 46521
21 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | ATHLETIC FIELD BLEACHERS C OF O | Scope | Complete | 2023-05-23 | 2023-09-22 | 2023-09-19 | 11722 | 16643 | 16643
21 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | ATHLETIC FIELD BLEACHERS C OF O | Design | Complete | 2023-09-28 | 2024-04-05 | 2024-03-11 | 52748 | 49376 | 8364
21 | EDWARD R. MURROW HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA GYM PARTITION REPLACEMENT | Scope | Complete | 2021-11-30 | 2022-04-04 | 2022-08-01 | 20049 | 18708 | 18708
21 | EDWARD R. MURROW HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA GYM PARTITION REPLACEMENT | Design | Complete | 2022-08-10 | 2022-12-28 | 2023-02-08 | 96465 | 62506 | 59144
21 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | Scope | Complete | 2018-10-30 | 2021-03-04 | 2020-12-17 | 416999 | 388107 | 385817
21 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | Design | Complete | 2021-01-14 | 2021-09-14 | 2021-05-06 | 2085001 | 884154 | 873792
21 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | Construction | Complete | 2021-07-06 | 2024-07-04 | 2024-07-04 | 46912500 | 43886353 | 40557786
21 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | CM,F&E | Complete | 2021-07-06 | 2024-07-04 | 2024-07-04 | 2919000 | 1563297 | 1542847
21 | JOHN DEWEY HS - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 2019-03-27 | 2019-08-26 | 2021-05-15 | 786600 | 873670 | 813811
21 | JOHN DEWEY HS - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2021-09-14 | 2022-09-13 |  | 11536800 | 10458406 | 8941391
21 | JOHN DEWEY HS - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2021-09-14 | 2022-09-13 |  | 786600 | 720851 | 698495
21 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Scope | Complete | 2021-07-01 | 2021-10-29 | 2021-11-01 | 544440 | 413438 | 413438
21 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Design | Complete | 2021-11-02 | 2022-04-15 | 2022-05-13 | 2449980 | 771174 | 720912
21 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 2022-09-12 | 2025-09-03 |  | 30896970 | 28731287 | 26665755
21 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 2022-09-12 | 2025-09-03 |  | 4355520 | 3041037 | 1492148
21 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | Scope | Complete | 2018-09-10 | 2019-01-10 | 2020-02-04 | 22790 | 25549 | 25549
21 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | Design | Complete | 2020-02-04 | 2020-06-24 | 2022-08-12 | 113950 | 120218 | 118558
21 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | Construction | In-Progress | 2023-08-14 | 2024-08-12 |  | 2563875 | 2411259 | 1556747
21 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | CM,F&E | In-Progress | 2023-08-14 | 2024-08-12 |  | 159530 | 162761 | 147871
21 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Scope | Complete | 2018-10-24 | 2019-03-14 | 2019-10-22 | 48970 | 118234 | 113384
21 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Design | Complete | 2019-10-22 | 2020-03-26 | 2023-05-17 | 238879 | 385645 | 344893
21 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Construction | In-Progress | 2023-10-04 | 2025-10-02 |  | 4858162 | 4506233 | 1022375
21 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | CM,F&E | In-Progress | 2023-10-04 | 2025-10-02 |  | 387585 | 223514 | 220602
21 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2019-11-01 | 2020-02-05 | 2020-03-31 | 22680 | 40107 | 40107
21 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2020-03-31 | 2020-09-30 | 2020-06-30 | 113400 | 208080 | 208080
21 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2022-01-24 | 2023-04-18 |  | 2551500 | 2404668 | 2103399
21 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2022-01-24 | 2023-04-18 |  | 158760 | 150004 | 150004
21 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-17 | 2023-06-20 | 2023-03-02 | 4044 | 1176 | 1176
21 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-02 | 2023-08-25 | 2023-05-03 | 18196 | 4704 | 4704
21 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-20 | 2024-11-18 |  | 234530 | 210873 | 119827
21 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-20 | 2024-11-18 |  | 101632 | 77361 | 28582
21 | K721 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A KITCHEN UPGRADE | Design | Complete | 2022-08-11 | 2023-01-17 | 2023-02-02 | 150000 | 96752 | 85945
21 | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Scope | Complete | 2021-03-02 | 2022-08-04 | 2022-11-02 | 18945 | 11164 | 4388
21 | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Design | Complete | 2022-11-02 | 2023-03-01 | 2023-04-26 | 94132 | 76053 | 13991
21 | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Construction | In-Progress | 2023-11-13 | 2025-05-05 |  | 2066842 | 1927389 | 547986
21 | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | CM,F&E | In-Progress | 2023-11-13 | 2025-05-05 |  | 137044 | 154233 | 54505
22 | I.S. 14 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-07-06 | 2023-11-21 | 2024-02-23 | 22437 | 57183 | 57183
22 | I.S. 14 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 2024-02-26 | 2024-07-26 | 2024-05-15 | 112188 | 147503 | 11395
22 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2019-07-24 | 2019-12-03 | 2020-01-10 | 104430 | 136045 | 136045
22 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2020-01-15 | 2020-06-16 | 2020-06-26 | 522150 | 537265 | 520608
22 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2021-04-14 | 2023-01-03 |  | 11748374 | 10732253 | 9271137
22 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-04-14 | 2023-01-03 |  | 731009 | 1021113 | 1012880
22 | P.S. 52 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 2022-03-03 | 2022-07-01 | 2022-07-15 | 17405 | 35419 | 132
22 | P.S. 52 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 2022-07-15 | 2022-07-15 | 2022-07-15 | 78324 | 37813 | 529
22 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2022-04-29 | 2022-09-29 | 2022-07-07 | 131097 | 51786 | 51786
22 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-07-11 | 2022-12-12 | 2022-11-17 | 645809 | 293033 | 209995
22 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2024-07-18 | 2027-01-03 |  | 13693621 | 12461123 | 118422
22 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2024-07-18 | 2027-01-03 |  | 990258 | 148421 | 148066
22 | P.S. 119 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-06-14 | 2021-10-28 | 2021-11-08 | 27291 | 63311 | 45060
22 | P.S. 119 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2021-11-10 | 2022-04-15 | 2022-04-27 | 134863 | 105391 | 105391
22 | P.S. 119 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | Complete | 2023-02-13 | 2024-05-07 | 2023-11-02 | 2896817 | 2747683 | 2713205
22 | P.S. 119 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 2023-02-13 | 2024-05-07 | 2023-11-02 | 202967 | 274781 | 274239
22 | P.S. 119 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | Complete | 2024-03-05 | 2024-07-19 | 2024-08-13 | 44481 | 45420 | 27896
22 | P.S. 119 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2024-03-06 | 2024-06-05 | 2024-04-12 | 1973 | 1973 | 1973
22 | P.S. 119 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2024-04-23 | 2024-08-26 | 2024-08-13 | 7892 | 7892 | 7892
22 | P.S. 139 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2023-05-15 | 2023-09-29 | 2023-09-26 | 10606 | 18496 | 18412
22 | P.S. 139 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2023-10-05 | 2024-03-12 | 2024-03-19 | 47728 | 37303 | 36714
22 | P.S. 139 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-06-05 | 2023-10-19 | 2023-10-17 | 48600 | 58018 | 48457
22 | P.S. 139 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2024-05-08 | 2025-04-02 |  | 712800 | 679514 | 6014
22 | P.S. 139 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2024-05-08 | 2025-04-02 |  | 48600 | 59777 | 9881
22 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2015-10-20 | 2016-01-22 | 2015-12-21 | 18645 | 31453 | 31453
22 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2016-01-28 | 2016-07-29 | 2016-06-03 | 74580 | 131792 | 123019
22 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2018-01-08 | 2018-11-03 |  | 1398375 | 2363031 | 1963952
22 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2018-01-08 | 2018-11-03 |  | 87010 | 941544 | 874855
22 | P.S. 315 - BROOKLYN | SCA CIP | HVAC UPGRADE / BMS UPGRADE | Scope | Complete | 2022-11-10 | 2023-04-17 | 2023-11-15 | 84809 | 103652 | 103652
22 | P.S. 315 - BROOKLYN | SCA CIP | HVAC UPGRADE / BMS UPGRADE | Design | Complete | 2023-11-28 | 2024-04-30 | 2024-08-26 | 424041 | 331340 | 182954
22 | P.S. 315 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS / FLOOD ELIMINATION / PAVED AREA- CONCRETE | Scope | Complete | 2023-06-12 | 2023-12-11 | 2023-11-03 | 369898 | 245642 | 244175
22 | P.S. 315 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS / FLOOD ELIMINATION / PAVED AREA- CONCRETE | Design | In-Progress | 2024-08-15 | 2025-01-21 |  | 1840084 | 1840084 | 228928
22 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-04-21 | 2023-09-07 | 2023-09-01 | 33000 | 47090 | 42898
22 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-04-16 | 2024-08-30 |  | 87000 | 71782 | 5378
22 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2021-03-26 | 2022-11-22 | 2023-07-19 | 237237 | 395766 | 388860
22 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2023-08-21 | 2024-01-25 | 2024-04-04 | 1167416 | 853563 | 355534
22 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2024-07-18 | 2027-01-03 |  | 24643557 | 22971249 | 386814
22 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2024-07-18 | 2027-01-03 |  | 1801406 | 151941 | 149860
22 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-02-26 | 2021-07-13 | 2021-11-29 | 109900 | 96167 | 96167
22 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2021-11-29 | 2022-05-17 | 2023-02-08 | 549500 | 370800 | 251508
22 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2023-09-18 | 2025-11-05 |  | 12363750 | 11418956 | 1170165
22 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2023-09-18 | 2025-11-05 |  | 771474 | 303802 | 296370
22 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2021-06-02 | 2021-10-18 | 2021-12-22 | 19147 | 30026 | 30026
22 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2021-12-22 | 2022-05-25 | 2022-05-05 | 95734 | 80669 | 78896
22 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2023-01-09 | 2024-04-02 |  | 2154024 | 1946000 | 1054395
22 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-01-09 | 2024-04-02 |  | 134028 | 302493 | 297372
22 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | Scope | Complete | 2023-11-28 | 2024-04-15 | 2024-02-08 | 13400 | 20747 | 20747
22 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | Design | Complete | 2024-02-12 | 2024-07-15 | 2024-05-14 | 67000 | 59203 | 59203
22 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | Construction | In-Progress | 2024-08-05 | 2025-08-04 |  | 1507500 | 1478035 | 26605
22 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | CM,F&E | In-Progress | 2024-08-05 | 2025-08-04 |  | 93800 | 138896 | 138896
22 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY24 RESO A (MA) CAFETERIA UPGRADE | Design | In-Progress | 2024-04-17 | 2024-09-03 |  | 77043 | 57872 | 30069
22 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A (MA) CAFETERIA UPGRADE | Scope | Complete | 2024-04-09 | 2024-07-11 | 2024-06-10 | 10748 | 10748 | 795
22 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A (MA) CAFETERIA UPGRADE | Design | In-Progress | 2024-06-17 | 2024-10-16 |  | 3181 | 3181 | 3181
22 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | Scope | Complete | 2022-05-10 | 2022-08-26 | 2022-08-26 | 1192000 | 857109 | 848375
22 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | Design | Complete | 2022-08-29 | 2023-03-03 | 2023-04-12 | 5364000 | 3101772 | 1422396
22 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | Construction | In-Progress | 2024-02-21 | 2026-09-03 |  | 67646000 | 60728323 | 403475
22 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | CM,Art,F&E | In-Progress | 2024-02-21 | 2026-09-03 |  | 9536000 | 4153753 | 744734
22 | P.S. 206 - BROOKLYN | SCA CIP | EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING-EXISTING BUILDING-INTERIOR RENOVATIONS/PROGRAM ACCESSIBILITY | Scope | Complete | 2022-09-21 | 2023-01-26 | 2023-03-13 | 91591 | 97679 | 62772
22 | P.S. 206 - BROOKLYN | SCA CIP | EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING-EXISTING BUILDING-INTERIOR RENOVATIONS/PROGRAM ACCESSIBILITY | Design | Complete | 2023-03-15 | 2023-08-15 | 2023-10-23 | 455057 | 239908 | 215541
22 | P.S. 206 - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2022-07-22 | 2022-07-22 | 2022-07-22 | 33672 | 83785 | 83785
22 | P.S. 206 - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 2022-07-25 | 2022-11-18 | 2023-03-15 | 168359 | 241785 | 241784
22 | P.S. 206 - BROOKLYN | SCA CIP | DEMOLITION | Construction | Complete | 2023-07-06 | 2024-03-01 | 2024-05-01 | 3788071 | 3614108 | 3280418
22 | P.S. 206 - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | Complete | 2023-07-06 | 2024-03-01 | 2024-05-01 | 235702 | 266463 | 255377
22 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-14 | 2023-06-14 | 2023-03-02 | 3779 | 1385 | 1385
22 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-02 | 2023-08-25 | 2023-05-03 | 17007 | 5539 | 5539
22 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-20 | 2024-11-18 |  | 219208 | 197665 | 85977
22 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-20 | 2024-11-18 |  | 70632 | 49228 | 19226
22 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2021-05-07 | 2021-09-22 | 2021-11-16 | 158000 | 186244 | 176456
22 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2021-11-17 | 2022-04-21 | 2022-05-11 | 790000 | 570040 | 512296
22 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2022-09-12 | 2024-09-10 |  | 17775000 | 17142735 | 12078719
22 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2022-09-12 | 2024-09-10 |  | 1107166 | 880472 | 877461
22 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-15 | 2023-06-15 | 2023-03-13 | 4077 | 696 | 696
22 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-13 | 2023-09-06 | 2023-05-03 | 18346 | 2785 | 2785
22 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-20 | 2024-11-18 |  | 236463 | 213144 | 78286
22 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-20 | 2024-11-18 |  | 78622 | 58404 | 26167
22 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 2024-08-30 | 2025-02-05 |  | 60000 | 40389 | 2092
22 | P.S. 207 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 2024-09-20 | 2025-01-28 |  | 7365 | 7365 | 0
22 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-06-09 | 2021-10-22 | 2022-05-12 | 59276 | 104204 | 75772
22 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2023-02-27 | 2024-01-22 |  | 869387 | 828410 | 627068
22 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-02-27 | 2024-01-22 |  | 59276 | 101563 | 93758
22 | P.S. 217 - BROOKLYN | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Design | Complete | 2021-01-06 | 2021-05-25 | 2021-05-10 | 81589 | 53830 | 53830
22 | P.S. 217 - BROOKLYN | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Construction | Complete | 2023-09-27 | 2024-08-21 | 2024-06-20 | 1196638 | 652845 | 602752
22 | P.S. 217 - BROOKLYN | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | CM,F&E | Complete | 2023-09-27 | 2024-08-21 | 2024-06-20 | 81589 | 65506 | 63810
22 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-24 | 2023-11-22 | 2023-08-02 | 4870 | 2135 | 2135
22 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-02 | 2024-01-31 | 2023-11-01 | 21915 | 8540 | 8540
22 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-03-01 | 2025-01-24 |  | 282460 | 268146 | 79012
22 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-03-01 | 2025-01-24 |  | 131371 | 111019 | 55838
22 | P.S. 222 - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-08-04 | 2023-12-21 | 2024-02-12 | 60000 | 71862 | 57162
22 | P.S. 222 - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2024-07-31 | 2025-06-25 |  | 880000 | 597212 | 32101
22 | P.S. 222 - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2024-07-31 | 2025-06-25 |  | 60000 | 56769 | 13409
22 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | Scope | Complete | 2021-03-24 | 2021-07-23 | 2021-10-14 | 27406 | 50420 | 38631
22 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | Design | Complete | 2021-12-01 | 2022-05-04 | 2022-09-23 | 137029 | 220810 | 208269
22 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | Construction | In-Progress | 2023-07-10 | 2025-04-09 |  | 3083153 | 2917482 | 1925689
22 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | CM,F&E | In-Progress | 2023-07-10 | 2025-04-09 |  | 191841 | 284345 | 281824
22 | I.S. 234 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2024-06-18 | 2024-11-04 | 2024-09-19 | 270897 | 72405 | 47805
22 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 2019-05-30 | 2019-10-15 | 2019-11-01 | 177065 | 113088 | 113088
22 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 2019-12-18 | 2020-06-05 | 2021-11-04 | 876028 | 631330 | 569062
22 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | Complete | 2022-06-06 | 2024-06-04 | 2024-08-20 | 18906655 | 17444485 | 14799518
22 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | Complete | 2022-06-06 | 2024-06-04 | 2024-08-20 | 1440770 | 1633474 | 1623919
22 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-07 | 2023-05-24 | 2023-02-15 | 5600 | 3171 | 3171
22 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-15 | 2023-08-11 | 2023-05-02 | 25200 | 12684 | 12684
22 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-28 | 2024-08-22 |  | 324800 | 292530 | 226995
22 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-28 | 2024-08-22 |  | 118295 | 92774 | 87457
22 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-05-22 | 2020-09-22 | 2020-07-06 | 5931 | 9271 | 9271
22 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-06 | 2020-12-31 | 2021-05-05 | 26688 | 37088 | 37088
22 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-19 | 2023-03-14 |  | 343977 | 319012 | 251868
22 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-19 | 2023-03-14 |  | 304957 | 288151 | 207959
22 | P.S. 251 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2023-05-30 | 2023-10-05 | 2023-11-07 | 45000 | 66050 | 65925
22 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | Scope | Complete | 2019-01-30 | 2019-05-01 | 2019-04-03 | 33660 | 69367 | 69367
22 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | Design | Complete | 2019-04-12 | 2019-10-04 | 2021-07-15 | 168300 | 608851 | 370849
22 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | Construction | In-Progress | 2023-09-05 | 2024-09-04 |  | 3786750 | 3643216 | 2327404
22 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | CM,F&E | In-Progress | 2023-09-05 | 2024-09-04 |  | 444768 | 553726 | 336081
22 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-25 | 2023-11-24 | 2023-08-02 | 4870 | 1581 | 1581
22 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-02 | 2024-01-31 | 2023-11-01 | 21915 | 6324 | 6324
22 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-03-01 | 2025-01-24 |  | 282460 | 254210 | 71967
22 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-03-01 | 2025-01-24 |  | 52353 | 32497 | 17293
22 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-03-12 | 2021-07-27 | 2021-11-29 | 48965 | 99463 | 97856
22 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2021-12-08 | 2022-05-11 | 2022-05-13 | 237607 | 284929 | 272585
22 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2022-09-12 | 2024-03-04 |  | 4722126 | 4512173 | 3828289
22 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-09-12 | 2024-03-04 |  | 398088 | 591826 | 586366
22 | P.S. 277 - BROOKLYN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Design | Complete | 2018-07-25 | 2018-12-27 | 2019-03-13 | 32974 | 95244 | 87145
22 | P.S. 277 - BROOKLYN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 2019-08-05 | 2020-03-01 |  | 483624 | 604173 | 301676
22 | P.S. 277 - BROOKLYN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 2019-08-05 | 2020-03-01 |  | 32974 | 64009 | 49445
22 | I.S. 278 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2021-05-28 | 2021-10-14 | 2021-12-16 | 20883 | 34164 | 33918
22 | I.S. 278 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2021-12-28 | 2022-05-31 | 2022-05-11 | 102209 | 181721 | 147920
22 | I.S. 278 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | Complete | 2022-08-29 | 2024-02-19 | 2023-10-31 | 2109208 | 1912282 | 1830923
22 | I.S. 278 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | Complete | 2022-08-29 | 2024-02-19 | 2023-10-31 | 162694 | 236594 | 202793
22 | K811 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2019-08-29 | 2020-01-17 | 2021-06-08 | 126919 | 186068 | 170015
22 | K811 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | In-Progress | 2022-08-31 | 2023-03-09 |  | 634596 | 634596 | 242655
22 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2021-03-26 | 2021-08-10 | 2021-11-03 | 153170 | 163233 | 163233
22 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2021-11-15 | 2022-05-04 | 2022-09-30 | 765850 | 404866 | 356862
22 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2023-09-05 | 2025-09-03 |  | 17231625 | 15752259 | 7587306
22 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2023-09-05 | 2025-09-03 |  | 1073222 | 265095 | 254832
22 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 2023-07-18 | 2023-12-04 | 2024-01-26 | 102000 | 51399 | 48560
22 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY16 RESO A LEARNING GARDEN | Design | Complete | 2017-11-07 | 2018-03-28 | 2019-05-17 | 888362 | 1426370 | 1336139
22 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY16 RESO A LEARNING GARDEN | Construction | In-Progress | 2022-06-06 | 2024-06-04 |  | 13029311 | 12634889 | 9456528
22 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY16 RESO A LEARNING GARDEN | CM,F&E | In-Progress | 2022-06-06 | 2024-06-04 |  | 888362 | 472391 | 470104
22 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2021-02-26 | 2021-07-13 | 2021-11-05 | 195699 | 111768 | 111268
22 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2021-11-10 | 2022-04-15 | 2022-05-11 | 978501 | 512561 | 330297
22 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-12-18 | 2026-05-05 |  | 22016250 | 19908966 | 1038405
22 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-12-18 | 2026-05-05 |  | 1369900 | 157385 | 141104
22 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 2020-08-14 | 2020-12-14 | 2021-03-24 | 114450 | 81345 | 78715
22 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 2021-03-29 | 2021-09-09 | 2021-12-01 | 572250 | 363102 | 54061
22 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2023-09-18 | 2025-12-05 |  | 12875625 | 12490148 | 2301494
22 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2023-09-18 | 2025-12-05 |  | 808729 | 328523 | 315264
22 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | Scope | Complete | 2023-06-01 | 2023-11-30 | 2023-10-04 | 393500 | 292801 | 288226
22 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | Design | Complete | 2023-10-26 | 2024-06-10 | 2024-04-15 | 1967502 | 501163 | 488960
22 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | Construction | In-Progress | 2024-08-27 | 2029-02-01 |  | 44268750 | 40105688 | 511102
22 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | CM,F&E | In-Progress | 2024-08-27 | 2029-02-01 |  | 2754500 | 160986 | 36762
22 | JAMES MADISON HS - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Design | In-Progress | 2022-07-18 | 2023-01-13 |  | 21562 | 26189 | 24688
22 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 2019-09-27 | 2020-02-18 | 2021-11-29 | 138070 | 156676 | 155057
22 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 2021-11-30 | 2022-05-03 | 2022-05-11 | 690350 | 502488 | 485955
22 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 2022-09-12 | 2024-09-10 |  | 15532875 | 14481524 | 7980968
22 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 2022-09-12 | 2024-09-10 |  | 966490 | 437214 | 434425
22 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-05-29 | 2020-09-28 | 2020-07-27 | 4629 | 6577 | 6577
22 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-27 | 2021-01-21 | 2021-05-05 | 20832 | 26309 | 26309
22 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-19 | 2023-03-14 |  | 268503 | 250489 | 244066
22 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-19 | 2023-03-14 |  | 198089 | 192393 | 186268
23 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | Scope | Complete | 2023-06-07 | 2023-12-06 | 2023-10-24 | 144603 | 242179 | 201371
23 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | Design | Complete | 2023-10-30 | 2024-06-10 | 2024-04-26 | 715414 | 605475 | 592594
23 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | Construction | In-Progress | 2024-07-22 | 2027-01-07 |  | 15439113 | 13881000 | 44000
23 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | CM,F&E | In-Progress | 2024-07-22 | 2027-01-07 |  | 1069250 | 55670 | 55670
23 | P.S. 12 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-23 | 2023-10-23 | 2023-10-24 | 17834 | 18745 | 18745
23 | P.S. 12 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-26 | 2024-03-26 | 2024-04-01 | 80254 | 65256 | 53902
23 | I.S. 484 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 2024-05-24 |  |  | 404149 | 404149 | 404149
23 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-05-22 | 2023-09-21 | 2023-06-01 | 4800 | 555 | 555
23 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-06-01 | 2023-11-29 | 2023-11-08 | 21600 | 2221 | 2221
23 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2024-04-23 | 2025-03-18 |  | 278400 | 262175 | 3545
23 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2024-04-23 | 2025-03-18 |  | 170865 | 149982 | 81833
23 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 2021-04-06 | 2021-08-19 | 2021-11-02 | 191370 | 298199 | 271472
23 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 2021-11-10 | 2022-05-02 | 2023-05-23 | 956850 | 890093 | 762943
23 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | In-Progress | 2024-04-15 | 2026-09-01 |  | 21529126 | 19378173 | 1169193
23 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 2024-04-15 | 2026-09-01 |  | 1339590 | 194970 | 193850
23 | P.S. 150 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-03 | 2024-09-04 | 2024-05-07 | 4891 | 1808 | 1808
23 | P.S. 150 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-05-07 | 2024-11-01 | 2024-08-07 | 22009 | 7230 | 7230
23 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | Scope | Complete | 2017-11-03 | 2018-10-04 | 2018-11-26 | 314342 | 142162 | 142162
23 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | Design | Complete | 2019-01-23 | 2019-06-24 | 2019-05-17 | 1252506 | 973714 | 971462
23 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | Construction | In-Progress | 2022-05-09 | 2024-05-07 |  | 23048198 | 22329141 | 19852001
23 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | CM,F&E | In-Progress | 2022-05-09 | 2024-05-07 |  | 1531334 | 717795 | 704523
23 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-30 | 2023-05-30 | 2023-02-15 | 5400 | 1806 | 1806
23 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-15 | 2023-08-11 | 2023-05-02 | 24300 | 7222 | 7222
23 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-28 | 2024-08-22 |  | 313200 | 281151 | 244316
23 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-28 | 2024-08-22 |  | 112734 | 89960 | 84255
23 | P.S. 178 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | In-Progress | 2024-06-12 | 2024-10-29 |  | 118852 | 118852 | 52734
23 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 2021-01-26 | 2021-05-26 | 2021-10-20 | 41950 | 26892 | 26892
23 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 2021-10-28 | 2022-03-28 | 2022-04-18 | 209750 | 204412 | 151407
23 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2023-09-11 | 2025-03-03 |  | 4719375 | 4713981 | 839679
23 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2023-09-11 | 2025-03-03 |  | 293650 | 249688 | 215511
23 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-06-07 | 2023-10-06 | 2023-06-20 | 4694 | 1330 | 1330
23 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-06-20 | 2023-12-15 | 2023-10-04 | 21123 | 5320 | 5320
23 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2024-02-16 | 2025-01-10 |  | 272252 | 246210 | 175937
23 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2024-02-16 | 2025-01-10 |  | 72514 | 53139 | 40511
23 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-07-19 | 2023-12-20 | 2024-01-31 | 47086 | 55628 | 53071
23 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 2023-01-27 | 2023-04-28 | 2023-08-01 | 305 | 305 | 305
23 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-08-02 | 2023-12-06 | 2024-01-31 | 1220 | 1220 | 1220
23 | P.S. 184 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND SURFACES | Scope | Complete | 2019-08-21 | 2020-01-09 | 2019-12-20 | 2315 | 16531 | 16531
23 | P.S. 184 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND SURFACES | Design | Complete | 2020-02-18 | 2020-08-03 | 2020-05-07 | 10417 | 66122 | 66122
23 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-24 | 2023-05-23 | 2023-02-01 | 4964 | 1993 | 1993
23 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-01 | 2023-07-28 | 2023-04-26 | 22338 | 7970 | 7970
23 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-30 | 2024-07-24 |  | 287912 | 258605 | 134970
23 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-30 | 2024-07-24 |  | 107665 | 87552 | 75369
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | Scope | Complete | 2023-06-21 | 2023-12-19 | 2023-11-02 | 286001 | 181305 | 172293
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | Design | Complete | 2023-12-27 | 2024-05-29 | 2024-04-23 | 1430000 | 377750 | 377750
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | Construction | In-Progress | 2024-09-16 | 2027-03-04 |  | 32175001 | 28971937 | 250390
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | CM,F&E | In-Progress | 2024-09-16 | 2027-03-04 |  | 2002002 | 49018 | 46965
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-19 | 2023-05-18 | 2023-02-01 | 6276 | 982 | 982
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-01 | 2023-07-28 | 2023-04-26 | 28242 | 3926 | 3926
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-30 | 2024-07-24 |  | 364008 | 326195 | 225192
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-30 | 2024-07-24 |  | 139745 | 117019 | 109078
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2023-12-01 | 2024-04-04 | 2024-03-01 | 9413 | 9413 | 3648
23 | P.S./I.S. 323 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | Complete | 2024-03-05 | 2024-07-19 | 2024-07-25 | 14589 | 14589 | 14589
23 | I.S. 518 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-07-19 | 2023-12-20 | 2023-11-21 | 30000 | 29994 | 5253
23 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | Scope | Complete | 2019-04-02 | 2019-07-17 | 2020-03-16 | 8440 | 14978 | 14978
23 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | Design | Complete | 2020-03-16 | 2020-08-28 | 2022-11-01 | 37980 | 60871 | 57671
23 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 2023-04-27 | 2024-03-21 |  | 489520 | 508619 | 130461
23 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | CM,F&E | In-Progress | 2023-04-27 | 2024-03-21 |  | 90730 | 79982 | 57298
23 | P.S. 284 - BROOKLYN | SCA CIP | SWIMMING POOL / FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / EXTERIOR DOORS / FLOOD ELIMINATION / PATH OF TRAVEL SWIMMING POOL | Scope | Complete | 2017-04-18 | 2023-07-20 | 2023-06-06 | 286668 | 393208 | 384173
23 | P.S. 284 - BROOKLYN | SCA CIP | SWIMMING POOL / FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / EXTERIOR DOORS / FLOOD ELIMINATION / PATH OF TRAVEL SWIMMING POOL | Design | Complete | 2023-06-07 | 2023-10-11 | 2024-04-23 | 1408606 | 753589 | 573275
23 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2023-07-06 | 2023-11-03 | 2023-07-07 | 4760 | 1050 | 1050
23 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2023-07-07 | 2024-01-04 | 2023-11-08 | 21420 | 4201 | 4201
23 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2024-04-23 | 2025-03-18 |  | 276080 | 265884 | 9254
23 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2024-04-23 | 2025-03-18 |  | 73487 | 52950 | 27282
23 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | Scope | Complete | 2019-03-08 | 2019-06-06 | 2019-05-23 | 15539 | 36201 | 36201
23 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | Design | Complete | 2019-06-26 | 2019-12-31 | 2019-11-08 | 77694 | 136216 | 136216
23 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | Construction | In-Progress | 2022-10-17 | 2024-01-09 |  | 1748116 | 1605144 | 18818
23 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 2022-10-17 | 2024-01-09 |  | 108772 | 78187 | 78187
23 | P.S. 327 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-07-03 | 2023-11-17 | 2023-10-13 | 120761 | 121975 | 121975
23 | P.S. 327 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-10-16 | 2024-03-20 | 2024-03-26 | 591584 | 357210 | 339597
31 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | CM,F&E | In-Progress | 2022-07-18 | 2023-07-17 |  | 216084 | 674649 | 671218
23 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | Scope | Complete | 2019-06-28 | 2019-12-27 | 2019-11-19 | 138348 | 167150 | 160514
23 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | Design | Complete | 2019-12-03 | 2020-06-15 | 2020-05-01 | 686840 | 456742 | 456742
23 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | Construction | In-Progress | 2024-08-05 | 2026-08-04 |  | 15030267 | 13706847 | 200008
23 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | CM,F&E | In-Progress | 2024-08-05 | 2026-08-04 |  | 1005165 | 108131 | 103867
23 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-03 | 2024-09-04 | 2024-05-07 | 3974 | 1182 | 1182
23 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-05-07 | 2024-11-01 | 2024-08-07 | 17883 | 4727 | 4727
23 | P.S. 156 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2023-06-07 | 2023-12-06 | 2023-10-18 | 82651 | 151830 | 134427
23 | P.S. 156 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2023-10-30 | 2024-06-28 | 2024-04-08 | 408065 | 248435 | 245668
23 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-06-30 | 2023-10-31 | 2023-07-25 | 3684 | 1170 | 1170
23 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-07-25 | 2024-01-23 | 2023-10-04 | 16578 | 4682 | 4682
23 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-16 | 2025-01-10 |  | 213672 | 193550 | 144473
23 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-16 | 2025-01-10 |  | 64640 | 50783 | 39041
23 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2024-07-10 | 2024-11-25 |  | 24000 | 17233 | 3157
23 | HOPE FAITH AND CHARITY | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 2021-04-05 | 2021-05-28 | 2021-08-03 | 14285 | 16472 | 16472
23 | HOPE FAITH AND CHARITY | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Design | Complete | 2022-01-04 | 2022-05-04 | 2023-05-12 | 64283 | 41240 | 36872
23 | LOVE IN ACTION DAY CARE | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 2021-04-09 | 2021-07-09 | 2021-08-04 | 9686 | 14506 | 14506
23 | LOVE IN ACTION DAY CARE | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Design | In-Progress | 2022-01-04 | 2022-05-04 |  | 43588 | 43588 | 11319
23 | K000 - BROOKLYN | SCA CIP | PATH OF TRAVEL ACS EARLY LEARN LEASE RENEWAL | Scope | In-Progress | 2024-05-15 | 2024-08-16 |  | 660 | 660 | 0
23 | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 2021-04-09 | 2021-07-09 | 2021-08-03 | 13540 | 17412 | 17412
23 | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | Complete | 2022-10-26 | 2023-03-29 | 2023-05-12 | 60930 | 3995 | 3995
23 | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Construction | In-Progress | 2024-01-08 | 2024-12-02 |  | 785320 | 737713 | 101198
23 | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | CM,F&E | In-Progress | 2024-01-08 | 2024-12-02 |  | 145555 | 124462 | 22168
24 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | Scope | Complete | 2014-06-12 | 2014-09-11 | 2014-11-05 | 70650 | 61506 | 61506
24 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | Design | Complete | 2014-11-13 | 2015-04-17 | 2015-08-21 | 282600 | 797734 | 698090
24 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | Construction | In-Progress | 2016-01-19 | 2017-01-17 |  | 5298750 | 6320949 | 4823138
24 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | CM,F&E | In-Progress | 2016-01-19 | 2017-01-17 |  | 329700 | 640330 | 575341
24 | I.S. 5 - QUEENS | SCA CIP | SMOKE PURGE SYSTEM | Scope | Complete | 2019-03-14 | 2019-06-12 | 2019-11-27 | 3872 | 18842 | 18842
24 | I.S. 5 - QUEENS | SCA CIP | SMOKE PURGE SYSTEM | Design | Complete | 2020-01-06 | 2020-02-06 | 2020-01-15 | 17426 | 88325 | 88325
24 | I.S. 5 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-05-01 | 2023-09-15 | 2023-09-22 | 30000 | 58253 | 10341
24 | I.S. 5 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2024-08-26 | 2025-06-21 |  | 440000 | 391518 | 590
24 | I.S. 5 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2024-08-26 | 2025-06-21 |  | 30000 | 44560 | 4372
24 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2021-10-29 | 2022-02-02 | 2022-07-15 | 27650 | 41699 | 41699
24 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2022-07-18 | 2022-12-02 | 2023-04-12 | 138250 | 99013 | 88357
24 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2023-10-10 | 2024-10-08 |  | 3110625 | 2811163 | 230513
24 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2023-10-10 | 2024-10-08 |  | 193550 | 89542 | 45123
24 | P.S. 7 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2023-06-01 | 2023-11-30 | 2023-11-15 | 140732 | 153992 | 135142
24 | P.S. 7 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-12-20 | 2024-05-22 | 2024-04-04 | 703660 | 235516 | 235516
24 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | Scope | Complete | 2018-12-17 | 2021-05-07 | 2021-05-20 | 196818 | 226086 | 226086
24 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | Design | Complete | 2021-05-21 | 2021-11-30 | 2022-01-31 | 974931 | 792797 | 689303
24 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | Construction | In-Progress | 2023-07-28 | 2024-10-19 |  | 21143803 | 19318929 | 2220770
31 | P.S. 29 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PLAYGROUNDS | Scope | Complete | 2022-05-20 | 2022-08-22 | 2022-08-23 | 7607 | 7607 | 7607
24 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | CM,F&E | In-Progress | 2023-07-28 | 2024-10-19 |  | 1446408 | 299185 | 212197
24 | P.S. 12 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-09 | 2024-08-08 | 2024-05-08 | 4493 | 3548 | 3548
24 | P.S. 12 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-05-08 | 2024-11-04 |  | 20216 | 20216 | 14193
24 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 2019-06-24 | 2019-12-20 | 2019-11-19 | 142812 | 291348 | 289480
24 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 2019-12-02 | 2020-06-15 | 2020-05-04 | 708443 | 530368 | 525734
24 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | In-Progress | 2021-05-17 | 2023-11-02 |  | 15453582 | 14203626 | 13705665
24 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | In-Progress | 2021-05-17 | 2023-11-02 |  | 1041860 | 1175020 | 1133290
24 | P.S. 13 - QUEENS | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Design | Complete | 2024-06-24 | 2024-12-27 | 2024-09-13 | 30000 | 25022 | 7728
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-06-26 | 2024-11-12 |  | 30000 | 17586 | 5941
24 | P.S. 14 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-06-26 | 2024-10-25 |  | 1610 | 1610 | 0
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SOCCER PITCH / FY20 RESO A SOCCER PITCH | Design | Complete | 2022-03-15 | 2022-05-11 | 2022-05-04 | 42600 | 59903 | 52942
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SOCCER PITCH / FY20 RESO A SOCCER PITCH | Construction | In-Progress | 2023-10-09 | 2024-11-11 |  | 624800 | 558681 | 185057
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SOCCER PITCH / FY20 RESO A SOCCER PITCH | CM,F&E | In-Progress | 2023-10-09 | 2024-11-11 |  | 42600 | 67284 | 60530
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-06-13 | 2023-10-13 | 2023-08-08 | 32337 | 64713 | 52615
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2024-04-22 | 2025-04-21 |  | 474275 | 454758 | 8506
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2024-04-22 | 2025-04-21 |  | 32337 | 57936 | 14429
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 2024-01-12 | 2024-05-15 | 2024-02-16 | 30000 | 28858 | 26555
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | In-Progress | 2024-07-15 | 2025-05-10 |  | 440000 | 407037 | 20621
24 | P.S. 14 - QUEENS | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | In-Progress | 2024-07-15 | 2025-05-10 |  | 30000 | 53097 | 23991
24 | P.S. 19 - QUEENS | SCA CIP | PARAPETS / ROOFS / WINDOWS | Scope | Complete | 2023-07-13 | 2023-11-29 | 2023-11-15 | 98632 | 85284 | 84781
24 | P.S. 19 - QUEENS | SCA CIP | PARAPETS / ROOFS / WINDOWS | Design | Complete | 2023-11-20 | 2024-04-23 | 2024-04-24 | 488781 | 342458 | 335560
24 | P.S. 19 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-11-17 | 2022-03-18 | 2022-04-18 | 115996 | 162740 | 144303
24 | P.S. 19 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2022-07-14 | 2023-07-13 |  | 1701275 | 1698734 | 1537794
24 | P.S. 19 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2022-07-14 | 2023-07-13 |  | 115996 | 94683 | 88320
24 | P.S. 28 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / REPLACEMENT OF RTUS / ROOFS | Scope | Complete | 2020-05-21 | 2020-11-18 | 2020-10-08 | 72015 | 139916 | 121351
24 | P.S. 28 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / REPLACEMENT OF RTUS / ROOFS | Design | Complete | 2020-10-20 | 2021-06-15 | 2021-04-14 | 354828 | 312162 | 312162
24 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2021-11-30 | 2022-03-03 | 2022-02-28 | 21300 | 29430 | 29430
24 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2022-03-16 | 2022-07-29 | 2022-09-14 | 106500 | 164288 | 145402
24 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2023-05-15 | 2024-05-13 |  | 2396250 | 2203581 | 1532000
24 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2023-05-15 | 2024-05-13 |  | 149100 | 157343 | 140204
24 | P.S. 49 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2024-06-10 | 2024-10-25 | 2024-09-18 | 143642 | 85401 | 39451
24 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | Scope | Complete | 2019-07-11 | 2019-11-26 | 2019-11-26 | 58926 | 38935 | 38935
24 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | Design | Complete | 2019-11-26 | 2020-04-29 | 2020-06-30 | 286603 | 311574 | 299887
24 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | Construction | In-Progress | 2021-06-25 | 2023-03-16 |  | 5754009 | 5134552 | 4765131
24 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | CM,F&E | In-Progress | 2021-06-25 | 2023-03-16 |  | 472707 | 496198 | 465816
24 | P.S. 71 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-05-02 | 2024-09-03 | 2024-05-08 | 5171 | 2814 | 2814
24 | P.S. 71 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-05-08 | 2024-11-04 |  | 23269 | 23269 | 11257
24 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Scope | Complete | 2021-01-28 | 2021-12-30 | 2022-02-01 | 92135 | 162555 | 162555
24 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Design | Complete | 2022-02-08 | 2022-07-08 | 2023-05-12 | 436890 | 431018 | 335573
24 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Construction | In-Progress | 2023-09-14 | 2025-12-01 |  | 8984548 | 9075486 | 2077621
24 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 2023-09-14 | 2025-12-01 |  | 657395 | 254912 | 251073
24 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | Scope | Complete | 2011-10-11 | 2012-01-12 | 2011-12-06 | 27750 | 18465 | 18465
24 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | Design | Complete | 2011-12-15 | 2012-06-19 | 2012-04-24 | 83250 | 94716 | 88277
24 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | Construction | In-Progress | 2012-11-28 | 2014-02-20 |  | 1059125 | 1027565 | 846190
24 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2012-11-28 | 2014-02-20 |  | 212750 | 193004 | 186565
24 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2018-10-03 | 2019-03-11 | 2018-12-05 | 117150 | 144929 | 144929
24 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2018-12-07 | 2019-05-10 | 2019-05-07 | 468600 | 646950 | 625431
24 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2019-07-22 | 2021-07-20 |  | 8786250 | 7877848 | 6291473
24 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2019-07-22 | 2021-07-20 |  | 546700 | 987414 | 960719
24 | I.S. 73 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2019-07-03 | 2019-10-02 | 2021-06-17 | 18661 | 37531 | 37531
24 | I.S. 73 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2021-06-29 | 2022-01-04 | 2022-01-21 | 83973 | 63522 | 61263
24 | I.S. 73 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-06-14 | 2021-11-15 | 2021-11-01 | 45000 | 61620 | 61620
24 | I.S. 73 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2022-04-04 | 2022-12-29 |  | 660000 | 409058 | 332548
24 | I.S. 73 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2022-04-04 | 2022-12-29 |  | 45000 | 46688 | 37186
24 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2018-10-15 | 2019-03-05 | 2019-01-31 | 87983 | 354962 | 349513
24 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2019-01-31 | 2019-07-02 | 2022-05-11 | 439202 | 1115855 | 497576
24 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2022-08-22 | 2024-05-12 |  | 9820913 | 10278784 | 8593340
24 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2022-08-22 | 2024-05-12 |  | 621175 | 667353 | 370180
24 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-11-18 | 2023-03-23 | 2022-12-09 | 3311 | 6610 | 6610
24 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-09 | 2023-06-07 | 2023-04-04 | 14900 | 26440 | 26440
24 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-07 | 2024-06-01 |  | 192038 | 174441 | 136299
24 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-07 | 2024-06-01 |  | 126869 | 127220 | 82022
24 | Q075 SPED - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 2023-02-27 | 2023-06-30 | 2023-03-10 | 2177 | 0 | 0
24 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | Scope | Complete | 2023-08-17 | 2024-01-05 | 2023-12-08 | 97939 | 230900 | 186579
24 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | Design | Complete | 2023-12-14 | 2024-05-16 | 2024-05-03 | 489696 | 510400 | 494720
24 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | Construction | In-Progress | 2024-08-12 | 2026-05-03 |  | 11018171 | 10160360 | 106078
24 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | CM,F&E | In-Progress | 2024-08-12 | 2026-05-03 |  | 685576 | 85629 | 85629
24 | P.S. 87 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 2021-10-22 | 2022-02-28 | 2022-06-15 | 8471 | 11985 | 11985
24 | P.S. 87 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 2022-09-21 | 2023-02-09 | 2023-03-03 | 38121 | 31392 | 27731
24 | P.S. 87 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 2023-06-21 | 2023-11-06 | 2023-11-01 | 81356 | 139319 | 121550
24 | P.S. 87 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | Complete | 2023-11-17 | 2024-04-22 | 2024-05-01 | 406777 | 240537 | 233395
24 | P.S. 87 - QUEENS | SCA CIP RESOA | FY19 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Design | Complete | 2019-07-25 | 2019-12-11 | 2020-06-23 | 186000 | 222256 | 220281
24 | P.S. 87 - QUEENS | SCA CIP RESOA | FY19 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Construction | In-Progress | 2022-08-03 | 2023-09-01 |  | 2728000 | 1372815 | 1285516
24 | P.S. 87 - QUEENS | SCA CIP RESOA | FY19 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | CM,F&E | In-Progress | 2022-08-03 | 2023-09-01 |  | 186000 | 121025 | 120877
24 | P.S. 87 - QUEENS | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Design | In-Progress | 2023-07-12 | 2024-01-12 |  | 90000 | 71116 | 6183
24 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2018-02-06 | 2018-05-07 | 2018-03-23 | 26304 | 23155 | 23155
24 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2018-04-25 | 2018-10-26 | 2018-08-27 | 96448 | 104251 | 76639
24 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2019-04-03 | 2020-04-01 |  | 1021472 | 1006444 | 752824
24 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2019-04-03 | 2020-04-01 |  | 236736 | 299430 | 293408
24 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | Scope | Complete | 2019-11-19 | 2020-02-21 | 2021-04-21 | 17468 | 67116 | 67116
24 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | Design | Complete | 2021-04-27 | 2021-09-10 | 2022-05-11 | 87340 | 111596 | 111596
24 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2022-12-16 | 2023-12-15 |  | 1965150 | 1836973 | 1114631
24 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2022-12-16 | 2023-12-15 |  | 122276 | 155206 | 138206
24 | P.S. 89 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT / VENTILATION | Scope | Complete | 2019-03-14 | 2019-07-15 | 2020-01-21 | 65275 | 140837 | 132888
24 | P.S. 89 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT / VENTILATION | Design | Complete | 2020-01-21 | 2020-06-19 | 2022-09-30 | 326375 | 293448 | 268350
24 | P.S. 89 - QUEENS | SCA CIP | ROOFS / WINDOWS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 2023-06-20 | 2023-11-03 | 2023-11-07 | 115182 | 181520 | 181520
24 | P.S. 89 - QUEENS | SCA CIP | ROOFS / WINDOWS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 2023-11-13 | 2024-04-16 | 2024-04-30 | 568834 | 319261 | 303749
24 | P.S. 89 - QUEENS | SCA CIP | AIR HANDLING UNITS | Scope | Complete | 2023-11-14 | 2023-11-14 | 2023-11-14 | 10646 | 9206 | 4444
24 | P.S. 89 - QUEENS | SCA CIP | AIR HANDLING UNITS | Design | Complete | 2023-11-14 | 2024-05-15 | 2024-05-15 | 53230 | 75303 | 17775
24 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2014-08-27 | 2015-04-13 | 2015-03-09 | 309057 | 263726 | 263726
24 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2015-05-01 | 2017-11-16 | 2018-04-19 | 1227451 | 1712059 | 1215870
24 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 2018-07-20 | 2020-08-07 |  | 22226862 | 23772451 | 12448645
24 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 2018-07-20 | 2020-08-07 |  | 1556381 | 1710053 | 1544764
24 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 2022-07-05 | 2022-11-18 | 2023-11-02 | 44636 | 150098 | 87003
24 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | Complete | 2023-11-08 | 2024-04-12 | 2024-05-15 | 214997 | 168062 | 122830
24 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2024-09-09 | 2026-03-02 |  | 4129279 | 3740939 | 31123
24 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2024-09-09 | 2026-03-02 |  | 373856 | 84074 | 47472
24 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | Scope | Complete | 2019-06-24 | 2019-12-20 | 2019-11-18 | 207142 | 384241 | 384241
24 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | Design | Complete | 2019-12-02 | 2020-06-15 | 2020-05-12 | 1021278 | 686816 | 664580
24 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | Construction | In-Progress | 2022-03-02 | 2024-02-29 |  | 21730387 | 20450683 | 18606244
24 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | CM,F&E | In-Progress | 2022-03-02 | 2024-02-29 |  | 1558231 | 725477 | 690486
24 | I.S. 119 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Design | Complete | 2023-09-05 | 2024-02-08 | 2024-05-24 | 30000 | 55696 | 29515
24 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | Scope | Complete | 2019-09-19 | 2020-02-25 | 2021-07-19 | 26700 | 40776 | 40776
24 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | Design | Complete | 2021-11-08 | 2022-03-29 | 2022-03-16 | 133500 | 128573 | 115830
24 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | Construction | In-Progress | 2023-03-06 | 2025-03-04 |  | 3003750 | 2918276 | 1557299
24 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | CM,F&E | In-Progress | 2023-03-06 | 2025-03-04 |  | 186900 | 135470 | 94067
24 | I.S. 125 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2023-01-19 | 2023-06-05 | 2023-11-08 | 12366 | 47250 | 47250
24 | I.S. 125 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2023-11-20 | 2024-04-23 | 2024-08-02 | 61828 | 78077 | 76202
24 | P.S. 143 - QUEENS | SCA CIP | PHASE 3-PLAYGROUND REDEVELOPMENT FOR JOP | Scope | Complete | 2018-12-12 | 2019-04-16 | 2019-07-15 | 27774 | 68898 | 55733
24 | P.S. 143 - QUEENS | SCA CIP | PHASE 3-PLAYGROUND REDEVELOPMENT FOR JOP | Design | Complete | 2019-07-17 | 2019-12-03 | 2022-05-11 | 138868 | 293276 | 179085
24 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | Scope | Complete | 2019-06-25 | 2020-12-28 | 2020-11-05 | 329900 | 336731 | 329731
24 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | Design | Complete | 2020-11-05 | 2021-04-12 | 2021-04-28 | 1649501 | 910338 | 815746
24 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | Construction | In-Progress | 2022-10-24 | 2025-04-10 |  | 37113749 | 34307688 | 9565127
24 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | CM,F&E | In-Progress | 2022-10-24 | 2025-04-10 |  | 2310821 | 1041238 | 974873
24 | P.S. 143 - QUEENS | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2024-07-24 |  | 2024-09-23 | 75000 | 75000 | 74606
24 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 2019-07-22 | 2019-10-21 | 2019-09-25 | 19800 | 15463 | 15463
24 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 2019-12-18 | 2020-05-20 | 2020-05-08 | 89100 | 61966 | 61966
24 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Construction | In-Progress | 2021-07-26 | 2022-05-21 |  | 1148399 | 1023642 | 996402
24 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2021-07-26 | 2022-05-21 |  | 212850 | 202792 | 194679
24 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | Scope | Complete | 2018-03-12 | 2018-06-08 | 2019-05-14 | 25050 | 41749 | 41749
24 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | Design | Complete | 2019-05-14 | 2019-10-15 | 2019-05-16 | 91850 | 98382 | 87849
24 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | Construction | In-Progress | 2019-07-15 | 2020-07-13 |  | 972775 | 1039080 | 817618
24 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 2019-07-15 | 2020-07-13 |  | 225450 | 121371 | 97673
24 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2018-12-19 | 2019-07-26 | 2019-03-28 | 19950 | 6024 | 6024
24 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2019-03-28 | 2019-08-27 | 2019-05-10 | 73150 | 24225 | 24225
24 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2019-07-22 | 2020-04-16 |  | 774725 | 932275 | 931334
24 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2019-07-22 | 2020-04-16 |  | 179550 | 109597 | 109597
24 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2019-08-12 | 2019-12-13 | 2021-03-25 | 77600 | 111212 | 111212
24 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2021-10-28 | 2022-04-25 | 2022-09-19 | 388000 | 566355 | 278159
24 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2024-03-21 | 2026-03-20 |  | 8730000 | 7837809 | 213482
24 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2024-03-21 | 2026-03-20 |  | 543200 | 22988 | 22988
24 | P.S. 239 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2022-06-30 | 2022-11-16 | 2023-03-27 | 17175 | 55231 | 53469
24 | P.S. 239 - QUEENS | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2023-04-04 | 2023-09-05 | 2023-09-06 | 85875 | 70796 | 56609
24 | P.S. 239 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 2023-06-27 | 2023-11-13 | 2024-01-26 | 38275 | 48501 | 47470
24 | P.S. 305 - QUEENS | SCA CIP | ROOFS / ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | Complete | 2023-12-04 | 2024-05-03 | 2024-04-18 | 85454 | 163011 | 163011
24 | P.S. 305 - QUEENS | SCA CIP | ROOFS / ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | Complete | 2024-04-18 | 2024-11-13 | 2024-09-25 | 427267 | 199544 | 23008
24 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 2022-03-24 | 2022-07-22 | 2022-04-11 | 3050 | 3925 | 3925
24 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 2022-04-11 | 2022-10-04 | 2022-08-17 | 13725 | 15699 | 15699
24 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 2023-02-21 | 2023-12-17 |  | 176900 | 153265 | 130914
24 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 2023-02-21 | 2023-12-17 |  | 114181 | 124811 | 88469
24 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 2024-03-20 | 2024-08-20 | 2024-09-09 | 57000 | 30524 | 18972
24 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | Complete | 2024-03-20 | 2024-08-05 | 2024-09-09 | 96000 | 38537 | 22815
24 | P.S. 307 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2023-06-26 | 2023-11-09 | 2023-12-11 | 20641 | 147715 | 115090
24 | P.S. 307 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2023-12-11 | 2024-05-13 | 2024-06-18 | 99129 | 67142 | 50645
24 | P.S. 307 - QUEENS | SCA CIP | IPDVS | Scope | Complete | 2022-03-22 | 2022-07-20 | 2022-03-30 | 3330 | 4097 | 4097
24 | P.S. 307 - QUEENS | SCA CIP | IPDVS | Design | Complete | 2022-03-30 | 2022-09-22 | 2022-08-17 | 14985 | 16386 | 16386
24 | P.S. 307 - QUEENS | SCA CIP | IPDVS | Construction | In-Progress | 2023-02-21 | 2023-12-17 |  | 193140 | 171302 | 144451
24 | P.S. 307 - QUEENS | SCA CIP | IPDVS | CM,F&E | In-Progress | 2023-02-21 | 2023-12-17 |  | 185672 | 189572 | 147134
24 | P.S. 143 - QUEENS | SCA CIP | PARAPETS / FLOOD ELIMINATION / ROOFS / WINDOWS / EXTERIOR MASONRY | Scope | In-Progress | 2021-03-11 | 2021-07-26 |  | 71811 | 87725 | 50961
24 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-08-31 | 2023-01-20 | 2023-03-22 | 18150 | 27459 | 27459
24 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-11-13 | 2024-08-08 |  | 266200 | 242182 | 3032
24 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-11-13 | 2024-08-08 |  | 18150 | 28255 | 13098
24 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 2024-06-17 | 2024-11-19 |  | 30000 | 22916 | 12195
24 | P.S. 110 - QUEENS | SCA CIP RESOA | RESO A ROOM CONVERSION | Design | Complete | 2023-01-25 | 2023-06-27 | 2023-05-11 | 39635 | 54159 | 17829
24 | P.S. 110 - QUEENS | SCA CIP RESOA | RESO A ROOM CONVERSION | Construction | In-Progress | 2023-11-13 | 2024-09-07 |  | 581316 | 291408 | 193605
24 | P.S. 110 - QUEENS | SCA CIP RESOA | RESO A ROOM CONVERSION | CM,F&E | In-Progress | 2023-11-13 | 2024-09-07 |  | 40273 | 50491 | 44852
24 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | Scope | Complete | 2022-02-08 | 2022-04-14 | 2022-04-25 | 171608 | 180713 | 173507
24 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | Design | Complete | 2022-04-26 | 2022-06-14 | 2023-01-06 | 772234 | 639298 | 501450
24 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | Construction | Complete | 2023-01-20 | 2023-09-03 | 2024-07-24 | 9738729 | 9897797 | 9772864
24 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | CM,F&E | Complete | 2023-01-20 | 2023-09-03 | 2024-07-24 | 1460449 | 454760 | 1377966
24 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2019-01-17 | 2019-07-02 | 2019-07-16 | 627900 | 618029 | 524158
24 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 2019-07-17 | 2020-01-16 | 2020-08-13 | 2825550 | 2167652 | 1404878
24 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2024-07-08 | 2026-09-03 |  | 35633325 | 33002114 | 737571
24 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2024-07-08 | 2026-09-03 |  | 5023200 | 2224896 | 386559
24 | 3K CENTER @ 63-57 FRESH POND ROAD - QUEENS | 3K | LEASE | Scope | Complete | 2022-02-04 | 2022-03-11 | 2022-03-11 | 295191 | 282908 | 273795
24 | 3K CENTER @ 63-57 FRESH POND ROAD - QUEENS | 3K | LEASE | Design | Complete | 2022-03-14 | 2022-06-03 | 2022-09-06 | 1328358 | 819109 | 784196
24 | 3K CENTER @ 63-57 FRESH POND ROAD - QUEENS | 3K | LEASE | Construction | Complete | 2022-11-03 | 2023-09-03 | 2024-06-26 | 16752069 | 16970635 | 16847805
24 | 3K CENTER @ 63-57 FRESH POND ROAD - QUEENS | 3K | LEASE | CM,F&E | Complete | 2022-11-03 | 2023-09-03 | 2024-06-26 | 2472452 | 782255 | 1771670
24 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | Scope | Complete | 2021-11-01 | 2021-12-21 | 2022-02-03 | 179859 | 171674 | 171674
24 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | Design | Complete | 2022-02-04 | 2022-02-18 | 2023-10-19 | 809367 | 591835 | 492020
24 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | Construction | In-Progress | 2023-12-05 | 2024-09-03 |  | 10207014 | 9539795 | 8671770
24 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | CM,F&E | In-Progress | 2023-12-05 | 2024-09-03 |  | 1505657 | 476627 | 1008261
24 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2018-03-29 | 2019-05-23 | 2019-01-29 | 18776 | 27202 | 27202
24 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2019-01-29 | 2019-06-28 | 2019-05-16 | 74387 | 78595 | 78595
24 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2019-07-22 | 2020-04-16 |  | 1330370 | 1244697 | 1106161
24 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2019-07-22 | 2020-04-16 |  | 96949 | 217349 | 213511
24 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Scope | Complete | 2018-08-16 | 2019-01-08 | 2022-10-03 | 409223 | 405438 | 405438
24 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Design | Complete | 2022-12-02 | 2023-05-05 | 2023-05-12 | 2046114 | 1756268 | 1372873
24 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Construction | In-Progress | 2023-08-21 | 2026-02-05 |  | 46037588 | 42017852 | 4612913
24 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-08-21 | 2026-02-05 |  | 2865150 | 838734 | 598178
24 | NEWTOWN HS - QUEENS | SCA CIP RESOA | FY22 RESO A CAFETERIA UPGRADE | Design | Complete | 2023-07-10 | 2023-11-24 | 2023-10-24 | 30000 | 91807 | 46663
24 | NEWTOWN HS - QUEENS | SCA CIP RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2024-02-26 | 2024-12-21 |  | 440000 | 304903 | 35563
24 | NEWTOWN HS - QUEENS | SCA CIP RESOA | FY22 RESO A CAFETERIA UPGRADE | CM,F&E | In-Progress | 2024-02-26 | 2024-12-21 |  | 30000 | 85107 | 29834
24 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2020-01-10 | 2020-05-27 | 2021-06-18 | 116705 | 2756 | 2756
24 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2023-03-29 | 2023-08-29 | 2024-04-30 | 583526 | 627506 | 510361
24 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | Scope | Complete | 2021-03-11 | 2021-07-26 | 2021-12-08 | 23094 | 39059 | 39059
24 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | Design | Complete | 2022-01-05 | 2022-07-08 | 2022-05-11 | 115470 | 150444 | 137996
24 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | Construction | In-Progress | 2022-07-11 | 2023-07-10 |  | 2598075 | 2512535 | 2390336
24 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 2022-07-11 | 2023-07-10 |  | 289644 | 557318 | 520089
24 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | Scope | Complete | 2021-06-16 | 2021-11-01 | 2022-01-06 | 31515 | 44784 | 42098
24 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | Design | Complete | 2022-01-25 | 2022-06-24 | 2022-05-11 | 155850 | 121571 | 121571
24 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | Construction | In-Progress | 2022-09-19 | 2024-03-11 |  | 3357412 | 3093348 | 2794921
24 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | CM,F&E | In-Progress | 2022-09-19 | 2024-03-11 |  | 233540 | 422568 | 375114
24 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | Scope | Complete | 2019-05-08 | 2019-09-23 | 2020-02-11 | 18899 | 50203 | 50203
24 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | Design | Complete | 2020-02-11 | 2020-07-13 | 2020-06-30 | 85045 | 97902 | 97902
24 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | Construction | In-Progress | 2022-04-12 | 2023-07-05 |  | 1096136 | 985846 | 961013
24 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | CM,F&E | In-Progress | 2022-04-12 | 2023-07-05 |  | 203163 | 267264 | 258538
24 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | Scope | Complete | 2021-04-20 | 2022-01-22 | 2022-02-04 | 38155 | 46217 | 46217
24 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | Design | Complete | 2022-02-04 | 2022-04-28 | 2022-07-28 | 190152 | 183845 | 183375
24 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | Construction | In-Progress | 2023-04-13 | 2024-04-11 |  | 4224206 | 3879516 | 2848766
24 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | CM,F&E | In-Progress | 2023-04-13 | 2024-04-11 |  | 317682 | 231784 | 186725
24 | QUEENS TECH HS - Q | SCA CIP RESOA | FY18 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2020-04-29 | 2020-10-23 | 2020-05-14 | 29039 | 28147 | 28147
24 | QUEENS TECH HS - Q | SCA CIP RESOA | FY18 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-09 | 2023-03-04 |  | 425907 | 209609 | 188333
24 | QUEENS TECH HS - Q | SCA CIP RESOA | FY18 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-09 | 2023-03-04 |  | 225892 | 221714 | 202188
24 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2021-03-17 | 2021-06-15 | 2021-06-17 | 12500 | 21109 | 21109
24 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2021-06-22 | 2021-12-27 | 2021-12-14 | 62500 | 121887 | 100055
24 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 2024-04-08 | 2025-04-07 |  | 1406250 | 1291717 | 117072
24 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2024-04-08 | 2025-04-07 |  | 87500 | 22639 | 22308
24 | AVIATION HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES | Scope | Complete | 2021-12-03 | 2022-10-14 | 2023-01-09 | 103266 | 105301 | 105301
24 | AVIATION HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES | Design | Complete | 2023-01-12 | 2023-06-14 | 2023-08-24 | 502200 | 325733 | 287069
24 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2021-10-29 | 2022-02-02 | 2022-07-15 | 18980 | 38100 | 38100
24 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2022-07-18 | 2022-12-02 | 2023-04-18 | 94900 | 102765 | 96300
24 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2023-12-04 | 2024-12-02 |  | 2135250 | 1951018 | 1078526
24 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2023-12-04 | 2024-12-02 |  | 132860 | 125973 | 69239
24 | P.S. 16 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-02-01 | 2024-05-31 | 2024-03-27 | 6731 | 3105 | 3105
24 | P.S. 16 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-27 | 2024-09-20 | 2024-06-14 | 30291 | 12418 | 12418
24 | Q721 SPED - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-02-15 | 2022-06-30 | 2023-02-02 | 47346 | 47565 | 47565
24 | Q721 SPED - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | Complete | 2023-05-29 | 2024-04-22 | 2024-05-29 | 694411 | 664174 | 614520
24 | Q721 SPED - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 2023-05-29 | 2024-04-22 | 2024-05-29 | 47346 | 66800 | 65564
24 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-02-01 | 2024-05-31 | 2024-03-27 | 7755 | 3683 | 3683
24 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-03-27 | 2024-09-20 | 2024-06-14 | 34896 | 14731 | 14731
24 | P.S. 81 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE / FY21 RESO A CAFETERIA UPGRADE | Design | Complete | 2022-05-06 | 2022-06-13 | 2022-05-11 | 22998 | 30917 | 29922
24 | P.S. 81 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE / FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2023-04-10 | 2024-01-04 |  | 337306 | 275492 | 253234
24 | P.S. 81 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE / FY21 RESO A CAFETERIA UPGRADE | CM,F&E | In-Progress | 2023-04-10 | 2024-01-04 |  | 22998 | 44884 | 44362
24 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | Scope | Complete | 2022-06-02 | 2022-11-28 | 2022-10-06 | 243079 | 221469 | 204836
24 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | Design | Complete | 2022-10-18 | 2023-06-05 | 2023-04-17 | 1206317 | 516245 | 516245
24 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | Construction | In-Progress | 2023-10-03 | 2025-10-01 |  | 26356778 | 24026106 | 4209515
24 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-10-03 | 2025-10-01 |  | 1769648 | 308252 | 195704
24 | BETTER CCOMMUNITY LIFE DAY CARE CENTER SITE | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | Scope | In-Progress | 2023-08-21 | 2024-01-17 |  | 712 | 7946 | 2181
25 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 2017-12-18 | 2018-05-04 | 2018-03-21 | 103128 | 89232 | 89232
25 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 2018-03-21 | 2018-08-20 | 2018-05-18 | 407457 | 573749 | 525828
25 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 2018-07-23 | 2020-01-13 |  | 7186455 | 7548188 | 6320772
25 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 2018-07-23 | 2020-01-13 |  | 546930 | 982389 | 926223
25 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | Scope | Complete | 2013-07-23 | 2017-12-18 | 2017-12-18 | 141166 | 69808 | 69808
25 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | Design | Complete | 2018-04-20 | 2018-10-22 | 2019-05-16 | 564660 | 564810 | 530325
25 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | Construction | In-Progress | 2019-07-29 | 2021-07-17 |  | 10587375 | 9972939 | 9003450
25 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | CM,F&E | In-Progress | 2019-07-29 | 2021-07-17 |  | 658769 | 163648 | 153752
25 | P.S. 20 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-12-13 | 2024-06-10 | 2024-03-06 | 30000 | 23195 | 23195
25 | P.S. 20 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-07-29 | 2025-05-24 |  | 440000 | 281815 | 5725
25 | P.S. 20 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-07-29 | 2025-05-24 |  | 30000 | 26421 | 6093
25 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-06-27 | 2019-11-29 | 2019-09-18 | 58253 | 73861 | 73861
25 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-09-25 | 2020-03-02 | 2020-01-23 | 291265 | 374605 | 341120
25 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-07-06 | 2023-07-05 |  | 6553445 | 6042235 | 5414051
25 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-07-06 | 2023-07-05 |  | 407770 | 348951 | 310011
25 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2018-08-27 | 2018-11-28 | 2018-12-10 | 12200 | 27434 | 27434
25 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2019-01-03 | 2019-05-20 | 2020-02-28 | 60999 | 119386 | 98453
25 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2021-08-16 | 2022-08-15 |  | 1372472 | 1589581 | 1317965
25 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2021-08-16 | 2022-08-15 |  | 85398 | 154344 | 134656
25 | P.S. 24 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 2024-02-26 | 2024-07-26 | 2024-05-06 | 34620 | 47837 | 46593
25 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-06-25 | 2019-11-26 | 2019-09-25 | 79750 | 114109 | 114109
25 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-09-27 | 2020-03-04 | 2020-01-23 | 398750 | 568412 | 494090
25 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-04-12 | 2023-04-11 |  | 8971875 | 9670970 | 8276141
25 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-04-12 | 2023-04-11 |  | 558250 | 1144752 | 1074632
25 | J.H.S. 25 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2023-06-14 | 2023-10-31 | 2023-11-06 | 33761 | 60358 | 59633
25 | J.H.S. 25 - QUEENS | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2023-11-15 | 2024-04-18 | 2024-05-06 | 168805 | 118845 | 112800
25 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2017-12-18 | 2018-05-04 | 2018-04-03 | 85230 | 56741 | 56741
25 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2018-04-03 | 2018-08-31 | 2023-02-24 | 426150 | 481151 | 405747
25 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 2023-07-10 | 2025-09-06 |  | 9588375 | 8775584 | 5627604
25 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-07-10 | 2025-09-06 |  | 596610 | 426018 | 329163
25 | P.S. 29 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS | Scope | In-Progress | 2024-06-07 | 2024-10-24 |  | 166654 | 166654 | 39291
25 | P.S. 32 - QUEENS | SCA Capacity | ADDITION | Scope | Complete | 2019-09-10 | 2020-02-24 | 2020-02-21 | 967475 | 638086 | 632442
25 | P.S. 32 - QUEENS | SCA Capacity | ADDITION | Design | Complete | 2020-02-24 | 2020-09-09 | 2021-05-13 | 4353640 | 3652099 | 3025045
25 | P.S. 32 - QUEENS | SCA Capacity | ADDITION | Construction | Complete | 2022-01-11 | 2024-09-03 | 2024-06-18 | 54904232 | 51381230 | 49073138
25 | P.S. 32 - QUEENS | SCA Capacity | ADDITION | CM,Art,F&E | Complete | 2022-01-11 | 2024-09-03 | 2024-06-18 | 7739804 | 7380854 | 5668125
25 | P.S. 32 - QUEENS | SCA CIP | EXISTING BUILDING WORK | Scope | Complete | 2021-03-25 | 2021-07-23 | 2021-07-26 | 70576 | 80195 | 80195
25 | P.S. 32 - QUEENS | SCA CIP | EXISTING BUILDING WORK | Design | Complete | 2021-07-26 | 2022-01-18 | 2023-02-06 | 352881 | 534412 | 321302
25 | P.S. 32 - QUEENS | SCA CIP RESOA | FY19 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 2019-10-21 | 2020-01-21 | 2020-02-14 | 67421 | 85412 | 73171
25 | P.S. 32 - QUEENS | SCA CIP RESOA | FY19 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | Complete | 2023-03-06 | 2024-03-04 | 2024-04-09 | 988849 | 654432 | 453441
25 | P.S. 32 - QUEENS | SCA CIP RESOA | FY19 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | Complete | 2023-03-06 | 2024-03-04 | 2024-04-09 | 73841 | 103454 | 102206
25 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2021-04-19 | 2021-09-17 | 2021-07-20 | 78720 | 75072 | 75072
25 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2021-07-22 | 2022-01-21 | 2022-03-30 | 393600 | 325415 | 277681
25 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-06-22 | 2024-02-11 |  | 8856000 | 8353053 | 4359282
25 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-06-22 | 2024-02-11 |  | 551040 | 200690 | 190508
25 | P.S. 79 - QUEENS | SCA CIP | HVAC PIPING REPLACEMENT | Scope | Complete | 2021-12-29 | 2022-06-01 | 2022-01-04 | 19000 | 3695 | 3695
25 | P.S. 79 - QUEENS | SCA CIP | HVAC PIPING REPLACEMENT | Design | Complete | 2022-01-04 | 2022-06-06 | 2022-02-24 | 85502 | 14780 | 14780
25 | P.S. 79 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-09 | 2024-08-08 | 2024-05-07 | 6454 | 1877 | 1877
25 | P.S. 79 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-05-07 | 2024-11-01 |  | 29041 | 29041 | 7508
25 | P.S. 79 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Design | Complete | 2023-05-23 | 2023-10-10 | 2023-11-28 | 61425 | 42000 | 41064
25 | P.S. 107 - QUEENS | SCA CIP | RTU REPLACEMENT | Scope | Complete | 2023-04-14 | 2023-04-14 | 2023-04-14 | 5809 | 692 | 692
25 | P.S. 107 - QUEENS | SCA CIP | RTU REPLACEMENT | Design | Complete | 2023-04-14 | 2023-06-07 | 2023-06-07 | 26140 | 2768 | 2768
25 | P.S. 107 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM / LIGHTING UPGRADE | Scope | Complete | 2023-08-23 | 2024-01-22 | 2023-12-22 | 314790 | 273867 | 260661
25 | P.S. 107 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM / LIGHTING UPGRADE | Design | In-Progress | 2024-01-03 | 2024-08-09 |  | 1529388 | 1529388 | 422911
25 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-06-20 | 2023-10-19 | 2023-06-26 | 4934 | 3171 | 3171
25 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-26 | 2023-12-21 | 2023-11-01 | 22203 | 12685 | 12685
25 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-09 | 2025-01-03 |  | 286175 | 251836 | 26300
25 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-09 | 2025-01-03 |  | 53041 | 80372 | 80372
25 | P.S. 107 - QUEENS | SCA CIP RESOA | FY16 RESO A MEDIA CENTER UPGRADE | Design | Complete | 2021-05-03 | 2021-09-16 | 2022-01-27 | 42000 | 81383 | 58635
25 | P.S. 107 - QUEENS | SCA CIP RESOA | FY16 RESO A MEDIA CENTER UPGRADE | Construction | In-Progress | 2022-06-09 | 2023-03-05 |  | 616000 | 353226 | 178618
25 | P.S. 107 - QUEENS | SCA CIP RESOA | FY16 RESO A MEDIA CENTER UPGRADE | CM,F&E | In-Progress | 2022-06-09 | 2023-03-05 |  | 264544 | 276668 | 258853
25 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | Scope | Complete | 2020-05-27 | 2021-11-17 | 2021-09-15 | 239846 | 281135 | 281135
25 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | Design | Complete | 2021-10-19 | 2022-06-30 | 2022-04-27 | 1197635 | 559727 | 534559
25 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | Construction | In-Progress | 2022-09-06 | 2024-09-04 |  | 26808715 | 24389271 | 18176901
25 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | CM,F&E | In-Progress | 2022-09-06 | 2024-09-04 |  | 1690897 | 408974 | 359074
25 | P.S. 129 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 2024-06-13 | 2024-10-30 | 2024-09-13 | 244389 | 42900 | 29617
25 | P.S. 129 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | In-Progress | 2024-09-23 | 2025-02-27 |  | 1140482 | 1140482 | 58463
25 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-14 | 2023-04-17 | 2022-12-21 | 4269 | 5420 | 5420
25 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-21 | 2023-06-20 | 2023-04-04 | 19211 | 21680 | 21680
25 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-08-07 | 2024-06-01 |  | 247602 | 223741 | 170284
25 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-08-07 | 2024-06-01 |  | 152797 | 145049 | 93420
25 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2021-04-28 | 2021-09-13 | 2021-11-08 | 13340 | 16918 | 16918
25 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2021-11-19 | 2022-04-25 | 2022-05-17 | 60030 | 54487 | 54487
25 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 2022-10-24 | 2024-02-15 |  | 773720 | 752997 | 457571
25 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 2022-10-24 | 2024-02-15 |  | 143405 | 132840 | 116273
25 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-05-31 | 2022-11-23 | 2022-09-09 | 155491 | 148986 | 142439
25 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2022-09-23 | 2023-06-12 | 2023-04-14 | 777450 | 423460 | 423460
25 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-07-17 | 2025-10-03 |  | 17492626 | 15884931 | 4727952
25 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-07-17 | 2025-10-03 |  | 1088430 | 507467 | 390246
25 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-05-23 | 2022-09-21 | 2022-06-15 | 5787 | 4435 | 4435
25 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-15 | 2022-12-12 | 2022-12-07 | 26043 | 17739 | 17739
25 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-05-22 | 2024-03-16 |  | 335670 | 306037 | 262386
25 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-05-22 | 2024-03-16 |  | 180245 | 162363 | 90565
25 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-06-16 | 2023-10-18 | 2023-06-21 | 4985 | 2000 | 2000
25 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-21 | 2023-12-18 | 2023-11-01 | 22433 | 7998 | 7998
25 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-09 | 2025-01-03 |  | 289135 | 257697 | 87000
25 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-09 | 2025-01-03 |  | 53590 | 82188 | 82188
25 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 2021-07-22 | 2021-10-21 | 2021-10-20 | 14360 | 8505 | 8505
25 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 2021-10-27 | 2022-04-01 | 2022-01-19 | 64620 | 34019 | 34019
25 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | Construction | In-Progress | 2022-04-11 | 2023-01-05 |  | 832880 | 750944 | 669840
25 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2022-04-11 | 2023-01-05 |  | 154370 | 97638 | 96193
25 | I.S. 294 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 2022-01-04 | 2022-06-06 | 2022-05-02 | 47400 | 31797 | 31070
25 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-21 | 2022-12-07 | 2023-08-10 | 30349 | 127385 | 126795
25 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-09-06 | 2024-02-09 | 2024-04-18 | 149646 | 272388 | 168090
25 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-09-23 | 2026-09-12 |  | 3185472 | 2994124 | 69494
25 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-09-23 | 2026-09-12 |  | 228186 | 310519 | 209777
25 | P.S. 184 - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-08-09 | 2022-12-27 | 2023-03-13 | 77136 | 86185 | 64414
25 | P.S. 184 - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-11-27 | 2024-10-20 |  | 1131331 | 803091 | 319744
25 | P.S. 184 - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-11-27 | 2024-10-20 |  | 77136 | 108354 | 62761
25 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2019-07-24 | 2019-10-23 | 2019-09-25 | 18000 | 10188 | 10188
25 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2019-10-22 | 2020-03-26 | 2020-03-26 | 81000 | 40798 | 40798
25 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2021-06-09 | 2022-04-04 |  | 1044000 | 928549 | 896292
25 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2021-06-09 | 2022-04-04 |  | 193500 | 101877 | 99304
25 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 2022-05-20 | 2022-10-05 | 2022-12-27 | 157000 | 231554 | 229974
25 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Design | Complete | 2023-01-18 | 2023-06-20 | 2023-05-09 | 785001 | 679639 | 589393
25 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Construction | In-Progress | 2023-07-07 | 2025-10-03 |  | 17662500 | 16270217 | 6535853
25 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-07-07 | 2025-10-03 |  | 1099001 | 612914 | 495569
25 | J.H.S. 189 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-07-08 | 2024-12-09 |  | 42300 | 24806 | 1117
25 | J.H.S. 189 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-08-12 | 2024-12-16 |  | 12686 | 12686 | 0
25 | P.S. 193 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-07-13 | 2023-11-29 | 2024-01-09 | 21160 | 70670 | 70670
25 | P.S. 193 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 2024-01-19 | 2024-06-20 | 2024-05-14 | 102927 | 42164 | 7466
25 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | Scope | Complete | 2016-09-22 | 2018-06-05 | 2018-03-22 | 145334 | 225336 | 225336
25 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | Design | Complete | 2018-04-04 | 2018-09-04 | 2018-10-05 | 582551 | 913169 | 837282
25 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2019-07-15 | 2021-07-13 |  | 10858766 | 10874577 | 9655274
25 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2019-07-15 | 2021-07-13 |  | 693003 | 1311194 | 1277737
25 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 2021-06-09 | 2021-11-24 | 2021-11-05 | 42780 | 46302 | 46302
25 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | Design | Complete | 2021-11-19 | 2022-04-25 | 2022-05-11 | 213900 | 118968 | 118968
25 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | Construction | In-Progress | 2022-07-15 | 2024-01-05 |  | 4812750 | 4569249 | 4331584
25 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | CM,F&E | In-Progress | 2022-07-15 | 2024-01-05 |  | 299460 | 165524 | 140762
25 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-05-25 | 2022-09-23 | 2022-06-15 | 7070 | 3868 | 3868
25 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-15 | 2022-12-12 | 2022-12-07 | 31815 | 15472 | 15472
25 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-05-22 | 2024-03-16 |  | 410058 | 370633 | 325153
25 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-05-22 | 2024-03-16 |  | 212233 | 187671 | 114922
25 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-09-01 | 2024-01-23 | 2023-12-29 | 82831 | 139645 | 134561
25 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2024-01-03 | 2024-06-04 | 2024-04-22 | 406321 | 356348 | 356348
25 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-09-16 | 2027-01-13 |  | 8464905 | 7630751 | 88509
25 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-09-16 | 2027-01-13 |  | 638536 | 51136 | 51136
25 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-23 | 2023-05-22 | 2023-02-03 | 4170 | 2723 | 2723
25 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-03 | 2023-08-01 | 2023-05-02 | 18765 | 10893 | 10893
25 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-11 | 2024-10-05 |  | 241860 | 223845 | 64867
25 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-11 | 2024-10-05 |  | 94240 | 83480 | 39610
25 | P.S. 201 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-04-09 | 2024-08-08 | 2024-04-23 | 5134 | 930 | 930
25 | P.S. 201 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2024-04-23 | 2024-10-18 | 2024-09-25 | 23102 | 3718 | 3718
25 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2018-08-27 | 2019-06-19 | 2019-02-21 | 17660 | 9410 | 9410
25 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2019-02-21 | 2019-07-23 | 2019-05-16 | 70249 | 37574 | 37574
25 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2019-07-22 | 2020-05-16 |  | 1281825 | 1193206 | 1105266
25 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2019-07-22 | 2020-05-16 |  | 87535 | 331939 | 321442
25 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | Scope | Complete | 2022-09-30 | 2024-01-24 | 2023-12-22 | 158001 | 267569 | 258241
25 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | Design | Complete | 2024-01-03 | 2024-05-17 | 2024-05-02 | 790000 | 645168 | 645168
25 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | Construction | In-Progress | 2024-09-23 | 2027-01-20 |  | 17775001 | 16065979 | 253029
25 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | CM,F&E | In-Progress | 2024-09-23 | 2027-01-20 |  | 1105999 | 66480 | 66480
25 | P.S. 209 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 2022-04-18 | 2022-09-16 | 2022-07-13 | 23400 | 16118 | 16118
25 | P.S. 209 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2023-02-20 | 2023-11-16 |  | 343200 | 296562 | 271876
25 | P.S. 209 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-02-20 | 2023-11-16 |  | 23400 | 49594 | 49034
25 | P.S. 219 - QUEENS | SCA CIP | RTU / HVAC REPLACEMENT | Scope | Complete | 2019-03-26 | 2019-07-29 | 2020-03-24 | 19660 | 21203 | 21203
25 | P.S. 219 - QUEENS | SCA CIP | RTU / HVAC REPLACEMENT | Design | Complete | 2020-03-27 | 2020-08-17 | 2021-04-19 | 98300 | 148275 | 127664
25 | P.S. 219 - QUEENS | SCA CIP | RTU / HVAC REPLACEMENT | Construction | Complete | 2022-07-15 | 2023-07-14 | 2023-07-14 | 2211750 | 2017366 | 1985960
25 | P.S. 219 - QUEENS | SCA CIP | RTU / HVAC REPLACEMENT | CM,F&E | Complete | 2022-07-15 | 2023-07-14 | 2023-07-14 | 137620 | 210451 | 192308
25 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-02-01 | 2023-06-01 | 2023-02-06 | 4340 | 4388 | 4388
25 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-06 | 2023-08-02 | 2023-05-02 | 19530 | 17552 | 17552
25 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-12-11 | 2024-10-05 |  | 251720 | 233762 | 53376
25 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-12-11 | 2024-10-05 |  | 105988 | 97392 | 40550
25 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | Scope | Complete | 2018-02-27 | 2018-05-25 | 2018-07-31 | 142290 | 127209 | 121490
25 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | Design | Complete | 2018-08-28 | 2019-01-16 | 2019-04-16 | 569160 | 761112 | 664382
25 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | Construction | In-Progress | 2019-07-29 | 2021-07-17 |  | 10671750 | 9973800 | 8723895
25 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | CM,F&E | In-Progress | 2019-07-29 | 2021-07-17 |  | 664020 | 464817 | 452576
25 | J.H.S. 237 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Design | Complete | 2021-09-23 | 2022-02-24 | 2022-02-07 | 105240 | 137427 | 109384
25 | J.H.S. 237 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 2022-06-17 | 2023-03-13 |  | 1543520 | 803496 | 133803
25 | J.H.S. 237 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | CM,F&E | In-Progress | 2022-06-17 | 2023-03-13 |  | 105240 | 95705 | 91321
25 | P.S. 244 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Scope | Complete | 2023-10-10 | 2024-03-08 | 2024-03-25 | 56562 | 152829 | 150643
25 | P.S. 244 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Design | Complete | 2024-03-25 | 2024-08-23 | 2024-05-15 | 282809 | 334729 | 33489
25 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE / RESO A EXTERIOR DOOR | Design | Complete | 2023-10-25 | 2024-03-25 | 2024-02-05 | 54359 | 89409 | 55140
25 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE / RESO A EXTERIOR DOOR | Construction | In-Progress | 2024-06-10 | 2025-05-05 |  | 797263 | 659210 | 49352
25 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE / RESO A EXTERIOR DOOR | CM,F&E | In-Progress | 2024-06-10 | 2025-05-05 |  | 54359 | 87689 | 20042
25 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2022-03-25 | 2022-09-02 | 2022-10-12 | 1787500 | 1467839 | 1298493
25 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 2022-10-13 | 2023-04-07 | 2023-05-12 | 8043750 | 2560685 | 1606914
25 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2024-04-22 | 2026-09-03 |  | 101440625 | 90595559 | 283348
25 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2024-04-22 | 2026-09-03 |  | 14300000 | 5480918 | 429146
25 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2022-09-08 | 2022-09-08 | 2022-09-08 | 65500 | 49200 | 49200
25 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2022-09-08 | 2022-12-08 | 2023-04-18 | 327500 | 119565 | 119565
25 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 2023-07-03 | 2024-03-28 |  | 7368750 | 6658418 | 338140
25 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2023-07-03 | 2024-03-28 |  | 458500 | 110094 | 99898
25 | DISTRICT 25 PRE-K CENTER | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2022-09-28 | 2022-12-30 | 2022-12-20 | 17580 | 27210 | 27210
25 | DISTRICT 25 PRE-K CENTER | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-12-21 | 2023-06-27 | 2023-05-01 | 87901 | 81857 | 79440
25 | JOHN BOWNE HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 2021-10-14 | 2022-02-17 | 2022-03-30 | 96080 | 128486 | 118609
25 | JOHN BOWNE HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 2023-04-14 | 2023-08-30 | 2024-04-16 | 472411 | 312168 | 268132
25 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA GYM FLOOR REPLACEMENT | Scope | Complete | 2023-01-13 | 2023-04-17 | 2023-02-15 | 2739 | 15811 | 398
25 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA GYM FLOOR REPLACEMENT | Design | Complete | 2023-04-13 | 2023-08-14 | 2024-04-16 | 12325 | 1319 | 1319
25 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Scope | Complete | 2023-08-09 | 2023-12-12 | 2023-08-24 | 2093 | 20350 | 336
25 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Design | Complete | 2023-08-25 | 2024-01-17 | 2024-04-16 | 9419 | 21342 | 1344
25 | FLUSHING HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 2023-11-13 | 2024-04-01 | 2024-08-21 | 45000 | 60633 | 56462
25 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 2020-02-24 | 2020-07-08 | 2021-11-29 | 10073 | 18095 | 18095
25 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | Design | Complete | 2021-12-08 | 2022-05-11 | 2022-12-02 | 45329 | 87748 | 69532
25 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | Construction | In-Progress | 2023-12-18 | 2024-12-16 |  | 584240 | 634917 | 95982
25 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | CM,F&E | In-Progress | 2023-12-18 | 2024-12-16 |  | 108286 | 97137 | 50570
25 | FLUSHING HS - QUEENS | SCA CIP RESOA | FY23 RESO A ATHLETIC FIELD UPGRADE | Design | Complete | 2023-07-25 | 2024-01-25 | 2024-05-14 | 77472 | 315752 | 286538
25 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2023-04-13 | 2023-08-17 | 2023-09-18 | 1195340 | 1228892 | 1065122
25 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 2023-09-19 | 2024-04-12 | 2024-05-09 | 5379030 | 1464002 | 1314065
25 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2024-09-16 | 2027-09-03 |  | 67835545 | 60945525 | 346972
25 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2024-09-16 | 2027-09-03 |  | 9562720 | 3700759 | 347560
25 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2023-05-11 | 2023-05-11 | 2023-05-11 | 39545 | 1077 | 1077
25 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2023-05-12 | 2023-08-31 | 2024-01-16 | 197723 | 103071 | 91219
25 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 2024-05-20 | 2024-12-15 |  | 4448759 | 4703256 | 173750
25 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2024-05-20 | 2024-12-15 |  | 276812 | 121292 | 121182
25 | JOHN BOWNE HS ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2023-04-20 | 2023-08-24 | 2023-08-17 | 952120 | 734470 | 671572
25 | JOHN BOWNE HS ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 2023-08-18 | 2024-03-28 | 2024-05-09 | 4284540 | 978389 | 921307
25 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2023-06-02 | 2023-07-07 | 2023-06-02 | 15889 | 19866 | 19779
25 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2023-06-05 | 2023-10-27 | 2023-11-17 | 71501 | 98363 | 76401
25 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 2024-07-08 | 2025-05-03 |  | 921563 | 838238 | 4387
25 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2024-07-08 | 2025-05-03 |  | 170807 | 85337 | 80690
25 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2024-04-22 | 2024-09-17 | 2024-09-17 | 763046 | 315003 | 253083
25 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | In-Progress | 2024-09-18 | 2025-04-21 |  | 3052183 | 3052183 | 582946
25 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2024-04-23 | 2024-04-23 | 2024-04-23 | 32564 | 2772 | 2772
25 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA CIP | DEMOLITION | Design | In-Progress | 2024-04-24 | 2024-08-23 |  | 151965 | 151965 | 25190
26 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2020-01-21 | 2020-06-19 | 2020-05-27 | 64200 | 77135 | 77135
26 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2020-05-27 | 2020-10-27 | 2020-08-19 | 321000 | 352504 | 297671
26 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-05-10 | 2024-05-08 |  | 7222500 | 6555743 | 6242044
26 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-05-10 | 2024-05-08 |  | 449400 | 556714 | 551552
26 | P.S. 18 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | In-Progress | 2024-08-15 | 2025-01-03 |  | 123787 | 123787 | 23841
26 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | Scope | Complete | 2019-10-25 | 2021-09-21 | 2021-09-21 | 1198860 | 863967 | 823640
26 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | Design | Complete | 2021-09-21 | 2022-05-11 | 2022-05-09 | 5394870 | 2750653 | 1972783
26 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | Construction | In-Progress | 2022-08-08 | 2025-09-03 |  | 68035305 | 61951933 | 56622250
26 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | CM,Art,F&E | In-Progress | 2022-08-08 | 2025-09-03 |  | 9590880 | 5787775 | 2514856
26 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2018-01-19 | 2018-06-20 | 2018-04-09 | 108255 | 71205 | 71205
26 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2018-05-02 | 2018-11-29 | 2018-08-21 | 433020 | 238935 | 226020
26 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2019-01-14 | 2021-01-12 |  | 8119125 | 7776967 | 7269329
26 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2019-01-14 | 2021-01-12 |  | 505190 | 671900 | 659001
26 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING RENOVATIONS | Scope | Complete | 2021-08-05 | 2021-10-18 | 2021-12-06 | 79322 | 73318 | 73318
26 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING RENOVATIONS | Design | Complete | 2021-12-15 | 2022-06-10 | 2023-07-19 | 396611 | 230534 | 210114
26 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING-GYMNASIUM / EXISTING BUILDING-AUDITORIUM | Scope | Complete | 2022-02-10 | 2022-06-27 | 2022-07-27 | 11184 | 9015 | 3250
26 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING-GYMNASIUM / EXISTING BUILDING-AUDITORIUM | Design | Complete | 2022-08-09 | 2023-01-30 | 2023-05-11 | 50326 | 13997 | 13997
26 | P.S. 26 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 2021-12-01 | 2022-06-24 | 2022-07-08 | 23546 | 22672 | 22672
26 | P.S. 26 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 2022-07-11 | 2022-12-12 | 2023-05-22 | 105958 | 68745 | 65309
26 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 2014-09-17 | 2015-02-05 | 2015-03-16 | 226470 | 129723 | 129723
26 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 2016-02-12 | 2016-07-14 | 2016-10-12 | 898205 | 1019021 | 931008
26 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 2017-05-08 | 2019-04-07 |  | 16151973 | 32506517 | 23377268
26 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 2017-05-08 | 2019-04-07 |  | 1156717 | 1818018 | 1752758
26 | P.S. 41 - QUEENS | SCA Capacity | ADDITION / DEMOLITION | Scope | Complete | 2019-02-25 | 2019-08-02 | 2019-08-02 | 1026305 | 799639 | 792131
26 | P.S. 41 - QUEENS | SCA Capacity | ADDITION / DEMOLITION | Design | Complete | 2019-08-05 | 2020-02-28 | 2020-03-30 | 4618376 | 2996399 | 2605326
26 | P.S. 41 - QUEENS | SCA Capacity | ADDITION / DEMOLITION | Construction | Complete | 2021-07-19 | 2024-09-03 | 2024-06-25 | 58242856 | 54458150 | 51348568
26 | P.S. 41 - QUEENS | SCA Capacity | ADDITION / DEMOLITION | CM,Art,F&E | Complete | 2021-07-19 | 2024-09-03 | 2024-06-25 | 8210447 | 9014722 | 6790028
26 | P.S. 41 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2018-11-16 | 2019-04-05 | 2019-06-19 | 69195 | 175393 | 139968
26 | P.S. 41 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 2024-07-10 | 2024-12-11 |  | 276782 | 276782 | 2937
26 | P.S. 41 - QUEENS | SCA CIP | SSBA - WORK IN EXISTING BUILDING | Scope | Complete | 2021-06-08 | 2021-10-20 | 2022-02-08 | 20400 | 66933 | 66933
26 | P.S. 41 - QUEENS | SCA CIP | SSBA - WORK IN EXISTING BUILDING | Design | Complete | 2022-02-17 | 2022-07-20 | 2023-01-04 | 101998 | 226249 | 215939
26 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | Scope | Complete | 2019-10-28 | 2019-12-19 | 2020-02-28 | 67959 | 130632 | 130632
26 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | Design | Complete | 2020-03-11 | 2020-10-13 | 2021-12-22 | 339795 | 364047 | 213489
26 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | Construction | In-Progress | 2024-07-10 | 2026-03-01 |  | 7645388 | 7032030 | 17151
26 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | CM,F&E | In-Progress | 2024-07-10 | 2026-03-01 |  | 475713 | 528036 | 419648
26 | J.H.S. 67 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA GYM PARTITION & BLEACHERS | Scope | Complete | 2021-11-05 | 2022-03-28 | 2023-12-04 | 84779 | 321120 | 267144
26 | J.H.S. 67 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA GYM PARTITION & BLEACHERS | Design | In-Progress | 2023-12-05 | 2024-09-27 |  | 415109 | 415109 | 156935
26 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-21 | 2022-12-07 | 2023-03-31 | 97063 | 132275 | 132170
26 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-04-21 | 2023-09-22 | 2023-10-10 | 485315 | 458655 | 354876
26 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-05-06 | 2026-05-05 |  | 10919587 | 10026143 | 920836
26 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-05-06 | 2026-05-05 |  | 680443 | 162840 | 162265
31 | P.S. 29 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PLAYGROUNDS | Design | Complete | 2022-09-01 | 2023-01-05 | 2023-01-27 | 25426 | 25426 | 22928
26 | I.S. 74 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA DOMESTIC PIPING / IDA ELECTRICAL SYSTEMS / IDA CLIMATE CONTROL | Scope | Complete | 2021-10-08 | 2022-02-14 | 2022-02-03 | 65530 | 85203 | 85203
26 | I.S. 74 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA DOMESTIC PIPING / IDA ELECTRICAL SYSTEMS / IDA CLIMATE CONTROL | Design | Complete | 2022-09-21 | 2023-02-09 | 2023-02-16 | 316124 | 250740 | 238687
26 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-07-01 | 2022-11-01 | 2022-07-22 | 4534 | 3758 | 3758
26 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-07-22 | 2023-01-20 | 2023-01-18 | 20403 | 15035 | 15035
26 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-12 | 2024-04-06 |  | 262972 | 232369 | 205176
26 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-12 | 2024-04-06 |  | 163606 | 167899 | 111549
26 | P.S. 94 - QUEENS | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2024-06-06 |  | 2024-08-14 | 100000 | 100000 | 100000
26 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | Scope | Complete | 2018-03-14 | 2018-07-27 | 2018-08-22 | 59355 | 20865 | 20865
26 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | Design | Complete | 2018-09-19 | 2019-02-25 | 2019-05-13 | 237420 | 150757 | 135425
26 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | Construction | In-Progress | 2019-07-29 | 2020-10-20 |  | 4451625 | 4522066 | 4086181
26 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | CM,F&E | In-Progress | 2019-07-29 | 2020-10-20 |  | 276990 | 203199 | 172662
26 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2022-04-28 | 2022-09-13 | 2022-08-09 | 10940 | 26008 | 15031
26 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2022-08-12 | 2023-01-18 | 2022-12-22 | 49230 | 59433 | 58021
26 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 2023-04-17 | 2024-02-10 |  | 634520 | 561076 | 40325
26 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-04-17 | 2024-02-10 |  | 117605 | 84783 | 80488
26 | P.S. 98 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Design | Complete | 2021-06-08 | 2021-11-29 | 2022-02-11 | 48700 | 91408 | 15544
26 | P.S. 98 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 2022-06-06 | 2023-03-02 |  | 714265 | 471747 | 326351
26 | P.S. 98 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | CM,F&E | In-Progress | 2022-06-06 | 2023-03-02 |  | 48700 | 93021 | 44950
26 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2021-04-20 | 2021-09-20 | 2021-07-23 | 80154 | 66860 | 66860
26 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2021-07-27 | 2022-01-27 | 2021-12-15 | 400084 | 369033 | 301882
26 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-08-03 | 2024-08-01 |  | 8942768 | 8246813 | 7453685
26 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-08-03 | 2024-08-01 |  | 566200 | 276306 | 273384
26 | P.S. 133 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2023-06-30 | 2023-11-16 | 2023-11-22 | 89511 | 204516 | 204516
26 | P.S. 133 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2023-12-13 | 2024-05-15 | 2024-04-30 | 446924 | 420323 | 337977
26 | J.H.S. 158 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-11-13 | 2024-04-01 | 2024-06-04 | 158932 | 171026 | 171026
26 | J.H.S. 158 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 2024-06-06 | 2024-11-07 |  | 773118 | 836866 | 195345
26 | J.H.S. 158 - QUEENS | SCA CIP | GYM CEILING | Scope | Complete | 2023-07-06 | 2023-11-06 | 2024-01-10 | 22052 | 22367 | 22367
26 | J.H.S. 158 - QUEENS | SCA CIP | GYM CEILING | Design | In-Progress | 2024-01-22 | 2024-06-05 |  | 102911 | 102911 | 31528
26 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2018-09-13 | 2019-06-19 | 2019-02-20 | 39159 | 28776 | 28776
26 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2019-02-20 | 2019-07-22 | 2019-05-16 | 151190 | 117519 | 117082
26 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2019-07-22 | 2020-05-16 |  | 2346034 | 2266189 | 2031298
26 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2019-07-22 | 2020-05-16 |  | 253539 | 166544 | 151890
26 | J.H.S. 158 - QUEENS | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-12-01 | 2024-05-29 | 2024-03-06 | 66300 | 21925 | 21925
26 | J.H.S. 158 - QUEENS | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-07-29 | 2025-05-24 |  | 972400 | 162560 | 0
26 | J.H.S. 158 - QUEENS | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-07-29 | 2025-05-24 |  | 66300 | 16354 | 5112
26 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-06-27 | 2022-11-10 | 2023-01-13 | 145740 | 285393 | 275306
26 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-01-18 | 2023-06-20 | 2023-05-05 | 728699 | 700564 | 602626
26 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2023-07-10 | 2025-10-06 |  | 16395751 | 14944905 | 6373197
26 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2023-07-10 | 2025-10-06 |  | 1020180 | 522348 | 401289
26 | P.S. 162 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2024-05-15 | 2024-10-01 | 2024-09-17 | 32273 | 46877 | 4159
26 | P.S. 162 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | In-Progress | 2024-09-24 | 2025-02-28 |  | 150606 | 150606 | 4236
26 | P.S. 162 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-06-01 | 2024-01-26 | 2023-12-20 | 14541 | 64025 | 51367
26 | P.S. 162 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Design | Complete | 2024-01-23 | 2024-05-23 | 2024-05-10 | 71092 | 152206 | 148198
26 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2019-06-11 | 2019-10-25 | 2019-10-25 | 151880 | 217371 | 217371
26 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2019-11-13 | 2020-06-15 | 2020-04-14 | 759401 | 721358 | 568650
26 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2021-08-16 | 2023-08-15 |  | 17086500 | 20590883 | 15431250
26 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2021-08-16 | 2023-08-15 |  | 1063161 | 1017797 | 838410
26 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-05-16 | 2022-09-14 | 2022-06-15 | 5258 | 4117 | 4117
26 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-15 | 2022-12-12 | 2022-12-07 | 23661 | 16466 | 16466
26 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-06-12 | 2024-04-06 |  | 304964 | 279476 | 239861
26 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-06-12 | 2024-04-06 |  | 176647 | 158642 | 104451
26 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-06-16 | 2021-12-15 | 2021-11-04 | 63240 | 150549 | 150549
26 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2021-11-18 | 2022-06-30 | 2022-04-18 | 316200 | 301863 | 301863
26 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2022-07-15 | 2024-04-04 |  | 7114500 | 6481598 | 4831251
26 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-07-15 | 2024-04-04 |  | 443909 | 318725 | 317377
26 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2015-10-15 | 2016-03-21 | 2015-12-31 | 122396 | 132963 | 118763
26 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2016-01-06 | 2016-06-07 | 2016-06-24 | 480196 | 555060 | 549191
26 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2016-10-17 | 2018-04-09 |  | 8161174 | 8116966 | 7876023
26 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2016-10-17 | 2018-04-09 |  | 693216 | 812171 | 807105
26 | Q177 SPED - QUEENS | SCA CIP | IDA FLOOD ELIMINATION | Scope | Complete | 2022-01-20 | 2022-05-23 | 2022-08-05 | 28144 | 49861 | 2671
26 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2017-09-20 | 2019-04-10 | 2019-03-26 | 251255 | 197789 | 197586
26 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2019-03-26 | 2019-08-23 | 2019-05-17 | 994516 | 620741 | 551146
26 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2019-10-21 | 2021-08-10 |  | 17704514 | 18444247 | 17019520
26 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2019-10-21 | 2021-08-10 |  | 1309066 | 581493 | 506709
26 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-05-26 | 2022-09-26 | 2022-06-15 | 3814 | 4553 | 4553
26 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-15 | 2022-12-12 | 2022-12-07 | 17165 | 18211 | 18211
26 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-27 | 2024-09-21 |  | 221235 | 204573 | 154534
26 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-27 | 2024-09-21 |  | 106219 | 96243 | 90321
26 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | In-Progress | 2024-07-08 | 2024-11-21 |  | 88366 | 64221 | 8364
26 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-06-29 | 2022-10-28 | 2022-09-28 | 3560 | 4864 | 4864
26 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-09-28 | 2023-03-29 | 2023-03-29 | 16020 | 19454 | 19454
26 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-27 | 2024-09-21 |  | 206480 | 187143 | 132809
26 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-27 | 2024-09-21 |  | 84906 | 73724 | 50693
26 | Q004 SPED - QUEENS | SCA CIP | ROOFS | Scope | In-Progress | 2024-06-18 | 2024-11-04 |  | 62803 | 62803 | 20318
26 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-14 | 2023-04-17 | 2023-01-03 | 4078 | 4810 | 4810
26 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-03 | 2023-06-29 | 2023-03-29 | 18349 | 19239 | 19239
26 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-27 | 2024-09-21 |  | 236501 | 217174 | 154953
26 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-27 | 2024-09-21 |  | 106867 | 97417 | 75002
26 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | Scope | Complete | 2020-01-14 | 2020-05-29 | 2021-05-03 | 123354 | 174365 | 174351
26 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | Design | Complete | 2021-05-24 | 2021-10-25 | 2022-02-02 | 615417 | 576155 | 491421
26 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | Construction | In-Progress | 2022-09-06 | 2024-09-04 |  | 13729741 | 13002976 | 9637301
26 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | CM,F&E | In-Progress | 2022-09-06 | 2024-09-04 |  | 873635 | 621835 | 574779
26 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-17 | 2023-07-18 | 2023-03-28 | 4640 | 2926 | 2926
26 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-28 | 2023-09-21 | 2023-05-03 | 20880 | 11704 | 11704
26 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-30 | 2024-08-24 |  | 269120 | 241620 | 134250
26 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-30 | 2024-08-24 |  | 172129 | 153681 | 149866
26 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-10 | 2023-07-11 | 2023-03-29 | 4800 | 1852 | 1852
26 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-29 | 2023-09-22 | 2023-05-03 | 21600 | 7407 | 7407
26 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-30 | 2024-08-24 |  | 278400 | 253015 | 201428
26 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-30 | 2024-08-24 |  | 76455 | 55755 | 46923
26 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | Scope | Complete | 2017-12-22 | 2018-05-10 | 2018-03-02 | 58200 | 78279 | 78279
26 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | Design | Complete | 2018-03-14 | 2018-08-13 | 2018-05-14 | 232800 | 323404 | 281698
26 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | Construction | In-Progress | 2018-07-23 | 2019-10-15 |  | 4365000 | 5108142 | 3766392
26 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | CM,F&E | In-Progress | 2018-07-23 | 2019-10-15 |  | 271600 | 701830 | 644153
26 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-06-27 | 2019-11-29 | 2019-08-23 | 65750 | 58621 | 58621
26 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-09-10 | 2020-02-13 | 2019-12-20 | 328750 | 279484 | 279484
26 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-10-10 | 2024-10-08 |  | 7396875 | 6711941 | 2761823
26 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-10-10 | 2024-10-08 |  | 461282 | 349022 | 302403
26 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-01 | 2023-06-29 | 2023-03-03 | 3700 | 7021 | 7021
26 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-03 | 2023-08-28 | 2023-05-03 | 16650 | 28085 | 28085
26 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-02 | 2024-07-27 |  | 214600 | 200706 | 3984
26 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-02 | 2024-07-27 |  | 46862 | 35205 | 18701
26 | P.S./I.S. 208 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 2024-06-11 | 2024-09-11 |  | 10000 | 42873 | 4430
26 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | Complete | 2019-06-03 | 2019-10-17 | 2019-12-23 | 219544 | 246745 | 233661
26 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | Complete | 2021-10-06 | 2022-04-13 | 2023-01-05 | 1080292 | 963036 | 802489
26 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | Construction | In-Progress | 2023-04-17 | 2025-10-02 |  | 22799480 | 20440381 | 10708067
26 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | CM,F&E | In-Progress | 2023-04-17 | 2025-10-02 |  | 1667470 | 272064 | 234799
26 | P.S. 213 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 2022-10-14 | 2023-03-06 | 2023-02-22 | 156066 | 158212 | 154315
26 | P.S. 213 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 2023-04-04 | 2023-09-05 | 2023-09-07 | 780330 | 333723 | 333723
26 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | Scope | Complete | 2022-05-16 | 2023-02-28 | 2023-02-28 | 1281380 | 791344 | 754930
26 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | Design | Complete | 2023-02-28 | 2023-06-12 | 2023-05-12 | 5766210 | 1788272 | 1223407
26 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | Construction | In-Progress | 2023-09-25 | 2026-09-03 |  | 72718315 | 65217146 | 5686567
26 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | CM,Art,F&E | In-Progress | 2023-09-25 | 2026-09-03 |  | 10251040 | 4064859 | 560533
26 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2014-12-16 | 2015-05-19 | 2015-04-10 | 90011 | 96465 | 96465
26 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2015-04-17 | 2015-09-17 | 2015-09-22 | 360045 | 303431 | 287334
26 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2017-04-17 | 2018-07-17 |  | 6750856 | 7061221 | 6716597
26 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2017-04-17 | 2018-07-17 |  | 420054 | 1069360 | 1058955
26 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2018-10-29 | 2019-03-19 | 2019-03-21 | 257999 | 136796 | 136796
26 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2019-03-21 | 2019-08-09 | 2019-05-17 | 1032001 | 653717 | 651217
26 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2019-07-22 | 2021-04-11 |  | 19350000 | 18435809 | 18258753
26 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2019-07-22 | 2021-04-11 |  | 1204000 | 487476 | 470830
26 | J.H.S. 216 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA WASTE SYSTEMS / IDA MECHANICAL PIPING / IDA INTERIOR SPACES | Scope | Complete | 2022-06-16 | 2022-11-01 | 2024-09-18 | 294820 | 23725 | 23725
26 | J.H.S. 216 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA WASTE SYSTEMS / IDA MECHANICAL PIPING / IDA INTERIOR SPACES | Design | In-Progress | 2024-09-18 | 2025-02-24 |  | 1411719 | 1411719 | 15119
26 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | Scope | Complete | 2022-06-06 | 2022-11-29 | 2022-11-29 | 28900 | 32864 | 32864
26 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | Design | Complete | 2022-11-29 | 2023-03-16 | 2023-03-21 | 144499 | 124371 | 115064
26 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | Construction | In-Progress | 2023-06-26 | 2024-06-24 |  | 3251222 | 3074468 | 2757001
26 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | CM,F&E | In-Progress | 2023-06-26 | 2024-06-24 |  | 202299 | 339165 | 317084
26 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2022-08-31 | 2023-03-01 | 2022-12-09 | 96409 | 189852 | 189601
26 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2022-12-09 | 2023-06-07 | 2023-04-21 | 478159 | 468655 | 468581
26 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2023-07-17 | 2025-10-13 |  | 10422440 | 9673735 | 8261394
26 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-07-17 | 2025-10-13 |  | 705506 | 467396 | 358571
26 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY19 RESO A ROOM CONVERSION | Design | Complete | 2021-04-21 | 2021-09-10 | 2022-03-09 | 72738 | 88757 | 81267
26 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY19 RESO A ROOM CONVERSION | Construction | In-Progress | 2024-02-12 | 2024-12-07 |  | 1066826 | 1019744 | 271826
26 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY19 RESO A ROOM CONVERSION | CM,F&E | In-Progress | 2024-02-12 | 2024-12-07 |  | 72738 | 97889 | 31053
26 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A GREENHOUSE | Design | In-Progress | 2022-09-22 | 2023-03-30 |  | 279059 | 173641 | 84897
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | RPZ VALVES | Scope | Complete | 2018-10-23 | 2019-04-23 | 2019-09-12 | 10924 | 40933 | 40933
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | RPZ VALVES | Design | Complete | 2022-09-06 | 2023-03-07 | 2023-03-02 | 54621 | 133621 | 133621
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | Scope | Complete | 2021-03-04 | 2021-07-02 | 2021-07-22 | 24450 | 20729 | 20729
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | Design | Complete | 2021-07-28 | 2021-12-30 | 2021-12-29 | 122250 | 79175 | 79175
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | Construction | In-Progress | 2023-04-10 | 2024-04-08 |  | 2750625 | 2678124 | 2036957
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | CM,F&E | In-Progress | 2023-04-10 | 2024-04-08 |  | 171150 | 137404 | 124492
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2020-08-05 | 2021-01-08 | 2020-12-23 | 116640 | 154281 | 154281
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2020-12-28 | 2021-07-30 | 2021-07-01 | 583200 | 671261 | 642321
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-01-03 | 2024-01-02 |  | 13122000 | 12680549 | 11605584
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-01-03 | 2024-01-02 |  | 816480 | 499318 | 472745
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2020-03-05 | 2020-07-06 | 2020-03-06 | 15792 | 9506 | 9506
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2020-03-06 | 2020-08-05 | 2020-05-12 | 58829 | 38027 | 38027
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2021-01-11 | 2021-10-07 |  | 1111005 | 1111005 | 1022299
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2021-01-11 | 2021-10-07 |  | 125025 | 103892 | 102898
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / NON-IDA REINFORCE SUPPORT ELEMENTS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES | Scope | Complete | 2022-09-29 | 2023-02-17 | 2023-02-21 | 114924 | 181019 | 177742
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / NON-IDA REINFORCE SUPPORT ELEMENTS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES | Design | Complete | 2023-02-21 | 2023-07-24 | 2023-07-26 | 568324 | 420902 | 382827
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | Scope | Complete | 2018-03-19 | 2019-05-24 | 2019-07-30 | 30972 | 46993 | 46993
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | Design | Complete | 2019-09-12 | 2020-03-19 | 2020-06-10 | 148068 | 207365 | 207049
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | Construction | In-Progress | 2022-07-06 | 2023-07-05 |  | 2744023 | 2666723 | 2512472
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | CM,F&E | In-Progress | 2022-07-06 | 2023-07-05 |  | 267746 | 428010 | 421122
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2022-03-21 | 2022-04-04 | 2022-04-04 | 11376 | 28137 | 63
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2022-04-05 | 2022-08-12 | 2023-04-12 | 56882 | 65759 | 31627
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 2023-08-07 | 2025-11-03 |  | 1279836 | 1142951 | 1015346
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2023-08-07 | 2025-11-03 |  | 79634 | 34689 | 34689
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP RESOA | FY20 RESO A ATHLETIC FIELD UPGRADE | Design | Complete | 2022-03-21 | 2022-08-18 | 2023-04-12 | 746531 | 519555 | 426171
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP RESOA | FY20 RESO A ATHLETIC FIELD UPGRADE | Construction | In-Progress | 2023-08-07 | 2025-11-03 |  | 10949121 | 10740110 | 1737329
26 | FRANCIS LEWIS HS - QUEENS | SCA CIP RESOA | FY20 RESO A ATHLETIC FIELD UPGRADE | CM,F&E | In-Progress | 2023-08-07 | 2025-11-03 |  | 747121 | 309063 | 309063
26 | MARTIN VAN BUREN HS - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2022-06-30 | 2022-11-16 | 2023-06-15 | 107878 | 162223 | 162223
26 | MARTIN VAN BUREN HS - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | In-Progress | 2023-07-11 | 2024-01-16 |  | 539391 | 539391 | 173506
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-11-06 | 2024-02-08 | 2024-02-07 | 5146 | 26758 | 26758
26 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2024-02-07 | 2024-06-24 | 2024-04-18 | 23159 | 107026 | 107026
26 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Scope | Complete | 2023-06-26 | 2023-12-22 | 2023-10-03 | 148504 | 144417 | 131995
26 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Design | Complete | 2023-10-10 | 2024-06-10 | 2024-04-02 | 735127 | 320329 | 320329
26 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Construction | In-Progress | 2024-09-23 | 2027-01-20 |  | 15900755 | 14111036 | 36
26 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-09-23 | 2027-01-20 |  | 1094986 | 54486 | 54486
26 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2015-09-25 | 2016-01-25 | 2015-12-18 | 83700 | 136933 | 126733
26 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2016-09-07 | 2017-02-10 | 2017-05-05 | 334800 | 681337 | 665837
26 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2017-08-22 | 2018-11-19 |  | 6277500 | 7751386 | 6938111
26 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2017-08-22 | 2018-11-19 |  | 390600 | 891806 | 863418
26 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-15 | 2023-07-14 | 2023-03-20 | 3900 | 2239 | 2239
26 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-20 | 2023-09-13 | 2023-05-03 | 17550 | 8954 | 8954
26 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-10-02 | 2024-07-27 |  | 226200 | 209126 | 2405
26 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-10-02 | 2024-07-27 |  | 91424 | 73841 | 20998
26 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 515 | 515
26 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2004-12-01 | 2005-05-15 | 2005-04-18 | 2600 | 20145 | 20145
26 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2006-05-22 | 2007-05-31 |  | 77000 | 325018 | 310012
26 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2006-05-22 | 2007-05-31 |  | 12240 | 92000 | 92000
27 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | Scope | Complete | 2014-02-07 | 2014-07-10 | 2014-04-08 | 251956 | 218691 | 218691
27 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | Design | Complete | 2014-04-08 | 2014-09-08 | 2014-09-11 | 991112 | 1581649 | 1450071
27 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | Construction | In-Progress | 2015-01-06 | 2017-03-15 |  | 17083341 | 17440290 | 16168197
27 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | CM,F&E | In-Progress | 2015-01-06 | 2017-03-15 |  | 1393945 | 4476053 | 4431178
27 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 2021-03-12 | 2021-07-27 | 2021-09-01 | 166231 | 167700 | 167700
27 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 2021-09-17 | 2022-02-23 | 2022-03-10 | 824628 | 562834 | 544807
27 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Construction | In-Progress | 2022-08-05 | 2024-08-03 |  | 17989111 | 16314265 | 4621407
27 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | CM,F&E | In-Progress | 2022-08-05 | 2024-08-03 |  | 1212610 | 312053 | 286927
27 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2018-07-31 | 2018-10-30 | 2018-12-12 | 17685 | 39477 | 39477
27 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2019-01-07 | 2019-05-29 | 2019-05-17 | 70740 | 143998 | 143070
27 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2019-12-18 | 2020-12-16 |  | 1326375 | 1613648 | 831310
27 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2019-12-18 | 2020-12-16 |  | 82530 | 324161 | 322096
27 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | Scope | Complete | 2019-08-30 | 2020-01-21 | 2021-10-27 | 140840 | 193990 | 193990
27 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | Design | Complete | 2021-11-05 | 2022-04-12 | 2022-05-05 | 704200 | 539644 | 475909
27 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | Construction | In-Progress | 2022-08-15 | 2024-05-05 |  | 15844499 | 14366040 | 11523649
27 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-08-15 | 2024-05-05 |  | 987109 | 330273 | 291385
27 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2018-10-17 | 2019-03-07 | 2019-02-20 | 182490 | 114694 | 114694
27 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2019-02-20 | 2019-07-22 | 2019-05-10 | 729960 | 679654 | 580970
27 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2019-08-05 | 2021-08-03 |  | 13686750 | 13345131 | 10664910
27 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2019-08-05 | 2021-08-03 |  | 851621 | 1550142 | 1512855
27 | P.S. 51 - QUEENS | SCA CIP | C OF O | Scope | Complete | 2021-06-07 | 2021-09-10 | 2021-11-01 | 7920 | 27204 | 27204
27 | P.S. 51 - QUEENS | SCA CIP | C OF O | Design | Complete | 2021-12-22 | 2022-06-16 | 2022-10-13 | 35640 | 54321 | 44720
27 | P.S. 51 - QUEENS | SCA CIP | C OF O | Construction | Complete | 2023-02-06 | 2023-12-02 | 2023-11-29 | 459360 | 414765 | 355588
27 | P.S. 51 - QUEENS | SCA CIP | C OF O | CM,F&E | Complete | 2023-02-06 | 2023-12-02 | 2023-11-29 | 85140 | 64731 | 63914
27 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2018-10-03 | 2019-03-11 | 2019-01-14 | 141298 | 141108 | 141108
27 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-01-30 | 2019-07-01 | 2019-05-15 | 608905 | 661166 | 644194
27 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2019-07-15 | 2021-07-13 |  | 12236625 | 11118590 | 10408638
27 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2019-07-15 | 2021-07-13 |  | 761390 | 1259846 | 1257760
27 | I.S. 53 - QUEENS | SCA CIP | WALK-IN REFRIGERTAORS AND FREEZERS | Scope | Complete | 2023-06-23 | 2023-10-23 | 2023-09-25 | 11669 | 15501 | 15501
27 | I.S. 53 - QUEENS | SCA CIP | WALK-IN REFRIGERTAORS AND FREEZERS | Design | Complete | 2023-10-02 | 2024-03-01 | 2024-02-07 | 52511 | 45806 | 43297
27 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | Scope | Complete | 2021-06-24 | 2022-01-12 | 2022-01-20 | 15933 | 21058 | 21058
27 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | Design | Complete | 2022-01-21 | 2022-05-23 | 2022-04-11 | 79562 | 74014 | 74014
27 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | Construction | In-Progress | 2023-07-20 | 2024-07-18 |  | 1781235 | 1620530 | 1225494
27 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | CM,F&E | In-Progress | 2023-07-20 | 2024-07-18 |  | 112302 | 105648 | 83651
27 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2019-01-31 | 2019-03-15 | 2019-03-27 | 18375 | 39878 | 39878
27 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2019-03-27 | 2019-05-17 | 2019-05-17 | 73500 | 110142 | 98295
27 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2019-08-07 | 2020-08-05 |  | 1378125 | 1494486 | 1166228
27 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2019-08-07 | 2020-08-05 |  | 85750 | 244274 | 231268
27 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2019-10-08 | 2020-01-10 | 2020-01-31 | 17800 | 27547 | 27547
27 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2020-02-19 | 2020-07-20 | 2021-10-06 | 80100 | 115376 | 102211
27 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2024-02-05 | 2025-02-03 |  | 1032400 | 923531 | 27263
27 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2024-02-05 | 2025-02-03 |  | 191350 | 45329 | 45329
27 | P.S. 56 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2022-01-06 | 2022-07-01 | 2022-03-02 | 24000 | 10503 | 10503
27 | P.S. 56 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-20 | 2023-03-15 |  | 352000 | 237403 | 162298
27 | P.S. 56 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-20 | 2023-03-15 |  | 143856 | 155086 | 153041
27 | P.S. 60 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | In-Progress | 2024-06-06 | 2024-10-23 |  | 22500 | 22500 | 169
27 | P.S. 60 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-04-16 | 2024-08-30 |  | 30000 | 58335 | 11631
27 | P.S. 60 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-09-19 | 2025-01-27 |  | 6703 | 1362 | 1362
27 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2023-06-22 | 2023-11-07 | 2023-11-03 | 110505 | 192691 | 166878
27 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-11-15 | 2024-04-18 | 2024-05-07 | 547485 | 397209 | 266525
27 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2024-09-12 | 2026-09-01 |  | 11882344 | 10897843 | 156191
27 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2024-09-12 | 2026-09-01 |  | 811344 | 132274 | 42485
27 | P.S. 62 - QUEENS | SCA CIP RESOA | FY20 RESO A COMPUTER LAB | Design | Complete | 2022-02-10 | 2022-08-01 | 2022-08-10 | 72000 | 74678 | 58807
27 | P.S. 62 - QUEENS | SCA CIP RESOA | FY20 RESO A COMPUTER LAB | Construction | In-Progress | 2023-03-13 | 2024-01-06 |  | 1056000 | 504125 | 434780
27 | P.S. 62 - QUEENS | SCA CIP RESOA | FY20 RESO A COMPUTER LAB | CM,F&E | In-Progress | 2023-03-13 | 2024-01-06 |  | 154109 | 154237 | 130745
27 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | Scope | Complete | 2019-08-22 | 2020-01-28 | 2020-02-24 | 19870 | 59530 | 59530
27 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | Design | Complete | 2021-02-16 | 2021-07-16 | 2022-02-22 | 99350 | 353007 | 294848
27 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | Construction | In-Progress | 2022-08-05 | 2023-08-04 |  | 2235375 | 2041766 | 1500390
27 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | CM,F&E | In-Progress | 2022-08-05 | 2023-08-04 |  | 139090 | 160701 | 141701
27 | P.S. 63 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS | Scope | In-Progress | 2024-06-10 | 2024-10-25 |  | 106706 | 144107 | 113159
27 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | Scope | Complete | 2017-06-13 | 2017-10-13 | 2017-09-25 | 27870 | 25449 | 25449
27 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | Design | Complete | 2018-02-21 | 2018-07-23 | 2018-05-18 | 102190 | 146069 | 145944
27 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | Construction | In-Progress | 2018-07-23 | 2019-07-22 |  | 1082285 | 951320 | 890731
27 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2018-07-23 | 2019-07-22 |  | 250830 | 142643 | 142518
27 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Scope | Complete | 2020-01-13 | 2020-04-13 | 2021-09-24 | 83050 | 91254 | 91254
27 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Design | Complete | 2021-09-29 | 2022-04-06 | 2023-05-10 | 415250 | 438755 | 349553
27 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Construction | In-Progress | 2023-09-12 | 2024-12-04 |  | 9343125 | 9213780 | 3903831
27 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | CM,F&E | In-Progress | 2023-09-12 | 2024-12-04 |  | 581350 | 247218 | 154737
27 | P.S. 90 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | In-Progress | 2024-06-21 | 2024-11-06 |  | 184640 | 190735 | 22411
27 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | Scope | Complete | 2020-01-27 | 2021-03-01 | 2021-03-09 | 1142001 | 765038 | 673538
27 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | Design | Complete | 2021-03-10 | 2021-08-26 | 2022-05-11 | 5138999 | 2766588 | 1817462
27 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | Construction | Complete | 2022-07-25 | 2024-09-03 | 2024-09-05 | 64808500 | 71805710 | 37099513
27 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | CM,Art,F&E | Complete | 2022-07-25 | 2024-09-03 | 2024-09-05 | 9136001 | 7127195 | 4519014
27 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2020-10-27 | 2020-10-27 | 2020-10-27 | 15255 | 19371 | 19371
27 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2020-12-18 | 2021-05-28 | 2022-01-20 | 68649 | 31719 | 31719
27 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2020-10-27 | 2020-10-27 | 2020-10-27 | 29810 | 65191 | 65191
27 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2020-10-28 | 2021-02-01 | 2021-02-02 | 149050 | 356566 | 323659
27 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 2021-05-24 | 2021-10-20 |  | 3353625 | 3316300 | 2875856
27 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2021-05-24 | 2021-10-20 |  | 208670 | 216551 | 203047
27 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | Scope | Complete | 2020-01-29 | 2020-06-12 | 2021-11-19 | 94746 | 147366 | 129997
27 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | Design | Complete | 2021-12-01 | 2022-05-04 | 2022-05-13 | 464365 | 444799 | 411971
27 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | Construction | In-Progress | 2022-07-12 | 2024-04-01 |  | 9638032 | 8731493 | 6226196
27 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | CM,F&E | In-Progress | 2022-07-12 | 2024-04-01 |  | 734207 | 744796 | 715516
27 | P.S. 97 - QUEENS | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 2022-01-05 | 2022-05-04 | 2022-03-28 | 55500 | 82134 | 80424
27 | P.S. 97 - QUEENS | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | Complete | 2023-02-27 | 2024-01-22 | 2024-01-22 | 814000 | 628659 | 568582
27 | P.S. 97 - QUEENS | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | Complete | 2023-02-27 | 2024-01-22 | 2024-01-22 | 172531 | 180144 | 165651
27 | P.S. 100 - QUEENS | SCA CIP | ROOFS / EMERGENCY GENERATOR / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 2023-06-07 | 2023-12-06 | 2023-10-06 | 162840 | 272979 | 246515
27 | P.S. 100 - QUEENS | SCA CIP | ROOFS / EMERGENCY GENERATOR / EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 2023-11-03 | 2024-06-28 | 2024-04-19 | 804579 | 472745 | 461724
27 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | Scope | Complete | 2019-05-22 | 2019-08-21 | 2019-08-13 | 13950 | 31091 | 31091
27 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | Design | Complete | 2019-08-27 | 2020-01-15 | 2020-03-31 | 62775 | 81374 | 74898
27 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | Construction | In-Progress | 2021-06-09 | 2022-06-08 |  | 809100 | 842946 | 668138
27 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | CM,F&E | In-Progress | 2021-06-09 | 2022-06-08 |  | 149963 | 97706 | 72339
27 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2022-07-08 | 2022-11-23 | 2023-04-11 | 44850 | 69697 | 32433
27 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2023-12-01 | 2024-05-03 | 2024-05-08 | 224250 | 326553 | 12055
27 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2024-07-29 | 2026-04-19 |  | 5045625 | 4655666 | 27307
27 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-07-29 | 2026-04-19 |  | 313950 | 116607 | 77243
27 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 2022-06-10 | 2022-09-09 | 2022-09-14 | 14880 | 3551 | 3551
27 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 2022-09-14 | 2023-02-17 | 2023-02-15 | 66960 | 14206 | 14206
27 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Construction | In-Progress | 2023-09-18 | 2024-08-12 |  | 863034 | 766133 | 250967
27 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-09-18 | 2024-08-12 |  | 159959 | 108471 | 38638
27 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-09-07 | 2023-01-10 | 2022-11-15 | 4575 | 5553 | 5553
27 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-11-15 | 2023-05-12 | 2023-03-08 | 20588 | 22212 | 22212
27 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-10 | 2024-05-04 |  | 265350 | 236740 | 204557
27 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-10 | 2024-05-04 |  | 156764 | 159235 | 113161
27 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | Scope | Complete | 2015-07-20 | 2016-01-21 | 2015-10-21 | 16230 | 58517 | 58517
27 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | Design | Complete | 2015-11-10 | 2016-05-13 | 2016-05-10 | 64920 | 171005 | 169001
27 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2016-11-18 | 2017-11-17 |  | 1217250 | 1165402 | 1054042
27 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2016-11-18 | 2017-11-17 |  | 75740 | 418968 | 416964
27 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2021-06-03 | 2021-12-02 | 2021-10-28 | 239100 | 197674 | 197674
27 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2021-11-24 | 2022-06-30 | 2022-04-25 | 1195500 | 343750 | 343750
27 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2024-02-22 | 2026-02-20 |  | 26898750 | 24337707 | 98257
27 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2024-02-22 | 2026-02-20 |  | 1673700 | 51358 | 51358
27 | P.S. 123 - QUEENS | SCA CIP RESOA | FY19 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2019-12-03 | 2020-04-03 | 2021-04-02 | 37599 | 97472 | 97366
27 | P.S. 123 - QUEENS | SCA CIP RESOA | FY19 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 2021-06-16 | 2022-03-12 |  | 551452 | 434977 | 387452
27 | P.S. 123 - QUEENS | SCA CIP RESOA | FY19 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2021-06-16 | 2022-03-12 |  | 91275 | 108211 | 83693
27 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2016-10-17 | 2017-03-22 | 2016-11-22 | 81210 | 126281 | 126281
27 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2016-12-07 | 2017-05-10 | 2017-05-11 | 324840 | 716031 | 664794
27 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2018-05-21 | 2019-08-13 |  | 6090750 | 6799857 | 5671667
27 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2018-05-21 | 2019-08-13 |  | 378980 | 1065415 | 1015507
27 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Scope | Complete | 2019-05-28 | 2019-09-30 | 2019-11-21 | 82346 | 49659 | 49659
27 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Design | Complete | 2020-01-08 | 2020-06-15 | 2022-09-30 | 403783 | 335819 | 272631
27 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Construction | In-Progress | 2023-08-14 | 2025-02-03 |  | 8397811 | 7799469 | 746070
27 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | CM,F&E | In-Progress | 2023-08-14 | 2025-02-03 |  | 636015 | 190592 | 117108
27 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 2022-03-11 | 2022-07-11 | 2022-03-11 | 3800 | 5517 | 5517
27 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | Design | Complete | 2022-03-16 | 2022-09-08 | 2022-07-18 | 17100 | 22067 | 22067
27 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2023-02-27 | 2023-12-23 |  | 220400 | 195559 | 130103
27 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2023-02-27 | 2023-12-23 |  | 167436 | 162251 | 104036
27 | P.S. 124 - QUEENS | SCA CIP RESOA | FY21 RESO A ATHLETIC FIELDS | Design | Complete | 2022-03-16 | 2022-09-06 | 2023-03-31 | 184726 | 79477 | 71146
27 | P.S. 124 - QUEENS | SCA CIP RESOA | FY21 RESO A ATHLETIC FIELDS | Construction | In-Progress | 2023-10-23 | 2025-01-14 |  | 2709321 | 2561719 | 1568947
27 | P.S. 124 - QUEENS | SCA CIP RESOA | FY21 RESO A ATHLETIC FIELDS | CM,F&E | In-Progress | 2023-10-23 | 2025-01-14 |  | 184726 | 142825 | 92046
27 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 2020-05-01 | 2021-01-29 | 2020-12-23 | 22184 | 28065 | 28065
27 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2021-05-19 | 2022-02-12 | 2023-12-05 | 325359 | 341938 | 290898
27 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 2021-05-19 | 2022-02-12 | 2023-12-05 | 22184 | 38586 | 37908
27 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A GYMNASIUM UPGRADE | Design | Complete | 2022-09-06 | 2023-01-25 | 2023-03-08 | 32076 | 41455 | 40844
27 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2023-09-05 | 2024-06-30 |  | 470455 | 432544 | 201150
27 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A GYMNASIUM UPGRADE | CM,F&E | In-Progress | 2023-09-05 | 2024-06-30 |  | 32076 | 52700 | 31292
27 | P.S. 146 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2023-10-04 | 2024-02-23 | 2024-09-05 | 17815 | 83009 | 57194
27 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-11-22 | 2023-03-27 | 2023-01-06 | 4425 | 1533 | 1533
27 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-06 | 2023-07-05 | 2023-03-08 | 19913 | 6133 | 6133
27 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-10 | 2024-05-04 |  | 256650 | 236229 | 206139
27 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-10 | 2024-05-04 |  | 175570 | 166273 | 120392
27 | P.S. 146 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-08-06 | 2024-12-23 |  | 42000 | 14393 | 7898
27 | P.S. 146 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-07-09 | 2024-11-08 |  | 2532 | 2355 | 2355
27 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2018-10-30 | 2019-03-20 | 2019-04-01 | 144558 | 109736 | 109206
27 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2019-04-01 | 2019-08-29 | 2019-05-17 | 576841 | 606067 | 553413
27 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2021-06-14 | 2022-12-05 |  | 10690817 | 10045460 | 9133512
27 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-06-14 | 2022-12-05 |  | 692703 | 634105 | 574637
27 | P.S. 155 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-05-03 | 2024-09-19 |  | 45000 | 46143 | 2706
27 | P.S. 155 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-05-03 | 2024-09-03 |  | 6913 | 782 | 782
27 | P.S. 155 - QUEENS | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2024-07-18 |  | 2024-09-20 | 80000 | 80000 | 75848
27 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-05-10 | 2021-09-23 | 2022-01-21 | 70940 | 88041 | 88041
27 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2022-01-26 | 2022-06-27 | 2022-09-13 | 354701 | 386145 | 342930
27 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2023-07-17 | 2025-04-06 |  | 7980750 | 7360006 | 1438661
27 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-07-17 | 2025-04-06 |  | 496580 | 246250 | 151756
27 | P.S. 183 - QUEENS | SCA CIP RESOA | FY19 RESO A PLAYGROUND / PATH OF TRAVEL RESO A PLAYGROUND | Design | Complete | 2019-09-18 | 2019-11-15 | 2019-09-20 | 76620 | 138194 | 102608
27 | P.S. 183 - QUEENS | SCA CIP RESOA | FY19 RESO A PLAYGROUND / PATH OF TRAVEL RESO A PLAYGROUND | Construction | In-Progress | 2021-05-17 | 2022-05-16 |  | 1123763 | 1210806 | 941852
27 | P.S. 183 - QUEENS | SCA CIP RESOA | FY19 RESO A PLAYGROUND / PATH OF TRAVEL RESO A PLAYGROUND | CM,F&E | In-Progress | 2021-05-17 | 2022-05-16 |  | 76620 | 258533 | 240839
27 | P.S. 197 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE / FY21 RESO A PLAYGROUND UPGRADE / RETAINING WALL | Design | Complete | 2022-02-07 | 2022-06-07 | 2022-04-14 | 44818 | 52381 | 41220
27 | P.S. 197 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE / FY21 RESO A PLAYGROUND UPGRADE / RETAINING WALL | Construction | In-Progress | 2022-06-20 | 2023-03-16 |  | 657333 | 494404 | 365342
27 | P.S. 197 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE / FY21 RESO A PLAYGROUND UPGRADE / RETAINING WALL | CM,F&E | In-Progress | 2022-06-20 | 2023-03-16 |  | 44818 | 72427 | 66285
27 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2019-07-03 | 2019-11-19 | 2020-01-13 | 85659 | 126169 | 126169
27 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2020-01-13 | 2020-06-12 | 2021-04-23 | 425946 | 498752 | 404146
27 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 2021-07-22 | 2023-04-12 |  | 9380598 | 9672876 | 3015641
27 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 2021-07-22 | 2023-04-12 |  | 617231 | 985363 | 949215
27 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-01 | 2023-04-04 | 2023-01-04 | 4080 | 1163 | 1163
27 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-04 | 2023-06-30 | 2023-03-15 | 18360 | 4650 | 4650
27 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-10 | 2024-05-04 |  | 236640 | 210378 | 123040
27 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-10 | 2024-05-04 |  | 168996 | 163763 | 115209
27 | I.S. 202 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY / SIDEWALK REPAIR / WINDOWS | Scope | Complete | 2022-03-15 | 2022-09-13 | 2022-07-22 | 213666 | 204330 | 201540
27 | I.S. 202 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY / SIDEWALK REPAIR / WINDOWS | Design | Complete | 2022-07-28 | 2023-01-26 | 2023-01-12 | 1057363 | 373260 | 372698
27 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2020-08-13 | 2021-01-19 | 2020-12-28 | 82125 | 70485 | 70485
27 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2020-12-31 | 2021-07-30 | 2021-07-06 | 410625 | 292732 | 267814
27 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-06-22 | 2024-06-20 |  | 9239062 | 8542745 | 5759296
27 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-06-22 | 2024-06-20 |  | 574875 | 296033 | 265569
27 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-23 | 2023-10-23 | 2023-09-25 | 14789 | 15828 | 15828
27 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-02 | 2024-03-01 | 2024-02-07 | 66551 | 69219 | 52153
27 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-07-22 | 2025-05-16 |  | 857762 | 784636 | 7428
27 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-07-22 | 2025-05-16 |  | 158982 | 108282 | 13533
27 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | In-Progress | 2024-07-31 | 2024-12-17 |  | 90000 | 76992 | 921
27 | P.S. 207 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2023-07-11 | 2023-11-27 | 2023-11-08 | 37896 | 81772 | 73194
27 | P.S. 207 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2023-11-15 | 2024-04-18 | 2024-05-14 | 188387 | 198182 | 175977
27 | P.S. 207 - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2023-07-05 | 2023-11-06 | 2023-09-26 | 45000 | 62721 | 56457
27 | P.S. 207 - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 2024-02-20 | 2024-12-15 |  | 660000 | 514867 | 128002
27 | P.S. 207 - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2024-02-20 | 2024-12-15 |  | 45000 | 55519 | 34117
27 | P.S. 362 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-10 | 2024-11-07 | 2024-07-16 | 4615 | 777 | 777
27 | P.S. 362 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-16 | 2025-01-13 |  | 20768 | 20768 | 3109
27 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2022-07-08 | 2022-11-23 | 2023-12-04 | 113791 | 253376 | 248313
27 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2023-12-08 | 2024-05-10 | 2024-04-29 | 568955 | 400064 | 355660
27 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2024-09-30 | 2026-09-19 |  | 12801488 | 11438722 | 40103
27 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2024-09-30 | 2026-09-19 |  | 796538 | 58780 | 57069
27 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-05-24 | 2023-09-25 | 2023-05-25 | 3454 | 251 | 251
27 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-05-25 | 2023-11-22 | 2023-09-20 | 15543 | 1006 | 1006
27 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-01-08 | 2024-11-02 |  | 200331 | 183313 | 72153
27 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-01-08 | 2024-11-02 |  | 101409 | 95540 | 55825
27 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | Scope | Complete | 2019-02-14 | 2019-05-31 | 2022-03-14 | 36801 | 43438 | 43438
27 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | Design | Complete | 2022-03-14 | 2022-09-13 | 2022-05-11 | 184005 | 190368 | 176694
27 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | Construction | In-Progress | 2022-08-10 | 2023-11-02 |  | 4140113 | 3955266 | 3758424
27 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | CM,F&E | In-Progress | 2022-08-10 | 2023-11-02 |  | 492290 | 700800 | 669213
27 | I.S. 226 - QUEENS | SCA CIP | RTU REPLACEMENT / ROOFS | Scope | Complete | 2021-09-22 | 2022-01-31 | 2022-05-10 | 72216 | 55373 | 55373
27 | I.S. 226 - QUEENS | SCA CIP | RTU REPLACEMENT / ROOFS | Design | Complete | 2022-06-27 | 2022-11-29 | 2023-04-13 | 357504 | 227797 | 187644
27 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | Scope | Complete | 2018-04-10 | 2018-08-23 | 2018-08-21 | 243681 | 219947 | 216136
27 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | Design | Complete | 2018-09-19 | 2019-02-25 | 2019-05-07 | 967549 | 755815 | 655486
27 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | Construction | In-Progress | 2019-08-05 | 2021-08-03 |  | 17497696 | 16645442 | 15000326
27 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | CM,F&E | In-Progress | 2019-08-05 | 2021-08-03 |  | 1230438 | 1966910 | 1936708
27 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-21 | 2023-04-24 | 2023-01-06 | 5000 | 901 | 901
27 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-06 | 2023-07-05 | 2023-03-15 | 22500 | 3606 | 3606
27 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-10 | 2024-05-04 |  | 290000 | 252346 | 141044
27 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-10 | 2024-05-04 |  | 186668 | 167328 | 118652
27 | P.S. 254 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-07-05 | 2024-11-04 | 2024-07-16 | 4124 | 562 | 562
27 | P.S. 254 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-07-16 | 2025-01-13 |  | 18559 | 18559 | 2248
27 | P.S. 306 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS / FIRE ALARM PANEL | Scope | Complete | 2023-10-12 | 2024-03-12 | 2024-03-01 | 128835 | 282882 | 14954
27 | P.S. 306 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS / FIRE ALARM PANEL | Design | Complete | 2024-03-01 | 2024-10-01 | 2024-05-07 | 638381 | 393964 | 39960
27 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 2022-04-01 | 2022-08-01 | 2022-05-03 | 2480 | 1463 | 1463
27 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 2022-05-03 | 2022-10-27 | 2022-07-18 | 11160 | 5852 | 5852
27 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 2023-02-27 | 2023-12-23 |  | 143840 | 126869 | 2868
27 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 2023-02-27 | 2023-12-23 |  | 128778 | 127268 | 93026
27 | P.S. 273 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | Complete | 2023-10-18 | 2024-03-18 | 2024-03-04 | 64756 | 150639 | 119606
27 | P.S. 273 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | Complete | 2024-03-04 | 2024-08-02 | 2024-05-14 | 323780 | 569922 | 36226
27 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | Scope | Complete | 2020-05-22 | 2022-11-14 | 2022-11-09 | 439294 | 1046675 | 1030855
27 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | Design | Complete | 2022-11-18 | 2023-05-18 | 2023-04-25 | 2193674 | 2450939 | 2347543
27 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | Construction | In-Progress | 2024-02-05 | 2027-01-19 |  | 49116028 | 44632554 | 3148199
27 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | CM,F&E | In-Progress | 2024-02-05 | 2027-01-19 |  | 3096007 | 329648 | 321868
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | SEA WALL / BULKHEAD REPAIR | Scope | Complete | 2019-04-16 | 2019-07-16 | 2019-10-10 | 166282 | 176449 | 174871
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | SEA WALL / BULKHEAD REPAIR | Design | In-Progress | 2019-11-20 | 2020-04-08 |  | 775983 | 779102 | 441204
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-04-11 | 2022-08-24 | 2023-03-15 | 39968 | 96792 | 77384
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2023-03-16 | 2023-08-16 | 2023-05-12 | 199839 | 227987 | 208210
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 2023-08-07 | 2025-01-17 |  | 4496384 | 4107021 | 712616
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-08-07 | 2025-01-17 |  | 279775 | 155886 | 99535
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP RESOA | FY20 RESO A WEIGHT ROOM | Design | Complete | 2023-09-19 | 2024-02-07 | 2024-04-09 | 156382 | 96027 | 92399
27 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 210 | 210
27 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2004-12-01 | 2005-05-15 | 2005-04-18 | 2600 | 6281 | 6281
27 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2006-09-07 | 2007-04-15 |  | 77000 | 81513 | 81342
27 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2006-09-07 | 2007-04-15 |  | 12240 | 20175 | 20175
27 | ROCKAWAY PARK HS FOR ENVIRONMENTAL SUST - Q | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LAB | F&E | In-Progress | 2024-04-30 |  |  | 50000 | 50000 | 0
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | Scope | Complete | 2019-06-18 | 2019-10-18 | 2019-09-13 | 43620 | 82381 | 82381
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | Design | Complete | 2019-11-04 | 2020-04-08 | 2021-11-04 | 218100 | 557678 | 501004
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | Construction | In-Progress | 2022-02-28 | 2023-08-21 |  | 4907250 | 5166538 | 4498109
27 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | CM,F&E | In-Progress | 2022-02-28 | 2023-08-21 |  | 305340 | 905293 | 896157
27 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | Scope | Complete | 2021-05-21 | 2021-08-20 | 2021-07-20 | 25550 | 127063 | 107450
27 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | Design | Complete | 2021-08-04 | 2021-12-21 | 2021-11-22 | 127750 | 208414 | 192727
27 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | Construction | In-Progress | 2022-07-29 | 2024-01-19 |  | 2874375 | 3082614 | 2491810
27 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | CM,F&E | In-Progress | 2022-07-29 | 2024-01-19 |  | 178850 | 169738 | 166278
27 | M.S. 282 - QUEENS | SCA CIP | SWIMMING POOL / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2021-03-05 | 2024-04-11 | 2024-05-08 | 83498 | 99922 | 99922
27 | M.S. 282 - QUEENS | SCA CIP | SWIMMING POOL / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2024-05-08 | 2024-10-09 | 2024-05-15 | 417490 | 296271 | 273816
27 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Design | Complete | 2023-11-07 | 2024-04-11 | 2024-04-24 | 30000 | 16772 | 16772
27 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | RESO A RECORDING STUDIO | Scope | In-Progress | 2023-06-29 | 2023-10-30 |  | 67956 | 67956 | 16181
27 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-08-23 | 2025-01-29 |  | 44426 | 19511 | 11818
27 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 2024-07-16 | 2024-10-15 | 2024-08-23 | 6341 | 6341 | 0
27 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-08-30 | 2024-12-30 |  | 574 | 574 | 0
27 | M.S. 282 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM CONVERSION / FY20 RESO A ROBOTICS LAB | Design | Complete | 2022-03-16 | 2022-08-15 | 2023-04-04 | 187765 | 141899 | 128465
27 | M.S. 282 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM CONVERSION / FY20 RESO A ROBOTICS LAB | Construction | In-Progress | 2023-11-24 | 2024-10-18 |  | 2753887 | 2853133 | 521947
27 | M.S. 282 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM CONVERSION / FY20 RESO A ROBOTICS LAB | CM,F&E | In-Progress | 2023-11-24 | 2024-10-18 |  | 204727 | 131120 | 71650
27 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | Scope | Complete | 2019-11-01 | 2022-04-26 | 2022-04-26 | 244246 | 217526 | 216718
27 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | Design | Complete | 2022-04-27 | 2022-07-27 | 2022-05-06 | 1216979 | 1400629 | 1241122
27 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | Construction | In-Progress | 2022-07-11 | 2024-07-09 |  | 27014556 | 24775046 | 13026636
27 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | CM,F&E | In-Progress | 2022-07-11 | 2024-07-09 |  | 1741576 | 770398 | 748071
27 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Design | Complete | 2022-11-18 | 2023-03-23 | 2023-01-13 | 54701 | 145811 | 91707
27 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 2023-07-10 | 2024-05-04 |  | 802285 | 671560 | 214339
27 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2023-07-10 | 2024-05-04 |  | 62063 | 126603 | 71596
27 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 784 | 784
27 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2004-12-01 | 2005-05-15 | 2005-04-18 | 2600 | 62101 | 62101
27 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2005-08-12 | 2006-10-10 |  | 77000 | 152341 | 151607
27 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2005-08-12 | 2006-10-10 |  | 12240 | 26218 | 26218
27 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 2021-03-03 | 2021-06-02 | 2021-06-03 | 8740 | 18719 | 18719
27 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | Complete | 2021-06-14 | 2021-10-28 | 2021-12-02 | 39330 | 73278 | 61977
27 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2022-04-11 | 2023-01-05 |  | 506920 | 461470 | 374673
27 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2022-04-11 | 2023-01-05 |  | 93955 | 84225 | 83177
27 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 205 | 205
27 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2004-12-01 | 2005-05-15 | 2005-04-18 | 2600 | 25502 | 25502
27 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2007-07-15 | 2008-05-30 |  | 77000 | 148429 | 148276
27 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2007-07-15 | 2008-05-30 |  | 12240 | 47259 | 47259
27 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | Scope | Complete | 2022-06-09 | 2022-10-19 | 2022-10-19 | 234660 | 227032 | 227032
27 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | Design | Complete | 2022-10-19 | 2023-03-23 | 2023-04-10 | 1055970 | 577324 | 429248
27 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | Construction | In-Progress | 2023-07-12 | 2025-09-03 |  | 13316955 | 12188450 | 5075060
27 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | CM,F&E | In-Progress | 2023-07-12 | 2025-09-03 |  | 1877280 | 1077207 | 184583
27 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2024-01-23 | 2024-06-26 | 2024-06-26 | 1824024 | 1436643 | 1308022
27 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | In-Progress | 2024-06-27 | 2025-02-24 |  | 7296095 | 7296095 | 110528
27 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2024-03-26 | 2024-03-26 | 2024-03-26 | 56496 | 5253 | 5253
27 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Design | In-Progress | 2024-03-27 | 2024-06-26 |  | 263647 | 263647 | 214684
27 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2024-05-16 | 2024-05-16 | 2024-05-16 | 43889 | 1069 | 1069
27 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Design | In-Progress | 2024-05-17 | 2024-08-30 |  | 204817 | 204817 | 4276
27 | P.S. 47 - QUEENS | SCA CIP | PATH OF TRAVEL | Scope | Complete | 2024-01-03 | 2024-04-04 | 2024-03-20 | 2918 | 20436 | 284
27 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP | ROOFS / WINDOWS / PARAPETS | Scope | Complete | 2023-12-21 | 2024-05-08 | 2024-09-03 | 55627 | 72264 | 72264
27 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP | ROOFS / WINDOWS / PARAPETS | Design | In-Progress | 2024-09-17 | 2025-02-21 |  | 259937 | 259937 | 6892
27 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 2019-06-06 | 2019-11-06 | 2020-05-15 | 41805 | 78714 | 78714
27 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2022-02-08 | 2022-11-04 |  | 613140 | 478780 | 421400
27 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2022-02-08 | 2022-11-04 |  | 41805 | 58332 | 56812
27 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-06-24 | 2020-10-23 | 2020-09-23 | 2400 | 3740 | 3740
27 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-09-23 | 2021-03-19 | 2021-05-05 | 10800 | 14959 | 14959
27 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-20 | 2023-03-15 |  | 139200 | 127893 | 111187
27 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-20 | 2023-03-15 |  | 113026 | 116472 | 114531
27 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | Scope | Complete | 2018-05-08 | 2018-08-07 | 2018-05-08 | 109140 | 2097 | 2097
27 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | Design | Complete | 2018-05-09 | 2018-09-24 | 2018-05-09 | 436558 | 88718 | 69557
27 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2021-08-16 | 2023-02-06 |  | 8185466 | 7479874 | 6553991
27 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2021-08-16 | 2023-02-06 |  | 509318 | 225366 | 195112
28 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2020-02-14 | 2020-06-30 | 2021-03-09 | 50630 | 79856 | 79856
28 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2021-04-06 | 2021-09-03 | 2021-10-21 | 253151 | 496159 | 454754
28 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2022-04-14 | 2023-10-05 |  | 5695875 | 5072651 | 4920933
28 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-04-14 | 2023-10-05 |  | 354411 | 768386 | 754382
28 | J.H.S. 8 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-06-22 | 2023-11-07 | 2023-12-05 | 135084 | 235214 | 235214
28 | J.H.S. 8 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 2024-01-02 | 2024-06-03 |  | 666336 | 666336 | 206017
28 | J.H.S. 8 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM / ELECTRICAL UPGRADE | Scope | Complete | 2023-10-05 | 2024-03-05 | 2024-04-08 | 376066 | 12391 | 12391
28 | J.H.S. 8 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM / ELECTRICAL UPGRADE | Design | In-Progress | 2024-05-23 | 2024-12-19 |  | 1844786 | 1844786 | 49560
28 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 2024-07-08 | 2024-12-09 |  | 30000 | 35374 | 5037
28 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | Scope | Complete | 2022-06-22 | 2022-11-07 | 2023-02-02 | 136780 | 127665 | 127665
28 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | Design | Complete | 2023-02-08 | 2023-07-12 | 2023-05-04 | 683900 | 424448 | 359025
28 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | Construction | In-Progress | 2024-08-26 | 2026-08-25 |  | 15387750 | 14239600 | 242219
28 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | CM,F&E | In-Progress | 2024-08-26 | 2026-08-25 |  | 957460 | 86416 | 35628
28 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | Scope | Complete | 2020-08-07 | 2020-12-07 | 2021-03-22 | 19800 | 46153 | 46153
28 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | Design | Complete | 2021-03-31 | 2021-09-07 | 2021-12-22 | 99000 | 287970 | 287970
28 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | Construction | In-Progress | 2022-07-25 | 2024-01-15 |  | 2227500 | 2991810 | 2567736
28 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | CM,F&E | In-Progress | 2022-07-25 | 2024-01-15 |  | 138600 | 587775 | 585670
28 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-04-23 | 2024-09-24 |  | 89156 | 68139 | 36855
28 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 2024-04-23 | 2024-09-24 |  | 30000 | 43478 | 25464
28 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 2024-05-28 | 2024-08-28 | 2024-08-20 | 14475 | 14475 | 14475
28 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | In-Progress | 2024-08-22 | 2024-12-27 |  | 1635 | 1635 | 1635
28 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 2024-05-28 | 2024-08-28 | 2024-07-10 | 201 | 201 | 201
28 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | Scope | Complete | 2019-05-23 | 2020-08-13 | 2021-12-16 | 101108 | 159737 | 159737
28 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | Design | Complete | 2021-12-20 | 2022-05-23 | 2022-05-09 | 487192 | 556614 | 480244
28 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | Construction | In-Progress | 2022-08-15 | 2024-08-13 |  | 9374718 | 8648174 | 7884296
28 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2022-08-15 | 2024-08-13 |  | 845365 | 547791 | 519782
28 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 2022-08-24 | 2023-01-30 | 2023-01-04 | 32983 | 65826 | 55213
28 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2023-05-15 | 2024-04-08 | 2023-12-14 | 483756 | 449042 | 365306
28 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 2023-05-15 | 2024-04-08 | 2023-12-14 | 58174 | 87395 | 52276
28 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2022-11-02 | 2023-03-02 | 2023-03-21 | 76748 | 104339 | 92400
28 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 2023-09-25 | 2024-08-19 |  | 1125646 | 592022 | 199300
28 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2023-09-25 | 2024-08-19 |  | 76748 | 85080 | 71361
28 | P.S. 80 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Design | Complete | 2024-02-09 | 2024-06-12 | 2024-04-18 | 49697 | 62378 | 40845
28 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 2021-09-13 | 2021-12-14 | 2021-12-13 | 13460 | 49326 | 49326
28 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | Design | Complete | 2021-12-14 | 2022-05-02 | 2022-05-11 | 60570 | 78676 | 77158
28 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | Construction | In-Progress | 2023-01-03 | 2024-01-02 |  | 780680 | 707318 | 537070
28 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-01-03 | 2024-01-02 |  | 144695 | 106044 | 104678
28 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | Scope | Complete | 2021-09-22 | 2023-03-02 | 2023-03-15 | 30769 | 88294 | 78453
28 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | Design | Complete | 2023-03-16 | 2023-07-19 | 2023-03-16 | 143615 | 167054 | 48144
28 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | Construction | In-Progress | 2023-06-12 | 2024-09-03 |  | 2346552 | 2143734 | 1818355
28 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-06-12 | 2024-09-03 |  | 292100 | 188130 | 160163
28 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 2021-03-11 | 2021-07-26 | 2021-11-22 | 45500 | 67886 | 66928
28 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | Design | Complete | 2021-12-01 | 2022-05-04 | 2022-04-27 | 227500 | 194915 | 194915
28 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | Construction | In-Progress | 2022-08-22 | 2024-02-12 |  | 5118751 | 4673412 | 4234506
28 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | CM,F&E | In-Progress | 2022-08-22 | 2024-02-12 |  | 318500 | 311029 | 272255
28 | P.S. 117 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-12-22 | 2022-03-14 | 2022-04-12 | 72000 | 111817 | 111817
28 | P.S. 117 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2022-06-20 | 2023-06-19 |  | 1056000 | 815714 | 593327
28 | P.S. 117 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2022-06-20 | 2023-06-19 |  | 72000 | 118522 | 116396
28 | P.S. 139 - QUEENS | SCA CIP | IPDVS | Scope | Complete | 2022-01-06 | 2022-05-06 | 2022-01-20 | 6000 | 6853 | 6853
28 | P.S. 139 - QUEENS | SCA CIP | IPDVS | Design | Complete | 2022-01-21 | 2022-07-18 | 2022-07-18 | 27000 | 27411 | 27411
28 | P.S. 139 - QUEENS | SCA CIP | IPDVS | Construction | In-Progress | 2023-02-27 | 2023-12-23 |  | 348000 | 254457 | 180659
28 | P.S. 139 - QUEENS | SCA CIP | IPDVS | CM,F&E | In-Progress | 2023-02-27 | 2023-12-23 |  | 140877 | 162352 | 160869
28 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | Scope | Complete | 2021-03-30 | 2022-04-12 | 2022-08-08 | 64360 | 121592 | 121592
28 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | Design | Complete | 2022-09-22 | 2023-02-28 | 2023-04-27 | 321800 | 407040 | 283924
28 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | Construction | In-Progress | 2023-10-03 | 2025-04-01 |  | 7240500 | 6673426 | 448157
28 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | CM,F&E | In-Progress | 2023-10-03 | 2025-04-01 |  | 450520 | 227141 | 158547
28 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 2021-05-21 | 2021-10-06 | 2022-01-21 | 52876 | 103998 | 103998
28 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 2022-01-21 | 2022-06-22 | 2022-05-11 | 261507 | 418845 | 409146
28 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 2022-09-12 | 2024-06-02 |  | 5635639 | 5326721 | 4906623
28 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 2022-09-12 | 2024-06-02 |  | 392417 | 158033 | 151592
28 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-05-29 | 2020-09-28 | 2020-07-21 | 3616 | 9403 | 9403
28 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-21 | 2021-01-15 | 2021-06-02 | 16272 | 37612 | 37612
28 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-20 | 2023-03-15 |  | 209728 | 193811 | 164696
28 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-20 | 2023-03-15 |  | 202120 | 206997 | 205795
28 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 336 | 336
28 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2004-12-01 | 2005-05-15 | 2005-04-18 | 2600 | 29037 | 29037
28 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2006-09-06 | 2006-10-10 |  | 77000 | 21743 | 19743
28 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2006-09-06 | 2006-10-10 |  | 12240 | 35302 | 35302
28 | P.S. 144 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2019-06-19 | 2019-11-04 | 2019-12-13 | 97441 | 105724 | 105398
28 | P.S. 144 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2019-12-13 | 2020-04-15 | 2020-07-30 | 487200 | 479613 | 417498
28 | P.S. 144 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | Complete | 2021-08-16 | 2023-08-15 | 2024-02-12 | 10962001 | 11648984 | 9911160
28 | P.S. 144 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 2021-08-16 | 2023-08-15 | 2024-02-12 | 682081 | 879830 | 815765
28 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | Scope | Complete | 2021-01-12 | 2022-01-28 | 2022-03-21 | 1154320 | 843797 | 812461
28 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | Design | Complete | 2022-03-21 | 2022-08-18 | 2022-04-29 | 5194440 | 3193894 | 2490983
28 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | Construction | In-Progress | 2022-07-25 | 2025-09-03 |  | 65507660 | 60646432 | 47232346
28 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | CM,Art,F&E | In-Progress | 2022-07-25 | 2025-09-03 |  | 9234560 | 7310663 | 3933702
28 | P.S. 160 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA / EXISTING BUILDING-GYMNASIUM | Scope | Complete | 2022-06-14 | 2022-10-28 | 2023-12-18 | 47871 | 48956 | 7460
28 | P.S. 160 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA / EXISTING BUILDING-GYMNASIUM | Design | In-Progress | 2024-01-02 | 2024-06-18 |  | 224983 | 224983 | 29860
28 | P.S. 160 - QUEENS | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | Design | In-Progress | 2023-06-15 | 2023-11-01 |  | 108511 | 84954 | 32374
28 | P.S. 161 - QUEENS | SCA CIP | WINDOWS / PARAPETS | Scope | Complete | 2023-04-26 | 2023-09-12 | 2023-09-20 | 56238 | 81492 | 81492
28 | P.S. 161 - QUEENS | SCA CIP | WINDOWS / PARAPETS | Design | Complete | 2023-10-04 | 2024-03-11 | 2024-04-24 | 279049 | 221355 | 214866
28 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | Scope | Complete | 2020-09-30 | 2022-03-04 | 2022-04-06 | 994026 | 777767 | 748109
28 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | Design | Complete | 2022-04-06 | 2022-05-16 | 2022-04-25 | 4473117 | 2688951 | 1996250
28 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | Construction | Complete | 2022-07-11 | 2024-09-03 | 2024-08-15 | 56410974 | 56134968 | 51304520
28 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | CM,Art,F&E | Complete | 2022-07-11 | 2024-09-03 | 2024-08-15 | 7952208 | 6550712 | 4718993
28 | P.S. 174 - QUEENS | SCA CIP | EXISTING BUILDING-PA/CLOCK SYSTEMS / EXISTING BUILDING-FIRE ALARM SYSTEM / EXISTING BUILDING- INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-GYMNASIUM | Scope | Complete | 2021-10-28 | 2022-03-04 | 2022-06-03 | 46084 | 60855 | 60855
28 | P.S. 174 - QUEENS | SCA CIP | EXISTING BUILDING-PA/CLOCK SYSTEMS / EXISTING BUILDING-FIRE ALARM SYSTEM / EXISTING BUILDING- INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-GYMNASIUM | Design | Complete | 2022-06-22 | 2022-12-09 | 2023-07-17 | 220019 | 203306 | 198725
28 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2020-01-27 | 2020-06-25 | 2020-04-10 | 79690 | 71062 | 71062
28 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2020-04-15 | 2020-09-15 | 2020-07-29 | 398450 | 365819 | 304404
28 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-06-06 | 2024-06-04 |  | 8965125 | 8224527 | 7711750
28 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-06-06 | 2024-06-04 |  | 557830 | 789781 | 761476
28 | J.H.S. 190 - QUEENS | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Design | Complete | 2023-08-24 | 2024-01-12 | 2024-05-30 | 60000 | 64745 | 58640
28 | P.S. 206 - QUEENS | SCA CIP | SSBA - EXISTING SCHOOL RENOVATION WORK | Scope | Complete | 2020-02-19 | 2020-07-17 | 2021-07-27 | 35448 | 47023 | 47023
28 | P.S. 206 - QUEENS | SCA CIP | SSBA - EXISTING SCHOOL RENOVATION WORK | Design | Complete | 2021-08-10 | 2022-01-04 | 2023-07-24 | 177239 | 228874 | 211840
28 | P.S. 206 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-13 | 2022-11-29 | 2023-07-25 | 78905 | 178697 | 177228
28 | P.S. 206 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-08-25 | 2024-01-31 | 2024-04-25 | 394527 | 300729 | 291538
28 | P.S. 206 - QUEENS | SCA CIP | SSBA - DEMOLITION OF TCU UNIT AND PLAYGROUND DEVELOPMENT | Scope | Complete | 2022-12-06 | 2023-03-09 | 2023-05-15 | 27156 | 46122 | 46122
28 | P.S. 206 - QUEENS | SCA CIP | SSBA - DEMOLITION OF TCU UNIT AND PLAYGROUND DEVELOPMENT | Design | Complete | 2023-05-16 | 2023-10-02 | 2024-04-25 | 108623 | 137328 | 66959
28 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-09-12 | 2023-03-10 | 2022-12-22 | 98970 | 156174 | 156174
28 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-01-05 | 2023-07-03 | 2023-04-25 | 494851 | 332473 | 332473
28 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2023-07-13 | 2025-07-01 |  | 11134126 | 10468004 | 4201672
28 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-07-13 | 2025-07-01 |  | 692790 | 425131 | 303645
28 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2020-02-05 | 2020-07-07 | 2020-05-07 | 69332 | 71806 | 71806
28 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2020-05-11 | 2020-12-31 | 2020-08-19 | 338529 | 342679 | 281467
28 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-04-04 | 2024-04-02 |  | 6913462 | 6329034 | 5832350
28 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-04-04 | 2024-04-02 |  | 546318 | 647899 | 629595
28 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2022-01-10 | 2022-05-10 | 2022-05-02 | 54983 | 87100 | 87100
28 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-07-11 | 2023-01-12 | 2023-02-10 | 269594 | 429530 | 327819
28 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2023-10-04 | 2025-01-01 |  | 5605382 | 5177475 | 3177316
28 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2023-10-04 | 2025-01-01 |  | 424812 | 113782 | 60923
28 | P.S. 220 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2023-12-21 | 2024-05-08 | 2024-08-02 | 14019 | 69033 | 32687
28 | P.S. 220 - QUEENS | SCA CIP | EXTERIOR MASONRY | Design | In-Progress | 2024-08-07 | 2025-01-10 |  | 70094 | 70094 | 9188
28 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | Scope | Complete | 2022-01-21 | 2022-03-18 | 2022-03-22 | 88660 | 147222 | 147222
28 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | Design | Complete | 2022-03-23 | 2022-09-09 | 2022-11-16 | 398970 | 602770 | 182922
28 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 2023-08-07 | 2025-09-03 |  | 5031455 | 4903454 | 441772
28 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 2023-08-07 | 2025-09-03 |  | 709280 | 861145 | 184533
28 | 3K CENTER @ 98-05 63 DRIVE - QUEENS | 3K | LEASE | Scope | Complete | 2021-05-03 | 2021-06-22 | 2021-06-24 | 169100 | 239690 | 239690
28 | 3K CENTER @ 98-05 63 DRIVE - QUEENS | 3K | LEASE | Design | Complete | 2021-06-25 | 2021-09-22 | 2022-05-19 | 760950 | 1379767 | 457573
28 | 3K CENTER @ 98-05 63 DRIVE - QUEENS | 3K | LEASE | Construction | Complete | 2022-06-13 | 2023-09-03 | 2023-08-21 | 9596425 | 11235402 | 10291293
28 | 3K CENTER @ 98-05 63 DRIVE - QUEENS | 3K | LEASE | CM,F&E | Complete | 2022-06-13 | 2023-09-03 | 2023-08-21 | 1479529 | 448115 | 1460147
28 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | Scope | Complete | 2021-05-20 | 2021-08-13 | 2021-06-28 | 18770 | 31485 | 31485
28 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | Design | Complete | 2021-08-25 | 2022-01-31 | 2022-02-16 | 93850 | 139005 | 107485
28 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | Construction | In-Progress | 2022-08-08 | 2023-11-05 |  | 2111625 | 1933356 | 1488886
28 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2022-08-08 | 2023-11-05 |  | 131390 | 35954 | 35954
28 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | Scope | Complete | 2021-06-16 | 2021-11-01 | 2021-11-03 | 13700 | 39304 | 39304
28 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | Design | Complete | 2021-12-13 | 2022-05-16 | 2022-04-13 | 61650 | 51130 | 51130
28 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | Construction | In-Progress | 2022-06-20 | 2023-04-15 |  | 794600 | 729037 | 388870
28 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | CM,F&E | In-Progress | 2022-06-20 | 2023-04-15 |  | 147275 | 92996 | 91219
28 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2023-01-05 | 2023-05-31 | 2023-11-03 | 157000 | 171914 | 155579
28 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-11-13 | 2024-04-16 | 2024-05-14 | 785000 | 711386 | 524343
28 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2024-09-20 | 2026-09-19 |  | 17662500 | 16031117 | 51344
28 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2024-09-20 | 2026-09-19 |  | 1099000 | 193589 | 51846
28 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 466 | 466
28 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2004-12-01 | 2005-05-15 | 2005-04-18 | 2600 | 13288 | 13288
28 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2006-05-16 | 2007-05-31 |  | 77000 | 141520 | 141520
28 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2006-05-16 | 2007-05-31 |  | 12240 | 25106 | 25106
28 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2023-07-26 | 2023-12-12 | 2024-02-08 | 25127 | 82761 | 54009
28 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2024-03-01 | 2024-08-01 | 2024-07-18 | 117260 | 55516 | 7227
28 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | Scope | Complete | 2022-02-09 | 2022-11-09 | 2022-09-19 | 35940 | 4997 | 4997
28 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | Design | Complete | 2022-09-20 | 2023-01-20 | 2023-01-05 | 161730 | 179562 | 138716
28 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | Construction | In-Progress | 2024-05-09 | 2025-08-01 |  | 2084520 | 2138479 | 176689
28 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 2024-05-09 | 2025-08-01 |  | 386355 | 81803 | 52065
28 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2021-04-05 | 2021-08-31 | 2021-08-31 | 2215100 | 1293618 | 1245597
28 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 2021-09-01 | 2022-04-05 | 2022-04-28 | 9967950 | 4214195 | 3788006
28 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2022-10-01 | 2026-09-03 |  | 125706925 | 112441827 | 16673113
28 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2022-10-01 | 2026-09-03 |  | 17720800 | 7459352 | 936643
28 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | Scope | Complete | 2018-11-05 | 2019-02-07 | 2020-02-04 | 20970 | 28154 | 28154
28 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | Design | Complete | 2020-02-04 | 2020-08-05 | 2021-04-19 | 104850 | 152690 | 134142
28 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | Construction | In-Progress | 2023-06-05 | 2024-06-03 |  | 2359125 | 2155123 | 8633
28 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | CM,F&E | In-Progress | 2023-06-05 | 2024-06-03 |  | 146790 | 80934 | 66179
28 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | Scope | Complete | 2020-02-25 | 2020-05-22 | 2021-11-24 | 30525 | 52272 | 52272
28 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | Design | Complete | 2021-11-29 | 2022-04-15 | 2022-08-25 | 146797 | 91199 | 91199
28 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | Construction | In-Progress | 2023-02-01 | 2024-03-01 |  | 2799135 | 2627476 | 2274149
28 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | CM,F&E | In-Progress | 2023-02-01 | 2024-03-01 |  | 257352 | 275887 | 254746
28 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-01-25 | 2023-05-25 | 2023-04-11 | 17500 | 18548 | 18548
28 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-04-18 | 2023-10-18 | 2023-08-14 | 78750 | 63027 | 48416
28 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-02-26 | 2025-01-25 |  | 1015000 | 897112 | 5717
28 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-02-26 | 2025-01-25 |  | 188125 | 112646 | 33556
28 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 470 | 470
28 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2004-12-01 | 2005-05-15 | 2005-04-18 | 2600 | 22405 | 22405
28 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2006-06-14 | 2007-05-31 |  | 77000 | 57758 | 57570
28 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2006-06-14 | 2007-05-31 |  | 12240 | 22036 | 22036
28 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Scope | Complete | 2024-01-09 | 2024-04-04 | 2024-07-23 | 111193 | 111193 | 26388
28 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Design | In-Progress | 2024-07-31 | 2025-01-03 |  | 218169 | 218169 | 7047
28 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Design | In-Progress | 2024-09-20 | 2025-01-28 |  | 13637 | 618 | 618
28 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | Scope | Complete | 2022-06-27 | 2022-11-10 | 2022-12-20 | 149285 | 257692 | 247091
28 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | Design | Complete | 2023-01-24 | 2023-06-26 | 2023-05-10 | 742837 | 754202 | 655943
28 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | Construction | In-Progress | 2023-07-17 | 2026-01-01 |  | 16403796 | 14946496 | 6763949
28 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-07-17 | 2026-01-01 |  | 1071872 | 478426 | 323723
28 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-16 | 2023-07-17 | 2023-03-21 | 3581 | 826 | 826
28 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-21 | 2023-09-14 | 2023-05-03 | 16116 | 3304 | 3304
28 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-20 | 2024-11-18 |  | 207714 | 190670 | 5540
28 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-20 | 2024-11-18 |  | 42763 | 21585 | 21585
28 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | Scope | Complete | 2019-12-17 | 2020-04-21 | 2020-03-25 | 12420 | 60529 | 60529
28 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | Design | Complete | 2020-03-25 | 2020-08-14 | 2020-06-30 | 55890 | 225092 | 102104
28 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | Construction | In-Progress | 2022-02-25 | 2022-11-21 |  | 720360 | 851130 | 509791
28 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | CM,F&E | In-Progress | 2022-02-25 | 2022-11-21 |  | 133515 | 219971 | 148034
28 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 2023-09-22 | 2024-02-22 | 2024-04-23 | 74118 | 67193 | 61178
28 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | Scope | Complete | 2021-06-03 | 2023-11-03 | 2024-01-08 | 128800 | 158115 | 122714
28 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | Design | Complete | 2024-01-19 | 2024-07-23 | 2024-05-15 | 644000 | 596875 | 507467
28 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | Construction | In-Progress | 2024-08-26 | 2026-08-25 |  | 14490000 | 13187022 | 177999
28 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | CM,F&E | In-Progress | 2024-08-26 | 2026-08-25 |  | 901600 | 115834 | 50963
28 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 2023-06-29 | 2023-11-15 | 2024-04-18 | 48000 | 44856 | 4895
28 | HS FOR LAW ENFORCEMENT - QUEENS | SCA CIP RESOA | FY24 RESO A ROOFTOP PLAYGROUND | Design | In-Progress | 2024-06-25 | 2024-11-26 |  | 90000 | 57181 | 11983
29 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-08-15 | 2023-12-15 | 2023-09-05 | 3871 | 2266 | 2266
29 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-09-05 | 2024-03-05 | 2023-11-01 | 17419 | 9065 | 9065
29 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-02-09 | 2025-01-03 |  | 224510 | 200560 | 99984
29 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-02-09 | 2025-01-03 |  | 45876 | 50742 | 50742
29 | P.S. 34 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2021-07-30 | 2021-12-16 | 2022-04-01 | 6269 | 1297 | 6
29 | P.S. 34 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2022-04-01 | 2022-06-01 | 2022-04-01 | 28213 | 20240 | 23
29 | P.S. 34 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-02-04 | 2022-06-06 | 2022-02-22 | 73224 | 54840 | 50394
29 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 2022-06-30 | 2022-12-27 | 2022-10-04 | 109490 | 160705 | 144978
29 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Design | Complete | 2022-10-14 | 2023-06-12 | 2023-04-26 | 547449 | 496975 | 490697
29 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Construction | In-Progress | 2023-07-12 | 2025-01-01 |  | 12317625 | 11373863 | 5042795
29 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | CM,F&E | In-Progress | 2023-07-12 | 2025-01-01 |  | 767710 | 550714 | 433316
29 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2021-03-01 | 2021-07-16 | 2021-10-26 | 64814 | 137996 | 132754
29 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2021-11-03 | 2022-04-08 | 2022-03-24 | 314425 | 386503 | 259304
29 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 2022-07-18 | 2024-09-14 |  | 6240379 | 5722734 | 2538183
29 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 2022-07-18 | 2024-09-14 |  | 526761 | 380101 | 366018
29 | P.S. 36 - QUEENS | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | In-Progress | 2023-05-18 |  |  | 100000 | 100000 | 100000
29 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2017-05-09 | 2017-10-10 | 2017-07-07 | 154256 | 149205 | 149205
29 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2017-07-14 | 2017-12-15 | 2017-11-06 | 617025 | 584541 | 572580
29 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2018-06-18 | 2019-12-09 |  | 11569214 | 6811737 | 6575643
29 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2018-06-18 | 2019-12-09 |  | 719862 | 530591 | 516390
29 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 2013-08-15 | 2015-05-11 | 2015-11-03 | 245222 | 260613 | 260613
29 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | Design | Complete | 2016-04-05 | 2016-09-02 | 2017-02-14 | 967305 | 1051101 | 820479
29 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | Construction | In-Progress | 2017-07-18 | 2019-04-08 |  | 16918073 | 15568159 | 14777595
29 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2017-07-18 | 2019-04-08 |  | 1320918 | 2032976 | 2025520
29 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2019-08-30 | 2020-01-13 | 2019-09-10 | 4431 | 2717 | 2717
29 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2019-09-10 | 2020-02-13 | 2020-02-05 | 19939 | 10936 | 10936
29 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2020-10-15 | 2021-07-11 |  | 256987 | 314455 | 299454
29 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2020-10-15 | 2021-07-11 |  | 47631 | 30091 | 27127
29 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | Scope | Complete | 2021-05-11 | 2021-09-24 | 2021-12-07 | 152878 | 139829 | 139829
29 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | Design | Complete | 2021-12-10 | 2022-05-13 | 2022-10-06 | 754443 | 659500 | 576124
29 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | Construction | In-Progress | 2023-02-06 | 2025-03-26 |  | 16114442 | 14557220 | 8781540
29 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | CM,F&E | In-Progress | 2023-02-06 | 2025-03-26 |  | 1144755 | 217821 | 158116
29 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 2019-08-30 | 2020-01-06 | 2019-09-09 | 2279 | 1963 | 1963
29 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 2019-09-09 | 2020-02-12 | 2020-02-05 | 10256 | 7937 | 7937
29 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 2020-10-15 | 2021-07-11 |  | 132185 | 191081 | 182175
29 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 2020-10-15 | 2021-07-11 |  | 24500 | 18625 | 18625
29 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-08 | 2022-11-23 | 2023-05-04 | 96428 | 148324 | 146906
29 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-05-22 | 2023-10-24 | 2023-10-23 | 482141 | 457002 | 344999
29 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-06-15 | 2026-03-06 |  | 10848150 | 10000069 | 210105
29 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-06-15 | 2026-03-06 |  | 674996 | 39864 | 39864
29 | I.S. 59 - QUEENS | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE | Design | Complete | 2022-01-04 | 2022-05-19 | 2022-07-13 | 54182 | 65570 | 65570
29 | I.S. 59 - QUEENS | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | In-Progress | 2023-02-27 | 2023-11-23 |  | 794666 | 628242 | 578069
29 | I.S. 59 - QUEENS | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2023-02-27 | 2023-11-23 |  | 195277 | 228844 | 180063
29 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | Scope | Complete | 2022-04-28 | 2022-11-29 | 2022-11-14 | 1076660 | 1032175 | 799628
29 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | Design | Complete | 2022-11-14 | 2023-05-18 | 2023-04-28 | 4844970 | 2264641 | 1467931
29 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | Construction | In-Progress | 2023-09-18 | 2026-09-03 |  | 61100455 | 55658809 | 2212598
29 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | CM,Art,F&E | In-Progress | 2023-09-18 | 2026-09-03 |  | 8613281 | 3910584 | 1047515
29 | P.S. 95 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Scope | Complete | 2022-08-26 | 2022-12-30 | 2022-11-14 | 31548 | 70951 | 66606
29 | P.S. 95 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Design | Complete | 2023-05-04 | 2023-11-20 | 2024-04-01 | 157740 | 208701 | 102488
29 | P.S. 95 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2022-04-28 | 2022-05-26 | 2022-05-19 | 23090 | 29160 | 29160
29 | P.S. 95 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2022-05-20 | 2022-08-11 | 2022-09-30 | 115450 | 263701 | 234517
29 | P.S. 95 - QUEENS | SCA CIP | DEMOLITION | Construction | Complete | 2023-04-13 | 2024-01-07 | 2024-04-11 | 2597625 | 2447998 | 2281541
29 | P.S. 95 - QUEENS | SCA CIP | DEMOLITION | CM,F&E | Complete | 2023-04-13 | 2024-01-07 | 2024-04-11 | 161630 | 245287 | 236624
29 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | Scope | Complete | 2021-03-16 | 2021-07-29 | 2021-12-07 | 124001 | 208763 | 208763
29 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | Design | Complete | 2021-12-08 | 2022-05-11 | 2022-05-10 | 620000 | 408686 | 396556
29 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | Construction | In-Progress | 2022-11-28 | 2024-11-16 |  | 13950000 | 12718255 | 10434844
29 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | CM,F&E | In-Progress | 2022-11-28 | 2024-11-16 |  | 868000 | 226609 | 128724
29 | I.S. 109 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2022-02-14 | 2022-05-13 | 2022-04-18 | 16059 | 12196 | 12196
29 | I.S. 109 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2022-04-19 | 2022-09-19 | 2022-09-21 | 80295 | 48778 | 48778
29 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2019-08-06 | 2020-03-25 | 2019-11-21 | 5030 | 6265 | 6265
29 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2019-11-21 | 2020-04-24 | 2020-02-05 | 22635 | 25126 | 25126
29 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2020-10-15 | 2021-07-11 |  | 291749 | 394917 | 376138
29 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2020-10-15 | 2021-07-11 |  | 54074 | 40845 | 32442
29 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | Scope | Complete | 2022-05-10 | 2023-04-17 | 2023-02-17 | 1296661 | 829465 | 824163
29 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | Design | Complete | 2023-02-21 | 2023-08-23 | 2023-04-20 | 5834970 | 2301025 | 1439199
29 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | Construction | In-Progress | 2023-12-15 | 2026-09-03 |  | 73585455 | 65245092 | 4168606
29 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | CM,Art,F&E | In-Progress | 2023-12-15 | 2026-09-03 |  | 10373281 | 4064688 | 696669
29 | P.S. 116 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION/PROGRAM ACCESSIBILITY | Scope | Complete | 2023-05-26 | 2023-10-26 | 2023-10-02 | 46664 | 44926 | 44926
29 | P.S. 116 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION/PROGRAM ACCESSIBILITY | Design | Complete | 2023-10-10 | 2024-03-14 | 2024-08-26 | 233321 | 159248 | 87274
29 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2022-07-05 | 2022-07-05 | 2022-07-05 | 46456 | 2807 | 2807
29 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2022-07-06 | 2022-09-16 | 2022-10-25 | 232280 | 316811 | 284671
29 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 2023-04-10 | 2024-07-02 |  | 5226300 | 5004025 | 3064667
29 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2023-04-10 | 2024-07-02 |  | 325192 | 500723 | 478975
29 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-06-21 | 2021-11-04 | 2022-01-26 | 156001 | 231097 | 231091
29 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2022-01-27 | 2022-06-28 | 2022-05-11 | 780000 | 554099 | 546598
29 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2022-08-15 | 2024-05-05 |  | 17550000 | 16029317 | 11818818
29 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-08-15 | 2024-05-05 |  | 1093229 | 668535 | 660180
29 | P.S. 118 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-09-11 | 2025-01-30 |  | 60000 | 6614 | 6614
29 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | Scope | Complete | 2017-12-19 | 2023-05-31 | 2023-08-04 | 146611 | 294415 | 287808
29 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | Design | Complete | 2023-08-04 | 2023-12-21 | 2024-04-30 | 733051 | 698370 | 492579
29 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | Construction | In-Progress | 2024-08-19 | 2026-05-10 |  | 16493625 | 14803902 | 85639
29 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | CM,F&E | In-Progress | 2024-08-19 | 2026-05-10 |  | 1026270 | 131933 | 131933
29 | P.S. 132 - QUEENS | SCA CIP RESOA | FY18 RESO A KITCHEN AREAS | Design | Complete | 2018-05-15 | 2018-10-16 | 2019-05-06 | 264016 | 335134 | 288942
29 | P.S. 132 - QUEENS | SCA CIP RESOA | FY18 RESO A KITCHEN AREAS | Construction | In-Progress | 2021-07-12 | 2023-01-12 |  | 3872238 | 3651645 | 3209608
29 | P.S. 132 - QUEENS | SCA CIP RESOA | FY18 RESO A KITCHEN AREAS | CM,F&E | In-Progress | 2021-07-12 | 2023-01-12 |  | 264016 | 468700 | 429072
29 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | Scope | Complete | 2019-02-15 | 2021-09-15 | 2021-11-23 | 254504 | 170773 | 170773
29 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | Design | Complete | 2021-12-03 | 2022-05-23 | 2023-03-01 | 1266898 | 826136 | 706140
29 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | Construction | In-Progress | 2023-07-13 | 2025-07-01 |  | 28018687 | 25714132 | 13051631
29 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | CM,F&E | In-Progress | 2023-07-13 | 2025-07-01 |  | 1823719 | 326678 | 210880
29 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-19 | 2023-04-20 | 2023-01-03 | 4051 | 3630 | 3630
29 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-03 | 2023-06-29 | 2023-05-03 | 18230 | 14519 | 14519
29 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-20 | 2024-11-18 |  | 234963 | 210969 | 2348
29 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-20 | 2024-11-18 |  | 47813 | 21919 | 21919
29 | P.S. 135 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-08-15 | 2024-12-17 | 2024-08-21 | 5572 | 733 | 733
29 | P.S. 135 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-08-21 | 2025-02-20 |  | 25076 | 25076 | 2934
29 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 2019-05-17 | 2019-10-02 | 2019-09-05 | 126420 | 155120 | 152567
29 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 2019-09-25 | 2020-03-17 | 2020-07-01 | 632103 | 689931 | 656702
29 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | In-Progress | 2022-06-30 | 2025-02-13 |  | 14222328 | 12888717 | 6369570
29 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 2022-06-30 | 2025-02-13 |  | 884945 | 156804 | 156804
29 | P.S. 136 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2024-08-16 | 2024-12-18 | 2024-08-22 | 5090 | 829 | 829
29 | P.S. 136 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 2024-08-22 | 2025-02-21 |  | 22903 | 22903 | 3315
29 | P.S. 136 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-07-15 | 2024-11-29 |  | 60000 | 39340 | 8290
29 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2022-06-09 | 2022-12-05 | 2022-10-11 | 249042 | 285868 | 267264
29 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 2022-10-14 | 2023-06-12 | 2023-04-18 | 1238169 | 569320 | 569320
29 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 2023-07-21 | 2026-07-19 |  | 27249649 | 24637888 | 8318789
29 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-07-21 | 2026-07-19 |  | 1796112 | 374833 | 232758
29 | P.S. 138 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-04-22 | 2024-09-06 |  | 78000 | 60284 | 14522
29 | P.S. 138 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-07-23 | 2024-11-25 |  | 4604 | 1178 | 1178
29 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-19 | 2022-12-05 | 2023-06-12 | 56463 | 138039 | 132820
29 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-07-05 | 2023-12-06 | 2023-12-08 | 282314 | 322959 | 230235
29 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-04-29 | 2025-10-20 |  | 6352043 | 5917942 | 139098
29 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-04-29 | 2025-10-20 |  | 395238 | 94842 | 94572
29 | P.S. 156 - QUEENS | SCA CIP RESOA | FY22 RESO A ELECTRICAL UPGRADE | Design | Complete | 2022-06-10 | 2022-11-10 | 2022-09-28 | 22079 | 65637 | 59887
29 | P.S. 156 - QUEENS | SCA CIP RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | Complete | 2023-04-03 | 2023-12-28 | 2023-10-16 | 323825 | 283983 | 262601
29 | P.S. 156 - QUEENS | SCA CIP RESOA | FY22 RESO A ELECTRICAL UPGRADE | CM,F&E | Complete | 2023-04-03 | 2023-12-28 | 2023-10-16 | 22079 | 34285 | 33681
29 | P.S. 156 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE / PATH OF TRAVEL RESO A COMPUTER LAB UPGRADE | Design | Complete | 2023-05-30 | 2023-10-30 | 2023-11-15 | 45913 | 76561 | 63845
29 | P.S. 156 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE / PATH OF TRAVEL RESO A COMPUTER LAB UPGRADE | Construction | In-Progress | 2024-06-21 | 2025-04-16 |  | 673393 | 504559 | 14248
29 | P.S. 156 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE / PATH OF TRAVEL RESO A COMPUTER LAB UPGRADE | CM,F&E | In-Progress | 2024-06-21 | 2025-04-16 |  | 45913 | 62980 | 14459
29 | P.S. 176 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 2013-11-26 | 2014-02-28 | 2014-02-28 | 52357 | 97205 | 97205
29 | P.S. 176 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | Complete | 2014-03-26 | 2014-08-08 | 2014-09-26 | 261784 | 282799 | 282799
29 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | Scope | Complete | 2020-01-14 | 2020-05-29 | 2021-06-21 | 99024 | 93270 | 93270
29 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | Design | Complete | 2021-07-26 | 2021-12-28 | 2022-02-28 | 486988 | 337674 | 337674
29 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2022-07-13 | 2024-04-02 |  | 10253598 | 9280049 | 8042202
29 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2022-07-13 | 2024-04-02 |  | 754182 | 739183 | 722393
29 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | Scope | Complete | 2019-08-02 | 2019-12-19 | 2021-05-24 | 80105 | 68383 | 61827
29 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | Design | Complete | 2021-05-26 | 2021-10-27 | 2022-05-12 | 400526 | 350430 | 350430
29 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | Construction | In-Progress | 2022-07-27 | 2024-01-17 |  | 9011847 | 8244844 | 5133369
29 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | CM,F&E | In-Progress | 2022-07-27 | 2024-01-17 |  | 561944 | 636502 | 608763
29 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | Scope | Complete | 2018-11-08 | 2019-03-26 | 2019-03-01 | 208401 | 139787 | 112537
29 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | Design | Complete | 2019-03-01 | 2019-07-31 | 2022-05-10 | 1042001 | 690811 | 642453
29 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2022-08-15 | 2024-10-02 |  | 23445015 | 21316427 | 12446382
29 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2022-08-15 | 2024-10-02 |  | 1458801 | 184710 | 179300
29 | I.S. 238 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 2024-09-06 | 2024-09-06 | 2024-09-06 | 82656 | 0 | 0
29 | I.S. 238 - QUEENS | SCA CIP | ROOFS | Design | In-Progress | 2024-09-06 | 2024-11-15 |  | 385726 | 385726 | 0
29 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 410 | 410
29 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2004-12-01 | 2005-05-15 | 2005-04-18 | 2600 | 19693 | 19693
29 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2005-12-01 | 2006-06-25 |  | 77000 | 75241 | 75241
29 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2005-12-01 | 2006-06-25 |  | 12240 | 24370 | 24370
29 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | Scope | Complete | 2020-01-17 | 2020-06-03 | 2021-06-28 | 116100 | 125708 | 125708
29 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | Design | Complete | 2021-08-26 | 2022-02-01 | 2022-02-23 | 572361 | 436832 | 413369
29 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | Construction | In-Progress | 2022-07-18 | 2024-11-13 |  | 12173990 | 6577843 | 1015571
29 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | CM,F&E | In-Progress | 2022-07-18 | 2024-11-13 |  | 882155 | 371127 | 363671
29 | P.S. 268 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2022-07-08 | 2022-11-23 | 2023-08-24 | 26008 | 94172 | 91287
29 | P.S. 268 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 2023-09-21 | 2024-02-27 | 2024-04-25 | 117036 | 93397 | 71370
29 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-12-13 | 2023-04-14 | 2023-01-03 | 3168 | 3791 | 3791
29 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-03 | 2023-06-29 | 2023-05-03 | 14254 | 15165 | 15165
29 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-11-20 | 2024-11-18 |  | 183723 | 164449 | 0
29 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-11-20 | 2024-11-18 |  | 38316 | 21622 | 21622
29 | P.S. 268 - QUEENS | SCA CIP RESOA | FY18 RESO A ROOFTOP PLAYGROUND | Design | Complete | 2019-01-16 | 2019-06-03 | 2020-05-18 | 46500 | 95184 | 95184
29 | P.S. 268 - QUEENS | SCA CIP RESOA | FY18 RESO A ROOFTOP PLAYGROUND | Construction | In-Progress | 2021-05-14 | 2022-02-07 |  | 682000 | 579826 | 538484
29 | P.S. 268 - QUEENS | SCA CIP RESOA | FY18 RESO A ROOFTOP PLAYGROUND | CM,F&E | In-Progress | 2021-05-14 | 2022-02-07 |  | 46500 | 56922 | 55819
29 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | Scope | Complete | 2021-04-20 | 2022-02-11 | 2022-01-19 | 36710 | 46720 | 46720
29 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | Design | Complete | 2022-01-20 | 2022-03-09 | 2022-03-02 | 170636 | 134348 | 128348
29 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | Construction | In-Progress | 2023-07-24 | 2024-10-20 |  | 2722682 | 2403984 | 1544092
29 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-07-24 | 2024-10-20 |  | 353782 | 592948 | 558534
29 | P.S. / I.S. 270 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 2024-04-02 | 2024-08-16 |  | 40200 | 24889 | 18664
29 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2020-08-06 | 2021-10-28 | 2022-06-17 | 76540 | 130195 | 126200
29 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2022-08-31 | 2023-02-28 | 2023-03-10 | 382701 | 414723 | 307028
29 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 2024-05-20 | 2025-11-10 |  | 8610750 | 8093105 | 289146
29 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2024-05-20 | 2025-11-10 |  | 535780 | 149907 | 103619
29 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 2024-07-03 | 2024-12-05 |  | 36000 | 57951 | 6536
29 | QUEENS PREPARATORY ACADEMY - Q | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 2024-07-03 | 2024-12-05 |  | 52186 | 33133 | 6775
29 | QUEENS PREPARATORY ACADEMY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | In-Progress | 2024-08-08 | 2024-12-09 |  | 2461 | 534 | 534
29 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 2024-08-08 | 2024-12-09 |  | 2496 | 593 | 593
29 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION / FY20 RESO A PATH OF TRAVEL ROOM CONVERSION | Design | Complete | 2023-01-19 | 2023-05-05 | 2023-04-28 | 115311 | 96981 | 85794
29 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION / FY20 RESO A PATH OF TRAVEL ROOM CONVERSION | Construction | In-Progress | 2023-11-21 | 2025-05-13 |  | 1691219 | 1509532 | 1173900
29 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION / FY20 RESO A PATH OF TRAVEL ROOM CONVERSION | CM,F&E | In-Progress | 2023-11-21 | 2025-05-13 |  | 222864 | 217728 | 144636
29 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | Scope | Complete | 2021-11-30 | 2022-03-18 | 2022-02-09 | 22260 | 38010 | 38010
29 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | Design | Complete | 2022-02-16 | 2022-07-19 | 2022-05-09 | 111300 | 152043 | 152043
29 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | Construction | In-Progress | 2022-08-08 | 2023-08-07 |  | 2504250 | 2279111 | 1599476
29 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 2022-08-08 | 2023-08-07 |  | 155820 | 190461 | 165247
29 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY20 RESO A LOW VOLTAGE | Design | Complete | 2021-05-26 | 2021-10-27 | 2021-09-28 | 96813 | 24428 | 24428
29 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY20 RESO A LOW VOLTAGE | Construction | In-Progress | 2022-01-24 | 2022-11-19 |  | 1419922 | 1192898 | 1040837
29 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY20 RESO A LOW VOLTAGE | CM,F&E | In-Progress | 2022-01-24 | 2022-11-19 |  | 96813 | 28605 | 28477
29 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 2022-09-09 | 2023-02-14 | 2023-02-17 | 50280 | 60496 | 47880
29 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2023-07-17 | 2024-05-11 | 2024-04-11 | 737440 | 659550 | 576938
29 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 2023-07-17 | 2024-05-11 | 2024-04-11 | 50280 | 96345 | 56472
29 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Design | Complete | 2024-04-08 | 2024-09-09 | 2024-08-16 | 29775 | 42590 | 17694
29 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2024-05-06 | 2024-09-20 |  | 59781 | 44975 | 3623
29 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 2024-04-08 | 2024-08-06 | 2024-08-16 | 225 | 225 | 0
29 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 2024-03-15 | 2024-06-14 | 2024-05-23 | 267 | 267 | 267
29 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | In-Progress | 2024-06-04 | 2024-10-07 |  | 1068 | 1068 | 1068
29 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 2003-09-12 | 2003-09-12 | 2003-09-12 | 720 | 60 | 60
29 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 2004-12-01 | 2005-05-15 | 2005-04-18 | 2600 | 17481 | 17481
29 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 2005-10-18 | 2006-06-18 |  | 77000 | 300429 | 300429
29 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 2005-10-18 | 2006-06-18 |  | 12240 | 37203 | 37203
29 | EAGLE ACADEMY III - QUEENS | SCA CIP RESOA | FY24 RESO A WEIGHT ROOM | Design | In-Progress | 2024-07-03 | 2024-11-19 |  | 30000 | 17377 | 2154
29 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2019-05-17 | 2019-10-02 | 2019-09-05 | 11789 | 6339 | 6339
29 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2019-09-25 | 2020-03-17 | 2020-07-01 | 58947 | 34497 | 32924
29 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 2022-06-30 | 2025-02-13 |  | 1326297 | 1359549 | 1217900
29 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 2022-06-30 | 2025-02-13 |  | 82525 | 22163 | 18922
29 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 2023-07-05 | 2023-07-05 | 2023-07-05 | 17023 | 15144 | 15144
29 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | Design | Complete | 2023-07-05 | 2023-12-06 | 2023-12-08 | 76605 | 67890 | 44186
29 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | Construction | In-Progress | 2024-04-29 | 2025-10-20 |  | 987349 | 896503 | 25208
29 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | CM,F&E | In-Progress | 2024-04-29 | 2025-10-20 |  | 183000 | 12267 | 12267
29 | MERRICK ACADEMY CHARTER SCHOOL - QUEENS | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 2024-07-17 |  |  | 350000 | 350000 | 923
30 | P.S. 2 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS | Scope | Complete | 2024-06-12 | 2024-10-29 | 2024-09-27 | 108598 | 101518 | 56292
30 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | Scope | Complete | 2019-08-22 | 2020-01-10 | 2020-02-21 | 15433 | 37961 | 37961
30 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | Design | Complete | 2021-06-01 | 2021-11-01 | 2022-04-11 | 77163 | 79684 | 79684
30 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | Construction | In-Progress | 2022-06-21 | 2023-09-13 |  | 1736156 | 1620785 | 1593173
30 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | CM,F&E | In-Progress | 2022-06-21 | 2023-09-13 |  | 108028 | 178257 | 172851
30 | P.S. 17 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-06-18 | 2019-11-19 | 2019-10-02 | 66300 | 89840 | 89840
30 | P.S. 17 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-10-16 | 2020-03-20 | 2020-04-17 | 331501 | 341070 | 323830
30 | P.S. 17 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | Complete | 2021-07-06 | 2023-07-05 | 2023-07-28 | 7458750 | 6860642 | 6442070
30 | P.S. 17 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | Complete | 2021-07-06 | 2023-07-05 | 2023-07-28 | 464100 | 502744 | 497183
30 | P.S. 17 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 2023-06-07 | 2023-12-06 | 2023-10-20 | 143584 | 122185 | 121009
30 | P.S. 17 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 2023-11-09 | 2024-06-28 | 2024-04-11 | 708217 | 236804 | 236773
30 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-06-14 | 2023-10-16 | 2023-06-29 | 4106 | 1608 | 1608
30 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-06-29 | 2023-12-27 | 2023-09-20 | 18477 | 6433 | 6433
30 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-01-08 | 2024-11-02 |  | 238149 | 215006 | 142422
30 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-01-08 | 2024-11-02 |  | 113648 | 103339 | 93601
30 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | Scope | Complete | 2019-01-23 | 2019-04-05 | 2019-05-03 | 32890 | 58247 | 58247
30 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | Design | Complete | 2019-05-08 | 2019-11-08 | 2019-10-11 | 164450 | 388292 | 332223
30 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | Construction | In-Progress | 2020-01-21 | 2021-01-19 |  | 3700125 | 3425934 | 3121358
30 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | CM,F&E | In-Progress | 2020-01-21 | 2021-01-19 |  | 230230 | 262873 | 257723
30 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 2021-06-22 | 2021-11-05 | 2021-11-01 | 7118 | 14499 | 14499
30 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 2021-11-08 | 2022-04-13 | 2022-04-06 | 32033 | 37080 | 14895
30 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | Construction | In-Progress | 2022-09-06 | 2023-06-02 |  | 412868 | 411280 | 303328
30 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | CM,F&E | In-Progress | 2022-09-06 | 2023-06-02 |  | 76523 | 66440 | 65403
30 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 2019-05-06 | 2019-09-05 | 2019-05-21 | 2510 | 2510 | 2510
30 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 2019-05-21 | 2019-10-22 | 2019-10-30 | 10760 | 10109 | 10109
30 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 2020-09-16 | 2021-06-12 |  | 291520 | 291520 | 291019
30 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 2020-09-16 | 2021-06-12 |  | 43125 | 43125 | 43125
30 | P.S. 70 - QUEENS | SCA CIP RESOA | FY20 RESO LIBRARY UPGRADE | Design | Complete | 2022-08-30 | 2023-01-19 | 2023-01-31 | 35850 | 44143 | 44143
30 | P.S. 70 - QUEENS | SCA CIP RESOA | FY20 RESO LIBRARY UPGRADE | Construction | In-Progress | 2023-05-22 | 2024-04-15 |  | 525802 | 310509 | 145579
30 | P.S. 70 - QUEENS | SCA CIP RESOA | FY20 RESO LIBRARY UPGRADE | CM,F&E | In-Progress | 2023-05-22 | 2024-04-15 |  | 155488 | 163046 | 53109
30 | P.S. 76 - QUEENS | SCA CIP | RETAINING WALL | Scope | In-Progress | 2024-05-24 | 2024-10-10 |  | 5000 | 8261 | 0
30 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-11-16 | 2023-03-21 | 2022-12-05 | 5100 | 6836 | 6836
30 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-05 | 2023-06-01 | 2023-03-08 | 22950 | 27342 | 27342
30 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-10 | 2024-05-04 |  | 295800 | 261602 | 211421
30 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-10 | 2024-05-04 |  | 178563 | 165475 | 101252
30 | P.S. 84 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / FIRE ALARM SYSTEM REPLACEMENT / HVAC UPGRADES / WINDOWS | Scope | Complete | 2022-07-12 | 2022-11-28 | 2023-05-15 | 138000 | 223068 | 212497
30 | P.S. 84 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / FIRE ALARM SYSTEM REPLACEMENT / HVAC UPGRADES / WINDOWS | Design | Complete | 2023-06-13 | 2023-12-18 | 2024-02-09 | 658175 | 400007 | 374071
30 | P.S. 84 - QUEENS | SCA CIP | STRUCTURAL REPAIRS | Scope | In-Progress | 2024-09-18 | 2025-02-06 |  | 43770 | 53676 | 17852
30 | P.S. 85 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 2024-06-24 | 2024-11-07 | 2024-09-27 | 193939 | 34169 | 18569
30 | P.S. 85 - QUEENS | SCA CIP RESOA | FY21 RESO A CAFETERIA UPGRADE / PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | Complete | 2022-03-04 | 2022-05-20 | 2022-05-13 | 64425 | 51890 | 47631
30 | P.S. 85 - QUEENS | SCA CIP RESOA | FY21 RESO A CAFETERIA UPGRADE / PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2023-08-07 | 2024-09-29 |  | 944900 | 679866 | 18821
30 | P.S. 85 - QUEENS | SCA CIP RESOA | FY21 RESO A CAFETERIA UPGRADE / PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | In-Progress | 2023-08-07 | 2024-09-29 |  | 64425 | 71088 | 39684
30 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2019-08-26 | 2020-01-15 | 2021-11-17 | 75080 | 133842 | 130813
30 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Design | Complete | 2021-12-08 | 2022-05-11 | 2022-05-05 | 375404 | 339374 | 339374
30 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2022-08-15 | 2024-02-05 |  | 8446568 | 7834758 | 5049322
30 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2022-08-15 | 2024-02-05 |  | 528886 | 955715 | 888574
30 | P.S. 112 - QUEENS | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Design | Complete | 2017-03-24 | 2017-08-08 | 2017-05-17 | 84467 | 104140 | 104140
30 | P.S. 112 - QUEENS | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2017-08-22 | 2018-05-18 |  | 1238846 | 1227090 | 1103155
30 | P.S. 112 - QUEENS | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2017-08-22 | 2018-05-18 |  | 84467 | 416603 | 416048
30 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2021-05-27 | 2021-08-26 | 2021-10-08 | 11000 | 42301 | 42301
30 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2021-12-28 | 2022-06-30 | 2022-09-23 | 55000 | 170415 | 121894
30 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2023-10-06 | 2024-07-01 |  | 1237500 | 1309720 | 1137149
30 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2023-10-06 | 2024-07-01 |  | 77000 | 155341 | 116571
30 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-07-14 | 2022-11-30 | 2023-06-12 | 117730 | 174183 | 151233
30 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2023-07-05 | 2023-12-06 | 2024-03-29 | 588650 | 352213 | 345556
30 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 2024-07-05 | 2027-06-19 |  | 13244625 | 12127544 | 189114
30 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 2024-07-05 | 2027-06-19 |  | 824110 | 63847 | 63847
30 | P.S. 122 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 2019-06-05 | 2020-07-31 | 2020-05-26 | 12853 | 43770 | 41981
30 | P.S. 122 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 2020-05-27 | 2020-07-28 | 2020-06-30 | 63039 | 101837 | 101837
30 | P.S. 122 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Construction | Complete | 2022-05-23 | 2023-08-15 | 2023-01-17 | 1312653 | 1207568 | 1191172
30 | P.S. 122 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | CM,F&E | Complete | 2022-05-23 | 2023-08-15 | 2023-01-17 | 99134 | 82434 | 82360
30 | P.S. 122 - QUEENS | SCA CIP RESOA | FY16 RESO A SOLAR PANELS | Design | Complete | 2017-11-07 | 2018-04-12 | 2018-05-09 | 76563 | 252433 | 218695
30 | P.S. 122 - QUEENS | SCA CIP RESOA | FY16 RESO A SOLAR PANELS | Construction | Complete | 2019-10-25 | 2020-08-19 | 2022-11-29 | 1122921 | 999621 | 936920
30 | P.S. 122 - QUEENS | SCA CIP RESOA | FY16 RESO A SOLAR PANELS | CM,F&E | Complete | 2019-10-25 | 2020-08-19 | 2022-11-29 | 76563 | 115914 | 115914
30 | I.S. 126 - QUEENS | SCA CIP | WATER INFILTRATION | Scope | Complete | 2019-05-17 | 2019-10-02 | 2019-11-12 | 15580 | 33744 | 33736
30 | I.S. 126 - QUEENS | SCA CIP | WATER INFILTRATION | Design | Complete | 2020-01-14 | 2020-06-15 | 2021-05-06 | 70110 | 82335 | 71930
30 | I.S. 126 - QUEENS | SCA CIP | WATER INFILTRATION | Construction | Complete | 2022-01-19 | 2022-10-15 | 2023-07-28 | 903640 | 843364 | 703293
30 | I.S. 126 - QUEENS | SCA CIP | WATER INFILTRATION | CM,F&E | Complete | 2022-01-19 | 2022-10-15 | 2023-07-28 | 167485 | 123679 | 106373
30 | I.S. 126 - QUEENS | SCA CIP RESOA | FY23 RESO A SCIENCE LAB | Scope | Complete | 2023-03-02 | 2023-07-03 | 2023-10-27 | 35619 | 35619 | 27619
30 | I.S. 126 - QUEENS | SCA CIP RESOA | FY23 RESO A SCIENCE LAB | Design | In-Progress | 2023-10-31 | 2024-04-04 |  | 76136 | 76136 | 32118
30 | I.S. 126 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB | Scope | Complete | 2023-03-24 | 2023-07-03 | 2023-10-31 | 6049 | 6049 | 1004
30 | I.S. 126 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB | Design | In-Progress | 2023-11-14 | 2024-03-14 |  | 4018 | 4018 | 4018
30 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-11-28 | 2023-03-30 | 2022-12-05 | 4600 | 3750 | 3750
30 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-05 | 2023-06-01 | 2023-03-08 | 20700 | 15000 | 15000
30 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-10 | 2024-05-04 |  | 266800 | 236975 | 195598
30 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-10 | 2024-05-04 |  | 163854 | 150145 | 106153
30 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 2019-08-22 | 2020-02-10 | 2019-10-07 | 4958 | 4583 | 4583
30 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2019-10-07 | 2020-03-12 | 2020-01-29 | 20346 | 18459 | 18459
30 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2021-02-05 | 2021-11-01 |  | 366521 | 366521 | 359810
30 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2021-02-05 | 2021-11-01 |  | 50396 | 50396 | 50396
30 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2014-12-12 | 2015-05-15 | 2015-02-26 | 127455 | 107761 | 107761
30 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2015-04-01 | 2015-08-31 | 2015-08-26 | 509820 | 345008 | 337857
30 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2017-01-09 | 2018-12-09 |  | 9559125 | 8546608 | 8146057
30 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2017-01-09 | 2018-12-09 |  | 594790 | 695262 | 695262
30 | I.S. 145 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / EMERGENCY GENERATOR | Scope | Complete | 2023-06-21 | 2023-11-06 | 2023-12-15 | 119002 | 228082 | 181983
30 | I.S. 145 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / EMERGENCY GENERATOR | Design | In-Progress | 2023-12-27 | 2024-05-29 |  | 584024 | 584024 | 44216
30 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 2019-03-25 | 2019-07-24 | 2019-06-19 | 6008 | 6008 | 6008
30 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 2019-06-19 | 2019-11-20 | 2019-11-07 | 24132 | 24132 | 24132
30 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 2020-09-16 | 2021-06-12 |  | 274494 | 274494 | 273993
30 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 2020-09-16 | 2021-06-12 |  | 41438 | 41438 | 41438
30 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | Scope | Complete | 2023-06-09 | 2023-12-08 | 2023-11-01 | 233536 | 328794 | 311729
30 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | Design | Complete | 2023-12-18 | 2024-05-20 | 2024-04-22 | 1163035 | 381834 | 381834
30 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | Construction | In-Progress | 2024-09-18 | 2027-09-02 |  | 25766388 | 23057161 | 161837
30 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | CM,F&E | In-Progress | 2024-09-18 | 2027-09-02 |  | 1669604 | 83759 | 83759
30 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2019-06-28 | 2019-11-14 | 2019-11-06 | 88879 | 169380 | 166527
30 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2019-11-13 | 2020-04-16 | 2020-06-26 | 444401 | 1132838 | 761548
30 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2021-06-08 | 2023-06-07 |  | 9998999 | 22842913 | 11678271
30 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-06-08 | 2023-06-07 |  | 622161 | 2265907 | 1935807
30 | P.S. 150 - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 2023-11-28 | 2024-04-30 | 2024-03-21 | 90000 | 56555 | 49960
30 | P.S. 152 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / GYM WINDOWS / RTU REPLACEMENT / FIRE ALARM REPLACEMENT | Scope | Complete | 2021-06-02 | 2021-10-18 | 2021-10-28 | 136645 | 144485 | 144485
30 | P.S. 152 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / GYM WINDOWS / RTU REPLACEMENT / FIRE ALARM REPLACEMENT | Design | Complete | 2021-11-19 | 2022-04-25 | 2022-10-20 | 658969 | 396100 | 381871
30 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 2019-05-28 | 2019-09-26 | 2019-07-02 | 5660 | 3310 | 3310
30 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 2019-07-02 | 2019-12-04 | 2019-11-06 | 25472 | 13298 | 13298
30 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 2020-09-16 | 2021-06-12 |  | 453324 | 453324 | 452673
30 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 2020-09-16 | 2021-06-12 |  | 60849 | 55433 | 55433
30 | P.S. 166 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2023-06-05 | 2023-12-04 | 2023-10-26 | 131122 | 165348 | 165348
30 | P.S. 166 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-11-07 | 2024-06-28 | 2024-04-22 | 655614 | 324438 | 324438
30 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2020-03-06 | 2020-06-22 | 2021-07-09 | 36021 | 71967 | 71967
30 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | Complete | 2021-07-27 | 2021-12-29 | 2022-01-19 | 175581 | 238814 | 215157
30 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 2022-07-27 | 2024-01-17 |  | 3559571 | 6637290 | 5910334
30 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 2022-07-27 | 2024-01-17 |  | 286043 | 886792 | 878953
30 | P.S. 171 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM UPGRADE / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 2023-08-25 | 2024-01-22 | 2024-05-21 | 170996 | 132444 | 3349
30 | P.S. 171 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM UPGRADE / ELECTRICAL SERVICE UPGRADE | Design | In-Progress | 2024-06-19 | 2025-01-16 |  | 832113 | 832113 | 12622
30 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2020-05-14 | 2020-11-10 | 2020-09-09 | 138890 | 203120 | 203120
30 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2020-09-21 | 2021-07-01 | 2021-05-07 | 694451 | 594862 | 589218
30 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2021-07-15 | 2023-10-02 |  | 15625125 | 14338616 | 13444590
30 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2021-07-15 | 2023-10-02 |  | 972230 | 745765 | 714863
30 | P.S. 222 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 2024-01-08 | 2024-05-22 | 2024-09-04 | 15458 | 9771 | 9771
30 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 2019-08-26 | 2019-11-26 | 2020-03-09 | 13800 | 52229 | 52229
30 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 2020-03-11 | 2020-08-10 | 2021-12-09 | 69000 | 139956 | 137799
30 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Construction | In-Progress | 2022-06-13 | 2023-06-12 |  | 1552500 | 1390189 | 1303939
30 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2022-06-13 | 2023-06-12 |  | 96600 | 63835 | 63360
30 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-08-11 | 2022-12-13 | 2022-08-25 | 6010 | 2367 | 2367
30 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-08-25 | 2023-03-31 | 2023-03-08 | 27045 | 9468 | 9468
30 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-24 | 2024-05-18 |  | 348580 | 311881 | 219165
30 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-24 | 2024-05-18 |  | 177491 | 156333 | 99980
31 | P.S. 29 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 2022-09-22 | 2023-02-10 | 2023-04-28 | 49176 | 128419 | 125984
31 | P.S. 29 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 2023-05-02 | 2023-10-03 | 2023-10-25 | 245880 | 316901 | 301648
31 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-06-25 | 2020-10-26 | 2020-07-07 | 2247 | 3593 | 3593
31 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-07 | 2021-01-01 | 2021-01-06 | 10112 | 14370 | 14370
31 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-12 | 2023-03-07 |  | 130339 | 120986 | 102391
31 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-12 | 2023-03-07 |  | 161422 | 209405 | 209405
31 | P.S. 30 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2024-01-16 | 2024-05-16 | 2024-04-25 | 42000 | 57644 | 56224
30 | I.S. 227 - QUEENS | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 2021-04-02 | 2021-09-01 | 2022-09-29 | 126000 | 88017 | 86976
30 | I.S. 227 - QUEENS | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2023-07-20 | 2024-04-14 |  | 1848000 | 1718900 | 669250
30 | I.S. 227 - QUEENS | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2023-07-20 | 2024-04-14 |  | 126000 | 91698 | 55108
30 | I.S. 227 - QUEENS | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Design | Complete | 2022-01-18 | 2022-06-17 | 2022-05-11 | 146763 | 140827 | 138235
30 | I.S. 227 - QUEENS | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 2023-03-20 | 2024-03-18 |  | 2152520 | 2155675 | 1440143
30 | I.S. 227 - QUEENS | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 2023-03-20 | 2024-03-18 |  | 247430 | 196384 | 192716
30 | P.S. 228 - QUEENS | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2020-05-20 | 2020-11-17 | 2020-10-30 | 49706 | 204303 | 204273
30 | P.S. 228 - QUEENS | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 2021-05-27 | 2021-11-23 | 2021-11-22 | 242850 | 412263 | 412263
30 | I.S. 230 - QUEENS | SCA CIP | FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE | Scope | Complete | 2019-11-07 | 2020-03-27 | 2021-12-07 | 117767 | 167300 | 164148
30 | I.S. 230 - QUEENS | SCA CIP | FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE | Design | In-Progress | 2022-01-26 | 2022-06-27 |  | 588832 | 588832 | 210167
30 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2019-06-27 | 2019-11-13 | 2019-12-13 | 37229 | 48833 | 48833
30 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2019-12-13 | 2020-05-15 | 2020-07-16 | 175017 | 230010 | 223275
30 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 2022-06-27 | 2023-12-18 |  | 2975201 | 2663084 | 2462553
30 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 2022-06-27 | 2023-12-18 |  | 344072 | 224146 | 201922
30 | P.S. 234 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 2021-10-21 | 2022-02-25 | 2022-07-11 | 19517 | 20389 | 1134
30 | P.S. 234 - QUEENS | SCA CIP | ROOFS | Scope | In-Progress | 2024-06-21 | 2024-11-06 |  | 45596 | 74031 | 21531
30 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 2019-10-29 | 2020-04-28 | 2020-02-20 | 3740 | 19176 | 19176
30 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2020-02-25 | 2020-08-18 | 2020-04-28 | 16830 | 76701 | 76701
30 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 2021-06-23 | 2022-03-19 |  | 216920 | 214510 | 131850
30 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 2021-06-23 | 2022-03-19 |  | 40205 | 37675 | 37280
30 | P.S. 92 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 2021-06-08 | 2021-10-22 | 2021-12-30 | 39437 | 47852 | 47852
30 | P.S. 92 - QUEENS | SCA CIP | ROOFS | Design | Complete | 2022-01-25 | 2022-06-24 | 2022-05-05 | 197184 | 162430 | 162430
30 | P.S. 92 - QUEENS | SCA CIP | ROOFS | Construction | In-Progress | 2022-08-18 | 2024-02-08 |  | 4436634 | 3949354 | 3705248
30 | P.S. 92 - QUEENS | SCA CIP | ROOFS | CM,F&E | In-Progress | 2022-08-18 | 2024-02-08 |  | 276057 | 115912 | 95102
30 | P.S. 92 - QUEENS | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 2023-02-08 | 2024-03-13 | 2024-02-12 | 17052 | 44876 | 44876
30 | P.S. 92 - QUEENS | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 2024-02-21 | 2024-06-24 | 2024-03-27 | 76736 | 74719 | 67621
30 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 2024-07-09 | 2024-11-22 |  | 60000 | 43417 | 3351
30 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2016-12-21 | 2017-06-28 | 2017-06-28 | 1494500 | 1342610 | 1337978
30 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 2017-06-29 | 2018-01-09 | 2023-05-12 | 6725250 | 2879751 | 2718395
30 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2024-09-30 | 2027-09-03 |  | 84812875 | 75616023 | 844182
30 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2024-09-30 | 2027-09-03 |  | 11956000 | 4756389 | 521599
30 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2022-11-14 | 2022-11-14 | 2022-11-14 | 187000 | 3580 | 3580
30 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2022-11-15 | 2023-01-11 | 2023-04-27 | 935000 | 293289 | 213404
30 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 2024-07-23 | 2025-01-18 |  | 21037500 | 18908014 | 79127
30 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2024-07-23 | 2025-01-18 |  | 1309000 | 178741 | 166349
30 | WILLIAM C. BRYANT HS - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Design | Complete | 2021-10-13 | 2021-12-17 | 2021-12-01 | 73297 | 181188 | 167706
30 | WILLIAM C. BRYANT HS - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2022-04-11 | 2023-01-05 |  | 1075015 | 945797 | 783674
30 | WILLIAM C. BRYANT HS - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | CM,F&E | In-Progress | 2022-04-11 | 2023-01-05 |  | 73297 | 115294 | 113335
30 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | Scope | Complete | 2021-08-03 | 2021-08-24 | 2021-08-24 | 239760 | 228413 | 228413
30 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | Design | Complete | 2021-08-25 | 2021-11-22 | 2022-03-08 | 1078920 | 1113793 | 1037707
30 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | Construction | In-Progress | 2022-07-13 | 2023-09-03 |  | 13606380 | 12337959 | 12032171
30 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | CM,F&E | In-Progress | 2022-07-13 | 2023-09-03 |  | 1940169 | 635364 | 1068841
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | Scope | Complete | 2016-09-27 | 2016-09-28 | 2016-09-28 | 11670 | 16187 | 16187
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | Design | Complete | 2016-09-28 | 2017-03-28 | 2017-04-24 | 42790 | 65621 | 65621
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | Construction | In-Progress | 2017-06-27 | 2017-12-23 |  | 453185 | 461583 | 430158
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | CM,F&E | In-Progress | 2017-06-27 | 2017-12-23 |  | 105030 | 65326 | 64526
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-08-04 | 2022-12-06 | 2022-09-28 | 5550 | 3984 | 3984
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-09-28 | 2023-03-29 | 2023-03-08 | 24975 | 15935 | 15935
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-07-24 | 2024-05-18 |  | 321900 | 291434 | 194814
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-07-24 | 2024-05-18 |  | 164768 | 146709 | 88801
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | Scope | Complete | 2020-08-10 | 2023-05-25 | 2023-02-22 | 91056 | 112762 | 105289
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | Design | Complete | 2023-02-22 | 2023-06-26 | 2023-05-11 | 449880 | 550014 | 499818
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | Construction | In-Progress | 2023-08-11 | 2025-05-01 |  | 9654766 | 8954674 | 796713
30 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | CM,F&E | In-Progress | 2023-08-11 | 2025-05-01 |  | 679429 | 1079852 | 990294
30 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2014-05-05 | 2014-09-18 | 2014-12-22 | 325500 | 206837 | 206837
30 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Design | Complete | 2015-03-10 | 2015-08-07 | 2015-12-23 | 1302001 | 1510513 | 1302207
30 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2019-08-05 | 2021-08-03 |  | 24412499 | 30050375 | 15057882
30 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2019-08-05 | 2021-08-03 |  | 1519000 | 2103747 | 1901013
30 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | Scope | Complete | 2015-08-24 | 2015-12-24 | 2016-12-12 | 32700 | 47542 | 47542
30 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | Design | Complete | 2016-12-14 | 2017-05-08 | 2017-12-29 | 130800 | 218157 | 209038
30 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | Construction | In-Progress | 2018-04-16 | 2019-04-15 |  | 2452500 | 2740433 | 2551048
30 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | CM,F&E | In-Progress | 2018-04-16 | 2019-04-15 |  | 177728 | 508051 | 486291
30 | LONG ISLAND CITY HS - Q | SCA CIP | PUBLIC ADDRESS SYSTEM REPLACEMENT | Scope | Complete | 2023-06-07 | 2023-09-07 | 2023-09-08 | 13456 | 4491 | 4491
30 | LONG ISLAND CITY HS - Q | SCA CIP | PUBLIC ADDRESS SYSTEM REPLACEMENT | Design | Complete | 2023-09-20 | 2024-02-26 | 2024-02-23 | 67278 | 17967 | 17967
30 | LONG ISLAND CITY H.S. | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Design | In-Progress | 2024-08-08 | 2025-01-13 |  | 45000 | 43243 | 7029
30 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2018-06-11 | 2019-01-04 | 2019-01-04 | 3577000 | 2420970 | 2288663
30 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 2019-01-07 | 2019-12-11 | 2021-05-05 | 16096500 | 9658845 | 9331091
30 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2021-09-15 | 2025-09-03 |  | 202994750 | 197609872 | 183369020
30 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2021-09-15 | 2025-09-03 |  | 28616000 | 16143014 | 7600957
30 | P.S. 85 ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2019-06-24 | 2019-12-12 | 2019-12-13 | 1127000 | 812747 | 804672
30 | P.S. 85 ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 2019-12-16 | 2020-06-23 | 2021-05-07 | 5071500 | 3434081 | 3021962
30 | P.S. 85 ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Construction | Complete | 2021-10-26 | 2024-09-03 | 2024-06-07 | 63957250 | 59522185 | 57246605
30 | P.S. 85 ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 2021-10-26 | 2024-09-03 | 2024-06-07 | 9016000 | 6950145 | 5573279
30 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 2023-04-06 | 2023-09-25 | 2023-10-26 | 1627873 | 1028861 | 1020915
30 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 2023-10-27 | 2024-04-15 | 2024-05-14 | 7325428 | 1562491 | 1247353
30 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 2023-04-14 | 2023-04-14 | 2023-04-14 | 90859 | 6861 | 6861
30 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 2023-04-17 | 2023-10-06 | 2023-11-29 | 454294 | 349829 | 349829
30 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | Scope | Complete | 2018-07-17 | 2018-10-16 | 2018-09-24 | 42642 | 48620 | 48620
30 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | Design | Complete | 2018-12-06 | 2019-06-07 | 2019-05-16 | 170568 | 191513 | 190842
30 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | Construction | In-Progress | 2019-08-12 | 2020-07-11 |  | 3198151 | 3539286 | 3053418
30 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | CM,F&E | In-Progress | 2019-08-12 | 2020-07-11 |  | 200191 | 291921 | 281306
30 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-10-28 | 2023-03-03 | 2022-12-06 | 2169 | 1647 | 1647
30 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-12-06 | 2023-06-02 | 2023-04-11 | 9759 | 6586 | 6586
30 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-05 | 2024-09-03 |  | 125783 | 119096 | 88178
30 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-05 | 2024-09-03 |  | 119137 | 115257 | 69690
30 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP RESOA | FY21 RESO A ROBOTICS LAB | Design | Complete | 2023-03-10 | 2023-08-10 | 2023-08-11 | 42000 | 82539 | 78248
30 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-11-09 | 2023-03-15 | 2023-01-18 | 2046 | 3391 | 3391
30 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-01-18 | 2023-07-14 | 2023-04-11 | 9205 | 13563 | 13563
30 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-05 | 2024-09-03 |  | 118639 | 115189 | 17515
30 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-05 | 2024-09-03 |  | 122985 | 119571 | 74003
30 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-01-25 | 2023-05-24 | 2023-02-21 | 2168 | 2113 | 2113
30 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-02-21 | 2023-08-16 | 2023-04-11 | 9756 | 8453 | 8453
30 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-05 | 2024-09-03 |  | 125746 | 120843 | 17042
30 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-05 | 2024-09-03 |  | 113154 | 102745 | 56913
30 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP | RTU REPLACEMENT / BMS SYSTEM UPGRADE / FIRE ALARM REPLACEMENT | Scope | Complete | 2021-03-02 | 2021-07-15 | 2021-07-15 | 74411 | 72813 | 72813
30 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP | RTU REPLACEMENT / BMS SYSTEM UPGRADE / FIRE ALARM REPLACEMENT | Design | Complete | 2021-09-08 | 2022-03-16 | 2022-09-13 | 372050 | 294846 | 280325
31 | P.S. 1 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A BREEZEWAY | Design | Complete | 2022-07-05 | 2022-12-06 | 2023-01-25 | 37040 | 49693 | 47950
31 | P.S. 1 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A BREEZEWAY | Construction | In-Progress | 2023-11-10 | 2024-09-04 |  | 543255 | 482683 | 75928
31 | P.S. 1 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A BREEZEWAY | CM,F&E | In-Progress | 2023-11-10 | 2024-09-04 |  | 37040 | 60594 | 24115
31 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2019-11-21 | 2020-04-09 | 2021-12-29 | 11580 | 31774 | 31774
31 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2022-01-07 | 2022-06-09 | 2022-05-04 | 52110 | 31814 | 31814
31 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 2023-05-08 | 2024-04-01 |  | 671640 | 617300 | 348278
31 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 2023-05-08 | 2024-04-01 |  | 124485 | 106212 | 95925
31 | P.S. 3 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Scope | Complete | 2018-03-06 | 2018-07-06 | 2018-08-15 | 24980 | 22905 | 22905
31 | P.S. 3 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Design | Complete | 2018-12-06 | 2019-06-07 | 2019-05-17 | 124900 | 80171 | 72025
31 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-06-18 | 2019-11-19 | 2019-10-04 | 69300 | 100890 | 100890
31 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-10-08 | 2020-03-13 | 2020-01-23 | 346500 | 394615 | 377303
31 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-06-14 | 2023-06-13 |  | 7796250 | 7381085 | 6863481
31 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-06-14 | 2023-06-13 |  | 485100 | 957123 | 951390
31 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2019-06-20 | 2019-11-21 | 2019-08-27 | 68770 | 121205 | 121205
31 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-09-10 | 2020-02-13 | 2020-02-19 | 343850 | 451918 | 419971
31 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2021-06-22 | 2023-06-21 |  | 7736625 | 7952476 | 5324103
31 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2021-06-22 | 2023-06-21 |  | 481390 | 1378388 | 1366483
31 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | Scope | Complete | 2020-11-06 | 2021-01-15 | 2021-01-26 | 39300 | 29106 | 29106
31 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | Design | Complete | 2021-02-02 | 2021-07-02 | 2021-11-16 | 196500 | 184941 | 143326
31 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | Construction | In-Progress | 2022-07-29 | 2024-01-19 |  | 4421250 | 3979122 | 2693335
31 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | CM,F&E | In-Progress | 2022-07-29 | 2024-01-19 |  | 275100 | 249896 | 249896
31 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Design | Complete | 2022-08-12 | 2022-12-30 | 2023-01-24 | 28800 | 46573 | 43728
31 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Design | Complete | 2023-10-17 | 2024-04-15 | 2024-01-31 | 28500 | 18474 | 18474
31 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Construction | In-Progress | 2024-07-25 | 2025-06-19 |  | 418000 | 243972 | 666
31 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | CM,F&E | In-Progress | 2024-07-25 | 2025-06-19 |  | 32764 | 8019 | 8019
31 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | Scope | Complete | 2020-01-21 | 2020-07-14 | 2021-01-19 | 1277800 | 713604 | 707587
31 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | Design | Complete | 2021-01-20 | 2021-01-13 | 2022-05-11 | 5750100 | 3932916 | 3007818
31 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | Construction | In-Progress | 2022-07-18 | 2025-09-03 |  | 72515150 | 72002179 | 28072390
31 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | CM,Art,F&E | In-Progress | 2022-07-18 | 2025-09-03 |  | 10222400 | 7177956 | 3318708
31 | P.S. 5 - STATEN ISLAND | SCA CIP | EXISTING BUILDING WORK / EXISTING BUILDING-AUD/GYM | Scope | Complete | 2021-03-08 | 2021-05-14 | 2021-04-28 | 20684 | 72680 | 72680
31 | P.S. 5 - STATEN ISLAND | SCA CIP | EXISTING BUILDING WORK / EXISTING BUILDING-AUD/GYM | Design | Complete | 2021-04-29 | 2021-09-20 | 2022-01-20 | 102919 | 348483 | 181926
31 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | Scope | Complete | 2019-02-15 | 2019-07-18 | 2020-03-31 | 134750 | 132918 | 131593
31 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | Design | Complete | 2021-07-26 | 2021-12-28 | 2023-03-31 | 673750 | 703793 | 429660
31 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | Construction | In-Progress | 2023-08-01 | 2025-07-20 |  | 15159375 | 13606590 | 364653
31 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | CM,F&E | In-Progress | 2023-08-01 | 2025-07-20 |  | 943250 | 270418 | 256551
31 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2019-06-18 | 2019-11-01 | 2021-07-06 | 24551 | 62315 | 59938
31 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | Design | Complete | 2021-07-06 | 2021-12-07 | 2022-05-16 | 122753 | 95298 | 78472
31 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 2023-03-10 | 2024-06-01 |  | 2761938 | 2481157 | 1773649
31 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-03-10 | 2024-06-01 |  | 173384 | 404581 | 395244
31 | P.S. 6 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | Complete | 2024-03-25 | 2024-08-08 | 2024-08-16 | 48000 | 30198 | 15814
31 | I.S. 7 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2023-11-07 | 2024-05-06 | 2024-01-31 | 30000 | 20589 | 20589
31 | I.S. 7 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-07-25 | 2025-06-19 |  | 440000 | 273667 | 8739
31 | I.S. 7 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-07-25 | 2025-06-19 |  | 34264 | 9992 | 9992
31 | P.S. 8 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS / PATH OF TRAVEL RESO A PLAYGROUNDS | Design | Complete | 2021-03-26 | 2021-06-04 | 2021-05-14 | 255558 | 294410 | 269693
31 | P.S. 8 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS / PATH OF TRAVEL RESO A PLAYGROUNDS | Construction | In-Progress | 2023-08-03 | 2024-08-01 |  | 3748189 | 3612659 | 913305
31 | P.S. 8 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS / PATH OF TRAVEL RESO A PLAYGROUNDS | CM,F&E | In-Progress | 2023-08-03 | 2024-08-01 |  | 255558 | 186170 | 176382
31 | P.S. 8 - STATEN ISLAND | SCA Furniture & Equipment | FY22 RESO A (MA) MOBILE SCIENCE | F&E | Complete | 2024-01-04 |  | 2024-02-29 | 200000 | 200000 | 199337
31 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | Scope | Complete | 2018-10-26 | 2019-03-18 | 2019-03-12 | 178169 | 93520 | 92974
31 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | Design | Complete | 2019-03-12 | 2019-08-09 | 2019-05-17 | 703945 | 497192 | 351349
31 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | Construction | In-Progress | 2021-07-19 | 2023-04-09 |  | 12414816 | 13141308 | 9865493
31 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | CM,F&E | In-Progress | 2021-07-19 | 2023-04-09 |  | 945039 | 778527 | 632547
31 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Scope | Complete | 2018-03-06 | 2018-07-06 | 2018-08-15 | 12340 | 11679 | 11679
31 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Design | Complete | 2018-12-06 | 2019-06-07 | 2019-05-17 | 55530 | 107425 | 66531
31 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Construction | In-Progress | 2024-03-04 | 2025-01-27 |  | 715720 | 638923 | 173198
31 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | CM,F&E | In-Progress | 2024-03-04 | 2025-01-27 |  | 132655 | 86553 | 30001
31 | P.S. 078 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-03-14 | 2022-07-12 | 2022-08-02 | 49054 | 59361 | 47622
31 | P.S. 078 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-11-03 | 2024-09-27 |  | 719458 | 679068 | 229239
31 | P.S. 078 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-11-03 | 2024-09-27 |  | 49054 | 81156 | 37981
31 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 2019-06-13 | 2019-10-29 | 2021-07-06 | 36449 | 137674 | 129759
31 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 2021-08-25 | 2022-01-31 | 2022-02-03 | 180225 | 271103 | 268295
31 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | In-Progress | 2022-07-18 | 2024-01-08 |  | 3879953 | 3517139 | 3336799
31 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-07-18 | 2024-01-08 |  | 270330 | 614547 | 611362
31 | P.S. 19 - STATEN ISLAND | SCA Capacity | ADDITION | Scope | Complete | 2023-11-20 | 2024-06-10 | 2024-05-06 | 1219599 | 925971 | 844085
31 | P.S. 19 - STATEN ISLAND | SCA Capacity | ADDITION | Design | In-Progress | 2024-05-07 | 2024-11-20 |  | 4878398 | 4878398 | 627730
31 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING - ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING - IPDVS UPGRADE / EXISTING BUILDING - FIRE ALARM UPGRADE | Scope | Complete | 2024-02-13 | 2024-06-13 | 2024-05-15 | 20301 | 5067 | 0
31 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING - ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING - IPDVS UPGRADE / EXISTING BUILDING - FIRE ALARM UPGRADE | Design | In-Progress | 2024-05-15 | 2024-11-19 |  | 91357 | 91357 | 0
31 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 2023-11-30 | 2023-11-30 | 2023-11-30 | 31031 | 1708 | 1708
31 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 2023-12-01 | 2024-03-22 | 2024-04-15 | 144813 | 229748 | 80055
31 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | Construction | In-Progress | 2024-08-27 | 2025-08-26 |  | 2296313 | 2156434 | 52350
31 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2024-08-27 | 2025-08-26 |  | 227563 | 101766 | 101515
31 | P.S. 20 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 2024-01-26 | 2024-06-11 | 2024-07-03 | 53036 | 65543 | 27352
31 | P.S. 20 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | In-Progress | 2024-07-09 | 2024-12-10 |  | 252493 | 252493 | 9265
31 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2019-08-08 | 2019-12-26 | 2020-03-13 | 100062 | 287191 | 229522
31 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2020-03-13 | 2020-08-12 | 2020-06-30 | 499671 | 725060 | 455095
31 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2021-08-23 | 2023-05-14 |  | 11186958 | 13676178 | 6264434
31 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2021-08-23 | 2023-05-14 |  | 705791 | 947722 | 838398
31 | P.S. 22 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2024-02-01 | 2024-06-04 | 2024-04-25 | 68396 | 52855 | 41749
31 | P.S. 23 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 2023-10-20 | 2024-02-23 | 2024-04-18 | 27000 | 52280 | 51001
31 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | Scope | Complete | 2021-04-20 | 2021-09-02 | 2021-12-15 | 30364 | 30419 | 30419
31 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | Design | Complete | 2021-12-27 | 2022-05-27 | 2022-11-01 | 146362 | 134759 | 113659
31 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | Construction | In-Progress | 2023-07-24 | 2024-10-15 |  | 2820920 | 2579473 | 830129
31 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | CM,F&E | In-Progress | 2023-07-24 | 2024-10-15 |  | 253493 | 131084 | 123804
31 | R025 SPED - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2024-01-26 | 2024-06-11 | 2024-09-25 | 46652 | 37665 | 17514
31 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2021-04-16 | 2021-09-16 | 2021-07-28 | 83700 | 199905 | 185405
31 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2021-07-30 | 2022-01-31 | 2022-04-13 | 418501 | 816988 | 773918
31 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2022-08-08 | 2024-08-06 |  | 9416250 | 8801688 | 8243453
31 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2022-08-08 | 2024-08-06 |  | 585900 | 541471 | 537618
31 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-07-14 | 2022-11-30 | 2023-03-17 | 69170 | 203722 | 193952
31 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-04-27 | 2023-09-28 | 2024-05-13 | 338283 | 315779 | 278437
31 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2024-08-15 | 2026-08-14 |  | 6956497 | 6377904 | 94580
31 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-08-15 | 2026-08-14 |  | 540974 | 51778 | 51718
31 | P.S. 32 - STATEN ISLAND | SCA CIP | FACADE RESTORATION | Scope | Complete | 2023-08-01 | 2023-12-18 | 2023-12-19 | 20473 | 37933 | 37933
31 | P.S. 32 - STATEN ISLAND | SCA CIP | FACADE RESTORATION | Design | Complete | 2024-01-08 | 2024-06-07 | 2024-05-14 | 102363 | 99444 | 56800
31 | P.S. 32 - STATEN ISLAND | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 2023-05-04 |  | 2023-12-14 | 238000 | 238000 | 237857
31 | I.S. 34 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / CLIMATE CONTROL | Scope | Complete | 2019-06-19 | 2019-11-20 | 2019-08-14 | 89392 | 61734 | 61734
31 | I.S. 34 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / CLIMATE CONTROL | Design | Complete | 2019-09-12 | 2020-02-18 | 2020-02-26 | 446960 | 233577 | 227577
31 | P.S. 36 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-01-04 | 2022-05-19 | 2022-07-15 | 59379 | 64402 | 64402
31 | P.S. 36 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-06-28 | 2024-05-22 |  | 870892 | 662520 | 588503
31 | P.S. 36 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-06-28 | 2024-05-22 |  | 59379 | 64409 | 63106
31 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2021-04-08 | 2021-08-23 | 2021-11-17 | 43730 | 103421 | 103421
31 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 2021-11-29 | 2022-05-02 | 2022-04-22 | 208391 | 250385 | 241897
31 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2022-09-26 | 2024-03-18 |  | 3801630 | 3458826 | 2636842
31 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2022-09-26 | 2024-03-18 |  | 383027 | 555621 | 554837
31 | P.S. 41 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2021-07-06 | 2022-11-23 | 2023-02-14 | 202251 | 382517 | 380434
31 | P.S. 41 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2023-06-16 | 2023-12-14 | 2024-05-13 | 1011250 | 415711 | 376292
31 | P.S. 42 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 2023-12-18 | 2024-05-03 | 2024-07-16 | 78268 | 59683 | 59683
31 | P.S. 42 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | In-Progress | 2024-08-13 | 2025-01-16 |  | 368672 | 368672 | 7404
31 | P.S. 42 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Design | Complete | 2018-02-28 | 2018-07-13 | 2018-12-14 | 58860 | 60849 | 60849
31 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | Scope | Complete | 2022-03-14 | 2022-07-12 | 2022-04-13 | 4003 | 2870 | 2870
31 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | Design | Complete | 2022-04-13 | 2022-10-06 | 2022-07-20 | 18015 | 11477 | 11477
31 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | Construction | In-Progress | 2023-03-24 | 2024-02-16 |  | 232195 | 202316 | 173206
31 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | CM,F&E | In-Progress | 2023-03-24 | 2024-02-16 |  | 219240 | 206550 | 205064
31 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE / FY21 RESO A SCIENCE LAB UPGRADES | Design | Complete | 2022-02-14 | 2022-08-05 | 2023-03-21 | 139501 | 107172 | 76272
31 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE / FY21 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 2024-05-02 | 2026-05-01 |  | 2046000 | 1488569 | 12569
31 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE / FY21 RESO A SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 2024-05-02 | 2026-05-01 |  | 144737 | 123891 | 113031
31 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE CARTS | F&E | Complete | 2024-05-29 |  | 2024-07-01 | 175000 | 175000 | 55878
31 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2017-09-13 | 2019-02-01 | 2019-02-19 | 170358 | 246758 | 246758
31 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | Design | Complete | 2019-02-19 | 2019-07-19 | 2019-05-16 | 757717 | 987101 | 845690
31 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2020-02-10 | 2022-02-08 |  | 15637502 | 15556440 | 14256138
31 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2020-02-10 | 2022-02-08 |  | 973000 | 1312646 | 1266618
31 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | Complete | 2021-06-30 | 2021-11-16 | 2023-02-02 | 517935 | 87278 | 85159
31 | P.S. 52 - STATEN ISLAND | SCA CIP | ROOFS | Scope | In-Progress | 2024-05-22 | 2024-10-08 |  | 62803 | 62803 | 404
31 | P.S. 53 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2022-09-02 | 2023-01-24 | 2023-03-28 | 22400 | 93108 | 63295
31 | P.S. 53 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2023-04-18 | 2023-09-19 | 2023-12-14 | 112000 | 75186 | 66256
31 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2021-04-15 | 2021-09-15 | 2021-07-02 | 84190 | 108145 | 108145
31 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2021-07-08 | 2021-12-09 | 2022-03-31 | 420950 | 572335 | 481061
31 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-07-05 | 2024-07-03 |  | 9471375 | 8726505 | 8026529
31 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-07-05 | 2024-07-03 |  | 589330 | 643762 | 633518
31 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2022-06-30 | 2022-11-16 | 2022-10-26 | 84240 | 142824 | 122370
31 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2022-11-09 | 2023-04-14 | 2023-04-04 | 421199 | 439772 | 393144
31 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2023-07-07 | 2025-01-06 |  | 9477000 | 8511464 | 5486602
31 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2023-07-07 | 2025-01-06 |  | 589679 | 464384 | 458214
31 | P.S. 56 - STATEN ISLAND | SCA Furniture & Equipment | FY23 RESO A MOBILE STEM CARTS | F&E | In-Progress | 2024-06-22 |  |  | 349502 | 349502 | 5536
31 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2022-02-11 | 2022-06-28 | 2022-10-17 | 142100 | 164681 | 161049
31 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 2022-11-04 | 2023-04-26 | 2023-05-10 | 710500 | 525201 | 458919
31 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 2023-07-10 | 2025-07-08 |  | 15986250 | 14516648 | 3039038
31 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 2023-07-10 | 2025-07-08 |  | 995437 | 484415 | 476945
31 | P.S. 57 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-06-29 | 2022-12-13 | 2022-11-22 | 76804 | 92980 | 82133
31 | P.S. 57 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | Complete | 2023-05-31 | 2024-04-24 | 2024-04-24 | 1126464 | 1095817 | 736179
31 | P.S. 57 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 2023-05-31 | 2024-04-24 | 2024-04-24 | 76804 | 101663 | 100547
31 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-08-09 | 2022-12-27 | 2022-12-01 | 30138 | 53848 | 52728
31 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | Complete | 2023-05-08 | 2024-04-01 | 2024-04-01 | 442023 | 393340 | 373762
31 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 2023-05-08 | 2024-04-01 | 2024-04-01 | 30138 | 40554 | 39766
31 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Design | Complete | 2023-01-11 | 2023-05-26 | 2023-05-11 | 20200 | 36123 | 34784
31 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Construction | In-Progress | 2023-12-08 | 2024-11-01 |  | 296272 | 285001 | 237448
31 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-12-08 | 2024-11-01 |  | 20200 | 33716 | 30889
31 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Design | Complete | 2023-11-30 | 2024-05-28 | 2024-01-31 | 27000 | 14873 | 14873
31 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Construction | In-Progress | 2024-07-25 | 2025-06-19 |  | 396000 | 180296 | 910
31 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | CM,F&E | In-Progress | 2024-07-25 | 2025-06-19 |  | 31264 | 7681 | 7681
31 | P.S. 60 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 2024-03-05 | 2024-07-19 | 2024-08-13 | 8536 | 36325 | 21475
31 | P.S. 60 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | Design | In-Progress | 2024-08-28 | 2025-02-03 |  | 37244 | 37244 | 3944
31 | P.S. 60 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-01-20 | 2022-04-22 | 2022-03-28 | 37248 | 43452 | 43452
31 | P.S. 60 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2022-07-05 | 2023-05-30 |  | 546315 | 520211 | 462862
31 | P.S. 60 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2022-07-05 | 2023-05-30 |  | 37248 | 68706 | 67328
31 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-29 | 2023-10-30 | 2023-10-03 | 11748 | 15871 | 15871
31 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-11 | 2024-03-12 | 2024-02-13 | 52864 | 57168 | 43751
31 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-07-26 | 2025-08-29 |  | 681356 | 623304 | 8387
31 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-07-26 | 2025-08-29 |  | 126286 | 93424 | 17891
31 | I.S. 61 - STATEN ISLAND | SCA CIP | PAVED AREA- BLACKTOP | Scope | Complete | 2024-03-26 | 2024-06-25 | 2024-08-12 | 11567 | 49345 | 35926
31 | I.S. 61 - STATEN ISLAND | SCA CIP | PAVED AREA- BLACKTOP | Design | In-Progress | 2024-08-19 | 2025-01-07 |  | 52051 | 52051 | 8556
31 | I.S. 61 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PAVED AREA- BLACKTOP | Scope | In-Progress | 2024-09-23 | 2024-12-23 |  | 647 | 647 | 0
31 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2021-07-29 | 2021-11-30 | 2021-08-18 | 4477 | 6223 | 6223
31 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-08-18 | 2022-02-16 | 2021-12-29 | 20148 | 24890 | 24890
31 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-12 | 2023-03-07 |  | 259685 | 236074 | 209120
31 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-12 | 2023-03-07 |  | 194121 | 194895 | 194735
31 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2023-02-16 | 2023-07-05 | 2023-11-15 | 31000 | 161758 | 161758
31 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2023-12-05 | 2024-05-07 | 2024-04-17 | 155000 | 252033 | 218756
31 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 2024-09-27 | 2026-06-18 |  | 3487500 | 3194743 | 89743
31 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 2024-09-27 | 2026-06-18 |  | 217000 | 44143 | 44143
31 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Design | In-Progress | 2024-05-09 | 2024-10-10 |  | 30000 | 28504 | 5984
31 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2018-10-09 | 2019-03-14 | 2018-12-21 | 119640 | 118837 | 118837
31 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2019-01-09 | 2019-06-11 | 2019-05-07 | 478560 | 524610 | 491200
31 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2019-07-22 | 2021-07-20 |  | 8973000 | 9555967 | 8470682
31 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2019-07-22 | 2021-07-20 |  | 558320 | 1564403 | 1532103
31 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | Scope | Complete | 2019-02-13 | 2019-07-15 | 2020-02-12 | 92360 | 110022 | 110022
31 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | Design | Complete | 2021-09-09 | 2022-02-14 | 2022-04-15 | 461800 | 329496 | 303084
31 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | Construction | In-Progress | 2022-08-08 | 2024-08-06 |  | 10390500 | 9404325 | 5426403
31 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | CM,F&E | In-Progress | 2022-08-08 | 2024-08-06 |  | 646520 | 650006 | 648737
31 | I.S. 72 - STATEN ISLAND | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 2024-05-24 | 2024-08-26 | 2024-08-28 | 66586 | 58554 | 1930
31 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2022-01-28 | 2022-09-23 | 2023-01-20 | 168263 | 245277 | 237850
31 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | Design | Complete | 2023-01-31 | 2023-07-03 | 2023-09-20 | 836921 | 755045 | 503888
31 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2024-08-19 | 2026-08-18 |  | 18450750 | 19002027 | 1977740
31 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2024-08-19 | 2026-08-18 |  | 1210786 | 569284 | 299553
31 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2021-11-29 | 2022-05-02 | 2022-02-23 | 104190 | 54160 | 54160
31 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2022-02-25 | 2022-07-27 | 2022-05-12 | 520950 | 293710 | 235333
31 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2023-07-12 | 2025-01-01 |  | 11721375 | 10617916 | 6535977
31 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2023-07-12 | 2025-01-01 |  | 729330 | 394965 | 388316
31 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2017-05-24 | 2020-06-09 | 2021-05-26 | 214034 | 453539 | 445514
31 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 2021-06-02 | 2021-10-18 | 2022-02-15 | 1025603 | 1076037 | 888369
31 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2022-08-03 | 2024-08-01 |  | 21352656 | 19259171 | 3566256
31 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2022-08-03 | 2024-08-01 |  | 1567818 | 1018466 | 1009764
31 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | SCA CIP | STEAM PIPE REPLACEMENT | Scope | Complete | 2024-02-23 | 2024-07-25 | 2024-07-25 | 14207 | 1229 | 1229
31 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | SCA CIP | STEAM PIPE REPLACEMENT | Design | In-Progress | 2024-08-06 | 2025-01-09 |  | 63932 | 63932 | 4916
31 | THE RICHMOND PRE-K CENTER | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / PATH OF TRAVEL IDA INTERIOR SPACES | Scope | Complete | 2022-04-08 | 2023-11-16 | 2023-09-14 | 27675 | 45387 | 14403
31 | THE RICHMOND PRE-K CENTER | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / PATH OF TRAVEL IDA INTERIOR SPACES | Design | Complete | 2023-09-27 | 2024-02-02 | 2023-12-15 | 124535 | 97833 | 84883
31 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | Scope | Complete | 2021-04-28 | 2022-01-18 | 2022-04-20 | 26871 | 54728 | 50020
31 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | Design | Complete | 2022-04-20 | 2022-09-01 | 2023-03-06 | 133620 | 193189 | 146252
31 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | Construction | In-Progress | 2023-10-16 | 2025-04-15 |  | 2942927 | 2721039 | 1667622
31 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | CM,F&E | In-Progress | 2023-10-16 | 2025-04-15 |  | 193604 | 34820 | 34579
31 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 2021-03-25 | 2021-08-12 | 2021-08-27 | 1537800 | 987269 | 951682
31 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Design | Complete | 2021-08-30 | 2022-04-25 | 2022-09-02 | 6920100 | 3363484 | 2210198
31 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2023-03-27 | 2025-09-03 |  | 87270150 | 78585908 | 58034694
31 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2023-03-27 | 2025-09-03 |  | 12302400 | 6877331 | 2608472
31 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 2023-03-28 | 2023-09-05 | 2023-09-05 | 1337500 | 928181 | 922484
31 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Design | Complete | 2023-09-06 | 2024-03-29 | 2024-05-06 | 6018750 | 1304649 | 1160187
31 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 2024-08-15 | 2027-09-03 |  | 75903125 | 68274254 | 691333
31 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 2024-08-15 | 2027-09-03 |  | 10700000 | 4223726 | 409347
31 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 2023-03-28 | 2023-03-28 | 2023-03-28 | 23890 | 36871 | 20397
31 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 2023-03-28 | 2023-09-15 | 2023-09-22 | 119450 | 248432 | 196953
31 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | Construction | In-Progress | 2024-04-15 | 2025-04-14 |  | 2687625 | 3075484 | 574333
31 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2024-04-15 | 2025-04-14 |  | 167230 | 229352 | 223568
31 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | In-Progress | 2024-03-19 | 2024-10-10 |  | 3303519 | 3303519 | 979949
31 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 2024-03-19 | 2024-08-01 | 2024-07-25 | 778932 | 993162 | 991791
31 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Design | In-Progress | 2024-07-26 | 2025-02-06 |  | 3635015 | 3635015 | 82203
31 | P.S./I.S. @ 27 LANDIS AVENUE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 2024-03-19 | 2024-10-03 | 2024-09-26 | 1797314 | 1091025 | 546659
31 | P.S./I.S. @ 27 LANDIS AVENUE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Design | In-Progress | 2024-09-27 | 2025-04-17 |  | 7189255 | 7189255 | 45176
31 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | CHAPEL RENOVATION @ 57 CLEVELAND PLACE | Scope | In-Progress | 2024-03-19 | 2024-10-29 |  | 520138 | 520138 | 343622
31 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 2023-07-21 | 2023-07-21 | 2023-07-21 | 94980 | 119788 | 118774
31 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 2023-07-21 | 2023-12-15 | 2024-05-13 | 474900 | 910062 | 22295
31 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Construction | In-Progress | 2024-07-22 | 2025-07-21 |  | 10685250 | 18229066 | 2427472
31 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2024-07-22 | 2025-07-21 |  | 672768 | 612426 | 437609
31 | MAINTENANCE BUILDING @ 12 HASTINGS STREET - STATEN ISLAND | SCA Capacity | NEW MAINTENANCE BUILDING | Scope | In-Progress | 2024-03-19 | 2024-10-10 |  | 74374 | 74374 | 67594
31 | ATHLETIC FIELD @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | ATHLETIC FIELD & FINAL SITEWORK @ 57 CLEVELAND PLACE | Scope | Complete | 2024-03-19 | 2024-08-01 | 2024-07-25 | 361935 | 645706 | 645706
31 | ATHLETIC FIELD @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | ATHLETIC FIELD & FINAL SITEWORK @ 57 CLEVELAND PLACE | Design | In-Progress | 2024-07-26 | 2025-04-17 |  | 1447738 | 1447738 | 4113
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2019-07-19 | 2019-12-05 | 2019-12-23 | 294742 | 400910 | 400910
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2020-01-08 | 2020-06-09 | 2020-06-25 | 1473705 | 1334586 | 1294447
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2021-07-06 | 2024-06-19 |  | 33158366 | 31306720 | 25472629
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2021-07-06 | 2024-06-19 |  | 2063187 | 1216220 | 1164128
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | Scope | Complete | 2021-10-07 | 2022-02-28 | 2022-01-24 | 26467 | 40301 | 40301
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | Design | Complete | 2022-02-02 | 2022-08-04 | 2022-10-05 | 132335 | 129147 | 129147
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | Construction | In-Progress | 2023-05-15 | 2024-05-13 |  | 2977547 | 2944891 | 2555411
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 2023-05-15 | 2024-05-13 |  | 227466 | 245070 | 229642
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | Scope | Complete | 2019-01-11 | 2020-12-04 | 2021-06-04 | 110078 | 107608 | 104122
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | Design | Complete | 2021-06-15 | 2021-11-15 | 2022-02-03 | 543998 | 455218 | 397345
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | Construction | In-Progress | 2022-08-08 | 2024-08-06 |  | 11687077 | 10964361 | 9044898
31 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | CM,F&E | In-Progress | 2022-08-08 | 2024-08-06 |  | 818478 | 479097 | 436292
31 | NEW DORP HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Design | In-Progress | 2023-01-04 | 2023-06-30 |  | 832200 | 510622 | 249612
31 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 2023-09-28 | 2024-02-16 | 2023-12-22 | 16458 | 26659 | 26195
31 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 2024-01-08 | 2024-06-07 | 2024-04-25 | 82291 | 50393 | 16407
31 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-05-12 | 2022-09-12 | 2022-05-31 | 6400 | 5308 | 5308
31 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-05-31 | 2022-11-25 | 2022-08-31 | 28800 | 21229 | 21229
31 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-05-31 | 2024-04-24 |  | 371200 | 324728 | 208803
31 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-05-31 | 2024-04-24 |  | 181284 | 158748 | 102303
31 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Scope | Complete | 2020-08-05 | 2020-12-04 | 2021-03-01 | 85860 | 40881 | 40881
31 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Design | Complete | 2021-03-03 | 2021-08-13 | 2022-01-24 | 429300 | 379259 | 304385
31 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Construction | In-Progress | 2022-06-29 | 2023-12-20 |  | 9659250 | 9390556 | 8701884
31 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | CM,F&E | In-Progress | 2022-06-29 | 2023-12-20 |  | 601020 | 408101 | 365829
31 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | Scope | Complete | 2020-08-26 | 2020-12-24 | 2021-04-27 | 36280 | 108372 | 108372
31 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | Design | Complete | 2021-05-25 | 2021-10-19 | 2021-11-08 | 181400 | 351083 | 308323
31 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | Construction | In-Progress | 2022-04-12 | 2023-08-09 |  | 4081500 | 4337129 | 3481091
31 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 2022-04-12 | 2023-08-09 |  | 253960 | 690785 | 685984
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2022-03-02 | 2022-07-15 | 2023-01-03 | 117350 | 134324 | 134324
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | In-Progress | 2023-01-06 | 2023-06-26 |  | 586752 | 586752 | 212445
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY - PERM FIX FOR RED DOT 131992 / EXTERIOR DOORS | Scope | Complete | 2022-10-20 | 2023-03-10 | 2023-12-01 | 103957 | 153669 | 153669
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY - PERM FIX FOR RED DOT 131992 / EXTERIOR DOORS | Design | In-Progress | 2023-12-12 | 2024-05-14 |  | 516758 | 516758 | 152575
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EMERGENCY GENERATOR | Scope | Complete | 2024-03-27 | 2024-07-29 | 2024-03-27 | 47368 | 26166 | 1035
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EMERGENCY GENERATOR | Design | In-Progress | 2024-03-27 | 2024-08-27 |  | 221052 | 221052 | 4141
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2018-02-27 | 2020-01-06 | 2020-01-03 | 135212 | 242224 | 242224
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2020-01-08 | 2020-06-09 | 2020-06-30 | 667839 | 1490380 | 903375
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 2021-06-14 | 2023-06-13 |  | 14315154 | 13860519 | 12616476
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 2021-06-14 | 2023-06-13 |  | 1008151 | 1119252 | 921404
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | NEW FIELDHOUSE BUILDING | Scope | Complete | 2022-03-02 | 2022-06-30 | 2023-01-03 | 243495 | 210956 | 189753
31 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | NEW FIELDHOUSE BUILDING | Design | Complete | 2023-01-10 | 2023-06-12 | 2024-05-14 | 1217475 | 480161 | 431882
31 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Design | Complete | 2022-01-14 | 2022-06-16 | 2022-05-13 | 280864 | 184490 | 184490
31 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Construction | In-Progress | 2023-07-10 | 2024-07-08 |  | 4119341 | 3821168 | 3521720
31 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | CM,F&E | In-Progress | 2023-07-10 | 2024-07-08 |  | 280864 | 91806 | 91713
31 | CONCORD HS - R | SCA CIP RESOA | FY22 RESO A (MA) CULINARY KITCHEN / PATH OF TRAVEL RESO A (MA) CULINARY KITCHEN | Design | Complete | 2023-01-31 | 2023-05-31 | 2023-02-13 | 240001 | 124809 | 121800
31 | CONCORD HS - R | SCA CIP RESOA | FY22 RESO A (MA) CULINARY KITCHEN / PATH OF TRAVEL RESO A (MA) CULINARY KITCHEN | Construction | In-Progress | 2023-08-07 | 2024-08-05 |  | 3520001 | 2694300 | 892522
31 | CONCORD HS - R | SCA CIP RESOA | FY22 RESO A (MA) CULINARY KITCHEN / PATH OF TRAVEL RESO A (MA) CULINARY KITCHEN | CM,F&E | In-Progress | 2023-08-07 | 2024-08-05 |  | 240001 | 362599 | 362599
31 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2021-07-14 | 2021-11-12 | 2021-07-30 | 3795 | 7388 | 7388
31 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2021-07-30 | 2022-01-28 | 2021-12-29 | 17080 | 29552 | 29552
31 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-05-12 | 2023-03-07 |  | 220137 | 207993 | 183248
31 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-05-12 | 2023-03-07 |  | 223893 | 259327 | 259327
31 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 2022-04-07 | 2022-04-07 | 2022-04-07 | 95738 | 105970 | 101836
31 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 2022-05-13 | 2022-11-15 | 2022-11-14 | 478689 | 220646 | 186084
31 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | Construction | In-Progress | 2023-11-15 | 2024-11-13 |  | 10770495 | 11069717 | 6823879
31 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 2023-11-15 | 2024-11-13 |  | 670164 | 403777 | 392136
31 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | Scope | Complete | 2023-10-02 | 2024-02-13 | 2023-11-09 | 15600 | 20462 | 3702
31 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | Design | Complete | 2023-11-15 | 2024-04-18 | 2024-03-07 | 70200 | 62718 | 14807
31 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | Construction | In-Progress | 2024-07-19 | 2025-07-18 |  | 904800 | 1088892 | 66440
31 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | CM,F&E | In-Progress | 2024-07-19 | 2025-07-18 |  | 167700 | 70604 | 45259
31 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 2022-03-29 | 2022-07-27 | 2022-04-13 | 1600 | 3556 | 3556
31 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 2022-04-13 | 2022-10-06 | 2022-07-20 | 7200 | 14221 | 14221
31 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 2023-03-24 | 2024-02-16 |  | 92800 | 83953 | 70128
31 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 2023-03-24 | 2024-02-16 |  | 122798 | 123439 | 65725
31 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | Scope | Complete | 2019-07-22 | 2019-12-06 | 2019-11-26 | 58970 | 80118 | 80118
31 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | Design | Complete | 2019-11-26 | 2020-04-29 | 2020-06-30 | 294850 | 296017 | 258451
31 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | Construction | In-Progress | 2023-09-13 | 2025-06-03 |  | 6634125 | 6335918 | 3301114
31 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | CM,F&E | In-Progress | 2023-09-13 | 2025-06-03 |  | 413675 | 422543 | 407024
31 | P.S. 74 - STATEN ISLAND | SCA CIP RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | Design | Complete | 2016-05-11 | 2016-09-26 | 2016-09-02 | 32198 | 52114 | 52114
31 | P.S. 74 - STATEN ISLAND | SCA CIP RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2017-04-07 | 2018-01-01 |  | 472237 | 197682 | 197626
31 | P.S. 74 - STATEN ISLAND | SCA CIP RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2017-04-07 | 2018-01-01 |  | 32198 | 59224 | 59224
31 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 2023-03-10 | 2023-06-08 | 2023-07-05 | 16559 | 31734 | 31734
31 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | In-Progress | 2023-07-14 | 2023-11-30 |  | 82794 | 82794 | 34051
31 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-05-11 | 2022-09-09 | 2022-06-07 | 3340 | 4537 | 4537
31 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-06-07 | 2022-12-02 | 2022-08-31 | 15030 | 18145 | 18145
31 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-05-31 | 2024-04-24 |  | 193720 | 175595 | 151918
31 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-05-31 | 2024-04-24 |  | 149421 | 140200 | 90181
31 | P.S. 36 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 2021-03-09 | 2021-07-22 | 2021-11-22 | 53051 | 151396 | 151197
31 | P.S. 36 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2021-11-23 | 2022-04-27 | 2022-04-27 | 249126 | 212957 | 212957
31 | P.S. 36 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | Complete | 2022-07-20 | 2024-07-18 | 2024-06-07 | 4210286 | 4495871 | 4266184
31 | P.S. 36 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | Complete | 2022-07-20 | 2024-07-18 | 2024-06-07 | 492316 | 399692 | 389299
31 | P.S. 861 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2022-02-17 | 2022-07-05 | 2022-05-11 | 21000 | 34494 | 29458
31 | P.S. 861 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 2023-12-01 | 2024-09-25 |  | 308000 | 238597 | 210050
31 | P.S. 861 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 2023-12-01 | 2024-09-25 |  | 21000 | 22927 | 22444
31 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | Scope | Complete | 2019-01-31 | 2019-06-03 | 2022-10-12 | 271750 | 232023 | 231873
31 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | Design | Complete | 2022-10-19 | 2023-03-24 | 2023-09-11 | 1358750 | 1148533 | 658463
31 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | Construction | In-Progress | 2024-07-02 | 2026-07-01 |  | 30571876 | 29075128 | 1370372
31 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | CM,F&E | In-Progress | 2024-07-02 | 2026-07-01 |  | 1902250 | 504754 | 264116
31 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2023-06-29 | 2023-10-30 | 2023-10-10 | 18500 | 15840 | 15840
31 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 2023-10-11 | 2024-03-12 | 2024-02-15 | 83250 | 88601 | 60971
31 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2024-08-14 | 2025-09-17 |  | 1073000 | 1031119 | 51145
31 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2024-08-14 | 2025-09-17 |  | 198875 | 141982 | 22219
31 | P.S. 80 - STATEN ISLAND | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 2023-07-18 | 2023-12-04 | 2023-11-14 | 20629 | 33462 | 33462
31 | P.S. 80 - STATEN ISLAND | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 2023-11-24 | 2024-04-26 | 2024-04-30 | 103147 | 81245 | 71982
31 | R373 SPED - STATEN ISLAND | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2021-03-05 | 2021-07-20 | 2021-07-27 | 43048 | 70663 | 70663
32 | P.S. 45 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2021-04-08 | 2021-08-23 | 2021-10-18 | 139471 | 153301 | 150726
32 | P.S. 45 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2021-10-26 | 2022-04-15 | 2023-08-04 | 697357 | 441136 | 377275
32 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2021-04-09 | 2021-09-09 | 2021-07-01 | 78996 | 81029 | 81029
32 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 2021-07-14 | 2021-12-15 | 2021-11-18 | 394980 | 444548 | 361946
32 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2022-11-07 | 2024-11-05 |  | 8887050 | 8949917 | 6395279
32 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2022-11-07 | 2024-11-05 |  | 554494 | 345127 | 298491
32 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / ROOFTOP EXHAUST FAN REPLACEMENT | Scope | Complete | 2021-05-18 | 2021-10-01 | 2022-08-03 | 136225 | 211448 | 199079
32 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / ROOFTOP EXHAUST FAN REPLACEMENT | Design | Complete | 2022-09-13 | 2023-02-16 | 2023-03-30 | 681124 | 661893 | 391880
32 | P.S. 86 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 2022-07-01 | 2022-11-17 | 2023-02-28 | 59136 | 149264 | 147061
32 | P.S. 86 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2023-03-09 | 2023-08-09 | 2023-08-25 | 292443 | 295387 | 275658
32 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | Design | Complete | 2023-03-03 | 2023-07-06 | 2023-03-20 | 39000 | 44423 | 40052
32 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | Construction | Complete | 2023-07-21 | 2024-06-14 | 2024-09-19 | 572000 | 478092 | 297196
32 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | CM,F&E | Complete | 2023-07-21 | 2024-06-14 | 2024-09-19 | 39000 | 52806 | 41000
32 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Scope | Complete | 2023-06-12 | 2023-10-27 | 2023-11-24 | 123700 | 258084 | 237346
32 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Design | Complete | 2023-12-06 | 2024-05-08 | 2024-05-03 | 618501 | 512748 | 389287
32 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Construction | In-Progress | 2024-09-03 | 2026-09-02 |  | 13916250 | 12738087 | 162336
32 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | CM,F&E | In-Progress | 2024-09-03 | 2026-09-02 |  | 865899 | 178086 | 54782
32 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2023-07-11 | 2023-11-27 | 2023-11-14 | 82281 | 86148 | 86147
32 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2023-11-15 | 2024-04-18 | 2024-04-26 | 408683 | 430144 | 288605
32 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2024-07-17 | 2027-01-02 |  | 8960023 | 8196083 | 54524
32 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2024-07-17 | 2027-01-02 |  | 596373 | 39484 | 36460
32 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | Scope | Complete | 2021-03-26 | 2021-08-10 | 2021-11-02 | 175410 | 167551 | 167551
32 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | Design | Complete | 2021-11-03 | 2022-04-25 | 2022-10-05 | 877050 | 574878 | 463137
32 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | Construction | In-Progress | 2023-09-15 | 2026-03-02 |  | 19733625 | 18131977 | 1826349
32 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | CM,F&E | In-Progress | 2023-09-15 | 2026-03-02 |  | 1229197 | 527020 | 514718
32 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | Scope | Complete | 2021-04-07 | 2021-08-06 | 2021-10-26 | 11796 | 20663 | 20663
32 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | Design | Complete | 2021-11-01 | 2022-03-22 | 2022-03-04 | 58979 | 103360 | 94185
32 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | Construction | In-Progress | 2023-05-15 | 2025-05-03 |  | 1327022 | 1419611 | 1221043
32 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | CM,F&E | In-Progress | 2023-05-15 | 2025-05-03 |  | 82570 | 203713 | 198136
32 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-08-07 | 2023-12-07 | 2023-09-18 | 5000 | 5995 | 5995
32 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-09-18 | 2024-03-18 | 2023-11-15 | 22500 | 23982 | 23982
32 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-04-26 | 2025-03-21 |  | 290000 | 261013 | 2413
32 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-04-26 | 2025-03-21 |  | 53750 | 31608 | 4473
32 | P.S. 145 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Design | In-Progress | 2024-06-18 | 2024-11-20 |  | 15000 | 12643 | 9429
32 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | Scope | Complete | 2019-11-18 | 2020-04-06 | 2020-03-10 | 164682 | 231070 | 230893
32 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | Design | Complete | 2020-03-10 | 2020-08-07 | 2020-05-28 | 814277 | 610416 | 606434
32 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | Construction | In-Progress | 2021-07-19 | 2024-01-04 |  | 17531338 | 16910514 | 15750115
32 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | CM,F&E | In-Progress | 2021-07-19 | 2024-01-04 |  | 1221262 | 965529 | 907240
32 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2023-07-20 | 2023-11-20 | 2023-08-02 | 4700 | 5881 | 5881
32 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2023-08-02 | 2024-01-31 | 2023-11-15 | 21150 | 23528 | 23528
32 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2024-04-26 | 2025-03-21 |  | 272600 | 306123 | 62523
32 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2024-04-26 | 2025-03-21 |  | 50525 | 34669 | 9020
32 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 2020-06-03 | 2020-10-01 | 2020-07-02 | 3266 | 5566 | 5566
32 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2020-07-02 | 2020-12-30 | 2021-05-19 | 14697 | 22267 | 22267
32 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2022-07-15 | 2023-05-10 |  | 189428 | 168881 | 135802
32 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2022-07-15 | 2023-05-10 |  | 174542 | 174762 | 87233
32 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 2023-01-24 | 2023-11-30 | 2023-12-27 | 368600 | 340338 | 339013
32 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 2024-01-12 | 2024-10-03 | 2024-05-14 | 1843001 | 1162576 | 1047120
32 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Construction | In-Progress | 2024-08-05 | 2028-08-03 |  | 41467501 | 37321559 | 120702
32 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | CM,F&E | In-Progress | 2024-08-05 | 2028-08-03 |  | 2580201 | 144594 | 144594
32 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | Scope | Complete | 2020-01-22 | 2022-01-07 | 2021-12-15 | 16909 | 65260 | 65180
32 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | Design | Complete | 2021-12-16 | 2022-04-19 | 2022-03-18 | 76093 | 121835 | 93219
32 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | Construction | In-Progress | 2022-07-05 | 2023-07-04 |  | 980757 | 2269407 | 1655795
32 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | CM,F&E | In-Progress | 2022-07-05 | 2023-07-04 |  | 181778 | 351328 | 349636
32 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 2021-10-08 | 2022-11-10 | 2023-01-25 | 72818 | 112986 | 112986
32 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 2023-01-26 | 2023-05-25 | 2023-06-09 | 362617 | 379859 | 297204
32 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Construction | In-Progress | 2024-07-08 | 2026-07-07 |  | 8031738 | 7465269 | 143407
32 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | CM,F&E | In-Progress | 2024-07-08 | 2026-07-07 |  | 520744 | 69785 | 64020
32 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Scope | Complete | 2021-04-05 | 2021-08-18 | 2021-08-13 | 133519 | 131528 | 131528
32 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Design | Complete | 2021-09-15 | 2022-03-08 | 2022-09-08 | 661849 | 558615 | 433530
32 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Construction | In-Progress | 2024-02-21 | 2026-08-08 |  | 14394248 | 13080747 | 634884
32 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2024-02-21 | 2026-08-08 |  | 977759 | 149820 | 143819
32 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2022-06-03 | 2022-10-03 | 2022-09-01 | 3560 | 2717 | 2717
32 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2022-09-01 | 2023-03-03 | 2023-03-02 | 16020 | 10869 | 10869
32 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-27 | 2024-08-21 |  | 206480 | 191034 | 109104
32 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-27 | 2024-08-21 |  | 113860 | 106211 | 84840
32 | P.S. 384 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 2019-03-05 | 2019-07-05 | 2022-01-26 | 118641 | 2659 | 2659
32 | P.S. 384 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / FLOOD ELIMINATION / PARAPETS | Design | Complete | 2022-12-29 | 2023-07-05 | 2023-12-13 | 568100 | 165095 | 99747
32 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | Scope | Complete | 2015-08-10 | 2015-12-28 | 2016-03-28 | 103442 | 91741 | 91741
32 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | Design | Complete | 2016-06-24 | 2016-11-28 | 2017-02-07 | 404279 | 645179 | 616941
32 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | Construction | In-Progress | 2018-05-21 | 2019-11-11 |  | 6728865 | 7113181 | 6676004
32 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | CM,F&E | In-Progress | 2018-05-21 | 2019-11-11 |  | 606049 | 1386670 | 1380492
32 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | Scope | Complete | 2013-06-18 | 2013-12-02 | 2013-11-18 | 130880 | 130183 | 130183
32 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | Design | Complete | 2013-11-19 | 2014-05-22 | 2020-05-14 | 654400 | 1869689 | 1622287
32 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | Construction | In-Progress | 2022-07-11 | 2024-07-09 |  | 14724000 | 18504982 | 17189488
32 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | CM,F&E | In-Progress | 2022-07-11 | 2024-07-09 |  | 1037749 | 1521338 | 1482274
32 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2023-03-10 | 2023-07-25 | 2023-03-15 | 4720 | 2062 | 2062
32 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2023-03-15 | 2023-09-08 | 2023-05-02 | 21240 | 8247 | 8247
32 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2023-09-27 | 2024-08-21 |  | 273760 | 246203 | 154618
32 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2023-09-27 | 2024-08-21 |  | 113730 | 93210 | 89099
32 | BETHESDA DAY CARE CENTER OF BROOKLYN | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 2021-04-08 | 2021-08-09 | 2021-07-19 | 2522 | 13929 | 13929
32 | BETHESDA DAY CARE CENTER OF BROOKLYN | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | In-Progress | 2022-05-03 | 2022-10-03 |  | 11349 | 19225 | 1108
32 | 200 CENTRAL AVENUE DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 2021-04-12 | 2021-08-11 | 2021-07-19 | 4950 | 15471 | 15471
32 | 200 CENTRAL AVENUE DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Design | Complete | 2022-01-03 | 2022-05-03 | 2023-01-06 | 22277 | 29044 | 7574