## Sheet1
Project Geographic District | Project Building Identifier | Project School Name | Project Type | Project Description | Project Phase Name | Project Status Name | Project Phase Actual Start Date | Project Phase Planned End Date | Project Phase Actual End Date | Project Budget Amount | Final Estimate of Actual Costs Through End of Phase Amount | Total Phase Actual Spending Amount | DSF Number(s)
1 | M015 | P.S. 15 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE THE FLOOR IN THE FOLLOWING ROOMS: 202, 208, 210, 212, 315, 402, 406, 408, 50 | Construction | Complete | 7/19/2024 | IEH | 10/9/2024 | IEH | 0 | 0 | SCA0000073155
1 | M015 | P.S. 15 - MANHATTAN | SCA IEH | PO18-/ABATEMENT OF PIPE INSULATION RM 219 PIPE INSULATION IS PAINTED ORANGE, TOTAL OF APPROXIMATELY | Construction | Complete | 9/17/2024 | IEH | 9/29/2024 | IEH | 0 | 0 | SCA0000073384
1 | M015 | P.S. 15 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 6/28/2024 | DOER |  | DOER | 206654 | 0 | DSF0001086173
1 | M015 | P.S. 15 - MANHATTAN | DOE - Skilled Trades | SCHOOLYARD RESURFACING | Construction | In-Progress | 2/19/2024 | DOES |  | DOES | 814540 | 0 | DSF0001017369
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 4/13/2021 | 9/13/2021 | 7/1/2021 | 68660 | 74771 | 74771 | DSF0001008800, DSF0000991942
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/6/2021 | 12/7/2021 | 11/29/2021 | 343300 | 378273 | 316860 | DSF0001008800, DSF0000991942
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/18/2022 | 7/16/2024 |  | 7724250 | 7131032 | 5575856 | DSF0001008800, DSF0000991942
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/18/2022 | 7/16/2024 |  | 480620 | 193553 | 193338 | DSF0001008800, DSF0000991942
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/22/2023 | 10/23/2023 | 7/6/2023 | 4240 | 1703 | 1703 | DSF0001035045
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/6/2023 | 1/3/2024 | 12/13/2023 | 19080 | 6814 | 6814 | DSF0001035045
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/27/2024 | 5/26/2025 |  | 245920 | 224898 | 4666 | DSF0001035045
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/27/2024 | 5/26/2025 |  | 49844 | 32189 | 18574 | DSF0001035045
1 | M019 | P.S. 19 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/23/2024 | DOER |  | DOER | 141466 | 0 | DSF0001035064
1 | M019 | P.S. 315 - MANHATTAN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0 | DSF0001086175
1 | M020 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 5/26/2021 | 10/12/2021 | 1/21/2022 | 124674 | 160771 | 160771 | DSF0000991960, DSF0000991962, DSF0001017426, DSF0001017414, DSF0001017413
1 | M020 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | Design | Complete | 1/21/2022 | 6/22/2022 | 5/10/2022 | 613841 | 521743 | 513615 | DSF0000991960, DSF0000991962, DSF0001017426, DSF0001017414, DSF0001017413
1 | M020 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 9/19/2022 | 6/9/2024 |  | 12987707 | 12196322 | 11928701 | DSF0000991960, DSF0000991962, DSF0001017426, DSF0001017414, DSF0001017413
1 | M020 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 9/19/2022 | 6/9/2024 |  | 944133 | 344598 | 315667 | DSF0000991960, DSF0000991962, DSF0001017426, DSF0001017414, DSF0001017413
1 | M020 | P.S. 20 - MANHATTAN | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 12/27/2024 | FTK |  | FTK | 2244 | 2244 | DSF0001087468
1 | M020 | P.S. 20 - MANHATTAN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | Complete | 3/22/2019 | DOER | 4/13/2020 | DOER | 162518 | 162518 | DSF0000890659
1 | M020 | P.S. 20 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/7/2021 | DOES |  | DOES | 195021 | 0 | DSF0001008690
1 | M022 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 4/22/2021 | 9/7/2021 | 12/21/2021 | 195550 | 193921 | 191326 | DSF0000961144, DSF0001017428
1 | M022 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/22/2021 | 6/10/2022 | 9/16/2022 | 977750 | 609823 | 463743 | DSF0000961144, DSF0001017428
1 | M022 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 8/7/2023 | 8/5/2025 |  | 21999375 | 21250021 | 10387633 | DSF0000961144, DSF0001017428
1 | M022 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 8/7/2023 | 8/5/2025 |  | 1377802 | 312458 | 243506 | DSF0000961144, DSF0001017428
1 | M022 | NEW EXPLORATIONS - M | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 3/5/2024 | 6/3/2024 |  | 0 | 7108 | 1343 | DSF0001086176
1 | M022 | NEW EXPLORATIONS - M | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 6000 | 5372 | 5372 | DSF0001086176
1 | M022 | NEW EXPLORATIONS - M | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 1128 | DSF0001086176
1 | M022 | NEW EXPLORATIONS - M | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 4181 | DSF0001086176
1 | M022 | NEW EXPLORATIONS - M | Fast Track Projects | LSP- VACUUM PUMPS REPLACEMENTS | Construction | In-Progress | 2/8/2024 | FTK |  | FTK | 186188 | 130500 | DSF0001068167
1 | M022 | NEW EXPLORATIONS - M | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0 | DSF0001033717
1 | M022 | NEW EXPLORATIONS - M | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/6/2021 | DOER |  | DOER | 80736 | 0 | DSF0000961298
1 | M022 | NEW EXPLORATIONS - M | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 8/16/2022 | DOER | 4/11/2023 | DOER | 189971 | 921 | DSF0001033234
1 | M022 | NEW EXPLORATIONS - M | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 265000 | 0 | DSF0001112760
1 | M022 | NEW EXPLORATIONS - M | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0001035621
1 | M022 | NEW EXPLORATIONS - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/12/2024 | DOES | 9/6/2024 | DOES | 65832 |  | DSF0001084938
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | Scope | Complete | 10/23/2018 | 3/13/2019 | 1/24/2020 | 118770 | 254421 | 253613 | DSF0000874992, DSF0000874993, DSF0000943293, DSF0000943295
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | Design | Complete | 1/24/2020 | 6/24/2020 | 5/5/2021 | 586080 | 583102 | 537959 | DSF0000874992, DSF0000874993, DSF0000943293, DSF0000943295
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | Construction | Complete | 8/13/2021 | 8/11/2024 | 8/14/2024 | 12514695 | 12852770 | 11782160 | DSF0000874992, DSF0000874993, DSF0000943293, DSF0000943295
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | CM,F&E | Complete | 8/13/2021 | 8/11/2024 | 8/14/2024 | 889665 | 1572480 | 1525727 | DSF0000874992, DSF0000874993, DSF0000943293, DSF0000943295
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/25/2020 | 10/26/2020 | 7/21/2020 | 3482 | 4450 | 4450 | DSF0000960787
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/21/2020 | 1/15/2021 | 3/30/2021 | 15667 | 17800 | 17800 | DSF0000960787
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/24/2022 | 3/19/2023 |  | 201929 | 188076 | 169532 | DSF0000960787
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/24/2022 | 3/19/2023 |  | 234839 | 263751 | 258409 | DSF0000960787
1 | M025 | I.S. 378 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | Complete | 2/1/2019 | EMER | 6/5/2024 | EMER | 523752 | 519082 | SCA0000056151
1 | M025 | LOWER EAST SIDE PREP HS - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/22/2024 | DOES | 8/9/2024 | DOES | 65832 | 12546 | DSF0001084778
1 | M025 | I.S. 378 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/22/2024 | DOES |  | DOES | 593902 | 0 | DSF0001085731
1 | M034 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | Scope | Complete | 10/19/2018 | 12/30/2019 | 3/31/2020 | 294023 | 349176 | 323187 | DSF0000992072, DSF0000897945, DSF0000897946, DSF0000897947, DSF0000943350, DSF0000960885, DSF0000960884, DSF0001008630, DSF0000992069, DSF0001034277
1 | M034 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | Design | Complete | 12/7/2020 | 5/10/2021 | 5/18/2021 | 1450039 | 1194364 | 1055994 | DSF0000992072, DSF0000897945, DSF0000897946, DSF0000897947, DSF0000943350, DSF0000960885, DSF0000960884, DSF0001008630, DSF0000992069, DSF0001034277
1 | M034 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | Construction | Complete | 7/5/2022 | 12/20/2024 | 9/30/2024 | 31392155 | 29244704 | 28353608 | DSF0000992072, DSF0000897945, DSF0000897946, DSF0000897947, DSF0000943350, DSF0000960885, DSF0000960884, DSF0001008630, DSF0000992069, DSF0001034277
1 | M034 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | CM,F&E | Complete | 7/5/2022 | 12/20/2024 | 9/30/2024 | 2211023 | 686339 | 636127 | DSF0000992072, DSF0000897945, DSF0000897946, DSF0000897947, DSF0000943350, DSF0000960885, DSF0000960884, DSF0001008630, DSF0000992069, DSF0001034277
1 | M034 | P.S. 34 - MANHATTAN | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 140000 | 140000 | 0 | DSF0000913873
1 | M034 | P.S. 34 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001007798
1 | M034 | P.S. 34 - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 12/1/2022 | DOER |  | DOER | 34574 | 0 | DSF0001007800
1 | M034 | P.S. 34 - MANHATTAN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 3/15/2024 | DOER |  | DOER | 103169 | 0 | DSF0001035626
1 | M034 | P.S. 34 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/25/2022 | DOES |  | DOES | 92365 | 0 | DSF0001008949
1 | M034 | P.S. 34 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/6/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084623
1 | M056 | J.H.S. 292 - MANHATTAN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 4/30/2021 | 7/30/2021 | 7/22/2021 | 27380 | 43074 | 43074 | DSF0000992308
1 | M056 | J.H.S. 292 - MANHATTAN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 8/2/2021 | 2/7/2022 | 2/1/2022 | 136900 | 172065 | 162459 | DSF0000992308
1 | M056 | J.H.S. 292 - MANHATTAN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | PNS | PNS | PNS | PNS | 3080255 | 3080255 | 104497 | DSF0000992308
1 | M056 | J.H.S. 292 - MANHATTAN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 191660 | 191660 | 23938 | DSF0000992308
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 51 | 51 | DSF0001035639
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 92049 | 91998 | 202 | DSF0001035639
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1350049 | 1687561 | 0 | DSF0001035639
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 92049 | 115061 | 344 | DSF0001035639
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035640
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035640
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035640
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035640
1 | M056 | J.H.S. 292 - MANHATTAN | SCA IEH | PO18-WE ARE GOING TO NEED AN ABATEMENT AT M056. THE LOCATIONS ARE RMS. 313 AND 213 AND IT'S APPROXIM | Construction | In-Progress | 4/12/2024 | IEH |  | IEH | 0 | 0 | SCA0000072923
1 | M056 | J.H.S. 292 - MANHATTAN | SCA IEH | PO18-HAVE THE GYM FLOOR CORE DRILLED AND TEST FOR ASBESTOS PRINCIPAL WOULD LIKE 2 HOLES MADE TO SUPP | Construction | Complete | 7/29/2024 | IEH | 9/4/2024 | IEH | 0 | 0 | SCA0000073193
1 | M056 | J.H.S. 292 - MANHATTAN | SCA IEH | PO18-IN BASEMENT MECHANICAL ROOM CELLAR: FAN ROOM# C25 (1025) - AUDITORIUM BLOWER CELLAR: FAN ROOM ( | Construction | Complete | 8/23/2024 | IEH | 8/25/2024 | IEH | 0 | 0 | SCA0000073370
1 | M056 | J.H.S. 292 - MANHATTAN | SCA IEH | PO18-TEST AND ABATE GYM CEILING DRAIN LINE THAT IS LEAKING WE HAVE EARLY VOTING IN THE GYM COMING U | Construction | Complete | 9/19/2024 | IEH | 9/21/2024 | IEH | 0 | 0 | SCA0000073398
1 | M056 | J.H.S. 292 - MANHATTAN | SCA IEH | PO18-ABATEMENT OF PIPE INSULATION 3RD FL SLOP SINK CRAWL SPACE SPACE ID : 4313A ( PIPE CHASE) IT IS | Construction | Complete | 10/22/2024 | IEH | 11/10/2024 | IEH | 0 | 0 | SCA0000073527
1 | M056 | J.H.S. 292 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0 | DSF0000913568
1 | M056 | J.H.S. 292 - MANHATTAN | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 120291 | 0 | DSF0000913081
1 | M056 | J.H.S. 292 - MANHATTAN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 8669 | 0 | DSF0001007786
1 | M056 | J.H.S. 292 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/3/2024 | DOES | 12/16/2024 | DOES | 65832 |  | DSF0001084783
1 | M056 | I.S. 332 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/8/2024 | DOES |  | DOES | 574909 | 0 | DSF0001085733
1 | M056 | MANHATTAN CHARTER SCHOOL II | Trust For Public Land | TPL- EXTREME WEATHER PLAYGROUND UPGRADE | Construction | Complete | 2/10/2024 | TPL | 10/26/2024 | TPL | 2775498 | 2385830 | DSF0001034698
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 5/16/2022 | 9/16/2022 | 8/2/2022 | 53927 | 79069 | 79069 | DSF0001083923, DSF0001017824
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 8/8/2022 | 2/13/2023 | 5/8/2023 | 259893 | 204680 | 187734 | DSF0001083923, DSF0001017824
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 5005043 | 5005043 | 590322 | DSF0001083923, DSF0001017824
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 450541 | 450541 | 94567 | DSF0001083923, DSF0001017824
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 3/14/2024 | 7/30/2024 | 11/18/2024 | 64763 | 93999 | 22859 | DSF0001111940, DSF0001124017, DSF0001124021
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | PNS | PNS | PNS | PNS | 304809 | 304809 | 5890 | DSF0001111940, DSF0001124017, DSF0001124021
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 5700807 | 5700807 | 1787 | DSF0001111940, DSF0001124017, DSF0001124021
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 540475 | 540475 | 17587 | DSF0001111940, DSF0001124017, DSF0001124021
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION 2ND FLOOR HALLWAY BETWEEN ROOMS 206 AND 208 WE ARE GOING TO NEED | Construction | In-Progress | 9/3/2024 | IEH |  | IEH | 0 | 0 | SCA0000073343
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA IEH | PO18-ABATEMENT OF CEILING PLASTER IN THE BASEMENT IN FRONT OF AUDITORIUM DOORS AHERA BOOK 2006 - SPA | Construction | Complete | 9/4/2024 | IEH | 9/4/2024 | IEH | 0 | 0 | SCA0000073350
1 | M060 | EAST SIDE COMMUNITY SCHOOL | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 11/3/2020 | FTK |  | FTK | 207210 | 190289 | DSF0000961040
1 | M060 | EAST SIDE COMMUNITY SCHOOL | Fast Track Projects | ROOF | Construction | In-Progress | 5/16/2019 | FTK |  | FTK | 1719207 | 1630567 | DSF0000912294
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/31/2022 | DOER |  | DOER | 38764 | 0 | DSF0000961294
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 2623911 | 0 | DSF0001035641
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 174000 | 0 | DSF0001112773
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112774
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 6/5/2023 | DOES | 10/23/2023 | DOES | 60921 |  | DSF0000866117
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/14/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084941
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/1/2024 | DOES |  | DOES | 444473 | 0 | DSF0001085734
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | Scope | Complete | 4/9/2019 | 8/22/2019 | 9/20/2019 | 22622 | 12127 | 12127 | DSF0000898235
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | Design | Complete | 10/23/2019 | 3/27/2020 | 6/8/2020 | 113110 | 130382 | 116041 | DSF0000898235
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | Construction | In-Progress | 10/18/2021 | 4/10/2023 |  | 2544967 | 2361261 | 2024565 | DSF0000898235
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | CM,F&E | In-Progress | 10/18/2021 | 4/10/2023 |  | 158354 | 635954 | 553755 | DSF0000898235
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 5/14/2024 | 9/30/2024 | 10/31/2024 | 96886 | 102296 | 89670 | DSF0001111902, DSF0001124039, DSF0001124041
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | In-Progress | 11/15/2024 | 4/21/2025 |  | 452136 | 452136 | 17858 | DSF0001111902, DSF0001124039, DSF0001124041
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 7169580 | 7169580 | 38069 | DSF0001111902, DSF0001124039, DSF0001124041
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 710499 | 710499 | 21040 | DSF0001111902, DSF0001124039, DSF0001124041
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/7/2022 | 11/4/2022 | 7/27/2022 | 3838 | 2363 | 2363 | DSF0001034584
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/27/2022 | 1/25/2023 | 9/21/2022 | 17271 | 9450 | 9450 | DSF0001034584
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/5/2023 | 4/29/2024 |  | 222607 | 204544 | 177952 | DSF0001034584
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/5/2023 | 4/29/2024 |  | 117815 | 107139 | 75331 | DSF0001034584
1 | M061 | P.S. 361 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION OVER THE AUDITORIUM ENTRY DOORS LOCATED IN THE 1ST FLOOR THE INS | Construction | In-Progress | 7/24/2024 | IEH |  | IEH | 0 | 0 | SCA0000073170
1 | M061 | P.S. 361 - MANHATTAN | SCA IEH | PO18-ABATE WALL PLASTER IN ROOM 306 APPROX. 50 SQFT. | Construction | Complete | 10/22/2024 | IEH | 12/17/2024 | IEH | 0 | 0 | SCA0000073526
1 | M061 | P.S. 361 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112775
1 | M061 | P.S. 361 - MANHATTAN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 7/29/2022 | DOER | 4/11/2023 | DOER | 219727 |  | DSF0001033207
1 | M061 | P.S. 361 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086194
1 | M061 | P.S. 315 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/31/2022 | DOES |  | DOES | 72044 | 0 | DSF0001008951
1 | M063 | P.S. 63 - MANHATTAN | SCA IEH | PO18-ABATEMENT OF PIPE INSULATION 1ST FL GIRL BATHROOM AREAS ARE MARKED AND IT IS ABOUT 40 BY 45 LIN | Construction | Complete | 10/8/2024 | IEH | 10/19/2024 | IEH | 0 | 0 | SCA0000073479
1 | M063 | P.S. 363 - MANHATTAN | Fast Track Projects | LSP FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/29/2023 | FTK |  | FTK | 108253 | 90475 | DSF0001035647
1 | M063 | P.S. 63 - MANHATTAN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/7/2022 | DOER |  | DOER | 202779 | 0 | DSF0001033635
1 | M063 | P.S. 363 - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 3/15/2024 | DOER | 6/18/2024 | DOER | 201403 |  | DSF0001035646
1 | M063 | P.S. 63 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112776
1 | M063 | P.S. 363 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 7/27/2022 | DOES |  | DOES | 94774 | 0 | DSF0001009098
1 | M063 | P.S. 63 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/24/2023 | DOES | 11/26/2024 | DOES | 65832 |  | DSF0001084198
1 | M064 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/20/2019 | 11/5/2019 | 12/23/2019 | 111561 | 221344 | 217281 | DSF0000898265, DSF0000898268, DSF0000898269, DSF0000898270
1 | M064 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/8/2020 | 6/9/2020 | 6/30/2020 | 551747 | 734661 | 664523 | DSF0000898265, DSF0000898268, DSF0000898269, DSF0000898270
1 | M064 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 5/24/2021 | 5/23/2023 |  | 11889967 | 11828583 | 10023823 | DSF0000898265, DSF0000898268, DSF0000898269, DSF0000898270
1 | M064 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 5/24/2021 | 5/23/2023 |  | 826395 | 1320514 | 1282146 | DSF0000898265, DSF0000898268, DSF0000898269, DSF0000898270
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/2/2019 | 3/4/2020 | 2/11/2020 | 0 | 27695 | 27695 | DSF0000913307
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 2/11/2020 | 6/25/2020 | 1/2/2024 | 74829 | 139951 | 78818 | DSF0000913307
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1097491 | 1097491 | 24575 | DSF0000913307
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 74829 | 74829 | 25677 | DSF0000913307
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 3/18/2020 | 6/17/2020 | 12/4/2020 | 0 | 18840 | 18840 | DSF0000913306
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 12/4/2020 | 5/24/2021 | 1/2/2024 | 2354 | 22197 | 15280 | DSF0000913306
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 34522 | 34522 | 0 | DSF0000913306
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 2354 | 2648 | 2648 | DSF0000913306
1 | M064 | I.S. 839 - MANHATTAN | SCA IEH | PO18-REMOVE AND REPLACE 9X9 ACM TILES IN 1ST AND 2ND FLOORS SQFT FOR 1ST FLOOR IS 510 2ND FLOOR | Construction | Complete | 5/29/2024 | IEH | 7/2/2024 | IEH | 0 | 0 | SCA0000073035
1 | M064 | I.S. 839 - MANHATTAN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | In-Progress | 3/8/2024 | DOER |  | DOER | 168677 | 0 | DSF0001086195
1 | M064 | I.S. 839 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112777
1 | M064 | P.S. 64 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 6/5/2023 | DOES | 11/21/2023 | DOES | 62522 |  | DSF0000866118
1 | M064 | I.S. 839 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/25/2024 | DOES | 9/9/2024 | DOES | 65832 | 10141 | DSF0001084199
1 | M097 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 1/7/2021 | 5/7/2021 | 6/15/2021 | 39541 | 51009 | 50970 | DSF0000943937, DSF0000992663, DSF0000992664
1 | M097 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | Design | Complete | 7/15/2021 | 12/16/2021 | 4/21/2022 | 186049 | 146528 | 121192 | DSF0000943937, DSF0000992663, DSF0000992664
1 | M097 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 1/15/2024 | 1/3/2026 |  | 3178051 | 2811396 | 196226 | DSF0000943937, DSF0000992663, DSF0000992664
1 | M097 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 1/15/2024 | 1/3/2026 |  | 364189 | 71144 | 71144 | DSF0000943937, DSF0000992663, DSF0000992664
1 | M097 | BARD COLLEGE HS - MANHATTAN | SCA IEH | PO18-ABATE INSUL PIPE RM 221 GIRL B/R, WILL BE MARK BY SHOPS (LESS 10 FT.) | Construction | Complete | 11/29/2024 | IEH | 12/7/2024 | IEH | 0 | 0 | SCA0000073655
1 | M097 | BARD COLLEGE HS - MANHATTAN | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/10/2019 | FTK |  | FTK | 54508 | 54508 | DSF0000866416
1 | M097 | BARD COLLEGE HS - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000961304
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 223957 | 0 | DSF0000913084
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001112793
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - Skilled Trades | DOMESTIC WATER HEATER | Construction | In-Progress | 3/1/2022 | DOES |  | DOES | 90361 | 376 | DSF0000961169
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - Skilled Trades | SCHOOLYARD RESURFACING | Construction | In-Progress | 8/14/2023 | DOES |  | DOES | 567979 | 0 | DSF0001034279
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/31/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084945
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/26/2024 | DOES |  | DOES | 197896 | 0 | DSF0001085735
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP | FACADE REMEDIATION @M110 / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 8/4/2021 | 12/21/2021 | 2/2/2022 | 75912 | 195932 | 177643 | DSF0001085128, DSF0001018329, DSF0001018328, DSF0001018326
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP | FACADE REMEDIATION @M110 / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 6/1/2022 | 11/22/2022 | 5/12/2023 | 369667 | 313370 | 290581 | DSF0001085128, DSF0001018329, DSF0001018328, DSF0001018326
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP | FACADE REMEDIATION @M110 / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 7461767 | 7461767 | 280165 | DSF0001085128, DSF0001018329, DSF0001018328, DSF0001018326
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP | FACADE REMEDIATION @M110 / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 605580 | 605580 | 27296 | DSF0001085128, DSF0001018329, DSF0001018328, DSF0001018326
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112055
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112055
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 733 | 733 | DSF0001112055
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 2603 | 2603 | DSF0001112055
1 | M110 | P.S. 110 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/18/2021 | EMER |  | EMER | 1353134 | 898752 | SCA0000069969
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-ACM TEST FOR WALL TO INSTALL BOTTLE FILLERS 2 LOCATIONS GYMNASIUM / BUBBLER / M11001GM000GYM.1B | Construction | Complete | 4/12/2024 | IEH | 7/13/2024 | IEH | 0 | 0 | SCA0000072925
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-2 AREAS IN GYMNASIUM NEEDS TO BE ABATED ONE AREA IS THE GYMNASIUM PHONE THAT FELL FROM THE WALL | Construction | In-Progress | 7/30/2024 | IEH |  | IEH | 0 | 0 | SCA0000073197
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-CORE DRILLING HOLES FOR ELECTRICAL CONDUITS IN THE GYM | Construction | Complete | 8/23/2024 | IEH | 8/30/2024 | IEH | 0 | 0 | SCA0000073313
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-/ABATE CEILING AND PIPE INSULATION IN CAFE & KITCHEN (KITCHEN 2002) (CAFETERIA 2001) LOCATED ON | Construction | Complete | 10/18/2024 | IEH | 10/20/2024 | IEH | 0 | 0 | SCA0000073534
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-ABATE CEILING PLASTER IN STORAGE ROOM 408A THAT FELL | Construction | Complete | 11/14/2024 | IEH | 11/23/2024 | IEH | 0 | 0 | SCA0000073607
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-ABATE CEILING PLASTER IN THE AUDITORIUM IT IS 1SQ FT PLASTER THAT FELL AHERA BOOK 2014- POSITV | Construction | Complete | 12/12/2024 | IEH | 12/14/2024 | IEH | 0 | 0 | SCA0000073706
1 | M110 | P.S. 110 - MANHATTAN | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 809267 | 0 | DSF0001035663
1 | M134 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 10/23/2018 | 3/13/2019 | 1/18/2019 | 371656 | 171344 | 171344 | DSF0000876062, DSF0000876063, DSF0000876064, DSF0000876065
1 | M134 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/22/2019 | 6/21/2019 | 5/17/2019 | 1486620 | 808561 | 771823 | DSF0000876062, DSF0000876063, DSF0000876064, DSF0000876065
1 | M134 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 10/21/2019 | 8/15/2022 |  | 27874124 | 26674648 | 22942090 | DSF0000876062, DSF0000876063, DSF0000876064, DSF0000876065
1 | M134 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 10/21/2019 | 8/15/2022 |  | 1734390 | 807276 | 772020 | DSF0000876062, DSF0000876063, DSF0000876064, DSF0000876065
1 | M134 | P.S. 134 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033658
1 | M134 | P.S. 134 - MANHATTAN | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001111926
1 | M134 | P.S. 134 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0000913319
1 | M134 | P.S. 134 - MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 1/18/2022 | DOES |  | DOES | 391092 | 0 | DSF0000911918
1 | M134 | P.S. 134 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/19/2022 | DOES |  | DOES | 77253 | 0 | DSF0001009093
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Scope | Complete | 1/24/2018 | 1/20/2021 | 5/19/2021 | 15710 | 29800 | 29800 | DSF0000866352, DSF0000961102, DSF0001018706
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Design | Complete | 7/7/2021 | 12/10/2021 | 3/3/2022 | 62520 | 104539 | 75761 | DSF0000866352, DSF0000961102, DSF0001018706
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Construction | In-Progress | 5/17/2023 | 5/15/2024 |  | 723155 | 729635 | 619551 | DSF0000866352, DSF0000961102, DSF0001018706
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 5/17/2023 | 5/15/2024 |  | 151715 | 129284 | 117191 | DSF0000866352, DSF0000961102, DSF0001018706
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/11/2022 | 11/8/2022 | 7/28/2022 | 5326 | 2660 | 2660 | DSF0001034607
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/28/2022 | 1/26/2023 | 9/21/2022 | 23966 | 10640 | 10640 | DSF0001034607
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/5/2023 | 4/29/2024 |  | 308893 | 280585 | 251656 | DSF0001034607
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/5/2023 | 4/29/2024 |  | 165385 | 142402 | 110594 | DSF0001034607
1 | M137 | P.S. 184 - MANHATTAN | DOE - RESOA | FY15 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0000800504
1 | M137 | P.S. 184 - MANHATTAN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/6/2022 | DOER |  | DOER | 97723 | 0 | DSF0000913320
1 | M137 | P.S. 184 - MANHATTAN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 128263 | 0 | DSF0000786134
1 | M137 | P.S. 184 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/25/2024 | DOES | 12/9/2024 | DOES | 65832 |  | DSF0001084636
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/24/2018 | 3/14/2019 | 1/18/2019 | 504775 | 552699 | 508563 | DSF0000876119, DSF0000876120, DSF0000876121, DSF0000912290, DSF0001034291, DSF0001018730, DSF0001018731, DSF0001034290, DSF0001034288, DSF0001018723
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 1/22/2019 | 6/21/2019 | 9/16/2022 | 2518835 | 2379488 | 1902809 | DSF0000876119, DSF0000876120, DSF0000876121, DSF0000912290, DSF0001034291, DSF0001018730, DSF0001018731, DSF0001034290, DSF0001034288, DSF0001018723
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 6/5/2023 | 6/3/2026 |  | 56237200 | 51049208 | 5963118 | DSF0000876119, DSF0000876120, DSF0000876121, DSF0000912290, DSF0001034291, DSF0001018730, DSF0001018731, DSF0001034290, DSF0001034288, DSF0001018723
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 6/5/2023 | 6/3/2026 |  | 3571289 | 1237989 | 1230226 | DSF0000876119, DSF0000876120, DSF0000876121, DSF0000912290, DSF0001034291, DSF0001018730, DSF0001018731, DSF0001034290, DSF0001034288, DSF0001018723
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/6/2022 | 11/3/2022 | 7/22/2022 | 4336 | 4223 | 4223 | DSF0001034595
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/22/2022 | 1/20/2023 | 9/21/2022 | 19513 | 17729 | 17729 | DSF0001034595
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/5/2023 | 4/29/2024 |  | 251500 | 237972 | 215181 | DSF0001034595
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/5/2023 | 4/29/2024 |  | 149910 | 139865 | 108057 | DSF0001034595
1 | M140 | P.S. 140 - MANHATTAN | SCA IEH | PO18-ABATE RISER VALVE LOCATED IN B6 - STORAGE ROOM, APPROX 15 FT OF PIPING VALVE IS SPRAY PAINED | Construction | Complete | 10/12/2024 | IEH | 10/13/2024 | IEH | 0 | 0 | SCA0000073504
1 | M140 | P.S. 140 - MANHATTAN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 73000 | 73000 | 0 | DSF0001086230
1 | M140 | P.S. 140 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000961347
1 | M140 | P.S. 140 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 9/22/2022 | DOES | 11/17/2022 | DOES | 81461 | 80366 | DSF0001009096
1 | M142 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/22/2020 | 11/19/2020 | 8/19/2020 | 86400 | 154847 | 154847 | DSF0000944456, DSF0000944457, DSF0000944458
1 | M142 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/1/2020 | 6/15/2021 | 4/6/2021 | 432000 | 373465 | 359154 | DSF0000944456, DSF0000944457, DSF0000944458
1 | M142 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 9/13/2021 | 6/4/2023 |  | 9720000 | 10011420 | 7529463 | DSF0000944456, DSF0000944457, DSF0000944458
1 | M142 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/13/2021 | 6/4/2023 |  | 604800 | 560079 | 545370 | DSF0000944456, DSF0000944457, DSF0000944458
1 | M142 | P.S. 142 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR DUCTWORK INSULATION IN MCHANICAL ROOM | Construction | Complete | 8/28/2024 | IEH | 9/21/2024 | IEH | 0 | 0 | SCA0000073333
1 | M142 | P.S. 142 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/11/2024 | DOER |  | DOER | 112434 | 0 | DSF0001033170
1 | M142 | P.S. 142 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 10/2/2023 | DOER | 11/7/2023 | DOER | 249419 |  | DSF0001035690
1 | M142 | P.S. 142 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112813
1 | M142 | P.S. 142 - MANHATTAN | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 7/30/2022 | DOES |  | DOES |  | 0 | SCA0000070971
1 | M188 | P.S. 188 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR IN ROOM 501A, AHERA BOOK SHOWS IT AS HOT. | Construction | Complete | 4/15/2024 | IEH | 8/4/2024 | IEH | 0 | 0 | SCA0000072930
1 | M188 | P.S. 188 - MANHATTAN | SCA Furniture & Equipment | FY24 RESO A STEM LAB | F&E | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001086254
1 | M188 | P.S. 188 - MANHATTAN | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 9/5/2019 | FTK |  | FTK | 76709 | 76709 | DSF0000912317
1 | M188 | M094 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 60000 | 59448 | DSF0001086252
1 | M188 | P.S. 188 - MANHATTAN | DOE - RESOA | FY11 RESO A PLAYGROUND REDEVELOPMEN | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0000710824
1 | M188 | P.S. 188 - MANHATTAN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0000913037
1 | M188 | P.S. 188 - MANHATTAN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 135000 | 0 | DSF0001035712
1 | M188 | P.S. 188 - MANHATTAN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001035713
1 | M188 | M094 SPED - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/3/2022 | DOES |  | DOES | 313034 | 0 | DSF0001008697
1 | M188 | P.S. 188 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/21/2024 | DOES | 12/2/2024 | DOES | 65832 |  | DSF0001084643
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / PARAPETS / ROOFS | Scope | Complete | 6/22/2023 | 11/7/2023 | 3/26/2024 | 154686 | 231641 | 205544 | DSF0001070360, DSF0001098052, DSF0001098055, DSF0001112186, DSF0001098054
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / PARAPETS / ROOFS | Design | In-Progress | 4/17/2024 | 9/18/2024 |  | 720869 | 720869 | 195474 | DSF0001070360, DSF0001098052, DSF0001098055, DSF0001112186, DSF0001098054
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / PARAPETS / ROOFS | Construction | PNS | PNS | PNS | PNS | 12159505 | 12159505 | 102809 | DSF0001070360, DSF0001098052, DSF0001098055, DSF0001112186, DSF0001098054
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / PARAPETS / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 1227741 | 1227741 | 44153 | DSF0001070360, DSF0001098052, DSF0001098055, DSF0001112186, DSF0001098054
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | SCA IEH | PO18-ABATE CEILING ABOVE STAIRCASE E , BATHROOM ON 5TH FL BOYS BATHROOM AND 5TH FLOOR NEAR THE ELEV | Construction | Complete | 7/10/2024 | IEH | 12/16/2024 | IEH | 0 | 0 | SCA0000073129
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | Fast Track Projects | FY18 RESO A SAFETY SYSTEMS | Construction | In-Progress | 11/13/2018 | FTK |  | FTK | 15012 | 12702 | DSF0000867371
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | DOE - RESOA | FY18 RESO A MEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 235237 | 0 | DSF0000866377
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 2/26/2021 | DOER |  | DOER | 53288 | 0 | DSF0000913094
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | DOE - Skilled Trades | REPAIRS TO FIRE DAMAGE | Construction | In-Progress | 11/12/2019 | DOES |  | DOES | 266861 | 0 | SCA0000062188
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/23/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084954
1 | M510 | SATELLITE AT FORSYTHE | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/6/2023 | DOER |  | DOER | 151912 | 0 | DSF0000913098
1 | M510 | CASCADES CTR FOR TCHING & LNG - M | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 5/13/2024 | DOER |  | DOER | 47394 | 0 | DSF0001035770
1 | M510 | SATELLITE AT FORSYTHE | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086309
1 | M510 | CASCADES CTR FOR TCHING & LNG - M | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 8/21/2023 | DOES | 11/16/2023 | DOES | 62190 |  | DSF0000866124
1 | M510 | CASCADES CTR FOR TCHING & LNG - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/4/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084968
1 | M751 | M751 SPED - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ M751 | Construction | In-Progress | 9/30/2024 | EMER |  | EMER | 80946 | 0 | SCA0000073449
1 | M751 | M751 SPED - MANHATTAN | SCA IEH | PO18-COLLAPSED AND ACM CEILING MATERIAL IN ROOM 505 TEACHERS' S LOUNGE ROOM HAS BEEN CLOSED OFF . | Construction | Complete | 7/8/2024 | IEH | 7/21/2024 | IEH | 0 | 0 | SCA0000073120
1 | M751 | M751 SPED - MANHATTAN | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 4/6/2023 | DOER |  | DOER | 318711 | 0 | DSF0001033728
1 | M751 | M751 SPED - MANHATTAN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/6/2023 | DOER |  | DOER | 290515 | 0 | DSF0001086320
1 | M751 | M751 SPED - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 12/26/2018 | DOES |  | DOES | 236177 | 0 | DSF0000877431
1 | M751 | M751 SPED - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/12/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084981
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | Scope | Complete | 10/12/2018 | 3/4/2019 | 1/3/2019 | 373649 | 159135 | 159120 | DSF0000874691, DSF0000874693, DSF0000874694, DSF0000912459
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | Design | Complete | 1/3/2019 | 6/5/2019 | 5/14/2019 | 1494600 | 1142383 | 968160 | DSF0000874691, DSF0000874693, DSF0000874694, DSF0000912459
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | Construction | In-Progress | 10/9/2019 | 10/7/2021 |  | 28023750 | 34259646 | 28447835 | DSF0000874691, DSF0000874693, DSF0000874694, DSF0000912459
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | CM,F&E | In-Progress | 10/9/2019 | 10/7/2021 |  | 1743699 | 2445349 | 2268344 | DSF0000874691, DSF0000874693, DSF0000874694, DSF0000912459
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/22/2024 | 5/20/2024 | 1/22/2024 | 5982 | 1923 | 1923 | DSF0001087462
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2024 | 9/16/2024 | 8/13/2024 | 26919 | 7693 | 7693 | DSF0001087462
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 346951 | 346951 | 0 | DSF0001087462
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 68046 | 68046 | 6574 | DSF0001087462
2 | M001 | P.S. 1 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 199373 | 0 | DSF0001035605
2 | M001 | P.S. 1 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 12/27/2021 | DOES |  | DOES | 307767 | 0 | DSF0001008689
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | Scope | Complete | 2/14/2019 | 6/17/2019 | 10/29/2019 | 113406 | 3228 | 3228 | DSF0000960574, DSF0000943000, DSF0000943001, DSF0001017158
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | Design | Complete | 11/25/2019 | 4/28/2020 | 3/22/2022 | 559432 | 348902 | 345299 | DSF0000960574, DSF0000943000, DSF0000943001, DSF0001017158
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | Construction | In-Progress | 8/15/2022 | 8/13/2024 |  | 11930288 | 10674084 | 9718493 | DSF0000960574, DSF0000943000, DSF0000943001, DSF0001017158
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | CM,F&E | In-Progress | 8/15/2022 | 8/13/2024 |  | 850799 | 64105 | 63745 | DSF0000960574, DSF0000943000, DSF0000943001, DSF0001017158
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/26/2024 | 6/25/2024 | 3/20/2024 | 3740 | 1090 | 1090 | DSF0001087463
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/20/2024 | 9/13/2024 | 8/13/2024 | 16830 | 4362 | 4362 | DSF0001087463
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 216920 | 216920 | 10726 | DSF0001087463
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 43945 | 43945 | 3937 | DSF0001087463
2 | M002 | P.S. 2 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/13/2019 | EMER |  | EMER | 12196 | 12196 | SCA0000056407
2 | M002 | P.S. 2 - MANHATTAN | Fast Track Projects | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/14/2021 | FTK |  | FTK | 37701 | 34965 | DSF0000913071
2 | M002 | P.S. 2 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 117999 | 0 | DSF0001009091
2 | M002 | P.S. 2 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/1/2022 | DOES |  | DOES | 494086 | 0 | DSF0001034237
2 | M003 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/26/2023 | 10/25/2023 | 7/6/2023 | 4065 | 1585 | 1585 | DSF0001035027
2 | M003 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/6/2023 | 1/3/2024 | 10/18/2023 | 18290 | 6342 | 6342 | DSF0001035027
2 | M003 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/28/2024 | 12/23/2024 |  | 235742 | 221652 | 146834 | DSF0001035027
2 | M003 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/28/2024 | 12/23/2024 |  | 90709 | 72789 | 62144 | DSF0001035027
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/22/2022 | DOER |  | DOER | 35857 | 0 | DSF0000913291
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001007811
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086164
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY24 RESO A (MA) CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 3109 | 0 | DSF0001086165
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 69000 | 0 | DSF0001112749
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112750
2 | M003 | P.S. 3 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/13/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084177
2 | M006 | P.S. 6 - MANHATTAN | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 6/14/2021 | 3/25/2022 | 1/31/2022 | 0 | 22402 | 22402 | DSF0001007823, DSF0001007848
2 | M006 | P.S. 6 - MANHATTAN | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 1/31/2022 | 3/28/2022 | 4/4/2022 | 60518 | 89611 | 80611 | DSF0001007823, DSF0001007848
2 | M006 | P.S. 6 - MANHATTAN | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 6/15/2023 | 3/15/2024 |  | 887607 | 549068 | 460949 | DSF0001007823, DSF0001007848
2 | M006 | P.S. 6 - MANHATTAN | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 6/15/2023 | 3/15/2024 |  | 201380 | 228788 | 168967 | DSF0001007823, DSF0001007848
2 | M006 | P.S. 6 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001086167
2 | M006 | P.S. 6 - MANHATTAN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112754
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 2/3/2021 | DOER |  | DOER | 274039 | 0 | DSF0000890809
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 429332 | 0 | DSF0000913072
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/6/2022 | DOER |  | DOER | 32577 | 0 | DSF0000913294
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 135418 | 0 | DSF0001035618
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001112758
2 | M011 | P.S. 11 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/24/2022 | DOES |  | DOES | 95590 | 0 | DSF0001009100
2 | M017 | P.P.A.S. - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/28/2024 | 7/29/2024 | 4/16/2024 | 5043 | 1889 | 1889 | DSF0001087467
2 | M017 | P.P.A.S. - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/16/2024 | 10/10/2024 | 9/25/2024 | 22694 | 7555 | 7555 | DSF0001087467
2 | M017 | P.P.A.S. - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 292506 | 292506 | 3189 | DSF0001087467
2 | M017 | P.P.A.S. - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 54214 | 54214 | 3962 | DSF0001087467
2 | M017 | P.S. 212 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 40000 | 0 | DSF0000961572
2 | M017 | P.S. 212 - MANHATTAN | DOE - RESOA | FY16 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 6/8/2024 | DOER |  | DOER | 270785 | 0 | DSF0000822765
2 | M017 | P.S. 212 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/17/2022 | DOER |  | DOER | 39884 | 0 | DSF0000913298
2 | M017 | P.P.A.S. - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 94776 | 0 | DSF0001086174
2 | M017 | P.S. 212 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112759
2 | M017 | P.S. 212 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 11/1/2021 | DOES |  | DOES | 57782 | 0 | DSF0001008942
2 | M017 | P.P.A.S. - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/17/2024 | DOES | 9/11/2024 | DOES | 65832 | 13796 | DSF0001084186
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | Scope | Complete | 2/28/2019 | 7/29/2019 | 10/3/2019 | 39007 | 69916 | 69916 | DSF0001008783, DSF0000960919
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | Design | Complete | 11/13/2019 | 4/16/2020 | 9/1/2021 | 192928 | 239444 | 239444 | DSF0001008783, DSF0000960919
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | Construction | Complete | 8/15/2022 | 8/13/2024 | 8/13/2024 | 4158625 | 3929254 | 3563059 | DSF0001008783, DSF0000960919
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | CM,F&E | Complete | 8/15/2022 | 8/13/2024 | 8/13/2024 | 288851 | 841763 | 833785 | DSF0001008783, DSF0000960919
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/6/2022 | 10/4/2022 | 9/7/2022 | 6015 | 5531 | 5531 | DSF0001034606
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/7/2022 | 3/8/2023 | 3/8/2023 | 27067 | 22122 | 22122 | DSF0001034606
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/3/2023 | 8/28/2024 |  | 348863 | 314096 | 6558 | DSF0001034606
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/3/2023 | 8/28/2024 |  | 174352 | 152149 | 28308 | DSF0001034606
2 | M033 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113603
2 | M033 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113603
2 | M033 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113603
2 | M033 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113603
2 | M033 | P.S. 33 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 120000 | 0 | DSF0000913075
2 | M033 | M138 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/20/2023 | DIIR |  | DIIR | 50000 | 0 | DSF0001035625
2 | M033 | P.S. 33 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 1/5/2022 | DOER | 6/23/2022 | DOER | 20668 | 20390 | DSF0000913300
2 | M033 | P.S. 33 - MANHATTAN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 6/27/2022 | DOER |  | DOER | 93353 | 0 | DSF0001007804
2 | M033 | P.S. 33 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 162651 | 0 | DSF0001035624
2 | M033 | P.S. 33 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/26/2023 | DOER |  | DOER | 225000 | 9700 | DSF0001086177
2 | M033 | M138 SPED - MANHATTAN | DOE - RESOA | FY24 RESO A (MA) ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 235250 | 0 | DSF0001086178
2 | M033 | M138 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112763
2 | M033 | P.S. 33 - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 2/26/2024 | DOES |  | DOES | 544403 | 1908 | DSF0001095935
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 3/3/2021 | 7/16/2021 | 1/25/2022 | 319430 | 369254 | 366465 | DSF0000943382, DSF0000943384, DSF0000943386, DSF0000943385, DSF0001034496
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 1/25/2022 | 6/24/2022 | 5/10/2022 | 1597150 | 1153095 | 1015221 | DSF0000943382, DSF0000943384, DSF0000943386, DSF0000943385, DSF0001034496
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | In-Progress | 8/10/2023 | 2/4/2026 |  | 35935875 | 32593045 | 9701773 | DSF0000943382, DSF0000943384, DSF0000943386, DSF0000943385, DSF0001034496
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | In-Progress | 8/10/2023 | 2/4/2026 |  | 2237013 | 273274 | 272635 | DSF0000943382, DSF0000943384, DSF0000943386, DSF0000943385, DSF0001034496
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Scope | Complete | 3/12/2020 | 7/27/2020 | 6/8/2021 | 0 | 33452 | 33452 | DSF0000913301
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Design | Complete | 6/15/2021 | 12/2/2021 | 1/12/2022 | 45049 | 96021 | 93479 | DSF0000913301
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Construction | In-Progress | 7/22/2022 | 7/21/2023 |  | 660724 | 595403 | 424022 | DSF0000913301
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | CM,F&E | In-Progress | 7/22/2022 | 7/21/2023 |  | 45049 | 68983 | 67944 | DSF0000913301
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Scope | Complete | 4/25/2022 | 12/8/2022 | 11/1/2022 | 0 | 23281 | 23281 | DSF0001033629, DSF0001033630
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Design | Complete | 11/2/2022 | 3/2/2023 | 1/20/2023 | 56909 | 79380 | 70380 | DSF0001033629, DSF0001033630
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 6/13/2023 | 3/13/2024 |  | 834669 | 713992 | 401885 | DSF0001033629, DSF0001033630
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 6/13/2023 | 3/13/2024 |  | 147046 | 187486 | 139166 | DSF0001033629, DSF0001033630
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY21 RESO A (MA) SCIENCE LAB UPGRADE | Scope | Complete | 3/3/2021 | 6/16/2021 | 9/1/2021 | 0 | 35876 | 35876 | DSF0001008578
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY21 RESO A (MA) SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 6078 | 6078 | DSF0001008578
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY21 RESO A (MA) SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 1548 | 1548 | DSF0001008578
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY21 RESO A (MA) SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 5457 | 5457 | DSF0001008578
2 | M040 | P.S. 40 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- INVESTIGATION @ M040 | Construction | In-Progress | 6/9/2023 | EMER |  | EMER | 103375 | 103375 | SCA0000072062
2 | M040 | P.S. 40 - MANHATTAN | SCA IEH | PO18-ACM CORE DRILLING NEEDED IN THE KITCHEN (2) 1.25' HOLES DRILLED THRU THE WALL (12) 1/2' HOLES D | Construction | Complete | 7/18/2024 | IEH | 12/12/2024 | IEH | 0 | 0 | SCA0000073149
2 | M040 | I.S. 255 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 55000 | 47753 | DSF0001035628
2 | M040 | I.S. 255 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086180
2 | M040 | P.S. 40 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112765
2 | M040 | P.S. 40 - MANHATTAN | DOE - RESOA | FY 15 RESO A CAFETERIA FLOORING UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 43622 | 0 | DSF0000800292
2 | M040 | P.S. 40 - MANHATTAN | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/25/2019 | DOER |  | DOER | 505108 | 0 | DSF0000890661
2 | M040 | I.S. 255 - MANHATTAN | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 3199 | 0 | DSF0001033677
2 | M040 | P.S. 40 - MANHATTAN | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 8/30/2024 | DOER |  | DOER | 87923 | 0 | DSF0001035627
2 | M040 | I.S. 255 - MANHATTAN | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 6/21/2024 | DOER |  | DOER | 74117 | 0 | DSF0001035629
2 | M040 | I.S. 255 - MANHATTAN | DOE - RESOA | FY25 RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112764
2 | M040 | P.S. 40 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/26/2024 | DOES | 7/31/2024 | DOES | 65832 | 12569 | DSF0001084192
2 | M040 | I.S. 255 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/13/2024 | DOES |  | DOES | 401401 | 0 | DSF0001111636
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/27/2019 | 11/13/2019 | 2/11/2020 | 172368 | 155826 | 153965 | DSF0000897983, DSF0000897984, DSF0000897985, DSF0001008626
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2/11/2020 | 7/13/2020 | 5/14/2021 | 860032 | 585461 | 526699 | DSF0000897983, DSF0000897984, DSF0000897985, DSF0001008626
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 9/5/2023 | 1/1/2026 |  | 19194327 | 17257355 | 7084649 | DSF0000897983, DSF0000897984, DSF0000897985, DSF0001008626
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 9/5/2023 | 1/1/2026 |  | 1221137 | 141110 | 139767 | DSF0000897983, DSF0000897984, DSF0000897985, DSF0001008626
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/27/2024 | 7/26/2024 | 4/16/2024 | 4394 | 2011 | 2011 | DSF0001087470
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/16/2024 | 10/10/2024 | 9/25/2024 | 19773 | 8044 | 8044 | DSF0001087470
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 254849 | 254849 | 2460 | DSF0001087470
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 47235 | 47235 | 4214 | DSF0001087470
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/14/2023 | 5/15/2023 | 6/27/2023 | 0 | 11562 | 11562 | DSF0001035630
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 25593 | 14031 | 2537 | DSF0001035630
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 375357 | 435366 | 0 | DSF0001035630
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 25593 | 29684 | 499 | DSF0001035630
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035631
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035631
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035631
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 142 | 142 | DSF0001035631
2 | M041 | P.S. 41 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/22/2024 | DIIR | 174371 | 174371 | DSF0001033153
2 | M041 | P.S. 41 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/24/2021 | DOER |  | DOER | 61043 | 0 | DSF0001007803
2 | M041 | P.S. 41 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/8/2023 | DOER |  | DOER | 150000 | 9653 | DSF0001086181
2 | M041 | P.S. 41 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112766
2 | M041 | P.S. 41 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 11/12/2021 | DOES |  | DOES | 83081 | 0 | DSF0001009024
2 | M041 | P.S. 41 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832 | 16919 | DSF0001084193
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 7/17/2019 | 12/3/2019 | 1/23/2020 | 129854 | 175675 | 170124 | DSF0000898000, DSF0000898002, DSF0000898003, DSF0000898004, DSF0000898005
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/23/2020 | 6/23/2020 | 6/30/2020 | 643030 | 607328 | 586109 | DSF0000898000, DSF0000898002, DSF0000898003, DSF0000898004, DSF0000898005
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2/28/2022 | 3/28/2024 |  | 13927885 | 13133596 | 11227204 | DSF0000898000, DSF0000898002, DSF0000898003, DSF0000898004, DSF0000898005
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2/28/2022 | 3/28/2024 |  | 955827 | 375005 | 348036 | DSF0000898000, DSF0000898002, DSF0000898003, DSF0000898004, DSF0000898005
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/3/2023 | 11/1/2023 | 7/12/2023 | 4335 | 1674 | 1674 | DSF0001035046
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/12/2023 | 1/9/2024 | 10/18/2023 | 19510 | 6698 | 6698 | DSF0001035046
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/28/2024 | 12/23/2024 |  | 251458 | 227745 | 148916 | DSF0001035046
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/28/2024 | 12/23/2024 |  | 121417 | 102594 | 87195 | DSF0001035046
2 | M042 | P.S. 42 - MANHATTAN | SCA IEH | PO18-ROOM 205B ABATE 10 SQ. FT. WALL PLASTER, 5 SQ. FT. CEILING PLASTER - ROOM 208A ABATE 8 SQ. FT. | Construction | Complete | 9/9/2024 | IEH | 9/15/2024 | IEH | 0 | 0 | SCA0000073359
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | RESO A- SOLAR ROOF INSTALL | Construction | PNS | PNS | PNS | PNS | DOER | 111545 | 0 | DSF0000777448
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 3/24/2022 | DOER |  | DOER | 32804 | 0 | DSF0000913077
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/18/2023 | DOER |  | DOER | 85430 | 0 | DSF0000913302
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 113550 | 0 | DSF0001033154
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 3892 | 0 | DSF0001035632
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086182
2 | M042 | P.S. 42 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/1/2022 | DOES |  | DOES | 91622 | 0 | DSF0001034239
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 12/18/2019 | 3/20/2020 | 3/16/2020 | 27730 | 55463 | 55463 | DSF0000943498
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 4/20/2021 | 10/21/2021 | 8/3/2022 | 138650 | 360287 | 244457 | DSF0000943498
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 5/1/2023 | 10/21/2024 |  | 3119625 | 3529496 | 2773346 | DSF0000943498
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 5/1/2023 | 10/21/2024 |  | 194110 | 299460 | 291841 | DSF0000943498
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | Scope | Complete | 4/29/2022 | 9/14/2022 | 12/7/2022 | 247331 | 324660 | 324650 | DSF0001085109, DSF0001083829, DSF0001068422, DSF0001083828, DSF0001068421
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | Design | Complete | 12/22/2022 | 5/25/2023 | 4/28/2023 | 1236651 | 940903 | 767182 | DSF0001085109, DSF0001083829, DSF0001068422, DSF0001083828, DSF0001068421
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | Construction | In-Progress | 8/21/2023 | 2/15/2026 |  | 27824626 | 24928128 | 7277557 | DSF0001085109, DSF0001083829, DSF0001068422, DSF0001083828, DSF0001068421
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | CM,F&E | In-Progress | 8/21/2023 | 2/15/2026 |  | 1731310 | 341007 | 340212 | DSF0001085109, DSF0001083829, DSF0001068422, DSF0001083828, DSF0001068421
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 3/22/2022 | EMER |  | EMER | 33094 | 21895 | SCA0000070945
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA IEH | PO18-ABATEMENT OF PIPE INSULATION IN THE CAFETERIA SPACE ID# 2300 - APPROX 10 FEET | Construction | In-Progress | 9/18/2024 | IEH |  | IEH | 0 | 0 | SCA0000073391
2 | M047 | P.S. 347 - MANHATTAN | DOE - RESOA | FY16 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 44000 | 0 | DSF0000822300
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/19/2024 | DOER |  | DOER | 310580 | 0 | DSF0001035636
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 340584 | 0 | DSF0001086187
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100307 | 0 | DSF0001112395
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/10/2022 | DOES |  | DOES | 125997 | 0 | DSF0001034240
2 | M058 | M035 SPED - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION IN ROOM B12. ABOUT 30FT TOTAL AREAS ARE SPRAYED. GATE VALVES - R | Construction | In-Progress | 7/10/2024 | IEH |  | IEH | 0 | 0 | SCA0000073126
2 | M058 | M035 SPED - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/27/2024 | DOES | 9/6/2024 | DOES | 65832 | 2838 | DSF0001084940
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 12/12/2023 | 4/29/2024 | 7/19/2024 | 64251 | 140488 | 77289 | DSF0001068625, DSF0001112401, DSF0001096326
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | In-Progress | 7/30/2024 | 1/2/2025 |  | 294049 | 294049 | 14325 | DSF0001068625, DSF0001112401, DSF0001096326
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 4611309 | 4611309 | 11368 | DSF0001068625, DSF0001112401, DSF0001096326
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 535555 | 535555 | 41922 | DSF0001068625, DSF0001112401, DSF0001096326
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/30/2020 | 10/29/2020 | 7/13/2020 | 2081 | 6193 | 6193 | DSF0000960793
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/13/2020 | 1/7/2021 | 3/30/2021 | 9363 | 24772 | 24772 | DSF0000960793
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/24/2022 | 3/19/2023 |  | 120678 | 116860 | 102313 | DSF0000960793
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/24/2022 | 3/19/2023 |  | 118762 | 156869 | 152443 | DSF0000960793
2 | M066 | P.S. 151 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ M066 | Construction | In-Progress | 3/7/2024 | EMER |  | EMER | 49029 | 12520 | SCA0000072799
2 | M066 | P.S. 151 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086196
2 | M066 | P.S. 151 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112778
2 | M066 | P.S. 151 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/11/2024 | DOER |  | DOER | 323500 | 0 | DSF0001035648
2 | M066 | P.S. 151 - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 12/20/2023 | DOER | 2/20/2024 | DOER | 59343 |  | DSF0001035649
2 | M066 | P.S. 151 - MANHATTAN | DOE - RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 293631 | 0 | DSF0001112246
2 | M066 | P.S. 151 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/2/2022 | DOES |  | DOES | 78332 | 0 | DSF0001009109
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 7/19/2022 | 1/22/2024 | 1/9/2024 | 0 | 45275 | 39790 | DSF0001035065, DSF0001087238
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | Complete | 1/12/2024 | 5/30/2024 | 5/22/2024 | 196308 | 127366 | 119627 | DSF0001035065, DSF0001087238
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 2879187 | 2879187 | 62028 | DSF0001035065, DSF0001087238
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 196308 | 196799 | 70627 | DSF0001035065, DSF0001087238
2 | M070 | NYC LAB HS - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF THE STEAM LINE ELBOW LOCATED IN THE BOILER ROOM OF BOILER 3 APPROX 24 INCHES | Construction | In-Progress | 10/17/2024 | IEH |  | IEH | 0 | 0 | SCA0000073510
2 | M070 | NYC LAB HS - MANHATTAN | SCA IEH | PO18-/REMOVE 8' OF ACM FROM STEM PIPES B3 BASEMENT STORAGE AREA DUE TO LEAKING | Construction | Complete | 11/15/2024 | IEH | 11/16/2024 | IEH | 0 | 0 | SCA0000073610
2 | M070 | MUSEUM SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/1/2024 | DIIR | 7/10/2024 | DIIR | 65000 | 64604 | DSF0001086197
2 | M070 | NYC LAB HS - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/14/2024 | DIIR | 11/6/2024 | DIIR | 65000 | 65000 | DSF0001086198
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112779
2 | M070 | NYC LAB HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112780
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 7/8/2021 | DOER |  | DOER | 84686 | 0 | DSF0001007809
2 | M070 | MUSEUM SCHOOL - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 10/13/2023 | DOER | 12/18/2023 | DOER | 153775 |  | DSF0001035221
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 5/13/2016 | DOES |  | DOES | 205854 | 0 | DSF0000799864
2 | M089 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/20/2023 | 11/20/2023 | 8/10/2023 | 4160 | 4833 | 4833 | DSF0001035029
2 | M089 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/10/2023 | 2/8/2024 | 12/13/2023 | 18720 | 19334 | 19334 | DSF0001035029
2 | M089 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/27/2024 | 5/26/2025 |  | 241280 | 220457 | 455 | DSF0001035029
2 | M089 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/27/2024 | 5/26/2025 |  | 78212 | 61889 | 22719 | DSF0001035029
2 | M089 | P.S. 89 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001086203
2 | M089 | P.S. 89 - MANHATTAN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 64000 | 0 | DSF0001086204
2 | M089 | P.S. 89 - MANHATTAN | DOE - Skilled Trades | GYMNASIUM FLOOR | Construction | In-Progress | 5/26/2016 | DOES |  | DOES | 210102 | 0 | DSF0000842684
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 5/28/2024 | 10/11/2024 | 11/6/2024 | 128240 | 109279 | 42097 | DSF0001068999, DSF0001124455, DSF0001113869, DSF0001124456
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | In-Progress | 11/18/2024 | 4/22/2025 |  | 590649 | 590649 | 11915 | DSF0001068999, DSF0001124455, DSF0001113869, DSF0001124456
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 11646784 | 11646784 | 0 | DSF0001068999, DSF0001124455, DSF0001113869, DSF0001124456
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1289424 | 1289424 | 30590 | DSF0001068999, DSF0001124455, DSF0001113869, DSF0001124456
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112795
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001112795
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001112795
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001112795
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113605
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113605
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113605
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113605
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY 21 RESO A (MA) FITNESS ROOM / PATH OF TRAVEL RESO A FITNESS ROOM | Scope | Complete | 4/6/2021 | 12/20/2021 | 11/3/2021 | 0 | 25066 | 25066 | DSF0001008815, DSF0001032955
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY 21 RESO A (MA) FITNESS ROOM / PATH OF TRAVEL RESO A FITNESS ROOM | Design | Complete | 11/4/2021 | 3/10/2022 | 4/14/2022 | 90524 | 94457 | 84017 | DSF0001008815, DSF0001032955
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY 21 RESO A (MA) FITNESS ROOM / PATH OF TRAVEL RESO A FITNESS ROOM | Construction | In-Progress | 8/7/2024 | 7/2/2025 |  | 1327691 | 1279565 | 63185 | DSF0001008815, DSF0001032955
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY 21 RESO A (MA) FITNESS ROOM / PATH OF TRAVEL RESO A FITNESS ROOM | CM,F&E | In-Progress | 8/7/2024 | 7/2/2025 |  | 90524 | 139279 | 51404 | DSF0001008815, DSF0001032955
2 | M104 | I.S. 104 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- FACADE SPALLING @ M104 | Construction | In-Progress | 11/13/2024 | EMER |  | EMER | 18595 | 0 | SCA0000073605
2 | M104 | I.S. 104 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/19/2021 | DOER |  | DOER | 161767 | 0 | DSF0001007818
2 | M104 | I.S. 104 - MANHATTAN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/12/2023 | DOER |  | DOER | 257073 | 0 | DSF0001033646
2 | M104 | I.S. 104 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/11/2024 | DOER |  | DOER | 168590 | 0 | DSF0001035659
2 | M104 | I.S. 104 - MANHATTAN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 6/1/2016 | DOES |  | DOES | 270403 | 0 | DSF0000785705
2 | M111 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/10/2023 | 12/12/2023 | 8/22/2023 | 4480 | 3770 | 3770 | DSF0001035030
2 | M111 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/22/2023 | 2/21/2024 | 12/13/2023 | 20160 | 15080 | 15080 | DSF0001035030
2 | M111 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/27/2024 | 5/26/2025 |  | 259840 | 237982 | 975 | DSF0001035030
2 | M111 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/27/2024 | 5/26/2025 |  | 80949 | 63899 | 49237 | DSF0001035030
2 | M111 | P.S. 111 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 1/10/2022 | DOER | 8/29/2022 | DOER | 25152 | 24814 | DSF0000913311
2 | M111 | P.S. 111 - MANHATTAN | DOE - RESOA | FY21 RESO A INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001007806
2 | M111 | P.S. 111 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 346455 | 0 | DSF0001035664
2 | M111 | P.S. 111 - MANHATTAN | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 286457 | 0 | DSF0001086212
2 | M111 | CITY KNOLL MIDDLE SCHOOL | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112796
2 | M111 | P.S. 111 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/26/2022 | DOES |  | DOES | 110754 | 0 | DSF0001009103
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY25 RESO A INTERIOR SPACES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112798
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY25 RESO A INTERIOR SPACES | Design | PNS | PNS | PNS | PNS | 12000 | 12000 | 0 | DSF0001112798
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY25 RESO A INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 176000 | 176000 | 0 | DSF0001112798
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY25 RESO A INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 12000 | 12000 | 0 | DSF0001112798
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A INTERIOR SPACES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113606
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A INTERIOR SPACES | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113606
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113606
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113606
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY16 RESO A GREEN ROOF | Scope | Complete | 1/26/2016 | 6/9/2016 | 3/8/2016 | 0 | 29585 | 29585 | DSF0000823590
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY16 RESO A GREEN ROOF | Design | Complete | 5/18/2016 | 10/19/2016 | 5/17/2019 | 30714 | 183531 | 183531 | DSF0000823590
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY16 RESO A GREEN ROOF | Construction | PNS | PNS | PNS | PNS | 450471 | 2228830 | 0 | DSF0000823590
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY16 RESO A GREEN ROOF | CM,F&E | PNS | PNS | PNS | PNS | 30714 | 151966 | 27430 | DSF0000823590
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | RESO A- DANCE STUDIO | Scope | Complete | 4/9/2021 | 7/12/2021 | 7/28/2021 | 0 | 18510 | 18510 | DSF0001008762
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | RESO A- DANCE STUDIO | Design | Complete | 8/9/2021 | 1/12/2022 | 8/8/2022 | 45750 | 111720 | 81430 | DSF0001008762
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | RESO A- DANCE STUDIO | Construction | In-Progress | 9/16/2024 | 6/12/2025 |  | 671000 | 489762 | 0 | DSF0001008762
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | RESO A- DANCE STUDIO | CM,F&E | In-Progress | 9/16/2024 | 6/12/2025 |  | 45750 | 44200 | 10682 | DSF0001008762
2 | M114 | M138 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/20/2023 | DIIR |  | DIIR | 54000 | 0 | DSF0001035667
2 | M114 | M138 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 49310 | 0 | DSF0001086214
2 | M114 | M138 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112799
2 | M114 | I.S. 114 - MANHATTAN | DOE - RESOA | RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/7/2023 | DOER |  | DOER | 551514 | 0 | DSF0001008761
2 | M114 | I.S. 114 - MANHATTAN | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | Complete | 12/18/2023 | DOER | 12/18/2023 | DOER | 237435 |  | DSF0001035666
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 6/14/2024 | 10/31/2024 | 10/16/2024 | 143853 | 134884 | 92719 | DSF0001069127, DSF0001069129, DSF0001096830, DSF0001113803
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | In-Progress | 11/8/2024 | 4/15/2025 |  | 696379 | 710561 | 259536 | DSF0001069127, DSF0001069129, DSF0001096830, DSF0001113803
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Construction | PNS | PNS | PNS | PNS | 13670632 | 13670632 | 34560 | DSF0001069127, DSF0001069129, DSF0001096830, DSF0001113803
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1044380 | 1044380 | 24975 | DSF0001069127, DSF0001069129, DSF0001096830, DSF0001113803
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/24/2022 | 6/22/2022 | 11/3/2022 | 0 | 56514 | 53262 | DSF0001033651
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 11/17/2023 | 4/5/2024 |  | 55616 | 58783 | 37962 | DSF0001033651
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 815708 | 815708 | 9244 | DSF0001033651
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 55616 | 55616 | 13732 | DSF0001033651
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 4/17/2024 | 7/18/2024 | 8/19/2024 | 0 | 0 | 1455 | DSF0001033650
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Design | In-Progress | 8/19/2024 | 12/19/2024 |  | 1384 | 1384 | 5820 | DSF0001033650
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 20292 | 20292 | 0 | DSF0001033650
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 1384 | 1384 | 3916 | DSF0001033650
2 | M116 | P.S. 116 - MANHATTAN | SCA IEH | PO18-ROOM 506 ABATE 624 SQ. FT. DAMAGED WOODEN FLOORING ASSIGNED TO SCA ON 06/27/2024 | Construction | In-Progress | 6/28/2024 | IEH |  | IEH | 0 | 0 | SCA0000073102
2 | M116 | P.S. 116 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 49000 | 0 | DSF0000890168
2 | M116 | P.S. 116 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 180000 | 0 | DSF0001007830
2 | M116 | P.S. 116 - MANHATTAN | DOE - RESOA | FY17 RESO A KITCHEN AREAS | Construction | PNS | PNS | PNS | PNS | DOER | 103801 | 0 | DSF0000844793
2 | M116 | P.S. 116 - MANHATTAN | DOE - RESOA | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/10/2023 | DOER |  | DOER | 307625 | 0 | DSF0000866435
2 | M116 | P.S. 116 - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 8/30/2021 | DOER |  | DOER | 324251 | 0 | DSF0000961300
2 | M116 | P.S. 116 - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112801
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 5/15/2020 | 11/12/2020 | 10/23/2020 | 154300 | 253860 | 253860 | DSF0000944209, DSF0000944210, DSF0000944211, DSF0000944212
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 10/29/2020 | 6/15/2021 | 7/1/2021 | 771500 | 474271 | 474271 | DSF0000944209, DSF0000944210, DSF0000944211, DSF0000944212
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 9/6/2022 | 8/5/2024 |  | 17358751 | 15772733 | 14820288 | DSF0000944209, DSF0000944210, DSF0000944211, DSF0000944212
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/6/2022 | 8/5/2024 |  | 1080100 | 308534 | 306870 | DSF0000944209, DSF0000944210, DSF0000944211, DSF0000944212
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033652
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033652
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033652
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033652
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113608
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113608
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113608
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113608
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/25/2022 | 4/25/2022 | 8/11/2022 | 0 | 52539 | 50219 | DSF0001033653
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/7/2023 | 12/22/2023 | 12/26/2023 | 42000 | 42000 | 15204 | DSF0001033653
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 616000 | 616000 | 46487 | DSF0001033653
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 42000 | 42000 | 18434 | DSF0001033653
2 | M124 | P.S. 124 - MANHATTAN | SCA IEH | PO18-2 HOLES WE NEED DRILLED IN THE FLOOR BY ACM CONTRACTOR LOCATED IN THE CAFETERIA . THIS IS FOR S | Construction | Complete | 8/30/2024 | IEH | 9/3/2024 | IEH | 0 | 0 | SCA0000073339
2 | M124 | P.S. 124 - MANHATTAN | SCA IEH | PO18-ABATE CEILING PLASTER IN RM 325, 326 AS PER AHERA BOOK DATED 3/17/2017 ROOM 326 HAS A SIMILAR S | Construction | Complete | 9/3/2024 | IEH | 9/8/2024 | IEH | 0 | 0 | SCA0000073351
2 | M124 | P.S. 124 - MANHATTAN | SCA IEH | PO18-ABATE DRAIN PIPE IN THE BASEMENT (PARKING GARAGE) APPX 40 FT | Construction | Complete | 9/3/2024 | IEH | 12/16/2024 | IEH | 0 | 0 | SCA0000073435
2 | M124 | P.S. 124 - MANHATTAN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035677
2 | M124 | P.S. 124 - MANHATTAN | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 7/12/2022 | DOER |  | DOER | 93124 | 0 | DSF0000913315
2 | M124 | P.S. 124 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/25/2022 | DOER |  | DOER | 316643 | 0 | DSF0000961306
2 | M124 | P.S. 124 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 310000 | 0 | DSF0001112803
2 | M124 | P.S. 124 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/20/2022 | DOES |  | DOES | 123403 | 0 | DSF0001034241
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 10/23/2018 | 3/13/2019 | 1/10/2019 | 279097 | 290351 | 290351 | DSF0000875925, DSF0000875926, DSF0000875927, DSF0000875928
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/16/2019 | 6/17/2019 | 5/29/2020 | 1385660 | 860679 | 843118 | DSF0000875925, DSF0000875926, DSF0000875927, DSF0000875928
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 7/15/2021 | 7/13/2024 |  | 30327154 | 28154200 | 18027074 | DSF0000875925, DSF0000875926, DSF0000875927, DSF0000875928
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/15/2021 | 7/13/2024 |  | 2027404 | 639079 | 621202 | DSF0000875925, DSF0000875926, DSF0000875927, DSF0000875928
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/17/2023 | 7/18/2023 | 3/24/2023 | 5645 | 2792 | 2792 | DSF0001034612
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/24/2023 | 9/19/2023 | 5/8/2023 | 25403 | 11167 | 11167 | DSF0001034612
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/3/2023 | 8/28/2024 |  | 327417 | 297876 | 121901 | DSF0001034612
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/3/2023 | 8/28/2024 |  | 152609 | 131082 | 78447 | DSF0001034612
2 | M126 | P.S. 126 - MANHATTAN | SCA IEH | PO18-ABATEMENT IN PIPE SPACE APPROXIMATELY 8', PAINTED BLACK | Construction | Complete | 7/30/2024 | IEH | 8/22/2024 | IEH | 0 | 0 | SCA0000073202
2 | M126 | P.S. 126 - MANHATTAN | Fast Track Projects | FY20 RESO A ROOM CONVERSION | Construction | PNS | FTK | FTK | FTK | FTK | 52000 | 0 | DSF0000913085
2 | M126 | P.S. 126 - MANHATTAN | DOE - RESOA | FY17 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 1/15/2019 | DOER |  | DOER | 225277 | 0 | DSF0000844196
2 | M126 | P.S. 126 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0000913317
2 | M126 | P.S. 126 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/25/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084634
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/12/2024 | 10/11/2024 | 6/13/2024 | 5200 | 2352 | 2352 | DSF0001087480
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/13/2024 | 12/11/2024 | 12/11/2024 | 23402 | 9409 | 9409 | DSF0001087480
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 301624 | 301624 | 0 | DSF0001087480
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 60169 | 60169 | 9181 | DSF0001087480
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | ROOFS | Scope | Complete | 9/17/2024 | 9/17/2024 | 9/17/2024 | 3109 | 6608 | 843 | DSF0001097009
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | ROOFS | Design | Complete | 9/17/2024 | 1/17/2025 | 11/22/2024 | 12434 | 3373 | 3373 | DSF0001097009
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 178740 | 178740 | 0 | DSF0001097009
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 45851 | 45851 | 0 | DSF0001097009
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/26/2022 | 4/26/2022 | 8/11/2022 | 0 | 13499 | 13499 | DSF0001033656
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/15/2022 | 1/3/2023 | 12/8/2022 | 36000 | 53998 | 53998 | DSF0001033656
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 11/7/2023 | 8/2/2024 |  | 528000 | 489278 | 67914 | DSF0001033656
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 11/7/2023 | 8/2/2024 |  | 36000 | 56694 | 54456 | DSF0001033656
2 | M130 | P.S. 130 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/6/2022 | DOER |  | DOER | 91489 | 0 | DSF0000961341
2 | M130 | P.S. 130 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/9/2024 | DOES | 8/5/2024 | DOES | 65832 | 16660 | DSF0001084220
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112808
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 49500 | 49500 | 0 | DSF0001112808
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 726000 | 726000 | 0 | DSF0001112808
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 49500 | 49500 | 0 | DSF0001112808
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113609
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113609
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113609
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113609
2 | M131 | I.S. 131 - MANHATTAN | Fast Track Projects | LSP DANCE FLOOR REPLACEMENT | Construction | In-Progress | 12/22/2020 | FTK |  | FTK | 215114 | 171412 | DSF0000914244
2 | M131 | EMMA LAZARUS HIGH SCHOOL | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000913593
2 | M131 | I.S. 131 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/14/2022 | DOER |  | DOER | 115913 | 0 | DSF0000961351
2 | M131 | I.S. 131 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/17/2024 | DOES | 11/25/2024 | DOES | 50832 | 15516 | DSF0001084948
2 | M158 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Scope | Complete | 9/9/2020 | 1/20/2021 | 10/1/2021 | 30137 | 38697 | 38697 | DSF0000961103, DSF0000993401
2 | M158 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Design | Complete | 10/13/2021 | 4/19/2022 | 7/12/2022 | 145516 | 227348 | 196161 | DSF0000961103, DSF0000993401
2 | M158 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Construction | In-Progress | 5/3/2023 | 5/1/2025 |  | 2827207 | 2756476 | 2496667 | DSF0000961103, DSF0000993401
2 | M158 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | CM,F&E | In-Progress | 5/3/2023 | 5/1/2025 |  | 249701 | 374170 | 336958 | DSF0000961103, DSF0000993401
2 | M158 | P.S. 158 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: RM: 313 APPROX. 700SF RM: 314 APPROX. 700SF RM: 315 APP | Construction | Complete | 3/11/2024 | IEH | 7/25/2024 | IEH | 0 | 0 | SCA0000072806
2 | M158 | P.S. 158 - MANHATTAN | SCA IEH | PO18-/ABATE CEILING IN CLASSROOM 509 THAT FELL AHERA BOOK IS PRIOR MAY 2016 | Construction | Complete | 9/27/2024 | IEH | 9/29/2024 | IEH | 0 | 0 | SCA0000073445
2 | M158 | P.S. 158 - MANHATTAN | SCA IEH | PO18-SCA TO ABATE AND REPLACE THE TILES- 9X9 UNDER TILES. DISTURBANCE OF SUBFLOOR WILL BE NEEDED TO | Construction | In-Progress | 10/1/2024 | IEH |  | IEH | 0 | 0 | SCA0000073461
2 | M158 | YORKVILLE EAST MIDDLE SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112822
2 | M158 | P.S. 158 - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/16/2023 | DOER |  | DOER | 229362 | 0 | DSF0001035695
2 | M158 | P.S. 158 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001112821
2 | M158 | P.S. 158 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 7/5/2023 | DOES | 11/16/2023 | DOES | 69818 |  | DSF0000866121
2 | M158 | P.S. 158 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/21/2024 | DOES | 9/11/2024 | DOES | 65832 | 9961 | DSF0001084231
2 | M167 | I.S. 167 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/28/2023 | 6/29/2023 | 10/11/2023 | 0 | 15704 | 15704 | DSF0001035702, DSF0001035703
2 | M167 | I.S. 167 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 1/8/2024 | 5/31/2024 | 8/20/2024 | 31610 | 51774 | 46763 | DSF0001035702, DSF0001035703
2 | M167 | I.S. 167 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 463615 | 764851 | 5025 | DSF0001035702, DSF0001035703
2 | M167 | I.S. 167 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 31610 | 56358 | 17007 | DSF0001035702, DSF0001035703
2 | M167 | I.S. 167 - MANHATTAN | SCA IEH | PO18-ABATE 12' OF PIPE COVERING 2ND FLOOR, GIRL'S LOCKER ROOM 231 TO COMPLETE THE REPAIRS | Construction | Complete | 9/25/2024 | IEH | 11/9/2024 | IEH | 0 | 0 | SCA0000073422
2 | M167 | I.S. 167 - MANHATTAN | Fast Track Projects | LSP ASPHALT PAVEMENT AT PLAYGROUND | Construction | In-Progress | 4/24/2024 | FTK |  | FTK | 55125 | 0 | DSF0001087255
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY12 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 162502 | 0 | DSF0000731866
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0 | DSF0001033177
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035323
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001086245
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 223000 | 0 | DSF0001112827
2 | M167 | I.S. 167 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001112825
2 | M167 | I.S. 167 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001112826
2 | M167 | I.S. 167 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/6/2017 | DOES |  | DOES | 170000 | 0 | DSF0000866004
2 | M167 | I.S. 167 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/16/2024 | DOES | 10/28/2024 | DOES | 65832 | 17333 | DSF0001084791
2 | M169 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | Scope | Complete | 10/12/2018 | 6/12/2020 | 5/26/2020 | 61639 | 88607 | 88607 | DSF0000876436, DSF0000876437, DSF0000876438, DSF0000944753, DSF0000960829
2 | M169 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | Design | Complete | 5/26/2020 | 9/18/2020 | 12/30/2020 | 301587 | 180402 | 155833 | DSF0000876436, DSF0000876437, DSF0000876438, DSF0000944753, DSF0000960829
2 | M169 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | Construction | In-Progress | 7/10/2023 | 1/7/2025 |  | 6214007 | 5722517 | 2173666 | DSF0000876436, DSF0000876437, DSF0000876438, DSF0000944753, DSF0000960829
2 | M169 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | CM,F&E | In-Progress | 7/10/2023 | 1/7/2025 |  | 481042 | 473749 | 473749 | DSF0000876436, DSF0000876437, DSF0000876438, DSF0000944753, DSF0000960829
2 | M169 | M169 SPED - MANHATTAN | Fast Track Projects | FY20 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 11/17/2022 | FTK |  | FTK | 107283 | 103296 | DSF0000913089
2 | M169 | M169 SPED - MANHATTAN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 10852 | 0 | DSF0001086246
2 | M169 | M169 SPED - MANHATTAN | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112325
2 | M169 | M169 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 296000 | 0 | DSF0001112828
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Scope | Complete | 10/10/2018 | 12/10/2018 | 12/3/2018 | 0 | 16165 | 16165 | DSF0000890826
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Design | Complete | 12/3/2018 | 4/29/2019 | 4/1/2019 | 36000 | 58475 | 49903 | DSF0000890826
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 6/14/2019 | 3/9/2020 |  | 528000 | 365454 | 352053 | DSF0000890826
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | CM,F&E | In-Progress | 6/14/2019 | 3/9/2020 |  | 36000 | 71088 | 70418 | DSF0000890826
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | NYS IPDVS NEW INSTALLATION | Scope | Complete | 5/11/2023 | 9/12/2023 | 5/26/2023 | 0 | 908 | 908 | DSF0001083973
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | NYS IPDVS NEW INSTALLATION | Design | Complete | 5/26/2023 | 11/24/2023 | 8/30/2023 | 30000 | 3634 | 3634 | DSF0001083973
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | NYS IPDVS NEW INSTALLATION | Construction | In-Progress | 2/9/2024 | 1/3/2025 |  | 440000 | 199047 | 4124 | DSF0001083973
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | NYS IPDVS NEW INSTALLATION | CM,F&E | In-Progress | 2/9/2024 | 1/3/2025 |  | 161302 | 256774 | 192516 | DSF0001083973
2 | M183 | P.S. 183 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112835
2 | M183 | P.S. 183 - MANHATTAN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/14/2022 | DOER |  | DOER | 22009 | 0 | DSF0000961394
2 | M183 | P.S. 183 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/4/2024 | DOES | 7/5/2024 | DOES | 65832 |  | DSF0001084239
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP RESOA | RESO A ROOFTOP PLAYGROUND | Scope | Complete | 10/26/2022 | 3/16/2023 | 1/30/2023 | 0 | 142533 | 89137 | DSF0001035068
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP RESOA | RESO A ROOFTOP PLAYGROUND | Design | Complete | 2/6/2023 | 7/10/2023 | 12/26/2023 | 643687 | 258337 | 27724 | DSF0001035068
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP RESOA | RESO A ROOFTOP PLAYGROUND | Construction | In-Progress | 8/2/2024 | 8/1/2026 |  | 9440749 | 8821545 | 199046 | DSF0001035068
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP RESOA | RESO A ROOFTOP PLAYGROUND | CM,F&E | In-Progress | 8/2/2024 | 8/1/2026 |  | 643687 | 62020 | 60456 | DSF0001035068
2 | M190 | P.S. 290 - MANHATTAN | DIIT - RESOA | FY 14 RESO A SECURITY CAMERAS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 42078 | 0 | DSF0000800321
2 | M190 | P.S. 290 - MANHATTAN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 325000 | 0 | DSF0001112840
2 | M198 | P.S. 77 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/9/2023 | 3/14/2024 | 11/14/2023 | 0 | 4941 | 4941 | DSF0001086266
2 | M198 | P.S. 77 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/14/2023 | 5/10/2024 | 3/5/2024 | 27000 | 19762 | 19762 | DSF0001086266
2 | M198 | P.S. 77 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 396000 | 396000 | 6227 | DSF0001086266
2 | M198 | P.S. 77 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 30740 | 27000 | 4501 | DSF0001086266
2 | M198 | P.S. 198 - MANHATTAN | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/28/2023 | FTK |  | FTK | 141188 | 0 | DSF0000866420
2 | M198 | P.S. 77 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/4/2023 | DIIR | 2/26/2024 | DIIR | 314000 | 314000 | DSF0001035724
2 | M198 | P.S. 77 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112846
2 | M198 | P.S. 198 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112847
2 | M198 | P.S. 198 - MANHATTAN | DOE - RESOA | FY18 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0000866425
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 142335 | 0 | DSF0001007826
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 194507 | 0 | DSF0001007844
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 58813 | 0 | DSF0001035725
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001086265
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112845
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 3/12/2018 | 7/25/2018 | 12/16/2019 | 28750 | 95254 | 93861 | DSF0000960912
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 1/8/2020 | 6/9/2020 | 6/26/2020 | 143751 | 187935 | 120611 | DSF0000960912
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 7/22/2021 | 4/12/2023 |  | 3234403 | 3171243 | 2629577 | DSF0000960912
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 7/22/2021 | 4/12/2023 |  | 201252 | 461369 | 444162 | DSF0000960912
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/10/2024 | 10/9/2024 | 6/14/2024 | 3516 | 978 | 978 | DSF0001087488
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/14/2024 | 12/12/2024 | 12/11/2024 | 15820 | 3912 | 3912 | DSF0001087488
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 203902 | 203902 | 4646 | DSF0001087488
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 42056 | 42056 | 4123 | DSF0001087488
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 7/1/2024 | 9/30/2024 | 8/21/2024 | 30637 | 30057 | 1956 | DSF0001097894
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | In-Progress | 8/22/2024 | 2/28/2025 |  | 142975 | 142975 | 7824 | DSF0001097894
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 2267168 | 2267168 | 0 | DSF0001097894
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 224674 | 224674 | 24519 | DSF0001097894
2 | M234 | P.S. 234 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/13/2017 | EMER |  | EMER | 366821 | 326322 | SCA0000049766
2 | M234 | P.S. 234 - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0000961345
2 | M234 | P.S. 234 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 9/28/2022 | DOES | 11/17/2022 | DOES | 106148 | 104720 | DSF0001009090
2 | M267 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/21/2022 | 7/19/2022 | 4/12/2022 | 3341 | 5686 | 5686 | DSF0001034368
2 | M267 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/12/2022 | 10/5/2022 | 7/19/2022 | 15033 | 22743 | 22743 | DSF0001034368
2 | M267 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 3/9/2023 | 2/1/2024 |  | 193762 | 178974 | 165938 | DSF0001034368
2 | M267 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 3/9/2023 | 2/1/2024 |  | 166229 | 160270 | 116120 | DSF0001034368
2 | M267 | P.S. 267 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/13/2024 | DIIR | 7/22/2024 | DIIR | 126000 | 125525 | DSF0001086270
2 | M267 | P.S. 267 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001112852
2 | M267 | P.S. 267 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/21/2022 | DOER |  | DOER | 79328 | 0 | DSF0001007819
2 | M267 | P.S. 267 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001007832
2 | M267 | P.S. 267 - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 89238 | 0 | DSF0001035731
2 | M271 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/23/2023 | 7/24/2023 | 3/28/2023 | 4130 | 2155 | 2155 | DSF0001034634
2 | M271 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/28/2023 | 9/21/2023 | 5/5/2023 | 18586 | 8619 | 8619 | DSF0001034634
2 | M271 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 2/9/2024 | 1/3/2025 |  | 239549 | 209434 | 160 | DSF0001034634
2 | M271 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 2/9/2024 | 1/3/2025 |  | 114879 | 194923 | 146497 | DSF0001034634
2 | M271 | P.S./I.S. 217 - MANHATTAN | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 35000 | 0 | DSF0000867883
2 | M271 | P.S./I.S. 217 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 7/10/2020 | DIIR |  | DIIR | 35000 | 0 | DSF0000890184
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/24/2022 | DOER |  | DOER | 95603 | 0 | DSF0000961409
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/12/2022 | DOER |  | DOER | 145990 | 0 | DSF0001033191
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 300000 | 9025 | DSF0001086271
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112853
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/11/2024 | DOES | 10/17/2024 | DOES | 50832 |  | DSF0001084647
2 | M276 | P.S./I.S. 276 - MANHATTAN | SCA CIP | IDA INTERIOR SPACES / IDA FLOOD ELIMINATION | Scope | Complete | 1/19/2022 | 5/19/2022 | 4/6/2023 | 18284 | 40597 | 39742 | DSF0001111906, DSF0001111907
2 | M276 | P.S./I.S. 276 - MANHATTAN | SCA CIP | IDA INTERIOR SPACES / IDA FLOOD ELIMINATION | Design | Complete | 4/24/2023 | 10/24/2023 | 2/21/2024 | 82275 | 60573 | 56240 | DSF0001111906, DSF0001111907
2 | M276 | P.S./I.S. 276 - MANHATTAN | SCA CIP | IDA INTERIOR SPACES / IDA FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 1060437 | 1060437 | 160 | DSF0001111906, DSF0001111907
2 | M276 | P.S./I.S. 276 - MANHATTAN | SCA CIP | IDA INTERIOR SPACES / IDA FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 196547 | 196547 | 18504 | DSF0001111906, DSF0001111907
2 | M276 | M094 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001112854
2 | M276 | P.S./I.S. 276 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112855
2 | M276 | P.S./I.S. 276 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086272
2 | M276 | P.S./I.S. 276 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/3/2024 | DOES | 11/19/2024 | DOES | 50832 |  | DSF0001085480
2 | M281 | PS 281 - THE RIVER SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 7/1/2024 | DIIR | 100000 | 100000 | DSF0001086273
2 | M281 | M094 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 50000 | 50000 | DSF0001086274
2 | M281 | M094 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 54000 | 0 | DSF0001112856
2 | M281 | PS 281 - THE RIVER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112857
2 | M281 | PS 281 - THE RIVER SCHOOL | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 85000 | 0 | DSF0001033680
2 | M281 | PS 281 - THE RIVER SCHOOL | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 10/2/2023 | DOER | 11/8/2023 | DOER | 209309 |  | DSF0001035734
2 | M282 | I.S. 896 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/1/2023 | 11/2/2023 | 9/28/2023 | 0 | 15829 | 15829 | DSF0001035735, DSF0001035736
2 | M282 | I.S. 896 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 9/28/2023 | 2/5/2024 | 7/22/2024 | 32212 | 43689 | 41823 | DSF0001035735, DSF0001035736
2 | M282 | I.S. 896 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 472450 | 472450 | 7086 | DSF0001035735, DSF0001035736
2 | M282 | I.S. 896 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 32212 | 33238 | 12980 | DSF0001035735, DSF0001035736
2 | M282 | RICHARD R. GREEN HS OF TEACHING - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033241
2 | M282 | RICHARD R. GREEN HS OF TEACHING - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112858
2 | M282 | I.S. 896 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112859
2 | M282 | URBAN ASSEMBLY SCHOOL - MANHATTAN | DOE - Skilled Trades | AHU CHILLED WATER COIL REPLACEMENT | Construction | Complete | 1/3/2024 | DOES | 6/13/2024 | DOES | 49412 |  | DSF0001111876
2 | M323 | M.S. 297 | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/7/2023 | 3/11/2024 | 6/18/2024 | 0 | 7991 | 7991 | DSF0001086275
2 | M323 | M.S. 297 | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 7/5/2024 | 11/20/2024 |  | 6000 | 24383 | 7089 | DSF0001086275
2 | M323 | M.S. 297 | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001086275
2 | M323 | M.S. 297 | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 2679 | DSF0001086275
2 | M323 | M751 SPED - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 149532 | 0 | DSF0001086276
2 | M338 | P.S. 51 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Scope | Complete | 4/30/2021 | 8/2/2021 | 9/29/2021 | 0 | 7806 | 7806 | DSF0000913333
2 | M338 | P.S. 51 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Design | Complete | 10/1/2021 | 3/24/2022 | 7/15/2022 | 15913 | 29640 | 29640 | DSF0000913333
2 | M338 | P.S. 51 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Construction | In-Progress | 4/17/2023 | 1/11/2024 |  | 233395 | 202051 | 668 | DSF0000913333
2 | M338 | P.S. 51 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | CM,F&E | In-Progress | 4/17/2023 | 1/11/2024 |  | 15913 | 39271 | 38798 | DSF0000913333
2 | M338 | M094 SPED - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001033641
2 | M338 | P.S. 51 - MANHATTAN | DOE - RESOA | FY20 RESO A ROOFTOP PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 52384 | 0 | DSF0000913093
2 | M338 | P.S. 51 - MANHATTAN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 390271 | 0 | DSF0001007805
2 | M338 | P.S. 51 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 50832 | 0 | DSF0001084253
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 3/8/2024 | 7/24/2024 | 11/1/2024 | 12483 | 39366 | 18576 | DSF0001097980
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Design | In-Progress | 11/15/2024 | 4/21/2025 |  | 62414 | 62414 | 8011 | DSF0001097980
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 1404325 | 1404325 | 65820 | DSF0001097980
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 87380 | 87380 | 21421 | DSF0001097980
2 | M340 | M094 SPED - MANHATTAN | Fast Track Projects | FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 5/17/2022 | FTK |  | FTK | 131361 | 121636 | DSF0000913335
2 | M340 | M094 SPED - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 50000 | 10439 | DSF0001033642
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/9/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001035737
2 | M340 | M094 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112861
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001112862
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 233693 | 0 | DSF0001086277
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/22/2024 | DOES | 10/23/2024 | DOES | 50832 |  | DSF0001084254
2 | M343 | P.S. 343 - MANHATTAN | Fast Track Projects | FY23 RESO A ROOFING | Construction | In-Progress | 4/3/2024 | FTK |  | FTK | 142011 | 106052 | DSF0001035738
2 | M343 | P.S. 343 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/10/2024 | DOES | 12/5/2024 | DOES | 50832 |  | DSF0001084255
2 | M391 | DISTRICT 2 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113617
2 | M391 | DISTRICT 2 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113617
2 | M391 | DISTRICT 2 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113617
2 | M391 | DISTRICT 2 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113617
2 | M391 | DISTRICT 2 PRE-K CENTER | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0 | DSF0001086280
2 | M391 | DISTRICT 2 PRE-K CENTER | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 213000 | 0 | DSF0001112864
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | DEFECTIVE POOL FOUNDATION WALLS | Scope | Complete | 6/17/2015 | 11/17/2015 | 6/22/2016 | 176680 | 154529 | 154529 | DSF0000821943
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | DEFECTIVE POOL FOUNDATION WALLS | Design | Complete | 4/16/2019 | 10/18/2019 | 6/30/2020 | 883400 | 521017 | 480422 | DSF0000821943
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | DEFECTIVE POOL FOUNDATION WALLS | Construction | PNS | PNS | PNS | PNS | 19876500 | 19876500 | 275416 | DSF0000821943
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | DEFECTIVE POOL FOUNDATION WALLS | CM,F&E | PNS | PNS | PNS | PNS | 1236760 | 1236760 | 70556 | DSF0000821943
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Scope | Complete | 8/1/2018 | 12/18/2018 | 11/21/2018 | 98775 | 132497 | 132497 | DSF0000899747, DSF0000899743, DSF0000912286
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Design | Complete | 2/6/2019 | 7/9/2019 | 9/18/2019 | 492101 | 415753 | 376638 | DSF0000899747, DSF0000899743, DSF0000912286
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Construction | In-Progress | 11/16/2020 | 11/15/2022 |  | 10918714 | 12855545 | 11571191 | DSF0000899747, DSF0000899743, DSF0000912286
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | CM,F&E | In-Progress | 11/16/2020 | 11/15/2022 |  | 704739 | 1236111 | 1197226 | DSF0000899747, DSF0000899743, DSF0000912286
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/16/2020 | 10/15/2020 | 6/22/2020 | 3418 | 6911 | 6911 | DSF0000960798
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/22/2020 | 12/17/2020 | 12/23/2020 | 15380 | 27643 | 27643 | DSF0000960798
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/24/2022 | 3/19/2023 |  | 198231 | 190677 | 166368 | DSF0000960798
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/24/2022 | 3/19/2023 |  | 206690 | 229046 | 224210 | DSF0000960798
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 7/12/2018 | EMER |  | EMER | 132662 | 119143 | SCA0000052647
2 | M440 | QUEST TO LEARN - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033222
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112865
2 | M440 | QUEST TO LEARN - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001112867
2 | M440 | LANDMARK HS - MANHATTAN | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 4/8/2016 | DOER |  | DOER | 84401 | 0 | DSF0000800468
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - RESOA | FY19 RESO A AUDITORIUM SUPPLEMENTAL COOLING | Construction | In-Progress | 5/24/2019 | DOER |  | DOER | 900052 | 0 | DSF0000912578
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 3/7/2022 | DOER |  | DOER | 37177 | 0 | DSF0000913338
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 3/5/2024 | DOER |  | DOER | 665711 | 0 | DSF0001007812
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086283
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 8/21/2023 | DOES | 11/16/2023 | DOES | 70047 |  | DSF0000866123
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/15/2022 | DOES | 11/30/2023 | DOES | 181274 | 177722 | DSF0001034245
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/10/2024 | DOES | 65832 | 21259 | DSF0001084952
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | DOE - Skilled Trades | CONDENSATE PUMP REPLACEMENT | Construction | In-Progress | 8/18/2023 | DOES |  | DOES | 395156 | 0 | DSF0001070326
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/6/2024 | DOES |  | DOES | 606170 | 0 | DSF0001085743
2 | M444 | DISTRICT 2 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/29/2024 | DOES | 10/15/2024 | DOES | 50832 | 6390 | DSF0001085483
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | FY25 RESO A SOLAR PANEL INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112868
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | FY25 RESO A SOLAR PANEL INSTALLATION | Design | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0001112868
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | FY25 RESO A SOLAR PANEL INSTALLATION | Construction | PNS | PNS | PNS | PNS | 66000 | 66000 | 0 | DSF0001112868
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | FY25 RESO A SOLAR PANEL INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0001112868
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A SOLAR PANEL INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113618
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A SOLAR PANEL INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113618
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A SOLAR PANEL INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113618
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A SOLAR PANEL INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113618
2 | M445 | LOWER MANHATTAN ARTS - MANHATTAN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/17/2021 | 4/22/2022 | 7/5/2022 | 0 | 19448 | 19448 | DSF0000961352, DSF0001007745
2 | M445 | LOWER MANHATTAN ARTS - MANHATTAN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 7/5/2022 | 11/2/2022 | 11/2/2022 | 125400 | 134578 | 96499 | DSF0000961352, DSF0001007745
2 | M445 | LOWER MANHATTAN ARTS - MANHATTAN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | Complete | 1/16/2024 | 1/14/2025 | 10/11/2024 | 1839200 | 1745890 | 1681431 | DSF0000961352, DSF0001007745
2 | M445 | LOWER MANHATTAN ARTS - MANHATTAN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 1/16/2024 | 1/14/2025 | 10/11/2024 | 125400 | 79705 | 74387 | DSF0000961352, DSF0001007745
2 | M445 | NEW DESIGN HS - MANHATTAN | SCA IEH | PO18-ABATEMENT OF PIPE ISULATION IN ROOM 419 AREA IS MARKED. PLEASE EXPEDITE BECAUSE ALL THE CORNERS | Construction | Complete | 10/18/2024 | IEH | 10/26/2024 | IEH | 0 | 0 | SCA0000073519
2 | M445 | DUAL LANGUAGE HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112869
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 9/30/2023 | DOER |  | DOER | 121089 | 0 | DSF0001007783
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | DOE - RESOA | RESO A SWIMMING POOL UPGRADE | Construction | In-Progress | 11/3/2023 | DOER |  | DOER | 135662 | 0 | DSF0001083741
2 | M445 | NEW DESIGN HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084953
2 | M447 | ESSEX STREET ACADEMY - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001112870
2 | M451 | LIBERTY HS ACADEMY FOR NEWCOMERS-M | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000889897
2 | M451 | LIBERTY HS ACADEMY FOR NEWCOMERS-M | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/3/2024 | DIIR | 10/17/2024 | DIIR | 75000 | 75000 | DSF0001033237
2 | M451 | LIBERTY HS ACADEMY FOR NEWCOMERS-M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/1/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084955
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 8/20/2020 | 12/18/2020 | 6/18/2021 | 198200 | 240797 | 191961 | DSF0000961124, DSF0000994059, DSF0001009247
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 6/30/2021 | 11/30/2021 | 12/20/2021 | 991001 | 903768 | 732405 | DSF0000961124, DSF0000994059, DSF0001009247
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 7/17/2023 | 7/15/2025 |  | 22297501 | 21214821 | 4729835 | DSF0000961124, DSF0000994059, DSF0001009247
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 7/17/2023 | 7/15/2025 |  | 1387695 | 411770 | 409203 | DSF0000961124, DSF0000994059, DSF0001009247
2 | M460 | ACADEMY FOR SOFTWARE ENGINEERING - MANHATTAN | SCA CIP RESOA | FY24 RESO A MOBILE SCIENCE LABS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086286
2 | M460 | ACADEMY FOR SOFTWARE ENGINEERING - MANHATTAN | SCA CIP RESOA | FY24 RESO A MOBILE SCIENCE LABS | Design | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0001086286
2 | M460 | ACADEMY FOR SOFTWARE ENGINEERING - MANHATTAN | SCA CIP RESOA | FY24 RESO A MOBILE SCIENCE LABS | Construction | PNS | PNS | PNS | PNS | 44000 | 44000 | 0 | DSF0001086286
2 | M460 | ACADEMY FOR SOFTWARE ENGINEERING - MANHATTAN | SCA CIP RESOA | FY24 RESO A MOBILE SCIENCE LABS | CM,F&E | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0001086286
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113619
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113619
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113619
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113619
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Scope | In-Progress | 12/12/2023 | 4/12/2024 |  | 0 | 59584 | 1373 | DSF0001086285
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Design | PNS | PNS | PNS | PNS | 227691 | 168107 | 5494 | DSF0001086285
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | 3339471 | 3630000 | 0 | DSF0001086285
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP RESOA | FY24 RESO A SUPPLEMENTAL COOLING | CM,F&E | PNS | PNS | PNS | PNS | 227691 | 247500 | 2987 | DSF0001086285
2 | M460 | INT'L HS AT UNION SQUARE - MANHATTAN | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 6/11/2024 |  |  | 50000 | 50000 | 43276 | DSF0000961308
2 | M460 | ACADEMY FOR SOFTWARE ENGINEERING - MANHATTAN | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 11/5/2021 | FTK |  | FTK | 487145 | 416163 | DSF0001008924
2 | M460 | INT'L HS AT UNION SQUARE - MANHATTAN | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 8/25/2021 | FTK |  | FTK | 1975639 | 1701616 | DSF0001008923
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000961301
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033208
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 6/6/2024 | DIIR | 159749 | 159749 | DSF0001035747
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112872
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001112873
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112874
2 | M460 | INT'L HS AT UNION SQUARE - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112875
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DOE - RESOA | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/5/2024 | DOER |  | DOER | 310141 | 0 | DSF0000866344
2 | M460 | INT'L HS AT UNION SQUARE - MANHATTAN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 3/9/2023 | DOER |  | DOER | 578508 | 0 | DSF0000961319
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 5/19/2023 | DOER |  | DOER | 255755 | 0 | DSF0001033693
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001035743
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086288
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112871
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | DOE - RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112876
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/23/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084956
2 | M460 | WASHINGTON IRVING HS - MANHATTAN | DOE - Skilled Trades | WATER MAIN LEAK REPAIR | Construction | In-Progress | 5/17/2024 | DOES |  | DOES | 65000 | 0 | DSF0001104157
2 | M464 | P.S. 150 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/31/2024 | DOES | 12/5/2024 | DOES | 50832 |  | DSF0001084256
2 | M471 | DISTRICT 2 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/29/2024 | DOES | 9/3/2024 | DOES | 65832 | 9768 | DSF0001085484
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 5/21/2020 | 1/29/2021 | 10/27/2020 | 37305 | 105678 | 105678 | DSF0000890579, DSF0000994124
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 11/24/2020 | 7/28/2021 | 12/13/2021 | 180483 | 378860 | 378860 | DSF0000890579, DSF0000994124
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 8/15/2022 | 12/14/2023 |  | 3537910 | 3673299 | 3523468 | DSF0000890579, DSF0000994124
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 8/15/2022 | 12/14/2023 |  | 306482 | 239775 | 239571 | DSF0000890579, DSF0000994124
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 1/27/2020 | 12/13/2021 | 11/9/2021 | 277969 | 186338 | 186338 | DSF0000945333, DSF0000994130, DSF0001009309, DSF0001019732, DSF0001019733, DSF0001034529
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/9/2021 | 1/20/2022 | 5/12/2023 | 1388986 | 715478 | 599320 | DSF0000945333, DSF0000994130, DSF0001009309, DSF0001019732, DSF0001019733, DSF0001034529
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 8/7/2023 | 2/1/2026 |  | 31177883 | 28116370 | 3650156 | DSF0000945333, DSF0000994130, DSF0001009309, DSF0001019732, DSF0001019733, DSF0001034529
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 8/7/2023 | 2/1/2026 |  | 1952963 | 230574 | 229624 | DSF0000945333, DSF0000994130, DSF0001009309, DSF0001019732, DSF0001019733, DSF0001034529
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | Fast Track Projects | PATH OF TRAVEL LSP CTF ROOM CONVERSION | Construction | In-Progress | 12/6/2021 | FTK |  | FTK | 208057 | 170139 | DSF0000912267
2 | M475 | INSTITUTE FOR COLLABORATIVE ED - M | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 4/1/2020 | DIIR |  | DIIR | 35000 | 0 | DSF0000890208
2 | M475 | INSTITUTE FOR COLLABORATIVE ED - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 60000 | 59772 | DSF0001086292
2 | M475 | M226 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112886
2 | M475 | INSTITUTE FOR COLLABORATIVE ED - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112887
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0 | DSF0001086293
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112885
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/19/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084959
2 | M477 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | Scope | Complete | 6/28/2018 | 8/2/2019 | 3/2/2021 | 111561 | 297070 | 297070 | DSF0000877020, DSF0000899905, DSF0000899889, DSF0000945339
2 | M477 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | Design | Complete | 3/2/2021 | 8/31/2021 | 6/8/2021 | 557801 | 934033 | 659195 | DSF0000877020, DSF0000899905, DSF0000899889, DSF0000945339
2 | M477 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | Construction | In-Progress | 3/10/2023 | 3/8/2026 |  | 12550500 | 11267633 | 6026237 | DSF0000877020, DSF0000899905, DSF0000899889, DSF0000945339
2 | M477 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | CM,F&E | In-Progress | 3/10/2023 | 3/8/2026 |  | 780920 | 116513 | 116234 | DSF0000877020, DSF0000899905, DSF0000899889, DSF0000945339
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/31/2018 | DOER |  | DOER | 69832 | 0 | DSF0000822281
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY17 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 2/28/2017 | DOER |  | DOER | 512808 | 0 | DSF0000844212
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 7/20/2022 | DOER |  | DOER | 852255 | 0 | DSF0000866395
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY22 RESO A RECORDING STUDIO | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 666277 | 0 | DSF0001033225
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0001086294
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086295
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112888
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | Scope | Complete | 3/5/2021 | 7/20/2021 | 1/25/2022 | 198437 | 442128 | 421448 | DSF0000945365, DSF0000945367, DSF0000945368, DSF0001019789, DSF0001019774, DSF0001034507
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | Design | Complete | 1/25/2022 | 6/24/2022 | 5/12/2022 | 982629 | 844302 | 844302 | DSF0000945365, DSF0000945367, DSF0000945368, DSF0001019789, DSF0001019774, DSF0001034507
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | Construction | In-Progress | 8/15/2022 | 8/13/2024 |  | 21282452 | 20144552 | 16968497 | DSF0000945365, DSF0000945367, DSF0000945368, DSF0001019789, DSF0001019774, DSF0001034507
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | CM,F&E | In-Progress | 8/15/2022 | 8/13/2024 |  | 1460742 | 1036968 | 1025477 | DSF0000945365, DSF0000945367, DSF0000945368, DSF0001019789, DSF0001019774, DSF0001034507
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | Scope | Complete | 9/11/2020 | 1/20/2021 | 12/15/2021 | 32665 | 48211 | 48211 | DSF0000961104, DSF0001019766
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | Design | Complete | 12/15/2021 | 5/18/2022 | 9/30/2022 | 159563 | 220247 | 190979 | DSF0000961104, DSF0001019766
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | Construction | In-Progress | 8/4/2023 | 2/1/2025 |  | 3264430 | 3899590 | 2028969 | DSF0000961104, DSF0001019766
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | CM,F&E | In-Progress | 8/4/2023 | 2/1/2025 |  | 256902 | 459504 | 450667 | DSF0000961104, DSF0001019766
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 2/1/2023 | 6/2/2023 | 6/15/2023 | 0 | 23389 | 23370 | DSF0001035763, DSF0001035764
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | Complete | 6/15/2023 | 11/2/2023 | 1/24/2024 | 234785 | 121049 | 99392 | DSF0001035763, DSF0001035764
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | In-Progress | 7/18/2024 | 1/8/2026 |  | 3443514 | 2493807 | 3107 | DSF0001035763, DSF0001035764
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | In-Progress | 7/18/2024 | 1/8/2026 |  | 234785 | 82297 | 81273 | DSF0001035763, DSF0001035764
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 6/15/2022 | 7/9/2024 | 6/28/2024 | 0 | 26730 | 26730 | DSF0001033712, DSF0001087044
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 6/28/2024 | 10/31/2024 | 10/23/2024 | 82460 | 79109 | 23054 | DSF0001033712, DSF0001087044
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1209416 | 1209416 | 60374 | DSF0001033712, DSF0001087044
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 82460 | 82460 | 40383 | DSF0001033712, DSF0001087044
2 | M480 | P.S. 225 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/31/2018 | EMER |  | EMER | 86719 | 86719 | SCA0000050465
2 | M480 | VANGUARD HS - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001007846
2 | M480 | M226 SPED - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/1/2023 | DIIR | 4/17/2024 | DIIR | 50000 | 50000 | DSF0001033676
2 | M480 | VANGUARD HS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 50000 | 0 | DSF0001033703
2 | M480 | M226 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/9/2024 | DIIR | 7/18/2024 | DIIR | 50000 | 50000 | DSF0001035753
2 | M480 | URBAN ACADEMY LABORATORY HS - M | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035757
2 | M480 | VANGUARD HS - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086298
2 | M480 | MANHATTAN INTERNATIONAL HS - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/12/2024 | DIIR | 7/10/2024 | DIIR | 50000 | 50000 | DSF0001086299
2 | M480 | URBAN ACADEMY LABORATORY HS - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 50000 | 49812 | DSF0001086300
2 | M480 | P.S. 225 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 50000 | 45560 | DSF0001086301
2 | M480 | M226 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086302
2 | M480 | P.S. 225 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112889
2 | M480 | M226 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112890
2 | M480 | VANGUARD HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112891
2 | M480 | MANHATTAN INTERNATIONAL HS - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112892
2 | M480 | TALENT UNLIMITED HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112893
2 | M480 | URBAN ACADEMY LABORATORY HS - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112894
2 | M480 | TALENT UNLIMITED HS - MANHATTAN | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/24/2018 | DOER |  | DOER | 241208 | 0 | DSF0000822321
2 | M480 | TALENT UNLIMITED HS - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/3/2023 | DOER |  | DOER | 315391 | 0 | DSF0001086297
2 | M480 | P.S. 225 - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 10/12/2023 | DOES |  | DOES | 1156470 | 325233 | DSF0001070503
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS / WINDOWS | Scope | Complete | 10/15/2018 | 3/5/2019 | 4/12/2019 | 90044 | 180570 | 180570 | DSF0000877067, DSF0000877069, DSF0000877070, DSF0000899958, DSF0000899960
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS / WINDOWS | Design | Complete | 4/12/2019 | 9/12/2019 | 6/30/2020 | 437233 | 351036 | 343171 | DSF0000877067, DSF0000877069, DSF0000877070, DSF0000899958, DSF0000899960
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS / WINDOWS | Construction | PNS | PNS | PNS | PNS | 8714249 | 8714249 | 38539 | DSF0000877067, DSF0000877069, DSF0000877070, DSF0000899958, DSF0000899960
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 727725 | 727725 | 61295 | DSF0000877067, DSF0000877069, DSF0000877070, DSF0000899958, DSF0000899960
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | Fast Track Projects | LSP - FY22 RESO A ELECTRICAL UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 192845 | 34865 | DSF0001033715
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086304
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/12/2022 | DOES |  | DOES | 73822 | 540468 | DSF0001019820
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/25/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084963
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY20 RESO A GREENROOF | Scope | Complete | 10/30/2019 | 4/3/2020 | 3/10/2020 | 0 | 28662 | 28662 | DSF0000912749
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY20 RESO A GREENROOF | Design | Complete | 3/11/2020 | 8/10/2020 | 8/23/2022 | 194775 | 127213 | 121352 | DSF0000912749
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY20 RESO A GREENROOF | Construction | In-Progress | 3/20/2023 | 9/9/2024 |  | 2856700 | 2708240 | 579288 | DSF0000912749
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY20 RESO A GREENROOF | CM,F&E | In-Progress | 3/20/2023 | 9/9/2024 |  | 194775 | 305659 | 296905 | DSF0000912749
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/12/2023 | 3/14/2024 | 9/19/2024 | 0 | 11144 | 889 | DSF0001086305
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 9/26/2024 | 2/14/2025 |  | 30000 | 18856 | 3556 | DSF0001086305
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001086305
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 22353 | DSF0001086305
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 7/8/2024 | 10/7/2024 |  | 0 | 61 | 61 | DSF0001087046
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 243 | 243 | DSF0001087046
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087046
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 168 | 168 | DSF0001087046
2 | M488 | P.S. 59 - MANHATTAN | SCA Emergency Response | EMERGENCY- FACADE INVESTIGATION @ M488 | Construction | Complete | 6/5/2023 | EMER | 11/22/2023 | EMER | 582115 | 386130 | SCA0000072052
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000866505
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112896
2 | M488 | P.S. 59 - MANHATTAN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/23/2020 | DOER |  | DOER | 123066 | 0 | DSF0000913343
2 | M488 | P.S. 59 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 60000 | 0 | DSF0001033633
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 68527 | 0 | DSF0001033723
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001033724
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001035761
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 9/27/2023 | DOER |  | DOER | 254242 | 0 | DSF0001035762
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 130000 | 0 | DSF0001086306
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - Skilled Trades | IP DIGITAL VIDEO SURVEILLANCE SYSTE | Construction | In-Progress | 5/23/2014 | DOES |  | DOES | 83000 | 0 | DSF0000799890
2 | M491 | DISTRICT 2 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/10/2024 | DOES | 10/15/2024 | DOES | 50832 |  | DSF0001085485
2 | M493 | P.S. @ 2 HUDSON SQUARE - MANHATTAN | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/19/2018 | 10/9/2018 | 1/25/2021 | 661838 | 837011 | 834915 | DSF0000798236
2 | M493 | P.S. @ 2 HUDSON SQUARE - MANHATTAN | SCA Capacity | NEW SCHOOL | Design | Complete | 1/26/2021 | 4/10/2019 | 4/4/2023 | 2647352 | 1458404 | 1367678 | DSF0000798236
2 | M493 | P.S. @ 2 HUDSON SQUARE - MANHATTAN | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 36566551 | 36566551 | 26595 | DSF0000798236
2 | M493 | P.S. @ 2 HUDSON SQUARE - MANHATTAN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 4798326 | 4798326 | 195836 | DSF0000798236
2 | M508 | M000 - MANHATTAN | SCA IEH | PO18- SAFE ACCESS ABATEMENT | Construction | Complete | 10/23/2024 | IEH | 11/5/2024 | IEH | 0 | 0 | SCA0000073506
2 | M508 | M000 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/8/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085486
2 | M512 | M000 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/23/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085487
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | Scope | Complete | 11/18/2020 | 2/16/2021 | 5/7/2021 | 71190 | 119477 | 119477 | DSF0001019951, DSF0001019957
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | Design | Complete | 5/18/2021 | 10/19/2021 | 12/17/2021 | 355950 | 354107 | 325791 | DSF0001019951, DSF0001019957
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | Construction | In-Progress | 9/5/2022 | 9/3/2024 |  | 8008876 | 8691756 | 7481777 | DSF0001019951, DSF0001019957
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | CM,F&E | In-Progress | 9/5/2022 | 9/3/2024 |  | 498330 | 354530 | 329291 | DSF0001019951, DSF0001019957
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | GENERATOR REPLACEMENT / NEW GAS METER ROOM | Scope | Complete | 3/5/2021 | 7/6/2021 | 3/5/2021 | 18902 | 2734 | 2734 | DSF0000945528, DSF0000945529
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | GENERATOR REPLACEMENT / NEW GAS METER ROOM | Design | Complete | 3/5/2021 | 8/4/2021 | 2/23/2023 | 85062 | 10932 | 10932 | DSF0000945528, DSF0000945529
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | GENERATOR REPLACEMENT / NEW GAS METER ROOM | Construction | PNS | PNS | PNS | PNS | 1096346 | 3562031 | 271042 | DSF0000945528, DSF0000945529
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | GENERATOR REPLACEMENT / NEW GAS METER ROOM | CM,F&E | PNS | PNS | PNS | PNS | 203203 | 203203 | 102832 | DSF0000945528, DSF0000945529
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | Scope | Complete | 7/6/2021 | 11/19/2021 | 10/25/2021 | 151512 | 92464 | 92464 | DSF0000994327, DSF0000994328, DSF0001019950
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | Design | Complete | 11/24/2021 | 4/28/2022 | 5/11/2022 | 754168 | 433484 | 380453 | DSF0000994327, DSF0000994328, DSF0001019950
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | Construction | In-Progress | 1/4/2024 | 1/2/2026 |  | 16675372 | 15052966 | 3852098 | DSF0000994327, DSF0000994328, DSF0001019950
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | CM,F&E | In-Progress | 1/4/2024 | 1/2/2026 |  | 1086024 | 143921 | 141191 | DSF0000994327, DSF0000994328, DSF0001019950
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | Scope | Complete | 3/9/2022 | 5/13/2022 | 9/12/2022 | 20950 | 7327 | 7327 | DSF0001034382
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | Design | Complete | 9/13/2022 | 1/13/2023 | 1/27/2023 | 104750 | 164761 | 164761 | DSF0001034382
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | Construction | Complete | 6/5/2023 | 10/1/2024 | 10/1/2024 | 2356875 | 2187293 | 1405202 | DSF0001034382
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | CM,F&E | Complete | 6/5/2023 | 10/1/2024 | 10/1/2024 | 146650 | 81878 | 80181 | DSF0001034382
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA IEH | PO18-ABATE EXISTING VCT TILES AND FLOOR MOUNTED CONDUITS IN RM B43 RM B43 TO ACCOMMODATE NEW AMBULAN | Construction | Complete | 9/26/2024 | IEH | 10/4/2024 | IEH | 0 | 0 | SCA0000073439
2 | M520 | BERGTRAUM HS - MANHATTAN | Fast Track Projects | LSP- LIGHTING UPGRADE | Construction | In-Progress | 2/21/2023 | FTK |  | FTK | 315936 | 207817 | DSF0001034385
2 | M520 | BERGTRAUM HS - MANHATTAN | Fast Track Projects | LSP- CEILING AND LIGHTING UPGRADE | Construction | In-Progress | 2/21/2023 | FTK |  | FTK | 449207 | 345168 | DSF0001034386
2 | M520 | BERGTRAUM HS - MANHATTAN | Fast Track Projects | LSP- GYMNASIUM UPGRADE | Construction | In-Progress | 5/1/2023 | FTK |  | FTK | 438062 | 385981 | DSF0001034384
2 | M520 | BERGTRAUM HS - MANHATTAN | Fast Track Projects | LSP- AUDITORIUM UPGRADE | Construction | In-Progress | 1/23/2023 | FTK |  | FTK | 589049 | 482659 | DSF0001034383
2 | M520 | URBAN ASSEMBLY MAKER ACADEMY | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033198
2 | M520 | URBAN ASSEMBLY MAKER ACADEMY | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 334291 | 0 | DSF0001035771
2 | M520 | THE URBAN ASSEMBLY EARLY COLLEGE HIGH SCHOOL OF EMERGENCY MEDICINE | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 190214 | 0 | DSF0001086310
2 | M520 | THE URBAN ASSEMBLY EARLY COLLEGE HIGH SCHOOL OF EMERGENCY MEDICINE | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112899
2 | M520 | BERGTRAUM HS - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 7/23/2019 | DOES |  | DOES | 601173 | 97181 | DSF0000877174
2 | M520 | BERGTRAUM HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/7/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084969
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | ATHLETIC FIELD UPGRADE | Scope | Complete | 8/15/2019 | 2/3/2020 | 1/24/2020 | 83930 | 144894 | 144894 | DSF0000900081
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | ATHLETIC FIELD UPGRADE | Design | In-Progress | 4/18/2022 | 10/11/2022 |  | 419648 | 459812 | 287067 | DSF0000900081
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | ATHLETIC FIELD UPGRADE | Construction | PNS | PNS | PNS | PNS | 9442071 | 9442071 | 159874 | DSF0000900081
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | ATHLETIC FIELD UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 587507 | 587507 | 41789 | DSF0000900081
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | FIELD HOUSE | Scope | Complete | 6/18/2024 | 10/18/2024 | 12/13/2024 | 218485 | 89952 | 9121 | DSF0001112060
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | FIELD HOUSE | Design | In-Progress | 12/18/2024 | 7/18/2025 |  | 1019598 | 1019598 | 36482 | DSF0001112060
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | FIELD HOUSE | Construction | PNS | PNS | PNS | PNS | 16167911 | 16167911 | 11323 | DSF0001112060
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | FIELD HOUSE | CM,F&E | PNS | PNS | PNS | PNS | 1602225 | 1602225 | 74906 | DSF0001112060
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | DEMOLITION OF EXISTING FIELD HOUSE | Scope | Complete | 10/8/2024 | 1/8/2025 | 12/13/2024 | 16780 | 308 | 308 | DSF0001113801
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | DEMOLITION OF EXISTING FIELD HOUSE | Design | In-Progress | 12/24/2024 | 4/11/2025 |  | 67122 | 67122 | 1233 | DSF0001113801
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | DEMOLITION OF EXISTING FIELD HOUSE | Construction | PNS | PNS | PNS | PNS | 964872 | 964872 | 0 | DSF0001113801
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | DEMOLITION OF EXISTING FIELD HOUSE | CM,F&E | PNS | PNS | PNS | PNS | 247511 | 247511 | 339 | DSF0001113801
2 | M523 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | Scope | Complete | 11/1/2021 | 12/21/2021 | 1/31/2022 | 216951 | 326806 | 202242 | DSF0001034161
2 | M523 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | Design | Complete | 2/1/2022 | 2/18/2022 | 4/5/2023 | 976282 | 694028 | 570702 | DSF0001034161
2 | M523 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | Construction | In-Progress | 10/18/2023 | 9/3/2024 |  | 12311996 | 13276639 | 12791721 | DSF0001034161
2 | M523 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | CM,F&E | In-Progress | 10/18/2023 | 9/3/2024 |  | 1887927 | 574921 | 1357946 | DSF0001034161
2 | M524 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | Scope | Complete | 2/4/2022 | 3/4/2022 | 3/11/2022 | 268658 | 265637 | 247613 | DSF0001034356
2 | M524 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | Design | Complete | 3/14/2022 | 6/10/2022 | 2/6/2023 | 1208963 | 1326615 | 1088431 | DSF0001034356
2 | M524 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | Construction | Complete | 2/27/2023 | 9/3/2023 | 11/25/2024 | 15246363 | 16050653 | 15256723 | DSF0001034356
2 | M524 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | CM,F&E | Complete | 2/27/2023 | 9/3/2023 | 11/25/2024 | 2149267 | 711945 | 1514235 | DSF0001034356
2 | M533 | HARBOR HIGH SCHOOL ATHLETIC COMPLEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Scope | Complete | 10/4/2022 | 2/1/2023 | 2/1/2023 | 2396800 | 1419308 | 1358599 | DSF0001008866
2 | M533 | HARBOR HIGH SCHOOL ATHLETIC COMPLEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Design | Complete | 2/2/2023 | 10/4/2023 | 5/9/2024 | 10785600 | 4914251 | 4704241 | DSF0001008866
2 | M533 | HARBOR HIGH SCHOOL ATHLETIC COMPLEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 11/13/2024 | 9/3/2027 |  | 136018400 | 120522564 | 417867 | DSF0001008866
2 | M533 | HARBOR HIGH SCHOOL ATHLETIC COMPLEX - MANHATTAN | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 11/13/2024 | 9/3/2027 |  | 19174400 | 7244010 | 518737 | DSF0001008866
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 11/10/2021 | 3/31/2022 | 1/25/2022 | 160567 | 133630 | 133630 | DSF0001019987, DSF0001019985, DSF0001019986
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 2/1/2022 | 7/1/2022 | 5/12/2022 | 793146 | 553452 | 518389 | DSF0001019987, DSF0001019985, DSF0001019986
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 7/18/2022 | 7/16/2024 |  | 17007903 | 15621792 | 14463102 | DSF0001019987, DSF0001019985, DSF0001019986
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 7/18/2022 | 7/16/2024 |  | 1196615 | 1101004 | 1099232 | DSF0001019987, DSF0001019985, DSF0001019986
2 | M535 | URBAN ASSEMBLY HS - MANHATTAN | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 100000 | 100000 | 0 | DSF0001033203
2 | M535 | FACING HISTORY SCHOOL - MANHATTAN | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 77000 | 77000 | 0 | DSF0001034994
2 | M535 | FOOD AND FINANCE HS - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001007815
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 650000 | 0 | DSF0001035772
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 7/3/2019 | DOES |  | DOES | 5555 | 139963 | DSF0000900100
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/25/2024 | DOES | 12/13/2024 | DOES | 65832 |  | DSF0001084970
2 | M600 | FASHION INDUSTRIES VOC HS - M | SCA IEH | PO18-WE WILL NEED APPROXIMATELY 5 TO 6 FEET OF PIPING ABATED IN THE CEILING OF ROOM 702. AREAS ARE M | Construction | Complete | 7/23/2024 | IEH | 8/16/2024 | IEH | 0 | 0 | SCA0000073168
2 | M600 | FASHION INDUSTRIES VOC HS - M | SCA IEH | PO18-ABATEMENT OF PIPE INSULATION STORAGE SPACE B1 (SPACE ID 1001) APPROXIMATELY 10 FEET AND PAINTED | Construction | Complete | 9/10/2024 | IEH | 9/28/2024 | IEH | 0 | 0 | SCA0000073366
2 | M600 | FASHION INDUSTRIES VOC HS - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112901
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - RESOA | FY17 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/29/2018 | DOER |  | DOER | 74401 | 0 | DSF0000844215
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 424824 | 0 | DSF0000913100
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/9/2021 | DOER |  | DOER | 224140 | 0 | DSF0000961398
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/5/2023 | DOER |  | DOER | 78745 | 0 | DSF0001086314
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/13/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084972
2 | M600 | M751 SPED - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/14/2023 | DOES |  | DOES | 704438 | 0 | DSF0001085747
2 | M615 | CHELSEA VOC HS - MANHATTAN | SCA IEH | PO18-ROOM 405A ABATE APPROX 10 SQ. FT. LOOSE AND BROKEN FLOOR TILES, ENCAPSULATE FLOOR | Construction | Complete | 6/27/2024 | IEH | 11/3/2024 | IEH | 0 | 0 | SCA0000073096
2 | M615 | CHELSEA VOCATIONAL H.S. | DOE - RESOA | FY09 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 78577 | 0 | DSF0000623118
2 | M615 | NYC ISCHOOL - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/19/2024 | DOER |  | DOER | 150000 | 9025 | DSF0001086315
2 | M615 | CHELSEA VOC HS - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 8/21/2023 | DOES | 10/23/2023 | DOES | 62070 |  | DSF0000866125
2 | M615 | CHELSEA VOC HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/21/2024 | DOES | 8/28/2024 | DOES | 65832 |  | DSF0001084973
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 10/2/2015 | 2/23/2016 | 4/25/2016 | 176283 | 197110 | 197110 | DSF0000822668, DSF0000891037, DSF0000877297, DSF0000877298, DSF0000877299
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS | Design | Complete | 10/10/2018 | 3/15/2019 | 5/2/2019 | 865743 | 507479 | 487077 | DSF0000822668, DSF0000891037, DSF0000877297, DSF0000877298, DSF0000877299
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS | Construction | PNS | PNS | PNS | PNS | 18965971 | 18965971 | 461479 | DSF0000822668, DSF0000891037, DSF0000877297, DSF0000877298, DSF0000877299
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1257488 | 1257488 | 43974 | DSF0000822668, DSF0000891037, DSF0000877297, DSF0000877298, DSF0000877299
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | Scope | Complete | 11/23/2016 | 3/29/2017 | 4/20/2017 | 258990 | 138919 | 138919 | DSF0000832752, DSF0000877293, DSF0000877313
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | Design | Complete | 10/10/2018 | 3/15/2019 | 5/10/2019 | 1035960 | 814645 | 676177 | DSF0000832752, DSF0000877293, DSF0000877313
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | Construction | Complete | 5/21/2021 | 5/19/2024 | 7/31/2024 | 19424250 | 18286436 | 17022401 | DSF0000832752, DSF0000877293, DSF0000877313
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | CM,F&E | Complete | 5/21/2021 | 5/19/2024 | 7/31/2024 | 1208621 | 1161473 | 1136730 | DSF0000832752, DSF0000877293, DSF0000877313
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | Scope | Complete | 9/11/2019 | 1/13/2020 | 12/18/2019 | 8140 | 11171 | 11171 | DSF0000912803
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | Design | Complete | 1/8/2020 | 6/15/2020 | 6/30/2020 | 36630 | 40469 | 36724 | DSF0000912803
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | Construction | In-Progress | 3/30/2022 | 12/24/2022 |  | 472120 | 483127 | 378000 | DSF0000912803
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | CM,F&E | In-Progress | 3/30/2022 | 12/24/2022 |  | 205263 | 181087 | 176730 | DSF0000912803
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP RESOA | FY22 RESO ESCALATOR UPGRADE | Scope | Complete | 5/31/2022 | 8/29/2022 | 12/22/2022 | 0 | 40189 | 40189 | DSF0001033701
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP RESOA | FY22 RESO ESCALATOR UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 4811 | 1724 | DSF0001033701
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP RESOA | FY22 RESO ESCALATOR UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 23906598 | 0 | DSF0001033701
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP RESOA | FY22 RESO ESCALATOR UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 1629995 | 6051 | DSF0001033701
2 | M620 | MANHATTAN ACADEMY OF ARTS AND LANGUAGE - MANHATTAN | Fast Track Projects | CTF- ROOM CONVERSION | Construction | In-Progress | 10/31/2014 | FTK |  | FTK | 445969 | 420198 | DSF0000800277
2 | M620 | UNITY HS - MANHATTAN | Fast Track Projects | CTF- ROOM CONVERSION | Construction | In-Progress | 11/4/2014 | FTK |  | FTK | 501369 | 447160 | DSF0000800278
2 | M620 | MURRAY HILL ACADEMY HS - M | Fast Track Projects | TEMPORARY EMERGENCY GENERATOR | Construction | In-Progress | 7/10/2017 | FTK |  | FTK | 718461 | 675106 | DSF0000866187
2 | M620 | UNITY HS - MANHATTAN | DOE - Skilled Trades | CHILLER REPLACEMENT | Construction | In-Progress | 7/2/2019 | DOES |  | DOES | 3668432 | 0 | DSF0000877310
2 | M620 | MURRAY HILL ACADEMY HS - M | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMP | Construction | In-Progress | 7/13/2018 | DOES |  | DOES | 203473 | 0 | DSF0000889362
2 | M620 | MURRAY HILL ACADEMY HS - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/29/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084974
2 | M620 | MANHATTAN ACADEMY OF ARTS AND LANGUAGE - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/20/2024 | DOES |  | DOES | 647736 | 0 | DSF0001085748
2 | M625 | THE BUSINESS OF SPORTS SCHOOL | SCA IEH | PO18-ACM CORE DRILLING REQUEST 2 HOLES THAT NEED TO BE DRILLED IN THE FLOOR DUE TO ASSUMED ACM WE NE | Construction | In-Progress | 7/5/2024 | IEH |  | IEH | 0 | 0 | SCA0000073118
2 | M625 | THE BUSINESS OF SPORTS SCHOOL | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION IN THE 7TH FLOOR HALLWAY CEILING ACCESS PANEL. WE ARE GOING TO N | Construction | Complete | 8/23/2024 | IEH | 10/27/2024 | IEH | 0 | 0 | SCA0000073314
2 | M625 | URBAN ASSEMBLY GATEWAY SCHOOL FOR TECHNOLOGY - M | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 75000 | 0 | DSF0001033228
2 | M625 | STEPHEN T. MATHER BUILDING ARTS & CRAFTSMANSHIP HS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035773
2 | M625 | THE BUSINESS OF SPORTS SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/22/2024 | DOES | 8/30/2024 | DOES | 65832 | 9037 | DSF0001084975
2 | M634 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Scope | Complete | 9/16/2014 | 10/31/2014 | 10/27/2014 | 716528 | 905005 | 902594 | DSF0000800281
2 | M634 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Design | Complete | 10/28/2014 | 4/15/2015 | 4/19/2019 | 3224378 | 4446724 | 3369190 | DSF0000800281
2 | M634 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 8/19/2024 | 9/3/2026 |  | 40662990 | 37784151 | 2004299 | DSF0000800281
2 | M634 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 8/19/2024 | 9/3/2026 |  | 5732228 | 2984729 | 381644 | DSF0000800281
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | Scope | Complete | 6/19/2019 | 11/4/2019 | 1/30/2020 | 266212 | 259797 | 258442 | DSF0000900222, DSF0000900224, DSF0000900225, DSF0000900234, DSF0000945688, DSF0000945680, DSF0000960728, DSF0000945679
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | Design | Complete | 2/5/2020 | 7/7/2020 | 10/28/2021 | 1321071 | 1125803 | 886241 | DSF0000900222, DSF0000900224, DSF0000900225, DSF0000900234, DSF0000945688, DSF0000945680, DSF0000960728, DSF0000945679
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | Construction | In-Progress | 8/15/2023 | 2/9/2026 |  | 28859726 | 25890691 | 6450265 | DSF0000900222, DSF0000900224, DSF0000900225, DSF0000900234, DSF0000945688, DSF0000945680, DSF0000960728, DSF0000945679
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | CM,F&E | In-Progress | 8/15/2023 | 2/9/2026 |  | 1938432 | 938735 | 932842 | DSF0000900222, DSF0000900224, DSF0000900225, DSF0000900234, DSF0000945688, DSF0000945680, DSF0000960728, DSF0000945679
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/17/2023 | 7/18/2023 | 3/21/2023 | 4200 | 3334 | 3334 | DSF0001034645
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/4/2023 | 18900 | 13336 | 13336 | DSF0001034645
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 3/13/2024 | 1/6/2025 |  | 243600 | 220260 | 3760 | DSF0001034645
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 3/13/2024 | 1/6/2025 |  | 82532 | 61550 | 57368 | DSF0001034645
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA IEH | PO18-ROOM B20, ABATE 30 SQ. FT. BROKEN AND MISSING FLOOR TILES ROOM 310, ABATE 4 SQ. FT. BROKEN AND | Construction | Complete | 5/9/2024 | IEH | 10/9/2024 | IEH | 0 | 0 | SCA0000072993
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | Fast Track Projects | LSP VACUUM PUMPS | Construction | In-Progress | 11/22/2024 | FTK |  | FTK | 98438 | 0 | DSF0001098542
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000961314
2 | M641 | M721 SPED - MANHATTAN | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/14/2023 | DOER |  | DOER | 135106 | 0 | DSF0000890682
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DOE - RESOA | FY21 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 49085 | 0 | DSF0001007813
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 6/20/2024 | DOER | 8/15/2024 | DOER | 24870 |  | DSF0001035225
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112902
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/5/2021 | DOES |  | DOES | 149409 | 0 | DSF0001008699
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | Scope | Complete | 5/18/2021 | 8/17/2021 | 6/15/2022 | 75078 | 92877 | 92877 | DSF0000994498, DSF0001020127
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | Design | Complete | 6/16/2022 | 12/20/2022 | 5/5/2023 | 375390 | 374090 | 317444 | DSF0000994498, DSF0001020127
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | Construction | In-Progress | 8/7/2023 | 8/5/2025 |  | 8446279 | 8078304 | 4949459 | DSF0000994498, DSF0001020127
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | CM,F&E | In-Progress | 8/7/2023 | 8/5/2025 |  | 525546 | 281866 | 277814 | DSF0000994498, DSF0001020127
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | Fast Track Projects | LSP HOT WATER HEATER | Construction | In-Progress | 12/26/2018 | FTK |  | FTK | 238445 | 231046 | DSF0000854763
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112903
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 9/19/2022 | DOES | 11/17/2022 | DOES | 76580 | 75550 | DSF0001009108
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/3/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084977
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2/24/2021 | 7/9/2021 | 12/7/2021 | 38648 | 135138 | 127579 | DSF0000945735, DSF0000945739, DSF0000945740
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Design | Complete | 12/15/2021 | 5/18/2022 | 5/10/2022 | 180499 | 136798 | 113147 | DSF0000945735, DSF0000945739, DSF0000945740
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 2959136 | 2959136 | 264918 | DSF0000945735, DSF0000945739, DSF0000945740
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 366093 | 366093 | 57070 | DSF0000945735, DSF0000945739, DSF0000945740
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/2/2022 | 1/6/2023 | 10/28/2022 | 6200 | 11767 | 11767 | DSF0001034585
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/28/2022 | 4/27/2023 | 3/8/2023 | 27900 | 47071 | 47071 | DSF0001034585
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/8/2023 | 7/3/2024 |  | 359600 | 322548 | 289029 | DSF0001034585
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/8/2023 | 7/3/2024 |  | 189922 | 175067 | 123692 | DSF0001034585
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 12/6/2023 | 4/9/2024 | 5/17/2024 | 0 | 15247 | 15247 | DSF0001086318, DSF0001087047
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | Complete | 5/21/2024 | 10/7/2024 | 12/20/2024 | 32556 | 47406 | 17276 | DSF0001086318, DSF0001087047
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 477494 | 477494 | 2706 | DSF0001086318, DSF0001087047
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 32556 | 33018 | 31919 | DSF0001086318, DSF0001087047
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA Emergency Response | EMERGENCY SIDEWALK BRIDGING | Construction | In-Progress | 4/15/2022 | EMER |  | EMER |  | 0 | SCA0000071043
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION IN THE GYM | Construction | Complete | 10/31/2024 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000073557
2 | M660 | M226 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001086319
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112904
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832 | 11092 | DSF0001084979
2 | M661 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | Scope | Complete | 3/7/2019 | 7/8/2020 | 6/22/2020 | 61612 | 162061 | 157142 | DSF0000961180, DSF0000960822, DSF0000945755, DSF0000945753, DSF0000960823
2 | M661 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | Design | Complete | 6/22/2020 | 8/3/2020 | 6/30/2020 | 288665 | 253378 | 247739 | DSF0000961180, DSF0000960822, DSF0000945755, DSF0000945753, DSF0000960823
2 | M661 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | Construction | In-Progress | 1/3/2022 | 8/25/2023 |  | 4817622 | 4629024 | 4209555 | DSF0000961180, DSF0000960822, DSF0000945755, DSF0000945753, DSF0000960823
2 | M661 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | CM,F&E | In-Progress | 1/3/2022 | 8/25/2023 |  | 576714 | 650990 | 636639 | DSF0000961180, DSF0000960822, DSF0000945755, DSF0000945753, DSF0000960823
2 | M661 | MNHT COMPR. NIGHT & DAY HS - M | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/10/2023 | DOES | 12/15/2023 | DOES | 195635 | 6868 | DSF0001034246
2 | M661 | MNHT COMPR. NIGHT & DAY HS - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/20/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084980
2 | M777 | M000 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033619
2 | M777 | M000 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033619
2 | M777 | M000 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033619
2 | M777 | M000 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033619
2 | M777 | M000 - MANHATTAN | DOE - RESOA | FY23 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 70000 | 0 | DSF0001035209
2 | M807 | HARVEY MILK SCHOOL - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 11/6/2024 | IEH |  | IEH | 0 | 0 | SCA0000073578
2 | M807 | HARVEY MILK SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/11/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001086322
2 | M816 | P.S. 527 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001086324
2 | M816 | P.S. 527 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001112906
2 | M816 | P.S. 527 - MANHATTAN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 176702 | 0 | DSF0001033713
2 | M816 | P.S. 527 - MANHATTAN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/25/2023 | DOER |  | DOER | 259030 | 0 | DSF0001034301
2 | M816 | P.S. 527 - MANHATTAN | DOE - Skilled Trades | BOILER REPLACEMENT | Construction | In-Progress | 4/24/2019 | DOES |  | DOES | 1429795 | 0 | DSF0000911437
2 | M816 | P.S. 527 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 12/26/2022 | DOES |  | DOES | 194652 | 0 | DSF0001009207
2 | M824 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | Scope | Complete | 5/20/2019 | 9/23/2019 | 7/18/2019 | 140676 | 220748 | 220748 | SCA0000049166, DSF0000960503
2 | M824 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | Design | Complete | 7/24/2019 | 12/26/2019 | 12/5/2019 | 696032 | 1274414 | 1034547 | SCA0000049166, DSF0000960503
2 | M824 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/14/2023 | 2/2/2025 |  | 15025246 | 13538747 | 10027674 | SCA0000049166, DSF0000960503
2 | M824 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/14/2023 | 2/2/2025 |  | 1140339 | 961544 | 530666 | SCA0000049166, DSF0000960503
2 | M824 | MILLENNIUM HS - MANHATTAN | Fast Track Projects | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/1/2019 | FTK |  | FTK | 154172 | 133756 | DSF0000890674
2 | M824 | MILLENNIUM HS - MANHATTAN | DOE - RESOA | FY18 RESO A LIBRARY UPGRADES | Construction | In-Progress | 1/16/2018 | DOER |  | DOER | 479756 | 0 | DSF0000866404
2 | M824 | MILLENNIUM HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/11/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085488
2 | M833 | HS FOR ECONOMICS & FINANCE - M | SCA CIP | ABSORBER REPLACEMENT | Scope | Complete | 8/12/2019 | 12/13/2019 | 3/30/2020 | 43701 | 53188 | 53188 | DSF0000900344
2 | M833 | HS FOR ECONOMICS & FINANCE - M | SCA CIP | ABSORBER REPLACEMENT | Design | Complete | 3/31/2020 | 7/17/2020 | 6/19/2020 | 218503 | 204306 | 199884 | DSF0000900344
2 | M833 | HS FOR ECONOMICS & FINANCE - M | SCA CIP | ABSORBER REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 4916315 | 4916315 | 8878 | DSF0000900344
2 | M833 | HS FOR ECONOMICS & FINANCE - M | SCA CIP | ABSORBER REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 305904 | 305904 | 67376 | DSF0000900344
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | Scope | Complete | 1/30/2019 | 6/14/2019 | 1/10/2022 | 25250 | 52598 | 41086 | DSF0000891027
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | Design | Complete | 1/13/2022 | 6/15/2022 | 4/22/2022 | 126250 | 328613 | 197842 | DSF0000891027
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | Construction | Complete | 9/12/2022 | 3/12/2024 | 8/5/2024 | 2840625 | 2612134 | 2502596 | DSF0000891027
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | CM,F&E | Complete | 9/12/2022 | 3/12/2024 | 8/5/2024 | 176750 | 379227 | 376989 | DSF0000891027
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | HEATING PLANT UPGRADE | Scope | Complete | 6/24/2021 | 11/26/2021 | 1/19/2022 | 34972 | 60928 | 60928 | DSF0001009200
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | HEATING PLANT UPGRADE | Design | Complete | 1/20/2022 | 6/21/2022 | 10/27/2022 | 174858 | 193903 | 170048 | DSF0001009200
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | HEATING PLANT UPGRADE | Construction | PNS | PNS | PNS | PNS | 3934303 | 3934303 | 9081 | DSF0001009200
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | HEATING PLANT UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 244801 | 244801 | 8939 | DSF0001009200
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113622
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113622
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113622
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113622
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | FY24 RESO A CULINARY KITCHEN | Scope | Complete | 12/6/2023 | 3/25/2024 | 7/19/2024 | 0 | 29990 | 29928 | DSF0001086325
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | FY24 RESO A CULINARY KITCHEN | Design | In-Progress | 7/30/2024 | 1/2/2025 |  | 41664 | 41664 | 63689 | DSF0001086325
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | FY24 RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 611072 | 611072 | 0 | DSF0001086325
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | FY24 RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 41664 | 41664 | 24370 | DSF0001086325
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | Complete | 7/9/2024 | 10/8/2024 | 11/15/2024 | 0 | 0 | 0 | DSF0001087048
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | In-Progress | 11/18/2024 | 3/20/2025 |  | 336 | 336 | 0 | DSF0001087048
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 4928 | 4928 | 0 | DSF0001087048
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 336 | 336 | 1410 | DSF0001087048
2 | M834 | INDEPENDENCE HS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033235
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/30/2023 | DIIR | 10/10/2024 | DIIR | 50000 | 50000 | DSF0001035219
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | DOE - RESOA | FY25 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112907
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 10/16/2021 | DOES |  | DOES | 349608 | 417316 | DSF0001009249
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/30/2024 | DOES | 11/1/2024 | DOES | 65832 | 9038 | DSF0001085489
2 | M844 | M721 SPED - MANHATTAN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 12/12/2023 | 4/29/2024 | 7/9/2024 | 45876 | 53424 | 50713 | DSF0001071036, DSF0001098735, DSF0001098739
2 | M844 | M721 SPED - MANHATTAN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | In-Progress | 7/24/2024 | 12/26/2024 |  | 208429 | 208429 | 31518 | DSF0001071036, DSF0001098735, DSF0001098739
2 | M844 | M721 SPED - MANHATTAN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 3082233 | 3082233 | 6415 | DSF0001071036, DSF0001098735, DSF0001098739
2 | M844 | M721 SPED - MANHATTAN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 422105 | 422105 | 41310 | DSF0001071036, DSF0001098735, DSF0001098739
2 | M844 | M721 SPED - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ M844 | Construction | In-Progress | 3/8/2024 | EMER |  | EMER | 24515 | 5041 | SCA0000072804
2 | M844 | M721 SPED - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/1/2024 | IEH | 8/11/2024 | IEH | 0 | 0 | SCA0000073213
2 | M844 | M721 SPED - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/15/2021 | DOES |  | DOES | 140265 | 0 | DSF0001008700
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 7/2/2024 | DIIR | 50000 | 49812 | DSF0001086328
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112910
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0 | DSF0001008859
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 260000 | 0 | DSF0001112909
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/3/2024 | DOES | 7/24/2024 | DOES | 65832 | 8176 | DSF0001085491
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 882948 | 0 | DSF0001098802
2 | M868 | I.S. 260 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 4/1/2021 | EMER |  | EMER | 18233 | 18233 | SCA0000069129
2 | M868 | I.S. 260 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001086329
2 | M868 | I.S. 260 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112911
2 | M871 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/7/2024 | IEH | 8/19/2024 | IEH | 0 | 0 | SCA0000073256
2 | M873 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/24/2023 | 9/25/2023 | 6/15/2023 | 3327 | 659 | 659 | DSF0001035036
2 | M873 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/15/2023 | 12/13/2023 | 8/30/2023 | 14970 | 2634 | 2634 | DSF0001035036
2 | M873 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/9/2024 | 1/3/2025 |  | 192950 | 173804 | 4702 | DSF0001035036
2 | M873 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/9/2024 | 1/3/2025 |  | 49174 | 143827 | 138544 | DSF0001035036
2 | M874 | BARUCH COLLEGE CAMPUS HS - M | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 160000 | 0 | DSF0001035782
2 | M874 | BARUCH COLLEGE CAMPUS HS - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001112912
2 | M874 | BARUCH COLLEGE CAMPUS HS - M | DOE - RESOA | FY15 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 205255 | 0 | DSF0000800428
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 2/8/2023 | 5/9/2023 |  | 0 | 23778 | 378 | DSF0001035784
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 96000 | 72222 | 1514 | DSF0001035784
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1408000 | 1408000 | 0 | DSF0001035784
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 96000 | 96000 | 61 | DSF0001035784
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 8/2/2024 | 11/4/2024 |  | 0 | 0 | 0 | DSF0001035785
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035785
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035785
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035785
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | DOE - RESOA | FY13 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 289814 | 0 | DSF0000754573
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112914
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 12/12/2024 | DOES | 65832 | 8956 | DSF0001085493
2 | M883 | HARVEST COLLEGIATE HIGH SCHOOL - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/20/2024 | IEH | 9/10/2024 | IEH | 0 | 0 | SCA0000073009
2 | M883 | HARVEST COLLEGIATE HIGH SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 50000 | 49808 | DSF0001086332
2 | M883 | HARVEST COLLEGIATE HIGH SCHOOL - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112915
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | SCA CIP | EMERGENCY GENERATOR REPLACEMENT | Scope | Complete | 7/17/2019 | 11/18/2019 | 3/11/2021 | 5770 | 11587 | 11587 | DSF0000900446
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | SCA CIP | EMERGENCY GENERATOR REPLACEMENT | Design | In-Progress | 4/9/2021 | 9/9/2021 |  | 25963 | 81173 | 56465 | DSF0000900446
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | SCA CIP | EMERGENCY GENERATOR REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 334636 | 334636 | 5559 | DSF0000900446
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | SCA CIP | EMERGENCY GENERATOR REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 62023 | 62023 | 20127 | DSF0000900446
2 | M894 | A SCHOOL WITHOUT WALLS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112916
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | DOE - RESOA | FY18 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 6/27/2024 | DOER |  | DOER | 98900 | 0 | DSF0000866433
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | DOE - Skilled Trades | COOLING TOWER | Construction | In-Progress | 7/22/2019 | DOES |  | DOES | 1239004 | 0 | DSF0000867178
2 | M896 | NYC PUBLIC SCHOOL REPERTORY CO - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112917
2 | M912 | BEACON HS - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB FACADE @ M912 | Construction | In-Progress | 5/9/2023 | EMER |  | EMER | 319702 | 101692 | SCA0000071956
2 | M912 | M035 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112918
2 | M912 | BEACON HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112919
2 | M912 | BEACON HS - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 180000 | 0 | DSF0001086334
2 | M920 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/13/2022 | 2/15/2023 | 10/28/2022 | 4780 | 6694 | 6694 | DSF0001034549
2 | M920 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/28/2022 | 4/27/2023 | 3/8/2023 | 21510 | 26777 | 26777 | DSF0001034549
2 | M920 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/8/2023 | 7/3/2024 |  | 277240 | 259350 | 194600 | DSF0001034549
2 | M920 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/8/2023 | 7/3/2024 |  | 153291 | 140567 | 76105 | DSF0001034549
2 | M920 | SATELLITE ACADEMY - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/31/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085494
2 | M971 | THE SPRUCE STREET EDUCATIONAL CAMPUS - M | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001086338
2 | M971 | THE SPRUCE STREET EDUCATIONAL CAMPUS - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084649
2 | MBDF | BROOME STREET ACADEMY CHARTER SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 100000 | 0 | DSF0001033710
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/26/2019 | 11/27/2019 | 9/17/2019 | 73499 | 84712 | 84712 | DSF0000890581, DSF0000912537, DSF0000912538
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/26/2019 | 3/3/2020 | 2/11/2020 | 354838 | 368432 | 349509 | DSF0000890581, DSF0000912537, DSF0000912538
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 8/16/2021 | 8/15/2023 |  | 7569284 | 7003469 | 4832064 | DSF0000890581, DSF0000912537, DSF0000912538
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 8/16/2021 | 8/15/2023 |  | 533487 | 484551 | 480769 | DSF0000890581, DSF0000912537, DSF0000912538
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113599
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113599
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113599
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113599
3 | M009 | P.S. 9 - MANHATTAN | DIIT - RESOA | FY17 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35255 | 0 | DSF0000845395
3 | M009 | P.S. 9 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 175000 | 174340 | DSF0001086169
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/18/2018 | DOER |  | DOER | 474166 | 0 | DSF0000867223
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/8/2022 | DOER |  | DOER | 402261 | 0 | DSF0000913293
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001033622
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 280000 | 0 | DSF0001035615
3 | M009 | I.S. 243 - MANHATTAN | DOE - RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0 | DSF0001086168
3 | M009 | I.S. 243 - MANHATTAN | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112755
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112756
3 | M009 | P.S. 9 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/14/2022 | DOES | 9/27/2022 | DOES | 141282 | 149148 | DSF0001034238
3 | M044 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/14/2021 | 12/13/2021 | 9/16/2021 | 192000 | 188075 | 178801 | DSF0000992165, DSF0000992166, DSF0000992167, DSF0001034201
3 | M044 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 10/20/2021 | 6/30/2022 | 4/25/2022 | 960000 | 413616 | 413616 | DSF0000992165, DSF0000992166, DSF0000992167, DSF0001034201
3 | M044 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 9/5/2023 | 9/3/2025 |  | 21600000 | 19625837 | 3637598 | DSF0000992165, DSF0000992166, DSF0000992167, DSF0001034201
3 | M044 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 9/5/2023 | 9/3/2025 |  | 1345280 | 173504 | 172012 | DSF0000992165, DSF0000992166, DSF0000992167, DSF0001034201
3 | M044 | I.S. 245 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/17/2021 | EMER |  | EMER |  | 0 | SCA0000069929
3 | M044 | P.S. 334 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF BOILER# 1 INSULATION. IT IS APPROXIMATELY 20 SQ/FT. | Construction | In-Progress | 9/27/2024 | IEH |  | IEH | 0 | 0 | SCA0000073444
3 | M044 | P.S. 334 - MANHATTAN | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 8/8/2023 |  |  | 135342 | 135342 | 923 | DSF0000913078
3 | M044 | I.S. 245 - MANHATTAN | DIIT - RESOA | FY 14 RESO A SECURITY CAMERAS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 98129 | 0 | DSF0000777417
3 | M044 | I.S. 245 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035633
3 | M044 | I.S. 245 - MANHATTAN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 24511 | 0 | DSF0001033632
3 | M044 | I.S. 245 - MANHATTAN | DOE - RESOA | RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/19/2024 | DOER |  | DOER | 32774 | 0 | DSF0001085189
3 | M044 | P.S. 334 - MANHATTAN | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086184
3 | M044 | I.S. 245 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 155275 | 0 | DSF0001086185
3 | M044 | P.S. 334 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0 | DSF0001112767
3 | M044 | P.S. 334 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/5/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084780
3 | M044 | I.S. 245 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 521275 | 0 | DSF0001085732
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 10/5/2018 | 3/13/2019 | 12/3/2018 | 100920 | 94238 | 94238 | DSF0000890594, DSF0000890592
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/12/2018 | 5/15/2019 | 5/13/2019 | 403680 | 430519 | 415270 | DSF0000890594, DSF0000890592
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 10/3/2019 | 10/1/2021 |  | 7569000 | 7730185 | 7147550 | DSF0000890594, DSF0000890592
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 10/3/2019 | 10/1/2021 |  | 470960 | 1148426 | 1138313 | DSF0000890594, DSF0000890592
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/5/2023 | 12/4/2023 | 10/12/2023 | 142980 | 141042 | 140431 | DSF0001017752, DSF0001017753, DSF0001017754, DSF0001087236
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 10/18/2023 | 6/11/2024 | 4/10/2024 | 714900 | 275801 | 271403 | DSF0001017752, DSF0001017753, DSF0001017754, DSF0001087236
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 8/15/2024 | 8/14/2026 |  | 16085250 | 14449461 | 983196 | DSF0001017752, DSF0001017753, DSF0001017754, DSF0001087236
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 8/15/2024 | 8/14/2026 |  | 1000860 | 78455 | 74864 | DSF0001017752, DSF0001017753, DSF0001017754, DSF0001087236
3 | M054 | I.S. 54 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000889838
3 | M054 | I.S. 54 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 200000 | 0 | DSF0000890158
3 | M054 | I.S. 54 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/30/2023 | DOER |  | DOER | 334092 | 0 | DSF0000913080
3 | M054 | I.S. 54 - MANHATTAN | DOE - RESOA | FY21 RESO A ROOM UPGRADE | Construction | In-Progress | 11/11/2022 | DOER |  | DOER | 1031251 | 0 | DSF0000961405
3 | M054 | I.S. 54 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112772
3 | M054 | I.S. 54 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/26/2024 | DOES | 9/4/2024 | DOES | 65832 | 8902 | DSF0001084782
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 10/30/2019 | 4/29/2020 | 2/13/2020 | 14136 | 28741 | 28741 | DSF0000890583
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2/25/2020 | 8/18/2020 | 4/8/2020 | 63611 | 126021 | 122393 | DSF0000890583
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 8/16/2021 | 11/8/2022 |  | 819872 | 902218 | 788260 | DSF0000890583
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 8/16/2021 | 11/8/2022 |  | 151959 | 274641 | 270012 | DSF0000890583
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | ROOFS / STAIRWELL WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 8/3/2023 | 12/20/2023 | 12/29/2023 | 136647 | 239976 | 235281 | DSF0001068672, DSF0001085313, DSF0001111904, DSF0001096372, DSF0001096375
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | ROOFS / STAIRWELL WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 1/12/2024 | 6/13/2024 | 5/14/2024 | 672871 | 575792 | 575792 | DSF0001068672, DSF0001085313, DSF0001111904, DSF0001096372, DSF0001096375
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | ROOFS / STAIRWELL WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | In-Progress | 10/14/2024 | 4/11/2027 |  | 14242786 | 12900657 | 147982 | DSF0001068672, DSF0001085313, DSF0001111904, DSF0001096372, DSF0001096375
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | ROOFS / STAIRWELL WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | In-Progress | 10/14/2024 | 4/11/2027 |  | 1034290 | 137889 | 136671 | DSF0001068672, DSF0001085313, DSF0001111904, DSF0001096372, DSF0001096375
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/19/2023 | 11/17/2023 | 7/26/2023 | 4800 | 2655 | 2655 | DSF0001035025
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/26/2023 | 1/24/2024 | 11/1/2023 | 21600 | 10624 | 10624 | DSF0001035025
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/28/2024 | 12/23/2024 |  | 278400 | 247110 | 61705 | DSF0001035025
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/28/2024 | 12/23/2024 |  | 55864 | 38435 | 12515 | DSF0001035025
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY19 RESO A PLAYGROUND | Construction | In-Progress | 12/23/2019 | DOER |  | DOER | 462752 | 0 | DSF0000890811
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001033637
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 286387 | 0 | DSF0001035650
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086200
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112781
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 9/30/2022 | 2/21/2023 | 1/11/2023 | 142110 | 152521 | 126511 | DSF0001017957, DSF0001017958, DSF0001083744
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/24/2023 | 6/26/2023 | 5/4/2023 | 710551 | 421997 | 421997 | DSF0001017957, DSF0001017958, DSF0001083744
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 7/25/2023 | 1/19/2026 |  | 15987375 | 14662057 | 7267889 | DSF0001017957, DSF0001017958, DSF0001083744
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 7/25/2023 | 1/19/2026 |  | 994770 | 900163 | 892759 | DSF0001017957, DSF0001017958, DSF0001083744
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/7/2023 | 7/6/2023 | 3/8/2023 | 4980 | 2039 | 2039 | DSF0001034615
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/8/2023 | 8/31/2023 | 5/3/2023 | 22410 | 8155 | 8155 | DSF0001034615
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/8/2023 | 12/6/2024 |  | 288840 | 260132 | 95248 | DSF0001034615
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/8/2023 | 12/6/2024 |  | 134058 | 114937 | 84372 | DSF0001034615
3 | M076 | P.S. 76 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/9/2022 | DOES |  | DOES | 65729 | 0 | DSF0001009119
3 | M076 | P.S. 76 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/18/2024 | DOES | 12/13/2024 | DOES | 65832 |  | DSF0001084628
3 | M081 | MID-MAN ADULT LEARNING CENTER - M | SCA IEH | PO18-ABATE AND REPAIRS ARE NEEDED IN VARIOUS LACTIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT | Construction | In-Progress | 5/22/2023 | IEH |  | IEH | 0 | 0 | SCA0000072002
3 | M081 | MID-MAN ADULT LEARNING CENTER - M | SCA IEH | PO18-PATCH AND REPAIR PIPE INSULATION: CUSTODIAN WORKSHOP, BASEMENT STAIRCASE G&H, 2ND FLOOR HALLWAY | Construction | In-Progress | 8/20/2024 | IEH |  | IEH | 0 | 0 | SCA0000073303
3 | M081 | MID-MAN ADULT LEARNING CENTER - M | DOE - Skilled Trades | PA SYSTEM REPLACEMENT | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 195731 | 45000 | DSF0001035085
3 | M081 | MID-MAN ADULT LEARNING CENTER - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/20/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084943
3 | M084 | P.S. 84 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/2/2018 | 10/1/2018 | 10/12/2018 | 0 | 30736 | 30736 | DSF0000888809
3 | M084 | P.S. 84 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUND UPGRADE | Design | Complete | 10/29/2018 | 3/19/2019 | 5/20/2019 | 51674 | 66374 | 64914 | DSF0000888809
3 | M084 | P.S. 84 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 9/10/2019 | 9/8/2020 |  | 757879 | 749781 | 709122 | DSF0000888809
3 | M084 | P.S. 84 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 9/10/2019 | 9/8/2020 |  | 51674 | 102300 | 71789 | DSF0000888809
3 | M084 | P.S. 84 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIRS AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT | Construction | In-Progress | 5/22/2023 | IEH |  | IEH | 0 | 0 | SCA0000072010
3 | M084 | P.S. 84 - MANHATTAN | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 50000 | 50000 | 0 | DSF0000961414
3 | M084 | P.S. 84 - MANHATTAN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADE | Construction | In-Progress | 8/2/2023 | DOER |  | DOER | 38124 | 0 | DSF0001034166
3 | M084 | P.S. 84 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | Complete | 11/6/2023 | DOER | 6/4/2024 | DOER | 308409 |  | DSF0001035651
3 | M087 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | Scope | Complete | 6/19/2018 | 3/6/2019 | 11/30/2018 | 387378 | 233407 | 233407 | DSF0000889086, DSF0000890584, DSF0000890595, DSF0000890596, DSF0000898417, DSF0000898418, DSF0000898420, DSF0000898428
3 | M087 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | Design | Complete | 12/5/2018 | 5/16/2019 | 4/18/2019 | 1528452 | 936297 | 898829 | DSF0000889086, DSF0000890584, DSF0000890595, DSF0000890596, DSF0000898417, DSF0000898418, DSF0000898420, DSF0000898428
3 | M087 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | Construction | In-Progress | 12/16/2019 | 6/2/2022 |  | 26768125 | 25729737 | 22512684 | DSF0000889086, DSF0000890584, DSF0000890595, DSF0000890596, DSF0000898417, DSF0000898418, DSF0000898420, DSF0000898428
3 | M087 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | CM,F&E | In-Progress | 12/16/2019 | 6/2/2022 |  | 2081581 | 1747390 | 1705831 | DSF0000889086, DSF0000890584, DSF0000890595, DSF0000890596, DSF0000898417, DSF0000898418, DSF0000898420, DSF0000898428
3 | M087 | P.S. 87 - MANHATTAN | DOE - RESOA | FY17 RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 48000 | 0 | DSF0000844205
3 | M087 | P.S. 87 - MANHATTAN | DOE - RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 238196 | 0 | DSF0001086202
3 | M087 | P.S. 87 - MANHATTAN | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112785
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | Scope | Complete | 8/4/2021 | 11/3/2021 | 12/8/2021 | 157660 | 186501 | 186501 | DSF0000992594, DSF0000992579, DSF0001068778
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | Design | Complete | 12/8/2021 | 6/13/2022 | 5/8/2023 | 788300 | 700884 | 475374 | DSF0000992594, DSF0000992579, DSF0001068778
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | Construction | In-Progress | 7/10/2023 | 7/8/2025 |  | 17736750 | 15864981 | 3732324 | DSF0000992594, DSF0000992579, DSF0001068778
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | CM,F&E | In-Progress | 7/10/2023 | 7/8/2025 |  | 1104652 | 395590 | 393566 | DSF0000992594, DSF0000992579, DSF0001068778
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 1/20/2023 | 6/6/2023 | 8/10/2023 | 29051 | 60231 | 60231 | DSF0001068782
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 8/25/2023 | 1/31/2024 | 2/5/2024 | 145255 | 112335 | 106282 | DSF0001068782
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 3268229 | 3268229 | 174452 | DSF0001068782
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 203356 | 203356 | 37502 | DSF0001068782
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/21/2023 | 11/6/2023 | 11/1/2023 | 70724 | 90211 | 88954 | DSF0001068784, DSF0001111767
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 11/8/2023 | 4/12/2024 | 4/22/2024 | 353618 | 236121 | 229228 | DSF0001068784, DSF0001111767
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 7956390 | 7956390 | 44118 | DSF0001068784, DSF0001111767
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 495064 | 495064 | 31419 | DSF0001068784, DSF0001111767
3 | M088 | J.H.S. 860 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113604
3 | M088 | J.H.S. 860 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113604
3 | M088 | J.H.S. 860 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113604
3 | M088 | J.H.S. 860 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113604
3 | M088 | J.H.S. 860 - MANHATTAN | SCA Emergency Response | STABILIZATION- SWB @ M088 | Construction | In-Progress | 2/29/2024 | EMER |  | EMER | 24515 | 5624 | SCA0000072778
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | DOE - RESOA | FY13 RESO A AUDITORIUM BLACKBOX THE | Construction | In-Progress | 7/20/2022 | DOER |  | DOER | 110440 | 0 | DSF0000775556
3 | M088 | J.H.S. 860 - MANHATTAN | DOE - RESOA | FY25 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112786
3 | M088 | SUCCESS ACADEMY CHARTER SCHOOL - HARLEM 1 | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112787
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 7/31/2017 | DOES |  | DOES | 121244 | 0 | DSF0000865894
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 1375724 | 0 | DSF0000912201
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/19/2024 | DOES | 8/30/2024 | DOES | 65832 |  | DSF0001084944
3 | M113 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | Scope | Complete | 6/2/2021 | 10/18/2021 | 11/9/2021 | 68681 | 65778 | 65778 | DSF0001034350, DSF0001018363, DSF0001018362
3 | M113 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | Design | Complete | 11/19/2021 | 4/25/2022 | 5/5/2022 | 335836 | 270950 | 270950 | DSF0001034350, DSF0001018363, DSF0001018362
3 | M113 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | Construction | In-Progress | 6/12/2023 | 12/2/2024 |  | 6901376 | 6842329 | 4925981 | DSF0001034350, DSF0001018363, DSF0001018362
3 | M113 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | CM,F&E | In-Progress | 6/12/2023 | 12/2/2024 |  | 538335 | 518069 | 512978 | DSF0001034350, DSF0001018363, DSF0001018362
3 | M113 | P.S. 241 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 4/2/2021 | EMER |  | EMER | 33094 | 21596 | SCA0000069149
3 | M113 | P.S. 241 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIRS ARE NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT | Construction | Complete | 5/16/2023 | IEH | 9/8/2024 | IEH | 0 | 0 | SCA0000071971
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 9/13/2019 | 3/16/2020 | 10/11/2019 | 13310 | 11691 | 11691 | DSF0000890586
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 11/21/2019 | 5/19/2020 | 2/24/2020 | 66550 | 55261 | 55261 | DSF0000890586
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 11/12/2024 | 11/11/2025 |  | 1497375 | 1341411 | 10411 | DSF0000890586
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 11/12/2024 | 11/11/2025 |  | 93170 | 7868 | 7868 | DSF0000890586
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 8/2/2023 | 12/1/2023 | 11/16/2023 | 10874 | 15970 | 15970 | DSF0001083813
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 12/4/2023 | 5/6/2024 | 5/3/2024 | 48933 | 51695 | 40612 | DSF0001083813
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/9/2024 | 9/8/2025 |  | 630692 | 561640 | 3368 | DSF0001083813
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/9/2024 | 9/8/2025 |  | 116896 | 72649 | 13930 | DSF0001083813
3 | M118 | I.S. 258 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000890668
3 | M118 | I.S. 258 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Design | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0000890668
3 | M118 | I.S. 258 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0000890668
3 | M118 | I.S. 258 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SCIENCE LAB UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0000890668
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 51 | 51 | DSF0001086219
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 33984 | 33933 | 202 | DSF0001086219
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 498434 | 498434 | 0 | DSF0001086219
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 33984 | 33984 | 0 | DSF0001086219
3 | M118 | P.S. 333 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 440335 | 0 | DSF0001007849
3 | M118 | I.S. 258 - MANHATTAN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/17/2022 | DOER |  | DOER | 117218 | 0 | DSF0001033231
3 | M118 | P.S. 333 - MANHATTAN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/17/2023 | DOER |  | DOER | 249282 | 0 | DSF0001035673
3 | M118 | I.S. 258 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 80753 | 0 | DSF0001086218
3 | M118 | P.S. 333 - MANHATTAN | DOE - RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Construction | Complete | 4/5/2024 | DOER | 4/8/2024 | DOER | 9912 |  | DSF0001086221
3 | M118 | P.S. 333 - MANHATTAN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 10/5/2016 | DOES |  | DOES | 1504948 | 0 | DSF0001083752
3 | M118 | P.S. 333 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/11/2024 | DOES | 11/18/2024 | DOES | 65832 |  | DSF0001084788
3 | M144 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 11/15/2018 | 4/4/2019 | 3/6/2019 | 49435 | 50347 | 50347 | DSF0000876167
3 | M144 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 3/6/2019 | 8/5/2019 | 11/18/2021 | 197741 | 116925 | 110115 | DSF0000876167
3 | M144 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 7/11/2022 | 7/9/2024 |  | 3707639 | 3504328 | 3319484 | DSF0000876167
3 | M144 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 7/11/2022 | 7/9/2024 |  | 230698 | 234514 | 229094 | DSF0000876167
3 | M144 | P.S. 242 - MANHATTAN | SCA IEH | PO18-ACM PIPE INSULATION REMOVAL/ ACM REMOVAL - BASEMENT B15 PROVIDE AN ABATEMENT ON THREE SEPERATE | Construction | Complete | 10/8/2024 | IEH | 10/12/2024 | IEH | 0 | 0 | SCA0000073472
3 | M144 | P.S. 242 - MANHATTAN | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/5/2023 | DOER |  | DOER | 57479 | 0 | DSF0000913086
3 | M144 | P.S. 242 - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 196000 | 0 | DSF0001112815
3 | M144 | P.S. 242 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/17/2021 | DOES | 12/21/2022 | DOES | 181418 | 4648 | DSF0001008695
3 | M144 | P.S. 242 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/14/2024 | DOES | 10/24/2024 | DOES | 65832 | 13724 | DSF0001084638
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/15/2023 | 11/1/2023 | 11/20/2023 | 111046 | 121472 | 121472 | DSF0001069524, DSF0001097226, DSF0001097225
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2/28/2024 | 7/30/2024 | 5/3/2024 | 555232 | 381748 | 16757 | DSF0001069524, DSF0001097226, DSF0001097225
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | PNS | PNS | PNS | PNS | 12492730 | 12492730 | 30948 | DSF0001069524, DSF0001097226, DSF0001097225
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 777326 | 777326 | 28317 | DSF0001069524, DSF0001097226, DSF0001097225
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT P | Construction | In-Progress | 5/22/2023 | IEH |  | IEH | 0 | 0 | SCA0000072001
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA IEH | PO18-ABATE SINK UNDERCOATING RM 105 (AS PER AHERA RM 106) | Construction | Complete | 7/29/2024 | IEH | 8/14/2024 | IEH | 0 | 0 | SCA0000073196
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA IEH | PO18-ABATE & REPLACE FLOORING WITHIN THE LIBRARY SQ FT WOULD BE 1736 SQ FT. SPACE ID# 4307 THEY ARE | Construction | Complete | 12/11/2024 | IEH | 12/27/2024 | IEH | 0 | 0 | SCA0000073699
3 | M145 | WEST PREP ACADEMY - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 7/2/2024 | DIIR | 50000 | 49795 | DSF0001086233
3 | M145 | P.S. 145 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | Complete | 12/23/2021 | DOER | 9/21/2022 | DOER | 376754 | 5665 | DSF0001007854
3 | M145 | P.S. 145 - MANHATTAN | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 99272 | 0 | DSF0001007856
3 | M145 | P.S. 145 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/19/2024 | DOER |  | DOER | 350000 | 7000 | DSF0001086232
3 | M145 | P.S. 145 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/22/2022 | DOES | 3/29/2023 | DOES | 169313 | 7085 | DSF0001008696
3 | M145 | WEST PREP ACADEMY - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 9/1/2022 | DOES | 9/26/2022 | DOES | 64366 | 63500 | DSF0001009118
3 | M145 | WEST PREP ACADEMY - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/16/2024 | DOES | 9/5/2024 | DOES | 65832 | 20757 | DSF0001084225
3 | M149 | M811 SPED - MANHATTAN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/9/2023 | 12/8/2023 | 9/22/2023 | 104451 | 130528 | 130522 | DSF0001069561, DSF0001087213, DSF0001087212, DSF0001087211
3 | M149 | M811 SPED - MANHATTAN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 10/25/2023 | 6/10/2024 | 4/3/2024 | 522249 | 316453 | 316453 | DSF0001069561, DSF0001087213, DSF0001087212, DSF0001087211
3 | M149 | M811 SPED - MANHATTAN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 10/14/2024 | 10/3/2026 |  | 11750625 | 10606118 | 144493 | DSF0001069561, DSF0001087213, DSF0001087212, DSF0001087211
3 | M149 | M811 SPED - MANHATTAN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 10/14/2024 | 10/3/2026 |  | 731150 | 52567 | 52087 | DSF0001069561, DSF0001087213, DSF0001087212, DSF0001087211
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112817
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001112817
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001112817
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001112817
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113611
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113611
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113611
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113611
3 | M149 | P.S. 149 - MANHATTAN | DOE - RESOA | FY08 RESO A HALL, STAIR & FLR RENO. | Construction | PNS | PNS | PNS | PNS | DOER | 387821 | 0 | DSF0000622315
3 | M163 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 6/21/2021 | 12/20/2021 | 10/14/2021 | 203462 | 186710 | 175815 | DSF0000993432, DSF0000993434, DSF0001034286, DSF0001018971, DSF0001018973
3 | M163 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Design | Complete | 10/26/2021 | 6/30/2022 | 4/22/2022 | 1012328 | 404083 | 404083 | DSF0000993432, DSF0000993434, DSF0001034286, DSF0001018971, DSF0001018973
3 | M163 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 7/18/2022 | 7/16/2024 |  | 22346452 | 20402265 | 17996300 | DSF0000993432, DSF0000993434, DSF0001034286, DSF0001018971, DSF0001018973
3 | M163 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 7/18/2022 | 7/16/2024 |  | 1461598 | 481408 | 478688 | DSF0000993432, DSF0000993434, DSF0001034286, DSF0001018971, DSF0001018973
3 | M163 | P.S. 163 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR ARE NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVELLANCE REPORT P | Construction | In-Progress | 5/22/2023 | IEH |  | IEH | 0 | 0 | SCA0000072003
3 | M163 | P.S. 163 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086241
3 | M163 | P.S. 163 - MANHATTAN | DOE - RESOA | FY16 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/7/2019 | DOER |  | DOER | 205675 | 0 | DSF0000822716
3 | M163 | P.S. 163 - MANHATTAN | DOE - Skilled Trades | VACUUM CONDENSATE PUMPS | Construction | In-Progress | 11/15/2021 | DOES |  | DOES | 61502 | 0 | DSF0001008558
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/15/2020 | 1/29/2021 | 10/19/2020 | 11777 | 34510 | 34510 | DSF0000890587
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 10/27/2020 | 7/28/2021 | 7/28/2021 | 52996 | 138049 | 138049 | DSF0000890587
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 6/28/2022 | 6/27/2023 |  | 683061 | 620702 | 7968 | DSF0000890587
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 6/28/2022 | 6/27/2023 |  | 126602 | 93789 | 89532 | DSF0000890587
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035698
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035698
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035698
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035698
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/13/2023 | 7/13/2023 | 10/11/2023 | 0 | 25716 | 25716 | DSF0001035699
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 10/17/2023 | 3/6/2024 | 4/22/2024 | 82500 | 109776 | 83946 | DSF0001035699
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1210000 | 1750040 | 19075 | DSF0001035699
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 82500 | 119321 | 30062 | DSF0001035699
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/13/2023 | 6/12/2023 | 11/7/2023 | 0 | 293 | 293 | DSF0001035700
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 11/7/2023 | 3/14/2024 | 4/22/2024 | 9483 | 1171 | 1171 | DSF0001035700
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 139081 | 139081 | 0 | DSF0001035700
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 9483 | 9483 | 3042 | DSF0001035700
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/13/2023 | 2/13/2024 | 1/5/2024 | 0 | 20154 | 20154 | DSF0001087151
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 1/10/2024 | 5/13/2024 | 11/7/2024 | 0 | 29323 | 1862 | DSF0001087151
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 2200 | 500 | DSF0001087151
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 11057 | 11057 | DSF0001087151
3 | M165 | P.S. 165 - MANHATTAN | Fast Track Projects | LSP VACUUM PUMP REPLACEMENT | Construction | In-Progress | 8/1/2024 | FTK |  | FTK | 167625 | 0 | DSF0001069738
3 | M165 | P.S. 165 - MANHATTAN | Fast Track Projects | LSP GYMNASIUM FLOOR | Construction | In-Progress | 1/8/2021 | FTK |  | FTK | 832651 | 619254 | DSF0000899269
3 | M165 | P.S. 165 - MANHATTAN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 897374 | 0 | DSF0000890822
3 | M165 | P.S. 165 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 5/13/2022 | DOER |  | DOER | 265245 | 0 | DSF0000913323
3 | M165 | I.S. 862 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/22/2023 | DOES |  | DOES | 230678 | 0 | DSF0001085739
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 9/29/2017 | 2/20/2018 | 3/29/2018 | 195014 | 274856 | 274856 | DSF0000852189, DSF0000899281, DSF0000899282, DSF0000912308
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | Design | Complete | 3/4/2019 | 8/1/2019 | 9/13/2019 | 973425 | 710944 | 625913 | DSF0000852189, DSF0000899281, DSF0000899282, DSF0000912308
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | Construction | In-Progress | 4/5/2021 | 5/24/2023 |  | 21759878 | 22058758 | 19150868 | DSF0000852189, DSF0000899281, DSF0000899282, DSF0000912308
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | CM,F&E | In-Progress | 4/5/2021 | 5/24/2023 |  | 1377423 | 1215207 | 1185544 | DSF0000852189, DSF0000899281, DSF0000899282, DSF0000912308
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | Scope | Complete | 3/1/2019 | 5/30/2019 | 12/13/2019 | 13750 | 70483 | 70483 | DSF0000890621
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | Design | Complete | 1/15/2020 | 7/17/2020 | 6/29/2020 | 68750 | 159947 | 108387 | DSF0000890621
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | Construction | In-Progress | 7/22/2021 | 7/21/2022 |  | 1546875 | 1482290 | 1374220 | DSF0000890621
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | CM,F&E | In-Progress | 7/22/2021 | 7/21/2022 |  | 96250 | 225850 | 224626 | DSF0000890621
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADES | Scope | Complete | 6/5/2019 | 8/12/2019 | 8/23/2019 | 0 | 6655 | 6655 | DSF0000912385
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADES | Design | Complete | 9/3/2019 | 11/5/2019 | 1/31/2020 | 2100 | 1819 | 1819 | DSF0000912385
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADES | Construction | PNS | PNS | PNS | PNS | 30800 | 30800 | 2615 | DSF0000912385
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 2100 | 2100 | 1459 | DSF0000912385
3 | M166 | P.S. 166 - MANHATTAN | SCA IEH | PO18-ACM AND LEAD DUST WIPE CLEARANCE ABATE WALL AND CEILING PLASTER IN ROOMS #210, 502(GYM) | Construction | Complete | 7/23/2024 | IEH | 8/4/2024 | IEH | 0 | 0 | SCA0000073165
3 | M166 | P.S. 166 - MANHATTAN | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 80000 | 80000 | 0 | DSF0001083870
3 | M166 | P.S. 166 - MANHATTAN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001033666
3 | M166 | P.S. 166 - MANHATTAN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 4/5/2024 | DOER |  | DOER | 40790 | 0 | DSF0001035701
3 | M166 | P.S. 166 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086243
3 | M166 | P.S. 166 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112824
3 | M166 | P.S. 166 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/16/2021 | DOES |  | DOES | 189953 | 0 | DSF0000889609
3 | M166 | P.S. 166 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 9/8/2022 | DOES | 11/17/2022 | DOES | 206642 |  | DSF0001009106
3 | M180 | P.S. 180 - MANHATTAN | SCA IEH | PO18-ABATEMENT OF PIPE INSULATION ENTRANCE OF BOILER RM WE ARE GOING TO NEED APPROXIMATELY 10' OF CO | Construction | Complete | 10/8/2024 | IEH | 10/19/2024 | IEH | 0 | 0 | SCA0000073478
3 | M180 | P.S. 180 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033181
3 | M180 | P.S. 180 - MANHATTAN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/16/2019 | DOER |  | DOER | 170000 | 0 | DSF0000913327
3 | M180 | P.S. 180 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 10/18/2022 | DOES | 11/17/2022 | DOES | 104412 | 103007 | DSF0001009121
3 | M180 | P.S. 180 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/9/2024 | DOES | 8/23/2024 | DOES | 65832 |  | DSF0001084641
3 | M185 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 3/16/2022 | 7/14/2022 | 4/12/2022 | 5962 | 3389 | 3389 | DSF0001034363
3 | M185 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 4/12/2022 | 10/5/2022 | 7/19/2022 | 26831 | 13554 | 13554 | DSF0001034363
3 | M185 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 3/9/2023 | 2/1/2024 |  | 345820 | 310900 | 289277 | DSF0001034363
3 | M185 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 3/9/2023 | 2/1/2024 |  | 234789 | 203351 | 198293 | DSF0001034363
3 | M185 | P.S. 185 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035706
3 | M185 | P.S. 185 - MANHATTAN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | Complete | 7/15/2022 | DOER | 4/23/2024 | DOER | 296996 | 927 | DSF0000913091
3 | M185 | P.S. 185 - MANHATTAN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 7/15/2022 | DOER | 11/30/2023 | DOER | 206073 | 194474 | DSF0001033182
3 | M185 | P.S. 185 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112836
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 8/13/2021 | 1/3/2022 | 7/29/2022 | 124270 | 127547 | 127547 | DSF0001009215
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 9/2/2022 | 2/24/2023 | 5/3/2023 | 621350 | 379906 | 306740 | DSF0001009215
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 8/7/2023 | 8/5/2025 |  | 13980375 | 12728220 | 5045798 | DSF0001009215
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 8/7/2023 | 8/5/2025 |  | 869890 | 384418 | 383524 | DSF0001009215
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | GYM CEILING RESTORATION- PERMANENT FIX | Scope | Complete | 5/17/2023 | 9/19/2023 | 8/23/2023 | 12427 | 12932 | 12932 | DSF0001111845
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | GYM CEILING RESTORATION- PERMANENT FIX | Design | Complete | 8/30/2023 | 1/19/2024 | 12/12/2023 | 55919 | 30850 | 27128 | DSF0001111845
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | GYM CEILING RESTORATION- PERMANENT FIX | Construction | PNS | PNS | PNS | PNS | 720737 | 720737 | 1801 | DSF0001111845
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | GYM CEILING RESTORATION- PERMANENT FIX | CM,F&E | PNS | PNS | PNS | PNS | 133585 | 133585 | 12619 | DSF0001111845
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP RESOA | FY19 RESO A PLAYGROUND | Scope | Complete | 12/20/2018 | 3/25/2019 | 8/7/2019 | 0 | 27407 | 27407 | DSF0000890836
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP RESOA | FY19 RESO A PLAYGROUND | Design | Complete | 8/10/2021 | 12/28/2021 | 1/18/2022 | 84113 | 78796 | 78796 | DSF0000890836
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP RESOA | FY19 RESO A PLAYGROUND | Construction | In-Progress | 10/31/2022 | 7/27/2023 |  | 1233650 | 1196936 | 1050727 | DSF0000890836
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP RESOA | FY19 RESO A PLAYGROUND | CM,F&E | In-Progress | 10/31/2022 | 7/27/2023 |  | 84113 | 112319 | 87266 | DSF0000890836
3 | M191 | P.S. 452 - MANHATTAN | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 175000 | 175000 | 0 | DSF0001112841
3 | M191 | P.S. 452 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 340000 | 0 | DSF0001035716
3 | M191 | P.S. 452 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 9/30/2022 | DOES | 11/17/2022 | DOES | 90450 | 89233 | DSF0001009104
3 | M191 | P.S. 452 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/11/2024 | DOES | 7/18/2024 | DOES | 65832 | 9997 | DSF0001084243
3 | M199 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/18/2023 | 11/16/2023 | 7/26/2023 | 4400 | 2480 | 2480 | DSF0001035049
3 | M199 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/26/2023 | 1/24/2024 | 11/1/2023 | 19800 | 9922 | 9922 | DSF0001035049
3 | M199 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/28/2024 | 12/23/2024 |  | 255200 | 227463 | 29238 | DSF0001035049
3 | M199 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/28/2024 | 12/23/2024 |  | 51564 | 33473 | 9713 | DSF0001035049
3 | M199 | P.S. 199 - MANHATTAN | SCA IEH | PO18-ABATE FOR FLOOR TILES IN STORAGE ROOM B4 TILES ARE 9X9 | Construction | Complete | 7/25/2024 | IEH | 10/27/2024 | IEH | 0 | 0 | SCA0000073174
3 | M199 | P.S. 199 - MANHATTAN | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 2/26/2021 | DOER |  | DOER | 210783 | 0 | DSF0000913332
3 | M199 | P.S. 199 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 107298 | 0 | DSF0001033188
3 | M199 | P.S. 199 - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 502264 | 0 | DSF0001035727
3 | M199 | P.S. 199 - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0 | DSF0001112848
3 | M199 | P.S. 199 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/14/2022 | DOES |  | DOES | 89313 | 0 | DSF0001009105
3 | M199 | P.S. 199 - MANHATTAN | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 9/4/2023 | DOES |  | DOES | 175407 | 0 | DSF0001085614
3 | M207 | P.S. 149 - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 41365 | 0 | DSF0001086268
3 | M207 | P.S. 149 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/8/2024 | DOES | 10/10/2024 | DOES | 65832 | 9967 | DSF0001084645
3 | M342 | THE RIVERSIDE SCHOOL FOR MAKERS AND ARTISTS - MANHATTAN | SCA Furniture & Equipment | FY22 RESO A MOBILE STEM LAB | F&E | Complete | 11/4/2024 |  | 11/12/2024 | 100000 | 100000 | 99566 | DSF0001033186
3 | M342 | THE RIVERSIDE SCHOOL FOR MAKERS AND ARTISTS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033672
3 | M342 | THE RIVERSIDE SCHOOL FOR MAKERS AND ARTISTS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001112863
3 | M342 | THE RIVERSIDE SCHOOL FOR MAKERS AND ARTISTS - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 213427 | 0 | DSF0001086278
3 | M342 | THE RIVERSIDE SCHOOL FOR MAKERS AND ARTISTS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 50832 | 9192 | DSF0001084648
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | Scope | Complete | 5/20/2013 | 9/20/2013 | 11/4/2013 | 49058 | 58427 | 48452 | DSF0000764431, DSF0000764420
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | Design | Complete | 11/13/2013 | 5/15/2014 | 10/27/2014 | 189433 | 210497 | 207760 | DSF0000764431, DSF0000764420
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | Construction | In-Progress | 8/14/2018 | 10/7/2019 |  | 2941946 | 3534155 | 3442547 | DSF0000764431, DSF0000764420
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | CM,F&E | In-Progress | 8/14/2018 | 10/7/2019 |  | 317281 | 712661 | 710343 | DSF0000764431, DSF0000764420
3 | M470 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | Scope | Complete | 2/14/2020 | 5/14/2020 | 9/23/2021 | 112212 | 104405 | 99517 | DSF0000945296, DSF0001019706, DSF0001019693
3 | M470 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | Design | Complete | 10/13/2021 | 4/19/2022 | 7/11/2022 | 561061 | 598978 | 388374 | DSF0000945296, DSF0001019706, DSF0001019693
3 | M470 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | Construction | In-Progress | 5/15/2023 | 5/13/2025 |  | 12623864 | 11522246 | 9173611 | DSF0000945296, DSF0001019706, DSF0001019693
3 | M470 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | CM,F&E | In-Progress | 5/15/2023 | 5/13/2025 |  | 786541 | 254533 | 254252 | DSF0000945296, DSF0001019706, DSF0001019693
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Scope | Complete | 6/23/2017 | 9/25/2017 | 10/10/2017 | 0 | 12421 | 12421 | DSF0000844926
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Design | Complete | 1/31/2018 | 6/18/2018 | 5/21/2018 | 41220 | 49682 | 39615 | DSF0000844926
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/9/2018 | 4/4/2019 |  | 604563 | 613632 | 546607 | DSF0000844926
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | CM,F&E | In-Progress | 7/9/2018 | 4/4/2019 |  | 41763 | 92754 | 90781 | DSF0000844926
3 | M470 | FRANK MCCOURT HS- MANHATTAN | SCA Emergency Response | EMERGENCY TEMPORARY FUEL TANK @ M470 | Construction | In-Progress | 10/2/2023 | EMER |  | EMER | 509720 | 368411 | SCA0000072189
3 | M470 | FRANK MCCOURT HS- MANHATTAN | Fast Track Projects | PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 9/6/2023 | FTK |  | FTK | 304691 | 262011 | DSF0001083826
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 11/10/2022 | DOER | 6/24/2023 | DOER | 288329 | 244847 | DSF0001034940
3 | M470 | INNOVATION DIPLOMA PLUS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112883
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112884
3 | M470 | FRANK MCCOURT HS- MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/21/2024 | DOES | 11/12/2024 | DOES | 65832 |  | DSF0001084958
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | STAIRWELL WALLS | Scope | Complete | 5/25/2023 | 9/25/2023 | 9/21/2023 | 31036 | 36304 | 36304 | DSF0001085138
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | STAIRWELL WALLS | Design | Complete | 10/2/2023 | 3/7/2024 | 5/10/2024 | 155181 | 114433 | 108134 | DSF0001085138
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | STAIRWELL WALLS | Construction | PNS | PNS | PNS | PNS | 3491582 | 3491582 | 21644 | DSF0001085138
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | STAIRWELL WALLS | CM,F&E | PNS | PNS | PNS | PNS | 217254 | 217254 | 26114 | DSF0001085138
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | Scope | Complete | 5/18/2020 | 1/29/2021 | 8/11/2020 | 29299 | 59138 | 59138 | DSF0000890566, DSF0000945398
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | Design | Complete | 8/19/2020 | 7/28/2021 | 7/28/2021 | 137177 | 235677 | 227065 | DSF0000890566, DSF0000945398
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | Construction | In-Progress | 7/21/2022 | 1/11/2024 |  | 2280149 | 2153366 | 1983726 | DSF0000890566, DSF0000945398
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | CM,F&E | In-Progress | 7/21/2022 | 1/11/2024 |  | 275011 | 383551 | 378240 | DSF0000890566, DSF0000945398
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | FY15 RESO A TECHNICAL THEATER SHOP | Scope | Complete | 5/14/2015 | 9/14/2015 | 12/23/2015 | 0 | 216895 | 214889 | DSF0000800083
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | FY15 RESO A TECHNICAL THEATER SHOP | Design | Complete | 7/28/2016 | 3/28/2017 | 9/19/2018 | 285834 | 800614 | 734966 | DSF0000800083
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | FY15 RESO A TECHNICAL THEATER SHOP | Construction | In-Progress | 6/10/2022 | 12/1/2023 |  | 4192225 | 2696112 | 2564537 | DSF0000800083
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | FY15 RESO A TECHNICAL THEATER SHOP | CM,F&E | In-Progress | 6/10/2022 | 12/1/2023 |  | 489263 | 754200 | 732512 | DSF0000800083
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087045
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087045
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087045
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087045
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 825000 | 0 | DSF0001086303
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/1/2024 | DOES | 11/25/2024 | DOES | 50832 |  | DSF0001084962
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/27/2024 | DOES |  | DOES | 814967 | 0 | DSF0001085744
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - Skilled Trades | HOT WATER HEATER SYSTEM REPLACEMENT | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 94271 | 0 | DSF0001070541
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - Skilled Trades | COOLING TOWER FILL REPLACEMENT | Construction | In-Progress | 5/16/2024 | DOES |  | DOES | 121500 | 0 | DSF0001111868
3 | M490 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | Scope | Complete | 5/4/2021 | 9/2/2021 | 11/16/2021 | 89950 | 70680 | 70680 | DSF0001008857, DSF0001019856
3 | M490 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | Design | Complete | 12/1/2021 | 4/19/2022 | 10/7/2022 | 449750 | 400858 | 335840 | DSF0001008857, DSF0001019856
3 | M490 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | Construction | In-Progress | 8/7/2023 | 2/6/2026 |  | 10119375 | 9152849 | 3829316 | DSF0001008857, DSF0001019856
3 | M490 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | CM,F&E | In-Progress | 8/7/2023 | 2/6/2026 |  | 778696 | 467604 | 301327 | DSF0001008857, DSF0001019856
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | Scope | Complete | 6/8/2022 | 9/7/2022 | 8/30/2022 | 14950 | 22740 | 22740 | DSF0001034924
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | Design | Complete | 9/12/2022 | 3/20/2023 | 4/21/2023 | 74750 | 116651 | 14787 | DSF0001034924
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | Construction | In-Progress | 4/18/2024 | 10/9/2025 |  | 1681875 | 1696592 | 133147 | DSF0001034924
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | CM,F&E | In-Progress | 4/18/2024 | 10/9/2025 |  | 104650 | 155945 | 123671 | DSF0001034924
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Scope | Complete | 6/14/2023 | 3/8/2024 | 3/15/2024 | 73928 | 77040 | 77040 | DSF0001070582, DSF0001111814
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Design | Complete | 4/3/2024 | 8/6/2024 | 8/13/2024 | 344878 | 244582 | 237281 | DSF0001070582, DSF0001111814
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Construction | PNS | PNS | PNS | PNS | 5459466 | 5459466 | 82253 | DSF0001070582, DSF0001111814
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | CM,F&E | PNS | PNS | PNS | PNS | 544518 | 544518 | 44412 | DSF0001070582, DSF0001111814
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112309
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | Design | PNS | PNS | PNS | PNS | 7080 | 7080 | 0 | DSF0001112309
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | Construction | PNS | PNS | PNS | PNS | 103840 | 103840 | 0 | DSF0001112309
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | CM,F&E | PNS | PNS | PNS | PNS | 123415 | 116335 | 0 | DSF0001112309
3 | M490 | P.S. 859 - MANHATTAN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 50000 | 50000 | 0 | DSF0001035768
3 | M490 | THE MAXINE GREEN HIGH SCHOOL FOR IMAGINATIVE INQUIRY - M | Fast Track Projects | FY20 RESO A INTERIOR SPACES | Construction | In-Progress | 7/7/2022 | FTK |  | FTK | 190034 | 182606 | DSF0000913097
3 | M490 | P.S. 859 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 116665 | 0 | DSF0000960055
3 | M490 | HUNTER SCIENCE HS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033718
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 193000 | 74718 | DSF0001086307
3 | M490 | HUNTER SCIENCE HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112897
3 | M490 | P.S. 859 - MANHATTAN | DOE - RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 88818 | 0 | DSF0000844211
3 | M490 | P.S. 859 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/15/2024 | DOER |  | DOER | 722884 | 0 | DSF0001033249
3 | M490 | SCHOOL SAFETY - MANHATTAN | DOE - Skilled Trades | INTERIOR SPACES | Construction | In-Progress | 11/1/2020 | DOES |  | DOES | 663032 | 0 | DSF0000994249
3 | M490 | SCHOOL SAFETY - MANHATTAN | DOE - Skilled Trades | LIGHTING UPGRADE | Construction | In-Progress | 3/12/2021 | DOES |  | DOES | 145591 | 0 | DSF0001008734
3 | M490 | SCHOOL SAFETY - MANHATTAN | DOE - Skilled Trades | INTERIOR SPACES | Construction | In-Progress | 3/29/2021 | DOES |  | DOES | 302521 | 0 | DSF0001008737
3 | M490 | SCHOOL BASED HEALTH CENTER - MANHATTAN | DOE - Skilled Trades | STUDENT BATHROOM UPGRADE | Construction | In-Progress | 7/2/2021 | DOES |  | DOES | 620614 | 0 | DSF0001008823
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/10/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084964
3 | M506 | EDWARD A. REYNOLDS WEST SIDE HS-M | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/15/2021 | DOES |  | DOES | 278403 | 0 | DSF0000865898
3 | M506 | EDWARD A. REYNOLDS WEST SIDE HS-M | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/6/2022 | DOES |  | DOES | 85598 | 0 | DSF0001009117
3 | M506 | EDWARD A. REYNOLDS WEST SIDE HS-M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 9/5/2024 | DOES | 50832 |  | DSF0001084967
3 | M514 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | Scope | Complete | 7/29/2021 | 9/16/2021 | 9/16/2021 | 331100 | 221828 | 221828 | DSF0001009268
3 | M514 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | Design | Complete | 9/17/2021 | 12/20/2021 | 5/4/2022 | 1489950 | 713215 | 692018 | DSF0001009268
3 | M514 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | Construction | In-Progress | 6/13/2022 | 9/3/2023 |  | 18789925 | 19137843 | 18363594 | DSF0001009268
3 | M514 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | CM,F&E | In-Progress | 6/13/2022 | 9/3/2023 |  | 2648800 | 877415 | 1769727 | DSF0001009268
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 2/1/2023 | 6/1/2023 | 2/6/2023 | 0 | 2773 | 2773 | DSF0000822325
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2/6/2023 | 8/2/2023 | 5/3/2023 | 20584 | 11090 | 11090 | DSF0000822325
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 12/8/2023 | 12/6/2024 |  | 301894 | 208878 | 112185 | DSF0000822325
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 12/8/2023 | 12/6/2024 |  | 112468 | 117867 | 88519 | DSF0000822325
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY18 RESO A MEDIA CENTER UPGRADE | Scope | Complete | 4/24/2018 | 8/23/2018 | 8/20/2018 | 0 | 11728 | 11728 | DSF0000866559
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY18 RESO A MEDIA CENTER UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 1837 | 1837 | DSF0000866559
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY18 RESO A MEDIA CENTER UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 1402 | 1402 | DSF0000866559
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY18 RESO A MEDIA CENTER UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 3321 | 3321 | DSF0000866559
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000867494
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 7/10/2020 | DIIR |  | DIIR | 100000 | 0 | DSF0000889866
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 7/10/2020 | DIIR |  | DIIR | 50000 | 0 | DSF0000890190
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 2/17/2022 | DIIR |  | DIIR | 111666 | 0 | DSF0000913651
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 40000 | 0 | DSF0000960898
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 153995 | 0 | DSF0001008144
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033682
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086326
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112908
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/24/2024 | DOES | 7/31/2024 | DOES | 65832 |  | DSF0001085490
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | Scope | Complete | 4/27/2021 | 9/10/2021 | 9/8/2021 | 56358 | 68816 | 68816 | DSF0000994645
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | Design | Complete | 9/9/2021 | 2/14/2022 | 5/6/2022 | 281792 | 251114 | 251114 | DSF0000994645
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | Construction | In-Progress | 6/12/2023 | 12/2/2024 |  | 6340318 | 5755968 | 3158762 | DSF0000994645
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | CM,F&E | In-Progress | 6/12/2023 | 12/2/2024 |  | 394509 | 242834 | 236302 | DSF0000994645
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/9/2023 | 7/10/2023 | 3/21/2023 | 4500 | 2013 | 2013 | DSF0001034564
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/3/2023 | 20250 | 8052 | 8052 | DSF0001034564
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/8/2023 | 12/6/2024 |  | 261000 | 233371 | 119942 | DSF0001034564
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/8/2023 | 12/6/2024 |  | 130544 | 109889 | 54981 | DSF0001034564
3 | M841 | M811 SPED - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/8/2021 | EMER |  | EMER | 25923 | 25923 | SCA0000069792
3 | M841 | M811 SPED - MANHATTAN | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001086327
3 | M841 | M811 SPED - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 3/21/2022 | DOES |  | DOES | 72385 | 374843 | DSF0001020263
3 | M841 | M811 SPED - MANHATTAN | DOE - Skilled Trades | CHILLED WATER COIL REPLACEMENT | Construction | In-Progress | 2/23/2024 | DOES |  | DOES | 67305 | 0 | DSF0001111830
3 | M932 | P.S. 859 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086336
3 | MQAE | HARLEM HEBREW LANGUAGE CHARTER SCHOOL | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000913659
3 | MQAE | HARLEM HEBREW LANGUAGE CHARTER SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 99648 | 0 | DSF0001033183
4 | M007 | P.S. 7 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 12/14/2023 | 5/1/2024 | 5/10/2024 | 96443 | 91322 | 91259 | DSF0001067975, DSF0001095677
4 | M007 | P.S. 7 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 5/28/2024 | 10/29/2024 |  | 437829 | 437829 | 7295 | DSF0001067975, DSF0001095677
4 | M007 | P.S. 7 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 6833914 | 6833914 | 40193 | DSF0001067975, DSF0001095677
4 | M007 | P.S. 7 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 843361 | 843361 | 48868 | DSF0001067975, DSF0001095677
4 | M007 | P.S. 7 - MANHATTAN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 10/23/2020 | FTK |  | FTK | 207020 | 165322 | DSF0000912697, DSF0000912923
4 | M007 | P.S. 7 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/9/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084622
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA ROOFS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES / NON-IDA PLAYGROUND UPGRADE | Scope | Complete | 1/21/2022 | 6/7/2022 | 12/21/2022 | 121867 | 247614 | 112052 | SCA0000070741, DSF0001083709, DSF0001068069, DSF0001068072, DSF0001083710, DSF0001086883
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA ROOFS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES / NON-IDA PLAYGROUND UPGRADE | Design | In-Progress | 12/23/2022 | 5/26/2023 |  | 607409 | 705677 | 430547 | SCA0000070741, DSF0001083709, DSF0001068069, DSF0001068072, DSF0001083710, DSF0001086883
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA ROOFS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES / NON-IDA PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 13499879 | 13499879 | 160863 | SCA0000070741, DSF0001083709, DSF0001068069, DSF0001068072, DSF0001083710, DSF0001086883
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA ROOFS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES / NON-IDA PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 867539 | 867539 | 146835 | SCA0000070741, DSF0001083709, DSF0001068069, DSF0001068072, DSF0001083710, DSF0001086883
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | PATH OF TRAVEL IDA FLOOD ELIMINATION | Scope | Complete | 1/25/2023 | 4/26/2023 | 3/27/2023 | 9146 | 12871 | 0 | DSF0001083734
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | PATH OF TRAVEL IDA FLOOD ELIMINATION | Design | In-Progress | 3/28/2023 | 7/27/2023 |  | 41157 | 41157 | 0 | DSF0001083734
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | PATH OF TRAVEL IDA FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 530468 | 530468 | 53 | DSF0001083734
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | PATH OF TRAVEL IDA FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 98320 | 98320 | 2896 | DSF0001083734
4 | M013 | P.S. 497 - MANHATTAN | SCA IEH | PO18-ABATE & REPLACE CAFETERIA CEILING | Construction | Complete | 7/18/2024 | IEH | 7/20/2024 | IEH | 0 | 0 | SCA0000073154
4 | M013 | P.S. 497 - MANHATTAN | SCA IEH | PO18-ABATE CAFETERIA CEILING DUE TO WATER PENETRATION CAUSING SEVERAL TILES TO FALL . THE CEILING IS | Construction | Complete | 8/19/2024 | IEH | 8/25/2024 | IEH | 0 | 0 | SCA0000073301
4 | M013 | P.S. 497 - MANHATTAN | DOE - RESOA | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/16/2018 | DOER |  | DOER | 127861 | 0 | DSF0000866429
4 | M013 | EAST HARLEM SCHOLARS ACADEMY CHARTER SCHOOL II - M | DOE - RESOA | FY19 RESO A TOILET STUDENTS | Construction | In-Progress | 6/21/2019 | DOER |  | DOER | 79836 | 0 | DSF0000889851
4 | M013 | P.S. 497 - MANHATTAN | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/15/2023 | DOER |  | DOER | 60436 | 0 | DSF0000913073
4 | M013 | EAST HARLEM SCHOLARS ACADEMY CHARTER SCHOOL II - M | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 5/9/2022 | DOER |  | DOER | 37611 | 0 | DSF0000913295
4 | M013 | CENTRAL PARK EAST HS - MANHATTAN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 3/5/2020 | DOER |  | DOER | 75000 | 0 | DSF0000913339
4 | M013 | P.S. 497 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 218617 | 0 | DSF0001086171
4 | M013 | CENTRAL PARK EAST HS - MANHATTAN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 288000 | 0 | DSF0001086172
4 | M013 | P.S. 497 - MANHATTAN | DOE - Skilled Trades | ACE BOILER BURNER CONVERSIONS | Construction | In-Progress | 4/29/2022 | DOES |  | DOES | 3390158 | 0 | DSF0000912464
4 | M013 | CENTRAL PARK EAST HS - MANHATTAN | DOE - Skilled Trades | GYM CEILING | Construction | In-Progress | 5/5/2023 | DOES |  | DOES | 167171 | 0 | DSF0001085127
4 | M045 | P.S. 37 - MANHATTAN | SCA CIP | SIDEWALK REPAIR / ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 1/17/2023 | 2/6/2024 | 12/5/2023 | 173001 | 255269 | 239706 | DSF0001083716, DSF0001068381, DSF0001096081, DSF0001096080, DSF0001096076
4 | M045 | P.S. 37 - MANHATTAN | SCA CIP | SIDEWALK REPAIR / ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | Complete | 12/21/2023 | 5/23/2024 | 4/26/2024 | 865002 | 474802 | 377677 | DSF0001083716, DSF0001068381, DSF0001096081, DSF0001096080, DSF0001096076
4 | M045 | P.S. 37 - MANHATTAN | SCA CIP | SIDEWALK REPAIR / ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Construction | In-Progress | 11/20/2024 | 5/8/2027 |  | 19462500 | 17532055 | 159903 | DSF0001083716, DSF0001068381, DSF0001096081, DSF0001096080, DSF0001096076
4 | M045 | P.S. 37 - MANHATTAN | SCA CIP | SIDEWALK REPAIR / ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | CM,F&E | In-Progress | 11/20/2024 | 5/8/2027 |  | 1211001 | 123714 | 117879 | DSF0001083716, DSF0001068381, DSF0001096081, DSF0001096080, DSF0001096076
4 | M045 | P.S. 37 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL FOR PIPE INSULATION ON A STEAM PIPE, 8' LOCATED IN THE STORAGE ROOM THE BASEMENT AR | Construction | Complete | 8/1/2024 | IEH | 9/18/2024 | IEH | 0 | 0 | SCA0000073222
4 | M045 | P.S. 37 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112768
4 | M045 | P.S. 37 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 446089 | 0 | DSF0001035634
4 | M045 | P.S. 37 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/10/2024 | DOES | 7/24/2024 | DOES | 65832 | 10624 | DSF0001084195
4 | M045 | P.S. 37 - MANHATTAN | DOE - Skilled Trades | SWIMMING POOL | Construction | In-Progress | 5/29/2024 | DOES |  | DOES | 360648 | 0 | DSF0001096078
4 | M050 | P.S. 964 - MANHATTAN | SCA IEH | PO18-ROOM 122, ABATE 10 SQ. FT. CEILING PLASTER, 10 L.F. PIPE INSULATION ROOM 208, ABATE 5 SQ. FT. W | Construction | In-Progress | 5/29/2024 | IEH |  | IEH | 0 | 0 | SCA0000073036
4 | M050 | NY CENTER FOR AUTISM CHARTER - M | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/11/2023 | DOER |  | DOER | 189281 | 0 | DSF0001033687
4 | M050 | P.S. 964 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/3/2024 | DOES | 9/6/2024 | DOES | 65832 | 9955 | DSF0001084625
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 7/27/2018 | 12/13/2018 | 3/21/2019 | 124610 | 157587 | 154843 | DSF0000889342
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/6/2019 | 4/27/2020 | 5/14/2021 | 623050 | 450847 | 446926 | DSF0000889342
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 7/20/2022 | 7/18/2024 |  | 14018625 | 14507928 | 5909235 | DSF0000889342
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 7/20/2022 | 7/18/2024 |  | 978062 | 1383715 | 1372187 | DSF0000889342
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/2/2022 | 9/30/2022 | 6/9/2022 | 3426 | 2739 | 2739 | DSF0001034624
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/9/2022 | 12/6/2022 | 10/25/2022 | 15415 | 10955 | 10955 | DSF0001034624
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 4/17/2023 | 3/11/2024 |  | 198679 | 184722 | 161917 | DSF0001034624
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 4/17/2023 | 3/11/2024 |  | 142519 | 145234 | 131244 | DSF0001034624
4 | M057 | P.S. 57 - MANHATTAN | SCA IEH | PO18-BASEMENT STAIRWAY, ABATE 93 L.F. PIPE INSULATION ROOM B15, ABATE 170 L.F. PIPE INSULATION MARKE | Construction | Complete | 7/17/2024 | IEH | 9/13/2024 | IEH | 0 | 0 | SCA0000073144
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY | Scope | Complete | 7/13/2023 | 11/29/2023 | 11/7/2023 | 34411 | 56213 | 54528 | DSF0001085177, DSF0001111826
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY | Design | Complete | 11/17/2023 | 4/22/2024 | 4/24/2024 | 172055 | 129205 | 124281 | DSF0001085177, DSF0001111826
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 3871250 | 3871250 | 91414 | DSF0001085177, DSF0001111826
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 240877 | 240877 | 55908 | DSF0001085177, DSF0001111826
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/14/2022 | 10/13/2022 | 6/28/2022 | 4689 | 4028 | 4028 | DSF0001034582
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/28/2022 | 12/23/2022 | 10/25/2022 | 21099 | 16109 | 16109 | DSF0001034582
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 4/17/2023 | 3/11/2024 |  | 271948 | 247047 | 218454 | DSF0001034582
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 4/17/2023 | 3/11/2024 |  | 155435 | 139309 | 125307 | DSF0001034582
4 | M072 | P.S. 72 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SIDEWALK BRIDGE @ PS72M | Construction | In-Progress | 10/2/2023 | EMER |  | EMER | 199023 | 105817 | SCA0000072367
4 | M072 | P.S. 72 - MANHATTAN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 7/13/2021 | FTK |  | FTK | 119228 | 111965 | DSF0000912082
4 | M072 | P.S. 72 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000889840
4 | M072 | P.S. 72 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000890161
4 | M072 | P.S. 72 - MANHATTAN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 1/23/2024 | DOEL |  | DOEL | 55323 | 50323
4 | M072 | P.S. 72 - MANHATTAN | DOE - RESOA | FY17 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 79400 | 0 | DSF0000844208
4 | M072 | P.S. 72 - MANHATTAN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/1/2022 | DOER |  | DOER | 197247 | 0 | DSF0001033636
4 | M072 | P.S. 72 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 6/22/2022 | DOES |  | DOES | 444648 | 0 | DSF0000992462
4 | M072 | P.S. 72 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/26/2024 | DOES | 9/4/2024 | DOES | 65832 |  | DSF0001084627
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2/4/2020 | 7/6/2020 | 4/2/2020 | 59840 | 92204 | 92204 | DSF0000960648, DSF0000943795
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 4/3/2020 | 9/2/2020 | 7/16/2020 | 299201 | 465126 | 396920 | DSF0000960648, DSF0000943795
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 9/20/2021 | 9/19/2023 |  | 6732000 | 6401037 | 5274824 | DSF0000960648, DSF0000943795
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 9/20/2021 | 9/19/2023 |  | 420477 | 1120763 | 1093492 | DSF0000960648, DSF0000943795
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 9/29/2023 | 2/20/2024 | 11/9/2023 | 173903 | 125439 | 121931 | DSF0001068739, DSF0001111834, DSF0001111833, DSF0001111832
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/20/2023 | 5/22/2024 | 5/7/2024 | 869516 | 324288 | 324168 | DSF0001068739, DSF0001111834, DSF0001111833, DSF0001111832
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 19564118 | 19564118 | 205429 | DSF0001068739, DSF0001111834, DSF0001111833, DSF0001111832
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1217322 | 1217322 | 48354 | DSF0001068739, DSF0001111834, DSF0001111833, DSF0001111832
4 | M083 | P.S. 83 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- PUBLIC PROTECTION @ M083 | Construction | In-Progress | 10/11/2023 | EMER |  | EMER | 89262 | 56375 | SCA0000072390
4 | M083 | P.S. 83 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN THE GYM 2ND FLOOR APPROXIMATELY 64 SQFT. FLOOR TILES 9X9, CRAC | Construction | In-Progress | 3/28/2024 | IEH |  | IEH | 0 | 0 | SCA0000072884
4 | M083 | P.S. 83 - MANHATTAN | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 10/25/2024 | FTK |  | FTK | 6541 | 561 | DSF0001087473
4 | M083 | P.S. 182 - MANHATTAN | DOE - RESOA | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 11/27/2019 | DOER |  | DOER | 93994 | 0 | DSF0000866427
4 | M083 | P.S. 83 - MANHATTAN | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 357339 | 0 | DSF0001086201
4 | M083 | P.S. 83 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112783
4 | M083 | P.S. 182 - MANHATTAN | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0 | DSF0001112784
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2/18/2020 | 7/17/2020 | 4/27/2020 | 96801 | 175086 | 151088 | DSF0000960649, DSF0000960650, DSF0000943905
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 4/28/2020 | 9/28/2020 | 10/29/2020 | 484003 | 613645 | 548355 | DSF0000960649, DSF0000960650, DSF0000943905
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 8/4/2022 | 8/2/2024 |  | 10890057 | 9993369 | 8743735 | DSF0000960649, DSF0000960650, DSF0000943905
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 8/4/2022 | 8/2/2024 |  | 677603 | 499641 | 496541 | DSF0000960649, DSF0000960650, DSF0000943905
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 5/10/2024 | 9/26/2024 | 11/18/2024 | 171414 | 179553 | 56205 | DSF0001096581, DSF0001096585, DSF0001124338, DSF0001124341, DSF0001124339
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Design | In-Progress | 11/27/2024 | 5/1/2025 |  | 793701 | 793701 | 8963 | DSF0001096581, DSF0001096585, DSF0001124338, DSF0001124341, DSF0001124339
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | PNS | PNS | PNS | PNS | 12530400 | 12530400 | 55145 | DSF0001096581, DSF0001096585, DSF0001124338, DSF0001124341, DSF0001124339
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 1326382 | 1326382 | 30618 | DSF0001096581, DSF0001096585, DSF0001124338, DSF0001124341, DSF0001124339
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/11/2022 | 11/8/2022 | 8/18/2022 | 3986 | 4160 | 4160 | DSF0001034599
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/18/2022 | 2/16/2023 | 10/25/2022 | 17936 | 16641 | 16641 | DSF0001034599
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 4/17/2023 | 3/11/2024 |  | 231173 | 213570 | 190453 | DSF0001034599
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 4/17/2023 | 3/11/2024 |  | 141724 | 133544 | 122327 | DSF0001034599
4 | M096 | P.S. 96 - MANHATTAN | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 764952 | 0 | DSF0001008937
4 | M096 | P.S. 96 - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADE | Construction | In-Progress | 4/1/2024 | DOER |  | DOER | 101050 | 0 | DSF0001035321
4 | M096 | P.S. 96 - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112792
4 | M096 | P.S. 96 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/7/2024 | DOES | 9/13/2024 | DOES | 65832 |  | DSF0001084630
4 | M099 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/21/2020 | 1/29/2021 | 9/24/2020 | 14880 | 31213 | 31213 | DSF0000875653
4 | M099 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 10/14/2020 | 7/28/2021 | 8/18/2021 | 66960 | 116570 | 116570 | DSF0000875653
4 | M099 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 7/1/2022 | 6/30/2023 |  | 863040 | 812175 | 429242 | DSF0000875653
4 | M099 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 7/1/2022 | 6/30/2023 |  | 159960 | 153115 | 139065 | DSF0000875653
4 | M099 | I.S. 224 - MANHATTAN | SCA IEH | PO18-M385@M099 SUCCESS ACADEMY #2024-63662 DRILL TO INSTALL A WIRELESS ACCESS POINT ON CEILING | Construction | Complete | 8/1/2024 | IEH | 8/10/2024 | IEH | 0 | 0 | SCA0000073220
4 | M099 | I.S. 224 - MANHATTAN | SCA IEH | PO18-10' OF ACM REMOVAL FROM CEILING PLASTER AND AREOUND PIPE INSULATION IN ROOM 410A AREA SPRAYED | Construction | Complete | 12/5/2024 | IEH | 12/14/2024 | IEH | 0 | 0 | SCA0000073677
4 | M099 | INNOVATION CHARTER HS - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 10/16/2023 | DOES | 11/21/2023 | DOES | 62543 |  | DSF0000866119
4 | M099 | I.S. 224 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/30/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084946
4 | M099 | I.S. 224 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/11/2024 | DOES |  | DOES | 520161 | 0 | DSF0001085736
4 | M101 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/26/2020 | 2/2/2021 | 10/15/2020 | 15640 | 21211 | 21211 | DSF0000890568
4 | M101 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 11/3/2020 | 7/28/2021 | 7/28/2021 | 70380 | 84886 | 84886 | DSF0000890568
4 | M101 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 6/24/2022 | 6/23/2023 |  | 907120 | 841057 | 745419 | DSF0000890568
4 | M101 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 6/24/2022 | 6/23/2023 |  | 168130 | 140223 | 123392 | DSF0000890568
4 | M101 | PS/IS 375 - MANHATTAN | SCA IEH | PO18-ABATE PIPE INSULATION IN THE OIL TANK ROOM (SPACE ID# 1018) LOCATED IN THE BASEMENT NEXT TO BOI | Construction | Complete | 11/14/2024 | IEH | 11/17/2024 | IEH | 0 | 0 | SCA0000073608
4 | M101 | PS/IS 375 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 10/2/2023 | DOER | 12/4/2023 | DOER | 229748 |  | DSF0001035657
4 | M102 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/9/2021 | 9/9/2021 | 6/14/2021 | 75000 | 112742 | 112742 | DSF0000992739, DSF0000798322
4 | M102 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 6/16/2021 | 11/17/2021 | 11/4/2021 | 375000 | 530144 | 481403 | DSF0000992739, DSF0000798322
4 | M102 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 8/8/2022 | 8/6/2024 |  | 8437501 | 7699099 | 6436237 | DSF0000992739, DSF0000798322
4 | M102 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 8/8/2022 | 8/6/2024 |  | 525000 | 1108875 | 1093048 | DSF0000992739, DSF0000798322
4 | M102 | M169 SPED - MANHATTAN | DOE - RESOA | FY14 RESO A PLAYGROUND REDEVELOPMEN | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0000798674
4 | M102 | P.S. 102 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 95448 | 0 | DSF0001009113
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/11/2023 | 5/11/2023 | 1/24/2023 | 2412 | 2397 | 2397 | DSF0001034552
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/24/2023 | 7/20/2023 | 4/11/2023 | 10852 | 9588 | 9588 | DSF0001034552
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/3/2023 | 10/1/2024 |  | 139875 | 134291 | 38808 | DSF0001034552
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/3/2023 | 10/1/2024 |  | 76719 | 112313 | 63445 | DSF0001034552
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 8/25/2022 | DOER |  | DOER | 34498 | 0 | DSF0001033727
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 30194 | 0 | DSF0001035660
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/6/2017 | DOES |  | DOES | 252768 | 0 | DSF0000866002
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/29/2023 | 10/30/2023 | 10/13/2023 | 8560 | 15709 | 15709 | DSF0001083801
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/25/2023 | 3/26/2024 | 3/20/2024 | 38520 | 80189 | 41468 | DSF0001083801
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/26/2024 | 9/25/2025 |  | 496480 | 464375 | 16095 | DSF0001083801
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/26/2024 | 9/25/2025 |  | 92020 | 61004 | 14780 | DSF0001083801
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/24/2023 | 5/23/2023 | 2/13/2023 | 4119 | 3546 | 3546 | DSF0001034616
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/13/2023 | 8/9/2023 | 4/11/2023 | 18537 | 14187 | 14187 | DSF0001034616
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/3/2023 | 10/1/2024 |  | 238925 | 220823 | 118264 | DSF0001034616
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/3/2023 | 10/1/2024 |  | 135004 | 162141 | 102232 | DSF0001034616
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY17 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/10/2019 | DOER |  | DOER | 212061 | 0 | DSF0000844856
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/1/2018 | DOER |  | DOER | 36612 | 0 | DSF0000890663
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 418983 | 0 | DSF0000913310
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 7/15/2022 | DOER | 6/24/2023 | DOER | 174853 | 157381 | DSF0001033162
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY23 RESO A STEM LAB | Construction | Complete | 10/2/2023 | DOER | 11/9/2023 | DOER | 100141 |  | DSF0001035661
4 | M112 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 7/8/2019 | 11/21/2019 | 10/3/2019 | 173003 | 185613 | 130113 | DSF0000912339
4 | M112 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 3/3/2021 | 8/17/2021 | 3/27/2023 | 865016 | 1042217 | 539751 | DSF0000912339
4 | M112 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 7/17/2023 | 1/1/2026 |  | 19462868 | 17706312 | 3836630 | DSF0000912339
4 | M112 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 7/17/2023 | 1/1/2026 |  | 1211023 | 499148 | 493671 | DSF0000912339
4 | M112 | P.S. 112 - MANHATTAN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 150000 | 0 | DSF0001086213
4 | M112 | P.S. 112 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0 | DSF0001112797
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-R/R STEAM LEAK IN RM EB11 (TEST WALL) | Construction | In-Progress | 12/22/2023 | IEH |  | IEH | 0 | 0 | SCA0000072591
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-ABATED AND REPAIRE 9X9 FLOOR TILES ROOM 312. 9X9 TILES ARE DETERIORATING, CRACKED AND POPPIN | Construction | Complete | 6/27/2024 | IEH | 7/5/2024 | IEH | 0 | 0 | SCA0000073093
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-ABATE FLOOR IN WEST #322 (CORE DRILLING REQUIRED) THROUGH THE CEILING IN RM #222. NEW FEED IS N | Construction | Complete | 6/28/2024 | IEH | 7/2/2024 | IEH | 0 | 0 | SCA0000073097
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-ABATED AND REPAIR 9X9 FLOOR TILES ROOM 310. TILES ARE DETERIORATING, CRACKED AND POPPING UP | Construction | Complete | 7/1/2024 | IEH | 7/24/2024 | IEH | 0 | 0 | SCA0000073112
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-TEST FOR ACM IN GYM ALL LAYERS OF FLOORING CORE DRILLING NEEDED TO INSTALL VOLLYBALL POST ASSIG | Construction | Complete | 7/29/2024 | IEH | 10/25/2024 | IEH | 0 | 0 | SCA0000073190
4 | M117 | I.S. 12 - MANHATTAN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 6/22/2024 |  | 9/26/2024 | 75000 | 75000 | 74839 | DSF0001035669
4 | M117 | M138 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 55000 | 0 | DSF0001086217
4 | M117 | I.S. 12 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/2/2024 | DOER |  | DOER | 1035973 | 0 | DSF0001035326
4 | M117 | M138 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112802
4 | M117 | I.S. 12 - MANHATTAN | DOE - Skilled Trades | ACE BOILER BURNER CONVERSIONS | Construction | In-Progress | 5/24/2021 | DOES |  | DOES | 2974717 | 0 | DSF0000912465
4 | M117 | I.S. 12 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/18/2022 | DOES |  | DOES | 173826 | 0 | DSF0001008693
4 | M117 | I.S. 12 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/30/2024 | DOES | 10/11/2024 | DOES | 65832 | 7900 | DSF0001084632
4 | M121 | P.S. 38 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 5/4/2023 | 9/20/2023 | 11/7/2023 | 58698 | 102511 | 98461 | DSF0001069181, DSF0001069183, DSF0001111816, DSF0001111815
4 | M121 | P.S. 38 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | Complete | 11/27/2023 | 4/29/2024 | 4/29/2024 | 285575 | 223431 | 210405 | DSF0001069181, DSF0001069183, DSF0001111816, DSF0001111815
4 | M121 | P.S. 38 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 5740485 | 5740485 | 155847 | DSF0001069181, DSF0001069183, DSF0001111816, DSF0001111815
4 | M121 | P.S. 38 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 470281 | 470281 | 68676 | DSF0001069181, DSF0001069183, DSF0001111816, DSF0001111815
4 | M121 | P.S. 38 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/31/2022 | EMER |  | EMER | 33094 | 17348 | SCA0000070829
4 | M121 | P.S. 38 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033628
4 | M121 | P.S. 38 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001035211
4 | M121 | P.S. 38 - MANHATTAN | DOE - Skilled Trades | DOMESTIC WATER BOOSTER PUMPS | Construction | In-Progress | 3/3/2021 | DOES |  | DOES | 68672 | 0 | DSF0001008751
4 | M121 | P.S. 38 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 10/20/2022 | DOES | 11/17/2022 | DOES | 65999 | 65111 | DSF0001009111
4 | M121 | P.S. 38 - MANHATTAN | DOE - Skilled Trades | BOILER FEED & VACUUM PUMP REPLACEMENT | Construction | In-Progress | 3/11/2024 | DOES |  | DOES | 60712 | 0 | DSF0001097039
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 11/5/2019 | 5/5/2020 | 12/18/2019 | 16980 | 19972 | 19972 | DSF0000890574
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 1/8/2020 | 7/2/2020 | 3/30/2020 | 76410 | 61132 | 61132 | DSF0000890574
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 10/21/2022 | 10/20/2023 |  | 984840 | 917404 | 538308 | DSF0000890574
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 10/21/2022 | 10/20/2023 |  | 182535 | 150616 | 144610 | DSF0000890574
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 7/12/2022 | 11/28/2022 | 1/31/2023 | 211757 | 218209 | 218085 | DSF0001018822, DSF0001018823, DSF0001083887
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2/3/2023 | 7/7/2023 | 11/1/2023 | 1058784 | 583059 | 548803 | DSF0001018822, DSF0001018823, DSF0001083887
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 23822632 | 23822632 | 213020 | DSF0001018822, DSF0001018823, DSF0001083887
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 1482297 | 1482297 | 225501 | DSF0001018822, DSF0001018823, DSF0001083887
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/8/2023 | 6/8/2023 | 3/2/2023 | 3369 | 3265 | 3265 | DSF0001034623
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/2/2023 | 8/25/2023 | 4/11/2023 | 15160 | 13061 | 13061 | DSF0001034623
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/3/2023 | 10/1/2024 |  | 195400 | 182191 | 96968 | DSF0001034623
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/3/2023 | 10/1/2024 |  | 68933 | 76906 | 75414 | DSF0001034623
4 | M146 | P.S. 146 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION - CONCRETE/STEEL SPALL | Construction | In-Progress | 8/4/2022 | EMER |  | EMER | 55686 | 25056 | SCA0000071353
4 | M146 | P.S. 146 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION IN THE CRAWLSPACE APPROXIMATELY 10 FT OF PIPING ON BOTH LINES IN | Construction | In-Progress | 7/2/2024 | IEH |  | IEH | 0 | 0 | SCA0000073114
4 | M146 | P.S. 146 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/1/2023 | DOER |  | DOER | 500000 | 9025 | DSF0001086234
4 | M146 | P.S. 146 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0 | DSF0001112816
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | Scope | Complete | 9/8/2021 | 1/27/2022 | 12/28/2021 | 136319 | 186999 | 186319 | DSF0001009294, DSF0001018917, DSF0001034393
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | Design | Complete | 2/2/2022 | 7/20/2022 | 11/10/2022 | 681596 | 542333 | 481561 | DSF0001009294, DSF0001018917, DSF0001034393
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | Construction | In-Progress | 8/3/2023 | 8/1/2025 |  | 15335909 | 14076197 | 4980331 | DSF0001009294, DSF0001018917, DSF0001034393
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | CM,F&E | In-Progress | 8/3/2023 | 8/1/2025 |  | 974642 | 739707 | 694238 | DSF0001009294, DSF0001018917, DSF0001034393
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | Scope | Complete | 12/22/2022 | 6/22/2023 | 12/13/2023 | 273180 | 321437 | 316821 | DSF0001083675, DSF0001111895, DSF0001097338, DSF0001097341
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | Design | Complete | 12/20/2023 | 9/12/2024 | 5/8/2024 | 1365900 | 1176937 | 1124734 | DSF0001083675, DSF0001111895, DSF0001097338, DSF0001097341
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | Construction | In-Progress | 9/27/2024 | 9/11/2027 |  | 30732750 | 27542018 | 147326 | DSF0001083675, DSF0001111895, DSF0001097338, DSF0001097341
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | CM,F&E | In-Progress | 9/27/2024 | 9/11/2027 |  | 1912260 | 193445 | 188253 | DSF0001083675, DSF0001111895, DSF0001097338, DSF0001097341
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/22/2023 | 9/21/2023 | 6/13/2023 | 3810 | 947 | 947 | DSF0001035031
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/13/2023 | 12/11/2023 | 8/16/2023 | 17145 | 3788 | 3788 | DSF0001035031
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/26/2024 | 12/21/2024 |  | 220980 | 205904 | 71826 | DSF0001035031
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/26/2024 | 12/21/2024 |  | 115677 | 100249 | 93703 | DSF0001035031
4 | M155 | I.S. 377 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/23/2022 | DOER |  | DOER | 41643 | 0 | DSF0000913336
4 | M155 | P.S. 155 - MANHATTAN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 5/9/2016 | DOES |  | DOES | 75200 | 0 | DSF0000786334
4 | M155 | P.S. 155 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/14/2023 | DOES |  | DOES | 342806 | 0 | DSF0001035129
4 | M155 | P.S. 155 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/8/2024 | DOES | 11/12/2024 | DOES | 65832 | 10135 | DSF0001084230
4 | M171 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2023 | 6/29/2023 | 3/9/2023 | 5310 | 1200 | 1200 | DSF0001034633
4 | M171 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/9/2023 | 9/1/2023 | 5/3/2023 | 23895 | 4799 | 4799 | DSF0001034633
4 | M171 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/6/2023 | 9/30/2024 |  | 307980 | 279393 | 170357 | DSF0001034633
4 | M171 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/6/2023 | 9/30/2024 |  | 195761 | 170784 | 113060 | DSF0001034633
4 | M171 | P.S. 171 - MANHATTAN | SCA IEH | PO18-/ABATE 8' OF PIPE COVERING IN KITCHEN CEILING IT IS MARKED WITH WHITE PAINT | Construction | Complete | 10/1/2024 | IEH | 10/5/2024 | IEH | 0 | 0 | SCA0000073458
4 | M171 | P.S. 171 - MANHATTAN | SCA IEH | PO18-ABATEMENT OF PIPE INSULATION: BASEMENT - BACK NORTH/EAST WALKWAY IN BOILER RM WATER SUPPLY LINE | Construction | Complete | 11/7/2024 | IEH | 11/10/2024 | IEH | 0 | 0 | SCA0000073592
4 | M171 | P.S. 171 - MANHATTAN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 1/13/2020 | FTK |  | FTK | 241049 | 212458 | DSF0000911966, DSF0000912467
4 | M171 | P.S. 171 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112829
4 | M171 | P.S. 171 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/26/2024 | DOES | 9/6/2024 | DOES | 65832 |  | DSF0001084640
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 7/8/2019 | 11/21/2019 | 10/3/2019 | 136097 | 217884 | 162345 | DSF0000912338
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 3/3/2021 | 8/17/2021 | 3/27/2023 | 680484 | 799858 | 412099 | DSF0000912338
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 7/17/2023 | 1/1/2026 |  | 15310882 | 13977894 | 3780473 | DSF0000912338
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 7/17/2023 | 1/1/2026 |  | 953709 | 866626 | 857566 | DSF0000912338
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/3/2023 | 7/3/2023 | 3/9/2023 | 6490 | 2057 | 2057 | DSF0001034591
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/9/2023 | 9/1/2023 | 5/3/2023 | 29205 | 8225 | 8225 | DSF0001034591
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/6/2023 | 9/30/2024 |  | 376420 | 339582 | 158724 | DSF0001034591
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/6/2023 | 9/30/2024 |  | 201024 | 169187 | 80841 | DSF0001034591
4 | M206 | P.S. 206 - MANHATTAN | SCA IEH | PO18-ABATE STEAM PIPE IN MECHANICAL ROOM | Construction | Complete | 9/26/2024 | IEH | 12/17/2024 | IEH | 0 | 0 | SCA0000073442
4 | M206 | P.S. 206 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/12/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084644
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/20/2020 | 1/29/2021 | 8/7/2020 | 14940 | 43434 | 43434 | DSF0000890576
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 8/19/2020 | 7/28/2021 | 12/15/2021 | 67230 | 164886 | 164886 | DSF0000890576
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 7/11/2022 | 7/10/2023 |  | 866520 | 806862 | 575777 | DSF0000890576
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 7/11/2022 | 7/10/2023 |  | 160605 | 129552 | 119792 | DSF0000890576
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/2/2020 | 9/30/2020 | 6/26/2020 | 4926 | 3868 | 3868 | DSF0000960797
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/26/2020 | 12/23/2020 | 12/22/2020 | 22168 | 15470 | 15470 | DSF0000960797
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/17/2022 | 9/12/2023 |  | 285722 | 251947 | 238122 | DSF0000960797
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 11/17/2022 | 9/12/2023 |  | 181104 | 185772 | 180822 | DSF0000960797
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA IEH | PO18-PERFORM ABATEMENT & ONE 4' INCH CORE DRILLING ON THE FLOOR LOCATED IN THE WORK ROOM IN LIBRARY | Construction | In-Progress | 8/23/2024 | IEH |  | IEH | 0 | 0 | SCA0000073311
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 171300 | 0 | DSF0000913337
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 1/20/2023 | DOES | 10/30/2023 | DOES | 935298 | 924073 | DSF0000960856
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/8/2022 | DOES | 10/24/2022 | DOES | 193378 | 196610 | DSF0001034244
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/18/2020 | 1/29/2021 | 9/3/2020 | 10937 | 28830 | 28830 | DSF0000877109
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 10/14/2020 | 7/28/2021 | 7/28/2021 | 49214 | 115316 | 115316 | DSF0000877109
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 6/12/2023 | 6/10/2024 |  | 634317 | 593650 | 300623 | DSF0000877109
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 6/12/2023 | 6/10/2024 |  | 117567 | 102092 | 100403 | DSF0000877109
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 12/18/2023 | 5/3/2024 | 6/26/2024 | 35050 | 72817 | 69905 | DSF0001070600, DSF0001098301, DSF0001098302
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 7/8/2024 | 12/9/2024 |  | 167921 | 167921 | 70864 | DSF0001070600, DSF0001098301, DSF0001098302
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 3540183 | 3540183 | 34195 | DSF0001070600, DSF0001098301, DSF0001098302
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 302110 | 302110 | 64848 | DSF0001070600, DSF0001098301, DSF0001098302
4 | M495 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000011757
4 | M495 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 9/15/2003 | 10/30/2003 | 10/30/2003 | 0 | 0 | 0 | DSF0000011757
4 | M495 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 5/10/2004 | 3/15/2006 |  | 0 | 0 | 0 | DSF0000011757
4 | M495 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 5/10/2004 | 3/15/2006 |  | 0 | 0 | 0 | DSF0000011757
4 | M495 | PARK EAST HS - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 75000 | 54394 | DSF0001086308
4 | M495 | PARK EAST HS - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 3/28/2023 | DOER |  | DOER | 43664 | 0 | DSF0001035769
4 | M495 | PARK EAST HS - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112898
4 | M495 | PARK EAST HS - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 2/21/2023 | DOES |  | DOES | 178998 | 0 | DSF0001034921
4 | M495 | PARK EAST HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/27/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084965
4 | M495 | PARK EAST HS - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/22/2024 | DOES |  | DOES | 299106 | 0 | DSF0001085746
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | EXTERIOR MASONRY- PERMANENT FIX / PARAPETS | Scope | Complete | 5/31/2023 | 10/17/2023 | 10/25/2023 | 73701 | 85330 | 85330 | DSF0001098580, DSF0001098579
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | EXTERIOR MASONRY- PERMANENT FIX / PARAPETS | Design | In-Progress | 12/20/2023 | 5/22/2024 |  | 330731 | 330731 | 95480 | DSF0001098580, DSF0001098579
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | EXTERIOR MASONRY- PERMANENT FIX / PARAPETS | Construction | PNS | PNS | PNS | PNS | 5127026 | 5127026 | 28502 | DSF0001098580, DSF0001098579
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | EXTERIOR MASONRY- PERMANENT FIX / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 687382 | 687382 | 21379 | DSF0001098580, DSF0001098579
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/22/2023 | 9/21/2023 | 6/6/2023 | 4010 | 678 | 678 | DSF0001035035
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/6/2023 | 12/4/2023 | 8/16/2023 | 18045 | 2712 | 2712 | DSF0001035035
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/26/2024 | 12/21/2024 |  | 232580 | 221944 | 75804 | DSF0001035035
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/26/2024 | 12/21/2024 |  | 127437 | 114161 | 79756 | DSF0001035035
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA Emergency Response | EMERGENCY STABILIZATION- EXTERIOR MASONRY | Construction | In-Progress | 11/28/2022 | EMER |  | EMER | 1053160 | 994956 | SCA0000071580
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 7/30/2021 | FTK |  | FTK | 145232 | 132840 | DSF0000961567
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084978
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | DOE - Skilled Trades | ROOFS | Construction | In-Progress | 10/4/2023 | DOES |  | DOES | 460219 | 0 | DSF0001087246
4 | M895 | YOUNG WOMEN'S LEADERSHIP SCHOOL | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 50000 | 50000 | 0 | DSF0001033243
4 | M895 | YOUNG WOMEN'S LEADERSHIP SCHOOL | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 10/31/2024 | FTK |  | FTK | 356280 | 167539 | DSF0001085097
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | ROOF LEAK / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 10/7/2022 | 1/11/2023 | 1/27/2023 | 218792 | 265386 | 265386 | DSF0001068033, DSF0001068034, DSF0001083841
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | ROOF LEAK / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2/9/2023 | 7/13/2023 | 11/29/2023 | 1093958 | 508865 | 487154 | DSF0001068033, DSF0001068034, DSF0001083841
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | ROOF LEAK / EXTERIOR MASONRY / WINDOWS | Construction | PNS | PNS | PNS | PNS | 24614044 | 24614044 | 33485 | DSF0001068033, DSF0001068034, DSF0001083841
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | ROOF LEAK / EXTERIOR MASONRY / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1531540 | 1531540 | 127335 | DSF0001068033, DSF0001068034, DSF0001083841
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/28/2021 | 11/29/2021 | 8/18/2021 | 6205 | 8646 | 8646 | DSF0000960786
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/18/2021 | 2/16/2022 | 12/22/2021 | 27922 | 34582 | 34582 | DSF0000960786
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/17/2022 | 9/12/2023 |  | 359888 | 317851 | 300987 | DSF0000960786
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 11/17/2022 | 9/12/2023 |  | 252923 | 244026 | 238910 | DSF0000960786
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113600
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113600
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113600
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113600
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | DOE - RESOA | FY25 RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112757
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/16/2024 | DOES |  | DOES | 704000 | 0 | DSF0001112130
5 | M030 | P.S. 30 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Scope | In-Progress | 11/15/2024 | 4/18/2025 |  | 175442 | 203179 | 192579 | DSF0001083892, DSF0001111794
5 | M030 | P.S. 30 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Design | PNS | PNS | PNS | PNS | 877211 | 877211 | 774199 | DSF0001083892, DSF0001111794
5 | M030 | P.S. 30 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Construction | PNS | PNS | PNS | PNS | 19737237 | 19737237 | 192801 | DSF0001083892, DSF0001111794
5 | M030 | P.S. 30 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 1228095 | 1228095 | 104132 | DSF0001083892, DSF0001111794
5 | M030 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113602
5 | M030 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113602
5 | M030 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113602
5 | M030 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113602
5 | M030 | M138 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112762
5 | M036 | P.S. 36 - MANHATTAN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 1/10/2018 | 2/9/2018 | 3/26/2018 | 0 | 11151 | 11151 | DSF0000866392
5 | M036 | P.S. 36 - MANHATTAN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Design | PNS | PNS | PNS | PNS | 650 | 5026 | 5026 | DSF0000866392
5 | M036 | P.S. 36 - MANHATTAN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | 9535 | 539601 | 940 | DSF0000866392
5 | M036 | P.S. 36 - MANHATTAN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 650 | 36791 | 1020 | DSF0000866392
5 | M036 | P.S. 36 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000913874
5 | M036 | P.S. 36 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001033627
5 | M036 | P.S. 36 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 330000 | 306098 | DSF0001086179
5 | M036 | P.S. 36 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/14/2022 | DOES |  | DOES | 83169 | 0 | DSF0001009116
5 | M043 | URBAN ASSEMBLY SCHOOL FOR THE PERFORMING ARTS | Fast Track Projects | FY18 RESO A LIBRARY UPGRADES | Construction | In-Progress | 10/4/2019 | FTK |  | FTK | 247362 | 191852 | DSF0000866408
5 | M043 | URBAN ASSEMBLY SCHOOL FOR THE PERFORMING ARTS | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/1/2024 | DOER |  | DOER | 129688 | 0 | DSF0000913303
5 | M043 | I.S. 286 - MANHATTAN | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 5/31/2022 | DOER |  | DOER | 442101 | 0 | DSF0000913304
5 | M043 | URBAN ASSEMBLY SCHOOL FOR THE PERFORMING ARTS | DOE - RESOA | FY22 RESO A FLOORING | Construction | In-Progress | 7/17/2023 | DOER |  | DOER | 75918 | 0 | DSF0001033692
5 | M043 | I.S. 367 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 10/30/2023 | DOES | 11/21/2023 | DOES | 62190 |  | DSF0000866116
5 | M043 | I.S. 286 - MANHATTAN | DOE - Skilled Trades | CHARTER MATCH FLOOR REPLACEMENT | Construction | In-Progress | 8/15/2021 | DOES |  | DOES | 1114304 | 0 | DSF0001009263
5 | M043 | URBAN ASSEMBLY SCHOOL FOR THE PERFORMING ARTS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 8/13/2024 | DOES | 65832 | 17994 | DSF0001084779
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 3/3/2021 | 7/16/2021 | 9/13/2021 | 119974 | 167991 | 167991 | DSF0001008563
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 9/28/2021 | 3/21/2022 | 1/10/2023 | 599870 | 474146 | 356804 | DSF0001008563
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 8/3/2023 | 8/1/2025 |  | 13497075 | 12387959 | 3975139 | DSF0001008563
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 8/3/2023 | 8/1/2025 |  | 840789 | 444427 | 432540 | DSF0001008563
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PAVED AREA-CONCRETE | Scope | Complete | 3/14/2023 | 6/12/2023 | 6/20/2023 | 22522 | 66752 | 66752 | DSF0001083893
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PAVED AREA-CONCRETE | Design | Complete | 7/14/2023 | 11/30/2023 | 5/14/2024 | 112609 | 181130 | 171991 | DSF0001083893
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PAVED AREA-CONCRETE | Construction | PNS | PNS | PNS | PNS | 2533712 | 2533712 | 88438 | DSF0001083893
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PAVED AREA-CONCRETE | CM,F&E | PNS | PNS | PNS | PNS | 157653 | 157653 | 32701 | DSF0001083893
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | PERMANENT FIX- PIPING REPLACEMENT @ M046 / VENTILATION | Scope | Complete | 3/1/2024 | 6/17/2024 | 7/1/2024 | 51955 | 82620 | 30014 | SCA0000072736, DSF0001112400
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | PERMANENT FIX- PIPING REPLACEMENT @ M046 / VENTILATION | Design | In-Progress | 7/22/2024 | 12/23/2024 |  | 250193 | 250193 | 15387 | SCA0000072736, DSF0001112400
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | PERMANENT FIX- PIPING REPLACEMENT @ M046 / VENTILATION | Construction | PNS | PNS | PNS | PNS | 4738337 | 4738337 | 2872 | SCA0000072736, DSF0001112400
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | PERMANENT FIX- PIPING REPLACEMENT @ M046 / VENTILATION | CM,F&E | PNS | PNS | PNS | PNS | 373263 | 373263 | 35075 | SCA0000072736, DSF0001112400
5 | M046 | P.S. 46 - MANHATTAN | SCA IEH | PO18-COLD LINE VALVE # 23 HAS ACM LOCATED IN THE BASEMENT HALLWAY PICTURES ARE ATTACHED | Construction | Complete | 8/19/2024 | IEH | 9/15/2024 | IEH | 0 | 0 | SCA0000073302
5 | M046 | P.S. 46 - MANHATTAN | SCA IEH | PO18-ABATEMENT OF PIPE INSULATION LOCATED IN THE BASEMENT HALLWAY 16 FEET OF INSULATION THAT IS PAIN | Construction | Complete | 11/14/2024 | IEH | 12/26/2024 | IEH | 0 | 0 | SCA0000073609
5 | M046 | P.S. 46 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 153000 | 0 | DSF0000913565
5 | M046 | P.S. 46 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/28/2024 | DIIR | 9/6/2024 | DIIR | 100000 | 76635 | DSF0001086186
5 | M046 | P.S. 46 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001112769
5 | M046 | P.S. 46 - MANHATTAN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/17/2022 | DOER |  | DOER | 273745 | 0 | DSF0000890662
5 | M046 | P.S. 46 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084624
5 | M079 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/20/2021 | 9/20/2021 | 8/3/2021 | 83510 | 176803 | 121403 | DSF0000992500, DSF0001008799
5 | M079 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 8/5/2021 | 1/10/2022 | 4/6/2022 | 417550 | 582119 | 527894 | DSF0000992500, DSF0001008799
5 | M079 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 7/18/2022 | 7/16/2024 |  | 9394875 | 8691233 | 7511373 | DSF0000992500, DSF0001008799
5 | M079 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 7/18/2022 | 7/16/2024 |  | 584570 | 1392429 | 1380003 | DSF0000992500, DSF0001008799
5 | M079 | M079 SPED - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/30/2021 | 9/29/2021 | 1/10/2022 | 0 | 0 | 18113 | DSF0001008870
5 | M079 | M079 SPED - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | In-Progress | 1/14/2022 | 6/1/2022 |  | 15000 | 15000 | 17704 | DSF0001008870
5 | M079 | M079 SPED - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 220000 | 220000 | 16173 | DSF0001008870
5 | M079 | M079 SPED - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 15000 | 15000 | 14227 | DSF0001008870
5 | M079 | M079 SPED - MANHATTAN | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 9/15/2022 | FTK |  | FTK | 530851 | 521345 | DSF0001034613
5 | M079 | M079 SPED - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/5/2022 | DOER |  | DOER | 230949 | 0 | DSF0000913082
5 | M079 | M079 SPED - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | Complete | 7/3/2023 | DOER | 9/27/2023 | DOER | 377957 | 10997 | DSF0001035320
5 | M079 | M079 SPED - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/20/2021 | DOES | 3/25/2022 | DOES | 140016 | 7274 | DSF0001008691
5 | M079 | M079 SPED - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/12/2024 | DOES | 8/19/2024 | DOES | 65832 | 29379 | DSF0001084942
5 | M079 | M079 SPED - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 4/11/2024 | DOES |  | DOES | 578713 | 1408 | DSF0001096407
5 | M092 | P.S. 92 - MANHATTAN | SCA IEH | PO18-ABATE PIPE INSULATION WATER MAIN IN RM B19 (GAS METER RM AHERA SPACE ID 1016) PIPE COVER ITSELF | Construction | Complete | 8/26/2024 | IEH | 9/26/2024 | IEH | 0 | 0 | SCA0000073319
5 | M092 | P.S. 92 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112790
5 | M092 | P.S. 92 - MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 8/4/2018 | DOES |  | DOES | 103926 | 0 | DSF0000865895
5 | M092 | P.S. 92 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 1330000 | 0 | DSF0001112133
5 | M092 | P.S. 92 - MANHATTAN | Trust For Public Land | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | TPL |  | 0 | DSF0001112791
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/22/2020 | 2/1/2021 | 10/27/2020 | 13482 | 30001 | 30001 | DSF0000890580
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 11/16/2020 | 7/28/2021 | 7/28/2021 | 60669 | 120099 | 120099 | DSF0000890580
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 7/8/2022 | 7/7/2023 |  | 781957 | 706653 | 223598 | DSF0000890580
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 7/8/2022 | 7/7/2023 |  | 144932 | 107259 | 79054 | DSF0000890580
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/4/2023 | 88046 | 78519 | 78519 | DSF0001069199, DSF0001069200
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | WINDOWS / EXTERIOR MASONRY | Design | Complete | 10/30/2023 | 6/28/2024 | 4/22/2024 | 431183 | 172913 | 172913 | DSF0001069199, DSF0001069200
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 10/14/2024 | 10/27/2026 |  | 8919163 | 7982602 | 46387 | DSF0001069199, DSF0001069200
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 10/14/2024 | 10/27/2026 |  | 684160 | 58311 | 57961 | DSF0001069199, DSF0001069200
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/21/2022 | 11/21/2022 | 8/10/2022 | 5368 | 3749 | 3749 | DSF0001034653
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/10/2022 | 2/8/2023 | 1/18/2023 | 24157 | 14997 | 14997 | DSF0001034653
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/20/2023 | 6/18/2024 |  | 311361 | 277036 | 260086 | DSF0001034653
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/20/2023 | 6/18/2024 |  | 182785 | 208077 | 174539 | DSF0001034653
5 | M123 | P.S. 123 - MANHATTAN | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 100000 | 100000 | 0 | DSF0000913588
5 | M123 | P.S. 123 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 10/2/2023 | DOER | 12/18/2023 | DOER | 174266 |  | DSF0001035322
5 | M123 | P.S. 123 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/7/2024 | DOES | 11/25/2024 | DOES | 65832 | 21040 | DSF0001084633
5 | M123 | P.S. 123 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/29/2024 | DOES |  | DOES | 963000 | 0 | DSF0001112134
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2/12/2020 | 7/14/2020 | 4/11/2022 | 217910 | 246947 | 235922 | DSF0000960449, DSF0000960448, DSF0001018517, DSF0001034497
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 4/11/2022 | 10/12/2022 | 3/24/2023 | 1089550 | 852838 | 650441 | DSF0000960449, DSF0000960448, DSF0001018517, DSF0001034497
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 8/7/2023 | 2/1/2026 |  | 24514875 | 22551716 | 10420968 | DSF0000960449, DSF0000960448, DSF0001018517, DSF0001034497
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 8/7/2023 | 2/1/2026 |  | 1525665 | 611864 | 608226 | DSF0000960449, DSF0000960448, DSF0001018517, DSF0001034497
5 | M125 | I.S. 362 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/8/2024 | 11/5/2024 | 7/12/2024 | 3557 | 1838 | 1838 | DSF0001087479
5 | M125 | I.S. 362 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/12/2024 | 1/9/2025 |  | 16006 | 16006 | 7350 | DSF0001087479
5 | M125 | I.S. 362 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 206297 | 206297 | 1810 | DSF0001087479
5 | M125 | I.S. 362 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 42500 | 42500 | 3174 | DSF0001087479
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 3/1/2023 | 6/30/2023 | 7/11/2023 | 0 | 13634 | 13633 | DSF0001035680
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | Complete | 7/14/2023 | 11/30/2023 | 2/13/2024 | 33324 | 34639 | 32770 | DSF0001035680
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 488756 | 488756 | 45464 | DSF0001035680
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 33324 | 33324 | 18827 | DSF0001035680
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A POOL UPGRADE | Scope | Complete | 3/1/2023 | 5/31/2023 | 10/31/2023 | 0 | 135630 | 135630 | DSF0001035678
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A POOL UPGRADE | Design | In-Progress | 11/1/2023 | 3/8/2024 |  | 464122 | 328492 | 119368 | DSF0001035678
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A POOL UPGRADE | Construction | PNS | PNS | PNS | PNS | 6807119 | 6807119 | 8852 | DSF0001035678
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A POOL UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 464122 | 464122 | 26892 | DSF0001035678
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A POOL UPGRADE | Scope | Complete | 3/1/2023 | 5/31/2023 | 10/6/2023 | 0 | 0 | 504 | DSF0001035679
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A POOL UPGRADE | Design | In-Progress | 10/17/2023 | 2/22/2024 |  | 878 | 878 | 2115 | DSF0001035679
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A POOL UPGRADE | Construction | PNS | PNS | PNS | PNS | 12881 | 12881 | 2542 | DSF0001035679
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A POOL UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 878 | 878 | 2792 | DSF0001035679
5 | M125 | P.S. 125 - MANHATTAN | SCA Emergency Response | EMR PROTECTIVE MEASURES- IDA | Construction | In-Progress | 9/21/2021 | EMER |  | EMER | 92837 | 92837 | SCA0000070538
5 | M125 | I.S. 362 - MANHATTAN | SCA IEH | PO18-ABATE PIPE INSULATION SECURITY OFFICE (109) & THE FIRST FLOOR STAFF BATHROOM | Construction | Complete | 12/6/2024 | IEH | 12/30/2024 | IEH | 0 | 0 | SCA0000073688
5 | M125 | I.S. 362 - MANHATTAN | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 11/7/2024 | FTK |  | FTK | 123670 | 76934 | DSF0001112045
5 | M125 | P.S. 125 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/9/2024 | DIIR |  | DIIR | 286000 | 0 | DSF0001086222
5 | M125 | P.S. 125 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112804
5 | M125 | I.S. 362 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112805
5 | M125 | I.S. 362 - MANHATTAN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 1/10/2024 | DOEL |  | DOEL | 134526 | 134526
5 | M125 | I.S. 362 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 719000 | 0 | DSF0001112136
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 10/31/2018 | 3/21/2019 | 1/10/2019 | 297170 | 320505 | 320467 | DSF0000875961, DSF0000875962, DSF0000875963, DSF0000875964
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/16/2019 | 6/17/2019 | 3/30/2021 | 1485850 | 992791 | 886097 | DSF0000875961, DSF0000875962, DSF0000875963, DSF0000875964
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2/3/2022 | 2/1/2025 |  | 33431626 | 31208417 | 6010122 | DSF0000875961, DSF0000875962, DSF0000875963, DSF0000875964
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2/3/2022 | 2/1/2025 |  | 2080190 | 1080088 | 1060290 | DSF0000875961, DSF0000875962, DSF0000875963, DSF0000875964
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 4/24/2023 | 9/21/2023 | 12/14/2023 | 302501 | 215620 | 208800 | DSF0001083817, DSF0001096992, DSF0001096984
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/26/2023 | 7/22/2024 | 5/15/2024 | 1512501 | 687624 | 556525 | DSF0001083817, DSF0001096992, DSF0001096984
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 34031250 | 34031250 | 121640 | DSF0001083817, DSF0001096992, DSF0001096984
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 2117501 | 2117501 | 201172 | DSF0001083817, DSF0001096992, DSF0001096984
5 | M129 | P.S. 129 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: RM :233 APPROX. 200SF RM: 234 APPROX. 675SF RM: 236 APP | Construction | Complete | 3/30/2023 | IEH | 9/10/2024 | IEH | 0 | 0 | SCA0000071853
5 | M129 | P.S. 129 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING ROOMS: RM: 217 APPROX. 510SF RM: 219 APPROX. 645 | Construction | In-Progress | 9/27/2023 | IEH |  | IEH | 0 | 0 | SCA0000072352
5 | M129 | P.S. 129 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION & RISER VALVE NEEDS TO BE ABATED LOCATION: 1ST FL HALLWAY ACROSS | Construction | Complete | 8/20/2024 | IEH | 9/14/2024 | IEH | 0 | 0 | SCA0000073304
5 | M129 | P.S. 129 - MANHATTAN | SCA IEH | PO18-OIL TANK ROOM ABATE 10 L.F. PIPE INSULATION, SPRAYED RED - BOILER ROOM ABATE 10 L.F. FROM BURNE | Construction | Complete | 9/24/2024 | IEH | 11/18/2024 | IEH | 0 | 0 | SCA0000073413
5 | M129 | SCHOOL OF EARTH EXPLORATION AND DISCOVERY HARLEM (SEED HARLEM) | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035635
5 | M129 | P.S. 129 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112807
5 | M129 | P.S. 129 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/22/2021 | DOER |  | DOER | 269150 | 0 | DSF0000913182
5 | M133 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/25/2021 | 11/23/2021 | 10/14/2021 | 119803 | 141950 | 141950 | DSF0000993122, DSF0000993123, DSF0000993124
5 | M133 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/10/2021 | 6/30/2022 | 4/20/2022 | 599020 | 602519 | 585800 | DSF0000993122, DSF0000993123, DSF0000993124
5 | M133 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 8/8/2022 | 8/6/2024 |  | 13477951 | 12384316 | 11949060 | DSF0000993122, DSF0000993123, DSF0000993124
5 | M133 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/8/2022 | 8/6/2024 |  | 838628 | 764816 | 755440 | DSF0000993122, DSF0000993123, DSF0000993124
5 | M133 | P.S. 133 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | Complete | 9/10/2021 | EMER | 8/22/2022 | EMER | 11177 | 11177 | SCA0000070492
5 | M133 | P.S. 133 - MANHATTAN | SCA IEH | PO18-REPAIR LEAKING RADIATORE ON 3RD FLOOR HALLWAY | Construction | In-Progress | 11/1/2023 | IEH |  | IEH | 0 | 0 | SCA0000072452
5 | M133 | P.S. 133 - MANHATTAN | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 10/31/2024 | FTK |  | FTK | 149701 | 94602 | DSF0001035047
5 | M133 | P.S. 133 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 257505 | 0 | DSF0000960012
5 | M133 | P.S. 133 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/7/2021 | DOES | 10/15/2021 | DOES | 173926 | 182366 | DSF0001008694
5 | M133 | P.S. 133 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/16/2024 | DOES |  | DOES | 172000 | 0 | DSF0001112138
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/27/2020 | 9/24/2020 | 6/19/2020 | 3269 | 4468 | 4468 | DSF0000960794
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/19/2020 | 12/16/2020 | 12/16/2020 | 14710 | 17872 | 17872 | DSF0000960794
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/17/2022 | 9/12/2023 |  | 189590 | 170244 | 155302 | DSF0000960794
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 11/17/2022 | 9/12/2023 |  | 132665 | 163999 | 159448 | DSF0000960794
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113610
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113610
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113610
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113610
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 11/3/2020 | FTK |  | FTK | 523860 | 509836 | DSF0000961041
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 182118 | 0 | DSF0000960014
5 | M136 | MOTT HALL HS - MANHATTAN | DIIT - RESOA | ENY TECHNOLOGY | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 120163 | 0 | DSF0001008913
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | DIIT - RESOA | ENY TECHNOLOGY | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 119257 | 0 | DSF0001008914
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/18/2024 | DIIR |  | DIIR | 100000 | 0 | DSF0001086229
5 | M136 | MOTT HALL HS - MANHATTAN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 118978 | 0 | DSF0001085316
5 | M136 | MOTT HALL HS - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 312360 | 9700 | DSF0001086228
5 | M136 | MOTT HALL HS - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 145000 | 0 | DSF0001112812
5 | M136 | I.S. 302 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 6/5/2023 | DOES | 9/22/2023 | DOES | 62190 |  | DSF0000866120
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 7/17/2024 | DOES | 65832 | 189 | DSF0001084949
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 9/13/2022 | 2/1/2023 | 12/19/2022 | 16053 | 11976 | 11976 | DSF0001035028
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/21/2022 | 6/27/2023 | 7/11/2023 | 72239 | 47899 | 47899 | DSF0001035028
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 931075 | 931075 | 15841 | DSF0001035028
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 172570 | 172570 | 34127 | DSF0001035028
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/25/2024 | 11/25/2024 | 7/29/2024 | 4105 | 1084 | 1084 | DSF0001087485
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/29/2024 | 1/27/2025 |  | 18471 | 18471 | 4336 | DSF0001087485
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 238076 | 238076 | 0 | DSF0001087485
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 48390 | 48390 | 4289 | DSF0001087485
5 | M154 | P.S. 154 - MANHATTAN | SCA IEH | PO18-CUSTODIAN'S LOCKER ROOM PICK UP 2 SQ. FT. FLOOR TILES AND ENCAPSULATE FLOOR | Construction | In-Progress | 7/22/2024 | IEH |  | IEH | 0 | 0 | SCA0000073159
5 | M154 | P.S. 154 - MANHATTAN | SCA IEH | PO18-ABATE PIPE INSULATION BASEMENT THROUGH ROOM B12 ABOUT 12 FEET OF PIPE INSULATION CUSTODIAN ENGI | Construction | In-Progress | 12/13/2024 | IEH |  | IEH | 0 | 0 | SCA0000073710
5 | M154 | P.S. 154 - MANHATTAN | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 65000 | 65000 | 0 | DSF0000961384
5 | M154 | P.S. 154 - MANHATTAN | Fast Track Projects | LSP- VACUUM PUMPS REPLACEMENT | Construction | In-Progress | 5/2/2024 | FTK |  | FTK | 100125 | 0 | DSF0001069623
5 | M154 | P.S. 154 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001086237
5 | M154 | P.S. 154 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112820
5 | M154 | P.S. 154 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 9/25/2022 | DOES | 11/17/2022 | DOES | 116620 | 115051 | DSF0001009120
5 | M154 | P.S. 154 - MANHATTAN | DOE - Skilled Trades | HEATING PLANT UPGRADE | Construction | In-Progress | 8/11/2023 | DOES |  | DOES | 72922 | 0 | DSF0001085782
5 | M161 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/6/2022 | 2/9/2023 | 10/20/2022 | 4900 | 3289 | 3289 | DSF0001034632
5 | M161 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/20/2022 | 4/19/2023 | 1/18/2023 | 22050 | 13154 | 13154 | DSF0001034632
5 | M161 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/20/2023 | 6/18/2024 |  | 284194 | 256196 | 239946 | DSF0001034632
5 | M161 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/20/2023 | 6/18/2024 |  | 170421 | 197251 | 148554 | DSF0001034632
5 | M161 | P.S. 161 - MANHATTAN | SCA IEH | PO18-REMOVE ACM TILE UNDER CABINETS ROOM 117 | Construction | Complete | 9/15/2023 | IEH | 9/10/2024 | IEH | 0 | 0 | SCA0000072298
5 | M161 | P.S. 161 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 10/24/2024 | DIIR | 99648 | 99648 | DSF0001086240
5 | M161 | P.S. 161 - MANHATTAN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/13/2023 | DOER |  | DOER | 65741 | 0 | DSF0001085317
5 | M161 | P.S. 161 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/16/2019 | DOES |  | DOES | 205755 | 0 | DSF0000889608
5 | M161 | P.S. 161 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/6/2024 | DOES |  | DOES | 308022 | 0 | DSF0001085737
5 | M161 | P.S. 161 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 9/23/2024 | DOES |  | DOES | 666000 | 0 | DSF0001112140
5 | M175 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Scope | Complete | 3/2/2021 | 11/10/2021 | 11/5/2021 | 23406 | 27432 | 27432 | DSF0000960913, DSF0001008895
5 | M175 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Design | Complete | 11/9/2021 | 4/5/2022 | 5/9/2022 | 116471 | 119742 | 96550 | DSF0000960913, DSF0001008895
5 | M175 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Construction | In-Progress | 5/15/2023 | 8/11/2024 |  | 2572569 | 2080139 | 1076103 | DSF0000960913, DSF0001008895
5 | M175 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | CM,F&E | In-Progress | 5/15/2023 | 8/11/2024 |  | 168001 | 343643 | 338914 | DSF0000960913, DSF0001008895
5 | M175 | P.S. 175 HENRY H GARNET - M | SCA IEH | PO18-PLEASE REMOVE ASBESTOS AROUND GATE VALVES AND LINE, SO PLUMBERS CAN REPLACE VALVES TO ALLOW WAT | Construction | Complete | 9/24/2024 | IEH | 11/24/2024 | IEH | 0 | 0 | SCA0000073416
5 | M175 | P.S. 175 HENRY H GARNET - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001112830
5 | M175 | P.S. 175 HENRY H GARNET - M | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/27/2022 | DOER |  | DOER | 389963 | 0 | DSF0000913090
5 | M175 | P.S. 175 HENRY H GARNET - M | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 3/4/2024 | DOER |  | DOER | 41801 | 0 | DSF0001033180
5 | M175 | P.S. 175 HENRY H GARNET - M | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 3/1/2024 | DOES |  | DOES | 126420 | 0 | DSF0000809867
5 | M175 | P.S. 175 HENRY H GARNET - M | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 507000 | 0 | DSF0001112141
5 | M194 | P.S. 194 - MANHATTAN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 7/15/2024 |  | 7/19/2024 | 50000 | 50000 | 49774 | DSF0001035324
5 | M194 | HARLEM VILLAGE ACADEMIES HIGH CHARTER SCHOOL - MANHATTAN | DIIT - Project Connect | COMPUTERS | Purch & Install | In-Progress | 9/1/2021 | DIIT |  | DIIT | 60000 | 0 | DSF0000488443
5 | M194 | P.S. 194 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 150000 | 149433 | DSF0001086261
5 | M194 | P.S. 194 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 247000 | 0 | DSF0001086260
5 | M194 | P.S. 194 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 9/12/2022 | DOES | 9/26/2022 | DOES | 67910 | 66996 | DSF0001009123
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 1/27/2023 | 5/26/2023 | 4/19/2023 | 8380 | 15725 | 15725 | DSF0001083793
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 4/24/2023 | 10/24/2023 | 8/28/2023 | 37710 | 48107 | 44988 | DSF0001083793
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 3/5/2024 | 3/4/2025 |  | 486040 | 489340 | 60150 | DSF0001083793
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 3/5/2024 | 3/4/2025 |  | 90085 | 62464 | 17212 | DSF0001083793
5 | M195 | I.S. 195 - MANHATTAN | DOE - RESOA | FY10 RESO A GYM RENOVATION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0000690086
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112843
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 11/21/2022 | DOES | 10/31/2023 | DOES | 443438 | 450161 | DSF0000960855
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/5/2024 | DOES | 12/13/2024 | DOES | 65832 |  | DSF0001084792
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 4/29/2021 | 9/14/2021 | 11/17/2021 | 210430 | 166021 | 148324 | DSF0001008648, DSF0001019357
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 11/17/2021 | 5/6/2022 | 10/21/2022 | 1052150 | 455488 | 403205 | DSF0001008648, DSF0001019357
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 8/3/2023 | 8/1/2025 |  | 23673375 | 21306480 | 1297475 | DSF0001008648, DSF0001019357
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 8/3/2023 | 8/1/2025 |  | 1482881 | 493491 | 480746 | DSF0001008648, DSF0001019357
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/26/2024 | 11/26/2024 | 7/29/2024 | 3126 | 1576 | 1576 | DSF0001087487
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/29/2024 | 1/27/2025 |  | 14066 | 14066 | 6302 | DSF0001087487
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 181299 | 181299 | 0 | DSF0001087487
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 37867 | 37867 | 6992 | DSF0001087487
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113614
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113614
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113614
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113614
5 | M197 | P.S. 197 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 263698 | 0 | DSF0000960032
5 | M197 | P.S. 197 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 55000 | 0 | DSF0001035722
5 | M197 | P.S. 197 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 150000 | 140109 | DSF0001086263
5 | M197 | P.S. 197 - MANHATTAN | DOE - RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112844
5 | M200 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113615
5 | M200 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113615
5 | M200 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113615
5 | M200 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113615
5 | M200 | P.S. 200 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113616
5 | M200 | P.S. 200 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113616
5 | M200 | P.S. 200 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113616
5 | M200 | P.S. 200 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113616
5 | M200 | P.S. 200 - MANHATTAN | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | In-Progress | 12/3/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001085319
5 | M200 | M811 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 145000 | 0 | DSF0001112849
5 | M200 | P.S. 200 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112850
5 | M223 | I.S. 223 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 3/19/2018 | EMER |  | EMER | 327887 | 283548 | SCA0000050925
5 | M223 | I.S. 223 - MANHATTAN | DIIT - RESOA | FY12 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0000732158
5 | M223 | I.S. 223 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001033192
5 | M223 | I.S. 223 - MANHATTAN | DOE - RESOA | FY15 RESO A SCIENCE LAB CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0000800072
5 | M223 | I.S. 223 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001086269
5 | M371 | P.S. 318 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/8/2024 | DIIR | 10/16/2024 | DIIR | 99409 | 99409 | DSF0001086279
5 | M484 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/1/2024 | IEH | 8/8/2024 | IEH | 0 | 0 | SCA0000073215
5 | M484 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001035758
5 | M484 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112895
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2/27/2023 | 7/27/2023 | 12/14/2023 | 613798 | 340255 | 335480 | DSF0001083743, DSF0001085799, DSF0001098324, DSF0001098318
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 1/10/2024 | 8/12/2024 | 8/23/2024 | 2864394 | 962623 | 851682 | DSF0001083743, DSF0001085799, DSF0001098324, DSF0001098318
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 45421110 | 45421110 | 275879 | DSF0001083743, DSF0001085799, DSF0001098324, DSF0001098318
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 4501191 | 4501191 | 324084 | DSF0001083743, DSF0001085799, DSF0001098324, DSF0001098318
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA Emergency Response | TEMPORARY MOBILE CHILLER @ M501 | Construction | In-Progress | 11/1/2023 | EMER |  | EMER | 15269054 | 7790758 | SCA0000071688
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION ROOM 119 TO REPAIR THE LEAK IT IS 12 FEET | Construction | In-Progress | 12/5/2024 | IEH |  | IEH | 0 | 0 | SCA0000073673
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 11/21/2022 | DOES | 2/22/2024 | DOES | 568857 | 559114 | DSF0001034908
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/1/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084966
5 | M911 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/18/2021 | 10/1/2021 | 1/14/2022 | 80048 | 192462 | 189360 | DSF0000994755, DSF0000994757, DSF0000994758, DSF0000994759
5 | M911 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/2/2022 | 7/5/2022 | 5/9/2022 | 395977 | 291360 | 261294 | DSF0000994755, DSF0000994757, DSF0000994758, DSF0000994759
5 | M911 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 7/18/2023 | 7/16/2025 |  | 8541042 | 7957978 | 3209452 | DSF0000994755, DSF0000994757, DSF0000994758, DSF0000994759
5 | M911 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/18/2023 | 7/16/2025 |  | 592275 | 566002 | 560758 | DSF0000994755, DSF0000994757, DSF0000994758, DSF0000994759
5 | M911 | HARLEM RENAISSANCE HS - M | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 128087 | 0 | DSF0001035787
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY19 RESO A PLAYGROUND UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000890677
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY19 RESO A PLAYGROUND UPGRADES | Design | PNS | PNS | PNS | PNS | 16500 | 16500 | 0 | DSF0000890677
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY19 RESO A PLAYGROUND UPGRADES | Construction | PNS | PNS | PNS | PNS | 242000 | 242000 | 0 | DSF0000890677
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY19 RESO A PLAYGROUND UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 16500 | 16500 | 0 | DSF0000890677
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000961367
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000961367
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000961367
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000961367
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007750
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007750
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007750
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007750
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 166851 | 0 | DSF0001035788
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0 | DSF0001112920
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/17/2022 | 2/17/2023 | 11/10/2022 | 3672 | 2400 | 2400 | DSF0001034596
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 11/10/2022 | 5/10/2023 | 1/18/2023 | 16523 | 9599 | 9599 | DSF0001034596
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/20/2023 | 6/18/2024 |  | 212964 | 194780 | 180430 | DSF0001034596
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/20/2023 | 6/18/2024 |  | 161344 | 226590 | 178191 | DSF0001034596
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001085320
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 175000 | 156110 | DSF0001086337
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0 | DSF0001112922
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/10/2024 | DOES | 10/15/2024 | DOES | 65832 | 189 | DSF0001085495
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/11/2024 | DOES |  | DOES | 253000 | 0 | DSF0001112146
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/13/2024 | 9/13/2024 | 9/5/2024 | 0 | 50441 | 36041 | DSF0001111873
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | In-Progress | 9/9/2024 | 1/28/2025 |  | 32829 | 32829 | 90605 | DSF0001111873
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 481496 | 481496 | 272 | DSF0001111873
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 32829 | 32829 | 8933 | DSF0001111873
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Scope | Complete | 9/4/2024 | 12/5/2024 | 10/16/2024 | 0 | 1086 | 1086 | DSF0001112233
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Design | In-Progress | 10/17/2024 | 2/18/2025 |  | 6554 | 4346 | 4346 | DSF0001112233
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 96125 | 96125 | 0 | DSF0001112233
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 6554 | 6554 | 4827 | DSF0001112233
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/27/2024 | 4/1/2025 | 12/9/2024 | 0 | 5831 | 5831 | DSF0001112752
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 12000 | 23322 | 23322 | DSF0001112752
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 176000 | 176000 | 0 | DSF0001112752
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 12000 | 12000 | 0 | DSF0001112752
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113598
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113598
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113598
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113598
6 | M004 | P.S. 4 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112751
6 | M004 | P.S. 4 - MANHATTAN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 76666 | 0 | DSF0001035610
6 | M004 | P.S. 4 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 130000 | 0 | DSF0001035611
6 | M004 | P.S. 4 - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086166
6 | M004 | P.S. 4 - MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMPS | Construction | In-Progress | 6/11/2021 | DOES |  | DOES | 672485 | 0 | DSF0000911919
6 | M005 | P.S. 5 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/4/2024 | 8/5/2024 | 4/16/2024 | 4635 | 2671 | 2671 | DSF0001087465
6 | M005 | P.S. 5 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/16/2024 | 10/10/2024 | 9/24/2024 | 20855 | 10684 | 10684 | DSF0001087465
6 | M005 | P.S. 5 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 268803 | 268803 | 21798 | DSF0001087465
6 | M005 | P.S. 5 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 49821 | 49821 | 7889 | DSF0001087465
6 | M005 | P.S. 5 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001112753
6 | M005 | P.S. 5 - MANHATTAN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 12/22/2022 | DOER |  | DOER | 136794 | 0 | DSF0000961334
6 | M005 | P.S. 5 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 650000 | 0 | DSF0001035612
6 | M005 | P.S. 5 - MANHATTAN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001035210
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 1/9/2024 | 5/23/2024 | 6/12/2024 | 38191 | 21181 | 21181 | DSF0001067993, DSF0001095696
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 6/24/2024 | 11/25/2024 | 12/4/2024 | 171440 | 109839 | 105352 | DSF0001067993, DSF0001095696
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 2658249 | 2658249 | 303 | DSF0001067993, DSF0001095696
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 355501 | 355501 | 58197 | DSF0001067993, DSF0001095696
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035614
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001035614
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 220000 | 220000 | 0 | DSF0001035614
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001035614
6 | M008 | P.S. 8 - MANHATTAN | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 11/21/2024 |  |  | 250000 | 250000 | 246485 | DSF0000913869
6 | M008 | P.S. 8 - MANHATTAN | Fast Track Projects | LSP BOOSTER PUMP REPLACEMENT | Construction | In-Progress | 10/9/2024 | FTK |  | FTK | 151688 | 0 | DSF0001086880
6 | M008 | P.S. 8 - MANHATTAN | Fast Track Projects | LSP HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 11/20/2024 | FTK |  | FTK | 321817 | 35692 | DSF0001087261
6 | M008 | P.S. 8 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 500000 | 0 | DSF0001008524
6 | M008 | P.S. 8 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 10/28/2021 | DOES |  | DOES | 112875 | 0 | DSF0001009125
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP | WATER INFILTRATION INTO ELECTRCIAL EQUIPMENT / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 3/7/2023 | 7/21/2023 | 6/26/2023 | 20595 | 14256 | 14256 | DSF0001083877, DSF0001085604
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP | WATER INFILTRATION INTO ELECTRCIAL EQUIPMENT / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 7/17/2023 | 12/18/2023 | 12/15/2023 | 97886 | 84549 | 81357 | DSF0001083877, DSF0001085604
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP | WATER INFILTRATION INTO ELECTRCIAL EQUIPMENT / FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 1762551 | 1762551 | 4968 | DSF0001083877, DSF0001085604
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP | WATER INFILTRATION INTO ELECTRCIAL EQUIPMENT / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 182299 | 182299 | 8603 | DSF0001083877, DSF0001085604
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112761
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001112761
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001112761
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001112761
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113601
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113601
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113601
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113601
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ROOM 306B ASBESTOS ABATEMENT AREA TESTED POSITIVE. D75 SCHOOL MOVING IN BMURPHY16@ SCHOOLS.NYC | Construction | Complete | 8/28/2023 | IEH | 10/10/2024 | IEH | 0 | 0 | SCA0000072240
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ROOM 212, 7 L.F. WATER DAMAGED PIPE INSULATION ROOM 306A, 9 SQ. FT. BROKEN & MISSING FLOOR TILE | Construction | Complete | 7/1/2024 | IEH | 12/17/2024 | IEH | 0 | 0 | SCA0000073107
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION IN THE CRAWL SPACE. 2 LINES PAINTED RED WE WILL NEED APPROXIMATE | Construction | Complete | 8/2/2024 | IEH | 8/29/2024 | IEH | 0 | 0 | SCA0000073227
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ABATE CEILING TILES IN CLOSET IN CR # B07 THAT ARE FALLEN 1X 1 CEIILING TILES AS PER AHERA BOOK | Construction | Complete | 8/15/2024 | IEH | 8/16/2024 | IEH | 0 | 0 | SCA0000073291
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ABATE APPROX. 30LF OF CONDUCTORS ACM WIRING BETWEEN EXISTING CT CABINET AND EXISTING FACILITY M | Construction | Complete | 8/16/2024 | IEH | 8/18/2024 | IEH | 0 | 0 | SCA0000073305
6 | M028 | P.S. 28 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001035622
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | CERTIFICATE OF OCCUPANCY | Scope | Complete | 9/7/2016 | 12/8/2016 | 10/27/2017 | 18951 | 131283 | 131283 | DSF0000844690
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | CERTIFICATE OF OCCUPANCY | Design | Complete | 11/7/2017 | 5/14/2018 | 5/22/2018 | 75804 | 106822 | 105493 | DSF0000844690
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | CERTIFICATE OF OCCUPANCY | Construction | PNS | PNS | PNS | PNS | 1421328 | 1421328 | 28329 | DSF0000844690
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | CERTIFICATE OF OCCUPANCY | CM,F&E | PNS | PNS | PNS | PNS | 88438 | 88438 | 22947 | DSF0000844690
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 1/17/2023 | 5/16/2023 | 9/26/2023 | 457850 | 304648 | 303945 | DSF0001017700, DSF0001068448, DSF0001085132, DSF0001111793
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 10/4/2023 | 5/6/2024 | 5/8/2024 | 2289250 | 1283915 | 853634 | DSF0001017700, DSF0001068448, DSF0001085132, DSF0001111793
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Construction | In-Progress | 7/17/2024 | 7/16/2027 |  | 51508124 | 46282855 | 290163 | DSF0001017700, DSF0001068448, DSF0001085132, DSF0001111793
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | CM,F&E | In-Progress | 7/17/2024 | 7/16/2027 |  | 3204950 | 622615 | 611667 | DSF0001017700, DSF0001068448, DSF0001085132, DSF0001111793
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/17/2024 | 8/16/2024 | 4/30/2024 | 4202 | 3911 | 3911 | DSF0001087471
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/30/2024 | 10/25/2024 | 10/24/2024 | 18908 | 15648 | 15648 | DSF0001087471
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 243699 | 243699 | 0 | DSF0001087471
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 45168 | 45168 | 1283 | DSF0001087471
6 | M048 | P.S. 48 - MANHATTAN | SCA Furniture & Equipment | RESO A STEM CENTER UPGRADE | F&E | PNS | PNS | PNS | PNS | 550000 | 550000 | 545520 | DSF0000960892
6 | M048 | M138 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/20/2023 | DIIR |  | DIIR | 59000 | 0 | DSF0001035689
6 | M048 | P.S. 48 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001112770
6 | M048 | P.S. 48 - MANHATTAN | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 6/23/2023 | DOER |  | DOER | 191529 | 0 | DSF0001008525
6 | M048 | P.S. 48 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/19/2024 | DOER |  | DOER | 200000 | 9025 | DSF0001086188
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/29/2021 | 10/28/2021 | 7/27/2021 | 2596 | 12332 | 12332 | DSF0000960791
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/27/2021 | 1/25/2022 | 12/15/2021 | 11682 | 49340 | 49340 | DSF0000960791
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 7/15/2022 | 4/10/2023 | 11/6/2023 | 150568 | 156282 | 113142 | DSF0000960791
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 7/15/2022 | 4/10/2023 | 11/6/2023 | 189179 | 190004 | 185285 | DSF0000960791
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 1/20/2023 | 6/6/2023 | 11/1/2023 | 205580 | 240402 | 168222 | DSF0001068467, DSF0001068464, DSF0001111798, DSF0001111797, DSF0001111796
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Design | Complete | 11/20/2023 | 4/23/2024 | 11/15/2024 | 1022721 | 591274 | 342806 | DSF0001068467, DSF0001068464, DSF0001111798, DSF0001111797, DSF0001111796
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 22563347 | 22563347 | 23392 | DSF0001068467, DSF0001068464, DSF0001111798, DSF0001111797, DSF0001111796
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 1477892 | 1477892 | 80821 | DSF0001068467, DSF0001068464, DSF0001111798, DSF0001111797, DSF0001111796
6 | M052 | J.H.S. 52 - MANHATTAN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 62000 | 62000 | 61677 | DSF0001086192
6 | M052 | J.H.S. 52 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001033156
6 | M052 | INWOOD EARLY COLLEGE FOR HEALTH AND INFORMATION TECHNOLOGY (PTECH) | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035215
6 | M052 | J.H.S. 52 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 50000 | 49575 | DSF0001086190
6 | M052 | J.H.S. 52 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035638
6 | M052 | INWOOD EARLY COLLEGE FOR HEALTH AND INFORMATION TECHNOLOGY (PTECH) | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 132249 | 0 | DSF0001086191
6 | M052 | J.H.S. 52 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112771
6 | M052 | J.H.S. 52 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/3/2023 | DOES | 11/22/2023 | DOES | 483536 | 394651 | DSF0001035166
6 | M052 | J.H.S. 52 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/7/2024 | DOES | 8/14/2024 | DOES | 65832 |  | DSF0001084781
6 | M090 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2/16/2023 | 6/16/2023 | 4/25/2023 | 12972 | 19332 | 19332 | DSF0001083786
6 | M090 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 4/25/2023 | 10/25/2023 | 8/25/2023 | 58374 | 67674 | 52299 | DSF0001083786
6 | M090 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 3/4/2024 | 3/3/2025 |  | 752371 | 53 | 53 | DSF0001083786
6 | M090 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 3/4/2024 | 3/3/2025 |  | 139448 | 8254 | 8254 | DSF0001083786
6 | M090 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | Scope | Complete | 8/20/2020 | 11/10/2022 | 9/9/2022 | 338022 | 446361 | 404580 | DSF0000961126, DSF0000943864, DSF0001009314, DSF0001018105, DSF0001018104, DSF0001018103, DSF0001018102, DSF0001018113, DSF0001068822
6 | M090 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | Design | Complete | 9/27/2022 | 6/12/2023 | 5/5/2023 | 1684198 | 1135203 | 915774 | DSF0000961126, DSF0000943864, DSF0001009314, DSF0001018105, DSF0001018104, DSF0001018103, DSF0001018102, DSF0001018113, DSF0001068822
6 | M090 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | Construction | In-Progress | 8/14/2023 | 8/7/2026 |  | 37383068 | 33417924 | 13475280 | DSF0000961126, DSF0000943864, DSF0001009314, DSF0001018105, DSF0001018104, DSF0001018103, DSF0001018102, DSF0001018113, DSF0001068822
6 | M090 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | CM,F&E | In-Progress | 8/14/2023 | 8/7/2026 |  | 2410487 | 326649 | 310817 | DSF0000961126, DSF0000943864, DSF0001009314, DSF0001018105, DSF0001018104, DSF0001018103, DSF0001018102, DSF0001018113, DSF0001068822
6 | M090 | I.S. 319 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 3/22/2022 | EMER |  | EMER | 11437 | 11437 | SCA0000070943
6 | M090 | I.S. 319 - MANHATTAN | Fast Track Projects | LSP- PLAYGROUND SAFETY SURFACE | Construction | In-Progress | 12/5/2024 | FTK |  | FTK | 74216 | 0 | DSF0000992618
6 | M090 | I.S. 319 - MANHATTAN | Fast Track Projects | LSP FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 184356 | 0 | DSF0001035652
6 | M090 | I.S. 319 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033205
6 | M090 | M138 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 68000 | 0 | DSF0001112788
6 | M090 | I.S. 324 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112789
6 | M090 | I.S. 319 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001035218
6 | M090 | I.S. 324 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 263000 | 0 | DSF0001086205
6 | M090 | I.S. 324 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086206
6 | M090 | I.S. 319 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 2/20/2023 | DOES | 10/25/2023 | DOES | 639908 | 503486 | DSF0001035167
6 | M090 | I.S. 324 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/29/2024 | DOES | 11/25/2024 | DOES | 50832 |  | DSF0001084785
6 | M093 | P.S. 210 - MANHATTAN | SCA CIP | ROOFS | Scope | Complete | 3/10/2021 | 7/23/2021 | 11/1/2021 | 22378 | 55044 | 52372 | DSF0000957415
6 | M093 | P.S. 210 - MANHATTAN | SCA CIP | ROOFS | Design | Complete | 11/1/2021 | 4/6/2022 | 3/29/2022 | 111889 | 107297 | 98454 | DSF0000957415
6 | M093 | P.S. 210 - MANHATTAN | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 2517513 | 2517513 | 0 | DSF0000957415
6 | M093 | P.S. 210 - MANHATTAN | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 156645 | 156645 | 24434 | DSF0000957415
6 | M093 | P.S. 210 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/25/2024 | DIIR | 10/29/2024 | DIIR | 165000 | 165000 | DSF0001035655
6 | M093 | P.S. 210 - MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMP | Construction | In-Progress | 8/6/2018 | DOES |  | DOES | 128252 | 0 | DSF0000889359
6 | M093 | P.S. 210 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086207
6 | M093 | P.S. 210 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/30/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084629
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/25/2023 | 4/25/2023 | 4/20/2023 | 21522 | 85658 | 85658 | DSF0001083711
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | In-Progress | 5/1/2023 | 9/15/2023 |  | 107608 | 120808 | 70517 | DSF0001083711
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2421173 | 2421173 | 139875 | DSF0001083711
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 150651 | 150651 | 45993 | DSF0001083711
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Scope | Complete | 3/28/2023 | 6/28/2023 | 7/13/2023 | 3784 | 8344 | 1651 | DSF0001083961
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Design | In-Progress | 7/17/2023 | 12/4/2023 |  | 17029 | 17029 | 6604 | DSF0001083961
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Construction | PNS | PNS | PNS | PNS | 219484 | 219484 | 3336 | DSF0001083961
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | CM,F&E | PNS | PNS | PNS | PNS | 40680 | 40680 | 5744 | DSF0001083961
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/28/2024 | 10/29/2024 | 7/9/2024 | 4467 | 0 | 0 | DSF0001087475
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/9/2024 | 1/6/2025 | 12/26/2024 | 20100 | 0 | 0 | DSF0001087475
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 259070 | 259070 | 0 | DSF0001087475
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 52281 | 52281 | 6907 | DSF0001087475
6 | M098 | P.S. 98 - MANHATTAN | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 75000 | 75000 | 0 | DSF0001112794
6 | M098 | P.S. 98 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 11/15/2024 | DIIR | 65000 | 65000 | DSF0000961335
6 | M098 | P.S. 98 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086208
6 | M098 | P.S. 98 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 186322 | 0 | DSF0001086209
6 | M098 | P.S. 98 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 6/27/2023 | DOES |  | DOES | 352453 | 0 | DSF0001034922
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL UPGRADE | Scope | Complete | 6/22/2021 | 11/5/2021 | 1/7/2022 | 93227 | 167472 | 151203 | DSF0000944110, DSF0000944112, DSF0000944114, DSF0000944113, DSF0001018389
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL UPGRADE | Design | Complete | 1/12/2022 | 6/14/2022 | 5/11/2022 | 466141 | 340601 | 313892 | DSF0000944110, DSF0000944112, DSF0000944114, DSF0000944113, DSF0001018389
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | 10488173 | 10488173 | 218172 | DSF0000944110, DSF0000944112, DSF0000944114, DSF0000944113, DSF0001018389
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 652597 | 652597 | 34517 | DSF0000944110, DSF0000944112, DSF0000944114, DSF0000944113, DSF0001018389
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 8/18/2020 | 1/20/2021 | 12/16/2021 | 71574 | 89208 | 89208 | DSF0000961101, DSF0001018382
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/16/2021 | 6/21/2022 | 8/15/2022 | 357872 | 269042 | 239706 | DSF0000961101, DSF0001018382
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 8052126 | 8052126 | 768991 | DSF0000961101, DSF0001018382
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 501021 | 501021 | 134238 | DSF0000961101, DSF0001018382
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113607
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113607
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113607
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113607
6 | M115 | P.S. 115 - MANHATTAN | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 9/19/2024 | FTK |  | FTK | 180659 | 106768 | DSF0001112043
6 | M115 | P.S. 115 - MANHATTAN | Fast Track Projects | PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 11/7/2024 | FTK |  | FTK | 74713 | 36242 | DSF0001112044
6 | M115 | P.S. 115 - MANHATTAN | DOE - RESOA | FY17 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 35000 | 0 | DSF0000844916
6 | M115 | P.S. 115 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001035668
6 | M115 | P.S. 115 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/15/2023 | DOER |  | DOER | 274048 | 0 | DSF0001086216
6 | M115 | P.S. 115 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 335000 | 0 | DSF0001112800
6 | M115 | KIPP NYC WASHINGTON HEIGHTS ACADEMY I CS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 1/14/2022 | DOES |  | DOES | 165210 | 0 | DSF0001008692
6 | M115 | P.S. 115 - MANHATTAN | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 166413 | 0 | DSF0001112039
6 | M128 | P.S. 128 - MANHATTAN | SCA Emergency Response | TEMPORARY BOILER | Construction | In-Progress | 3/11/2024 | EMER |  | EMER | 958679 | 765183 | SCA0000071820
6 | M128 | P.S. 128 - MANHATTAN | SCA IEH | PO18-/ABATEMENT OF PIPE INSULATION LOCATED IN BASEMENT HALLWAY BY ROOM B-5. NEED APPROXIMATELY 14FT | Construction | Complete | 11/22/2024 | IEH | 12/26/2024 | IEH | 0 | 0 | SCA0000073633
6 | M128 | P.S. 513 - MANHATTAN | SCA Furniture & Equipment | FY24 RESO A MOBILE STEM CARTS | F&E | Complete | 7/11/2024 |  | 8/29/2024 | 49930 | 49930 | 49930 | DSF0001086223
6 | M128 | P.S. 128 - MANHATTAN | Fast Track Projects | FY20 RESO A CAFETERIA UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 4137 | 4137 | DSF0000913318
6 | M128 | P.S. 128 - MANHATTAN | Fast Track Projects | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | FTK | FTK | FTK | FTK | 7916 | 4176 | DSF0001035682
6 | M128 | P.S. 513 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112806
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 12/15/2020 | 4/5/2021 | 11/16/2021 | 120420 | 129719 | 129719 | DSF0000993115, DSF0001018640, DSF0001018630
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 11/29/2021 | 5/23/2022 | 8/30/2022 | 595229 | 426281 | 340691 | DSF0000993115, DSF0001018640, DSF0001018630
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 8/7/2023 | 8/5/2025 |  | 12798419 | 12698768 | 6074799 | DSF0000993115, DSF0001018640, DSF0001018630
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 8/7/2023 | 8/5/2025 |  | 894461 | 443924 | 442447 | DSF0000993115, DSF0001018640, DSF0001018630
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/3/2024 | 11/1/2024 | 7/9/2024 | 5694 | 28 | 28 | DSF0001087481
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/9/2024 | 1/6/2025 | 12/26/2024 | 25622 | 112 | 112 | DSF0001087481
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 330239 | 330239 | 9481 | DSF0001087481
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 65472 | 65472 | 7559 | DSF0001087481
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 4/6/2015 | 2/1/2018 | 12/18/2017 | 157058 | 160626 | 160626 | DSF0000809387, DSF0000822927, DSF0000853418, DSF0000888992, DSF0000876030
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 1/26/2018 | 6/27/2018 | 5/9/2018 | 635343 | 1214752 | 1148946 | DSF0000809387, DSF0000822927, DSF0000853418, DSF0000888992, DSF0000876030
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 7/16/2018 | 11/1/2020 |  | 11140918 | 12623742 | 10828597 | DSF0000809387, DSF0000822927, DSF0000853418, DSF0000888992, DSF0000876030
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 7/16/2018 | 11/1/2020 |  | 889516 | 1846582 | 1766268 | DSF0000809387, DSF0000822927, DSF0000853418, DSF0000888992, DSF0000876030
6 | M132 | P.S. 132 - MANHATTAN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 12/27/2018 | FTK |  | FTK | 225031 | 209415 | DSF0000868317
6 | M132 | P.S. 132 - MANHATTAN | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 38400 | 0 | DSF0000867266
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0 | DSF0001008530
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 75000 | 73904 | DSF0001035685
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001086226
6 | M132 | P.S. 132 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 79000 | 0 | DSF0001112811
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DOE - RESOA | FY21 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 8/30/2021 | DOER |  | DOER | 51697 | 0 | DSF0000961372
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY21 RESO A SECURITY LIGHTING | Construction | In-Progress | 7/1/2022 | DOER |  | DOER | 20721 | 0 | DSF0001008529
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/31/2023 | DOER |  | DOER | 152641 | 0 | DSF0001033645
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 10/2/2023 | DOER | 11/19/2023 | DOER | 241419 |  | DSF0001035686
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY23 RESO A EXTERIOR UPGRADES | Construction | In-Progress | 7/26/2024 | DOER |  | DOER | 340636 | 0 | DSF0001035687
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001085117
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 113836 | 0 | DSF0001086227
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0 | DSF0001112809
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112810
6 | M132 | P.S. 132 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/4/2024 | DOES | 12/7/2024 | DOES | 65832 | 189 | DSF0001084221
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | Scope | Complete | 7/8/2021 | 11/23/2021 | 11/15/2021 | 256450 | 150002 | 150002 | DSF0001034320, DSF0001018768
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | Design | Complete | 12/1/2021 | 5/19/2022 | 5/11/2022 | 1282250 | 1043358 | 617968 | DSF0001034320, DSF0001018768
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | Construction | In-Progress | 7/18/2022 | 7/16/2024 |  | 28850625 | 26201360 | 3765170 | DSF0001034320, DSF0001018768
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | CM,F&E | In-Progress | 7/18/2022 | 7/16/2024 |  | 1795150 | 386339 | 383581 | DSF0001034320, DSF0001018768
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS ELECTRICAL SERVICE UPGRADE / DCAS LIGHTING UPGRADE | Scope | Complete | 8/31/2023 | 1/30/2024 | 2/26/2024 | 371903 | 280547 | 269784 | DSF0001085598, DSF0001111921, DSF0001112080
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS ELECTRICAL SERVICE UPGRADE / DCAS LIGHTING UPGRADE | Design | In-Progress | 7/2/2024 | 1/29/2025 |  | 1838016 | 1838016 | 420399 | DSF0001085598, DSF0001111921, DSF0001112080
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS ELECTRICAL SERVICE UPGRADE / DCAS LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | 39412203 | 39412203 | 0 | DSF0001085598, DSF0001111921, DSF0001112080
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS ELECTRICAL SERVICE UPGRADE / DCAS LIGHTING UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 2681391 | 2681391 | 74176 | DSF0001085598, DSF0001111921, DSF0001112080
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/10/2018 | 4/10/2019 | 9/6/2019 | 31096 | 35148 | 35148 | DSF0000889654, DSF0000960508
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 9/11/2019 | 5/20/2020 | 4/15/2020 | 147389 | 142699 | 142699 | DSF0000889654, DSF0000960508
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 9/15/2021 | 1/17/2023 |  | 2616721 | 2390218 | 2200321 | DSF0000889654, DSF0000960508
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 9/15/2021 | 1/17/2023 |  | 278322 | 51569 | 50780 | DSF0000889654, DSF0000960508
6 | M143 | I.S. 143 - MANHATTAN | SCA Emergency Response | EMERGENCY TEMPORARY BOILER @ M143 | Construction | In-Progress | 5/22/2023 | EMER |  | EMER | 1084276 | 938067 | SCA0000072012
6 | M143 | I.S. 143 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOM B-2. MULTIPLE BROKEN 9X9 TILES MEASURING 130 SQ. FT., CON | Construction | Complete | 7/29/2024 | IEH | 8/21/2024 | IEH | 0 | 0 | SCA0000073194
6 | M143 | I.S. 348 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0 | DSF0000913894
6 | M143 | I.S. 348 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001033689
6 | M143 | I.S. 348 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001086231
6 | M143 | I.S. 348 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112814
6 | M143 | I.S. 143 - MANHATTAN | DOE - RESOA | FY14 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0000798849
6 | M143 | I.S. 143 - MANHATTAN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 11/21/2022 | DOES | 8/30/2023 | DOES | 631642 | 622828 | DSF0000960854
6 | M143 | I.S. 143 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/21/2024 | DOES | 10/9/2024 | DOES | 65832 |  | DSF0001084789
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/25/2018 | 9/24/2018 | 10/9/2018 | 67246 | 83555 | 83555 | DSF0000912306, DSF0000960652
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Design | Complete | 10/16/2018 | 3/6/2019 | 4/29/2019 | 269075 | 358833 | 334507 | DSF0000912306, DSF0000960652
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 7/31/2019 | 1/20/2021 |  | 5040282 | 5653881 | 4795439 | DSF0000912306, DSF0000960652
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 7/31/2019 | 1/20/2021 |  | 314939 | 904728 | 875074 | DSF0000912306, DSF0000960652
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | Scope | Complete | 9/10/2019 | 1/14/2020 | 8/16/2021 | 14579 | 22049 | 22049 | DSF0000912586
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | Design | Complete | 8/31/2021 | 2/4/2022 | 5/11/2022 | 72894 | 85968 | 84293 | DSF0000912586
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | Construction | In-Progress | 11/14/2022 | 5/6/2024 |  | 1640115 | 1488972 | 1200591 | DSF0000912586
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | CM,F&E | In-Progress | 11/14/2022 | 5/6/2024 |  | 102052 | 186649 | 182437 | DSF0000912586
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Scope | Complete | 8/31/2021 | 12/3/2021 | 3/25/2022 | 801 | 801 | 18526 | DSF0001009248
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Design | Complete | 3/25/2022 | 7/25/2022 | 1/3/2024 | 3606 | 3606 | 15907 | DSF0001009248
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 46472 | 46472 | 188 | DSF0001009248
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PATH OF TRAVEL NYS AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 8613 | 8613 | 5640 | DSF0001009248
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | Scope | Complete | 5/30/2023 | 10/16/2023 | 9/25/2023 | 229330 | 253071 | 246682 | DSF0001018857, DSF0001018858, DSF0001018859, DSF0001018860, DSF0001087210, DSF0001087209
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | Design | Complete | 10/25/2023 | 6/10/2024 | 4/25/2024 | 1131307 | 429831 | 421653 | DSF0001018857, DSF0001018858, DSF0001018859, DSF0001018860, DSF0001087210, DSF0001087209
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | Construction | In-Progress | 8/15/2024 | 2/10/2027 |  | 24127238 | 21853073 | 220305 | DSF0001018857, DSF0001018858, DSF0001018859, DSF0001018860, DSF0001087210, DSF0001087209
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | CM,F&E | In-Progress | 8/15/2024 | 2/10/2027 |  | 1720382 | 96214 | 95494 | DSF0001018857, DSF0001018858, DSF0001018859, DSF0001018860, DSF0001087210, DSF0001087209
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/27/2023 | 10/27/2023 | 10/5/2023 | 10634 | 17944 | 17881 | DSF0001083803
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/17/2023 | 3/18/2024 | 4/10/2024 | 47852 | 57518 | 45646 | DSF0001083803
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 10/4/2024 | 10/3/2025 |  | 616753 | 547511 | 4109 | DSF0001083803
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 10/4/2024 | 10/3/2025 |  | 114312 | 70354 | 12823 | DSF0001083803
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/2/2023 | 3/7/2024 | 11/17/2023 | 0 | 4501 | 4501 | DSF0001086235
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/17/2023 | 5/15/2024 | 4/2/2024 | 27000 | 18005 | 18005 | DSF0001086235
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 396000 | 396000 | 6970 | DSF0001086235
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 30740 | 27000 | 4573 | DSF0001086235
6 | M152 | P.S. 152 - MANHATTAN | SCA IEH | PO18-THIN LAYER OF WATERPROOFING BEHIND THE WALL PLASTER BROWN COAT (BLACK)IS ACM ABATE APPROXIMATEL | Construction | Complete | 2/21/2024 | IEH | 9/22/2024 | IEH | 0 | 0 | SCA0000073079
6 | M152 | P.S. 152 - MANHATTAN | SCA IEH | PO18-ROOM CLOSER, APPROX 80 SQ ABATEMENT NEEDED - IN WALL AND CEILINGS IN RM 217 DUE TO WATER DAMAGE | Construction | In-Progress | 6/21/2024 | IEH |  | IEH | 0 | 0 | SCA0000073328
6 | M153 | P.S. 153 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 241250 | 0 | DSF0000960019
6 | M153 | P.S. 153 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001033174
6 | M153 | P.S. 368 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/15/2024 | DIIR | 10/17/2024 | DIIR | 49821 | 49821 | DSF0001086236
6 | M153 | P.S. 153 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112819
6 | M153 | P.S. 153 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/8/2022 | DOER |  | DOER | 285143 | 0 | DSF0000913322
6 | M153 | P.S. 368 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | Complete | 7/14/2021 | DOER | 12/10/2021 | DOER | 82950 | 76508 | DSF0001007855
6 | M153 | P.S. 368 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 375000 | 0 | DSF0001112818
6 | M153 | P.S. 153 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/16/2022 | DOES | 3/29/2023 | DOES | 92941 | 98190 | DSF0001034243
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/20/2022 | 12/6/2022 | 5/4/2023 | 77350 | 143338 | 143338 | DSF0001018989, DSF0001018990, DSF0001018991
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 6/14/2023 | 11/16/2023 | 10/27/2023 | 386750 | 457641 | 323858 | DSF0001018989, DSF0001018990, DSF0001018991
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 8/15/2024 | 2/10/2027 |  | 8701876 | 7939254 | 112254 | DSF0001018989, DSF0001018990, DSF0001018991
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/15/2024 | 2/10/2027 |  | 541450 | 107896 | 105150 | DSF0001018989, DSF0001018990, DSF0001018991
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Scope | Complete | 10/12/2022 | 7/14/2023 | 9/28/2023 | 15192 | 77713 | 48889 | DSF0001035195, DSF0001083872
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Design | Complete | 10/11/2023 | 2/15/2024 | 4/19/2024 | 74053 | 69957 | 61519 | DSF0001035195, DSF0001083872
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 1501152 | 1501152 | 13602 | DSF0001035195, DSF0001083872
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 120656 | 121861 | 80055 | DSF0001035195, DSF0001083872
6 | M164 | I.S. 328 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/3/2022 | EMER |  | EMER | 49068 | 29991 | SCA0000071088
6 | M164 | I.S. 223 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086242
6 | M164 | I.S. 328 - MANHATTAN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/22/2024 | DOER |  | DOER | 383835 | 0 | DSF0001035696
6 | M164 | I.S. 223 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112823
6 | M164 | I.S. 328 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/3/2024 | DOES | 9/13/2024 | DOES | 65832 |  | DSF0001084790
6 | M164 | I.S. 328 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/9/2024 | DOES |  | DOES | 646666 | 0 | DSF0001085738
6 | M173 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | Scope | Complete | 12/18/2017 | 5/4/2018 | 3/23/2018 | 165873 | 150089 | 150087 | DSF0000876476, DSF0000876478, DSF0000876479, DSF0000876485, DSF0000889082
6 | M173 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | Design | Complete | 3/23/2018 | 8/22/2018 | 5/18/2018 | 652179 | 589079 | 529862 | DSF0000876476, DSF0000876478, DSF0000876479, DSF0000876485, DSF0000889082
6 | M173 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | Construction | In-Progress | 8/13/2018 | 8/11/2020 |  | 11212637 | 12835262 | 9280184 | DSF0000876476, DSF0000876478, DSF0000876479, DSF0000876485, DSF0000889082
6 | M173 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | CM,F&E | In-Progress | 8/13/2018 | 8/11/2020 |  | 921201 | 2138268 | 2078825 | DSF0000876476, DSF0000876478, DSF0000876479, DSF0000876485, DSF0000889082
6 | M173 | P.S. 173 - MANHATTAN | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/1/2023 | FTK |  | FTK | 566123 | 423997 | DSF0001035033
6 | M173 | I.S. 349 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033690
6 | M173 | P.S. 173 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 10/22/2023 | DOES | 10/23/2023 | DOES | 62166 |  | DSF0000866122
6 | M173 | I.S. 349 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/3/2024 | DOES |  | DOES | 352968 | 0 | DSF0001085740
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/27/2023 | 10/27/2023 | 10/13/2023 | 10620 | 13624 | 13561 | DSF0001083799
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/16/2023 | 3/15/2024 | 4/10/2024 | 47790 | 69852 | 54894 | DSF0001083799
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/12/2024 | 9/11/2025 |  | 615960 | 536310 | 0 | DSF0001083799
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/12/2024 | 9/11/2025 |  | 114165 | 69001 | 11409 | DSF0001083799
6 | M176 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | Scope | Complete | 6/27/2019 | 7/13/2021 | 9/23/2021 | 68580 | 96161 | 96161 | DSF0000899402, DSF0000913326, DSF0000944835
6 | M176 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | Design | Complete | 1/11/2022 | 5/26/2022 | 7/19/2022 | 326100 | 301061 | 280380 | DSF0000899402, DSF0000913326, DSF0000944835
6 | M176 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | Construction | In-Progress | 5/3/2023 | 5/1/2025 |  | 7085251 | 6803265 | 1488562 | DSF0000899402, DSF0000913326, DSF0000944835
6 | M176 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | CM,F&E | In-Progress | 5/3/2023 | 5/1/2025 |  | 442390 | 586002 | 584246 | DSF0000899402, DSF0000913326, DSF0000944835
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/28/2022 | 10/27/2022 | 7/6/2022 | 3660 | 5635 | 5635 | DSF0001034586
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/6/2022 | 1/3/2023 | 1/4/2023 | 16470 | 22539 | 22539 | DSF0001034586
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/21/2023 | 4/15/2024 |  | 212280 | 189728 | 159132 | DSF0001034586
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/21/2023 | 4/15/2024 |  | 176297 | 167346 | 155793 | DSF0001034586
6 | M176 | P.S. 314 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 68000 | 0 | DSF0001112833
6 | M176 | P.S. 314 - MANHATTAN | DOE - RESOA | FY14 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0000798716
6 | M176 | P.S. 311 - MANHATTAN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 7/15/2022 | DOER | 5/14/2023 | DOER | 202574 | 191631 | DSF0001033204
6 | M176 | P.S. 314 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 10/2/2023 | DOER | 12/18/2023 | DOER | 394369 |  | DSF0001035217
6 | M176 | P.S. 314 - MANHATTAN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 250000 | 0 | DSF0001086248
6 | M176 | P.S. 311 - MANHATTAN | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001112831
6 | M176 | P.S. 311 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0 | DSF0001112832
6 | M176 | P.S. 314 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035705
6 | M176 | P.S. 314 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 9/22/2022 | DOES | 11/17/2022 | DOES | 69546 | 68610 | DSF0001009127
6 | M176 | P.S. 311 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/6/2023 | DOES |  | DOES | 50832 | 0 | DSF0001084237
6 | M178 | P.S. 178 - MANHATTAN | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/1/2023 | FTK |  | FTK | 327295 | 251947 | DSF0001035048
6 | M178 | P.S. 178 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 7/5/2024 | DIIR | 150000 | 132383 | DSF0001086249
6 | M178 | P.S. 178 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112834
6 | M178 | P.S. 178 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/6/2023 | DOES | 12/6/2024 | DOES | 50832 |  | DSF0001084238
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/16/2020 | 5/24/2021 | 2/15/2022 | 0 | 0 | 99073 | DSF0000844920, DSF0000960975
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2/16/2022 | 4/18/2022 | 11/1/2022 | 55434 | 55434 | 79738 | DSF0000844920, DSF0000960975
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 6/12/2023 | 5/6/2024 |  | 813024 | 709292 | 531373 | DSF0000844920, DSF0000960975
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 6/12/2023 | 5/6/2024 |  | 55434 | 55434 | 85833 | DSF0000844920, DSF0000960975
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/20/2023 | 4/21/2023 | 8/8/2023 | 0 | 50219 | 42046 | DSF0001035708, DSF0001035709
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 8/9/2023 | 12/13/2023 | 11/1/2023 | 112677 | 58370 | 53555 | DSF0001035708, DSF0001035709
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1652592 | 1652592 | 9559 | DSF0001035708, DSF0001035709
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 112677 | 114308 | 27501 | DSF0001035708, DSF0001035709
6 | M187 | P.S. 187 - MANHATTAN | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 11/27/2023 | FTK |  | FTK | 443172 | 119660 | DSF0001019222
6 | M187 | P.S. 187 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 437848 | 9025 | DSF0001086251
6 | M187 | P.S. 187 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112837
6 | M187 | P.S. 187 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/29/2024 | DOES | 8/9/2024 | DOES | 65832 | 5306 | DSF0001084642
6 | M187 | P.S. 187 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/1/2024 | DOES |  | DOES | 284719 | 0 | DSF0001085742
6 | M189 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | Scope | Complete | 12/18/2017 | 5/4/2018 | 2/28/2018 | 185319 | 257285 | 257239 | DSF0000876592, DSF0000876594, DSF0000876595, DSF0000876596, DSF0000889278
6 | M189 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | Design | Complete | 2/28/2018 | 7/30/2018 | 5/17/2018 | 735179 | 1309915 | 949703 | DSF0000876592, DSF0000876594, DSF0000876595, DSF0000876596, DSF0000889278
6 | M189 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | Construction | In-Progress | 8/13/2018 | 8/11/2020 |  | 13237508 | 21219664 | 16455924 | DSF0000876592, DSF0000876594, DSF0000876595, DSF0000876596, DSF0000889278
6 | M189 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | CM,F&E | In-Progress | 8/13/2018 | 8/11/2020 |  | 944063 | 1742065 | 1543459 | DSF0000876592, DSF0000876594, DSF0000876595, DSF0000876596, DSF0000889278
6 | M189 | P.S. 189 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 9/4/2024 | DIIR | 75000 | 75000 | DSF0001033185
6 | M189 | P.S. 189 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 11/27/2024 | DIIR | 49825 | 49825 | DSF0001086255
6 | M189 | P.S. 189 - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 346778 | 0 | DSF0001086256
6 | M189 | P.S. 189 - MANHATTAN | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0 | DSF0001112839
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | PATH OF TRAVEL OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 12/10/2024 | 3/13/2025 |  | 647 | 647 | 0 | DSF0001113848
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | PATH OF TRAVEL OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | PNS | PNS | PNS | PNS | 2589 | 2589 | 0 | DSF0001113848
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | PATH OF TRAVEL OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 37216 | 37216 | 0 | DSF0001113848
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | PATH OF TRAVEL OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 9547 | 9547 | 453 | DSF0001113848
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | EXTERIOR STAIRS / PAVED AREAS - CONCRETE / NON-TCU TEMPORARY REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/22/2020 | 5/17/2023 | 6/5/2023 | 37500 | 134310 | 120131 | DSF0000961134, DSF0000944965, DSF0001083712
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | EXTERIOR STAIRS / PAVED AREAS - CONCRETE / NON-TCU TEMPORARY REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 6/6/2023 | 10/23/2023 | 12/29/2023 | 186383 | 293786 | 205427 | DSF0000961134, DSF0000944965, DSF0001083712
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | EXTERIOR STAIRS / PAVED AREAS - CONCRETE / NON-TCU TEMPORARY REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 4097088 | 4097088 | 179747 | DSF0000961134, DSF0000944965, DSF0001083712
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | EXTERIOR STAIRS / PAVED AREAS - CONCRETE / NON-TCU TEMPORARY REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 270869 | 270869 | 76273 | DSF0000961134, DSF0000944965, DSF0001083712
6 | M192 | HAMILTON GRANGE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/13/2023 | 7/13/2023 | 8/8/2023 | 0 | 12532 | 12532 | DSF0001035718
6 | M192 | HAMILTON GRANGE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 8/8/2023 | 1/11/2024 | 1/5/2024 | 14461 | 54518 | 51850 | DSF0001035718
6 | M192 | HAMILTON GRANGE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 212097 | 981978 | 4208 | DSF0001035718
6 | M192 | HAMILTON GRANGE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 14461 | 66953 | 5851 | DSF0001035718
6 | M192 | P.S. 192 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN 3RS FLOOR HALLWAY APPROX. 2976SF | Construction | In-Progress | 2/2/2024 | IEH |  | IEH | 0 | 0 | SCA0000072709
6 | M192 | P.S. 192 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE 9X9 FLOOR TILES IN THE FOLLOWING ROOMS 226A APPROX 408 SQ FT AND ROOM 145 A | Construction | In-Progress | 4/12/2024 | IEH |  | IEH | 0 | 0 | SCA0000072926
6 | M192 | P.S. 192 - MANHATTAN | SCA IEH | PO18-ABATE PIPE INSULATION IN PIPE CHASE INSIDE CLOSET 235 FOR WOMEN'S TOILET #233 (1958 WING); THIS | Construction | Complete | 11/15/2024 | IEH | 12/8/2024 | IEH | 0 | 0 | SCA0000073613
6 | M192 | P.S. 192 - MANHATTAN | Fast Track Projects | LSP- LSP HOT WATER HEATER | Construction | In-Progress | 7/15/2022 | FTK |  | FTK | 253602 | 56384 | DSF0000889646
6 | M192 | P.S. 192 - MANHATTAN | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/1/2023 | FTK |  | FTK | 459258 | 401146 | DSF0001035034
6 | M192 | P.S. 325 - MANHATTAN | DIIT - RESOA | FY16 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0000823169
6 | M192 | P.S. 325 - MANHATTAN | DIIT - RESOA | FY17 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0 | DSF0000845250
6 | M192 | P.S. 192 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 140000 | 0 | DSF0000961368
6 | M192 | P.S. 192 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 200000 | 120910 | DSF0001035717
6 | M192 | HAMILTON GRANGE MIDDLE SCHOOL | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 9/19/2022 | DOER |  | DOER | 347821 | 0 | DSF0000913331
6 | M192 | P.S. 192 - MANHATTAN | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 637558 | 0 | DSF0001086259
6 | M192 | P.S. 192 - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112842
6 | M192 | P.S. 192 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/17/2024 | DOES | 7/15/2024 | DOES | 65832 | 10170 | DSF0001084244
6 | M218 | I.S. 293 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ELECTRIFICATION/HEAT PUMP SYSTEMS / EXTERIOR MASONRY / PARAPETS / ROOFS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SERVICE UPGRADE / WINDOWS / LIGHTING UPGRADE | Scope | Complete | 7/8/2022 | 11/22/2023 | 3/1/2024 | 673976 | 951431 | 688606 | DSF0001019445, DSF0001083676, DSF0001070179, DSF0001070178, DSF0001070177, DSF0001097868, DSF0001097877, DSF0001112079, DSF0001112078
6 | M218 | I.S. 293 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ELECTRIFICATION/HEAT PUMP SYSTEMS / EXTERIOR MASONRY / PARAPETS / ROOFS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SERVICE UPGRADE / WINDOWS / LIGHTING UPGRADE | Design | Complete | 3/1/2024 | 8/1/2024 | 5/15/2024 | 3365191 | 3290107 | 1695852 | DSF0001019445, DSF0001083676, DSF0001070179, DSF0001070178, DSF0001070177, DSF0001097868, DSF0001097877, DSF0001112079, DSF0001112078
6 | M218 | I.S. 293 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ELECTRIFICATION/HEAT PUMP SYSTEMS / EXTERIOR MASONRY / PARAPETS / ROOFS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SERVICE UPGRADE / WINDOWS / LIGHTING UPGRADE | Construction | In-Progress | 10/14/2024 | 10/12/2028 |  | 75311522 | 67437187 | 5952 | DSF0001019445, DSF0001083676, DSF0001070179, DSF0001070178, DSF0001070177, DSF0001097868, DSF0001097877, DSF0001112079, DSF0001112078
6 | M218 | I.S. 293 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ELECTRIFICATION/HEAT PUMP SYSTEMS / EXTERIOR MASONRY / PARAPETS / ROOFS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SERVICE UPGRADE / WINDOWS / LIGHTING UPGRADE | CM,F&E | In-Progress | 10/14/2024 | 10/12/2028 |  | 4752963 | 165551 | 157517 | DSF0001019445, DSF0001083676, DSF0001070179, DSF0001070178, DSF0001070177, DSF0001097868, DSF0001097877, DSF0001112079, DSF0001112078
6 | M218 | I.S. 293 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 239412 | 0 | DSF0000960033
6 | M218 | I.S. 322 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/11/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001033206
6 | M218 | I.S. 293 - MANHATTAN | DOE - RESOA | RESO A ATHLETIC FIELD | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001085115
6 | M218 | I.S. 293 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/15/2023 | DOES | 11/6/2023 | DOES | 415529 | 333254 | DSF0001035168
6 | M218 | I.S. 322 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/28/2024 | DOES | 11/6/2024 | DOES | 50832 |  | DSF0001084793
6 | M263 | P.S. 366 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112851
6 | M263 | P.S. 366 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/4/2024 | DOES | 10/22/2024 | DOES | 50832 |  | DSF0001084646
6 | M387 | SUCCESS ACADEMY CHARTER SCHOOL - WASHINGTON HEIGHTS - NEW YORK 1 | SCA IEH | PO18-ABATE LOBBY CEILING BY EXIT 13 VESTIBULE APPROX. 13 SQ FT SPACE ID ( 0022V) AHERA BOOK 2022 | Construction | Complete | 11/7/2024 | IEH | 12/24/2024 | IEH | 0 | 0 | SCA0000073588
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | Scope | Complete | 9/11/2017 | 9/14/2017 | 9/21/2017 | 26700 | 70515 | 70515 | DSF0000868064
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | Design | Complete | 9/21/2017 | 6/29/2018 | 8/8/2018 | 97900 | 131857 | 125462 | DSF0000868064
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | Construction | In-Progress | 4/3/2019 | 4/1/2020 |  | 1036850 | 1107579 | 916876 | DSF0000868064
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | CM,F&E | In-Progress | 4/3/2019 | 4/1/2020 |  | 240300 | 296454 | 290059 | DSF0000868064
6 | M465 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | Scope | Complete | 4/2/2018 | 7/31/2018 | 8/6/2018 | 27662 | 127216 | 127216 | DSF0001085151
6 | M465 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | Design | Complete | 12/1/2021 | 5/4/2022 | 5/12/2023 | 138310 | 312366 | 274192 | DSF0001085151
6 | M465 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | Construction | In-Progress | 8/14/2023 | 2/3/2025 |  | 3111982 | 2862214 | 2274597 | DSF0001085151
6 | M465 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | CM,F&E | In-Progress | 8/14/2023 | 2/3/2025 |  | 193634 | 182158 | 182021 | DSF0001085151
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 11/15/2018 | 4/4/2019 | 4/4/2019 | 564406 | 472132 | 472132 | DSF0000876943, DSF0000876941, DSF0000876942, DSF0000876944
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 4/5/2019 | 9/5/2019 | 5/16/2019 | 2257620 | 1238106 | 1028425 | DSF0000876943, DSF0000876941, DSF0000876942, DSF0000876944
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 7/22/2019 | 6/15/2022 |  | 42330374 | 43481092 | 36989698 | DSF0000876943, DSF0000876941, DSF0000876942, DSF0000876944
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/22/2019 | 6/15/2022 |  | 2633889 | 2818930 | 2588273 | DSF0000876943, DSF0000876941, DSF0000876942, DSF0000876944
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | Scope | Complete | 1/3/2020 | 5/19/2020 | 10/14/2021 | 57240 | 124379 | 106364 | DSF0000960511
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | Design | Complete | 10/18/2021 | 4/22/2022 | 9/26/2022 | 286200 | 464585 | 439569 | DSF0000960511
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | Construction | In-Progress | 5/8/2023 | 5/6/2025 |  | 6439500 | 5924202 | 3855710 | DSF0000960511
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | CM,F&E | In-Progress | 5/8/2023 | 5/6/2025 |  | 400680 | 284832 | 283321 | DSF0000960511
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 9/18/2013 | 10/4/2019 | 10/1/2019 | 216730 | 203507 | 203507 | DSF0000754658, DSF0000899817
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 10/1/2019 | 3/6/2020 | 5/12/2021 | 1083650 | 1142529 | 1066011 | DSF0000754658, DSF0000899817
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 7/11/2022 | 1/7/2025 |  | 24382125 | 22901360 | 19370878 | DSF0000754658, DSF0000899817
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 7/11/2022 | 1/7/2025 |  | 1517110 | 993449 | 985938 | DSF0000754658, DSF0000899817
6 | M465 | HS FOR MEDIA & COMM - MANHATTAN | SCA CIP RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000890837
6 | M465 | HS FOR MEDIA & COMM - MANHATTAN | SCA CIP RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Design | PNS | PNS | PNS | PNS | 45465 | 45465 | 0 | DSF0000890837
6 | M465 | HS FOR MEDIA & COMM - MANHATTAN | SCA CIP RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | 666813 | 689321 | 0 | DSF0000890837
6 | M465 | HS FOR MEDIA & COMM - MANHATTAN | SCA CIP RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | CM,F&E | PNS | PNS | PNS | PNS | 45465 | 46999 | 0 | DSF0000890837
6 | M465 | GEORGE WASHINGTON CAMPUS YABC | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 8/2/2018 | EMER |  | EMER | 582706 | 534580 | SCA0000051113
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA IEH | PO18-ABATE AND REMOVE PIPE INSULATION IN ROOM B-39 CURRENTLY PAINTED IN RED IT IS 12 FT ACM | Construction | Complete | 7/10/2024 | IEH | 7/10/2024 | IEH | 0 | 0 | SCA0000073127
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA IEH | PO18-PATCH UP /REMOVE FRIABLE ACM IN SOUTH BLOWER ROOM BASEMENT LEVEL PIPING IS ABOUT 10 FEET UP IN | Construction | Complete | 8/19/2024 | IEH | 9/8/2024 | IEH | 0 | 0 | SCA0000073300
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | Fast Track Projects | CAFETERIA CHILLER | Construction | In-Progress | 3/30/2021 | FTK |  | FTK | 8608245 | 8565073 | DSF0000945291
6 | M465 | THE COLLEGE ACADEMY - M | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001008939
6 | M465 | THE COLLEGE ACADEMY - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/16/2024 | DIIR |  | DIIR | 124000 | 0 | DSF0001086289
6 | M465 | HS FOR MEDIA & COMM - MANHATTAN | DIIT - RESOA | FY25 RESO A CLASSROOM CONNECTIVITY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112880
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMP | Construction | In-Progress | 8/20/2018 | DOES |  | DOES | 351365 | 0 | DSF0000889361
6 | M465 | THE COLLEGE ACADEMY - M | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 35000 | 0 | DSF0000822831
6 | M465 | THE COLLEGE ACADEMY - M | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175219 | 0 | DSF0000867197
6 | M465 | THE COLLEGE ACADEMY - M | DOE - RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 5/27/2022 | DOER |  | DOER | 669714 | 0 | DSF0000890675
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - RESOA | FY19 RESO A ROOM CONVERSION | Construction | In-Progress | 6/28/2019 | DOER |  | DOER | 177840 | 0 | DSF0000890838
6 | M465 | HS FOR LAW AND PUBLIC SERVICE - M | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 164306 | 0 | DSF0000913340
6 | M465 | HS FOR LAW AND PUBLIC SERVICE - M | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001035748
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086290
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0 | DSF0001112877
6 | M465 | HS FOR MEDIA & COMM - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112878
6 | M465 | HS FOR LAW AND PUBLIC SERVICE - M | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112881
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112882
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 731791 | 0 | DSF0000912214
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/30/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084957
6 | M466 | HS FOR MEDIA & COMM - MANHATTAN | DOE - Skilled Trades | ATHLETIC FIELD | Construction | Complete | 11/29/2023 | DOES | 6/19/2024 | DOES | 1386120 | 34691 | DSF0001087143
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | Scope | Complete | 10/26/2020 | 3/23/2021 | 3/23/2021 | 2036860 | 1509269 | 1474406 | DSF0000912556
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | Design | Complete | 3/24/2021 | 10/25/2021 | 11/3/2021 | 9165870 | 5581937 | 5266367 | DSF0000912556
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 9/15/2022 | 9/3/2024 |  | 115591805 | 106149144 | 102837562 | DSF0000912556
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 9/15/2022 | 9/3/2024 |  | 16294880 | 9942221 | 7606503 | DSF0000912556
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | Scope | Complete | 1/20/2021 | 1/20/2021 | 1/20/2021 | 17304 | 36685 | 36685 | DSF0000912556
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | Design | Complete | 1/20/2021 | 10/25/2021 | 12/1/2021 | 86520 | 146745 | 146745 | DSF0000912556
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | Construction | In-Progress | 1/3/2022 | 7/1/2022 |  | 1946700 | 2840866 | 2682544 | DSF0000912556
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 1/3/2022 | 7/1/2022 |  | 121128 | 834934 | 296033 | DSF0000912556
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/6/2022 | 11/3/2022 | 7/19/2022 | 5800 | 7772 | 7772 | DSF0001034547
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/19/2022 | 1/17/2023 | 1/4/2023 | 26100 | 31091 | 31091 | DSF0001034547
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/21/2023 | 4/15/2024 |  | 336400 | 299652 | 216802 | DSF0001034547
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/21/2023 | 4/15/2024 |  | 114284 | 110920 | 87183 | DSF0001034547
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Scope | In-Progress | 4/28/2022 | 8/29/2022 |  | 0 | 11407 | 479 | DSF0001033714
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 30000 | 18593 | 1917 | DSF0001033714
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001033714
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001033714
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 9/1/2022 | 12/5/2022 | 12/20/2022 | 0 | 25271 | 25271 | DSF0000913346
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 12/21/2022 | 5/9/2023 | 7/5/2023 | 83526 | 66393 | 65113 | DSF0000913346
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1225041 | 1225041 | 5910 | DSF0000913346
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 83526 | 83526 | 17239 | DSF0000913346
6 | M528 | I.S. 528 - MANHATTAN | Fast Track Projects | LSP HOT WATER HEATER | Construction | In-Progress | 3/9/2020 | FTK |  | FTK | 321193 | 36971 | DSF0000900089
6 | M528 | I.S. 528 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033232
6 | M528 | I.S. 528 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 75000 | 74718 | DSF0001086311
6 | M528 | I.S. 528 - MANHATTAN | DOE - RESOA | FY17 RESO A TOILETS-STUDENTS | Construction | PNS | PNS | PNS | PNS | DOER | 145000 | 0 | DSF0000844911
6 | M528 | I.S. 528 - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/28/2022 | DOER |  | DOER | 29572 | 0 | DSF0000961327
6 | M528 | I.S. 528 - MANHATTAN | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112900
6 | M528 | I.S. 528 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084795
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | SCA CIP RESOA | FY19 RESO A WEIGHT ROOM UPGRADE | Scope | Complete | 1/31/2019 | 6/3/2019 | 9/3/2019 | 0 | 6854 | 6854 | DSF0000890679
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | SCA CIP RESOA | FY19 RESO A WEIGHT ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 15000 | 8146 | 3503 | DSF0000890679
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | SCA CIP RESOA | FY19 RESO A WEIGHT ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 220000 | 175542 | 0 | DSF0000890679
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | SCA CIP RESOA | FY19 RESO A WEIGHT ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 15000 | 11969 | 0 | DSF0000890679
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 6/17/2024 | DOER |  | DOER | 103793 | 0 | DSF0000913350
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 2/15/2018 | DOES |  | DOES | 434801 | 3174 | DSF0000911915
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATIONS | Construction | In-Progress | 5/7/2019 | DOES |  | DOES | 181697 | 24294 | DSF0000900121
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/30/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084971
6 | M812 | HS FOR MATH, SCI AND ENGINEERING-M | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001085321
6 | M812 | HS FOR MATH, SCI AND ENGINEERING-M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 100000 | 91870 | DSF0001086323
6 | M812 | HS FOR MATH, SCI AND ENGINEERING-M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112905
6 | M814 | I.S. 346 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 9/4/2024 | DIIR | 250000 | 116079 | DSF0000913934
6 | M814 | I.S. 346 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033688
6 | M814 | I.S. 346 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035327
6 | M814 | I.S. 346 - MANHATTAN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0000961292
6 | M814 | I.S. 346 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/14/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084982
6 | M847 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | Scope | Complete | 6/25/2018 | 9/24/2018 | 10/9/2018 | 20269 | 77062 | 77062 | DSF0000888968
6 | M847 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | Design | Complete | 10/16/2018 | 3/6/2019 | 4/29/2019 | 81077 | 210834 | 210834 | DSF0000888968
6 | M847 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | Construction | In-Progress | 7/31/2019 | 1/20/2021 |  | 1520197 | 1398265 | 1277223 | DSF0000888968
6 | M847 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | CM,F&E | In-Progress | 7/31/2019 | 1/20/2021 |  | 94590 | 73519 | 73519 | DSF0000888968
6 | M859 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | Scope | Complete | 1/11/2021 | 4/12/2021 | 1/19/2021 | 1584 | 1037 | 1037 | DSF0001008646
6 | M859 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | Design | Complete | 1/20/2021 | 6/21/2021 | 4/12/2021 | 7127 | 4772 | 4147 | DSF0001008646
6 | M859 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | Construction | In-Progress | 9/15/2021 | 1/17/2023 |  | 91856 | 138821 | 96050 | DSF0001008646
6 | M859 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | CM,F&E | In-Progress | 9/15/2021 | 1/17/2023 |  | 17025 | 217770 | 217145 | DSF0001008646
6 | M859 | I.S. 348 - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/1/2024 | IEH | 8/13/2024 | IEH | 0 | 0 | SCA0000073214
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/28/2022 | 7/26/2022 | 4/14/2022 | 1477 | 3177 | 3177 | DSF0001034369
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/14/2022 | 10/7/2022 | 7/19/2022 | 6646 | 12705 | 12705 | DSF0001034369
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 3/9/2023 | 2/1/2024 |  | 85658 | 83295 | 72203 | DSF0001034369
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 3/9/2023 | 2/1/2024 |  | 123026 | 137261 | 97865 | DSF0001034369
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY22 RESO A (MA) MEDIA CENTER | Scope | In-Progress | 6/1/2022 | 10/3/2022 |  | 0 | 96704 | 704 | DSF0001032956
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY22 RESO A (MA) MEDIA CENTER | Design | PNS | PNS | PNS | PNS | 600000 | 503296 | 2425 | DSF0001032956
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY22 RESO A (MA) MEDIA CENTER | Construction | PNS | PNS | PNS | PNS | 8800000 | 8800000 | 0 | DSF0001032956
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY22 RESO A (MA) MEDIA CENTER | CM,F&E | PNS | PNS | PNS | PNS | 600000 | 600000 | 0 | DSF0001032956
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 7/12/2021 | 10/26/2021 | 11/1/2024 | 0 | 9285 | 3244 | DSF0001008533
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 1411 | 1411 | DSF0001008533
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001008533
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001008533
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007782
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007782
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007782
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007782
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | Fast Track Projects | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/18/2022 | FTK |  | FTK | 202962 | 183015 | DSF0000913352
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2/20/2024 | DOER |  | DOER | 79775 | 0 | DSF0001035328
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0 | DSF0001086331
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112913
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | DOE - Skilled Trades | WATER MAIN REPAIRS | Construction | In-Progress | 9/15/2020 | DOES |  | DOES | 43847 | 489 | DSF0000961536
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/19/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084985
6 | M898 | P.S. 18 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0 | DSF0001033147
6 | M898 | P.S. 18 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 99000 | 0 | DSF0001035786
6 | M918 | P.S./I.S. 278 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 280000 | 0 | DSF0001035789
6 | M918 | P.S./I.S. 278 - MANHATTAN | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001085118
6 | M918 | P.S./I.S. 278 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/8/2024 | DIIR | 9/16/2024 | DIIR | 75000 | 38281 | DSF0001086335
6 | M918 | P.S./I.S. 278 - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112921
6 | MBEQ | U.F.B.C.O. | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 4/7/2021 | 7/7/2021 | 8/6/2021 | 780 | 35345 | 35345 | DSF0001008781
6 | MBEQ | U.F.B.C.O. | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | PNS | PNS | PNS | PNS | 3512 | 46047 | 40802 | DSF0001008781
6 | MBEQ | U.F.B.C.O. | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Construction | PNS | PNS | PNS | PNS | 45263 | 45263 | 8830 | DSF0001008781
6 | MBEQ | U.F.B.C.O. | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | CM,F&E | PNS | PNS | PNS | PNS | 8389 | 9971 | 9971 | DSF0001008781
7 | Q535 | NEW RIKERS ISLAND SCHOOL - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | In-Progress | 12/12/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001113728
7 | X001 | P.S. 1 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM SYSTEM / PARAPETS / ROOFS / LIGHTING UPGRADE | Scope | Complete | 8/13/2024 | 2/12/2025 | 10/11/2024 | 473277 | 103482 | 71882 | DSF0001112300, DSF0001112317, DSF0001113843, DSF0001113845, DSF0001113844, DSF0001134541
7 | X001 | P.S. 1 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM SYSTEM / PARAPETS / ROOFS / LIGHTING UPGRADE | Design | In-Progress | 10/23/2024 | 4/25/2025 |  | 2198624 | 2198624 | 287517 | DSF0001112300, DSF0001112317, DSF0001113843, DSF0001113845, DSF0001113844, DSF0001134541
7 | X001 | P.S. 1 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM SYSTEM / PARAPETS / ROOFS / LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | 34774967 | 34774967 | 35732 | DSF0001112300, DSF0001112317, DSF0001113843, DSF0001113845, DSF0001113844, DSF0001134541
7 | X001 | P.S. 1 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM SYSTEM / PARAPETS / ROOFS / LIGHTING UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 3581945 | 3581945 | 56309 | DSF0001112300, DSF0001112317, DSF0001113843, DSF0001113845, DSF0001113844, DSF0001134541
7 | X001 | P.S. 1 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 331345 | 0 | DSF0000960280
7 | X001 | P.S. 1 - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 125000 | 0 | DSF0000914156
7 | X001 | P.S. 1 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113301
7 | X001 | P.S. 1 - BRONX | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 189966 | 0 | DSF0000822349
7 | X001 | P.S. 1 - BRONX | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/12/2024 | DOER |  | DOER | 237465 | 0 | DSF0001036163
7 | X001 | P.S. 1 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 238239 | 0 | DSF0001086684
7 | X001 | P.S. 1 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 5/27/2024 | DOES |  | DOES | 232507 | 0 | DSF0001106881
7 | X005 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 6/26/2019 | 11/12/2019 | 12/3/2019 | 57964 | 82112 | 82112 | DSF0000906328, DSF0000952061, DSF0000952060
7 | X005 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 12/18/2019 | 5/20/2020 | 2/28/2022 | 285806 | 233037 | 233037 | DSF0000906328, DSF0000952061, DSF0000952060
7 | X005 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | Complete | 7/11/2022 | 1/1/2024 | 9/6/2024 | 6083424 | 6153993 | 5887676 | DSF0000906328, DSF0000952061, DSF0000952060
7 | X005 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | Complete | 7/11/2022 | 1/1/2024 | 9/6/2024 | 435851 | 319331 | 318855 | DSF0000906328, DSF0000952061, DSF0000952060
7 | X005 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/28/2022 | 11/29/2022 | 11/15/2022 | 3721 | 9384 | 9384 | DSF0001034608
7 | X005 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 11/15/2022 | 5/12/2023 | 2/15/2023 | 16744 | 37533 | 37533 | DSF0001034608
7 | X005 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/5/2023 | 6/3/2024 |  | 215817 | 199168 | 182941 | DSF0001034608
7 | X005 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/5/2023 | 6/3/2024 |  | 129296 | 123035 | 96543 | DSF0001034608
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | FY23 RESO A SBHC | Scope | Complete | 2/3/2023 | 6/5/2023 | 10/25/2023 | 0 | 27152 | 27152 | DSF0001036166
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | FY23 RESO A SBHC | Design | PNS | PNS | PNS | PNS | 19200 | 1977 | 1977 | DSF0001036166
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | FY23 RESO A SBHC | Construction | PNS | PNS | PNS | PNS | 281600 | 2024803 | 5738 | DSF0001036166
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | FY23 RESO A SBHC | CM,F&E | PNS | PNS | PNS | PNS | 19200 | 138055 | 2005 | DSF0001036166
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SBHC | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036167
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SBHC | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036167
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SBHC | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036167
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SBHC | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036167
7 | X005 | P.S. 5 - BRONX | SCA IEH | PO18-ABATE AND REPLACE 9 X 9 ACM TILES IN ROOM 320 APPROX. 450 SQ. FT | Construction | Complete | 9/13/2023 | IEH | 9/10/2024 | IEH | 0 | 0 | SCA0000072285
7 | X005 | P.S. 5 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/9/2024 | DIIR |  | DIIR | 220000 | 0 | DSF0001086686
7 | X005 | P.S. 5 - BRONX | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/25/2024 | DOER |  | DOER | 233598 | 0 | DSF0001033345
7 | X005 | P.S. 5 - BRONX | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113302
7 | X005 | P.S. 5 - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113303
7 | X005 | P.S. 5 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 11/17/2015 | DOES |  | DOES | 75200 | 0 | DSF0000793698
7 | X005 | P.S. 5 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 4/18/2022 | DOES |  | DOES | 235510 | 0 | DSF0001008718
7 | X005 | P.S. 5 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/21/2024 | DOES | 10/31/2024 | DOES | 65832 |  | DSF0001084699
7 | X005 | P.S. 5 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 2/27/2024 | DOES |  | DOES | 910908 | 0 | DSF0001112148
7 | X018 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 9/25/2018 | 8/29/2019 | 5/1/2019 | 25281 | 18071 | 18071 | DSF0000891034, DSF0000912508
7 | X018 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 5/1/2019 | 10/1/2019 | 5/16/2019 | 93087 | 76344 | 72407 | DSF0000891034, DSF0000912508
7 | X018 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/22/2019 | 4/16/2020 |  | 990715 | 1693228 | 1337479 | DSF0000891034, DSF0000912508
7 | X018 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 7/22/2019 | 4/16/2020 |  | 228349 | 471134 | 449015 | DSF0000891034, DSF0000912508
7 | X018 | P.S. 18 - BRONX | SCA CIP RESOA | FY17 RESO A ELECTRICAL UPGRADE | Scope | Complete | 9/14/2017 | 11/14/2017 | 10/17/2017 | 0 | 11544 | 11544 | DSF0000844860
7 | X018 | P.S. 18 - BRONX | SCA CIP RESOA | FY17 RESO A ELECTRICAL UPGRADE | Design | PNS | PNS | PNS | PNS | 10894 | 2589 | 2589 | DSF0000844860
7 | X018 | P.S. 18 - BRONX | SCA CIP RESOA | FY17 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | 159785 | 581141 | 0 | DSF0000844860
7 | X018 | P.S. 18 - BRONX | SCA CIP RESOA | FY17 RESO A ELECTRICAL UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 10894 | 39623 | 0 | DSF0000844860
7 | X018 | P.S. 18 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 408000 | 408000 | 408000 | DSF0001086696
7 | X018 | P.S. 18 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 5/27/2024 | DOES |  | DOES | 427462 | 0 | DSF0001112149
7 | X025 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/8/2023 | 12/8/2023 | 8/22/2023 | 4690 | 1788 | 1788 | DSF0001035054
7 | X025 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/22/2023 | 2/21/2024 | 11/29/2023 | 21105 | 7154 | 7154 | DSF0001035054
7 | X025 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 4/12/2024 | 2/5/2025 |  | 272020 | 249600 | 94340 | DSF0001035054
7 | X025 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 4/12/2024 | 2/5/2025 |  | 145615 | 127462 | 102661 | DSF0001035054
7 | X025 | P.S. 25 - BRONX | SCA IEH | PO18-TEST AND ABATE 9' X 9' FLOOR TILES IF POSITIVE IN THE KITCHEN WHERE OLD OVEN USED TO BE. | Construction | Complete | 8/13/2024 | IEH | 9/26/2024 | IEH | 0 | 0 | SCA0000073280
7 | X025 | P.S. 25 - BRONX | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 11/14/2022 | DOER | 4/20/2023 | DOER | 150652 | 119497 | DSF0001034026
7 | X025 | P.S. 25 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 328000 | 0 | DSF0001086699
7 | X025 | P.S. 25 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/1/2019 | DOES |  | DOES | 104860 | 0 | DSF0000891059
7 | X025 | P.S. 25 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/18/2024 | DOES | 9/4/2024 | DOES | 65832 | 15935 | DSF0001084478
7 | X025 | P.S. 25 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | Complete | 1/29/2024 | DOES | 9/1/2024 | DOES | 885356 | 50380 | DSF0001112150
7 | X027 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 11/6/2018 | 3/27/2019 | 2/26/2019 | 115360 | 98202 | 98202 | DSF0000883791, DSF0000883792, DSF0000883793
7 | X027 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 2/27/2019 | 7/29/2019 | 5/17/2019 | 454495 | 545700 | 409744 | DSF0000883791, DSF0000883792, DSF0000883793
7 | X027 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 7/22/2019 | 1/11/2021 |  | 7898289 | 8237654 | 7739907 | DSF0000883791, DSF0000883792, DSF0000883793
7 | X027 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/22/2019 | 1/11/2021 |  | 628661 | 996595 | 992230 | DSF0000883791, DSF0000883792, DSF0000883793
7 | X027 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 12/22/2020 | 4/22/2021 | 11/23/2021 | 76950 | 106298 | 106298 | DSF0001001489
7 | X027 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 11/29/2021 | 5/23/2022 | 8/16/2022 | 384750 | 377396 | 338042 | DSF0001001489
7 | X027 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 4/10/2023 | 3/9/2025 |  | 8656875 | 8898335 | 4053288 | DSF0001001489
7 | X027 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 4/10/2023 | 3/9/2025 |  | 538650 | 450226 | 440419 | DSF0001001489
7 | X027 | P.S. 277 - BRONX | SCA CIP | RETAINING WALL | Scope | Complete | 2/23/2022 | 5/23/2022 | 3/29/2022 | 8577 | 0 | 0 | DSF0001028608
7 | X027 | P.S. 277 - BRONX | SCA CIP | RETAINING WALL | Design | Complete | 3/29/2022 | 3/29/2022 | 3/29/2022 | 38597 | 0 | 0 | DSF0001028608
7 | X027 | P.S. 277 - BRONX | SCA CIP | RETAINING WALL | Construction | PNS | PNS | PNS | PNS | 497468 | 1248276 | 1055023 | DSF0001028608
7 | X027 | P.S. 277 - BRONX | SCA CIP | RETAINING WALL | CM,F&E | PNS | PNS | PNS | PNS | 92203 | 92203 | 31133 | DSF0001028608
7 | X027 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/18/2020 | 12/18/2020 | 8/21/2020 | 5200 | 3694 | 3694 | DSF0000960792
7 | X027 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/21/2020 | 2/17/2021 | 5/26/2021 | 23400 | 14777 | 14777 | DSF0000960792
7 | X027 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/29/2022 | 4/24/2023 |  | 301600 | 287411 | 240608 | DSF0000960792
7 | X027 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/29/2022 | 4/24/2023 |  | 187128 | 178379 | 176811 | DSF0000960792
7 | X027 | P.S. 277 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/29/2021 | FTK |  | FTK | 49670 | 48792 | DSF0000961566
7 | X027 | P.S. 277 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033399
7 | X027 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | Complete | 7/20/2023 | DOER | 11/19/2023 | DOER | 129994 |  | DSF0001034136
7 | X027 | P.S. 277 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | Complete | 8/28/2024 | DOES | 9/1/2024 | DOES | 161854 |  | DSF0001112152
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113314
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113314
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001113314
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113314
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113685
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113685
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113685
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113685
7 | X029 | P.S. 29 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 159619 | 0 | DSF0001086702
7 | X029 | P.S. 29 - BRONX | DOE - Skilled Trades | ACE BOILER BURNER CONVERSION | Construction | In-Progress | 8/8/2022 | DOES |  | DOES | 2261921 | 0 | DSF0000912466
7 | X029 | P.S. 29 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/5/2024 | DOES | 8/13/2024 | DOES | 65832 | 5865 | DSF0001084703
7 | X029 | P.S. 29 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 8/28/2024 | DOES |  | DOES | 341779 | 0 | DSF0001112153
7 | X030 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 6/4/2021 | 10/20/2021 | 12/7/2021 | 96300 | 137083 | 137083 | DSF0001028656, DSF0001028654, DSF0001028655
7 | X030 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 12/8/2021 | 5/11/2022 | 5/12/2022 | 481500 | 421066 | 421066 | DSF0001028656, DSF0001028654, DSF0001028655
7 | X030 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 8/15/2022 | 8/13/2024 |  | 10833750 | 10052030 | 7456268 | DSF0001028656, DSF0001028654, DSF0001028655
7 | X030 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 8/15/2022 | 8/13/2024 |  | 675329 | 478441 | 478227 | DSF0001028656, DSF0001028654, DSF0001028655
7 | X030 | P.S. 30 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 224159 | 0 | DSF0000794103
7 | X030 | P.S. 30 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/26/2024 | DOES | 7/8/2024 | DOES | 65832 | 5942 | DSF0001085048
7 | X040 | P.S. 179 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/5/2024 | DIIR | 11/7/2024 | DIIR | 149474 | 149474 | DSF0001033381
7 | X040 | YOUNG LEADERS ELEM - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 8/12/2024 | DIIR | 300000 | 300000 | DSF0001036190
7 | X040 | YOUNG LEADERS ELEM - BRONX | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/1/2021 | DOER |  | DOER | 19410 | 0 | DSF0000913482
7 | X040 | P.S. 179 - BRONX | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113317
7 | X040 | P.S. 179 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/4/2022 | DOES |  | DOES | 206922 | 0 | DSF0001008720
7 | X040 | P.S. 179 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 5/27/2024 | DOES |  | DOES | 893681 | 0 | DSF0001112157
7 | X043 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | Scope | Complete | 10/27/2015 | 2/16/2017 | 2/27/2017 | 331508 | 452076 | 452076 | DSF0000817455, DSF0000839445, DSF0000861382, DSF0000861385, DSF0000861379, DSF0000861387
7 | X043 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | Design | Complete | 4/26/2017 | 9/26/2017 | 4/20/2018 | 1318825 | 1455085 | 1186583 | DSF0000817455, DSF0000839445, DSF0000861382, DSF0000861385, DSF0000861379, DSF0000861387
7 | X043 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | Construction | In-Progress | 7/9/2018 | 9/5/2020 |  | 24081321 | 29939002 | 22856734 | DSF0000817455, DSF0000839445, DSF0000861382, DSF0000861385, DSF0000861379, DSF0000861387
7 | X043 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | CM,F&E | In-Progress | 7/9/2018 | 9/5/2020 |  | 1682970 | 3592637 | 3306608 | DSF0000817455, DSF0000839445, DSF0000861382, DSF0000861385, DSF0000861379, DSF0000861387
7 | X043 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/29/2022 | 8/29/2022 | 8/25/2022 | 4663 | 7401 | 7401 | DSF0001034638
7 | X043 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/25/2022 | 2/24/2023 | 2/15/2023 | 20982 | 29602 | 29602 | DSF0001034638
7 | X043 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/5/2023 | 6/3/2024 |  | 270432 | 247372 | 228695 | DSF0001034638
7 | X043 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/5/2023 | 6/3/2024 |  | 174742 | 158618 | 121265 | DSF0001034638
7 | X043 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | Scope | Complete | 5/29/2019 | 8/19/2021 | 7/12/2021 | 170880 | 149317 | 148819 | DSF0000912340, DSF0001001702
7 | X043 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | Design | Complete | 10/20/2021 | 4/11/2022 | 3/20/2023 | 854400 | 546880 | 456689 | DSF0000912340, DSF0001001702
7 | X043 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | Construction | In-Progress | 8/14/2023 | 8/2/2025 |  | 19224000 | 17956405 | 5707148 | DSF0000912340, DSF0001001702
7 | X043 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | CM,F&E | In-Progress | 8/14/2023 | 8/2/2025 |  | 1196160 | 404095 | 402433 | DSF0000912340, DSF0001001702
7 | X043 | X017 SPED - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 50000 | 50000 | 0 | DSF0001036193
7 | X043 | P.S. 43 - BRONX | Fast Track Projects | FY20 RESO A LIBRARY UPGRADE | Construction | Complete | 8/31/2023 | FTK | 8/1/2024 | FTK | 255839 | 171647 | DSF0000913161
7 | X043 | X017 SPED - BRONX | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | Complete | 4/4/2023 | DOER | 5/23/2024 | DOER | 190341 | 1028 | DSF0000890720
7 | X043 | P.S. 43 - BRONX | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/1/2021 | DOER |  | DOER | 29020 | 0 | DSF0000913484
7 | X043 | X017 SPED - BRONX | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/20/2023 | DOER |  | DOER | 303494 | 0 | DSF0000913485
7 | X049 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 3/23/2021 | 8/5/2021 | 1/27/2022 | 161224 | 147328 | 147328 | DSF0000961145, DSF0001028945
7 | X049 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 5/27/2022 | 12/1/2022 | 5/12/2023 | 801894 | 676158 | 598973 | DSF0000961145, DSF0001028945
7 | X049 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 7/10/2023 | 8/7/2025 |  | 17677282 | 16155459 | 2875917 | DSF0000961145, DSF0001028945
7 | X049 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 7/10/2023 | 8/7/2025 |  | 1160238 | 743690 | 728244 | DSF0000961145, DSF0001028945
7 | X049 | P.S. 49 - BRONX | SCA Furniture & Equipment | FY23 RESO A AUDITORIUM UPGRADE | F&E | In-Progress | 11/18/2024 |  |  | 188000 | 188000 | 0 | DSF0001036194
7 | X049 | P.S. 49 - BRONX | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 188000 | 0 | DSF0001085188
7 | X049 | P.S. 49 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 188469 | 0 | DSF0001086708
7 | X065 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 8/5/2020 | 12/4/2020 | 7/2/2021 | 44200 | 22516 | 20065 | DSF0000961082
7 | X065 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 7/7/2021 | 12/8/2021 | 12/22/2021 | 221000 | 233602 | 160429 | DSF0000961082
7 | X065 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 7/15/2024 | 5/15/2026 |  | 4972500 | 4879108 | 403633 | DSF0000961082
7 | X065 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 7/15/2024 | 5/15/2026 |  | 309400 | 60496 | 60496 | DSF0000961082
7 | X065 | P.S. 65 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/11/2024 | 1/14/2025 | 9/18/2024 | 4093 | 1628 | 1628 | DSF0001087566
7 | X065 | P.S. 65 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 9/18/2024 | 3/19/2025 |  | 18417 | 18417 | 6513 | DSF0001087566
7 | X065 | P.S. 65 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 237372 | 237372 | 0 | DSF0001087566
7 | X065 | P.S. 65 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 43996 | 43996 | 4637 | DSF0001087566
7 | X065 | P.S. 65 - BRONX | SCA IEH | PO18-ROOM 118 CUSTODIAN'S OFFICE, ABATE 3 L.F. PIPE INSULATION MARKED BLUE ROOM 251 OFFICE, ABATE 30 | Construction | Complete | 7/1/2024 | IEH | 9/11/2024 | IEH | 0 | 0 | SCA0000073111
7 | X065 | P.S. 65 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 4/2/2024 | DOES |  | DOES | 346372 | 0 | DSF0001112159
7 | X139 | I.S. 224 - BRONX | SCA IEH | PO18-ABATE VALVES SPRAYED RED FOR ID TO COMPLETE PLUMBING REPAIRS SPACE ID#1028, 3/4' ROOT WATER VAL | Construction | Complete | 10/17/2024 | IEH | 10/27/2024 | IEH | 0 | 0 | SCA0000073516
7 | X139 | I.S. 224 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/14/2024 | DIIR | 8/23/2024 | DIIR | 288000 | 116098 | DSF0001086767
7 | X139 | I.S. 343 - BRONX | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/12/2023 | DOER |  | DOER | 235275 | 0 | DSF0000913167
7 | X139 | I.S. 343 - BRONX | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/22/2023 | DOER |  | DOER | 237455 | 0 | DSF0001036251
7 | X139 | I.S. 224 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/11/2024 | DOES |  | DOES | 674064 | 0 | DSF0001111641
7 | X139 | I.S. 224 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 6/14/2024 | DOES |  | DOES | 737143 | 0 | DSF0001112161
7 | X149 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | Scope | Complete | 8/12/2020 | 1/15/2021 | 12/4/2020 | 75640 | 117117 | 117117 | DSF0000961024, DSF0000954449, DSF0001003581
7 | X149 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | Design | Complete | 12/7/2020 | 5/10/2021 | 3/17/2021 | 378200 | 471846 | 449118 | DSF0000961024, DSF0000954449, DSF0001003581
7 | X149 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | Construction | In-Progress | 5/23/2022 | 5/21/2024 |  | 8509501 | 7803521 | 6916453 | DSF0000961024, DSF0000954449, DSF0001003581
7 | X149 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | CM,F&E | In-Progress | 5/23/2022 | 5/21/2024 |  | 529480 | 476523 | 475201 | DSF0000961024, DSF0000954449, DSF0001003581
7 | X149 | I.S. 221 - BRONX | SCA IEH | PO18-ABATE PIPE INSULATION ROOMS - BASEMENT GIRLS LOCKER ROOM(SPACE ID-1021), TOILET IN 107, 115, 21 | Construction | Complete | 7/25/2024 | IEH | 9/13/2024 | IEH | 0 | 0 | SCA0000073178
7 | X149 | I.S. 221 - BRONX | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/25/2019 | FTK |  | FTK | 74638 | 73454 | DSF0000912326
7 | X149 | THE LABORATORY SCHOOL OF FINANCE AND TECHNOLOGY: X223 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 95000 | 0 | DSF0001034085
7 | X149 | I.S. 221 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/8/2024 | DOES |  | DOES | 588718 | 0 | DSF0001085774
7 | X149 | I.S. 221 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 2/6/2024 | DOES |  | DOES | 792811 | 0 | DSF0001112124
7 | X151 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/12/2021 | 7/12/2021 | 3/25/2021 | 4700 | 6857 | 6857 | DSF0000960756
7 | X151 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/25/2021 | 8/17/2021 | 8/25/2021 | 21150 | 27499 | 27499 | DSF0000960756
7 | X151 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/29/2022 | 4/24/2023 |  | 272600 | 248269 | 218053 | DSF0000960756
7 | X151 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/29/2022 | 4/24/2023 |  | 265097 | 255831 | 178334 | DSF0000960756
7 | X151 | P.S. 31 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113383
7 | X151 | P.S. 31 - BRONX | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 11/9/2022 | DOER |  | DOER | 211775 | 0 | DSF0000961499
7 | X151 | P.S. 31 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/14/2024 | DOES |  | DOES | 523834 | 0 | DSF0001085775
7 | X154 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 7/25/2018 | 12/11/2018 | 9/23/2019 | 97962 | 137785 | 137785 | DSF0000889382, DSF0000954548
7 | X154 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 11/6/2019 | 4/27/2020 | 6/30/2020 | 481290 | 466884 | 451774 | DSF0000889382, DSF0000954548
7 | X154 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | Complete | 8/16/2021 | 5/17/2023 | 10/30/2024 | 10091829 | 10071175 | 9050209 | DSF0000889382, DSF0000954548
7 | X154 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | Complete | 8/16/2021 | 5/17/2023 | 10/30/2024 | 749657 | 1069785 | 1053262 | DSF0000889382, DSF0000954548
7 | X154 | P.S. 154 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/24/2024 | 1/28/2025 | 10/2/2024 | 7550 | 1457 | 1457 | DSF0001087587
7 | X154 | P.S. 154 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 10/2/2024 | 4/2/2025 |  | 33975 | 33975 | 5827 | DSF0001087587
7 | X154 | P.S. 154 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 437895 | 437895 | 0 | DSF0001087587
7 | X154 | P.S. 154 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 81162 | 81162 | 0 | DSF0001087587
7 | X154 | P.S. 154 - BRONX | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/22/2023 | 6/21/2023 | 7/3/2023 | 0 | 33467 | 33467 | DSF0001007867
7 | X154 | P.S. 154 - BRONX | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 7/19/2023 | 12/20/2023 | 1/22/2024 | 56764 | 110097 | 102407 | DSF0001007867
7 | X154 | P.S. 154 - BRONX | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 832541 | 832541 | 42217 | DSF0001007867
7 | X154 | P.S. 154 - BRONX | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 161411 | 125951 | 102263 | DSF0001007867
7 | X154 | P.S. 154 - BRONX | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 148338 | 0 | DSF0000819504
7 | X155 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/15/2023 | 12/14/2023 | 10/25/2023 | 135892 | 99950 | 98741 | DSF0001081649, DSF0001111761, DSF0001111762
7 | X155 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 11/6/2023 | 6/28/2024 | 4/4/2024 | 679460 | 243755 | 243755 | DSF0001081649, DSF0001111761, DSF0001111762
7 | X155 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 9/16/2024 | 11/4/2026 |  | 15287850 | 13849633 | 118541 | DSF0001081649, DSF0001111761, DSF0001111762
7 | X155 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 9/16/2024 | 11/4/2026 |  | 951243 | 85368 | 85007 | DSF0001081649, DSF0001111761, DSF0001111762
7 | X155 | P.S. 754 SPED - BRONX | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 3/12/2021 | DOER |  | DOER | 311942 | 0 | DSF0000913701
7 | X155 | P.S. 754 SPED - BRONX | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 3/14/2024 | DOES |  | DOES | 156771 | 0 | DSF0000819523
7 | X155 | P.S. 754 SPED - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/6/2022 | DOES |  | DOES | 206250 | 0 | DSF0001034471
7 | X155 | P.S. 754 SPED - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/25/2023 | DOES | 10/16/2023 | DOES | 542190 | 195342 | DSF0001035169
7 | X155 | P.S. 754 SPED - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/18/2024 | DOES | 11/26/2024 | DOES | 65832 | 5950 | DSF0001084712
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/3/2024 | 9/4/2024 | 5/13/2024 | 5477 | 732 | 732 | DSF0001087588
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/13/2024 | 3/12/2025 | 9/17/2024 | 24648 | 2927 | 2927 | DSF0001087588
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 317689 | 317689 | 15663 | DSF0001087588
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 63146 | 63146 | 7229 | DSF0001087588
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/3/2024 | DIIR |  | DIIR | 100000 | 0 | DSF0001086781
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/8/2024 | DOES | 11/25/2024 | DOES | 65832 | 11976 | DSF0001084713
7 | X157 | P.S. 157 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/19/2024 | 8/20/2024 | 4/23/2024 | 4663 | 453 | 453 | DSF0001087589
7 | X157 | P.S. 157 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/23/2024 | 10/18/2024 | 9/17/2024 | 20982 | 1812 | 1812 | DSF0001087589
7 | X157 | P.S. 157 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 270428 | 270428 | 2412 | DSF0001087589
7 | X157 | P.S. 157 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 54387 | 54387 | 8602 | DSF0001087589
7 | X161 | P.S. 161 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 1/12/2023 | 5/30/2023 | 12/6/2023 | 30756 | 102144 | 102111 | DSF0001109699, DSF0001109700
7 | X161 | P.S. 161 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/8/2023 | 5/10/2024 | 5/14/2024 | 153783 | 147065 | 140133 | DSF0001109699, DSF0001109700
7 | X161 | P.S. 161 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 3460110 | 3460110 | 3336 | DSF0001109699, DSF0001109700
7 | X161 | P.S. 161 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 215295 | 215295 | 13391 | DSF0001109699, DSF0001109700
7 | X161 | X017 SPED - BRONX | SCA CIP | ELECTRICAL SERVICE UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Scope | Complete | 8/30/2024 | 1/31/2025 | 10/24/2024 | 367251 | 97927 | 79228 | DSF0001112390, DSF0001112389, DSF0001113804
7 | X161 | X017 SPED - BRONX | SCA CIP | ELECTRICAL SERVICE UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Design | In-Progress | 10/24/2024 | 4/28/2025 |  | 1713837 | 1713837 | 267328 | DSF0001112390, DSF0001112389, DSF0001113804
7 | X161 | X017 SPED - BRONX | SCA CIP | ELECTRICAL SERVICE UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Construction | PNS | PNS | PNS | PNS | 27176558 | 27176558 | 796 | DSF0001112390, DSF0001112389, DSF0001113804
7 | X161 | X017 SPED - BRONX | SCA CIP | ELECTRICAL SERVICE UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 2693172 | 2693172 | 39783 | DSF0001112390, DSF0001112389, DSF0001113804
7 | X161 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/31/2022 | 1/4/2023 | 11/15/2022 | 3596 | 9540 | 9540 | DSF0001034610
7 | X161 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 11/15/2022 | 5/12/2023 | 2/15/2023 | 16184 | 38160 | 38160 | DSF0001034610
7 | X161 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/5/2023 | 6/3/2024 |  | 208591 | 192224 | 177327 | DSF0001034610
7 | X161 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/5/2023 | 6/3/2024 |  | 149998 | 153477 | 111733 | DSF0001034610
7 | X161 | P.S. 161 - BRONX | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 1/12/2023 | 5/30/2023 | 12/6/2023 | 71302 | 71302 | 71296 | DSF0001031015
7 | X161 | P.S. 161 - BRONX | SCA CIP | ROOF REPLACEMENT | Design | Complete | 12/8/2023 | 5/10/2024 | 5/14/2024 | 47303 | 47303 | 45275 | DSF0001031015
7 | X161 | P.S. 161 - BRONX | SCA CIP | ROOF REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 9137 | 9137 | 9113 | DSF0001031015
7 | X161 | P.S. 161 - BRONX | SCA CIP | ROOF REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 23641 | 23641 | 23641 | DSF0001031015
7 | X161 | P.S. 161 - BRONX | SCA IEH | PO18-ABATE FLOOR IN CAFETERIA | Construction | Complete | 7/26/2024 | IEH | 9/13/2024 | IEH | 0 | 0 | SCA0000073181
7 | X161 | SOUTH BRONX LITERACY ACADEMY | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113388
7 | X161 | P.S. 161 - BRONX | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001113386
7 | X161 | P.S. 161 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 149129 | 0 | DSF0000799873
7 | X161 | P.S. 161 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 6/14/2024 | DOES |  | DOES | 567206 | 0 | DSF0001112126
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/11/2022 | 11/25/2022 | 11/22/2023 | 52640 | 209563 | 209563 | DSF0001031035, DSF0001031036
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/28/2023 | 4/30/2024 | 5/2/2024 | 263200 | 411674 | 318903 | DSF0001031035, DSF0001031036
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 9/9/2024 | 8/9/2026 |  | 5922000 | 5434432 | 111792 | DSF0001031035, DSF0001031036
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/9/2024 | 8/9/2026 |  | 368480 | 60978 | 60869 | DSF0001031035, DSF0001031036
7 | X162 | I.S. 584 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 8/1/2024 | DIIR | 99649 | 99649 | DSF0001033441
7 | X162 | I.S. 162 - BRONX | DOE - Skilled Trades | GYMNASIUM UPGRADE | Construction | In-Progress | 7/24/2017 | DOES |  | DOES | 136414 | 0 | DSF0000863476
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 3/30/2023 | DOES |  | DOES | 233473 | 0 | SCA0000070999
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/27/2024 | DOES | 10/8/2024 | DOES | 65832 | 5950 | DSF0001084866
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 5/27/2024 | DOES |  | DOES | 808609 | 0 | DSF0001112127
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 7/6/2023 | 11/6/2023 | 10/25/2023 | 11900 | 16395 | 16395 | DSF0001083808
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/1/2023 | 4/1/2024 | 4/12/2024 | 53550 | 105727 | 52542 | DSF0001083808
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/12/2024 | 9/11/2025 |  | 690200 | 620808 | 14808 | DSF0001083808
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/12/2024 | 9/11/2025 |  | 127925 | 78516 | 14256 | DSF0001083808
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 377804 | 0 | DSF0000960362
7 | X183 | SUCCESS ACADEMY CHARTER SCHOOL - BRONX 1 | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/24/2023 | DOES | 12/28/2023 | DOES | 508513 | 497620 | DSF0001035149
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | DOE - Skilled Trades | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 2/20/2024 | DOES |  | DOES | 128769 | 0 | DSF0001111900
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | DOE - Skilled Trades | CHARTER MATCH INTERIOR SPACES | Construction | In-Progress | 11/13/2023 | DOES |  | DOES | 275173 | 0 | DSF0001110017
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 4/7/2021 | 8/20/2021 | 9/2/2021 | 44214 | 177921 | 175150 | DSF0000954961, DSF0000954963, DSF0000954964
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/15/2021 | 2/18/2022 | 5/5/2022 | 216529 | 258283 | 253006 | DSF0000954961, DSF0000954963, DSF0000954964
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Construction | Complete | 7/11/2022 | 1/1/2024 | 10/4/2024 | 4479323 | 4265074 | 4014063 | DSF0000954961, DSF0000954963, DSF0000954964
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 7/11/2022 | 1/1/2024 | 10/4/2024 | 343538 | 431688 | 423178 | DSF0000954961, DSF0000954963, DSF0000954964
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/11/2020 | 7/9/2020 | 6/4/2020 | 3546 | 3557 | 3557 | DSF0000960761
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/4/2020 | 12/1/2020 | 12/1/2020 | 15956 | 14226 | 14226 | DSF0000960761
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 7/18/2022 | 5/13/2023 |  | 205654 | 188832 | 178893 | DSF0000960761
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 7/18/2022 | 5/13/2023 |  | 194321 | 222707 | 217804 | DSF0000960761
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | SCIENCE LAB UPGRADE / PATH OF TRAVEL SCIENCE LAB UPGRADE | Scope | Complete | 3/5/2024 | 9/5/2024 | 7/2/2024 | 26193 | 43349 | 3862 | DSF0001110055, DSF0001112231
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | SCIENCE LAB UPGRADE / PATH OF TRAVEL SCIENCE LAB UPGRADE | Design | Complete | 8/5/2024 | 12/4/2024 | 10/15/2024 | 120142 | 84305 | 15447 | DSF0001110055, DSF0001112231
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | SCIENCE LAB UPGRADE / PATH OF TRAVEL SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 1886511 | 1886511 | 1966 | DSF0001110055, DSF0001112231
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | SCIENCE LAB UPGRADE / PATH OF TRAVEL SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 215351 | 215351 | 31057 | DSF0001110055, DSF0001112231
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA IEH | PO18-ABATEMENT & HOLES DRILLED FOR PLUMBING. ROOM #227 | Construction | Complete | 7/8/2024 | IEH | 9/16/2024 | IEH | 0 | 0 | SCA0000073121
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 250000 | 250000 | 0 | DSF0001113393
7 | X184 | I.S. 296 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/21/2024 | DIIR | 10/31/2024 | DIIR | 99649 | 99649 | DSF0001033404
7 | X184 | I.S. 298 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 2/21/2024 | DIIR |  | DIIR | 250000 | 0 | DSF0001036275
7 | X184 | I.S. 296 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/16/2024 | DIIR |  | DIIR | 300000 | 0 | DSF0001086797
7 | X184 | X017 SPED - BRONX | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | Complete | 10/7/2022 | DOER | 7/19/2023 | DOER | 150766 | 58116 | DSF0000890951
7 | X184 | I.S. 296 - BRONX | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/22/2023 | DOER |  | DOER | 391883 | 0 | DSF0001034092
7 | X184 | X017 SPED - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 305565 | 0 | DSF0001086798
7 | X184 | I.S. 298 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086799
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086800
7 | X184 | I.S. 296 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 1/4/2021 | DOES |  | DOES | 157393 | 0 | DSF0000886351
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/4/2024 | DOES |  | DOES | 556294 | 0 | DSF0001111654
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 3/8/2024 | DOES |  | DOES | 549675 | 402309 | DSF0001112049
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 6/14/2024 | DOES |  | DOES | 1182773 | 0 | DSF0001112129
7 | X354 | LEARNING THROUGH PLAY PRE-K CENTER | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LABS | F&E | Complete | 5/30/2024 |  | 7/10/2024 | 65000 | 65000 | 65000 | DSF0001033433
7 | X354 | LEARNING THROUGH PLAY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/13/2024 | DOES | 10/9/2024 | DOES | 50832 |  | DSF0001085565
7 | X356 | LEARNING THROUGH PLAY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/27/2023 | DOES |  | DOES | 50832 | 0 | DSF0001085566
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | Scope | Complete | 11/7/2018 | 9/9/2021 | 12/15/2021 | 89549 | 241569 | 241569 | DSF0000889643, DSF0000960593, DSF0000955453, DSF0001032102
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | Design | Complete | 12/17/2021 | 5/20/2022 | 2/15/2023 | 409361 | 599576 | 550930 | DSF0000889643, DSF0000960593, DSF0000955453, DSF0001032102
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 6/20/2023 | 5/19/2025 |  | 8279391 | 7888707 | 4698321 | DSF0000889643, DSF0000960593, DSF0000955453, DSF0001032102
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 6/20/2023 | 5/19/2025 |  | 586171 | 450839 | 409925 | DSF0000889643, DSF0000960593, DSF0000955453, DSF0001032102
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 200000 | 200000 | 0 | DSF0001035309
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 250000 | 250000 | 0 | DSF0001113425
7 | X470 | MOTT HAVEN VILLAGE PREP - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 159376 | 0 | DSF0000960435
7 | X470 | CAREERS IN SPORTS HIGH SCHOOL - BRONX | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086846
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 11/21/2022 | DOES | 3/13/2024 | DOES | 613615 | 608201 | DSF0000960876
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 11/11/2022 | DOES |  | DOES | 128988 | 0 | DSF0001034474
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/26/2024 | DOES | 10/4/2024 | DOES | 65832 | 10795 | DSF0001085083
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | STRUCTURAL CONCRETE FAILURE @ X600 | Scope | Complete | 8/5/2022 | 12/22/2022 | 12/14/2022 | 15977 | 12959 | 12959 | DSF0001083832
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | STRUCTURAL CONCRETE FAILURE @ X600 | Design | Complete | 12/23/2022 | 5/26/2023 | 8/2/2023 | 71898 | 48834 | 3914 | DSF0001083832
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | STRUCTURAL CONCRETE FAILURE @ X600 | Construction | In-Progress | 12/12/2024 | 3/11/2026 |  | 926683 | 810075 | 0 | DSF0001083832
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | STRUCTURAL CONCRETE FAILURE @ X600 | CM,F&E | In-Progress | 12/12/2024 | 3/11/2026 |  | 171756 | 92241 | 5964 | DSF0001083832
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/9/2020 | 7/7/2020 | 6/4/2020 | 3806 | 3584 | 3584 | DSF0000960764
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/4/2020 | 12/1/2020 | 12/1/2020 | 17128 | 14336 | 14336 | DSF0000960764
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 7/18/2022 | 5/13/2023 |  | 220758 | 203161 | 186333 | DSF0000960764
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 7/18/2022 | 5/13/2023 |  | 223156 | 258213 | 249833 | DSF0000960764
7 | X600 | ALFRED E. SMITH HS - X | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 9/15/2023 | DOER |  | DOER | 271547 | 2796 | DSF0001086850
7 | X600 | BRONX DESIGN AND CONSTRUCTION ACADEMY - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 12/20/2023 | DOER |  | DOER | 100000 | 0 | DSF0001086851
7 | X600 | ALFRED E. SMITH HS - X | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 8/31/2015 | DOES |  | DOES | 75200 | 0 | DSF0000797255
7 | X600 | ALFRED E. SMITH HS - X | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/11/2024 | DOES | 11/25/2024 | DOES | 65832 | 7316 | DSF0001085085
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | Scope | Complete | 9/7/2018 | 2/6/2019 | 11/26/2018 | 43770 | 26073 | 26073 | DSF0000890619
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | Design | Complete | 12/5/2018 | 5/29/2019 | 5/17/2019 | 175080 | 262672 | 123140 | DSF0000890619
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | Construction | In-Progress | 8/5/2019 | 8/3/2020 |  | 3282750 | 3200785 | 2894174 | DSF0000890619
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | CM,F&E | In-Progress | 8/5/2019 | 8/3/2020 |  | 289590 | 1142834 | 1133790 | DSF0000890619
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | Scope | Complete | 2/10/2020 | 7/7/2020 | 5/3/2021 | 37750 | 60357 | 60357 | DSF0000955547, DSF0000955554
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | Design | Complete | 5/10/2021 | 10/26/2021 | 5/13/2022 | 188750 | 284485 | 246758 | DSF0000955547, DSF0000955554
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | Construction | In-Progress | 8/11/2022 | 2/1/2024 |  | 4246876 | 3939052 | 2367745 | DSF0000955547, DSF0000955554
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | CM,F&E | In-Progress | 8/11/2022 | 2/1/2024 |  | 264250 | 381268 | 376577 | DSF0000955547, DSF0000955554
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 9/1/2021 | DIIR |  | DIIR | 110000 | 0 | DSF0001009251
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 9/27/2024 | DOER |  | DOER | 112568 | 0 | DSF0000913174
7 | X655 | MOTT HAVEN COMMUNITY HIGH SCHOOL - BRONX | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 1/4/2021 | DOES |  | DOES | 226128 | 0 | DSF0000886914
7 | X790 | X188 SPED - BRONX | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/8/2021 | 2/14/2022 | 2/3/2022 | 26831 | 19849 | 19849 | SCA0000070755, DSF0001083781
7 | X790 | X188 SPED - BRONX | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 12/20/2022 | 5/8/2023 | 6/15/2023 | 129250 | 102038 | 90493 | SCA0000070755, DSF0001083781
7 | X790 | X188 SPED - BRONX | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 2483533 | 2483533 | 10401 | SCA0000070755, DSF0001083781
7 | X790 | X188 SPED - BRONX | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 224638 | 224638 | 25707 | SCA0000070755, DSF0001083781
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | SCA CIP | EXTERIOR FACADE @ X790 | Scope | Complete | 4/8/2024 | 8/22/2024 | 10/8/2024 | 61233 | 72639 | 72639 | SCA0000072764
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | SCA CIP | EXTERIOR FACADE @ X790 | Design | In-Progress | 10/8/2024 | 3/14/2025 |  | 285755 | 285755 | 3499 | SCA0000072764
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | SCA CIP | EXTERIOR FACADE @ X790 | Construction | PNS | PNS | PNS | PNS | 4531254 | 4531254 | 0 | SCA0000072764
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | SCA CIP | EXTERIOR FACADE @ X790 | CM,F&E | PNS | PNS | PNS | PNS | 449043 | 449043 | 4866 | SCA0000072764
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | SCA Emergency Response | EMERGENCY- FAILING ALUMINUM SIDING @ X790 | Construction | In-Progress | 2/7/2024 | EMER |  | EMER | 277202 | 41227 | SCA0000072720
7 | X790 | BRONX LEGACY HIGH SCHOOL | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 125000 | DSF0001086854
7 | X790 | X188 SPED - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 3/7/2024 | DIIR | 166000 | 166000 | DSF0001007952
7 | X790 | X188 SPED - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001113432
7 | X790 | X188 SPED - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113433
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | DOE - Skilled Trades | ACE BMS UPGRADE | Construction | In-Progress | 2/28/2023 | DOES |  | DOES | 1554000 | 0 | DSF0001083016
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/15/2024 | DOES | 8/14/2024 | DOES | 50832 |  | DSF0001085089
7 | X807 | DOE ADMINISTRATIVE OFFICE - BRONX | SCA CIP | SITE WALLS | Scope | Complete | 5/7/2024 | 9/23/2024 | 10/8/2024 | 12948 | 26929 | 26929 | SCA0000072929
7 | X807 | DOE ADMINISTRATIVE OFFICE - BRONX | SCA CIP | SITE WALLS | Design | In-Progress | 10/8/2024 | 3/14/2025 |  | 58267 | 58267 | 26497 | SCA0000072929
7 | X807 | DOE ADMINISTRATIVE OFFICE - BRONX | SCA CIP | SITE WALLS | Construction | PNS | PNS | PNS | PNS | 750997 | 750997 | 0 | SCA0000072929
7 | X807 | DOE ADMINISTRATIVE OFFICE - BRONX | SCA CIP | SITE WALLS | CM,F&E | PNS | PNS | PNS | PNS | 139193 | 139193 | 8542 | SCA0000072929
7 | X807 | DOE ADMINISTRATIVE OFFICE - BRONX | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 12/1/2023 | DOER |  | DOER | 95568 | 0 | DSF0000913519
7 | X807 | DOE ADMINISTRATIVE OFFICE - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 314000 | 0 | DSF0001086855
7 | X855 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 10/23/2024 | IEH |  | IEH | 0 | 0 | SCA0000073528
7 | X855 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001034134
7 | X884 | HEALTH OPPORTUNITIES (HS LVL) - X | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 454000 | 454000 | 0 | DSF0001086863
7 | X884 | COMM HS FOR SOCIAL JUSTICE - X | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/13/2024 | DIIR |  | DIIR | 200000 | 0 | DSF0001034126
7 | X884 | COMM HS FOR SOCIAL JUSTICE - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086862
7 | X884 | COMM HS FOR SOCIAL JUSTICE - X | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113440
7 | X884 | HEALTH OPPORTUNITIES (HS LVL) - X | DOE - RESOA | FY15 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 56818 | 0 | DSF0000777446
7 | X884 | HEALTH OPPORTUNITIES (HS LVL) - X | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 6/12/2024 | DOER | 7/24/2024 | DOER | 139199 |  | DSF0001036307
7 | X897 | RESTART - CITYWIDE | SCA IEH | PO18-ABATE AND REPAIR AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT P | Construction | Complete | 5/22/2023 | IEH | 9/26/2024 | IEH | 0 | 0 | SCA0000072008
7 | XAGV | FAMILY LIFE ACADEMY CHARTER SCHOOL II - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35000 | 0 | DSF0000914235
7 | XAXQ | HEKETI COMMUNITY CHARTER SCHOOL - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35000 | 0 | DSF0000914236
7 | XBBX | STOREFRONT ACADEMY CHARTER SCHOOL | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 200000 | 200000 | 200000 | DSF0001086868
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Scope | In-Progress | 2/16/2023 | 5/17/2023 |  | 0 | 37899 | 15320 | DSF0001036171
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Design | PNS | PNS | PNS | PNS | 120000 | 82101 | 0 | DSF0001036171
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Construction | PNS | PNS | PNS | PNS | 1760000 | 1760000 | 0 | DSF0001036171
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001036171
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SCHOOLYARD UPGRADE | Scope | In-Progress | 2/14/2023 | 5/16/2023 |  | 0 | 0 | 0 | DSF0001036172
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SCHOOLYARD UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036172
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SCHOOLYARD UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036172
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SCHOOLYARD UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 62 | 62 | DSF0001036172
8 | X014 | P.S. 14 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001113306
8 | X014 | P.S. 14 - BRONX | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 490756 | 0 | DSF0001086692
8 | X014 | P.S. 14 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/31/2022 | DOES |  | DOES | 59477 | 0 | DSF0001034446
8 | X036 | P.S. 36 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 3/3/2021 | FTK |  | FTK | 10291 | 10291 | DSF0001008606
8 | X036 | P.S. 36 - BRONX | DOE - RESOA | FY14 RESO A TECHNOLOGY | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0000798766
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 9/21/2017 | 2/9/2018 | 12/19/2017 | 23694 | 29368 | 29176 | DSF0000864950
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | Design | Complete | 8/1/2018 | 1/4/2019 | 4/23/2019 | 94776 | 164322 | 152479 | DSF0000864950
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 7/15/2019 | 10/6/2020 |  | 1777049 | 1910651 | 1483237 | DSF0000864950
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 7/15/2019 | 10/6/2020 |  | 110572 | 358981 | 348142 | DSF0000864950
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | COVID VENTILATION | Scope | Complete | 1/5/2021 | 5/5/2021 | 9/15/2021 | 57262 | 107560 | 107560 | DSF0001006129
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | COVID VENTILATION | Design | Complete | 9/24/2021 | 2/24/2022 | 3/1/2022 | 286311 | 221462 | 210355 | DSF0001006129
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | COVID VENTILATION | Construction | PNS | PNS | PNS | PNS | 6442002 | 6442002 | 327986 | DSF0001006129
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | COVID VENTILATION | CM,F&E | PNS | PNS | PNS | PNS | 400836 | 400836 | 45908 | DSF0001006129
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113316
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001113316
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001113316
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001113316
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113686
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113686
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113686
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113686
8 | X039 | HOLCOMBE L. RUCKER SCHOOLOF COMMUNITY RESEARCH - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/25/2016 | 9/26/2016 | 8/25/2016 | 0 | 74597 | 74597 | DSF0000822346
8 | X039 | HOLCOMBE L. RUCKER SCHOOLOF COMMUNITY RESEARCH - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE | Design | Complete | 9/15/2016 | 3/9/2017 | 3/8/2017 | 38450 | 299050 | 298514 | DSF0000822346
8 | X039 | HOLCOMBE L. RUCKER SCHOOLOF COMMUNITY RESEARCH - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/21/2018 | 12/17/2018 |  | 563932 | 606760 | 538239 | DSF0000822346
8 | X039 | HOLCOMBE L. RUCKER SCHOOLOF COMMUNITY RESEARCH - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 6/21/2018 | 12/17/2018 |  | 38450 | 111305 | 104747 | DSF0000822346
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN ROOMS: RM: 105 APPROX. 610 SF RM: 206 APPROX. 287SF | Construction | Complete | 9/5/2023 | IEH | 8/26/2024 | IEH | 0 | 0 | SCA0000072269
8 | X039 | LONGWOOD PREPARATORY ACADEMY | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/27/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085050
8 | X039 | LONGWOOD PREPARATORY ACADEMY | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/17/2024 | DOES |  | DOES | 593106 | 0 | DSF0001085768
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Scope | Complete | 8/2/2022 | 12/5/2022 | 11/15/2022 | 0 | 13756 | 13756 | DSF0001034096
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 11/29/2022 | 4/17/2023 | 5/3/2023 | 90954 | 63582 | 56534 | DSF0001034096
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1333990 | 1333990 | 4587 | DSF0001034096
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90954 | 90954 | 26614 | DSF0001034096
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 1/15/2020 | 5/14/2020 | 1/30/2020 | 0 | 8025 | 8025 | DSF0000913488
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2/5/2020 | 7/30/2020 | 5/14/2020 | 27000 | 32440 | 32195 | DSF0000913488
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/9/2021 | 4/4/2022 |  | 396000 | 180665 | 159599 | DSF0000913488
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/9/2021 | 4/4/2022 |  | 186857 | 216102 | 191707 | DSF0000913488
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY21 RESO A STEM LAB / PATH OF TRAVEL RESO A STEM LAB | Scope | Complete | 6/9/2022 | 4/25/2023 | 3/22/2023 | 0 | 29545 | 29545 | DSF0000961509, DSF0001083866
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY21 RESO A STEM LAB / PATH OF TRAVEL RESO A STEM LAB | Design | Complete | 3/22/2023 | 7/25/2023 | 5/2/2023 | 48927 | 86478 | 84392 | DSF0000961509, DSF0001083866
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY21 RESO A STEM LAB / PATH OF TRAVEL RESO A STEM LAB | Construction | In-Progress | 12/22/2023 | 12/20/2024 |  | 717589 | 644813 | 112643 | DSF0000961509, DSF0001083866
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY21 RESO A STEM LAB / PATH OF TRAVEL RESO A STEM LAB | CM,F&E | In-Progress | 12/22/2023 | 12/20/2024 |  | 48927 | 80891 | 39934 | DSF0000961509, DSF0001083866
8 | X052 | I.S. 302 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 294752 | 0 | DSF0001086711
8 | X052 | I.S. 302 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084845
8 | X052 | I.S. 302 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/15/2024 | DOES |  | DOES | 617486 | 0 | DSF0001085769
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | FLOOD ELIMINATION / ROOFS | Scope | Complete | 1/9/2024 | 5/23/2024 | 8/13/2024 | 26981 | 84189 | 52728 | DSF0001107851, DSF0001113735
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | FLOOD ELIMINATION / ROOFS | Design | In-Progress | 9/6/2024 | 2/11/2025 |  | 121397 | 121397 | 6264 | DSF0001107851, DSF0001113735
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | FLOOD ELIMINATION / ROOFS | Construction | PNS | PNS | PNS | PNS | 1884896 | 1884896 | 15190 | DSF0001107851, DSF0001113735
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | FLOOD ELIMINATION / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 248052 | 248052 | 15717 | DSF0001107851, DSF0001113735
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/20/2024 | 10/21/2024 | 7/1/2024 | 7457 | 3327 | 3327 | DSF0001087564
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/1/2024 | 12/27/2024 | 12/26/2024 | 33557 | 13307 | 13307 | DSF0001087564
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 432513 | 432513 | 2356 | DSF0001087564
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 84428 | 84428 | 5259 | DSF0001087564
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 250000 | 250000 | 250000 | DSF0001086717
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 1/30/2020 | FTK |  | FTK | 48382 | 48382 | DSF0000912615
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 2/10/2023 | DOER |  | DOER | 163424 | 0 | DSF0001034108
8 | X062 | P.S. 62 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/18/2024 | 11/18/2024 | 7/23/2024 | 3908 | 2839 | 2839 | DSF0001087565
8 | X062 | P.S. 62 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/23/2024 | 1/21/2025 | 12/26/2024 | 17586 | 11357 | 11357 | DSF0001087565
8 | X062 | P.S. 62 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 226663 | 226663 | 2405 | DSF0001087565
8 | X062 | P.S. 62 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 46275 | 46275 | 5047 | DSF0001087565
8 | X062 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | Scope | Complete | 4/1/2021 | 9/22/2021 | 11/3/2021 | 185950 | 202971 | 202971 | DSF0001002011, DSF0001008820
8 | X062 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/10/2021 | 5/2/2022 | 8/9/2022 | 929750 | 722239 | 703779 | DSF0001002011, DSF0001008820
8 | X062 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 3/15/2023 | 3/13/2025 |  | 20919375 | 19267397 | 4681456 | DSF0001002011, DSF0001008820
8 | X062 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 3/15/2023 | 3/13/2025 |  | 1301650 | 187780 | 187003 | DSF0001002011, DSF0001008820
8 | X062 | P.S. 62 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 8/17/2020 | FTK |  | FTK | 246392 | 240464 | DSF0000912127, DSF0000912638
8 | X062 | P.S. 62 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 75200 | 0 | DSF0000794627
8 | X062 | P.S. 62 - BRONX | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 1/31/2022 | DOES | 8/16/2022 | DOES | 68599 | 67677 | DSF0001009012
8 | X069 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/19/2019 | 11/4/2019 | 11/1/2019 | 59740 | 140486 | 140212 | DSF0001034396, DSF0000960627
8 | X069 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | Design | Complete | 2/19/2020 | 7/20/2020 | 4/29/2022 | 298700 | 291444 | 290321 | DSF0001034396, DSF0000960627
8 | X069 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | Construction | Complete | 10/12/2022 | 7/2/2024 | 10/31/2024 | 6720750 | 6096564 | 5435556 | DSF0001034396, DSF0000960627
8 | X069 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | CM,F&E | Complete | 10/12/2022 | 7/2/2024 | 10/31/2024 | 425671 | 483194 | 482762 | DSF0001034396, DSF0000960627
8 | X069 | P.S. 69 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | Complete | 4/18/2019 | EMER | 9/5/2024 | EMER | 57663 | 57663 | SCA0000057328
8 | X069 | P.S. 69 - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001113327
8 | X071 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 7/29/2019 | 7/9/2021 | 11/24/2021 | 409144 | 532157 | 515968 | DSF0000961018, DSF0000912613, DSF0001008631, DSF0001008650, DSF0001009322, DSF0001029358, DSF0001029357, DSF0001029356, DSF0001029354
8 | X071 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 12/7/2021 | 5/10/2022 | 10/11/2022 | 2032006 | 1820987 | 1478577 | DSF0000961018, DSF0000912613, DSF0001008631, DSF0001008650, DSF0001009322, DSF0001029358, DSF0001029357, DSF0001029356, DSF0001029354
8 | X071 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 8/3/2023 | 8/2/2026 |  | 44534318 | 40623808 | 10249415 | DSF0000961018, DSF0000912613, DSF0001008631, DSF0001008650, DSF0001009322, DSF0001029358, DSF0001029357, DSF0001029356, DSF0001029354
8 | X071 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 8/3/2023 | 8/2/2026 |  | 2967754 | 630306 | 623967 | DSF0000961018, DSF0000912613, DSF0001008631, DSF0001008650, DSF0001009322, DSF0001029358, DSF0001029357, DSF0001029356, DSF0001029354
8 | X071 | P.S. 71 - BRONX | SCA IEH | PO18-CAFETERIA - ABATE 6' OF ACM PIPE INSULATION - MARKED RED FOR ID. | Construction | Complete | 7/23/2024 | IEH | 7/26/2024 | IEH | 0 | 0 | SCA0000073167
8 | X071 | P.S. 71 - BRONX | SCA IEH | PO18-SPACE ID: 2115C - NURSE'S OFFICE - ABATE BROKEN FLOOR TILES - 182 SF | Construction | Complete | 11/18/2024 | IEH | 12/27/2024 | IEH | 0 | 0 | SCA0000073616
8 | X071 | P.S. 71 - BRONX | DIIT - RESOA | FY 15 RESO A SECURITY CAMERAS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 244256 | 0 | DSF0000821678
8 | X071 | P.S. 71 - BRONX | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0000890950
8 | X071 | P.S. 71 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001086720
8 | X071 | P.S. 71 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/18/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084705
8 | X072 | P.S. 72 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 3/17/2022 | 8/1/2022 | 2/7/2023 | 92868 | 175030 | 164785 | DSF0001108096, DSF0001083886, DSF0001080118
8 | X072 | P.S. 72 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 5/17/2023 | 10/19/2023 | 5/13/2024 | 460223 | 342009 | 332465 | DSF0001108096, DSF0001083886, DSF0001080118
8 | X072 | P.S. 72 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Construction | PNS | PNS | PNS | PNS | 9998816 | 9998816 | 501636 | DSF0001108096, DSF0001083886, DSF0001080118
8 | X072 | P.S. 72 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 680963 | 680963 | 133618 | DSF0001108096, DSF0001083886, DSF0001080118
8 | X072 | P.S. 72 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/4/2022 | EMER |  | EMER |  | 0 | SCA0000070848
8 | X072 | P.S. 72 - BRONX | SCA IEH | PO18-ROOM 211, REPAIR 1 L.F. PIPE INSULATION ROOM 306, ABATE 2 SQ. FT. DAMAGE FLOOR TILE ROOM 308, A | Construction | Complete | 7/1/2024 | IEH | 10/15/2024 | IEH | 0 | 0 | SCA0000073106
8 | X072 | P.S. 72 - BRONX | SCA IEH | PO18-ABATE/REPLACE ACM 9X9 FLOOR TILES IN THE FOLLOWING ROOMS: 307,306,351,308,309,310,312,314 APPR | Construction | Complete | 7/30/2024 | IEH | 9/11/2024 | IEH | 0 | 0 | SCA0000073205
8 | X072 | P.S. 72 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/25/2019 | FTK |  | FTK | 205576 | 204038 | DSF0000868248, DSF0000912240
8 | X072 | P.S. 72 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | Complete | 10/31/2023 | DOER | 5/17/2024 | DOER | 149460 | 30390 | DSF0001008474
8 | X072 | P.S. 72 - BRONX | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001086721
8 | X074 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/19/2018 | 3/11/2019 | 10/3/2019 | 89717 | 163514 | 163513 | DSF0000884587, DSF0000884588, DSF0000884589, DSF0000884590
8 | X074 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/4/2019 | 5/6/2020 | 4/13/2021 | 433912 | 968626 | 740932 | DSF0000884587, DSF0000884588, DSF0000884589, DSF0000884590
8 | X074 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 7/13/2021 | 4/3/2023 |  | 8493945 | 15721539 | 11113446 | DSF0000884587, DSF0000884588, DSF0000884589, DSF0000884590
8 | X074 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/13/2021 | 4/3/2023 |  | 738053 | 932364 | 740085 | DSF0000884587, DSF0000884588, DSF0000884589, DSF0000884590
8 | X074 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 10/16/2020 | 2/19/2021 | 2/12/2021 | 3944 | 3962 | 3962 | DSF0000960749
8 | X074 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2/12/2021 | 8/9/2021 | 7/14/2021 | 17748 | 15849 | 15849 | DSF0000960749
8 | X074 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 7/29/2022 | 5/24/2023 |  | 228752 | 208950 | 180509 | DSF0000960749
8 | X074 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 7/29/2022 | 5/24/2023 |  | 243606 | 240198 | 159906 | DSF0000960749
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 8/3/2021 | 11/2/2021 | 1/7/2022 | 0 | 17793 | 17793 | DSF0001007951
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 1/10/2022 | 5/25/2022 | 5/10/2024 | 97500 | 90275 | 86664 | DSF0001007951
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1429996 | 1429996 | 5373 | DSF0001007951
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 97500 | 97500 | 8142 | DSF0001007951
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/24/2022 | 4/25/2022 | 3/22/2022 | 0 | 11732 | 11732 | DSF0001007954
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 3/22/2022 | 7/25/2022 | 5/10/2024 | 1960 | 22895 | 22890 | DSF0001007954
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 28747 | 28747 | 0 | DSF0001007954
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 1960 | 1960 | 569 | DSF0001007954
8 | X074 | I.S. 424 - BRONX | SCA IEH | PO18-ROOMS 328 & 330 ABATE RADIATOR INSULATION WALL RESET AND RADIATOR COVER TAR | Construction | Complete | 7/15/2024 | IEH | 8/12/2024 | IEH | 0 | 0 | SCA0000073133
8 | X074 | I.S. 424 - BRONX | SCA Furniture & Equipment | FY23 RESO A LOCKER ROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036210
8 | X074 | HYDE LEADERSHIP CHARTER SCHOOL - X | Fast Track Projects | LSP AUDITORIUM STAGE & SPOT LIGHTING | Construction | In-Progress | 9/20/2021 | FTK |  | FTK | 178172 | 165832 | DSF0000907439
8 | X074 | I.S. 424 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001036209
8 | X074 | I.S. 424 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1203975 | 0 | DSF0001007942
8 | X074 | I.S. 424 - BRONX | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 730572 | 0 | DSF0000912207
8 | X074 | I.S. 424 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/7/2023 | DOES |  | DOES | 426789 | 0 | DSF0001085770
8 | X075 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 10/24/2018 | 2/22/2019 | 4/8/2019 | 358164 | 319216 | 319216 | DSF0000961194, DSF0000907450, DSF0000907451, DSF0000907447, DSF0000912919
8 | X075 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | Complete | 8/7/2019 | 1/15/2020 | 6/30/2020 | 1790823 | 1074270 | 1071030 | DSF0000961194, DSF0000907450, DSF0000907451, DSF0000907447, DSF0000912919
8 | X075 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Construction | In-Progress | 8/2/2021 | 7/16/2024 |  | 40293507 | 36539320 | 23254881 | DSF0000961194, DSF0000907450, DSF0000907451, DSF0000907447, DSF0000912919
8 | X075 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | CM,F&E | In-Progress | 8/2/2021 | 7/16/2024 |  | 2507152 | 790738 | 769055 | DSF0000961194, DSF0000907450, DSF0000907451, DSF0000907447, DSF0000912919
8 | X075 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 8/3/2020 | 12/3/2020 | 6/30/2021 | 34550 | 23504 | 23470 | DSF0000961091
8 | X075 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 7/7/2021 | 12/8/2021 | 11/22/2021 | 172750 | 120855 | 120855 | DSF0000961091
8 | X075 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 7/10/2023 | 10/1/2024 |  | 3886875 | 3915293 | 523433 | DSF0000961091
8 | X075 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 7/10/2023 | 10/1/2024 |  | 241850 | 79355 | 79355 | DSF0000961091
8 | X075 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/16/2022 | 3/21/2023 | 12/13/2022 | 4672 | 5811 | 5811 | DSF0001034644
8 | X075 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/13/2022 | 6/9/2023 | 2/8/2023 | 21026 | 23245 | 23245 | DSF0001034644
8 | X075 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/10/2023 | 6/4/2024 |  | 270999 | 241552 | 214815 | DSF0001034644
8 | X075 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/10/2023 | 6/4/2024 |  | 166957 | 157729 | 120186 | DSF0001034644
8 | X075 | P.S. 75 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/12/2021 | 3/18/2022 | 3/11/2022 | 0 | 47543 | 42999 | DSF0001007955, DSF0001007995
8 | X075 | P.S. 75 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 3/14/2022 | 7/15/2022 | 5/11/2022 | 77520 | 71543 | 53103 | DSF0001007955, DSF0001007995
8 | X075 | P.S. 75 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 8/11/2023 | 5/6/2024 |  | 1136960 | 989068 | 7453 | DSF0001007955, DSF0001007995
8 | X075 | P.S. 75 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 8/11/2023 | 5/6/2024 |  | 77520 | 84448 | 13039 | DSF0001007955, DSF0001007995
8 | X075 | P.S. 75 - BRONX | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOOR TILES 506, 415, 511A, 511B, 416B, 415A, 412B, 411B, 414 AND 316 | Construction | In-Progress | 12/9/2024 | IEH |  | IEH | 0 | 0 | SCA0000073689
8 | X075 | X352 SPED - BRONX | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | Complete | 3/19/2020 | DOER | 5/23/2024 | DOER | 278308 | 86515 | DSF0000913495
8 | X075 | P.S. 75 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 7/20/2023 | DOER | 11/19/2023 | DOER | 235796 | 1131 | DSF0001036211
8 | X093 | P.S. 93 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/4/2024 | 3/10/2025 | 11/8/2024 | 4765 | 3730 | 3730 | DSF0001087573
8 | X093 | P.S. 93 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 11/8/2024 | 5/8/2025 |  | 21442 | 21442 | 14919 | DSF0001087573
8 | X093 | P.S. 93 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 276361 | 276361 | 0 | DSF0001087573
8 | X093 | P.S. 93 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 51222 | 51222 | 0 | DSF0001087573
8 | X093 | ICAHN CHARTER SCHOOL 7 | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 250000 | 250000 | 0 | DSF0001113340
8 | X093 | P.S. 93 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 37041 | 0 | DSF0000800226
8 | X093 | P.S. 93 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 126000 | 0 | DSF0001086736
8 | X093 | P.S. 93 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001113339
8 | X093 | P.S. 93 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 12/9/2022 | DOES |  | DOES | 69021 | 0 | DSF0001034461
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A TECHNOLOGY | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086742
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A TECHNOLOGY | Design | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0001086742
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A TECHNOLOGY | Construction | PNS | PNS | PNS | PNS | 66000 | 66000 | 0 | DSF0001086742
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A TECHNOLOGY | CM,F&E | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0001086742
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112251
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | Design | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0001112251
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | Construction | PNS | PNS | PNS | PNS | 66000 | 66000 | 0 | DSF0001112251
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | CM,F&E | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0001112251
8 | X100 | P.S. 100 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 33512 | 0 | DSF0001086743
8 | X100 | P.S. 100 - BRONX | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001113348
8 | X101 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 5/15/2017 | 10/16/2017 | 7/7/2017 | 99450 | 120993 | 120993 | DSF0000798384, DSF0000795357
8 | X101 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/14/2017 | 12/15/2017 | 1/12/2018 | 397800 | 420115 | 409513 | DSF0000798384, DSF0000795357
8 | X101 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/9/2018 | 7/7/2020 |  | 7458750 | 7052282 | 6543372 | DSF0000798384, DSF0000795357
8 | X101 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/9/2018 | 7/7/2020 |  | 464100 | 995953 | 988467 | DSF0000798384, DSF0000795357
8 | X101 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/28/2022 | 3/30/2023 | 12/13/2022 | 5300 | 6526 | 6526 | DSF0001034664
8 | X101 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/13/2022 | 6/9/2023 | 2/8/2023 | 23850 | 26106 | 26106 | DSF0001034664
8 | X101 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/10/2023 | 6/4/2024 |  | 307400 | 274511 | 246341 | DSF0001034664
8 | X101 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/10/2023 | 6/4/2024 |  | 191294 | 181373 | 129587 | DSF0001034664
8 | X101 | P.S. 304 - BRONX | SCA IEH | PO18-SPACE ID: 4314 - CLASSROOM 314 - ABATE FLOOR TILES - 841 SF SPACE ID: 4321 - CLASSROOM 321 - AB | Construction | Complete | 10/24/2024 | IEH | 11/27/2024 | IEH | 0 | 0 | SCA0000073536
8 | X101 | X010 SPED - BRONX | Fast Track Projects | CTF ROOM CONVERSIONS / PARTITIONING / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 5/18/2023 | FTK |  | FTK | 1667022 | 1483941 | DSF0001083686, DSF0001083860
8 | X101 | X010 SPED - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 100000 | 0 | DSF0001033347
8 | X101 | I.S. 101 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113349
8 | X101 | P.S. 304 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 228570 | 0 | DSF0001086744
8 | X101 | P.S. 304 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/22/2024 | DOES | 8/30/2024 | DOES | 65832 | 6479 | DSF0001085054
8 | X107 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 6/28/2022 | 11/14/2022 | 10/26/2022 | 71874 | 81821 | 81821 | DSF0001080800, DSF0001080799, DSF0001080798, DSF0001080795
8 | X107 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 11/30/2022 | 5/3/2023 | 11/15/2023 | 347396 | 317811 | 267284 | DSF0001080800, DSF0001080799, DSF0001080798, DSF0001080795
8 | X107 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 4/26/2024 | 4/15/2026 |  | 6780659 | 6253995 | 1357710 | DSF0001080800, DSF0001080799, DSF0001080798, DSF0001080795
8 | X107 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 4/26/2024 | 4/15/2026 |  | 592923 | 186115 | 186115 | DSF0001080800, DSF0001080799, DSF0001080798, DSF0001080795
8 | X107 | P.S. 107 - BRONX | SCA Emergency Response | SIDEWALK BRIDGE | Construction | In-Progress | 6/3/2022 | EMER |  | EMER | 86499 | 77253 | SCA0000071201
8 | X107 | P.S. 107 - BRONX | SCA IEH | PO18-ABATE/REPLACE DETERIORATED 9X9 TILES IN ROOM B10 / HALLWAY | Construction | In-Progress | 12/11/2024 | IEH |  | IEH | 0 | 0 | SCA0000073691
8 | X107 | BOYS PREPARATORY CHARTER SCHOOL OF THE BRONX | Fast Track Projects | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/23/2023 | FTK |  | FTK | 153900 | 0 | DSF0000961519
8 | X107 | P.S. 107 - BRONX | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0 | DSF0001113354
8 | X119 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | Scope | Complete | 9/15/2017 | 2/5/2018 | 2/2/2018 | 16049 | 17430 | 17430 | DSF0000862747, DSF0000885410
8 | X119 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | Design | Complete | 3/16/2018 | 8/15/2018 | 10/17/2018 | 58847 | 116393 | 63875 | DSF0000862747, DSF0000885410
8 | X119 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 2/21/2019 | 11/17/2019 |  | 623246 | 449483 | 361692 | DSF0000862747, DSF0000885410
8 | X119 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 2/21/2019 | 11/17/2019 |  | 144443 | 207222 | 199614 | DSF0000862747, DSF0000885410
8 | X119 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | Scope | Complete | 6/5/2023 | 12/4/2023 | 10/30/2023 | 124676 | 141366 | 140223 | DSF0001108995, DSF0001081028, DSF0001111763, DSF0001111764
8 | X119 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | Design | Complete | 11/14/2023 | 4/17/2024 | 4/16/2024 | 623380 | 391037 | 391037 | DSF0001108995, DSF0001081028, DSF0001111763, DSF0001111764
8 | X119 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | Construction | In-Progress | 8/2/2024 | 8/1/2026 |  | 14026051 | 12803342 | 670487 | DSF0001108995, DSF0001081028, DSF0001111763, DSF0001111764
8 | X119 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | CM,F&E | In-Progress | 8/2/2024 | 8/1/2026 |  | 872733 | 167813 | 165144 | DSF0001108995, DSF0001081028, DSF0001111763, DSF0001111764
8 | X119 | P.S. 119 - BRONX | SCA Emergency Response | EMERGENCY- STRUCTURAL ISSUES/BUILDING FACADES | Construction | In-Progress | 12/27/2022 | EMER |  | EMER | 548266 | 510394 | SCA0000071651
8 | X119 | P.S. 119 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001086758
8 | X120 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 7/9/2020 | 12/10/2020 | 9/15/2020 | 88770 | 72616 | 72616 | DSF0000961021, DSF0000961020
8 | X120 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 9/18/2020 | 2/24/2021 | 1/8/2021 | 443850 | 305572 | 277372 | DSF0000961021, DSF0000961020
8 | X120 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 7/5/2023 | 7/3/2025 |  | 9986625 | 9128629 | 3517192 | DSF0000961021, DSF0000961020
8 | X120 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 7/5/2023 | 7/3/2025 |  | 622422 | 473464 | 457248 | DSF0000961021, DSF0000961020
8 | X120 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/17/2023 | 5/16/2023 | 2/2/2023 | 2960 | 2794 | 2794 | DSF0001034650
8 | X120 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/2/2023 | 7/31/2023 | 4/12/2023 | 13320 | 11177 | 11177 | DSF0001034650
8 | X120 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/6/2023 | 9/30/2024 |  | 171680 | 159324 | 2094 | DSF0001034650
8 | X120 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/6/2023 | 9/30/2024 |  | 34681 | 27338 | 20952 | DSF0001034650
8 | X120 | I.S. 301 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/18/2024 | DIIR |  | DIIR | 75000 | 0 | DSF0001036236
8 | X120 | I.S. 301 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001086759
8 | X120 | I.S. 301 - BRONX | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 110053 | 0 | DSF0000913163
8 | X120 | GIRLS PREP CHARTER SCHOOL - X | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0000913501
8 | X120 | I.S. 301 - BRONX | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001036235
8 | X120 | X188 SPED - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113365
8 | X120 | I.S. 301 - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 10/21/2021 | DOES | 5/10/2023 | DOES | 388374 |  | DSF0000960869
8 | X123 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 9/1/2017 | 1/23/2018 | 1/30/2018 | 68640 | 121119 | 121119 | DSF0000862816, DSF0000866311, DSF0000862814
8 | X123 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/8/2020 | 6/9/2020 | 5/7/2020 | 343200 | 532297 | 498318 | DSF0000862816, DSF0000866311, DSF0000862814
8 | X123 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/6/2021 | 7/5/2023 |  | 7722000 | 8657841 | 7413177 | DSF0000862816, DSF0000866311, DSF0000862814
8 | X123 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/6/2021 | 7/5/2023 |  | 480479 | 830431 | 796452 | DSF0000862816, DSF0000866311, DSF0000862814
8 | X123 | I.S. 123 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 12/11/2023 | 4/26/2024 | 7/31/2024 | 190360 | 257891 | 255578 | DSF0001081103, DSF0001109068, DSF0001113738, DSF0001113737, DSF0001113736
8 | X123 | I.S. 123 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | In-Progress | 8/27/2024 | 1/31/2025 |  | 881723 | 881723 | 19390 | DSF0001081103, DSF0001109068, DSF0001113738, DSF0001113737, DSF0001113736
8 | X123 | I.S. 123 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 15344326 | 15344326 | 80827 | DSF0001081103, DSF0001109068, DSF0001113738, DSF0001113737, DSF0001113736
8 | X123 | I.S. 123 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 1628235 | 1628235 | 41810 | DSF0001081103, DSF0001109068, DSF0001113738, DSF0001113737, DSF0001113736
8 | X123 | I.S. 337 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001086761
8 | X125 | P.S. 119 - BRONX | SCA CIP | SEWAGE TANK REPLACEMENT- PERM FIX @ X125 | Scope | Complete | 10/4/2023 | 2/8/2024 | 1/5/2024 | 7019 | 12061 | 12061 | DSF0001112033
8 | X125 | P.S. 119 - BRONX | SCA CIP | SEWAGE TANK REPLACEMENT- PERM FIX @ X125 | Design | Complete | 1/22/2024 | 5/15/2024 | 4/25/2024 | 31586 | 30153 | 28620 | DSF0001112033
8 | X125 | P.S. 119 - BRONX | SCA CIP | SEWAGE TANK REPLACEMENT- PERM FIX @ X125 | Construction | PNS | PNS | PNS | PNS | 407104 | 407104 | 29689 | DSF0001112033
8 | X125 | P.S. 119 - BRONX | SCA CIP | SEWAGE TANK REPLACEMENT- PERM FIX @ X125 | CM,F&E | PNS | PNS | PNS | PNS | 75455 | 75455 | 25312 | DSF0001112033
8 | X125 | I.S. 562 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/7/2023 | 6/8/2023 | 5/9/2023 | 0 | 32461 | 32460 | DSF0001036237, DSF0001036238
8 | X125 | I.S. 562 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 5/18/2023 | 10/20/2023 | 12/18/2023 | 45000 | 64080 | 48331 | DSF0001036237, DSF0001036238
8 | X125 | I.S. 562 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/8/2024 | 10/7/2025 |  | 660000 | 492267 | 44869 | DSF0001036237, DSF0001036238
8 | X125 | I.S. 562 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 10/8/2024 | 10/7/2025 |  | 45000 | 47717 | 14883 | DSF0001036237, DSF0001036238
8 | X125 | P.S. 119 - BRONX | SCA IEH | PO18-TEST AND ABATE (IF NEEDED) 4' OF PIPE INSULATION IN ROOM 202 TO REPAIR ROOF DRAIN. | Construction | Complete | 7/23/2024 | IEH | 9/26/2024 | IEH | 0 | 0 | SCA0000073163
8 | X125 | P.S. 119 - BRONX | SCA IEH | PO18-PLANNED DATA UPGRADE PROJECT, CONDUIT INSTALLATION IS REQUIRED IN THE CEILING OF THE 3RD-FLOOR | Construction | In-Progress | 10/8/2024 | IEH |  | IEH | 0 | 0 | SCA0000073473
8 | X125 | I.S. 562 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 126000 | 126000 | 0 | DSF0001086762
8 | X125 | I.S. 562 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 164041 | 0 | DSF0001035317
8 | X125 | P.S. 119 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/22/2023 | DOES | 10/18/2023 | DOES | 431009 |  | DSF0001035151
8 | X125 | P.S. 119 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/2/2024 | DOES | 12/18/2024 | DOES | 65832 |  | DSF0001084857
8 | X130 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/21/2019 | 11/22/2019 | 9/25/2019 | 60358 | 63924 | 63924 | DSF0000912536, DSF0000908405
8 | X130 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 10/4/2019 | 3/11/2020 | 2/11/2020 | 294168 | 289176 | 272138 | DSF0000912536, DSF0000908405
8 | X130 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/12/2021 | 7/11/2023 |  | 5959342 | 5910016 | 5526990 | DSF0000912536, DSF0000908405
8 | X130 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/12/2021 | 7/11/2023 |  | 479686 | 511440 | 509378 | DSF0000912536, DSF0000908405
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113371
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 162000 | 162000 | 0 | DSF0001113371
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 2376000 | 2376000 | 0 | DSF0001113371
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 162000 | 162000 | 0 | DSF0001113371
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113697
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113697
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113697
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113697
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 12/12/2024 | 4/16/2025 |  | 0 | 0 | 0 | DSF0001113821
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0001113821
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 44000 | 44000 | 0 | DSF0001113821
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 3000 | 3000 | 506 | DSF0001113821
8 | X130 | P.S. 130 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION- FACADE DAMAGE @ X130 | Construction | In-Progress | 11/6/2024 | EMER |  | EMER | 44638 | 0 | SCA0000073573
8 | X130 | P.S. 130 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 125000 | DSF0001086764
8 | X131 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | Scope | Complete | 1/15/2020 | 6/3/2022 | 11/15/2022 | 11900 | 31873 | 31873 | DSF0000914293, DSF0001034513
8 | X131 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | Design | Complete | 11/25/2022 | 4/7/2023 | 4/17/2023 | 53550 | 118629 | 49832 | DSF0000914293, DSF0001034513
8 | X131 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | Construction | In-Progress | 8/16/2023 | 6/10/2024 |  | 690200 | 711240 | 305444 | DSF0000914293, DSF0001034513
8 | X131 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 8/16/2023 | 6/10/2024 |  | 149122 | 133400 | 106422 | DSF0000914293, DSF0001034513
8 | X131 | I.S. 131 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/28/2018 | 4/2/2019 | 3/13/2019 | 0 | 51661 | 17987 | DSF0000890723
8 | X131 | I.S. 131 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 4/3/2019 | 9/3/2019 | 3/25/2022 | 49500 | 63829 | 37502 | DSF0000890723
8 | X131 | I.S. 131 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2/10/2023 | 11/6/2023 | 10/27/2023 | 726000 | 409015 | 369875 | DSF0000890723
8 | X131 | I.S. 131 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 2/10/2023 | 11/6/2023 | 10/27/2023 | 49500 | 43787 | 42990 | DSF0000890723
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/2/2024 | 6/4/2024 | 6/24/2024 | 0 | 16026 | 16026 | DSF0001036243
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 7/1/2024 | 12/3/2024 |  | 57000 | 40974 | 10133 | DSF0001036243
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 836000 | 836000 | 0 | DSF0001036243
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 57000 | 57000 | 29794 | DSF0001036243
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036244
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036244
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036244
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036244
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/23/2023 | 7/10/2023 | 9/25/2024 | 0 | 17235 | 1738 | DSF0001036241
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 9/30/2024 | 3/6/2025 |  | 59357 | 42122 | 6954 | DSF0001036241
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 870573 | 870573 | 0 | DSF0001036241
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 59357 | 59357 | 23700 | DSF0001036241
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 9/18/2024 | 12/20/2024 | 11/1/2024 | 0 | 559 | 559 | DSF0001036242
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 11/6/2024 | 3/11/2025 |  | 643 | 2235 | 2235 | DSF0001036242
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 9427 | 9427 | 6213 | DSF0001036242
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 643 | 18311 | 18311 | DSF0001036242
8 | X131 | I.S. 131 - BRONX | SCA IEH | PO18-SPACE ID: 2144 - ROOM 144 - TEST AND ABATE PIPE INSULATION IN ROOM 144, MARKED GREY FOR ID. | Construction | In-Progress | 8/28/2024 | IEH |  | IEH | 0 | 0 | SCA0000073326
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 7/15/2021 | FTK |  | FTK | 1231077 | 1180384 | DSF0000913034
8 | X131 | I.S. 131 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113373
8 | X131 | SUCCESS ACADEMY CHARTER SCHOOL - BRONX 4 - NEW YORK 2 | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 12/7/2022 | DOER |  | DOER | 909014 | 0 | DSF0001036245
8 | X131 | I.S. 131 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 7/29/2015 | DOES |  | DOES | 188220 | 0 | DSF0000799872
8 | X131 | I.S. 131 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 8/30/2022 | DOES |  | DOES | 216748 | 0 | DSF0001034464
8 | X131 | I.S. 131 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/21/2023 | DOES | 3/13/2024 | DOES | 567791 |  | DSF0001035152
8 | X131 | I.S. 131 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/16/2024 | DOES | 9/27/2024 | DOES | 65832 | 5992 | DSF0001084859
8 | X138 | P.S. 138 - BRONX | SCA Capacity | ADDITION | Scope | Complete | 9/6/2019 | 3/12/2020 | 10/23/2020 | 1155980 | 734336 | 733314 | DSF0000911814
8 | X138 | P.S. 138 - BRONX | SCA Capacity | ADDITION | Design | Complete | 10/26/2020 | 9/14/2020 | 8/12/2021 | 5201910 | 2958968 | 2493561 | DSF0000911814
8 | X138 | P.S. 138 - BRONX | SCA Capacity | ADDITION | Construction | Complete | 1/19/2022 | 9/3/2024 | 9/1/2024 | 65601865 | 69618093 | 59386944 | DSF0000911814
8 | X138 | P.S. 138 - BRONX | SCA Capacity | ADDITION | CM,Art,F&E | Complete | 1/19/2022 | 9/3/2024 | 9/1/2024 | 9247840 | 9143542 | 6585644 | DSF0000911814
8 | X138 | P.S. 138 - BRONX | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS | Scope | Complete | 2/7/2023 | 6/7/2023 | 12/14/2023 | 21447 | 42390 | 42390 | DSF0000911814
8 | X138 | P.S. 138 - BRONX | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS | Design | Complete | 12/19/2023 | 5/21/2024 | 10/30/2024 | 107234 | 124534 | 113651 | DSF0000911814
8 | X138 | P.S. 138 - BRONX | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS | Construction | PNS | PNS | PNS | PNS | 2412771 | 2412771 | 65008 | DSF0000911814
8 | X138 | P.S. 138 - BRONX | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS | CM,F&E | PNS | PNS | PNS | PNS | 150128 | 150128 | 55716 | DSF0000911814
8 | X138 | P.S. 138 - BRONX | DOE - RESOA | FY21 RESO A COMPUTER LAB | Construction | Complete | 10/12/2022 | DOER | 4/27/2023 | DOER | 118534 | 255213 | DSF0001007958
8 | X138 | P.S. 138 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/12/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084550
8 | X140 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 5/12/2022 | 9/27/2022 | 8/31/2022 | 46285 | 42360 | 42360 | DSF0001030616, DSF0001030614, DSF0001036313
8 | X140 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | Design | Complete | 9/2/2022 | 2/8/2023 | 2/8/2023 | 224497 | 186291 | 174803 | DSF0001030616, DSF0001030614, DSF0001036313
8 | X140 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 6/16/2023 | 6/14/2025 |  | 4451993 | 4114755 | 3091981 | DSF0001030616, DSF0001030614, DSF0001036313
8 | X140 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 6/16/2023 | 6/14/2025 |  | 375946 | 481027 | 472147 | DSF0001030616, DSF0001030614, DSF0001036313
8 | X140 | P.S. 140 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 4/5/2023 | 7/6/2023 | 8/2/2023 | 24894 | 62175 | 62175 | DSF0001083719
8 | X140 | P.S. 140 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 8/7/2023 | 12/22/2023 | 4/30/2024 | 124469 | 137633 | 126405 | DSF0001083719
8 | X140 | P.S. 140 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2800545 | 2800545 | 119580 | DSF0001083719
8 | X140 | P.S. 140 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 174256 | 174256 | 72485 | DSF0001083719
8 | X140 | P.S. 140 - BRONX | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/29/2023 | 10/31/2023 | 10/2/2023 | 7313 | 14548 | 722 | DSF0001085301
8 | X140 | P.S. 140 - BRONX | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 10/13/2023 | 2/20/2024 | 4/30/2024 | 32908 | 33235 | 2887 | DSF0001085301
8 | X140 | P.S. 140 - BRONX | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 424145 | 424145 | 3546 | DSF0001085301
8 | X140 | P.S. 140 - BRONX | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 78613 | 78613 | 11961 | DSF0001085301
8 | X140 | P.S. 140 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/8/2024 | 9/9/2024 | 5/17/2024 | 6337 | 1955 | 1955 | DSF0001087584
8 | X140 | P.S. 140 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/17/2024 | 11/14/2024 | 11/14/2024 | 28518 | 7822 | 7822 | DSF0001087584
8 | X140 | P.S. 140 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 367567 | 367567 | 2681 | DSF0001087584
8 | X140 | P.S. 140 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 72391 | 72391 | 3368 | DSF0001087584
8 | X140 | P.S. 140 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 12/7/2023 | 6/14/2024 | 6/7/2024 | 0 | 19561 | 13762 | DSF0001086768, DSF0001087126
8 | X140 | P.S. 140 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 6/11/2024 | 10/15/2024 | 8/13/2024 | 32250 | 35889 | 34889 | DSF0001086768, DSF0001087126
8 | X140 | P.S. 140 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 473001 | 473001 | 4636 | DSF0001086768, DSF0001087126
8 | X140 | P.S. 140 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 32250 | 34367 | 23117 | DSF0001086768, DSF0001087126
8 | X140 | P.S. 140 - BRONX | SCA IEH | PO18-SPACE ID: 1004 - CRAWLSPACE - ABATE 15 LINEAR FEET OF ACM PIPE INSULATION ON THE WATER MAIN. MA | Construction | In-Progress | 12/19/2024 | IEH |  | IEH | 0 | 0 | SCA0000073731
8 | X146 | P.S. 146 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 11/19/2018 | 4/8/2019 | 3/6/2019 | 170028 | 186366 | 186366 | DSF0000885832, DSF0000885833, DSF0000885834, DSF0001109436
8 | X146 | P.S. 146 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | In-Progress | 7/17/2024 | 12/18/2024 |  | 744831 | 744831 | 14899 | DSF0000885832, DSF0000885833, DSF0000885834, DSF0001109436
8 | X146 | P.S. 146 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | PNS | PNS | PNS | PNS | 12294727 | 12294727 | 21136 | DSF0000885832, DSF0000885833, DSF0000885834, DSF0001109436
8 | X146 | P.S. 146 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1108022 | 1108022 | 36109 | DSF0000885832, DSF0000885833, DSF0000885834, DSF0001109436
8 | X146 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 8/1/2019 | 12/18/2019 | 12/3/2019 | 89740 | 113872 | 113872 | DSF0000912341, DSF0000954398
8 | X146 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 1/22/2020 | 7/8/2020 | 1/12/2022 | 448700 | 560883 | 555834 | DSF0000912341, DSF0000954398
8 | X146 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 7/11/2022 | 7/9/2024 |  | 10095750 | 9927013 | 8708145 | DSF0000912341, DSF0000954398
8 | X146 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 7/11/2022 | 7/9/2024 |  | 629386 | 1535260 | 1515570 | DSF0000912341, DSF0000954398
8 | X146 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/21/2022 | 4/24/2023 | 1/26/2023 | 5000 | 3938 | 3938 | DSF0001034604
8 | X146 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/26/2023 | 7/24/2023 | 4/12/2023 | 22500 | 15749 | 15749 | DSF0001034604
8 | X146 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/6/2023 | 9/30/2024 |  | 290000 | 262060 | 1810 | DSF0001034604
8 | X146 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/6/2023 | 9/30/2024 |  | 118542 | 98292 | 44993 | DSF0001034604
8 | X146 | P.S. 146 - BRONX | SCA IEH | PO18-SPACE ID: 3207 CLASSROOM 207 TEST AND ABATE DAMAGED 9' X 9' FLOOR TILES | Construction | In-Progress | 11/22/2024 | IEH |  | IEH | 0 | 0 | SCA0000073639
8 | X146 | P.S. 146 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001086775
8 | X146 | P.S. 146 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 125000 | 0 | DSF0001007933
8 | X146 | P.S. 146 - BRONX | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | Complete | 9/13/2023 | DOER | 12/4/2024 | DOER | 259411 |  | DSF0001036256
8 | X146 | X186 SPED - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 247827 | 0 | DSF0001086774
8 | X152 | P.S. 152 - BRONX | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / CHILLER PLANT UPGRADE / FLOOD ELIMINATION | Scope | Complete | 6/5/2019 | 10/21/2019 | 10/10/2019 | 128000 | 189649 | 166630 | DSF0000908768, DSF0000908767, DSF0000912506, DSF0000954505, DSF0000960653
8 | X152 | P.S. 152 - BRONX | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / CHILLER PLANT UPGRADE / FLOOD ELIMINATION | Design | Complete | 11/20/2019 | 4/23/2020 | 6/15/2020 | 603485 | 482898 | 467870 | DSF0000908768, DSF0000908767, DSF0000912506, DSF0000954505, DSF0000960653
8 | X152 | P.S. 152 - BRONX | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / CHILLER PLANT UPGRADE / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 12382700 | 12382700 | 220713 | DSF0000908768, DSF0000908767, DSF0000912506, DSF0000954505, DSF0000960653
8 | X152 | P.S. 152 - BRONX | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / CHILLER PLANT UPGRADE / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 950762 | 950762 | 95629 | DSF0000908768, DSF0000908767, DSF0000912506, DSF0000954505, DSF0000960653
8 | X152 | P.S. 152 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/15/2024 | 9/16/2024 | 5/21/2024 | 5681 | 592 | 592 | DSF0001087586
8 | X152 | P.S. 152 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/21/2024 | 11/18/2024 | 11/14/2024 | 25567 | 2368 | 2368 | DSF0001087586
8 | X152 | P.S. 152 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 329525 | 329525 | 0 | DSF0001087586
8 | X152 | P.S. 152 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 65340 | 65340 | 4542 | DSF0001087586
8 | X152 | P.S. 152 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ X152 | Construction | In-Progress | 6/21/2023 | EMER |  | EMER | 89592 | 48836 | SCA0000072078
8 | X152 | P.S. 152 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086779
8 | X174 | BRONX MATH PREP - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 126000 | 126000 | 0 | DSF0001086788
8 | X174 | ARCHIMEDES ACADEMY FOR MATH - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 175000 | 175000 | 172727 | DSF0001086789
8 | X174 | BRONX MATH PREP - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035300
8 | X174 | ARCHIMEDES ACADEMY FOR MATH - BRONX | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 141712 | 0 | DSF0001036271
8 | X174 | ARCHIMEDES ACADEMY FOR MATH - BRONX | DOE - RESOA | FY23 RESO A ROBOTICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 153135 | 0 | DSF0001036272
8 | X174 | WOMEN'S ACADEMY OF EXCELLENCE - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 700000 | 0 | DSF0001086787
8 | X174 | ARCHIMEDES ACADEMY FOR MATH - BRONX | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/16/2022 | DOES |  | DOES | 61230 | 0 | DSF0001008972
8 | X174 | WOMEN'S ACADEMY OF EXCELLENCE - BRONX | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 11/17/2022 | DOES |  | DOES | 1803128 | 0 | SCA0000070986
8 | X174 | WOMEN'S ACADEMY OF EXCELLENCE - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/28/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085063
8 | X182 | P.S. 182 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/29/2024 | 9/27/2024 | 6/5/2024 | 3624 | 1966 | 1966 | DSF0001087593
8 | X182 | P.S. 182 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/5/2024 | 12/3/2024 | 11/27/2024 | 16307 | 7864 | 7864 | DSF0001087593
8 | X182 | P.S. 182 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 210175 | 210175 | 0 | DSF0001087593
8 | X182 | P.S. 182 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 43219 | 43219 | 4522 | DSF0001087593
8 | X182 | P.S. 182 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 10/22/2021 | FTK |  | FTK | 63761 | 63761 | DSF0000911992
8 | X182 | P.S. 182 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001086796
8 | X182 | P.S. 182 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/30/2024 | DIIR | 10/17/2024 | DIIR | 99649 | 99649 | DSF0001086795
8 | X192 | BRONX DELTA SCHOOL | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001113394
8 | X192 | MOTT HALL COMMUNITY SCHOOL - BRONX | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 4/1/2020 | DIIR |  | DIIR | 100000 | 0 | DSF0000890550
8 | X192 | BRONX DELTA SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0 | DSF0001008477
8 | X192 | BRONX DELTA SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 75000 | 0 | DSF0001034120
8 | X192 | I.S. 371 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 575000 | 0 | DSF0001086802
8 | X192 | BRONX DELTA SCHOOL | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086803
8 | X192 | I.S. 366 - X | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 148683 | 0 | DSF0000796723
8 | X317 | P.S. 583 - BRONX | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | Complete | 6/25/2024 | DOER | 7/24/2024 | DOER | 142938 |  | DSF0001036281
8 | X392 | M.S./H.S. 269 - BRONX | DOE - RESOA | FY19 RESO A KITCHEN AREAS | Construction | In-Progress | 6/30/2022 | DOER |  | DOER | 78308 | 0 | DSF0000890966
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | Scope | Complete | 11/20/2020 | 2/16/2021 | 12/15/2021 | 164800 | 96998 | 96998 | DSF0001034401
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | Design | Complete | 1/13/2022 | 6/20/2022 | 9/28/2022 | 824000 | 771832 | 459878 | DSF0001034401
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | Construction | In-Progress | 3/6/2024 | 3/5/2026 |  | 18540000 | 16725678 | 492505 | DSF0001034401
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | CM,F&E | In-Progress | 3/6/2024 | 3/5/2026 |  | 1153600 | 172285 | 170939 | DSF0001034401
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | Scope | Complete | 11/10/2021 | 1/13/2022 | 1/12/2022 | 10500 | 19205 | 19205 | DSF0001004375
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | Design | Complete | 1/31/2022 | 6/3/2022 | 5/10/2022 | 52500 | 110527 | 83346 | DSF0001004375
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | Construction | In-Progress | 4/4/2023 | 4/2/2024 |  | 1181250 | 1257735 | 1053492 | DSF0001004375
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | CM,F&E | In-Progress | 4/4/2023 | 4/2/2024 |  | 73500 | 181990 | 181990 | DSF0001004375
8 | X405 | HERBERT H. LEHMAN HS - X | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN VARIOUS BATHROOMS | Construction | Complete | 1/13/2023 | IEH | 9/10/2024 | IEH | 0 | 0 | SCA0000071697
8 | X405 | SCHUYLERVILLE PREPARATORY HIGH SCHOOL | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 126000 | 126000 | 0 | DSF0001113408
8 | X405 | HERBERT H. LEHMAN HS - X | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 126000 | 126000 | 0 | DSF0001113409
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 5/24/2016 | FTK |  | FTK | 1013337 | 941254 | DSF0000823642
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | CTF-ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/17/2017 | FTK |  | FTK | 2513122 | 2443733 | DSF0000865818
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 5/2/2022 | FTK |  | FTK | 3315031 | 3001336 | DSF0001009262
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 5/2/2022 | FTK |  | FTK | 3129214 | 2852880 | DSF0001009261
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 8/22/2023 | FTK |  | FTK | 157166 | 140568 | DSF0001034296
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | GAS METER ROOM COMPLIANCE PROJECT | Construction | In-Progress | 9/25/2018 | FTK |  | FTK | 371579 | 337804 | DSF0000889570
8 | X405 | WESTCHESTER SQUARE ACADEMY - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 75000 | 70856 | DSF0001034146
8 | X405 | HERBERT H. LEHMAN HS - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/2/2024 | DIIR | 7/11/2024 | DIIR | 100000 | 3258 | DSF0001086824
8 | X405 | X721 SPED - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113406
8 | X405 | BRONX RIVER HIGH SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001113407
8 | X405 | RENAISSANCE HS FOR MUS THEATRE - X | DOE - RESOA | FY20 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75795 | 0 | DSF0000914216
8 | X405 | HERBERT H. LEHMAN HS - X | DOE - Skilled Trades | INTERIOR SPACES | Construction | In-Progress | 6/15/2021 | DOES |  | DOES | 1298930 | 0 | DSF0001004383
8 | X405 | HERBERT H. LEHMAN HS - X | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/14/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001085069
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113420
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 240000 | 240000 | 0 | DSF0001113420
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 3520000 | 3520000 | 0 | DSF0001113420
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 240000 | 240000 | 0 | DSF0001113420
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113704
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113704
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113704
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113704
8 | X450 | MILLENIUM ART ACADEMY - BRONX | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/13/2018 | 10/15/2018 | 8/23/2018 | 0 | 4886 | 4886 | DSF0000867210
8 | X450 | MILLENIUM ART ACADEMY - BRONX | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 57630 | 52744 | 19543 | DSF0000867210
8 | X450 | MILLENIUM ART ACADEMY - BRONX | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 845240 | 1023959 | 6458 | DSF0000867210
8 | X450 | MILLENIUM ART ACADEMY - BRONX | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 57630 | 69815 | 2440 | DSF0000867210
8 | X450 | BRONX COMMUNITY HIGH SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 272000 | 0 | DSF0001113419
8 | X450 | MILLENIUM ART ACADEMY - BRONX | DOE - RESOA | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/15/2019 | DOER |  | DOER | 209669 | 0 | DSF0000866385
8 | X450 | ANTONIA PANTOJA PREP ACADEMY - X | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | Complete | 11/10/2021 | DOER | 5/16/2022 | DOER | 443074 | 427311 | DSF0000913518
8 | X450 | X017 SPED - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 12/1/2023 | DOER | 9/13/2024 | DOER | 303149 |  | DSF0001036293
8 | X450 | X017 SPED - BRONX | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 215748 | 0 | DSF0001036294
8 | X450 | X017 SPED - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 384704 | 0 | DSF0001086842
8 | X450 | MILLENIUM ART ACADEMY - BRONX | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 12/24/2020 | DOES |  | DOES | 234472 | 0 | DSF0000960501
8 | X450 | MILLENIUM ART ACADEMY - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/3/2022 | DOES |  | DOES | 223320 | 0 | DSF0001008729
8 | X450 | MILLENIUM ART ACADEMY - BRONX | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 11/4/2022 | DOES |  | DOES | 1850964 | 0 | SCA0000071001
8 | X450 | MILLENIUM ART ACADEMY - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/3/2024 | DOES | 9/13/2024 | DOES | 65832 | 5948 | DSF0001085079
8 | X451 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | Scope | Complete | 3/22/2019 | 11/1/2021 | 11/24/2021 | 264990 | 382792 | 382792 | DSF0000886790, DSF0000960817
8 | X451 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | Design | Complete | 11/29/2021 | 4/28/2022 | 9/30/2022 | 1324948 | 1583513 | 1519143 | DSF0000886790, DSF0000960817
8 | X451 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/7/2023 | 1/1/2025 |  | 29811319 | 32448408 | 3264892 | DSF0000886790, DSF0000960817
8 | X451 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | CM,F&E | In-Progress | 7/7/2023 | 1/1/2025 |  | 1857101 | 305374 | 305374 | DSF0000886790, DSF0000960817
8 | X521 | I.S. @ 2169 BLACKROCK AVENUE - BRONX | DOE Managed PRE-K | LEASE RENOVATION | Construction | In-Progress | 5/31/2024 | DOEP |  | DOEP | 500287 | 0 | DSF0001087146
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 9/21/2018 | 12/24/2018 | 1/10/2019 | 59010 | 87548 | 87548 | DSF0000889644
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 1/16/2019 | 6/3/2019 | 5/16/2019 | 236040 | 432892 | 432892 | DSF0000889644
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | Complete | 7/13/2021 | 1/3/2023 | 11/7/2024 | 4425750 | 1882869 | 2785058 | DSF0000889644
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | Complete | 7/13/2021 | 1/3/2023 | 11/7/2024 | 275380 | 224584 | 224584 | DSF0000889644
8 | X650 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 9/15/2021 | 1/19/2022 | 9/30/2021 | 4600 | 3095 | 3095 | DSF0000960765
8 | X650 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/30/2021 | 3/31/2022 | 1/11/2022 | 20700 | 12378 | 12378 | DSF0000960765
8 | X650 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 7/25/2022 | 4/19/2023 |  | 266800 | 244788 | 181490 | DSF0000960765
8 | X650 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 7/25/2022 | 4/19/2023 |  | 219927 | 208442 | 202187 | DSF0000960765
8 | X650 | NEW VISIONS CHARTER HS FOR ADVANCED MATH AND SCIENCE, II | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 12/17/2024 | IEH |  | IEH | 0 | 0 | SCA0000073724
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | DOE - RESOA | FY16 RESO A ROOM CONVERSIONS / LEARNING KITCHEN | Construction | PNS | PNS | PNS | PNS | DOER | 989965 | 0 | DSF0000822711
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/28/2019 | DOES |  | DOES | 230617 | 0 | DSF0000891065
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/4/2021 | DOES |  | DOES | 61009 | 0 | DSF0000911898
8 | X650 | NEW VISIONS CHARTER HS FOR ADVANCED MATH AND SCIENCE, II | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 130470 | 80759 | DSF0001082925
8 | X823 | BOYS PREPARATORY CHARTER SCHOOL OF THE BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 35000 | 0 | DSF0000914229
8 | X833 | REGION 2 SUPERINTENDENT - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000913719
8 | X848 | P.S. 48 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 12/18/2024 | IEH |  | IEH | 0 | 0 | SCA0000073727
8 | X869 | P.S. 69 - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001113439
8 | X953 | HOSPITAL SCHOOLS - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0 | DSF0000913720
8 | X953 | CONTINUING EDUCATION PROGRAM - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/6/2024 | DOES | 12/3/2024 | DOES | 65832 | 5727 | DSF0001085582
8 | XOLA | EARL MONROE NEW RENAISSANCE BASKETBALL CHARTER SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001035318
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/14/2023 | 10/13/2023 | 10/17/2023 | 8800 | 16275 | 16275 | DSF0001083792
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/24/2023 | 3/25/2024 | 3/27/2024 | 39600 | 52900 | 41175 | DSF0001083792
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/16/2024 | 9/15/2025 |  | 510400 | 524421 | 72476 | DSF0001083792
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/16/2024 | 9/15/2025 |  | 94600 | 68209 | 20579 | DSF0001083792
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/25/2023 | 5/24/2023 | 2/24/2023 | 4080 | 4697 | 4697 | DSF0001034589
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/24/2023 | 8/21/2023 | 5/3/2023 | 18360 | 18787 | 18787 | DSF0001034589
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/12/2023 | 12/10/2024 |  | 236640 | 213929 | 102696 | DSF0001034589
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/12/2023 | 12/10/2024 |  | 78489 | 61137 | 52586 | DSF0001034589
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA IEH | PO18-ABATE AND REPLACE BROKEN ACM FLOOR TILES IN ROOMS 208 AND 227. | Construction | Complete | 8/27/2024 | IEH | 9/1/2024 | IEH | 0 | 0 | SCA0000073322
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 175000 | 155465 | DSF0001086685
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/6/2023 | DOER |  | DOER | 466645 | 0 | DSF0001008867
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/8/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001085046
9 | X004 | P.S. 4 - BRONX | SCA CIP | SWIMMING POOLS | Scope | Complete | 11/22/2023 | 5/17/2024 | 7/22/2024 | 89722 | 117071 | 6071 | DSF0001111673
9 | X004 | P.S. 4 - BRONX | SCA CIP | SWIMMING POOLS | Design | In-Progress | 10/23/2024 | 3/28/2025 |  | 418701 | 418701 | 7514 | DSF0001111673
9 | X004 | P.S. 4 - BRONX | SCA CIP | SWIMMING POOLS | Construction | PNS | PNS | PNS | PNS | 6639407 | 6639407 | 10526 | DSF0001111673
9 | X004 | P.S. 4 - BRONX | SCA CIP | SWIMMING POOLS | CM,F&E | PNS | PNS | PNS | PNS | 657959 | 657959 | 12693 | DSF0001111673
9 | X004 | P.S. 4 - BRONX | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 6/10/2024 | 10/25/2024 | 10/17/2024 | 307156 | 307956 | 188952 | DSF0001078957, DSF0001106923, DSF0001106928, DSF0001113830, DSF0001134604
9 | X004 | P.S. 4 - BRONX | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | In-Progress | 11/8/2024 | 4/15/2025 |  | 1434223 | 1434223 | 264687 | DSF0001078957, DSF0001106923, DSF0001106928, DSF0001113830, DSF0001134604
9 | X004 | P.S. 4 - BRONX | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS / PARAPETS | Construction | PNS | PNS | PNS | PNS | 23956445 | 23956445 | 30207 | DSF0001078957, DSF0001106923, DSF0001106928, DSF0001113830, DSF0001134604
9 | X004 | P.S. 4 - BRONX | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 2377902 | 2377902 | 32678 | DSF0001078957, DSF0001106923, DSF0001106928, DSF0001113830, DSF0001134604
9 | X004 | P.S. 4 - BRONX | SCA CIP | PATH OF TRAVEL SWIMMING POOL | Scope | In-Progress | 12/11/2024 | 3/14/2025 |  | 647 | 647 | 65 | DSF0001113847
9 | X004 | P.S. 4 - BRONX | SCA CIP | PATH OF TRAVEL SWIMMING POOL | Design | PNS | PNS | PNS | PNS | 2589 | 2589 | 260 | DSF0001113847
9 | X004 | P.S. 4 - BRONX | SCA CIP | PATH OF TRAVEL SWIMMING POOL | Construction | PNS | PNS | PNS | PNS | 37216 | 37216 | 0 | DSF0001113847
9 | X004 | P.S. 4 - BRONX | SCA CIP | PATH OF TRAVEL SWIMMING POOL | CM,F&E | PNS | PNS | PNS | PNS | 9547 | 9547 | 436 | DSF0001113847
9 | X004 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | Scope | Complete | 2/11/2016 | 9/17/2021 | 10/5/2021 | 62480 | 72580 | 72580 | DSF0000843908, DSF0000912668, DSF0001008846
9 | X004 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | Design | Complete | 10/6/2021 | 3/3/2022 | 5/11/2022 | 312400 | 423875 | 339157 | DSF0000843908, DSF0000912668, DSF0001008846
9 | X004 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | Construction | In-Progress | 8/8/2022 | 8/6/2024 |  | 7029000 | 6563750 | 3971311 | DSF0000843908, DSF0000912668, DSF0001008846
9 | X004 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | CM,F&E | In-Progress | 8/8/2022 | 8/6/2024 |  | 444685 | 274799 | 236285 | DSF0000843908, DSF0000912668, DSF0001008846
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036164
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001036164
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001036164
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001036164
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036165
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036165
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036165
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036165
9 | X004 | P.S. 4 - BRONX | SCA Emergency Response | EMERGENCY- SWB @ X004 | Construction | In-Progress | 3/18/2024 | EMER |  | EMER | 49148 | 22042 | SCA0000072819
9 | X011 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | Scope | Complete | 2/24/2021 | 6/8/2021 | 1/18/2022 | 144418 | 486036 | 463729 | DSF0000952148, DSF0000952149, DSF0000952145, DSF0000952147, DSF0001028363, DSF0001034483, DSF0001034484
9 | X011 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | Design | Complete | 1/26/2022 | 6/27/2022 | 5/11/2022 | 705001 | 610416 | 599177 | DSF0000952148, DSF0000952149, DSF0000952145, DSF0000952147, DSF0001028363, DSF0001034483, DSF0001034484
9 | X011 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | Construction | Complete | 7/18/2022 | 7/16/2024 | 7/22/2024 | 14384433 | 13579922 | 13296646 | DSF0000952148, DSF0000952149, DSF0000952145, DSF0000952147, DSF0001028363, DSF0001034483, DSF0001034484
9 | X011 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | CM,F&E | Complete | 7/18/2022 | 7/16/2024 | 7/22/2024 | 1168540 | 863348 | 863348 | DSF0000952148, DSF0000952149, DSF0000952145, DSF0000952147, DSF0001028363, DSF0001034483, DSF0001034484
9 | X011 | P.S. 11 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/16/2023 | 10/16/2023 | 10/16/2023 | 9700 | 12384 | 12384 | DSF0001083795
9 | X011 | P.S. 11 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/24/2023 | 3/25/2024 | 4/5/2024 | 43650 | 94039 | 41819 | DSF0001083795
9 | X011 | P.S. 11 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 10/10/2024 | 10/9/2025 |  | 562600 | 519027 | 8877 | DSF0001083795
9 | X011 | P.S. 11 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 10/10/2024 | 10/9/2025 |  | 104275 | 72019 | 19529 | DSF0001083795
9 | X022 | I.S. 22 - BRONX | SCA CIP | ROOFS / GYMNASIUM FLOORING / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 6/5/2023 | 12/4/2023 | 10/2/2023 | 182777 | 209371 | 209371 | DSF0001079239, DSF0001087222, DSF0001087217, DSF0001087218, DSF0001087216
9 | X022 | I.S. 22 - BRONX | SCA CIP | ROOFS / GYMNASIUM FLOORING / EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 10/18/2023 | 6/11/2024 | 4/19/2024 | 910109 | 376506 | 376506 | DSF0001079239, DSF0001087222, DSF0001087217, DSF0001087218, DSF0001087216
9 | X022 | I.S. 22 - BRONX | SCA CIP | ROOFS / GYMNASIUM FLOORING / EXTERIOR MASONRY / WINDOWS / PARAPETS | Construction | In-Progress | 10/2/2024 | 10/1/2027 |  | 20150719 | 18286241 | 160841 | DSF0001079239, DSF0001087222, DSF0001087217, DSF0001087218, DSF0001087216
9 | X022 | I.S. 22 - BRONX | SCA CIP | ROOFS / GYMNASIUM FLOORING / EXTERIOR MASONRY / WINDOWS / PARAPETS | CM,F&E | In-Progress | 10/2/2024 | 10/1/2027 |  | 1307765 | 99922 | 99212 | DSF0001079239, DSF0001087222, DSF0001087217, DSF0001087218, DSF0001087216
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034023
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034023
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034023
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034023
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY25 RESO A SHBC | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113310
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY25 RESO A SHBC | Design | PNS | PNS | PNS | PNS | 51000 | 51000 | 0 | DSF0001113310
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY25 RESO A SHBC | Construction | PNS | PNS | PNS | PNS | 748000 | 748000 | 0 | DSF0001113310
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY25 RESO A SHBC | CM,F&E | PNS | PNS | PNS | PNS | 51000 | 51000 | 0 | DSF0001113310
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SHBC | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113683
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SHBC | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113683
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SHBC | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113683
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SHBC | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113683
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY21 RESO A (MA) AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/10/2022 | 12/29/2022 | 1/31/2023 | 0 | 72637 | 72419 | DSF0001008611, DSF0001008658
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY21 RESO A (MA) AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2/1/2023 | 6/2/2023 | 10/13/2023 | 90000 | 105109 | 101087 | DSF0001008611, DSF0001008658
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY21 RESO A (MA) AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 9329 | DSF0001008611, DSF0001008658
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY21 RESO A (MA) AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 25657 | DSF0001008611, DSF0001008658
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-ROOM 108, REPLACE 15 MISSING AND BROKEN FLOOR TILES ROOM 233, REPLACE 1 BROKEN FLOOR TILE ROOM | Construction | Complete | 6/28/2024 | IEH | 9/4/2024 | IEH | 0 | 0 | SCA0000073104
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-SPACE ID: 4338 - CLASSROOM 338 ABATE 12' X 12' FLOOR TILES AND REMOVE OLD LAB SINK NEAR WHITEBO | Construction | Complete | 7/31/2024 | IEH | 12/23/2024 | IEH | 0 | 0 | SCA0000073206
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-ABATE ACM FOR CORE DRILLING FOR ELECTRICAL OUTLET INSTALLATIONS, AND THE INSTALLATION OF CONDUI | Construction | Complete | 8/14/2024 | IEH | 8/18/2024 | IEH | 0 | 0 | SCA0000073284
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-ABATE FLOOR ROOM 121B - EXISTING VCT FLOORING AROUND WOODEN BUILT-IN CABINETRY AND LOCKER ROOM | Construction | Complete | 8/23/2024 | IEH | 9/17/2024 | IEH | 0 | 0 | SCA0000073315
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-SPACE ID: 3235 - ROOM 235 REQUIRES THE REPLACEMENT OF PIPE HANGERS, NECESSITATING THE TESTING A | Construction | In-Progress | 9/26/2024 | IEH |  | IEH | 0 | 0 | SCA0000073434
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-ROOM 123 - REMOVE PIPE COVER ON BOTH ENDS MARKED IN RED FOR | Construction | In-Progress | 12/2/2024 | IEH |  | IEH | 0 | 0 | SCA0000073657
9 | X022 | I.S. 22 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 6/10/2021 | FTK |  | FTK | 169934 | 163548 | DSF0000961187
9 | X022 | I.S. 22 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 165713 | 0 | DSF0000960291
9 | X022 | I.S. 22 - BRONX | DOE - RESOA | FY21 RESO A (MA) SUPPLEMENTAL COOLING | Construction | In-Progress | 4/6/2023 | DOER |  | DOER | 381416 | 0 | DSF0001009255
9 | X022 | I.S. 22 - BRONX | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/6/2023 | DOER |  | DOER | 811497 | 0 | DSF0001034024
9 | X022 | I.S. 22 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/2/2024 | DOES | 12/10/2024 | DOES | 65832 |  | DSF0001084843
9 | X022 | I.S. 22 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/20/2024 | DOES |  | DOES | 540717 | 0 | DSF0001111709
9 | X028 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 9/19/2017 | 11/15/2021 | 3/4/2022 | 383131 | 386056 | 386056 | DSF0000861172, DSF0000889384, DSF0000906668, DSF0001028619, DSF0001028618
9 | X028 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | Design | Complete | 3/4/2022 | 8/3/2022 | 5/16/2022 | 1905372 | 1903966 | 1690674 | DSF0000861172, DSF0000889384, DSF0000906668, DSF0001028619, DSF0001028618
9 | X028 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 9/5/2022 | 3/4/2026 |  | 42534156 | 39962955 | 11141979 | DSF0000861172, DSF0000889384, DSF0000906668, DSF0001028619, DSF0001028618
9 | X028 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 9/5/2022 | 3/4/2026 |  | 2697337 | 1433939 | 1124801 | DSF0000861172, DSF0000889384, DSF0000906668, DSF0001028619, DSF0001028618
9 | X028 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/13/2023 | 7/12/2023 | 3/21/2023 | 3320 | 3000 | 3000 | DSF0001035055
9 | X028 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/21/2023 | 9/14/2023 | 5/3/2023 | 14940 | 11998 | 11998 | DSF0001035055
9 | X028 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 12/12/2023 | 12/10/2024 |  | 192560 | 174870 | 115466 | DSF0001035055
9 | X028 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 12/12/2023 | 12/10/2024 |  | 64260 | 51683 | 45013 | DSF0001035055
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035275
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Design | PNS | PNS | PNS | PNS | 12000 | 12000 | 0 | DSF0001035275
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Construction | PNS | PNS | PNS | PNS | 176000 | 176000 | 0 | DSF0001035275
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PROJECT TBD | CM,F&E | PNS | PNS | PNS | PNS | 12000 | 12000 | 0 | DSF0001035275
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036186
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001036186
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001036186
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001036186
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036187
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036187
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036187
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036187
9 | X028 | P.S. 28 - BRONX | SCA IEH | PO18-PRINCIPAL'S OFFICE ROOM 205 REMOVE 4' OF ACM PIPE INSULATION MARKED FOR ID. REMOVE 1' OF ACM PI | Construction | Complete | 8/30/2024 | IEH | 10/9/2024 | IEH | 0 | 0 | SCA0000073337
9 | X035 | P.S. 35 - BRONX | SCA IEH | PO18-REMOVE 8' OF 3' PIPE COVER ON HYDRONIC HEATING LINE IN LUNCH ROOM, MARKED RED FOR ID. CAFETERIA | Construction | Complete | 10/11/2024 | IEH | 10/27/2024 | IEH | 0 | 0 | SCA0000073495
9 | X035 | P.S. 35 - BRONX | DOE - RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 25000 | 0 | DSF0001113811
9 | X042 | P.S. 42 - BRONX | DIIT - RESOA | FY 11 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 247499 | 0 | DSF0000801056
9 | X042 | P.S. 42 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/21/2024 | DIIR | 8/6/2024 | DIIR | 150000 | 150000 | DSF0001086706
9 | X042 | P.S. 42 - BRONX | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001036192
9 | X053 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | Scope | Complete | 3/14/2022 | 7/12/2022 | 7/20/2022 | 29950 | 29110 | 29110 | DSF0001034505
9 | X053 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | Design | Complete | 8/4/2022 | 1/19/2023 | 5/11/2023 | 149750 | 130820 | 109247 | DSF0001034505
9 | X053 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | Construction | In-Progress | 1/17/2024 | 7/9/2025 |  | 3369375 | 3075316 | 1418927 | DSF0001034505
9 | X053 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | CM,F&E | In-Progress | 1/17/2024 | 7/9/2025 |  | 211498 | 169907 | 168059 | DSF0001034505
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113319
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 48000 | 48000 | 0 | DSF0001113319
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 704000 | 704000 | 0 | DSF0001113319
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 48000 | 48000 | 0 | DSF0001113319
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113687
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113687
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113687
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113687
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 19 | 19 | DSF0001087115
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 76 | 76 | DSF0001087115
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087115
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087115
9 | X053 | P.S. 53 - BRONX | SCA IEH | PO18-ABATE APP.14LF OF PIPE INSULATION IN ROOM #407 | Construction | Complete | 7/29/2024 | IEH | 8/6/2024 | IEH | 0 | 0 | SCA0000073195
9 | X053 | P.S. 53 - BRONX | SCA IEH | PO18-ABATE/REPLACE 9 X 9 ACM FLOOR TILES ROOM 309 APPROX: 607 SQ. FT. | Construction | Complete | 7/31/2024 | IEH | 8/31/2024 | IEH | 0 | 0 | SCA0000073209
9 | X053 | P.S. 53 - BRONX | SCA IEH | PO18-ABATE APP.14LF OF PIPE INSULATION IN ROOM #407 | Construction | Complete | 8/5/2024 | IEH | 8/27/2024 | IEH | 0 | 0 | SCA0000073235
9 | X053 | P.S. 53 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 65300 | 0
9 | X053 | P.S. 53 - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/3/2024 | DOER |  | DOER | 209865 | 0 | DSF0001034942
9 | X053 | P.S. 53 - BRONX | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0 | DSF0001086712
9 | X055 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Scope | Complete | 8/6/2021 | 6/3/2022 | 11/15/2022 | 22639 | 38939 | 38939 | DSF0001001896, DSF0001034512
9 | X055 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Design | Complete | 11/25/2022 | 4/7/2023 | 4/17/2023 | 112861 | 158408 | 121247 | DSF0001001896, DSF0001034512
9 | X055 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Construction | In-Progress | 8/24/2023 | 11/20/2024 |  | 2510442 | 2449037 | 2068483 | DSF0001001896, DSF0001034512
9 | X055 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | CM,F&E | In-Progress | 8/24/2023 | 11/20/2024 |  | 160983 | 155138 | 155138 | DSF0001001896, DSF0001034512
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 12/12/2023 | 3/14/2024 |  | 0 | 11667 | 556 | DSF0001086714
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 17880 | 6213 | 2223 | DSF0001086714
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 262240 | 262240 | 0 | DSF0001086714
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 17880 | 17880 | 0 | DSF0001086714
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087116
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087116
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087116
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087116
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007941
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007941
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007941
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007941
9 | X055 | P.S. 55 - BRONX | SCA IEH | PO18-ABATE BROKEN/CRACKED 9' X 9' ACM FLOORING TILES ON THE FOLLOWING FLOORS- 2ND FLOOR - 50' X 90' | Construction | Complete | 4/26/2024 | IEH | 8/18/2024 | IEH | 0 | 0 | SCA0000072965
9 | X055 | P.S. 55 - BRONX | DOE - RESOA | FY18 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Construction | In-Progress | 3/5/2018 | DOER |  | DOER | 371013 | 0 | DSF0000867280
9 | X055 | P.S. 55 - BRONX | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 1/29/2024 | DOER |  | DOER | 700000 | 0 | DSF0001007920
9 | X055 | P.S. 55 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 8/22/2022 | DOES |  | DOES | 165359 | 0 | DSF0001034456
9 | X058 | P.S. 58 - BRONX | SCA CIP | SITE DRAINAGE | Scope | Complete | 3/18/2024 | 3/18/2024 | 3/18/2024 | 17000 | 6124 | 359 | DSF0001107815
9 | X058 | P.S. 58 - BRONX | SCA CIP | SITE DRAINAGE | Design | Complete | 3/18/2024 | 6/28/2024 | 6/26/2024 | 76500 | 34776 | 1436 | DSF0001107815
9 | X058 | P.S. 58 - BRONX | SCA CIP | SITE DRAINAGE | Construction | PNS | PNS | PNS | PNS | 986000 | 986000 | 1595 | DSF0001107815
9 | X058 | P.S. 58 - BRONX | SCA CIP | SITE DRAINAGE | CM,F&E | PNS | PNS | PNS | PNS | 182750 | 182750 | 9904 | DSF0001107815
9 | X058 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | Scope | Complete | 11/28/2017 | 12/11/2018 | 12/12/2018 | 283697 | 209934 | 209885 | DSF0000861625, DSF0000889385, DSF0000884273, DSF0000912156, DSF0000912157, DSF0000907120
9 | X058 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | Design | Complete | 1/3/2019 | 6/20/2019 | 5/17/2019 | 1120106 | 605986 | 539154 | DSF0000861625, DSF0000889385, DSF0000884273, DSF0000912156, DSF0000912157, DSF0000907120
9 | X058 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | Construction | In-Progress | 3/9/2020 | 3/8/2023 |  | 19683701 | 19755143 | 17891980 | DSF0000861625, DSF0000889385, DSF0000884273, DSF0000912156, DSF0000912157, DSF0000907120
9 | X058 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | CM,F&E | In-Progress | 3/9/2020 | 3/8/2023 |  | 1514872 | 1270314 | 1219598 | DSF0000861625, DSF0000889385, DSF0000884273, DSF0000912156, DSF0000912157, DSF0000907120
9 | X063 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 3/11/2021 | 7/26/2021 | 8/23/2021 | 208115 | 236644 | 236644 | DSF0000952938, DSF0001029204, DSF0001034190, DSF0001029195, DSF0001034187, DSF0001029196
9 | X063 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 9/29/2021 | 3/7/2022 | 3/2/2022 | 1035400 | 814709 | 651446 | DSF0000952938, DSF0001029204, DSF0001034190, DSF0001029195, DSF0001034187, DSF0001029196
9 | X063 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 10/13/2023 | 10/11/2026 |  | 22848863 | 20770898 | 2566829 | DSF0000952938, DSF0001029204, DSF0001034190, DSF0001029195, DSF0001034187, DSF0001029196
9 | X063 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 10/13/2023 | 10/11/2026 |  | 1495617 | 172112 | 166090 | DSF0000952938, DSF0001029204, DSF0001034190, DSF0001029195, DSF0001034187, DSF0001029196
9 | X063 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 10/20/2020 | 2/23/2021 | 10/23/2020 | 5772 | 5570 | 5570 | DSF0000960746
9 | X063 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 10/23/2020 | 4/22/2021 | 6/9/2021 | 25974 | 22280 | 22280 | DSF0000960746
9 | X063 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/30/2022 | 9/25/2023 |  | 334776 | 295260 | 273780 | DSF0000960746
9 | X063 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 11/30/2022 | 9/25/2023 |  | 203376 | 184274 | 148427 | DSF0000960746
9 | X063 | P.S. 63 - BRONX | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 12/19/2023 | 6/17/2024 | 7/12/2024 | 0 | 19020 | 19020 | DSF0001086718, DSF0001087117
9 | X063 | P.S. 63 - BRONX | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 7/12/2024 | 10/31/2024 | 11/1/2024 | 49200 | 50014 | 31992 | DSF0001086718, DSF0001087117
9 | X063 | P.S. 63 - BRONX | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 721600 | 721600 | 41038 | DSF0001086718, DSF0001087117
9 | X063 | P.S. 63 - BRONX | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 49200 | 53251 | 29675 | DSF0001086718, DSF0001087117
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 5/18/2020 | 11/13/2020 | 11/3/2020 | 205690 | 363077 | 327077 | DSF0000952964, DSF0000952961, DSF0000952965, DSF0000952966, DSF0001008582
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | Design | Complete | 11/19/2020 | 6/15/2021 | 7/1/2021 | 1028450 | 688755 | 686818 | DSF0000952964, DSF0000952961, DSF0000952965, DSF0000952966, DSF0001008582
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 12/13/2021 | 9/3/2023 |  | 23140125 | 22227421 | 18274921 | DSF0000952964, DSF0000952961, DSF0000952965, DSF0000952966, DSF0001008582
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 12/13/2021 | 9/3/2023 |  | 1439830 | 1186451 | 1107624 | DSF0000952964, DSF0000952961, DSF0000952965, DSF0000952966, DSF0001008582
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 5/24/2023 | 8/24/2023 | 11/16/2023 | 20798 | 36017 | 36017 | DSF0001083950
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 11/27/2023 | 4/12/2024 | 5/17/2024 | 103990 | 125604 | 120070 | DSF0001083950
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2339780 | 2339780 | 53763 | DSF0001083950
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 145586 | 145586 | 26945 | DSF0001083950
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PATH OF TRAVEL- TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 3/15/2024 | 6/13/2024 | 5/8/2024 | 4073 | 8073 | 932 | DSF0001112077
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PATH OF TRAVEL- TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 5/13/2024 | 9/16/2024 | 5/17/2024 | 16291 | 3728 | 3728 | DSF0001112077
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PATH OF TRAVEL- TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 234185 | 234185 | 0 | DSF0001112077
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PATH OF TRAVEL- TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 60074 | 60074 | 3181 | DSF0001112077
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113324
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001113324
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1760000 | 1760000 | 0 | DSF0001113324
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001113324
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113689
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113689
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113689
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113689
9 | X064 | THE WALTON AVENUE SCHOOL | SCA IEH | PO18-THE CAFETERIA FLOOR HAS SEVERAL AREAS WITH MISSING TILES, EXPOSING THE UNDERLAYMENT. THESE SCAT | Construction | In-Progress | 8/22/2024 | IEH |  | IEH | 0 | 0 | SCA0000073308
9 | X064 | THE WALTON AVENUE SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 228000 | 0 | DSF0001033403
9 | X064 | LUCERO ELEMENTARY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113325
9 | X064 | THE WALTON AVENUE SCHOOL | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 725000 | 0 | DSF0001113323
9 | X064 | THE WALTON AVENUE SCHOOL | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/18/2022 | DOES |  | DOES | 330405 | 0 | DSF0000913010
9 | X070 | P.S. 70 - BRONX | SCA CIP | STH SBHC | Scope | Complete | 3/7/2022 | 7/5/2022 | 8/10/2022 | 32500 | 25290 | 25290 | DSF0001034506
9 | X070 | P.S. 70 - BRONX | SCA CIP | STH SBHC | Design | Complete | 8/12/2022 | 1/26/2023 | 3/17/2023 | 162500 | 165123 | 93091 | DSF0001034506
9 | X070 | P.S. 70 - BRONX | SCA CIP | STH SBHC | Construction | In-Progress | 11/6/2023 | 11/4/2025 |  | 3656250 | 3332247 | 1032347 | DSF0001034506
9 | X070 | P.S. 70 - BRONX | SCA CIP | STH SBHC | CM,F&E | In-Progress | 11/6/2023 | 11/4/2025 |  | 229348 | 141641 | 137831 | DSF0001034506
9 | X070 | P.S. 70 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Scope | Complete | 9/30/2022 | 1/4/2023 | 12/30/2022 | 36545 | 112866 | 112716 | DSF0001035074, DSF0001083783
9 | X070 | P.S. 70 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Design | Complete | 9/5/2023 | 4/2/2024 | 5/7/2024 | 178968 | 377068 | 371645 | DSF0001035074, DSF0001083783
9 | X070 | P.S. 70 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Construction | In-Progress | 10/1/2024 | 9/20/2026 |  | 3701756 | 3394927 | 38038 | DSF0001035074, DSF0001083783
9 | X070 | P.S. 70 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | CM,F&E | In-Progress | 10/1/2024 | 9/20/2026 |  | 283996 | 106132 | 99193 | DSF0001035074, DSF0001083783
9 | X070 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 7/6/2023 | 11/6/2023 | 10/25/2023 | 9680 | 16580 | 16580 | DSF0001083811
9 | X070 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/1/2023 | 4/1/2024 | 4/9/2024 | 43560 | 98624 | 46361 | DSF0001083811
9 | X070 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/20/2024 | 9/19/2025 |  | 561440 | 513722 | 2823 | DSF0001083811
9 | X070 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/20/2024 | 9/19/2025 |  | 104060 | 66820 | 14438 | DSF0001083811
9 | X070 | P.S. 70 - BRONX | SCA Emergency Response | EMERGENCY- COLLAPSED CEILING @ X070 | Construction | In-Progress | 4/3/2024 | EMER |  | EMER | 254186 | 164727 | SCA0000072888
9 | X070 | P.S. 70 - BRONX | SCA IEH | PO18-ABATE (IF NEEDED) 15' OF PIPE INSULATION IN BOILER ROOM. SPRAYED RED | Construction | In-Progress | 12/2/2024 | IEH |  | IEH | 0 | 0 | SCA0000073656
9 | X070 | P.S. 70 - BRONX | DIIT - RESOA | FY10 RESO A DESKTOP COMPUTERS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 1000 | 0 | DSF0000689979
9 | X073 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/15/2021 | 7/28/2021 | 11/24/2021 | 157770 | 183993 | 183993 | DSF0001008821, DSF0001029396
9 | X073 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/8/2021 | 5/26/2022 | 8/26/2022 | 788850 | 469992 | 397685 | DSF0001008821, DSF0001029396
9 | X073 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 8/7/2023 | 2/1/2026 |  | 17749125 | 16431051 | 6672186 | DSF0001008821, DSF0001029396
9 | X073 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 8/7/2023 | 2/1/2026 |  | 1105446 | 620439 | 607812 | DSF0001008821, DSF0001029396
9 | X073 | P.S. 73 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/14/2023 | 9/14/2023 | 11/21/2023 | 19010 | 46283 | 46283 | DSF0001085110
9 | X073 | P.S. 73 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 1/10/2024 | 5/24/2024 | 11/8/2024 | 95049 | 138877 | 22783 | DSF0001085110
9 | X073 | P.S. 73 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2138597 | 2138597 | 70300 | DSF0001085110
9 | X073 | P.S. 73 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 133068 | 133068 | 29934 | DSF0001085110
9 | X073 | P.S. 73 - BRONX | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 2/6/2023 | 6/7/2023 | 9/29/2023 | 0 | 5765 | 5765 | DSF0001036206
9 | X073 | P.S. 73 - BRONX | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | Complete | 10/2/2023 | 10/2/2023 | 10/2/2023 | 45000 | 18027 | 0 | DSF0001036206
9 | X073 | P.S. 73 - BRONX | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 2293 | DSF0001036206
9 | X073 | P.S. 73 - BRONX | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 2388 | DSF0001036206
9 | X073 | P.S. 73 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 7/1/2021 | EMER |  | EMER | 124404 | 124404 | SCA0000070129
9 | X073 | P.S. 73 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001036207
9 | X073 | P.S. 73 - BRONX | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/5/2021 | DOER |  | DOER | 28941 | 0 | DSF0000913492
9 | X073 | P.S. 73 - BRONX | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 6/30/2022 | DOER |  | DOER | 290644 | 0 | DSF0000913493
9 | X082 | I.S. 303 - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/1/2023 | 6/2/2023 | 5/9/2023 | 0 | 12979 | 12979 | DSF0001036216
9 | X082 | I.S. 303 - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 5/18/2023 | 10/4/2023 | 10/3/2023 | 31200 | 44007 | 31642 | DSF0001036216
9 | X082 | I.S. 303 - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | In-Progress | 5/15/2024 | 2/13/2025 |  | 457600 | 227320 | 45253 | DSF0001036216
9 | X082 | I.S. 303 - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 5/15/2024 | 2/13/2025 |  | 31200 | 33690 | 16711 | DSF0001036216
9 | X082 | I.S. 232 - BRONX | SCA IEH | PO18-ABATE (6) 4' SECTIONS OF THE GYM FLOOR TO REPAIR SECTIONS THAT ARE BUCKLING. SOFT CONCRETE FILL | Construction | Complete | 9/22/2023 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000072334
9 | X082 | I.S. 232 - BRONX | SCA IEH | PO18-ONE HOLE IS A 2' X 4' SQUARE WE NEED ABATED AND WE NEED ( 1.25') HOLES DRILLED THRU WALL IN ELE | Construction | In-Progress | 10/8/2024 | IEH |  | IEH | 0 | 0 | SCA0000073471
9 | X082 | I.S. 303 - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 482000 | 482000 | 0 | DSF0001113333
9 | X082 | ACADEMY FOR LANGUAGE & TECH - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 7/25/2023 | FTK |  | FTK | 1090988 | 967253 | DSF0001034943
9 | X082 | I.S. 232 - BRONX | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/27/2020 | DOER |  | DOER | 421013 | 0 | DSF0000890728
9 | X082 | I.S. 303 - BRONX | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | In-Progress | 9/27/2023 | DOER |  | DOER | 92127 | 0 | DSF0001034525
9 | X082 | I.S. 303 - BRONX | DOE - RESOA | RESO A ROOM CONVERSION | Construction | In-Progress | 6/5/2023 | DOER |  | DOER | 21715 | 0 | DSF0001034526
9 | X082 | I.S. 303 - BRONX | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/5/2023 | DOER |  | DOER | 380938 | 0 | DSF0001034527
9 | X082 | ACADEMY FOR LANGUAGE & TECH - X | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113332
9 | X082 | I.S. 232 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/15/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001084850
9 | X082 | I.S. 232 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/22/2024 | DOES |  | DOES | 336067 | 0 | DSF0001085771
9 | X088 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/16/2021 | 9/16/2021 | 8/5/2021 | 51235 | 89854 | 89854 | DSF0001008802, DSF0001008801
9 | X088 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 8/9/2021 | 1/12/2022 | 1/13/2022 | 252730 | 378632 | 360126 | DSF0001008802, DSF0001008801
9 | X088 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 7/5/2022 | 7/3/2024 |  | 5388433 | 5203823 | 5181137 | DSF0001008802, DSF0001008801
9 | X088 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 7/5/2022 | 7/3/2024 |  | 384483 | 837098 | 829934 | DSF0001008802, DSF0001008801
9 | X088 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/6/2019 | 1/6/2020 | 9/3/2019 | 2901 | 2074 | 2074 | DSF0000912743, DSF0000914242
9 | X088 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 9/3/2019 | 2/6/2020 | 1/31/2020 | 13056 | 8340 | 8340 | DSF0000912743, DSF0000914242
9 | X088 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | Complete | 10/5/2020 | 7/1/2021 | 7/15/2021 | 168282 | 225463 | 211956 | DSF0000912743, DSF0000914242
9 | X088 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | Complete | 10/5/2020 | 7/1/2021 | 7/15/2021 | 31190 | 42635 | 42635 | DSF0000912743, DSF0000914242
9 | X088 | P.S. 88 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 296931 | 0 | DSF0001086733
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 7/2/2019 | 11/1/2019 | 7/24/2019 | 2537 | 1166 | 1166 | DSF0000912132
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 7/24/2019 | 12/26/2019 | 12/30/2019 | 11418 | 4719 | 4719 | DSF0000912132
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 10/5/2020 | 7/1/2021 | 7/15/2021 | 147165 | 154131 | 145191 | DSF0000912132
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | Complete | 10/5/2020 | 7/1/2021 | 7/15/2021 | 27276 | 34311 | 34311 | DSF0000912132
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113337
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 45720 | 45720 | 0 | DSF0001113337
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 670560 | 670560 | 0 | DSF0001113337
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45720 | 45720 | 0 | DSF0001113337
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113690
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113690
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113690
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113690
9 | X090 | THE FAMILY SCHOOL - BRONX | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 309491 | 0 | DSF0000890981
9 | X104 | P.S. 199 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 11/5/2021 | 3/28/2022 | 1/30/2023 | 169266 | 144792 | 144792 | DSF0001034194
9 | X104 | P.S. 199 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2/6/2023 | 7/25/2023 | 10/9/2024 | 789909 | 447558 | 400669 | DSF0001034194
9 | X104 | P.S. 199 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | PNS | PNS | PNS | PNS | 12525703 | 12525703 | 576372 | DSF0001034194
9 | X104 | P.S. 199 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | PNS | PNS | PNS | PNS | 1241286 | 1241286 | 101546 | DSF0001034194
9 | X104 | P.S. 199 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 7/12/2022 | 11/28/2022 | 9/20/2023 | 185321 | 351974 | 222287 | DSF0001029994, DSF0001029995, DSF0001029996, DSF0001083865
9 | X104 | P.S. 199 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 9/26/2023 | 3/1/2024 | 10/9/2024 | 926610 | 616090 | 329864 | DSF0001029994, DSF0001029995, DSF0001029996, DSF0001083865
9 | X104 | P.S. 199 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | PNS | PNS | PNS | PNS | 20848720 | 20848720 | 104888 | DSF0001029994, DSF0001029995, DSF0001029996, DSF0001083865
9 | X104 | P.S. 199 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1297252 | 1297252 | 82155 | DSF0001029994, DSF0001029995, DSF0001029996, DSF0001083865
9 | X104 | P.S. 199 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 9/6/2022 | EMER |  | EMER | 1889012 | 1859469 | SCA0000071034
9 | X104 | P.S. 199 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 139500 | 0
9 | X104 | P.S. 199 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 1/5/2021 | DOES |  | DOES | 192500 | 0 | DSF0001029990
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS UPGRADE / WINDOWS / ROOFS / PARAPETS / LIGHTING UPGRADE | Scope | Complete | 10/5/2023 | 3/5/2024 | 3/13/2024 | 487765 | 338444 | 335394 | DSF0001085601, DSF0001112236, DSF0001112235, DSF0001112234, DSF0001112232, DSF0001112237, DSF0001136471
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS UPGRADE / WINDOWS / ROOFS / PARAPETS / LIGHTING UPGRADE | Design | In-Progress | 8/12/2024 | 3/11/2025 |  | 2344122 | 2344122 | 477740 | DSF0001085601, DSF0001112236, DSF0001112235, DSF0001112234, DSF0001112232, DSF0001112237, DSF0001136471
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS UPGRADE / WINDOWS / ROOFS / PARAPETS / LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | 44601201 | 44601201 | 164045 | DSF0001085601, DSF0001112236, DSF0001112235, DSF0001112234, DSF0001112232, DSF0001112237, DSF0001136471
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS UPGRADE / WINDOWS / ROOFS / PARAPETS / LIGHTING UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 3583353 | 3583353 | 124660 | DSF0001085601, DSF0001112236, DSF0001112235, DSF0001112234, DSF0001112232, DSF0001112237, DSF0001136471
9 | X109 | P.S. 109 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 11/14/2024 | 2/18/2025 |  | 28215 | 28215 | 0 | DSF0001112064
9 | X109 | P.S. 109 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | PNS | PNS | PNS | PNS | 131670 | 131670 | 0 | DSF0001112064
9 | X109 | P.S. 109 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2087908 | 2087908 | 0 | DSF0001112064
9 | X109 | P.S. 109 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 206910 | 206910 | 0 | DSF0001112064
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 6/3/2019 | 10/2/2019 | 6/24/2019 | 12141 | 4568 | 4568 | DSF0000911985
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 6/24/2019 | 11/25/2019 | 12/3/2019 | 54636 | 18313 | 18313 | DSF0000911985
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 10/5/2020 | 7/1/2021 | 7/15/2021 | 704194 | 562576 | 403252 | DSF0000911985
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | Complete | 10/5/2020 | 7/1/2021 | 7/15/2021 | 130519 | 95438 | 95077 | DSF0000911985
9 | X109 | P.S. 109 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113694
9 | X109 | P.S. 109 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113694
9 | X109 | P.S. 109 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113694
9 | X109 | P.S. 109 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113694
9 | X109 | P.S. 109 - BRONX | SCA IEH | PO18-CELLAR FAN ROOM, ABATE 30 L.F. PIPE INSULATION PAINTED RED BOILER ROOM, ABATE 14 L.F. PIPE INSU | Construction | Complete | 6/26/2024 | IEH | 12/23/2024 | IEH | 0 | 0 | SCA0000073088
9 | X109 | P.S. 109 - BRONX | Fast Track Projects | PAVED AREAS- BLACKTOP | Construction | In-Progress | 10/2/2019 | FTK |  | FTK | 274731 | 273605 | DSF0000908063
9 | X109 | P.S. 109 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/8/2024 | DIIR | 12/5/2024 | DIIR | 335000 | 335000 | DSF0001034063
9 | X109 | P.S. 109 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/18/2024 | DIIR | 12/5/2024 | DIIR | 106000 | 106000 | DSF0001086749
9 | X109 | P.S. 109 - BRONX | DOE - RESOA | FY21 RESO A ACCESSIBILITY | Construction | In-Progress | 6/30/2024 | DOER |  | DOER | 335667 | 0 | DSF0001007903
9 | X109 | P.S. 109 - BRONX | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 375000 | 0 | DSF0001113356
9 | X109 | P.S. 109 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 185872 | 0 | DSF0000795508
9 | X110 | P.S. 110 - BRONX | SCA CIP | REPAIR RETAINING WALLS | Scope | Complete | 8/2/2018 | 12/19/2018 | 12/3/2018 | 15503 | 148836 | 141535 | DSF0001085148
9 | X110 | P.S. 110 - BRONX | SCA CIP | REPAIR RETAINING WALLS | Design | Complete | 5/3/2022 | 5/12/2023 | 5/10/2023 | 77514 | 77633 | 71124 | DSF0001085148
9 | X110 | P.S. 110 - BRONX | SCA CIP | REPAIR RETAINING WALLS | Construction | PNS | PNS | PNS | PNS | 1744061 | 1744061 | 82841 | DSF0001085148
9 | X110 | P.S. 110 - BRONX | SCA CIP | REPAIR RETAINING WALLS | CM,F&E | PNS | PNS | PNS | PNS | 108519 | 108519 | 22353 | DSF0001085148
9 | X110 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/28/2019 | 11/16/2022 | 2/8/2023 | 150499 | 178507 | 175850 | DSF0000912343, DSF0001002907, DSF0001030116, DSF0001030117
9 | X110 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/9/2023 | 7/13/2023 | 5/11/2023 | 748896 | 685297 | 539008 | DSF0000912343, DSF0001002907, DSF0001030116, DSF0001030117
9 | X110 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 2/5/2024 | 8/2/2026 |  | 16538847 | 15222389 | 1897789 | DSF0000912343, DSF0001002907, DSF0001030116, DSF0001030117
9 | X110 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2/5/2024 | 8/2/2026 |  | 1080486 | 180206 | 177550 | DSF0000912343, DSF0001002907, DSF0001030116, DSF0001030117
9 | X110 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/6/2023 | 11/3/2023 | 7/18/2023 | 5400 | 1094 | 1094 | DSF0001035043
9 | X110 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/18/2023 | 1/16/2024 | 10/11/2023 | 24300 | 4377 | 4377 | DSF0001035043
9 | X110 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/2/2024 | 11/27/2024 |  | 313200 | 281947 | 2747 | DSF0001035043
9 | X110 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/2/2024 | 11/27/2024 |  | 127919 | 102558 | 74036 | DSF0001035043
9 | X110 | P.S. 110 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 8/1/2018 | EMER |  | EMER |  | 0 | SCA0000053026
9 | X110 | P.S. 110 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 8/10/2020 | FTK |  | FTK | 364147 | 351823 | DSF0000911986
9 | X110 | P.S. 110 - BRONX | DIIT - RESOA | FY 11 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 79187 | 0 | DSF0000801059
9 | X110 | P.S. 110 - BRONX | DOE - RESOA | FY22 RESO A FENCING | Construction | In-Progress | 10/15/2022 | DOER |  | DOER | 181144 | 0 | DSF0001034064
9 | X110 | M.S. 128 - BRONX | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 446001 | 0 | DSF0001036225
9 | X110 | P.S. 110 - BRONX | DOE - RESOA | RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 6/28/2024 | DOER |  | DOER | 60376 | 0 | DSF0001087228
9 | X110 | P.S. 110 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113357
9 | X110 | P.S. 110 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/5/2023 | DOES | 8/23/2023 | DOES | 452640 |  | DSF0001035140
9 | X110 | P.S. 110 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 7/10/2024 | DOES | 65832 | 7724 | DSF0001084851
9 | X114 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 9/28/2018 | 3/6/2019 | 11/15/2018 | 99750 | 95139 | 95139 | DSF0000798352, DSF0000795596
9 | X114 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 11/30/2018 | 5/3/2019 | 4/12/2019 | 399000 | 414928 | 407210 | DSF0000798352, DSF0000795596
9 | X114 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/22/2019 | 7/20/2021 |  | 7481250 | 7356053 | 6309398 | DSF0000798352, DSF0000795596
9 | X114 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/22/2019 | 7/20/2021 |  | 465500 | 1402154 | 1380284 | DSF0000798352, DSF0000795596
9 | X114 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/6/2023 | 11/3/2023 | 7/18/2023 | 4136 | 1074 | 1074 | DSF0001035057
9 | X114 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/18/2023 | 1/16/2024 | 10/11/2023 | 18612 | 4296 | 4296 | DSF0001035057
9 | X114 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/2/2024 | 11/27/2024 |  | 239888 | 218456 | 3088 | DSF0001035057
9 | X114 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/2/2024 | 11/27/2024 |  | 108744 | 89295 | 65041 | DSF0001035057
9 | X114 | P.S. 114 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113361
9 | X114 | P.S. 114 - BRONX | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001036231
9 | X117 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 8/17/2020 | 1/21/2021 | 1/4/2021 | 74140 | 90731 | 90731 | DSF0000961019, DSF0000953914
9 | X117 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/5/2021 | 7/30/2021 | 7/28/2021 | 370700 | 373818 | 354181 | DSF0000961019, DSF0000953914
9 | X117 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 6/15/2022 | 6/13/2024 |  | 8340750 | 7506695 | 5199335 | DSF0000961019, DSF0000953914
9 | X117 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 6/15/2022 | 6/13/2024 |  | 518980 | 651679 | 645433 | DSF0000961019, DSF0000953914
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | SCA CIP RESOA | FY16 RESO A SCIENCE LAB UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000822725
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | SCA CIP RESOA | FY16 RESO A SCIENCE LAB UPGRADES | Design | PNS | PNS | PNS | PNS | 60027 | 60027 | 0 | DSF0000822725
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | SCA CIP RESOA | FY16 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | 880400 | 880400 | 0 | DSF0000822725
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | SCA CIP RESOA | FY16 RESO A SCIENCE LAB UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 60027 | 60027 | 0 | DSF0000822725
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113364
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 135000 | 135000 | 0 | DSF0001113364
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 1980000 | 1980000 | 0 | DSF0001113364
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 135000 | 135000 | 0 | DSF0001113364
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113695
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113695
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113695
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113695
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300620 | 0 | DSF0001036234
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/19/2024 | DOER |  | DOER | 65507 | 0 | DSF0001086754
9 | X117 | I.S. 117 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/17/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001085055
9 | X126 | P.S. 126 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 11/10/2021 | 3/31/2022 | 1/19/2023 | 118408 | 202042 | 199536 | DSF0001034195, DSF0001081137
9 | X126 | P.S. 126 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 1/20/2023 | 7/10/2023 | 9/12/2024 | 592044 | 398394 | 378928 | DSF0001034195, DSF0001081137
9 | X126 | P.S. 126 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 13321004 | 13321004 | 214279 | DSF0001034195, DSF0001081137
9 | X126 | P.S. 126 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 828862 | 828862 | 42584 | DSF0001034195, DSF0001081137
9 | X126 | P.S. 126 - BRONX | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 12/12/2023 | 4/29/2024 | 9/25/2024 | 212590 | 159175 | 84211 | DSF0001109105, DSF0001136764, DSF0001136761, DSF0001136765
9 | X126 | P.S. 126 - BRONX | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | In-Progress | 11/6/2024 | 4/11/2025 |  | 987507 | 987507 | 11506 | DSF0001109105, DSF0001136764, DSF0001136761, DSF0001136765
9 | X126 | P.S. 126 - BRONX | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 15618340 | 15618340 | 15285 | DSF0001109105, DSF0001136764, DSF0001136761, DSF0001136765
9 | X126 | P.S. 126 - BRONX | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1609914 | 1609914 | 39403 | DSF0001109105, DSF0001136764, DSF0001136761, DSF0001136765
9 | X126 | P.S. 126 - BRONX | SCA IEH | PO18-ABATE BATHROOM WALL IN ROOM 232 APPROX. 18 1/2 X 30 | Construction | In-Progress | 7/27/2023 | IEH |  | IEH | 0 | 0 | SCA0000072169
9 | X126 | P.S. 126 - BRONX | SCA IEH | PO18-REMOVE 12' OF ACM IN BASEMENT CRAWLSPACE BOILER ROOM #4. SPRAYED BLACK FOR ID. | Construction | Complete | 11/4/2024 | IEH | 11/5/2024 | IEH | 0 | 0 | SCA0000073563
9 | X126 | P.S. 126 - BRONX | DIIT - RESOA | FY 11 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 59397 | 0 | DSF0000801057
9 | X126 | P.S. 126 - BRONX | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 6/1/2023 | DOER |  | DOER | 27535 | 0 | DSF0001034067
9 | X126 | P.S. 126 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 220677 | 0 | DSF0001036239
9 | X126 | P.S. 126 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 188137 | 0 | DSF0000795813
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113374
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 36000 | 36000 | 0 | DSF0001113374
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 528000 | 528000 | 0 | DSF0001113374
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 36000 | 36000 | 0 | DSF0001113374
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113699
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113699
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113699
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113699
9 | X132 | P.S. 132 - BRONX | SCA IEH | PO18-ABATE/REPLACE CEILING/WALL TILES KITCHEN VESTIBULE (BY EXIT 6): CERAMIC TILE MASTIC Y* - ASSUME | Construction | Complete | 8/5/2024 | IEH | 8/9/2024 | IEH | 0 | 0 | SCA0000073234
9 | X132 | P.S. 132 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001035285
9 | X132 | P.S. 132 - BRONX | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 10/13/2023 | DOES |  | DOES | 177587 | 0 | DSF0000819092
9 | X132 | P.S. 132 - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 7/20/2018 | DOES |  | DOES | 351661 | 0 | DSF0000889373
9 | X132 | P.S. 132 - BRONX | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 1/20/2021 | DOES |  | DOES | 85761 | 0 | DSF0000960494
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | SCA IEH | PO18-CHARTER SCHOOL ABATEMENT - REMOVE LEDGES AND REPLACE FLOORING IN ROOMS 402, 403, 404, 405 406 A | Construction | Complete | 5/28/2024 | IEH | 8/29/2024 | IEH | 0 | 0 | SCA0000073026
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 9/10/2019 | FTK |  | FTK | 142933 | 141396 | DSF0000868260, DSF0000912402
9 | X145 | M.S. 593 - BRONX | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 2/2/2021 | FTK |  | FTK | 502510 | 373077 | DSF0000913033, DSF0000960465
9 | X145 | M.S. 594 - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 125000 | 0 | DSF0000914200
9 | X145 | M.S. 593 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 11/20/2024 | DIIR | 50000 | 50000 | DSF0001007930
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 100000 | 89765 | DSF0001086773
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | DOE - RESOA | FY21 RESO A COURTYARD UPGRADE | Construction | In-Progress | 6/29/2023 | DOER |  | DOER | 315765 | 0 | DSF0001008466
9 | X145 | I.S. 145 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/15/2016 | DOES |  | DOES | 172211 | 0 | DSF0000796122
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 219564 | 0 | DSF0001034467
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/6/2024 | DOES | 11/20/2024 | DOES | 65832 |  | DSF0001085059
9 | X147 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/15/2023 | 10/16/2023 | 9/22/2023 | 9899 | 16018 | 12505 | DSF0001083796
9 | X147 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/4/2023 | 3/5/2024 | 4/4/2024 | 44546 | 61332 | 50353 | DSF0001083796
9 | X147 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/25/2024 | 9/24/2025 |  | 574142 | 537407 | 35912 | DSF0001083796
9 | X147 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/25/2024 | 9/24/2025 |  | 106414 | 75732 | 22277 | DSF0001083796
9 | X147 | I.S. 339 - BRONX | SCA IEH | PO18-REPLACE DAMAGE FLOOR TILE PRINCIPAL OFFICE ACM YES LOCATION ROOM 248 SECOND FLOOR DESCRIPTION F | Construction | Complete | 3/6/2024 | IEH | 7/20/2024 | IEH | 0 | 0 | SCA0000072794
9 | X147 | I.S. 339 - BRONX | SCA IEH | PO18-ABATE/REPLACE ACM FLOOR TILES ROOM 429 | Construction | Complete | 7/31/2024 | IEH | 9/22/2024 | IEH | 0 | 0 | SCA0000073208
9 | X147 | I.S. 339 - BRONX | SCA IEH | PO18-ABATE/REPLACE ACM FLOOR TILES ROOM 232 | Construction | Complete | 8/9/2024 | IEH | 10/1/2024 | IEH | 0 | 0 | SCA0000073269
9 | X147 | I.S. 339 - BRONX | SCA IEH | PO18-STAIRCASE D BETWEEN 4TH FLOOR AND 3RD FLOOR LANDING DAMAGE FLOOR TILE (TRIP HAZARD IS PRESENT) | Construction | Complete | 8/14/2024 | IEH | 11/6/2024 | IEH | 0 | 0 | SCA0000073288
9 | X147 | I.S. 313 - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 233000 | 0 | DSF0000913695
9 | X147 | I.S. 339 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086776
9 | X147 | I.S. 339 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/30/2023 | DOES | 9/29/2023 | DOES | 475126 | 413261 | DSF0001035175
9 | X147 | I.S. 339 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/22/2024 | DOES | 8/29/2024 | DOES | 65832 |  | DSF0001084864
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 11/21/2018 | 4/10/2019 | 2/11/2020 | 15826 | 61429 | 61409 | DSF0000908694
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2/11/2020 | 7/13/2020 | 5/14/2021 | 71215 | 144147 | 127542 | DSF0000908694
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 1/25/2022 | 1/24/2023 |  | 917879 | 817220 | 220105 | DSF0000908694
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 1/25/2022 | 1/24/2023 |  | 170124 | 178771 | 159247 | DSF0000908694
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/10/2024 | 10/25/2024 | 10/4/2024 | 163281 | 88150 | 86615 | DSF0001081507, DSF0001137141
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 11/8/2024 | 4/15/2025 |  | 801746 | 801746 | 227072 | DSF0001081507, DSF0001137141
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 16675924 | 16675924 | 23581 | DSF0001081507, DSF0001137141
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1157627 | 1157627 | 17423 | DSF0001081507, DSF0001137141
9 | X148 | I.S. 219 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 4/30/2021 | 8/31/2021 | 8/6/2021 | 0 | 20584 | 20584 | DSF0000913505
9 | X148 | I.S. 219 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 8/17/2021 | 1/21/2022 | 2/10/2022 | 67074 | 75848 | 74293 | DSF0000913505
9 | X148 | I.S. 219 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/13/2022 | 9/12/2023 |  | 983748 | 968065 | 821135 | DSF0000913505
9 | X148 | I.S. 219 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 9/13/2022 | 9/12/2023 |  | 67074 | 102991 | 62634 | DSF0000913505
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/22/2023 | 6/21/2023 | 11/9/2023 | 0 | 106546 | 68746 | DSF0001036257
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 8/7/2024 | 12/24/2024 |  | 143830 | 168755 | 14037 | DSF0001036257
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 2109501 | 2109501 | 3733 | DSF0001036257
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 143830 | 143830 | 3735 | DSF0001036257
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 5/25/2023 | 8/25/2023 | 11/9/2023 | 0 | 610 | 610 | DSF0001036258
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 11/22/2024 | 3/26/2025 |  | 590 | 2440 | 2440 | DSF0001036258
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 8659 | 8659 | 0 | DSF0001036258
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 590 | 2496 | 2496 | DSF0001036258
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA IEH | PO18-ABATE ACM PIPE INSULATION IN BASMENT PIPE CHASE APPROX: 5 FT EACH | Construction | Complete | 9/3/2024 | IEH | 10/29/2024 | IEH | 0 | 0 | SCA0000073342
9 | X148 | I.S. 215 - BRONX | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 10/27/2023 | DOER | 1/22/2024 | DOER | 195522 | 937 | DSF0001034083
9 | X148 | I.S. 215 - BRONX | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/5/2024 | DOER |  | DOER | 346105 | 0 | DSF0001086777
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/25/2024 | DOES | 11/4/2024 | DOES | 65832 |  | DSF0001084865
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087130
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087130
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087130
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087130
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/23/2019 | 12/1/2021 | 12/3/2021 | 0 | 25990 | 25990 | DSF0000890967, DSF0000912344
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 12/3/2021 | 1/18/2022 | 1/13/2022 | 111956 | 159049 | 142435 | DSF0000890967, DSF0000912344
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | Complete | 7/6/2022 | 7/5/2023 | 3/12/2024 | 1642030 | 1674385 | 1540975 | DSF0000890967, DSF0000912344
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 7/6/2022 | 7/5/2023 | 3/12/2024 | 111956 | 181914 | 181914 | DSF0000890967, DSF0000912344
9 | X166 | BRONX EARLY COLLEGE ACADEMY | SCA IEH | PO18-ABATE FLOOR IN ROOM #420 | Construction | Complete | 8/9/2024 | IEH | 8/17/2024 | IEH | 0 | 0 | SCA0000073272
9 | X166 | SCIENCE AND TECHNOLOGY ACADEMY: A MOTT HALL SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/30/2024 | DIIR | 7/9/2024 | DIIR | 100000 | 12698 | DSF0001033427
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/20/2023 | DOER |  | DOER | 1400000 | 0 | DSF0001086783
9 | X166 | SCIENCE AND TECHNOLOGY ACADEMY: A MOTT HALL SCHOOL | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 7/16/2021 | DOES |  | DOES | 183729 | 0 | DSF0000865993
9 | X166 | BRONX EARLY COLLEGE ACADEMY | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 2/10/2021 | DOES |  | DOES | 193120 | 0 | DSF0000960498
9 | X166 | BRONX EARLY COLLEGE ACADEMY | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/22/2024 | DOES |  | DOES | 361789 | 0 | DSF0001085776
9 | X170 | P.S. 170 - BRONX | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/26/2023 | DOER |  | DOER | 199056 | 0 | DSF0001007904
9 | X170 | P.S. 170 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/8/2024 | DOER |  | DOER | 17781 | 0 | DSF0001086786
9 | X172 | P.S. 11 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 12/7/2023 | 4/24/2024 | 11/6/2024 | 35829 | 42961 | 42961 | DSF0001081884, DSF0001137514
9 | X172 | P.S. 11 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 12/4/2024 | 5/7/2025 |  | 173374 | 173374 | 16934 | DSF0001081884, DSF0001137514
9 | X172 | P.S. 11 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 3364053 | 3364053 | 0 | DSF0001081884, DSF0001137514
9 | X172 | P.S. 11 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 256578 | 256578 | 18384 | DSF0001081884, DSF0001137514
9 | X172 | P.S. 11 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/23/2024 | IEH | 8/28/2024 | IEH | 0 | 0 | SCA0000073162
9 | X172 | P.S. 11 - BRONX | DOE - RESOA | FY21 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001007912
9 | X229 | I.S. 229 - BRONX | SCA IEH | PO18-SPACE ID: 2154 CLASSROOM 154 TEST AND ABATE DAMAGED 12' X 12' FLOOR TILES STORAGE ROOM | Construction | Complete | 11/22/2024 | IEH | 12/27/2024 | IEH | 0 | 0 | SCA0000073636
9 | X229 | THE NEW AMERICAN ACADEMY AT ROBERTO CLEMENT STATE PARK - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001113399
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2/1/2019 | 6/18/2019 | 1/21/2022 | 60992 | 67704 | 67704 | DSF0000887848, DSF0001031531, DSF0001034495, DSF0001031528
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Design | Complete | 2/2/2022 | 7/5/2022 | 5/11/2022 | 299610 | 297020 | 297020 | DSF0000887848, DSF0001031531, DSF0001034495, DSF0001031528
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Construction | Complete | 9/21/2022 | 3/13/2024 | 5/3/2024 | 6278234 | 5775040 | 5551039 | DSF0000887848, DSF0001031531, DSF0001034495, DSF0001031528
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | CM,F&E | Complete | 9/21/2022 | 3/13/2024 | 5/3/2024 | 467092 | 227259 | 226553 | DSF0000887848, DSF0001031531, DSF0001034495, DSF0001031528
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/9/2023 | 6/9/2023 | 3/15/2023 | 4440 | 5165 | 5165 | DSF0001034647
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/15/2023 | 9/8/2023 | 5/3/2023 | 19980 | 20659 | 20659 | DSF0001034647
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/12/2023 | 12/10/2024 |  | 257520 | 229765 | 2297 | DSF0001034647
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/12/2023 | 12/10/2024 |  | 148396 | 127086 | 60339 | DSF0001034647
9 | X235 | P.S./I.S. 218 - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/15/2024 | DOER |  | DOER | 223000 | 0 | DSF0001086806
9 | X236 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | SCA CIP | PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 7/25/2023 | 32629 | 70153 | 39666 | DSF0001031545, DSF0001031546, DSF0001031547
9 | X236 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | SCA CIP | PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 9/7/2023 | 2/12/2024 | 4/10/2024 | 146829 | 90327 | 81818 | DSF0001031545, DSF0001031546, DSF0001031547
9 | X236 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | SCA CIP | PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 1892461 | 1892461 | 41485 | DSF0001031545, DSF0001031546, DSF0001031547
9 | X236 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | SCA CIP | PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 350758 | 350758 | 37049 | DSF0001031545, DSF0001031546, DSF0001031547
9 | X236 | P.S. 163 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/8/2024 | IEH | 7/24/2024 | IEH | 0 | 0 | SCA0000073119
9 | X240 | I.S. 327 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036278
9 | X240 | I.S. 327 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036278
9 | X240 | I.S. 327 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036278
9 | X240 | I.S. 327 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036278
9 | X240 | I.S. 327 - BRONX | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 91538 | 0 | DSF0001036277
9 | X256 | HARRIET TUBMAN CHARTER SCHOOL - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0001007924
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 203732 | 0 | DSF0000960379
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/12/2024 | DIIR | 10/3/2024 | DIIR | 100000 | 100000 | DSF0001086809
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113400
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001036279
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 375000 | 0 | DSF0001113430
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 375000 | 0 | DSF0001113817
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/22/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084873
9 | X338 | P.S. 204 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 300000 | 0 | DSF0001034080
9 | X338 | P.S. 204 - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 5/19/2023 | DOER |  | DOER | 49205 | 0 | DSF0001034081
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | Scope | Complete | 9/18/2014 | 2/6/2015 | 2/6/2015 | 586154 | 423610 | 408018 | DSF0000800334, DSF0000842000, DSF0000844751, DSF0000844752, DSF0000844753
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | Design | Complete | 7/29/2016 | 1/3/2017 | 5/15/2017 | 2327215 | 2061826 | 1702585 | DSF0000800334, DSF0000842000, DSF0000844751, DSF0000844752, DSF0000844753
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | Construction | In-Progress | 7/24/2017 | 12/9/2021 |  | 42073721 | 43027359 | 38685933 | DSF0000800334, DSF0000842000, DSF0000844751, DSF0000844752, DSF0000844753
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | CM,F&E | In-Progress | 7/24/2017 | 12/9/2021 |  | 2961572 | 3249004 | 3175058 | DSF0000800334, DSF0000842000, DSF0000844751, DSF0000844752, DSF0000844753
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADES | Scope | Complete | 11/24/2021 | 8/15/2023 | 9/8/2023 | 18702 | 41718 | 41718 | DSF0001004333, DSF0001085106
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADES | Design | Complete | 9/11/2023 | 1/11/2024 | 12/15/2023 | 92656 | 149621 | 104104 | DSF0001004333, DSF0001085106
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADES | Construction | In-Progress | 12/2/2024 | 5/5/2026 |  | 2011105 | 1811858 | 9008 | DSF0001004333, DSF0001085106
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 12/2/2024 | 5/5/2026 |  | 137296 | 56183 | 54958 | DSF0001004333, DSF0001085106
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/29/2021 | 9/6/2022 | 10/11/2022 | 35710 | 199522 | 199522 | DSF0001032950, DSF0001034475
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 10/12/2022 | 2/13/2023 | 12/22/2023 | 177477 | 412499 | 344187 | DSF0001032950, DSF0001034475
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 8/22/2024 | 8/11/2026 |  | 3900656 | 3578481 | 65309 | DSF0001032950, DSF0001034475
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 8/22/2024 | 8/11/2026 |  | 257995 | 141081 | 137977 | DSF0001032950, DSF0001034475
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034121
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034121
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034121
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034121
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034122
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 53294 | 53294 | 0 | DSF0001034122
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 781645 | 792000 | 0 | DSF0001034122
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 53294 | 54000 | 0 | DSF0001034122
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOOR TILES 2ND FLOOR HALLWAY | Construction | Complete | 8/5/2024 | IEH | 12/23/2024 | IEH | 0 | 0 | SCA0000073232
9 | X400 | HS FOR VIOLIN AND DANCE - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001035315
9 | X400 | HS FOR VIOLIN AND DANCE - BRONX | Fast Track Projects | CTF ROOM CONVERSION | Construction | Complete | 8/1/2022 | FTK | 10/20/2022 | FTK | 374018 | 359736 | DSF0001009317
9 | X400 | BRONX INTERNATIONAL - BRONX | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 6/6/2022 | FTK |  | FTK | 1244721 | 1152037 | DSF0001009318
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 8/11/2022 | FTK |  | FTK | 353651 | 343277 | DSF0001034300
9 | X400 | BRONX INTERNATIONAL - BRONX | Fast Track Projects | LSP LIGHTING UPGRADE | Construction | In-Progress | 12/27/2022 | FTK |  | FTK | 1825094 | 10904 | DSF0001034193
9 | X400 | HS FOR VIOLIN AND DANCE - BRONX | Fast Track Projects | LSP- INTERIOR SPACES | Construction | In-Progress | 7/22/2022 | FTK |  | FTK | 164788 | 153562 | DSF0001034156
9 | X400 | BRONX INTERNATIONAL - BRONX | Fast Track Projects | LSP- GYM UPGRADE | Construction | In-Progress | 7/12/2022 | FTK |  | FTK | 197850 | 176919 | DSF0001034207
9 | X400 | BRONX INTERNATIONAL - BRONX | Fast Track Projects | LSP- INTERIOR SPACES FOR ROOM 501 | Construction | In-Progress | 7/12/2022 | FTK |  | FTK | 125369 | 91239 | DSF0001034310
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 130000 | 0 | DSF0001086821
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 8/14/2024 | DIIR | 10/1/2024 | DIIR | 200000 | 200000 | DSF0001086822
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 263513 | 0 | DSF0001034093
9 | X400 | HS FOR VIOLIN AND DANCE - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086823
9 | X400 | BRONX INTERNATIONAL - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/27/2019 | DOES |  | DOES | 246546 | 0 | DSF0000891063
9 | X400 | BRONX INTERNATIONAL - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/18/2024 | DOES | 11/27/2024 | DOES | 65832 |  | DSF0001085067
9 | X410 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 1/23/2023 | 5/23/2023 | 3/28/2023 | 11680 | 16689 | 16689 | DSF0001083788
9 | X410 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 3/31/2023 | 9/29/2023 | 8/2/2023 | 52560 | 51366 | 36984 | DSF0001083788
9 | X410 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 3/29/2024 | 3/28/2025 |  | 677440 | 597449 | 5609 | DSF0001083788
9 | X410 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 3/29/2024 | 3/28/2025 |  | 125560 | 79438 | 45604 | DSF0001083788
9 | X410 | NEW DIRECTIONS SECONDARY SCHOOL | DIIT - RESOA | FY 11 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 49571 | 0 | DSF0000801061
9 | X410 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176099 | 0 | DSF0001034135
9 | X410 | DREAMYARD PREPARATORY SCHOOL | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086825
9 | X410 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086826
9 | X410 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 8/5/2022 | DOES | 11/15/2022 | DOES | 129517 | 106515 | DSF0001034273
9 | X410 | HS OF BUSINESS - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/12/2023 | DOES | 10/18/2023 | DOES | 852629 | 220000 | DSF0001035178
9 | X410 | HS OF BUSINESS - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/19/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085070
9 | X411 | HS OF BUSINESS - BRONX | DOE - RESOA | FY24 RESO A ATHLETIC FIELDS | Construction | In-Progress | 4/1/2024 | DOER |  | DOER | 4135256 | 0 | DSF0001086827
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/30/2022 | 11/16/2022 | 4/3/2024 | 133228 | 245227 | 86846 | DSF0001032073, DSF0001032074, DSF0001032075, DSF0001110768
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | In-Progress | 8/2/2024 | 1/7/2025 |  | 653250 | 653250 | 206400 | DSF0001032073, DSF0001032074, DSF0001032075, DSF0001110768
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 14279067 | 14279067 | 78159 | DSF0001032073, DSF0001032074, DSF0001032075, DSF0001110768
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 1032523 | 1032523 | 77176 | DSF0001032073, DSF0001032074, DSF0001032075, DSF0001110768
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/6/2023 | 6/7/2023 | 6/27/2023 | 0 | 11044 | 11044 | DSF0001036297
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 7/5/2023 | 11/20/2023 | 11/21/2023 | 30000 | 34311 | 816 | DSF0001036297
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001036297
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 2297 | DSF0001036297
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 176000 | 176000 | 0 | DSF0001113423
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 446766 | 0 | DSF0001086845
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 598429 | 0 | DSF0000912204
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/8/2023 | DOES | 8/23/2023 | DOES | 529323 | 520002 | DSF0001035148
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/23/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085081
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/21/2024 | 3/26/2025 | 11/25/2024 | 0 | 1785 | 1785 | DSF0001113424
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | In-Progress | 11/25/2024 | 5/22/2025 |  | 30000 | 28215 | 7139 | DSF0001113424
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001113424
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001113424
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113706
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113706
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113706
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113706
9 | X468 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | Scope | Complete | 8/20/2019 | 1/14/2020 | 1/15/2020 | 1150660 | 842974 | 842974 | DSF0000889040
9 | X468 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | Design | Complete | 1/16/2020 | 8/31/2020 | 5/4/2021 | 5177970 | 3149204 | 2585125 | DSF0000889040
9 | X468 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | Construction | Complete | 12/20/2021 | 9/3/2024 | 7/3/2024 | 65299955 | 61885654 | 59865155 | DSF0000889040
9 | X468 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 12/20/2021 | 9/3/2024 | 7/3/2024 | 9205280 | 6925286 | 5433270 | DSF0000889040
9 | X496 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | Scope | Complete | 6/13/2019 | 11/29/2019 | 12/5/2019 | 1595980 | 1110730 | 1094593 | DSF0000889664, DSF0000889664
9 | X496 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | Design | Complete | 12/6/2019 | 6/15/2020 | 10/28/2021 | 7181910 | 5275840 | 4223732 | DSF0000889664, DSF0000889664
9 | X496 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | Construction | Complete | 5/18/2022 | 9/3/2024 | 8/28/2024 | 90571865 | 87433942 | 76110662 | DSF0000889664, DSF0000889664
9 | X496 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | CM,Art,F&E | Complete | 5/18/2022 | 9/3/2024 | 8/28/2024 | 12767840 | 9343923 | 7483498 | DSF0000889664, DSF0000889664
9 | X582 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 91698 | 0 | DSF0001086849
9 | X782 | THE HIGHBRIDGE GREEN SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113707
9 | X782 | THE HIGHBRIDGE GREEN SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113707
9 | X782 | THE HIGHBRIDGE GREEN SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113707
9 | X782 | THE HIGHBRIDGE GREEN SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113707
9 | X851 | P.S. 53 - BRONX | SCA CIP | PS53X @ X851/X874 OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 7/24/2024 | 10/23/2024 | 10/8/2024 | 52694 | 164367 | 52167 | DSF0001112388
9 | X851 | P.S. 53 - BRONX | SCA CIP | PS53X @ X851/X874 OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | In-Progress | 11/15/2024 | 4/4/2025 |  | 245906 | 245906 | 142332 | DSF0001112388
9 | X851 | P.S. 53 - BRONX | SCA CIP | PS53X @ X851/X874 OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 3899372 | 3899372 | 1090 | DSF0001112388
9 | X851 | P.S. 53 - BRONX | SCA CIP | PS53X @ X851/X874 OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 386424 | 386424 | 8965 | DSF0001112388
9 | X851 | P.S. 53 - BRONX | DOE - RESOA | FY21 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001007913
9 | X876 | BRONX LEADERSHIP ACADEMY - X | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086861
9 | X909 | X723 SPED - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/26/2023 | DOES | 11/15/2024 | DOES | 50832 |  | DSF0001085581
9 | X927 | X723 SPED - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/23/2024 | IEH | 8/6/2024 | IEH | 0 | 0 | SCA0000073166
9 | X970 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 2/24/2020 | 7/8/2020 | 11/29/2021 | 90790 | 81337 | 79684 | DSF0000960683
9 | X970 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | Design | Complete | 12/8/2021 | 5/11/2022 | 5/10/2022 | 453950 | 369014 | 334825 | DSF0000960683
9 | X970 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | Construction | In-Progress | 9/1/2022 | 8/15/2025 |  | 10213875 | 9315716 | 7974002 | DSF0000960683
9 | X970 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | CM,F&E | In-Progress | 9/1/2022 | 8/15/2025 |  | 636178 | 236456 | 230928 | DSF0000960683
9 | X970 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 3/22/2022 | 7/20/2022 | 4/12/2022 | 3732 | 3456 | 3456 | DSF0001034365
9 | X970 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | Design | Complete | 4/12/2022 | 10/5/2022 | 7/27/2022 | 16793 | 13824 | 13824 | DSF0001034365
9 | X970 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 4/14/2023 | 2/7/2024 |  | 216439 | 205597 | 150032 | DSF0001034365
9 | X970 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 4/14/2023 | 2/7/2024 |  | 194338 | 189756 | 118091 | DSF0001034365
9 | X970 | MOTT HALL BRONX HS - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 300000 | 300000 | 0 | DSF0001113442
9 | X970 | VALIDUS PREPRATORY ACADEMY -X | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 306000 | 0 | DSF0001113441
9 | X970 | I.S. 241 - BRONX | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/30/2022 | DOER |  | DOER | 646553 | 0 | DSF0001007914
9 | X970 | I.S. 241 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 516339 | 0 | DSF0001085779
9 | XADW | BRONX CHARTER SCHOOL FOR EXCELLENCE 5 | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086865
9 | XAIN | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | Scope | Complete | 3/10/2021 | 1/13/2022 | 4/11/2022 | 23164 | 88262 | 57635 | DSF0001008763, DSF0001009219
9 | XAIN | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | Design | Complete | 4/11/2022 | 8/10/2022 | 5/11/2022 | 114030 | 115828 | 25423 | DSF0001008763, DSF0001009219
9 | XAIN | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | Construction | In-Progress | 3/5/2024 | 9/2/2025 |  | 2410555 | 2345271 | 625953 | DSF0001008763, DSF0001009219
9 | XAIN | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | CM,F&E | In-Progress | 3/5/2024 | 9/2/2025 |  | 175599 | 347124 | 229478 | DSF0001008763, DSF0001009219
10 | X003 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/6/2022 | 2/9/2023 | 10/18/2022 | 4464 | 9077 | 9077 | DSF0001034602
10 | X003 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/18/2022 | 4/17/2023 | 2/15/2023 | 20088 | 36310 | 36310 | DSF0001034602
10 | X003 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/23/2023 | 6/17/2024 |  | 258910 | 225430 | 193198 | DSF0001034602
10 | X003 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/23/2023 | 6/17/2024 |  | 177762 | 158411 | 100970 | DSF0001034602
10 | X003 | P.S. 3 - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/3/2021 | DOES |  | DOES | 145434 | 0 | DSF0000911904
10 | X007 | P.S. 7 - BRONX | SCA CIP | PERM FIX- RETAINING WALL @ X007 | Scope | Complete | 7/18/2024 | 12/4/2024 | 10/21/2024 | 12734 | 18298 | 18172 | SCA0000072717
10 | X007 | P.S. 7 - BRONX | SCA CIP | PERM FIX- RETAINING WALL @ X007 | Design | In-Progress | 10/21/2024 | 3/26/2025 |  | 63672 | 63672 | 8544 | SCA0000072717
10 | X007 | P.S. 7 - BRONX | SCA CIP | PERM FIX- RETAINING WALL @ X007 | Construction | PNS | PNS | PNS | PNS | 1432625 | 1432625 | 0 | SCA0000072717
10 | X007 | P.S. 7 - BRONX | SCA CIP | PERM FIX- RETAINING WALL @ X007 | CM,F&E | PNS | PNS | PNS | PNS | 89141 | 89141 | 13639 | SCA0000072717
10 | X007 | P.S. 7 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/18/2024 | DIIR |  | DIIR | 150000 | 0 | DSF0001086688
10 | X007 | P.S. 7 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001113304
10 | X007 | P.S. 7 - BRONX | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/31/2022 | DOER |  | DOER | 337640 | 0 | DSF0001034018
10 | X007 | P.S. 7 - BRONX | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0 | DSF0001036169
10 | X007 | P.S. 7 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 1/24/2023 | DOES |  | DOES | 69054 | 0 | DSF0001034445
10 | X008 | P.S. 8 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/7/2024 | 12/9/2024 | 8/15/2024 | 4041 | 4278 | 4278 | DSF0001087552
10 | X008 | P.S. 8 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 8/15/2024 | 2/13/2025 |  | 18183 | 18183 | 17113 | DSF0001087552
10 | X008 | P.S. 8 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 234355 | 234355 | 0 | DSF0001087552
10 | X008 | P.S. 8 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 47700 | 47700 | 1300 | DSF0001087552
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | Scope | In-Progress | 8/7/2024 | 11/6/2024 |  | 0 | 346 | 346 | DSF0001034019
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | Design | PNS | PNS | PNS | PNS | 40500 | 40154 | 1382 | DSF0001034019
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | 594000 | 594000 | 0 | DSF0001034019
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 40500 | 40500 | 3737 | DSF0001034019
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/6/2023 | 4/9/2024 | 3/4/2024 | 0 | 14050 | 14050 | DSF0001086689
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 3/4/2024 | 8/2/2024 | 7/16/2024 | 33000 | 38307 | 38307 | DSF0001086689
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 484000 | 484000 | 1728 | DSF0001086689
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 33000 | 33000 | 5564 | DSF0001086689
10 | X009 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | Scope | Complete | 1/12/2018 | 5/30/2018 | 6/5/2018 | 233995 | 175679 | 175679 | DSF0000912493, DSF0000906399, DSF0000906398
10 | X009 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | Design | Complete | 11/28/2018 | 5/1/2019 | 4/30/2019 | 935980 | 777989 | 720706 | DSF0000912493, DSF0000906399, DSF0000906398
10 | X009 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | Construction | Complete | 8/13/2019 | 8/1/2021 | 11/29/2024 | 17549627 | 16263893 | 14871405 | DSF0000912493, DSF0000906399, DSF0000906398
10 | X009 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | CM,F&E | Complete | 8/13/2019 | 8/1/2021 | 11/29/2024 | 1091977 | 791745 | 790814 | DSF0000912493, DSF0000906399, DSF0000906398
10 | X009 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | Scope | Complete | 4/12/2022 | 8/10/2022 | 9/12/2022 | 62504 | 66593 | 2573 | DSF0001034502, DSF0001034501, DSF0001079070
10 | X009 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | Design | Complete | 9/26/2022 | 3/13/2023 | 3/31/2023 | 308752 | 600986 | 282309 | DSF0001034502, DSF0001034501, DSF0001079070
10 | X009 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | Construction | In-Progress | 9/15/2023 | 9/13/2025 |  | 6620774 | 5995048 | 2611439 | DSF0001034502, DSF0001034501, DSF0001079070
10 | X009 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | CM,F&E | In-Progress | 9/15/2023 | 9/13/2025 |  | 465813 | 116386 | 116386 | DSF0001034502, DSF0001034501, DSF0001079070
10 | X009 | P.S. 9 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 5/31/2024 | 8/30/2024 |  | 28215 | 60541 | 17225 | DSF0001112063
10 | X009 | P.S. 9 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | PNS | PNS | PNS | PNS | 131670 | 131670 | 6270 | DSF0001112063
10 | X009 | P.S. 9 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2087908 | 2087908 | 25359 | DSF0001112063
10 | X009 | P.S. 9 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 206910 | 206910 | 15595 | DSF0001112063
10 | X009 | P.S. 9 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/4/2024 | 3/10/2025 | 11/8/2024 | 6030 | 2570 | 2570 | DSF0001087553
10 | X009 | P.S. 9 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 11/8/2024 | 5/8/2025 |  | 27136 | 27136 | 10281 | DSF0001087553
10 | X009 | P.S. 9 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 349747 | 349747 | 0 | DSF0001087553
10 | X009 | P.S. 9 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 64824 | 64824 | 360 | DSF0001087553
10 | X009 | P.S. 9 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/8/2023 | 4/11/2024 | 3/22/2024 | 0 | 16588 | 16462 | DSF0001086690
10 | X009 | P.S. 9 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 3/25/2024 | 8/23/2024 | 8/19/2024 | 60000 | 51878 | 49164 | DSF0001086690
10 | X009 | P.S. 9 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 8516 | DSF0001086690
10 | X009 | P.S. 9 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 13767 | DSF0001086690
10 | X009 | P.S. 9 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001086691
10 | X009 | P.S. 9 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001087164
10 | X015 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 3/11/2021 | 7/26/2021 | 10/4/2021 | 48803 | 53202 | 51935 | DSF0000952194, DSF0001028391
10 | X015 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 11/10/2021 | 4/15/2022 | 5/3/2022 | 237462 | 223739 | 220329 | DSF0000952194, DSF0001028391
10 | X015 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | Complete | 12/15/2022 | 6/6/2024 | 10/24/2024 | 4776062 | 4344725 | 4283690 | DSF0000952194, DSF0001028391
10 | X015 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | Complete | 12/15/2022 | 6/6/2024 | 10/24/2024 | 390768 | 1209902 | 1183842 | DSF0000952194, DSF0001028391
10 | X015 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/6/2022 | 2/9/2023 | 10/18/2022 | 5456 | 9132 | 9132 | DSF0001034656
10 | X015 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/18/2022 | 4/17/2023 | 2/15/2023 | 24552 | 36527 | 36527 | DSF0001034656
10 | X015 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/23/2023 | 6/17/2024 |  | 316445 | 275525 | 227222 | DSF0001034656
10 | X015 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/23/2023 | 6/17/2024 |  | 194611 | 175230 | 73275 | DSF0001034656
10 | X015 | P.S. 15 - BRONX | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 7/25/2023 | 11/27/2023 | 11/8/2023 | 0 | 16035 | 16035 | DSF0001036173
10 | X015 | P.S. 15 - BRONX | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 11/20/2023 | 4/8/2024 | 3/18/2024 | 58500 | 39441 | 6869 | DSF0001036173
10 | X015 | P.S. 15 - BRONX | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 858000 | 858000 | 3385 | DSF0001036173
10 | X015 | P.S. 15 - BRONX | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 58500 | 58500 | 21068 | DSF0001036173
10 | X015 | P.S. 15 - BRONX | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086694
10 | X015 | P.S. 15 - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/4/2021 | DOES |  | DOES | 285032 | 0 | DSF0000911903
10 | X015 | P.S. 15 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/18/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084700
10 | X020 | P.S. 20 - BRONX | SCA CIP | HVAC AND BMS UPGRADE / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 5/26/2022 | 10/27/2022 | 1/3/2023 | 310975 | 154826 | 154826 | DSF0001028452, DSF0001079200, DSF0001079189
10 | X020 | P.S. 20 - BRONX | SCA CIP | HVAC AND BMS UPGRADE / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 1/13/2023 | 6/15/2023 | 5/12/2023 | 1554876 | 923410 | 827473 | DSF0001028452, DSF0001079200, DSF0001079189
10 | X020 | P.S. 20 - BRONX | SCA CIP | HVAC AND BMS UPGRADE / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 34984692 | 34984692 | 535 | DSF0001028452, DSF0001079200, DSF0001079189
10 | X020 | P.S. 20 - BRONX | SCA CIP | HVAC AND BMS UPGRADE / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 2176826 | 2176826 | 55088 | DSF0001028452, DSF0001079200, DSF0001079189
10 | X020 | P.S. 20 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/9/2021 | 10/7/2021 | 11/17/2021 | 0 | 71294 | 71294 | DSF0001007879
10 | X020 | P.S. 20 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 11/30/2021 | 4/18/2022 | 5/12/2022 | 90000 | 86904 | 80219 | DSF0001007879
10 | X020 | P.S. 20 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 876 | DSF0001007879
10 | X020 | P.S. 20 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 23417 | DSF0001007879
10 | X020 | X168 SPED - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION / FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/10/2021 | 3/16/2022 | 12/6/2021 | 0 | 5532 | 5532 | DSF0000913477, DSF0001086698
10 | X020 | X168 SPED - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION / FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 12/6/2021 | 6/2/2022 | 2/23/2022 | 37500 | 40131 | 22131 | DSF0000913477, DSF0001086698
10 | X020 | X168 SPED - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION / FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/30/2022 | 9/25/2023 |  | 550000 | 445318 | 112693 | DSF0000913477, DSF0001086698
10 | X020 | X168 SPED - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION / FY24 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 11/30/2022 | 9/25/2023 |  | 141926 | 173277 | 151784 | DSF0000913477, DSF0001086698
10 | X020 | P.S. 20 - BRONX | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 5/4/2018 | FTK |  | FTK | 142544 | 121469 | DSF0000861041
10 | X020 | P.S. 20 - BRONX | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 5/8/2024 | DOER | 6/18/2024 | DOER | 72118 | 64680 | DSF0001036177
10 | X020 | P.S. 20 - BRONX | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113309
10 | X020 | P.S. 20 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/29/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084702
10 | X023 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/25/2023 | 9/26/2023 | 6/6/2023 | 3690 | 2125 | 2125 | DSF0001035053
10 | X023 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/6/2023 | 12/4/2023 | 10/3/2023 | 16605 | 8500 | 8500 | DSF0001035053
10 | X023 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/12/2024 | 12/7/2024 |  | 214020 | 186345 | 86885 | DSF0001035053
10 | X023 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/12/2024 | 12/7/2024 |  | 64090 | 56161 | 50572 | DSF0001035053
10 | X023 | P.S. 23 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 4/1/2019 | DOES |  | DOES | 88910 | 0 | DSF0000891058
10 | X024 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | Scope | Complete | 4/19/2021 | 9/1/2021 | 11/24/2021 | 43398 | 30858 | 30858 | DSF0001001436, DSF0001079282
10 | X024 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | Design | Complete | 11/29/2021 | 5/2/2022 | 12/27/2022 | 216989 | 324406 | 171108 | DSF0001001436, DSF0001079282
10 | X024 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | Construction | In-Progress | 9/15/2023 | 9/13/2025 |  | 4882259 | 4597616 | 1552449 | DSF0001001436, DSF0001079282
10 | X024 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | CM,F&E | In-Progress | 9/15/2023 | 9/13/2025 |  | 303785 | 573123 | 550332 | DSF0001001436, DSF0001079282
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113311
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113311
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001113311
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113311
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113684
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113684
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113684
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113684
10 | X024 | P.S. 24 - BRONX | SCA IEH | PO18-SPACE ID 1023: ABATE ACM PIPE INSULATION IN COLD CAFETERIA APPROX. 15' SPRAYED RED | Construction | Complete | 7/30/2024 | IEH | 8/8/2024 | IEH | 0 | 0 | SCA0000073200
10 | X024 | P.S. 24 - BRONX | SCA IEH | PO18-SPACE ID 1023: ABATE ACM PIPE INSULATION IN COLD CAFETERIA APPROX. 10' SPRAYED RED ALSO ABATE P | Construction | Complete | 9/18/2024 | IEH | 9/29/2024 | IEH | 0 | 0 | SCA0000073396
10 | X024 | P.S. 24 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 3/15/2021 | FTK |  | FTK | 8786 | 8786 | DSF0001008604
10 | X024 | P.S. 24 - BRONX | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | Complete | 8/5/2022 | DOER | 11/15/2022 | DOER | 118632 | 124694 | DSF0001034025
10 | X024 | P.S. 24 - BRONX | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 475306 | 0 | DSF0001036180
10 | X024 | P.S. 24 - BRONX | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 4/9/2024 | DOER | 5/14/2024 | DOER | 107911 |  | DSF0001036181
10 | X026 | I.S. 390 - BRONX | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 3/7/2023 | 6/5/2023 | 8/9/2023 | 35198 | 47722 | 47722 | DSF0001083909
10 | X026 | I.S. 390 - BRONX | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 9/8/2023 | 3/15/2024 | 11/26/2024 | 164259 | 159018 | 88940 | DSF0001083909
10 | X026 | I.S. 390 - BRONX | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 2604671 | 2604671 | 72834 | DSF0001083909
10 | X026 | I.S. 390 - BRONX | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 258121 | 258121 | 49822 | DSF0001083909
10 | X026 | P.S. 396 - BRONX | SCA CIP RESOA | FY21 RESO A PA SYSTEM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007894
10 | X026 | P.S. 396 - BRONX | SCA CIP RESOA | FY21 RESO A PA SYSTEM UPGRADE | Design | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001007894
10 | X026 | P.S. 396 - BRONX | SCA CIP RESOA | FY21 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001007894
10 | X026 | P.S. 396 - BRONX | SCA CIP RESOA | FY21 RESO A PA SYSTEM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001007894
10 | X026 | I.S. 390 - BRONX | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Scope | Complete | 1/19/2023 | 6/16/2023 | 8/23/2023 | 0 | 69704 | 69704 | DSF0001036183
10 | X026 | I.S. 390 - BRONX | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Design | Complete | 3/7/2024 | 8/7/2024 | 11/26/2024 | 119124 | 219391 | 119300 | DSF0001036183
10 | X026 | I.S. 390 - BRONX | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 1747148 | 1747148 | 51072 | DSF0001036183
10 | X026 | I.S. 390 - BRONX | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 119124 | 119124 | 39909 | DSF0001036183
10 | X026 | I.S. 390 - BRONX | SCA IEH | PO18-SPACE ID 4393(RM 315). THE 12X12 IS HOT AND THE SOFT CONCRETE FLOOR FILLER APPROXL 25 SQ. FT. | Construction | Complete | 8/15/2024 | IEH | 9/1/2024 | IEH | 0 | 0 | SCA0000073290
10 | X026 | P.S. 396 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 274000 | 274000 | 274000 | DSF0001086701
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY22 RESO A LEARNING GARDEN | Construction | Complete | 4/13/2023 | DOER | 6/27/2023 | DOER | 54161 | 2013 | DSF0001033422
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 574640 | 0 | DSF0001034103
10 | X026 | P.S. 396 - BRONX | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 152064 | 0 | DSF0001036185
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 650000 | 0 | DSF0001086700
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001087166
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113312
10 | X026 | P.S. 396 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001113313
10 | X026 | I.S. 390 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/26/2024 | DOES | 7/31/2024 | DOES | 65832 |  | DSF0001084479
10 | X032 | P.S. 32 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT: | Scope | Complete | 9/6/2023 | 12/7/2023 | 11/27/2023 | 39758 | 84261 | 7886 | DSF0001035071
10 | X032 | P.S. 32 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT: | Design | In-Progress | 6/4/2024 | 10/21/2024 |  | 185539 | 185539 | 3769 | DSF0001035071
10 | X032 | P.S. 32 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT: | Construction | PNS | PNS | PNS | PNS | 2942114 | 2942114 | 152 | DSF0001035071
10 | X032 | P.S. 32 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT: | CM,F&E | PNS | PNS | PNS | PNS | 291561 | 291561 | 7368 | DSF0001035071
10 | X032 | P.S. 32 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 12/20/2023 | 3/22/2024 | 12/11/2024 | 2195 | 6341 | 0 | DSF0001111759
10 | X032 | P.S. 32 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | In-Progress | 12/12/2024 | 4/11/2025 |  | 8780 | 8780 | 0 | DSF0001111759
10 | X032 | P.S. 32 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 126219 | 126219 | 0 | DSF0001111759
10 | X032 | P.S. 32 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 32378 | 32378 | 3269 | DSF0001111759
10 | X032 | P.S. 32 - BRONX | SCA IEH | PO18-SPACE ID: 4310 - ROOM 310 - TEST CEILINGS AND WALLS ABATE AND REPAIR CEILING PLASTER | Construction | Complete | 7/23/2024 | IEH | 8/7/2024 | IEH | 0 | 0 | SCA0000073169
10 | X032 | P.S. 32 - BRONX | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 8/10/2022 | DOER |  | DOER | 292094 | 0 | DSF0000913480
10 | X032 | P.S. 32 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/4/2023 | DOER |  | DOER | 202596 | 0 | DSF0001035276
10 | X034 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/28/2022 | 2/1/2023 | 10/3/2022 | 5181 | 3391 | 3391 | DSF0001034621
10 | X034 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/3/2022 | 4/3/2023 | 1/11/2023 | 23314 | 13564 | 13564 | DSF0001034621
10 | X034 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/5/2023 | 6/3/2024 |  | 300491 | 272873 | 246235 | DSF0001034621
10 | X034 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/5/2023 | 6/3/2024 |  | 192788 | 172437 | 140629 | DSF0001034621
10 | X034 | X188 SPED - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001086703
10 | X034 | X188 SPED - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 50832 | 5927 | DSF0001085049
10 | X037 | P.S. 37 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 3/24/2022 | 7/22/2022 | 4/5/2022 | 0 | 4364 | 4364 | DSF0000913481
10 | X037 | P.S. 37 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 4/5/2022 | 9/28/2022 | 7/19/2022 | 24000 | 17454 | 17454 | DSF0000913481
10 | X037 | P.S. 37 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/14/2023 | 4/8/2024 |  | 352000 | 238328 | 214022 | DSF0000913481
10 | X037 | P.S. 37 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/14/2023 | 4/8/2024 |  | 144549 | 157324 | 96599 | DSF0000913481
10 | X037 | P.S. 37 - BRONX | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 6/7/2022 |  |  | 100000 | 100000 | 0 | DSF0001007890
10 | X037 | P.S. 37 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001036189
10 | X037 | P.S. 37 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113315
10 | X037 | P.S. 37 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086704
10 | X037 | P.S. 37 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/6/2024 | DOES | 8/13/2024 | DOES | 50832 | 5883 | DSF0001084704
10 | X045 | I.S. 45 - BRONX | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/3/2021 | 2/7/2022 | 5/13/2022 | 0 | 153386 | 128913 | DSF0001009327
10 | X045 | I.S. 45 - BRONX | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | Complete | 5/17/2022 | 9/30/2022 | 1/27/2023 | 363000 | 279703 | 279703 | DSF0001009327
10 | X045 | I.S. 45 - BRONX | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 5324000 | 5324000 | 62160 | DSF0001009327
10 | X045 | I.S. 45 - BRONX | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 363000 | 363000 | 123676 | DSF0001009327
10 | X045 | I.S. 45 - BRONX | SCA IEH | PO18-ABATE AND REPAIR TROWELLED ON FIREPROOFING IN FAN ROOM APPROX. 25SF VIOLATION 35273285K | Construction | In-Progress | 11/17/2022 | IEH |  | IEH | 0 | 0 | SCA0000071569
10 | X045 | I.S. 45 - BRONX | SCA IEH | PO18-TEST WALLS ROOM 407 DRILL WALLS FOR ELECTRIC CONDUITS | Construction | Complete | 7/31/2024 | IEH | 8/23/2024 | IEH | 0 | 0 | SCA0000073210
10 | X045 | I.S. 45 - BRONX | SCA Furniture & Equipment | FY22 RESO A MOBILE STEM LAB | F&E | Complete | 7/15/2024 |  | 9/16/2024 | 50000 | 50000 | 50000 | DSF0001034033
10 | X045 | I.S. 45 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/2/2024 | DIIR |  | DIIR | 150000 | 0 | DSF0001086707
10 | X045 | I.S. 45 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/19/2024 | DOES | 8/28/2024 | DOES | 65832 |  | DSF0001084844
10 | X046 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Scope | Complete | 8/4/2014 | 12/19/2014 | 12/19/2014 | 112122 | 241029 | 241029 | DSF0000794346, DSF0000794342, DSF0000794345, DSF0000794344
10 | X046 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Design | Complete | 7/13/2015 | 12/14/2015 | 6/28/2016 | 558225 | 648170 | 605860 | DSF0000794346, DSF0000794342, DSF0000794345, DSF0000794344
10 | X046 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Construction | Complete | 6/13/2022 | 6/11/2024 | 9/25/2024 | 12354085 | 13387734 | 12755210 | DSF0000794346, DSF0000794342, DSF0000794345, DSF0000794344
10 | X046 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | CM,F&E | Complete | 6/13/2022 | 6/11/2024 | 9/25/2024 | 802709 | 1085608 | 1084851 | DSF0000794346, DSF0000794342, DSF0000794345, DSF0000794344
10 | X054 | P.S. 54 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 7/14/2022 | 11/30/2022 | 7/25/2023 | 37560 | 52769 | 51007 | DSF0001029022, DSF0001029023, DSF0001085803
10 | X054 | P.S. 54 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 8/23/2023 | 1/29/2024 | 3/21/2024 | 187049 | 196128 | 188794 | DSF0001029022, DSF0001029023, DSF0001085803
10 | X054 | P.S. 54 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | PNS | PNS | PNS | PNS | 4143577 | 4143577 | 0 | DSF0001029022, DSF0001029023, DSF0001085803
10 | X054 | P.S. 54 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 268558 | 268558 | 17145 | DSF0001029022, DSF0001029023, DSF0001085803
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113320
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001113320
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1760000 | 1760000 | 0 | DSF0001113320
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001113320
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113688
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113688
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113688
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113688
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/2/2023 | 5/3/2023 | 9/12/2023 | 0 | 42185 | 42185 | DSF0001036196
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 8/1/2024 | 12/18/2024 |  | 18000 | 70345 | 38118 | DSF0001036196
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 264000 | 264000 | 111 | DSF0001036196
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 18000 | 18000 | 5148 | DSF0001036196
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 5/25/2023 | 9/26/2023 | 6/6/2023 | 0 | 943 | 943 | DSF0001036198
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 6/6/2023 | 12/4/2023 | 10/3/2023 | 24000 | 3772 | 3772 | DSF0001036198
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/12/2024 | 12/7/2024 |  | 352000 | 189375 | 86616 | DSF0001036198
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/12/2024 | 12/7/2024 |  | 55511 | 60865 | 56252 | DSF0001036198
10 | X054 | P.S. 54 - BRONX | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 3/31/2023 |  |  | 100000 | 100000 | 15744 | DSF0001033360
10 | X054 | P.S. 54 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001113321
10 | X054 | P.S. 54 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001086713
10 | X056 | P.S. 56 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 125000 | DSF0001086715
10 | X056 | P.S. 56 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 80000 | 0 | DSF0001034037
10 | X056 | P.S. 56 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 11/12/2024 | DIIR | 59789 | 59789 | DSF0001036200
10 | X056 | P.S. 56 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001113322
10 | X056 | P.S. 56 - BRONX | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 1/18/2021 | DOES | 4/9/2021 | DOES | 439 | 755 | DSF0001008609
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/1/2023 | 5/2/2023 | 9/20/2023 | 0 | 40517 | 40517 | DSF0001036201
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 5214 | 3200 | 3200 | DSF0001036201
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 76468 | 1608063 | 4084 | DSF0001036201
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 5214 | 109641 | 3875 | DSF0001036201
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/27/2023 | 5/26/2023 | 11/20/2023 | 0 | 534 | 534 | DSF0001036202
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 440 | 2137 | 2137 | DSF0001036202
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 6459 | 241604 | 1840 | DSF0001036202
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 440 | 16473 | 2371 | DSF0001036202
10 | X059 | P.S. 59 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 3/2/2020 | FTK |  | FTK | 214362 | 212494 | DSF0000911983, DSF0000912600
10 | X079 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | Scope | Complete | 4/30/2021 | 8/30/2021 | 7/28/2021 | 13940 | 47233 | 47233 | DSF0001083775
10 | X079 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | Design | Complete | 8/5/2021 | 2/3/2022 | 11/17/2021 | 62730 | 188938 | 188938 | DSF0001083775
10 | X079 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | Construction | In-Progress | 4/27/2023 | 10/17/2024 |  | 808520 | 754850 | 272557 | DSF0001083775
10 | X079 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | CM,F&E | In-Progress | 4/27/2023 | 10/17/2024 |  | 149855 | 111989 | 109324 | DSF0001083775
10 | X079 | I.S. 447 - BRONX | SCA CIP RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 8/26/2019 | 12/27/2019 | 9/5/2019 | 0 | 4783 | 4783 | DSF0000890982
10 | X079 | I.S. 447 - BRONX | SCA CIP RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 9/5/2019 | 3/5/2020 | 3/10/2020 | 28617 | 25075 | 19131 | DSF0000890982
10 | X079 | I.S. 447 - BRONX | SCA CIP RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 8/5/2021 | 5/1/2022 |  | 419720 | 347301 | 205400 | DSF0000890982
10 | X079 | I.S. 447 - BRONX | SCA CIP RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 8/5/2021 | 5/1/2022 |  | 175088 | 176213 | 164036 | DSF0000890982
10 | X079 | SCHOOL FOR ENVIR CITIZEN - BRONX | SCA CIP RESOA | FY21 RESO A SUPPLEMENTAL COOLING / FY21 RESO A ROOM CONVERSION | Scope | Complete | 9/2/2021 | 1/7/2022 | 1/20/2022 | 0 | 24328 | 24328 | DSF0001007895, DSF0001007899
10 | X079 | SCHOOL FOR ENVIR CITIZEN - BRONX | SCA CIP RESOA | FY21 RESO A SUPPLEMENTAL COOLING / FY21 RESO A ROOM CONVERSION | Design | Complete | 1/20/2022 | 6/20/2022 | 7/22/2022 | 82267 | 93329 | 93329 | DSF0001007895, DSF0001007899
10 | X079 | SCHOOL FOR ENVIR CITIZEN - BRONX | SCA CIP RESOA | FY21 RESO A SUPPLEMENTAL COOLING / FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 10/25/2023 | 10/23/2024 |  | 1206575 | 1133828 | 21111 | DSF0001007895, DSF0001007899
10 | X079 | SCHOOL FOR ENVIR CITIZEN - BRONX | SCA CIP RESOA | FY21 RESO A SUPPLEMENTAL COOLING / FY21 RESO A ROOM CONVERSION | CM,F&E | In-Progress | 10/25/2023 | 10/23/2024 |  | 82267 | 127365 | 86868 | DSF0001007895, DSF0001007899
10 | X079 | I.S. 447 - BRONX | SCA IEH | PO18-SPACE ID: 2113 - TEST AND ABATE ACM PIPE INSULATION SPRAYED RED FOR ID, SLOP SINK ROOM 113 | Construction | Complete | 7/29/2024 | IEH | 8/29/2024 | IEH | 0 | 0 | SCA0000073192
10 | X079 | I.S. 447 - BRONX | DOE - RESOA | FY13 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 148495 | 0 | DSF0000754720
10 | X079 | I.S. 447 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001086723
10 | X079 | SCHOOL FOR ENVIR CITIZEN - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001113330
10 | X079 | I.S. 447 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 10/4/2019 | DOES |  | DOES | 157746 | 0 | DSF0000889053
10 | X079 | I.S. 447 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/30/2024 | DOES | 10/8/2024 | DOES | 65832 | 5935 | DSF0001084849
10 | X080 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/28/2022 | 11/14/2022 | 2/2/2023 | 88790 | 175531 | 174375 | DSF0001029537, DSF0001029538, DSF0001080283
10 | X080 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/13/2023 | 7/17/2023 | 5/10/2023 | 443950 | 489367 | 404423 | DSF0001029537, DSF0001029538, DSF0001080283
10 | X080 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 8/15/2023 | 10/14/2025 |  | 9988876 | 9067854 | 6032250 | DSF0001029537, DSF0001029538, DSF0001080283
10 | X080 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/15/2023 | 10/14/2025 |  | 623060 | 207368 | 201779 | DSF0001029537, DSF0001029538, DSF0001080283
10 | X080 | I.S. 80 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/6/2023 | 4/19/2024 | 6/18/2024 | 0 | 21864 | 21864 | DSF0001036213, DSF0001036214
10 | X080 | I.S. 80 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 6/28/2024 | 10/31/2024 | 9/6/2024 | 56339 | 72972 | 47402 | DSF0001036213, DSF0001036214
10 | X080 | I.S. 80 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 826302 | 826302 | 21179 | DSF0001036213, DSF0001036214
10 | X080 | I.S. 80 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 56339 | 56339 | 23962 | DSF0001036213, DSF0001036214
10 | X080 | I.S. 80 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ X080 | Construction | In-Progress | 3/21/2023 | EMER |  | EMER | 21873 | 21873 | SCA0000071837
10 | X080 | P.S. 280 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 405000 | 0 | DSF0001086724
10 | X080 | I.S. 80 - BRONX | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/5/2020 | DOER |  | DOER | 665874 | 2339 | DSF0000913496
10 | X080 | P.S. 280 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/19/2024 | DOES | 8/26/2024 | DOES | 65832 | 6472 | DSF0001084706
10 | X081 | P.S. 81 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 1/6/2020 | 5/5/2020 | 1/29/2020 | 0 | 9666 | 9666 | DSF0000913497
10 | X081 | P.S. 81 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2/5/2020 | 7/30/2020 | 5/14/2020 | 27818 | 38788 | 38788 | DSF0000913497
10 | X081 | P.S. 81 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/9/2021 | 4/4/2022 |  | 407999 | 345556 | 329511 | DSF0000913497
10 | X081 | P.S. 81 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/9/2021 | 4/4/2022 |  | 135535 | 178036 | 173644 | DSF0000913497
10 | X081 | P.S. 81 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001034045
10 | X081 | P.S. 81 - BRONX | DOE - RESOA | FY10 RESO A FENCING FOR PLAYGROUND | Construction | PNS | PNS | PNS | PNS | DOER | 76000 | 0 | DSF0000690172
10 | X081 | P.S. 81 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113331
10 | X085 | P.S. 85 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 3/2/2023 | 5/31/2023 | 8/18/2023 | 51736 | 86624 | 86624 | DSF0001083907
10 | X085 | P.S. 85 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 8/18/2023 | 1/8/2024 | 5/14/2024 | 258680 | 199437 | 172809 | DSF0001083907
10 | X085 | P.S. 85 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 5820299 | 5820299 | 189769 | DSF0001083907
10 | X085 | P.S. 85 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 362152 | 362152 | 61908 | DSF0001083907
10 | X085 | P.S. 85 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDELOPMENT | Scope | Complete | 8/4/2023 | 12/6/2023 | 9/1/2023 | 2915 | 6158 | 6158 | DSF0001085311
10 | X085 | P.S. 85 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDELOPMENT | Design | Complete | 9/6/2023 | 1/5/2024 | 5/14/2024 | 13119 | 18833 | 18833 | DSF0001085311
10 | X085 | P.S. 85 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDELOPMENT | Construction | PNS | PNS | PNS | PNS | 169093 | 169093 | 32848 | DSF0001085311
10 | X085 | P.S. 85 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 31341 | 31341 | 14204 | DSF0001085311
10 | X085 | P.S. 85 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/28/2024 | 10/29/2024 | 7/8/2024 | 3412 | 1528 | 1528 | DSF0001087570
10 | X085 | P.S. 85 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/8/2024 | 1/3/2025 |  | 15352 | 15352 | 6111 | DSF0001087570
10 | X085 | P.S. 85 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 197869 | 197869 | 0 | DSF0001087570
10 | X085 | P.S. 85 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 40938 | 40938 | 8696 | DSF0001087570
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/5/2023 | 3/7/2024 | 4/23/2024 | 0 | 10924 | 1628 | DSF0001086730
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | Complete | 5/1/2024 | 9/17/2024 | 9/24/2024 | 23061 | 37097 | 6512 | DSF0001086730
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 338235 | 338235 | 21623 | DSF0001086730
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 23061 | 23061 | 15347 | DSF0001086730
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/12/2024 | 6/11/2024 | 6/20/2024 | 0 | 0 | 107 | DSF0001087121
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 6/25/2024 | 10/28/2024 | 9/24/2024 | 939 | 939 | 426 | DSF0001087121
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 13765 | 13765 | 0 | DSF0001087121
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 939 | 939 | 2775 | DSF0001087121
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/5/2023 | 6/10/2024 | 6/20/2024 | 0 | 22631 | 1680 | DSF0001086729, DSF0001087120
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 6/25/2024 | 10/28/2024 | 9/17/2024 | 60000 | 66728 | 6721 | DSF0001086729, DSF0001087120
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 880001 | 880001 | 49847 | DSF0001086729, DSF0001087120
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 63042 | 21047 | DSF0001086729, DSF0001087120
10 | X085 | P.S. 85 - BRONX | SCA IEH | PO18-ABATE/REPLACE 9X9 ACM FLOOR TILES ROOMS 306,309,310 EACH ROOM APPROX. 632 SQ. FT. | Construction | Complete | 9/17/2024 | IEH | 12/28/2024 | IEH | 0 | 0 | SCA0000073385
10 | X085 | P.S. 85 - BRONX | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 9/6/2023 | DOER |  | DOER | 385643 | 0 | DSF0001034047
10 | X085 | P.S. 85 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 323536 | 0 | DSF0001087165
10 | X085 | P.S. 85 - BRONX | DOE - Skilled Trades | PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 6/28/2022 | DOES |  | DOES | 305973 | 0 | DSF0000866192
10 | X085 | P.S. 85 - BRONX | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 11/2/2023 | DOES |  | DOES | 319218 | 0 | DSF0001080382
10 | X086 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | Scope | Complete | 3/17/2022 | 8/1/2022 | 1/13/2023 | 108367 | 167122 | 162169 | DSF0001085134, DSF0001083864, DSF0001080395, DSF0001080398, DSF0001080399
10 | X086 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | Design | Complete | 1/18/2023 | 6/20/2023 | 5/9/2023 | 534877 | 452586 | 384092 | DSF0001085134, DSF0001083864, DSF0001080395, DSF0001080398, DSF0001080399
10 | X086 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | Construction | In-Progress | 8/21/2023 | 8/19/2025 |  | 11432973 | 10616943 | 5432901 | DSF0001085134, DSF0001083864, DSF0001080395, DSF0001080398, DSF0001080399
10 | X086 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | CM,F&E | In-Progress | 8/21/2023 | 8/19/2025 |  | 810742 | 449870 | 440305 | DSF0001085134, DSF0001083864, DSF0001080395, DSF0001080398, DSF0001080399
10 | X086 | P.S. 86 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/8/2024 | 4/8/2024 | 9/26/2024 | 28422 | 58967 | 42767 | DSF0001111889
10 | X086 | P.S. 86 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | In-Progress | 10/7/2024 | 2/26/2025 |  | 132636 | 132636 | 11358 | DSF0001111889
10 | X086 | P.S. 86 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2103234 | 2103234 | 152 | DSF0001111889
10 | X086 | P.S. 86 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 208429 | 208429 | 19167 | DSF0001111889
10 | X086 | P.S. 86 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/3/2024 | 11/1/2024 | 7/9/2024 | 3526 | 1547 | 1547 | DSF0001087571
10 | X086 | P.S. 86 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/9/2024 | 1/6/2025 |  | 15865 | 15865 | 6188 | DSF0001087571
10 | X086 | P.S. 86 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 204482 | 204482 | 1810 | DSF0001087571
10 | X086 | P.S. 86 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 42164 | 42164 | 7473 | DSF0001087571
10 | X086 | P.S. 86 - BRONX | SCA CIP | PATH OF TRAVEL OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 4/1/2024 | 7/1/2024 | 10/17/2024 | 10368 | 1274 | 1274 | DSF0001112099
10 | X086 | P.S. 86 - BRONX | SCA CIP | PATH OF TRAVEL OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | In-Progress | 10/30/2024 | 3/5/2025 |  | 41471 | 41471 | 5097 | DSF0001112099
10 | X086 | P.S. 86 - BRONX | SCA CIP | PATH OF TRAVEL OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 596142 | 596142 | 790 | DSF0001112099
10 | X086 | P.S. 86 - BRONX | SCA CIP | PATH OF TRAVEL OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 152923 | 152923 | 4109 | DSF0001112099
10 | X086 | P.S. 86 - BRONX | SCA IEH | PO18-ABATE ACM PIPE INSULATION HOT WATER LINE ON THE 4TH FLOOR. LINE IS APPROXIMATELY 12' FROM THE G | Construction | Complete | 8/12/2024 | IEH | 9/7/2024 | IEH | 0 | 0 | SCA0000073274
10 | X086 | P.S. 86 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113335
10 | X086 | P.S. 86 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 431859 | 0 | DSF0001086731
10 | X086 | P.S. 86 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/9/2024 | DOES | 11/1/2024 | DOES | 65832 | 2335 | DSF0001084708
10 | X091 | P.S. 91 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/18/2023 | 10/4/2023 | 11/1/2023 | 325236 | 249736 | 248171 | DSF0001080499, DSF0001080500, DSF0001111772, DSF0001111771
10 | X091 | P.S. 91 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/8/2023 | 4/12/2024 | 9/18/2024 | 1517765 | 673978 | 647278 | DSF0001080499, DSF0001080500, DSF0001111772, DSF0001111771
10 | X091 | P.S. 91 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | PNS | PNS | PNS | PNS | 24067417 | 24067417 | 83133 | DSF0001080499, DSF0001080500, DSF0001111772, DSF0001111771
10 | X091 | P.S. 91 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 2385059 | 2385059 | 63544 | DSF0001080499, DSF0001080500, DSF0001111772, DSF0001111771
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/12/2022 | 10/11/2022 | 3/1/2023 | 0 | 86087 | 86087 | DSF0001034050
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 8/2/2023 | 12/19/2023 |  | 422678 | 336591 | 87196 | DSF0001034050
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 6199277 | 6199277 | 34891 | DSF0001034050
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 422678 | 422678 | 43440 | DSF0001034050
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/5/2023 | 3/8/2024 | 4/9/2024 | 0 | 0 | 1213 | DSF0001083681
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 4/16/2024 | 8/19/2024 |  | 322 | 322 | 4852 | DSF0001083681
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 4723 | 4723 | 213 | DSF0001083681
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 322 | 322 | 8299 | DSF0001083681
10 | X091 | P.S. 91 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ X091 | Construction | In-Progress | 9/11/2023 | EMER |  | EMER | 278200 | 245438 | SCA0000072283
10 | X091 | P.S. 91 - BRONX | Fast Track Projects | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/14/2019 | FTK |  | FTK | 75926 | 68645 | DSF0000867315
10 | X091 | P.S. 91 - BRONX | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 194000 | 0 | DSF0001086734
10 | X091 | P.S. 91 - BRONX | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 194000 | 0 | DSF0001086735
10 | X091 | P.S. 91 - BRONX | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/1/2023 | DOER |  | DOER | 376212 | 0 | DSF0000912791
10 | X091 | P.S. 91 - BRONX | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | Complete | 3/10/2023 | DOER | 10/25/2023 | DOER | 111165 |  | DSF0001034052
10 | X094 | P.S. 94 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/17/2024 | 11/15/2024 | 7/23/2024 | 3536 | 1225 | 1225 | DSF0001087574
10 | X094 | P.S. 94 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/23/2024 | 1/21/2025 |  | 15912 | 15912 | 4900 | DSF0001087574
10 | X094 | P.S. 94 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 205093 | 205093 | 0 | DSF0001087574
10 | X094 | P.S. 94 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 42277 | 42277 | 9152 | DSF0001087574
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113691
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113691
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113691
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113691
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 12/14/2023 | 3/18/2024 |  | 0 | 11342 | 414 | DSF0001086738
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 30000 | 18658 | 1657 | DSF0001086738
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 2482 | DSF0001086738
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 6776 | DSF0001086738
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087124
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087124
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087124
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087124
10 | X094 | P.S. 94 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113342
10 | X094 | P.S. 94 - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 111424 | 0 | DSF0001086737
10 | X094 | P.S. 94 - BRONX | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0 | DSF0001113341
10 | X095 | P.S. 95 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/5/2019 | FTK |  | FTK | 119534 | 114798 | DSF0000868255, DSF0000912241
10 | X095 | P.S. 344 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/8/2024 | DIIR | 8/13/2024 | DIIR | 125000 | 125000 | DSF0001033413
10 | X095 | P.S. 95 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/30/2024 | DIIR | 7/9/2024 | DIIR | 75000 | 71391 | DSF0001034055
10 | X095 | P.S. 344 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001086739
10 | X095 | P.S. 344 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113343
10 | X095 | P.S. 95 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001113344
10 | X095 | P.S. 95 - BRONX | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086740
10 | X095 | P.S. 95 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/13/2023 | DOES | 8/29/2024 | DOES | 65832 |  | DSF0001084527
10 | X115 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | Scope | Complete | 7/28/2021 | 8/25/2023 | 8/2/2023 | 78240 | 79916 | 79916 | DSF0001009250, SCA0000070638, DSF0001034499, DSF0001083708
10 | X115 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | Design | Complete | 8/8/2023 | 12/26/2023 | 1/31/2024 | 391201 | 361732 | 272612 | DSF0001009250, SCA0000070638, DSF0001034499, DSF0001083708
10 | X115 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | Construction | In-Progress | 9/20/2024 | 9/19/2026 |  | 8802000 | 8050476 | 75911 | DSF0001009250, SCA0000070638, DSF0001034499, DSF0001083708
10 | X115 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | CM,F&E | In-Progress | 9/20/2024 | 9/19/2026 |  | 547679 | 122410 | 119015 | DSF0001009250, SCA0000070638, DSF0001034499, DSF0001083708
10 | X115 | M.S. 363 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113820
10 | X115 | M.S. 363 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113820
10 | X115 | M.S. 363 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113820
10 | X115 | M.S. 363 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113820
10 | X115 | M.S. 363 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/27/2019 | 6/27/2019 | 10/16/2019 | 0 | 25154 | 23633 | DSF0000890978
10 | X115 | M.S. 363 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 10/30/2024 | 4/4/2025 |  | 163500 | 138346 | 8026 | DSF0000890978
10 | X115 | M.S. 363 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 2398000 | 2398000 | 10353 | DSF0000890978
10 | X115 | M.S. 363 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 163500 | 163500 | 5573 | DSF0000890978
10 | X115 | M.S. 363 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 10/26/2021 | EMER |  | EMER | 123322 | 85193 | SCA0000070625
10 | X115 | M.S. 363 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 8/8/2024 | DIIR | 299857 | 299857 | DSF0001036232
10 | X115 | M.S. 363 - BRONX | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 755000 | 0 | DSF0000890976
10 | X115 | M.S. 363 - BRONX | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 188000 | 0 | DSF0001113362
10 | X115 | M.S. 363 - BRONX | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113363
10 | X115 | M.S. 363 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/21/2022 | DOES | 8/22/2023 | DOES | 201812 |  | DSF0001008726
10 | X115 | M.S. 363 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/1/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084853
10 | X118 | I.S. 118 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 8/4/2023 | 11/3/2023 | 10/23/2023 | 29061 | 48913 | 48913 | DSF0001035072
10 | X118 | I.S. 118 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 11/1/2023 | 3/21/2024 | 3/26/2024 | 145306 | 112483 | 99571 | DSF0001035072
10 | X118 | I.S. 118 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 3269383 | 3269383 | 149155 | DSF0001035072
10 | X118 | I.S. 118 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 203428 | 203428 | 42377 | DSF0001035072
10 | X118 | I.S. 118 - BRONX | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Scope | Complete | 12/5/2018 | 3/5/2019 | 3/4/2019 | 0 | 36456 | 27239 | DSF0000890958
10 | X118 | I.S. 118 - BRONX | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Design | Complete | 12/9/2021 | 5/11/2022 | 7/21/2022 | 122580 | 81812 | 75482 | DSF0000890958
10 | X118 | I.S. 118 - BRONX | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | Complete | 4/20/2023 | 2/13/2024 | 11/1/2024 | 1797840 | 724556 | 585401 | DSF0000890958
10 | X118 | I.S. 118 - BRONX | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | CM,F&E | Complete | 4/20/2023 | 2/13/2024 | 11/1/2024 | 140624 | 86717 | 68590 | DSF0000890958
10 | X118 | I.S. 118 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0 | DSF0001034065
10 | X118 | I.S. 118 - BRONX | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086757
10 | X118 | I.S. 118 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/22/2024 | DOES | 12/4/2024 | DOES | 65832 |  | DSF0001084855
10 | X118 | I.S. 118 - BRONX | DOE - Skilled Trades | CAFETERIA LIGHTING UPGRADE & CEILING INSTALLATION | Construction | In-Progress | 8/1/2023 | DOES |  | DOES | 145120 | 0 | DSF0001085333
10 | X118 | I.S. 118 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/2/2024 | DOES |  | DOES | 388882 | 0 | DSF0001085741
10 | X122 | P.S. 310 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113696
10 | X122 | P.S. 310 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113696
10 | X122 | P.S. 310 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113696
10 | X122 | P.S. 310 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113696
10 | X122 | P.S. 310 - BRONX | SCA IEH | PO18-REMOVE 4' OF 2' PIPE COVER IN CRAWLSPACE. REMOVE 12' OF 2.5' PIPE COVER IN CRAWLSPACE. | Construction | Complete | 11/12/2024 | IEH | 11/17/2024 | IEH | 0 | 0 | SCA0000073599
10 | X122 | P.S. 310 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 4/9/2021 | FTK |  | FTK | 494014 | 491030 | DSF0000912137, DSF0000912944
10 | X122 | P.S. 310 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086760
10 | X122 | P.S. 310 - BRONX | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 228000 | 0 | DSF0001113367
10 | X122 | P.S. 310 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113368
10 | X137 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/14/2019 | 6/12/2019 | 3/10/2020 | 22890 | 114350 | 97173 | DSF0000912304
10 | X137 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 3/11/2020 | 9/10/2020 | 6/30/2020 | 114450 | 180606 | 162633 | DSF0000912304
10 | X137 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 10/20/2023 | 10/18/2025 |  | 2575125 | 2507766 | 1460173 | DSF0000912304
10 | X137 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 10/20/2023 | 10/18/2025 |  | 160230 | 68916 | 68122 | DSF0000912304
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A STEM LAB | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034117
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A STEM LAB | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034117
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034117
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A STEM LAB | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034117
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY22 RESO A STEM LAB | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034118
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY22 RESO A STEM LAB | Design | PNS | PNS | PNS | PNS | 24000 | 24000 | 0 | DSF0001034118
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | 352000 | 352000 | 0 | DSF0001034118
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY22 RESO A STEM LAB | CM,F&E | PNS | PNS | PNS | PNS | 24000 | 24000 | 0 | DSF0001034118
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086766
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 12006 | 12006 | 0 | DSF0001086766
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 176092 | 176000 | 0 | DSF0001086766
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 12006 | 12000 | 170 | DSF0001086766
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087125
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087125
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087125
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087125
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/31/2023 | 5/1/2023 | 6/14/2023 | 0 | 102667 | 102667 | DSF0001036250
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 6/26/2023 | 11/9/2023 | 5/15/2024 | 380596 | 272617 | 216705 | DSF0001036250
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 5582078 | 5582078 | 29437 | DSF0001036250
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 380596 | 380596 | 24514 | DSF0001036250
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/27/2023 | 5/26/2023 | 11/20/2023 | 0 | 0 | 2285 | DSF0001036249
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 11/30/2023 | 4/1/2024 | 5/15/2024 | 404 | 404 | 9140 | DSF0001036249
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 5922 | 5922 | 2995 | DSF0001036249
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 404 | 404 | 10123 | DSF0001036249
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 7/13/2023 | 11/13/2023 | 7/31/2023 | 0 | 2317 | 2317 | DSF0001036248
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 7/31/2023 | 1/29/2024 | 10/18/2023 | 24000 | 9267 | 9267 | DSF0001036248
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 3/15/2024 | 1/8/2025 |  | 352000 | 225421 | 83241 | DSF0001036248
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 3/15/2024 | 1/8/2025 |  | 95984 | 95792 | 88258 | DSF0001036248
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY22 RESO A ROOM CONVERSION | Scope | Complete | 6/17/2022 | 11/30/2023 | 10/13/2023 | 0 | 32610 | 24477 | DSF0001033388, DSF0001033389
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY22 RESO A ROOM CONVERSION | Design | Complete | 10/20/2023 | 3/5/2024 | 4/15/2024 | 155400 | 114218 | 84916 | DSF0001033388, DSF0001033389
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 2279200 | 2279200 | 5823 | DSF0001033388, DSF0001033389
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY22 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 155400 | 159511 | 14444 | DSF0001033388, DSF0001033389
10 | X137 | I.S. 391 - BRONX | SCA IEH | PO18-ROOM 308 REPLACE 1 BROKEN FLOOR TILE AT SOUTH END OF CLASSROOM - ROOM 312 REPLACE 2 BROKEN FLOO | Construction | In-Progress | 6/28/2024 | IEH |  | IEH | 0 | 0 | SCA0000073103
10 | X137 | I.S. 391 - BRONX | DIIT - RESOA | FY17 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 76250 | 0 | DSF0000845569
10 | X137 | I.S. 391 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 7/15/2024 | DIIR | 250000 | 250000 | DSF0001035302
10 | X137 | I.S. 391 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/23/2024 | DOES | 9/30/2024 | DOES | 65832 | 5932 | DSF0001085056
10 | X141 | M.S./H.S. 141 - BRONX | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007893
10 | X141 | M.S./H.S. 141 - BRONX | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001007893
10 | X141 | M.S./H.S. 141 - BRONX | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001007893
10 | X141 | M.S./H.S. 141 - BRONX | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001007893
10 | X141 | M.S./H.S. 141 - BRONX | SCA IEH | PO18-ABATE/REPLACE DETERIORATED 9X9 ACM FLOOR TILES, NO SUMMER PROGRAM 304A; 35 SQ.FT., 107; 756 SQ. | Construction | Complete | 8/9/2024 | IEH | 9/26/2024 | IEH | 0 | 0 | SCA0000073270
10 | X141 | M.S./H.S. 141 - BRONX | SCA IEH | PO18-ABATE AND REPAIR DAMAGED FLOOR TILES ROOM #107 | Construction | Complete | 8/12/2024 | IEH | 8/20/2024 | IEH | 0 | 0 | SCA0000073278
10 | X141 | M.S./H.S. 141 - BRONX | SCA IEH | PO18-SPACE ID: 1028G - TEST & ABATE 10'-15' OF PIPE INSULATION, COVERED & TAPED. | Construction | In-Progress | 11/29/2024 | IEH |  | IEH | 0 | 0 | SCA0000073653
10 | X141 | M.S./H.S. 141 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0 | DSF0001113375
10 | X141 | M.S./H.S. 141 - BRONX | DOE - RESOA | FY22 RESO A CAFETRIA UPGRADE | Construction | In-Progress | 8/25/2023 | DOER |  | DOER | 167651 | 0 | DSF0001034069
10 | X141 | M.S./H.S. 141 - BRONX | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 1/27/2021 | DOES |  | DOES | 154029 | 0 | DSF0000960495
10 | X141 | M.S./H.S. 141 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 11/1/2022 | DOES |  | DOES | 140998 | 0 | DSF0001034466
10 | X141 | M.S./H.S. 141 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/23/2024 | DOES | 10/30/2024 | DOES | 65832 |  | DSF0001085058
10 | X143 | I.S. 244 - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/14/2019 | 12/16/2022 | 12/7/2022 | 0 | 14578 | 14578 | DSF0000822721, DSF0001035083
10 | X143 | I.S. 244 - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 12/16/2022 | 4/21/2023 | 5/12/2023 | 98731 | 84319 | 53545 | DSF0000822721, DSF0001035083
10 | X143 | I.S. 244 - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | Complete | 8/21/2023 | 5/16/2024 | 7/31/2024 | 1448058 | 504503 | 5752 | DSF0000822721, DSF0001035083
10 | X143 | I.S. 244 - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 8/21/2023 | 5/16/2024 | 7/31/2024 | 98731 | 57997 | 55417 | DSF0000822721, DSF0001035083
10 | X143 | I.S. 244 - BRONX | SCA IEH | PO18-REMOVE APPX 8 FEET OF ACM COVERING LOCATED IN 5TH FLOOR PIPE CHASE IN GIRLS BATHROOM SPRAYED RE | Construction | Complete | 7/29/2024 | IEH | 8/18/2024 | IEH | 0 | 0 | SCA0000073188
10 | X143 | I.S. 244 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 200000 | 200000 | 0 | DSF0001036254
10 | X143 | MARIE CURIE HS FOR NURSING - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/21/2024 | DIIR | 7/18/2024 | DIIR | 50000 | 50000 | DSF0001086771
10 | X143 | I.S. 244 - BRONX | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113378
10 | X143 | I.S. 244 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113379
10 | X143 | MARIE CURIE HS FOR NURSING - BRONX | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113380
10 | X143 | I.S. 244 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/16/2024 | DOES | 8/30/2024 | DOES | 65832 | 8998 | DSF0001084862
10 | X177 | BEDFORD PARK ELEMENTARY SCHOOL | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 187000 | 187000 | 187000 | DSF0001086791
10 | X177 | BEDFORD PARK ELEMENTARY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113390
10 | X177 | BEDFORD PARK ELEMENTARY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/8/2024 | DOES | 7/18/2024 | DOES | 50832 |  | DSF0001085064
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113397
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113397
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001113397
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113397
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113398
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113398
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001113398
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113398
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113702
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113702
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113702
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113702
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113703
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113703
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113703
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113703
10 | X205 | P.S. 205 - BRONX | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | Complete | 7/22/2022 | DOER | 6/3/2024 | DOER | 261803 | 140407 | DSF0000913515
10 | X205 | P.S. 205 - BRONX | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113816
10 | X206 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/19/2022 | 1/23/2023 | 9/27/2022 | 2847 | 3629 | 3629 | DSF0001034556
10 | X206 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/27/2022 | 7/20/2023 | 1/11/2023 | 12812 | 14513 | 14513 | DSF0001034556
10 | X206 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/5/2023 | 6/3/2024 |  | 165134 | 158048 | 142518 | DSF0001034556
10 | X206 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/5/2023 | 6/3/2024 |  | 129628 | 136494 | 105260 | DSF0001034556
10 | X206 | I.S. 206B - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 281000 | 281000 | 0 | DSF0001086805
10 | X206 | I.S. 206B - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001033384
10 | X206 | I.S. 206B - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 28172 | 0 | DSF0001086804
10 | X206 | I.S. 206B - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 2/5/2015 | DOES |  | DOES | 171784 | 0 | DSF0000796800
10 | X206 | I.S. 206B - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/18/2024 | DOES | 11/26/2024 | DOES | 50832 |  | DSF0001084870
10 | X209 | P.S. 209 - BRONX | SCA CIP | PLAYGROUND SAFETY SURFACE | Scope | Complete | 4/13/2023 | 7/14/2023 | 4/13/2023 | 3336 | 5765 | 0 | DSF0001083965
10 | X209 | P.S. 209 - BRONX | SCA CIP | PLAYGROUND SAFETY SURFACE | Design | Complete | 4/13/2023 | 8/29/2023 | 5/24/2023 | 15010 | 0 | 0 | DSF0001083965
10 | X209 | P.S. 209 - BRONX | SCA CIP | PLAYGROUND SAFETY SURFACE | Construction | PNS | PNS | PNS | PNS | 193461 | 193461 | 0 | DSF0001083965
10 | X209 | P.S. 209 - BRONX | SCA CIP | PLAYGROUND SAFETY SURFACE | CM,F&E | PNS | PNS | PNS | PNS | 35857 | 35857 | 0 | DSF0001083965
10 | X254 | I.S. 254 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/24/2023 | DOES | 6/20/2024 | DOES | 354611 | 349841 | DSF0001035177
10 | X254 | I.S. 254 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/6/2024 | DOES | 8/16/2024 | DOES | 50832 | 8909 | DSF0001084872
10 | X279 | P.S. 279 - BRONX | SCA CIP RESOA | PLAYGROUND UPGRADE | Scope | Complete | 12/6/2021 | 4/8/2022 | 9/21/2022 | 0 | 237409 | 234571 | DSF0001031599
10 | X279 | P.S. 279 - BRONX | SCA CIP RESOA | PLAYGROUND UPGRADE | Design | In-Progress | 8/14/2023 | 1/2/2024 |  | 660000 | 422591 | 131945 | DSF0001031599
10 | X279 | P.S. 279 - BRONX | SCA CIP RESOA | PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 9680000 | 9680000 | 2932 | DSF0001031599
10 | X279 | P.S. 279 - BRONX | SCA CIP RESOA | PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 660000 | 660000 | 22276 | DSF0001031599
10 | X279 | P.S. 279 - BRONX | Fast Track Projects | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 80000 | 0 | DSF0000890968
10 | X279 | P.S. 279 - BRONX | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 435000 | 0 | DSF0000800475
10 | X279 | P.S. 279 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | Complete | 6/24/2022 | DOER | 11/15/2022 | DOER | 28508 | 28125 | DSF0001007905
10 | X279 | P.S. 279 - BRONX | DOE - Skilled Trades | ACE FAN SYSTEM UPGRADE | Construction | In-Progress | 10/2/2019 | DOES |  | DOES | 14946 | 95806 | DSF0000909328
10 | X279 | P.S. 279 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/4/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084720
10 | X283 | I.S. 228 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/27/2024 | DOER |  | DOER | 133464 | 0 | DSF0001035295
10 | X283 | I.S. 228 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/20/2023 | DOES |  | DOES | 50832 | 0 | DSF0001085562
10 | X306 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/17/2018 | 3/7/2019 | 9/3/2019 | 172980 | 232788 | 232788 | DSF0000886521, DSF0000886522, DSF0000886523, DSF0000886524
10 | X306 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/4/2019 | 2/7/2020 | 5/14/2021 | 864901 | 990299 | 968882 | DSF0000886521, DSF0000886522, DSF0000886523, DSF0000886524
10 | X306 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | Complete | 7/19/2021 | 10/6/2023 | 12/10/2024 | 19460250 | 18748741 | 17374945 | DSF0000886521, DSF0000886522, DSF0000886523, DSF0000886524
10 | X306 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 7/19/2021 | 10/6/2023 | 12/10/2024 | 1210860 | 781551 | 780302 | DSF0000886521, DSF0000886522, DSF0000886523, DSF0000886524
10 | X306 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/20/2022 | 1/24/2023 | 9/29/2022 | 6272 | 3036 | 3036 | DSF0001034671
10 | X306 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/29/2022 | 3/30/2023 | 1/11/2023 | 28224 | 12143 | 12143 | DSF0001034671
10 | X306 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/5/2023 | 6/3/2024 |  | 363775 | 332451 | 302201 | DSF0001034671
10 | X306 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/5/2023 | 6/3/2024 |  | 260621 | 229294 | 194954 | DSF0001034671
10 | X306 | P.S. 306 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 11/29/2023 | 4/2/2024 | 2/28/2024 | 0 | 13189 | 13189 | DSF0001086814
10 | X306 | P.S. 306 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | Complete | 2/29/2024 | 7/16/2024 | 5/1/2024 | 30000 | 32039 | 31337 | DSF0001086814
10 | X306 | P.S. 306 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 8451 | DSF0001086814
10 | X306 | P.S. 306 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 11573 | DSF0001086814
10 | X306 | P.S. 306 - BRONX | SCA Emergency Response | EMERGENCY WORK- FIRE PUMP | Construction | In-Progress | 1/25/2013 | EMER |  | EMER |  | 0 | SCA0000024572
10 | X306 | P.S. 306 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001086811
10 | X306 | X186 SPED - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 110000 | 0 | DSF0001086812
10 | X306 | X186 SPED - BRONX | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 104000 | 0 | DSF0001113401
10 | X306 | P.S. 306 - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMPS | Construction | In-Progress | 6/21/2019 | DOES |  | DOES | 230055 | 0 | DSF0000911901
10 | X306 | P.S. 306 - BRONX | DOE - Skilled Trades | PUBLIC ADDRESS SYSTEM | Construction | In-Progress | 6/8/2021 | DOES |  | DOES | 182479 | 0 | DSF0001004294
10 | X306 | I.S. 331 - BRONX | Trust For Public Land | FY22 RESO A PLAYGROUND UPGRADE | Construction | Complete | 1/20/2024 | TPL | 10/25/2024 | TPL | 5099430 | 4015666 | DSF0001033409
10 | X340 | P.S. 340 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 10/7/2024 | DIIR | 49824 | 49824 | DSF0001008471
10 | X347 | P.S. 33 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 11/12/2024 | IEH | 11/22/2024 | IEH | 0 | 0 | SCA0000073597
10 | X360 | P.S. 360 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 12/5/2023 | 3/7/2024 |  | 0 | 8411 | 1875 | DSF0001086815
10 | X360 | P.S. 360 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 15000 | 7500 | 7500 | DSF0001086815
10 | X360 | P.S. 360 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 220000 | 220000 | 0 | DSF0001086815
10 | X360 | P.S. 360 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 15000 | 15000 | 1858 | DSF0001086815
10 | X360 | P.S. 360 - BRONX | Fast Track Projects | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 12/10/2019 | FTK |  | FTK | 78481 | 77364 | DSF0000866428
10 | X361 | P.S. 94 - BRONX | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 9/29/2020 | FTK |  | FTK | 153154 | 122661 | DSF0000961063
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ASPHALT PAVEMENT AT TIBBETT AVE | Scope | Complete | 3/14/2023 | 6/12/2023 | 2/5/2024 | 108500 | 306976 | 306976 | DSF0001082482
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ASPHALT PAVEMENT AT TIBBETT AVE | Design | Complete | 2/20/2024 | 7/5/2024 | 5/16/2024 | 542500 | 184418 | 23824 | DSF0001082482
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ASPHALT PAVEMENT AT TIBBETT AVE | Construction | PNS | PNS | PNS | PNS | 12206250 | 12206250 | 16521 | DSF0001082482
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ASPHALT PAVEMENT AT TIBBETT AVE | CM,F&E | PNS | PNS | PNS | PNS | 759500 | 759500 | 30964 | DSF0001082482
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/14/2024 | 10/31/2024 | 9/16/2024 | 130463 | 112841 | 100629 | DSF0001082473, DSF0001110429
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 10/29/2024 | 4/3/2025 |  | 644865 | 644865 | 312889 | DSF0001082473, DSF0001110429
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 13816756 | 13816756 | 152 | DSF0001082473, DSF0001110429
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 920689 | 920689 | 18753 | DSF0001082473, DSF0001110429
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | Scope | Complete | 4/28/2022 | 7/29/2022 | 7/20/2022 | 0 | 0 | 84927 | DSF0001034112
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | Design | In-Progress | 8/9/2022 | 1/12/2023 |  | 63000 | 63000 | 52051 | DSF0001034112
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | Construction | PNS | PNS | PNS | PNS | 924000 | 924000 | 49101 | DSF0001034112
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 63000 | 63000 | 21634 | DSF0001034112
10 | X368 | X721 SPED - BRONX | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001008575
10 | X368 | M.S./H.S. 368 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113405
10 | X368 | M.S./H.S. 368 - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086820
10 | X373 | ROSE HILL PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/11/2023 | DOES | 12/11/2024 | DOES | 50832 |  | DSF0001085568
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | Scope | Complete | 6/18/2019 | 12/16/2019 | 11/20/2019 | 403971 | 366171 | 363130 | DSF0000909503, DSF0000909505, DSF0000909506, DSF0000909507, DSF0000955325, DSF0000955327
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | Design | Complete | 12/18/2019 | 6/15/2020 | 5/15/2020 | 2007396 | 754868 | 749358 | DSF0000909503, DSF0000909505, DSF0000909506, DSF0000909507, DSF0000955325, DSF0000955327
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | Construction | In-Progress | 5/17/2021 | 5/15/2024 |  | 44088491 | 41694034 | 39013312 | DSF0000909503, DSF0000909505, DSF0000909506, DSF0000909507, DSF0000955325, DSF0000955327
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 5/17/2021 | 5/15/2024 |  | 2954624 | 1052285 | 1039003 | DSF0000909503, DSF0000909505, DSF0000909506, DSF0000909507, DSF0000955325, DSF0000955327
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FIRE SPRINKLER SYSTEM | Scope | Complete | 8/10/2023 | 11/9/2023 | 11/8/2023 | 19190 | 49566 | 49566 | DSF0001082667
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FIRE SPRINKLER SYSTEM | Design | Complete | 11/20/2023 | 5/23/2024 | 8/5/2024 | 76759 | 71345 | 63878 | DSF0001082667
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FIRE SPRINKLER SYSTEM | Construction | PNS | PNS | PNS | PNS | 1103408 | 1103408 | 2710 | DSF0001082667
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FIRE SPRINKLER SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 283048 | 283048 | 19308 | DSF0001082667
10 | X430 | M.S./H.S. 342 - BRONX | SCA IEH | PO18-REPAIR HEATING VENTILATOR FOR GYM 3 1ST COIL ON THE RIGHT IS LEAKING. COIL IS ISOLATED BUT CONT | Construction | Complete | 11/4/2024 | IEH | 11/10/2024 | IEH | 0 | 0 | SCA0000073566
10 | X430 | CELIA CRUZ HS OF MUSIC - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 125000 | DSF0001086836
10 | X430 | DISCOVERY HS - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 130000 | 0 | DSF0001086835
10 | X430 | KINGSBRIDGE INTERNATIONAL HS - X | DOE - RESOA | FY11 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0 | DSF0000710916
10 | X430 | KINGSBRIDGE INTERNATIONAL HS - X | DOE - RESOA | FY14 RESO A ROOM CONVERSIONS / PART | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0 | DSF0000798838
10 | X430 | M.S./H.S. 342 - BRONX | DOE - RESOA | FY18 RESO A LIBRARY UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 724826 | 0 | DSF0000866411
10 | X430 | M.S./H.S. 342 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 12/12/2022 | DOES |  | DOES | 65771 | 0 | DSF0001034473
10 | X430 | KINGSBRIDGE INTERNATIONAL HS - X | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/24/2023 | DOES | 3/15/2024 | DOES | 530995 |  | DSF0001035131
10 | X430 | M.S./H.S. 342 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 10/10/2024 | DOES | 65832 | 18252 | DSF0001085075
10 | X431 | M.S./H.S. 342 - BRONX | DOE - RESOA | RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113729
10 | X432 | ROSE HILL PRE-K CENTER | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 161000 | 0 | DSF0001113416
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | Scope | Complete | 2/7/2020 | 7/21/2023 | 8/4/2023 | 223330 | 163994 | 134288 | DSF0000955347, DSF0001034191, DSF0001110655
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | Design | Complete | 8/30/2023 | 1/5/2024 | 4/11/2024 | 1116650 | 717229 | 394155 | DSF0000955347, DSF0001034191, DSF0001110655
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | Construction | In-Progress | 9/16/2024 | 9/15/2027 |  | 25124625 | 22530055 | 85676 | DSF0000955347, DSF0001034191, DSF0001110655
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | CM,F&E | In-Progress | 9/16/2024 | 9/15/2027 |  | 1563310 | 80271 | 80002 | DSF0000955347, DSF0001034191, DSF0001110655
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP RESOA | RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/17/2023 | 3/22/2024 | 11/4/2024 | 0 | 18994 | 1748 | DSF0001087229
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP RESOA | RESO A AUDITORIUM UPGRADE | Design | In-Progress | 11/4/2024 | 4/9/2025 |  | 54000 | 35006 | 6991 | DSF0001087229
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 792000 | 792000 | 0 | DSF0001087229
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP RESOA | RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 54000 | 54000 | 11735 | DSF0001087229
10 | X435 | KAPPA - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/25/2024 | DIIR | 10/18/2024 | DIIR | 100000 | 100000 | DSF0001033419
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 9/11/2024 | DIIR | 11/20/2024 | DIIR | 200000 | 200000 | DSF0001086837
10 | X435 | BELMONT PREPARATORY HS - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/26/2024 | DOER |  | DOER | 208250 | 0 | DSF0001035304
10 | X435 | HS OF LAW & COMMUNITY SERV - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/25/2023 | DOER |  | DOER | 179084 | 0 | DSF0001035305
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0 | DSF0001112248
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 2/17/2023 | DOES | 2/22/2024 | DOES | 968456 | 1600 | DSF0000960873
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/26/2024 | DOES | 10/8/2024 | DOES | 65832 |  | DSF0001085076
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE | Scope | In-Progress | 6/18/2021 | 10/20/2021 |  | 0 | 19172 | 19172 | DSF0001007873
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 89250 | 70078 | 6414 | DSF0001007873
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 1308998 | 1320000 | 0 | DSF0001007873
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 89250 | 90000 | 503 | DSF0001007873
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007878
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007878
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007878
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007878
10 | X440 | DEWITT CLINTON HS - X | SCA IEH | PO18-ABATE ACM PIPE INSULATION ROOM 201 A PIECE OF ACM FELL OFF NO KIDS WERE IN THE ROOM ROOM IS NOW | Construction | In-Progress | 1/26/2024 | IEH |  | IEH | 0 | 0 | SCA0000072689
10 | X440 | DEWITT CLINTON HS - X | SCA IEH | PO18-TEST AND REMOVE 10' OF ACM PIPE COVERING - ROOM B56 - SPRAYED RED FOR ID | Construction | Complete | 10/25/2024 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000073545
10 | X440 | DEWITT CLINTON HS - X | SCA IEH | PO18-REMOVE 10' OF ACM PIPE COVER IN CRAWLSPACE, MARKED ORANGE FOR ID. SPACE ID #3091 | Construction | Complete | 11/26/2024 | IEH | 11/29/2024 | IEH | 0 | 0 | SCA0000073644
10 | X440 | DEWITT CLINTON HS - X | Fast Track Projects | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/28/2022 | FTK |  | FTK | 222773 | 210688 | DSF0000913517
10 | X440 | PATHWAYS TO GRADUATION - CITYWIDE | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001113417
10 | X440 | DEWITT CLINTON HS - X | DOE - Skilled Trades | ACE- STEAM SYSTEM UPGRADE | Construction | In-Progress | 4/9/2019 | DOES |  | DOES | 286139 | 0 | DSF0000909543
10 | X440 | DEWITT CLINTON HS - X | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 2/3/2023 | DOES |  | DOES | 1036316 | 0 | DSF0000960874
10 | X440 | DEWITT CLINTON HS - X | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/23/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085077
10 | X441 | DEWITT CLINTON HS - X | SCA IEH | PO18-ABATE AND REPAIR AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVELLANCE REPORT PL | Construction | Complete | 5/22/2023 | IEH | 10/6/2024 | IEH | 0 | 0 | SCA0000072006
10 | X443 | ROSE HILL PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/18/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085572
10 | X444 | ROSE HILL PRE-K CENTER | SCA IEH | PO18-ABATE 7 FT X 9 FT SECTION OF THE WOOD FLOOR IN CLASSROOM 303 SOFT CONCRETE FILLER MATERIAL / FE | Construction | In-Progress | 8/28/2023 | IEH |  | IEH | 0 | 0 | SCA0000072248
10 | X444 | ROSE HILL PRE-K CENTER | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 153000 | 0 | DSF0001113418
10 | X445 | BRONX HS OF SCIENCE - X | SCA CIP RESOA | RESO A CAFETERIA UPGRADE | Scope | In-Progress | 3/22/2022 | 7/21/2022 |  | 0 | 42212 | 26002 | DSF0001034528
10 | X445 | BRONX HS OF SCIENCE - X | SCA CIP RESOA | RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 30000 | 4049 | 4049 | DSF0001034528
10 | X445 | BRONX HS OF SCIENCE - X | SCA CIP RESOA | RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001034528
10 | X445 | BRONX HS OF SCIENCE - X | SCA CIP RESOA | RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001034528
10 | X445 | BRONX HS OF SCIENCE - X | SCA IEH | PO18-ABATE BASEMENT HALLWAY CEILING ABATE AND REPAIR PIPE INSULATION IN BASEMENT HALLWAY | Construction | Complete | 8/1/2024 | IEH | 8/4/2024 | IEH | 0 | 0 | SCA0000073221
10 | X445 | BRONX HS OF SCIENCE - X | SCA IEH | PO18-ABATE MEDICAL SUITE CEILING 049, 049A, 049B, 049C, 049D, 049E | Construction | Complete | 8/7/2024 | IEH | 8/11/2024 | IEH | 0 | 0 | SCA0000073257
10 | X445 | BRONX HS OF SCIENCE - X | SCA IEH | PO18-SPACE ID: 1095F - OIL TANK ROOM - REMOVE 10 LF OF FALLEN ACM PIPE INSULATION. | Construction | Complete | 10/8/2024 | IEH | 11/16/2024 | IEH | 0 | 0 | SCA0000073474
10 | X445 | BRONX HS OF SCIENCE - X | DOE - RESOA | FY14 RESO A ROOM CONVERSIONS / PART | Construction | PNS | PNS | PNS | PNS | DOER | 16902 | 0 | DSF0000798839
10 | X445 | BRONX HS OF SCIENCE - X | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 10/11/2023 | DOES |  | DOES | 179841 | 0 | DSF0000820296
10 | X445 | BRONX HS OF SCIENCE - X | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 3/8/2021 | DOES |  | DOES | 220921 | 0 | DSF0000960500
10 | X445 | BRONX HS OF SCIENCE - X | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/12/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085078
10 | X445 | BRONX HS OF SCIENCE - X | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 388699 | 0 | DSF0001085777
10 | X448 | P.S. 340 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 11/1/2024 | IEH | 11/8/2024 | IEH | 0 | 0 | SCA0000073560
10 | X469 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | Scope | Complete | 9/24/2019 | 3/5/2020 | 3/12/2020 | 1153240 | 901254 | 900397 | DSF0000889039, DSF0000889039
10 | X469 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | Design | Complete | 3/13/2020 | 9/23/2020 | 5/14/2021 | 5189580 | 3358162 | 2999764 | DSF0000889039, DSF0000889039
10 | X469 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 12/20/2021 | 9/3/2024 |  | 65446370 | 65169463 | 58653067 | DSF0000889039, DSF0000889039
10 | X469 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | CM,Art,F&E | In-Progress | 12/20/2021 | 9/3/2024 |  | 9225920 | 7235245 | 5991643 | DSF0000889039, DSF0000889039
10 | X469 | X000 - BRONX | SCA CIP RESOA | FY19 RESO A ROOFTOP PLAYGROUND | Scope | PNS | PNS | PNS | PNS | 0 | 17078 | 39 | DSF0000890947
10 | X469 | X000 - BRONX | SCA CIP RESOA | FY19 RESO A ROOFTOP PLAYGROUND | Design | PNS | PNS | PNS | PNS | 1022 | 154 | 154 | DSF0000890947
10 | X469 | X000 - BRONX | SCA CIP RESOA | FY19 RESO A ROOFTOP PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 14994 | 844800 | 0 | DSF0000890947
10 | X469 | X000 - BRONX | SCA CIP RESOA | FY19 RESO A ROOFTOP PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 1022 | 57600 | 0 | DSF0000890947
10 | X475 | BRONX THEATRE HS - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 5/3/2023 | 9/19/2023 | 10/28/2024 | 36140 | 154417 | 1552 | DSF0001083933
10 | X475 | BRONX THEATRE HS - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | In-Progress | 12/4/2024 | 5/7/2025 |  | 180701 | 180701 | 6209 | DSF0001083933
10 | X475 | BRONX THEATRE HS - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Construction | PNS | PNS | PNS | PNS | 4065769 | 4065769 | 542617 | DSF0001083933
10 | X475 | BRONX THEATRE HS - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | CM,F&E | PNS | PNS | PNS | PNS | 252981 | 252981 | 134193 | DSF0001083933
10 | X475 | ELLIS PREPARATORY ACADEMY-X | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 200000 | 200000 | 0 | DSF0001086848
10 | X475 | BRONX SCHOOL OF LAW & FINANCE - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 151000 | 134200 | DSF0001086847
10 | X475 | BRONX THEATRE HS - BRONX | DOE - RESOA | FY19 RESO A HYDROPONIC LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0000890983
10 | X475 | ELLIS PREPARATORY ACADEMY-X | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | Complete | 12/26/2022 | DOER | 7/8/2024 | DOER | 304739 | 250149 | DSF0001007883
10 | X475 | BRONX THEATRE HS - BRONX | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 55000 | 0 | DSF0001034143
10 | X475 | MARBLE HILL INTERNATIONAL HS - X | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/12/2021 | DOES |  | DOES | 200590 | 0 | DSF0000913016
10 | X475 | MARBLE HILL INTERNATIONAL HS - X | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 1/19/2022 | DOES | 4/29/2022 | DOES | 269992 | 266359 | DSF0001009041
10 | X475 | BX ENGINEERING & TECH ACADEMY - X | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/2/2024 | DOES |  | DOES | 1567633 | 0 | DSF0001085778
10 | X475 | BRONX THEATRE HS - BRONX | DOE - Skilled Trades | EXTERIOR MASONRY REPAIRS | Construction | In-Progress | 11/29/2023 | DOES |  | DOES | 260000 | 0 | DSF0001110825
10 | X475 | BRONX THEATRE HS - BRONX | DOE - Skilled Trades | ELEVATOR CABLE REPLACEMENT | Construction | In-Progress | 3/12/2024 | DOES |  | DOES | 78000 | 0 | DSF0001110820
10 | X476 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | Scope | Complete | 4/14/2021 | 8/13/2021 | 1/21/2022 | 36500 | 111873 | 107021 | DSF0000955493
10 | X476 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | Design | Complete | 1/21/2022 | 6/13/2022 | 5/10/2022 | 182499 | 275191 | 203468 | DSF0000955493
10 | X476 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | Construction | Complete | 8/15/2022 | 2/5/2024 | 7/24/2024 | 4106226 | 3868391 | 3810325 | DSF0000955493
10 | X476 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | CM,F&E | Complete | 8/15/2022 | 2/5/2024 | 7/24/2024 | 255499 | 386960 | 386529 | DSF0000955493
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA Capacity | NEW SCHOOL | Scope | Complete | 7/19/2022 | 12/30/2022 | 1/20/2023 | 1788220 | 905274 | 878322 | DSF0000867118
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA Capacity | NEW SCHOOL | Design | Complete | 1/23/2023 | 8/18/2023 | 5/14/2024 | 8046990 | 2707680 | 1746505 | DSF0000867118
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 11/5/2024 | 9/3/2028 |  | 101481485 | 90003390 | 563067 | DSF0000867118
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 11/5/2024 | 9/3/2028 |  | 14305760 | 5486611 | 427479 | DSF0000867118
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | Scope | Complete | 1/26/2023 | 1/26/2023 | 1/26/2023 | 42240 | 4388 | 4388 | DSF0000867118
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | Design | Complete | 1/26/2023 | 5/25/2023 | 12/8/2023 | 211200 | 281599 | 221311 | DSF0000867118
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | Construction | In-Progress | 7/22/2024 | 4/17/2025 |  | 4752000 | 4351954 | 1502045 | DSF0000867118
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 7/22/2024 | 4/17/2025 |  | 295680 | 317983 | 309201 | DSF0000867118
10 | X533 | P.S. @ 6389-6393 BROADWAY - BRONX | SCA Capacity | NEW SCHOOL | Scope | In-Progress | 10/10/2024 | 4/10/2025 |  | 2000000 | 2000000 | 14948 | DSF0001034280
10 | X533 | P.S. @ 6389-6393 BROADWAY - BRONX | SCA Capacity | NEW SCHOOL | Design | PNS | PNS | PNS | PNS | 8000000 | 8000000 | 16192 | DSF0001034280
10 | X533 | P.S. @ 6389-6393 BROADWAY - BRONX | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 110500000 | 110500000 | 304569 | DSF0001034280
10 | X533 | P.S. @ 6389-6393 BROADWAY - BRONX | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 14500000 | 14500000 | 142297 | DSF0001034280
10 | X533 | P.S. @ 6389-6393 BROADWAY - BRONX | SCA CIP | DEMOLITION | Scope | Complete | 10/31/2024 | 10/31/2024 | 10/31/2024 | 68495 | 0 | 0 | DSF0001034280
10 | X533 | P.S. @ 6389-6393 BROADWAY - BRONX | SCA CIP | DEMOLITION | Design | In-Progress | 10/31/2024 | 4/15/2025 |  | 319644 | 319644 | 0 | DSF0001034280
10 | X533 | P.S. @ 6389-6393 BROADWAY - BRONX | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 5068646 | 5068646 | 0 | DSF0001034280
10 | X533 | P.S. @ 6389-6393 BROADWAY - BRONX | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 502298 | 502298 | 4753 | DSF0001034280
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/3/2023 | 5/4/2023 | 7/19/2023 | 0 | 73400 | 57647 | DSF0001036301
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/16/2023 | 1/4/2024 | 4/9/2024 | 225512 | 106066 | 103164 | DSF0001036301
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 3307510 | 3307510 | 30358 | DSF0001036301
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 225512 | 225512 | 20445 | DSF0001036301
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/6/2023 | 7/6/2023 | 11/20/2023 | 0 | 0 | 2698 | DSF0001036300
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 11/30/2023 | 4/1/2024 |  | 433 | 433 | 10793 | DSF0001036300
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 6353 | 6353 | 1725 | DSF0001036300
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 433 | 433 | 37628 | DSF0001036300
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | SCA IEH | PO18-SPACE ID: 5302 CLASSROOM 302 - DAMAGED 9' X 9' FLOOR TILES ASSUMED UNDER SINK IN CLASSROOM. TES | Construction | Complete | 9/19/2024 | IEH | 11/2/2024 | IEH | 0 | 0 | SCA0000073402
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | SCA IEH | PO18-CLASSROOM 309 - DAMAGED 9' X 9' FLOOR TILES ASSUMED REMOVE HALF DIVIDING WALL (DOES NOT CONNECT | Construction | In-Progress | 11/14/2024 | IEH |  | IEH | 0 | 0 | SCA0000073606
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES CLOSET IN ROOM #117D | Construction | Complete | 11/26/2024 | IEH | 12/31/2024 | IEH | 0 | 0 | SCA0000073646
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 9/11/2024 | DIIR | 11/19/2024 | DIIR | 200000 | 200000 | DSF0001086852
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 58336 | 0 | DSF0001035312
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/12/2022 | DOES |  | DOES | 68617 | 538855 | DSF0001032220
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 8/4/2023 | DOES | 11/6/2023 | DOES | 549827 |  | DSF0001035132
10 | X779 | P.S. 315 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY22 RESO A GYMNASIUM UPGRADE | Scope | Complete | 8/11/2022 | 3/1/2023 | 1/13/2023 | 0 | 20810 | 20810 | DSF0001034102, DSF0001034104
10 | X779 | P.S. 315 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 1/18/2023 | 5/11/2023 | 5/5/2023 | 72000 | 70097 | 21533 | DSF0001034102, DSF0001034104
10 | X779 | P.S. 315 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/29/2023 | 9/23/2024 |  | 1056000 | 609959 | 387970 | DSF0001034102, DSF0001034104
10 | X779 | P.S. 315 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY22 RESO A GYMNASIUM UPGRADE | CM,F&E | In-Progress | 11/29/2023 | 9/23/2024 |  | 72000 | 77796 | 68633 | DSF0001034102, DSF0001034104
10 | X779 | P.S. 315 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 300000 | 300000 | 0 | DSF0001036303
10 | X779 | P.S. 315 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113428
10 | X779 | P.S. 315 - BRONX | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001034101
10 | X779 | P.S. 315 - BRONX | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001034705
10 | X779 | P.S. 315 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/3/2024 | DOES | 10/24/2024 | DOES | 65832 | 6102 | DSF0001085577
10 | X780 | SUCCESS ACADEMY CHARTER SCHOOL - HARLEM 6 | SCA IEH | PO18-ABATE ACM PIPE INSULATION IN CAFETERIA APPROX: 40 FT. | Construction | Complete | 8/30/2024 | IEH | 9/12/2024 | IEH | 0 | 0 | SCA0000073338
10 | X781 | THE BRONX STEM AND ARTS ACADEMY - BRONX | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 812000 | 0 | DSF0001113429
10 | X819 | P.S. 207 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 437000 | 0 | DSF0001007881
10 | X819 | P.S. 207 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/22/2024 | DIIR |  | DIIR | 75000 | 0 | DSF0001034082
10 | X819 | P.S. 207 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001113434
10 | X819 | P.S. 207 - BRONX | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 2/11/2022 | DOER |  | DOER | 456732 | 0 | DSF0000890963
10 | X819 | P.S. 207 - BRONX | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 263537 | 0 | DSF0000913521
10 | X826 | P.S. 226 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/16/2024 | 11/14/2024 | 7/23/2024 | 3305 | 1562 | 1562 | DSF0001087597
10 | X826 | P.S. 226 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/23/2024 | 1/21/2025 |  | 14872 | 14872 | 6248 | DSF0001087597
10 | X826 | P.S. 226 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 191687 | 191687 | 1810 | DSF0001087597
10 | X826 | P.S. 226 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 39792 | 39792 | 10764 | DSF0001087597
10 | X826 | P.S. 226 - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 472000 | 472000 | 0 | DSF0001113435
10 | X826 | P.S. 226 - BRONX | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | In-Progress | 3/22/2024 | DOER |  | DOER | 272491 | 0 | DSF0001086856
10 | X827 | P.S. 226 - BRONX | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | In-Progress | 11/22/2023 | DOER |  | DOER | 98973 | 0 | DSF0001036304
10 | X842 | X168 SPED - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/29/2024 | IEH | 9/26/2024 | IEH | 0 | 0 | SCA0000073187
10 | X843 | P.S. 246 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/13/2024 | DIIR | 10/18/2024 | DIIR | 249122 | 249122 | DSF0001086858
10 | X843 | P.S. 246 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 11/22/2023 | DOEL |  | DOEL | 121996 | 121996
10 | X843 | P.S. 246 - BRONX | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 52000 | 0 | DSF0000913522
10 | X852 | BRONX DANCE ACADEMY - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001036305
10 | X852 | BRONX DANCE ACADEMY - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113438
10 | X852 | BRONX DANCE ACADEMY - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | Complete | 8/2/2023 | DOER | 8/31/2023 | DOER | 16863 |  | DSF0001034100
10 | X852 | BRONX DANCE ACADEMY - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086860
10 | X853 | P.S. 59 - BRONX | SCA CIP | ROOFS | Scope | Complete | 7/19/2019 | 12/5/2019 | 11/6/2019 | 21987 | 21606 | 21606 | DSF0000909948
10 | X853 | P.S. 59 - BRONX | SCA CIP | ROOFS | Design | Complete | 11/13/2019 | 4/16/2020 | 5/12/2021 | 109937 | 118840 | 111696 | DSF0000909948
10 | X853 | P.S. 59 - BRONX | SCA CIP | ROOFS | Construction | In-Progress | 4/17/2023 | 7/9/2024 |  | 2473592 | 2870461 | 1558453 | DSF0000909948
10 | X853 | P.S. 59 - BRONX | SCA CIP | ROOFS | CM,F&E | In-Progress | 4/17/2023 | 7/9/2024 |  | 153912 | 1359492 | 1296749 | DSF0000909948
10 | X859 | KIPP FREEDOM CHARTER SCHOOL - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/16/2024 | DOES | 9/24/2024 | DOES | 65832 |  | DSF0001085579
10 | X886 | GIRLS PREPARATORY CHARTER SCHOOL OF THE BRONX II | SCA CIP | HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 12/15/2023 | 5/17/2024 | 5/24/2024 | 72617 | 124643 | 124643 | DSF0001111813, DSF0001111340
10 | X886 | GIRLS PREPARATORY CHARTER SCHOOL OF THE BRONX II | SCA CIP | HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM | Design | In-Progress | 6/11/2024 | 12/16/2024 |  | 355133 | 355133 | 124851 | DSF0001111813, DSF0001111340
10 | X886 | GIRLS PREPARATORY CHARTER SCHOOL OF THE BRONX II | SCA CIP | HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | PNS | PNS | PNS | PNS | 7251294 | 7251294 | 24454 | DSF0001111813, DSF0001111340
10 | X886 | GIRLS PREPARATORY CHARTER SCHOOL OF THE BRONX II | SCA CIP | HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 516261 | 516261 | 34538 | DSF0001111813, DSF0001111340
10 | X930 | P.S. 9 - BRONX | SCA CIP | ROOF | Scope | Complete | 1/12/2018 | 5/30/2018 | 6/5/2018 | 18067 | 33365 | 33365 | DSF0000960658
10 | X930 | P.S. 9 - BRONX | SCA CIP | ROOF | Design | Complete | 11/28/2018 | 5/1/2019 | 4/30/2019 | 90336 | 132795 | 98771 | DSF0000960658
10 | X930 | P.S. 9 - BRONX | SCA CIP | ROOF | Construction | Complete | 8/13/2019 | 8/1/2021 | 11/29/2024 | 2032570 | 888104 | 864361 | DSF0000960658
10 | X930 | P.S. 9 - BRONX | SCA CIP | ROOF | CM,F&E | Complete | 8/13/2019 | 8/1/2021 | 11/29/2024 | 126471 | 23351 | 22883 | DSF0000960658
10 | XAYF | MINIVENTURES OF NY, INC.- SITE #4 - BRONX | Fast Track Projects | LSP - ACS EARLY LEARN LEASE RENEWAL | Construction | In-Progress | 11/30/2023 | FTK |  | FTK | 165549 | 79956 | DSF0001008791
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 10/19/2023 | 2/23/2024 | 2/26/2024 | 0 | 10741 | 3206 | DSF0001036170
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | In-Progress | 2/27/2024 | 7/12/2024 |  | 40860 | 38657 | 12824 | DSF0001036170
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 599280 | 599280 | 5452 | DSF0001036170
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 40860 | 40860 | 27735 | DSF0001036170
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 1/10/2024 | 5/24/2024 | 4/24/2024 | 0 | 490 | 490 | DSF0001111910
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | In-Progress | 4/25/2024 | 8/26/2024 |  | 5787 | 1961 | 1961 | DSF0001111910
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 84871 | 84871 | 0 | DSF0001111910
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 5787 | 5787 | 2698 | DSF0001111910
11 | X012 | X012 SPED - BRONX | SCA IEH | PO18-REMOVE 10' OF ACM PIPE INSULATION COVERING 3 LINES IN THE BASEMENT OUTSIDE B1 BY B7 AND ROOM #1 | Construction | Complete | 10/25/2024 | IEH | 11/23/2024 | IEH | 0 | 0 | SCA0000073543
11 | X012 | X012 SPED - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113305
11 | X012 | X012 SPED - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/3/2024 | DOES | 10/14/2024 | DOES | 65832 | 13490 | DSF0001085047
11 | X016 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | Scope | Complete | 1/17/2020 | 6/3/2020 | 10/19/2021 | 58202 | 113247 | 113247 | DSF0000960536, DSF0001001306, DSF0001028410, DSF0001028409, DSF0001028411
11 | X016 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | Design | Complete | 10/22/2021 | 3/29/2022 | 3/9/2022 | 281335 | 358696 | 358696 | DSF0000960536, DSF0001001306, DSF0001028410, DSF0001028409, DSF0001028411
11 | X016 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | Construction | Complete | 6/20/2022 | 3/10/2024 | 9/10/2024 | 5493262 | 5100665 | 4548575 | DSF0000960536, DSF0001001306, DSF0001028410, DSF0001028409, DSF0001028411
11 | X016 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | CM,F&E | Complete | 6/20/2022 | 3/10/2024 | 9/10/2024 | 479968 | 523533 | 519221 | DSF0000960536, DSF0001001306, DSF0001028410, DSF0001028409, DSF0001028411
11 | X016 | P.S. 16 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001113307
11 | X016 | P.S. 16 - BRONX | DOE - RESOA | FY23 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001036175
11 | X016 | P.S. 16 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086695
11 | X019 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 6/14/2023 | 10/31/2023 | 11/9/2023 | 71503 | 115650 | 115650 | DSF0001085113, DSF0001111852, DSF0001107147
11 | X019 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | Complete | 11/20/2023 | 4/23/2024 | 5/15/2024 | 348241 | 316919 | 270250 | DSF0001085113, DSF0001111852, DSF0001107147
11 | X019 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Construction | In-Progress | 8/19/2024 | 5/10/2026 |  | 7033353 | 6453073 | 192825 | DSF0001085113, DSF0001111852, DSF0001107147
11 | X019 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | CM,F&E | In-Progress | 8/19/2024 | 5/10/2026 |  | 570060 | 89994 | 89124 | DSF0001085113, DSF0001111852, DSF0001107147
11 | X019 | P.S. 19 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/24/2020 | EMER |  | EMER | 62340 | 39453 | SCA0000063351
11 | X019 | P.S. 19 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 5/10/2024 |  | 8/16/2024 | 280000 | 280000 | 279979 | DSF0001036176
11 | X019 | P.S. 19 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001113308
11 | X019 | P.S. 19 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086697
11 | X019 | P.S. 19 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/18/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084701
11 | X021 | P.S. 21 - BRONX | SCA IEH | PO18-BOILER ROOM, REPAIR 6 SQ. FT. DAMAGED BOILER SHELL - REPAIR AND ENCAPSULATE FLOOR: CAFETERIA, 3 | Construction | Complete | 7/3/2024 | IEH | 12/7/2024 | IEH | 0 | 0 | SCA0000073117
11 | X021 | P.S. 21 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 8/9/2019 | DOES |  | DOES | 301364 | 0 | DSF0000906546
11 | X041 | P.S. 41 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 1/9/2020 | 5/8/2020 | 1/15/2020 | 0 | 6825 | 6825 | DSF0000913483
11 | X041 | P.S. 41 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 1/29/2020 | 7/23/2020 | 5/6/2020 | 30000 | 27384 | 27384 | DSF0000913483
11 | X041 | P.S. 41 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/9/2021 | 4/4/2022 |  | 440000 | 220890 | 204028 | DSF0000913483
11 | X041 | P.S. 41 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/9/2021 | 4/4/2022 |  | 127480 | 155075 | 151569 | DSF0000913483
11 | X041 | P.S. 41 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 200000 | 200000 | 200000 | DSF0001086705
11 | X041 | P.S. 41 - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 347000 | 347000 | 0 | DSF0001113318
11 | X041 | P.S. 41 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/24/2022 | DOER |  | DOER | 372443 | 0 | DSF0001008460
11 | X068 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/25/2023 | 9/26/2023 | 6/7/2023 | 3490 | 2057 | 2057 | DSF0001035056
11 | X068 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/7/2023 | 12/5/2023 | 10/18/2023 | 15705 | 8228 | 8228 | DSF0001035056
11 | X068 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 3/15/2024 | 1/8/2025 |  | 202420 | 185095 | 59161 | DSF0001035056
11 | X068 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 3/15/2024 | 1/8/2025 |  | 97276 | 88885 | 81504 | DSF0001035056
11 | X068 | P.S. 68 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087118
11 | X068 | P.S. 68 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 1383 | 1383 | 0 | DSF0001087118
11 | X068 | P.S. 68 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 20282 | 20282 | 0 | DSF0001087118
11 | X068 | P.S. 68 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 1383 | 3138 | 2633 | DSF0001087118
11 | X068 | P.S. 68 - BRONX | Fast Track Projects | FY24 RESO A CTF ROOM CONVERSION | Construction | In-Progress | 5/15/2024 | FTK |  | FTK | 411718 | 349598 | DSF0001086719
11 | X076 | P.S. 76 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 7/19/2024 | 12/5/2024 | 12/6/2024 | 115963 | 100488 | 41764 | DSF0001108182, DSF0001113898, DSF0001135839
11 | X076 | P.S. 76 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | In-Progress | 12/11/2024 | 5/14/2025 |  | 537479 | 537479 | 10859 | DSF0001108182, DSF0001113898, DSF0001135839
11 | X076 | P.S. 76 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | PNS | PNS | PNS | PNS | 8490202 | 8490202 | 3630 | DSF0001108182, DSF0001113898, DSF0001135839
11 | X076 | P.S. 76 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 891288 | 891288 | 10520 | DSF0001108182, DSF0001113898, DSF0001135839
11 | X076 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 10/17/2022 | 5/26/2023 | 4/19/2023 | 15993 | 40243 | 15730 | DSF0001029478, DSF0001083913
11 | X076 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 4/19/2023 | 8/22/2023 | 5/12/2023 | 71969 | 85738 | 55855 | DSF0001029478, DSF0001083913
11 | X076 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Construction | In-Progress | 2/5/2024 | 10/31/2024 |  | 927594 | 909986 | 145529 | DSF0001029478, DSF0001083913
11 | X076 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | CM,F&E | In-Progress | 2/5/2024 | 10/31/2024 |  | 171924 | 153340 | 117068 | DSF0001029478, DSF0001083913
11 | X076 | P.S. 76 - BRONX | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 9/29/2020 | FTK |  | FTK | 105863 | 105863 | DSF0000961062
11 | X076 | P.S. 76 - BRONX | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0000961505
11 | X076 | P.S. 76 - BRONX | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 316078 | 0 | DSF0001036212
11 | X076 | P.S. 76 - BRONX | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 3/18/2022 | DOES | 4/29/2022 | DOES | 108529 | 107069 | DSF0001008944
11 | X078 | P.S. 78 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/15/2024 | 2/18/2025 | 10/18/2024 | 4887 | 299 | 299 | DSF0001087569
11 | X078 | P.S. 78 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 10/18/2024 | 4/17/2025 |  | 21989 | 21989 | 1197 | DSF0001087569
11 | X078 | P.S. 78 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 283418 | 283418 | 0 | DSF0001087569
11 | X078 | P.S. 78 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 52530 | 52530 | 1660 | DSF0001087569
11 | X078 | P.S. 78 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 375000 | 375000 | 375000 | DSF0001086722
11 | X078 | P.S. 78 - BRONX | DOE - RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 90000 | 0 | DSF0000844817
11 | X083 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/12/2022 | 9/12/2022 | 6/13/2022 | 5500 | 5796 | 5796 | DSF0001034603
11 | X083 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/13/2022 | 12/8/2022 | 12/7/2022 | 24750 | 23184 | 23184 | DSF0001034603
11 | X083 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/21/2023 | 4/15/2024 |  | 319000 | 284386 | 205234 | DSF0001034603
11 | X083 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/21/2023 | 4/15/2024 |  | 201639 | 183332 | 151647 | DSF0001034603
11 | X083 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 6/17/2022 | 11/2/2022 | 3/9/2023 | 120306 | 112568 | 110918 | DSF0001029596, DSF0001029595, DSF0001029594
11 | X083 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 3/10/2023 | 8/10/2023 | 5/12/2023 | 601528 | 403203 | 361851 | DSF0001029596, DSF0001029595, DSF0001029594
11 | X083 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 8/7/2023 | 11/3/2025 |  | 13534365 | 12504893 | 5981371 | DSF0001029596, DSF0001029595, DSF0001029594
11 | X083 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 8/7/2023 | 11/3/2025 |  | 842138 | 829815 | 806631 | DSF0001029596, DSF0001029595, DSF0001029594
11 | X083 | P.S. 83 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001086727
11 | X083 | P.S. 83 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113334
11 | X083 | P.S. 83 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/5/2024 | DOES | 9/13/2024 | DOES | 65832 |  | DSF0001084707
11 | X087 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | Scope | Complete | 4/30/2019 | 9/20/2019 | 9/20/2019 | 1096620 | 848014 | 845792 | DSF0000889274, DSF0000889274
11 | X087 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | Design | Complete | 9/23/2019 | 3/30/2020 | 6/30/2020 | 4934790 | 2962443 | 2604551 | DSF0000889274, DSF0000889274
11 | X087 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | Construction | Complete | 8/23/2021 | 9/3/2024 | 7/5/2024 | 62233185 | 58253027 | 56034214 | DSF0000889274, DSF0000889274
11 | X087 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | CM,Art,F&E | Complete | 8/23/2021 | 9/3/2024 | 7/5/2024 | 8772960 | 7499217 | 6362897 | DSF0000889274, DSF0000889274
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086732
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001086732
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001086732
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001086732
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087123
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087123
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087123
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087123
11 | X087 | P.S. 87 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0001008461
11 | X087 | P.S. 87 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 200000 | 192965 | DSF0001036219
11 | X089 | P.S. 89 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 12/13/2023 | 4/30/2024 | 9/13/2024 | 62238 | 2717 | 852 | DSF0001136088, DSF0001136092, DSF0001136091
11 | X089 | P.S. 89 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Design | In-Progress | 11/6/2024 | 4/11/2025 |  | 284754 | 284754 | 3406 | DSF0001136088, DSF0001136092, DSF0001136091
11 | X089 | P.S. 89 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Construction | PNS | PNS | PNS | PNS | 4464736 | 4464736 | 0 | DSF0001136088, DSF0001136092, DSF0001136091
11 | X089 | P.S. 89 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 519767 | 519767 | 17592 | DSF0001136088, DSF0001136092, DSF0001136091
11 | X089 | P.S. 89 - BRONX | SCA CIP | ROOFS | Scope | Complete | 12/13/2023 | 4/30/2024 | 9/13/2024 | 34256 | 34256 | 23707 | DSF0001080458
11 | X089 | P.S. 89 - BRONX | SCA CIP | ROOFS | Design | PNS | PNS | PNS | PNS | 6374 | 6374 | 6374 | DSF0001080458
11 | X089 | P.S. 89 - BRONX | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 10903 | 10903 | 10903 | DSF0001080458
11 | X089 | P.S. 89 - BRONX | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 3593 | 3593 | 3593 | DSF0001080458
11 | X089 | P.S. 89 - BRONX | SCA CIP | WINDOWS | Scope | Complete | 12/13/2023 | 4/30/2024 | 9/13/2024 | 964 | 964 | 114 | DSF0001108430
11 | X089 | P.S. 89 - BRONX | SCA CIP | WINDOWS | Design | PNS | PNS | PNS | PNS | 455 | 455 | 455 | DSF0001108430
11 | X089 | P.S. 89 - BRONX | SCA CIP | WINDOWS | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001108430
11 | X089 | P.S. 89 - BRONX | SCA CIP | WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 938 | 938 | 938 | DSF0001108430
11 | X089 | P.S. 89 - BRONX | SCA IEH | PO18-ABATE AND REPLACE FLOORING ROOMS #204, 407, 413 | Construction | Complete | 7/9/2024 | IEH | 7/20/2024 | IEH | 0 | 0 | SCA0000073122
11 | X089 | P.S. 89 - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001113336
11 | X089 | P.S. 89 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 100000 | 0 | DSF0001034049
11 | X089 | P.S. 89 - BRONX | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 3/9/2020 | DOES |  | DOES | 352561 | 0 | DSF0000911949
11 | X089 | P.S. 89 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/19/2024 | DOES | 12/13/2024 | DOES | 65832 |  | DSF0001084709
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113692
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113692
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113692
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113692
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 5/3/2022 | 8/2/2022 | 7/22/2022 | 0 | 30487 | 30487 | DSF0001034057
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/9/2022 | 12/27/2022 | 12/27/2022 | 22151 | 35333 | 28723 | DSF0001034057
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 12/29/2023 | 12/27/2024 |  | 324880 | 295914 | 251506 | DSF0001034057
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 12/29/2023 | 12/27/2024 |  | 22151 | 47883 | 47104 | DSF0001034057
11 | X096 | P.S. 96 - BRONX | SCA IEH | PO18-REMOVE 10' OF ACM IN ROOM 431 BEHIND METAL JACKET - MARKED RED FOR ID. | Construction | Complete | 10/15/2024 | IEH | 11/2/2024 | IEH | 0 | 0 | SCA0000073497
11 | X096 | P.S. 96 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 200000 | 200000 | 199842 | DSF0001086741
11 | X096 | P.S. 96 - BRONX | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113345
11 | X097 | P.S. 97 - BRONX | SCA CIP | ROOM CONVERSION AND ADA WORK IN EXISTING BUILDING (PHASE 3) | Scope | Complete | 6/1/2018 | 11/2/2018 | 5/2/2022 | 17296 | 4607 | 4607 | DSF0000798178
11 | X097 | P.S. 97 - BRONX | SCA CIP | ROOM CONVERSION AND ADA WORK IN EXISTING BUILDING (PHASE 3) | Design | Complete | 5/2/2022 | 5/2/2022 | 5/2/2022 | 63419 | 65962 | 18426 | DSF0000798178
11 | X097 | P.S. 97 - BRONX | SCA CIP | ROOM CONVERSION AND ADA WORK IN EXISTING BUILDING (PHASE 3) | Construction | PNS | PNS | PNS | PNS | 671669 | 671669 | 40337 | DSF0000798178
11 | X097 | P.S. 97 - BRONX | SCA CIP | ROOM CONVERSION AND ADA WORK IN EXISTING BUILDING (PHASE 3) | CM,F&E | PNS | PNS | PNS | PNS | 155666 | 155666 | 17401 | DSF0000798178
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/24/2022 | 4/22/2022 | 5/20/2022 | 0 | 36016 | 36016 | DSF0001034060
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 8/28/2024 | 1/16/2025 |  | 39000 | 6605 | 6605 | DSF0001034060
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 572000 | 572000 | 0 | DSF0001034060
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 39000 | 39000 | 16228 | DSF0001034060
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034059
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034059
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034059
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034059
11 | X097 | P.S. 97 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/19/2022 | DOES |  | DOES | 63866 | 0 | DSF0001034462
11 | X097 | P.S. 97 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/28/2023 | DOES | 8/9/2024 | DOES | 65832 |  | DSF0001084529
11 | X103 | P.S. 103 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001113352
11 | X103 | P.S. 103 - BRONX | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/31/2024 | DOER |  | DOER | 773021 | 0 | DSF0001036222
11 | X103 | P.S. 103 - BRONX | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/11/2022 | DOES |  | DOES | 878758 | 0 | DSF0000912642
11 | X105 | P.S. 105 - BRONX | SCA Capacity | ADDITION | Scope | Complete | 10/19/2020 | 4/6/2021 | 4/14/2021 | 1067475 | 721810 | 719545 | DSF0000911832
11 | X105 | P.S. 105 - BRONX | SCA Capacity | ADDITION | Design | Complete | 4/15/2021 | 11/9/2021 | 9/16/2022 | 4803640 | 2388235 | 1870674 | DSF0000911832
11 | X105 | P.S. 105 - BRONX | SCA Capacity | ADDITION | Construction | In-Progress | 4/6/2023 | 9/3/2025 |  | 60579232 | 54766978 | 38771094 | DSF0000911832
11 | X105 | P.S. 105 - BRONX | SCA Capacity | ADDITION | CM,Art,F&E | In-Progress | 4/6/2023 | 9/3/2025 |  | 8539804 | 6897979 | 3697766 | DSF0000911832
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-IPDVS WORK / EXISTING BUILDING-FIRE ALARM WORK / EXISTING BUILDING-ELECTRICAL SYSTEMS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/14/2022 | 1/31/2023 | 10/23/2023 | 149604 | 172167 | 172145 | DSF0000911832, DSF0000911832, DSF0000911832, DSF0000911832, DSF0000911832, DSF0001080765, DSF0001080767
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-IPDVS WORK / EXISTING BUILDING-FIRE ALARM WORK / EXISTING BUILDING-ELECTRICAL SYSTEMS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 10/25/2023 | 4/15/2024 |  | 695712 | 695712 | 210754 | DSF0000911832, DSF0000911832, DSF0000911832, DSF0000911832, DSF0000911832, DSF0001080765, DSF0001080767
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-IPDVS WORK / EXISTING BUILDING-FIRE ALARM WORK / EXISTING BUILDING-ELECTRICAL SYSTEMS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 11385166 | 11385166 | 13495 | DSF0000911832, DSF0000911832, DSF0000911832, DSF0000911832, DSF0000911832, DSF0001080765, DSF0001080767
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-IPDVS WORK / EXISTING BUILDING-FIRE ALARM WORK / EXISTING BUILDING-ELECTRICAL SYSTEMS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1166041 | 1166041 | 70415 | DSF0000911832, DSF0000911832, DSF0000911832, DSF0000911832, DSF0000911832, DSF0001080765, DSF0001080767
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-GYMNASIUM | Scope | Complete | 10/14/2022 | 1/31/2023 | 3/10/2023 | 18206 | 12613 | 12613 | DSF0000911832
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-GYMNASIUM | Design | Complete | 3/15/2023 | 8/30/2023 | 11/21/2023 | 81926 | 54764 | 52258 | DSF0000911832
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-GYMNASIUM | Construction | PNS | PNS | PNS | PNS | 1055941 | 1055941 | 23949 | DSF0000911832
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-GYMNASIUM | CM,F&E | PNS | PNS | PNS | PNS | 195713 | 195713 | 30993 | DSF0000911832
11 | X105 | P.S. 105 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION- SIDEWALK BRIDGE INSTALLATION @ X105 | Construction | In-Progress | 1/30/2023 | EMER |  | EMER | 158854 | 131786 | SCA0000071728
11 | X105 | P.S. 105 - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 200000 | 200000 | 0 | DSF0001113353
11 | X105 | P.S. 105 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033369
11 | X105 | P.S. 105 - BRONX | Trust For Public Land | FY18 RESO A PLAYGROUNDS | Construction | PNS | PNS | PNS | PNS | TPL | 800000 | 0 | DSF0000867341
11 | X106 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 4/11/2023 | 8/25/2023 | 12/20/2023 | 19293 | 57946 | 57946 | DSF0001080785
11 | X106 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | Design | Complete | 1/2/2024 | 6/3/2024 | 5/7/2024 | 96467 | 170536 | 130535 | DSF0001080785
11 | X106 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 8/12/2024 | 4/3/2026 |  | 2170514 | 1970700 | 50118 | DSF0001080785
11 | X106 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 8/12/2024 | 4/3/2026 |  | 135054 | 96939 | 96077 | DSF0001080785
11 | X106 | P.S. 106 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/6/2020 | EMER |  | EMER | 114284 | 85140 | SCA0000063150
11 | X106 | P.S. 106 - BRONX | SCA IEH | PO18-REMOVE 8' OF ACM PIPE INSULATION FROM EACH SIDE OF THE WALL IN BOILER ROOM. MARKED FOR ID - TOT | Construction | Complete | 11/7/2024 | IEH | 11/9/2024 | IEH | 0 | 0 | SCA0000073590
11 | X108 | P.S. 108 - BRONX | SCA Capacity | ADDITION | Scope | Complete | 7/1/2019 | 12/2/2019 | 1/16/2020 | 1237400 | 891489 | 850024 | DSF0000911831
11 | X108 | P.S. 108 - BRONX | SCA Capacity | ADDITION | Design | Complete | 1/17/2020 | 6/16/2020 | 5/14/2021 | 5568300 | 3004355 | 2404195 | DSF0000911831
11 | X108 | P.S. 108 - BRONX | SCA Capacity | ADDITION | Construction | Complete | 10/4/2021 | 9/3/2024 | 7/23/2024 | 70222450 | 64847694 | 62632619 | DSF0000911831
11 | X108 | P.S. 108 - BRONX | SCA Capacity | ADDITION | CM,Art,F&E | Complete | 10/4/2021 | 9/3/2024 | 7/23/2024 | 9899200 | 7398348 | 5782260 | DSF0000911831
11 | X108 | P.S. 108 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 3/4/2024 |  | 9/5/2024 | 200000 | 200000 | 199728 | DSF0001035283
11 | X108 | P.S. 108 - BRONX | DOE - RESOA | FY19 RESO A TOILETS - STUDENTS | Construction | In-Progress | 3/17/2022 | DOER |  | DOER | 169357 | 0 | DSF0000890956
11 | X108 | P.S. 108 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113355
11 | X111 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2/11/2020 | 7/13/2020 | 3/25/2020 | 59720 | 87003 | 87003 | DSF0000960651, DSF0000798407
11 | X111 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 4/2/2020 | 9/1/2020 | 8/12/2020 | 298600 | 406474 | 351170 | DSF0000960651, DSF0000798407
11 | X111 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | Complete | 5/10/2022 | 5/8/2024 | 9/25/2024 | 6718500 | 6187211 | 5971713 | DSF0000960651, DSF0000798407
11 | X111 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | Complete | 5/10/2022 | 5/8/2024 | 9/25/2024 | 418040 | 524216 | 519238 | DSF0000960651, DSF0000798407
11 | X111 | P.S. 111 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/25/2024 | 2/28/2025 | 11/4/2024 | 5220 | 133 | 133 | DSF0001087578
11 | X111 | P.S. 111 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 11/4/2024 | 5/2/2025 |  | 23492 | 23492 | 532 | DSF0001087578
11 | X111 | P.S. 111 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 302780 | 302780 | 0 | DSF0001087578
11 | X111 | P.S. 111 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 56119 | 56119 | 1983 | DSF0001087578
11 | X111 | P.S. 111 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Scope | Complete | 4/3/2024 | 8/19/2024 | 9/11/2024 | 114324 | 37514 | 21322 | DSF0001108842, DSF0001108845, DSF0001108844
11 | X111 | P.S. 111 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Design | In-Progress | 9/17/2024 | 2/21/2025 |  | 530877 | 530877 | 13711 | DSF0001108842, DSF0001108845, DSF0001108844
11 | X111 | P.S. 111 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Construction | PNS | PNS | PNS | PNS | 8207171 | 8207171 | 13689 | DSF0001108842, DSF0001108845, DSF0001108844
11 | X111 | P.S. 111 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 892352 | 892352 | 23046 | DSF0001108842, DSF0001108845, DSF0001108844
11 | X111 | P.S. 111 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000961514
11 | X111 | P.S. 111 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086750
11 | X112 | P.S. 112 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 1/23/2024 | 6/6/2024 | 7/12/2024 | 122210 | 1784 | 1784 | DSF0001113792, DSF0001108865, DSF0001108864, DSF0001113797
11 | X112 | P.S. 112 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | In-Progress | 10/16/2024 | 3/21/2025 |  | 566901 | 566901 | 7131 | DSF0001113792, DSF0001108865, DSF0001108864, DSF0001113797
11 | X112 | P.S. 112 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 8959109 | 8959109 | 0 | DSF0001113792, DSF0001108865, DSF0001108864, DSF0001113797
11 | X112 | P.S. 112 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 934119 | 934119 | 5033 | DSF0001113792, DSF0001108865, DSF0001108864, DSF0001113797
11 | X112 | P.S. 112 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/26/2023 | 4/26/2023 | 6/21/2023 | 0 | 66549 | 48240 | DSF0001036227
11 | X112 | P.S. 112 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 1/17/2024 | 5/31/2024 | 5/6/2024 | 45000 | 35343 | 34726 | DSF0001036227
11 | X112 | P.S. 112 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 3607 | DSF0001036227
11 | X112 | P.S. 112 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 18923 | DSF0001036227
11 | X112 | P.S. 112 - BRONX | SCA Emergency Response | EMERGENCY- PUBLIC PROTECTION @X112 FALLING DEBRIS | Construction | In-Progress | 10/28/2024 | EMER |  | EMER | 20139 | 0 | SCA0000073552
11 | X112 | P.S. 112 - BRONX | Fast Track Projects | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/14/2019 | FTK |  | FTK | 130816 | 128934 | DSF0000890957
11 | X112 | P.S. 112 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 221000 | 0 | DSF0001113358
11 | X112 | P.S. 112 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 170000 | 0 | DSF0001086751
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 5/22/2020 | 11/19/2020 | 10/21/2020 | 273270 | 291992 | 291992 | DSF0000953838, DSF0000953840, DSF0000953841, DSF0000953842, DSF0000953843
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 10/27/2020 | 6/15/2021 | 7/1/2021 | 1366350 | 650708 | 631971 | DSF0000953838, DSF0000953840, DSF0000953841, DSF0000953842, DSF0000953843
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 2/22/2022 | 5/11/2024 |  | 30742876 | 27993089 | 25166222 | DSF0000953838, DSF0000953840, DSF0000953841, DSF0000953842, DSF0000953843
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2/22/2022 | 5/11/2024 |  | 1912890 | 740536 | 739065 | DSF0000953838, DSF0000953840, DSF0000953841, DSF0000953842, DSF0000953843
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | AUDITORIUM UPGRADE | Scope | Complete | 10/17/2022 | 2/21/2023 | 2/9/2023 | 15645 | 52422 | 40741 | DSF0001030181
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | AUDITORIUM UPGRADE | Design | Complete | 3/2/2023 | 8/2/2023 | 12/7/2023 | 78227 | 198618 | 166172 | DSF0001030181
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1760102 | 1760102 | 47091 | DSF0001030181
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 109517 | 109517 | 33110 | DSF0001030181
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 3/22/2023 | 6/22/2023 | 6/1/2023 | 7065 | 9821 | 9821 | DSF0001083911
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 6/1/2023 | 10/4/2023 | 12/7/2023 | 31792 | 36745 | 36745 | DSF0001083911
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | PATH OF TRAVEL AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 409764 | 409764 | 6946 | DSF0001083911
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | PATH OF TRAVEL AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 75948 | 75948 | 14894 | DSF0001083911
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034113
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034113
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034113
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034113
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | FY22 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 10/7/2022 | 5/22/2023 | 4/20/2023 | 0 | 23797 | 23797 | DSF0001034114, DSF0001083917
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | FY22 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 4/20/2023 | 8/21/2023 | 5/12/2023 | 180168 | 131266 | 75473 | DSF0001034114, DSF0001083917
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | FY22 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 6/17/2024 | 1/7/2026 |  | 2642462 | 2578370 | 301421 | DSF0001034114, DSF0001083917
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | FY22 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 6/17/2024 | 1/7/2026 |  | 180168 | 25416 | 25416 | DSF0001034114, DSF0001083917
11 | X113 | THE YOUNG SCHOLARS ACADEMY - BRONX | DIIT - RESOA | FY16 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 1/28/2020 | DIIR |  | DIIR | 35000 | 0 | DSF0000844060
11 | X113 | NORTH BRONX SCHOOL OF EMPOWERMENT | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001113360
11 | X113 | NORTH BRONX SCHOOL OF EMPOWERMENT | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 235017 | 0 | DSF0001086753
11 | X113 | SCHOOL OF DIPLOMACY | DOE - RESOA | RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 97566 | 0 | DSF0001112247
11 | X113 | SCHOOL OF DIPLOMACY | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113359
11 | X113 | SCHOOL OF DIPLOMACY | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/16/2022 | DOES |  | DOES | 196585 | 0 | DSF0000866079
11 | X113 | SCHOOL OF DIPLOMACY | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/7/2023 | DOES | 10/18/2023 | DOES | 874246 |  | DSF0001035134
11 | X113 | SCHOOL OF DIPLOMACY | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/4/2024 | DOES | 10/11/2024 | DOES | 65832 | 19106 | DSF0001084852
11 | X121 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/25/2019 | 11/26/2019 | 9/25/2019 | 65450 | 96985 | 96985 | DSF0000912535, DSF0000908275
11 | X121 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 10/2/2019 | 3/9/2020 | 3/6/2020 | 327250 | 472298 | 450158 | DSF0000912535, DSF0000908275
11 | X121 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | Complete | 6/14/2021 | 6/13/2023 | 10/8/2024 | 7363125 | 7145885 | 6707182 | DSF0000912535, DSF0000908275
11 | X121 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | Complete | 6/14/2021 | 6/13/2023 | 10/8/2024 | 458150 | 909504 | 907065 | DSF0000912535, DSF0000908275
11 | X121 | P.S. 121 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113366
11 | X127 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 8/18/2020 | 1/22/2021 | 11/16/2020 | 96030 | 118715 | 118715 | DSF0000961022, DSF0000954086
11 | X127 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 11/18/2020 | 4/22/2021 | 2/3/2021 | 480151 | 490644 | 463313 | DSF0000961022, DSF0000954086
11 | X127 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 6/14/2022 | 6/12/2024 |  | 10803375 | 10320001 | 9522693 | DSF0000961022, DSF0000954086
11 | X127 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 6/14/2022 | 6/12/2024 |  | 672210 | 511676 | 511676 | DSF0000961022, DSF0000954086
11 | X127 | I.S. 127 - BRONX | SCA CIP | FLOOD ELIMINATION | Scope | In-Progress | 8/21/2024 | 1/9/2025 |  | 20000 | 43018 | 7098 | DSF0001109124
11 | X127 | I.S. 127 - BRONX | SCA CIP | FLOOD ELIMINATION | Design | PNS | PNS | PNS | PNS | 80000 | 80000 | 3992 | DSF0001109124
11 | X127 | I.S. 127 - BRONX | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 1150000 | 1150000 | 683 | DSF0001109124
11 | X127 | I.S. 127 - BRONX | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 295000 | 295000 | 15720 | DSF0001109124
11 | X127 | I.S. 127 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001113370
11 | X127 | I.S. 127 - BRONX | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001113369
11 | X127 | I.S. 127 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/28/2022 | DOES |  | DOES | 195345 | 0 | DSF0001034271
11 | X127 | I.S. 127 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/5/2024 | DOES |  | DOES | 686331 | 0 | DSF0001085772
11 | X127 | I.S. 127 - BRONX | DOE - Skilled Trades | WATER MAIN REPAIR | Construction | In-Progress | 1/23/2023 | DOES |  | DOES | 148733 | 0 | DSF0001111808
11 | X135 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/8/2021 | 11/23/2021 | 11/5/2021 | 71743 | 84165 | 84165 | DSF0001003331, DSF0001030537
11 | X135 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/1/2021 | 5/4/2022 | 5/12/2022 | 351722 | 297023 | 297023 | DSF0001003331, DSF0001030537
11 | X135 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Construction | Complete | 8/15/2022 | 5/5/2024 | 8/26/2024 | 7308851 | 6787198 | 6434361 | DSF0001003331, DSF0001030537
11 | X135 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 8/15/2022 | 5/5/2024 | 8/26/2024 | 555705 | 333369 | 333369 | DSF0001003331, DSF0001030537
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP GARDEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034131
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP GARDEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034131
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP GARDEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034131
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001034131
11 | X135 | I.S. 556 - BRONX | SCA IEH | PO18-REMOVE ASBESTOS FLOORS AND CLOSETS IN CLASSROOMS PRINCIPAL WOULD LIKE CLOSETS REMOVE FOR MORE S | Construction | In-Progress | 10/7/2022 | IEH |  | IEH | 0 | 0 | SCA0000071482
11 | X135 | I.S. 556 - BRONX | SCA IEH | PO18-ABATE PIPE INSULATION WATER FEED LINE APPROX: 6-7 FT PIPE INSULATON ON FEED LINE BOILER 1 APPRO | Construction | Complete | 12/20/2024 | IEH | 12/21/2024 | IEH | 0 | 0 | SCA0000073733
11 | X135 | I.S. 326 - BRONX | Fast Track Projects | EMERGENCY STABILIZATION- GYM ROOF REPLACEMENT | Construction | In-Progress | 5/8/2019 | FTK |  | FTK | 1378661 | 1238651 | SCA0000051725
11 | X135 | I.S. 326 - BRONX | Fast Track Projects | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 32000 | 0 | DSF0000890972
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0 | DSF0001008488
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 6/28/2023 | DOER |  | DOER | 156559 | 0 | DSF0001034688
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/27/2023 | DOER |  | DOER | 527115 | 0 | DSF0001034687
11 | X135 | I.S. 326 - BRONX | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 10/13/2023 | DOES |  | DOES | 159616 | 0 | DSF0000819133
11 | X135 | I.S. 556 - BRONX | DOE - Skilled Trades | PLAYGROUND | Construction | In-Progress | 12/13/2019 | DOES |  | DOES | 181595 | 0 | DSF0000908477
11 | X135 | I.S. 556 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/23/2024 | DOES | 8/5/2024 | DOES | 65832 | 6790 | DSF0001084860
11 | X135 | I.S. 326 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/19/2024 | DOES |  | DOES | 643718 | 0 | DSF0001085773
11 | X142 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | Scope | Complete | 7/22/2021 | 12/23/2021 | 1/14/2022 | 95580 | 103681 | 103681 | DSF0001003450
11 | X142 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | Design | Complete | 1/14/2022 | 6/16/2022 | 7/12/2022 | 477900 | 883677 | 461668 | DSF0001003450
11 | X142 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | Construction | In-Progress | 4/13/2023 | 10/3/2024 |  | 10752750 | 10221342 | 7177489 | DSF0001003450
11 | X142 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | CM,F&E | In-Progress | 4/13/2023 | 10/3/2024 |  | 669060 | 655545 | 641454 | DSF0001003450
11 | X142 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 7/26/2021 | 12/10/2021 | 11/18/2021 | 269000 | 313278 | 313278 | DSF0001003447, DSF0001030654, DSF0001034329, DSF0001034330
11 | X142 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 12/1/2021 | 5/4/2022 | 5/10/2022 | 1345001 | 831076 | 790677 | DSF0001003447, DSF0001030654, DSF0001034329, DSF0001034330
11 | X142 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Construction | In-Progress | 4/10/2023 | 4/8/2025 |  | 30262501 | 28105133 | 8660577 | DSF0001003447, DSF0001030654, DSF0001034329, DSF0001034330
11 | X142 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | CM,F&E | In-Progress | 4/10/2023 | 4/8/2025 |  | 1884057 | 784865 | 760963 | DSF0001003447, DSF0001030654, DSF0001034329, DSF0001034330
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/5/2023 | 4/8/2024 | 4/15/2024 | 0 | 28195 | 28132 | DSF0001086769
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | Complete | 4/16/2024 | 8/30/2024 | 12/4/2024 | 122340 | 74537 | 70786 | DSF0001086769
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1794327 | 1794327 | 3921 | DSF0001086769
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 122340 | 122340 | 13385 | DSF0001086769
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/28/2024 | 6/28/2024 | 9/16/2024 | 0 | 0 | 1258 | DSF0001087127
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 9/16/2024 | 1/22/2025 | 12/4/2024 | 288 | 288 | 5030 | DSF0001087127
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 4228 | 4228 | 1805 | DSF0001087127
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 288 | 288 | 3937 | DSF0001087127
11 | X142 | I.S. 529 - BRONX | SCA IEH | PO18-PLEASE REMOVE 7 LINEAR FEET OF PIPE INSULATION AND DISCARD ANY WATERDAMAGE BOXES, PAPER | Construction | Complete | 10/10/2024 | IEH | 10/27/2024 | IEH | 0 | 0 | SCA0000073490
11 | X142 | I.S. 529 - BRONX | SCA IEH | PO18-ABATE ACM PIPE INSULATION BASEMENT BOYS BATHROOM B15/ CRAWLSPACE | Construction | Complete | 10/18/2024 | IEH | 12/28/2024 | IEH | 0 | 0 | SCA0000073520
11 | X142 | I.S. 529 - BRONX | SCA IEH | PO18-TEST WALLS AND CEILING WITH(X) IN RM 319 AND HALLWAY NEXT TO RM 319, 324 & 337 FOR ELECTRICAL W | Construction | In-Progress | 11/26/2024 | IEH |  | IEH | 0 | 0 | SCA0000073649
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 388000 | 388000 | 0 | DSF0001113377
11 | X142 | I.S. 529 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 8/1/2019 | FTK |  | FTK | 158956 | 146234 | DSF0000868259, DSF0000912364
11 | X142 | I.S. 529 - BRONX | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | Complete | 1/18/2020 | DOER | 3/10/2023 | DOER | 267179 | 144278 | DSF0000866339
11 | X142 | I.S. 532 - BRONX | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001008455
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 361909 | 0 | DSF0001034896
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/11/2024 | DOER |  | DOER | 400000 | 0 | DSF0001111869
11 | X142 | I.S. 532 - BRONX | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113376
11 | X142 | I.S. 529 - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 2/2/2023 | DOES | 3/14/2023 | DOES | 569355 | 552476 | DSF0001034909
11 | X144 | I.S. 144 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 12/5/2023 | 4/22/2024 | 3/13/2024 | 17928 | 35588 | 19802 | DSF0001112090
11 | X144 | I.S. 144 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 3/15/2024 | 8/15/2024 | 9/6/2024 | 71711 | 59503 | 13974 | DSF0001112090
11 | X144 | I.S. 144 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Construction | PNS | PNS | PNS | PNS | 1030842 | 1030842 | 38558 | DSF0001112090
11 | X144 | I.S. 144 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | CM,F&E | PNS | PNS | PNS | PNS | 264433 | 264433 | 31636 | DSF0001112090
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | In-Progress | 12/4/2024 | 4/7/2025 |  | 0 | 595 | 595 | DSF0001113381
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 24000 | 23405 | 2380 | DSF0001113381
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 352000 | 352000 | 0 | DSF0001113381
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 24000 | 24000 | 0 | DSF0001113381
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113700
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113700
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113700
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113700
11 | X144 | I.S. 144 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 9/27/2023 | DOER | 2/21/2024 | DOER | 140396 |  | DSF0001036255
11 | X144 | I.S. 144 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001086772
11 | X144 | I.S. 144 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/2/2024 | DOES | 12/17/2024 | DOES | 65832 |  | DSF0001084863
11 | X153 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 3/8/2021 | 7/21/2021 | 11/12/2021 | 255795 | 281991 | 281991 | DSF0000954535, DSF0000954536, DSF0000954531, DSF0000954533, DSF0000954534, DSF0001030883, DSF0001030872
11 | X153 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/2/2021 | 5/5/2022 | 9/22/2022 | 1265251 | 953177 | 818309 | DSF0000954535, DSF0000954536, DSF0000954531, DSF0000954533, DSF0000954534, DSF0001030883, DSF0001030872
11 | X153 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 7/24/2023 | 10/20/2025 |  | 27280913 | 24567112 | 10845105 | DSF0000954535, DSF0000954536, DSF0000954531, DSF0000954533, DSF0000954534, DSF0001030883, DSF0001030872
11 | X153 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 7/24/2023 | 10/20/2025 |  | 1894858 | 589453 | 584928 | DSF0000954535, DSF0000954536, DSF0000954531, DSF0000954533, DSF0000954534, DSF0001030883, DSF0001030872
11 | X153 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/4/2022 | 9/1/2022 | 6/6/2022 | 4200 | 2936 | 2936 | DSF0001034626
11 | X153 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/6/2022 | 12/1/2022 | 11/30/2022 | 18900 | 11745 | 11745 | DSF0001034626
11 | X153 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/21/2023 | 4/15/2024 |  | 243600 | 221818 | 157567 | DSF0001034626
11 | X153 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/21/2023 | 4/15/2024 |  | 187419 | 175013 | 144739 | DSF0001034626
11 | X153 | P.S. 153 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036264
11 | X153 | P.S. 153 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 33000 | 33000 | 0 | DSF0001036264
11 | X153 | P.S. 153 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 484000 | 484000 | 0 | DSF0001036264
11 | X153 | P.S. 153 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 33000 | 33000 | 0 | DSF0001036264
11 | X153 | P.S. 153 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001086780
11 | X160 | P.S. 160 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/4/2021 | 7/2/2021 | 6/15/2021 | 0 | 15215 | 15215 | DSF0000913511
11 | X160 | P.S. 160 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 6/15/2021 | 11/16/2021 | 11/1/2021 | 20657 | 60318 | 60318 | DSF0000913511
11 | X160 | P.S. 160 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/28/2022 | 8/24/2023 |  | 302971 | 111693 | 75443 | DSF0000913511
11 | X160 | P.S. 160 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 11/28/2022 | 8/24/2023 |  | 20657 | 45953 | 45078 | DSF0000913511
11 | X160 | P.S. 160 - BRONX | SCA IEH | PO18-REPLACE APPROXIMATELY 900 SQ FT OF ACM FLOOR TILES IN CLASSROOM 110 CLASSROOM IS A D75 CLASSROO | Construction | Complete | 9/25/2024 | IEH | 11/16/2024 | IEH | 0 | 0 | SCA0000073424
11 | X160 | P.S. 160 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | In-Progress | 12/20/2024 |  |  | 289000 | 289000 | 0 | DSF0001036267
11 | X160 | P.S. 160 - BRONX | Fast Track Projects | LSP HOT WATER TANK IN BOILER ROOM | Construction | In-Progress | 7/15/2022 | FTK |  | FTK | 235492 | 63826 | DSF0000960821
11 | X160 | THE EQUALITY CHARTER SCHOOL - X | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 6/18/2022 | DOER |  | DOER | 318856 | 0 | DSF0001008458
11 | X160 | P.S. 160 - BRONX | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 155715 | 0 | DSF0001085824
11 | X160 | P.S. 160 - BRONX | DOE - Skilled Trades | CHARTER MATCH CEILING TILE REPLACEMENT | Construction | In-Progress | 12/22/2023 | DOES |  | DOES | 463919 | 0 | DSF0001083697
11 | X160 | P.S. 160 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/13/2024 | DOES | 9/20/2024 | DOES | 65832 | 5948 | DSF0001085062
11 | X169 | P.S. 169 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001086785
11 | X175 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/27/2022 | 9/27/2022 | 6/15/2022 | 3950 | 5940 | 5940 | DSF0001034560
11 | X175 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 17775 | 23758 | 23758 | DSF0001034560
11 | X175 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/16/2023 | 4/10/2024 |  | 229100 | 206572 | 182816 | DSF0001034560
11 | X175 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/16/2023 | 4/10/2024 |  | 127985 | 119326 | 100772 | DSF0001034560
11 | X175 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/19/2022 | 6/2/2023 | 3/14/2023 | 32289 | 131461 | 127626 | DSF0001034284, DSF0001083688
11 | X175 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 3/15/2023 | 12/4/2023 | 4/26/2023 | 158330 | 165443 | 153083 | DSF0001034284, DSF0001083688
11 | X175 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 11/9/2023 | 5/1/2025 |  | 3292915 | 3117917 | 781840 | DSF0001034284, DSF0001083688
11 | X175 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 11/9/2023 | 5/1/2025 |  | 249392 | 212831 | 201645 | DSF0001034284, DSF0001083688
11 | X175 | P.S. 175 - BRONX | SCA Furniture & Equipment | RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001086900
11 | X175 | P.S. 175 - BRONX | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/5/2019 | FTK |  | FTK | 46277 | 46277 | DSF0000890622
11 | X175 | P.S. 175 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0 | DSF0001086790
11 | X175 | P.S. 175 - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001113389
11 | X175 | P.S. 175 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75150 | 0 | DSF0000796587
11 | X178 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 1/24/2022 | 6/8/2022 | 8/12/2022 | 68310 | 63358 | 63358 | DSF0001034389, DSF0001031227
11 | X178 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 8/24/2022 | 2/14/2023 | 5/12/2023 | 341550 | 266407 | 257518 | DSF0001034389, DSF0001031227
11 | X178 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 7/24/2023 | 2/2/2025 |  | 7684875 | 7031358 | 3220021 | DSF0001034389, DSF0001031227
11 | X178 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 7/24/2023 | 2/2/2025 |  | 478170 | 248852 | 247182 | DSF0001034389, DSF0001031227
11 | X178 | P.S. 178 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/26/2024 | DIIR | 10/15/2024 | DIIR | 228068 | 228068 | DSF0001086792
11 | X178 | P.S. X596 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113391
11 | X178 | P.S. 178 - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 322828 | 0 | DSF0001033380
11 | X178 | P.S. 178 - BRONX | DOE - RESOA | RESO A MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 84116 | 0 | DSF0001086889
11 | X178 | P.S. 178 - BRONX | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 207276 | 0 | DSF0001086890
11 | X178 | P.S. 178 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/13/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001084716
11 | X180 | I.S. 180 - BRONX | SCA Emergency Response | EMERGENCY- CONCRETE AWNINGS @ IS180X | Construction | In-Progress | 8/1/2024 | EMER |  | EMER | 40786 | 4530 | SCA0000073226
11 | X180 | I.S. 180 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/26/2024 | DIIR | 10/4/2024 | DIIR | 150000 | 13730 | DSF0001086793
11 | X180 | I.S. 180 - BRONX | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001036273
11 | X181 | I.S. 181 - BRONX | Fast Track Projects | FY15 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 1/1/2024 | FTK |  | FTK | 2540243 | 171602 | DSF0000800367
11 | X181 | I.S. 181 - BRONX | DIIT - RESOA | FY14 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35000 | 0 | DSF0000799321
11 | X181 | I.S. 181 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/8/2024 | DIIR | 10/9/2024 | DIIR | 99518 | 99518 | DSF0001086794
11 | X181 | I.S. 181 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113392
11 | X181 | I.S. 181 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/17/2024 | DOES | 10/24/2024 | DOES | 65832 | 5935 | DSF0001084868
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Scope | Complete | 4/9/2021 | 7/12/2021 | 7/27/2022 | 0 | 12652 | 10900 | DSF0000913514
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Design | Complete | 8/17/2022 | 2/2/2023 | 3/31/2023 | 36000 | 48749 | 16432 | DSF0000913514
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Construction | Complete | 12/18/2023 | 9/12/2024 | 8/22/2024 | 528000 | 285830 | 182021 | DSF0000913514
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | CM,F&E | Complete | 12/18/2023 | 9/12/2024 | 8/22/2024 | 128751 | 125767 | 105742 | DSF0000913514
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001033428
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 161246 | 0 | DSF0001086801
11 | X194 | P.S./I.S. 194 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 195000 | 195000 | 0 | DSF0001035290
11 | X194 | P.S./I.S. 194 - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 300000 | 300000 | 0 | DSF0001113395
11 | X194 | P.S./I.S. 194 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/21/2023 | DIIR | 5/24/2024 | DIIR | 100000 | 100000 | DSF0001033383
11 | X194 | P.S./I.S. 194 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/17/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084718
11 | X292 | YOUNG VOICES ACADEMY OF THE BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001034109
11 | X311 | THE STEAM BRIDGE SCHOOL - BRONX | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 318668 | 0 | DSF0001035307
11 | X314 | THE MATILDA AVENUE SCHOOL - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113402
11 | X314 | THE MATILDA AVENUE SCHOOL - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/6/2024 | DOES | 9/10/2024 | DOES | 65832 | 7234 | DSF0001085564
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/24/2022 | 7/22/2022 | 4/12/2022 | 3008 | 3604 | 3604 | DSF0001034378
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/12/2022 | 10/5/2022 | 7/27/2022 | 13537 | 14414 | 14414 | DSF0001034378
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 4/14/2023 | 2/7/2024 |  | 174481 | 152864 | 123076 | DSF0001034378
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 4/14/2023 | 2/7/2024 |  | 197884 | 189851 | 130624 | DSF0001034378
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 325000 | 325000 | 325000 | DSF0001086818
11 | X362 | NEW WORLD HS - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001033431
11 | X362 | NEW WORLD HS - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 81000 | 0 | DSF0001035311
11 | X362 | NEW WORLD HS - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086816
11 | X362 | THE BRONXWOOD PREPARATORY ACADEMY - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086817
11 | X362 | NEW WORLD HS - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 196000 | 0 | DSF0001113404
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001113403
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/17/2024 | DOES | 12/6/2024 | DOES | 50832 |  | DSF0001085065
11 | X415 | BRONXDALE HIGH SCHOOL - BRONX | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE / PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | Complete | 12/1/2023 | 6/6/2024 | 5/1/2024 | 0 | 13438 | 3640 | DSF0001086828, DSF0001087135
11 | X415 | BRONXDALE HIGH SCHOOL - BRONX | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE / PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | Complete | 5/14/2024 | 9/12/2024 | 7/26/2024 | 43553 | 44613 | 14309 | DSF0001086828, DSF0001087135
11 | X415 | BRONXDALE HIGH SCHOOL - BRONX | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE / PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 638784 | 638784 | 2663 | DSF0001086828, DSF0001087135
11 | X415 | BRONXDALE HIGH SCHOOL - BRONX | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE / PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 43553 | 43553 | 21064 | DSF0001086828, DSF0001087135
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | SCA IEH | PO18-ABATE/ REPLACE PATCHED LENOLEUM FLOOR WITH NEW VINYLE TILE. LOCATION IS ROOM 211, CLASSROOM IS | Construction | In-Progress | 8/28/2023 | IEH |  | IEH | 0 | 0 | SCA0000072247
11 | X415 | PELHAM PREP HS - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 0 | DSF0001113411
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 350000 | 350000 | 0 | DSF0001113412
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 139586 | 0 | DSF0000960404
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001034090
11 | X415 | ASTOR COLLEGIATE HS - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001034094
11 | X415 | PELHAM PREP HS - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/25/2024 | DIIR | 3/26/2024 | DIIR | 74731 | 74731 | DSF0001034141
11 | X415 | BRONXDALE HIGH SCHOOL - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113410
11 | X415 | PELHAM PREP HS - BRONX | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086829
11 | X415 | CHRISTOPHER COLUMBUS CAMPUS YABC | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 4/2/2019 | DOES |  | DOES | 331927 | 0 | DSF0000891064
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | DOE - Skilled Trades | ELEVATOR MODERNIZATIONS | Construction | In-Progress | 3/31/2022 | DOES |  | DOES | 103592 | 18828 | DSF0001031842
11 | X415 | CHRISTOPHER COLUMBUS CAMPUS YABC | DOE - Skilled Trades | BCC PLAN REVIEW- ELEVATOR MACHINE ROOM UPGRADE | Construction | In-Progress | 7/8/2023 | DOES |  | DOES |  | 0 | SCA0000071477
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/2/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085071
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 8/5/2020 | 12/4/2020 | 5/28/2021 | 64200 | 92974 | 92972 | DSF0000961080
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 6/8/2021 | 11/15/2021 | 11/23/2021 | 321000 | 323149 | 318758 | DSF0000961080
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 6/21/2022 | 6/19/2024 |  | 7222500 | 7663556 | 5384792 | DSF0000961080
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 6/21/2022 | 6/19/2024 |  | 449400 | 329490 | 325259 | DSF0000961080
11 | X425 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 6/9/2022 | 12/5/2022 | 10/25/2022 | 499900 | 357089 | 357010 | DSF0001082653, DSF0001031907, DSF0001031908, DSF0001036323, DSF0001031904
11 | X425 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | Design | Complete | 11/8/2022 | 6/12/2023 | 5/8/2023 | 2499499 | 684127 | 684127 | DSF0001082653, DSF0001031907, DSF0001031908, DSF0001036323, DSF0001031904
11 | X425 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 7/17/2023 | 1/1/2026 |  | 56238751 | 50862669 | 21705175 | DSF0001082653, DSF0001031907, DSF0001031908, DSF0001036323, DSF0001031904
11 | X425 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 7/17/2023 | 1/1/2026 |  | 3499300 | 667208 | 645241 | DSF0001082653, DSF0001031907, DSF0001031908, DSF0001036323, DSF0001031904
11 | X425 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | FY22 RESO A LOCKER ROOM UPGRADE / REINFORCING SUPPORT ELEMENTS / SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Scope | Complete | 5/27/2022 | 1/25/2024 | 12/5/2023 | 283042 | 275253 | 257302 | DSF0001034089, DSF0001082649, DSF0001083953, DSF0001086892, DSF0001110614
11 | X425 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | FY22 RESO A LOCKER ROOM UPGRADE / REINFORCING SUPPORT ELEMENTS / SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Design | Complete | 12/20/2023 | 5/1/2024 | 5/13/2024 | 1406413 | 983758 | 576452 | DSF0001034089, DSF0001082649, DSF0001083953, DSF0001086892, DSF0001110614
11 | X425 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | FY22 RESO A LOCKER ROOM UPGRADE / REINFORCING SUPPORT ELEMENTS / SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Construction | In-Progress | 11/4/2024 | 3/3/2027 |  | 30882812 | 27546805 | 60809 | DSF0001034089, DSF0001082649, DSF0001083953, DSF0001086892, DSF0001110614
11 | X425 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | FY22 RESO A LOCKER ROOM UPGRADE / REINFORCING SUPPORT ELEMENTS / SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | CM,F&E | In-Progress | 11/4/2024 | 3/3/2027 |  | 2047325 | 92399 | 92399 | DSF0001034089, DSF0001082649, DSF0001083953, DSF0001086892, DSF0001110614
11 | X425 | X176 SPED - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | Complete | 11/1/2021 | EMER | 9/29/2023 | EMER | 12028 | 12028 | SCA0000070637
11 | X425 | HS FOR WRITING & COMM ARTS - X | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | Complete | 12/17/2021 | EMER | 9/29/2023 | EMER | 1621507 | 1621507 | SCA0000070734
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN BASEMENT OIL TANK ROOM AND BASEMENT BOILER ROOM | Construction | In-Progress | 7/17/2023 | IEH |  | IEH | 0 | 0 | SCA0000072144
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN 1ST FLOOR PLENUM ABOVE GYM #2 ABATE AND REPAIR SOFFIT PLAST | Construction | In-Progress | 2/29/2024 | IEH |  | IEH | 0 | 0 | SCA0000072780
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA IEH | PO18-ABATE 400 LF OF PIPE LOCATED LOCATED IN BASEMENT CAFETERIA & KITCHEN 760 GUN HILL ROAD - IMMACU | Construction | Complete | 9/18/2024 | IEH | 10/1/2024 | IEH | 0 | 0 | SCA0000073390
11 | X425 | BRONX LAB SCHOOL - BRONX | Fast Track Projects | INTERIOR SPACES | Construction | In-Progress | 9/18/2018 | FTK |  | FTK | 157414 | 137414 | DSF0000889329
11 | X425 | HS FOR CONTEMPORARY ARTS - X | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 9/24/2024 | DIIR | 100000 | 8715 | DSF0000914224
11 | X425 | BRONX AEROSPACE HS - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 326000 | 0 | DSF0001036292
11 | X425 | BRONX ACAD OF HEALTH CAREERS - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 9/11/2024 | DIIR | 10/30/2024 | DIIR | 200000 | 200000 | DSF0001086832
11 | X425 | HS FOR CONTEMPORARY ARTS - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001086833
11 | X425 | COMM HS FOR SOCIAL JUSTICE - X | DOE - RESOA | FY10 RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0000690150
11 | X425 | BRONX LAB SCHOOL - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 109334 | 0 | DSF0001036287
11 | X425 | HS OF COMPUTERS & TECHNOLOGY - X | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 520694 | 0 | DSF0001036288
11 | X425 | HS FOR WRITING & COMM ARTS - X | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086834
11 | X425 | BRONX LAB SCHOOL - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 1/6/2023 | DOES | 2/22/2024 | DOES | 784344 | 763419 | DSF0000960872
11 | X425 | BRONX LAB SCHOOL - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/18/2024 | DOES | 8/28/2024 | DOES | 65832 | 21993 | DSF0001085074
11 | X425 | BRONX LAB SCHOOL - BRONX | DOE - Skilled Trades | GYMNASIUM UPGRADE | Construction | In-Progress | 1/5/2024 | DOES |  | DOES | 282000 | 0 | DSF0001112102
11 | X426 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | Scope | Complete | 6/29/2018 | 12/28/2018 | 12/11/2018 | 174630 | 501805 | 501805 | DSF0000886685, DSF0000960480
11 | X426 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | Design | Complete | 9/17/2019 | 10/2/2020 | 10/5/2020 | 873151 | 1841208 | 1660687 | DSF0000886685, DSF0000960480
11 | X426 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | Construction | In-Progress | 8/15/2022 | 9/2/2024 |  | 19645875 | 18575839 | 9667229 | DSF0000886685, DSF0000960480
11 | X426 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | CM,F&E | In-Progress | 8/15/2022 | 9/2/2024 |  | 1223173 | 858786 | 844965 | DSF0000886685, DSF0000960480
11 | X426 | HS OF COMPUTERS & TECHNOLOGY - X | DOE - RESOA | FY16 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0000822768
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | Scope | Complete | 3/18/2021 | 8/2/2021 | 1/14/2022 | 195096 | 181665 | 181665 | DSF0001004602, DSF0001032046, DSF0001034488
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | Design | Complete | 1/18/2022 | 6/17/2022 | 5/11/2022 | 966382 | 596027 | 596027 | DSF0001004602, DSF0001032046, DSF0001034488
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | Construction | In-Progress | 7/18/2022 | 8/5/2024 |  | 20956834 | 21812759 | 11546391 | DSF0001004602, DSF0001032046, DSF0001034488
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | CM,F&E | In-Progress | 7/18/2022 | 8/5/2024 |  | 1433884 | 496498 | 495636 | DSF0001004602, DSF0001032046, DSF0001034488
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 3/10/2022 | 7/25/2022 | 8/30/2022 | 117480 | 103650 | 103650 | DSF0001034388
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 9/6/2022 | 2/27/2023 | 5/9/2023 | 587400 | 421689 | 382403 | DSF0001034388
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 7/10/2023 | 10/6/2025 |  | 13216500 | 12097154 | 2732109 | DSF0001034388
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 7/10/2023 | 10/6/2025 |  | 822360 | 273771 | 271974 | DSF0001034388
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113705
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113705
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113705
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113705
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 1/27/2023 | 5/30/2023 | 7/13/2023 | 0 | 12222 | 12222 | DSF0001036295
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | In-Progress | 8/3/2023 | 12/20/2023 |  | 4730 | 30750 | 21465 | DSF0001036295
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 69377 | 636568 | 19650 | DSF0001036295
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 4730 | 43402 | 20236 | DSF0001036295
11 | X455 | HARRY S. TRUMAN HS - X | SCA IEH | PO18-TEST FLOOR/ WALL IN ROOM 110 REMOVE KILN FROM FLOOR | Construction | In-Progress | 8/16/2024 | IEH |  | IEH | 0 | 0 | SCA0000073293
11 | X455 | X176 SPED - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/14/2023 | DIIR | 5/30/2023 | DIIR | 100000 | 100000 | DSF0001033379
11 | X455 | X176 SPED - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 327946 | 0 | DSF0001086843
11 | X455 | BRONX HEALTH SCIENCES HS - X | DOE - RESOA | RESO A INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | DOER | 543937 | 0 | DSF0001112084
11 | X455 | BRONX HEALTH SCIENCES HS - X | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 151386 | 0 | DSF0001112082
11 | X455 | BRONX HEALTH SCIENCES HS - X | DOE - RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113421
11 | X455 | X176 SPED - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 626000 | 0 | DSF0001113422
11 | X455 | HARRY S. TRUMAN HS - X | DOE - Skilled Trades | COOLING TOWER REPLACEMENT | Construction | In-Progress | 3/2/2017 | DOES |  | DOES | 954161 | 0 | DSF0000842273
11 | X455 | HARRY S. TRUMAN HS - X | DOE - Skilled Trades | GAS LINE REPAIR | Construction | In-Progress | 3/9/2018 | DOES |  | DOES | 32806 | 0 | DSF0000888827
11 | X455 | HARRY S. TRUMAN HS - X | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/18/2024 | DOES | 10/28/2024 | DOES | 65832 |  | DSF0001085080
11 | X455 | HARRY S. TRUMAN HS - X | DOE - Skilled Trades | SWIMMING POOL | Construction | In-Progress | 9/25/2023 | DOES |  | DOES | 1847326 | 0 | DSF0001087149
11 | X456 | HARRY S. TRUMAN HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD / FY22 RESO A ATHLETIC FIELD UPGRADE | Scope | Complete | 5/12/2022 | 8/12/2022 | 7/29/2022 | 0 | 130132 | 111066 | DSF0001034128, DSF0001034129
11 | X456 | HARRY S. TRUMAN HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD / FY22 RESO A ATHLETIC FIELD UPGRADE | Design | Complete | 8/21/2023 | 2/20/2024 | 5/8/2024 | 732001 | 448565 | 316665 | DSF0001034128, DSF0001034129
11 | X456 | HARRY S. TRUMAN HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD / FY22 RESO A ATHLETIC FIELD UPGRADE | Construction | In-Progress | 12/16/2024 | 1/4/2027 |  | 10736008 | 8767165 | 26214 | DSF0001034128, DSF0001034129
11 | X456 | HARRY S. TRUMAN HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD / FY22 RESO A ATHLETIC FIELD UPGRADE | CM,F&E | In-Progress | 12/16/2024 | 1/4/2027 |  | 732001 | 47521 | 46225 | DSF0001034128, DSF0001034129
11 | X498 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 5/3/2021 | 9/16/2021 | 7/20/2021 | 28224 | 36508 | 36508 | DSF0001032148, DSF0001009275
11 | X498 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | Complete | 8/4/2021 | 1/7/2022 | 12/20/2021 | 137389 | 165125 | 165125 | DSF0001032148, DSF0001009275
11 | X498 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | Construction | Complete | 6/1/2022 | 11/22/2023 | 1/21/2024 | 2768198 | 2507695 | 2465848 | DSF0001032148, DSF0001009275
11 | X498 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | CM,F&E | Complete | 6/1/2022 | 11/22/2023 | 1/21/2024 | 225584 | 286454 | 280150 | DSF0001032148, DSF0001009275
11 | X498 | P.S. / I.S. 498 - BRONX | Fast Track Projects | FY17 RESO A ROOFTOP PLAYGROUND | Construction | PNS | FTK | FTK | FTK | FTK | 22293 | 11048 | DSF0000845557
11 | X498 | P.S. / I.S. 498 - BRONX | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/19/2019 | FTK |  | FTK | 80494 | 73288 | DSF0000867683
11 | X498 | P.S. / I.S. 498 - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000914227
11 | X498 | P.S. / I.S. 498 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 100000 | 0 | DSF0001034138
11 | X498 | P.S. / I.S. 498 - BRONX | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0000913172
11 | X498 | P.S. / I.S. 498 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001008492
11 | X501 | X000 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 10/28/2024 | IEH | 11/12/2024 | IEH | 0 | 0 | SCA0000073550
11 | X501 | X000 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/26/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085575
11 | X511 | SUCCESS ACADEMY WILLIAMSBRIDGE ELEMENTARY | SCA IEH | PO18-ABATE 400LF OF PIPE LOCATED IN BASEMENT CAFETERIA AND KITCHEN | Construction | In-Progress | 9/25/2024 | IEH |  | IEH | 0 | 0 | SCA0000073430
11 | X511 | P.S. @ 760 EAST GUN HILL ROAD - BRONX | DOE Managed PRE-K | LEASE RENOVATION | Construction | In-Progress | 3/8/2024 | DOEP |  | DOEP | 664037 | 0 | DSF0001087145
11 | X701 | X723 SPED - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001113426
11 | X722 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 11/13/2012 | 4/2/2013 | 3/25/2013 | 162009 | 150965 | 150965 | DSF0000775579, DSF0000775995, DSF0000775993, DSF0000775994, DSF0000776000
11 | X722 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | Design | Complete | 5/6/2013 | 10/4/2013 | 2/28/2014 | 633969 | 700055 | 630263 | DSF0000775579, DSF0000775995, DSF0000775993, DSF0000775994, DSF0000776000
11 | X722 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 2/12/2018 | 11/3/2019 |  | 10624754 | 11526380 | 9664829 | DSF0000775579, DSF0000775995, DSF0000775993, DSF0000775994, DSF0000776000
11 | X722 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 2/12/2018 | 11/3/2019 |  | 938858 | 1613382 | 1583094 | DSF0000775579, DSF0000775995, DSF0000775993, DSF0000775994, DSF0000776000
11 | X722 | X721 SPED - BRONX | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 1/18/2023 | 6/2/2023 | 10/3/2024 | 31204 | 41711 | 41648 | DSF0001082987
11 | X722 | X721 SPED - BRONX | SCA CIP | ROOF REPLACEMENT | Design | In-Progress | 10/8/2024 | 3/14/2025 |  | 156018 | 156018 | 202 | DSF0001082987
11 | X722 | X721 SPED - BRONX | SCA CIP | ROOF REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 3510403 | 3510403 | 7868 | DSF0001082987
11 | X722 | X721 SPED - BRONX | SCA CIP | ROOF REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 218425 | 218425 | 14698 | DSF0001082987
11 | X722 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/3/2022 | 10/3/2022 | 6/16/2022 | 4490 | 4260 | 4260 | DSF0001034563
11 | X722 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/16/2022 | 12/13/2022 | 12/7/2022 | 20205 | 17038 | 17038 | DSF0001034563
11 | X722 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 6/16/2023 | 4/10/2024 |  | 260420 | 234990 | 210470 | DSF0001034563
11 | X722 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 6/16/2023 | 4/10/2024 |  | 164056 | 170441 | 121191 | DSF0001034563
11 | X722 | X721 SPED - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001034148
11 | X722 | X721 SPED - BRONX | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 67000 | 0 | DSF0001034534
11 | X722 | X721 SPED - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 129955 | 0 | DSF0001086853
11 | X722 | X721 SPED - BRONX | DOE - Skilled Trades | CHILLER REPLACEMENT | Construction | In-Progress | 12/1/2021 | DOES |  | DOES | 1237315 | 0 | DSF0000891021
11 | X722 | X721 SPED - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/10/2024 | DOES | 10/23/2024 | DOES | 50832 |  | DSF0001085088
11 | X778 | BRONX HS FOR THE VISUAL ARTS - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113427
11 | X784 | ICAHN CHARTER SCHOOL 5 - BRONX | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001113431
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 5/21/2024 | 10/7/2024 | 12/6/2024 | 105887 | 59390 | 15390 | DSF0001032389, DSF0001032390, DSF0001111137
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | PNS | PNS | PNS | PNS | 490518 | 490518 | 8684 | DSF0001032389, DSF0001032390, DSF0001111137
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | PNS | PNS | PNS | PNS | 7487735 | 7487735 | 0 | DSF0001032389, DSF0001032390, DSF0001111137
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 850816 | 850816 | 19727 | DSF0001032389, DSF0001032390, DSF0001111137
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | In-Progress | 12/18/2024 | 5/16/2025 |  | 75000 | 75000 | 195 | DSF0001113876
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | PNS | PNS | PNS | PNS | 350000 | 350000 | 778 | DSF0001113876
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Construction | PNS | PNS | PNS | PNS | 5550000 | 5550000 | 0 | DSF0001113876
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 550000 | 550000 | 0 | DSF0001113876
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 105597 | DSF0001086857
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113437
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/17/2024 | DOES | 9/24/2024 | DOES | 50832 |  | DSF0001085090
11 | X923 | P.S. 103 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 11/6/2024 | IEH | 11/14/2024 | IEH | 0 | 0 | SCA0000073575
11 | X981 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | Scope | Complete | 6/8/2021 | 10/22/2021 | 1/25/2022 | 94105 | 37807 | 37807 | DSF0001006466, DSF0001032912
11 | X981 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | Design | Complete | 2/2/2022 | 7/5/2022 | 1/27/2023 | 470523 | 403996 | 317080 | DSF0001006466, DSF0001032912
11 | X981 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | Construction | In-Progress | 8/7/2023 | 11/3/2025 |  | 10586761 | 9646745 | 2517941 | DSF0001006466, DSF0001032912
11 | X981 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | CM,F&E | In-Progress | 8/7/2023 | 11/3/2025 |  | 658732 | 81830 | 81830 | DSF0001006466, DSF0001032912
11 | X981 | P.S. 83 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 12/3/2024 | IEH |  | IEH | 0 | 0 | SCA0000073660
11 | XACO | BRONX CHARTER SCHOOL FOR EXCELLENCE 2 | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001086864
11 | XAEE | X000 - BRONX | SCA Furniture & Equipment | FY16 RESO A TECHNOLOGY | F&E | In-Progress | 12/20/2016 |  |  | 35000 | 35000 | 0 | DSF0000843720
11 | XAEF | BRONX CHARTER SCHOOL FOR EXCELLENCE 3 | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001086866
11 | XAJK | BRONX CHARTER FOR EXCELLENCE - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001086808
11 | XAPX | WILLIAMSBRIDGE NAACP EARLY CHILDHOOD EDUCATION CEN - BRONX | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | Scope | Complete | 11/8/2023 | 3/15/2024 | 6/13/2024 | 712 | 18548 | 18548 | DSF0001085336
11 | XAPX | WILLIAMSBRIDGE NAACP EARLY CHILDHOOD EDUCATION CEN - BRONX | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | Design | PNS | PNS | PNS | PNS | 3203 | 3203 | 0 | DSF0001085336
11 | XAPX | WILLIAMSBRIDGE NAACP EARLY CHILDHOOD EDUCATION CEN - BRONX | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | Construction | PNS | PNS | PNS | PNS | 41281 | 41281 | 7641 | DSF0001085336
11 | XAPX | WILLIAMSBRIDGE NAACP EARLY CHILDHOOD EDUCATION CEN - BRONX | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | CM,F&E | PNS | PNS | PNS | PNS | 7651 | 8230 | 8230 | DSF0001085336
11 | XATE | SUSAN E. WAGNER DAY SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086867
12 | X006 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 7/11/2019 | 11/26/2019 | 1/31/2020 | 112064 | 214472 | 208551 | DSF0000906343, DSF0000906346, DSF0000906347, DSF0000906348, DSF0001008766, DSF0001001146
12 | X006 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2/3/2020 | 7/2/2020 | 3/2/2022 | 551088 | 654669 | 641972 | DSF0000906343, DSF0000906346, DSF0000906347, DSF0000906348, DSF0001008766, DSF0001001146
12 | X006 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 6/21/2022 | 6/19/2024 |  | 11600694 | 10737988 | 10323218 | DSF0000906343, DSF0000906346, DSF0000906347, DSF0000906348, DSF0001008766, DSF0001001146
12 | X006 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 6/21/2022 | 6/19/2024 |  | 853705 | 1165619 | 1164921 | DSF0000906343, DSF0000906346, DSF0000906347, DSF0000906348, DSF0001008766, DSF0001001146
12 | X006 | P.S. 6 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/13/2024 | 3/18/2025 | 11/21/2024 | 3984 | 2975 | 2975 | DSF0001087551
12 | X006 | P.S. 6 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 11/21/2024 | 5/20/2025 |  | 17929 | 17929 | 11899 | DSF0001087551
12 | X006 | P.S. 6 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 231082 | 231082 | 0 | DSF0001087551
12 | X006 | P.S. 6 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 42830 | 42830 | 0 | DSF0001087551
12 | X006 | P.S. 6 - BRONX | SCA IEH | PO18-REPAIR OF ACM/ LEAD DAMAGED PLASTER IN ROOM 308 | Construction | Complete | 9/6/2024 | IEH | 9/8/2024 | IEH | 0 | 0 | SCA0000073355
12 | X006 | P.S. 6 - BRONX | SCA IEH | PO18-REPAIR, ENCAPSULATE AND PAINT ALL DAMAGED ACM PLASTER AREAS IN ROOM# 213 UPPER WALL #3 UPPER WA | Construction | Complete | 9/17/2024 | IEH | 9/21/2024 | IEH | 0 | 0 | SCA0000073388
12 | X006 | P.S. 6 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SICENCE LAB | F&E | Complete | 7/15/2024 |  | 7/26/2024 | 200000 | 200000 | 199814 | DSF0001035272
12 | X006 | P.S. 6 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 172234 | 0 | DSF0000960281
12 | X006 | P.S. 6 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001036168
12 | X006 | P.S. 6 - BRONX | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/5/2022 | DOES |  | DOES | 81867 | 0 | DSF0001008966
12 | X006 | P.S. 6 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/8/2021 | DOES |  | DOES | 192500 | 0 | DSF0001028264
12 | X044 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | Scope | Complete | 9/30/2021 | 2/18/2022 | 1/24/2022 | 15435 | 97452 | 97452 | DSF0001028859
12 | X044 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | Design | Complete | 2/2/2022 | 6/10/2022 | 5/11/2022 | 77175 | 80076 | 80076 | DSF0001028859
12 | X044 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | Construction | In-Progress | 8/10/2022 | 11/2/2023 |  | 1736438 | 1603267 | 1300459 | DSF0001028859
12 | X044 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | CM,F&E | In-Progress | 8/10/2022 | 11/2/2023 |  | 108045 | 145086 | 144871 | DSF0001028859
12 | X047 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 4/17/2019 | 8/30/2019 | 8/30/2019 | 127200 | 158392 | 158392 | DSF0000912345, DSF0000906948
12 | X047 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 10/4/2019 | 3/26/2020 | 6/30/2020 | 636000 | 556622 | 552207 | DSF0000912345, DSF0000906948
12 | X047 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 7/11/2022 | 7/9/2024 |  | 14310000 | 13088540 | 11747028 | DSF0000912345, DSF0000906948
12 | X047 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 7/11/2022 | 7/9/2024 |  | 983987 | 763143 | 714025 | DSF0000912345, DSF0000906948
12 | X047 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 1/23/2023 | 5/23/2023 | 3/30/2023 | 7040 | 11889 | 11826 | DSF0001083784
12 | X047 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 4/10/2023 | 10/11/2023 | 8/2/2023 | 31680 | 38449 | 34424 | DSF0001083784
12 | X047 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2/1/2024 | 1/30/2025 |  | 408320 | 370258 | 7274 | DSF0001083784
12 | X047 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2/1/2024 | 1/30/2025 |  | 75680 | 48079 | 25744 | DSF0001083784
12 | X047 | P.S. 47 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/29/2024 | 3/4/2025 | 11/4/2024 | 4524 | 3296 | 3296 | DSF0001087559
12 | X047 | P.S. 47 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 11/4/2024 | 5/2/2025 |  | 20359 | 20359 | 13182 | DSF0001087559
12 | X047 | P.S. 47 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 262400 | 262400 | 0 | DSF0001087559
12 | X047 | P.S. 47 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 48635 | 48635 | 0 | DSF0001087559
12 | X047 | P.S. 47 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/19/2024 | DOES | 9/9/2024 | DOES | 65832 | 20066 | DSF0001084492
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Scope | Complete | 6/14/2022 | 10/28/2022 | 1/9/2023 | 58592 | 143710 | 141548 | DSF0001028968, DSF0001028967, DSF0001079717
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Design | Complete | 1/18/2023 | 6/20/2023 | 5/12/2023 | 289823 | 220610 | 210313 | DSF0001028968, DSF0001028967, DSF0001079717
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 6249562 | 6249562 | 213493 | DSF0001028968, DSF0001028967, DSF0001079717
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 433686 | 433686 | 71123 | DSF0001028968, DSF0001028967, DSF0001079717
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/12/2020 | 12/14/2020 | 8/21/2020 | 4730 | 2851 | 2851 | DSF0000960742
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/21/2020 | 2/17/2021 | 3/31/2021 | 21284 | 11405 | 11405 | DSF0000960742
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/16/2022 | 3/11/2023 |  | 274326 | 248993 | 195789 | DSF0000960742
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/16/2022 | 3/11/2023 |  | 176996 | 172280 | 172120 | DSF0000960742
12 | X050 | P.S. 50 - BRONX | SCA CIP RESOA | FY11 RESO A PLAYGROUND REDEVELOPMEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000710897
12 | X050 | P.S. 50 - BRONX | SCA CIP RESOA | FY11 RESO A PLAYGROUND REDEVELOPMEN | Design | PNS | PNS | PNS | PNS | 6986 | 6986 | 0 | DSF0000710897
12 | X050 | P.S. 50 - BRONX | SCA CIP RESOA | FY11 RESO A PLAYGROUND REDEVELOPMEN | Construction | PNS | PNS | PNS | PNS | 102456 | 102456 | 0 | DSF0000710897
12 | X050 | P.S. 50 - BRONX | SCA CIP RESOA | FY11 RESO A PLAYGROUND REDEVELOPMEN | CM,F&E | PNS | PNS | PNS | PNS | 6986 | 6986 | 0 | DSF0000710897
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/16/2024 | DIIR | 9/19/2024 | DIIR | 200000 | 125752 | DSF0001086709
12 | X050 | X186 SPED - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 240813 | 0 | DSF0001086710
12 | X057 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/8/2023 | 12/8/2023 | 8/22/2023 | 4300 | 1951 | 1951 | DSF0001035042
12 | X057 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/22/2023 | 2/21/2024 | 11/29/2023 | 19350 | 7802 | 7802 | DSF0001035042
12 | X057 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 4/12/2024 | 2/5/2025 |  | 249400 | 230930 | 98557 | DSF0001035042
12 | X057 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 4/12/2024 | 2/5/2025 |  | 124663 | 110182 | 53898 | DSF0001035042
12 | X057 | I.S. 273 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 65000 | 65000 | 0 | DSF0001035296
12 | X057 | P.S. 57 - BRONX | Fast Track Projects | LSP FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 1/12/2022 | FTK |  | FTK | 137188 | 65819 | DSF0000913491
12 | X057 | I.S. 273 - BRONX | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50400 | 0 | DSF0000822696
12 | X057 | P.S. 57 - BRONX | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113819
12 | X057 | P.S. 57 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/18/2021 | DOES |  | DOES | 3457 | 0 | DSF0001008721
12 | X057 | P.S. 57 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/29/2024 | DOES | 11/5/2024 | DOES | 65832 |  | DSF0001084846
12 | X057 | I.S. 273 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/13/2024 | DOES |  | DOES | 387561 | 0 | DSF0001085606
12 | X057 | P.S. 57 - BRONX | Trust For Public Land | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | TPL | 1370000 | 0 | DSF0001086716
12 | X061 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 1/7/2021 | 5/7/2021 | 12/22/2021 | 41250 | 95843 | 95843 | DSF0001002004
12 | X061 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 12/23/2021 | 5/26/2022 | 8/24/2022 | 206250 | 314354 | 279152 | DSF0001002004
12 | X061 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | Construction | In-Progress | 6/21/2023 | 6/19/2025 |  | 4640625 | 4870869 | 2238246 | DSF0001002004
12 | X061 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 6/21/2023 | 6/19/2025 |  | 288750 | 282911 | 276745 | DSF0001002004
12 | X061 | P.S. 61 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/17/2024 | DOEL |  | DOEL | 138594 | 0
12 | X061 | P.S. 61 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 8/11/2022 | DOES |  | DOES | 165073 | 0 | DSF0001008722
12 | X061 | P.S. 61 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/4/2024 | DOES | 9/13/2024 | DOES | 65832 | 5932 | DSF0001084847
12 | X066 | P.S. 66 - BRONX | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 3/24/2022 | 12/8/2022 | 11/1/2022 | 0 | 16050 | 16050 | DSF0001034039, DSF0001034040
12 | X066 | P.S. 66 - BRONX | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 11/7/2022 | 3/7/2023 | 12/28/2022 | 100688 | 87166 | 78166 | DSF0001034039, DSF0001034040
12 | X066 | P.S. 66 - BRONX | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 6/15/2023 | 3/15/2024 |  | 1476743 | 1325498 | 1263389 | DSF0001034039, DSF0001034040
12 | X066 | P.S. 66 - BRONX | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 6/15/2023 | 3/15/2024 |  | 178866 | 238762 | 176256 | DSF0001034039, DSF0001034040
12 | X066 | P.S. 66 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 176406 | 0 | DSF0000960312
12 | X066 | P.S. 66 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 130000 | 0 | DSF0001113326
12 | X066 | P.S. 66 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/3/2024 | DOES |  | DOES | 157171 | 0 | DSF0001008719
12 | X066 | P.S. 66 - BRONX | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 3/20/2023 | DOES |  | DOES | 55318 | 0 | DSF0001080004
12 | X066 | P.S. 66 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/8/2024 | DOES | 7/18/2024 | DOES | 65832 | 16121 | DSF0001084507
12 | X067 | P.S. 67 - BRONX | SCA CIP | KITCHEN ANSUL SYSTEM | Scope | Complete | 2/3/2020 | 6/11/2020 | 10/8/2021 | 12477 | 25102 | 25102 | DSF0000960577
12 | X067 | P.S. 67 - BRONX | SCA CIP | KITCHEN ANSUL SYSTEM | Design | Complete | 10/26/2021 | 5/13/2022 | 10/25/2022 | 56144 | 67445 | 24803 | DSF0000960577
12 | X067 | P.S. 67 - BRONX | SCA CIP | KITCHEN ANSUL SYSTEM | Construction | PNS | PNS | PNS | PNS | 723639 | 723639 | 24510 | DSF0000960577
12 | X067 | P.S. 67 - BRONX | SCA CIP | KITCHEN ANSUL SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 134123 | 134123 | 25233 | DSF0000960577
12 | X067 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | Scope | Complete | 10/10/2018 | 5/13/2019 | 3/28/2019 | 319702 | 240815 | 240815 | DSF0000884454, DSF0000884456, DSF0000884457, DSF0000884458, DSF0000884459, DSF0000911807, DSF0000912446, DSF0000912512
12 | X067 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | Design | Complete | 3/28/2019 | 8/12/2019 | 5/17/2019 | 1275345 | 737988 | 594968 | DSF0000884454, DSF0000884456, DSF0000884457, DSF0000884458, DSF0000884459, DSF0000911807, DSF0000912446, DSF0000912512
12 | X067 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | Construction | In-Progress | 8/5/2019 | 8/3/2021 |  | 23602220 | 22599759 | 14400740 | DSF0000884454, DSF0000884456, DSF0000884457, DSF0000884458, DSF0000884459, DSF0000911807, DSF0000912446, DSF0000912512
12 | X067 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | CM,F&E | In-Progress | 8/5/2019 | 8/3/2021 |  | 1536914 | 1679531 | 1673034 | DSF0000884454, DSF0000884456, DSF0000884457, DSF0000884458, DSF0000884459, DSF0000911807, DSF0000912446, DSF0000912512
12 | X067 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | Scope | Complete | 2/15/2019 | 3/27/2020 | 3/25/2021 | 13687 | 33764 | 33764 | DSF0000884466, DSF0000960568
12 | X067 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | Design | Complete | 4/5/2021 | 8/24/2021 | 1/7/2022 | 61592 | 117324 | 113028 | DSF0000884466, DSF0000960568
12 | X067 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | Construction | In-Progress | 7/20/2022 | 4/14/2023 |  | 793858 | 864658 | 564838 | DSF0000884466, DSF0000960568
12 | X067 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | CM,F&E | In-Progress | 7/20/2022 | 4/14/2023 |  | 147137 | 147895 | 107912 | DSF0000884466, DSF0000960568
12 | X067 | P.S. 67 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/6/2018 | EMER |  | EMER | 41270 | 41270 | SCA0000055286
12 | X067 | P.S. 67 - BRONX | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 627221 | 0 | DSF0001036205
12 | X077 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | Scope | Complete | 4/25/2019 | 2/5/2020 | 2/5/2020 | 1385261 | 1375373 | 1342035 | DSF0000798238, DSF0000798238, DSF0000798238
12 | X077 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | Design | Complete | 2/5/2020 | 5/15/2020 | 8/17/2020 | 6233670 | 4295000 | 3883733 | DSF0000798238, DSF0000798238, DSF0000798238
12 | X077 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | Construction | Complete | 8/2/2021 | 9/3/2024 | 7/1/2024 | 78613505 | 72818624 | 67646377 | DSF0000798238, DSF0000798238, DSF0000798238
12 | X077 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | CM,Art,F&E | Complete | 8/2/2021 | 9/3/2024 | 7/1/2024 | 11082080 | 9761846 | 8723008 | DSF0000798238, DSF0000798238, DSF0000798238
12 | X077 | P.S. 195 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/13/2023 | 4/14/2023 | 5/31/2023 | 21800 | 64549 | 64549 | DSF0001083715
12 | X077 | P.S. 195 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 6/6/2023 | 10/23/2023 | 5/1/2024 | 109001 | 124150 | 121013 | DSF0001083715
12 | X077 | P.S. 195 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2452529 | 2452529 | 189787 | DSF0001083715
12 | X077 | P.S. 195 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 152602 | 152602 | 18352 | DSF0001083715
12 | X077 | P.S. 195 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/4/2023 | 1/9/2024 | 12/21/2023 | 708 | 708 | 7283 | DSF0001087148
12 | X077 | P.S. 195 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 12/28/2023 | 5/30/2024 | 5/1/2024 | 3187 | 3187 | 6066 | DSF0001087148
12 | X077 | P.S. 195 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 41077 | 41077 | 2754 | DSF0001087148
12 | X077 | P.S. 195 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 7613 | 7613 | 4874 | DSF0001087148
12 | X077 | P.S. 195 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/3/2024 | DIIR | 10/21/2024 | DIIR | 100000 | 100000 | DSF0001035291
12 | X077 | P.S. 196 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113329
12 | X077 | P.S. 195 - BRONX | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113328
12 | X084 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/9/2023 | 7/10/2023 | 3/16/2023 | 7180 | 2377 | 2377 | DSF0001034667
12 | X084 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/16/2023 | 9/11/2023 | 5/2/2023 | 32310 | 9505 | 9505 | DSF0001034667
12 | X084 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/1/2023 | 8/26/2024 |  | 416440 | 371443 | 2353 | DSF0001034667
12 | X084 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/1/2023 | 8/26/2024 |  | 142832 | 108888 | 23869 | DSF0001034667
12 | X084 | X811 SPED - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/15/2023 | DOER |  | DOER | 367063 | 0 | DSF0001036218
12 | X084 | X811 SPED - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/8/2022 | DOES |  | DOES | 218551 | 0 | DSF0001034268
12 | X092 | X352 SPED - BRONX | SCA CIP | EXTERIOR MASONRY @ X092- PERMANENT FIX | Scope | Complete | 5/24/2024 | 10/10/2024 | 10/9/2024 | 51865 | 93929 | 14771 | SCA0000072845
12 | X092 | X352 SPED - BRONX | SCA CIP | EXTERIOR MASONRY @ X092- PERMANENT FIX | Design | In-Progress | 10/15/2024 | 3/20/2025 |  | 259324 | 259324 | 13688 | SCA0000072845
12 | X092 | X352 SPED - BRONX | SCA CIP | EXTERIOR MASONRY @ X092- PERMANENT FIX | Construction | PNS | PNS | PNS | PNS | 5834800 | 5834800 | 0 | SCA0000072845
12 | X092 | X352 SPED - BRONX | SCA CIP | EXTERIOR MASONRY @ X092- PERMANENT FIX | CM,F&E | PNS | PNS | PNS | PNS | 363054 | 363054 | 14905 | SCA0000072845
12 | X092 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/9/2023 | 7/24/2023 | 3/14/2023 | 4880 | 1804 | 1804 | DSF0001034609
12 | X092 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/14/2023 | 9/7/2023 | 5/2/2023 | 21960 | 7214 | 7214 | DSF0001034609
12 | X092 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/1/2023 | 8/26/2024 |  | 283040 | 253813 | 873 | DSF0001034609
12 | X092 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/1/2023 | 8/26/2024 |  | 98951 | 75892 | 18270 | DSF0001034609
12 | X092 | P.S. 595 - BRONX | SCA Emergency Response | EMERGENCY- SWB @ X092 | Construction | In-Progress | 3/18/2024 | EMER |  | EMER | 70952 | 34929 | SCA0000072820
12 | X092 | X352 SPED - BRONX | SCA IEH | PO18-REMOVE 10' OF ACM MARKED RED FOR ID IN CRAWLSPACE UNDER EXIT-10. CRAWL SPACE UNDER AUDITORIUM I | Construction | Complete | 9/18/2024 | IEH | 11/9/2024 | IEH | 0 | 0 | SCA0000073393
12 | X092 | P.S. 595 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033366
12 | X092 | P.S. 595 - BRONX | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113338
12 | X098 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Scope | Complete | 2/13/2019 | 6/28/2019 | 2/19/2020 | 89700 | 257033 | 256987 | DSF0001029880, DSF0001002690, DSF0001002692, DSF0001008863
12 | X098 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Design | Complete | 4/12/2021 | 9/10/2021 | 2/3/2022 | 442641 | 529080 | 529039 | DSF0001029880, DSF0001002690, DSF0001002692, DSF0001008863
12 | X098 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Construction | In-Progress | 10/3/2022 | 10/1/2024 |  | 9452510 | 8692236 | 674701 | DSF0001029880, DSF0001002690, DSF0001002692, DSF0001008863
12 | X098 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | CM,F&E | In-Progress | 10/3/2022 | 10/1/2024 |  | 679175 | 368654 | 309649 | DSF0001029880, DSF0001002690, DSF0001002692, DSF0001008863
12 | X098 | EXPLORATIONS ACADEMY - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 250000 | 250000 | 0 | DSF0001035356
12 | X098 | I.S. 98 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 133140 | 0 | DSF0000960321
12 | X098 | EXPLORATIONS ACADEMY - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001033394
12 | X098 | I.S. 98 - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 2/17/2023 | DOES | 2/22/2024 | DOES | 452606 | 410559 | DSF0000960868
12 | X098 | I.S. 98 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/13/2024 | DOES | 9/20/2024 | DOES | 65832 | 26220 | DSF0001085052
12 | X099 | METROPOLITAN HS - BRONX | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/20/2024 | 11/5/2024 | 10/29/2024 | 146454 | 175861 | 116334 | DSF0001080651, DSF0001080652, DSF0001113835
12 | X099 | METROPOLITAN HS - BRONX | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Design | In-Progress | 11/29/2024 | 5/2/2025 |  | 719788 | 719788 | 343717 | DSF0001080651, DSF0001080652, DSF0001113835
12 | X099 | METROPOLITAN HS - BRONX | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 15789660 | 15789660 | 20578 | DSF0001080651, DSF0001080652, DSF0001113835
12 | X099 | METROPOLITAN HS - BRONX | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1121886 | 1121886 | 21259 | DSF0001080651, DSF0001080652, DSF0001113835
12 | X099 | METROPOLITAN HS - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113347
12 | X099 | METROPOLITAN HS - BRONX | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0 | DSF0001113346
12 | X099 | METROPOLITAN HS - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 5/31/2023 | DOES |  | DOES | 175885 | 0 | DSF0000911902
12 | X102 | P.S. 536 - BRONX | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/14/2024 | FTK |  | FTK | 69195 | 0 | DSF0000867260
12 | X102 | P.S. 536 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/28/2023 | DIIR | 5/22/2024 | DIIR | 100000 | 100000 | DSF0001033437
12 | X102 | P.S. 536 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113351
12 | X102 | ARCHER ELEMENTARY SCHOOL - BRONX | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113350
12 | X102 | ARCHER ELEMENTARY SCHOOL - BRONX | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 544254 | 0 | DSF0000912208
12 | X102 | ARCHER ELEMENTARY SCHOOL - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/30/2022 | DOES |  | DOES | 310500 | 0 | DSF0001034269
12 | X116 | I.S. 217 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/14/2024 | 10/31/2024 | 10/2/2024 | 213527 | 108796 | 97301 | DSF0001080970, DSF0001136597, DSF0001136598
12 | X116 | I.S. 217 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 10/29/2024 | 4/3/2025 |  | 1032126 | 1032126 | 269446 | DSF0001080970, DSF0001136597, DSF0001136598
12 | X116 | I.S. 217 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 20519039 | 20519039 | 22729 | DSF0001080970, DSF0001136597, DSF0001136598
12 | X116 | I.S. 217 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1596979 | 1596979 | 15792 | DSF0001080970, DSF0001136597, DSF0001136598
12 | X116 | I.S. 341 - BRONX | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 0 | DSF0001007943
12 | X116 | I.S. 217 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/1/2023 | DIIR |  | DIIR | 150000 | 0 | DSF0001034084
12 | X116 | I.S. 217 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0001036233
12 | X116 | I.S. 217 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/30/2022 | DOES |  | DOES | 209387 | 0 | DSF0001034270
12 | X116 | I.S. 217 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/14/2023 | DOES | 12/1/2023 | DOES | 576486 | 566531 | DSF0001035137
12 | X116 | I.S. 217 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/3/2024 | DOES | 11/7/2024 | DOES | 65832 |  | DSF0001084854
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 9/24/2020 | 3/2/2021 | 1/12/2021 | 92200 | 94858 | 94858 | DSF0000954110, DSF0000961023
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 1/14/2021 | 8/2/2021 | 12/7/2021 | 461000 | 368512 | 344091 | DSF0000954110, DSF0000961023
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 8/4/2022 | 8/2/2024 |  | 10372501 | 9311528 | 6265703 | DSF0000954110, DSF0000961023
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 8/4/2022 | 8/2/2024 |  | 645695 | 284198 | 283714 | DSF0000954110, DSF0000961023
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/28/2024 | 9/27/2024 | 11/25/2024 | 30165 | 38840 | 23720 | DSF0001109160
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | In-Progress | 12/5/2024 | 4/23/2025 |  | 140769 | 140769 | 9772 | DSF0001109160
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2232200 | 2232200 | 13708 | DSF0001109160
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 221209 | 221209 | 7583 | DSF0001109160
12 | X129 | I.S. 129 - BRONX | SCA CIP | PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 12/2/2024 | 3/5/2025 |  | 647 | 647 | 0 | DSF0001113748
12 | X129 | I.S. 129 - BRONX | SCA CIP | PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Design | PNS | PNS | PNS | PNS | 2589 | 2589 | 0 | DSF0001113748
12 | X129 | I.S. 129 - BRONX | SCA CIP | PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 37216 | 37216 | 0 | DSF0001113748
12 | X129 | I.S. 129 - BRONX | SCA CIP | PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 9547 | 9547 | 0 | DSF0001113748
12 | X129 | I.S. 129 - BRONX | SCA IEH | PO18-ABATE ACM PIPE INSULATION 1ST FLOOR GIRLS BATHROOM CRAWLSPACE APPROX: 4 FT. | Construction | Complete | 7/31/2024 | IEH | 8/10/2024 | IEH | 0 | 0 | SCA0000073207
12 | X129 | I.S. 316 - BRONX | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 9/28/2024 | FTK |  | FTK | 145654 | 90071 | DSF0001112196
12 | X129 | I.S. 316 - BRONX | Fast Track Projects | CTF- PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 11/30/2024 | FTK |  | FTK | 40623 | 15166 | DSF0001112197
12 | X129 | I.S. 129 - BRONX | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 12/31/2024 | FTK |  | FTK | 62086 | 0 | DSF0001112290
12 | X129 | I.S. 129 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/10/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084858
12 | X134 | P.S. 134 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/7/2024 | 12/9/2024 | 9/5/2024 | 4928 | 2380 | 2380 | DSF0001087583
12 | X134 | P.S. 134 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 9/5/2024 | 3/6/2025 |  | 22176 | 22176 | 9519 | DSF0001087583
12 | X134 | P.S. 134 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 285827 | 285827 | 3597 | DSF0001087583
12 | X134 | P.S. 134 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 57241 | 57241 | 1904 | DSF0001087583
12 | X134 | P.S. 134 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LIGHTING UPGRADE | Scope | Complete | 7/23/2024 | 1/22/2025 | 9/26/2024 | 322790 | 92489 | 66990 | DSF0001081257, DSF0001112299, DSF0001112318, DSF0001113807
12 | X134 | P.S. 134 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LIGHTING UPGRADE | Design | In-Progress | 11/6/2024 | 5/9/2025 |  | 1506353 | 1506353 | 267963 | DSF0001081257, DSF0001112299, DSF0001112318, DSF0001113807
12 | X134 | P.S. 134 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | 23886463 | 23886463 | 22112 | DSF0001081257, DSF0001112299, DSF0001112318, DSF0001113807
12 | X134 | P.S. 134 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LIGHTING UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 2367127 | 2367127 | 41881 | DSF0001081257, DSF0001112299, DSF0001112318, DSF0001113807
12 | X134 | P.S. 134 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/19/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084549
12 | X136 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | Scope | Complete | 8/30/2016 | 2/3/2017 | 10/13/2016 | 134195 | 142661 | 142661 | DSF0000798387, DSF0000795961, DSF0000865946
12 | X136 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | Design | Complete | 10/26/2016 | 3/31/2017 | 4/26/2017 | 530645 | 524016 | 503370 | DSF0000798387, DSF0000795961, DSF0000865946
12 | X136 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | Construction | In-Progress | 4/16/2018 | 4/14/2020 |  | 9399158 | 9099556 | 8657473 | DSF0000798387, DSF0000795961, DSF0000865946
12 | X136 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | CM,F&E | In-Progress | 4/16/2018 | 4/14/2020 |  | 705971 | 1319872 | 1312027 | DSF0000798387, DSF0000795961, DSF0000865946
12 | X136 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 8/10/2021 | 12/28/2021 | 11/30/2021 | 72720 | 103009 | 103009 | DSF0001009216
12 | X136 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 12/15/2021 | 6/3/2022 | 7/1/2022 | 363600 | 735765 | 405452 | DSF0001009216
12 | X136 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 9/18/2023 | 9/16/2025 |  | 8181000 | 7674961 | 3612134 | DSF0001009216
12 | X136 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 9/18/2023 | 9/16/2025 |  | 647774 | 487895 | 478999 | DSF0001009216
12 | X136 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/20/2022 | 4/21/2023 | 1/25/2023 | 7315 | 4371 | 4371 | DSF0001034663
12 | X136 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/25/2023 | 7/21/2023 | 4/19/2023 | 32918 | 17481 | 17481 | DSF0001034663
12 | X136 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/27/2023 | 8/21/2024 |  | 424270 | 377668 | 14635 | DSF0001034663
12 | X136 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/27/2023 | 8/21/2024 |  | 122179 | 89887 | 23984 | DSF0001034663
12 | X136 | X186 SPED - BRONX | SCA Emergency Response | SIDEWALK BRIDGING | Construction | In-Progress | 1/13/2012 | EMER |  | EMER |  | 0 | SCA0000019974
12 | X136 | X186 SPED - BRONX | SCA IEH | PO18-REPLACE 9X9 TILES ON THE FOLLOWING ROOMS: ROOM 101 - TRIPPING HAZZARD 752 SQ. FT + CLOSET 54 SQ | Construction | Complete | 9/25/2024 | IEH | 11/5/2024 | IEH | 0 | 0 | SCA0000073429
12 | X136 | X186 SPED - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001086765
12 | X136 | X186 SPED - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/13/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084710
12 | X150 | P.S. 150 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/6/2024 | 1/9/2025 | 9/12/2024 | 4788 | 2175 | 2175 | DSF0001087585
12 | X150 | P.S. 150 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 9/12/2024 | 3/13/2025 |  | 21545 | 21545 | 8699 | DSF0001087585
12 | X150 | P.S. 150 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 277696 | 277696 | 0 | DSF0001087585
12 | X150 | P.S. 150 - BRONX | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 51469 | 51469 | 1465 | DSF0001087585
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113382
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113382
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001113382
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113382
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113701
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113701
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113701
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113701
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 4/9/2021 | 8/10/2021 | 12/7/2021 | 0 | 16639 | 16639 | DSF0000913507
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 12/7/2021 | 5/10/2022 | 9/14/2022 | 59731 | 78976 | 67639 | DSF0000913507
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 876051 | 876051 | 58316 | DSF0000913507
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 59731 | 59731 | 22745 | DSF0000913507
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/25/2022 | 7/25/2022 | 7/20/2022 | 0 | 37094 | 35389 | DSF0001034071
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 7/20/2022 | 12/6/2022 | 2/23/2023 | 56743 | 79569 | 79569 | DSF0001034071
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | Complete | 8/21/2023 | 5/16/2024 | 8/23/2024 | 832230 | 788047 | 356115 | DSF0001034071
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 8/21/2023 | 5/16/2024 | 8/23/2024 | 56743 | 77268 | 40606 | DSF0001034071
12 | X150 | P.S. 150 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033375
12 | X150 | P.S. 150 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086778
12 | X150 | P.S. 150 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 86992 | 0 | DSF0000796218
12 | X158 | DR. IZQUIERDO HEALTH CHARTER SCHL - X | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 5/29/2024 |  | 7/31/2024 | 250000 | 250000 | 249770 | DSF0001035308
12 | X158 | BRONX CAREER AND COLLEGE PREPARATORY HIGH SCHOOL | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 250000 | 250000 | 0 | DSF0001113385
12 | X158 | I.S. 267 - BRONX | Fast Track Projects | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 10/11/2024 | FTK |  | FTK | 176853 | 8425 | DSF0001086782
12 | X158 | BRONX CAREER AND COLLEGE PREPARATORY HIGH SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0 | DSF0001007915
12 | X158 | DR. IZQUIERDO HEALTH CHARTER SCHL - X | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 60000 | 0 | DSF0001007921
12 | X158 | I.S. 267 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 115000 | 0 | DSF0001034087
12 | X158 | I.S. 267 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113384
12 | X158 | I.S. 267 - BRONX | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 2/3/2023 | DOER | 4/20/2023 | DOER | 159458 | 934 | DSF0001033397
12 | X158 | I.S. 267 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/12/2023 | DOES | 6/15/2023 | DOES | 403118 | 395495 | DSF0001035138
12 | X158 | I.S. 267 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832 | 12747 | DSF0001085061
12 | X167 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/12/2023 | 10/12/2023 | 9/22/2023 | 12387 | 15695 | 15695 | DSF0001083798
12 | X167 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/4/2023 | 3/5/2024 | 4/4/2024 | 55743 | 56580 | 43333 | DSF0001083798
12 | X167 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/16/2024 | 9/15/2025 |  | 718463 | 652436 | 17286 | DSF0001083798
12 | X167 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/16/2024 | 9/15/2025 |  | 133163 | 85664 | 18503 | DSF0001083798
12 | X167 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/22/2020 | 11/20/2020 | 7/27/2020 | 5317 | 3872 | 3872 | DSF0000960759
12 | X167 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/27/2020 | 1/21/2021 | 3/30/2021 | 23925 | 15488 | 15488 | DSF0000960759
12 | X167 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/16/2022 | 3/11/2023 |  | 308370 | 280609 | 222231 | DSF0000960759
12 | X167 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/16/2022 | 3/11/2023 |  | 199976 | 187766 | 184660 | DSF0000960759
12 | X167 | P.S. 214 - BRONX | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LAB | F&E | Complete | 8/16/2024 |  | 11/12/2024 | 200000 | 200000 | 199931 | DSF0001086784
12 | X167 | P.S. 214 - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 11/21/2022 | DOES | 10/31/2023 | DOES | 498168 | 497218 | DSF0000960870
12 | X193 | P.S. 211 - BRONX | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 7/25/2024 | 12/11/2024 | 10/11/2024 | 203734 | 93828 | 51928 | DSF0001082129, DSF0001113881, DSF0001137758, DSF0001137757
12 | X193 | P.S. 211 - BRONX | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Design | In-Progress | 11/25/2024 | 4/29/2025 |  | 986788 | 986788 | 198387 | DSF0001082129, DSF0001113881, DSF0001137758, DSF0001137757
12 | X193 | P.S. 211 - BRONX | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Construction | PNS | PNS | PNS | PNS | 20003146 | 20003146 | 19597 | DSF0001082129, DSF0001113881, DSF0001137758, DSF0001137757
12 | X193 | P.S. 211 - BRONX | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 1543383 | 1543383 | 16795 | DSF0001082129, DSF0001113881, DSF0001137758, DSF0001137757
12 | X193 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/22/2020 | 11/20/2020 | 7/27/2020 | 5214 | 4128 | 4128 | DSF0000960763
12 | X193 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/27/2020 | 1/21/2021 | 5/5/2021 | 23461 | 16512 | 16512 | DSF0000960763
12 | X193 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/16/2022 | 3/11/2023 |  | 302384 | 283647 | 223488 | DSF0000960763
12 | X193 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/16/2022 | 3/11/2023 |  | 203875 | 195744 | 184377 | DSF0000960763
12 | X193 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | Scope | Complete | 6/16/2022 | 5/5/2023 | 5/5/2023 | 31639 | 53115 | 41009 | DSF0001034503, DSF0001083868
12 | X193 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | Design | Complete | 5/8/2023 | 9/11/2023 | 5/12/2023 | 157666 | 137428 | 97312 | DSF0001034503, DSF0001083868
12 | X193 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | Construction | In-Progress | 4/8/2024 | 10/4/2025 |  | 3501726 | 3236547 | 130900 | DSF0001034503, DSF0001083868
12 | X193 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | CM,F&E | In-Progress | 4/8/2024 | 10/4/2025 |  | 225439 | 106058 | 105679 | DSF0001034503, DSF0001083868
12 | X193 | P.S. 211 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035294
12 | X193 | P.S. 211 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 245402 | 0 | DSF0000960371
12 | X193 | P.S. 211 - BRONX | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 530323 | 0 | DSF0000912211
12 | X193 | P.S. 211 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/26/2023 | DOES | 11/14/2023 | DOES | 509222 | 502372 | DSF0001035139
12 | X193 | P.S. 211 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/21/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084717
12 | X193 | I.S. 318 - BRONX | DOE - Skilled Trades | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 11/13/2023 | DOES |  | DOES | 271565 | 0 | DSF0001111901
12 | X193 | P.S. 211 - BRONX | DOE - Skilled Trades | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 11/13/2023 | DOES |  | DOES | 282423 | 0 | DSF0001110103
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/17/2023 | 5/16/2023 | 2/2/2023 | 4985 | 2546 | 2546 | DSF0001034640
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/2/2023 | 7/31/2023 | 4/19/2023 | 22433 | 10182 | 10182 | DSF0001034640
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/27/2023 | 8/21/2024 |  | 289130 | 260392 | 44475 | DSF0001034640
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/27/2023 | 8/21/2024 |  | 53589 | 32056 | 11869 | DSF0001034640
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/30/2023 | DIIR | 9/3/2024 | DIIR | 99964 | 99964 | DSF0001033429
12 | X198 | X188 SPED - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 2/20/2024 | DIIR |  | DIIR | 125000 | 0 | DSF0001035289
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113396
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | DOE - Skilled Trades | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 11/17/2023 | DOES |  | DOES | 288883 | 0 | DSF0001110144
12 | X234 | P.S. 300 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 8/6/2024 | 11/5/2024 | 12/23/2024 | 23801 | 33052 | 26930 | DSF0001112252
12 | X234 | P.S. 300 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | PNS | PNS | PNS | PNS | 111072 | 111072 | 69807 | DSF0001112252
12 | X234 | P.S. 300 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 1761285 | 1761285 | 0 | DSF0001112252
12 | X234 | P.S. 300 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 174542 | 174542 | 1541 | DSF0001112252
12 | X234 | P.S. 300 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 9/29/2022 | DOES |  | DOES | 155531 | 0 | DSF0001034272
12 | X234 | P.S. 300 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084571
12 | X358 | CROTONA ACADEMY HIGH SCHOOL - BRONX | SCA Furniture & Equipment | FY18 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 95000 | 95000 | 0 | DSF0000866736
12 | X358 | ALC- PS 6 | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/5/2024 | DOES | 11/5/2024 | DOES | 50832 |  | DSF0001085567
12 | X401 | BRONX REGIONAL HS - X | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/3/2024 | DOES | 9/10/2024 | DOES | 65832 | 10531 | DSF0001085068
12 | X401 | BRONX REGIONAL HS - X | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/22/2024 | DOES |  | DOES | 646666 | 0 | DSF0001085607
12 | X420 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | Scope | Complete | 3/5/2014 | 7/18/2014 | 2/12/2015 | 247379 | 200864 | 189936 | DSF0000797012, DSF0000842105, DSF0000842108, DSF0000844686, DSF0000844687
12 | X420 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | Design | Complete | 8/15/2016 | 1/19/2017 | 4/21/2017 | 982671 | 871301 | 731374 | DSF0000797012, DSF0000842105, DSF0000842108, DSF0000844686, DSF0000844687
12 | X420 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | Construction | In-Progress | 8/6/2018 | 8/4/2020 |  | 17810761 | 18113974 | 16568656 | DSF0000797012, DSF0000842105, DSF0000842108, DSF0000844686, DSF0000844687
12 | X420 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | CM,F&E | In-Progress | 8/6/2018 | 8/4/2020 |  | 1243414 | 2405003 | 2366123 | DSF0000797012, DSF0000842105, DSF0000842108, DSF0000844686, DSF0000844687
12 | X420 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Scope | Complete | 4/13/2021 | 9/26/2022 | 7/29/2022 | 101545 | 113778 | 102202 | DSF0000961013, DSF0001035000
12 | X420 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Design | Complete | 8/9/2022 | 12/9/2022 | 10/5/2022 | 507289 | 401533 | 348735 | DSF0000961013, DSF0001035000
12 | X420 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Construction | In-Progress | 6/12/2023 | 6/10/2025 |  | 11376396 | 10371552 | 2483749 | DSF0000961013, DSF0001035000
12 | X420 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | CM,F&E | In-Progress | 6/12/2023 | 6/10/2025 |  | 714075 | 203325 | 203325 | DSF0000961013, DSF0001035000
12 | X420 | WORLD CULTURES HS - X | SCA Furniture & Equipment | RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 12/9/2024 |  |  | 200000 | 200000 | 0 | DSF0001112221
12 | X420 | THE URBAN ASSEMBLY CHARTER SCHOOL FOR COMPUTER SCIENCE - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0 | DSF0001036286
12 | X420 | PAN AMERICAN INTER HS- X | DIIT - RESOA | FY24 RESO A TECHNOLOGY | Purch & Install | In-Progress | 10/16/2024 | DIIR |  | DIIR | 125000 | 125000 | DSF0001086830
12 | X420 | WORLD CULTURES HS - X | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001112223
12 | X420 | MONROE ACAD FOR VISUAL ARTS - X | DOE - RESOA | FY10 RESO A- HEALTH CLINIC | Construction | PNS | PNS | PNS | PNS | DOER | 83206 | 0 | DSF0000731157
12 | X420 | THE METROPOLITAN SOUNDVIEW HIGH SCHOOL - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 239699 | 0 | DSF0001086831
12 | X420 | WORLD CULTURES HS - X | DOE - Skilled Trades | CHARTER MATCH LIGHTING UPGRADE | Construction | In-Progress | 3/2/2020 | DOES |  | DOES | 971334 | 0 | DSF0000909450
12 | X420 | WORLD CULTURES HS - X | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/10/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085072
12 | X421 | WORLD CULTURES HS - X | DOE - Skilled Trades | ATHLETIC FIELD | Construction | In-Progress | 11/16/2023 | DOES |  | DOES | 2500000 | 1975233 | DSF0001082632
12 | X423 | I.S. 242 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 305000 | 0 | DSF0001113413
12 | X423 | X721 SPED - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113414
12 | X423 | THE CINEMA SCHOOL - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113415
12 | X493 | DISTRICT 12 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/20/2024 | DOES | 8/23/2024 | DOES | 65832 |  | DSF0001085573
12 | X817 | X010 SPED - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 10/10/2024 | IEH |  | IEH | 0 | 0 | SCA0000073488
12 | X879 | WINGS ACADEMY - X | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/15/2024 | IEH | 7/30/2024 | IEH | 0 | 0 | SCA0000073135
12 | X989 | PATHWAYS TO GRADUATION - CITYWIDE | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 10/10/2024 | IEH |  | IEH | 0 | 0 | SCA0000073486
12 | XA21 | X000 - BRONX | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 70000 | 0 | DSF0000890477
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 12/17/2021 | 5/5/2022 | 2/25/2022 | 104750 | 184455 | 149850 | DSF0001034160, DSF0001009448, DSF0001009446
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2/25/2022 | 7/27/2022 | 5/6/2022 | 523751 | 198601 | 198601 | DSF0001034160, DSF0001009448, DSF0001009446
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 7/18/2022 | 4/7/2024 |  | 11784376 | 10739800 | 9331620 | DSF0001034160, DSF0001009448, DSF0001009446
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 7/18/2022 | 4/7/2024 |  | 733250 | 550925 | 548815 | DSF0001034160, DSF0001009448, DSF0001009446
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/5/2024 | 7/3/2024 | 3/25/2024 | 3150 | 1478 | 1478 | DSF0001087360
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/25/2024 | 9/18/2024 | 8/13/2024 | 14175 | 5910 | 5910 | DSF0001087360
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/18/2024 | 11/12/2025 |  | 182700 | 174225 | 9675 | DSF0001087360
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/18/2024 | 11/12/2025 |  | 37603 | 25473 | 4602 | DSF0001087360
13 | K003 | P.S. 3 - BROOKLYN | SCA IEH | PO18-FAN ROOM ABATE FALLEN DUCT INSULATION | Construction | Complete | 10/30/2024 | IEH | 11/2/2024 | IEH | 0 | 0 | SCA0000073556
13 | K003 | P.S. 3 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/16/2024 | DOES | 9/30/2024 | DOES | 65832 | 7817 | DSF0001084582
13 | K008 | P.S. 8 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/14/2023 | 5/15/2023 | 6/2/2023 | 0 | 19756 | 19756 | DSF0001035365
13 | K008 | P.S. 8 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 6/5/2023 | 10/20/2023 | 1/10/2024 | 60000 | 69798 | 59384 | DSF0001035365
13 | K008 | P.S. 8 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 7/15/2024 | 8/18/2025 |  | 880000 | 592214 | 188073 | DSF0001035365
13 | K008 | P.S. 8 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 7/15/2024 | 8/18/2025 |  | 60000 | 66216 | 26435 | DSF0001035365
13 | K008 | P.S. 8 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001112513
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM REPLACEMENT / ROOFS | Scope | Complete | 9/23/2024 | 2/24/2025 | 11/12/2024 | 270744 | 82256 | 62256 | DSF0001112302, DSF0001112311, DSF0001113808, DSF0001087977
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM REPLACEMENT / ROOFS | Design | In-Progress | 12/16/2024 | 6/17/2025 |  | 1256734 | 1256734 | 179715 | DSF0001112302, DSF0001112311, DSF0001113808, DSF0001087977
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM REPLACEMENT / ROOFS | Construction | PNS | PNS | PNS | PNS | 19868298 | 19868298 | 379 | DSF0001112302, DSF0001112311, DSF0001113808, DSF0001087977
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM REPLACEMENT / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 2060415 | 2060415 | 41060 | DSF0001112302, DSF0001112311, DSF0001113808, DSF0001087977
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/31/2024 | 5/30/2024 | 3/25/2024 | 3150 | 1454 | 1454 | DSF0001087364
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/25/2024 | 9/18/2024 | 8/13/2024 | 14175 | 5814 | 5814 | DSF0001087364
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/18/2024 | 11/12/2025 |  | 182700 | 167011 | 2460 | DSF0001087364
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/18/2024 | 11/12/2025 |  | 37603 | 24984 | 4113 | DSF0001087364
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA IEH | PO18-ABATE WASTE LINE FOR ACM LOCATION: WASTE LINE ABOVE CEILING TILE IN KITCHEN PREP AREA | Construction | Complete | 9/20/2024 | IEH | 9/22/2024 | IEH | 0 | 0 | SCA0000073406
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOOR TILES LOC: ROOM 108: SPECIAL INSTRUCTION ROOM FOR 3RD GRADE 2 B | Construction | Complete | 9/25/2024 | IEH | 10/4/2024 | IEH | 0 | 0 | SCA0000073426
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 30109 | 0 | DSF0000777935
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/26/2024 | DOES | 8/27/2024 | DOES | 65832 | 9795 | DSF0001083989
13 | K011 | P.S. 11 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING TILES AND CLEAN UP DEBRIS STORAGE SPACE IN KITCHEN G50 (SPACE ID 2050) | Construction | Complete | 11/25/2024 | IEH | 11/28/2024 | IEH | 0 | 0 | SCA0000073648
13 | K011 | P.S. 11 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE 30 LINIER FEET OF ACM PIPE INSULATION FROM 2' BOILER FEED LINE FOR BOILER NUMB | Construction | In-Progress | 12/13/2024 | IEH |  | IEH | 0 | 0 | SCA0000073709
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/2/2022 | DOER |  | DOER | 43690 | 0 | DSF0000822741
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 7/12/2021 | DOER |  | DOER | 1156793 | 0 | DSF0001008219
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 4/3/2024 | DOER |  | DOER | 756212 | 0 | DSF0001085937
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112514
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001112516
13 | K011 | P.S. 11 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/9/2021 | DOES |  | DOES | 223492 | 0 | DSF0001008665
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/22/2024 | 12/24/2024 | 9/6/2024 | 3959 | 0 | 0 | DSF0001087371
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 9/6/2024 | 3/7/2025 |  | 17816 | 17816 | 0 | DSF0001087371
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 229622 | 229622 | 0 | DSF0001087371
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 42559 | 42559 | 2365 | DSF0001087371
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND RENOVATION / FIRE ALARM SYSTEM / FY24 RESO A GREEN ROOF | Scope | Complete | 2/11/2022 | 11/17/2022 | 2/15/2024 | 251152 | 413051 | 413051 | DSF0001034387, DSF0001009786, DSF0001009787, DSF0001009788, DSF0001083930, DSF0001085101, DSF0001085811
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND RENOVATION / FIRE ALARM SYSTEM / FY24 RESO A GREEN ROOF | Design | Complete | 2/16/2024 | 7/19/2024 | 9/18/2024 | 1243000 | 960020 | 661450 | DSF0001034387, DSF0001009786, DSF0001009787, DSF0001009788, DSF0001083930, DSF0001085101, DSF0001085811
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND RENOVATION / FIRE ALARM SYSTEM / FY24 RESO A GREEN ROOF | Construction | PNS | PNS | PNS | PNS | 26863663 | 26863663 | 181387 | DSF0001034387, DSF0001009786, DSF0001009787, DSF0001009788, DSF0001083930, DSF0001085101, DSF0001085811
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND RENOVATION / FIRE ALARM SYSTEM / FY24 RESO A GREEN ROOF | CM,F&E | PNS | PNS | PNS | PNS | 1853775 | 1853775 | 170414 | DSF0001034387, DSF0001009786, DSF0001009787, DSF0001009788, DSF0001083930, DSF0001085101, DSF0001085811
13 | K020 | P.S. 20 - BROOKLYN | SCA IEH | PO18-REMOVE APPROX. 10 LINEAR FEET OF PIPE INSULATION FROM MAIN STEAM HEADER ABOVE OIL TRANSFER PUMP | Construction | Complete | 11/21/2024 | IEH | 12/16/2024 | IEH | 0 | 0 | SCA0000073628
13 | K020 | P.S. 20 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | Complete | 8/26/2022 | DOER | 12/18/2023 | DOER | 312817 | 194699 | DSF0000961254
13 | K044 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Scope | Complete | 5/20/2022 | 10/5/2022 | 11/30/2022 | 136640 | 204578 | 195602 | DSF0001034904, DSF0001060807
13 | K044 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Design | Complete | 12/20/2022 | 6/8/2023 | 5/12/2023 | 683200 | 514363 | 449325 | DSF0001034904, DSF0001060807
13 | K044 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Construction | In-Progress | 10/16/2023 | 3/3/2026 |  | 15372000 | 14262118 | 3364441 | DSF0001034904, DSF0001060807
13 | K044 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 10/16/2023 | 3/3/2026 |  | 956480 | 235107 | 234053 | DSF0001034904, DSF0001060807
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 6/14/2023 | 10/16/2023 | 6/29/2023 | 4240 | 1319 | 1319 | DSF0001035002
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 6/29/2023 | 12/27/2023 | 9/27/2023 | 19080 | 5277 | 5277 | DSF0001035002
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 3/29/2024 | 2/21/2025 |  | 245920 | 226367 | 84015 | DSF0001035002
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 3/29/2024 | 2/21/2025 |  | 74471 | 57431 | 44502 | DSF0001035002
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGED ACM 9X9 TILE FLOOR LOCATION: ROOM 324 ESTIMATED 650SQ FT FLOORING IS | Construction | Complete | 9/23/2024 | IEH | 11/20/2024 | IEH | 0 | 0 | SCA0000073407
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA IEH | PO18-PERFORM QC SUPPLEMENTAL SAMPLING ON CEILING. AS PER SCHOOL, CEILING TILES ARE FALLING THROUGHOU | Construction | Complete | 9/27/2024 | IEH | 11/7/2024 | IEH | 0 | 0 | SCA0000073447
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA IEH | PO18-ABATE BASEMENT BOILER ROOM WORK COMPLETED ON 26-27 OCTOBER 2024 | Construction | Complete | 10/25/2024 | IEH | 10/27/2024 | IEH | 0 | 0 | SCA0000073623
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112542
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 328978 | 0 | DSF0001035394
13 | K046 | P.S. 46 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/23/2022 | DOES |  | DOES | 82229 | 0 | DSF0001009158
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 6/12/2019 | 10/28/2019 | 9/24/2021 | 124280 | 132066 | 128688 | DSF0000912346, DSF0000985569
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 10/5/2021 | 4/12/2022 | 8/31/2023 | 621399 | 343420 | 304285 | DSF0000912346, DSF0000985569
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 13981481 | 13981481 | 128697 | DSF0000912346, DSF0000985569
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 869958 | 869958 | 44953 | DSF0000912346, DSF0000985569
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 9/9/2019 | 1/28/2020 | 1/23/2020 | 12351 | 16586 | 16586 | DSF0001008792
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2/5/2020 | 7/7/2020 | 3/1/2021 | 61755 | 156766 | 111724 | DSF0001008792
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 7/19/2021 | 10/11/2022 |  | 1389488 | 1334838 | 1080947 | DSF0001008792
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 7/19/2021 | 10/11/2022 |  | 86457 | 45354 | 43229 | DSF0001008792
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 10/20/2023 | 104833 | 177201 | 176092 | DSF0001010285, DSF0001010286, DSF0001010287
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 10/26/2023 | 4/1/2024 | 3/19/2024 | 524168 | 369251 | 351106 | DSF0001010285, DSF0001010286, DSF0001010287
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 11793782 | 11793782 | 59960 | DSF0001010285, DSF0001010286, DSF0001010287
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 733835 | 733835 | 41094 | DSF0001010285, DSF0001010286, DSF0001010287
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/18/2024 | 1/22/2025 | 9/25/2024 | 3926 | 0 | 0 | DSF0001087380
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 9/25/2024 | 3/26/2025 |  | 17669 | 17669 | 0 | DSF0001087380
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 227728 | 227728 | 0 | DSF0001087380
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 42208 | 42208 | 3867 | DSF0001087380
13 | K056 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 6/15/2023 | 10/17/2023 | 6/29/2023 | 4000 | 1700 | 1700 | DSF0001035004
13 | K056 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 6/29/2023 | 12/27/2023 | 9/27/2023 | 18000 | 6799 | 6799 | DSF0001035004
13 | K056 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 3/29/2024 | 2/21/2025 |  | 232000 | 218647 | 96109 | DSF0001035004
13 | K056 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 3/29/2024 | 2/21/2025 |  | 69388 | 50543 | 33571 | DSF0001035004
13 | K056 | I.S. 351 - BROOKLYN | SCA CIP RESOA | FY18 RESO A COURTYARD GREENHOUSE | Scope | Complete | 1/16/2018 | 5/1/2018 | 10/24/2018 | 0 | 134367 | 60124 | DSF0000866389
13 | K056 | I.S. 351 - BROOKLYN | SCA CIP RESOA | FY18 RESO A COURTYARD GREENHOUSE | Design | Complete | 10/31/2018 | 4/5/2019 | 12/13/2019 | 195000 | 148985 | 145611 | DSF0000866389
13 | K056 | I.S. 351 - BROOKLYN | SCA CIP RESOA | FY18 RESO A COURTYARD GREENHOUSE | Construction | PNS | PNS | PNS | PNS | 2860000 | 2860000 | 20655 | DSF0000866389
13 | K056 | I.S. 351 - BROOKLYN | SCA CIP RESOA | FY18 RESO A COURTYARD GREENHOUSE | CM,F&E | PNS | PNS | PNS | PNS | 195000 | 195000 | 51274 | DSF0000866389
13 | K056 | P.S. 56 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 80000 | 79713 | DSF0001033453
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Scope | Complete | 6/3/2022 | 10/19/2022 | 12/6/2022 | 132263 | 210873 | 195336 | DSF0001034903, DSF0001061163
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Design | Complete | 2/6/2023 | 7/25/2023 | 5/15/2024 | 661316 | 480192 | 458553 | DSF0001034903, DSF0001061163
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 14879613 | 14879613 | 708833 | DSF0001034903, DSF0001061163
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 925842 | 925842 | 141285 | DSF0001034903, DSF0001061163
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/9/2023 | 6/9/2023 | 2/10/2023 | 4873 | 2099 | 2099 | DSF0001034649
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/10/2023 | 8/8/2023 | 4/26/2023 | 21929 | 8397 | 8397 | DSF0001034649
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/16/2023 | 7/10/2024 |  | 282634 | 262824 | 137179 | DSF0001034649
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/16/2023 | 7/10/2024 |  | 161663 | 146886 | 87141 | DSF0001034649
13 | K067 | P.S. 67 - BROOKLYN | SCA IEH | PO18-ABATE/REMOVE ACM STEAM PIPE INSULATION FOR TWO STEAM LINES & TRAP STATIONS ALSO CLEAN UP ALL SC | Construction | Complete | 10/21/2024 | IEH | 11/24/2024 | IEH | 0 | 0 | SCA0000073522
13 | K067 | P.S. 67 - BROOKLYN | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500255 | 0 | DSF0000867232
13 | K067 | COY L. COX SCHOOL | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 446453 | 0 | DSF0000913209
13 | K085 | K753 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS | Scope | Complete | 9/14/2021 | 11/21/2022 | 3/6/2023 | 90069 | 151663 | 151663 | DSF0001009292, DSF0001010674, DSF0001010675
13 | K085 | K753 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS | Design | Complete | 3/15/2023 | 8/15/2023 | 9/13/2023 | 450345 | 388044 | 351747 | DSF0001009292, DSF0001010674, DSF0001010675
13 | K085 | K753 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS | Construction | PNS | PNS | PNS | PNS | 10132738 | 10132738 | 92590 | DSF0001009292, DSF0001010674, DSF0001010675
13 | K085 | K753 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 630482 | 630482 | 67494 | DSF0001009292, DSF0001010674, DSF0001010675
13 | K085 | K753 SPED - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | Complete | 11/10/2023 | DOER | 2/21/2024 | DOER | 146885 |  | DSF0001035407
13 | K085 | K753 SPED - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/29/2023 | DOES |  | DOES | 18752 | 0 | DSF0001035111
13 | K085 | K753 SPED - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/20/2024 | DOES | 8/28/2024 | DOES | 65832 |  | DSF0001084878
13 | K093 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | Scope | Complete | 6/6/2023 | 10/5/2023 | 6/20/2023 | 4580 | 176 | 176 | DSF0001035015
13 | K093 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | Design | Complete | 6/20/2023 | 12/15/2023 | 8/30/2023 | 20610 | 705 | 705 | DSF0001035015
13 | K093 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | Construction | In-Progress | 2/16/2024 | 1/10/2025 |  | 265640 | 238744 | 145292 | DSF0001035015
13 | K093 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | CM,F&E | In-Progress | 2/16/2024 | 1/10/2025 |  | 104399 | 83771 | 64689 | DSF0001035015
13 | K093 | P.S. 93 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROX. 12 FT OF STEAM PIPE INSULATION FROM A 2' LINE RUNNING FROM GIRLS BATHROOM | Construction | Complete | 7/2/2024 | IEH | 11/24/2024 | IEH | 0 | 0 | SCA0000073113
13 | K093 | P.S. 93 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 156950 | 0 | DSF0000779133
13 | K113 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | Scope | Complete | 6/2/2021 | 12/1/2021 | 10/6/2021 | 194245 | 159075 | 159075 | DSF0000986358, DSF0000986359, DSF0000986360, DSF0001011128, DSF0001034212
13 | K113 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | Design | Complete | 10/18/2021 | 6/30/2022 | 4/27/2022 | 961994 | 545424 | 545424 | DSF0000986358, DSF0000986359, DSF0000986360, DSF0001011128, DSF0001034212
13 | K113 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | Construction | In-Progress | 7/18/2022 | 7/16/2024 |  | 20846287 | 19052198 | 17139545 | DSF0000986358, DSF0000986359, DSF0000986360, DSF0001011128, DSF0001034212
13 | K113 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | CM,F&E | In-Progress | 7/18/2022 | 7/16/2024 |  | 1428957 | 736133 | 725725 | DSF0000986358, DSF0000986359, DSF0000986360, DSF0001011128, DSF0001034212
13 | K113 | I.S. 113 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 450000 | 450000 | 450000 | DSF0001085977
13 | K113 | I.S. 113 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 580465 | 0 | DSF0001035158
13 | K113 | I.S. 113 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 2/28/2024 | DOES |  | DOES | 548587 | 248664 | DSF0001089539
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 4/8/2022 | 10/4/2022 | 7/25/2022 | 8980 | 13112 | 13112 | DSF0000892725
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 7/26/2022 | 1/24/2023 | 12/21/2022 | 40410 | 52446 | 52446 | DSF0000892725
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 5/31/2023 | 4/24/2024 |  | 520840 | 476661 | 383874 | DSF0000892725
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 5/31/2023 | 4/24/2024 |  | 96535 | 83517 | 78341 | DSF0000892725
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 5/5/2023 | DOER |  | DOER | 48558 | 0 | DSF0000961204
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 2/21/2023 | DOES | 11/6/2023 | DOES | 512395 | 478634 | DSF0001035142
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 6/4/2024 | DOES |  | DOES | 742232 | 0 | DSF0001083757
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 1/24/2023 | 6/8/2023 | 11/6/2023 | 61430 | 168779 | 168779 | DSF0001064348, DSF0001064347, DSF0001111801, DSF0001092010
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | In-Progress | 12/13/2023 | 5/15/2024 |  | 299444 | 299444 | 157984 | DSF0001064348, DSF0001064347, DSF0001111801, DSF0001092010
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 6448828 | 6448828 | 93450 | DSF0001064348, DSF0001064347, DSF0001111801, DSF0001092010
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 489565 | 489565 | 75211 | DSF0001064348, DSF0001064347, DSF0001111801, DSF0001092010
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/13/2024 | 12/13/2024 | 8/13/2024 | 4425 | 665 | 665 | DSF0001087438
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 8/13/2024 | 2/11/2025 |  | 19913 | 19913 | 2660 | DSF0001087438
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 256657 | 256657 | 2681 | DSF0001087438
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 47570 | 47570 | 5169 | DSF0001087438
13 | K256 | P.S. 256 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE APPROXIMATELY 10 LINEAR FEET OF PIPE COVERING FROM PIPE IN CORRIDOR AT CELLAR | Construction | Complete | 10/9/2024 | IEH | 10/13/2024 | IEH | 0 | 0 | SCA0000073481
13 | K256 | P.S. 256 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 1/13/2023 | DOER |  | DOER | 217022 | 0 | DSF0001008229
13 | K256 | P.S. 256 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/30/2023 | DOER |  | DOER | 224144 | 0 | DSF0001033047
13 | K258 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/22/2023 | 11/7/2023 | 12/5/2023 | 95880 | 270819 | 269298 | DSF0001064390, DSF0001064392
13 | K258 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 12/14/2023 | 5/16/2024 | 4/30/2024 | 479400 | 682231 | 311146 | DSF0001064390, DSF0001064392
13 | K258 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 7/18/2024 | 1/3/2027 |  | 10786500 | 9930970 | 900176 | DSF0001064390, DSF0001064392
13 | K258 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/18/2024 | 1/3/2027 |  | 671160 | 141412 | 139452 | DSF0001064390, DSF0001064392
13 | K258 | K140 SPED - BROOKLYN | SCA IEH | PO18-PLEASE TEST AND ABATE ACM IF NEEDED IN THE FOLLOWING AREAS. APPROXIMATELY 4 SQUARE FEET OF CEI | Construction | Complete | 8/12/2024 | IEH | 8/19/2024 | IEH | 0 | 0 | SCA0000073275
13 | K258 | K140 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR ACM ON PIPES | Construction | Complete | 8/29/2024 | IEH | 8/30/2024 | IEH | 0 | 0 | SCA0000073335
13 | K258 | K140 SPED - BROOKLYN | SCA IEH | PO18-ACM ABATEMENT IN ROOMS# 222 OPEN THE SOFFIT REMIOVE PIPE INSULATION WHICH IS ASSUMED ACM AND PR | Construction | Complete | 10/22/2024 | IEH | 10/27/2024 | IEH | 0 | 0 | SCA0000073529
13 | K258 | ALC - MS 258 | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 55000 | 0 | DSF0000913809
13 | K258 | K140 SPED - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/25/2024 | DOES | 12/9/2024 | DOES | 65832 |  | DSF0001084885
13 | K265 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/22/2019 | 12/6/2019 | 12/19/2019 | 103017 | 130059 | 130059 | DSF0000895099, DSF0000895100, DSF0000895101
13 | K265 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/30/2019 | 6/1/2020 | 6/30/2020 | 515089 | 363149 | 350973 | DSF0000895099, DSF0000895100, DSF0000895101
13 | K265 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 7/21/2021 | 4/1/2023 |  | 11589500 | 11394803 | 7912941 | DSF0000895099, DSF0000895100, DSF0000895101
13 | K265 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/21/2021 | 4/1/2023 |  | 721124 | 821147 | 796460 | DSF0000895099, DSF0000895100, DSF0000895101
13 | K265 | I.S. 265 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE 2FT X 2FT ON MARKED FLOORS IN BASEMENT BOYS LOCKER ROOM B53. (1) GANG SHOWER F | Construction | Complete | 11/4/2024 | IEH | 12/17/2024 | IEH | 0 | 0 | SCA0000073565
13 | K265 | I.S. 265 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 250000 | 0 | DSF0001008468
13 | K265 | I.S. 265 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/25/2024 | DOES |  | DOES | 546915 | 0 | DSF0001035185
13 | K265 | I.S. 265 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/28/2024 | DOES | 9/6/2024 | DOES | 65832 |  | DSF0001084886
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/16/2024 | 12/18/2024 | 8/20/2024 | 4221 | 432 | 432 | DSF0001087441
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 8/20/2024 | 2/19/2025 |  | 18996 | 18996 | 1729 | DSF0001087441
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 244840 | 244840 | 0 | DSF0001087441
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 45380 | 45380 | 5544 | DSF0001087441
13 | K270 | COMMUNITY PARTNERSHIP CHARTER SCHL - K | SCA CIP RESOA | FY11 RESO A- WIRING UPGRADE AND A/C | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000710976
13 | K270 | COMMUNITY PARTNERSHIP CHARTER SCHL - K | SCA CIP RESOA | FY11 RESO A- WIRING UPGRADE AND A/C | Design | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0000710976
13 | K270 | COMMUNITY PARTNERSHIP CHARTER SCHL - K | SCA CIP RESOA | FY11 RESO A- WIRING UPGRADE AND A/C | Construction | PNS | PNS | PNS | PNS | 44000 | 44000 | 0 | DSF0000710976
13 | K270 | COMMUNITY PARTNERSHIP CHARTER SCHL - K | SCA CIP RESOA | FY11 RESO A- WIRING UPGRADE AND A/C | CM,F&E | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0000710976
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112662
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112662
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001112662
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112662
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113583
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113583
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113583
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113583
13 | K270 | P.S. 270 - BROOKLYN | SCA IEH | PO18-ROOM 215 ABATE AND REPLACE FLOORING. TILES ARE MISSING AND BROKEN | Construction | Complete | 6/25/2024 | IEH | 7/7/2024 | IEH | 0 | 0 | SCA0000073087
13 | K270 | COMMUNITY PARTNERSHIP CHARTER SCHL - K | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000866465
13 | K270 | P.S. 270 - BROOKLYN | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | Complete | 1/3/2022 | DIIR | 9/6/2022 | DIIR | 50000 | 50000 | DSF0001034319
13 | K270 | P.S. 270 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/3/2024 | DOER |  | DOER | 510033 | 0 | DSF0001035511
13 | K270 | P.S. 270 - BROOKLYN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | In-Progress | 12/28/2023 | DOER |  | DOER | 150000 | 0 | DSF0001086061
13 | K270 | P.S. 270 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 105000 | 0 | DSF0001112661
13 | K270 | P.S. 270 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75150 | 0 | DSF0000782086
13 | K270 | P.S. 270 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/17/2024 | DOES | 7/12/2024 | DOES | 65832 | 18969 | DSF0001084127
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 5/29/2019 | 10/29/2019 | 8/1/2019 | 58280 | 87015 | 87015 | DSF0000912413, DSF0000895335
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 8/1/2019 | 1/6/2020 | 2/3/2020 | 291400 | 468228 | 404373 | DSF0000912413, DSF0000895335
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | Complete | 7/6/2021 | 7/5/2023 | 7/1/2024 | 6556500 | 7014710 | 5723171 | DSF0000912413, DSF0000895335
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | Complete | 7/6/2021 | 7/5/2023 | 7/1/2024 | 407960 | 650838 | 601612 | DSF0000912413, DSF0000895335
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 5/29/2024 | 10/15/2024 | 9/16/2024 | 101048 | 67517 | 4085 | DSF0001092436, DSF0001120163
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 12/3/2024 | 5/6/2025 |  | 471556 | 471556 | 6995 | DSF0001092436, DSF0001120163
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 7477533 | 7477533 | 2083 | DSF0001092436, DSF0001120163
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 741017 | 741017 | 13300 | DSF0001092436, DSF0001120163
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/15/2023 | 6/15/2023 | 2/17/2023 | 5007 | 2398 | 2398 | DSF0001034611
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/17/2023 | 8/15/2023 | 4/26/2023 | 22532 | 9592 | 9592 | DSF0001034611
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/16/2023 | 7/10/2024 |  | 290406 | 260506 | 174046 | DSF0001034611
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/16/2023 | 7/10/2024 |  | 126373 | 102655 | 97839 | DSF0001034611
13 | K282 | P.S. 282 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033534
13 | K282 | P.S. 282 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001035523
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 1/17/2020 | 6/18/2020 | 4/14/2020 | 71170 | 113080 | 113080 | DSF0000798438, DSF0000895405
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 4/15/2020 | 9/15/2020 | 7/31/2020 | 355850 | 418799 | 409028 | DSF0000798438, DSF0000895405
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 3/28/2022 | 3/26/2024 |  | 8006626 | 7371560 | 6866862 | DSF0000798438, DSF0000895405
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 3/28/2022 | 3/26/2024 |  | 498190 | 605543 | 602020 | DSF0000798438, DSF0000895405
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/10/2024 | 1/13/2025 | 9/13/2024 | 4287 | 266 | 266 | DSF0001087445
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 9/13/2024 | 3/14/2025 |  | 19292 | 19292 | 1064 | DSF0001087445
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 248649 | 248649 | 0 | DSF0001087445
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 46086 | 46086 | 1469 | DSF0001087445
13 | K287 | P.S. 287 - BROOKLYN | SCA IEH | PO18-ROOM B10, ABATE PIPE INSULATION MARKED IN RED HALLWAY OUTSIDE B15, ABATE PIPE INSULATION MARKED | Construction | Complete | 9/26/2024 | IEH | 10/29/2024 | IEH | 0 | 0 | SCA0000073432
13 | K287 | P.S. 287 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 226357 | 0 | DSF0000959874
13 | K287 | P.S. 287 - BROOKLYN | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 102000 | 0 | DSF0001113824
13 | K287 | P.S. 287 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/18/2024 | DOER |  | DOER | 301078 | 0 | DSF0001008221
13 | K287 | P.S. 287 - BROOKLYN | DOE - RESOA | RESO A- RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 209604 | 0 | DSF0001083927
13 | K287 | P.S. 287 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112671
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 9/13/2022 | 3/13/2023 | 1/5/2023 | 116173 | 252990 | 119412 | DSF0001014375, DSF0001014376, DSF0001083742
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/11/2023 | 7/10/2023 | 5/2/2023 | 580866 | 830458 | 336625 | DSF0001014375, DSF0001014376, DSF0001083742
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 10/3/2023 | 10/1/2025 |  | 13069464 | 12039614 | 5487214 | DSF0001014375, DSF0001014376, DSF0001083742
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 10/3/2023 | 10/1/2025 |  | 814213 | 457173 | 439838 | DSF0001014375, DSF0001014376, DSF0001083742
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/6/2023 | 7/5/2023 | 3/9/2023 | 4660 | 2529 | 2529 | DSF0001034617
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/9/2023 | 9/1/2023 | 5/4/2023 | 20970 | 10116 | 10116 | DSF0001034617
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/20/2023 | 9/13/2024 |  | 270280 | 249045 | 214870 | DSF0001034617
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/20/2023 | 9/13/2024 |  | 120700 | 102692 | 98714 | DSF0001034617
13 | K305 | I.S. 492- BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING 12'X12' ACCOUSTIC CEILING TILE FELL, 6'X6' BUBBLE ON CEILING LOC: 1ST | Construction | Complete | 7/18/2024 | IEH | 7/20/2024 | IEH | 0 | 0 | SCA0000073160
13 | K305 | I.S. 492- BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 346954 | 0 | DSF0001086077
13 | K305 | I.S. 492- BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/23/2024 | DOES | 10/30/2024 | DOES | 65832 |  | DSF0001084614
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/2/2023 | 10/3/2023 | 6/12/2023 | 4860 | 176 | 176 | DSF0001035021
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/12/2023 | 12/8/2023 | 8/30/2023 | 21870 | 705 | 705 | DSF0001035021
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/16/2024 | 1/10/2025 |  | 281880 | 253705 | 142233 | DSF0001035021
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/16/2024 | 1/10/2025 |  | 127025 | 105339 | 88552 | DSF0001035021
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/5/2023 | 3/7/2024 | 6/27/2024 | 0 | 35890 | 21334 | DSF0001086078
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 7/9/2024 | 11/22/2024 |  | 94173 | 58283 | 31509 | DSF0001086078
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1381210 | 1381210 | 6700 | DSF0001086078
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 94173 | 94173 | 21703 | DSF0001086078
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 5/15/2024 | 8/16/2024 | 7/30/2024 | 0 | 399 | 399 | DSF0001087025
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | In-Progress | 8/8/2024 | 12/12/2024 |  | 4345 | 1598 | 1598 | DSF0001087025
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 63724 | 63724 | 0 | DSF0001087025
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 4345 | 4345 | 665 | DSF0001087025
13 | K307 | P.S. 307 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/16/2019 | EMER |  | EMER | 269424 | 216838 | SCA0000055865
13 | K307 | P.S. 307 - BROOKLYN | Fast Track Projects | RENOVATION OF CLASSROOM 332 | Construction | In-Progress | 11/20/2013 | FTK |  | FTK | 329772 | 329772 | DSF0000777217
13 | K313 | I.S. 527 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / ROOFS / FIRE ALARM | Scope | Complete | 11/17/2023 | 4/17/2024 | 7/18/2024 | 377571 | 230528 | 230464 | DSF0001111632, DSF0001113726, DSF0001113725, DSF0001113727
13 | K313 | I.S. 527 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / ROOFS / FIRE ALARM | Design | In-Progress | 8/15/2024 | 3/14/2025 |  | 1753653 | 1753653 | 398052 | DSF0001111632, DSF0001113726, DSF0001113725, DSF0001113727
13 | K313 | I.S. 527 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / ROOFS / FIRE ALARM | Construction | PNS | PNS | PNS | PNS | 27733743 | 27733743 | 482990 | DSF0001111632, DSF0001113726, DSF0001113725, DSF0001113727
13 | K313 | I.S. 527 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / ROOFS / FIRE ALARM | CM,F&E | PNS | PNS | PNS | PNS | 2861672 | 2861672 | 143359 | DSF0001111632, DSF0001113726, DSF0001113725, DSF0001113727
13 | K313 | I.S. 527 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/17/2022 | DOER |  | DOER | 231846 | 0 | DSF0000913056
13 | K313 | I.S. 527 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/8/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084890
13 | K317 | P.S. 133 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008270
13 | K317 | P.S. 133 - BROOKLYN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 6/6/2024 | DOER | 8/15/2024 | DOER | 55294 |  | DSF0001035538
13 | K317 | P.S. 133 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112683
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | Scope | Complete | 2/28/2013 | 5/29/2013 | 7/24/2013 | 77238 | 68901 | 68901 | DSF0000760755, DSF0000777292
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | Design | Complete | 8/21/2013 | 2/27/2014 | 9/4/2014 | 300370 | 739899 | 692155 | DSF0000760755, DSF0000777292
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | Construction | In-Progress | 11/24/2014 | 2/16/2016 |  | 4861703 | 6115568 | 5582552 | DSF0000760755, DSF0000777292
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | CM,F&E | In-Progress | 11/24/2014 | 2/16/2016 |  | 472010 | 1155704 | 1148292 | DSF0000760755, DSF0000777292
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | Scope | Complete | 4/13/2016 | 8/26/2016 | 2/23/2017 | 367911 | 215006 | 215006 | DSF0000828949, DSF0000866288, DSF0000850828, DSF0000866289, DSF0000850833
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | Design | Complete | 5/22/2017 | 10/23/2017 | 3/15/2018 | 1463972 | 992914 | 891870 | DSF0000828949, DSF0000866288, DSF0000850828, DSF0000866289, DSF0000850833
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | Construction | In-Progress | 7/16/2018 | 1/14/2021 |  | 26760698 | 29159614 | 22547911 | DSF0000828949, DSF0000866288, DSF0000850828, DSF0000866289, DSF0000850833
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | CM,F&E | In-Progress | 7/16/2018 | 1/14/2021 |  | 1816689 | 1859537 | 1752742 | DSF0000828949, DSF0000866288, DSF0000850828, DSF0000866289, DSF0000850833
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 8/1/2017 | 1/4/2018 | 12/11/2018 | 362895 | 250125 | 250125 | DSF0000888926, DSF0000896356
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 12/12/2018 | 5/15/2019 | 5/17/2019 | 1451580 | 1003809 | 863763 | DSF0000888926, DSF0000896356
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/29/2019 | 7/12/2022 |  | 27217125 | 38449279 | 33852371 | DSF0000888926, DSF0000896356
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/29/2019 | 7/12/2022 |  | 1693510 | 2287463 | 2104817 | DSF0000888926, DSF0000896356
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 1/19/2018 | 5/4/2018 | 11/2/2018 | 0 | 51878 | 51878 | DSF0000866386
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Design | Complete | 7/9/2019 | 12/10/2019 | 5/28/2020 | 106865 | 132270 | 125883 | DSF0000866386
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 8/8/2022 | 8/7/2023 |  | 1567353 | 1429095 | 1342732 | DSF0000866386
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 8/8/2022 | 8/7/2023 |  | 106865 | 405797 | 405797 | DSF0000866386
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY13 RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/19/2013 | 10/21/2013 | 11/8/2013 | 0 | 79122 | 79122 | DSF0000754719
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY13 RESO A AUDITORIUM UPGRADE | Design | Complete | 5/27/2015 | 10/27/2015 | 9/6/2016 | 0 | 258009 | 251587 | DSF0000754719
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY13 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 43001 | 43001 | DSF0000754719
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY13 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 49247 | 49247 | DSF0000754719
13 | K430 | BROOKLYN TECH HS - K | SCA Emergency Response | SIDEWALK BRIDGING | Construction | In-Progress | 5/22/2013 | EMER |  | EMER | 1509825 | 1509825 | SCA0000026232
13 | K430 | BROOKLYN TECH HS - K | SCA IEH | PO18-ABATE AND REPLACE 9X9N TILES THAT ARE CRACKED AND DAMAGED. ACM ACCORDING TO THE AHERA BOOK . T | Construction | Complete | 7/30/2024 | IEH | 8/16/2024 | IEH | 0 | 0 | SCA0000073204
13 | K430 | BROOKLYN TECH HS - K | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES LOCATION: ROOM 4E12 TILES ARE CRACKING AND COMING UP APPROX 20SQF | Construction | Complete | 8/5/2024 | IEH | 8/23/2024 | IEH | 0 | 0 | SCA0000073236
13 | K430 | BROOKLYN TECH HS - K | SCA IEH | PO18-ABATE 50 LINEAR FT OF PIPE INSULATION IN ROOM BN2 ELECTRICAL ROOM THE PIPE PASSES THROUGH THE W | Construction | In-Progress | 12/23/2024 | IEH |  | IEH | 0 | 0 | SCA0000073734
13 | K430 | BROOKLYN TECH HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/2/2024 | DOES | 7/11/2024 | DOES | 65832 | 8671 | DSF0001084902
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | Scope | Complete | 3/18/2013 | 7/17/2013 | 8/23/2013 | 141546 | 308328 | 308328 | DSF0000775845
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | Design | Complete | 6/5/2015 | 1/11/2016 | 10/28/2016 | 566184 | 594138 | 562120 | DSF0000775845
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | Construction | In-Progress | 8/21/2017 | 8/20/2019 |  | 10615950 | 10737510 | 9855180 | DSF0000775845
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | CM,F&E | In-Progress | 8/21/2017 | 8/20/2019 |  | 660548 | 786434 | 754416 | DSF0000775845
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/22/2023 | 10/20/2023 | 10/18/2023 | 11105 | 19537 | 19537 | DSF0001083805
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/20/2023 | 3/20/2024 | 4/29/2024 | 49970 | 87378 | 73882 | DSF0001083805
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/17/2024 | 10/21/2025 |  | 644061 | 568402 | 4699 | DSF0001083805
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/17/2024 | 10/21/2025 |  | 119373 | 72065 | 11959 | DSF0001083805
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | Fast Track Projects | EMERGENCY INVESTIGATION | Construction | In-Progress | 7/30/2014 | FTK |  | FTK | 271001 | 166733 | DSF0000799787
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | DOE - Skilled Trades | GAS VENT LINE REROUTING | Construction | In-Progress | 11/6/2019 | DOES |  | DOES | 26795 | 10500 | DSF0000960539
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/21/2024 | DOES | 12/9/2024 | DOES | 65832 |  | DSF0001084771
13 | K580 | GEORGE WESTINGHOUSE VOC. HS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 1/6/2023 | DOES | 1/3/2024 | DOES | 573422 | 484548 | DSF0000960848
13 | K580 | GEORGE WESTINGHOUSE VOC. HS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/22/2024 | DOES | 8/2/2024 | DOES | 65832 | 7604 | DSF0001084773
13 | K611 | THE DOCK STREET SCHOOL FOR STEAM STUDIES - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 241280 | 0 | DSF0001086143
13 | K611 | THE DOCK STREET SCHOOL FOR STEAM STUDIES - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/9/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084774
13 | K694 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | Scope | Complete | 4/11/2016 | 7/7/2016 | 6/28/2016 | 71100 | 220825 | 220825 | DSF0000843969
13 | K694 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | Design | Complete | 6/29/2016 | 12/30/2016 | 3/6/2017 | 355500 | 1050350 | 645095 | DSF0000843969
13 | K694 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | Construction | Complete | 11/20/2023 | 9/3/2024 | 8/17/2024 | 7998750 | 7261478 | 6877283 | DSF0000843969
13 | K694 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | CM,F&E | Complete | 11/20/2023 | 9/3/2024 | 8/17/2024 | 1249806 | 1771894 | 1332589 | DSF0000843969
13 | K743 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 1/26/2016 | 6/9/2016 | 7/22/2016 | 179797 | 97216 | 97216 | DSF0000843680, DSF0000851506, DSF0000851523, DSF0000851509, DSF0000851510, DSF0000866095, DSF0000851507
13 | K743 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Design | Complete | 3/13/2017 | 8/10/2017 | 5/18/2018 | 698119 | 824701 | 804697 | DSF0000843680, DSF0000851506, DSF0000851523, DSF0000851509, DSF0000851510, DSF0000866095, DSF0000851507
13 | K743 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Construction | In-Progress | 8/27/2018 | 5/17/2020 |  | 11199258 | 12794573 | 11535702 | DSF0000843680, DSF0000851506, DSF0000851523, DSF0000851509, DSF0000851510, DSF0000866095, DSF0000851507
13 | K743 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | CM,F&E | In-Progress | 8/27/2018 | 5/17/2020 |  | 1112884 | 1418489 | 1388790 | DSF0000843680, DSF0000851506, DSF0000851523, DSF0000851509, DSF0000851510, DSF0000866095, DSF0000851507
13 | K743 | ADULT AND CONTINUING EDUCATION | SCA IEH | PO18-ABATE AND REMOVE APPROX. 25 LINEAR FEET OF ACM STEAM PIPE INSULATION FOM HIGH LINE IN ROOM 210 | Construction | Complete | 10/23/2024 | IEH | 10/29/2024 | IEH | 0 | 0 | SCA0000073533
13 | K777 | BROOKLYN NAVY YARD STEM CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 8/14/2024 | IEH |  | IEH | 0 | 0 | SCA0000073286
13 | K777 | BROOKLYN NAVY YARD STEM CENTER | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0 | DSF0001008217
13 | K777 | BROOKLYN NAVY YARD STEM CENTER | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0 | DSF0001008237
13 | K805 | BROOKLYN INTERNATIONAL HS - K | Fast Track Projects | LSP VACUUM PUMP SET REPLACEMENT | Construction | In-Progress | 4/20/2021 | FTK |  | FTK | 104458 | 88856 | DSF0000960820
13 | K805 | SCIENCE SKILLS CENTER HS - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001033089
13 | K805 | SCIENCE SKILLS CENTER HS - K | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 144109 | 0 | DSF0001033088
13 | K805 | BROOKLYN INTERNATIONAL HS - K | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 116467 | 0 | DSF0001086150
13 | K805 | BROOKLYN INTERNATIONAL HS - K | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 5/3/2021 | DOES |  | DOES | 316427 | 0 | DSF0000911920
13 | K805 | BROOKLYN INTERNATIONAL HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/23/2024 | DOES | 10/4/2024 | DOES | 65832 | 5851 | DSF0001084934
13 | K813 | ALC - FUNDAMENTAL ACADEMY | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 12/22/2023 | 5/9/2024 | 3/13/2024 | 10800 | 16758 | 16758 | DSF0001067166
13 | K813 | ALC - FUNDAMENTAL ACADEMY | SCA CIP | EXTERIOR MASONRY | Design | Complete | 3/15/2024 | 8/15/2024 | 8/2/2024 | 43200 | 48819 | 44970 | DSF0001067166
13 | K813 | ALC - FUNDAMENTAL ACADEMY | SCA CIP | EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 621000 | 621000 | 11347 | DSF0001067166
13 | K813 | ALC - FUNDAMENTAL ACADEMY | SCA CIP | EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 159300 | 159300 | 19473 | DSF0001067166
13 | K813 | ALC - FUNDAMENTAL ACADEMY | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 11/12/2024 | IEH | 12/6/2024 | IEH | 0 | 0 | SCA0000073596
13 | K831 | DIV. COMPUTER INFO-DATA CNTR - K | SCA CIP | DATA CENTER | Scope | Complete | 1/20/2015 | 5/19/2015 | 6/3/2015 | 407874 | 362965 | 362965 | DSF0000844684
13 | K831 | DIV. COMPUTER INFO-DATA CNTR - K | SCA CIP | DATA CENTER | Design | In-Progress | 12/21/2016 | 8/7/2017 |  | 2039370 | 2039370 | 956411 | DSF0000844684
13 | K831 | DIV. COMPUTER INFO-DATA CNTR - K | SCA CIP | DATA CENTER | Construction | PNS | PNS | PNS | PNS | 45885835 | 45885835 | 9349 | DSF0000844684
13 | K831 | DIV. COMPUTER INFO-DATA CNTR - K | SCA CIP | DATA CENTER | CM,F&E | PNS | PNS | PNS | PNS | 2855119 | 2855119 | 8145 | DSF0000844684
13 | K853 | K000 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/29/2024 | IEH | 8/7/2024 | IEH | 0 | 0 | SCA0000073184
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 6/5/2019 | 9/4/2019 | 8/15/2019 | 10700 | 21043 | 21043 | DSF0000897381
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/4/2019 | 6/8/2020 | 6/30/2020 | 48150 | 87274 | 68741 | DSF0000897381
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 7/22/2024 | 6/16/2025 |  | 620600 | 554086 | 5586 | DSF0000897381
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 7/22/2024 | 6/16/2025 |  | 115025 | 80426 | 22682 | DSF0000897381
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/2/2023 | 6/30/2023 | 3/9/2023 | 3140 | 2447 | 2447 | DSF0001034551
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/9/2023 | 9/1/2023 | 5/4/2023 | 14130 | 9789 | 9789 | DSF0001034551
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/20/2023 | 9/13/2024 |  | 182120 | 170777 | 143157 | DSF0001034551
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/20/2023 | 9/13/2024 |  | 112364 | 101651 | 96412 | DSF0001034551
13 | K874 | I.S. 340 - BROOKLYN | Fast Track Projects | LEAD SERVICE LINE | Construction | In-Progress | 10/17/2016 | FTK |  | FTK | 108067 | 108067 | DSF0000829872
13 | K874 | I.S. 340 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/30/2022 | DOES |  | DOES | 332097 | 0 | DSF0001008688
13 | K874 | I.S. 340 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/23/2024 | DOES | 8/30/2024 | DOES | 65832 |  | DSF0001084777
13 | K902 | K077 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086158
13 | K902 | K077 SPED - BROOKLYN | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 168527 | 0 | DSF0001111896
13 | K902 | K077 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112744
13 | K902 | I.S. 266 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/22/2024 | DOES | 10/29/2024 | DOES | 65832 |  | DSF0001084936
13 | K914 | BENJAMIN BANNEKER ACAD. (HS LVL)-K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/19/2024 | DOES |  | DOES | 780748 | 0 | DSF0001035193
13 | K914 | BENJAMIN BANNEKER ACAD. (HS LVL)-K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/10/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085477
13 | K994 | BEDFORD ACADEMY HS - K | DOE - RESOA | FY21 RESO A MEDIA CENTER UPGRADE | Construction | In-Progress | 10/11/2023 | DOER |  | DOER | 74399 | 0 | DSF0001008228
13 | K994 | BEDFORD ACADEMY HS - K | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 7/18/2024 | DOER | 8/15/2024 | DOER | 37945 |  | DSF0001035603
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/28/2024 | 9/26/2024 | 5/31/2024 | 5243 | 2590 | 2590 | DSF0001087368
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/31/2024 | 11/27/2024 | 11/6/2024 | 23593 | 10359 | 10359 | DSF0001087368
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 304093 | 304093 | 7895 | DSF0001087368
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 56362 | 56362 | 3658 | DSF0001087368
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113561
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113561
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113561
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113561
14 | K016 | P.S. 16 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 93000 | 0 | DSF0001112522
14 | K016 | P.S. 16 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0 | DSF0001112521
14 | K016 | P.S. 16 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 93000 | 0 | DSF0001112523
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 4/6/2017 | 11/2/2017 | 12/19/2017 | 183712 | 162802 | 162802 | DSF0000865947, DSF0001083702
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 4/25/2018 | 10/25/2018 | 9/30/2022 | 910025 | 549395 | 485039 | DSF0000865947, DSF0001083702
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 8/28/2023 | 8/16/2025 |  | 19737609 | 17865410 | 6380048 | DSF0000865947, DSF0001083702
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 8/28/2023 | 8/16/2025 |  | 1349963 | 239596 | 238038 | DSF0000865947, DSF0001083702
14 | K017 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 7/27/2023 | 11/28/2023 | 8/2/2023 | 3886 | 3429 | 3429 | DSF0001035001
14 | K017 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 12/20/2023 | 17487 | 13718 | 13718 | DSF0001035001
14 | K017 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 4/16/2024 | 3/11/2025 |  | 225388 | 201504 | 116989 | DSF0001035001
14 | K017 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 4/16/2024 | 3/11/2025 |  | 96525 | 81272 | 13383 | DSF0001035001
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113562
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113562
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113562
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113562
14 | K017 | I.S. 577 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE LOOSE & BROKEN TILES APPROX. 12 SF IN ROOM 103 CE JOSEPH PROVVISIERO 718-486 | Construction | Complete | 11/22/2024 | IEH | 12/1/2024 | IEH | 0 | 0 | SCA0000073635
14 | K017 | I.S. 577 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 12/6/2024 | IEH |  | IEH | 0 | 0 | SCA0000073680
14 | K017 | P.S. 17 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001112525
14 | K017 | P.S. 17 - BROOKLYN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001035372
14 | K017 | P.S. 17 - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0 | DSF0001112524
14 | K017 | I.S. 577 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112526
14 | K017 | P.S. 17 - BROOKLYN | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112527
14 | K017 | P.S. 17 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 1/7/2022 | DOES |  | DOES | 60651 | 0 | DSF0000866101
14 | K017 | I.S. 577 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/24/2024 | DOES | 10/14/2024 | DOES | 65832 |  | DSF0001084724
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND UPGRADE | Scope | Complete | 7/8/2022 | 11/23/2022 | 8/21/2023 | 84605 | 135804 | 135804 | DSF0001009742, DSF0001009743, DSF0001009744, DSF0001086874
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND UPGRADE | Design | Complete | 8/31/2023 | 2/6/2024 | 1/30/2024 | 417512 | 274198 | 260632 | DSF0001009742, DSF0001009743, DSF0001009744, DSF0001086874
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 8917115 | 8917115 | 261376 | DSF0001009742, DSF0001009743, DSF0001009744, DSF0001086874
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 633589 | 633589 | 51626 | DSF0001009742, DSF0001009743, DSF0001009744, DSF0001086874
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 12/13/2023 | 12/13/2023 | 12/13/2023 | 1049 | 8420 | 8420 | DSF0001111878
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 12/13/2023 | 4/12/2024 | 1/30/2024 | 4722 | 432 | 432 | DSF0001111878
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 60861 | 60861 | 0 | DSF0001111878
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 11280 | 11280 | 2387 | DSF0001111878
14 | K018 | P.S. 18 - BROOKLYN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 4/9/2024 | DOER |  | DOER | 50000 | 0 | DSF0001085942
14 | K018 | P.S. 18 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112528
14 | K018 | P.S. 18 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/22/2022 | DOES |  | DOES | 98632 | 0 | DSF0001034405
14 | K019 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | Scope | Complete | 6/6/2022 | 11/30/2022 | 10/4/2022 | 284352 | 508503 | 469696 | DSF0001033563, DSF0001033564, DSF0001009765, DSF0001009764, DSF0001009763, DSF0001009762, DSF0001036321, DSF0001009759
14 | K019 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | Design | Complete | 10/24/2022 | 6/12/2023 | 4/28/2023 | 1412403 | 827896 | 827896 | DSF0001033563, DSF0001033564, DSF0001009765, DSF0001009764, DSF0001009763, DSF0001009762, DSF0001036321, DSF0001009759
14 | K019 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | Construction | In-Progress | 9/4/2023 | 9/2/2026 |  | 30970227 | 28629235 | 6733295 | DSF0001033563, DSF0001033564, DSF0001009765, DSF0001009764, DSF0001009763, DSF0001009762, DSF0001036321, DSF0001009759
14 | K019 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | CM,F&E | In-Progress | 9/4/2023 | 9/2/2026 |  | 2060577 | 570488 | 549842 | DSF0001033563, DSF0001033564, DSF0001009765, DSF0001009764, DSF0001009763, DSF0001009762, DSF0001036321, DSF0001009759
14 | K019 | P.S. 414 - BROOKLYN | DIIT - RESOA | FY 07 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 64512 | 0 | DSF0000822695
14 | K019 | P.S. 414 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 468319 | 0 | DSF0000961280
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 8/18/2020 | 1/22/2021 | 1/6/2021 | 71320 | 109321 | 109321 | DSF0000961026, DSF0000936782
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/8/2021 | 9/30/2021 | 7/2/2021 | 356600 | 410653 | 403748 | DSF0000961026, DSF0000936782
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 4/4/2022 | 4/2/2024 |  | 8023500 | 7513473 | 7141077 | DSF0000961026, DSF0000936782
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 4/4/2022 | 4/2/2024 |  | 499240 | 484036 | 483306 | DSF0000961026, DSF0000936782
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/9/2022 | 12/5/2022 | 10/4/2022 | 64303 | 236281 | 199197 | DSF0001009848, DSF0001009849, DSF0001009850, DSF0001009846
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 10/21/2022 | 6/13/2023 | 4/25/2023 | 316912 | 426568 | 419896 | DSF0001009848, DSF0001009849, DSF0001009850, DSF0001009846
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 7/17/2023 | 7/15/2025 |  | 6732360 | 6273335 | 5004275 | DSF0001009848, DSF0001009849, DSF0001009850, DSF0001009846
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 7/17/2023 | 7/15/2025 |  | 484642 | 340242 | 326515 | DSF0001009848, DSF0001009849, DSF0001009850, DSF0001009846
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/16/2024 | 9/17/2024 | 5/20/2024 | 5149 | 3279 | 3279 | DSF0001087372
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/20/2024 | 11/15/2024 | 11/6/2024 | 23170 | 13115 | 13115 | DSF0001087372
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 298641 | 298641 | 0 | DSF0001087372
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 55352 | 55352 | 2054 | DSF0001087372
14 | K023 | P.S. 23 - BROOKLYN | SCA Emergency Response | EMERGENCY: EXTERIOR | Construction | In-Progress | 6/17/2022 | EMER |  | EMER | 353822 | 301027 | SCA0000071239
14 | K023 | P.S. 23 - BROOKLYN | SCA IEH | PO18-ABATE & REMOVE ACM INS FROM COLD WATER LINE IN CRAWL SPACE BEHIND BOILER ROOM IN BASEMENT. LINE | Construction | Complete | 12/13/2024 | IEH | 12/15/2024 | IEH | 0 | 0 | SCA0000073715
14 | K023 | P.S. 23 - BROOKLYN | DOE - RESOA | FY19 RESO A CAFETERIA SUPPLEMENTAL COOLING | Construction | Complete | 6/23/2021 | DOER | 10/28/2021 | DOER | 251447 | 180231 | DSF0000912522
14 | K023 | P.S. 23 - BROOKLYN | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 8/26/2023 | DOER |  | DOER | 137464 | 0 | DSF0001035375
14 | K023 | P.S. 23 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/1/2023 | DOER |  | DOER | 767000 | 378487 | DSF0001035376
14 | K023 | P.S. 23 - BROOKLYN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 4/9/2024 | DOER | 7/16/2024 | DOER | 92000 |  | DSF0001085944
14 | K031 | P.S. 31 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 5/13/2019 | 9/26/2019 | 10/1/2019 | 137336 | 148254 | 148254 | DSF0000912347
14 | K031 | P.S. 31 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 10/30/2019 | 4/20/2020 | 5/12/2023 | 686680 | 363969 | 343215 | DSF0000912347
14 | K031 | P.S. 31 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | PNS | PNS | PNS | PNS | 15450290 | 15450290 | 25793 | DSF0000912347
14 | K031 | P.S. 31 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | PNS | PNS | PNS | PNS | 961351 | 961351 | 105007 | DSF0000912347
14 | K031 | P.S. 31 - BROOKLYN | SCA IEH | PO18-ABATE AND DRILL 1ST. FL. CORRIDOR WALLS FOR ACM LOCATION: OUTSIDE OF RM. 102 BY BOTTLE FILLER A | Construction | Complete | 8/28/2024 | IEH | 9/22/2024 | IEH | 0 | 0 | SCA0000073325
14 | K031 | P.S. 31 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0 | DSF0001008210
14 | K031 | P.S. 31 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001033448
14 | K031 | P.S. 31 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001112534
14 | K031 | P.S. 31 - BROOKLYN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 78000 | 0 | DSF0001008205
14 | K031 | P.S. 31 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001085950
14 | K033 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/26/2022 | 11/21/2022 | 9/26/2022 | 203999 | 251729 | 225161 | DSF0001009995, DSF0001009996, DSF0001009997, DSF0001036324
14 | K033 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 9/28/2022 | 6/12/2023 | 4/13/2023 | 1020000 | 438334 | 438155 | DSF0001009995, DSF0001009996, DSF0001009997, DSF0001036324
14 | K033 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 12/4/2023 | 4/6/2027 |  | 22950000 | 21400996 | 4276122 | DSF0001009995, DSF0001009996, DSF0001009997, DSF0001036324
14 | K033 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 12/4/2023 | 4/6/2027 |  | 1428001 | 225172 | 208348 | DSF0001009995, DSF0001009996, DSF0001009997, DSF0001036324
14 | K033 | K368 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Scope | Complete | 6/10/2022 | 10/12/2022 | 10/12/2022 | 0 | 18340 | 18340 | DSF0001033076
14 | K033 | K368 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 10/17/2022 | 3/7/2023 | 3/20/2023 | 44520 | 70957 | 59088 | DSF0001033076
14 | K033 | K368 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 12/5/2023 | 10/29/2024 |  | 652960 | 394270 | 205311 | DSF0001033076
14 | K033 | K368 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | CM,F&E | In-Progress | 12/5/2023 | 10/29/2024 |  | 44520 | 67027 | 48009 | DSF0001033076
14 | K033 | K368 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS RM: B12 APPROX. 572SF RM: B46/ CLOSET APPROX. 400SF | Construction | Complete | 3/6/2024 | IEH | 8/7/2024 | IEH | 0 | 0 | SCA0000072793
14 | K033 | K368 SPED - BROOKLYN | SCA IEH | PO18-ABATE CERAMIC WALL TILE MASTIC AT THE FOLLOWING LOCATIONS: ROOM B32, TOILET STALL GIRLS BATHROO | Construction | Complete | 11/5/2024 | IEH | 12/9/2024 | IEH | 0 | 0 | SCA0000073569
14 | K033 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 5/6/2022 | DOER |  | DOER | 179138 | 0 | DSF0000961205
14 | K033 | K368 SPED - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/25/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084584
14 | K034 | P.S. 34 - BROOKLYN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/1/2024 | DOER |  | DOER | 497676 | 0 | DSF0001035385
14 | K034 | P.S. 34 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 209000 | 0 | DSF0001112535
14 | K034 | P.S. 34 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/17/2024 | DOES | 12/13/2024 | DOES | 65832 | 22117 | DSF0001084007
14 | K049 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/14/2020 | 1/11/2021 | 9/17/2020 | 4330 | 4804 | 4804 | DSF0000960736
14 | K049 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/17/2020 | 3/15/2021 | 3/31/2021 | 19483 | 19217 | 19217 | DSF0000960736
14 | K049 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/26/2022 | 3/21/2023 |  | 251117 | 225413 | 183519 | DSF0000960736
14 | K049 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/26/2022 | 3/21/2023 |  | 275558 | 270251 | 181328 | DSF0000960736
14 | K049 | THE WILLIAMSBURG HIGH SCHOOL OF ART AND TECHNOLOGY - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 9/20/2024 | DIIR |  | DIIR | 74000 | 0 | DSF0001035396
14 | K049 | THE WILLIAMSBURG HIGH SCHOOL OF ART AND TECHNOLOGY - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001085956
14 | K049 | BROOKLYN LATIN HS - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 375000 | 0 | DSF0001113451
14 | K049 | THE WILLIAMSBURG HIGH SCHOOL OF ART AND TECHNOLOGY - K | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 9/29/2022 | DOER |  | DOER | 45878 | 0 | DSF0001008411
14 | K049 | LYONS COMMUNITY SCHOOL - K | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 6/13/2022 | DOER |  | DOER | 323344 | 0 | DSF0001008419
14 | K049 | BROOKLYN LATIN HS - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1375000 | 0 | DSF0001112544
14 | K049 | LYONS COMMUNITY SCHOOL - K | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112545
14 | K049 | LYONS COMMUNITY SCHOOL - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 3/9/2023 | DOES | 11/6/2023 | DOES | 446581 | 402411 | DSF0000960839
14 | K049 | LYONS COMMUNITY SCHOOL - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/16/2024 | DOES | 11/8/2024 | DOES | 65832 |  | DSF0001084875
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | Scope | Complete | 2/4/2020 | 6/18/2020 | 6/8/2021 | 5860 | 8707 | 8707 | DSF0001010232
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | Design | Complete | 6/11/2021 | 9/30/2021 | 11/17/2021 | 26370 | 116972 | 105150 | DSF0001010232
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | Construction | In-Progress | 5/23/2022 | 2/16/2023 |  | 339880 | 453579 | 222271 | DSF0001010232
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | CM,F&E | In-Progress | 5/23/2022 | 2/16/2023 |  | 62995 | 98427 | 76089 | DSF0001010232
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 8/13/2020 | 1/19/2021 | 10/16/2020 | 79400 | 86699 | 86699 | DSF0000937133, DSF0000961027
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 10/19/2020 | 3/24/2021 | 2/5/2021 | 397000 | 346905 | 331656 | DSF0000937133, DSF0000961027
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 5/16/2022 | 5/14/2024 |  | 8932500 | 8239108 | 5012485 | DSF0000937133, DSF0000961027
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 5/16/2022 | 5/14/2024 |  | 555800 | 573079 | 571595 | DSF0000937133, DSF0000961027
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 1/10/2023 | 5/25/2023 | 6/14/2023 | 26018 | 37413 | 32023 | DSF0001060909
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 6/23/2023 | 11/27/2023 | 12/5/2023 | 130091 | 100824 | 88852 | DSF0001060909
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Construction | PNS | PNS | PNS | PNS | 2927052 | 2927052 | 3718 | DSF0001060909
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | CM,F&E | PNS | PNS | PNS | PNS | 182128 | 182128 | 6649 | DSF0001060909
14 | K050 | J.H.S. 50 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/14/2020 | EMER |  | EMER | 36190 | 36190 | SCA0000063248
14 | K050 | J.H.S. 50 - BROOKLYN | SCA IEH | PO18-ROOM 101 BY ROGHT SIDE CONVECTOR. PLEASE REMOVE ALL PIPE INSULATION FROM STEAM PIPE DOWN THROUG | Construction | Complete | 3/28/2024 | IEH | 8/10/2024 | IEH | 0 | 0 | SCA0000072882
14 | K050 | J.H.S. 50 - BROOKLYN | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 7/26/2024 | FTK |  | FTK | 630713 | 410751 | DSF0001111911
14 | K050 | J.H.S. 50 - BROOKLYN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | Complete | 10/11/2021 | DOER | 4/25/2023 | DOER | 206934 | 183735 | DSF0001008413
14 | K050 | J.H.S. 50 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001085957
14 | K050 | J.H.S. 50 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/10/2024 | DOES | 9/18/2024 | DOES | 65832 |  | DSF0001084726
14 | K059 | P.S. 59 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 1/4/2024 | 5/20/2024 | 5/24/2024 | 276103 | 130751 | 129159 | DSF0001061068, DSF0001112243, DSF0001088806, DSF0001088805
14 | K059 | P.S. 59 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 6/20/2024 | 11/21/2024 | 11/21/2024 | 1279234 | 410612 | 374411 | DSF0001061068, DSF0001112243, DSF0001088806, DSF0001088805
14 | K059 | P.S. 59 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Construction | PNS | PNS | PNS | PNS | 20202776 | 20202776 | 0 | DSF0001061068, DSF0001112243, DSF0001088806, DSF0001088805
14 | K059 | P.S. 59 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 2127612 | 2127612 | 75197 | DSF0001061068, DSF0001112243, DSF0001088806, DSF0001088805
14 | K059 | P.S. 59 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 450000 | 450000 | 450000 | DSF0001085961
14 | K059 | P.S. 59 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0 | DSF0001112548
14 | K059 | P.S. 59 - BROOKLYN | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 8/31/2020 | DOES |  | DOES | 4677 | 0 | DSF0000960909
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | Scope | Complete | 6/25/2018 | 11/8/2018 | 12/18/2018 | 14990 | 29962 | 29962 | DSF0000869347
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | Design | Complete | 12/18/2018 | 5/21/2019 | 5/14/2021 | 74950 | 160986 | 153216 | DSF0000869347
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | Construction | In-Progress | 2/21/2023 | 2/20/2024 |  | 1686375 | 1523840 | 788170 | DSF0000869347
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | CM,F&E | In-Progress | 2/21/2023 | 2/20/2024 |  | 104930 | 278445 | 277181 | DSF0000869347
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/30/2023 | 10/30/2023 | 10/31/2023 | 12900 | 20086 | 20086 | DSF0001083812
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/1/2023 | 4/1/2024 | 5/13/2024 | 58050 | 92645 | 75715 | DSF0001083812
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 11/1/2024 | 12/5/2025 |  | 748200 | 752131 | 32631 | DSF0001083812
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 11/1/2024 | 12/5/2025 |  | 138675 | 92379 | 22719 | DSF0001083812
14 | K071 | I.S. 71 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING OUTSIDE OF GYM AND GYM OFFICE CEILING PLASTER SPALLING DUE TO WATER PE | Construction | Complete | 7/9/2024 | IEH | 9/17/2024 | IEH | 0 | 0 | SCA0000073124
14 | K071 | I.S. 71 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGE /BROKEN 9X9 FLOOR TILES LOCATED IN FOYER AREA EXIT 7/8 STAIRWELL (D) | Construction | In-Progress | 10/30/2024 | IEH |  | IEH | 0 | 0 | SCA0000073554
14 | K071 | I.S. 71 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/16/2023 | DOES | 11/6/2023 | DOES | 624351 | 565766 | DSF0001035143
14 | K071 | I.S. 71 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/1/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084877
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | Scope | Complete | 6/28/2019 | 11/14/2019 | 12/6/2019 | 50683 | 76515 | 74627 | DSF0000912287, DSF0000960685, DSF0000937486
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | Design | Complete | 2/28/2020 | 7/29/2020 | 3/1/2022 | 251250 | 258761 | 258761 | DSF0000912287, DSF0000960685, DSF0000937486
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | Construction | In-Progress | 7/11/2022 | 1/1/2024 |  | 5465528 | 4977368 | 4469173 | DSF0000912287, DSF0000960685, DSF0000937486
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | CM,F&E | In-Progress | 7/11/2022 | 1/1/2024 |  | 371049 | 453386 | 442000 | DSF0000912287, DSF0000960685, DSF0000937486
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 8/5/2020 | 1/8/2021 | 12/22/2020 | 62300 | 96569 | 96569 | DSF0000937484, DSF0000961028
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/22/2020 | 5/25/2021 | 7/8/2021 | 311500 | 386860 | 382241 | DSF0000937484, DSF0000961028
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 5/16/2022 | 5/14/2024 |  | 7008751 | 6893027 | 6555870 | DSF0000937484, DSF0000961028
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 5/16/2022 | 5/14/2024 |  | 436100 | 623127 | 618215 | DSF0000937484, DSF0000961028
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 3/9/2021 | 7/22/2021 | 11/18/2021 | 76638 | 118146 | 117083 | DSF0001008564
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/29/2021 | 5/17/2022 | 9/30/2022 | 383191 | 291110 | 278505 | DSF0001008564
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | PNS | PNS | PNS | PNS | 8621786 | 8621786 | 35978 | DSF0001008564
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | PNS | PNS | PNS | PNS | 536467 | 536467 | 30153 | DSF0001008564
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/10/2023 | 7/11/2023 | 3/20/2023 | 4966 | 2190 | 2190 | DSF0001034631
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/20/2023 | 9/13/2023 | 5/2/2023 | 22347 | 8762 | 8762 | DSF0001034631
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 1/11/2024 | 12/5/2024 |  | 288028 | 260143 | 1810 | DSF0001034631
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 1/11/2024 | 12/5/2024 |  | 84793 | 64038 | 33481 | DSF0001034631
14 | K084 | P.S. 84 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/12/2019 | EMER |  | EMER | 93562 | 93562 | SCA0000056366
14 | K084 | P.S. 84 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 364000 | 364000 | 0 | DSF0001085965
14 | K084 | P.S. 84 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | Complete | 7/26/2023 | DOER | 5/23/2024 | DOER | 198196 |  | DSF0001035406
14 | K084 | P.S. 84 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001085964
14 | K084 | P.S. 84 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112558
14 | K084 | P.S. 84 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/12/2024 | DOES | 8/19/2024 | DOES | 65832 | 7216 | DSF0001084588
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 1/9/2020 | 5/26/2020 | 9/14/2021 | 12428 | 101287 | 101287 | DSF0000960592
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 11/17/2021 | 4/21/2022 | 12/7/2022 | 62138 | 171537 | 163959 | DSF0000960592
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 9/11/2023 | 6/6/2024 |  | 1398094 | 1322182 | 656445 | DSF0000960592
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 9/11/2023 | 6/6/2024 |  | 86993 | 332234 | 323500 | DSF0000960592
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 5/24/2024 | 10/10/2024 | 10/30/2024 | 26111 | 46550 | 19798 | DSF0001089479
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Design | In-Progress | 11/5/2024 | 4/10/2025 |  | 121853 | 121853 | 5617 | DSF0001089479
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 1932234 | 1932234 | 31744 | DSF0001089479
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 191483 | 191483 | 12705 | DSF0001089479
14 | K110 | P.S. 110 - BROOKLYN | SCA Emergency Response | STABILIZATION- SWB @ K110 | Construction | In-Progress | 4/19/2023 | EMER |  | EMER | 269122 | 146798 | SCA0000071900
14 | K110 | P.S. 110 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 226000 | 0 | DSF0001112569
14 | K110 | P.S. 110 - BROOKLYN | DOE - RESOA | ELECTRICAL UPGRADE | Construction | Complete | 1/30/2020 | DOER | 8/2/2021 | DOER | 35504 |  | DSF0000914323
14 | K110 | P.S. 110 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/26/2024 | DOES | 9/6/2024 | DOES | 65832 | 9669 | DSF0001084040
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/21/2023 | 7/20/2023 | 4/3/2023 | 6424 | 3164 | 3164 | DSF0001034637
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/3/2023 | 12/28/2023 | 5/2/2023 | 28908 | 12657 | 12657 | DSF0001034637
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 1/11/2024 | 12/5/2024 |  | 372592 | 335725 | 33118 | DSF0001034637
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 1/11/2024 | 12/5/2024 |  | 97937 | 70212 | 37391 | DSF0001034637
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 3/5/2021 | 11/22/2022 | 8/25/2022 | 192109 | 351767 | 350253 | DSF0000961143, DSF0001011242, DSF0001011244, DSF0001011245, DSF0001011246
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/21/2022 | 6/12/2023 | 11/14/2023 | 960550 | 878618 | 740438 | DSF0000961143, DSF0001011242, DSF0001011244, DSF0001011245, DSF0001011246
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 12/16/2024 | 6/3/2027 |  | 21612375 | 19803325 | 394215 | DSF0000961143, DSF0001011242, DSF0001011244, DSF0001011245, DSF0001011246
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 12/16/2024 | 6/3/2027 |  | 1344770 | 145690 | 145379 | DSF0000961143, DSF0001011242, DSF0001011244, DSF0001011245, DSF0001011246
14 | K120 | P.S. 120 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 264213 | 0 | DSF0001085980
14 | K120 | P.S. 120 - BROOKLYN | DOE - RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 114000 | 0 | DSF0001113921
14 | K120 | P.S. 120 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 6/1/2018 | DOES |  | DOES | 185158 | 0 | DSF0000865965
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 6/28/2023 | 11/14/2023 | 12/15/2023 | 54028 | 230697 | 203816 | DSF0001062004, DSF0001089744, DSF0001089747
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 12/19/2023 | 5/21/2024 | 5/9/2024 | 267615 | 385391 | 265224 | DSF0001062004, DSF0001089744, DSF0001089747
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | In-Progress | 10/15/2024 | 4/2/2027 |  | 5802600 | 5330808 | 106909 | DSF0001062004, DSF0001089744, DSF0001089747
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | In-Progress | 10/15/2024 | 4/2/2027 |  | 397166 | 95046 | 93488 | DSF0001062004, DSF0001089744, DSF0001089747
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113569
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113569
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113569
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113569
14 | K126 | J.H.S. 126 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0 | DSF0001112575
14 | K126 | J.H.S. 126 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0 | DSF0001112574
14 | K126 | J.H.S. 126 - BROOKLYN | DOE - Skilled Trades | ACCESSIBILITY | Construction | Complete | 2/21/2023 | DOES | 2/21/2023 | DOES | 304208 |  | SCA0000070970
14 | K126 | J.H.S. 126 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/26/2024 | DOES | 8/16/2024 | DOES | 65832 |  | DSF0001084736
14 | K132 | P.S. 132 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/30/2024 | 11/29/2024 | 9/4/2024 | 4333 | 1058 | 1058 | DSF0001087397
14 | K132 | P.S. 132 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 9/4/2024 | 3/5/2025 |  | 19497 | 19497 | 4233 | DSF0001087397
14 | K132 | P.S. 132 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 251292 | 251292 | 0 | DSF0001087397
14 | K132 | P.S. 132 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 46576 | 46576 | 314 | DSF0001087397
14 | K132 | P.S. 132 - BROOKLYN | SCA Emergency Response | EMERGENCY- SWB @ K132 | Construction | In-Progress | 3/18/2024 | EMER |  | EMER |  | 0 | SCA0000072825
14 | K132 | P.S. 132 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 153000 | 0 | DSF0001085989
14 | K132 | P.S. 132 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/15/2021 | DOES |  | DOES | 61741 | 0 | DSF0001008986
14 | K132 | P.S. 132 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/8/2024 | DOES | 11/12/2024 | DOES | 65832 | 9704 | DSF0001084053
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | ELECTRICAL SERVICE ROOM | Scope | Complete | 5/30/2019 | 9/30/2019 | 2/5/2020 | 10500 | 43113 | 43113 | DSF0000893060
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | ELECTRICAL SERVICE ROOM | Design | Complete | 2/6/2020 | 7/8/2020 | 10/27/2021 | 52500 | 92379 | 91179 | DSF0000893060
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | ELECTRICAL SERVICE ROOM | Construction | PNS | PNS | PNS | PNS | 1181250 | 1181250 | 1654 | DSF0000893060
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | ELECTRICAL SERVICE ROOM | CM,F&E | PNS | PNS | PNS | PNS | 73500 | 73500 | 19213 | DSF0000893060
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | FLOOR REPLACEMENT | Scope | Complete | 4/26/2023 | 9/27/2023 | 1/12/2024 | 7115 | 18102 | 18102 | DSF0001062249
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | FLOOR REPLACEMENT | Design | In-Progress | 1/25/2024 | 6/10/2024 |  | 32017 | 33816 | 11676 | DSF0001062249
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | FLOOR REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 412663 | 412663 | 36756 | DSF0001062249
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | FLOOR REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 76485 | 76485 | 31435 | DSF0001062249
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/23/2024 | 11/21/2024 | 7/30/2024 | 4171 | 1494 | 1494 | DSF0001087401
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/30/2024 | 1/28/2025 |  | 18769 | 18769 | 5977 | DSF0001087401
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 241912 | 241912 | 0 | DSF0001087401
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 44837 | 44837 | 2103 | DSF0001087401
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913225
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 102000 | 102000 | 0 | DSF0000913225
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1496000 | 1496000 | 0 | DSF0000913225
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 102000 | 102000 | 0 | DSF0000913225
14 | K147 | P.S. 147 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES LOCATED IN ROOM 412 CE BRIAN SCHETTINO 718-571-6621 | Construction | Complete | 9/17/2024 | IEH | 10/19/2024 | IEH | 0 | 0 | SCA0000073386
14 | K147 | P.S. 147 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001085995
14 | K147 | YOUNG WOMEN'S LEADERSHIP SCHOOL - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112585
14 | K147 | P.S. 147 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001112586
14 | K147 | P.S. 147 - BROOKLYN | DOE - RESOA | FY16 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/19/2017 | DOER |  | DOER | 677657 | 0 | DSF0000822304
14 | K147 | P.S. 147 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 7/14/2023 | DOER | 8/21/2023 | DOER | 230667 | 2181 | DSF0001033019
14 | K147 | YOUNG WOMEN'S LEADERSHIP SCHOOL - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/2/2024 | DOER |  | DOER | 150000 | 0 | DSF0001085994
14 | K148 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2/24/2021 | 7/9/2021 | 7/13/2021 | 150490 | 149617 | 149617 | DSF0001008652, DSF0001011574
14 | K148 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 7/22/2021 | 1/11/2022 | 10/12/2022 | 752450 | 707473 | 615193 | DSF0001008652, DSF0001011574
14 | K148 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 11/15/2023 | 4/2/2026 |  | 16930125 | 15524301 | 3524768 | DSF0001008652, DSF0001011574
14 | K148 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 11/15/2023 | 4/2/2026 |  | 1053430 | 732913 | 544441 | DSF0001008652, DSF0001011574
14 | K148 | K373 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR DAMAGED PLASTER | Construction | Complete | 8/28/2024 | IEH | 9/17/2024 | IEH | 0 | 0 | SCA0000073332
14 | K148 | K373 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE PIPE INSULATION IN BOILER ROOM. 30 LINEAR FT MARKED IN RED LOCATION: BOILER RO | Construction | Complete | 10/15/2024 | IEH | 10/29/2024 | IEH | 0 | 0 | SCA0000073499
14 | K148 | K373 SPED - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | Complete | 8/9/2019 | DOER | 12/28/2020 | DOER | 240201 | 8731 | DSF0000890656
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS | Scope | Complete | 6/4/2019 | 10/3/2019 | 12/18/2019 | 138929 | 156993 | 156977 | DSF0000986968, DSF0000938508, DSF0000938505, DSF0000938507
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS | Design | Complete | 1/14/2020 | 6/15/2020 | 3/30/2021 | 694646 | 441268 | 430029 | DSF0000986968, DSF0000938508, DSF0000938505, DSF0000938507
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS | Construction | PNS | PNS | PNS | PNS | 15629537 | 15629537 | 369049 | DSF0000986968, DSF0000938508, DSF0000938505, DSF0000938507
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 972505 | 972505 | 121023 | DSF0000986968, DSF0000938508, DSF0000938505, DSF0000938507
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/15/2023 | 10/16/2023 | 10/10/2023 | 10583 | 19497 | 19497 | DSF0001083802
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/12/2023 | 3/12/2024 | 4/29/2024 | 47621 | 108919 | 72160 | DSF0001083802
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/18/2024 | 10/22/2025 |  | 613786 | 550943 | 7103 | DSF0001083802
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/18/2024 | 10/22/2025 |  | 113762 | 73818 | 16672 | DSF0001083802
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/13/2023 | 7/12/2023 | 3/21/2023 | 5508 | 1394 | 1394 | DSF0001034641
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/2/2023 | 24786 | 5577 | 5577 | DSF0001034641
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/1/2023 | 9/25/2024 |  | 319464 | 283856 | 240637 | DSF0001034641
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/1/2023 | 9/25/2024 |  | 125311 | 100603 | 92961 | DSF0001034641
14 | K157 | P.S. 157 - BROOKLYN | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON DAMAGED PIPE INSULATION IN ROOM 202 APPROXIMATELY 12 LF OF D | Construction | Complete | 8/16/2024 | IEH | 8/23/2024 | IEH | 0 | 0 | SCA0000073294
14 | K157 | P.S. 157 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/20/2023 | DOEL |  | DOEL | 104804 | 74804
14 | K157 | P.S. 157 - BROOKLYN | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113810
14 | K157 | P.S. 157 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/24/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084596
14 | K196 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Scope | Complete | 8/12/2020 | 12/11/2020 | 2/18/2021 | 35350 | 27177 | 12431 | DSF0000961079, DSF0000987655
14 | K196 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Design | Complete | 3/1/2021 | 8/6/2021 | 9/10/2021 | 169952 | 162528 | 143449 | DSF0000961079, DSF0000987655
14 | K196 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Construction | In-Progress | 9/5/2023 | 9/3/2024 |  | 3235677 | 3277117 | 1613737 | DSF0000961079, DSF0000987655
14 | K196 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | CM,F&E | In-Progress | 9/5/2023 | 9/3/2024 |  | 298459 | 194857 | 190035 | DSF0000961079, DSF0000987655
14 | K196 | I.S. 582 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/8/2023 | 4/11/2024 | 6/6/2024 | 0 | 15799 | 15799 | DSF0001086019
14 | K196 | I.S. 582 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 6/12/2024 | 11/14/2024 | 10/25/2024 | 105000 | 44028 | 24500 | DSF0001086019
14 | K196 | I.S. 582 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1540000 | 1540000 | 35149 | DSF0001086019
14 | K196 | I.S. 582 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 105000 | 105000 | 6817 | DSF0001086019
14 | K196 | I.S. 582 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001033108
14 | K196 | P.S. 196 - BROOKLYN | DOE - RESOA | FY12 RESO A- LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0000732437
14 | K196 | I.S. 582 - BROOKLYN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/30/2021 | DOER |  | DOER | 353738 | 0 | DSF0000913238
14 | K196 | P.S. 196 - BROOKLYN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 2/24/2022 | DOER |  | DOER | 158062 | 0 | DSF0001008415
14 | K196 | P.S. 196 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 114095 | 0 | DSF0001035466
14 | K196 | P.S. 196 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086020
14 | K196 | P.S. 196 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/15/2024 | DOES | 8/23/2024 | DOES | 65832 |  | DSF0001084087
14 | K196 | I.S. 582 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/15/2024 | DOES |  | DOES | 513487 | 0 | DSF0001085720
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP | PARAPETS | Scope | Complete | 12/19/2023 | 5/6/2024 | 4/22/2024 | 4053 | 26398 | 22556 | DSF0001064233
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP | PARAPETS | Design | Complete | 5/7/2024 | 10/8/2024 | 12/18/2024 | 16212 | 36034 | 22613 | DSF0001064233
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP | PARAPETS | Construction | PNS | PNS | PNS | PNS | 233042 | 233042 | 6663 | DSF0001064233
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP | PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 59780 | 59780 | 22352 | DSF0001064233
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP RESOA | FY19 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Scope | Complete | 2/26/2019 | 6/2/2021 | 5/17/2021 | 0 | 33121 | 33121 | DSF0000890770, DSF0000912622
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP RESOA | FY19 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Design | Complete | 5/26/2021 | 10/1/2021 | 11/16/2021 | 35239 | 50698 | 50698 | DSF0000890770, DSF0000912622
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP RESOA | FY19 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Construction | Complete | 7/7/2022 | 5/2/2023 | 5/2/2023 | 516837 | 420912 | 360839 | DSF0000890770, DSF0000912622
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP RESOA | FY19 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | CM,F&E | Complete | 7/7/2022 | 5/2/2023 | 5/2/2023 | 107875 | 131799 | 130722 | DSF0000890770, DSF0000912622
14 | K250 | P.S. 250 - BROOKLYN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001083941
14 | K250 | P.S. 250 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001112649
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2/7/2023 | 6/23/2023 | 7/31/2023 | 58066 | 86530 | 84797 | DSF0001083705, DSF0001064365
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | In-Progress | 8/15/2023 | 2/21/2024 |  | 283467 | 283467 | 102218 | DSF0001083705, DSF0001064365
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 5784267 | 5784267 | 222367 | DSF0001083705, DSF0001064365
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 457942 | 457942 | 74946 | DSF0001083705, DSF0001064365
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/14/2023 | 12/13/2023 | 10/16/2023 | 79440 | 98399 | 98386 | DSF0001064369, DSF0001087256
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 10/20/2023 | 6/11/2024 | 4/5/2024 | 397197 | 277576 | 274606 | DSF0001064369, DSF0001087256
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 8936920 | 8936920 | 92412 | DSF0001064369, DSF0001087256
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 556075 | 556075 | 50077 | DSF0001064369, DSF0001087256
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ANSUL/FIRE SUPPRESSION SYSTEM | Scope | Complete | 9/5/2024 | 9/5/2024 | 9/5/2024 | 22785 | 22682 | 1102 | DSF0001113453
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ANSUL/FIRE SUPPRESSION SYSTEM | Design | In-Progress | 9/5/2024 | 2/10/2025 |  | 106328 | 106328 | 4411 | DSF0001113453
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ANSUL/FIRE SUPPRESSION SYSTEM | Construction | PNS | PNS | PNS | PNS | 1686061 | 1686061 | 0 | DSF0001113453
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ANSUL/FIRE SUPPRESSION SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 167087 | 167087 | 19045 | DSF0001113453
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/28/2023 | 12/29/2023 | 8/30/2023 | 4154 | 6008 | 6008 | DSF0001035013
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/30/2023 | 2/29/2024 | 12/12/2023 | 18693 | 24032 | 24032 | DSF0001035013
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/9/2024 | 4/3/2025 |  | 240932 | 214899 | 145485 | DSF0001035013
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/9/2024 | 4/3/2025 |  | 107730 | 90946 | 39569 | DSF0001035013
14 | K257 | P.S. 257 - BROOKLYN | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035503
14 | K257 | P.S. 257 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086048
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | Scope | Complete | 6/9/2022 | 12/5/2022 | 9/28/2022 | 155844 | 170650 | 134605 | DSF0001014264, DSF0001014265, DSF0001014266, DSF0001014273, DSF0001036328
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | Design | Complete | 10/19/2022 | 6/12/2023 | 4/4/2023 | 775746 | 345613 | 345533 | DSF0001014264, DSF0001014265, DSF0001014266, DSF0001014273, DSF0001036328
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | Construction | In-Progress | 9/5/2023 | 9/3/2025 |  | 17153786 | 15888103 | 11011308 | DSF0001014264, DSF0001014265, DSF0001014266, DSF0001014273, DSF0001036328
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | CM,F&E | In-Progress | 9/5/2023 | 9/3/2025 |  | 1116963 | 423518 | 418028 | DSF0001014264, DSF0001014265, DSF0001014266, DSF0001014273, DSF0001036328
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 9/27/2023 | 1/31/2024 | 10/10/2023 | 4404 | 1263 | 1263 | DSF0001035016
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 10/10/2023 | 4/8/2024 | 12/12/2023 | 19818 | 5053 | 5053 | DSF0001035016
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/9/2024 | 4/3/2025 |  | 255432 | 229036 | 73022 | DSF0001035016
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/9/2024 | 4/3/2025 |  | 78059 | 62420 | 36544 | DSF0001035016
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/13/2023 | 4/16/2024 | 5/7/2024 | 0 | 21592 | 5300 | DSF0001086073
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | Complete | 5/8/2024 | 9/24/2024 | 9/13/2024 | 54000 | 74299 | 25619 | DSF0001086073
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 792000 | 792000 | 0 | DSF0001086073
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 54000 | 54000 | 11454 | DSF0001086073
14 | K297 | P.S. 297 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/2/2019 | DOER |  | DOER | 151045 | 0 | DSF0000890655
14 | K297 | P.S. 297 - BROOKLYN | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001087226
14 | K318 | I.S. 318 - BROOKLYN | SCA Furniture & Equipment | RESO A MOBILE STEM CARTS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 0 | DSF0001033061
14 | K318 | I.S. 318 - BROOKLYN | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/22/2023 | DOER |  | DOER | 360845 | 0 | DSF0000913270
14 | K318 | I.S. 318 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/15/2016 | DOES |  | DOES | 152595 | 0 | DSF0000782769
14 | K318 | I.S. 318 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 2/27/2023 | DOES | 11/6/2023 | DOES | 642110 | 591602 | DSF0001035144
14 | K318 | I.S. 318 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/15/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001084766
14 | K319 | P.S. 319 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035539
14 | K319 | P.S. 319 - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 152030 | 0 | DSF0001008423
14 | K319 | P.S. 319 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112684
14 | K319 | P.S. 319 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/28/2024 | DOES | 8/27/2024 | DOES | 65832 | 9337 | DSF0001084151
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 6/4/2021 | 10/28/2021 | 1/26/2022 | 113560 | 137335 | 137335 | DSF0001008881
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 3/8/2022 | 8/22/2022 | 5/9/2023 | 567800 | 440568 | 359088 | DSF0001008881
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 9/5/2023 | 9/3/2025 |  | 12775500 | 11703218 | 5532303 | DSF0001008881
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 9/5/2023 | 9/3/2025 |  | 796450 | 542370 | 535288 | DSF0001008881
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/14/2023 | 7/13/2023 | 3/21/2023 | 6092 | 1913 | 1913 | DSF0001034652
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/2/2023 | 27414 | 7651 | 7651 | DSF0001034652
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/1/2023 | 9/25/2024 |  | 353336 | 319049 | 269993 | DSF0001034652
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/1/2023 | 9/25/2024 |  | 208089 | 177951 | 97708 | DSF0001034652
14 | K380 | P.S. 380 - BROOKLYN | SCA IEH | PO18-PERFORM QC SUPPLEMENTAL TESTING ON HALLWAY CEILING LOCATED OUTSIDE OF RM 120 ABATE AND REPAIR A | Construction | Complete | 9/23/2024 | IEH | 12/4/2024 | IEH | 0 | 0 | SCA0000073420
14 | K380 | P.S. 380 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112696
14 | K380 | P.S. 380 - BROOKLYN | DOE - RESOA | FY14 RESO A RENOVATE OUTDOOR DIGITAL SIGNAGE | Construction | In-Progress | 8/25/2014 | DOER |  | DOER | 30300 | 0 | DSF0000798859
14 | K380 | P.S. 380 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/2/2019 | DOER |  | DOER | 353999 | 0 | DSF0000890657
14 | K380 | P.S. 380 - BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/17/2024 | DOER |  | DOER | 249782 | 0 | DSF0001086105
14 | K380 | K141 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 240000 | 0 | DSF0001112697
14 | K380 | P.S. 380 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/10/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084165
14 | K450 | PROGRESS HS - K | SCA IEH | PO18-PLEASE DRILL 3/4'HOLE THROUGH FOURTH FLOOR NEXT TO ROOM# 415 | Construction | Complete | 8/27/2024 | IEH | 9/29/2024 | IEH | 0 | 0 | SCA0000073324
14 | K450 | PROGRESS HS - K | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 60000 | DSF0001086127
14 | K450 | HS OF ENTERPRISE, BUS. & TECH. - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 7/5/2024 | DIIR | 50000 | 50000 | DSF0001086124
14 | K450 | PROGRESS HS - K | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 235000 | 0 | DSF0000890792
14 | K450 | HS OF ENTERPRISE, BUS. & TECH. - K | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 90000 | 0 | DSF0001086126
14 | K450 | PROGRESS HS - K | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112713
14 | K451 | PROGRESS HS - K | DOE - RESOA | FY18 RESO A ATHLETIC FIELDS | Construction | In-Progress | 2/14/2020 | DOER |  | DOER | 10065740 | 0 | DSF0000866325
14 | K610 | A-TECH HIGH SCHOOL - K | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADE | Construction | Complete | 5/2/2022 | DOER | 12/18/2023 | DOER | 139575 | 13558 | DSF0000913180
14 | K610 | A-TECH HIGH SCHOOL - K | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 9/20/2023 | DOES |  | DOES | 245705 | 0 | DSF0001034233
14 | K610 | A-TECH HIGH SCHOOL - K | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/1/2022 | DOES |  | DOES | 279434 | 0 | DSF0001034416
14 | K610 | A-TECH HIGH SCHOOL - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/24/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084925
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | SCA CIP | FIRE ALARM SYSTEM | Scope | Complete | 7/22/2021 | 10/21/2021 | 10/4/2022 | 21607 | 63822 | 63822 | DSF0000990915
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | SCA CIP | FIRE ALARM SYSTEM | Design | Complete | 10/20/2022 | 4/26/2023 | 5/8/2023 | 108034 | 159098 | 155868 | DSF0000990915
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | SCA CIP | FIRE ALARM SYSTEM | Construction | PNS | PNS | PNS | PNS | 2430765 | 2430765 | 292417 | DSF0000990915
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | SCA CIP | FIRE ALARM SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 151248 | 151248 | 119973 | DSF0000990915
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | SCA IEH | PO18-ABATE FOUR MUDDED FITTINGS ON OIL PIPING AT BOILER ROOM CEILING. PIPING IS MARKED WITH GREEN SP | Construction | Complete | 7/9/2024 | IEH | 9/29/2024 | IEH | 0 | 0 | SCA0000073123
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | In-Progress | 12/21/2021 |  |  | 425000 | 425000 | 401664 | DSF0000961256
14 | K650 | WILLIAMSBURG HS FOR ARCH & DES-K | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/30/2023 | DOER |  | DOER | 516505 | 0 | DSF0001008216
14 | K650 | WILLIAMSBURG HS FOR ARCH & DES-K | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001033582
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 512708 | 0 | DSF0001086144
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 1/13/2023 | DOES | 3/22/2024 | DOES | 418781 | 256095 | DSF0000960850
14 | K778 | EL PUENTE ACADEMY - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 4/19/2024 | IEH |  | IEH | 0 | 0 | SCA0000072951
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 6/16/2022 | 11/1/2022 | 12/28/2022 | 91123 | 125407 | 125407 | DSF0001034906, DSF0001083827
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/28/2022 | 6/15/2023 | 6/15/2023 | 455615 | 414911 | 312441 | DSF0001034906, DSF0001083827
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 10251339 | 10251339 | 156338 | DSF0001034906, DSF0001083827
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 637862 | 637862 | 49447 | DSF0001034906, DSF0001083827
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/30/2022 | 11/16/2022 | 12/28/2022 | 33712 | 48878 | 48878 | DSF0001009409, DSF0001009410, DSF0001009411
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/29/2022 | 6/1/2023 | 6/15/2023 | 164498 | 162417 | 133672 | DSF0001009409, DSF0001009410, DSF0001009411
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 3349946 | 3349946 | 109418 | DSF0001009409, DSF0001009410, DSF0001009411
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 266440 | 266440 | 19924 | DSF0001009409, DSF0001009410, DSF0001009411
15 | K001 | P.S. 1 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001085930
15 | K001 | P.S. 1 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500000 | 0 | DSF0001112510
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 6/3/2022 | 9/15/2022 | 9/15/2022 | 1333540 | 911738 | 911634 | DSF0000890667
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 9/16/2022 | 4/5/2023 | 4/28/2023 | 6000930 | 3518252 | 1998913 | DSF0000890667
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 9/11/2023 | 9/3/2026 |  | 75678395 | 67077864 | 13485153 | DSF0000890667
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 9/11/2023 | 9/3/2026 |  | 10668320 | 5058209 | 1219003 | DSF0000890667
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 9/8/2022 | 9/8/2022 | 9/8/2022 | 78880 | 65266 | 65266 | DSF0000890667
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 9/21/2022 | 2/14/2023 | 2/24/2023 | 394400 | 188678 | 186050 | DSF0000890667
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | Construction | In-Progress | 3/6/2023 | 6/3/2023 |  | 8874000 | 8319772 | 8311146 | DSF0000890667
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 3/6/2023 | 6/3/2023 |  | 552160 | 395044 | 310940 | DSF0000890667
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/2/2020 | 11/30/2020 | 10/8/2020 | 166640 | 301302 | 301302 | DSF0000936536, DSF0000936532, DSF0000936534, DSF0000936535, DSF0000936537
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 10/16/2020 | 6/15/2021 | 4/23/2021 | 833202 | 549171 | 548546 | DSF0000936536, DSF0000936532, DSF0000936534, DSF0000936535, DSF0000936537
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 8/16/2021 | 8/15/2023 |  | 18747001 | 17729277 | 16883158 | DSF0000936536, DSF0000936532, DSF0000936534, DSF0000936535, DSF0000936537
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/16/2021 | 8/15/2023 |  | 1166479 | 639462 | 634197 | DSF0000936536, DSF0000936532, DSF0000936534, DSF0000936535, DSF0000936537
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/12/2024 | 5/13/2024 | 3/22/2024 | 3769 | 179 | 179 | DSF0001087365
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/22/2024 | 9/17/2024 | 7/16/2024 | 16961 | 717 | 717 | DSF0001087365
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/16/2024 | 11/10/2025 |  | 218602 | 197191 | 2941 | DSF0001087365
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/16/2024 | 11/10/2025 |  | 44257 | 27499 | 3286 | DSF0001087365
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112515
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001112515
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1760000 | 1760000 | 0 | DSF0001112515
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001112515
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113560
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113560
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113560
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113560
15 | K010 | P.S. 10 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/26/2024 | DIIR |  | DIIR | 100000 | 0 | DSF0001033443
15 | K010 | P.S. 10 - BROOKLYN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/7/2022 | DOER |  | DOER | 80055 | 0 | DSF0001008250
15 | K010 | P.S. 10 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 7/6/2022 | DOER |  | DOER | 101320 | 0 | DSF0001008255
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | Scope | Complete | 11/7/2018 | 11/6/2019 | 11/12/2019 | 179240 | 149812 | 149811 | DSF0000868633, DSF0000868634, DSF0000868635, DSF0000912348
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/13/2019 | 5/1/2020 | 4/2/2021 | 896202 | 729469 | 719604 | DSF0000868633, DSF0000868634, DSF0000868635, DSF0000912348
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 8/16/2021 | 8/15/2023 |  | 20164576 | 23830948 | 12810647 | DSF0000868633, DSF0000868634, DSF0000868635, DSF0000912348
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 8/16/2021 | 8/15/2023 |  | 1254685 | 966851 | 917925 | DSF0000868633, DSF0000868634, DSF0000868635, DSF0000912348
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/13/2023 | 11/13/2023 | 8/2/2023 | 3120 | 2253 | 2253 | DSF0001035003
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/8/2023 | 14040 | 9010 | 9010 | DSF0001035003
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/12/2024 | 5/7/2025 |  | 180960 | 164231 | 2681 | DSF0001035003
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/12/2024 | 5/7/2025 |  | 57171 | 46785 | 29937 | DSF0001035003
15 | K015 | P.S. 15 - BROOKLYN | Fast Track Projects | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 185213 | 120382 | DSF0000913200
15 | K015 | P.S. 15 - BROOKLYN | Fast Track Projects | GAS LEAK | Construction | In-Progress | 4/15/2019 | FTK |  | FTK | 37984 | 37984 | SCA0000056166
15 | K015 | P.S. 15 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112520
15 | K015 | P.S. 15 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | Complete | 4/19/2019 | DOER | 12/30/2020 | DOER | 224393 | 10795 | DSF0000890647
15 | K015 | P.S. 15 - BROOKLYN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 62427 | 0 | DSF0001085941
15 | K015 | P.S. 15 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/19/2024 | DOES | 65832 | 19568 | DSF0001083994
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | Scope | Complete | 10/16/2018 | 3/6/2019 | 1/22/2019 | 29395 | 24677 | 24677 | DSF0000868795, DSF0000891548
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | Design | Complete | 1/30/2019 | 7/1/2019 | 5/6/2020 | 132281 | 188960 | 187999 | DSF0000868795, DSF0000891548
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | Construction | In-Progress | 7/19/2021 | 10/11/2022 |  | 1704952 | 1445928 | 840128 | DSF0000868795, DSF0000891548
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | CM,F&E | In-Progress | 7/19/2021 | 10/11/2022 |  | 316004 | 160934 | 159973 | DSF0000868795, DSF0000891548
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/18/2023 | 11/16/2023 | 8/2/2023 | 3880 | 1908 | 1908 | DSF0001035006
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/8/2023 | 17460 | 7633 | 7633 | DSF0001035006
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/12/2024 | 5/7/2025 |  | 225040 | 199550 | 0 | DSF0001035006
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/12/2024 | 5/7/2025 |  | 64637 | 49127 | 28175 | DSF0001035006
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 2/3/2023 | 5/4/2023 |  | 0 | 78363 | 78363 | DSF0001035378
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 9708 | 9708 | DSF0001035378
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 2041593 | 0 | DSF0001035378
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 139200 | 2525 | DSF0001035378
15 | K024 | P.S. 24 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 9/1/2021 | DIIR |  | DIIR | 150000 | 0 | DSF0001009283
15 | K024 | P.S. 24 - BROOKLYN | DOE - RESOA | FY08 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 93750 | 0 | DSF0000545188
15 | K024 | P.S. 24 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 6/30/2022 | DOER |  | DOER | 283492 | 0 | DSF0001008256
15 | K024 | P.S. 24 - BROOKLYN | DOE - RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0 | DSF0001085945
15 | K024 | P.S. 24 - BROOKLYN | DOE - RESOA | FY24 RESO A LEARNING GARDEN | Construction | PNS | PNS | PNS | PNS | DOER | 306047 | 0 | DSF0001085946
15 | K024 | P.S. 24 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 681061 | 0 | DSF0000912200
15 | K024 | P.S. 24 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/9/2024 | DOES | 7/16/2024 | DOES | 50832 | 8802 | DSF0001084001
15 | K027 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 10/18/2018 | 4/18/2019 | 9/11/2019 | 10680 | 20211 | 20211 | DSF0000888997
15 | K027 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 9/25/2019 | 3/25/2020 | 4/13/2020 | 48060 | 57187 | 57187 | DSF0000888997
15 | K027 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 7/23/2021 | 7/22/2022 |  | 619440 | 553810 | 326737 | DSF0000888997
15 | K027 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 7/23/2021 | 7/22/2022 |  | 114810 | 81199 | 75688 | DSF0000888997
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/3/2022 | 11/29/2022 | 9/26/2022 | 150072 | 120354 | 109751 | DSF0001009924, DSF0001009925, DSF0001009926, DSF0001036329
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 9/30/2022 | 6/12/2023 | 4/14/2023 | 750365 | 379936 | 373979 | DSF0001009924, DSF0001009925, DSF0001009926, DSF0001036329
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 11/3/2023 | 11/1/2025 |  | 16883213 | 15485554 | 4999777 | DSF0001009924, DSF0001009925, DSF0001009926, DSF0001036329
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 11/3/2023 | 11/1/2025 |  | 1057830 | 260331 | 245623 | DSF0001009924, DSF0001009925, DSF0001009926, DSF0001036329
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 6/10/2022 | DOER |  | DOER | 260453 | 0 | DSF0001008247
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 255092 | 0 | DSF0001008252
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 157180 | 0 | DSF0001008253
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 200057 | 0 | DSF0001033124
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 7/1/2024 | DOER | 8/16/2024 | DOER | 70012 |  | DSF0001035381
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001085324
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/15/2022 | DOES |  | DOES | 64929 | 0 | DSF0001009145
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/5/2024 | DOES | 12/16/2024 | DOES | 65832 |  | DSF0001084874
15 | K029 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 5/12/2022 | 9/27/2022 | 11/14/2022 | 158750 | 196578 | 196578 | DSF0001034905, DSF0001060620
15 | K029 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/7/2022 | 5/25/2023 | 5/12/2023 | 793750 | 636618 | 526216 | DSF0001034905, DSF0001060620
15 | K029 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 8/5/2024 | 8/4/2026 |  | 17859375 | 16169347 | 647554 | DSF0001034905, DSF0001060620
15 | K029 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 8/5/2024 | 8/4/2026 |  | 1111250 | 98150 | 94659 | DSF0001034905, DSF0001060620
15 | K029 | P.S. 29 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE THE FOLLOWING FLOORS CAFE LOBBY 201B PLAY AREA 1 2030 PLAY AREA 2 2031 STUDEN | Construction | In-Progress | 9/22/2023 | IEH |  | IEH | 0 | 0 | SCA0000072342
15 | K029 | P.S. 29 - BROOKLYN | SCA IEH | PO18-PLEASE FERFORM ACM TESTING ON LOOSE FLOOR TILE IN STAIRCASE H AND I , AND ROOM 500 | Construction | In-Progress | 12/29/2023 | IEH |  | IEH | 0 | 0 | SCA0000072604
15 | K029 | P.S. 29 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR BY RADIATOR IN 204, 500 SCRAPE SOLID SUBSTRATE ON WALLS IN ROOM 500 | Construction | Complete | 7/17/2024 | IEH | 8/8/2024 | IEH | 0 | 0 | SCA0000073140
15 | K029 | P.S. 29 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOOR APP. 8X10 NEAR RADIATOR IN ROOM 500 | Construction | Complete | 8/22/2024 | IEH | 8/23/2024 | IEH | 0 | 0 | SCA0000073309
15 | K029 | P.S. 29 - BROOKLYN | Fast Track Projects | LSP WATER BOOSTER PUMP SET REPLACEMENT | Construction | In-Progress | 6/9/2023 | FTK |  | FTK | 206874 | 200012 | DSF0001060632
15 | K029 | P.S. 29 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0 | DSF0001112533
15 | K029 | P.S. 29 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/22/2024 | DOER |  | DOER | 750000 | 0 | DSF0001085948
15 | K032 | P.S. 32 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 10/8/2024 | DIIR | 249124 | 249124 | DSF0001085951
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 3/18/2022 | 3/18/2022 | 3/18/2022 | 0 | 0 | 0 | DSF0001021093
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 3/18/2022 | 4/18/2022 | 3/18/2022 | 0 | 0 | 0 | DSF0001021093
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Construction | PNS | PNS | PNS | PNS | 1 | 1 | 398838 | DSF0001021093
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 88093 | DSF0001021093
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/15/2024 | 7/16/2024 | 4/1/2024 | 3831 | 502 | 502 | DSF0001087375
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/1/2024 | 9/25/2024 | 7/16/2024 | 17240 | 2008 | 2008 | DSF0001087375
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/16/2024 | 11/10/2025 |  | 222198 | 204412 | 6584 | DSF0001087375
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/16/2024 | 11/10/2025 |  | 41183 | 32273 | 11465 | DSF0001087375
15 | K038 | P.S. 38 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 286097 | 0 | DSF0000959761
15 | K038 | P.S. 38 - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001112538
15 | K039 | P.S. 39 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Scope | Complete | 1/5/2024 | 4/5/2024 | 4/16/2024 | 0 | 1713 | 1713 | DSF0001085952
15 | K039 | P.S. 39 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Design | Complete | 5/9/2024 | 11/13/2024 | 11/13/2024 | 18000 | 6851 | 6851 | DSF0001085952
15 | K039 | P.S. 39 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | 264000 | 264000 | 19973 | DSF0001085952
15 | K039 | P.S. 39 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 18000 | 18000 | 10694 | DSF0001085952
15 | K039 | P.S. 39 - BROOKLYN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 8/31/2023 | DOER |  | DOER | 42783 | 0 | DSF0001034977
15 | K051 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/14/2022 | 1/18/2023 | 12/21/2022 | 4120 | 3008 | 3008 | DSF0001034648
15 | K051 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/21/2022 | 6/20/2023 | 2/22/2023 | 18540 | 12034 | 12034 | DSF0001034648
15 | K051 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 238960 | 215194 | 189892 | DSF0001034648
15 | K051 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 119423 | 109485 | 108224 | DSF0001034648
15 | K051 | I.S. 51 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 50000 | 40273 | DSF0001033451
15 | K051 | I.S. 51 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 130921 | 0 | DSF0001035398
15 | K051 | I.S. 51 - BROOKLYN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175667 | 0 | DSF0001085958
15 | K051 | I.S. 51 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/18/2024 | DOES | 9/26/2024 | DOES | 65832 |  | DSF0001084727
15 | K058 | P.S. 58 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/8/2021 | 8/9/2021 | 1/18/2022 | 0 | 35948 | 35948 | DSF0000913207, DSF0000913208
15 | K058 | P.S. 58 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 1/18/2022 | 4/22/2022 | 4/8/2022 | 64281 | 94991 | 94991 | DSF0000913207, DSF0000913208
15 | K058 | P.S. 58 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 3/31/2023 | 2/23/2024 |  | 942777 | 891455 | 91350 | DSF0000913207, DSF0000913208
15 | K058 | P.S. 58 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 3/31/2023 | 2/23/2024 |  | 64281 | 85494 | 26927 | DSF0000913207, DSF0000913208
15 | K058 | P.S. 58 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE ACM FLOOR LOC: ROOM 222, 2ND/3RD GRADE CLASSROOM 9 TILES LIFTING, STUDENTS AR | Construction | Complete | 10/3/2024 | IEH | 10/6/2024 | IEH | 0 | 0 | SCA0000073469
15 | K058 | P.S. 58 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 8/13/2021 | DOER | 1/10/2022 | DOER | 134331 | 155396 | DSF0000913040
15 | K058 | P.S. 58 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2024 | DOES |  | DOES | 223789 | 0 | DSF0001008669
15 | K088 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | Scope | Complete | 6/14/2021 | 12/13/2021 | 10/20/2021 | 232199 | 152590 | 152590 | DSF0000985945, DSF0000985946, DSF0000985947, DSF0000985948, DSF0001010717
15 | K088 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | Design | Complete | 11/3/2021 | 6/30/2022 | 4/22/2022 | 1158195 | 497427 | 497427 | DSF0000985945, DSF0000985946, DSF0000985947, DSF0000985948, DSF0001010717
15 | K088 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | Construction | In-Progress | 7/18/2022 | 10/4/2024 |  | 25817295 | 23336325 | 17093764 | DSF0000985945, DSF0000985946, DSF0000985947, DSF0000985948, DSF0001010717
15 | K088 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | CM,F&E | In-Progress | 7/18/2022 | 10/4/2024 |  | 1646382 | 602757 | 601365 | DSF0000985945, DSF0000985946, DSF0000985947, DSF0000985948, DSF0001010717
15 | K088 | I.S. 88 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 230673 | 0 | DSF0000959780
15 | K088 | I.S. 88 - BROOKLYN | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0 | DSF0000961276
15 | K088 | I.S. 88 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/25/2022 | DOER |  | DOER | 222356 | 0 | DSF0001008246
15 | K088 | I.S. 88 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 110000 | 0 | DSF0001033006
15 | K088 | I.S. 88 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/28/2024 | DOES | 11/6/2024 | DOES | 65832 |  | DSF0001084733
15 | K094 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | Scope | Complete | 12/23/2021 | 4/22/2022 | 9/12/2022 | 94564 | 85725 | 80590 | DSF0001010809, DSF0001061494, DSF0001061493
15 | K094 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | Design | Complete | 10/13/2022 | 4/13/2023 | 4/25/2023 | 466664 | 482865 | 311531 | DSF0001010809, DSF0001061494, DSF0001061493
15 | K094 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | Construction | In-Progress | 9/9/2024 | 9/8/2026 |  | 9967662 | 9293112 | 283503 | DSF0001010809, DSF0001061494, DSF0001061493
15 | K094 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | CM,F&E | In-Progress | 9/9/2024 | 9/8/2026 |  | 708094 | 99622 | 99207 | DSF0001010809, DSF0001061494, DSF0001061493
15 | K094 | P.S. 94 - BROOKLYN | SCA IEH | PO18-ABATE CEILING LAYERS FOR ACM LOC: ROOM 111 STAFF WILL BE PAINTING FOR CONVERSION TO MED | Construction | In-Progress | 9/20/2024 | IEH |  | IEH | 0 | 0 | SCA0000073404
15 | K094 | P.S. 94 - BROOKLYN | SCA IEH | PO18-ABATE KITCHEN LOCKER ROOM CEILING AHERA STATES ACM PRESENT FROM PREVIOUS TESTING PEELING PAINT; | Construction | In-Progress | 11/6/2024 | IEH |  | IEH | 0 | 0 | SCA0000073577
15 | K094 | P.S. 94 - BROOKLYN | SCA IEH | PO18-ABATE/REPAIR & CLEANUP FALLEN ACM TILES (2) AND PLASTER LOCATION: FOOD PANTRY, OLD PTA OFFICE, | Construction | Complete | 11/21/2024 | IEH | 11/23/2024 | IEH | 0 | 0 | SCA0000073632
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/20/2022 | DOER |  | DOER | 242297 | 0 | DSF0001008248
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/29/2022 | DOER |  | DOER | 700288 | 0 | DSF0001008254
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 108758 | 0 | DSF0001035411
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001112560
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0 | DSF0001112561
15 | K094 | P.S. 94 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 8/26/2024 | DOES | 65832 | 17162 | DSF0001084031
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/9/2023 | 5/10/2023 | 5/8/2023 | 0 | 24502 | 24502 | DSF0001035420
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 9/14/2023 | 2/2/2024 | 5/6/2024 | 29520 | 44266 | 42236 | DSF0001035420
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 432956 | 432956 | 8059 | DSF0001035420
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 29520 | 29520 | 19238 | DSF0001035420
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 9/14/2023 | 12/18/2023 | 2/7/2024 | 0 | 465 | 465 | DSF0001035421
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2/9/2024 | 6/12/2024 | 5/6/2024 | 480 | 480 | 1983 | DSF0001035421
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 7044 | 7044 | 1759 | DSF0001035421
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 480 | 480 | 5975 | DSF0001035421
15 | K107 | P.S. 107 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112567
15 | K107 | P.S. 107 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/29/2024 | DOES | 8/26/2024 | DOES | 65832 |  | DSF0001084038
15 | K124 | P.S. 124 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN FRONT OF ROOM 202 2 SQFT DAMAGE. PHOTO ATTACHED. LOCATION: 2ND | Construction | In-Progress | 12/12/2024 | IEH |  | IEH | 0 | 0 | SCA0000073707
15 | K124 | P.S. 124 - BROOKLYN | Fast Track Projects | FY24 RESO A CTF ROOM CONVERSION | Construction | PNS | FTK | FTK | FTK | FTK | 123534 | 67918 | DSF0001085983
15 | K124 | P.S. 124 - BROOKLYN | Fast Track Projects | PATH OF TRAVEL RESO A CTF ROOM CONVERSION | Construction | PNS | FTK | FTK | FTK | FTK | 7111 | 0 | DSF0001087009
15 | K124 | P.S. 124 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/28/2024 | DIIR | 11/6/2024 | DIIR | 50000 | 50000 | DSF0001033479
15 | K124 | P.S. 124 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/13/2024 | DIIR | 11/6/2024 | DIIR | 129360 | 129360 | DSF0001035430
15 | K130 | P.S. 130 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM RENOVATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913222
15 | K130 | P.S. 130 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM RENOVATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913222
15 | K130 | P.S. 130 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM RENOVATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913222
15 | K130 | P.S. 130 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM RENOVATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913222
15 | K130 | P.S. 130 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001085987
15 | K130 | P.S. 130 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/10/2024 | DOES | 8/26/2024 | DOES | 65832 | 16070 | DSF0001084051
15 | K131 | P.S. 131 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | In-Progress | 12/10/2024 | 3/13/2025 |  | 647 | 647 | 0 | DSF0001113883
15 | K131 | P.S. 131 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 2589 | 2589 | 0 | DSF0001113883
15 | K131 | P.S. 131 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 37216 | 37216 | 0 | DSF0001113883
15 | K131 | P.S. 131 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 9547 | 9547 | 0 | DSF0001113883
15 | K131 | P.S. 131 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 62500 | 0 | DSF0001033482
15 | K131 | P.S. 131 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 68000 | 68000 | DSF0001085988
15 | K131 | P.S. 131 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112578
15 | K131 | P.S. 131 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001008281
15 | K131 | P.S. 131 - BROOKLYN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/16/2023 | DOER |  | DOER | 505633 | 0 | DSF0001033483
15 | K131 | P.S. 131 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/9/2023 | DOER |  | DOER | 399710 | 0 | DSF0001035434
15 | K131 | P.S. 131 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/15/2022 | DOES |  | DOES | 99547 | 0 | DSF0001008943
15 | K136 | I.S. 821 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE 60SQFT OF DAMAGED FLOOR TILES IN ROOM 103 | Construction | Complete | 7/15/2024 | IEH | 7/19/2024 | IEH | 0 | 0 | SCA0000073138
15 | K136 | I.S. 821 - BROOKLYN | SCA IEH | PO18-ABATE, REPAIR AND REPLACE FLOORS IN ROOM 104 DAMAGE AREA 20SF | Construction | Complete | 7/31/2024 | IEH | 8/18/2024 | IEH | 0 | 0 | SCA0000073218
15 | K136 | I.S. 821 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION IN SOTRAGE ROOM OFF AUDITORIUM STORAGE(SPACE ID 2500C) ALSO SCRAPE CEILIN | Construction | Complete | 12/4/2024 | IEH | 12/7/2024 | IEH | 0 | 0 | SCA0000073663
15 | K136 | I.S. 821 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 150000 | 0 | DSF0000890142
15 | K136 | I.S. 136 - BROOKLYN | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/28/2021 | DOER |  | DOER | 721296 | 0 | DSF0000867217
15 | K136 | I.S. 821 - BROOKLYN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 355266 | 0 | DSF0000890807
15 | K136 | I.S. 821 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 2/21/2023 | DOES | 2/24/2023 | DOES | 387397 | 343967 | DSF0001035145
15 | K136 | I.S. 136 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 8/27/2024 | DOES |  | DOES | 822950 | 0 | DSF0001083758
15 | K136 | I.S. 821 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/27/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084737
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE ALL FLOOR LAYERS FOR ACM SUB FLOORING ACM PER AHEHA / HEAVING, CRUMBLING, AND | Construction | Complete | 7/24/2024 | IEH | 11/22/2024 | IEH | 0 | 0 | SCA0000073171
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE ALL FLOOR LAYERS FOR ACM SUB FLOORING ACM PER AHEHA / HEAVING, CRUMBLING, AND | Construction | Complete | 7/24/2024 | IEH | 9/29/2024 | IEH | 0 | 0 | SCA0000073173
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-ABATE WALLS AND CEILINGS FOR ACM STAIRWELL 3001 EXIT 1 | Construction | Complete | 8/6/2024 | IEH | 8/30/2024 | IEH | 0 | 0 | SCA0000073243
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON WALL AND CEILING PLASTER IN LOC: SPACE ID 5424 20/30% DAMAGE | Construction | In-Progress | 8/7/2024 | IEH |  | IEH | 0 | 0 | SCA0000073259
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON WALL AND CEILING PLASTERS IN ROOM 319 60% DAMAGED | Construction | In-Progress | 8/8/2024 | IEH |  | IEH | 0 | 0 | SCA0000073262
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE APPROX.12 LINEAR FEET OF AIR CELL PIPE INSULATION AND PIPE FITTING PLASTER, FR | Construction | Complete | 11/20/2024 | IEH | 11/27/2024 | IEH | 0 | 0 | SCA0000073625
15 | K142 | I.S. 448 - BROOKLYN | Fast Track Projects | LSP FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/19/2023 | FTK |  | FTK | 340331 | 327590 | DSF0001035561
15 | K142 | I.S. 448 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/21/2024 | DIIR | 11/8/2024 | DIIR | 117586 | 117586 | DSF0001085991
15 | K142 | P.S. 146 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/21/2024 | DIIR | 10/16/2024 | DIIR | 49825 | 49825 | DSF0001085992
15 | K142 | I.S. 448 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112582
15 | K142 | I.S. 448 - BROOKLYN | DOE - RESOA | FY16 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/9/2017 | DOER |  | DOER | 268312 | 0 | DSF0000822275
15 | K142 | I.S. 448 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0 | DSF0001112581
15 | K154 | P.S. 154 - BROOKLYN | SCA CIP | ROOFS | Scope | Complete | 12/19/2023 | 5/6/2024 | 6/25/2024 | 26077 | 40053 | 38623 | DSF0001062393
15 | K154 | P.S. 154 - BROOKLYN | SCA CIP | ROOFS | Design | In-Progress | 7/1/2024 | 12/3/2024 |  | 121693 | 121693 | 36953 | DSF0001062393
15 | K154 | P.S. 154 - BROOKLYN | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 1929706 | 1929706 | 4980 | DSF0001062393
15 | K154 | P.S. 154 - BROOKLYN | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 191232 | 191232 | 31912 | DSF0001062393
15 | K154 | P.S. 154 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 50000 | 44028 | DSF0001086001
15 | K154 | P.S. 154 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/18/2024 | DOER |  | DOER | 222480 | 0 | DSF0001035449
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 7/23/2018 | 12/7/2018 | 11/8/2018 | 87734 | 167125 | 158660 | DSF0000889377, DSF0000893420
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | In-Progress | 11/28/2018 | 5/16/2019 |  | 438667 | 438667 | 198102 | DSF0000889377, DSF0000893420
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | PNS | PNS | PNS | PNS | 9870003 | 9870003 | 84831 | DSF0000889377, DSF0000893420
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 614134 | 614134 | 74678 | DSF0000889377, DSF0000893420
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 2/14/2019 | 7/1/2019 | 8/26/2019 | 147899 | 187036 | 187036 | DSF0000870633, DSF0000938713, DSF0000938712, DSF0000960696
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 1/15/2020 | 6/16/2020 | 4/29/2022 | 739501 | 488576 | 488576 | DSF0000870633, DSF0000938713, DSF0000938712, DSF0000960696
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | Construction | In-Progress | 9/12/2022 | 9/10/2024 |  | 16638778 | 14996848 | 8302889 | DSF0000870633, DSF0000938713, DSF0000938712, DSF0000960696
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | CM,F&E | In-Progress | 9/12/2022 | 9/10/2024 |  | 1035301 | 551793 | 547367 | DSF0000870633, DSF0000938713, DSF0000938712, DSF0000960696
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/24/2021 | 6/22/2021 | 8/12/2021 | 0 | 18180 | 18180 | DSF0000913230
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 9/10/2021 | 1/31/2022 |  | 45000 | 50587 | 30280 | DSF0000913230
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 30391 | DSF0000913230
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 10244 | DSF0000913230
15 | K169 | P.S. 169 - BROOKLYN | SCA IEH | PO18-ABATE & REMOVE STEAM PIPE INSULATION AND ELBOW FROM HORIZONTAL 2' LINE ABOUT 10 FEET HIGH, MAR | Construction | In-Progress | 11/27/2024 | IEH |  | IEH | 0 | 0 | SCA0000073652
15 | K169 | P.S. 169 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 5/2/2022 | DOES | 8/12/2022 | DOES | 62704 | 61860 | DSF0000866108
15 | K172 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | Scope | Complete | 3/5/2019 | 7/18/2019 | 10/2/2020 | 164813 | 255430 | 255430 | DSF0000893457, DSF0000987217, DSF0000987218, DSF0000987225, DSF0001008596
15 | K172 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | Design | Complete | 12/10/2020 | 5/13/2021 | 4/21/2022 | 816891 | 634120 | 611177 | DSF0000893457, DSF0000987217, DSF0000987218, DSF0000987225, DSF0001008596
15 | K172 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | Construction | In-Progress | 9/19/2022 | 3/6/2025 |  | 17759605 | 16202393 | 12750374 | DSF0000893457, DSF0000987217, DSF0000987218, DSF0000987225, DSF0001008596
15 | K172 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | CM,F&E | In-Progress | 9/19/2022 | 3/6/2025 |  | 1208711 | 603435 | 593094 | DSF0000893457, DSF0000987217, DSF0000987218, DSF0000987225, DSF0001008596
15 | K172 | P.S. 172 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/15/2019 | EMER |  | EMER | 23214 | 23214 | SCA0000055826
15 | K172 | P.S. 172 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 0 | DSF0001086009
15 | K172 | P.S. 172 - BROOKLYN | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/21/2020 | FTK |  | FTK | 1142542 | 1064574 | DSF0000961057
15 | K172 | P.S. 172 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112595
15 | K172 | P.S. 172 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/28/2023 | DOES |  | DOES | 193011 | 0 | DSF0001034221
15 | K230 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 10/11/2018 | 3/1/2019 | 4/19/2019 | 127484 | 136853 | 136853 | DSF0000871728, DSF0000871729, DSF0000871730, DSF0000894514
15 | K230 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 4/19/2019 | 9/18/2019 | 5/15/2019 | 637422 | 595608 | 578779 | DSF0000871728, DSF0000871729, DSF0000871730, DSF0000894514
15 | K230 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 8/16/2021 | 8/15/2023 |  | 14342004 | 13447349 | 11798003 | DSF0000871728, DSF0000871729, DSF0000871730, DSF0000894514
15 | K230 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 8/16/2021 | 8/15/2023 |  | 892391 | 728879 | 711720 | DSF0000871728, DSF0000871729, DSF0000871730, DSF0000894514
15 | K230 | P.S. 230 - BROOKLYN | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 6/15/2024 | FTK |  | FTK | 303869 | 122443 | DSF0001087431
15 | K230 | P.S. 230 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112631
15 | K230 | P.S. 230 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 480000 | 0 | DSF0001112630
15 | K230 | P.S. 230 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 11/10/2021 | DOES |  | DOES | 84168 | 0 | DSF0001008969
15 | K230 | P.S. 230 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/5/2023 | DOES |  | DOES | 258266 | 0 | DSF0001035141
15 | K231 | K721 SPED - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 1/5/2024 | 7/18/2024 | 7/12/2024 | 15037 | 63586 | 45023 | DSF0001091583
15 | K231 | K721 SPED - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | In-Progress | 7/24/2024 | 12/26/2024 |  | 75185 | 75185 | 11813 | DSF0001091583
15 | K231 | K721 SPED - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | PNS | PNS | PNS | PNS | 1691665 | 1691665 | 0 | DSF0001091583
15 | K231 | K721 SPED - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | PNS | PNS | PNS | PNS | 105259 | 105259 | 20962 | DSF0001091583
15 | K231 | K721 SPED - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/1/2024 | IEH | 8/14/2024 | IEH | 0 | 0 | SCA0000073212
15 | K231 | K721 SPED - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/17/2024 | DIIR | 9/20/2024 | DIIR | 100000 | 84570 | DSF0001086034
15 | K231 | K721 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 163157 | 0 | DSF0001086035
15 | K231 | K721 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001112632
15 | K231 | K721 SPED - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/14/2022 | DOES |  | DOES | 134222 | 0 | DSF0001034225
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | Scope | Complete | 6/17/2022 | 4/25/2023 | 4/28/2023 | 27880 | 46189 | 33754 | DSF0001085150, DSF0001083699
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | Design | Complete | 5/5/2023 | 9/8/2023 | 5/12/2023 | 136639 | 103078 | 76893 | DSF0001085150, DSF0001083699
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | Construction | In-Progress | 1/4/2024 | 1/2/2025 |  | 2835771 | 2583601 | 829279 | DSF0001085150, DSF0001083699
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | CM,F&E | In-Progress | 1/4/2024 | 1/2/2025 |  | 215842 | 160759 | 158020 | DSF0001085150, DSF0001083699
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / PLAYGROUND REDEVELOPMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 9/18/2018 | 4/25/2023 | 4/28/2023 | 84394 | 111588 | 105723 | DSF0000872231, DSF0000895047, DSF0000895046, DSF0000940371, DSF0001035191, DSF0001083690
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / PLAYGROUND REDEVELOPMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 5/1/2023 | 9/1/2023 | 2/7/2024 | 396001 | 558543 | 443607 | DSF0000872231, DSF0000895047, DSF0000895046, DSF0000940371, DSF0001035191, DSF0001083690
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / PLAYGROUND REDEVELOPMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 10/14/2024 | 4/1/2027 |  | 6663650 | 6284179 | 273841 | DSF0000872231, DSF0000895047, DSF0000895046, DSF0000940371, DSF0001035191, DSF0001083690
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / PLAYGROUND REDEVELOPMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 10/14/2024 | 4/1/2027 |  | 785532 | 153108 | 149627 | DSF0000872231, DSF0000895047, DSF0000895046, DSF0000940371, DSF0001035191, DSF0001083690
15 | K261 | P.S. 261 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 115111 | 0 | DSF0001035506
15 | K261 | P.S. 261 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 556906 | 0 | DSF0001086049
15 | K261 | P.S. 261 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 129000 | 0 | DSF0001112655
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | Scope | Complete | 3/16/2016 | 3/16/2016 | 3/16/2016 | 231000 | 720511 | 720511 | DSF0000798184
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | Design | Complete | 3/17/2016 | 8/29/2016 | 4/19/2017 | 924000 | 2608905 | 2564133 | DSF0000798184
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | Construction | In-Progress | 8/7/2017 | 8/6/2019 |  | 17325000 | 20043057 | 18242671 | DSF0000798184
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | CM,F&E | In-Progress | 8/7/2017 | 8/6/2019 |  | 1584858 | 2381930 | 2074133 | DSF0000798184
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Scope | Complete | 2/6/2023 | 4/17/2023 | 4/10/2023 | 202000 | 189873 | 189873 | DSF0001008660
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Design | Complete | 4/11/2023 | 9/19/2023 | 2/16/2024 | 909000 | 494158 | 332034 | DSF0001008660
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 8/12/2024 | 9/3/2026 |  | 11463500 | 10454971 | 1200545 | DSF0001008660
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 8/12/2024 | 9/3/2026 |  | 1616000 | 787323 | 177987 | DSF0001008660
15 | K280 | I.S. 442 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/24/2024 | DIIR | 35000 | 34781 | DSF0000913813
15 | K280 | I.S. 442 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033567
15 | K280 | I.S. 442 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 55000 | 54083 | DSF0001086066
15 | K280 | PRE-K CENTER AT BISHOP FORD SCHOOL SITE | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112669
15 | K280 | I.S. 442 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/29/2024 | DOES | 8/5/2024 | DOES | 65832 | 6549 | DSF0001085442
15 | K293 | DIGITAL ARTS AND CINEMA TECHNOLOGY HIGH SCHOOL - K | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOOR TILES. APPROX 150 SQ FT. ABATE AND REMOVE (2) TWO HATCHES ON TH | Construction | Complete | 10/2/2024 | IEH | 10/31/2024 | IEH | 0 | 0 | SCA0000073464
15 | K293 | THE BOERUM HILL SCHOOL FOR INTERNATIONAL STUDIES - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 60000 | 0 | DSF0001008211
15 | K293 | THE BOERUM HILL SCHOOL FOR INTERNATIONAL STUDIES - K | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 9/22/2022 | DOER |  | DOER | 51442 | 0 | DSF0001008214
15 | K293 | SUCCESS ACADEMY CHARTER SCHOOL - COBBLE HILL | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 6/26/2024 | DOER |  | DOER | 210715 | 0 | DSF0001033480
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/14/2021 | 12/13/2021 | 10/28/2021 | 122827 | 246335 | 223338 | DSF0000989763, DSF0000989764, DSF0000989765, DSF0001034336
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 12/1/2021 | 6/30/2022 | 4/19/2022 | 614136 | 544412 | 541606 | DSF0000989763, DSF0000989764, DSF0000989765, DSF0001034336
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 7/18/2022 | 1/2/2025 |  | 13818037 | 12557564 | 12072002 | DSF0000989763, DSF0000989764, DSF0000989765, DSF0001034336
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 7/18/2022 | 1/2/2025 |  | 859789 | 602099 | 595126 | DSF0000989763, DSF0000989764, DSF0000989765, DSF0001034336
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/16/2022 | 9/15/2022 | 10/14/2022 | 0 | 38633 | 38633 | DSF0001033545
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 10/18/2022 | 3/8/2023 | 2/14/2023 | 46341 | 62948 | 60032 | DSF0001033545
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 679663 | 679663 | 29961 | DSF0001033545
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 46341 | 46341 | 21629 | DSF0001033545
15 | K321 | P.S. 321 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 50000 | 47097 | DSF0001086087
15 | K321 | P.S. 321 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112686
15 | K321 | P.S. 321 - BROOKLYN | DOE - RESOA | FY09 RESO A ROOM CONVERSIONS / PART | Construction | PNS | PNS | PNS | PNS | DOER | 95899 | 0 | DSF0000623083
15 | K321 | P.S. 321 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/19/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084153
15 | K333 | SUNSET PARK AVENUES ELEMENTARY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/29/2024 | DOES | 8/28/2024 | DOES | 65832 | 10176 | DSF0001085443
15 | K338 | P.S. 338 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE CARTS | F&E | In-Progress | 8/19/2024 |  |  | 150000 | 150000 | 14907 | DSF0001086092
15 | K338 | P.S. 338 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 149405 | DSF0001086093
15 | K338 | M.S. 890 | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 260000 | 0 | DSF0001112691
15 | K338 | M.S. 890 | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | Complete | 7/8/2019 | DOER | 12/30/2020 | DOER | 155023 | 194155 | DSF0000890658
15 | K347 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Scope | Complete | 1/21/2021 | 5/13/2021 | 5/11/2021 | 423340 | 395704 | 395704 | DSF0000866091
15 | K347 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Design | Complete | 5/12/2021 | 11/12/2021 | 4/11/2022 | 1905030 | 1256051 | 863400 | DSF0000866091
15 | K347 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Construction | Complete | 7/11/2022 | 9/3/2024 | 11/12/2024 | 24024545 | 25655573 | 21577172 | DSF0000866091
15 | K347 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | CM,F&E | Complete | 7/11/2022 | 9/3/2024 | 11/12/2024 | 3386720 | 3110482 | 2849426 | DSF0000866091
15 | K369 | COY L. COX SCHOOL | SCA CIP | WINDOWS | Scope | Complete | 5/21/2021 | 10/6/2021 | 8/18/2021 | 37780 | 73917 | 73917 | DSF0000989940
15 | K369 | COY L. COX SCHOOL | SCA CIP | WINDOWS | Design | Complete | 9/15/2021 | 2/18/2022 | 1/12/2022 | 188900 | 295668 | 295668 | DSF0000989940
15 | K369 | COY L. COX SCHOOL | SCA CIP | WINDOWS | Construction | In-Progress | 9/12/2022 | 3/4/2024 |  | 4250250 | 3948375 | 2191814 | DSF0000989940
15 | K369 | COY L. COX SCHOOL | SCA CIP | WINDOWS | CM,F&E | In-Progress | 9/12/2022 | 3/4/2024 |  | 264460 | 163873 | 163040 | DSF0000989940
15 | K369 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/16/2022 | 4/19/2023 | 12/27/2022 | 4140 | 3903 | 3903 | DSF0001034553
15 | K369 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/27/2022 | 6/23/2023 | 2/22/2023 | 18630 | 15613 | 15613 | DSF0001034553
15 | K369 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 240120 | 219424 | 183114 | DSF0001034553
15 | K369 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 152433 | 142635 | 86147 | DSF0001034553
15 | K369 | COY L. COX SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/21/2023 | DIIR | 2/26/2024 | DIIR | 385000 | 385000 | DSF0001033077
15 | K369 | COY L. COX SCHOOL | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 7/6/2022 | DOER |  | DOER | 337326 | 0 | DSF0000913196
15 | K369 | COY L. COX SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/23/2024 | DOES | 11/4/2024 | DOES | 65832 |  | DSF0001084891
15 | K369 | COY L. COX SCHOOL | DOE - Skilled Trades | PA- CLOCK SYSTEM | Construction | In-Progress | 11/6/2023 | DOES |  | DOES | 207140 | 0 | DSF0001087244
15 | K371 | K371 SPED - BROOKLYN | DOE - RESOA | FY19 RESO A ROOM CONVERSION/PARTITIONING | Construction | In-Progress | 2/29/2020 | DOER |  | DOER | 100712 | 0 | DSF0000889770
15 | K371 | K371 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086102
15 | K371 | K371 SPED - BROOKLYN | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 166279 | 0 | DSF0001112207
15 | K371 | K371 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112695
15 | K371 | K371 SPED - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/10/2024 | DOES | 10/16/2024 | DOES | 65832 | 9935 | DSF0001084893
15 | K437 | K053 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033452
15 | K437 | M.S. 839 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 8/14/2024 | DIIR | 100000 | 100000 | DSF0001033617
15 | K437 | M.S. 839 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112712
15 | K437 | P.S. 130 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/9/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084770
15 | K447 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | Scope | Complete | 5/28/2021 | 7/16/2021 | 7/15/2021 | 283140 | 233315 | 233315 | DSF0001008920
15 | K447 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | Design | Complete | 7/16/2021 | 10/7/2021 | 6/7/2022 | 1274130 | 1505132 | 1195386 | DSF0001008920
15 | K447 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | Construction | In-Progress | 8/15/2022 | 9/3/2023 |  | 16068195 | 16240369 | 15361951 | DSF0001008920
15 | K447 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | CM,F&E | In-Progress | 8/15/2022 | 9/3/2023 |  | 2265120 | 750321 | 1766946 | DSF0001008920
15 | K460 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | Scope | Complete | 12/21/2018 | 5/9/2019 | 9/24/2019 | 29978 | 74130 | 74097 | DSF0000960918
15 | K460 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | Design | Complete | 10/28/2019 | 4/1/2020 | 5/18/2020 | 149889 | 232500 | 149710 | DSF0000960918
15 | K460 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | Construction | In-Progress | 5/11/2021 | 11/1/2022 |  | 3372509 | 2472017 | 2029738 | DSF0000960918
15 | K460 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | CM,F&E | In-Progress | 5/11/2021 | 11/1/2022 |  | 209845 | 303078 | 297250 | DSF0000960918
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112715
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 33300 | 33300 | 0 | DSF0001112715
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 488400 | 488400 | 0 | DSF0001112715
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 33300 | 33300 | 0 | DSF0001112715
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113591
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113591
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113591
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113591
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | SCA IEH | PO18-ABATE AND REPLACE FLOORS IN ROOMS 330, 332, 336 | Construction | Complete | 6/6/2024 | IEH | 11/5/2024 | IEH | 0 | 0 | SCA0000073055
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | SCA IEH | PO18-ABATE PIPE INSULATION PIPE SPACE UNDER POOL MECHANICAL ROOM, 4TH STREET SIDE OF BUILDING BASEME | Construction | Complete | 7/17/2024 | IEH | 7/19/2024 | IEH | 0 | 0 | SCA0000073145
15 | K460 | PARK SLOPE COLLEGIATE - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 10/24/2024 | DIIR | 50000 | 50000 | DSF0001008283
15 | K460 | PARK SLOPE COLLEGIATE - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/16/2024 | DIIR | 10/24/2024 | DIIR | 50000 | 50000 | DSF0001033572
15 | K460 | PARK SLOPE COLLEGIATE - K | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/28/2023 | DOER |  | DOER | 100315 | 0 | DSF0001086128
15 | K460 | SECONDARY SCHOOL FOR LAW - K | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112716
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112717
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 12/1/2022 | DOES | 12/4/2023 | DOES | 827633 | 816499 | DSF0000960842
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/18/2024 | DOES | 7/26/2024 | DOES | 65832 |  | DSF0001084908
15 | K520 | BROOKLYN FRONTIERS HIGH SCHOOL - K | SCA IEH | PO18-ABATE WALLS, CEILINGS, AND FLOORS KITCHEN/CAFETERIA (1003) - WALLS,CEILING & FLOOR BOILER ROOM | Construction | In-Progress | 10/17/2024 | IEH |  | IEH | 0 | 0 | SCA0000073517
15 | K520 | BROOKLYN FRONTIERS HIGH SCHOOL - K | DOE - RESOA | FY17 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 201141 | 0 | DSF0000844843
15 | K520 | BROOKLYN FRONTIERS HIGH SCHOOL - K | DOE - RESOA | FY20 RESO A FABLABS | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0000913064
15 | K564 | SUNSET PARK HS - BROOKLYN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/21/2022 | DOER |  | DOER | 102406 | 0 | DSF0001008251
15 | K564 | SUNSET PARK HS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/28/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084921
15 | K655 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 10/23/2020 | 2/26/2021 | 3/3/2021 | 5800 | 6265 | 6265 | DSF0000960753
15 | K655 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/3/2021 | 8/25/2021 | 7/14/2021 | 26100 | 25063 | 25063 | DSF0000960753
15 | K655 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/5/2022 | 2/28/2023 |  | 336400 | 297211 | 250533 | DSF0000960753
15 | K655 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/5/2022 | 2/28/2023 |  | 353613 | 341004 | 238596 | DSF0000960753
15 | K655 | BROOKLYN HS OF THE ARTS - BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 2/10/2023 | DOES | 10/4/2023 | DOES | 489448 | 440142 | DSF0000960851
15 | K655 | BROOKLYN HS OF THE ARTS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/6/2024 | DOES | 11/18/2024 | DOES | 65832 |  | DSF0001084775
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 5/18/2017 | 10/19/2017 | 7/18/2017 | 109022 | 169741 | 169741 | DSF0000798263, DSF0000784013
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/20/2017 | 12/21/2017 | 1/19/2018 | 426177 | 527397 | 507338 | DSF0000798263, DSF0000784013
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 6/11/2018 | 3/1/2020 |  | 7101271 | 6930095 | 5611908 | DSF0000798263, DSF0000784013
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 6/11/2018 | 3/1/2020 |  | 637617 | 1000757 | 979718 | DSF0000798263, DSF0000784013
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | Scope | Complete | 1/26/2021 | 7/12/2021 | 11/3/2021 | 129522 | 250049 | 241536 | DSF0000942271, DSF0000942274, DSF0000942275, DSF0000942273, DSF0000990972
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | Design | Complete | 11/10/2021 | 4/15/2022 | 5/11/2022 | 639043 | 523169 | 472624 | DSF0000942271, DSF0000942274, DSF0000942275, DSF0000942273, DSF0000990972
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | Construction | In-Progress | 9/12/2022 | 9/10/2024 |  | 13637703 | 12608203 | 8663938 | DSF0000942271, DSF0000942274, DSF0000942275, DSF0000942273, DSF0000990972
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | CM,F&E | In-Progress | 9/12/2022 | 9/10/2024 |  | 970878 | 312747 | 300135 | DSF0000942271, DSF0000942274, DSF0000942275, DSF0000942273, DSF0000990972
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 12/5/2024 | IEH | 12/11/2024 | IEH | 0 | 0 | SCA0000073668
15 | K661 | THE LITTLE BROOKLYN PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/30/2024 | DOES | 8/28/2024 | DOES | 65832 | 8315 | DSF0001085455
15 | K671 | P.S. 958 | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112734
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 5/6/2021 | 9/30/2021 | 11/16/2021 | 2016007 | 1151031 | 1151031 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 11/17/2021 | 5/5/2022 | 10/8/2024 | 8064028 | 2019195 | 1953794 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 111384390 | 111384390 | 1629054 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 14616051 | 14616051 | 693260 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 9/13/2022 | 9/13/2022 | 9/13/2022 | 68074 | 60894 | 60894 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 9/13/2022 | 4/18/2023 | 7/14/2023 | 340372 | 153716 | 135902 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 7658377 | 7658377 | 240153 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 476521 | 476521 | 206117 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 7/1/2022 | 8/29/2022 | 7/1/2022 | 105550 | 60915 | 60915 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 7/1/2022 | 11/30/2022 | 12/19/2022 | 527750 | 119480 | 119480 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 11874375 | 11874375 | 71587 | DSF0000843826
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 738850 | 738850 | 131007 | DSF0000843826
15 | K682 | P.S. 896 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 101143 | 0 | DSF0001008257
15 | K692 | THE LITTLE BROOKLYN PRE-K CENTER | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033613
15 | K749 | THE LITTLE BROOKLYN PRE-K CENTER | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 8/13/2018 | DOES |  | DOES | 195142 | 0 | DSF0000888716
15 | K749 | THE LITTLE BROOKLYN PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/1/2024 | DOES | 9/6/2024 | DOES | 65832 | 9290 | DSF0001085464
15 | K751 | P.S. 58 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033454
15 | K751 | P.S. 58 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/1/2024 | DOES | 11/22/2024 | DOES | 65832 | 8887 | DSF0001085465
15 | K763 | THE MAURICE SENDAK COMMUNITY SCHOOL | SCA IEH | PO18-PERFORM QC SUPPLEMENTAL SAMPLING ON FLOORS IN ROOM 318. SOFT FILLER ASSUMED ACM. DAMAGE IS IN | Construction | Complete | 9/24/2024 | IEH | 10/24/2024 | IEH | 0 | 0 | SCA0000073418
15 | K763 | THE MAURICE SENDAK COMMUNITY SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 50000 | 28407 | DSF0001035588
15 | K763 | THE MAURICE SENDAK COMMUNITY SCHOOL | DOE - RESOA | FY18 RESO A HYDROPNICS CLASSROOM | Construction | Complete | 6/7/2019 | DOER | 9/25/2019 | DOER | 113347 |  | DSF0000867688
15 | K781 | WEST BROOKLYN COMMUNITY HS - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035589
15 | K781 | WEST BROOKLYN COMMUNITY HS - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/4/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001086149
15 | K781 | WEST BROOKLYN COMMUNITY HS - K | DOE - RESOA | FY18 RESO A LIBRARY UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 59842 | 0 | DSF0000867214
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | SCA IEH | PO18-PLEASE REMOVE 800SF OF RUG AND FLOOR TILE ACM IN ROOM 907 ON THE 9TH FLOOR. | Construction | In-Progress | 5/2/2024 | IEH |  | IEH | 0 | 0 | SCA0000072974
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | SCA IEH | PO18-REMOVAL OF RUG AND FLOOR TILES IN ROOM #703 | Construction | Complete | 5/28/2024 | IEH | 8/4/2024 | IEH | 0 | 0 | SCA0000073029
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | Fast Track Projects | ELEVATOR MODERNIZATION | Construction | In-Progress | 9/13/2017 | FTK |  | FTK | 4840626 | 4800037 | DSF0000851530
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | DOE - Skilled Trades | COOLING TOWER REPAIRS | Construction | In-Progress | 1/31/2022 | DOES |  | DOES | 233035 | 0 | DSF0000991068
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | DOE - Skilled Trades | MASONRY REPAIRS | Construction | In-Progress | 1/3/2024 | DOES |  | DOES | 302535 | 0 | DSF0001094771
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/28/2022 | 11/14/2022 | 11/16/2022 | 99214 | 99699 | 99699 | DSF0001016323, DSF0001016324, DSF0001016325, DSF0001067090
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 12/9/2022 | 5/12/2023 | 5/12/2023 | 490286 | 311634 | 297261 | DSF0001016323, DSF0001016324, DSF0001016325, DSF0001067090
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 10531370 | 10531370 | 58078 | DSF0001016323, DSF0001016324, DSF0001016325, DSF0001067090
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 737856 | 737856 | 32941 | DSF0001016323, DSF0001016324, DSF0001016325, DSF0001067090
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/22/2022 | 7/20/2022 | 3/28/2022 | 4700 | 3788 | 3788 | DSF0000960755
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/28/2022 | 9/20/2022 | 7/19/2022 | 21150 | 15152 | 15152 | DSF0000960755
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/8/2023 | 1/3/2024 |  | 272600 | 243589 | 174214 | DSF0000960755
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/8/2023 | 1/3/2024 |  | 247639 | 237633 | 140503 | DSF0000960755
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA IEH | PO18-ABATE AND REPAIR FLOORING IN SCIENCE LABS # 411 AND 416 | Construction | In-Progress | 7/28/2023 | IEH |  | IEH | 0 | 0 | SCA0000072171
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/3/2024 | DIIR | 11/20/2024 | DIIR | 100000 | 100000 | DSF0001033100
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/7/2024 | DOES | 10/17/2024 | DOES | 65832 |  | DSF0001084933
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086151
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0001086151
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 66000 | 66000 | 0 | DSF0001086151
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0001086151
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087036
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087036
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087036
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087036
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001035593
15 | K825 | SOUTH BROOKLYN COMM. HS - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001086152
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/26/2022 | 3/1/2023 | 12/23/2022 | 4140 | 5226 | 5226 | DSF0001034561
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/23/2022 | 6/22/2023 | 2/22/2023 | 18630 | 20907 | 20907 | DSF0001034561
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 240120 | 213785 | 180085 | DSF0001034561
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 70527 | 55265 | 52624 | DSF0001034561
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 3/29/2023 | 4/3/2024 | 2/5/2024 | 12557 | 49464 | 48406 | DSF0001083942, DSF0001111802
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 2/5/2024 | 7/23/2024 | 3/14/2024 | 56505 | 62222 | 43942 | DSF0001083942, DSF0001111802
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 728287 | 728287 | 5930 | DSF0001083942, DSF0001111802
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 134984 | 134984 | 23772 | DSF0001083942, DSF0001111802
15 | K834 | K372 SPED - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/12/2021 | 10/8/2021 | 10/5/2021 | 0 | 53537 | 53537 | DSF0001008277
15 | K834 | K372 SPED - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 11/15/2021 | 4/4/2022 | 10/31/2022 | 49603 | 77909 | 77909 | DSF0001008277
15 | K834 | K372 SPED - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 6/16/2023 | 7/19/2024 |  | 727510 | 545952 | 314058 | DSF0001008277
15 | K834 | K372 SPED - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 6/16/2023 | 7/19/2024 |  | 49603 | 78705 | 59687 | DSF0001008277
15 | K834 | K372 SPED - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 9/26/2024 | IEH | 10/9/2024 | IEH | 0 | 0 | SCA0000073433
15 | K834 | K372 SPED - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/7/2024 | DIIR | 8/5/2024 | DIIR | 150000 | 150000 | DSF0001035594
15 | K834 | K372 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 185659 | 0 | DSF0001086153
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 12/17/2020 | 4/16/2021 | 6/29/2021 | 22586 | 53170 | 53170 | DSF0000991254
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 6/30/2021 | 12/1/2021 | 11/5/2021 | 112931 | 101835 | 94234 | DSF0000991254
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | COVID VENTILATION | Construction | PNS | PNS | PNS | PNS | 2540943 | 2540943 | 706797 | DSF0000991254
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | COVID VENTILATION | CM,F&E | PNS | PNS | PNS | PNS | 158103 | 158103 | 78867 | DSF0000991254
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 11/27/2023 | 4/12/2024 | 6/5/2024 | 144280 | 157122 | 137215 | DSF0001111765, DSF0001111766, DSF0001094998
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 6/14/2024 | 11/18/2024 | 11/6/2024 | 673304 | 290179 | 8246 | DSF0001111765, DSF0001111766, DSF0001094998
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 10676683 | 10676683 | 23907 | DSF0001111765, DSF0001111766, DSF0001094998
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1058049 | 1058049 | 38848 | DSF0001111765, DSF0001111766, DSF0001094998
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | Scope | Complete | 11/28/2012 | 4/23/2014 | 6/23/2014 | 176917 | 289253 | 254282 | DSF0000754744, DSF0000775989, DSF0000761629, DSF0000784298, DSF0000784302, DSF0000807596, DSF0000807597, DSF0000807595
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | Design | Complete | 12/10/2014 | 5/13/2015 | 8/24/2015 | 672202 | 1303148 | 1241908 | DSF0000754744, DSF0000775989, DSF0000761629, DSF0000784298, DSF0000784302, DSF0000807596, DSF0000807597, DSF0000807595
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | Construction | In-Progress | 7/17/2017 | 1/7/2019 |  | 10351810 | 10354314 | 9178519 | DSF0000754744, DSF0000775989, DSF0000761629, DSF0000784298, DSF0000784302, DSF0000807596, DSF0000807597, DSF0000807595
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | CM,F&E | In-Progress | 7/17/2017 | 1/7/2019 |  | 1156748 | 1402257 | 1369928 | DSF0000754744, DSF0000775989, DSF0000761629, DSF0000784298, DSF0000784302, DSF0000807596, DSF0000807597, DSF0000807595
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/22/2023 | 9/21/2023 | 6/7/2023 | 4537 | 587 | 587 | DSF0001035024
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/7/2023 | 12/5/2023 | 8/30/2023 | 20417 | 2346 | 2346 | DSF0001035024
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/23/2024 | 1/17/2025 |  | 263158 | 249711 | 143056 | DSF0001035024
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/23/2024 | 1/17/2025 |  | 48775 | 32259 | 15141 | DSF0001035024
15 | K845 | P.S. 295 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB | Construction | In-Progress | 9/6/2022 | EMER |  | EMER | 18216 | 11332 | SCA0000071438
15 | K845 | I.S. 443 - BROOKLYN | Fast Track Projects | LSP VACUUM PUMP REPLACEMENT | Construction | In-Progress | 6/22/2021 | FTK |  | FTK | 561423 | 554612 | DSF0000942555
15 | K908 | P.S. 230 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 6/17/2024 | IEH |  | IEH | 0 | 0 | SCA0000073073
15 | K917 | BROOKLYN COLLEGE ACADEMY - K | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 4/19/2024 | IEH |  | IEH | 0 | 0 | SCA0000072945
15 | K917 | BROOKLYN COLLEGE ACADEMY - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033580
15 | K917 | BROOKLYN COLLEGE ACADEMY - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/7/2024 | DIIR | 50000 | 40273 | DSF0001086159
15 | K939 | I.S. 136 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086161
15 | KAGI | BROOKLYN PROSPECT CHARTER SCHOOL - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008259
15 | KAGI | BROOKLYN PROSPECT CHARTER SCHOOL - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112746
15 | KBGZ | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Scope | Complete | 3/2/2021 | 8/3/2022 | 2/22/2023 | 23316 | 43876 | 43876 | DSF0001008758, DSF0001009214
15 | KBGZ | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Design | Complete | 2/28/2023 | 6/30/2023 | 3/31/2023 | 115467 | 179372 | 116248 | DSF0001008758, DSF0001009214
15 | KBGZ | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Construction | In-Progress | 11/13/2023 | 5/5/2025 |  | 2501588 | 2852506 | 1552298 | DSF0001008758, DSF0001009214
15 | KBGZ | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | CM,F&E | In-Progress | 11/13/2023 | 5/5/2025 |  | 171572 | 276169 | 150608 | DSF0001008758, DSF0001009214
15 | KBNU | BROOKLYN URBAN CHARTER SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/23/2024 | DIIR | 6/21/2024 | DIIR | 50000 | 50000 | DSF0001035604
15 | KBNU | BROOKLYN URBAN CHARTER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112748
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | ELECTRIFICATION/CLIMATE CONTROL / ELECTRIFICATION/BOILER REMOVAL / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | Scope | Complete | 9/17/2020 | 2/23/2021 | 12/9/2020 | 167950 | 177538 | 163538 | DSF0000936438, DSF0000961025, DSF0000984743, DSF0000984750
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | ELECTRIFICATION/CLIMATE CONTROL / ELECTRIFICATION/BOILER REMOVAL / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | Design | Complete | 12/10/2020 | 8/31/2021 | 8/9/2021 | 839750 | 721066 | 667034 | DSF0000936438, DSF0000961025, DSF0000984743, DSF0000984750
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | ELECTRIFICATION/CLIMATE CONTROL / ELECTRIFICATION/BOILER REMOVAL / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | Construction | In-Progress | 8/8/2022 | 8/6/2024 |  | 18894375 | 17264324 | 15253132 | DSF0000936438, DSF0000961025, DSF0000984743, DSF0000984750
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | ELECTRIFICATION/CLIMATE CONTROL / ELECTRIFICATION/BOILER REMOVAL / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 8/8/2022 | 8/6/2024 |  | 1175650 | 917728 | 891952 | DSF0000936438, DSF0000961025, DSF0000984743, DSF0000984750
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/14/2022 | 10/13/2022 | 6/21/2022 | 4999 | 7452 | 7452 | DSF0001034618
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/21/2022 | 12/16/2022 | 12/7/2022 | 22495 | 29808 | 29808 | DSF0001034618
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 5/31/2023 | 4/24/2024 |  | 289930 | 258751 | 217021 | DSF0001034618
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 5/31/2023 | 4/24/2024 |  | 180882 | 161793 | 101385 | DSF0001034618
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035361
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | Design | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001035361
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001035361
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001035361
16 | K005 | P.S. 5 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/12/2024 | DIIR |  | DIIR | 100000 | 0 | DSF0001035362
16 | K005 | P.S. 5 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112511
16 | K005 | P.S. 5 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 9/19/2023 | DOER |  | DOER | 220310 | 0 | DSF0001034976
16 | K005 | P.S. 5 - BROOKLYN | DOE - RESOA | FY23 RESO A STEM LAB | Construction | In-Progress | 6/2/2023 | DOER |  | DOER | 279578 | 0 | DSF0001035360
16 | K005 | P.S. 5 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 8/18/2020 | DOES |  | DOES | 751864 | 0 | DSF0000865729
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 5/22/2019 | 10/7/2019 | 4/20/2021 | 113330 | 123282 | 123282 | DSF0000912349
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 7/21/2021 | 1/10/2022 | 10/31/2022 | 566650 | 290957 | 267568 | DSF0000912349
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 9/11/2023 | 7/1/2025 |  | 12749625 | 11695929 | 5956113 | DSF0000912349
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 9/11/2023 | 7/1/2025 |  | 793310 | 608949 | 605387 | DSF0000912349
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 1/31/2020 | 7/1/2020 | 4/30/2020 | 68800 | 108980 | 108980 | DSF0000798392, DSF0000936743
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/4/2020 | 10/2/2020 | 7/22/2020 | 344000 | 435741 | 414536 | DSF0000798392, DSF0000936743
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 2/7/2022 | 2/6/2024 |  | 7740000 | 7432279 | 6829544 | DSF0000798392, DSF0000936743
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 2/7/2022 | 2/6/2024 |  | 481600 | 885557 | 872855 | DSF0000798392, DSF0000936743
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | EXTERIOR MASONRY PERM FIX @ K021 / PARAPETS / ROOFS | Scope | Complete | 5/22/2024 | 10/8/2024 | 9/20/2024 | 127493 | 133914 | 18506 | SCA0000072886, DSF0001088218, DSF0001088217
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | EXTERIOR MASONRY PERM FIX @ K021 / PARAPETS / ROOFS | Design | In-Progress | 9/27/2024 | 3/5/2025 |  | 614095 | 614095 | 12271 | SCA0000072886, DSF0001088218, DSF0001088217
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | EXTERIOR MASONRY PERM FIX @ K021 / PARAPETS / ROOFS | Construction | PNS | PNS | PNS | PNS | 11643500 | 11643500 | 621 | SCA0000072886, DSF0001088218, DSF0001088217
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | EXTERIOR MASONRY PERM FIX @ K021 / PARAPETS / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 915827 | 915827 | 15359 | SCA0000072886, DSF0001088218, DSF0001088217
16 | K021 | P.S. 21 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION - SWB @ K021 | Construction | In-Progress | 3/29/2024 | EMER |  | EMER |  | 0 | SCA0000072885
16 | K021 | P.S. 21 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112529
16 | K025 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/28/2020 | 9/25/2020 | 7/2/2020 | 3070 | 8074 | 8074 | DSF0000960734
16 | K025 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/2/2020 | 12/30/2020 | 3/30/2021 | 13817 | 32300 | 32300 | DSF0000960734
16 | K025 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/26/2022 | 3/21/2023 |  | 178083 | 166715 | 132760 | DSF0000960734
16 | K025 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/26/2022 | 3/21/2023 |  | 218674 | 233714 | 146103 | DSF0000960734
16 | K025 | P.S. 25 - BROOKLYN | Fast Track Projects | PATH OF TRAVEL PLAY YARD | Construction | In-Progress | 7/11/2024 | FTK |  | FTK | 378844 | 43719 | DSF0000960720
16 | K025 | P.S. 25 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112530
16 | K025 | SUCCESS ACADEMY CHARTER SCHOOL - BED STUY 3 | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001035380
16 | K025 | P.S. 25 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 88092 | 0 | DSF0001034406
16 | K026 | I.S. 681 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112531
16 | K026 | P.S. 26 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112532
16 | K026 | P.S. 26 - BROOKLYN | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001008233
16 | K035 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/29/2020 | 9/28/2020 | 7/2/2020 | 5300 | 5549 | 5549 | DSF0000960735
16 | K035 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/2/2020 | 12/30/2020 | 3/31/2021 | 23850 | 22197 | 22197 | DSF0000960735
16 | K035 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/5/2022 | 2/28/2023 |  | 307394 | 271523 | 219110 | DSF0000960735
16 | K035 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/5/2022 | 2/28/2023 |  | 244767 | 234840 | 160433 | DSF0000960735
16 | K035 | I.S. 35 - BROOKLYN | SCA IEH | PO18-SURVEY & ABATE AND REPLACE IF NEEDED FLOOR TILES ROOM #301 REPAIR WORK IS NEEDED AS PER SCA | Construction | Complete | 7/26/2024 | IEH | 8/17/2024 | IEH | 0 | 0 | SCA0000073183
16 | K035 | I.S. 35 - BROOKLYN | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/15/2024 | FTK |  | FTK | 46946 | 46304 | DSF0000867278
16 | K035 | I.S. 35 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112536
16 | K035 | BKLYN BROWNSTONE SCL - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112537
16 | K035 | I.S. 35 - BROOKLYN | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 233231 | 0 | DSF0001035387
16 | K035 | I.S. 35 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/8/2024 | DOES |  | DOES | 466075 | 0 | DSF0001085711
16 | K035 | I.S. 35 - BROOKLYN | Trust For Public Land | TPL- EXTREME WEATHER PLAYGROUND UPGRADE | Construction | In-Progress | 6/1/2024 | TPL |  | TPL | 2023981 | 920859 | DSF0001034695
16 | K040 | P.S. 40 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/1/2024 | 10/30/2024 | 7/2/2024 | 5094 | 979 | 979 | DSF0001087377
16 | K040 | P.S. 40 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/2/2024 | 12/30/2024 | 12/18/2024 | 22923 | 3915 | 3915 | DSF0001087377
16 | K040 | P.S. 40 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 295457 | 295457 | 2274 | DSF0001087377
16 | K040 | P.S. 40 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 54761 | 54761 | 2575 | DSF0001087377
16 | K040 | P.S. 40 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112540
16 | K040 | GOTHAM PROFESSIONAL ARTS ACAD - K | DOE - RESOA | FY14 RESO A VENTILATION | Construction | PNS | PNS | PNS | PNS | DOER | 40000 | 0 | DSF0000798800
16 | K040 | P.S. 40 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 137402 | 0 | DSF0001035389
16 | K040 | P.S. 40 - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112539
16 | K040 | P.S. 40 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001112541
16 | K040 | P.S. 40 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/6/2024 | DOES | 9/3/2024 | DOES | 65832 | 7194 | DSF0001084011
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PAVED AREAS- CONCRETE | Scope | Complete | 7/6/2022 | 11/21/2022 | 5/26/2023 | 87871 | 128464 | 128464 | DSF0001010344, DSF0001010345, DSF0001085605, DSF0001061040
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PAVED AREAS- CONCRETE | Design | Complete | 7/26/2023 | 12/28/2023 | 2/13/2024 | 428097 | 388691 | 291626 | DSF0001010344, DSF0001010345, DSF0001085605, DSF0001061040
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PAVED AREAS- CONCRETE | Construction | In-Progress | 11/12/2024 | 4/5/2026 |  | 8658040 | 7755654 | 88654 | DSF0001010344, DSF0001010345, DSF0001085605, DSF0001061040
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PAVED AREAS- CONCRETE | CM,F&E | In-Progress | 11/12/2024 | 4/5/2026 |  | 699564 | 75885 | 74950 | DSF0001010344, DSF0001010345, DSF0001085605, DSF0001061040
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | Fast Track Projects | BUILDING DRAIN BACKUP | Construction | In-Progress | 10/12/2017 | FTK |  | FTK | 6606522 | 6261358 | SCA0000047569
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112546
16 | K057 | BROOKLYN ACADEMY OF GLOBAL FINANCE - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112547
16 | K057 | BROOKLYN ACADEMY OF GLOBAL FINANCE - K | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/7/2023 | DOER |  | DOER | 95591 | 0 | DSF0001033127
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/2/2024 | DOES | 12/11/2024 | DOES | 65832 |  | DSF0001084728
16 | K081 | P.S. 81 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/30/2022 | 11/16/2022 | 8/29/2023 | 61630 | 125021 | 120012 | DSF0001010642, DSF0001010644, DSF0001061328
16 | K081 | P.S. 81 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 9/18/2023 | 2/22/2024 | 2/15/2024 | 296459 | 147712 | 62623 | DSF0001010642, DSF0001010644, DSF0001061328
16 | K081 | P.S. 81 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 10/10/2024 | 4/2/2026 |  | 5659076 | 5483974 | 259115 | DSF0001010642, DSF0001010644, DSF0001061328
16 | K081 | P.S. 81 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 10/10/2024 | 4/2/2026 |  | 519090 | 136942 | 136182 | DSF0001010642, DSF0001010644, DSF0001061328
16 | K081 | P.S. 81 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112557
16 | K081 | P.S. 81 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | Complete | 6/28/2019 | DOER | 12/30/2020 | DOER | 184678 | 172387 | DSF0000890648
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/30/2019 | 12/16/2019 | 11/14/2019 | 57772 | 106737 | 106737 | DSF0000894741, DSF0000894742, DSF0000894743
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/2/2019 | 5/4/2020 | 5/11/2021 | 285216 | 438620 | 438620 | DSF0000894741, DSF0000894742, DSF0000894743
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 9/20/2021 | 12/8/2023 |  | 6102371 | 8491646 | 7181153 | DSF0000894741, DSF0000894742, DSF0000894743
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/20/2021 | 12/8/2023 |  | 431713 | 810120 | 808814 | DSF0000894741, DSF0000894742, DSF0000894743
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/18/2024 | 10/18/2024 | 6/24/2024 | 4202 | 746 | 746 | DSF0001087433
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/24/2024 | 12/19/2024 | 12/18/2024 | 18910 | 2985 | 2985 | DSF0001087433
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 243733 | 243733 | 15442 | DSF0001087433
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 45175 | 45175 | 4342 | DSF0001087433
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | TERRACOTTA PANEL REPLACEMENT | Scope | Complete | 8/29/2023 | 1/18/2024 | 11/3/2023 | 17082 | 17082 | 17082 | DSF0001085612
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | TERRACOTTA PANEL REPLACEMENT | Design | Complete | 11/15/2023 | 4/18/2024 | 3/26/2024 | 59284 | 59284 | 48206 | DSF0001085612
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | TERRACOTTA PANEL REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 3557 | 3557 | 3557 | DSF0001085612
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | TERRACOTTA PANEL REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 11909 | 11909 | 11909 | DSF0001085612
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112645
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112645
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001112645
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112645
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113580
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113580
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113580
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113580
16 | K243 | P.S. 243 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 825000 | 0 | DSF0001112646
16 | K243 | P.S. 243 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/29/2024 | DOES | 8/12/2024 | DOES | 65832 | 21386 | DSF0001084110
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 4/6/2021 | 9/3/2021 | 6/21/2021 | 89280 | 122569 | 122569 | DSF0000988931, DSF0001008798, DSF0000988932
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 6/22/2021 | 11/23/2021 | 11/10/2021 | 446400 | 562491 | 526675 | DSF0000988931, DSF0001008798, DSF0000988932
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 7/5/2022 | 7/3/2024 |  | 10044000 | 9541279 | 8629231 | DSF0000988931, DSF0001008798, DSF0000988932
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 7/5/2022 | 7/3/2024 |  | 624960 | 854837 | 844263 | DSF0000988931, DSF0001008798, DSF0000988932
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/30/2023 | 4/28/2023 | 4/12/2023 | 0 | 57276 | 57276 | DSF0001035507
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 4/21/2023 | 9/7/2023 | 5/21/2024 | 90886 | 97719 | 67647 | DSF0001035507
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1332993 | 1332993 | 31801 | DSF0001035507
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90886 | 90886 | 30739 | DSF0001035507
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/30/2023 | 5/1/2023 | 12/15/2023 | 0 | 14362 | 14362 | DSF0001035508
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 12/28/2023 | 5/1/2024 | 5/21/2024 | 2234 | 32358 | 9521 | DSF0001035508
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 32767 | 32767 | 2417 | DSF0001035508
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 2234 | 3622 | 3622 | DSF0001035508
16 | K262 | P.S. 262 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE 9X9 ASBESTOS TILES IN KITCHEN LOCKER ROOM TILES ARE DAMAGED.REMOVE TILES FOR NEW L | Construction | Complete | 5/7/2024 | IEH | 9/30/2024 | IEH | 0 | 0 | SCA0000072985
16 | K262 | P.S. 262 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112656
16 | K262 | P.S. 262 - BROOKLYN | DOE - RESOA | RESO A- RESO A PLAYGROUND | Construction | PNS | PNS | PNS | PNS | DOER | 223000 | 0 | DSF0001085308
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 7/17/2019 | 12/3/2019 | 8/8/2022 | 147804 | 142251 | 142251 | DSF0000912350, DSF0001014355
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 9/16/2022 | 3/24/2023 | 5/9/2023 | 730453 | 500757 | 434193 | DSF0000912350, DSF0001014355
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 9/18/2023 | 9/6/2025 |  | 15694471 | 14490705 | 5579904 | DSF0000912350, DSF0001014355
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 9/18/2023 | 9/6/2025 |  | 1098847 | 452381 | 450290 | DSF0000912350, DSF0001014355
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/14/2022 | 10/13/2022 | 6/22/2022 | 4721 | 7425 | 7425 | DSF0001034622
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/22/2022 | 12/19/2022 | 12/19/2022 | 21245 | 32295 | 32295 | DSF0001034622
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 5/31/2023 | 4/24/2024 |  | 273824 | 241418 | 207093 | DSF0001034622
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 5/31/2023 | 4/24/2024 |  | 167085 | 157031 | 101037 | DSF0001034622
16 | K304 | K140 SPED - BROOKLYN | SCA Emergency Response | EMERGENCY- CRACKED BRICKS - FACADE @ K304 | Construction | Complete | 2/29/2024 | EMER | 9/30/2024 | EMER | 262184 | 21180 | SCA0000072777
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA IEH | PO18-ABATE AND REPAIR DAMAGED FLOOR IN ROOM 323 TEACHERS BATHROOM | Construction | In-Progress | 2/7/2024 | IEH |  | IEH | 0 | 0 | SCA0000072719
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112673
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 7/10/2023 | DOER | 8/21/2023 | DOER | 171838 | 1761 | DSF0001033116
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 11/1/2022 | 2/3/2023 | 5/15/2023 | 25491 | 97487 | 97487 | DSF0001036311
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | Design | Complete | 5/30/2023 | 10/16/2023 | 2/5/2024 | 127455 | 257336 | 204084 | DSF0001036311
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | Construction | In-Progress | 9/16/2024 | 2/15/2026 |  | 2867739 | 2639913 | 17211 | DSF0001036311
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | CM,F&E | In-Progress | 9/16/2024 | 2/15/2026 |  | 178437 | 52070 | 47597 | DSF0001036311
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 1/5/2024 | 4/5/2024 | 6/5/2024 | 36006 | 42144 | 42144 | DSF0001092832
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEMS | Design | In-Progress | 6/17/2024 | 12/20/2024 |  | 168028 | 168028 | 24074 | DSF0001092832
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 2664442 | 2664442 | 14983 | DSF0001092832
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 264044 | 264044 | 17370 | DSF0001092832
16 | K308 | P.S. 308 - BROOKLYN | SCA IEH | PO18-TEST APPROX. 10 LINEAR FEET OF PIPE INSULATION IN 2' FEED LINE TO CONDENSATE TANK IN BOILER ROO | Construction | Complete | 10/24/2024 | IEH | 12/20/2024 | IEH | 0 | 0 | SCA0000073535
16 | K308 | P.S. 308 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112675
16 | K308 | P.S. 308 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/18/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084615
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 1/31/2020 | 7/1/2020 | 4/7/2020 | 69310 | 82097 | 82097 | DSF0000941045, DSF0000960645
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 4/8/2020 | 9/8/2020 | 8/12/2020 | 346550 | 371946 | 345146 | DSF0000941045, DSF0000960645
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 8/10/2023 | 8/8/2025 |  | 7797375 | 7326861 | 5446634 | DSF0000941045, DSF0000960645
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 8/10/2023 | 8/8/2025 |  | 485170 | 365914 | 356015 | DSF0000941045, DSF0000960645
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS | Scope | Complete | 5/14/2024 | 9/30/2024 | 10/22/2024 | 37572 | 47335 | 47271 | DSF0001092861, DSF0001092864
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS | Design | In-Progress | 10/31/2024 | 3/21/2025 |  | 173634 | 173634 | 4242 | DSF0001092861, DSF0001092864
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS | Construction | PNS | PNS | PNS | PNS | 2738227 | 2738227 | 31230 | DSF0001092861, DSF0001092864
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 294436 | 294436 | 8965 | DSF0001092861, DSF0001092864
16 | K309 | P.S. 309 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112677
16 | K309 | P.S. 309 - BROOKLYN | DOE - RESOA | RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 226890 | 0 | DSF0001033540
16 | K309 | P.S. 309 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112676
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | Scope | Complete | 4/21/2022 | 8/5/2022 | 9/13/2022 | 21510 | 31289 | 31289 | DSF0001014647
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | Design | Complete | 9/28/2022 | 3/6/2023 | 3/3/2023 | 107550 | 137975 | 115787 | DSF0001014647
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | Construction | In-Progress | 10/4/2023 | 10/2/2024 |  | 2419875 | 2204702 | 1784466 | DSF0001014647
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 10/4/2023 | 10/2/2024 |  | 150570 | 149855 | 149198 | DSF0001014647
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/26/2023 | 10/26/2023 | 10/25/2023 | 12302 | 19390 | 19390 | DSF0001083848
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/26/2023 | 3/26/2024 | 4/10/2024 | 55361 | 85939 | 71160 | DSF0001083848
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 9/12/2024 | 10/16/2025 |  | 713543 | 637182 | 8059 | DSF0001083848
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 9/12/2024 | 10/16/2025 |  | 132251 | 83165 | 16354 | DSF0001083848
16 | K324 | I.S. 267 - BROOKLYN | SCA IEH | PO18-TEST ALL ROOFTOP LAYERS FOR ACM, INCL TAR PAPER AND GRAVEL LOC: AROUND MAIN STAIRCASE A, 4TH FL | Construction | In-Progress | 1/9/2024 | IEH |  | IEH | 0 | 0 | SCA0000072636
16 | K324 | I.S. 267 - BROOKLYN | Fast Track Projects | CTF- ROOM CONVERSIONS | Construction | In-Progress | 6/7/2023 | FTK |  | FTK | 2907746 | 2507150 | DSF0001034682
16 | K324 | LA CIMA CHARTER SCL - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0 | DSF0001034676
16 | K324 | I.S. 267 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112687
16 | K324 | I.S. 267 - BROOKLYN | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 11/30/2022 | DOES |  | DOES | 930518 | 0 | SCA0000070989
16 | K324 | I.S. 267 - BROOKLYN | DOE - Skilled Trades | CHARTER MATCH INTERIOR SPACES | Construction | In-Progress | 7/5/2023 | DOES |  | DOES | 790765 | 0 | DSF0001083983
16 | K324 | I.S. 267 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/13/2024 | DOES | 9/23/2024 | DOES | 65832 |  | DSF0001084616
16 | K335 | P.S. 335 - BROOKLYN | SCA IEH | PO18-RM 47 - TEST CEILING PLASTER AND CEILING TILE ADHESIVE FOR ACM | Construction | Complete | 12/22/2023 | IEH | 7/23/2024 | IEH | 0 | 0 | SCA0000072593
16 | K335 | P.S. 335 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE PIPE INSULATION FROM PIPE IN THE CEILING OF ROOM# 29C. PIPE MARKED WITH RED PAINT | Construction | Complete | 6/3/2024 | IEH | 7/10/2024 | IEH | 0 | 0 | SCA0000073047
16 | K335 | M.S. 898 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112689
16 | K335 | P.S. 335 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112690
16 | K335 | P.S. 335 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001008231
16 | K335 | P.S. 335 - BROOKLYN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 9/13/2023 | DOER |  | DOER | 87298 | 0 | DSF0001033066
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2/25/2020 | 7/9/2020 | 9/21/2021 | 28730 | 36041 | 36041 | DSF0000941792
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 11/10/2021 | 4/15/2022 | 5/4/2022 | 143650 | 159924 | 159924 | DSF0000941792
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 9/12/2022 | 3/4/2024 |  | 3232125 | 3058096 | 2909710 | DSF0000941792
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 9/12/2022 | 3/4/2024 |  | 203546 | 463543 | 455375 | DSF0000941792
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | GYM UPGRADE | Scope | Complete | 1/25/2023 | 5/25/2023 | 5/24/2023 | 32796 | 39837 | 39837 | DSF0001066158
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | GYM UPGRADE | Design | Complete | 7/10/2023 | 11/24/2023 | 2/13/2024 | 163980 | 126181 | 111821 | DSF0001066158
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | GYM UPGRADE | Construction | PNS | PNS | PNS | PNS | 3689546 | 3689546 | 46022 | DSF0001066158
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | GYM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 229572 | 229572 | 26970 | DSF0001066158
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM UPGRADE | Scope | Complete | 1/25/2023 | 4/25/2023 | 6/28/2023 | 5668 | 16383 | 16383 | DSF0001083962
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM UPGRADE | Design | Complete | 7/10/2023 | 11/9/2023 | 2/13/2024 | 25507 | 28936 | 2632 | DSF0001083962
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM UPGRADE | Construction | PNS | PNS | PNS | PNS | 328751 | 328751 | 3401 | DSF0001083962
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60932 | 60932 | 3346 | DSF0001083962
16 | K455 | BOYS & GIRLS HS - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 8/4/2020 | FTK |  | FTK | 478159 | 421416 | DSF0000912757
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 99000 | 0 | DSF0001033092
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DOE - RESOA | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | Complete | 6/30/2021 | DOER | 2/23/2022 | DOER | 160421 | 158262 | DSF0000867359
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 3/25/2022 | DOER | 3/28/2022 | DOER | 165615 | 30100 | DSF0000913059
16 | K455 | NELSON MANDELA SCHOOL FOR SOCIAL JUSTICE | DOE - RESOA | FY21 RESO A FABLAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0000961251
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 3/31/2022 | DOES |  | DOES | 643109 | 0 | DSF0000911925
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/1/2023 | DOES |  | DOES | 1266556 | 0 | DSF0001083760
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/10/2024 | DOES | 9/17/2024 | DOES | 65832 |  | DSF0001084907
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/24/2022 | 7/22/2022 | 4/1/2022 | 3510 | 2826 | 2826 | DSF0000960783
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 4/1/2022 | 9/26/2022 | 7/19/2022 | 15795 | 11303 | 11303 | DSF0000960783
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/8/2023 | 1/3/2024 |  | 203580 | 182984 | 147127 | DSF0000960783
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/8/2023 | 1/3/2024 |  | 168148 | 158976 | 152774 | DSF0000960783
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001033097
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/7/2022 | DOES |  | DOES | 254093 | 0 | DSF0001034236
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/12/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085478
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/16/2018 | 3/6/2019 | 2/20/2019 | 133778 | 215607 | 134626 | DSF0000868429, DSF0000868430, DSF0000868432, DSF0000891044, DSF0000891163, DSF0000891142, DSF0000891143
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2/20/2019 | 7/22/2019 | 6/30/2020 | 660659 | 864912 | 697522 | DSF0000868429, DSF0000868430, DSF0000868432, DSF0000891044, DSF0000891163, DSF0000891142, DSF0000891143
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 7/14/2021 | 10/1/2023 |  | 14153170 | 14171163 | 12799814 | DSF0000868429, DSF0000868430, DSF0000868432, DSF0000891044, DSF0000891163, DSF0000891142, DSF0000891143
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 7/14/2021 | 10/1/2023 |  | 998143 | 1190434 | 1164625 | DSF0000868429, DSF0000868430, DSF0000868432, DSF0000891044, DSF0000891163, DSF0000891142, DSF0000891143
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/27/2020 | 9/24/2020 | 6/19/2020 | 2400 | 3747 | 3747 | DSF0000960733
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/19/2020 | 12/16/2020 | 12/1/2020 | 10800 | 14989 | 14989 | DSF0000960733
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 7/7/2022 | 5/2/2023 | 5/31/2024 | 139200 | 122857 | 113023 | DSF0000960733
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 7/7/2022 | 5/2/2023 | 5/31/2024 | 226903 | 245317 | 147006 | DSF0000960733
17 | K002 | K141 SPED - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001085935
17 | K002 | I.S. 2 - BROOKLYN | Fast Track Projects | FY24 RESO A ROOM CONVERSION | Construction | PNS | FTK | FTK | FTK | FTK | 148000 | 0 | DSF0001085933
17 | K002 | I.S. 2 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/16/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001035359
17 | K002 | K141 SPED - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 200000 | 182564 | DSF0001085931
17 | K002 | K141 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0001085934
17 | K002 | I.S. 2 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/28/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084722
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | Scope | Complete | 10/12/2022 | 3/2/2023 | 1/20/2023 | 22508 | 72272 | 71809 | DSF0001009491
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | Design | Complete | 2/1/2023 | 7/5/2023 | 5/9/2023 | 112539 | 186794 | 172922 | DSF0001009491
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | Construction | In-Progress | 9/18/2023 | 3/10/2025 |  | 2532134 | 2297225 | 1617673 | DSF0001009491
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | CM,F&E | In-Progress | 9/18/2023 | 3/10/2025 |  | 157850 | 258590 | 257217 | DSF0001009491
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/3/2023 | 6/6/2023 | 6/13/2023 | 0 | 14704 | 14704 | DSF0001035363
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 7/7/2023 | 12/8/2023 | 11/9/2023 | 33000 | 57138 | 52666 | DSF0001035363
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/1/2024 | 2/24/2025 |  | 484000 | 337864 | 277065 | DSF0001035363
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 4/1/2024 | 2/24/2025 |  | 33000 | 32910 | 20516 | DSF0001035363
17 | K006 | P.S. 6 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/10/2022 | EMER |  | EMER | 39412 | 12528 | SCA0000070859
17 | K006 | P.S. 6 - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112512
17 | K006 | P.S. 6 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 9/17/2018 | DOES |  | DOES | 90004 | 0 | DSF0000865885
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | Scope | Complete | 7/18/2019 | 12/4/2019 | 12/24/2019 | 53034 | 41789 | 41789 | DSF0000891499, DSF0000936767
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | Design | Complete | 12/24/2019 | 5/27/2020 | 6/30/2020 | 265169 | 228772 | 228733 | DSF0000891499, DSF0000936767
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | Construction | In-Progress | 10/21/2022 | 4/12/2024 |  | 5966302 | 6335231 | 6082078 | DSF0000891499, DSF0000936767
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | CM,F&E | In-Progress | 10/21/2022 | 4/12/2024 |  | 371237 | 328984 | 323916 | DSF0000891499, DSF0000936767
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/15/2023 | 10/16/2023 | 10/12/2023 | 11100 | 18898 | 18898 | DSF0001083789
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/12/2023 | 3/12/2024 | 3/19/2024 | 49950 | 67220 | 57825 | DSF0001083789
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 8/6/2024 | 9/9/2025 |  | 643800 | 570300 | 4755 | DSF0001083789
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 8/6/2024 | 9/9/2025 |  | 119325 | 80114 | 20064 | DSF0001083789
17 | K022 | P.S. 705 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 301292 | 0 | DSF0000959750
17 | K022 | P.S. 705 - BROOKLYN | DOE - RESOA | FY18 RESO A SCIENCE LAB | Construction | In-Progress | 5/14/2019 | DOER |  | DOER | 250000 | 22600 | DSF0000867774
17 | K022 | P.S. 705 - BROOKLYN | DOE - Skilled Trades | DOMESTIC WATER MAIN AND VALVE REPLACEMENTS | Construction | In-Progress | 6/5/2021 | DOES |  | DOES | 115180 | 0 | DSF0001008922
17 | K022 | P.S. 705 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/15/2024 | DOES | 8/27/2024 | DOES | 50832 | 5751 | DSF0001084583
17 | K061 | I.S. 61 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / DOORS / SIDEWALK ELEVATOR / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / ELECTRICAL UPGRADE / HOT WATER HEATERS / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 10/19/2018 | 3/11/2019 | 1/31/2019 | 762293 | 290118 | 290118 | DSF0000869270, DSF0000869271, DSF0000869272, DSF0000869273, DSF0000892040, DSF0000912331, DSF0001010395, DSF0001034510, DSF0001083771, DSF0001083770
17 | K061 | I.S. 61 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / DOORS / SIDEWALK ELEVATOR / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / ELECTRICAL UPGRADE / HOT WATER HEATERS / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2/6/2019 | 7/9/2019 | 5/8/2024 | 3788468 | 3963121 | 2528727 | DSF0000869270, DSF0000869271, DSF0000869272, DSF0000869273, DSF0000892040, DSF0000912331, DSF0001010395, DSF0001034510, DSF0001083771, DSF0001083770
17 | K061 | I.S. 61 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / DOORS / SIDEWALK ELEVATOR / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / ELECTRICAL UPGRADE / HOT WATER HEATERS / FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 83250639 | 83250639 | 131699 | DSF0000869270, DSF0000869271, DSF0000869272, DSF0000869273, DSF0000892040, DSF0000912331, DSF0001010395, DSF0001034510, DSF0001083771, DSF0001083770
17 | K061 | I.S. 61 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / DOORS / SIDEWALK ELEVATOR / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / ELECTRICAL UPGRADE / HOT WATER HEATERS / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 5508591 | 5508591 | 293094 | DSF0000869270, DSF0000869271, DSF0000869272, DSF0000869273, DSF0000892040, DSF0000912331, DSF0001010395, DSF0001034510, DSF0001083771, DSF0001083770
17 | K061 | I.S. 61 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REMOVE APPROXIMATELY 6 SQUARE FEET OF CAFE CEILING MARKED WITH GREY DUCT TAPE | Construction | Complete | 9/6/2024 | IEH | 9/7/2024 | IEH | 0 | 0 | SCA0000073362
17 | K061 | I.S. 61 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REMOVE APPROXIMATELY 6 SQUARE FEET OF CAFE CEILING MARKED WITH GREY DUCT TAPE | Construction | Complete | 9/9/2024 | IEH | 9/13/2024 | IEH | 0 | 0 | SCA0000073358
17 | K061 | I.S. 61 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 150000 | 0 | DSF0000890746
17 | K061 | K753 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001033133
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 12/1/2021 | 4/5/2022 | 1/19/2023 | 139292 | 212873 | 210287 | DSF0000985982, DSF0000985977, DSF0001083854, DSF0001061435, DSF0001061434, DSF0001061433
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 1/20/2023 | 6/22/2023 | 5/12/2023 | 691081 | 505855 | 441830 | DSF0000985982, DSF0000985977, DSF0001083854, DSF0001061435, DSF0001061434, DSF0001061433
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 9/18/2023 | 2/3/2026 |  | 15083717 | 13773738 | 7110346 | DSF0000985982, DSF0000985977, DSF0001083854, DSF0001061435, DSF0001061434, DSF0001061433
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 9/18/2023 | 2/3/2026 |  | 1015426 | 405821 | 402937 | DSF0000985982, DSF0000985977, DSF0001083854, DSF0001061435, DSF0001061434, DSF0001061433
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/30/2024 | 5/29/2024 | 4/2/2024 | 4403 | 5040 | 5040 | DSF0001087385
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/2/2024 | 9/26/2024 | 9/25/2024 | 19814 | 20160 | 20160 | DSF0001087385
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 255384 | 255384 | 3416 | DSF0001087385
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 51074 | 51074 | 4523 | DSF0001087385
17 | K091 | P.S. 91 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 7/6/2023 | DOEL |  | DOEL | 232182 | 230182
17 | K091 | P.S. 91 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/12/2024 | DOER |  | DOER | 18044 | 0 | DSF0001035410
17 | K091 | P.S. 91 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/20/2021 | DOES |  | DOES | 56204 | 0 | DSF0001009033
17 | K092 | P.S. 92 - BROOKLYN | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE CARTS | F&E | PNS | PNS | PNS | PNS | 200000 | 200000 | 0 | DSF0001112559
17 | K092 | P.S. 92 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0000913213
17 | K092 | P.S. 92 - BROOKLYN | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 9394 | 0 | DSF0001035599
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2/10/2021 | 7/20/2021 | 9/30/2022 | 2062074 | 1795143 | 1768469 | DSF0001008556
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | In-Progress | 10/3/2022 | 3/8/2022 |  | 8248296 | 8248296 | 1846485 | DSF0001008556
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 113929593 | 113929593 | 164933 | DSF0001008556
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 14950037 | 14950037 | 443794 | DSF0001008556
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2/8/2021 | 3/5/2021 | 3/5/2021 | 18590 | 71007 | 71007 | DSF0001008556
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 3/8/2021 | 5/21/2021 | 7/21/2022 | 92950 | 567237 | 319337 | DSF0001008556
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Construction | In-Progress | 10/31/2022 | 12/29/2022 |  | 2091375 | 2801260 | 2686314 | DSF0001008556
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 10/31/2022 | 12/29/2022 |  | 130130 | 471882 | 399121 | DSF0001008556
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 11/29/2018 | 4/17/2019 | 8/26/2019 | 86270 | 120061 | 120011 | DSF0000870205, DSF0000870207, DSF0000870208, DSF0000960499
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 8/28/2019 | 2/3/2020 | 4/28/2020 | 422009 | 409483 | 371598 | DSF0000870205, DSF0000870207, DSF0000870208, DSF0000960499
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 10/17/2022 | 7/7/2024 |  | 8687347 | 9077669 | 8278947 | DSF0000870205, DSF0000870207, DSF0000870208, DSF0000960499
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 10/17/2022 | 7/7/2024 |  | 673931 | 417350 | 400696 | DSF0000870205, DSF0000870207, DSF0000870208, DSF0000960499
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/8/2023 | 6/6/2023 | 6/13/2023 | 0 | 20696 | 20696 | DSF0001035439
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 46016 | 25320 | 6845 | DSF0001035439
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 674896 | 814904 | 8620 | DSF0001035439
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 46016 | 55562 | 1466 | DSF0001035439
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 3/8/2023 | 6/7/2023 |  | 0 | 0 | 0 | DSF0001035440
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 4 | 4 | 0 | DSF0001035440
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 64 | 0 | 0 | DSF0001035440
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 4 | 4 | 430 | DSF0001035440
17 | K138 | P.S. 138 - BROOKLYN | SCA IEH | PO18-ABATE WALLS, CEILING, AND PIPING LOC: ROOM 202 AND STAIRCASE J PIPE IS MARKED, PICTURES PROVIDE | Construction | Complete | 9/24/2024 | IEH | 11/2/2024 | IEH | 0 | 0 | SCA0000073417
17 | K138 | P.S. 138 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR ACM PLASTER WALLS AND CEILING IN LOCATION 211 - BOYS BATHROOM (SPACE ID 4011) | Construction | Complete | 12/17/2024 | IEH | 12/21/2024 | IEH | 0 | 0 | SCA0000073725
17 | K138 | P.S. 138 - BROOKLYN | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 200000 | 200000 | 0 | DSF0000961277
17 | K138 | P.S. 138 - BROOKLYN | Fast Track Projects | FIRE SPRINKLER | Construction | In-Progress | 9/12/2019 | FTK |  | FTK | 259025 | 259025 | DSF0000892983
17 | K138 | P.S. 138 - BROOKLYN | Fast Track Projects | RPZ VALVES | Construction | In-Progress | 9/12/2019 | FTK |  | FTK | 1288683 | 1284313 | DSF0000892975
17 | K138 | EXPLORE EMPOWER CHARTER SCHL - K | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 35000 | 0 | DSF0000913530
17 | K138 | P.S. 138 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | Complete | 12/14/2020 | DOES | 12/28/2021 | DOES | 119598 |  | DSF0000960486
17 | K138 | P.S. 138 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/30/2024 | DOES | 9/6/2024 | DOES | 65832 |  | DSF0001084594
17 | K161 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/10/2021 | 12/9/2021 | 10/22/2021 | 170674 | 211249 | 211249 | DSF0000987032, DSF0000987033, DSF0000987034, DSF0001011811
17 | K161 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 11/3/2021 | 6/30/2022 | 4/29/2022 | 848576 | 457749 | 457749 | DSF0000987032, DSF0000987033, DSF0000987034, DSF0001011811
17 | K161 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 8/11/2022 | 8/9/2024 |  | 18678278 | 17245441 | 16203401 | DSF0000987032, DSF0000987033, DSF0000987034, DSF0001011811
17 | K161 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 8/11/2022 | 8/9/2024 |  | 1231358 | 554009 | 551677 | DSF0000987032, DSF0000987033, DSF0000987034, DSF0001011811
17 | K161 | P.S. 161 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN STAIRCASE C, D, E, F & G LANDINGS, ON 1ST, 2ND, 3RD, 4TH, AND | Construction | Complete | 11/18/2024 | IEH | 11/19/2024 | IEH | 0 | 0 | SCA0000073618
17 | K161 | P.S. 161 - BROOKLYN | Fast Track Projects | CTF- CHARTER MATCH PROMETHEAN BOARDS | Construction | In-Progress | 7/29/2019 | FTK |  | FTK | 289087 | 288587 | DSF0000888771
17 | K161 | P.S. 161 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/12/2024 | DIIR | 10/16/2024 | DIIR | 225205 | 225205 | DSF0001086003
17 | K161 | SUCCESS ACADEMY CROWN HEIGHTS (BROOKLYN 7) | DOE - RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 11/2/2021 | DOER |  | DOER | 1008060 | 0 | DSF0000844991
17 | K167 | NEW BRIDGES | SCA CIP | COVID VENTILATION | Scope | Complete | 8/28/2020 | 12/28/2020 | 1/25/2021 | 50600 | 86110 | 86110 | DSF0000961099
17 | K167 | NEW BRIDGES | SCA CIP | COVID VENTILATION | Design | Complete | 2/3/2021 | 7/9/2021 | 12/22/2021 | 253000 | 465501 | 326642 | DSF0000961099
17 | K167 | NEW BRIDGES | SCA CIP | COVID VENTILATION | Construction | In-Progress | 7/5/2022 | 7/4/2023 |  | 5692500 | 5724065 | 3531090 | DSF0000961099
17 | K167 | NEW BRIDGES | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 7/5/2022 | 7/4/2023 |  | 354200 | 596780 | 592507 | DSF0000961099
17 | K167 | NEW BRIDGES | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 12/1/2023 | 4/2/2024 | 5/31/2024 | 0 | 14492 | 14429 | DSF0001086006
17 | K167 | NEW BRIDGES | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 6/4/2024 | 11/5/2024 |  | 30000 | 16625 | 16625 | DSF0001086006
17 | K167 | NEW BRIDGES | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 2861 | DSF0001086006
17 | K167 | NEW BRIDGES | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 13310 | DSF0001086006
17 | K167 | NEW BRIDGES | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 3/27/2024 | 6/27/2024 | 7/25/2024 | 0 | 253 | 253 | DSF0001087014
17 | K167 | NEW BRIDGES | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | In-Progress | 7/31/2024 | 12/2/2024 |  | 3438 | 1012 | 1012 | DSF0001087014
17 | K167 | NEW BRIDGES | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 50423 | 50423 | 0 | DSF0001087014
17 | K167 | NEW BRIDGES | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 3438 | 3438 | 2467 | DSF0001087014
17 | K167 | NEW BRIDGES | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 2/16/2024 | DOER |  | DOER | 76434 | 0 | DSF0001035453
17 | K167 | NEW BRIDGES | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/17/2021 | DOES |  | DOES | 74879 | 0 | DSF0001008989
17 | K181 | P.S. 181 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112597
17 | K181 | P.S. 181 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 6/23/2021 | DOER | 12/21/2021 | DOER | 155722 | 164846 | DSF0000913050
17 | K181 | P.S. 181 - BROOKLYN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 4/28/2023 | DOER |  | DOER | 71934 | 0 | DSF0001033495
17 | K181 | P.S. 181 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | Complete | 2/13/2020 | DOES | 1/13/2021 | DOES | 71940 |  | DSF0000960487
17 | K181 | P.S. 181 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084599
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 3/11/2021 | 7/26/2021 | 11/19/2021 | 84670 | 154383 | 154383 | DSF0001012285, DSF0001012289, DSF0001012288, DSF0001012287
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 12/22/2021 | 5/25/2022 | 5/11/2022 | 423350 | 488081 | 488081 | DSF0001012285, DSF0001012289, DSF0001012288, DSF0001012287
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 11/14/2022 | 8/4/2024 |  | 9525375 | 8942588 | 8065298 | DSF0001012285, DSF0001012289, DSF0001012288, DSF0001012287
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 11/14/2022 | 8/4/2024 |  | 593843 | 487388 | 486759 | DSF0001012285, DSF0001012289, DSF0001012288, DSF0001012287
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/20/2020 | 9/18/2020 | 6/19/2020 | 3720 | 4446 | 4446 | DSF0000960740
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/19/2020 | 12/16/2020 | 11/25/2020 | 16740 | 17785 | 17785 | DSF0000960740
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 7/7/2022 | 5/2/2023 | 5/31/2024 | 215760 | 192261 | 178230 | DSF0000960740
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 7/7/2022 | 5/2/2023 | 5/31/2024 | 200835 | 200222 | 108675 | DSF0000960740
17 | K189 | P.S. 189 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 12/6/2021 | DOER |  | DOER | 152582 | 0 | DSF0000913237
17 | K189 | P.S. 189 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 528550 | 0 | DSF0001083759
17 | K189 | P.S. 189 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/31/2024 | DOES | 11/8/2024 | DOES | 65832 |  | DSF0001084601
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM | Scope | Complete | 5/31/2023 | 11/29/2023 | 11/17/2023 | 291793 | 179883 | 176044 | DSF0001083815, DSF0001111856, DSF0001111858, DSF0001111860
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM | Design | Complete | 11/22/2023 | 6/28/2024 | 5/6/2024 | 1454172 | 683308 | 630541 | DSF0001083815, DSF0001111856, DSF0001111858, DSF0001111860
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM | Construction | PNS | PNS | PNS | PNS | 32304275 | 32304275 | 116781 | DSF0001083815, DSF0001111856, DSF0001111858, DSF0001111860
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM | CM,F&E | PNS | PNS | PNS | PNS | 2078497 | 2078497 | 122361 | DSF0001083815, DSF0001111856, DSF0001111858, DSF0001111860
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/14/2024 | 6/13/2024 | 4/19/2024 | 4068 | 3690 | 3690 | DSF0001087417
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/19/2024 | 10/16/2024 | 9/25/2024 | 18305 | 14758 | 14758 | DSF0001087417
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 235937 | 235937 | 9130 | DSF0001087417
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 43730 | 43730 | 3992 | DSF0001087417
17 | K191 | P.S. 191 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE APPROX 60 LF PIPE COVERING ABOVE 4TH FL HALLWAY CEILING PIPES ARE MARKED. ACTI | Construction | Complete | 11/13/2024 | IEH | 11/16/2024 | IEH | 0 | 0 | SCA0000073604
17 | K191 | P.S. 191 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 4/10/2023 | DOES |  | DOES | 1044424 | 0 | DSF0000889270
17 | K191 | P.S. 191 - BROOKLYN | DOE - Skilled Trades | REPLACE LEAKING STEEL HOT WATER STORAGE TANK | Construction | In-Progress | 8/1/2022 | DOES |  | DOES | 201216 | 0 | DSF0000893772
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 6/9/2023 | 12/8/2023 | 10/6/2023 | 186305 | 244335 | 244062 | DSF0001063444, DSF0001063446, DSF0001087234, DSF0001087233, DSF0001087235
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Design | Complete | 10/20/2023 | 6/11/2024 | 4/19/2024 | 919057 | 435737 | 432818 | DSF0001063444, DSF0001063446, DSF0001087234, DSF0001087233, DSF0001087235
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Construction | In-Progress | 7/22/2024 | 1/7/2027 |  | 19600625 | 17915072 | 1750245 | DSF0001063444, DSF0001063446, DSF0001087234, DSF0001087233, DSF0001087235
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | CM,F&E | In-Progress | 7/22/2024 | 1/7/2027 |  | 1397612 | 251143 | 246636 | DSF0001063444, DSF0001063446, DSF0001087234, DSF0001087233, DSF0001087235
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/5/2022 | 4/6/2023 | 12/9/2022 | 4880 | 6440 | 6440 | DSF0001034643
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/9/2022 | 6/7/2023 | 3/8/2023 | 21960 | 25758 | 25758 | DSF0001034643
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 6/5/2023 | 4/29/2024 | 7/8/2024 | 283040 | 255930 | 146886 | DSF0001034643
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 6/5/2023 | 4/29/2024 | 7/8/2024 | 169567 | 156197 | 102051 | DSF0001034643
17 | K210 | I.S. 394 - BROOKLYN | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Construction | Complete | 5/28/2021 | DOER | 9/27/2021 | DOER | 137992 | 185389 | DSF0000913053
17 | K210 | I.S. 394 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/7/2024 | DOES | 10/16/2024 | DOES | 65832 | 7779 | DSF0001084606
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 7/6/2022 | 11/21/2022 | 8/18/2023 | 55897 | 141078 | 137281 | DSF0001012957, DSF0001012958, DSF0001012959, DSF0001063667
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 9/12/2023 | 2/15/2024 | 3/7/2024 | 269329 | 189918 | 168440 | DSF0001012957, DSF0001012958, DSF0001012959, DSF0001063667
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 5181474 | 5181474 | 60961 | DSF0001012957, DSF0001012958, DSF0001012959, DSF0001063667
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 467445 | 467445 | 24985 | DSF0001012957, DSF0001012958, DSF0001012959, DSF0001063667
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/31/2024 | 5/30/2024 | 4/3/2024 | 3931 | 67 | 67 | DSF0001087430
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/3/2024 | 9/27/2024 | 9/19/2024 | 17689 | 270 | 270 | DSF0001087430
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 227985 | 227985 | 8092 | DSF0001087430
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 45996 | 45996 | 2998 | DSF0001087430
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/15/2023 | 4/18/2024 | 12/11/2024 | 0 | 22558 | 10537 | DSF0001086029
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 12/16/2024 | 5/19/2025 |  | 30000 | 15598 | 15598 | DSF0001086029
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001086029
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 8870 | DSF0001086029
17 | K221 | P.S. 221 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION @K221 | Construction | In-Progress | 7/21/2023 | EMER |  | EMER | 51653 | 48600 | SCA0000072154
17 | K221 | P.S. 221 - BROOKLYN | Fast Track Projects | PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 4/5/2019 | FTK |  | FTK | 52061 | 38184 | DSF0000912259
17 | K221 | P.S. 221 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001035477
17 | K221 | P.S. 221 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75150 | 0 | DSF0000781221
17 | K221 | P.S. 221 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/18/2022 | DOES |  | DOES | 31112 | 0 | DSF0001008679
17 | K221 | P.S. 221 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/14/2022 | DOES |  | DOES | 148252 | 0 | DSF0001034410
17 | K241 | P.S. 241 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/31/2024 | 5/30/2024 | 4/3/2024 | 4004 | 164 | 164 | DSF0001087432
17 | K241 | P.S. 241 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/3/2024 | 9/27/2024 | 9/19/2024 | 18019 | 656 | 656 | DSF0001087432
17 | K241 | P.S. 241 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 232248 | 232248 | 4073 | DSF0001087432
17 | K241 | P.S. 241 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 46786 | 46786 | 2757 | DSF0001087432
17 | K241 | P.S. 241 - BROOKLYN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 7/18/2024 |  | 7/26/2024 | 100000 | 100000 | 99829 | DSF0001035492
17 | K241 | P.S. 241 - BROOKLYN | DOE - Skilled Trades | EMERGENCY HEATING PLANT UPGRADE | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 722916 | 0 | DSF0001111880
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | Scope | Complete | 6/14/2023 | 10/13/2023 | 1/9/2024 | 149220 | 299877 | 149877 | DSF0001091859, DSF0001091850, DSF0001091849
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | Design | Complete | 1/16/2024 | 7/18/2024 | 5/10/2024 | 746100 | 791843 | 420790 | DSF0001091859, DSF0001091850, DSF0001091849
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | Construction | In-Progress | 8/12/2024 | 8/11/2026 |  | 16787250 | 15151849 | 6179 | DSF0001091859, DSF0001091850, DSF0001091849
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | CM,F&E | In-Progress | 8/12/2024 | 8/11/2026 |  | 1044540 | 210475 | 202480 | DSF0001091859, DSF0001091850, DSF0001091849
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/14/2023 | 6/15/2023 | 5/19/2023 | 0 | 28435 | 28435 | DSF0001035497, DSF0001035498
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 5/19/2023 | 10/5/2023 | 10/20/2023 | 60000 | 91202 | 62986 | DSF0001035497, DSF0001035498
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 4/25/2024 | 3/20/2025 |  | 880000 | 510690 | 359551 | DSF0001035497, DSF0001035498
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 4/25/2024 | 3/20/2025 |  | 130841 | 129328 | 56718 | DSF0001035497, DSF0001035498
17 | K246 | I.S. 246 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMPS | Construction | In-Progress | 4/1/2020 | DOES |  | DOES | 365485 | 0 | DSF0000911930
17 | K246 | I.S. 246 - BROOKLYN | DOE - Skilled Trades | SEWAGE EJECTOR PUMPS | Construction | In-Progress | 12/14/2020 | DOES |  | DOES | 79732 | 0 | DSF0000988664
17 | K246 | I.S. 246 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 10/12/2023 | DOES |  | DOES | 1749678 | 0 | DSF0001064179
17 | K246 | I.S. 246 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/4/2024 | DOES | 9/13/2024 | DOES | 65832 |  | DSF0001084755
17 | K246 | I.S. 246 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/29/2024 | DOES |  | DOES | 644608 | 0 | DSF0001111719
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/24/2022 | 11/9/2022 | 12/16/2022 | 93351 | 169728 | 163975 | DSF0001013489, DSF0001013490, DSF0001013491, DSF0001083822
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/10/2023 | 6/12/2023 | 5/10/2023 | 462806 | 390853 | 347640 | DSF0001013489, DSF0001013490, DSF0001013491, DSF0001083822
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 8/21/2023 | 1/6/2026 |  | 10071331 | 9254682 | 5281255 | DSF0001013489, DSF0001013490, DSF0001013491, DSF0001083822
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 8/21/2023 | 1/6/2026 |  | 683096 | 221915 | 220079 | DSF0001013489, DSF0001013490, DSF0001013491, DSF0001083822
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/25/2024 | 10/24/2024 | 8/8/2024 | 4706 | 2918 | 2918 | DSF0001087435
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 8/8/2024 | 2/6/2025 |  | 21178 | 21178 | 11671 | DSF0001087435
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 272958 | 272958 | 0 | DSF0001087435
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 50591 | 50591 | 4855 | DSF0001087435
17 | K249 | P.S. 249 - BROOKLYN | DOE - RESOA | RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001087169
17 | K249 | P.S. 249 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMPS | Construction | In-Progress | 6/28/2021 | DOES |  | DOES | 401566 | 0 | DSF0000911929
17 | K249 | P.S. 249 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 1/17/2020 | DOES |  | DOES | 262361 | 0 | DSF0000912217
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/27/2024 | 11/13/2024 | 11/6/2024 | 148133 | 96114 | 72539 | DSF0001064893, DSF0001120282
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 11/18/2024 | 4/22/2025 |  | 733791 | 733791 | 259734 | DSF0001064893, DSF0001120282
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 15871252 | 15871252 | 0 | DSF0001064893, DSF0001120282
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1043800 | 1043800 | 26800 | DSF0001064893, DSF0001120282
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/8/2022 | 4/11/2023 | 12/20/2022 | 5000 | 4185 | 4185 | DSF0001034635
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/20/2022 | 6/16/2023 | 3/8/2023 | 22500 | 16740 | 16740 | DSF0001034635
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 6/5/2023 | 4/29/2024 | 7/8/2024 | 290000 | 259509 | 145901 | DSF0001034635
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 6/5/2023 | 4/29/2024 | 7/8/2024 | 134871 | 115328 | 61164 | DSF0001034635
17 | K289 | P.S. 289 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE ACM-WRAPPED WASTELINE IN CRAWL SPACE SPACE ID 1013A. WASTELINE IS LEAKING APPR | Construction | Complete | 10/25/2024 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000073542
17 | K289 | P.S. 289 - BROOKLYN | DOE - Skilled Trades | REPLACE TELEDYNE LAARS HOT WATER BOILER | Construction | In-Progress | 7/11/2019 | DOES |  | DOES | 39172 | 0 | DSF0000872616
17 | K289 | P.S. 289 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | Complete | 11/18/2020 | DOES | 5/24/2021 | DOES | 103324 |  | DSF0000960489
17 | K289 | P.S. 289 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/4/2024 | DOES | 7/16/2024 | DOES | 65832 |  | DSF0001084137
17 | K316 | P.S. 316 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 7/21/2023 | 10/23/2023 |  | 0 | 0 | 0 | DSF0001035537
17 | K316 | P.S. 316 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035537
17 | K316 | P.S. 316 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035537
17 | K316 | P.S. 316 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035537
17 | K316 | P.S. 316 - BROOKLYN | SCA IEH | PO18-REMOVE IF POSITIVE, CORNER WALL & FLOOR CONTAINING STEAM PIPE TO ALLOW ACCESS TO LEAKING STEAM | Construction | Complete | 11/21/2024 | IEH | 11/24/2024 | IEH | 0 | 0 | SCA0000073630
17 | K316 | M.S. 353 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 326168 | 326168 | 0 | DSF0001086080
17 | K316 | P.S. 316 - BROOKLYN | Fast Track Projects | LSP- CONDENSATE PUMP & STEAM TRAP REPLACEMENT | Construction | In-Progress | 9/6/2023 | FTK |  | FTK | 660763 | 483920 | DSF0001065281
17 | K316 | M.S. 353 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001112680
17 | K316 | P.S. 316 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 10/27/2023 | DOEL |  | DOEL | 75790 | 75790
17 | K316 | P.S. 316 - BROOKLYN | DOE - RESOA | RESO A FENCING | Construction | In-Progress | 5/23/2017 | DOER |  | DOER | 126877 | 0 | DSF0000845591
17 | K316 | P.S. 316 - BROOKLYN | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 5/4/2021 | DOER |  | DOER | 156587 | 0 | DSF0000913269
17 | K316 | P.S. 316 - BROOKLYN | DOE - RESOA | FY22 RESO A CAFETERIA SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 227000 | 0 | DSF0001033543
17 | K316 | P.S. 316 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001035536
17 | K316 | P.S. 316 - BROOKLYN | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 170000 | 0 | DSF0001112682
17 | K316 | P.S. 316 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | Complete | 3/23/2020 | DOES | 8/18/2021 | DOES | 86832 |  | DSF0000960490
17 | K320 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/15/2023 | 12/14/2023 | 11/2/2023 | 129163 | 141157 | 141157 | DSF0001065337, DSF0001111776, DSF0001111774
17 | K320 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/20/2023 | 4/23/2024 | 4/18/2024 | 636400 | 331974 | 331974 | DSF0001065337, DSF0001111776, DSF0001111774
17 | K320 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 9/16/2024 | 3/4/2027 |  | 13504847 | 12674056 | 368289 | DSF0001065337, DSF0001111776, DSF0001111774
17 | K320 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/16/2024 | 3/4/2027 |  | 974731 | 100021 | 99661 | DSF0001065337, DSF0001111776, DSF0001111774
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/29/2023 | 3/1/2024 | 3/22/2024 | 0 | 20565 | 20565 | DSF0001086083
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 7/9/2024 | 11/22/2024 |  | 42141 | 34506 | 23818 | DSF0001086083
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 618066 | 618066 | 0 | DSF0001086083
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 42141 | 42141 | 12890 | DSF0001086083
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 8/8/2024 | 11/7/2024 | 9/19/2024 | 0 | 0 | 7630 | DSF0001087026
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 9/19/2024 | 1/27/2025 |  | 1659 | 1659 | 1168 | DSF0001087026
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 24334 | 24334 | 0 | DSF0001087026
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 1659 | 1659 | 11628 | DSF0001087026
17 | K320 | M.S. 352 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE CARTS | F&E | Complete | 3/21/2024 |  | 7/24/2024 | 150606 | 150606 | 67550 | DSF0001086085
17 | K320 | M.S. 352 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 150000 | DSF0001086086
17 | K320 | M.S. 352 - BROOKLYN | DIIT - RESOA | RESO A-FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 99647 | 0 | DSF0001008622
17 | K320 | P.S. 375 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/13/2021 | DOER |  | DOER | 298163 | 0 | DSF0001008222
17 | K320 | M.S. 352 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/18/2024 | DOER |  | DOER | 310349 | 0 | DSF0001035540
17 | K320 | M.S. 352 - BROOKLYN | DOE - RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086081
17 | K320 | P.S. 375 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086082
17 | K320 | M.S. 352 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001112685
17 | K320 | P.S. 375 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/29/2022 | DOES |  | DOES | 181789 | 0 | DSF0001034229
17 | K390 | M.S. 354 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / SECURITY LIGHTING / EXTERIOR DOORS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 7/13/2023 | 11/29/2023 | 1/11/2024 | 274233 | 433406 | 166970 | DSF0001065766, DSF0001065767, DSF0001111912, DSF0001093430, DSF0001093419, DSF0001093415, DSF0001112308
17 | K390 | M.S. 354 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / SECURITY LIGHTING / EXTERIOR DOORS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | In-Progress | 6/12/2024 | 11/14/2024 |  | 1339277 | 1339277 | 36698 | DSF0001065766, DSF0001065767, DSF0001111912, DSF0001093430, DSF0001093419, DSF0001093415, DSF0001112308
17 | K390 | M.S. 354 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / SECURITY LIGHTING / EXTERIOR DOORS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Construction | PNS | PNS | PNS | PNS | 28321044 | 28321044 | 239330 | DSF0001065766, DSF0001065767, DSF0001111912, DSF0001093430, DSF0001093419, DSF0001093415, DSF0001112308
17 | K390 | M.S. 354 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / SECURITY LIGHTING / EXTERIOR DOORS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 2163210 | 2163210 | 112627 | DSF0001065766, DSF0001065767, DSF0001111912, DSF0001093430, DSF0001093419, DSF0001093415, DSF0001112308
17 | K390 | M.S. 354 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0 | DSF0000889767
17 | K390 | M.S. 354 - BROOKLYN | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/12/2021 | DOER |  | DOER | 105553 | 0 | DSF0000913278
17 | K390 | M.S. 354 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 12/28/2020 | DOES |  | DOES | 149318 | 0 | DSF0000912585
17 | K390 | M.S. 354 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/9/2024 | DOES |  | DOES | 580759 | 0 | DSF0001085727
17 | K391 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | Scope | Complete | 6/15/2023 | 10/16/2023 | 10/2/2023 | 67150 | 45066 | 45066 | DSF0001093443, DSF0001087239
17 | K391 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | Design | Complete | 10/17/2023 | 4/22/2024 | 4/25/2024 | 335750 | 379073 | 271894 | DSF0001093443, DSF0001087239
17 | K391 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | Construction | In-Progress | 9/9/2024 | 9/8/2026 |  | 7554375 | 6807075 | 13485 | DSF0001093443, DSF0001087239
17 | K391 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | CM,F&E | In-Progress | 9/9/2024 | 9/8/2026 |  | 470050 | 71514 | 69680 | DSF0001093443, DSF0001087239
17 | K391 | I.S. 722 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 75200 | 0 | DSF0000783170
17 | K391 | I.S. 722 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/11/2023 | DOES | 11/6/2023 | DOES | 657741 |  | DSF0001035154
17 | K391 | I.S. 722 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/2/2024 | DOES | 11/20/2024 | DOES | 65832 |  | DSF0001084769
17 | K397 | P.S. 397 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 101563 | 0 | DSF0001086108
17 | K397 | P.S. 397 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 205000 | 0 | DSF0001112699
17 | K397 | P.S. 397 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/12/2019 | DOES |  | DOES | 112463 | 0 | DSF0000889595
17 | K398 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/18/2016 | 4/18/2017 | 2/14/2017 | 26400 | 98764 | 98725 | DSF0000844129
17 | K398 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | Complete | 7/11/2019 | 1/14/2020 | 12/31/2019 | 132000 | 238990 | 238990 | DSF0000844129
17 | K398 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 2/20/2023 | 2/19/2024 |  | 2970000 | 2988201 | 2663901 | DSF0000844129
17 | K398 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 2/20/2023 | 2/19/2024 |  | 184800 | 427540 | 414777 | DSF0000844129
17 | K398 | P.S. 398 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001033082
17 | K398 | P.S. 770 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001035552
17 | K398 | P.S. 770 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 2/2/2024 | DOER | 4/22/2024 | DOER | 140679 |  | DSF0001035553
17 | K398 | P.S. 770 - BROOKLYN | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 54633 | 0 | DSF0001035554
17 | K398 | P.S. 770 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112700
17 | K398 | P.S. 398 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 75200 | 0 | DSF0000799786
17 | K399 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | Scope | Complete | 1/27/2022 | 11/15/2022 | 11/16/2022 | 96020 | 110514 | 110514 | DSF0001015102, DSF0001015095, DSF0001015096, DSF0001015097, DSF0001015098, DSF0001015089
17 | K399 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | Design | Complete | 11/30/2022 | 5/3/2023 | 5/8/2023 | 465818 | 465149 | 360254 | DSF0001015102, DSF0001015095, DSF0001015096, DSF0001015097, DSF0001015098, DSF0001015089
17 | K399 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | Construction | In-Progress | 10/16/2023 | 3/3/2026 |  | 9245730 | 8552760 | 1986996 | DSF0001015102, DSF0001015095, DSF0001015096, DSF0001015097, DSF0001015098, DSF0001015089
17 | K399 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | CM,F&E | In-Progress | 10/16/2023 | 3/3/2026 |  | 780352 | 735959 | 731436 | DSF0001015102, DSF0001015095, DSF0001015096, DSF0001015097, DSF0001015098, DSF0001015089
17 | K399 | P.S. 399 - BROOKLYN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/7/2022 | DOER |  | DOER | 189222 | 0 | DSF0000913280
17 | K399 | P.S. 399 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086109
17 | K399 | P.S. 399 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/18/2021 | DOES |  | DOES | 138082 | 0 | DSF0001008684
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Scope | Complete | 12/7/2023 | 4/10/2024 | 5/16/2024 | 0 | 21859 | 4291 | DSF0001086121
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Design | Complete | 5/21/2024 | 10/7/2024 | 12/10/2024 | 135000 | 64289 | 16910 | DSF0001086121
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1980000 | 1980000 | 39763 | DSF0001086121
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 135000 | 135000 | 10137 | DSF0001086121
17 | K440 | BROOKLYN HS FOR MUSIC &THEATER - K | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/7/2023 | 4/10/2024 | 5/21/2024 | 0 | 19139 | 19139 | DSF0001086122
17 | K440 | BROOKLYN HS FOR MUSIC &THEATER - K | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | Complete | 5/22/2024 | 10/8/2024 | 12/10/2024 | 87000 | 64381 | 61098 | DSF0001086122
17 | K440 | BROOKLYN HS FOR MUSIC &THEATER - K | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1276000 | 1276000 | 3216 | DSF0001086122
17 | K440 | BROOKLYN HS FOR MUSIC &THEATER - K | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 87000 | 87000 | 9888 | DSF0001086122
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 4/4/2024 | 7/8/2024 | 7/23/2024 | 0 | 0 | 0 | DSF0001087032
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | Complete | 7/23/2024 | 11/25/2024 | 12/10/2024 | 10843 | 10843 | 0 | DSF0001087032
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 159034 | 159034 | 0 | DSF0001087032
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 10843 | 10843 | 4616 | DSF0001087032
17 | K440 | BROOKLYN HS FOR SCI & THE ENVI-K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 4/4/2024 | 7/8/2024 | 7/23/2024 | 0 | 0 | 0 | DSF0001087033
17 | K440 | BROOKLYN HS FOR SCI & THE ENVI-K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 7/23/2024 | 11/25/2024 | 12/10/2024 | 12268 | 12268 | 0 | DSF0001087033
17 | K440 | BROOKLYN HS FOR SCI & THE ENVI-K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 179935 | 179935 | 0 | DSF0001087033
17 | K440 | BROOKLYN HS FOR SCI & THE ENVI-K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 12268 | 12268 | 3047 | DSF0001087033
17 | K440 | THE INTERNATIONAL HS - BROOKLYN | Fast Track Projects | LSP STAGE RIGGING / STRUCTURAL STEEL | Construction | In-Progress | 3/31/2022 | FTK |  | FTK | 533607 | 328987 | DSF0000912582
17 | K440 | BROOKLYN HS FOR MUSIC &THEATER - K | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001033579
17 | K440 | THE INTERNATIONAL HS - BROOKLYN | DOE - RESOA | FY23 RESO A LOCKER ROOM UPGRADE | Construction | Complete | 5/10/2024 | DOER | 6/26/2024 | DOER | 269532 |  | DSF0001035574
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 124988 | 0 | DSF0001086123
17 | K440 | BROOKLYN HS FOR SCI & THE ENVI-K | DOE - Skilled Trades | REPLACE/UPGRADE STAGE RIGGING COMPONENTS | Construction | In-Progress | 12/21/2018 | DOES |  | DOES | 447006 | 0 | DSF0000873548
17 | K440 | THE INTERNATIONAL HS - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/29/2023 | DOES |  | DOES | 231648 | 0 | DSF0001034232
17 | K440 | THE INTERNATIONAL HS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/21/2024 | DOES | 10/31/2024 | DOES | 65832 |  | DSF0001084904
17 | K457 | BROOKLYN ACADEMY HS - BROOKLYN | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 766000 | 0 | DSF0001112714
17 | K457 | BROOKLYN ACADEMY HS - BROOKLYN | DOE - Skilled Trades | ATHLETIC FIELD | Construction | In-Progress | 9/7/2023 | DOES |  | DOES | 690893 | 0 | DSF0001086871
17 | K465 | I.S. 382 - BROOKLYN | SCA CIP | PARAPET AND SIDE OF BUILDING DAMAGE @ K465 / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION / WINDOWS / ROOFTOP MECHANICAL EQUIPMENT UPGRADE | Scope | Complete | 6/25/2021 | 11/24/2021 | 1/25/2022 | 622794 | 415741 | 415741 | DSF0001015453, DSF0001015455, DSF0001015452, DSF0001015450, DSF0001087242, DSF0001121709
17 | K465 | I.S. 382 - BROOKLYN | SCA CIP | PARAPET AND SIDE OF BUILDING DAMAGE @ K465 / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION / WINDOWS / ROOFTOP MECHANICAL EQUIPMENT UPGRADE | Design | Complete | 1/26/2022 | 6/27/2022 | 5/11/2022 | 3106712 | 1695616 | 1524989 | DSF0001015453, DSF0001015455, DSF0001015452, DSF0001015450, DSF0001087242, DSF0001121709
17 | K465 | I.S. 382 - BROOKLYN | SCA CIP | PARAPET AND SIDE OF BUILDING DAMAGE @ K465 / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION / WINDOWS / ROOFTOP MECHANICAL EQUIPMENT UPGRADE | Construction | PNS | PNS | PNS | PNS | 69226532 | 69226532 | 1180316 | DSF0001015453, DSF0001015455, DSF0001015452, DSF0001015450, DSF0001087242, DSF0001121709
17 | K465 | I.S. 382 - BROOKLYN | SCA CIP | PARAPET AND SIDE OF BUILDING DAMAGE @ K465 / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION / WINDOWS / ROOFTOP MECHANICAL EQUIPMENT UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 4366803 | 4366803 | 115982 | DSF0001015453, DSF0001015455, DSF0001015452, DSF0001015450, DSF0001087242, DSF0001121709
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112718
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 13980 | 13980 | 0 | DSF0001112718
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 205040 | 205040 | 0 | DSF0001112718
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 13980 | 13980 | 0 | DSF0001112718
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113592
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113592
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113592
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113592
17 | K465 | I.S. 382 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/1/2020 | EMER |  | EMER | 718071 | 601007 | SCA0000068027
17 | K465 | HS FOR SERVICE AND LEARNING - K | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 408000 | 408000 | 408000 | DSF0001086130
17 | K465 | HS FOR YOUTH & COMMUNITY DEV. - K | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 213000 | 213000 | 0 | DSF0001112721
17 | K465 | SCIENCE TECH & RESEARCH - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001033102
17 | K465 | ACAD. OF HOSP. & TOURISM - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/26/2024 | DIIR | 10/7/2024 | DIIR | 99645 | 99645 | DSF0001035576
17 | K465 | I.S. 382 - BROOKLYN | DOE - RESOA | FY17 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0000844788
17 | K465 | HS FOR YOUTH & COMMUNITY DEV. - K | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 49000 | 0 | DSF0000913286
17 | K465 | ACAD. OF HOSP. & TOURISM - K | DOE - RESOA | FY24 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1275000 | 0 | DSF0001086129
17 | K465 | HS FOR YOUTH & COMMUNITY DEV. - K | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 213000 | 0 | DSF0001112719
17 | K465 | SCIENCE TECH & RESEARCH - K | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 233000 | 0 | DSF0001112720
17 | K465 | I.S. 382 - BROOKLYN | DOE - Skilled Trades | ACE- STEAM SYSTEM UPGRADE | Construction | In-Progress | 3/11/2019 | DOES |  | DOES | 189100 | 0 | DSF0000896532
17 | K470 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 6/3/2021 | 12/2/2021 | 10/27/2021 | 382790 | 350187 | 350187 | DSF0000990534, DSF0000990532, DSF0000990533, DSF0001034322
17 | K470 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Design | Complete | 11/10/2021 | 6/30/2022 | 5/9/2022 | 1913951 | 786801 | 786801 | DSF0000990534, DSF0000990532, DSF0000990533, DSF0001034322
17 | K470 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Construction | In-Progress | 9/19/2022 | 12/6/2024 |  | 43063875 | 39422401 | 34534311 | DSF0000990534, DSF0000990532, DSF0000990533, DSF0001034322
17 | K470 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | CM,F&E | In-Progress | 9/19/2022 | 12/6/2024 |  | 2679530 | 1292009 | 1288679 | DSF0000990534, DSF0000990532, DSF0000990533, DSF0001034322
17 | K470 | H.S. 745 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112723
17 | K470 | HS FOR PUBLIC SERVICE - K | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001112722
17 | K470 | INTERNATIONAL ARTS BUSINESS HS - K | DOE - Skilled Trades | STAGE RIGGING & DRAPERY | Construction | In-Progress | 1/27/2020 | DOES |  | DOES | 407498 | 0 | DSF0000821588
17 | K470 | H.S. 745 - BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/27/2023 | DOES |  | DOES | 716512 | 0 | DSF0000960843
17 | K470 | H.S. 745 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 10/31/2023 | DOES |  | DOES | 764998 | 0 | DSF0001083762
17 | K470 | H.S. 745 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/16/2024 | DOES | 7/25/2024 | DOES | 65832 | 6235 | DSF0001084910
17 | K474 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | Scope | Complete | 12/4/2019 | 4/7/2020 | 4/7/2021 | 132420 | 169950 | 168573 | DSF0000889558
17 | K474 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | Design | Complete | 4/14/2021 | 9/14/2021 | 12/15/2021 | 529680 | 1081465 | 785033 | DSF0000889558
17 | K474 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | Construction | In-Progress | 3/28/2022 | 8/19/2023 |  | 9931500 | 9784289 | 9406114 | DSF0000889558
17 | K474 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | CM,F&E | In-Progress | 3/28/2022 | 8/19/2023 |  | 636343 | 683171 | 663356 | DSF0000889558
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0000913853
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - RESOA | FY18 RESO A LIBRARY UPGRADES | Construction | In-Progress | 8/14/2023 | DOER |  | DOER | 100000 | 0 | DSF0000867324
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Construction | Complete | 3/15/2021 | DOER | 3/23/2023 | DOER | 85968 | 164560 | DSF0000913066
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 105000 | 0 | DSF0001035584
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - RESOA | RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/1/2023 | DOER |  | DOER | 272000 | 0 | DSF0001083782
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/25/2024 | DOES | 7/12/2024 | DOES | 50832 |  | DSF0001084922
17 | K600 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/13/2020 | 9/11/2020 | 6/19/2020 | 4368 | 4330 | 4330 | DSF0000960750
17 | K600 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/19/2020 | 12/16/2020 | 12/14/2020 | 19657 | 17321 | 17321 | DSF0000960750
17 | K600 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/9/2022 | 4/4/2023 |  | 253356 | 228459 | 161471 | DSF0000960750
17 | K600 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/9/2022 | 4/4/2023 |  | 266617 | 268864 | 191066 | DSF0000960750
17 | K600 | CLARA BARTON HS - K | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON SAFE DOOR LINING INSIDE ROOM 418. ROOM AS BEEN SHUT DOWN. AB | Construction | In-Progress | 9/24/2024 | IEH |  | IEH | 0 | 0 | SCA0000073415
17 | K600 | CLARA BARTON HS - K | Fast Track Projects | CTF ROOM CONVERSION / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 6/30/2023 | FTK |  | FTK | 1704397 | 1586074 | DSF0001034944, DSF0001034967
17 | K600 | CLARA BARTON HS - K | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 5/13/2016 | DOES |  | DOES | 238391 | 0 | DSF0000783858
17 | K600 | CLARA BARTON HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/7/2024 | DOES | 8/14/2024 | DOES | 65832 |  | DSF0001084924
17 | K625 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 10/28/2020 | 3/3/2021 | 3/3/2021 | 3532 | 4345 | 4345 | DSF0000960751
17 | K625 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/3/2021 | 8/25/2021 | 7/14/2021 | 15893 | 17383 | 17383 | DSF0000960751
17 | K625 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 6/9/2022 | 4/4/2023 |  | 204844 | 184963 | 133196 | DSF0000960751
17 | K625 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 6/9/2022 | 4/4/2023 |  | 229756 | 234793 | 158329 | DSF0000960751
17 | K625 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/23/2024 | DOES | 10/4/2024 | DOES | 65832 | 6120 | DSF0001084928
17 | K824 | ASPIRATIONS DIPLOMA HS - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035591
17 | K867 | ALC- PROSPECT PLACE | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/14/2024 | IEH | 9/17/2024 | IEH | 0 | 0 | SCA0000073282
17 | K877 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 8/5/2019 | 12/20/2019 | 2/19/2020 | 57509 | 76618 | 76618 | DSF0000897420, DSF0000897422, DSF0000897423
17 | K877 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2/19/2020 | 7/20/2020 | 5/14/2021 | 277627 | 342409 | 311950 | DSF0000897420, DSF0000897422, DSF0000897423
17 | K877 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 7/14/2021 | 1/4/2023 |  | 5388593 | 5284483 | 4000462 | DSF0000897420, DSF0000897422, DSF0000897423
17 | K877 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/14/2021 | 1/4/2023 |  | 476962 | 515846 | 488182 | DSF0000897420, DSF0000897422, DSF0000897423
17 | K883 | ALTERNATE LEARNING CENTER - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | Complete | 11/3/2023 | DOER | 9/13/2024 | DOER | 86769 |  | DSF0001035598
17 | K907 | BROWNSVILLE ACADEMY HIGH SCHOOL - K | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/15/2024 | IEH | 7/27/2024 | IEH | 0 | 0 | SCA0000073137
17 | K907 | BROWNSVILLE ACADEMY HIGH SCHOOL - K | DOE - RESOA | FY22 RESO A FITNESS ROOM | Construction | PNS | PNS | PNS | PNS | DOER | 102497 | 0 | DSF0001033588
17 | K909 | K373 SPED - BROOKLYN | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 12/27/2022 | FTK |  | FTK | 5761650 | 4860981 | DSF0001034482
17 | K909 | GOTHAM PROFESSIONAL ARTS ACAD - K | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 11/17/2023 | DOER | 1/22/2024 | DOER | 193778 | 1761 | DSF0001033111
17 | KASV | MOSDOTH DAY CARE CENTER, INC. | SCA CIP | ACS EARLY LEARN RENEWAL | Scope | Complete | 1/19/2023 | 4/20/2023 | 8/15/2023 | 5065 | 59412 | 51810 | DSF0001035073
17 | KASV | MOSDOTH DAY CARE CENTER, INC. | SCA CIP | ACS EARLY LEARN RENEWAL | Design | Complete | 8/23/2023 | 2/29/2024 | 5/9/2024 | 22793 | 40144 | 40144 | DSF0001035073
17 | KASV | MOSDOTH DAY CARE CENTER, INC. | SCA CIP | ACS EARLY LEARN RENEWAL | Construction | PNS | PNS | PNS | PNS | 293771 | 293771 | 25479 | DSF0001035073
17 | KASV | MOSDOTH DAY CARE CENTER, INC. | SCA CIP | ACS EARLY LEARN RENEWAL | CM,F&E | PNS | PNS | PNS | PNS | 54449 | 54449 | 27657 | DSF0001035073
17 | KBOG | FRIENDS OF CROWN HEIGHTS #3 | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN VARIOUS LOCATIONS THROUGHTOUT THE BUILDING | Construction | Complete | 7/22/2024 | IEH | 8/9/2024 | IEH | 0 | 0 | SCA0000073158
17 | KBOR | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 3/2/2021 | 6/30/2021 | 7/2/2021 | 25326 | 47457 | 47457 | DSF0001008760
17 | KBOR | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | Complete | 10/1/2021 | 3/28/2022 | 8/9/2022 | 126629 | 101845 | 20196 | DSF0001008760
17 | KBOR | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Construction | In-Progress | 2/9/2024 | 8/1/2025 |  | 2849162 | 2715131 | 666248 | DSF0001008760
17 | KBOR | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | CM,F&E | In-Progress | 2/9/2024 | 8/1/2025 |  | 177281 | 293012 | 147590 | DSF0001008760
17 | KMCA | CUNY @ MEDGAR EVERS HS ANNEX - BROOKLYN | SCA Capacity | NEW BUILDING/CUNY CORE & SHELL | Scope | Complete | 7/15/2022 | 10/7/2022 | 9/30/2022 | 879281 | 62193 | 11514 | DSF0001008556
17 | KMCA | CUNY @ MEDGAR EVERS HS ANNEX - BROOKLYN | SCA Capacity | NEW BUILDING/CUNY CORE & SHELL | Design | In-Progress | 10/3/2022 | 4/20/2023 |  | 3956763 | 3956763 | 615185 | DSF0001008556
17 | KMCA | CUNY @ MEDGAR EVERS HS ANNEX - BROOKLYN | SCA Capacity | NEW BUILDING/CUNY CORE & SHELL | Construction | PNS | PNS | PNS | PNS | 49899172 | 49899172 | 293 | DSF0001008556
17 | KMCA | CUNY @ MEDGAR EVERS HS ANNEX - BROOKLYN | SCA Capacity | NEW BUILDING/CUNY CORE & SHELL | CM,Art,F&E | PNS | PNS | PNS | PNS | 7034244 | 7034244 | 93105 | DSF0001008556
18 | K066 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/7/2022 | 4/10/2023 | 12/23/2022 | 5000 | 4434 | 4434 | DSF0001034642
18 | K066 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/23/2022 | 6/22/2023 | 4/4/2023 | 22500 | 17933 | 17933 | DSF0001034642
18 | K066 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 290000 | 264397 | 240927 | DSF0001034642
18 | K066 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 155874 | 135846 | 104633 | DSF0001034642
18 | K066 | P.S. 66 - BROOKLYN | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIECNE CARTS | F&E | PNS | PNS | PNS | PNS | 500000 | 500000 | 0 | DSF0001112549
18 | K066 | K771 SPED - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112550
18 | K066 | P.S. 66 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/14/2021 | DOES |  | DOES | 118872 | 0 | DSF0001009059
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2/12/2020 | 7/14/2020 | 5/19/2020 | 77950 | 143803 | 139293 | DSF0000960643, DSF0000960644
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/19/2020 | 10/20/2020 | 11/5/2020 | 389751 | 491099 | 483180 | DSF0000960643, DSF0000960644
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 4/11/2022 | 5/9/2024 |  | 8769375 | 8204260 | 7807766 | DSF0000960643, DSF0000960644
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 4/11/2022 | 5/9/2024 |  | 545650 | 963390 | 963149 | DSF0000960643, DSF0000960644
18 | K068 | I.S. 68 - BROOKLYN | SCA IEH | PO18-ABATE ACM INSULATION FROM LINES SO GATE VALVES CAN BE RESTORED FOR BOTH COLD AND HOT WATER. LOC | Construction | Complete | 5/22/2024 | IEH | 9/4/2024 | IEH | 0 | 0 | SCA0000073024
18 | K068 | I.S. 68 - BROOKLYN | SCA IEH | PO18-ABATE & REPLACE LOOSE/BROKEN/MISSING 9X9 TILE AT EXIT#9 OF THE AUDITORIUM INCLUDING THE STAGE L | Construction | Complete | 9/13/2024 | IEH | 9/27/2024 | IEH | 0 | 0 | SCA0000073374
18 | K068 | I.S. 68 - BROOKLYN | SCA IEH | PO18-ABATE & REPLACE LOOSE/BROKEN 9X9 TILE IN ROOM 233. APPROXIMATELY 728SQFT THANK YOU, JAMES PELLE | Construction | Complete | 9/13/2024 | IEH | 11/24/2024 | IEH | 0 | 0 | SCA0000073375
18 | K068 | I.S. 68 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112551
18 | K068 | I.S. 68 - BROOKLYN | DOE - RESOA | FY19 RESO A LIBRARY UPGRADE | Construction | In-Progress | 2/21/2024 | DOER |  | DOER | 172357 | 0 | DSF0000890747
18 | K068 | I.S. 68 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/15/2023 | DOER |  | DOER | 139736 | 0 | DSF0000913210
18 | K068 | I.S. 68 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 7/29/2015 | DOES |  | DOES | 198919 | 0 | DSF0000778852
18 | K068 | I.S. 68 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/1/2023 | DOES |  | DOES | 487922 | 0 | DSF0001035159
18 | K068 | I.S. 68 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/9/2024 | DOES | 10/17/2024 | DOES | 65832 |  | DSF0001084731
18 | K114 | P.S. 114 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113567
18 | K114 | P.S. 114 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113567
18 | K114 | P.S. 114 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113567
18 | K114 | P.S. 114 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113567
18 | K114 | P.S. 114 - BROOKLYN | SCA IEH | PO18-ABATE PIPE COVERING IN NURSES OFFICE RM 216A MEDICAL OFFICE. ADDRESS ASAP STEAM LEAK NEEDS REP | Construction | Complete | 12/5/2024 | IEH | 12/21/2024 | IEH | 0 | 0 | SCA0000073679
18 | K114 | P.S. 114 - BROOKLYN | DOE - RESOA | FY16 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0000822800
18 | K114 | P.S. 114 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0 | DSF0001085978
18 | K114 | P.S. 114 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/10/2024 | DOES | 9/17/2024 | DOES | 65832 |  | DSF0001084592
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 3/8/2021 | 7/21/2021 | 8/11/2021 | 59831 | 72999 | 72999 | DSF0000937977, DSF0000986405, DSF0000986404, DSF0000986402
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 9/7/2021 | 2/10/2022 | 4/25/2022 | 287036 | 303956 | 295617 | DSF0000937977, DSF0000986405, DSF0000986404, DSF0000986402
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | Complete | 9/12/2022 | 9/10/2024 | 9/10/2024 | 5409692 | 5260477 | 4847818 | DSF0000937977, DSF0000986405, DSF0000986404, DSF0000986402
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | Complete | 9/12/2022 | 9/10/2024 | 9/10/2024 | 509744 | 732373 | 721829 | DSF0000937977, DSF0000986405, DSF0000986404, DSF0000986402
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/28/2024 | 9/26/2024 | 6/5/2024 | 4592 | 1098 | 1098 | DSF0001087391
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/5/2024 | 12/3/2024 | 11/20/2024 | 20662 | 4393 | 4393 | DSF0001087391
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 266313 | 266313 | 7093 | DSF0001087391
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 49360 | 49360 | 5998 | DSF0001087391
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/9/2023 | 6/12/2023 | 9/6/2023 | 0 | 17801 | 17801 | DSF0001035426
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 9/15/2023 | 2/5/2024 | 4/10/2024 | 54000 | 57307 | 55992 | DSF0001035426
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 792000 | 792000 | 2619 | DSF0001035426
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 54000 | 54000 | 9160 | DSF0001035426
18 | K115 | P.S. 115 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/9/2021 | DOER |  | DOER | 163585 | 0 | DSF0001008327
18 | K135 | P.S. 135 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | Scope | Complete | 9/19/2023 | 12/20/2023 | 12/21/2023 | 0 | 1813 | 1813 | DSF0001035437
18 | K135 | P.S. 135 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | Design | PNS | PNS | PNS | PNS | 6000 | 7250 | 7250 | DSF0001035437
18 | K135 | P.S. 135 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | 88000 | 360391 | 2604 | DSF0001035437
18 | K135 | P.S. 135 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 24572 | 5923 | DSF0001035437
18 | K135 | P.S. 135 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/19/2024 | DIIR |  | DIIR | 119576 | 119576 | DSF0001035438
18 | K135 | P.S. 135 - BROOKLYN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/29/2022 | DOER |  | DOER | 199729 | 0 | DSF0001033558
18 | K135 | P.S. 135 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/12/2024 | DOER |  | DOER | 237713 | 0 | DSF0001035435
18 | K135 | P.S. 135 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 217489 | 0 | DSF0001035436
18 | K135 | P.S. 135 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112579
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | Scope | Complete | 8/21/2020 | 12/21/2020 | 1/27/2021 | 55460 | 73551 | 76506 | DSF0000961074, DSF0001008796, DSF0000987912
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | Design | Complete | 2/2/2021 | 7/9/2021 | 6/29/2021 | 277301 | 399912 | 335189 | DSF0000961074, DSF0001008796, DSF0000987912
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | Construction | In-Progress | 5/8/2023 | 8/4/2024 |  | 6239250 | 5871385 | 4114358 | DSF0000961074, DSF0001008796, DSF0000987912
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | CM,F&E | In-Progress | 5/8/2023 | 8/4/2024 |  | 388220 | 590122 | 582912 | DSF0000961074, DSF0001008796, DSF0000987912
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/30/2024 | 9/30/2024 | 6/5/2024 | 4558 | 967 | 967 | DSF0001087424
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/5/2024 | 12/3/2024 | 11/20/2024 | 20512 | 3867 | 3867 | DSF0001087424
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 264378 | 264378 | 0 | DSF0001087424
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 49001 | 49001 | 3513 | DSF0001087424
18 | K208 | P.S. 208 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112618
18 | K208 | P.S. 208 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 1/25/2024 | DOEL |  | DOEL | 55361 | 0
18 | K208 | P.S. 208 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035473
18 | K208 | P.S. 208 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/15/2024 | DOER |  | DOER | 500000 | 0 | DSF0001086025
18 | K208 | P.S. 208 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/14/2022 | DOES |  | DOES | 60525 | 0 | DSF0001009110
18 | K211 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 6/29/2022 | 11/15/2022 | 3/1/2023 | 108440 | 128601 | 128601 | DSF0001034984
18 | K211 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 3/2/2023 | 8/17/2023 | 5/12/2023 | 542200 | 447051 | 389675 | DSF0001034984
18 | K211 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 10/16/2023 | 3/3/2026 |  | 12199500 | 11172016 | 5152659 | DSF0001034984
18 | K211 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 10/16/2023 | 3/3/2026 |  | 766103 | 265440 | 257028 | DSF0001034984
18 | K211 | I.S. 211 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING ROOMS WHERE ACM 9X9 TILES IS DAMAGED AND | Construction | Complete | 9/30/2024 | IEH | 10/9/2024 | IEH | 0 | 0 | SCA0000073448
18 | K211 | I.S. 211 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112619
18 | K211 | I.S. 211 - BROOKLYN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0000913243
18 | K211 | I.S. 211 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086026
18 | K211 | I.S. 211 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 8/1/2023 | DOES | 8/23/2023 | DOES | 537351 |  | DSF0001035155
18 | K211 | I.S. 211 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 7/5/2024 | DOES | 65832 | 10514 | DSF0001084745
18 | K219 | P.S. 219 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE / FY21 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 12/3/2021 | 2/6/2023 | 2/16/2023 | 0 | 47521 | 47521 | DSF0001007768, DSF0001008292
18 | K219 | P.S. 219 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE / FY21 RESO A SCIENCE LAB UPGRADE | Design | Complete | 2/17/2023 | 6/22/2023 | 5/12/2023 | 225000 | 160170 | 141529 | DSF0001007768, DSF0001008292
18 | K219 | P.S. 219 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE / FY21 RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 2/12/2024 | 8/4/2025 |  | 3300000 | 3092431 | 206953 | DSF0001007768, DSF0001008292
18 | K219 | P.S. 219 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE / FY21 RESO A SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 2/12/2024 | 8/4/2025 |  | 236223 | 137194 | 125764 | DSF0001007768, DSF0001008292
18 | K219 | P.S. 219 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: ROOM 215- 400 SQFT ROOM 216- 704 SQFT ROOM 218 | Construction | Complete | 12/15/2022 | IEH | 9/25/2024 | IEH | 0 | 0 | SCA0000071614
18 | K219 | P.S. 219 - BROOKLYN | SCA IEH | PO18-ABATE PIPE COVERING IN BASEMENT BOILER ROOM 3/4' COLD WATER LINE | Construction | Complete | 7/23/2024 | IEH | 7/26/2024 | IEH | 0 | 0 | SCA0000073164
18 | K219 | LAMAD ACADEMY CHARTER SCHOOL | DIIT - RESOA | RESO A- FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 250000 | 0 | DSF0000960936
18 | K219 | P.S. 219 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/2/2019 | DOER |  | DOER | 142925 | 0 | DSF0000890652
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | Fast Track Projects | PATH OF TRAVEL CTF ROOM CONVERSION / PATH OF TRAVEL CTF CHARTER MATCH ROOM CONVERSION / PATH OF TRAVEL CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 7/16/2024 | FTK |  | FTK | 292569 | 64663 | DSF0001008740, DSF0001008741, DSF0001008743
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033593
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/1/2021 | DOER |  | DOER | 312274 | 0 | DSF0000867245
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112633
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112634
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/21/2024 | DOES | 10/28/2024 | DOES | 65832 |  | DSF0001084751
18 | K233 | NEW AMERICAN CHARTER SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033132
18 | K233 | P.S. 233 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 120000 | 0 | DSF0001086036
18 | K233 | P.S. 233 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/26/2024 | DOES | 12/5/2024 | DOES | 65832 | 47 | DSF0001084106
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/9/2023 | 5/9/2023 | 1/25/2023 | 4200 | 3567 | 3567 | DSF0001034574
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/25/2023 | 7/21/2023 | 4/4/2023 | 18900 | 14269 | 14269 | DSF0001034574
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 243600 | 218361 | 205761 | DSF0001034574
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 105649 | 89591 | 84564 | DSF0001034574
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PA SYSTEM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113577
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PA SYSTEM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113577
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113577
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PA SYSTEM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113577
18 | K235 | P.S. 235 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 3/13/2020 | FTK |  | FTK | 384669 | 384668 | DSF0000912686
18 | K235 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 162000 | 0 | DSF0000890768
18 | K235 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112636
18 | K235 | P.S. 235 - BROOKLYN | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112635
18 | K235 | P.S. 235 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/10/2022 | DOES |  | DOES | 73047 | 0 | DSF0001008959
18 | K235 | P.S. 235 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/9/2024 | DOES | 9/19/2024 | DOES | 65832 |  | DSF0001084610
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 3/26/2021 | 8/10/2021 | 9/8/2021 | 48428 | 122843 | 122843 | DSF0000940048, DSF0000988584, DSF0000988585
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 9/20/2021 | 2/24/2022 | 5/12/2022 | 228254 | 274389 | 270095 | DSF0000940048, DSF0000988584, DSF0000988585
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 8/29/2022 | 2/19/2024 |  | 3934577 | 3671131 | 3606431 | DSF0000940048, DSF0000988584, DSF0000988585
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 8/29/2022 | 2/19/2024 |  | 443139 | 321019 | 321019 | DSF0000940048, DSF0000988584, DSF0000988585
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/30/2023 | 5/30/2023 | 2/13/2023 | 4200 | 2886 | 2886 | DSF0001034601
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/13/2023 | 8/9/2023 | 4/4/2023 | 18900 | 11545 | 11545 | DSF0001034601
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 243600 | 217432 | 204832 | DSF0001034601
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 105699 | 89109 | 84948 | DSF0001034601
18 | K242 | P.S. 235 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/4/2021 | EMER |  | EMER | 16536 | 11285 | SCA0000069469
18 | K242 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035493
18 | K242 | LENOX ACADEMY M. S. 961 | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001112644
18 | K242 | P.S. 235 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/28/2024 | DOES | 7/8/2024 | DOES | 65832 | 9326 | DSF0001084883
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033522
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033522
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033522
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033522
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/8/2023 | 6/9/2023 | 6/1/2023 | 0 | 16183 | 16183 | DSF0001035495
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 7/14/2023 | 11/30/2023 |  | 73510 | 57327 | 4825 | DSF0001035495
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1078149 | 1078149 | 36019 | DSF0001035495
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 73510 | 73510 | 21051 | DSF0001035495
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/8/2023 | 6/9/2023 | 5/22/2023 | 0 | 15654 | 15654 | DSF0001035494
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 4/17/2024 | 9/18/2024 | 11/4/2024 | 57000 | 65705 | 59055 | DSF0001035494
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 836000 | 836000 | 0 | DSF0001035494
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 57000 | 57000 | 5913 | DSF0001035494
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 10/30/2023 | 3/4/2024 | 11/1/2023 | 0 | 2990 | 2990 | DSF0001086043
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/1/2023 | 4/30/2024 | 3/20/2024 | 12012 | 11959 | 11959 | DSF0001086043
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/1/2024 | 8/27/2025 |  | 176183 | 93514 | 6574 | DSF0001086043
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 11/1/2024 | 8/27/2025 |  | 12012 | 10403 | 3709 | DSF0001086043
18 | K244 | P.S. 244 - BROOKLYN | SCA IEH | PO18-ABATE APPROX. 60 FEET OF ACM PIPE COVER FROM A 2' STEAM CONDENSTE PIPE IN FAN ROOM AT TWO SEPER | Construction | Complete | 9/26/2024 | IEH | 10/4/2024 | IEH | 0 | 0 | SCA0000073437
18 | K244 | P.S. 244 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 276128 | 0 | DSF0000959855
18 | K244 | P.S. 244 - BROOKLYN | DIIT - RESOA | FY15 RESO A IP SURVEILLANCE CAMERA INSTALLATION | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 271277 | 0 | DSF0000801008
18 | K244 | P.S. 244 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112647
18 | K244 | P.S. 244 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/21/2021 | DOER |  | DOER | 188847 | 0 | DSF0001008320
18 | K244 | P.S. 244 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/13/2024 | DOER |  | DOER | 300000 | 0 | DSF0001086042
18 | K244 | P.S. 244 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 12/8/2021 | DOES |  | DOES | 59232 | 317139 | DSF0001013421
18 | K244 | P.S. 244 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/17/2024 | DOES | 7/29/2024 | DOES | 65832 | 236 | DSF0001084111
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 3/1/2024 | 7/17/2024 | 10/3/2024 | 16166 | 56692 | 56692 | DSF0001091948
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | SCA CIP | FLOOD ELIMINATION | Design | In-Progress | 10/30/2024 | 4/4/2025 |  | 80831 | 80831 | 9018 | DSF0001091948
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 1818701 | 1818701 | 8565 | DSF0001091948
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 113164 | 113164 | 10289 | DSF0001091948
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/14/2024 | DIIR | 8/23/2024 | DIIR | 110000 | 95273 | DSF0001033109
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/22/2022 | DOER |  | DOER | 316605 | 0 | DSF0001033594
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112651
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/3/2024 | DOES | 10/10/2024 | DOES | 65832 |  | DSF0001084884
18 | K268 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/1/2022 | 11/25/2022 | 8/30/2022 | 145999 | 175403 | 138883 | DSF0001013798, DSF0001013799, DSF0001013800, DSF0001013801
18 | K268 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 9/29/2022 | 6/12/2023 | 3/15/2023 | 730000 | 415622 | 415622 | DSF0001013798, DSF0001013799, DSF0001013800, DSF0001013801
18 | K268 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 9/5/2023 | 9/3/2025 |  | 16425001 | 15209017 | 7841142 | DSF0001013798, DSF0001013799, DSF0001013800, DSF0001013801
18 | K268 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/5/2023 | 9/3/2025 |  | 1023032 | 504855 | 487535 | DSF0001013798, DSF0001013799, DSF0001013800, DSF0001013801
18 | K268 | P.S. 268 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE ACM WRAPPING FOR COHORT REMEDIATION SHUT OFF VALVES CAN BE FOUND IN THE CRAWL | Construction | Complete | 6/27/2024 | IEH | 7/25/2024 | IEH | 0 | 0 | SCA0000073090
18 | K268 | P.S. 268 - BROOKLYN | SCA IEH | PO18-INSULATION ABATEMENT THE PIPES ARE LOCATED IN THE CRAWL SPACE FOR RISERS THAT ARE FEEDING ROOMS | Construction | Complete | 7/30/2024 | IEH | 9/23/2024 | IEH | 0 | 0 | SCA0000073198
18 | K268 | P.S. 268 - BROOKLYN | DIIT - RESOA | FY09 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 193893 | 0 | DSF0000623076
18 | K268 | P.S. 268 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 375000 | 0 | DSF0001112659
18 | K268 | P.S. 268 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/11/2022 | DOES |  | DOES | 72429 | 0 | DSF0001009162
18 | K272 | P.S. 272 - BROOKLYN | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Scope | Complete | 2/6/2023 | 6/7/2023 | 5/19/2023 | 0 | 24801 | 21278 | DSF0001035513, DSF0001035514
18 | K272 | P.S. 272 - BROOKLYN | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Design | Complete | 5/19/2023 | 10/3/2023 | 10/16/2023 | 69000 | 76471 | 58494 | DSF0001035513, DSF0001035514
18 | K272 | P.S. 272 - BROOKLYN | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Construction | In-Progress | 5/9/2024 | 4/3/2025 |  | 1012000 | 540762 | 7532 | DSF0001035513, DSF0001035514
18 | K272 | P.S. 272 - BROOKLYN | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | CM,F&E | In-Progress | 5/9/2024 | 4/3/2025 |  | 69000 | 51373 | 12085 | DSF0001035513, DSF0001035514
18 | K272 | P.S. 272 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112663
18 | K272 | P.S. 272 - BROOKLYN | DOE - RESOA | FY17 RESO A ELECTRICAL SYSTEMS | Construction | In-Progress | 12/22/2017 | DOER |  | DOER | 117988 | 0 | DSF0000844853
18 | K272 | P.S. 272 - BROOKLYN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113752
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113585
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113585
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113585
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113585
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) CAFETERIA UPGRADE | Scope | Complete | 1/27/2023 | 5/30/2023 | 5/16/2023 | 0 | 8529 | 8529 | DSF0001035518
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) CAFETERIA UPGRADE | Design | In-Progress | 5/24/2023 | 10/11/2023 |  | 44958 | 36429 | 1039 | DSF0001035518
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 659391 | 509509 | 5335 | DSF0001035518
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 44958 | 34739 | 324 | DSF0001035518
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035519
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 42 | 42 | 0 | DSF0001035519
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 609 | 0 | 0 | DSF0001035519
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 42 | 1281 | 1281 | DSF0001035519
18 | K276 | P.S. 276 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/25/2021 | DOER |  | DOER | 249133 | 0 | DSF0000913257
18 | K276 | P.S. 276 - BROOKLYN | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/10/2023 | DOER |  | DOER | 105321 | 0 | DSF0001033530
18 | K276 | P.S. 276 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 5/1/2024 | DOER |  | DOER | 225594 | 0 | DSF0001086063
18 | K276 | P.S. 276 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112665
18 | K276 | P.S. 276 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 2/15/2020 | DOES | 4/13/2020 | DOES | 117240 | 149181 | DSF0000912969
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | Scope | Complete | 3/12/2018 | 7/10/2018 | 10/16/2018 | 22500 | 26603 | 26603 | DSF0000888831
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | Design | Complete | 11/14/2018 | 5/13/2019 | 5/10/2019 | 82500 | 113162 | 111956 | DSF0000888831
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 7/22/2019 | 7/15/2020 |  | 873750 | 795434 | 606624 | DSF0000888831
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 7/22/2019 | 7/15/2020 |  | 202500 | 120142 | 117564 | DSF0000888831
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/18/2024 | 11/4/2024 | 12/11/2024 | 102731 | 100321 | 20506 | DSF0001064739, DSF0001120102
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | PNS | PNS | PNS | PNS | 502421 | 502421 | 4849 | DSF0001064739, DSF0001120102
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 10939461 | 10939461 | 750 | DSF0001064739, DSF0001120102
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 806149 | 806149 | 19796 | DSF0001064739, DSF0001120102
18 | K279 | P.S. 279 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112668
18 | K279 | P.S. 279 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/27/2021 | DOES |  | DOES | 96964 | 0 | DSF0001008948
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113730
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0001113730
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 44000 | 44000 | 0 | DSF0001113730
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0001113730
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 4/6/2021 | 7/21/2021 | 11/5/2021 | 0 | 24208 | 24208 | DSF0000913265
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Design | Complete | 8/1/2023 | 1/4/2024 | 12/2/2024 | 125128 | 79769 | 72098 | DSF0000913265
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | 1835216 | 1835216 | 9000 | DSF0000913265
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 125128 | 125128 | 23447 | DSF0000913265
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES | Scope | Complete | 8/10/2023 | 11/9/2023 | 10/18/2023 | 0 | 0 | 8360 | DSF0000913264
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES | Design | Complete | 10/18/2023 | 2/20/2024 | 12/2/2024 | 872 | 872 | 10380 | DSF0000913264
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | 12784 | 12784 | 2997 | DSF0000913264
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 872 | 872 | 16284 | DSF0000913264
18 | K285 | I.S. 285 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001033535
18 | K285 | I.S. 285 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 100000 | 99625 | DSF0001086071
18 | K285 | I.S. 285 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/26/2024 | DOER |  | DOER | 211061 | 0 | DSF0001035526
18 | K285 | I.S. 285 - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001112670
18 | K285 | I.S. 285 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/8/2022 | DOES |  | DOES | 76791 | 0 | DSF0001008947
18 | K285 | I.S. 285 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/24/2024 | DOES | 11/20/2024 | DOES | 65832 |  | DSF0001084760
18 | K285 | I.S. 285 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/23/2024 | DOES |  | DOES | 643419 | 0 | DSF0001085725
18 | K366 | THE SCIENCE AND MEDICINE MIDDLE SCHOOL - K | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0 | DSF0001086100
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | Scope | Complete | 6/11/2019 | 12/9/2019 | 11/27/2019 | 235000 | 165509 | 165509 | DSF0000912525
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | Design | Complete | 3/4/2021 | 7/23/2021 | 5/6/2022 | 1175000 | 1068407 | 725845 | DSF0000912525
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | Construction | In-Progress | 9/12/2022 | 9/10/2024 |  | 26437500 | 24782576 | 18469073 | DSF0000912525
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | CM,F&E | In-Progress | 9/12/2022 | 9/10/2024 |  | 1645000 | 964219 | 951733 | DSF0000912525
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | CAFETERIA UPGRADE / PATH OF TRAVEL CAFETERIA UPGRADE | Scope | Complete | 1/5/2022 | 12/15/2022 | 1/19/2023 | 24690 | 69755 | 69755 | DSF0001034316, DSF0001034999
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | CAFETERIA UPGRADE / PATH OF TRAVEL CAFETERIA UPGRADE | Design | Complete | 1/24/2023 | 5/24/2023 | 3/15/2023 | 122212 | 285454 | 281195 | DSF0001034316, DSF0001034999
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | CAFETERIA UPGRADE / PATH OF TRAVEL CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 2642467 | 2642467 | 67518 | DSF0001034316, DSF0001034999
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | CAFETERIA UPGRADE / PATH OF TRAVEL CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 182137 | 182137 | 66071 | DSF0001034316, DSF0001034999
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | RESO A- CULINARY ARTS KITCHEN / PATH OF TRAVEL RESO A KITCHEN UPGRADE / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 11/30/2022 | 11/13/2023 | 11/30/2023 | 61605 | 76308 | 70543 | DSF0000960977, DSF0001035566, DSF0001085800
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | RESO A- CULINARY ARTS KITCHEN / PATH OF TRAVEL RESO A KITCHEN UPGRADE / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 11/30/2023 | 2/15/2024 | 4/23/2024 | 307087 | 457417 | 276389 | DSF0000960977, DSF0001035566, DSF0001085800
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | RESO A- CULINARY ARTS KITCHEN / PATH OF TRAVEL RESO A KITCHEN UPGRADE / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 10/4/2024 | 10/3/2026 |  | 6828645 | 6270343 | 40043 | DSF0000960977, DSF0001035566, DSF0001085800
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | RESO A- CULINARY ARTS KITCHEN / PATH OF TRAVEL RESO A KITCHEN UPGRADE / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 10/4/2024 | 10/3/2026 |  | 438238 | 159801 | 151544 | DSF0000960977, DSF0001035566, DSF0001085800
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | FY25 RESO A ATHLETIC FIELDS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112703
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | FY25 RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 105000 | 105000 | 0 | DSF0001112703
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 1540000 | 1540000 | 0 | DSF0001112703
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | FY25 RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 105000 | 105000 | 0 | DSF0001112703
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113590
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113590
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113590
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113590
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 1/5/2024 | 5/17/2024 | 5/14/2024 | 0 | 7165 | 7165 | DSF0001086114
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | Complete | 5/29/2024 | 10/30/2024 | 11/13/2024 | 29640 | 23402 | 13993 | DSF0001086114
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 434716 | 434716 | 0 | DSF0001086114
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 29640 | 29640 | 14623 | DSF0001086114
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 1/5/2024 | 3/8/2024 | 5/14/2024 | 0 | 12814 | 1886 | DSF0001086115
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | Complete | 5/29/2024 | 10/30/2024 | 11/13/2024 | 29640 | 26069 | 15692 | DSF0001086115
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 434716 | 434716 | 29102 | DSF0001086115
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 29640 | 29640 | 10706 | DSF0001086115
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 3/20/2024 | 6/20/2024 | 7/1/2024 | 0 | 496 | 496 | DSF0001087029
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 7/1/2024 | 11/1/2024 | 11/13/2024 | 360 | 360 | 1983 | DSF0001087029
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 5284 | 5284 | 1666 | DSF0001087029
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 360 | 360 | 6092 | DSF0001087029
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 3/19/2024 | 6/18/2024 | 7/1/2024 | 0 | 229 | 229 | DSF0001087030
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 7/1/2024 | 11/1/2024 | 11/13/2024 | 360 | 360 | 915 | DSF0001087030
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 5284 | 5284 | 0 | DSF0001087030
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 360 | 360 | 2424 | DSF0001087030
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | Fast Track Projects | CTF ROOM CONVERSION / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 5/17/2024 | FTK |  | FTK | 1533090 | 1153274 | DSF0001034931, DSF0001083861
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | Fast Track Projects | LSP- GYM UPGRADE | Construction | In-Progress | 8/16/2022 | FTK |  | FTK | 515875 | 515843 | DSF0001015200
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | Fast Track Projects | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/19/2023 | FTK |  | FTK | 26538 | 26509 | DSF0001008321
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 191927 | 0 | DSF0000959903
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 241000 | 0 | DSF0000961234
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/6/2024 | DIIR | 7/17/2024 | DIIR | 50000 | 50000 | DSF0001033590
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033597
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/7/2024 | DIIR | 7/17/2024 | DIIR | 54175 | 54175 | DSF0001035564
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001086113
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112704
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 4/13/2023 | DOER |  | DOER | 57318 | 0 | DSF0000961206
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/7/2022 | DOER |  | DOER | 150483 | 0 | DSF0000961207
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001033589
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001035563
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DOE - Skilled Trades | AUDITORIUM STAGE RIGGING | Construction | In-Progress | 12/9/2019 | DOES |  | DOES | 27299 | 10219 | DSF0000960512
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DOE - Skilled Trades | REPLACE (3) GALVANIZED WATER MAINS & CURB VALVES | Construction | In-Progress | 3/31/2022 | DOES |  | DOES | 246870 | 16921 | DSF0001015190
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/22/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084898
18 | K416 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086116
18 | K416 | IT TAKES A VILLAGE ACADEMY - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112705
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/1/2022 | 11/25/2022 | 9/15/2022 | 211895 | 151160 | 151128 | DSF0001015622, DSF0001015621, DSF0001015623
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 9/28/2022 | 6/12/2023 | 4/27/2023 | 1059470 | 453969 | 453969 | DSF0001015622, DSF0001015621, DSF0001015623
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 10/16/2023 | 4/2/2026 |  | 23838075 | 22052048 | 12730353 | DSF0001015622, DSF0001015621, DSF0001015623
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 10/16/2023 | 4/2/2026 |  | 1483258 | 645763 | 604220 | DSF0001015622, DSF0001015621, DSF0001015623
18 | K500 | HS FOR MEDICAL PROFESSIONS - K | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/13/2023 | 10/12/2023 | 8/29/2023 | 0 | 28616 | 28616 | DSF0001035577, DSF0001035578
18 | K500 | HS FOR MEDICAL PROFESSIONS - K | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 8/31/2023 | 1/2/2024 | 12/6/2023 | 84000 | 69825 | 66533 | DSF0001035577, DSF0001035578
18 | K500 | HS FOR MEDICAL PROFESSIONS - K | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 1232000 | 1232000 | 84935 | DSF0001035577, DSF0001035578
18 | K500 | HS FOR MEDICAL PROFESSIONS - K | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 84000 | 88693 | 22880 | DSF0001035577, DSF0001035578
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | SCA IEH | PO18-REMOVE APPROX. 40 FEET OF ACM PIPE INSULATION FROM A 3' WATER PIPE. LINE IS MARKED WITH BLUE S | Construction | Complete | 11/20/2024 | IEH | 12/22/2024 | IEH | 0 | 0 | SCA0000073626
18 | K500 | HS FOR MEDICAL PROFESSIONS - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112726
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/14/2024 | DOER |  | DOER | 1050000 | 0 | DSF0001086133
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/19/2024 | DOES | 11/4/2024 | DOES | 65832 | 9325 | DSF0001084915
18 | K501 | HS FOR MEDICAL PROFESSIONS - K | DOE - Skilled Trades | ATHLETIC FIELD | Construction | Complete | 10/5/2023 | DOES | 9/11/2024 | DOES | 3821368 |  | DSF0001066403
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | Scope | Complete | 5/23/2019 | 9/23/2019 | 11/27/2019 | 59160 | 55185 | 55185 | DSF0000912406, DSF0000942044, DSF0000942050
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | Design | Complete | 1/3/2020 | 7/7/2020 | 9/26/2022 | 295800 | 228104 | 219373 | DSF0000912406, DSF0000942044, DSF0000942050
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | Construction | In-Progress | 9/11/2023 | 3/3/2025 |  | 6655500 | 5990442 | 3676768 | DSF0000912406, DSF0000942044, DSF0000942050
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 9/11/2023 | 3/3/2025 |  | 414120 | 245568 | 235484 | DSF0000912406, DSF0000942044, DSF0000942050
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/16/2023 | 3/15/2024 | 1/5/2024 | 0 | 35247 | 35247 | DSF0001035580, DSF0001035581
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 1/10/2024 | 5/14/2024 | 7/12/2024 | 90120 | 81393 | 54053 | DSF0001035580, DSF0001035581
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1321761 | 1321761 | 20666 | DSF0001035580, DSF0001035581
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90120 | 103653 | 49196 | DSF0001035580, DSF0001035581
18 | K515 | BROOKLYN COMMUNITY HIGH SCHOOL FOR EXCELLENCE AND EQUITY - K | SCA IEH | PO18-ABATE AND DRILL ONE HOLE THROUGH THE WALL, FULL PENETRATION WITH A DIAMETER OF 1-1/8'. LOCATION | Construction | Complete | 10/9/2024 | IEH | 10/14/2024 | IEH | 0 | 0 | SCA0000073484
18 | K515 | BROOKLYN COMMUNITY HIGH SCHOOL FOR EXCELLENCE AND EQUITY - K | SCA IEH | PO18-REPLACE BROKEN 9X9 TILES IN ROOM 109 ROOM SIZE APPROX 420 SQ FT. | Construction | In-Progress | 10/10/2024 | IEH |  | IEH | 0 | 0 | SCA0000073493
18 | K515 | BROOKLYN BRIDGE ACADEMY - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035582
18 | K515 | BROOKLYN BRIDGE ACADEMY - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 150000 | 118835 | DSF0001086134
18 | K515 | ACAD FOR CONSERV & THE ENVIR - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 7/12/2024 | DIIR | 50000 | 50000 | DSF0001086135
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112727
18 | K515 | ACAD FOR CONSERV & THE ENVIR - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112728
18 | K515 | VICTORY COLLEGIATE HS - K | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086138
18 | K515 | BROOKLYN COMMUNITY HIGH SCHOOL FOR EXCELLENCE AND EQUITY - K | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086139
18 | K515 | BROOKLYN COMMUNITY HIGH SCHOOL FOR EXCELLENCE AND EQUITY - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 2/3/2023 | DOES | 12/4/2023 | DOES | 697978 | 561556 | DSF0000960847
18 | K515 | BROOKLYN COMMUNITY HIGH SCHOOL FOR EXCELLENCE AND EQUITY - K | DOE - Skilled Trades | BCC PLAN REVIEW FOR DSF WORK @ K515 | Construction | In-Progress | 3/3/2021 | DOES |  | DOES | 9617 | 0 | SCA0000064029
18 | K515 | BROOKLYN COMMUNITY HIGH SCHOOL FOR EXCELLENCE AND EQUITY - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/13/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084917
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | ROOFS | Scope | Complete | 7/23/2019 | 12/9/2019 | 10/10/2019 | 13205 | 17240 | 17240 | DSF0000911250
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | ROOFS | Design | Complete | 10/22/2019 | 3/26/2020 | 6/8/2020 | 66023 | 81181 | 81133 | DSF0000911250
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 1485521 | 1485521 | 90459 | DSF0000911250
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 92432 | 92432 | 43547 | DSF0000911250
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | Scope | Complete | 2/25/2020 | 7/24/2020 | 3/25/2021 | 50050 | 44890 | 44890 | DSF0000957676, DSF0001008851, DSF0001008852, DSF0001006906, DSF0001008853
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | Design | Complete | 6/7/2021 | 12/9/2021 | 12/7/2021 | 234927 | 231321 | 186739 | DSF0000957676, DSF0001008851, DSF0001008852, DSF0001006906, DSF0001008853
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | Construction | In-Progress | 8/7/2023 | 8/5/2025 |  | 3960743 | 3538066 | 2344563 | DSF0000957676, DSF0001008851, DSF0001008852, DSF0001006906, DSF0001008853
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | CM,F&E | In-Progress | 8/7/2023 | 8/5/2025 |  | 465242 | 175779 | 175483 | DSF0000957676, DSF0001008851, DSF0001008852, DSF0001006906, DSF0001008853
18 | K835 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | Scope | Complete | 2/4/2019 | 7/5/2019 | 9/10/2019 | 40883 | 25341 | 25341 | DSF0000894607, DSF0000942606
18 | K835 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | Design | Complete | 3/16/2021 | 8/13/2021 | 12/17/2021 | 199691 | 200545 | 125789 | DSF0000894607, DSF0000942606
18 | K835 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | Construction | In-Progress | 8/19/2024 | 2/4/2027 |  | 4084529 | 3872793 | 193467 | DSF0000894607, DSF0000942606
18 | K835 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | CM,F&E | In-Progress | 8/19/2024 | 2/4/2027 |  | 321597 | 173833 | 168523 | DSF0000894607, DSF0000942606
18 | K855 | P.S. 135 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 10/1/2024 | IEH | 11/14/2024 | IEH | 0 | 0 | SCA0000073459
18 | K855 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001035597
18 | K855 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086157
18 | K855 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112743
18 | K860 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | Scope | Complete | 8/1/2013 | 1/6/2014 | 12/5/2013 | 48840 | 25817 | 25817 | DSF0000761724
18 | K860 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | Design | Complete | 1/8/2014 | 6/10/2014 | 10/22/2014 | 195360 | 281775 | 281775 | DSF0000761724
18 | K860 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | Construction | In-Progress | 8/19/2019 | 8/17/2021 |  | 3663000 | 3384381 | 2594772 | DSF0000761724
18 | K860 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | CM,F&E | In-Progress | 8/19/2019 | 8/17/2021 |  | 227920 | 1015644 | 1015644 | DSF0000761724
18 | K860 | EAST BKLN COMMUNITY HS - K | SCA CIP | COVID VENTILATION | Scope | Complete | 12/10/2020 | 4/9/2021 | 6/9/2021 | 10487 | 43705 | 43705 | DSF0000991368
18 | K860 | EAST BKLN COMMUNITY HS - K | SCA CIP | COVID VENTILATION | Design | Complete | 6/14/2021 | 11/15/2021 | 10/27/2021 | 52434 | 68933 | 68933 | DSF0000991368
18 | K860 | EAST BKLN COMMUNITY HS - K | SCA CIP | COVID VENTILATION | Construction | PNS | PNS | PNS | PNS | 1179756 | 1179756 | 41611 | DSF0000991368
18 | K860 | EAST BKLN COMMUNITY HS - K | SCA CIP | COVID VENTILATION | CM,F&E | PNS | PNS | PNS | PNS | 73407 | 73407 | 22650 | DSF0000991368
18 | K860 | EAST BKLN COMMUNITY HS - K | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 4/26/2024 | IEH |  | IEH | 0 | 0 | SCA0000072964
19 | K007 | K004 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/11/2024 | 5/10/2024 | 1/11/2024 | 4063 | 1555 | 1555 | DSF0001087362
19 | K007 | K004 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/20/2024 | 9/13/2024 | 7/16/2024 | 18284 | 6224 | 6224 | DSF0001087362
19 | K007 | K004 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 235666 | 235666 | 0 | DSF0001087362
19 | K007 | K004 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 47419 | 47419 | 3934 | DSF0001087362
19 | K007 | P.S. 7 - BROOKLYN | SCA CIP RESOA | FY18 RESO A IP SECURITY CAMERAS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000866412
19 | K007 | P.S. 7 - BROOKLYN | SCA CIP RESOA | FY18 RESO A IP SECURITY CAMERAS | Design | PNS | PNS | PNS | PNS | 20737 | 20737 | 0 | DSF0000866412
19 | K007 | P.S. 7 - BROOKLYN | SCA CIP RESOA | FY18 RESO A IP SECURITY CAMERAS | Construction | PNS | PNS | PNS | PNS | 304138 | 304138 | 0 | DSF0000866412
19 | K007 | P.S. 7 - BROOKLYN | SCA CIP RESOA | FY18 RESO A IP SECURITY CAMERAS | CM,F&E | PNS | PNS | PNS | PNS | 366348 | 345611 | 345611 | DSF0000866412
19 | K007 | P.S. 7 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 466000 | 466000 | 80041 | DSF0001085936
19 | K013 | P.S. 13 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/18/2024 | 5/16/2024 | 4/2/2024 | 5365 | 2095 | 2095 | DSF0001087367
19 | K013 | P.S. 13 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/2/2024 | 9/26/2024 | 7/16/2024 | 24144 | 8383 | 8383 | DSF0001087367
19 | K013 | P.S. 13 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 311194 | 311194 | 2393 | DSF0001087367
19 | K013 | P.S. 13 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 61418 | 61418 | 4316 | DSF0001087367
19 | K013 | P.S. 13 - BROOKLYN | SCA IEH | PO18-ROOM 128, ABATE 70 SQ. FT. LOOSE, POPPING UP FLOOR TILES ROOM 131, ABATE 70 SQ. FT. LOOSE, POPP | Construction | Complete | 5/29/2024 | IEH | 10/12/2024 | IEH | 0 | 0 | SCA0000073034
19 | K013 | P.S. 13 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 350000 | 0 | DSF0001112517
19 | K013 | P.S. 13 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/3/2024 | DOER |  | DOER | 498205 | 0 | DSF0001085939
19 | K013 | P.S. 13 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 233000 | 0 | DSF0001085940
19 | K013 | P.S. 13 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 11/14/2022 | DOES |  | DOES | 1157455 | 0 | DSF0000911947
19 | K013 | P.S. 13 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 191366 | 0 | DSF0001034216
19 | K065 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | Scope | Complete | 5/25/2023 | 10/12/2023 | 9/26/2023 | 30980 | 99229 | 99166 | DSF0001088870
19 | K065 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | Design | Complete | 10/5/2023 | 3/12/2024 | 3/6/2024 | 154902 | 154082 | 118695 | DSF0001088870
19 | K065 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | Construction | In-Progress | 7/15/2024 | 12/6/2025 |  | 3485301 | 3511663 | 762809 | DSF0001088870
19 | K065 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | CM,F&E | In-Progress | 7/15/2024 | 12/6/2025 |  | 216863 | 65893 | 64542 | DSF0001088870
19 | K065 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ K065 | Construction | In-Progress | 4/13/2023 | EMER |  | EMER | 56326 | 53313 | SCA0000071882
19 | K065 | P.S. 65 - BROOKLYN | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035400
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 8/31/2023 | 1/4/2024 | 11/7/2023 | 5690 | 2602 | 2602 | DSF0001035005
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | Design | Complete | 11/7/2023 | 5/6/2024 | 1/24/2024 | 25603 | 10408 | 10408 | DSF0001035005
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 7/19/2024 | 6/13/2025 |  | 329997 | 297143 | 78401 | DSF0001035005
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 7/19/2024 | 6/13/2025 |  | 61163 | 43084 | 12048 | DSF0001035005
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/19/2020 | FTK |  | FTK | 372163 | 300718 | DSF0000912048
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112552
19 | K072 | EAST NEW YORK MIDDLE SCHOOL OF EXCELLENCE - K | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 4/8/2022 | DOER |  | DOER | 603731 | 0 | DSF0000913043
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/16/2020 | DOES |  | DOES | 760283 | 0 | DSF0000912644
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 9/1/2021 | DOES |  | DOES | 61744 | 304425 | DSF0000985802
19 | K108 | P.S. 108 - BROOKLYN | SCA IEH | PO18-ABATE AND PENETRATE WALL AND CEILINGS LAYERS LOCATIONS IN KITCHEN AND 2 BASEMENT HALLWAYS LOCAT | Construction | Complete | 10/9/2024 | IEH | 10/25/2024 | IEH | 0 | 0 | SCA0000073485
19 | K108 | P.S. 108 - BROOKLYN | SCA IEH | PO18-PLEASE REPAIR ENCAPSULATE AND PAINT DAMAGED ASBESTOS WALL PLASTER AT ALL FOUR WALLS AND CLOSETS | Construction | Complete | 10/10/2024 | IEH | 10/19/2024 | IEH | 0 | 0 | SCA0000073487
19 | K108 | P.S. 108 - BROOKLYN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/17/2024 | DOER |  | DOER | 179638 | 0 | DSF0001033471
19 | K108 | P.S. 108 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112568
19 | K149 | P.S. 149 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/9/2024 | 5/8/2024 | 3/22/2024 | 4062 | 1226 | 1226 | DSF0001087402
19 | K149 | P.S. 149 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/22/2024 | 9/17/2024 | 8/13/2024 | 18281 | 4908 | 4908 | DSF0001087402
19 | K149 | P.S. 149 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 235623 | 235623 | 0 | DSF0001087402
19 | K149 | P.S. 149 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 47411 | 47411 | 4770 | DSF0001087402
19 | K149 | P.S. 149 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 130000 | 130000 | 129171 | DSF0001085997
19 | K149 | P.S. 149 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 12/8/2021 | DOES |  | DOES | 60651 | 0 | DSF0000866106
19 | K158 | P.S. 158 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/11/2024 | 5/10/2024 | 1/11/2024 | 3924 | 1082 | 1082 | DSF0001087407
19 | K158 | P.S. 158 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2024 | 9/16/2024 | 8/13/2024 | 17660 | 4329 | 4329 | DSF0001087407
19 | K158 | P.S. 158 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 227619 | 227619 | 2320 | DSF0001087407
19 | K158 | P.S. 158 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 45928 | 45928 | 5537 | DSF0001087407
19 | K158 | P.S. 158 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE 9X9 FTS FROM THE FIRST FLOOR CORRIDOR- TILES ARE LOOSE, LIFTING AND CHIPPING | Construction | Complete | 11/6/2024 | IEH | 12/22/2024 | IEH | 0 | 0 | SCA0000073583
19 | K158 | P.S. 158 - BROOKLYN | Fast Track Projects | STRUCTURAL DEFECTS | Construction | In-Progress | 5/20/2016 | FTK |  | FTK | 640117 | 638757 | DSF0000825820
19 | K158 | P.S. 158 - BROOKLYN | DOE - RESOA | FY18 RESO A AUDITORIUM SOUND SYSTEM UPGRADE | Construction | In-Progress | 3/19/2024 | DOER |  | DOER | 137950 | 0 | DSF0000912487
19 | K158 | P.S. 158 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 1/30/2020 | DOER | 12/28/2021 | DOER | 215711 | 215592 | DSF0000913045
19 | K158 | P.S. 158 - BROOKLYN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 10/6/2023 | DOER | 12/12/2023 | DOER | 70321 |  | DSF0001035450
19 | K159 | P.S. 159 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 12/18/2019 | FTK |  | FTK | 359763 | 355958 | DSF0000912055, DSF0000912529
19 | K159 | P.S. 159 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/22/2021 | DOES |  | DOES | 74254 | 0 | DSF0001008965
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112591
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001112591
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001112591
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001112591
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113571
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113571
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113571
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113571
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA IEH | PO18-ABATE PIPE INSULATION AROUND BURNERS AT BOTH BOILERS PIPING IS SPRAY PAINTED ORANGE, PICTURES W | Construction | Complete | 10/28/2024 | IEH | 11/8/2024 | IEH | 0 | 0 | SCA0000073551
19 | K166 | NEW DISTRICT HS IN BUILDING K166 - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 64000 | 0 | DSF0001035452
19 | K166 | NEW DISTRICT HS IN BUILDING K166 - K | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0 | DSF0001086004
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086005
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1200000 | 0 | DSF0001112592
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/13/2023 | DOES | 11/6/2023 | DOES | 651994 |  | DSF0001035161
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/2/2024 | DOES | 10/9/2024 | DOES | 65832 |  | DSF0001084739
19 | K171 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 7/21/2022 | 12/7/2022 | 12/27/2022 | 37670 | 29683 | 29621 | DSF0001011982
19 | K171 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 1/4/2023 | 6/6/2023 | 5/3/2023 | 188350 | 117901 | 105589 | DSF0001011982
19 | K171 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 1/12/2024 | 11/1/2025 |  | 4237875 | 3859759 | 1590196 | DSF0001011982
19 | K171 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 1/12/2024 | 11/1/2025 |  | 263690 | 210177 | 203083 | DSF0001011982
19 | K171 | I.S. 171 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION OF FACADE | Construction | In-Progress | 2/4/2010 | EMER |  | EMER |  | 0 | SCA0000008888
19 | K171 | I.S. 171 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- CRACKED DETERIORATED COPING STONES | Construction | In-Progress | 11/30/2022 | EMER |  | EMER | 318566 | 288118 | SCA0000071587
19 | K171 | I.S. 171 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REMOVE APPROXIMATELY 6 SQUARE FEET OF FLOOR IN KITCHEN# 1 IDENTIFIED WITH RED | Construction | Complete | 9/4/2024 | IEH | 9/23/2024 | IEH | 0 | 0 | SCA0000073345
19 | K171 | I.S. 171 - BROOKLYN | DIIT - RESOA | FY18 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0000867433
19 | K171 | I.S. 171 - BROOKLYN | DOE - RESOA | FY16 RESO A GYMNASIUM | Construction | In-Progress | 7/22/2022 | DOER |  | DOER | 208177 | 0 | DSF0000844142
19 | K171 | I.S. 171 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001035455
19 | K171 | I.S. 171 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 152000 | 0 | DSF0001112594
19 | K171 | I.S. 171 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/27/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084740
19 | K174 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 8/29/2023 | 1/2/2024 | 11/7/2023 | 5170 | 1625 | 1625 | DSF0001035017
19 | K174 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Design | Complete | 11/7/2023 | 5/6/2024 | 1/24/2024 | 23267 | 6501 | 6501 | DSF0001035017
19 | K174 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 7/19/2024 | 6/13/2025 |  | 299883 | 271155 | 15329 | DSF0001035017
19 | K174 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 7/19/2024 | 6/13/2025 |  | 55582 | 34791 | 6871 | DSF0001035017
19 | K174 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 20 LINEAR FEET OF PIPE COVERING ACM FROM TWO STEAM RISERS LOCATED I | Construction | Complete | 8/23/2024 | IEH | 8/28/2024 | IEH | 0 | 0 | SCA0000073318
19 | K174 | SCHOOL OF THE FUTURE BROOKLYN | Fast Track Projects | FY20 RESO A LIBRARY UPGRADE | Construction | In-Progress | 5/30/2022 | FTK |  | FTK | 53609 | 51352 | DSF0000913048
19 | K174 | SCHOOL OF THE FUTURE BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 7/7/2023 | DOER | 8/21/2023 | DOER | 241380 |  | DSF0001033122
19 | K174 | BROOKLYN GARDENS ELEMENTARY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/9/2024 | DOES | 9/16/2024 | DOES | 65832 |  | DSF0001084741
19 | K190 | P.S. 190 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 9/26/2023 | 1/30/2024 | 9/27/2023 | 4582 | 1424 | 1424 | DSF0001035019
19 | K190 | P.S. 190 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 9/27/2023 | 3/27/2024 | 3/20/2024 | 20621 | 5696 | 5696 | DSF0001035019
19 | K190 | P.S. 190 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 11/1/2024 | 8/27/2025 |  | 265780 | 230807 | 1687 | DSF0001035019
19 | K190 | P.S. 190 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 11/1/2024 | 8/27/2025 |  | 49261 | 30658 | 5913 | DSF0001035019
19 | K190 | P.S. 190 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 3/16/2021 | DOER | 12/28/2021 | DOER | 207431 | 204641 | DSF0000913051
19 | K190 | P.S. 190 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 236903 | 0 | DSF0001034222
19 | K190 | P.S. 190 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/3/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084743
19 | K202 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 6/27/2022 | 12/21/2022 | 10/6/2022 | 257257 | 320292 | 310978 | DSF0001012557, DSF0001012558, DSF0001012559, DSF0001012554, DSF0001036327
19 | K202 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | Complete | 10/19/2022 | 6/26/2023 | 5/3/2023 | 1286286 | 434032 | 434032 | DSF0001012557, DSF0001012558, DSF0001012559, DSF0001012554, DSF0001036327
19 | K202 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Construction | In-Progress | 10/16/2023 | 3/3/2026 |  | 28941441 | 25982124 | 8546440 | DSF0001012557, DSF0001012558, DSF0001012559, DSF0001012554, DSF0001036327
19 | K202 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | CM,F&E | In-Progress | 10/16/2023 | 3/3/2026 |  | 1800800 | 475147 | 455950 | DSF0001012557, DSF0001012558, DSF0001012559, DSF0001012554, DSF0001036327
19 | K202 | P.S. 202 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 1/20/2023 | DOER | 3/27/2023 | DOER | 230140 | 1760 | DSF0001033037
19 | K202 | P.S. 202 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 7/12/2018 | DOES |  | DOES | 244560 | 0 | DSF0000823660
19 | K202 | P.S. 202 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/15/2024 | DOES | 10/22/2024 | DOES | 65832 |  | DSF0001084882
19 | K202 | P.S. 202 - BROOKLYN | DOE - Skilled Trades | BOOSTER PUMP REPLACEMENT | Construction | In-Progress | 5/16/2024 | DOES |  | DOES | 84139 | 0 | DSF0001112213
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 9/18/2019 | 2/6/2020 | 5/4/2021 | 28328 | 94375 | 74636 | DSF0001012796
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 5/13/2021 | 10/14/2021 | 2/7/2022 | 141640 | 213851 | 193446 | DSF0001012796
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 6/27/2022 | 12/18/2023 |  | 3186910 | 3387696 | 3171605 | DSF0001012796
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 6/27/2022 | 12/18/2023 |  | 199103 | 648458 | 646351 | DSF0001012796
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/5/2023 | 5/5/2023 | 1/13/2023 | 4395 | 4800 | 4800 | DSF0001034580
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/13/2023 | 7/12/2023 | 4/5/2023 | 19776 | 19202 | 19202 | DSF0001034580
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 254893 | 234890 | 189609 | DSF0001034580
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 108028 | 91708 | 87600 | DSF0001034580
19 | K213 | P.S. 213 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112620
19 | K214 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2/6/2019 | 9/3/2019 | 11/15/2019 | 154000 | 157885 | 157885 | DSF0000871422, DSF0000912353, DSF0000960613
19 | K214 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 1/23/2020 | 7/9/2020 | 5/10/2022 | 770000 | 813290 | 778801 | DSF0000871422, DSF0000912353, DSF0000960613
19 | K214 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 8/10/2022 | 11/2/2023 |  | 17325001 | 16531323 | 14104032 | DSF0000871422, DSF0000912353, DSF0000960613
19 | K214 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 8/10/2022 | 11/2/2023 |  | 1199985 | 859375 | 851631 | DSF0000871422, DSF0000912353, DSF0000960613
19 | K214 | P.S. 214 - BROOKLYN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 179000 | 0 | DSF0001035078
19 | K214 | P.S. 214 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 69820 | 0 | DSF0001035474
19 | K214 | P.S. 214 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 10/12/2021 | DOES |  | DOES | 60651 | 0 | DSF0000866110
19 | K214 | P.S. 214 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/8/2024 | DOES | 7/18/2024 | DOES | 65832 | 189 | DSF0001084097
19 | K218 | I.S. 218 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 8/14/2023 | 1/2/2024 | 10/27/2023 | 11560 | 25490 | 25181 | DSF0001085808
19 | K218 | I.S. 218 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 10/30/2023 | 4/3/2024 | 3/13/2024 | 52020 | 40056 | 37301 | DSF0001085808
19 | K218 | I.S. 218 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 670480 | 670480 | 11018 | DSF0001085808
19 | K218 | I.S. 218 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 124270 | 124270 | 34148 | DSF0001085808
19 | K218 | I.S. 218 - BROOKLYN | SCA Emergency Response | EARTHQUAKE REMEDIATION WORK - SWB @K218 | Construction | In-Progress | 4/8/2024 | EMER |  | EMER | 490110 | 297057 | SCA0000072900
19 | K218 | I.S. 218 - BROOKLYN | SCA IEH | PO18-ABATE EXPOSED ACM INSULATION APPROX. 10 LINEAR FEET | Construction | Complete | 8/8/2024 | IEH | 8/11/2024 | IEH | 0 | 0 | SCA0000073267
19 | K218 | I.S. 218 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE PIPE INSULATION MARKED WITH RED SPRAY PAINT ABOVE CEILING LOCATION IS IN KITCH | Construction | Complete | 11/26/2024 | IEH | 12/7/2024 | IEH | 0 | 0 | SCA0000073650
19 | K218 | SCHOOL FOR CLASSICS HS - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0 | DSF0001086028
19 | K218 | I.S. 218 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 12/6/2022 | DOER | 4/20/2023 | DOER | 243818 | 1761 | DSF0001033039
19 | K218 | I.S. 218 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/27/2024 | DOES | 7/5/2024 | DOES | 65832 | 13080 | DSF0001084746
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | Scope | Complete | 6/7/2019 | 10/23/2019 | 9/1/2021 | 112240 | 260184 | 260184 | DSF0001091441, DSF0000988245, DSF0000988242, DSF0001013030, DSF0001013035
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | Design | Complete | 9/29/2021 | 3/7/2022 | 5/9/2024 | 561200 | 686611 | 524096 | DSF0001091441, DSF0000988245, DSF0000988242, DSF0001013030, DSF0001013035
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | Construction | In-Progress | 7/22/2024 | 1/7/2027 |  | 12627000 | 11303737 | 256664 | DSF0001091441, DSF0000988245, DSF0000988242, DSF0001013030, DSF0001013035
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | CM,F&E | In-Progress | 7/22/2024 | 1/7/2027 |  | 785679 | 191904 | 186269 | DSF0001091441, DSF0000988245, DSF0000988242, DSF0001013030, DSF0001013035
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/1/2023 | 6/1/2023 | 2/6/2023 | 7639 | 5059 | 5059 | DSF0001034639
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/6/2023 | 8/2/2023 | 5/3/2023 | 34375 | 20234 | 20234 | DSF0001034639
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/9/2023 | 10/3/2024 |  | 443050 | 394863 | 328781 | DSF0001034639
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/9/2023 | 10/3/2024 |  | 143955 | 108020 | 88105 | DSF0001034639
19 | K224 | P.S. 224 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 3/28/2019 | EMER |  | EMER | 137118 | 110515 | SCA0000057028
19 | K224 | P.S. 224 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILE APPROX. 12SF LOCATED IN THE CAFETERIA | Construction | Complete | 7/23/2024 | IEH | 8/24/2024 | IEH | 0 | 0 | SCA0000073161
19 | K224 | P.S. 224 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112624
19 | K224 | P.S. 224 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 7/10/2023 | DOER | 8/21/2023 | DOER | 171834 |  | DSF0001033042
19 | K224 | P.S. 224 - BROOKLYN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086031
19 | K260 | THE FRESH CREEK SCHOOL - BROOKLYN | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 500000 | 500000 | 0 | DSF0001112654
19 | K260 | THE FRESH CREEK SCHOOL - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 10/2/2023 | DIIR | 5/28/2024 | DIIR | 200000 | 200000 | DSF0001033062
19 | K260 | THE FRESH CREEK SCHOOL - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/2/2022 | DOES |  | DOES | 169933 | 0 | DSF0001008681
19 | K260 | THE FRESH CREEK SCHOOL - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/11/2024 | DOES | 7/23/2024 | DOES | 65832 | 11170 | DSF0001084121
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 9/17/2021 | 2/7/2022 | 1/26/2022 | 104244 | 170652 | 170652 | DSF0001009293
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2/23/2022 | 8/9/2022 | 12/7/2022 | 521220 | 494429 | 444909 | DSF0001009293
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 9/4/2023 | 9/2/2025 |  | 11727450 | 10806917 | 2740624 | DSF0001009293
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 9/4/2023 | 9/2/2025 |  | 917333 | 577492 | 404419 | DSF0001009293
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/15/2024 | 8/14/2024 | 4/19/2024 | 4155 | 1430 | 1430 | DSF0001087442
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/19/2024 | 10/16/2024 | 9/11/2024 | 18697 | 5719 | 5719 | DSF0001087442
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 240977 | 240977 | 4882 | DSF0001087442
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 44664 | 44664 | 7447 | DSF0001087442
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113584
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113584
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113584
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113584
19 | K273 | P.S. 273 - BROOKLYN | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0000843695
19 | K273 | P.S. 273 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 515000 | 0 | DSF0001112664
19 | K273 | P.S. 273 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 146301 | 0 | DSF0000782141
19 | K273 | P.S. 273 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/29/2024 | DOES | 7/31/2024 | DOES | 65832 | 16197 | DSF0001084129
19 | K290 | P.S. 290 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/16/2024 | DOER |  | DOER | 300000 | 0 | DSF0001086072
19 | K290 | P.S. 290 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 105572 | 0 | DSF0000782405
19 | K292 | I.S. 292 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/7/2023 | 11/22/2023 | 11/20/2023 | 54000 | 146024 | 146024 | DSF0001064959, DSF0001092609
19 | K292 | I.S. 292 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 11/21/2023 | 4/24/2024 | 5/6/2024 | 270000 | 354646 | 285432 | DSF0001064959, DSF0001092609
19 | K292 | I.S. 292 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 10/9/2024 | 4/1/2026 |  | 6075001 | 5685354 | 119908 | DSF0001064959, DSF0001092609
19 | K292 | I.S. 292 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 10/9/2024 | 4/1/2026 |  | 378000 | 81235 | 79426 | DSF0001064959, DSF0001092609
19 | K292 | I.S. 292 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 220000 | 0 | DSF0001033057
19 | K292 | I.S. 292 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 121400 | 0 | DSF0000782446
19 | K292 | I.S. 292 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/26/2023 | DOES | 11/6/2023 | DOES | 595936 | 535120 | DSF0001035162
19 | K292 | I.S. 292 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/11/2024 | DOES | 11/21/2024 | DOES | 65832 |  | DSF0001084762
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 1/10/2023 | 5/25/2023 | 6/5/2023 | 69582 | 93226 | 85805 | DSF0001083707, DSF0001111837
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 6/21/2023 | 12/8/2023 | 8/29/2024 | 347914 | 236961 | 225661 | DSF0001083707, DSF0001111837
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 7828056 | 7828056 | 315110 | DSF0001083707, DSF0001111837
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 487079 | 487079 | 98446 | DSF0001083707, DSF0001111837
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/30/2023 | 10/30/2023 | 11/1/2023 | 11700 | 20121 | 20121 | DSF0001083809
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/2/2023 | 4/2/2024 | 4/30/2024 | 52650 | 92180 | 78074 | DSF0001083809
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 8/22/2024 | 9/25/2025 |  | 678600 | 604297 | 2772 | DSF0001083809
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 8/22/2024 | 9/25/2025 |  | 125775 | 76582 | 13402 | DSF0001083809
19 | K302 | VISTA ACADEMY - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES / FY20 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 2/25/2021 | 11/19/2021 | 10/5/2021 | 0 | 30772 | 30772 | DSF0000913266, DSF0000913267
19 | K302 | VISTA ACADEMY - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES / FY20 RESO A SCIENCE LAB UPGRADES | Design | Complete | 10/13/2021 | 12/30/2021 | 2/11/2022 | 57000 | 90049 | 86337 | DSF0000913266, DSF0000913267
19 | K302 | VISTA ACADEMY - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES / FY20 RESO A SCIENCE LAB UPGRADES | Construction | Complete | 5/19/2022 | 3/14/2023 | 8/19/2024 | 836000 | 688922 | 567656 | DSF0000913266, DSF0000913267
19 | K302 | VISTA ACADEMY - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES / FY20 RESO A SCIENCE LAB UPGRADES | CM,F&E | Complete | 5/19/2022 | 3/14/2023 | 8/19/2024 | 101494 | 171135 | 158082 | DSF0000913266, DSF0000913267
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA IEH | PO18-ABATE AND REMOVE PIPE INSULATION MARKED IN RED IN BOILER ROOM AT PUMP SET LESS THAN 10 LF | Construction | Complete | 8/21/2024 | IEH | 9/22/2024 | IEH | 0 | 0 | SCA0000073307
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOOR TILES IN ROOMS. 253, 255, 257, 259, 260A APPROX. FLOOR DAMAGE B | Construction | In-Progress | 10/10/2024 | IEH |  | IEH | 0 | 0 | SCA0000073492
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0 | DSF0001034297
19 | K302 | VISTA ACADEMY - BROOKLYN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/17/2022 | DOER |  | DOER | 42199 | 0 | DSF0001009260
19 | K302 | VISTA ACADEMY - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/20/2023 | DOES | 8/18/2023 | DOES | 309870 |  | DSF0001035163
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/22/2024 | DOES | 10/29/2024 | DOES | 65832 |  | DSF0001084764
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | Scope | Complete | 6/2/2022 | 11/28/2022 | 9/23/2022 | 140809 | 221165 | 186897 | DSF0001014393, DSF0001014394, DSF0001014395, DSF0001014404
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | Design | Complete | 9/27/2022 | 6/12/2023 | 4/19/2023 | 702158 | 502041 | 502041 | DSF0001014393, DSF0001014394, DSF0001014395, DSF0001014404
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | Construction | In-Progress | 9/5/2023 | 9/3/2025 |  | 15635113 | 14238632 | 4533751 | DSF0001014393, DSF0001014394, DSF0001014395, DSF0001014404
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | CM,F&E | In-Progress | 9/5/2023 | 9/3/2025 |  | 1001893 | 455324 | 440791 | DSF0001014393, DSF0001014394, DSF0001014395, DSF0001014404
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/17/2024 | 8/16/2024 | 4/24/2024 | 4992 | 1407 | 1407 | DSF0001087447
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/24/2024 | 10/21/2024 | 9/11/2024 | 22464 | 5626 | 5626 | DSF0001087447
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 289538 | 289538 | 2984 | DSF0001087447
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 53664 | 53664 | 4954 | DSF0001087447
19 | K306 | P.S. 306 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROX. 10 FEET OF ACM STEAM PIPE INSULATION FROM 1-1/4' PIPE IN BASMENT CRAWL SP | Construction | Complete | 6/3/2024 | IEH | 8/1/2024 | IEH | 0 | 0 | SCA0000073048
19 | K306 | P.S. 306 - BROOKLYN | DOE - RESOA | FY22 RESO A STEM LAB | Construction | In-Progress | 8/4/2023 | DOER |  | DOER | 174250 | 0 | DSF0001033059
19 | K306 | P.S. 306 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001112674
19 | K306 | P.S. 306 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75200 | 0 | DSF0000782639
19 | K306 | P.S. 306 - BROOKLYN | DOE - Skilled Trades | ACE BOILER BURNER CONVERSIONS | Construction | In-Progress | 6/30/2021 | DOES |  | DOES | 2393506 | 0 | DSF0000912463
19 | K328 | P.S. 328 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/17/2024 | 8/16/2024 | 5/1/2024 | 4249 | 1215 | 1215 | DSF0001087451
19 | K328 | P.S. 328 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/1/2024 | 10/28/2024 | 9/11/2024 | 19122 | 4859 | 4859 | DSF0001087451
19 | K328 | P.S. 328 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 246466 | 246466 | 0 | DSF0001087451
19 | K328 | P.S. 328 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 45681 | 45681 | 6145 | DSF0001087451
19 | K328 | P.S. 328 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROX. 10 LINEAR FEET OF STEAM PIPE INSULATION FROM HORRIZONTAL 6' PIPES ABOUT 8 | Construction | Complete | 6/10/2024 | IEH | 9/14/2024 | IEH | 0 | 0 | SCA0000073059
19 | K328 | P.S. 328 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 15 LINEAER FEET OF PIPE COVERING FROM PIPE AND VALVES# 38, 39 AND 4 | Construction | Complete | 9/23/2024 | IEH | 11/3/2024 | IEH | 0 | 0 | SCA0000073412
19 | K328 | P.S. 328 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 6/29/2022 | DOES |  | DOES | 333888 | 0 | DSF0000865740
19 | K345 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/22/2018 | 9/20/2018 | 10/19/2018 | 84019 | 104917 | 104917 | DSF0000888832, DSF0000895966, DSF0000989899
19 | K345 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | Design | Complete | 12/18/2018 | 3/11/2019 | 9/10/2019 | 380332 | 300305 | 296735 | DSF0000888832, DSF0000895966, DSF0000989899
19 | K345 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | Construction | Complete | 10/12/2022 | 4/3/2024 | 10/15/2024 | 7651235 | 7711829 | 6913663 | DSF0000888832, DSF0000895966, DSF0000989899
19 | K345 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | CM,F&E | Complete | 10/12/2022 | 4/3/2024 | 10/15/2024 | 563015 | 595419 | 590741 | DSF0000888832, DSF0000895966, DSF0000989899
19 | K345 | P.S. 345 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN AUDITORIUM | Construction | Complete | 6/27/2024 | IEH | 7/17/2024 | IEH | 0 | 0 | SCA0000073095
19 | K345 | P.S. 345 - BROOKLYN | SCA IEH | PO18-ABATE AND PENETRATE FLOOR AND REMOVE CONDUIT 1/4' HOLES X 4 PCS TO MOUNT THE POWER POLES - (2 H | Construction | Complete | 10/8/2024 | IEH | 10/12/2024 | IEH | 0 | 0 | SCA0000073476
19 | K345 | P.S. 345 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 10/28/2022 | DOER | 12/19/2022 | DOER | 205858 | 203088 | DSF0001033071
19 | K345 | P.S. 345 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/12/2024 | DOER |  | DOER | 250000 | 150000 | DSF0001086094
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 3/2/2021 | 7/15/2021 | 11/8/2021 | 128939 | 108064 | 108064 | DSF0000941309, DSF0000941310
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/9/2021 | 4/14/2022 | 5/13/2022 | 635011 | 395830 | 395830 | DSF0000941309, DSF0000941310
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 9/12/2022 | 6/2/2024 |  | 13450108 | 13364542 | 11897372 | DSF0000941309, DSF0000941310
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/12/2022 | 6/2/2024 |  | 975198 | 951257 | 936912 | DSF0000941309, DSF0000941310
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 9/22/2023 | 1/26/2024 | 10/24/2023 | 5074 | 1371 | 1371 | DSF0001035022
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 10/24/2023 | 4/22/2024 | 12/20/2023 | 22833 | 5485 | 5485 | DSF0001035022
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 4/16/2024 | 3/11/2025 |  | 294292 | 261197 | 99137 | DSF0001035022
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 4/16/2024 | 3/11/2025 |  | 90571 | 69336 | 46947 | DSF0001035022
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113587
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113587
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113587
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113587
19 | K346 | I.S. 452 | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/16/2023 | 10/12/2023 | 9/12/2023 | 0 | 22717 | 22717 | DSF0001035544, DSF0001035545
19 | K346 | I.S. 452 | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 9/12/2023 | 1/18/2024 | 11/29/2023 | 60000 | 76213 | 70117 | DSF0001035544, DSF0001035545
19 | K346 | I.S. 452 | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 4/30/2024 | 3/25/2025 |  | 880000 | 575474 | 192580 | DSF0001035544, DSF0001035545
19 | K346 | I.S. 452 | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 4/30/2024 | 3/25/2025 |  | 60066 | 71356 | 44829 | DSF0001035544, DSF0001035545
19 | K346 | P.S. 346 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 8/6/2020 | FTK |  | FTK | 397822 | 383490 | DSF0000912756, DSF0000913021
19 | K346 | P.S. 346 - BROOKLYN | DIIT - RESOA | RESO A- FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 105000 | 0 | DSF0000960939
19 | K346 | P.S. 346 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/30/2024 | DIIR | 150000 | 150000 | DSF0001033073
19 | K346 | I.S. 452 | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001033091
19 | K346 | P.S. 346 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1459000 | 0 | DSF0001086163
19 | K346 | P.S. 346 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 145000 | 0 | DSF0001086095
19 | K346 | P.S. 346 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 75200 | 0 | DSF0000782973
19 | K346 | P.S. 346 - BROOKLYN | DOE - Skilled Trades | PARTIAL ACCESSIBILITY - ELEVATORS | Construction | In-Progress | 6/1/2017 | DOES |  | DOES | 483511 | 0 | DSF0000845615
19 | K346 | I.S. 452 | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/25/2024 | DOES |  | DOES | 461151 | 0 | DSF0001085726
19 | K364 | I.S. 364 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 100000 | 100000 | 100000 | DSF0001086099
19 | K420 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | Scope | Complete | 2/22/2022 | 6/21/2022 | 6/24/2022 | 6362 | 30398 | 30398 | DSF0000865803
19 | K420 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | Design | Complete | 11/3/2022 | 5/3/2023 | 5/3/2023 | 23326 | 17831 | 11739 | DSF0000865803
19 | K420 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/9/2023 | 10/3/2024 |  | 247044 | 224142 | 169549 | DSF0000865803
19 | K420 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 11/9/2023 | 10/3/2024 |  | 173434 | 165246 | 129706 | DSF0000865803
19 | K420 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | SCA CIP | ACCESSIBLE RAMP / ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 1/27/2023 | 6/23/2023 | 8/29/2023 | 1229210 | 976679 | 942087 | DSF0001083714, DSF0001065973, DSF0001087215, DSF0001087214
19 | K420 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | SCA CIP | ACCESSIBLE RAMP / ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 10/5/2023 | 5/15/2024 | 5/13/2024 | 6146050 | 2624751 | 231091 | DSF0001083714, DSF0001065973, DSF0001087215, DSF0001087214
19 | K420 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | SCA CIP | ACCESSIBLE RAMP / ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SERVICE UPGRADE | Construction | PNS | PNS | PNS | PNS | 138286126 | 138286126 | 215941 | DSF0001083714, DSF0001065973, DSF0001087215, DSF0001087214
19 | K420 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | SCA CIP | ACCESSIBLE RAMP / ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SERVICE UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 8604470 | 8604470 | 175581 | DSF0001083714, DSF0001065973, DSF0001087215, DSF0001087214
19 | K420 | MULTICULTURAL HS - BROOKLYN | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 6/18/2024 |  | 9/3/2024 | 350000 | 350000 | 350000 | DSF0001035567
19 | K420 | MULTICULTURAL HS - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 137113 | 0 | DSF0000959906
19 | K420 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Construction | Complete | 10/1/2021 | DOER | 2/23/2022 | DOER | 139367 | 139252 | DSF0000913058
19 | K420 | ACADEMY OF INNOV TECH - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 129000 | 0 | DSF0001112706
19 | K420 | ACADEMY OF INNOV TECH - BROOKLYN | DOE - Skilled Trades | ENY AUDITORIUM UPGRADE | Construction | In-Progress | 10/16/2023 | DOES |  | DOES | 672083 | 0 | DSF0000865804
19 | K420 | CYPRESS HILLS COLLEGIATE - K | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 20005 | 0 | DSF0000912220
19 | K420 | FRANKLIN K LANE CAMPUS YABC | DOE - Skilled Trades | CHARTER MATCH CAFETERIA SERVING LINE | Construction | Complete | 6/29/2019 | DOES | 10/21/2020 | DOES | 243721 | 243721 | DSF0000912531
19 | K420 | BROOKLYN LAB SCHOOL - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/5/2024 | DOES | 8/16/2024 | DOES | 65832 |  | DSF0001084899
19 | K422 | K053 SPED - BROOKLYN | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 230000 | 230000 | 0 | DSF0001112708
19 | K422 | ACAD. FOR YOUNG WRITERS - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 205000 | 0 | DSF0001112707
19 | K422 | K053 SPED - BROOKLYN | DOE - RESOA | FY16 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 1/15/2018 | DOER |  | DOER | 131814 | 0 | DSF0000822283
19 | K422 | ACAD. FOR YOUNG WRITERS - K | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112709
19 | K422 | SPRING CREEK COMMUNITY SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/5/2024 | DOES |  | DOES | 599805 | 0 | DSF0001035164
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP | ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ANSUL SYSTEMS / FIRE ALARM SYSTEM | Scope | Complete | 6/20/2023 | 12/18/2023 | 11/2/2023 | 670392 | 380853 | 361322 | DSF0001066045, DSF0001111785, DSF0001111784, DSF0001111783, DSF0001111782, DSF0001111787, DSF0001111786
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP | ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ANSUL SYSTEMS / FIRE ALARM SYSTEM | Design | Complete | 12/27/2023 | 7/1/2024 | 5/13/2024 | 3346390 | 835136 | 835052 | DSF0001066045, DSF0001111785, DSF0001111784, DSF0001111783, DSF0001111782, DSF0001111787, DSF0001111786
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP | ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ANSUL SYSTEMS / FIRE ALARM SYSTEM | Construction | PNS | PNS | PNS | PNS | 74811771 | 74811771 | 425829 | DSF0001066045, DSF0001111785, DSF0001111784, DSF0001111783, DSF0001111782, DSF0001111787, DSF0001111786
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP | ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ANSUL SYSTEMS / FIRE ALARM SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 4734539 | 4734539 | 89754 | DSF0001066045, DSF0001111785, DSF0001111784, DSF0001111783, DSF0001111782, DSF0001111787, DSF0001111786
19 | K435 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Scope | Complete | 11/19/2021 | 6/30/2022 | 5/12/2022 | 16893 | 339061 | 22302 | DSF0000990366, DSF0001034677
19 | K435 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Design | Complete | 5/13/2022 | 9/26/2022 | 10/7/2022 | 83405 | 117356 | 73329 | DSF0000990366, DSF0001034677
19 | K435 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Construction | In-Progress | 10/23/2023 | 3/5/2025 |  | 1784836 | 1589683 | 866072 | DSF0000990366, DSF0001034677
19 | K435 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 10/23/2023 | 3/5/2025 |  | 126210 | 198020 | 196075 | DSF0000990366, DSF0001034677
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | Scope | Complete | 2/13/2023 | 5/12/2023 | 1/9/2024 | 0 | 54126 | 54126 | DSF0001035569
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | Design | PNS | PNS | PNS | PNS | 6000 | 5296 | 5296 | DSF0001035569
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | Construction | PNS | PNS | PNS | PNS | 88000 | 3571436 | 3297 | DSF0001035569
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 243507 | 7277 | DSF0001035569
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LEARNING GARDEN | Scope | In-Progress | 2/13/2023 | 5/15/2023 |  | 0 | 257 | 257 | DSF0001035570
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LEARNING GARDEN | Design | PNS | PNS | PNS | PNS | 0 | 1029 | 1029 | DSF0001035570
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LEARNING GARDEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035570
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LEARNING GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 2664 | 2664 | DSF0001035570
19 | K435 | THOMAS JEFFERSON CAMPUS YABC | SCA Emergency Response | EMERGENCY STABILIZATION- UNSAFE FACADE CONDITIONS @ K435 | Construction | In-Progress | 8/1/2023 | EMER |  | EMER | 1416247 | 1265032 | SCA0000072186
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 389000 | 389000 | 125336 | DSF0001086118
19 | K435 | FDNY - CAPTAIN VERNON A. RICHARDS HIGH SCHOOL FOR FIRE AND LIFE SAFETY-K | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 139930 | 0 | DSF0000959916
19 | K435 | PERFORMING ARTS AND TECH. HS - K | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/11/2022 | DOER |  | DOER | 1138269 | 0 | DSF0000822894
19 | K435 | PERFORMING ARTS AND TECH. HS - K | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 6/14/2021 | DOES |  | DOES | 202376 | 0 | DSF0000865741
19 | K435 | PERFORMING ARTS AND TECH. HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/7/2024 | DOES | 8/14/2024 | DOES | 65832 | 11906 | DSF0001084903
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | Scope | Complete | 3/9/2023 | 10/6/2023 | 10/25/2023 | 549000 | 703984 | 701944 | DSF0001083910, DSF0001066063
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | Design | Complete | 10/30/2023 | 5/15/2024 | 5/15/2024 | 2745000 | 1807013 | 1330999 | DSF0001083910, DSF0001066063
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | Construction | In-Progress | 9/23/2024 | 6/14/2026 |  | 61762500 | 55285492 | 305602 | DSF0001083910, DSF0001066063
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | CM,F&E | In-Progress | 9/23/2024 | 6/14/2026 |  | 3843000 | 368216 | 366309 | DSF0001083910, DSF0001066063
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | Scope | Complete | 10/25/2023 | 10/25/2023 | 10/25/2023 | 19252 | 21757 | 21757 | DSF0001087206
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | Design | Complete | 10/25/2023 | 2/29/2024 | 4/8/2024 | 96262 | 87309 | 11102 | DSF0001087206
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | Construction | In-Progress | 7/8/2024 | 1/3/2025 |  | 2165888 | 2692492 | 1749522 | DSF0001087206
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | CM,F&E | In-Progress | 7/8/2024 | 1/3/2025 |  | 135768 | 246539 | 236299 | DSF0001087206
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | DOE - Skilled Trades | ATHLETIC FIELD | Construction | In-Progress | 4/30/2023 | DOES |  | DOES | 3494120 | 0 | DSF0001083984
19 | K599 | EAST NY FAMILY ACAD. - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/18/2024 | DOES | 7/12/2024 | DOES | 50832 |  | DSF0001084923
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/27/2020 | 11/23/2020 | 10/22/2020 | 282728 | 357081 | 356275 | DSF0000942167, DSF0000942168, DSF0000942169, DSF0000942170, DSF0001008587
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/3/2020 | 6/15/2021 | 7/1/2021 | 1405112 | 764606 | 764606 | DSF0000942167, DSF0000942168, DSF0000942169, DSF0000942170, DSF0001008587
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 6/13/2022 | 6/11/2024 |  | 30877347 | 28106693 | 24799523 | DSF0000942167, DSF0000942168, DSF0000942169, DSF0000942170, DSF0001008587
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 6/13/2022 | 6/11/2024 |  | 2043050 | 740275 | 732277 | DSF0000942167, DSF0000942168, DSF0000942169, DSF0000942170, DSF0001008587
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA IEH | PO18-ABATE10-12 FEET OF WRAPPED PIPE INSULATION BASEMENT ROOM 36B CE LUIS CRUZ 718-647-5204 X6158 | Construction | Complete | 9/13/2024 | IEH | 9/15/2024 | IEH | 0 | 0 | SCA0000073376
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA IEH | PO18-ADDITIONAL WORK IN THE BOILER ROOM | Construction | Complete | 9/18/2024 | IEH | 9/22/2024 | IEH | 0 | 0 | SCA0000073397
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 3/4/2022 | DOES |  | DOES | 631884 | 0 | DSF0000911946
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 12/1/2022 | DOES | 12/28/2023 | DOES | 478803 | 470337 | DSF0000960849
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/18/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084926
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/23/2023 | 10/23/2023 | 10/18/2023 | 15100 | 24893 | 24893 | DSF0001083800
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/14/2023 | 4/15/2024 | 5/15/2024 | 75500 | 105064 | 85143 | DSF0001083800
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 10/1/2024 | 11/4/2025 |  | 1698750 | 1530795 | 161750 | DSF0001083800
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 10/1/2024 | 11/4/2025 |  | 105700 | 39083 | 38599 | DSF0001083800
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112732
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 42000 | 42000 | 0 | DSF0001112732
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 616000 | 616000 | 0 | DSF0001112732
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 42000 | 42000 | 0 | DSF0001112732
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113595
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113595
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113595
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113595
19 | K660 | WILLIAM MAXWELL VOC HS - K | Fast Track Projects | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/28/2023 | FTK |  | FTK | 101795 | 96015 | DSF0001035585
19 | K660 | WILLIAM MAXWELL VOC HS - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/26/2023 | DOES | 7/21/2023 | DOES | 471086 | 418274 | DSF0001035160
19 | K660 | WILLIAM MAXWELL VOC HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/21/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084930
19 | K660 | WILLIAM MAXWELL VOC HS - K | DOE - Skilled Trades | FIRE PUMP SYSTEM REPLACEMENT | Construction | In-Progress | 1/3/2024 | DOES |  | DOES | 98631 | 0 | DSF0001094470
19 | K667 | M.S. 935 - BROOKLYN | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 371000 | 0 | DSF0001033138
19 | K667 | P.S. 938 - BROOKLYN | DOE - RESOA | FY25 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112733
19 | K798 | P.S. 65 - BROOKLYN | SCA CIP | ROOFS | Scope | In-Progress | 8/20/2024 | 1/8/2025 |  | 38191 | 49059 | 1834 | DSF0001067039
19 | K798 | P.S. 65 - BROOKLYN | SCA CIP | ROOFS | Design | PNS | PNS | PNS | PNS | 190955 | 190955 | 7336 | DSF0001067039
19 | K798 | P.S. 65 - BROOKLYN | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 4296495 | 4296495 | 0 | DSF0001067039
19 | K798 | P.S. 65 - BROOKLYN | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 267337 | 267337 | 7464 | DSF0001067039
19 | K798 | K004 SPED - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 252708 | 0 | DSF0000959956
19 | K814 | P.S. 89 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 10/28/2024 | IEH | 11/9/2024 | IEH | 0 | 0 | SCA0000073549
19 | K848 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/16/2018 | 3/6/2019 | 2/8/2019 | 48184 | 44140 | 44140 | DSF0000874361, DSF0000874362, DSF0000897226
19 | K848 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/8/2019 | 7/11/2019 | 5/8/2019 | 183794 | 143825 | 135226 | DSF0000874361, DSF0000874362, DSF0000897226
19 | K848 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | Complete | 5/11/2023 | 8/2/2024 | 10/9/2024 | 2643522 | 2395976 | 1863502 | DSF0000874361, DSF0000874362, DSF0000897226
19 | K848 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 5/11/2023 | 8/2/2024 | 10/9/2024 | 341117 | 182143 | 180352 | DSF0000874361, DSF0000874362, DSF0000897226
19 | K848 | P.S. 149 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 11/19/2024 | IEH | 11/28/2024 | IEH | 0 | 0 | SCA0000073617
19 | K851 | P.S. 159 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 11/8/2024 | IEH |  | IEH | 0 | 0 | SCA0000073594
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | Scope | Complete | 10/25/2022 | 1/27/2023 | 7/20/2023 | 53682 | 69479 | 69477 | DSF0001016624, DSF0001016630, DSF0001085781
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | Design | Complete | 8/2/2023 | 2/7/2024 | 4/17/2024 | 250136 | 488831 | 174786 | DSF0001016624, DSF0001016630, DSF0001085781
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | Construction | In-Progress | 8/5/2024 | 8/4/2026 |  | 4047144 | 3610101 | 6075 | DSF0001016624, DSF0001016630, DSF0001085781
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 8/5/2024 | 8/4/2026 |  | 512852 | 60681 | 60266 | DSF0001016624, DSF0001016630, DSF0001085781
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/21/2022 | 3/24/2023 | 12/6/2022 | 3697 | 3217 | 3217 | DSF0001034557
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/6/2022 | 6/2/2023 | 4/5/2023 | 16638 | 12866 | 12866 | DSF0001034557
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 214442 | 197188 | 170739 | DSF0001034557
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 90566 | 76902 | 72808 | DSF0001034557
19 | K857 | K036 SPED - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/7/2022 | DOES |  | DOES | 173373 | 0 | DSF0001008687
19 | K872 | I.S. 364 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 7/11/2024 | IEH |  | IEH | 0 | 0 | SCA0000073132
19 | K932 | PASSAGES ACADEMY | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/14/2024 | IEH | 8/21/2024 | IEH | 0 | 0 | SCA0000073285
19 | KAKM | IMAGINE ME LEADERSHIP CHARTER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 633000 | 0 | DSF0001112747
19 | KAMH | COLLEGIATE ACADEMY FOR MATH AND PERSONAL AWARENESS CHARTER SCHOOL - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 250000 | 0 | DSF0000961217
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 4/9/2021 | 7/9/2021 | 8/3/2021 | 12644 | 26983 | 19209 | DSF0001008772
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | In-Progress | 9/28/2022 | 2/1/2023 |  | 56896 | 56896 | 31712 | DSF0001008772
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Construction | PNS | PNS | PNS | PNS | 733326 | 733326 | 15531 | DSF0001008772
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | CM,F&E | PNS | PNS | PNS | PNS | 137502 | 137502 | 16187 | DSF0001008772
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | PATH OF TRAVEL | Scope | Complete | 5/26/2023 | 9/25/2023 | 9/1/2023 | 1445 | 5765 | 0 | DSF0001008772
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | PATH OF TRAVEL | Design | In-Progress | 9/5/2023 | 1/10/2024 |  | 6504 | 6504 | 0 | DSF0001008772
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | PATH OF TRAVEL | Construction | PNS | PNS | PNS | PNS | 83824 | 83824 | 5254 | DSF0001008772
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | PATH OF TRAVEL | CM,F&E | PNS | PNS | PNS | PNS | 15536 | 15536 | 13037 | DSF0001008772
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 6/29/2020 | 9/28/2020 | 9/2/2020 | 17354 | 84149 | 84149 | DSF0000937107, DSF0000961569
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 11/25/2020 | 4/14/2021 | 4/14/2021 | 85416 | 183996 | 178626 | DSF0000937107, DSF0000961569
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | In-Progress | 9/20/2021 | 9/19/2022 |  | 1804739 | 1774075 | 1513955 | DSF0000937107, DSF0000961569
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | In-Progress | 9/20/2021 | 9/19/2022 |  | 131634 | 225697 | 217424 | DSF0000937107, DSF0000961569
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112543
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 18480 | 18480 | 0 | DSF0001112543
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 271040 | 271040 | 0 | DSF0001112543
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 18480 | 18480 | 0 | DSF0001112543
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113563
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113563
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113563
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113563
20 | K048 | P.S. 48 - BROOKLYN | SCA IEH | PO18-ABATE ACM PIPE COVERING ON 4' WASTE- LINE IN CAFETERIA COMING THROUGH CEILING FROM PRINCIPALS O | Construction | Complete | 9/17/2024 | IEH | 9/17/2024 | IEH | 0 | 0 | SCA0000073389
20 | K048 | P.S. 48 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/26/2024 | DIIR | 10/17/2024 | DIIR | 250000 | 250000 | DSF0001085955
20 | K048 | P.S. 48 - BROOKLYN | DOE - Skilled Trades | DOMESTIC WATER HEATER | Construction | In-Progress | 7/6/2020 | DOES |  | DOES | 42566 | 0 | DSF0000961133
20 | K048 | P.S. 48 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/23/2022 | DOES |  | DOES | 51304 | 0 | DSF0001009056
20 | K053 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/1/2021 | 10/12/2021 | 10/15/2021 | 1189920 | 908492 | 789539 | DSF0000843829
20 | K053 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 10/18/2021 | 4/1/2022 | 5/11/2022 | 5354640 | 2550300 | 1710352 | DSF0000843829
20 | K053 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 12/22/2022 | 9/3/2024 |  | 67527960 | 63676660 | 61209471 | DSF0000843829
20 | K053 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 12/22/2022 | 9/3/2024 |  | 9519360 | 5977216 | 3946427 | DSF0000843829
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 12/13/2017 | 5/16/2018 | 3/20/2018 | 111330 | 102001 | 102001 | DSF0000869288, DSF0000888784
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 3/23/2018 | 8/22/2018 | 7/31/2018 | 445320 | 470931 | 466277 | DSF0000869288, DSF0000888784
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 12/3/2018 | 12/1/2020 |  | 8349750 | 8125260 | 7901785 | DSF0000869288, DSF0000888784
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 12/3/2018 | 12/1/2020 |  | 519540 | 1009605 | 1004532 | DSF0000869288, DSF0000888784
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/6/2022 | 11/30/2022 | 9/23/2022 | 218830 | 253027 | 251346 | DSF0001010408, DSF0001010409, DSF0001010410, DSF0001010411, DSF0001010407
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 9/27/2022 | 6/12/2023 | 4/27/2023 | 1094151 | 501186 | 501186 | DSF0001010408, DSF0001010409, DSF0001010410, DSF0001010411, DSF0001010407
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 9/18/2023 | 2/3/2026 |  | 24618375 | 22173274 | 6910256 | DSF0001010408, DSF0001010409, DSF0001010410, DSF0001010411, DSF0001010407
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 9/18/2023 | 2/3/2026 |  | 1531810 | 315690 | 311241 | DSF0001010408, DSF0001010409, DSF0001010410, DSF0001010411, DSF0001010407
20 | K062 | I.S. 62 - BROOKLYN | SCA IEH | PO18-ABATE EXITING CEILING TILE AND PIPE INSULATION IN 1ST FLOOR GYMNASIUM ADJACENT TO THE MAIN LOBB | Construction | Complete | 3/16/2024 | IEH | 7/9/2024 | IEH | 0 | 0 | SCA0000072833
20 | K062 | I.S. 62 - BROOKLYN | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 9/11/2023 | DOER |  | DOER | 414117 | 0 | DSF0000867219
20 | K062 | I.S. 62 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 3/20/2023 | DOES |  | DOES | 614332 | 0 | DSF0001061100
20 | K062 | I.S. 62 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/16/2024 | DOES | 10/29/2024 | DOES | 65832 |  | DSF0001084730
20 | K062 | I.S. 62 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/8/2024 | DOES |  | DOES | 636369 | 0 | DSF0001085713
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2024 | 7/1/2024 | 4/4/2024 | 2934 | 2098 | 2098 | DSF0001087382
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/4/2024 | 9/30/2024 | 9/25/2024 | 13205 | 8392 | 8392 | DSF0001087382
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 170195 | 170195 | 0 | DSF0001087382
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 31545 | 31545 | 1677 | DSF0001087382
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/28/2022 | 4/28/2022 | 6/28/2022 | 0 | 22927 | 22927 | DSF0001033458
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 7/11/2022 | 11/25/2022 | 1/5/2023 | 48384 | 56147 | 56147 | DSF0001033458
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | Complete | 9/25/2023 | 8/19/2024 | 11/8/2024 | 709639 | 645126 | 552307 | DSF0001033458
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 9/25/2023 | 8/19/2024 | 11/8/2024 | 48384 | 63766 | 49504 | DSF0001033458
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/6/2023 | 4/9/2024 | 3/26/2024 | 0 | 16315 | 16315 | DSF0001085962
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 4/10/2024 | 9/11/2024 | 8/23/2024 | 75000 | 35402 | 31159 | DSF0001085962
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1100000 | 1100000 | 0 | DSF0001085962
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 75000 | 75000 | 5904 | DSF0001085962
20 | K069 | P.S. 69 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/31/2024 | DIIR | 7/9/2024 | DIIR | 200000 | 200000 | DSF0001035402
20 | K069 | P.S. 69 - BROOKLYN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 4/29/2024 | DOER | 5/16/2024 | DOER | 79073 | 70918 | DSF0001035403
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 11/1/2022 | 4/14/2023 | 4/13/2023 | 1274220 | 720341 | 720280 | DSF0000798187
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 4/14/2023 | 11/30/2023 | 5/1/2024 | 5733990 | 1259688 | 1020196 | DSF0000798187
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 12/2/2024 | 9/3/2027 |  | 72311985 | 64025147 | 283817 | DSF0000798187
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 12/2/2024 | 9/3/2027 |  | 10193760 | 3927480 | 319901 | DSF0000798187
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 1/26/2023 | 1/26/2023 | 1/26/2023 | 72660 | 1263 | 1263 | DSF0000798187
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 1/26/2023 | 7/5/2023 | 10/17/2023 | 363300 | 259250 | 180275 | DSF0000798187
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Construction | In-Progress | 12/18/2023 | 3/16/2024 |  | 8174250 | 7333983 | 4624434 | DSF0000798187
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 12/18/2023 | 3/16/2024 |  | 508620 | 319749 | 226592 | DSF0000798187
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 10/12/2023 | 3/1/2024 | 4/23/2024 | 31559 | 129634 | 129269 | DSF0001061622
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Design | In-Progress | 5/6/2024 | 10/7/2024 |  | 157794 | 157794 | 75213 | DSF0001061622
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 3550365 | 3550365 | 125743 | DSF0001061622
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 220912 | 220912 | 86309 | DSF0001061622
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | PATH OF TRAVEL FLOOD ELIMINATION | Scope | Complete | 2/15/2024 | 5/15/2024 | 10/21/2024 | 6164 | 620 | 620 | DSF0001112041
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | PATH OF TRAVEL FLOOD ELIMINATION | Design | In-Progress | 10/22/2024 | 2/24/2025 |  | 27737 | 27737 | 2480 | DSF0001112041
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | PATH OF TRAVEL FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 357495 | 357495 | 0 | DSF0001112041
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | PATH OF TRAVEL FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 66260 | 66260 | 2369 | DSF0001112041
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/28/2024 | 7/29/2024 | 4/19/2024 | 4429 | 3429 | 3429 | DSF0001087386
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/19/2024 | 10/16/2024 | 9/25/2024 | 19929 | 13714 | 13714 | DSF0001087386
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 256856 | 256856 | 2879 | DSF0001087386
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 47607 | 47607 | 3507 | DSF0001087386
20 | K102 | P.S. 102 - BROOKLYN | SCA IEH | PO18-DRILLING IS NEEDED FOR NEW ELECTRICAL WORK TO BE DONE IN KITCHEN | Construction | In-Progress | 6/4/2024 | IEH |  | IEH | 0 | 0 | SCA0000073051
20 | K102 | P.S. 102 - BROOKLYN | SCA IEH | PO18-ABATE ACM FROM HOT AND COLD WATER PIPES, LOCATED IN ROOM 110, NEAR CEILING , MARKED WITH BLACK | Construction | Complete | 10/15/2024 | IEH | 11/3/2024 | IEH | 0 | 0 | SCA0000073508
20 | K102 | P.S. 102 - BROOKLYN | SCA IEH | PO18-REMOVE APRROX 6 FT OF ACM PIPE INSULATION FROM A 3/4' WATER PIPE IN ROOM 232 NEAR CEILING MARK | Construction | Complete | 11/7/2024 | IEH | 11/9/2024 | IEH | 0 | 0 | SCA0000073589
20 | K102 | P.S. 102 - BROOKLYN | SCA IEH | PO18-ABATE AND DRILL AT LISTED LOCATIONS: OUTSIDE AND INSIDE MAIN ENTRANCE FOUNDATION WALLS IN BOILE | Construction | Complete | 11/13/2024 | IEH | 11/17/2024 | IEH | 0 | 0 | SCA0000073603
20 | K102 | P.S. 102 - BROOKLYN | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 100000 | 100000 | 0 | DSF0001008300
20 | K102 | P.S. 102 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 62828 | 62828 | 923 | DSF0001085974
20 | K102 | P.S. 102 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 123000 | 0 | DSF0001085973
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | Scope | Complete | 9/22/2016 | 7/26/2023 | 4/19/2023 | 239660 | 246608 | 246202 | DSF0000798257, DSF0000798260, DSF0000986211, DSF0001010957, DSF0001061643
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | Design | Complete | 4/20/2023 | 9/21/2023 | 5/9/2023 | 1198300 | 880222 | 669553 | DSF0000798257, DSF0000798260, DSF0000986211, DSF0001010957, DSF0001061643
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | Construction | In-Progress | 9/18/2023 | 3/5/2026 |  | 26961751 | 24430902 | 8685970 | DSF0000798257, DSF0000798260, DSF0000986211, DSF0001010957, DSF0001061643
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | CM,F&E | In-Progress | 9/18/2023 | 3/5/2026 |  | 1678591 | 429484 | 425236 | DSF0000798257, DSF0000798260, DSF0000986211, DSF0001010957, DSF0001061643
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY23 RESO A OUTDOOR STEM CENTER | Scope | Complete | 2/15/2023 | 5/16/2023 | 2/9/2024 | 0 | 57682 | 57682 | DSF0001035418
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY23 RESO A OUTDOOR STEM CENTER | Design | In-Progress | 2/21/2024 | 7/8/2024 |  | 51000 | 44933 | 30325 | DSF0001035418
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY23 RESO A OUTDOOR STEM CENTER | Construction | PNS | PNS | PNS | PNS | 748000 | 748000 | 7285 | DSF0001035418
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY23 RESO A OUTDOOR STEM CENTER | CM,F&E | PNS | PNS | PNS | PNS | 51000 | 51000 | 16786 | DSF0001035418
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A OUTDOOR STEM CENTER | Scope | Complete | 2/22/2023 | 5/23/2023 | 4/3/2024 | 0 | 1742 | 1742 | DSF0001035419
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A OUTDOOR STEM CENTER | Design | In-Progress | 4/12/2024 | 8/15/2024 |  | 7089 | 6965 | 6965 | DSF0001035419
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A OUTDOOR STEM CENTER | Construction | PNS | PNS | PNS | PNS | 103975 | 103975 | 0 | DSF0001035419
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A OUTDOOR STEM CENTER | CM,F&E | PNS | PNS | PNS | PNS | 7089 | 7089 | 3812 | DSF0001035419
20 | K104 | P.S. 104 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REPLACE THIRD FLOOR HALLWAY FLOOR TILES APPROX 2100 SQUARE FEET AHERA = YES | Construction | In-Progress | 8/28/2023 | IEH |  | IEH | 0 | 0 | SCA0000072241
20 | K104 | P.S. 104 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER AND CEILING PLASTER FOR ROOMS: 328,322,228,111,128,222,316,309, A | Construction | Complete | 6/27/2024 | IEH | 8/15/2024 | IEH | 0 | 0 | SCA0000073091
20 | K104 | P.S. 104 - BROOKLYN | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC SAMPLING ON CAFETERIA CEILING AND ABATE IF NEEDED, SPACE ID: 2500 | Construction | Complete | 10/9/2024 | IEH | 11/13/2024 | IEH | 0 | 0 | SCA0000073482
20 | K104 | P.S. 104 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/1/2023 | DOER |  | DOER | 4207 | 0 | DSF0000913218
20 | K104 | P.S. 104 - BROOKLYN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 1/27/2023 | DOER |  | DOER | 500000 | 0 | DSF0001033011
20 | K104 | P.S. 104 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/3/2024 | DOES | 9/10/2024 | DOES | 65832 | 16122 | DSF0001084591
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 4/19/2024 | 7/22/2024 |  | 0 | 20192 | 2623 | DSF0001085975
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 66000 | 45808 | 10494 | DSF0001085975
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 968000 | 968000 | 0 | DSF0001085975
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 66000 | 66000 | 7450 | DSF0001085975
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 4/19/2024 | 7/22/2024 |  | 0 | 0 | 0 | DSF0001087006
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087006
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087006
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 1517 | 1517 | DSF0001087006
20 | K105 | P.S. 105 - BROOKLYN | Fast Track Projects | LSP - REPLACE DOMESTIC WATER HEATER | Construction | In-Progress | 5/23/2018 | FTK |  | FTK | 149854 | 134334 | DSF0000867023
20 | K105 | P.S. 105 - BROOKLYN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/11/2020 | DOER |  | DOER | 477149 | 0 | DSF0000890751
20 | K105 | P.S. 105 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 274857 | 0 | DSF0001034218
20 | K112 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 6/18/2019 | 11/1/2019 | 12/31/2019 | 105581 | 165197 | 163449 | DSF0000892622, DSF0000892623, DSF0000892624, DSF0000892625, DSF0000937911
20 | K112 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | Design | Complete | 1/8/2020 | 6/9/2020 | 6/30/2020 | 521856 | 418412 | 396197 | DSF0000892622, DSF0000892623, DSF0000892624, DSF0000892625, DSF0000937911
20 | K112 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 2/6/2023 | 2/4/2025 |  | 11218306 | 10293248 | 8007319 | DSF0000892622, DSF0000892623, DSF0000892624, DSF0000892625, DSF0000937911
20 | K112 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 2/6/2023 | 2/4/2025 |  | 785642 | 276804 | 274773 | DSF0000892622, DSF0000892623, DSF0000892624, DSF0000892625, DSF0000937911
20 | K112 | P.S. 112 - BROOKLYN | SCA IEH | PO18-ABATE ACM PIPE COVERING IN DROP CEILING - ROOM 109 WATER PIPE. EMERGENCY PIPE REPAIR. AP | Construction | Complete | 9/26/2024 | IEH | 9/28/2024 | IEH | 0 | 0 | SCA0000073438
20 | K112 | P.S. 112 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE STAIRCASE #2 SPACE ID#3002S BETWEEN 2ND AND 3RD FL STAIRCASE #3 SPACE ID#2003 | Construction | In-Progress | 11/4/2024 | IEH |  | IEH | 0 | 0 | SCA0000073567
20 | K112 | P.S. 112 - BROOKLYN | DIIT - RESOA | FY21 RESO A (MA) TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001008618
20 | K127 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | Scope | Complete | 6/30/2017 | 12/6/2021 | 10/28/2021 | 262426 | 415422 | 415422 | DSF0000802991, DSF0000825427, DSF0000798424, DSF0000779662, DSF0000798189, DSF0000870064, DSF0001034341
20 | K127 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | Design | Complete | 11/18/2021 | 6/30/2022 | 4/26/2022 | 1293602 | 1527711 | 1447428 | DSF0000802991, DSF0000825427, DSF0000798424, DSF0000779662, DSF0000798189, DSF0000870064, DSF0001034341
20 | K127 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | Construction | In-Progress | 9/26/2022 | 12/13/2024 |  | 28828128 | 27566203 | 17608267 | DSF0000802991, DSF0000825427, DSF0000798424, DSF0000779662, DSF0000798189, DSF0000870064, DSF0001034341
20 | K127 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | CM,F&E | In-Progress | 9/26/2022 | 12/13/2024 |  | 1795257 | 1349834 | 1309888 | DSF0000802991, DSF0000825427, DSF0000798424, DSF0000779662, DSF0000798189, DSF0000870064, DSF0001034341
20 | K127 | P.S. 127 - BROOKLYN | SCA IEH | PO18-REMOVE DOORS AND FRAMES UNDER ABATEMENT ABATEMENT IS AT ROOMS 110, 110, 200 SEE CUSTODIAN FOR L | Construction | Complete | 6/30/2022 | IEH | 9/24/2024 | IEH | 0 | 0 | SCA0000071262
20 | K127 | P.S. 127 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001035431
20 | K127 | P.S. 127 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 285681 | 0 | DSF0001085984
20 | K127 | P.S. 127 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/6/2022 | DOES |  | DOES | 213538 | 0 | DSF0001034219
20 | K127 | P.S. 127 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/23/2024 | DOES | 9/6/2024 | DOES | 65832 |  | DSF0001084049
20 | K160 | P.S. 160 - BROOKLYN | SCA IEH | PO18-TEST AND ABATE WALL, CEILLING AND BRICK MORTAR FOR ACM SPACE ID 1004 SCHOOL KITCHEN AND 1004B S | Construction | Complete | 6/4/2024 | IEH | 10/19/2024 | IEH | 0 | 0 | SCA0000073052
20 | K160 | P.S. 160 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 55000 | 0 | DSF0000913768
20 | K160 | P.S. 160 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008521
20 | K160 | P.S. 160 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112589
20 | K160 | P.S. 160 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/29/2022 | DOES |  | DOES | 77473 | 0 | DSF0001009167
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/5/2023 | 10/20/2023 | 10/17/2023 | 48516 | 64618 | 64376 | DSF0001062546, DSF0001087262
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | Complete | 10/24/2023 | 3/28/2024 | 8/13/2024 | 222536 | 127463 | 121096 | DSF0001062546, DSF0001087262
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS | Construction | PNS | PNS | PNS | PNS | 3494381 | 3494381 | 47416 | DSF0001062546, DSF0001087262
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 398826 | 398826 | 40165 | DSF0001062546, DSF0001087262
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/28/2018 | 11/26/2019 | 11/13/2019 | 29171 | 115406 | 115406 | DSF0000889050, DSF0000912745
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | Design | Complete | 12/4/2019 | 5/21/2020 | 5/20/2020 | 118252 | 403105 | 402855 | DSF0000889050, DSF0000912745
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | Construction | Complete | 8/16/2021 | 8/15/2022 | 8/15/2022 | 2134466 | 1924381 | 1899846 | DSF0000889050, DSF0000912745
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | CM,F&E | Complete | 8/16/2021 | 8/15/2022 | 8/15/2022 | 155221 | 320633 | 317928 | DSF0000889050, DSF0000912745
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL GYMANSIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033609
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL GYMANSIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033609
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL GYMANSIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033609
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL GYMANSIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033609
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/10/2019 | 3/6/2020 | 5/3/2021 | 0 | 6638 | 6638 | DSF0000960542
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 5/3/2021 | 7/2/2021 | 5/12/2021 | 4680 | 154 | 154 | DSF0000960542
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 68640 | 68640 | 2716 | DSF0000960542
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 4680 | 4680 | 1603 | DSF0000960542
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Scope | Complete | 7/14/2023 | 11/15/2023 | 10/13/2023 | 0 | 1369 | 1369 | DSF0001035451
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Design | Complete | 10/16/2023 | 3/20/2024 | 2/28/2024 | 30000 | 5476 | 5476 | DSF0001035451
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 10/10/2024 | 8/5/2025 |  | 440000 | 381255 | 6605 | DSF0001035451
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | CM,F&E | In-Progress | 10/10/2024 | 8/5/2025 |  | 30000 | 35095 | 7556 | DSF0001035451
20 | K163 | P.S. 748 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/5/2019 | EMER |  | EMER | 50890 | 50890 | SCA0000062808
20 | K163 | P.S. 748 - BROOKLYN | SCA IEH | PO18-ABATE 12X12 BROWN LIGHT VFT SET IN MASTIC OVER GREY VFT'S IN ROOM 209A ABATE GREY VFT SET IN MA | Construction | Complete | 9/25/2024 | IEH | 10/3/2024 | IEH | 0 | 0 | SCA0000073425
20 | K163 | P.S. 748 - BROOKLYN | SCA IEH | PO18-ABATE WHOLE FLOOR IN ROOM 209A INCLUDING 12X12 FLOOR TILE SOFT CONCRETE FILLER FELT PAPER AND 9 | Construction | In-Progress | 10/30/2024 | IEH |  | IEH | 0 | 0 | SCA0000073555
20 | K163 | P.S. 748 - BROOKLYN | Fast Track Projects | LSP GYM FLOOR REPLACEMENT | Construction | In-Progress | 9/11/2023 | FTK |  | FTK | 178945 | 167384 | DSF0001085146
20 | K163 | P.S. 748 - BROOKLYN | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 9/8/2020 | DOES | 9/15/2020 | DOES | 1243 | 12273 | DSF0000960904
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Scope | Complete | 1/27/2021 | 5/27/2021 | 12/1/2021 | 67750 | 96443 | 96393 | DSF0000987100, DSF0001011868
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Design | Complete | 12/2/2021 | 5/2/2022 | 8/31/2022 | 338750 | 356078 | 340670 | DSF0000987100, DSF0001011868
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Construction | In-Progress | 3/6/2023 | 6/2/2024 |  | 7621875 | 8594825 | 6328075 | DSF0000987100, DSF0001011868
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 3/6/2023 | 6/2/2024 |  | 481273 | 465872 | 442839 | DSF0000987100, DSF0001011868
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 6/10/2024 | 10/25/2024 | 10/4/2024 | 139282 | 89252 | 67706 | DSF0001090294, DSF0001117908, DSF0001117909, DSF0001117905
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Design | In-Progress | 11/22/2024 | 4/28/2025 |  | 639901 | 639901 | 187605 | DSF0001090294, DSF0001117908, DSF0001117909, DSF0001117905
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 10057314 | 10057314 | 0 | DSF0001090294, DSF0001117908, DSF0001117909, DSF0001117905
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 1133597 | 1133597 | 14802 | DSF0001090294, DSF0001117908, DSF0001117909, DSF0001117905
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/14/2022 | 2/16/2023 | 12/21/2022 | 3769 | 6491 | 6491 | DSF0001034583
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/21/2022 | 6/20/2023 | 4/4/2023 | 16961 | 25965 | 25965 | DSF0001034583
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 218602 | 201092 | 158276 | DSF0001034583
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 93447 | 90374 | 85338 | DSF0001034583
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE PLASTER ON WALL AND CEILING AT LISTED LOCATIONS: 101,106,108,110,111,205,309,405A,407,409 | Construction | Complete | 7/10/2024 | IEH | 8/6/2024 | IEH | 0 | 0 | SCA0000073125
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE WALL PLASTER AND CEILING PLASTER AT LOCATIONS : 407A, 410 AND 301 | Construction | In-Progress | 7/18/2024 | IEH |  | IEH | 0 | 0 | SCA0000073151
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE DAMAGED CEILING PLASTER IN AUDITORIUM LOBBY BASEMENT PHOTOS AND LAS ATTACHED. 55X12FT / 6 | Construction | Complete | 8/7/2024 | IEH | 8/10/2024 | IEH | 0 | 0 | SCA0000073258
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE AND TAKE WALLS DOWN TO THE BRICK IN THE FOLLOWING LOCATIONS: 212, 310 | Construction | Complete | 8/13/2024 | IEH | 8/22/2024 | IEH | 0 | 0 | SCA0000073279
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOORS TILES IN ROOMS 205, 208, 210, 210A, 307 AND 311 | Construction | Complete | 8/15/2024 | IEH | 9/25/2024 | IEH | 0 | 0 | SCA0000073289
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-TAKE WALLS DOWN TO THE BRICK IN THE FOLLOWING LOCATIONS: 302, 312, 406A, 406B, 410A, STAIRCASE | Construction | Complete | 8/16/2024 | IEH | 9/23/2024 | IEH | 0 | 0 | SCA0000073295
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE WALLS DOWN TO THE BRICK IN ROOMS:410,402,406A,406B | Construction | Complete | 10/25/2024 | IEH | 11/4/2024 | IEH | 0 | 0 | SCA0000073544
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE ACM PLASTER WALLS AT LISTED AREAS DOWN TO BRICK ROOM 301 SPACE ID#5301 ROOM 30 | Construction | In-Progress | 10/31/2024 | IEH |  | IEH | 0 | 0 | SCA0000073558
20 | K164 | K077 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0 | DSF0001033460
20 | K164 | P.S. 164 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112590
20 | K164 | P.S. 164 - BROOKLYN | DOE - RESOA | FY10 RESO A- AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 35000 | 0 | DSF0000688243
20 | K164 | P.S. 164 - BROOKLYN | DOE - RESOA | FY11 RESO A FLOORS | Construction | PNS | PNS | PNS | PNS | DOER | 96830 | 0 | DSF0000710770
20 | K164 | P.S. 164 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/26/2022 | DOES |  | DOES | 59823 | 0 | DSF0001009166
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112593
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001112593
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001112593
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001112593
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113572
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113572
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113572
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113572
20 | K170 | P.S. 170 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION ON LEAKING WATER MAIN LOCATED IN BOILER | Construction | Complete | 2/2/2024 | IEH | 11/6/2024 | IEH | 0 | 0 | SCA0000072710
20 | K170 | P.S. 170 - BROOKLYN | DIIT - RESOA | FY21 RESO A (MA) TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001008615
20 | K176 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/15/2021 | 12/14/2021 | 10/4/2021 | 204217 | 262085 | 237067 | DSF0000987278, DSF0000987280, DSF0000987281, DSF0000987282, DSF0001034199
20 | K176 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 10/12/2021 | 6/30/2022 | 4/6/2022 | 1017869 | 497027 | 497027 | DSF0000987278, DSF0000987280, DSF0000987281, DSF0000987282, DSF0001034199
20 | K176 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 8/15/2022 | 8/13/2024 |  | 22623879 | 21014976 | 14586513 | DSF0000987278, DSF0000987280, DSF0000987281, DSF0000987282, DSF0001034199
20 | K176 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 8/15/2022 | 8/13/2024 |  | 1454854 | 434550 | 433503 | DSF0000987278, DSF0000987280, DSF0000987281, DSF0000987282, DSF0001034199
20 | K176 | P.S. 176 - BROOKLYN | SCA IEH | PO18-ABATE THE FALLING CEILING PLASTER AROUND THE 4 INCH WASTE LINE IN 4TH FLOOR GIRLS BATHROOM ROOM | Construction | Complete | 7/1/2024 | IEH | 7/24/2024 | IEH | 0 | 0 | SCA0000073108
20 | K176 | P.S. 176 - BROOKLYN | SCA IEH | PO18-ABATE AND DRILL HALLWAY WALLS BEHIND BUBBLERS BY LISTED ROOMS : 5TH FL WALL BEHIND BUBBLER BY | Construction | Complete | 8/23/2024 | IEH | 9/29/2024 | IEH | 0 | 0 | SCA0000073317
20 | K176 | P.S. 176 - BROOKLYN | SCA IEH | PO18-77/20K176/ ABATE AND REPAIR ACM PLASTER APPROX: 400 SF PEELING / CHIPPING / PLASTER ON CEILING | Construction | Complete | 8/29/2024 | IEH | 8/31/2024 | IEH | 0 | 0 | SCA0000073336
20 | K176 | P.S. 176 - BROOKLYN | SCA IEH | PO18-REVIEW AND ABATE ACM CEILINGS @ LISTED AREAS: 2ND FLOOR GIRLS BATHROOM CEILING PLASTER ROOM 265 | Construction | Complete | 10/21/2024 | IEH | 10/27/2024 | IEH | 0 | 0 | SCA0000073525
20 | K176 | P.S. 176 - BROOKLYN | SCA IEH | PO18-IN ROOM 365 BATHROOM, THE CEILING PLASTER IS FALLING DOWN. THE AHERA BOOK SAYS THE PLASTER IS | Construction | In-Progress | 12/20/2024 | IEH |  | IEH | 0 | 0 | SCA0000073738
20 | K176 | P.S. 176 - BROOKLYN | DIIT - RESOA | RESO A (MA) TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001008616
20 | K176 | P.S. 176 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/12/2019 | DOER |  | DOER | 140583 | 0 | DSF0000890649
20 | K176 | P.S. 176 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112596
20 | K176 | P.S. 176 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/29/2024 | DOES | 8/5/2024 | DOES | 65832 |  | DSF0001084077
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2/6/2020 | 6/22/2020 | 11/3/2021 | 23126 | 64702 | 64702 | DSF0000938875
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Design | Complete | 11/5/2021 | 4/12/2022 | 5/13/2022 | 115630 | 147499 | 145470 | DSF0000938875
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Construction | Complete | 3/10/2023 | 6/1/2024 | 6/14/2024 | 2601675 | 2507461 | 2465749 | DSF0000938875
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | CM,F&E | Complete | 3/10/2023 | 6/1/2024 | 6/14/2024 | 161882 | 334633 | 328168 | DSF0000938875
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/15/2024 | 9/16/2024 | 5/21/2024 | 4137 | 2653 | 2653 | DSF0001087414
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/21/2024 | 11/18/2024 | 11/7/2024 | 18616 | 10611 | 10611 | DSF0001087414
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 239937 | 239937 | 3233 | DSF0001087414
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 44471 | 44471 | 2549 | DSF0001087414
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/28/2024 | 10/30/2024 | 10/9/2024 | 0 | 28276 | 16847 | DSF0001086011
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 10/9/2024 | 3/17/2025 |  | 59544 | 92122 | 29172 | DSF0001086011
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 873312 | 873312 | 0 | DSF0001086011
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 59544 | 59544 | 9348 | DSF0001086011
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 8/30/2024 | 12/3/2024 |  | 0 | 0 | 3074 | DSF0001087015
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 456 | 456 | 12298 | DSF0001087015
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 6688 | 6688 | 0 | DSF0001087015
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 456 | 456 | 459 | DSF0001087015
20 | K179 | P.S. 179 - BROOKLYN | SCA IEH | PO18-TEST WALL, COLUMN, SOFFIT, BEAM AND CEILING PLASTER FOR ABESTOS IN ROOM 104 | Construction | Complete | 2/2/2024 | IEH | 3/20/2024 | IEH | 0 | 0 | SCA0000072753
20 | K179 | P.S. 179 - BROOKLYN | SCA IEH | PO18-ABATE & REPAIR DAMAGED ACM PIPE INS IN CAFETERIA BY GIRLS BR (SPACE ID 2001) DAMAGED ACM PIPE I | Construction | Complete | 8/12/2024 | IEH | 8/17/2024 | IEH | 0 | 0 | SCA0000073273
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 7/1/2024 | 11/15/2024 | 11/14/2024 | 388436 | 110636 | 110636 | DSF0001090551, DSF0001090552, DSF0001113794, DSF0001113793
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | In-Progress | 11/26/2024 | 4/30/2025 |  | 1812702 | 1812702 | 206260 | DSF0001090551, DSF0001090552, DSF0001113794, DSF0001113793
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 28744267 | 28744267 | 13082 | DSF0001090551, DSF0001090552, DSF0001113794, DSF0001113793
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 2848531 | 2848531 | 18123 | DSF0001090551, DSF0001090552, DSF0001113794, DSF0001113793
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | Scope | Complete | 2/11/2020 | 9/13/2021 | 11/3/2021 | 233776 | 241114 | 232897 | DSF0000938900, DSF0001008818, DSF0001034307
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | Design | Complete | 11/8/2021 | 4/28/2022 | 9/30/2022 | 1164456 | 670037 | 598384 | DSF0000938900, DSF0001008818, DSF0001034307
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | Construction | In-Progress | 9/18/2023 | 12/5/2025 |  | 25817368 | 23373808 | 2442123 | DSF0000938900, DSF0001008818, DSF0001034307
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | CM,F&E | In-Progress | 9/18/2023 | 12/5/2025 |  | 1669634 | 274869 | 268294 | DSF0000938900, DSF0001008818, DSF0001034307
20 | K180 | K231 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 130000 | 0 | DSF0001033515
20 | K180 | K231 SPED - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035458
20 | K180 | P.S. 180 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/26/2024 | DIIR | 10/15/2024 | DIIR | 950000 | 950000 | DSF0001086012
20 | K180 | K231 SPED - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/26/2024 | DOER |  | DOER | 253550 | 0 | DSF0001033043
20 | K180 | P.S. 180 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 7/27/2023 | DOER |  | DOER | 175383 | 0 | DSF0001083869
20 | K180 | P.S. 180 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/23/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084598
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/15/2021 | 12/1/2021 | 2/3/2022 | 61398 | 123616 | 123616 | DSF0000987452, DSF0000987454, DSF0000987456
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 2/3/2022 | 7/6/2022 | 5/16/2022 | 297421 | 322751 | 322751 | DSF0000987452, DSF0000987454, DSF0000987456
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Construction | Complete | 11/14/2022 | 8/4/2024 | 9/12/2024 | 5864363 | 5427337 | 5137202 | DSF0000987452, DSF0000987454, DSF0000987456
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | CM,F&E | Complete | 11/14/2022 | 8/4/2024 | 9/12/2024 | 502749 | 357737 | 355734 | DSF0000987452, DSF0000987454, DSF0000987456
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | CLASSROOM FLOORING / PATH OF TRAVEL CLASSROOM FLOORING | Scope | Complete | 3/21/2023 | 2/27/2024 | 12/12/2023 | 23958 | 28241 | 28241 | DSF0001062936, DSF0001111803
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | CLASSROOM FLOORING / PATH OF TRAVEL CLASSROOM FLOORING | Design | Complete | 12/13/2023 | 4/12/2024 | 4/11/2024 | 117330 | 61063 | 32827 | DSF0001062936, DSF0001111803
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | CLASSROOM FLOORING / PATH OF TRAVEL CLASSROOM FLOORING | Construction | PNS | PNS | PNS | PNS | 2427351 | 2427351 | 171016 | DSF0001062936, DSF0001111803
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | CLASSROOM FLOORING / PATH OF TRAVEL CLASSROOM FLOORING | CM,F&E | PNS | PNS | PNS | PNS | 186133 | 186133 | 48916 | DSF0001062936, DSF0001111803
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND | Scope | Complete | 7/10/2024 | 10/8/2024 | 10/29/2024 | 0 | 7815 | 2050 | DSF0001112336
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND | Design | In-Progress | 11/7/2024 | 3/28/2025 |  | 54150 | 46335 | 8199 | DSF0001112336
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 794200 | 794200 | 0 | DSF0001112336
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 54150 | 54150 | 4833 | DSF0001112336
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Scope | In-Progress | 10/31/2024 | 2/5/2025 |  | 0 | 0 | 0 | DSF0001113760
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113760
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113760
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113760
20 | K185 | P.S. 185 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN TWO LOCATIONS IN ROOM 307 | Construction | Complete | 11/15/2024 | IEH | 11/16/2024 | IEH | 0 | 0 | SCA0000073614
20 | K185 | P.S. 185 - BROOKLYN | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/8/2020 | FTK |  | FTK | 3630040 | 3537775 | DSF0000961052
20 | K185 | P.S. 185 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/13/2024 | DIIR |  | DIIR | 500000 | 0 | DSF0001086014
20 | K186 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/2/2020 | 9/30/2020 | 7/10/2020 | 2597 | 7463 | 7463 | DSF0000960739
20 | K186 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/10/2020 | 1/6/2021 | 5/5/2021 | 11687 | 29953 | 29855 | DSF0000960739
20 | K186 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 4/28/2022 | 2/21/2023 | 2/1/2024 | 150626 | 149918 | 117140 | DSF0000960739
20 | K186 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 4/28/2022 | 2/21/2023 | 2/1/2024 | 179038 | 182774 | 90932 | DSF0000960739
20 | K186 | P.S. 186 - BROOKLYN | SCA IEH | PO18-TEST / ABATE FALLING PLASTER IN STAIRCASE 6&7 1ST FLOOR APPROX 2SQ FT | Construction | Complete | 12/26/2023 | IEH | 11/4/2024 | IEH | 0 | 0 | SCA0000072618
20 | K186 | P.S. 186 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE APPROX 4 SQ FT OF DAMAGED FLOOR TILE IN ROOM 303 DAMAGE WAS CAUSED BY A STEAM | Construction | Complete | 7/18/2024 | IEH | 8/6/2024 | IEH | 0 | 0 | SCA0000073150
20 | K186 | P.S. 186 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001112599
20 | K186 | P.S. 186 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 8/1/2023 | DOEL |  | DOEL | 57206 | 57206
20 | K186 | P.S. 186 - BROOKLYN | DOE - RESOA | FY21 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/8/2024 | DOER |  | DOER | 55621 | 0 | DSF0001008448
20 | K186 | P.S. 186 - BROOKLYN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/26/2023 | DOER |  | DOER | 426105 | 0 | DSF0001009282
20 | K186 | P.S. 186 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086015
20 | K186 | P.S. 186 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 225187 | 0 | DSF0001086016
20 | K192 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/2/2022 | 1/6/2023 | 10/4/2022 | 3371 | 10162 | 10162 | DSF0001034590
20 | K192 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/4/2022 | 4/4/2023 | 4/4/2023 | 15170 | 40647 | 40647 | DSF0001034590
20 | K192 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 195518 | 179644 | 136692 | DSF0001034590
20 | K192 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 81696 | 83241 | 78137 | DSF0001034590
20 | K192 | P.S. 192 - BROOKLYN | Fast Track Projects | LSP REPLACE LEAKING PVI DOMESTIC WATER HEATER | Construction | In-Progress | 9/23/2020 | FTK |  | FTK | 185119 | 163976 | DSF0000912946
20 | K192 | P.S. 192 - BROOKLYN | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 9/29/2020 | FTK |  | FTK | 1134941 | 1101047 | DSF0000961056
20 | K192 | P.S. 192 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112600
20 | K192 | P.S. 192 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/28/2021 | DOES |  | DOES | 67952 | 0 | DSF0001009165
20 | K192 | P.S. 192 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 4/20/2023 | DOES |  | DOES | 610711 | 0 | DSF0001063056
20 | K192 | P.S. 192 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/3/2024 | DOES | 9/10/2024 | DOES | 65832 |  | DSF0001084602
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2/1/2017 | 6/16/2017 | 9/8/2017 | 119212 | 115321 | 115321 | DSF0000848464, DSF0000848463, DSF0000868163
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 10/11/2017 | 3/16/2018 | 1/31/2018 | 476847 | 520415 | 481607 | DSF0000848464, DSF0000848463, DSF0000868163
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 6/1/2018 | 2/20/2020 |  | 8940881 | 8968584 | 7112613 | DSF0000848464, DSF0000848463, DSF0000868163
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 6/1/2018 | 2/20/2020 |  | 556322 | 1849103 | 1810295 | DSF0000848464, DSF0000848463, DSF0000868163
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/23/2024 | 9/24/2024 | 5/29/2024 | 6615 | 2509 | 2509 | DSF0001087422
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/29/2024 | 11/25/2024 | 11/7/2024 | 29769 | 10036 | 10036 | DSF0001087422
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 383689 | 383689 | 4599 | DSF0001087422
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 71115 | 71115 | 3262 | DSF0001087422
20 | K200 | P.S. 200 - BROOKLYN | SCA IEH | PO18-ABATE & REPLACE - 1002 STAIRWELL. 9X9 FLOOR TILES ARE BROKEN 132 SQF -CLASS ROOM 2105. 9X | Construction | Complete | 7/30/2024 | IEH | 8/7/2024 | IEH | 0 | 0 | SCA0000073199
20 | K200 | P.S. 200 - BROOKLYN | SCA IEH | PO18-PLEASE TEST / ABATE APPROX. 3500 SQ. FT. OF VINYL FLOOR TILES ON THE 4TH FLOOR CORRIDOR.FROM S | Construction | In-Progress | 10/15/2024 | IEH |  | IEH | 0 | 0 | SCA0000073501
20 | K200 | P.S. 200 - BROOKLYN | DIIT - RESOA | RESO A (MA) TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001008617
20 | K200 | P.S. 200 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 3/27/2023 | DOER | 8/21/2023 | DOER | 128937 | 45195 | DSF0000913239
20 | K200 | P.S. 200 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/11/2024 | DOER |  | DOER | 296545 | 0 | DSF0001035469
20 | K200 | P.S. 200 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112610
20 | K200 | P.S. 200 - BROOKLYN | DOE - RESOA | FY25 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112611
20 | K200 | P.S. 200 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/30/2024 | DOES | 65832 | 189 | DSF0001084090
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | GYM FLOOR REPLACEMENT | Scope | Complete | 6/29/2023 | 10/31/2023 | 11/15/2023 | 18216 | 17651 | 2392 | DSF0001085174
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | GYM FLOOR REPLACEMENT | Design | Complete | 12/7/2023 | 4/24/2024 | 5/31/2024 | 85010 | 57411 | 9819 | DSF0001085174
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | GYM FLOOR REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 1348011 | 1348011 | 16748 | DSF0001085174
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | GYM FLOOR REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 133587 | 133587 | 20930 | DSF0001085174
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM FLOOR REPLACEMENT | Scope | Complete | 10/27/2023 | 2/1/2024 | 1/11/2024 | 1588 | 1588 | 15 | DSF0001087170
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM FLOOR REPLACEMENT | Design | Complete | 1/12/2024 | 5/15/2024 | 5/31/2024 | 6354 | 6354 | 59 | DSF0001087170
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM FLOOR REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 91334 | 91334 | 0 | DSF0001087170
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM FLOOR REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 23429 | 23429 | 3345 | DSF0001087170
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP RESOA | FY18 RESO A ROOM CONVERSION | Scope | Complete | 1/16/2018 | 4/16/2018 | 3/1/2018 | 0 | 21863 | 21863 | DSF0000867186
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP RESOA | FY18 RESO A ROOM CONVERSION | Design | Complete | 11/28/2018 | 4/29/2019 | 8/22/2019 | 114379 | 208297 | 192862 | DSF0000867186
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP RESOA | FY18 RESO A ROOM CONVERSION | Construction | Complete | 9/20/2021 | 9/19/2022 | 1/3/2024 | 1677559 | 1788533 | 1589941 | DSF0000867186
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP RESOA | FY18 RESO A ROOM CONVERSION | CM,F&E | Complete | 9/20/2021 | 9/19/2022 | 1/3/2024 | 145424 | 278050 | 271614 | DSF0000867186
20 | K201 | I.S. 201 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE 9 X 9 FLOOR TILES IN KITCHEN STORAGE ROOM 107 136 SQ FT FLOOR IS DETERIORATED | Construction | Complete | 8/1/2024 | IEH | 8/13/2024 | IEH | 0 | 0 | SCA0000073225
20 | K201 | I.S. 201 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 200000 | 0 | DSF0000961224
20 | K201 | I.S. 201 - BROOKLYN | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 6/2/2021 | DOES |  | DOES | 115955 | 0 | DSF0001008938
20 | K201 | I.S. 201 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/9/2024 | DOES | 10/7/2024 | DOES | 65832 | 6579 | DSF0001084744
20 | K204 | P.S. 204 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE 9X9 ASBESTOS TILES IN ROOM 101 THE FLOOR IS CRACKING IN SOME SPOTS CAUSING A TRIP | Construction | Complete | 7/31/2024 | IEH | 8/31/2024 | IEH | 0 | 0 | SCA0000073216
20 | K204 | P.S. 204 - BROOKLYN | DOE - RESOA | FY25 RESO A PHONE UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112614
20 | K204 | P.S. 204 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112615
20 | K204 | P.S. 204 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112616
20 | K204 | P.S. 204 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/13/2022 | DOES |  | DOES | 73215 | 0 | DSF0001009019
20 | K204 | P.S. 204 - BROOKLYN | Trust For Public Land | TPL- EXTREME WEATHER PLAYGROUND UPGRADE | Construction | Complete | 6/28/2023 | TPL | 5/30/2024 | TPL | 2971613 | 2971613 | DSF0001034696
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 1/19/2024 | 4/18/2024 | 3/25/2024 | 22834 | 30233 | 30233 | DSF0001091043
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 4/3/2024 | 10/4/2024 | 12/12/2024 | 106558 | 85912 | 50009 | DSF0001091043
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 1689699 | 1689699 | 5196 | DSF0001091043
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 167448 | 167448 | 24901 | DSF0001091043
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/24/2023 | 9/25/2023 | 6/16/2023 | 4223 | 630 | 630 | DSF0001035010
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/16/2023 | 12/14/2023 | 8/30/2023 | 19003 | 2519 | 2519 | DSF0001035010
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/23/2024 | 1/17/2025 |  | 244922 | 234744 | 119783 | DSF0001035010
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/23/2024 | 1/17/2025 |  | 132653 | 115788 | 102414 | DSF0001035010
20 | K205 | P.S. 205 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000913788
20 | K205 | P.S. 205 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033501
20 | K205 | P.S. 205 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 55000 | 0 | DSF0001035471
20 | K205 | P.S. 205 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/20/2023 | DOER |  | DOER | 4207 | 0 | DSF0001008437
20 | K205 | P.S. 205 - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112617
20 | K220 | I.S. 220 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 8/16/2023 | DOES | 10/27/2023 | DOES | 342811 |  | DSF0001035165
20 | K220 | I.S. 220 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/3/2024 | DOES | 10/10/2024 | DOES | 65832 |  | DSF0001084747
20 | K223 | I.S. 223 - BROOKLYN | SCA CIP | DAMAGED STEEL BEAM AT THE MAIN ENTRANCE #1 | Scope | Complete | 5/28/2015 | 9/25/2015 | 10/15/2015 | 8724 | 13848 | 13848 | DSF0000821911
20 | K223 | I.S. 223 - BROOKLYN | SCA CIP | DAMAGED STEEL BEAM AT THE MAIN ENTRANCE #1 | Design | Complete | 2/17/2016 | 5/31/2016 | 10/17/2016 | 31989 | 97833 | 97314 | DSF0000821911
20 | K223 | I.S. 223 - BROOKLYN | SCA CIP | DAMAGED STEEL BEAM AT THE MAIN ENTRANCE #1 | Construction | PNS | PNS | PNS | PNS | 338796 | 338796 | 36998 | DSF0000821911
20 | K223 | I.S. 223 - BROOKLYN | SCA CIP | DAMAGED STEEL BEAM AT THE MAIN ENTRANCE #1 | CM,F&E | PNS | PNS | PNS | PNS | 78519 | 78519 | 36897 | DSF0000821911
20 | K223 | I.S. 223 - BROOKLYN | SCA IEH | PO18-ABATE DETERIORATED PIPE COVERING WATER LINE PIPE COVERING LISTED POSSITIVE IN AHERA BOOK LOCATE | Construction | Complete | 11/7/2024 | IEH | 11/22/2024 | IEH | 0 | 0 | SCA0000073587
20 | K223 | I.S. 223 - BROOKLYN | Fast Track Projects | FY19 RESO A TREE GUARDS | Construction | PNS | FTK | FTK | FTK | FTK | 28000 | 0 | DSF0000890767
20 | K223 | URBAN ASSEMBLY SCHOOL FOR LEADERSHIP AND EMPOWERMENT | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 65000 | 0 | DSF0001033596
20 | K223 | I.S. 223 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001086030
20 | K223 | I.S. 223 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/2/2020 | DOES |  | DOES | 593370 | 0 | DSF0000865889
20 | K223 | I.S. 223 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 8/17/2022 | DOES | 9/27/2022 | DOES | 61693 | 30431 | DSF0000866112
20 | K223 | I.S. 223 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 619382 | 0 | DSF0001063717
20 | K223 | I.S. 223 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/9/2024 | DOES | 8/26/2024 | DOES | 65832 |  | DSF0001084748
20 | K223 | I.S. 223 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/9/2024 | DOES |  | DOES | 526472 | 0 | DSF0001085721
20 | K227 | I.S. 227 - BROOKLYN | DOE - RESOA | FY17 RESO A ELECTRICAL UPGRADES | Construction | In-Progress | 10/1/2018 | DOER |  | DOER | 171911 | 0 | DSF0000844873
20 | K227 | I.S. 227 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 5/7/2021 | DOES |  | DOES | 525582 | 0 | DSF0000911927
20 | K227 | I.S. 227 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/12/2024 | DOES | 9/20/2024 | DOES | 65832 |  | DSF0001084749
20 | K227 | I.S. 227 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/19/2023 | DOES |  | DOES | 582257 | 0 | DSF0001085722
20 | K229 | P.S. 229 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/1/2023 | 6/2/2023 | 5/15/2023 | 0 | 16363 | 16363 | DSF0001035482
20 | K229 | P.S. 229 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 5/15/2023 | 9/29/2023 | 9/27/2023 | 60000 | 61984 | 42260 | DSF0001035482
20 | K229 | P.S. 229 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | Complete | 5/1/2024 | 3/26/2025 | 9/25/2024 | 880000 | 504668 | 411467 | DSF0001035482
20 | K229 | P.S. 229 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | CM,F&E | Complete | 5/1/2024 | 3/26/2025 | 9/25/2024 | 228859 | 221371 | 113721 | DSF0001035482
20 | K229 | P.S. 229 - BROOKLYN | SCA IEH | PO18-ABATE APPROX. 6 FEET OF ACM PIPE COVER FROM A 6' STEM PIPE LOCATED IN BOILER ROOM ON 14 ACE SID | Construction | In-Progress | 11/26/2024 | IEH |  | IEH | 0 | 0 | SCA0000073645
20 | K229 | P.S. 229 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 7/11/2024 | DIIR | 82000 | 82000 | DSF0001086033
20 | K229 | P.S. 229 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001112629
20 | K229 | P.S. 229 - BROOKLYN | DOE - RESOA | FY20 RESO A MULTIPURPOSE ROOM UPGRADE | Construction | In-Progress | 3/23/2024 | DOER |  | DOER | 138695 | 0 | DSF0000913248
20 | K247 | P.S. 247 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113581
20 | K247 | P.S. 247 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113581
20 | K247 | P.S. 247 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113581
20 | K247 | P.S. 247 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113581
20 | K247 | P.S. 247 - BROOKLYN | DOE - RESOA | FY09 RESO A ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | DOER | 120000 | 0 | DSF0000623073
20 | K247 | P.S. 247 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0001086045
20 | K247 | P.S. 247 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 800000 | 0 | DSF0001112648
20 | K247 | P.S. 247 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/31/2023 | DOES |  | DOES | 65832 | 0 | DSF0001084112
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112653
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112653
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001112653
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112653
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113582
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113582
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113582
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113582
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 1/19/2023 | 5/4/2023 | 4/20/2023 | 0 | 20535 | 16156 | DSF0001035504, DSF0001035505
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 4/27/2023 | 9/27/2023 | 8/25/2023 | 66000 | 91198 | 79130 | DSF0001035504, DSF0001035505
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 5/3/2024 | 3/28/2025 |  | 968000 | 829700 | 582284 | DSF0001035504, DSF0001035505
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 5/3/2024 | 3/28/2025 |  | 66000 | 83383 | 44770 | DSF0001035504, DSF0001035505
20 | K259 | I.S. 259 - BROOKLYN | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/9/2021 | DOER |  | DOER | 1338397 | 0 | DSF0000890771
20 | K259 | I.S. 259 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 12/15/2021 | DOER | 4/24/2024 | DOER | 264124 | 69437 | DSF0000913253
20 | K259 | I.S. 259 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/7/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084756
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913254
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913254
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913254
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913254
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/13/2023 | 6/14/2023 | 7/6/2023 | 0 | 8552 | 8552 | DSF0001035509
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 7/17/2023 | 12/18/2023 | 2/16/2024 | 30000 | 35395 | 8468 | DSF0001035509
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/26/2024 | 5/21/2025 |  | 440000 | 301000 | 0 | DSF0001035509
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 7/26/2024 | 5/21/2025 |  | 30000 | 32649 | 9593 | DSF0001035509
20 | K264 | P.S. 264 - BROOKLYN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/29/2022 | DOER |  | DOER | 195341 | 0 | DSF0001033527
20 | K310 | P.S. 310 - BROOKLYN | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 400000 | 400000 | 0 | DSF0001112678
20 | K310 | P.S. 310 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035530
20 | K314 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | Scope | Complete | 1/10/2023 | 6/9/2023 | 4/25/2023 | 102004 | 94780 | 94780 | DSF0001065264, DSF0001065265, DSF0001085160
20 | K314 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | Design | Complete | 5/15/2023 | 10/17/2023 | 11/7/2023 | 501798 | 650002 | 386780 | DSF0001065264, DSF0001065265, DSF0001085160
20 | K314 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | Construction | In-Progress | 4/3/2024 | 4/2/2026 |  | 10579036 | 9477291 | 760438 | DSF0001065264, DSF0001065265, DSF0001085160
20 | K314 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | CM,F&E | In-Progress | 4/3/2024 | 4/2/2026 |  | 775715 | 169030 | 166320 | DSF0001065264, DSF0001065265, DSF0001085160
20 | K314 | P.S. 503 - BROOKLYN | SCA IEH | PO18-ABATE AND PENETRATE (2) TWO HOLES 1/4' INCHES DIAMETER / 2' INCHES DEPTH. FLOOR MARKED WITH WHI | Construction | In-Progress | 12/11/2024 | IEH |  | IEH | 0 | 0 | SCA0000073701
20 | K314 | P.S. 503 - BROOKLYN | Fast Track Projects | LSP FY16 RESO A EXTERIOR PLAYGROUND LIGHTING | Construction | In-Progress | 8/5/2021 | FTK |  | FTK | 258948 | 237751 | DSF0000912454
20 | K314 | P.S. 506 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 340000 | 0 | DSF0001033099
20 | K314 | P.S. 503 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 237142 | 0 | DSF0001086079
20 | K314 | P.S. 503 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 4/14/2023 | DOES |  | DOES | 2594445 | 0 | DSF0001065262
20 | K314 | P.S. 503 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/26/2024 | DOES | 9/5/2024 | DOES | 50832 | 8061 | DSF0001084148
20 | K322 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 1/6/2020 | 6/3/2020 | 6/3/2020 | 1215600 | 1313113 | 1287128 | DSF0000798188
20 | K322 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 6/4/2020 | 1/7/2021 | 1/7/2021 | 5470200 | 4922642 | 4454515 | DSF0000798188
20 | K322 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 11/22/2021 | 9/3/2024 |  | 68985300 | 71082249 | 60721976 | DSF0000798188
20 | K322 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 11/22/2021 | 9/3/2024 |  | 9724800 | 8583950 | 6785986 | DSF0000798188
20 | K331 | I.S. 30 - BROOKLYN | SCA CIP RESOA | RESO A LIBRARY UPGRADE | Scope | Complete | 1/31/2023 | 6/1/2023 | 11/15/2023 | 0 | 12426 | 12426 | DSF0001035542
20 | K331 | I.S. 30 - BROOKLYN | SCA CIP RESOA | RESO A LIBRARY UPGRADE | Design | Complete | 11/21/2023 | 4/9/2024 | 4/5/2024 | 30000 | 34519 | 32626 | DSF0001035542
20 | K331 | I.S. 30 - BROOKLYN | SCA CIP RESOA | RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001035542
20 | K331 | I.S. 30 - BROOKLYN | SCA CIP RESOA | RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 9443 | DSF0001035542
20 | K331 | I.S. 30 - BROOKLYN | DIIT - RESOA | RESO A (MA) TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001008614
20 | K331 | I.S. 30 - BROOKLYN | DOE - RESOA | RESO A FENCING | Construction | In-Progress | 10/19/2023 | DOER |  | DOER | 232966 | 0 | DSF0001086878
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | In-Progress | 11/7/2024 | 5/2/2025 |  | 457609 | 457609 | 4363 | DSF0000911837
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | PNS | PNS | PNS | PNS | 1830437 | 1830437 | 17453 | DSF0000911837
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 25282911 | 25282911 | 781546 | DSF0000911837
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 3317667 | 3317667 | 210392 | DSF0000911837
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 6/6/2023 | 6/6/2023 | 6/6/2023 | 40607 | 122390 | 116265 | DSF0000911837
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 6/13/2023 | 9/29/2023 | 11/8/2023 | 203037 | 96587 | 87898 | DSF0000911837
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 4568326 | 4568326 | 980280 | DSF0000911837
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 284251 | 284251 | 129204 | DSF0000911837
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/16/2024 | 9/10/2024 | 9/10/2024 | 2145618 | 801719 | 770101 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | In-Progress | 9/11/2024 | 4/14/2025 |  | 8582471 | 8582471 | 2488095 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 118545379 | 118545379 | 470787 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 15555728 | 15555728 | 327338 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | EARLY DEMO WORK-TANK REMOVAL | Scope | Complete | 4/15/2024 | 4/15/2024 | 4/15/2024 | 7427 | 308 | 308 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | EARLY DEMO WORK-TANK REMOVAL | Design | Complete | 4/16/2024 | 5/20/2024 | 5/20/2024 | 29708 | 1233 | 1233 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | EARLY DEMO WORK-TANK REMOVAL | Construction | PNS | PNS | PNS | PNS | 410346 | 410346 | 4748 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | EARLY DEMO WORK-TANK REMOVAL | CM,Art,F&E | PNS | PNS | PNS | PNS | 53846 | 53846 | 23389 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 4/15/2024 | 4/15/2024 | 4/15/2024 | 124450 | 59176 | 59176 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 4/16/2024 | 8/30/2024 | 12/20/2024 | 580767 | 311693 | 291783 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 9209311 | 9209311 | 88156 | DSF0001008552
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 912634 | 912634 | 104638 | DSF0001008552
20 | K404 | K000 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 9/13/2024 | IEH | 9/25/2024 | IEH | 0 | 0 | SCA0000073371
20 | K404 | K000 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/7/2024 | DOES | 10/14/2024 | DOES | 50832 |  | DSF0001085446
20 | K445 | NEW UTRECHT HS - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 9/14/2022 | DOES |  | DOES | 66214 | 0 | DSF0000866115
20 | K445 | NEW UTRECHT HS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/10/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084905
20 | K462 | K000 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 12/9/2024 | IEH | 12/16/2024 | IEH | 0 | 0 | SCA0000073685
20 | K464 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | Scope | Complete | 9/21/2021 | 4/4/2022 | 4/4/2022 | 235540 | 284502 | 284502 | DSF0001034200, DSF0001034200
20 | K464 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | Design | Complete | 4/4/2022 | 5/31/2022 | 8/16/2022 | 1059930 | 702114 | 679528 | DSF0001034200, DSF0001034200
20 | K464 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | Construction | In-Progress | 4/12/2023 | 9/3/2024 |  | 13366895 | 12618367 | 11319412 | DSF0001034200, DSF0001034200
20 | K464 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | CM,F&E | In-Progress | 4/12/2023 | 9/3/2024 |  | 1884320 | 1888167 | 1734151 | DSF0001034200, DSF0001034200
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 5/31/2019 | 10/15/2019 | 12/13/2019 | 54000 | 46070 | 46070 | DSF0000896588, DSF0000960684
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | Complete | 1/14/2020 | 6/15/2020 | 5/11/2021 | 270000 | 247422 | 247422 | DSF0000896588, DSF0000960684
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS | Construction | PNS | PNS | PNS | PNS | 6075000 | 6075000 | 9499 | DSF0000896588, DSF0000960684
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 378000 | 378000 | 27167 | DSF0000896588, DSF0000960684
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007769
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007769
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007769
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007769
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001008245
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 37500 | 37500 | 0 | DSF0001008245
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 550000 | 550000 | 0 | DSF0001008245
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 37500 | 37500 | 0 | DSF0001008245
20 | K485 | TELECOM. ARTS & TECH. HS - K | Fast Track Projects | LSP REPLACE BURNER CONTROLS | Construction | In-Progress | 8/15/2019 | FTK |  | FTK | 123052 | 93129 | DSF0000896594
20 | K485 | TELECOM. ARTS & TECH. HS - K | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1140782 | 0 | DSF0001008297
20 | K485 | TELECOM. ARTS & TECH. HS - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 12/23/2022 | DOES | 10/18/2023 | DOES | 460774 | 456642 | DSF0000960845
20 | K485 | TELECOM. ARTS & TECH. HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/12/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084912
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112724
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112724
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001112724
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112724
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113593
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113593
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113593
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113593
20 | K486 | I.S. 187 - BROOKLYN | DOE - RESOA | FY14 RESO A MULTIMEDIA ART STUDIO | Construction | PNS | PNS | PNS | PNS | DOER | 46747 | 0 | DSF0000798983
20 | K486 | I.S. 187 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | Complete | 10/11/2019 | DOER | 12/19/2022 | DOER | 182222 | 218224 | DSF0000890650
20 | K486 | I.S. 187 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/13/2022 | DOES |  | DOES | 282097 | 0 | DSF0001034414
20 | K486 | I.S. 187 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 12/5/2023 | DOES |  | DOES | 681745 | 0 | DSF0001083750
20 | K486 | I.S. 187 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/20/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084772
20 | K486 | I.S. 187 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/30/2024 | DOES |  | DOES | 586127 | 0 | DSF0001085729
20 | K490 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 7/9/2019 | 10/7/2019 | 2/12/2020 | 30510 | 61639 | 61639 | DSF0000896622
20 | K490 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2/12/2020 | 8/13/2020 | 6/3/2021 | 152550 | 283066 | 280579 | DSF0000896622
20 | K490 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 4/10/2023 | 4/8/2024 |  | 3432375 | 3098181 | 2306549 | DSF0000896622
20 | K490 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 4/10/2023 | 4/8/2024 |  | 213570 | 220900 | 219302 | DSF0000896622
20 | K490 | FORT HAMILTON HS - K | SCA CIP | REPLACE 6' FIRE DOMESTIC WATER MAIN VALVES | Scope | Complete | 6/4/2019 | 8/5/2019 | 7/12/2019 | 11889 | 2293 | 2293 | DSF0000912504
20 | K490 | FORT HAMILTON HS - K | SCA CIP | REPLACE 6' FIRE DOMESTIC WATER MAIN VALVES | Design | Complete | 7/12/2019 | 11/12/2019 | 8/27/2021 | 53501 | 68642 | 68642 | DSF0000912504
20 | K490 | FORT HAMILTON HS - K | SCA CIP | REPLACE 6' FIRE DOMESTIC WATER MAIN VALVES | Construction | In-Progress | 11/8/2024 | 10/3/2025 |  | 689562 | 1000319 | 59374 | DSF0000912504
20 | K490 | FORT HAMILTON HS - K | SCA CIP | REPLACE 6' FIRE DOMESTIC WATER MAIN VALVES | CM,F&E | In-Progress | 11/8/2024 | 10/3/2025 |  | 127807 | 119680 | 10787 | DSF0000912504
20 | K490 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | Scope | Complete | 6/15/2021 | 10/15/2021 | 10/27/2021 | 37080 | 142502 | 142502 | DSF0000990629
20 | K490 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | Design | Complete | 12/8/2021 | 5/2/2022 | 5/11/2022 | 185400 | 331652 | 328886 | DSF0000990629
20 | K490 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | Construction | In-Progress | 7/11/2022 | 10/3/2023 |  | 4171500 | 3841783 | 3442628 | DSF0000990629
20 | K490 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | CM,F&E | In-Progress | 7/11/2022 | 10/3/2023 |  | 259560 | 352419 | 351236 | DSF0000990629
20 | K490 | FORT HAMILTON HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / IDA CLIMATE CONTROL / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES / IDA POOL BOILER / IDA ELECTRICAL SYSTEMS | Scope | Complete | 1/31/2022 | 5/31/2022 | 6/13/2023 | 269669 | 303802 | 299101 | DSF0001112070, DSF0001035203, DSF0001035204, DSF0001035205, DSF0001085125, DSF0001085126, DSF0001066333
20 | K490 | FORT HAMILTON HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / IDA CLIMATE CONTROL / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES / IDA POOL BOILER / IDA ELECTRICAL SYSTEMS | Design | Complete | 6/14/2023 | 11/16/2023 | 4/9/2024 | 1339243 | 668272 | 630168 | DSF0001112070, DSF0001035203, DSF0001035204, DSF0001035205, DSF0001085125, DSF0001085126, DSF0001066333
20 | K490 | FORT HAMILTON HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / IDA CLIMATE CONTROL / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES / IDA POOL BOILER / IDA ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 29345098 | 29345098 | 97045 | DSF0001112070, DSF0001035203, DSF0001035204, DSF0001035205, DSF0001085125, DSF0001085126, DSF0001066333
20 | K490 | FORT HAMILTON HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / IDA CLIMATE CONTROL / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES / IDA POOL BOILER / IDA ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 1956008 | 1956008 | 56323 | DSF0001112070, DSF0001035203, DSF0001035204, DSF0001035205, DSF0001085125, DSF0001085126, DSF0001066333
20 | K490 | FORT HAMILTON HS - K | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Scope | Complete | 12/11/2023 | 3/13/2024 | 3/8/2024 | 11507 | 22751 | 22751 | DSF0001111805
20 | K490 | FORT HAMILTON HS - K | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Design | Complete | 3/12/2024 | 7/11/2024 | 12/3/2024 | 51780 | 39219 | 39219 | DSF0001111805
20 | K490 | FORT HAMILTON HS - K | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 667390 | 667390 | 4284 | DSF0001111805
20 | K490 | FORT HAMILTON HS - K | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 123697 | 123697 | 12136 | DSF0001111805
20 | K490 | FORT HAMILTON HS - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/12/2023 | DOES | 6/28/2023 | DOES | 801995 |  | DSF0001085312
20 | K491 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/8/2024 | DOES | 7/12/2024 | DOES | 50832 | 6349 | DSF0001085451
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/30/2022 | 11/16/2022 | 6/1/2023 | 296709 | 316715 | 312909 | DSF0001015643, DSF0001015644, DSF0001015645, DSF0001066412
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 6/12/2023 | 11/14/2023 | 12/12/2023 | 1477044 | 679169 | 651816 | DSF0001015643, DSF0001015644, DSF0001015645, DSF0001066412
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | PNS | PNS | PNS | PNS | 32671091 | 32671091 | 93409 | DSF0001015643, DSF0001015644, DSF0001015645, DSF0001066412
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 2125726 | 2125726 | 58774 | DSF0001015643, DSF0001015644, DSF0001015645, DSF0001066412
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | Scope | Complete | 1/12/2021 | 9/22/2022 | 8/25/2022 | 178605 | 241956 | 227982 | DSF0000990701, DSF0001034150, DSF0001015638, DSF0001015637, DSF0001035063
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | Design | Complete | 8/26/2022 | 12/28/2022 | 4/5/2023 | 892900 | 781148 | 582900 | DSF0000990701, DSF0001034150, DSF0001015638, DSF0001015637, DSF0001035063
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | Construction | In-Progress | 9/18/2023 | 3/5/2026 |  | 20079437 | 18770661 | 3200280 | DSF0000990701, DSF0001034150, DSF0001015638, DSF0001015637, DSF0001035063
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | CM,F&E | In-Progress | 9/18/2023 | 3/5/2026 |  | 1256508 | 328940 | 318617 | DSF0000990701, DSF0001034150, DSF0001015638, DSF0001015637, DSF0001035063
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DIIT - RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000890793
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0 | DSF0000912271
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/5/2023 | DOER |  | DOER | 228430 | 0 | DSF0001033576
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 12/16/2022 | DOES | 12/4/2023 | DOES | 748519 | 710157 | DSF0000960846
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DOE - Skilled Trades | BCC PLAN REVIEW FOR DSF WORK @ K505 | Construction | In-Progress | 3/4/2021 | DOES |  | DOES | 24042 | 0 | SCA0000064028
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/25/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084916
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DOE - Skilled Trades | CONDENSATE TANK REPLACEMENT | Construction | In-Progress | 8/21/2023 | DOES |  | DOES | 335456 | 0 | DSF0001066414
20 | K521 | P.S. 160 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112729
20 | K613 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/26/2024 | DOES | 7/3/2024 | DOES | 50832 |  | DSF0001084168
20 | K668 | PRE-K CENTER @ 412 63 STREET - BROOKLYN | PRE-K | LEASE | Scope | Complete | 11/10/2016 | 2/22/2017 | 2/22/2017 | 142794 | 68527 | 68527 | DSF0000866170
20 | K668 | PRE-K CENTER @ 412 63 STREET - BROOKLYN | PRE-K | LEASE | Design | Complete | 8/8/2017 | 11/22/2017 | 8/8/2024 | 642574 | 677653 | 651991 | DSF0000866170
20 | K668 | PRE-K CENTER @ 412 63 STREET - BROOKLYN | PRE-K | LEASE | Construction | PNS | PNS | PNS | PNS | 8103572 | 8103572 | 679726 | DSF0000866170
20 | K668 | PRE-K CENTER @ 412 63 STREET - BROOKLYN | PRE-K | LEASE | CM,F&E | PNS | PNS | PNS | PNS | 1142354 | 1142354 | 102725 | DSF0000866170
20 | K676 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/19/2020 | 8/11/2020 | 8/11/2020 | 1339880 | 1404304 | 1389358 | DSF0000845622
20 | K676 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 8/12/2020 | 3/19/2021 | 4/9/2021 | 6029460 | 5564601 | 5231770 | DSF0000845622
20 | K676 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | Complete | 9/13/2021 | 9/3/2024 | 9/3/2024 | 76038190 | 73172826 | 69362118 | DSF0000845622
20 | K676 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 9/13/2021 | 9/3/2024 | 9/3/2024 | 10719040 | 6659537 | 6099629 | DSF0000845622
20 | K678 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/21/2023 | DOES | 12/11/2024 | DOES | 65832 |  | DSF0001085457
20 | K695 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/13/2024 | DOES | 10/22/2024 | DOES | 65832 | 9140 | DSF0001085461
20 | K746 | SUNSET SCHOOL OF CULTURAL LEARNING - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112738
20 | K747 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/20/2024 | DOES | 9/24/2024 | DOES | 65832 | 5933 | DSF0001085463
20 | K780 | DISTRICT 20 PRE-K CENTER | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 7/3/2024 | DOEL |  | DOEL | 86450 | 0
20 | K780 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/3/2024 | DOES | 12/13/2024 | DOES | 65832 | 5729 | DSF0001085471
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2/5/2024 | 6/20/2024 | 7/22/2024 | 24271 | 33239 | 33239 | DSF0001067139, DSF0001094854
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 8/13/2024 | 1/16/2025 |  | 109148 | 109148 | 42578 | DSF0001067139, DSF0001094854
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 1694146 | 1694146 | 0 | DSF0001067139, DSF0001094854
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 223822 | 223822 | 14838 | DSF0001067139, DSF0001094854
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Scope | Complete | 5/5/2022 | 9/2/2022 | 8/30/2022 | 0 | 15618 | 15618 | DSF0001033610
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 9/6/2022 | 1/25/2023 | 2/1/2023 | 54623 | 59977 | 58416 | DSF0001033610
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | Complete | 6/28/2023 | 5/22/2024 | 5/22/2024 | 801143 | 559000 | 523076 | DSF0001033610
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | CM,F&E | Complete | 6/28/2023 | 5/22/2024 | 5/22/2024 | 83393 | 109848 | 101630 | DSF0001033610
20 | K807 | P.S. 163 - BROOKLYN | DIIT - RESOA | FY21 RESO A (MA) TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001008619
20 | K807 | P.S. 163 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/30/2022 | DOER |  | DOER | 603985 | 0 | DSF0001008305
20 | K807 | P.S. 163 - BROOKLYN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 3/20/2024 | DOER | 4/23/2024 | DOER | 232249 |  | DSF0001035590
20 | K971 | P.S. 971 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- FALLING MASONRY | Construction | In-Progress | 11/28/2022 | EMER |  | EMER | 373959 | 344950 | SCA0000071579
20 | K971 | P.S. 971 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 7/5/2024 | DIIR | 300000 | 295330 | DSF0001086162
20 | K971 | P.S. 971 - BROOKLYN | DOE - RESOA | FY23 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001035602
20 | K971 | P.S. 971 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001112745
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | Scope | Complete | 9/5/2019 | 1/24/2020 | 6/22/2021 | 115935 | 142083 | 139366 | DSF0001010111, DSF0001009243, DSF0001009242
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | Design | Complete | 7/12/2021 | 12/13/2021 | 1/25/2022 | 572050 | 366045 | 366045 | DSF0001010111, DSF0001009243, DSF0001009242
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | Construction | In-Progress | 6/13/2022 | 3/3/2024 |  | 12211563 | 11684919 | 10065299 | DSF0001010111, DSF0001009243, DSF0001009242
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | CM,F&E | In-Progress | 6/13/2022 | 3/3/2024 |  | 868733 | 746034 | 740854 | DSF0001010111, DSF0001009243, DSF0001009242
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/19/2022 | 11/17/2022 | 8/4/2022 | 5380 | 1741 | 1741 | DSF0001034662
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/4/2022 | 2/2/2023 | 1/11/2023 | 24210 | 6963 | 6963 | DSF0001034662
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/27/2023 | 8/21/2024 |  | 312040 | 277100 | 220316 | DSF0001034662
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/27/2023 | 8/21/2024 |  | 129400 | 108295 | 106309 | DSF0001034662
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION | Scope | Complete | 2/7/2023 | 6/7/2023 | 7/17/2024 | 0 | 16727 | 16727 | DSF0001035392
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION | Design | In-Progress | 7/17/2024 | 11/18/2024 |  | 45000 | 43129 | 25337 | DSF0001035392
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 750 | DSF0001035392
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 36235 | DSF0001035392
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 6/3/2024 | 9/4/2024 | 9/12/2024 | 0 | 1075 | 1075 | DSF0001035393
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | In-Progress | 9/12/2024 | 1/17/2025 |  | 7515 | 4300 | 4300 | DSF0001035393
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 110217 | 110217 | 0 | DSF0001035393
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 7515 | 7515 | 4907 | DSF0001035393
21 | K043 | I.S. 98 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 514634 | 0 | DSF0000959762
21 | K043 | I.S. 98 - BROOKLYN | DOE - RESOA | FY12 RESO A GYMNASIUM SUPPLEMENTAL COOLING | Construction | In-Progress | 6/15/2016 | DOER |  | DOER | 3887 | 0 | DSF0000844102
21 | K043 | I.S. 98 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001008344
21 | K043 | I.S. 98 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/27/2023 | DOES | 7/28/2023 | DOES | 737629 |  | DSF0001035170
21 | K043 | I.S. 98 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/10/2024 | DOES | 12/20/2024 | DOES | 65832 |  | DSF0001084725
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/20/2021 | 10/5/2021 | 12/16/2022 | 55740 | 119626 | 107124 | DSF0000985960, DSF0000985962, DSF0000985963, DSF0000985964
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 1/25/2023 | 6/27/2023 |  | 278019 | 278019 | 237627 | DSF0000985960, DSF0000985962, DSF0000985963, DSF0000985964
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 6196455 | 6245822 | 142403 | DSF0000985960, DSF0000985962, DSF0000985963, DSF0000985964
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 395296 | 395296 | 42393 | DSF0000985960, DSF0000985962, DSF0000985963, DSF0000985964
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/18/2024 | 7/17/2024 | 4/10/2024 | 4495 | 2543 | 2543 | DSF0001087384
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/10/2024 | 10/4/2024 | 8/22/2024 | 20228 | 10171 | 10171 | DSF0001087384
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 260722 | 260722 | 3088 | DSF0001087384
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 52063 | 52063 | 5137 | DSF0001087384
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | Scope | Complete | 2/18/2022 | 7/6/2022 | 12/6/2022 | 0 | 181728 | 119593 | DSF0001033464
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | Design | In-Progress | 2/3/2023 | 7/7/2023 |  | 425757 | 290147 | 258326 | DSF0001033464
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | Construction | PNS | PNS | PNS | PNS | 6244439 | 6244439 | 500 | DSF0001033464
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 425757 | 425757 | 41691 | DSF0001033464
21 | K090 | P.S. 90 - BROOKLYN | Fast Track Projects | FY18 RESO A LIBRARY UPGRADES | Construction | In-Progress | 7/3/2018 | FTK |  | FTK | 115400 | 108319 | DSF0000867325
21 | K090 | P.S. 90 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 333323 | 0 | DSF0000959781
21 | K090 | P.S. 90 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/17/2023 | DOER |  | DOER | 902920 | 0 | DSF0001008449
21 | K090 | P.S. 90 - BROOKLYN | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 460000 | 0 | DSF0001033462
21 | K090 | P.S. 90 - BROOKLYN | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035409
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2/3/2020 | 7/2/2020 | 5/19/2020 | 125407 | 125305 | 125305 | DSF0000798421, DSF0000892368, DSF0000937647, DSF0000937645
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 5/20/2020 | 10/21/2020 | 8/3/2020 | 609827 | 455418 | 455418 | DSF0000798421, DSF0000892368, DSF0000937647, DSF0000937645
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 4/25/2022 | 7/12/2024 |  | 12232723 | 11435278 | 8074001 | DSF0000798421, DSF0000892368, DSF0000937647, DSF0000937645
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 4/25/2022 | 7/12/2024 |  | 1006895 | 1125951 | 1117580 | DSF0000798421, DSF0000892368, DSF0000937647, DSF0000937645
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 3/8/2024 | 7/24/2024 | 7/22/2024 | 27996 | 76614 | 55722 | DSF0001089252, DSF0001112403
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | In-Progress | 7/24/2024 | 12/26/2024 |  | 134901 | 134901 | 53665 | DSF0001089252, DSF0001112403
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS | Construction | PNS | PNS | PNS | PNS | 2562848 | 2562848 | 733 | DSF0001089252, DSF0001112403
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 201052 | 201052 | 29428 | DSF0001089252, DSF0001112403
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033466
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033466
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033466
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033466
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE / FY21 RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/17/2021 | 3/2/2022 | 2/28/2022 | 0 | 32731 | 32731 | DSF0001007778, DSF0001008451
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE / FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 3/1/2022 | 6/1/2022 | 10/4/2022 | 196467 | 103816 | 103816 | DSF0001007778, DSF0001008451
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE / FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/6/2023 | 11/4/2024 |  | 2881511 | 2721310 | 1756464 | DSF0001007778, DSF0001008451
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE / FY21 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 11/6/2023 | 11/4/2024 |  | 196467 | 286931 | 282773 | DSF0001007778, DSF0001008451
21 | K095 | P.S. 95 - BROOKLYN | SCA IEH | PO18-ABATE 3X3 BUBBLING PLASTER IN HALLWAY BY ROOM 234 THIS IS NON ACM ACCORDING TO AHERA BOOK. CAN | Construction | Complete | 4/11/2024 | IEH | 9/4/2024 | IEH | 0 | 0 | SCA0000072921
21 | K095 | P.S. 95 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 443306 | 0 | DSF0000959783
21 | K095 | P.S. 95 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112562
21 | K095 | P.S. 95 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/5/2024 | DOES |  | DOES | 884548 | 0 | DSF0001034209
21 | K095 | P.S. 95 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/3/2024 | DOES | 11/6/2024 | DOES | 65832 |  | DSF0001084589
21 | K096 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 5/28/2020 | 11/24/2020 | 10/8/2020 | 198872 | 273397 | 273397 | DSF0000937664, DSF0000937667, DSF0000937669, DSF0000937668, DSF0000986089
21 | K096 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 10/16/2020 | 6/15/2021 | 4/27/2021 | 986690 | 508046 | 500502 | DSF0000937664, DSF0000937667, DSF0000937669, DSF0000937668, DSF0000986089
21 | K096 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | Complete | 8/3/2021 | 8/1/2024 | 8/1/2024 | 21536856 | 19724246 | 19052666 | DSF0000937664, DSF0000937667, DSF0000937669, DSF0000937668, DSF0000986089
21 | K096 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | Complete | 8/3/2021 | 8/1/2024 | 8/1/2024 | 1449656 | 1319762 | 1299392 | DSF0000937664, DSF0000937667, DSF0000937669, DSF0000937668, DSF0000986089
21 | K096 | SUCCESS ACADEMY CHARTER SCHOOL - BENSONHURST - NEW YORK 3 | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008522
21 | K096 | SUCCESS ACADEMY CHARTER SCHOOL - BENSONHURST - NEW YORK 3 | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0 | DSF0001033615
21 | K096 | SUCCESS ACADEMY CHARTER SCHOOL - BENSONHURST - NEW YORK 3 | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035412
21 | K096 | I.S. 96 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 600000 | 0 | DSF0001112563
21 | K096 | I.S. 96 - BROOKLYN | DOE - RESOA | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 12/15/2018 | DOER |  | DOER | 8367 | 0 | DSF0000866362
21 | K096 | I.S. 96 - BROOKLYN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/7/2024 | DOER |  | DOER | 505522 | 0 | DSF0001087177
21 | K096 | I.S. 96 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | Complete | 12/15/2020 | DOES | 3/22/2021 | DOES | 112296 |  | DSF0000960484
21 | K096 | I.S. 96 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/1/2024 | DOES | 8/8/2024 | DOES | 65832 |  | DSF0001084734
21 | K096 | I.S. 96 - BROOKLYN | DOE - Skilled Trades | CHARTER MATCH FLOOR REPLACEMENT | Construction | Complete | 9/1/2024 | DOES | 12/12/2024 | DOES | 340000 |  | DSF0001112101
21 | K097 | P.S. 97 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / EXISTING BUILDING WORK | Scope | Complete | 5/9/2017 | 3/21/2018 | 2/21/2018 | 129190 | 140956 | 140956 | DSF0000799391, DSF0000779204, DSF0000798193
21 | K097 | P.S. 97 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / EXISTING BUILDING WORK | Design | Complete | 2/21/2018 | 6/18/2018 | 2/4/2020 | 602780 | 778747 | 723600 | DSF0000799391, DSF0000779204, DSF0000798193
21 | K097 | P.S. 97 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / EXISTING BUILDING WORK | Construction | In-Progress | 10/15/2024 | 4/2/2027 |  | 12915001 | 11857962 | 63075 | DSF0000799391, DSF0000779204, DSF0000798193
21 | K097 | P.S. 97 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / EXISTING BUILDING WORK | CM,F&E | In-Progress | 10/15/2024 | 4/2/2027 |  | 806843 | 143038 | 135740 | DSF0000799391, DSF0000779204, DSF0000798193
21 | K097 | P.S. 97 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE TWO 16 FEET ROWS OF FLOOR OUTLETS AND ONE 2 FEET OF OUTLETS OLD COMPUTER ROOM | Construction | Complete | 9/23/2024 | IEH | 11/16/2024 | IEH | 0 | 0 | SCA0000073411
21 | K097 | P.S. 97 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/21/2023 | DIIR | 5/3/2024 | DIIR | 419153 | 419153 | DSF0001033010
21 | K097 | P.S. 97 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001035413
21 | K097 | P.S. 97 - BROOKLYN | DOE - RESOA | RESO A HYDROPONICS LAB | Construction | In-Progress | 4/15/2024 | DOER |  | DOER | 108641 | 0 | DSF0001085162
21 | K097 | P.S. 97 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0 | DSF0001085969
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 5/7/2019 | 9/20/2019 | 11/4/2019 | 127710 | 137907 | 132315 | DSF0000912354, DSF0000937704
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 11/13/2019 | 5/1/2020 | 11/19/2021 | 638550 | 567825 | 566875 | DSF0000912354, DSF0000937704
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 8/8/2022 | 8/6/2024 |  | 14367375 | 14332099 | 11571140 | DSF0000912354, DSF0000937704
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 8/8/2022 | 8/6/2024 |  | 1119367 | 734508 | 723212 | DSF0000912354, DSF0000937704
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/23/2023 | 5/22/2023 | 1/31/2023 | 4120 | 3295 | 3295 | DSF0001034597
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/31/2023 | 7/27/2023 | 4/4/2023 | 18540 | 13182 | 13182 | DSF0001034597
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/14/2023 | 6/7/2024 |  | 238960 | 219128 | 206768 | DSF0001034597
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/14/2023 | 6/7/2024 |  | 157810 | 147043 | 90230 | DSF0001034597
21 | K099 | P.S. 99 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE (27) EXISTING BULLETIN BOARDS IN SCHOOL CORRIDORS(3,2 &1) INSTALL (27) NEW BUL | Construction | Complete | 8/28/2023 | IEH | 8/29/2024 | IEH | 0 | 0 | SCA0000072242
21 | K099 | P.S. 99 - BROOKLYN | SCA IEH | PO18-TOUCH UP FLACKY PAINT ON ACM PLASTER @ VARIOUS LOCATIONS SCA CONTRACTOR TO ADDRESS | Construction | Complete | 8/28/2024 | IEH | 8/30/2024 | IEH | 0 | 0 | SCA0000073329
21 | K099 | P.S. 99 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/18/2024 | DIIR |  | DIIR | 250000 | 0 | DSF0001085970
21 | K099 | P.S. 99 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 128824 | 0 | DSF0001034407
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/14/2020 | 11/16/2020 | 10/16/2020 | 211376 | 380463 | 376182 | DSF0000937728, DSF0000937730, DSF0000937731, DSF0000937732, DSF0001008633
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 10/29/2020 | 6/15/2021 | 7/1/2021 | 1053403 | 648809 | 630510 | DSF0000937728, DSF0000937730, DSF0000937731, DSF0000937732, DSF0001008633
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 4/11/2022 | 4/9/2024 |  | 23400916 | 21892816 | 21060689 | DSF0000937728, DSF0000937730, DSF0000937731, DSF0000937732, DSF0001008633
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 4/11/2022 | 4/9/2024 |  | 1505699 | 769741 | 769126 | DSF0000937728, DSF0000937730, DSF0000937731, DSF0000937732, DSF0001008633
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Scope | Complete | 8/4/2020 | 12/4/2020 | 2/10/2021 | 39980 | 52969 | 52969 | DSF0000961071, DSF0001008759
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Design | Complete | 2/17/2021 | 7/16/2021 | 8/31/2021 | 199900 | 201523 | 149774 | DSF0000961071, DSF0001008759
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Construction | In-Progress | 5/2/2024 | 5/1/2026 |  | 4497750 | 4384561 | 830589 | DSF0000961071, DSF0001008759
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | CM,F&E | In-Progress | 5/2/2024 | 5/1/2026 |  | 279860 | 129805 | 129696 | DSF0000961071, DSF0001008759
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/25/2023 | 5/24/2023 | 2/3/2023 | 4000 | 2689 | 2689 | DSF0001034594
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/3/2023 | 8/1/2023 | 4/4/2023 | 18000 | 10758 | 10758 | DSF0001034594
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/14/2023 | 6/7/2024 |  | 232000 | 215237 | 203237 | DSF0001034594
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/14/2023 | 6/7/2024 |  | 101331 | 86781 | 83801 | DSF0001034594
21 | K100 | P.S. 100 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0000913214
21 | K100 | P.S. 100 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112564
21 | K101 | P.S. 101 - BROOKLYN | SCA CIP RESOA | RESO A IPDVS SYSTEM | Scope | Complete | 5/8/2023 | 9/7/2023 | 5/16/2023 | 0 | 1081 | 1081 | DSF0001083859
21 | K101 | P.S. 101 - BROOKLYN | SCA CIP RESOA | RESO A IPDVS SYSTEM | Design | Complete | 5/16/2023 | 11/13/2023 | 10/18/2023 | 14657 | 4326 | 4326 | DSF0001083859
21 | K101 | P.S. 101 - BROOKLYN | SCA CIP RESOA | RESO A IPDVS SYSTEM | Construction | In-Progress | 4/17/2024 | 3/12/2025 |  | 214965 | 187841 | 7541 | DSF0001083859
21 | K101 | P.S. 101 - BROOKLYN | SCA CIP RESOA | RESO A IPDVS SYSTEM | CM,F&E | In-Progress | 4/17/2024 | 3/12/2025 |  | 18921 | 22866 | 9468 | DSF0001083859
21 | K101 | P.S. 101 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE TILES AND SUB FLOORING IN ROOMS 327 (OLD ROOM 312) | Construction | Complete | 3/18/2024 | IEH | 8/13/2024 | IEH | 0 | 0 | SCA0000072818
21 | K101 | P.S. 101 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001085971
21 | K101 | P.S. 101 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112565
21 | K101 | P.S. 101 - BROOKLYN | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/31/2023 | DOER |  | DOER | 371675 | 0 | DSF0001033469
21 | K101 | P.S. 101 - BROOKLYN | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/7/2024 | DOER |  | DOER | 38992 | 0 | DSF0001111863
21 | K101 | P.S. 101 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 5/2/2022 | DOES |  | DOES | 62704 | 0 | DSF0000866102
21 | K121 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/20/2022 | 11/18/2022 | 8/4/2022 | 4260 | 1263 | 1263 | DSF0001034554
21 | K121 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/4/2022 | 2/2/2023 | 1/11/2023 | 19170 | 5052 | 5052 | DSF0001034554
21 | K121 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/27/2023 | 8/21/2024 |  | 247080 | 221100 | 170042 | DSF0001034554
21 | K121 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/27/2023 | 8/21/2024 |  | 151353 | 136373 | 112188 | DSF0001034554
21 | K121 | P.S. 121 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0 | DSF0001033477
21 | K121 | P.S. 121 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/4/2024 | DIIR |  | DIIR | 250000 | 0 | DSF0001085981
21 | K121 | P.S. 121 - BROOKLYN | DOE - RESOA | FY10 RESO A BALLFIELD | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0000690042
21 | K121 | P.S. 121 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/20/2024 | DOES | 9/27/2024 | DOES | 65832 |  | DSF0001084593
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 4/8/2022 | 10/4/2022 | 8/25/2022 | 11980 | 32502 | 32502 | DSF0000912651
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 8/26/2022 | 2/27/2023 | 2/23/2023 | 59900 | 130004 | 130004 | DSF0000912651
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 12/14/2023 | 11/7/2024 |  | 1347750 | 1263860 | 606171 | DSF0000912651
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 12/14/2023 | 11/7/2024 |  | 83860 | 167597 | 62433 | DSF0000912651
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 5/26/2022 | 9/27/2022 | 2/22/2023 | 44224 | 35936 | 35936 | DSF0001085147
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 3/3/2023 | 8/3/2023 | 5/11/2023 | 221120 | 126348 | 113123 | DSF0001085147
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 4975189 | 4975189 | 24542 | DSF0001085147
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 309567 | 309567 | 24031 | DSF0001085147
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112576
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 87900 | 87900 | 0 | DSF0001112576
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1289200 | 1289200 | 0 | DSF0001112576
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 87900 | 87900 | 0 | DSF0001112576
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113570
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113570
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113570
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113570
21 | K128 | P.S. 128 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 4/25/2022 | EMER |  | EMER | 120029 | 90900 | SCA0000071072
21 | K128 | P.S. 128 - BROOKLYN | SCA IEH | PO18-ABATE DAMAGED PLASTER LOCATED IN CLASSROOM 106 ID: 2106 APPROX: 10 SF PIECES ARE LOOSE AND READ | Construction | Complete | 8/22/2024 | IEH | 8/24/2024 | IEH | 0 | 0 | SCA0000073316
21 | K128 | P.S. 128 - BROOKLYN | SCA IEH | PO18-ABATE DAMAGED PIPE INSULATION IN ROOM 219 APPROX. 14LF | Construction | Complete | 12/13/2024 | IEH | 12/17/2024 | IEH | 0 | 0 | SCA0000073717
21 | K128 | P.S. 128 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112577
21 | K128 | P.S. 128 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001085985
21 | K128 | P.S. 128 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0001085986
21 | K128 | P.S. 128 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/18/2024 | DOES | 7/25/2024 | DOES | 65832 | 189 | DSF0001084050
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | Scope | Complete | 1/26/2021 | 5/26/2021 | 1/5/2022 | 69210 | 63498 | 63498 | DSF0000986919, DSF0001034394, DSF0001062373
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | Design | Complete | 1/6/2022 | 7/11/2022 | 4/4/2023 | 346050 | 324201 | 264560 | DSF0000986919, DSF0001034394, DSF0001062373
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | Construction | In-Progress | 12/4/2023 | 12/2/2025 |  | 7786124 | 7757403 | 2591217 | DSF0000986919, DSF0001034394, DSF0001062373
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | CM,F&E | In-Progress | 12/4/2023 | 12/2/2025 |  | 486055 | 199471 | 196075 | DSF0000986919, DSF0001034394, DSF0001062373
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 7/11/2024 | 11/12/2024 | 10/10/2024 | 0 | 32323 | 32323 | DSF0001086000
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 10/15/2024 | 3/20/2025 |  | 90000 | 104413 | 29769 | DSF0001086000
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001086000
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 10950 | DSF0001086000
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 9/11/2024 | 12/12/2024 | 11/7/2024 | 0 | 1476 | 1476 | DSF0001087013
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | In-Progress | 11/12/2024 | 3/12/2025 |  | 29473 | 5907 | 5907 | DSF0001087013
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 432273 | 432273 | 0 | DSF0001087013
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 29473 | 29473 | 3927 | DSF0001087013
21 | K153 | P.S. 153 - BROOKLYN | SCA IEH | PO18-REMOVE APPROX. 4 FEET OF ACM PIPE COVER FROM A 3' WATER MAIN VALVE. LOCATED IN BASEMENT ROOM | Construction | Complete | 8/5/2024 | IEH | 8/14/2024 | IEH | 0 | 0 | SCA0000073233
21 | K153 | P.S. 153 - BROOKLYN | SCA IEH | PO18-CORE DRILL APPROX 32 HOLES IN KITCHEN AND CAFETERIA CEILING IS CONFIRMED ACM PICTURES AND MARKI | Construction | Complete | 8/14/2024 | IEH | 9/14/2024 | IEH | 0 | 0 | SCA0000073283
21 | K153 | P.S. 153 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/17/2023 | DOES | 12/11/2024 | DOES | 65832 |  | DSF0001084064
21 | K177 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 1/18/2021 | 5/18/2021 | 5/12/2021 | 38000 | 54826 | 54826 | DSF0000987311
21 | K177 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 5/18/2021 | 10/19/2021 | 10/7/2021 | 190000 | 104229 | 98442 | DSF0000987311
21 | K177 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | Construction | In-Progress | 9/11/2023 | 3/3/2025 |  | 4275000 | 4047185 | 3420400 | DSF0000987311
21 | K177 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 9/11/2023 | 3/3/2025 |  | 266000 | 215020 | 200252 | DSF0000987311
21 | K177 | P.S. 177 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008514
21 | K177 | P.S. 177 - BROOKLYN | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 401125 | 0 | DSF0001111888
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 1/29/2021 | 5/28/2021 | 2/9/2022 | 48200 | 130418 | 130418 | DSF0001008592
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 2/9/2022 | 7/8/2022 | 9/7/2022 | 241000 | 242812 | 238277 | DSF0001008592
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | Construction | In-Progress | 9/5/2023 | 9/3/2024 |  | 5422500 | 8618773 | 5572353 | DSF0001008592
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 9/5/2023 | 9/3/2024 |  | 337400 | 499783 | 452041 | DSF0001008592
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2/14/2020 | 11/22/2022 | 10/27/2022 | 199005 | 237687 | 237687 | DSF0000960700, DSF0001012272, DSF0001012273, DSF0001012274
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/2/2022 | 4/7/2023 | 3/10/2023 | 990021 | 1135713 | 726341 | DSF0000960700, DSF0001012272, DSF0001012273, DSF0001012274
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 9/11/2023 | 9/9/2026 |  | 21842519 | 20491373 | 6426173 | DSF0000960700, DSF0001012272, DSF0001012273, DSF0001012274
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/11/2023 | 9/9/2026 |  | 1430576 | 718508 | 702729 | DSF0000960700, DSF0001012272, DSF0001012273, DSF0001012274
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/19/2024 | 8/20/2024 | 4/25/2024 | 5815 | 4145 | 4145 | DSF0001087416
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/25/2024 | 10/22/2024 | 8/22/2024 | 26166 | 16579 | 16579 | DSF0001087416
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 337244 | 337244 | 0 | DSF0001087416
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 62507 | 62507 | 3134 | DSF0001087416
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Scope | Complete | 4/7/2021 | 8/6/2021 | 9/28/2021 | 0 | 18907 | 18907 | DSF0001008452
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 10/26/2021 | 3/31/2022 | 7/13/2022 | 86564 | 65511 | 65511 | DSF0001008452
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/21/2023 | 4/19/2024 |  | 1269601 | 752096 | 656991 | DSF0001008452
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 4/21/2023 | 4/19/2024 |  | 86564 | 146043 | 143892 | DSF0001008452
21 | K188 | P.S. 188 - BROOKLYN | Fast Track Projects | EMERGENCY AUDITORIUM FLOOR | Construction | In-Progress | 9/5/2018 | FTK |  | FTK | 23085 | 22680 | DSF0000870923
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 10/18/2019 | DOER | 7/28/2021 | DOER | 305968 | 195389 | DSF0000913233
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY20 RESO A MEDIA CENTER | Construction | Complete | 7/6/2021 | DOER | 12/19/2022 | DOER | 235429 | 302658 | DSF0000913234
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 1/15/2020 | DOER |  | DOER | 112280 | 147493 | DSF0000913235
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | Complete | 8/23/2021 | DOER | 5/4/2024 | DOER | 262767 | 412315 | DSF0000913236
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 99519 | 0 | DSF0001033030
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 4/23/2024 | DOER |  | DOER | 250669 | 0 | DSF0001033497
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | Complete | 7/20/2023 | DOER | 11/19/2023 | DOER | 98395 |  | DSF0001034308
21 | K188 | P.S. 188 - BROOKLYN | DOE - Skilled Trades | WASTE LINE REPLACEMENT | Construction | In-Progress | 2/26/2021 | DOES |  | DOES | 84300 | 0 | DSF0000987503
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/14/2023 | 12/13/2023 | 10/6/2023 | 135720 | 113470 | 113470 | DSF0001012500, DSF0001012501, DSF0001012502, DSF0001087230
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/9/2023 | 6/28/2024 | 4/29/2024 | 678600 | 253138 | 252652 | DSF0001012500, DSF0001012501, DSF0001012502, DSF0001087230
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 7/22/2024 | 1/7/2027 |  | 15268501 | 13926330 | 366111 | DSF0001012500, DSF0001012501, DSF0001012502, DSF0001087230
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 7/22/2024 | 1/7/2027 |  | 950040 | 156917 | 151800 | DSF0001012500, DSF0001012501, DSF0001012502, DSF0001087230
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/15/2023 | 10/17/2023 | 7/3/2023 | 3920 | 1909 | 1909 | DSF0001035009
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/3/2023 | 12/29/2023 | 10/18/2023 | 17640 | 7638 | 7638 | DSF0001035009
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 4/17/2024 | 3/12/2025 |  | 227360 | 205470 | 3170 | DSF0001035009
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 4/17/2024 | 3/12/2025 |  | 87795 | 73033 | 10965 | DSF0001035009
21 | K199 | P.S. 199 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112608
21 | K199 | P.S. 199 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112609
21 | K199 | P.S. 199 - BROOKLYN | DOE - Skilled Trades | DOMESTIC WATER HEATER | Construction | In-Progress | 10/1/2020 | DOES |  | DOES | 43017 | 0 | DSF0000961195
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/15/2021 | 12/14/2021 | 10/28/2021 | 241601 | 322796 | 321884 | DSF0000987934, DSF0000987936, DSF0000987937, DSF0000987938, DSF0000987939
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 11/17/2021 | 6/30/2022 | 4/29/2022 | 1208001 | 574070 | 574070 | DSF0000987934, DSF0000987936, DSF0000987937, DSF0000987938, DSF0000987939
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 7/18/2022 | 7/16/2024 |  | 27180000 | 24923066 | 22446546 | DSF0000987934, DSF0000987936, DSF0000987937, DSF0000987938, DSF0000987939
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/18/2022 | 7/16/2024 |  | 1691200 | 435513 | 433702 | DSF0000987934, DSF0000987936, DSF0000987937, DSF0000987938, DSF0000987939
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/17/2023 | 4/17/2023 | 4/24/2023 | 27940 | 57838 | 57838 | DSF0001083687
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 4/25/2023 | 9/11/2023 | 10/31/2023 | 139700 | 160627 | 120869 | DSF0001083687
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 11/4/2024 | 11/3/2025 |  | 3143250 | 2855048 | 13683 | DSF0001083687
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 11/4/2024 | 11/3/2025 |  | 195580 | 48509 | 45989 | DSF0001083687
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/13/2022 | 4/14/2023 | 1/6/2023 | 3400 | 4733 | 4733 | DSF0001034578
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/6/2023 | 7/5/2023 | 4/4/2023 | 15300 | 18933 | 18933 | DSF0001034578
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 197200 | 194715 | 144930 | DSF0001034578
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 78931 | 86518 | 81060 | DSF0001034578
21 | K209 | P.S. 209 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE VFT IN ROOM 251 APPROX 336 SQFT REPORT AND PICTURES ATTACHED WITHIN EMAIL | Construction | Complete | 11/20/2024 | IEH | 12/5/2024 | IEH | 0 | 0 | SCA0000073624
21 | K209 | P.S. 209 - BROOKLYN | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 10/19/2024 | FTK |  | FTK | 292314 | 46 | DSF0001112198
21 | K212 | P.S. 212 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR/ SUB-FLOOR IN ROOM 257 PRINCIPALS OFFICE PRICIPALS FLOOR TO REMOVE TRIP | Construction | In-Progress | 8/8/2024 | IEH |  | IEH | 0 | 0 | SCA0000073261
21 | K212 | P.S. 212 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR 6LF OF PIPE INSULATION ON GYM CEILING BEHIND GATE. SPACE ID 4361: GYM. APPROXI | Construction | Complete | 9/26/2024 | IEH | 10/4/2024 | IEH | 0 | 0 | SCA0000073443
21 | K212 | P.S. 212 - BROOKLYN | Fast Track Projects | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 40000 | 0 | DSF0001033507
21 | K212 | P.S. 212 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 7/22/2021 | DOER | 2/23/2022 | DOER | 130357 | 180429 | DSF0000913054
21 | K212 | P.S. 212 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/3/2020 | DOES |  | DOES | 344539 | 0 | DSF0000912964
21 | K215 | P.S. 215 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION IN STUDENT BATHROOMS AND STAIRCASE C AND REINSULATE BOYS BATHROOM 119 AP | Construction | Complete | 7/15/2024 | IEH | 9/14/2024 | IEH | 0 | 0 | SCA0000073139
21 | K215 | P.S. 215 - BROOKLYN | Fast Track Projects | LSP REPLACE PVI DOMESTIC WATER HEATER | Construction | In-Progress | 12/23/2019 | FTK |  | FTK | 180512 | 166657 | DSF0000894225
21 | K215 | P.S. 215 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033508
21 | K215 | K231 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/1/2023 | DIIR |  | DIIR | 95000 | 0 | DSF0001033518
21 | K215 | P.S. 215 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112621
21 | K215 | P.S. 215 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 328159 | 0 | DSF0001035475
21 | K215 | P.S. 215 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/14/2022 | DOES |  | DOES | 57392 | 0 | DSF0001034409
21 | K215 | P.S. 215 - BROOKLYN | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 12/16/2022 | DOES |  | DOES | 447218 | 0 | SCA0000071041
21 | K216 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | Scope | Complete | 8/4/2020 | 12/4/2020 | 1/29/2021 | 54940 | 85348 | 85348 | DSF0000961073, DSF0001008767, DSF0001008768
21 | K216 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | Design | Complete | 2/2/2021 | 7/9/2021 | 7/9/2021 | 274700 | 398690 | 248222 | DSF0000961073, DSF0001008767, DSF0001008768
21 | K216 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | Construction | In-Progress | 8/2/2024 | 8/1/2026 |  | 6180750 | 5866496 | 651553 | DSF0000961073, DSF0001008767, DSF0001008768
21 | K216 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | CM,F&E | In-Progress | 8/2/2024 | 8/1/2026 |  | 384579 | 181475 | 169060 | DSF0000961073, DSF0001008767, DSF0001008768
21 | K216 | P.S. 216 - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM RENOVATION | Construction | In-Progress | 7/28/2022 | DOER |  | DOER | 145172 | 0 | DSF0001008440
21 | K216 | P.S. 216 - BROOKLYN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 4/30/2023 | DOER |  | DOER | 47411 | 0 | DSF0001033509
21 | K216 | P.S. 216 - BROOKLYN | DOE - RESOA | FY23 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 152267 | 0 | DSF0001035476
21 | K225 | K771 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033614
21 | K225 | P.S. 225 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001112627
21 | K225 | P.S. 225 - BROOKLYN | DOE - RESOA | FY05 RESO A TRASH COMPACTOR | Construction | PNS | PNS | PNS | PNS | DOER | 71023 | 0 | DSF0000544171
21 | K225 | K771 SPED - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 4/1/2024 | DOER | 8/20/2024 | DOER | 181030 |  | DSF0001035479
21 | K225 | P.S. 225 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 357383 | 0 | DSF0001086032
21 | K225 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112625
21 | K225 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 315000 | 0 | DSF0001112626
21 | K225 | P.S. 225 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/31/2022 | DOES |  | DOES | 273464 | 0 | DSF0001034411
21 | K225 | P.S. 225 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/31/2024 | DOES | 8/9/2024 | DOES | 65832 | 6479 | DSF0001084607
21 | K226 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/19/2022 | 4/20/2023 | 1/10/2023 | 3940 | 5119 | 5119 | DSF0001034627
21 | K226 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/10/2023 | 7/7/2023 | 4/4/2023 | 17730 | 20479 | 20479 | DSF0001034627
21 | K226 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/21/2023 | 6/14/2024 |  | 228520 | 202872 | 160659 | DSF0001034627
21 | K226 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/21/2023 | 6/14/2024 |  | 87740 | 89781 | 83454 | DSF0001034627
21 | K226 | P.S. 226 - BROOKLYN | SCA IEH | PO18-ABATE TILES IN ROOM 264/264A TILES ARE LISTED AS ACM IN THE AHERA BOOK CURRENTLY 12 TILES POPPE | Construction | Complete | 7/26/2024 | IEH | 7/28/2024 | IEH | 0 | 0 | SCA0000073186
21 | K226 | P.S. 226 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DETERIORATED 9X9 FLOOR TILE IN ROOM 254, ENTIRE ROOM | Construction | Complete | 9/10/2024 | IEH | 10/19/2024 | IEH | 0 | 0 | SCA0000073365
21 | K226 | P.S. 226 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 55000 | 0 | DSF0000913796
21 | K226 | P.S. 226 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/12/2024 | DOES | 11/19/2024 | DOES | 65832 |  | DSF0001084608
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 6/6/2023 | 12/5/2023 | 10/10/2023 | 240689 | 231453 | 231453 | DSF0001063832, DSF0001063833, DSF0001063834, DSF0001087232, DSF0001087231
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | Complete | 10/31/2023 | 6/28/2024 | 4/18/2024 | 1195757 | 381481 | 381481 | DSF0001063832, DSF0001063833, DSF0001063834, DSF0001087232, DSF0001087231
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Construction | In-Progress | 7/22/2024 | 7/5/2027 |  | 26239413 | 23525480 | 347133 | DSF0001063832, DSF0001063833, DSF0001063834, DSF0001087232, DSF0001087231
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | CM,F&E | In-Progress | 7/22/2024 | 7/5/2027 |  | 1742491 | 150725 | 146764 | DSF0001063832, DSF0001063833, DSF0001063834, DSF0001087232, DSF0001087231
21 | K228 | I.S. 228 - BROOKLYN | SCA IEH | PO18-TEST / ABATE STUDENT CAFETERIA CEILING AT EXIT 12 | Construction | Complete | 12/20/2023 | IEH | 10/11/2024 | IEH | 0 | 0 | SCA0000072587
21 | K228 | I.S. 228 - BROOKLYN | Fast Track Projects | LSP FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 10/11/2023 | FTK |  | FTK | 135000 | 134953 | DSF0001035481
21 | K228 | I.S. 228 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 95000 | 0 | DSF0000913797
21 | K228 | I.S. 228 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112628
21 | K228 | I.S. 228 - BROOKLYN | DOE - RESOA | FY09 RESO A CONTAINERIZATION | Construction | PNS | PNS | PNS | PNS | DOER | 151175 | 0 | DSF0000623070
21 | K228 | I.S. 228 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/24/2022 | DOES |  | DOES | 222926 | 0 | DSF0001034412
21 | K228 | I.S. 228 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/16/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084750
21 | K237 | THE ACADAMY OF TALENTED SCHOLARS - K | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 250000 | 250000 | 0 | DSF0000913541
21 | K237 | THE ACADAMY OF TALENTED SCHOLARS - K | DIIT - RESOA | FY15 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0000800596
21 | K237 | THE ACADAMY OF TALENTED SCHOLARS - K | DIIT - RESOA | FY16 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0000823508
21 | K237 | THE ACADAMY OF TALENTED SCHOLARS - K | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112639
21 | K238 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/2/2023 | 6/2/2023 | 2/3/2023 | 4444 | 7306 | 7306 | DSF0001034614
21 | K238 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/3/2023 | 8/1/2023 | 5/3/2023 | 19997 | 29225 | 29225 | DSF0001034614
21 | K238 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/16/2023 | 7/10/2024 |  | 257733 | 229834 | 197993 | DSF0001034614
21 | K238 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/16/2023 | 7/10/2024 |  | 112345 | 99976 | 90267 | DSF0001034614
21 | K238 | P.S. 238 - BROOKLYN | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON 9X9 ACM FLOOR TILES IF NEEDED ABATE AND REPLACE THE TILES I | Construction | Complete | 7/18/2024 | IEH | 9/27/2024 | IEH | 0 | 0 | SCA0000073152
21 | K238 | K231 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/1/2023 | DIIR |  | DIIR | 65000 | 0 | DSF0001033517
21 | K238 | K231 SPED - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035487
21 | K238 | P.S. 238 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001086038
21 | K238 | P.S. 238 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/13/2022 | DOES |  | DOES | 866375 | 0 | DSF0001034211
21 | K238 | P.S. 238 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/15/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084611
21 | K238 | P.S. 238 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 3/4/2024 | DOES |  | DOES | 539217 | 232018 | DSF0001091701
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 5/31/2022 | 11/23/2022 | 9/26/2022 | 270000 | 201721 | 189769 | DSF0001013320, DSF0001013319, DSF0001013318, DSF0001013317, DSF0001064037
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 9/28/2022 | 6/12/2023 | 4/26/2023 | 1350000 | 401602 | 401214 | DSF0001013320, DSF0001013319, DSF0001013318, DSF0001013317, DSF0001064037
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 10/23/2023 | 5/9/2026 |  | 30375002 | 27223732 | 6180604 | DSF0001013320, DSF0001013319, DSF0001013318, DSF0001013317, DSF0001064037
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 10/23/2023 | 5/9/2026 |  | 1891584 | 303565 | 281562 | DSF0001013320, DSF0001013319, DSF0001013318, DSF0001013317, DSF0001064037
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/18/2023 | 5/17/2023 | 1/24/2023 | 5467 | 7590 | 7590 | DSF0001034665
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/24/2023 | 7/20/2023 | 5/3/2023 | 24599 | 30359 | 30359 | DSF0001034665
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/16/2023 | 7/10/2024 |  | 317058 | 281487 | 237560 | DSF0001034665
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/16/2023 | 7/10/2024 |  | 134217 | 119256 | 115580 | DSF0001034665
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112640
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112640
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001112640
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112640
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113578
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113578
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113578
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113578
21 | K239 | I.S. 239 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ K239 | Construction | In-Progress | 6/27/2023 | EMER |  | EMER | 40350 | 36510 | SCA0000072084
21 | K239 | I.S. 239 - BROOKLYN | SCA IEH | PO18-REMOVE APPROX 6 FT OF ACM PIPE COVER FROM A 2' HOT WATER PIPE? LOCATED IN BASEMENT ABOVE THE | Construction | Complete | 10/25/2024 | IEH | 11/6/2024 | IEH | 0 | 0 | SCA0000073541
21 | K239 | I.S. 239 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001086039
21 | K239 | I.S. 239 - BROOKLYN | DOE - RESOA | FY17 RESO A ROOM CONVERSION | Construction | In-Progress | 12/31/2018 | DOER |  | DOER | 161728 | 0 | DSF0000844284
21 | K239 | I.S. 239 - BROOKLYN | DOE - RESOA | FY17 RESO A HYDROPONICS ROOM | Construction | Complete | 7/5/2019 | DOER | 12/19/2022 | DOER | 281782 | 239840 | DSF0000911812
21 | K239 | I.S. 239 - BROOKLYN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 180038 | 0 | DSF0001034895
21 | K239 | I.S. 239 - BROOKLYN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/19/2024 | DOER |  | DOER | 265522 | 0 | DSF0001035488
21 | K239 | I.S. 239 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/28/2022 | DOES |  | DOES | 170867 | 0 | DSF0001008981
21 | K239 | I.S. 239 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/17/2024 | DOES | 9/27/2024 | DOES | 65832 |  | DSF0001084753
21 | K253 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | Scope | Complete | 11/5/2019 | 3/6/2020 | 3/6/2020 | 1078540 | 769839 | 769839 | DSF0000911840
21 | K253 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | Design | Complete | 3/9/2020 | 9/1/2020 | 5/11/2021 | 4853430 | 2820912 | 2593289 | DSF0000911840
21 | K253 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | Construction | Complete | 12/20/2021 | 9/3/2024 | 6/25/2024 | 61207145 | 58808389 | 57926190 | DSF0000911840
21 | K253 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | CM,Art,F&E | Complete | 12/20/2021 | 9/3/2024 | 6/25/2024 | 8628320 | 8090902 | 6348058 | DSF0000911840
21 | K253 | P.S. 253 - BROOKLYN | SCA CIP | EXISTING BUILDING RENOVATION WORK | Scope | Complete | 6/3/2021 | 12/13/2021 | 2/9/2022 | 33418 | 66011 | 66011 | DSF0000911840
21 | K253 | P.S. 253 - BROOKLYN | SCA CIP | EXISTING BUILDING RENOVATION WORK | Design | Complete | 2/15/2022 | 8/4/2022 | 3/26/2024 | 167092 | 184831 | 169088 | DSF0000911840
21 | K253 | P.S. 253 - BROOKLYN | SCA CIP | EXISTING BUILDING RENOVATION WORK | Construction | PNS | PNS | PNS | PNS | 3759567 | 3759567 | 31271 | DSF0000911840
21 | K253 | P.S. 253 - BROOKLYN | SCA CIP | EXISTING BUILDING RENOVATION WORK | CM,F&E | PNS | PNS | PNS | PNS | 233929 | 233929 | 84579 | DSF0000911840
21 | K253 | P.S. 253 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 12/18/2019 | FTK |  | FTK | 437149 | 437092 | DSF0000912069, DSF0000912474
21 | K253 | P.S. 253 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 60765 | 0
21 | K253 | P.S. 253 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 12/28/2020 | DOES |  | DOES | 124986 | 0 | DSF0000912966
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 7/8/2022 | 11/23/2022 | 8/8/2023 | 148170 | 212670 | 212670 | DSF0001014023, DSF0001014022, DSF0001014021
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 8/16/2023 | 1/22/2024 | 4/1/2024 | 740850 | 634905 | 508393 | DSF0001014023, DSF0001014022, DSF0001014021
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | In-Progress | 7/12/2024 | 7/1/2026 |  | 16669126 | 15234313 | 197768 | DSF0001014023, DSF0001014022, DSF0001014021
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | In-Progress | 7/12/2024 | 7/1/2026 |  | 1037190 | 145174 | 140628 | DSF0001014023, DSF0001014022, DSF0001014021
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/9/2020 | 9/16/2021 | 9/13/2021 | 0 | 14204 | 14204 | DSF0000913260, DSF0000913261
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 9/14/2021 | 11/4/2021 | 1/14/2022 | 60605 | 61677 | 60302 | DSF0000913260, DSF0000913261
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 8/30/2022 | 7/25/2023 | 7/25/2023 | 888861 | 867957 | 658531 | DSF0000913260, DSF0000913261
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 8/30/2022 | 7/25/2023 | 7/25/2023 | 60605 | 111766 | 102201 | DSF0000913260, DSF0000913261
21 | K281 | I.S. 281 - BROOKLYN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 7/25/2022 | DOER |  | DOER | 86625 | 0 | DSF0001008431
21 | K281 | I.S. 281 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 146273 | 0 | DSF0001086067
21 | K281 | I.S. 281 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 109616 | 0 | DSF0001086069
21 | K281 | I.S. 281 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 1/7/2021 | DOES |  | DOES | 103718 | 0 | DSF0000912972
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2023 | 6/29/2023 | 3/8/2023 | 3793 | 2210 | 2210 | DSF0001034605
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/8/2023 | 8/31/2023 | 4/26/2023 | 17068 | 8839 | 8839 | DSF0001034605
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/19/2023 | 9/12/2024 |  | 219988 | 201053 | 52632 | DSF0001034605
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/19/2023 | 9/12/2024 |  | 156200 | 140339 | 98980 | DSF0001034605
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/25/2022 | 9/26/2022 | 10/5/2022 | 0 | 23190 | 23190 | DSF0001033537
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 10/11/2022 | 3/16/2023 | 3/21/2023 | 97065 | 88374 | 87394 | DSF0001033537
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/18/2023 | 1/9/2025 |  | 1423622 | 1341596 | 968632 | DSF0001033537
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 9/18/2023 | 1/9/2025 |  | 97065 | 141173 | 136307 | DSF0001033537
21 | K288 | P.S. 288 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/4/2024 | DIIR |  | DIIR | 150000 | 0 | DSF0001035528
21 | K288 | P.S. 288 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 750000 | 0 | DSF0001112672
21 | K288 | P.S. 288 - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 7/1/2022 | DOER |  | DOER | 286083 | 0 | DSF0001008443
21 | K288 | P.S. 288 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | Complete | 9/16/2021 | DOER | 5/25/2023 | DOER | 176351 | 173979 | DSF0001008549
21 | K288 | P.S. 288 - BROOKLYN | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001033536
21 | K288 | P.S. 288 - BROOKLYN | DOE - RESOA | RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/24/2024 | DOER |  | DOER | 404822 | 0 | DSF0001083919
21 | K288 | P.S. 288 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/30/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084613
21 | K303 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/22/2022 | 11/7/2022 | 1/5/2023 | 119977 | 249570 | 242172 | DSF0001014342, DSF0001014343, DSF0001014344, DSF0001065097
21 | K303 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 1/18/2023 | 6/20/2023 | 5/9/2023 | 589908 | 489475 | 430883 | DSF0001014342, DSF0001014343, DSF0001014344, DSF0001065097
21 | K303 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 9/18/2023 | 2/3/2026 |  | 12409921 | 11306253 | 3206525 | DSF0001014342, DSF0001014343, DSF0001014344, DSF0001065097
21 | K303 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 9/18/2023 | 2/3/2026 |  | 916197 | 468421 | 458851 | DSF0001014342, DSF0001014343, DSF0001014344, DSF0001065097
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSION | Scope | Complete | 4/19/2024 | 8/19/2024 | 10/10/2024 | 0 | 22740 | 2360 | DSF0001112072
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSION | Design | In-Progress | 10/21/2024 | 3/21/2025 |  | 69600 | 46860 | 9438 | DSF0001112072
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 1020800 | 1020800 | 0 | DSF0001112072
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 69600 | 69600 | 6558 | DSF0001112072
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 9/27/2024 | 12/26/2024 | 12/20/2024 | 0 | 0 | 0 | DSF0001113765
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | In-Progress | 12/20/2024 | 4/21/2025 |  | 9524 | 9524 | 0 | DSF0001113765
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 139682 | 139682 | 0 | DSF0001113765
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 9524 | 9524 | 2389 | DSF0001113765
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/2/2023 | 3/7/2024 | 11/15/2023 | 0 | 2835 | 2835 | DSF0001086076
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/15/2023 | 5/13/2024 | 3/20/2024 | 30000 | 11340 | 11340 | DSF0001086076
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/1/2024 | 8/27/2025 |  | 440000 | 194915 | 975 | DSF0001086076
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 11/1/2024 | 8/27/2025 |  | 33740 | 23037 | 4364 | DSF0001086076
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSIONS/PARTITIONING / PATH OF TRAVEL RESO A ROOM CONVERSIONS/PARTITIONING | Scope | Complete | 3/23/2023 | 11/30/2023 | 10/19/2023 | 0 | 18299 | 18299 | DSF0001083692, DSF0001085815
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSIONS/PARTITIONING / PATH OF TRAVEL RESO A ROOM CONVERSIONS/PARTITIONING | Design | Complete | 10/19/2023 | 2/26/2024 | 9/20/2024 | 104850 | 95491 | 90176 | DSF0001083692, DSF0001085815
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSIONS/PARTITIONING / PATH OF TRAVEL RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | 1537800 | 1537800 | 20662 | DSF0001083692, DSF0001085815
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSIONS/PARTITIONING / PATH OF TRAVEL RESO A ROOM CONVERSIONS/PARTITIONING | CM,F&E | PNS | PNS | PNS | PNS | 104850 | 106795 | 39393 | DSF0001083692, DSF0001085815
21 | K303 | I.S. 303 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION IN ROOM #110 | Construction | Complete | 7/29/2024 | IEH | 8/2/2024 | IEH | 0 | 0 | SCA0000073191
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 400000 | 45140 | DSF0001112073
21 | K303 | I.S. 303 - BROOKLYN | DOE - RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/12/2021 | DOER |  | DOER | 383887 | 0 | DSF0000844937
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/16/2023 | DOER |  | DOER | 216806 | 274869 | DSF0001033068
21 | K303 | I.S. 303 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001033538
21 | K303 | I.S. 303 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 8/5/2022 | DOER | 3/24/2023 | DOER | 175829 | 175645 | DSF0001033539
21 | K303 | I.S. 303 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 5/16/2024 | DOER |  | DOER | 250000 | 0 | DSF0001086075
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DOE - RESOA | RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112066
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DOE - RESOA | RESO A PHONE SYSTEM & WIRING UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 532185 | 0 | DSF0001112068
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001112069
21 | K303 | I.S. 303 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/18/2023 | DOES | 11/6/2023 | DOES | 449988 | 399919 | DSF0001035171
21 | K303 | I.S. 303 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/4/2024 | DOES | 10/11/2024 | DOES | 65832 | 10890 | DSF0001084765
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/7/2022 | 11/22/2022 | 6/29/2023 | 73554 | 182895 | 182895 | DSF0001014693, DSF0001014694, DSF0001014695
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 7/24/2023 | 12/26/2023 | 12/18/2023 | 363605 | 357640 | 269886 | DSF0001014693, DSF0001014694, DSF0001014695
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 8/2/2024 | 8/1/2026 |  | 7820974 | 7298255 | 319856 | DSF0001014693, DSF0001014694, DSF0001014695
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/2/2024 | 8/1/2026 |  | 546101 | 112167 | 108769 | DSF0001014693, DSF0001014694, DSF0001014695
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2023 | 6/29/2023 | 3/8/2023 | 3784 | 1973 | 1973 | DSF0001034630
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/8/2023 | 8/31/2023 | 4/26/2023 | 17028 | 7892 | 7892 | DSF0001034630
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/19/2023 | 9/12/2024 |  | 219478 | 198038 | 97842 | DSF0001034630
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/19/2023 | 9/12/2024 |  | 133287 | 123898 | 119906 | DSF0001034630
21 | K329 | P.S. 329 - BROOKLYN | SCA IEH | PO18-ABATE, AND REPLACE 240 & 340 COMPLEX CORRIDOR FLOORS AND CAFETERIA.CORRIDOR FLOORS ARE ACM IN | Construction | Complete | 9/30/2024 | IEH | 10/9/2024 | IEH | 0 | 0 | SCA0000073456
21 | K329 | P.S. 329 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001033065
21 | K329 | P.S. 329 - BROOKLYN | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0000800381
21 | K329 | P.S. 329 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 195000 | 0 | DSF0001086089
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2/28/2022 | 7/18/2022 | 7/18/2022 | 1554220 | 1365208 | 1318194 | DSF0001034275
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 7/19/2022 | 3/3/2023 | 3/3/2023 | 6993990 | 4765971 | 4414888 | DSF0001034275
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 9/1/2023 | 9/3/2026 |  | 88201985 | 79151388 | 28796769 | DSF0001034275
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 9/1/2023 | 9/3/2026 |  | 12433760 | 6078513 | 1621095 | DSF0001034275
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 5/3/2022 | 5/3/2022 | 5/3/2022 | 21847 | 19313 | 19313 | DSF0001034275
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 5/4/2022 | 8/12/2022 | 10/18/2022 | 109235 | 56691 | 56691 | DSF0001034275
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Construction | In-Progress | 12/8/2022 | 3/7/2023 |  | 2457798 | 2333489 | 1179860 | DSF0001034275
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 12/8/2022 | 3/7/2023 |  | 152930 | 260476 | 232732 | DSF0001034275
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 5/28/2019 | 8/26/2019 | 2/18/2020 | 10270 | 37716 | 37716 | DSF0000896016
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2/18/2020 | 8/18/2020 | 7/8/2022 | 51350 | 240025 | 102425 | DSF0000896016
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 5/3/2023 | 5/1/2024 |  | 1155375 | 1051788 | 886518 | DSF0000896016
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 5/3/2023 | 5/1/2024 |  | 71890 | 96646 | 96646 | DSF0000896016
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 7/7/2022 | 11/22/2022 | 3/14/2023 | 19702 | 56015 | 56015 | DSF0001014857
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 3/23/2023 | 8/23/2023 | 10/18/2023 | 98512 | 133249 | 44141 | DSF0001014857
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 8/12/2024 | 2/2/2026 |  | 2216530 | 1988503 | 5044 | DSF0001014857
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 8/12/2024 | 2/2/2026 |  | 137917 | 20641 | 20262 | DSF0001014857
21 | K370 | K370 SPED - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113588
21 | K370 | K370 SPED - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113588
21 | K370 | K370 SPED - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113588
21 | K370 | K370 SPED - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113588
21 | K370 | K370 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 4521 | 0 | DSF0001086101
21 | K370 | K370 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1425000 | 0 | DSF0001112694
21 | K370 | K370 SPED - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/1/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001084892
21 | K400 | LEADERS HIGH SCHOOL - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY21 RESO A LIBRARY UPGRADE | Scope | Complete | 10/7/2021 | 2/11/2022 | 1/13/2022 | 0 | 32861 | 32861 | DSF0001007777, DSF0001008450
21 | K400 | LEADERS HIGH SCHOOL - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY21 RESO A LIBRARY UPGRADE | Design | Complete | 2/11/2022 | 6/28/2022 | 5/9/2022 | 104081 | 131455 | 131455 | DSF0001007777, DSF0001008450
21 | K400 | LEADERS HIGH SCHOOL - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY21 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 1526532 | 1526532 | 3654 | DSF0001007777, DSF0001008450
21 | K400 | LEADERS HIGH SCHOOL - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY21 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 104081 | 106478 | 29551 | DSF0001007777, DSF0001008450
21 | K400 | LIFE ACADEMY H.S. FILM & MUSIC - K | DIIT - RESOA | FY17 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 40000 | 0 | DSF0000845404
21 | K400 | INTERNATIONAL HIGH SCHOOL - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0 | DSF0001033548
21 | K400 | HIGH SCHOOL OF SPORTS MGMT- K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0 | DSF0001033550
21 | K400 | LEADERS HIGH SCHOOL - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112701
21 | K400 | LEADERS HIGH SCHOOL - K | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | Complete | 7/5/2022 | DOER | 4/11/2023 | DOER | 96930 | 95626 | DSF0000961267
21 | K400 | LEADERS HIGH SCHOOL - K | DOE - RESOA | FY21 RESO A ROOM RENOVATION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001008809
21 | K400 | KINGSBOROUGH EARLY COLLEGE SCHOOL | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001033573
21 | K400 | HIGH SCHOOL OF SPORTS MGMT- K | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | Complete | 9/9/2024 | DOER | 9/26/2024 | DOER | 23284 |  | DSF0001035555
21 | K400 | LIFE ACADEMY H.S. FILM & MUSIC - K | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/14/2024 | DOER |  | DOER | 550281 | 0 | DSF0001085337
21 | K400 | INTERNATIONAL HIGH SCHOOL - K | DOE - Skilled Trades | STAGE RIGGING & DRAPERY MODERNIZATION | Construction | In-Progress | 3/2/2021 | DOES |  | DOES | 180912 | 0 | DSF0001008583
21 | K400 | INTERNATIONAL HIGH SCHOOL - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/3/2024 | DOES | 9/18/2024 | DOES | 65832 |  | DSF0001084895
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | RESO A ATHLETIC FIELD | Scope | Complete | 8/1/2023 | 10/31/2023 | 8/7/2024 | 0 | 136476 | 88948 | DSF0000866361
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | RESO A ATHLETIC FIELD | Design | In-Progress | 8/13/2024 | 12/17/2024 |  | 60091 | 358801 | 171706 | DSF0000866361
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | RESO A ATHLETIC FIELD | Construction | PNS | PNS | PNS | PNS | 881335 | 881335 | 4864 | DSF0000866361
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | RESO A ATHLETIC FIELD | CM,F&E | PNS | PNS | PNS | PNS | 60091 | 60091 | 25945 | DSF0000866361
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD | Scope | Complete | 7/15/2024 | 10/15/2024 | 10/25/2024 | 0 | 434 | 434 | DSF0001112376
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD | Design | In-Progress | 10/25/2024 | 3/4/2025 |  | 24733 | 24299 | 1735 | DSF0001112376
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD | Construction | PNS | PNS | PNS | PNS | 362751 | 362751 | 0 | DSF0001112376
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD | CM,F&E | PNS | PNS | PNS | PNS | 24733 | 24733 | 4568 | DSF0001112376
21 | K406 | MIDWOOD HS - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / IDA PAVED AREAS- BLACKTOP / IDA HEATING PLANT UPGRADE | Scope | Complete | 4/6/2022 | 7/6/2022 | 4/21/2023 | 39483 | 81899 | 81899 | DSF0001111831, DSF0001083844, DSF0001083979
21 | K406 | MIDWOOD HS - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / IDA PAVED AREAS- BLACKTOP / IDA HEATING PLANT UPGRADE | Design | Complete | 4/24/2023 | 9/25/2023 | 11/1/2023 | 193391 | 211168 | 167748 | DSF0001111831, DSF0001083844, DSF0001083979
21 | K406 | MIDWOOD HS - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / IDA PAVED AREAS- BLACKTOP / IDA HEATING PLANT UPGRADE | Construction | PNS | PNS | PNS | PNS | 4002764 | 4002764 | 27042 | DSF0001111831, DSF0001083844, DSF0001083979
21 | K406 | MIDWOOD HS - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / IDA PAVED AREAS- BLACKTOP / IDA HEATING PLANT UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 306607 | 306607 | 63072 | DSF0001111831, DSF0001083844, DSF0001083979
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Scope | Complete | 9/1/2023 | 3/13/2024 | 2/16/2024 | 195112 | 153928 | 153928 | DSF0001085834, DSF0001111804, DSF0001093591
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Design | Complete | 2/28/2024 | 7/1/2024 | 5/1/2024 | 975558 | 443445 | 393763 | DSF0001085834, DSF0001111804, DSF0001093591
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Construction | PNS | PNS | PNS | PNS | 21950046 | 21950046 | 121484 | DSF0001085834, DSF0001111804, DSF0001093591
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | CM,F&E | PNS | PNS | PNS | PNS | 1365781 | 1365781 | 112853 | DSF0001085834, DSF0001111804, DSF0001093591
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE / FY20 RESO A CAFETERIA UPGRADE | Scope | Complete | 11/18/2020 | 11/4/2021 | 11/17/2021 | 0 | 34527 | 34527 | DSF0000913282, DSF0000913283
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE / FY20 RESO A CAFETERIA UPGRADE | Design | Complete | 11/17/2021 | 3/18/2022 | 10/12/2022 | 60716 | 97428 | 63213 | DSF0000913282, DSF0000913283
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE / FY20 RESO A CAFETERIA UPGRADE | Construction | Complete | 10/5/2023 | 8/29/2024 | 8/29/2024 | 890494 | 575547 | 457683 | DSF0000913282, DSF0000913283
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE / FY20 RESO A CAFETERIA UPGRADE | CM,F&E | Complete | 10/5/2023 | 8/29/2024 | 8/29/2024 | 315901 | 350781 | 338505 | DSF0000913282, DSF0000913283
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 35000 | 0 | DSF0000889781
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 9/19/2022 | DOES |  | DOES | 66214 | 0 | DSF0000866114
21 | K411 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | ATHLETIC FIELD BLEACHERS C OF O | Scope | Complete | 5/23/2023 | 9/22/2023 | 9/19/2023 | 11722 | 16643 | 16643 | DSF0001085093
21 | K411 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | ATHLETIC FIELD BLEACHERS C OF O | Design | Complete | 9/28/2023 | 4/5/2024 | 3/11/2024 | 52748 | 49376 | 8364 | DSF0001085093
21 | K411 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | ATHLETIC FIELD BLEACHERS C OF O | Construction | PNS | PNS | PNS | PNS | 679862 | 679862 | 10007 | DSF0001085093
21 | K411 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | ATHLETIC FIELD BLEACHERS C OF O | CM,F&E | PNS | PNS | PNS | PNS | 126009 | 126009 | 22954 | DSF0001085093
21 | K411 | ABRAHAM LINCOLN HS - BROOKLYN | DOE - RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | Construction | In-Progress | 2/1/2023 | DOER |  | DOER | 153043 | 0 | DSF0001033562
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA GYM PARTITION REPLACEMENT | Scope | Complete | 11/30/2021 | 4/4/2022 | 8/1/2022 | 20049 | 18757 | 18757 | SCA0000070740, DSF0001015709
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA GYM PARTITION REPLACEMENT | Design | Complete | 8/10/2022 | 12/28/2022 | 2/8/2023 | 96465 | 62701 | 59339 | SCA0000070740, DSF0001015709
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA GYM PARTITION REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 1843616 | 1843616 | 5918 | SCA0000070740, DSF0001015709
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA GYM PARTITION REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 168678 | 168678 | 46357 | SCA0000070740, DSF0001015709
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 5/30/2024 | 8/29/2024 | 11/26/2024 | 38601 | 44691 | 10291 | DSF0001094155
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | In-Progress | 12/23/2024 | 6/27/2025 |  | 180136 | 180136 | 41161 | DSF0001094155
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 2856443 | 2856443 | 0 | DSF0001094155
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 283071 | 283071 | 11867 | DSF0001094155
21 | K525 | EDWARD R. MURROW HS - K | Fast Track Projects | IDA GYM FLOOR REPLACEMENT @ K525 | Construction | In-Progress | 5/12/2022 | FTK |  | FTK | 1130122 | 962763 | SCA0000070483
21 | K525 | EDWARD R. MURROW HS - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/5/2024 | DIIR | 8/9/2024 | DIIR | 247000 | 95911 | DSF0001086140
21 | K525 | EDWARD R. MURROW HS - K | DOE - RESOA | FY14 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/25/2014 | DOER |  | DOER | 82000 | 0 | DSF0000798755
21 | K525 | EDWARD R. MURROW HS - K | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 210000 | 0 | DSF0001112730
21 | K525 | EDWARD R. MURROW HS - K | DOE - Skilled Trades | BCC PLAN REVIEW FOR DSF WORK @ K525 | Construction | In-Progress | 3/2/2021 | DOES |  | DOES | 12566 | 0 | SCA0000064030
21 | K525 | EDWARD R. MURROW HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/7/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084918
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | Scope | Complete | 10/30/2018 | 3/4/2021 | 12/17/2020 | 416999 | 392504 | 390214 | DSF0000873907, DSF0000873908, DSF0000873909, DSF0000960579, DSF0000942102, DSF0000990765
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | Design | Complete | 1/14/2021 | 9/14/2021 | 5/6/2021 | 2085001 | 901670 | 891375 | DSF0000873907, DSF0000873908, DSF0000873909, DSF0000960579, DSF0000942102, DSF0000990765
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | Construction | Complete | 7/6/2021 | 7/4/2024 | 7/4/2024 | 46912500 | 44102232 | 42015456 | DSF0000873907, DSF0000873908, DSF0000873909, DSF0000960579, DSF0000942102, DSF0000990765
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | CM,F&E | Complete | 7/6/2021 | 7/4/2024 | 7/4/2024 | 2919000 | 1699028 | 1685367 | DSF0000873907, DSF0000873908, DSF0000873909, DSF0000960579, DSF0000942102, DSF0000990765
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/7/2018 | 3/14/2019 | 3/22/2019 | 0 | 94916 | 94916 | DSF0000890796
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 3/27/2019 | 8/26/2019 | 5/15/2021 | 786600 | 912359 | 887192 | DSF0000890796
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/14/2021 | 9/13/2022 |  | 11536800 | 10605405 | 9251051 | DSF0000890796
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 9/14/2021 | 9/13/2022 |  | 786600 | 813106 | 776138 | DSF0000890796
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 1/4/2022 | DOER |  | DOER | 54647 | 0 | DSF0000914292
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 6/15/2022 | DOER |  | DOER | 51194 | 0 | DSF0001008645
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/5/2024 | DOER |  | DOER | 850 | 0 | DSF0001033101
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 11/4/2023 | DOER |  | DOER | 50000 | 0 | DSF0001086141
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/1/2024 | DOES |  | DOES | 789345 | 0 | DSF0001085730
21 | K541 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY21 RESO A ATHLETIC FIELD UPGRADE | Construction | In-Progress | 4/5/2021 | DOER |  | DOER | 2160726 | 0 | DSF0001008742
21 | K597 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Scope | Complete | 7/1/2021 | 10/29/2021 | 11/1/2021 | 544440 | 415448 | 415448 | DSF0000911868
21 | K597 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Design | Complete | 11/2/2021 | 4/15/2022 | 5/13/2022 | 2449980 | 791779 | 766706 | DSF0000911868
21 | K597 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 9/12/2022 | 9/3/2025 |  | 30896970 | 29173871 | 27403847 | DSF0000911868
21 | K597 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 9/12/2022 | 9/3/2025 |  | 4355520 | 3340943 | 2064222 | DSF0000911868
21 | K620 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | Scope | Complete | 9/10/2018 | 1/10/2019 | 2/4/2020 | 22790 | 25679 | 25679 | DSF0000890994
21 | K620 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | Design | Complete | 2/4/2020 | 6/24/2020 | 8/12/2022 | 113950 | 124214 | 122554 | DSF0000890994
21 | K620 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | Construction | In-Progress | 8/14/2023 | 8/12/2024 |  | 2563875 | 2412318 | 2155028 | DSF0000890994
21 | K620 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | CM,F&E | In-Progress | 8/14/2023 | 8/12/2024 |  | 159530 | 240051 | 228144 | DSF0000890994
21 | K620 | WILLIAM E. GRADY VOC HS - K | Fast Track Projects | FY21 RESO A CTF ROOM CONVERSION | Construction | In-Progress | 5/14/2024 | FTK |  | FTK | 397930 | 11052 | DSF0001008550
21 | K620 | WILLIAM E. GRADY VOC HS - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008447
21 | K620 | WILLIAM E. GRADY VOC HS - K | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 3/2/2022 | DOER |  | DOER | 115345 | 0 | DSF0000913288
21 | K620 | WILLIAM E. GRADY VOC HS - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/22/2023 | DOES | 7/26/2023 | DOES | 358758 |  | DSF0001035172
21 | K620 | WILLIAM E. GRADY VOC HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/9/2024 | DOES | 12/5/2024 | DOES | 65832 |  | DSF0001084927
21 | K662 | BROOKLYN DAILY DISCOVERY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/30/2024 | DOES | 9/17/2024 | DOES | 65832 | 9372 | DSF0001085456
21 | K672 | K000 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 12/6/2024 | IEH | 12/14/2024 | IEH | 0 | 0 | SCA0000073678
21 | K687 | BROOKLYN DAILY DISCOVERY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/13/2024 | DOES | 8/26/2024 | DOES | 50832 | 7985 | DSF0001085459
21 | K721 | BKLYN STUDIO SEC. SCL - BROOKLYN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035586
21 | K721 | BKLYN STUDIO SEC. SCL - BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086146
21 | K721 | BKLYN STUDIO SEC. SCL - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112735
21 | K721 | BKLYN STUDIO SEC. SCL - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112736
21 | K721 | BKLYN STUDIO SEC. SCL - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/23/2024 | DOES | 12/17/2024 | DOES | 65832 |  | DSF0001084931
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Scope | Complete | 10/24/2018 | 3/14/2019 | 10/22/2019 | 48970 | 118462 | 118462 | DSF0000874161, DSF0001032952, DSF0001032951
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Design | Complete | 10/22/2019 | 3/26/2020 | 5/17/2023 | 238879 | 386553 | 357689 | DSF0000874161, DSF0001032952, DSF0001032951
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Construction | In-Progress | 10/4/2023 | 10/2/2025 |  | 4858162 | 4506983 | 1529612 | DSF0000874161, DSF0001032952, DSF0001032951
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | CM,F&E | In-Progress | 10/4/2023 | 10/2/2025 |  | 387585 | 326375 | 323877 | DSF0000874161, DSF0001032952, DSF0001032951
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 11/1/2019 | 2/5/2020 | 3/31/2020 | 22680 | 40107 | 40107 | DSF0000897008
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 3/31/2020 | 9/30/2020 | 6/30/2020 | 113400 | 208080 | 208080 | DSF0000897008
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 1/24/2022 | 4/18/2023 |  | 2551500 | 2404668 | 2104356 | DSF0000897008
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 1/24/2022 | 4/18/2023 |  | 158760 | 162456 | 162456 | DSF0000897008
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/17/2023 | 6/20/2023 | 3/2/2023 | 4044 | 1176 | 1176 | DSF0001034620
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/2/2023 | 8/25/2023 | 5/3/2023 | 18196 | 4704 | 4704 | DSF0001034620
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/20/2023 | 11/18/2024 |  | 234530 | 213569 | 152081 | DSF0001034620
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/20/2023 | 11/18/2024 |  | 105372 | 106793 | 82198 | DSF0001034620
21 | K722 | K721 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A KITCHEN UPGRADE | Scope | Complete | 2/2/2022 | 6/17/2022 | 8/10/2022 | 0 | 31034 | 31034 | DSF0001033606
21 | K722 | K721 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A KITCHEN UPGRADE | Design | Complete | 8/11/2022 | 1/17/2023 | 2/2/2023 | 150000 | 99912 | 94970 | DSF0001033606
21 | K722 | K721 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 2200000 | 2200000 | 45393 | DSF0001033606
21 | K722 | K721 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 27445 | DSF0001033606
21 | K722 | K721 SPED - BROOKLYN | Fast Track Projects | LSP- INTERIOR SPACES | Construction | In-Progress | 10/21/2022 | FTK |  | FTK | 225280 | 200529 | DSF0001034203
21 | K722 | K721 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033604
21 | K722 | K721 SPED - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/27/2024 | DIIR | 9/30/2024 | DIIR | 125000 | 115122 | DSF0001086147
21 | K722 | K721 SPED - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 4/26/2021 | DOER |  | DOER | 139947 | 0 | DSF0000913290
21 | K722 | K721 SPED - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/3/2024 | DOES | 7/11/2024 | DOES | 65832 |  | DSF0001084932
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113596
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113596
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113596
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113596
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001034956
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001112737
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/29/2024 | DOES | 9/20/2024 | DOES | 50832 |  | DSF0001085462
21 | K787 | BROOKLYN DAILY DISCOVERY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/6/2023 | DOES | 11/8/2024 | DOES | 50832 |  | DSF0001085472
21 | KBUH | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Scope | Complete | 3/2/2021 | 8/4/2022 | 11/2/2022 | 18945 | 11197 | 4421 | DSF0001008779, DSF0001009218
21 | KBUH | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Design | Complete | 11/2/2022 | 3/1/2023 | 4/26/2023 | 94132 | 76182 | 14120 | DSF0001008779, DSF0001009218
21 | KBUH | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Construction | In-Progress | 11/13/2023 | 5/5/2025 |  | 2066842 | 1945726 | 874381 | DSF0001008779, DSF0001009218
21 | KBUH | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | CM,F&E | In-Progress | 11/13/2023 | 5/5/2025 |  | 137044 | 202412 | 99437 | DSF0001008779, DSF0001009218
22 | K014 | I.S. 14 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/6/2023 | 11/21/2023 | 2/23/2024 | 31839 | 90450 | 90431 | DSF0001060336, DSF0001088082
22 | K014 | I.S. 14 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/26/2024 | 7/26/2024 | 5/15/2024 | 149793 | 190998 | 148412 | DSF0001060336, DSF0001088082
22 | K014 | I.S. 14 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 10/21/2024 | 4/8/2027 |  | 2557135 | 2314816 | 10809 | DSF0001060336, DSF0001088082
22 | K014 | I.S. 14 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 10/21/2024 | 4/8/2027 |  | 293383 | 78288 | 76396 | DSF0001060336, DSF0001088082
22 | K014 | I.S. 14 - BROOKLYN | DOE - RESOA | FY13 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 63000 | 0 | DSF0000754664
22 | K014 | I.S. 14 - BROOKLYN | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 7/16/2021 | DOER |  | DOER | 291871 | 0 | DSF0000800464
22 | K014 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0 | DSF0001112518
22 | K014 | I.S. 14 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112519
22 | K014 | I.S. 14 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/8/2023 | DOES | 11/6/2023 | DOES | 362752 | 326900 | DSF0001035093
22 | K014 | I.S. 14 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/19/2024 | DOES | 8/26/2024 | DOES | 65832 | 10437 | DSF0001084723
22 | K014 | I.S. 14 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 2/28/2024 | DOES |  | DOES | 573921 | 256198 | DSF0001088076
22 | K042 | THE JOAN SNOW PRE-K CENTER | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035391
22 | K042 | THE JOAN SNOW PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/17/2024 | DOES | 8/28/2024 | DOES | 65832 |  | DSF0001085440
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 7/24/2019 | 12/3/2019 | 1/10/2020 | 104430 | 136077 | 136077 | DSF0000891902, DSF0000891903, DSF0000891904
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/15/2020 | 6/16/2020 | 6/26/2020 | 522150 | 537269 | 530155 | DSF0000891902, DSF0000891903, DSF0000891904
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 4/14/2021 | 1/3/2023 |  | 11748374 | 10933493 | 9346059 | DSF0000891902, DSF0000891903, DSF0000891904
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 4/14/2021 | 1/3/2023 |  | 731009 | 1039037 | 1031676 | DSF0000891902, DSF0000891903, DSF0000891904
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 3/3/2022 | 7/1/2022 | 7/15/2022 | 17405 | 29626 | 13206 | DSF0001035130
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 7/15/2022 | 7/15/2022 | 7/15/2022 | 78324 | 37813 | 529 | DSF0001035130
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Construction | PNS | PNS | PNS | PNS | 1009505 | 1009505 | 47721 | DSF0001035130
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | CM,F&E | PNS | PNS | PNS | PNS | 187107 | 187107 | 13167 | DSF0001035130
22 | K052 | P.S. 52 - BROOKLYN | SCA Emergency Response | SIDEWALK BRIDGING | Construction | In-Progress | 2/25/2013 | EMER |  | EMER | 108886 | 108886 | SCA0000025072
22 | K052 | P.S. 52 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR ACOUSTICAL WALL PLASTER IN AUDITORIUM WINDOW WALLS #2 AND #4 1950 WING WILL BE | Construction | In-Progress | 3/26/2024 | IEH |  | IEH | 0 | 0 | SCA0000072863
22 | K052 | P.S. 52 - BROOKLYN | DOE - RESOA | FY13 RESO A ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | DOER | 22102 | 0 | DSF0000754706
22 | K052 | P.S. 52 - BROOKLYN | DOE - RESOA | FY22 RESO A PLAYGROUNDS | Construction | In-Progress | 6/6/2022 | DOER |  | DOER | 50000 | 0 | DSF0001034955
22 | K052 | P.S. 52 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/18/2022 | DOES |  | DOES | 75026 | 0 | DSF0001009175
22 | K063 | THE JOAN SNOW PRE-K CENTER | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035399
22 | K078 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 4/29/2022 | 9/29/2022 | 7/7/2022 | 131097 | 56303 | 56303 | DSF0001010620, DSF0000798425, DSF0001010621
22 | K078 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 7/11/2022 | 12/12/2022 | 11/17/2022 | 645809 | 311101 | 231933 | DSF0001010620, DSF0000798425, DSF0001010621
22 | K078 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 7/18/2024 | 1/3/2027 |  | 13693621 | 12460782 | 630574 | DSF0001010620, DSF0000798425, DSF0001010621
22 | K078 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 7/18/2024 | 1/3/2027 |  | 990258 | 258386 | 249229 | DSF0001010620, DSF0000798425, DSF0001010621
22 | K078 | I.S. 78 - BROOKLYN | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 250000 | 250000 | 0 | DSF0001112556
22 | K078 | I.S. 78 - BROOKLYN | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 250000 | 250000 | 0 | DSF0001112555
22 | K078 | I.S. 78 - BROOKLYN | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 11/2/2024 | FTK |  | FTK | 111829 | 79085 | DSF0001112107
22 | K078 | I.S. 78 - BROOKLYN | Fast Track Projects | LSP HOT WATER HEATER & VACUUM PUMP | Construction | In-Progress | 9/21/2018 | FTK |  | FTK | 908481 | 903518 | DSF0000888816
22 | K078 | I.S. 78 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/2/2024 | DOES | 12/11/2024 | DOES | 65832 |  | DSF0001084732
22 | K078 | I.S. 78 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/2/2024 | DOES |  | DOES | 492147 | 0 | DSF0001085715
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/6/2023 | 6/5/2024 | 4/12/2024 | 0 | 19575 | 19575 | DSF0001085979, DSF0001087007
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 4/23/2024 | 8/26/2024 | 8/13/2024 | 45000 | 54995 | 53943 | DSF0001085979, DSF0001087007
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 25431 | DSF0001085979, DSF0001087007
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 53013 | 21515 | DSF0001085979, DSF0001087007
22 | K119 | P.S. 119 - BROOKLYN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001033476
22 | K119 | P.S. 119 - BROOKLYN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 143844 | 0 | DSF0001035428
22 | K119 | P.S. 119 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/8/2024 | DOES | 10/14/2024 | DOES | 65832 | 378 | DSF0001084045
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 5/15/2023 | 9/29/2023 | 9/26/2023 | 10606 | 18414 | 18414 | DSF0001062173
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 10/5/2023 | 3/12/2024 | 3/19/2024 | 47728 | 37303 | 36714 | DSF0001062173
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 615165 | 615165 | 32252 | DSF0001062173
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 114018 | 114018 | 15924 | DSF0001062173
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/25/2023 | 5/25/2023 | 6/5/2023 | 0 | 13873 | 13873 | DSF0001035441, DSF0001035442
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 6/5/2023 | 10/19/2023 | 10/17/2023 | 48600 | 58018 | 53237 | DSF0001035441, DSF0001035442
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/8/2024 | 4/2/2025 |  | 712800 | 679514 | 6014 | DSF0001035441, DSF0001035442
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 5/8/2024 | 4/2/2025 |  | 48600 | 60111 | 10215 | DSF0001035441, DSF0001035442
22 | K139 | P.S. 139 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/9/2022 | EMER |  | EMER | 148276 | 89902 | SCA0000070852
22 | K139 | P.S. 139 - BROOKLYN | DOE - RESOA | RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113818
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/20/2015 | 1/22/2016 | 12/21/2015 | 18645 | 32865 | 32865 | DSF0000803297
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 1/28/2016 | 7/29/2016 | 6/3/2016 | 74580 | 131934 | 128669 | DSF0000803297
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 1/8/2018 | 11/3/2018 |  | 1398375 | 2252864 | 1966584 | DSF0000803297
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 1/8/2018 | 11/3/2018 |  | 87010 | 951468 | 893276 | DSF0000803297
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | HVAC UPGRADE / BMS UPGRADE | Scope | Complete | 11/10/2022 | 4/17/2023 | 11/15/2023 | 84809 | 104107 | 103950 | DSF0001011666, DSF0001111841
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | HVAC UPGRADE / BMS UPGRADE | Design | Complete | 11/28/2023 | 4/30/2024 | 8/26/2024 | 424041 | 332720 | 323046 | DSF0001011666, DSF0001111841
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | HVAC UPGRADE / BMS UPGRADE | Construction | PNS | PNS | PNS | PNS | 9540915 | 9540915 | 19189 | DSF0001011666, DSF0001111841
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | HVAC UPGRADE / BMS UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 593657 | 593657 | 73183 | DSF0001011666, DSF0001111841
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS / FLOOD ELIMINATION / PAVED AREA- CONCRETE | Scope | Complete | 6/12/2023 | 12/11/2023 | 11/3/2023 | 369898 | 320103 | 318800 | DSF0001062349, DSF0001062351, DSF0001111792, DSF0001111791, DSF0001111790, DSF0001111789
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS / FLOOD ELIMINATION / PAVED AREA- CONCRETE | Design | In-Progress | 8/15/2024 | 1/21/2025 |  | 1840084 | 1840084 | 527429 | DSF0001062349, DSF0001062351, DSF0001111792, DSF0001111791, DSF0001111790, DSF0001111789
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS / FLOOD ELIMINATION / PAVED AREA- CONCRETE | Construction | PNS | PNS | PNS | PNS | 40588577 | 40588577 | 10588 | DSF0001062349, DSF0001062351, DSF0001111792, DSF0001111791, DSF0001111790, DSF0001111789
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS / FLOOD ELIMINATION / PAVED AREA- CONCRETE | CM,F&E | PNS | PNS | PNS | PNS | 2659798 | 2659798 | 106254 | DSF0001062349, DSF0001062351, DSF0001111792, DSF0001111791, DSF0001111790, DSF0001111789
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/25/2023 | 4/25/2023 | 4/12/2023 | 0 | 30079 | 30079 | DSF0001035446
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 4/21/2023 | 9/7/2023 | 9/1/2023 | 33000 | 47090 | 42898 | DSF0001035446
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 484000 | 555011 | 500 | DSF0001035446
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 33000 | 37842 | 4714 | DSF0001035446
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/8/2023 | 4/11/2024 | 4/9/2024 | 0 | 16375 | 16375 | DSF0001085999
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 4/16/2024 | 8/30/2024 |  | 87000 | 70625 | 31124 | DSF0001085999
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 1276000 | 1276000 | 500 | DSF0001085999
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 87000 | 87000 | 13713 | DSF0001085999
22 | K152 | P.S. 152 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ K152 | Construction | In-Progress | 7/10/2023 | EMER |  | EMER | 74083 | 72376 | SCA0000072115
22 | K152 | P.S. 315 - BROOKLYN | SCA IEH | PO18-ABATE THE MARKED AREAS IN 2ND FLOOR BATHROOM FULL PENETRATION THROUGH FLOOR SLAB IS NEEDED FOR | Construction | Complete | 12/5/2024 | IEH | 12/26/2024 | IEH | 0 | 0 | SCA0000073672
22 | K152 | P.S. 315 - BROOKLYN | Fast Track Projects | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 9/14/2023 | FTK |  | FTK | 112509 | 106929 | DSF0001033542
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/7/2020 | DOER |  | DOER | 38382 | 0 | DSF0000913226
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/16/2022 | DOER |  | DOER | 132131 | 0 | DSF0001008310
22 | K152 | P.S. 152 - BROOKLYN | DOE - RESOA | FY20 RESO A DIGITAL SIGN | Construction | In-Progress | 10/11/2021 | DOER |  | DOER | 38760 | 0 | DSF0001008813
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001035448
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 5524 | 0 | DSF0001085998
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112587
22 | K152 | P.S. 315 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/13/2024 | DOES | 11/25/2024 | DOES | 65832 | 8178 | DSF0001084063
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 3/26/2021 | 11/22/2022 | 7/19/2023 | 237237 | 396354 | 389448 | DSF0001008653, DSF0000987593, DSF0001012375, DSF0001012376, DSF0001085832
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 8/21/2023 | 1/25/2024 | 4/4/2024 | 1167416 | 864110 | 634841 | DSF0001008653, DSF0000987593, DSF0001012375, DSF0001012376, DSF0001085832
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 7/18/2024 | 1/3/2027 |  | 24643557 | 22318449 | 387269 | DSF0001008653, DSF0000987593, DSF0001012375, DSF0001012376, DSF0001085832
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 7/18/2024 | 1/3/2027 |  | 1801406 | 370761 | 342236 | DSF0001008653, DSF0000987593, DSF0001012375, DSF0001012376, DSF0001085832
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112601
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001112601
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1760000 | 1760000 | 0 | DSF0001112601
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001112601
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113573
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113573
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113573
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113573
22 | K193 | P.S. 193 - BROOKLYN | Fast Track Projects | LSP PVI DOMESTIC WATER HEATER | Construction | In-Progress | 5/7/2019 | FTK |  | FTK | 251347 | 145443 | DSF0000893807
22 | K193 | P.S. 193 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 534000 | 0 | DSF0001033032
22 | K193 | P.S. 193 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001086017
22 | K193 | P.S. 193 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 3/23/2022 | DOER |  | DOER | 604523 | 0 | DSF0001008311
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2/26/2021 | 7/13/2021 | 11/29/2021 | 109900 | 96621 | 96621 | DSF0001008565
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/29/2021 | 5/17/2022 | 2/8/2023 | 549500 | 372616 | 264278 | DSF0001008565
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 9/18/2023 | 11/5/2025 |  | 12363750 | 11418956 | 1577974 | DSF0001008565
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 9/18/2023 | 11/5/2025 |  | 771474 | 612514 | 605962 | DSF0001008565
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112602
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112602
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001112602
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112602
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113574
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113574
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113574
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113574
22 | K194 | P.S. 194 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 50000 | 49812 | DSF0001086018
22 | K194 | P.S. 194 - BROOKLYN | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | Complete | 12/21/2018 | DOER | 12/17/2021 | DOER | 488768 | 493220 | DSF0000890761
22 | K194 | P.S. 194 - BROOKLYN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/15/2024 | DOER |  | DOER | 269352 | 0 | DSF0001033499
22 | K195 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/2/2021 | 10/18/2021 | 12/22/2021 | 19147 | 30068 | 30068 | DSF0000939151
22 | K195 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 12/22/2021 | 5/25/2022 | 5/5/2022 | 95734 | 80836 | 79063 | DSF0000939151
22 | K195 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 1/9/2023 | 4/2/2024 |  | 2154024 | 1946000 | 1283134 | DSF0000939151
22 | K195 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 1/9/2023 | 4/2/2024 |  | 134028 | 425175 | 416649 | DSF0000939151
22 | K195 | P.S. 195 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 8/23/2021 | EMER |  | EMER | 15642 | 15642 | SCA0000070421
22 | K195 | P.S. 195 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112604
22 | K195 | P.S. 195 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 210000 | 0 | DSF0001112603
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | Scope | Complete | 11/28/2023 | 4/15/2024 | 2/8/2024 | 13400 | 21201 | 21201 | DSF0001111959
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | Design | Complete | 2/12/2024 | 7/15/2024 | 5/14/2024 | 67000 | 77326 | 66211 | DSF0001111959
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | Construction | In-Progress | 8/5/2024 | 8/4/2025 |  | 1507500 | 1478035 | 26605 | DSF0001111959
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | CM,F&E | In-Progress | 8/5/2024 | 8/4/2025 |  | 93800 | 192296 | 192187 | DSF0001111959
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112605
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112605
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001112605
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001112605
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113575
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113575
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113575
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113575
22 | K197 | P.S. 197 - BROOKLYN | SCA IEH | PO18-ABATE FLOORING / ROOM 401/ CONCRETE SUBFLOORING LISTED POSITIVE FOR ACM IN ADHERA BOOK. LOOKING | Construction | Complete | 3/19/2024 | IEH | 8/15/2024 | IEH | 0 | 0 | SCA0000072827
22 | K197 | P.S. 197 - BROOKLYN | SCA IEH | PO18-ABATE FLOOR TILES IN ROOMS 111 AND ROOM 263 INCLUDING SUBFLOOR | Construction | Complete | 4/8/2024 | IEH | 7/13/2024 | IEH | 0 | 0 | SCA0000072899
22 | K197 | P.S. 197 - BROOKLYN | SCA IEH | PO18-ABATE CONCRETE SUB FLOOR AND FELT PAPER UDER THE FLOORING IN ROOM 314 FOR THE REMOVAL OF THE PO | Construction | Complete | 8/23/2024 | IEH | 8/30/2024 | IEH | 0 | 0 | SCA0000073312
22 | K197 | P.S. 197 - BROOKLYN | SCA IEH | PO18-PERFORE SUPPLEMENTAL QC SAMPLING OF WALL PLASTER IN ROOM 405 ABATE IF NECESSARY : WALL PLASTE | Construction | In-Progress | 12/11/2024 | IEH |  | IEH | 0 | 0 | SCA0000073693
22 | K197 | P.S. 197 - BROOKLYN | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 11/21/2024 | FTK |  | FTK | 41273 | 25998 | DSF0001087421
22 | K197 | P.S. 197 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001086021
22 | K197 | P.S. 197 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112606
22 | K197 | P.S. 197 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 4/12/2019 | DOER |  | DOER | 119721 | 0 | DSF0000890651
22 | K197 | P.S. 197 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 9/23/2021 | DOER |  | DOER | 90313 | 0 | DSF0001008342
22 | K197 | P.S. 197 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 128880 | 0 | DSF0001035467
22 | K197 | P.S. 197 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 7/1/2022 | DOES | 9/26/2022 | DOES | 62704 | 61860 | DSF0000866109
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112607
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001112607
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001112607
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001112607
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113576
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113576
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113576
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113576
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY24 RESO A (MA) CAFETERIA UPGRADE | Scope | Complete | 11/21/2023 | 3/26/2024 | 3/29/2024 | 0 | 20528 | 20465 | DSF0001086022
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY24 RESO A (MA) CAFETERIA UPGRADE | Design | In-Progress | 4/17/2024 | 9/3/2024 |  | 77039 | 59695 | 35497 | DSF0001086022
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY24 RESO A (MA) CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 1129901 | 1129901 | 18226 | DSF0001086022
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY24 RESO A (MA) CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 77039 | 77039 | 21111 | DSF0001086022
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A (MA) CAFETERIA UPGRADE | Scope | Complete | 4/9/2024 | 7/11/2024 | 6/10/2024 | 0 | 0 | 11564 | DSF0001087017
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A (MA) CAFETERIA UPGRADE | Design | In-Progress | 6/17/2024 | 10/16/2024 |  | 961 | 961 | 6444 | DSF0001087017
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A (MA) CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 14099 | 14099 | 0 | DSF0001087017
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A (MA) CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 961 | 961 | 2732 | DSF0001087017
22 | K198 | P.S. 198 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033500
22 | K198 | P.S. 198 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/2/2024 | DIIR |  | DIIR | 100000 | 0 | DSF0001035468
22 | K198 | P.S. 198 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001086023
22 | K198 | P.S. 198 - BROOKLYN | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 8/17/2020 | DOES | 9/15/2020 | DOES | 979 | 9473 | DSF0000960905
22 | K203 | P.S. 203 - BROOKLYN | DIIT - RESOA | FY14 RESO A SECURITY CAMERAS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 180000 | 0 | DSF0000798932
22 | K203 | P.S. 203 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112613
22 | K203 | P.S. 203 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/6/2023 | DOER |  | DOER | 313052 | 0 | DSF0001008329
22 | K203 | P.S. 203 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035470
22 | K203 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112612
22 | K203 | P.S. 203 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/11/2020 | DOES | 8/12/2021 | DOES | 185715 | 189174 | DSF0000912963
22 | K206 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | Scope | Complete | 5/10/2022 | 8/26/2022 | 8/26/2022 | 1192000 | 1136974 | 857577 | DSF0000911846
22 | K206 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | Design | Complete | 8/29/2022 | 3/3/2023 | 4/12/2023 | 5364000 | 2997864 | 1624370 | DSF0000911846
22 | K206 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | Construction | In-Progress | 2/21/2024 | 9/3/2026 |  | 67646000 | 60711972 | 3912800 | DSF0000911846
22 | K206 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | CM,Art,F&E | In-Progress | 2/21/2024 | 9/3/2026 |  | 9536000 | 4457194 | 1049004 | DSF0000911846
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING-EXISTING BUILDING-INTERIOR RENOVATIONS/PROGRAM ACCESSIBILITY | Scope | Complete | 9/21/2022 | 1/26/2023 | 3/13/2023 | 91591 | 97679 | 62772 | DSF0000911846, DSF0000911846, DSF0000911846
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING-EXISTING BUILDING-INTERIOR RENOVATIONS/PROGRAM ACCESSIBILITY | Design | Complete | 3/15/2023 | 8/15/2023 | 10/23/2023 | 455057 | 240253 | 228766 | DSF0000911846, DSF0000911846, DSF0000911846
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING-EXISTING BUILDING-INTERIOR RENOVATIONS/PROGRAM ACCESSIBILITY | Construction | PNS | PNS | PNS | PNS | 9987974 | 9987974 | 15721 | DSF0000911846, DSF0000911846, DSF0000911846
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING-EXISTING BUILDING-INTERIOR RENOVATIONS/PROGRAM ACCESSIBILITY | CM,F&E | PNS | PNS | PNS | PNS | 662886 | 662886 | 48289 | DSF0000911846, DSF0000911846, DSF0000911846
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/14/2023 | 6/14/2023 | 3/2/2023 | 3779 | 1385 | 1385 | DSF0001034646
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/2/2023 | 8/25/2023 | 5/3/2023 | 17007 | 5539 | 5539 | DSF0001034646
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/20/2023 | 11/18/2024 |  | 219208 | 200360 | 149438 | DSF0001034646
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/20/2023 | 11/18/2024 |  | 100584 | 106577 | 79582 | DSF0001034646
22 | K206 | P.S. 206 - BROOKLYN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/8/2020 | DOER |  | DOER | 406745 | 0 | DSF0000890764
22 | K206 | P.S. 206 - BROOKLYN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/30/2023 | DOER |  | DOER | 457374 | 0 | DSF0001008339
22 | K206 | P.S. 206 - BROOKLYN | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 456428 | 0 | DSF0001033502
22 | K206 | P.S. 206 - BROOKLYN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/1/2024 | DOER |  | DOER | 443040 | 0 | DSF0001035472
22 | K206 | P.S. 206 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/16/2024 | DOES | 9/24/2024 | DOES | 65832 |  | DSF0001084603
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/7/2021 | 9/22/2021 | 11/16/2021 | 158000 | 186923 | 177135 | DSF0000987895, DSF0000987898, DSF0001034923
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/17/2021 | 4/21/2022 | 5/11/2022 | 790000 | 572754 | 572754 | DSF0000987895, DSF0000987898, DSF0001034923
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 9/12/2022 | 9/10/2024 |  | 17775000 | 17144339 | 14099703 | DSF0000987895, DSF0000987898, DSF0001034923
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 9/12/2022 | 9/10/2024 |  | 1107166 | 1077188 | 1059524 | DSF0000987895, DSF0000987898, DSF0001034923
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/15/2023 | 6/15/2023 | 3/13/2023 | 4077 | 696 | 696 | DSF0001034579
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/13/2023 | 9/6/2023 | 5/3/2023 | 18346 | 2785 | 2785 | DSF0001034579
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/20/2023 | 11/18/2024 |  | 236463 | 215840 | 143182 | DSF0001034579
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/20/2023 | 11/18/2024 |  | 100721 | 111525 | 104039 | DSF0001034579
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/21/2024 | 7/8/2024 | 8/22/2024 | 0 | 19930 | 19930 | DSF0001086024
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 8/30/2024 | 2/5/2025 |  | 60000 | 40070 | 3370 | DSF0001086024
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001086024
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 28558 | DSF0001086024
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/21/2024 | 6/21/2024 | 8/22/2024 | 0 | 0 | 0 | DSF0001087018
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 9/20/2024 | 1/28/2025 |  | 7365 | 7365 | 0 | DSF0001087018
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 108013 | 108013 | 0 | DSF0001087018
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 7365 | 7365 | 3145 | DSF0001087018
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/10/2019 | 4/9/2020 | 6/9/2021 | 0 | 0 | 19953 | DSF0000867249, DSF0000960572
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 6/9/2021 | 10/22/2021 | 5/12/2022 | 59511 | 57155 | 102213 | DSF0000867249, DSF0000960572
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | Complete | 2/27/2023 | 1/22/2024 | 8/5/2024 | 872832 | 834443 | 642367 | DSF0000867249, DSF0000960572
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 2/27/2023 | 1/22/2024 | 8/5/2024 | 59511 | 59511 | 126587 | DSF0000867249, DSF0000960572
22 | K207 | P.S. 207 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/9/2020 | FTK |  | FTK | 838668 | 830663 | DSF0000912683
22 | K207 | P.S. 207 - BROOKLYN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/28/2020 | DOER |  | DOER | 12445 | 0 | DSF0000913242
22 | K207 | P.S. 207 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/23/2024 | DOES | 10/7/2024 | DOES | 65832 |  | DSF0001084604
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP | HVAC BMS UPGRADE / HVAC UPGRADE | Scope | Complete | 9/12/2023 | 2/15/2024 | 10/31/2024 | 137898 | 51427 | 3427 | DSF0001063587, DSF0001118928
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP | HVAC BMS UPGRADE / HVAC UPGRADE | Design | In-Progress | 11/27/2024 | 5/1/2025 |  | 647627 | 647627 | 13707 | DSF0001063587, DSF0001118928
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP | HVAC BMS UPGRADE / HVAC UPGRADE | Construction | PNS | PNS | PNS | PNS | 10678642 | 10678642 | 0 | DSF0001063587, DSF0001118928
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP | HVAC BMS UPGRADE / HVAC UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 1007142 | 1007142 | 4660 | DSF0001063587, DSF0001118928
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 6/7/2024 | 9/9/2024 | 12/18/2024 | 15306 | 15490 | 1311 | DSF0001112128
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | PNS | PNS | PNS | PNS | 76529 | 76529 | 5245 | DSF0001112128
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 1721903 | 1721903 | 0 | DSF0001112128
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 107141 | 107141 | 1995 | DSF0001112128
22 | K217 | P.S. 217 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000890071
22 | K217 | P.S. 217 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 9/7/2022 | DOER | 10/24/2022 | DOER | 172974 | 208855 | DSF0000913245
22 | K217 | P.S. 217 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001112622
22 | K217 | P.S. 217 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | Complete | 4/11/2022 | DOES | 9/26/2022 | DOES | 169282 | 63509 | DSF0000866111
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/24/2023 | 11/22/2023 | 8/2/2023 | 4870 | 2135 | 2135 | DSF0001035011
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/1/2023 | 21915 | 8540 | 8540 | DSF0001035011
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 3/1/2024 | 1/24/2025 |  | 282460 | 268431 | 79012 | DSF0001035011
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 3/1/2024 | 1/24/2025 |  | 131371 | 112822 | 59590 | DSF0001035011
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 9/2/2021 | 12/6/2021 | 3/2/2022 | 0 | 30431 | 30431 | DSF0001008330
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/4/2023 | 12/21/2023 | 2/12/2024 | 60000 | 72019 | 61290 | DSF0001008330
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 7/31/2024 | 6/25/2025 |  | 880000 | 601198 | 33087 | DSF0001008330
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 7/31/2024 | 6/25/2025 |  | 60000 | 58441 | 15082 | DSF0001008330
22 | K222 | P.S. 222 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112623
22 | K222 | P.S. 222 - BROOKLYN | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 297157 | 0 | DSF0000890766
22 | K222 | P.S. 222 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 11/4/2022 | DOER | 12/21/2022 | DOER | 131034 | 167309 | DSF0000913246
22 | K222 | P.S. 222 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | Complete | 12/7/2020 | DOES | 7/9/2021 | DOES | 106097 |  | DSF0000960488
22 | K222 | P.S. 222 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/20/2023 | DOES |  | DOES | 612137 | 423088 | DSF0001063688
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | Scope | Complete | 3/24/2021 | 7/23/2021 | 10/14/2021 | 27406 | 50420 | 38631 | DSF0001008580
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | Design | Complete | 12/1/2021 | 5/4/2022 | 9/23/2022 | 137029 | 220810 | 212032 | DSF0001008580
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | Construction | In-Progress | 7/10/2023 | 4/9/2025 |  | 3083153 | 2947202 | 1983618 | DSF0001008580
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | CM,F&E | In-Progress | 7/10/2023 | 4/9/2025 |  | 191841 | 413566 | 409308 | DSF0001008580
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/18/2024 | 11/4/2024 | 9/19/2024 | 271186 | 117953 | 117555 | DSF0001091641, DSF0001091642, DSF0001113796, DSF0001119298
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | In-Progress | 11/13/2024 | 4/17/2025 |  | 1250466 | 1250466 | 226650 | DSF0001091641, DSF0001091642, DSF0001113796, DSF0001119298
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 19694806 | 19694806 | 16596 | DSF0001091641, DSF0001091642, DSF0001113796, DSF0001119298
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 2156339 | 2156339 | 20473 | DSF0001091641, DSF0001091642, DSF0001113796, DSF0001119298
22 | K234 | I.S. 234 - BROOKLYN | DOE - RESOA | FY18 RESO A LIBRARY UPGRADE | Construction | In-Progress | 12/27/2021 | DOER |  | DOER | 52410 | 0 | DSF0000867187
22 | K234 | I.S. 234 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 12/3/2021 | DOER |  | DOER | 130678 | 0 | DSF0001008341
22 | K234 | I.S. 234 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 9/6/2022 | DOER |  | DOER | 423372 | 0 | DSF0001008343
22 | K234 | I.S. 234 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 11/5/2021 | DOES |  | DOES | 154677 | 0 | DSF0001008680
22 | K234 | I.S. 234 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 6/28/2023 | DOES |  | DOES | 508295 | 0 | DSF0001034210
22 | K234 | I.S. 234 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/16/2024 | DOES | 7/25/2024 | DOES | 65832 |  | DSF0001084752
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 5/30/2019 | 10/15/2019 | 11/1/2019 | 177065 | 113328 | 113328 | DSF0000912355, DSF0000960562
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 12/18/2019 | 6/5/2020 | 11/4/2021 | 876028 | 642246 | 572737 | DSF0000912355, DSF0000960562
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | Complete | 6/6/2022 | 6/4/2024 | 8/20/2024 | 18906655 | 17631714 | 17037483 | DSF0000912355, DSF0000960562
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | Complete | 6/6/2022 | 6/4/2024 | 8/20/2024 | 1441343 | 1735631 | 1717317 | DSF0000912355, DSF0000960562
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/7/2023 | 5/24/2023 | 2/15/2023 | 5600 | 3171 | 3171 | DSF0001034592
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/15/2023 | 8/11/2023 | 5/2/2023 | 25200 | 12684 | 12684 | DSF0001034592
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/28/2023 | 8/22/2024 |  | 324800 | 292530 | 263855 | DSF0001034592
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/28/2023 | 8/22/2024 |  | 118295 | 93911 | 88594 | DSF0001034592
22 | K236 | P.S. 236 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 10/1/2020 | FTK |  | FTK | 283620 | 273493 | DSF0000912807, DSF0000914326
22 | K236 | P.S. 236 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 11/12/2024 | DIIR | 49823 | 49823 | DSF0001086037
22 | K236 | P.S. 236 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112637
22 | K236 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112638
22 | K236 | P.S. 236 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/1/2022 | DOES |  | DOES | 105242 | 0 | DSF0001009062
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/22/2020 | 9/22/2020 | 7/6/2020 | 5931 | 9507 | 9507 | DSF0000960743
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/6/2020 | 12/31/2020 | 5/5/2021 | 26688 | 38033 | 38033 | DSF0000960743
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 5/19/2022 | 3/14/2023 | 6/18/2024 | 343977 | 317996 | 252903 | DSF0000960743
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 5/19/2022 | 3/14/2023 | 6/18/2024 | 304957 | 290504 | 210312 | DSF0000960743
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113579
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113579
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113579
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113579
22 | K240 | I.S. 381 - BROOKLYN | SCA Furniture & Equipment | FY23 RESO A GREENHOUSE | F&E | PNS | PNS | PNS | PNS | 100000 | 100000 | 0 | DSF0001035490
22 | K240 | I.S. 240 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0001008312
22 | K240 | I.S. 381 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/25/2024 | DIIR | 3/28/2024 | DIIR | 99641 | 99641 | DSF0001033557
22 | K240 | I.S. 240 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 10/23/2024 | DIIR | 99648 | 99648 | DSF0001086040
22 | K240 | I.S. 381 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001086041
22 | K240 | I.S. 381 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112643
22 | K240 | I.S. 240 - BROOKLYN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 179837 | 0 | DSF0001035489
22 | K240 | I.S. 240 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112641
22 | K240 | I.S. 240 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0 | DSF0001112642
22 | K240 | I.S. 240 - BROOKLYN | DOE - Skilled Trades | GAS PIPING REPAIR | Construction | In-Progress | 8/28/2019 | DOES |  | DOES | 198996 | 7065 | DSF0000894685
22 | K240 | I.S. 240 - BROOKLYN | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 3/22/2021 | DOES |  | DOES | 156929 | 0 | DSF0000988542
22 | K240 | I.S. 240 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/15/2024 | DOES | 8/2/2024 | DOES | 65832 | 7219 | DSF0001084754
22 | K251 | P.S. 251 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/6/2023 | 6/7/2023 | 5/22/2023 | 0 | 22772 | 22772 | DSF0001035500, DSF0001035501
22 | K251 | P.S. 251 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 5/30/2023 | 10/5/2023 | 11/7/2023 | 43216 | 77695 | 66050 | DSF0001035500, DSF0001035501
22 | K251 | P.S. 251 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 11/17/2024 | 9/12/2025 |  | 633832 | 486520 | 9384 | DSF0001035500, DSF0001035501
22 | K251 | P.S. 251 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 11/17/2024 | 9/12/2025 |  | 43216 | 45880 | 10734 | DSF0001035500, DSF0001035501
22 | K251 | P.S. 251 - BROOKLYN | SCA IEH | PO18-ABATE APPROX 30 LF OF PIPING IMPACTED BY SOW & ABATE THROUGH FLOOR PENETRATION INCLUDINF SOFT F | Construction | Complete | 11/15/2024 | IEH | 12/5/2024 | IEH | 0 | 0 | SCA0000073612
22 | K251 | P.S. 251 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 3/13/2020 | FTK | 2/4/2021 | FTK | 411305 | 411304 | DSF0000912068
22 | K251 | P.S. 251 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/11/2024 | DIIR |  | DIIR | 100000 | 100000 | DSF0001086047
22 | K251 | P.S. 251 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 11/1/2021 | DOER |  | DOER | 94456 | 0 | DSF0000913250
22 | K251 | P.S. 251 - BROOKLYN | DOE - RESOA | FY22 RESO A MEDIA STUDIO | Construction | PNS | PNS | PNS | PNS | DOER | 135000 | 0 | DSF0001033525
22 | K251 | P.S. 251 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001112650
22 | K254 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | Scope | Complete | 1/30/2019 | 5/1/2019 | 4/3/2019 | 33660 | 69367 | 69367 | DSF0000798194
22 | K254 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | Design | Complete | 4/12/2019 | 10/4/2019 | 7/15/2021 | 168300 | 608482 | 390816 | DSF0000798194
22 | K254 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | Construction | Complete | 9/5/2023 | 9/4/2024 | 9/4/2024 | 3786750 | 3474807 | 3195487 | DSF0000798194
22 | K254 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | CM,F&E | Complete | 9/5/2023 | 9/4/2024 | 9/4/2024 | 504817 | 479517 | 452635 | DSF0000798194
22 | K254 | P.S. 254 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001033526
22 | K254 | P.S. 254 - BROOKLYN | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001035502
22 | K254 | P.S. 254 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112652
22 | K254 | P.S. 254 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/20/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084117
22 | K255 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/25/2023 | 11/24/2023 | 8/2/2023 | 4870 | 1648 | 1648 | DSF0001035012
22 | K255 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/1/2023 | 21915 | 6590 | 6590 | DSF0001035012
22 | K255 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 3/1/2024 | 1/24/2025 |  | 282460 | 254496 | 71967 | DSF0001035012
22 | K255 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 3/1/2024 | 1/24/2025 |  | 124333 | 106746 | 89484 | DSF0001035012
22 | K255 | P.S. 255 - BROOKLYN | SCA IEH | PO18-REMOVE APPROX. 10 FEET OF ACM PIPE COVER FROM A 3' DRAIN PIPE. | Construction | Complete | 9/19/2024 | IEH | 9/22/2024 | IEH | 0 | 0 | SCA0000073399
22 | K269 | P.S. 361 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 100000 | 99638 | DSF0001035546
22 | K269 | P.S. 361 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 220000 | 201466 | DSF0001086059
22 | K269 | P.S. 361 - BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0 | DSF0001086058
22 | K269 | P.S. 361 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001112660
22 | K269 | P.S. 361 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/15/2022 | DOES |  | DOES | 201714 | 0 | DSF0001034413
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 3/12/2021 | 7/27/2021 | 11/29/2021 | 48965 | 100598 | 98991 | DSF0000989159, DSF0000989160, DSF0001013969
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/8/2021 | 5/11/2022 | 5/13/2022 | 237607 | 289469 | 277125 | DSF0000989159, DSF0000989160, DSF0001013969
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 9/12/2022 | 3/4/2024 |  | 4722126 | 4717268 | 4152226 | DSF0000989159, DSF0000989160, DSF0001013969
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/12/2022 | 3/4/2024 |  | 398088 | 732912 | 721499 | DSF0000989159, DSF0000989160, DSF0001013969
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 1/10/2018 | 4/26/2018 | 2/12/2018 | 0 | 11327 | 11326 | DSF0000867379
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Design | Complete | 7/25/2018 | 12/27/2018 | 3/13/2019 | 34157 | 113108 | 97416 | DSF0000867379
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 8/5/2019 | 3/1/2020 |  | 500966 | 640732 | 301676 | DSF0000867379
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 8/5/2019 | 3/1/2020 |  | 34157 | 66866 | 53883 | DSF0000867379
22 | K277 | P.S. 277 - BROOKLYN | SCA IEH | PO18-REMOVE APPROX 10 FEET OF ACM PIPE COVER FROM A 1' COLD WATER PIPE IN HALLWAY CEILING OUTSIDE | Construction | Complete | 10/23/2024 | IEH | 10/24/2024 | IEH | 0 | 0 | SCA0000073531
22 | K277 | P.S. 277 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112666
22 | K277 | P.S. 277 - BROOKLYN | DOE - RESOA | FY16 RESO A CAFETERIA/MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 97548 | 0 | DSF0000822807
22 | K277 | P.S. 277 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/29/2022 | DOER |  | DOER | 142267 | 0 | DSF0000913258
22 | K277 | P.S. 277 - BROOKLYN | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/18/2023 | DOER |  | DOER | 123904 | 0 | DSF0001033531
22 | K277 | P.S. 277 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/13/2024 | DOER |  | DOER | 300000 | 0 | DSF0001086064
22 | K277 | P.S. 277 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 1/17/2020 | DOES | 3/13/2020 | DOES | 150692 | 172076 | DSF0000912970
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/15/2024 | 3/20/2025 | 11/29/2024 | 0 | 6419 | 6419 | DSF0001112667
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | In-Progress | 11/29/2024 | 5/28/2025 |  | 18512 | 25675 | 25675 | DSF0001112667
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 271502 | 271502 | 0 | DSF0001112667
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 18512 | 18512 | 0 | DSF0001112667
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113586
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113586
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113586
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113586
22 | K278 | I.S. 278 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: RMS: 308A, 208A, 329 APPROX. 252SF EACH ROOM RM: 311 AP | Construction | Complete | 8/29/2023 | IEH | 7/28/2024 | IEH | 0 | 0 | SCA0000072256
22 | K278 | I.S. 278 - BROOKLYN | DIIT - RESOA | FY15 RESO A IP SURVEILLANCE CAMERA INSTALLATION | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 130728 | 0 | DSF0000801009
22 | K278 | I.S. 278 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 10/10/2024 | DIIR | 49821 | 49821 | DSF0001086065
22 | K278 | I.S. 278 - BROOKLYN | DOE - RESOA | FY08 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0000545194
22 | K278 | I.S. 278 - BROOKLYN | DOE - RESOA | FY10 RESO A- AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0000710069
22 | K278 | I.S. 278 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 11/4/2022 | DOER |  | DOER | 233803 | 0 | DSF0001033052
22 | K278 | I.S. 278 - BROOKLYN | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | In-Progress | 3/1/2024 | DOER |  | DOER | 65163 | 0 | DSF0001034987
22 | K278 | I.S. 278 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 1/20/2021 | DOES | 2/23/2021 | DOES | 151612 | 157632 | DSF0000912971
22 | K278 | I.S. 278 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/29/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084758
22 | K278 | I.S. 278 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/28/2024 | DOES |  | DOES | 655918 | 0 | DSF0001085724
22 | K286 | K811 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 8/29/2019 | 1/17/2020 | 6/8/2021 | 126919 | 188730 | 188730 | DSF0000912810, DSF0001014094
22 | K286 | K811 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | In-Progress | 8/31/2022 | 3/9/2023 |  | 634596 | 634596 | 281687 | DSF0000912810, DSF0001014094
22 | K286 | K811 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | PNS | PNS | PNS | PNS | 14278399 | 14278399 | 199190 | DSF0000912810, DSF0001014094
22 | K286 | K811 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 888433 | 888433 | 104074 | DSF0000912810, DSF0001014094
22 | K286 | K811 SPED - BROOKLYN | SCA IEH | PO18-REMOVE APPROX. 15FT OF ACM PIPE COVER FROM A 4' DRAIN PIPE LOCATED IN BOILER ROOM CRAWL SPACE, | Construction | In-Progress | 11/12/2024 | IEH |  | IEH | 0 | 0 | SCA0000073602
22 | K286 | K811 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES AND MASTIC IN GYM INSTRUCTOR'S OFFICE - RM #137A APPROX QUANTITY | Construction | Complete | 11/19/2024 | IEH | 12/28/2024 | IEH | 0 | 0 | SCA0000073622
22 | K286 | K811 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE @ LISTED AREASGENERAL OFFICE SPACE ID#2141 & 2080. ROOM 141, STAIRCASE EXIT | Construction | In-Progress | 12/10/2024 | IEH |  | IEH | 0 | 0 | SCA0000073690
22 | K286 | K811 SPED - BROOKLYN | Fast Track Projects | ELECTRICAL CODE COMPLIANCE | Construction | In-Progress | 5/8/2019 | FTK |  | FTK | 140992 | 140991 | DSF0000849869
22 | K286 | K811 SPED - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/4/2022 | DOER |  | DOER | 159589 | 0 | DSF0000913178
22 | K286 | K811 SPED - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 118000 | 0 | DSF0001033135
22 | K286 | K811 SPED - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | Complete | 7/26/2024 | DOER | 11/18/2024 | DOER | 234949 |  | DSF0001035527
22 | K286 | K811 SPED - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 7/19/2019 | DOES |  | DOES | 152471 | 0 | DSF0000889051
22 | K286 | K811 SPED - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/17/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084888
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 3/26/2021 | 8/10/2021 | 11/3/2021 | 153170 | 163233 | 163233 | DSF0000961142, DSF0001014480
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 11/15/2021 | 5/4/2022 | 9/30/2022 | 765850 | 408322 | 371397 | DSF0000961142, DSF0001014480
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 9/5/2023 | 9/3/2025 |  | 17231625 | 15764356 | 10975068 | DSF0000961142, DSF0001014480
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 9/5/2023 | 9/3/2025 |  | 1073222 | 356646 | 356333 | DSF0000961142, DSF0001014480
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/6/2023 | 6/7/2023 | 7/14/2023 | 0 | 16397 | 16397 | DSF0001035531
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 7/18/2023 | 12/4/2023 | 1/26/2024 | 102000 | 79724 | 52531 | DSF0001035531
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 1496000 | 1496000 | 4058 | DSF0001035531
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 102000 | 102000 | 20444 | DSF0001035531
22 | K312 | P.S. 312 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0 | DSF0001112679
22 | K312 | P.S. 312 - BROOKLYN | DOE - RESOA | FY10 RESO A- AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0000709494
22 | K312 | P.S. 312 - BROOKLYN | DOE - RESOA | FY16 RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 94000 | 0 | DSF0000865843
22 | K312 | P.S. 312 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 7/9/2015 | DOES |  | DOES | 183980 | 0 | DSF0000799863
22 | K342 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY16 RESO A LEARNING GARDEN | Scope | Complete | 9/27/2016 | 12/29/2016 | 1/20/2017 | 0 | 188360 | 186735 | DSF0000822797
22 | K342 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY16 RESO A LEARNING GARDEN | Design | Complete | 11/7/2017 | 3/28/2018 | 5/17/2019 | 889719 | 1453321 | 1408503 | DSF0000822797
22 | K342 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY16 RESO A LEARNING GARDEN | Construction | In-Progress | 6/6/2022 | 6/4/2024 |  | 13049213 | 13154921 | 12030671 | DSF0000822797
22 | K342 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY16 RESO A LEARNING GARDEN | CM,F&E | In-Progress | 6/6/2022 | 6/4/2024 |  | 889719 | 582605 | 578738 | DSF0000822797
22 | K395 | P.S. 109 - BROOKLYN | Fast Track Projects | LSP REPLACE LEAKING PVI DOMESTIC WATER HEATER | Construction | In-Progress | 5/22/2019 | FTK |  | FTK | 200609 | 187684 | DSF0000912160
22 | K395 | P.S. 109 - BROOKLYN | Fast Track Projects | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/31/2023 | FTK |  | FTK | 139545 | 138150 | DSF0001033472
22 | K395 | P.S. 109 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112698
22 | K395 | P.S. 109 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001086106
22 | K395 | P.S. 109 - BROOKLYN | DOE - RESOA | FY24 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086107
22 | K395 | P.S. 109 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/24/2024 | DOES | 12/5/2024 | DOES | 50832 |  | DSF0001084620
22 | K402 | K000 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/29/2024 | IEH | 9/5/2024 | IEH | 0 | 0 | SCA0000073327
22 | K402 | K000 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/20/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085445
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2/26/2021 | 7/13/2021 | 11/5/2021 | 195699 | 112191 | 111691 | DSF0000941578, DSF0000941575, DSF0000941579, DSF0001015136
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/10/2021 | 4/15/2022 | 5/11/2022 | 978501 | 514250 | 357699 | DSF0000941578, DSF0000941575, DSF0000941579, DSF0001015136
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 12/18/2023 | 5/5/2026 |  | 22016250 | 19908966 | 3722089 | DSF0000941578, DSF0000941575, DSF0000941579, DSF0001015136
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 12/18/2023 | 5/5/2026 |  | 1371484 | 237731 | 224460 | DSF0000941578, DSF0000941575, DSF0000941579, DSF0001015136
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112702
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 180000 | 180000 | 0 | DSF0001112702
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 2640000 | 2640000 | 0 | DSF0001112702
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 180000 | 180000 | 0 | DSF0001112702
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113589
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113589
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113589
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113589
22 | K405 | MIDWOOD HS - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 7/30/2020 | FTK |  | FTK | 326288 | 323937 | DSF0000912695
22 | K405 | MIDWOOD HS - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/11/2024 | DIIR | 10/28/2024 | DIIR | 199298 | 199298 | DSF0001086112
22 | K405 | MIDWOOD HS - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 8/23/2023 | DOER | 3/26/2024 | DOER | 319428 | 5593 | DSF0001035559
22 | K405 | MIDWOOD HS - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035560
22 | K405 | MIDWOOD HS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/11/2024 | DOES | 11/19/2024 | DOES | 65832 |  | DSF0001084896
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 8/14/2020 | 12/14/2020 | 3/24/2021 | 114450 | 81503 | 78873 | DSF0000961122
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 3/29/2021 | 9/9/2021 | 12/1/2021 | 572250 | 389765 | 71443 | DSF0000961122
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | Construction | In-Progress | 9/18/2023 | 12/5/2025 |  | 12875625 | 12492648 | 3894161 | DSF0000961122
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 9/18/2023 | 12/5/2025 |  | 808729 | 486647 | 470481 | DSF0000961122
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | Scope | Complete | 6/1/2023 | 11/30/2023 | 10/4/2023 | 393500 | 292431 | 289496 | DSF0001015245, DSF0001015244, DSF0001015243, DSF0001087221
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | Design | Complete | 10/26/2023 | 6/10/2024 | 4/15/2024 | 1967502 | 506243 | 494040 | DSF0001015245, DSF0001015244, DSF0001015243, DSF0001087221
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | Construction | In-Progress | 8/27/2024 | 2/1/2029 |  | 44268750 | 40103309 | 526761 | DSF0001015245, DSF0001015244, DSF0001015243, DSF0001087221
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | CM,F&E | In-Progress | 8/27/2024 | 2/1/2029 |  | 2754500 | 286050 | 150746 | DSF0001015245, DSF0001015244, DSF0001015243, DSF0001087221
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Scope | Complete | 1/20/2022 | 5/23/2022 | 7/14/2022 | 0 | 9911 | 9911 | DSF0001033565
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Design | Complete | 7/18/2022 | 1/13/2023 | 11/4/2024 | 0 | 26189 | 24688 | DSF0001033565
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 35052 | 35052 | DSF0001033565
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 8208 | 8208 | DSF0001033565
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR PIPE & CAFETERIA CEILING ROOM #'S AS PER AHERA PLAN# 1400 | Construction | Complete | 8/20/2024 | IEH | 8/22/2024 | IEH | 0 | 0 | SCA0000073306
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY12 RESO A FLOORING | Construction | PNS | PNS | PNS | PNS | DOER | 264039 | 0 | DSF0000865716
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | RESO A FIELDHOUSE UPGRADE | Construction | In-Progress | 12/20/2019 | DOER |  | DOER | 19630 | 0 | DSF0000865856
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | Complete | 4/16/2021 | DOER | 6/29/2021 | DOER | 673887 | 673887 | DSF0000913285
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 290000 | 0 | DSF0001033566
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112710
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/12/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084901
22 | K426 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY23 RESO A FIELD UPGRADE | Construction | In-Progress | 12/14/2023 | DOER |  | DOER | 2300000 | 232796 | DSF0001035568
22 | K426 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001112711
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA CIP | GYM BLEACHER REPLACEMENT | Scope | Complete | 8/21/2024 | 12/24/2024 | 12/26/2024 | 16536 | 16093 | 1914 | DSF0001015611
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA CIP | GYM BLEACHER REPLACEMENT | Design | PNS | PNS | PNS | PNS | 74414 | 74414 | 7655 | DSF0001015611
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA CIP | GYM BLEACHER REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 959109 | 959109 | 0 | DSF0001015611
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA CIP | GYM BLEACHER REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 177766 | 177766 | 4369 | DSF0001015611
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA CIP | OPHELIA- FLOOD ELIMINATION @ K495 | Scope | In-Progress | 6/26/2024 | 11/12/2024 |  | 20000 | 20000 | 1002 | SCA0000073054
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA CIP | OPHELIA- FLOOD ELIMINATION @ K495 | Design | PNS | PNS | PNS | PNS | 90000 | 90000 | 4007 | SCA0000073054
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA CIP | OPHELIA- FLOOD ELIMINATION @ K495 | Construction | PNS | PNS | PNS | PNS | 1160000 | 1160000 | 0 | SCA0000073054
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA CIP | OPHELIA- FLOOD ELIMINATION @ K495 | CM,F&E | PNS | PNS | PNS | PNS | 215000 | 215000 | 7730 | SCA0000073054
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA IEH | PO18-ABATE AND REPAIR DOOR FRAME CAULKING ON CORRIDOR SIDE THROUGHOUT ENTIRE BUILDING ROOMS: 235, 23 | Construction | Complete | 5/28/2024 | IEH | 7/24/2024 | IEH | 0 | 0 | SCA0000073031
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA IEH | PO18-ABATE ACM WRAPPING ON PIPING DETERIORATED IN ROOM B20. AHERA BOOK LISTS INSULATION AS CONFIRMED | Construction | Complete | 8/13/2024 | IEH | 8/14/2024 | IEH | 0 | 0 | SCA0000073277
22 | K495 | ORIGINS HIGH SCHOOL | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 10/19/2024 | FTK |  | FTK | 231552 | 21318 | DSF0001112111
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/6/2023 | DOES | 1/12/2024 | DOES | 671019 |  | DSF0001035091
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/17/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084914
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113594
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113594
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113594
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113594
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 3000000 | 0 | DSF0001112725
22 | K555 | BROOKLYN COLLEGE ACADEMY - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033581
22 | K555 | BROOKLYN COLLEGE ACADEMY - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112731
22 | K555 | BROOKLYN COLLEGE ACADEMY - K | DOE - RESOA | FY18 RESO A HYDROPONICS LAB | Construction | Complete | 7/27/2022 | DOER | 9/22/2022 | DOER | 194395 | 191780 | DSF0000867374
22 | K705 | MIDWOOD HS - BROOKLYN | SCA CIP | ROOFS | Scope | Complete | 8/20/2024 | 1/8/2025 | 12/13/2024 | 7393 | 33777 | 25777 | DSF0001066857
22 | K705 | MIDWOOD HS - BROOKLYN | SCA CIP | ROOFS | Design | PNS | PNS | PNS | PNS | 33269 | 33269 | 27413 | DSF0001066857
22 | K705 | MIDWOOD HS - BROOKLYN | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 428796 | 428796 | 0 | DSF0001066857
22 | K705 | MIDWOOD HS - BROOKLYN | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 79475 | 79475 | 10313 | DSF0001066857
22 | K705 | MIDWOOD HS - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/14/2024 | IEH | 8/30/2024 | IEH | 0 | 0 | SCA0000073287
22 | K735 | P.S. 245 - BROOKLYN | DOE - RESOA | FY16 RESO A ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0 | DSF0000822759
22 | K839 | P.S. 134 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0 | DSF0001033485
22 | K839 | P.S. 134 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035595
22 | K839 | P.S. 134 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112740
22 | K849 | P.S. 134 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113597
22 | K849 | P.S. 134 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113597
22 | K849 | P.S. 134 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113597
22 | K849 | P.S. 134 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113597
22 | K849 | P.S. 134 - BROOKLYN | DOE - RESOA | FY21 RESO A BREEZEWAY | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0000961231
22 | K849 | P.S. 134 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/13/2024 | DOER |  | DOER | 400000 | 0 | DSF0001086154
22 | K849 | P.S. 134 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112741
22 | K849 | P.S. 134 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/27/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084173
22 | K849 | P.S. 134 - BROOKLYN | DOE - Skilled Trades | ASPHALT REPLACEMENT IN YARD | Construction | In-Progress | 7/5/2023 | DOES |  | DOES | 365686 | 0 | DSF0001067318
22 | K852 | P.S. 326 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000867257
22 | K852 | P.S. 326 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0000867257
22 | K852 | P.S. 326 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 66000 | 66000 | 0 | DSF0000867257
22 | K852 | P.S. 326 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 4500 | 4500 | 0 | DSF0000867257
22 | K852 | P.S. 326 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/21/2024 | DIIR | 10/25/2024 | DIIR | 99650 | 99650 | DSF0001086156
22 | K852 | P.S. 326 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112742
22 | K852 | P.S. 326 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085473
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 9/27/2019 | 2/18/2020 | 11/29/2021 | 138070 | 156676 | 155057 | DSF0000897322, DSF0001016646, DSF0001016645
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 11/30/2021 | 5/3/2022 | 5/11/2022 | 690350 | 502488 | 485955 | DSF0000897322, DSF0001016646, DSF0001016645
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 9/12/2022 | 9/10/2024 |  | 15532875 | 14540261 | 11829827 | DSF0000897322, DSF0001016646, DSF0001016645
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 9/12/2022 | 9/10/2024 |  | 966490 | 566696 | 561197 | DSF0000897322, DSF0001016646, DSF0001016645
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/29/2020 | 9/28/2020 | 7/27/2020 | 4629 | 6637 | 6637 | DSF0000960781
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/27/2020 | 1/21/2021 | 5/5/2021 | 20832 | 26548 | 26548 | DSF0000960781
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 5/19/2022 | 3/14/2023 | 6/18/2024 | 268503 | 270846 | 245100 | DSF0000960781
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 5/19/2022 | 3/14/2023 | 6/18/2024 | 198089 | 195265 | 187003 | DSF0000960781
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/25/2024 | IEH | 7/25/2024 | IEH | 0 | 0 | SCA0000073080
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | Fast Track Projects | PATH OF TRAVEL WATER PENETRATION | Construction | In-Progress | 7/31/2024 | FTK |  | FTK | 291517 | 4905 | DSF0001034289
22 | KBZT | K000 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35000 | 0 | DSF0000913867
22 | KBZT | K000 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/1/2023 | DIIR |  | DIIR | 150000 | 0 | DSF0001032987
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/24/2023 | 144603 | 245201 | 205049 | DSF0001009615, DSF0001009616, DSF0001009617, DSF0001009618, DSF0001111760
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | Design | Complete | 10/30/2023 | 6/10/2024 | 4/26/2024 | 715414 | 620186 | 607305 | DSF0001009615, DSF0001009616, DSF0001009617, DSF0001009618, DSF0001111760
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | Construction | In-Progress | 7/22/2024 | 1/7/2027 |  | 15439113 | 14018000 | 258000 | DSF0001009615, DSF0001009616, DSF0001009617, DSF0001009618, DSF0001111760
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | CM,F&E | In-Progress | 7/22/2024 | 1/7/2027 |  | 1069250 | 151727 | 142773 | DSF0001009615, DSF0001009616, DSF0001009617, DSF0001009618, DSF0001111760
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/23/2023 | 10/23/2023 | 10/24/2023 | 17818 | 19339 | 19339 | DSF0001083797
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/26/2023 | 3/26/2024 | 4/1/2024 | 80183 | 67730 | 64749 | DSF0001083797
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | PNS | PNS | PNS | PNS | 1033468 | 1033468 | 0 | DSF0001083797
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | PNS | PNS | PNS | PNS | 191548 | 191548 | 13285 | DSF0001083797
23 | K012 | I.S. 484 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | Complete | 5/24/2024 |  | 9/25/2024 | 404149 | 404149 | 404149 | DSF0001085938
23 | K012 | P.S. 12 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/1/2023 | DIIR |  | DIIR | 355000 | 0 | DSF0001032993
23 | K012 | P.S. 12 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | Complete | 6/28/2019 | DOER | 12/30/2020 | DOER | 147096 | 178407 | DSF0000890646
23 | K012 | P.S. 12 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 5/9/2022 | DOER |  | DOER | 41371 | 0 | DSF0000913197
23 | K012 | I.S. 484 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 6/4/2021 | DOER |  | DOER | 89991 | 0 | DSF0000913198
23 | K012 | P.S. 12 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 215000 | 0 | DSF0001035368
23 | K012 | P.S. 12 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 6/21/2024 | DOER |  | DOER | 38808 | 0 | DSF0001035369
23 | K012 | I.S. 484 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/14/2021 | DOES |  | DOES | 114624 | 0 | DSF0001009150
23 | K012 | I.S. 484 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/9/2024 | DOES |  | DOES | 458324 | 0 | DSF0001085710
23 | K041 | P.S. 41 - BROOKLYN | SCA IEH | PO18-FLOOR UNDER PARTITION POSTS AND COUNTER IN ROOM 144 (GEN. OFFICE) NEEDS TO BE TESTED BEFORE THE | Construction | Complete | 5/7/2024 | IEH | 11/13/2024 | IEH | 0 | 0 | SCA0000072984
23 | K041 | P.S. 41 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001035390
23 | K041 | I.S. 522 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 226545 | 0 | DSF0001085953
23 | K041 | P.S. 41 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/24/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084585
23 | K041 | P.S. 41 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/31/2024 | DOES |  | DOES | 393570 | 0 | DSF0001111857
23 | K055 | BROOKLYN COLLEGIATE: A COLLEGE BOARD SCHOOL | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/5/2022 | DOES |  | DOES | 141048 | 0 | DSF0000912957
23 | K055 | BROOKLYN COLLEGIATE: A COLLEGE BOARD SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/31/2023 | DOES | 11/6/2023 | DOES | 621792 | 287848 | DSF0001035094
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 5/22/2023 | 9/21/2023 | 6/1/2023 | 4800 | 555 | 555 | DSF0001035014
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Design | Complete | 6/1/2023 | 11/29/2023 | 11/8/2023 | 21600 | 2221 | 2221 | DSF0001035014
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 4/23/2024 | 3/18/2025 |  | 278400 | 262175 | 152327 | DSF0001035014
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 4/23/2024 | 3/18/2025 |  | 170865 | 150864 | 87046 | DSF0001035014
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA IEH | PO18-ABATE & REPAIR DAMAGED PAINT/PLASTER IN THE FOLLOWING AREAS IN ROOMS: 307A - WALL BEHIND THE RA | Construction | Complete | 8/27/2024 | IEH | 9/1/2024 | IEH | 0 | 0 | SCA0000073323
23 | K073 | BROOKLYN ENVIRONMENTAL EXPLORATION SCHOOL (BEES) | Fast Track Projects | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/26/2024 | FTK |  | FTK | 234515 | 72941 | DSF0001033598
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | Fast Track Projects | LSP- AUDITORIUM UPGRADE | Construction | In-Progress | 5/19/2023 | FTK |  | FTK | 230445 | 230411 | DSF0001083835
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/10/2024 | DIIR | 8/29/2024 | DIIR | 99650 | 99650 | DSF0001033595
23 | K073 | P.S. 73 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 2/12/2024 | DOEL |  | DOEL | 68896 | 68896
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112553
23 | K073 | BROOKLYN ENVIRONMENTAL EXPLORATION SCHOOL (BEES) | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/12/2024 | DOES |  | DOES | 629267 | 0 | DSF0001085714
23 | K137 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 4/6/2021 | 8/19/2021 | 11/2/2021 | 191370 | 289483 | 272040 | DSF0001008819, DSF0001011444
23 | K137 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 11/10/2021 | 5/2/2022 | 5/23/2023 | 956850 | 892297 | 798361 | DSF0001008819, DSF0001011444
23 | K137 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | In-Progress | 4/15/2024 | 9/1/2026 |  | 21529126 | 19391553 | 2039601 | DSF0001008819, DSF0001011444
23 | K137 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 4/15/2024 | 9/1/2026 |  | 1339590 | 281901 | 278992 | DSF0001008819, DSF0001011444
23 | K137 | P.S. 137 - BROOKLYN | Fast Track Projects | LSP- HOT WATER HEATER | Construction | In-Progress | 5/10/2019 | FTK |  | FTK | 277408 | 242990 | DSF0000888922
23 | K137 | P.S. 137 - BROOKLYN | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0 | DSF0001112580
23 | K137 | P.S. 137 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/23/2022 | DOES |  | DOES | 87735 | 0 | DSF0001034408
23 | K150 | P.S. 150 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/3/2024 | 9/4/2024 | 5/7/2024 | 2966 | 1808 | 1808 | DSF0001087403
23 | K150 | P.S. 150 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/7/2024 | 11/1/2024 | 8/7/2024 | 13347 | 7230 | 7230 | DSF0001087403
23 | K150 | P.S. 150 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/12/2024 | 11/6/2025 |  | 172022 | 160719 | 3624 | DSF0001087403
23 | K150 | P.S. 150 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/12/2024 | 11/6/2025 |  | 31883 | 22212 | 6196 | DSF0001087403
23 | K150 | P.S. 150 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING LAYERS FOR ACM LOC: ROOM 403B, PRINCIPAL'S OFFICE APPROX 20 SQ FT OF D | Construction | Complete | 11/5/2024 | IEH | 11/9/2024 | IEH | 0 | 0 | SCA0000073571
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | Scope | Complete | 11/3/2017 | 10/4/2018 | 11/26/2018 | 314342 | 142204 | 142204 | DSF0000847745, DSF0000893206, DSF0000870432, DSF0000912205, DSF0000893207, DSF0000912206, DSF0000893205
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | Design | Complete | 1/23/2019 | 6/24/2019 | 5/17/2019 | 1252506 | 1103106 | 1012034 | DSF0000847745, DSF0000893206, DSF0000870432, DSF0000912205, DSF0000893207, DSF0000912206, DSF0000893205
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | Construction | In-Progress | 5/9/2022 | 5/7/2024 |  | 23048198 | 24300372 | 21800092 | DSF0000847745, DSF0000893206, DSF0000870432, DSF0000912205, DSF0000893207, DSF0000912206, DSF0000893205
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | CM,F&E | In-Progress | 5/9/2022 | 5/7/2024 |  | 1531334 | 840203 | 826439 | DSF0000847745, DSF0000893206, DSF0000870432, DSF0000912205, DSF0000893207, DSF0000912206, DSF0000893205
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/30/2023 | 5/30/2023 | 2/15/2023 | 5400 | 2061 | 2061 | DSF0001034575
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/15/2023 | 8/11/2023 | 5/2/2023 | 24300 | 8244 | 8244 | DSF0001034575
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/28/2023 | 8/22/2024 |  | 313200 | 281151 | 248116 | DSF0001034575
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/28/2023 | 8/22/2024 |  | 112734 | 89960 | 84255 | DSF0001034575
23 | K155 | P.S. 155 - BROOKLYN | Fast Track Projects | LSP AUDITORIUM UPGRADE | Construction | In-Progress | 5/5/2023 | FTK |  | FTK | 224389 | 210159 | DSF0001083836
23 | K155 | P.S. 155 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 62000 | 0 | DSF0001086002
23 | K155 | P.S. 155 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/19/2024 | DOEL |  | DOEL | 62212 | 0
23 | K155 | P.S. 155 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 9/15/2023 | DOER | 3/22/2024 | DOER | 221694 | 1971 | DSF0001033021
23 | K155 | P.S. 155 - BROOKLYN | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112588
23 | K155 | P.S. 155 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/14/2022 | DOES |  | DOES | 182719 | 0 | DSF0001008671
23 | K155 | P.S. 155 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/8/2024 | DOES | 7/12/2024 | DOES | 65832 | 189 | DSF0001084595
23 | K165 | P.S. 165 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR 1ST FL WALLS AND FLOOR TO HAVE ELECTRIC INSTALLED FOR WATER BOTTLE FILLER. | Construction | Complete | 4/19/2024 | IEH | 6/27/2024 | IEH | 0 | 0 | SCA0000072944
23 | K165 | P.S. 165 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 344187 | 0 | DSF0000959811
23 | K175 | FREDERICK DOUGLAS ACAD VII HS - K | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 5/3/2021 | DOER | 4/11/2023 | DOER | 143100 | 142575 | DSF0000913049
23 | K175 | TEACHERS PREP (HS LVL) - K | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/6/2023 | DOER |  | DOER | 238388 | 0 | DSF0001033128
23 | K175 | FREDERICK DOUGLAS ACAD VII HS - K | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/11/2024 | DOES |  | DOES | 819606 | 0 | DSF0001062737
23 | K175 | TEACHERS PREP (HS LVL) - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/23/2024 | DOES | 10/16/2024 | DOES | 65832 |  | DSF0001084881
23 | K175 | FREDERICK DOUGLAS ACAD VII HS - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/22/2024 | DOES |  | DOES | 211169 | 0 | DSF0001085719
23 | K178 | P.S. 178 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/12/2024 | 10/29/2024 | 10/3/2024 | 160459 | 140296 | 139663 | DSF0001090502
23 | K178 | P.S. 178 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | In-Progress | 12/17/2024 | 5/20/2025 |  | 748810 | 748810 | 197101 | DSF0001090502
23 | K178 | P.S. 178 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 11873980 | 11873980 | 0 | DSF0001090502
23 | K178 | P.S. 178 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1176701 | 1176701 | 23331 | DSF0001090502
23 | K178 | P.S. 178 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 12/26/2023 | DOEL |  | DOEL | 64735 | 64735
23 | K178 | P.S. 178 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 4/22/2019 | DOES |  | DOES | 262741 | 0 | DSF0000889599
23 | K178 | P.S. 178 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/14/2022 | DOES |  | DOES | 107334 | 0 | DSF0001009149
23 | K178 | P.S. 178 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/21/2024 | DOES | 11/15/2024 | DOES | 65832 |  | DSF0001084597
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 1/26/2021 | 5/26/2021 | 10/20/2021 | 41950 | 26892 | 26892 | DSF0000987418
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 10/28/2021 | 3/28/2022 | 4/18/2022 | 209750 | 204412 | 151407 | DSF0000987418
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | Construction | In-Progress | 9/11/2023 | 3/3/2025 |  | 4719375 | 4705829 | 955822 | DSF0000987418
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 9/11/2023 | 3/3/2025 |  | 293650 | 329509 | 311489 | DSF0000987418
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 6/7/2023 | 10/6/2023 | 6/20/2023 | 4694 | 1330 | 1330 | DSF0001035018
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 6/20/2023 | 12/15/2023 | 10/4/2023 | 21123 | 5320 | 5320 | DSF0001035018
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2/16/2024 | 1/10/2025 |  | 272252 | 242683 | 178760 | DSF0001035018
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2/16/2024 | 1/10/2025 |  | 101552 | 82471 | 65697 | DSF0001035018
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/27/2023 | 5/30/2023 | 8/1/2023 | 0 | 15737 | 15737 | DSF0001035461, DSF0001035462
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 8/2/2023 | 12/20/2023 | 1/31/2024 | 56170 | 56848 | 54291 | DSF0001035461, DSF0001035462
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 823829 | 823829 | 10258 | DSF0001035461, DSF0001035462
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 56170 | 63520 | 32831 | DSF0001035461, DSF0001035462
23 | K183 | P.S. 446 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE SURFACING MATERIAL ON BEAM WHERE BASKETBALL HOOP WAS IN 1ST FLOOR PLAY AREA. A | Construction | Complete | 7/17/2024 | IEH | 12/5/2024 | IEH | 0 | 0 | SCA0000073141
23 | K183 | P.S. 446 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR IN ROOM 202, APPROX 400 SQ FT SOFT CONCRETE FILLER IS CONFIRMED ACM | Construction | Complete | 9/16/2024 | IEH | 10/26/2024 | IEH | 0 | 0 | SCA0000073378
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112598
23 | K183 | P.S. 446 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/25/2023 | DOES |  | DOES | 331490 | 0 | DSF0001035095
23 | K183 | P.S. 446 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/12/2024 | DOES | 7/24/2024 | DOES | 65832 | 189 | DSF0001084742
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND SURFACES | Scope | Complete | 8/21/2019 | 1/9/2020 | 12/20/2019 | 2315 | 17140 | 17140 | DSF0000912942
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND SURFACES | Design | Complete | 2/18/2020 | 8/3/2020 | 5/7/2020 | 10417 | 68556 | 68556 | DSF0000912942
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND SURFACES | Construction | PNS | PNS | PNS | PNS | 134257 | 134257 | 91098 | DSF0000912942
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND SURFACES | CM,F&E | PNS | PNS | PNS | PNS | 24884 | 33181 | 33181 | DSF0000912942
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/24/2023 | 5/23/2023 | 2/1/2023 | 4964 | 1993 | 1993 | DSF0001034598
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/1/2023 | 7/28/2023 | 4/26/2023 | 22338 | 7970 | 7970 | DSF0001034598
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/30/2023 | 7/24/2024 |  | 287912 | 255735 | 137275 | DSF0001034598
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/30/2023 | 7/24/2024 |  | 107665 | 88287 | 82111 | DSF0001034598
23 | K184 | P.S. 184 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 25 LINEAR FEET OF ACM FROM PIPE LOCATED ABOVE ELECTRICAL PANEL IN | Construction | In-Progress | 7/26/2023 | IEH |  | IEH | 0 | 0 | SCA0000072165
23 | K184 | P.S. 184 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE AREA AROUND SINK DRAIN IN ROOM# 211 | Construction | Complete | 7/30/2024 | IEH | 8/29/2024 | IEH | 0 | 0 | SCA0000073201
23 | K184 | P.S. 184 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY TEN LINEAR FEET OF ACM FROM PIPE IN ROOM# 502 CRAWL SPACE FOR BOYS | Construction | Complete | 9/4/2024 | IEH | 9/7/2024 | IEH | 0 | 0 | SCA0000073347
23 | K184 | P.S. 184 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 2/24/2020 | FTK |  | FTK | 425387 | 414410 | DSF0000912057
23 | K184 | P.S. 184 - BROOKLYN | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001033028
23 | K184 | P.S. 184 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/18/2024 | DOES | 10/3/2024 | DOES | 65832 |  | DSF0001084600
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | Scope | Complete | 6/21/2023 | 12/19/2023 | 11/2/2023 | 286001 | 182069 | 177550 | DSF0001064483, DSF0001111780, DSF0001111777, DSF0001111778, DSF0001111779
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | Design | Complete | 12/27/2023 | 5/29/2024 | 4/23/2024 | 1430000 | 398784 | 398784 | DSF0001064483, DSF0001111780, DSF0001111777, DSF0001111778, DSF0001111779
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | Construction | In-Progress | 9/16/2024 | 3/4/2027 |  | 32175001 | 28976797 | 291057 | DSF0001064483, DSF0001111780, DSF0001111777, DSF0001111778, DSF0001111779
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | CM,F&E | In-Progress | 9/16/2024 | 3/4/2027 |  | 2002002 | 135825 | 131959 | DSF0001064483, DSF0001111780, DSF0001111777, DSF0001111778, DSF0001111779
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/19/2023 | 5/18/2023 | 2/1/2023 | 6276 | 982 | 982 | DSF0001034658
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/1/2023 | 7/28/2023 | 4/26/2023 | 28242 | 3926 | 3926 | DSF0001034658
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 8/30/2023 | 7/24/2024 |  | 364008 | 323325 | 227497 | DSF0001034658
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 8/30/2023 | 7/24/2024 |  | 166517 | 146044 | 112084 | DSF0001034658
23 | K263 | M.S. 671 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 5486 | 5486 | DSF0001086056
23 | K263 | M.S. 671 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 30000 | 24514 | 5510 | DSF0001086056
23 | K263 | M.S. 671 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001086056
23 | K263 | M.S. 671 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001086056
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/1/2023 | 4/4/2024 | 3/1/2024 | 0 | 9752 | 3987 | DSF0001086053
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | Complete | 3/5/2024 | 7/19/2024 | 7/25/2024 | 9000 | 9000 | 15947 | DSF0001086053
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 132000 | 132000 | 1941 | DSF0001086053
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 9000 | 9289 | 9289 | DSF0001086053
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE APPROX 12 FT OF PIPE INSULATION FROM PIPE. LOCATION IN BOILER ROOM. PIPES ARE | Construction | Complete | 9/26/2024 | IEH | 10/3/2024 | IEH | 0 | 0 | SCA0000073440
23 | K263 | P.S./I.S. 323 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/16/2024 | DIIR |  | DIIR | 333000 | 0 | DSF0001086054
23 | K263 | P.S./I.S. 323 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112657
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/24/2022 | DOER |  | DOER | 58788 | 0 | DSF0000913055
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 3/11/2022 | DOER |  | DOER | 308811 | 0 | DSF0001008295
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086052
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 14858 | 0 | DSF0001086055
23 | K263 | M.S. 671 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086057
23 | K263 | M.S. 671 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001112658
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/28/2023 | DOES |  | DOES | 873843 | 0 | DSF0000865736
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/19/2024 | DOES | 8/27/2024 | DOES | 65832 |  | DSF0001084757
23 | K271 | EAGLE ACAD YOUNG MEN AT OCEAN - K | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | Complete | 9/26/2022 | DOER | 12/27/2022 | DOER | 101524 | 57351 | DSF0000913256
23 | K271 | EAGLE ACAD YOUNG MEN AT OCEAN - K | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001035512
23 | K271 | EAGLE ACAD YOUNG MEN AT OCEAN - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 1/17/2022 | DOES | 9/20/2022 | DOES | 545985 | 54101 | DSF0000960840
23 | K271 | EAGLE ACAD YOUNG MEN AT OCEAN - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/3/2024 | DOES | 10/10/2024 | DOES | 65832 |  | DSF0001084887
23 | K275 | I.S. 518 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/25/2023 | 5/25/2023 | 7/14/2023 | 0 | 8674 | 8674 | DSF0001035515
23 | K275 | I.S. 518 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 7/19/2023 | 12/20/2023 | 11/21/2023 | 60000 | 32978 | 8237 | DSF0001035515
23 | K275 | I.S. 518 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 11768 | DSF0001035515
23 | K275 | I.S. 518 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 15738 | DSF0001035515
23 | K275 | BROOKLYN DEMOCRACY ACADEMY - K | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001035517
23 | K275 | I.S. 518 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 9/2/2016 | DOES |  | DOES | 178610 | 0 | DSF0000782173
23 | K275 | I.S. 518 - BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 4/5/2023 | DOES | 11/15/2023 | DOES | 655803 | 605195 | DSF0000960841
23 | K275 | I.S. 518 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/2/2024 | DOES | 7/18/2024 | DOES | 65832 | 189 | DSF0001084612
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | Scope | Complete | 4/2/2019 | 7/17/2019 | 3/16/2020 | 8440 | 14978 | 14978 | DSF0000912180
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | Design | Complete | 3/16/2020 | 8/28/2020 | 11/1/2022 | 37980 | 60871 | 57671 | DSF0000912180
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 4/27/2023 | 3/21/2024 |  | 489520 | 513940 | 130461 | DSF0000912180
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | CM,F&E | In-Progress | 4/27/2023 | 3/21/2024 |  | 90730 | 87813 | 66130 | DSF0000912180
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | SWIMMING POOL / FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / EXTERIOR DOORS / FLOOD ELIMINATION / PATH OF TRAVEL SWIMMING POOL | Scope | Complete | 4/18/2017 | 7/20/2023 | 6/6/2023 | 286668 | 401454 | 386654 | DSF0000849835, DSF0000913262, DSF0000913263, DSF0001014062, DSF0001014063, DSF0001014064, DSF0001036326, DSF0001014076, DSF0001014058, DSF0001083967
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | SWIMMING POOL / FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / EXTERIOR DOORS / FLOOD ELIMINATION / PATH OF TRAVEL SWIMMING POOL | Design | Complete | 6/7/2023 | 10/11/2023 | 4/23/2024 | 1408606 | 945769 | 741077 | DSF0000849835, DSF0000913262, DSF0000913263, DSF0001014062, DSF0001014063, DSF0001014064, DSF0001036326, DSF0001014076, DSF0001014058, DSF0001083967
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | SWIMMING POOL / FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / EXTERIOR DOORS / FLOOD ELIMINATION / PATH OF TRAVEL SWIMMING POOL | Construction | In-Progress | 10/15/2024 | 4/2/2027 |  | 30648061 | 27800105 | 495845 | DSF0000849835, DSF0000913262, DSF0000913263, DSF0001014062, DSF0001014063, DSF0001014064, DSF0001036326, DSF0001014076, DSF0001014058, DSF0001083967
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | SWIMMING POOL / FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / EXTERIOR DOORS / FLOOD ELIMINATION / PATH OF TRAVEL SWIMMING POOL | CM,F&E | In-Progress | 10/15/2024 | 4/2/2027 |  | 2070063 | 192776 | 178223 | DSF0000849835, DSF0000913262, DSF0000913263, DSF0001014062, DSF0001014063, DSF0001014064, DSF0001036326, DSF0001014076, DSF0001014058, DSF0001083967
23 | K284 | P.S. 284 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 423000 | 423000 | 0 | DSF0001086070
23 | K284 | P.S. 284 - BROOKLYN | DOE - RESOA | FY09 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0000623079
23 | K284 | P.S. 284 - BROOKLYN | DOE - Skilled Trades | AUDITORIUM STAIRS | Construction | In-Progress | 2/6/2018 | DOES |  | DOES | 351904 | 0 | DSF0000827950
23 | K284 | P.S. 284 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 11/11/2021 | DOES |  | DOES | 60651 | 0 | DSF0000866113
23 | K298 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 7/6/2023 | 11/3/2023 | 7/7/2023 | 4760 | 1050 | 1050 | DSF0001035020
23 | K298 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 7/7/2023 | 1/4/2024 | 11/8/2023 | 21420 | 4201 | 4201 | DSF0001035020
23 | K298 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 4/23/2024 | 3/18/2025 |  | 276080 | 265884 | 153428 | DSF0001035020
23 | K298 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 4/23/2024 | 3/18/2025 |  | 106250 | 85713 | 65888 | DSF0001035020
23 | K298 | P.S. 298 - BROOKLYN | SCA IEH | PO18-PIPE CHASE BY GYMNASIUM ABATE PIPE INSULATION MARKED IN RED | Construction | In-Progress | 12/13/2024 | IEH |  | IEH | 0 | 0 | SCA0000073711
23 | K298 | P.S. 298 - BROOKLYN | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 360000 | 360000 | 359866 | DSF0001086074
23 | K298 | I.S. 363 - BROOKLYN | DOE - RESOA | FY21 RESO A STEM LAB | Construction | In-Progress | 3/11/2024 | DOER |  | DOER | 162769 | 0 | DSF0001008242
23 | K298 | P.S. 298 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/25/2022 | DOES |  | DOES | 64443 | 0 | DSF0001009053
23 | K298 | P.S. 298 - BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 11/21/2022 | DOES | 5/17/2024 | DOES | 265867 | 187432 | DSF0001034928
23 | K327 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | Scope | Complete | 3/8/2019 | 6/6/2019 | 5/23/2019 | 15539 | 36331 | 36331 | DSF0000912293
23 | K327 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | Design | Complete | 6/26/2019 | 12/31/2019 | 11/8/2019 | 77694 | 136735 | 136735 | DSF0000912293
23 | K327 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | Construction | In-Progress | 10/17/2022 | 1/9/2024 |  | 1748116 | 1605144 | 18818 | DSF0000912293
23 | K327 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 10/17/2022 | 1/9/2024 |  | 108772 | 78187 | 78187 | DSF0000912293
23 | K327 | P.S. 327 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/3/2023 | 11/17/2023 | 10/13/2023 | 120761 | 121975 | 121975 | DSF0001065401, DSF0001065402, DSF0001087240
23 | K327 | P.S. 327 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 10/16/2023 | 3/20/2024 | 3/26/2024 | 591584 | 357210 | 339597 | DSF0001065401, DSF0001065402, DSF0001087240
23 | K327 | P.S. 327 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 12253292 | 12253292 | 82761 | DSF0001065401, DSF0001065402, DSF0001087240
23 | K327 | P.S. 327 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 937010 | 937010 | 72544 | DSF0001065401, DSF0001065402, DSF0001087240
23 | K327 | P.S. 327 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/10/2024 | DIIR | 11/22/2024 | DIIR | 250000 | 250000 | DSF0001033063
23 | K327 | P.S. 327 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/28/2024 | DIIR | 12/5/2024 | DIIR | 154451 | 154451 | DSF0001086088
23 | K327 | P.S. 327 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112688
23 | K327 | P.S. 327 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75200 | 0 | DSF0000782865
23 | K327 | P.S. 327 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 798516 | 0 | DSF0000912218
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | Scope | Complete | 6/28/2019 | 12/27/2019 | 11/19/2019 | 138348 | 172518 | 166482 | DSF0000895932, DSF0000895933, DSF0000895934, DSF0000960659, DSF0001065478
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | Design | Complete | 12/3/2019 | 6/15/2020 | 5/1/2020 | 686840 | 480613 | 480613 | DSF0000895932, DSF0000895933, DSF0000895934, DSF0000960659, DSF0001065478
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | Construction | In-Progress | 8/5/2024 | 8/4/2026 |  | 15030267 | 13706847 | 200008 | DSF0000895932, DSF0000895933, DSF0000895934, DSF0000960659, DSF0001065478
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | CM,F&E | In-Progress | 8/5/2024 | 8/4/2026 |  | 1005165 | 177271 | 171624 | DSF0000895932, DSF0000895933, DSF0000895934, DSF0000960659, DSF0001065478
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/3/2024 | 9/4/2024 | 5/7/2024 | 3614 | 1182 | 1182 | DSF0001087452
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/7/2024 | 11/1/2024 | 8/7/2024 | 16263 | 4727 | 4727 | DSF0001087452
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/12/2024 | 11/6/2025 |  | 209612 | 197477 | 0 | DSF0001087452
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/12/2024 | 11/6/2025 |  | 38851 | 25781 | 6265 | DSF0001087452
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086090
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001086090
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001086090
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001086090
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087027
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087027
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087027
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087027
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 8/2/2018 | EMER |  | EMER | 57369 | 57369 | SCA0000051111
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA Emergency Response | EMERGENCY STABILIZATION- COPING STONES SPALLING BRICK | Construction | In-Progress | 10/26/2022 | EMER |  | EMER | 36351 | 18137 | SCA0000071535
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 408000 | 408000 | 408000 | DSF0001086091
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | DOE - RESOA | FY21 RESO A MAKER LAB UPGRADE | Construction | In-Progress | 9/22/2023 | DOER |  | DOER | 146284 | 0 | DSF0000961252
23 | K332 | P.S. 332 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75200 | 0 | DSF0000782921
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/18/2023 | 82651 | 153239 | 135836 | DSF0001065560, DSF0001087258
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 10/30/2023 | 6/28/2024 | 4/8/2024 | 408065 | 254074 | 251307 | DSF0001065560, DSF0001087258
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 8732472 | 8732472 | 20420 | DSF0001065560, DSF0001087258
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 617486 | 617486 | 11322 | DSF0001065560, DSF0001087258
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/30/2023 | 10/31/2023 | 7/25/2023 | 3684 | 1170 | 1170 | DSF0001035023
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/25/2023 | 1/23/2024 | 10/4/2023 | 16578 | 4682 | 4682 | DSF0001035023
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/16/2024 | 1/10/2025 |  | 213672 | 190022 | 147295 | DSF0001035023
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/16/2024 | 1/10/2025 |  | 64640 | 52344 | 40665 | DSF0001035023
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033559
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033559
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033559
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033559
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/28/2022 | 10/28/2022 | 2/8/2023 | 0 | 11667 | 1089 | DSF0001033560
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 11/21/2024 | 4/25/2025 |  | 30000 | 18333 | 4356 | DSF0001033560
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 2155 | DSF0001033560
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 1572 | DSF0001033560
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/14/2023 | 4/17/2024 | 6/5/2024 | 0 | 7205 | 1227 | DSF0001086096
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 7/10/2024 | 11/25/2024 |  | 24000 | 16795 | 4909 | DSF0001086096
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 352000 | 352000 | 0 | DSF0001086096
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 24000 | 24000 | 6400 | DSF0001086096
23 | K356 | I.S. 392 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 275000 | 0 | DSF0000961279
23 | K356 | P.S. 156 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/16/2024 | DIIR |  | DIIR | 100000 | 100000 | DSF0001033022
23 | K356 | P.S. 156 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001086097
23 | K356 | I.S. 392 - BROOKLYN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001086098
23 | K356 | P.S. 156 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112693
23 | K356 | P.S. 156 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/13/2023 | DOES |  | DOES | 495211 | 0 | DSF0001035098
23 | K396 | K396 SPED - BROOKLYN | DOE - RESOA | FY20 RESO A SENSORY GYM | Construction | Complete | 11/3/2023 | DOER | 5/23/2024 | DOER | 218314 | 2315 | DSF0000913271
23 | K396 | K396 SPED - BROOKLYN | DOE - RESOA | FY23 RESO A CAFETERIA/ MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 659894 | 0 | DSF0001035550
23 | K396 | K396 SPED - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/15/2022 | DOES |  | DOES | 223197 | 0 | DSF0001008683
23 | K854 | DOE ADMINISTRATIVE OFFICE - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 12/20/2024 | IEH |  | IEH | 0 | 0 | SCA0000073732
23 | KAIX | KEY COLLEGIATE CHARTER SCHOOL - BROOKLYN | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000961278
23 | KAIX | KEY COLLEGIATE CHARTER SCHOOL - BROOKLYN | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 6600 | 6600 | 0 | DSF0000961278
23 | KAIX | KEY COLLEGIATE CHARTER SCHOOL - BROOKLYN | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 96800 | 96800 | 0 | DSF0000961278
23 | KAIX | KEY COLLEGIATE CHARTER SCHOOL - BROOKLYN | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 6600 | 6600 | 0 | DSF0000961278
23 | KAYT | HOPE FAITH AND CHARITY | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 4/5/2021 | 5/28/2021 | 8/3/2021 | 14285 | 16472 | 16472 | DSF0001008770
23 | KAYT | HOPE FAITH AND CHARITY | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Design | Complete | 1/4/2022 | 5/4/2022 | 5/12/2023 | 64283 | 41240 | 36872 | DSF0001008770
23 | KAYT | HOPE FAITH AND CHARITY | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Construction | PNS | PNS | PNS | PNS | 828530 | 828530 | 152625 | DSF0001008770
23 | KAYT | HOPE FAITH AND CHARITY | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | CM,F&E | PNS | PNS | PNS | PNS | 153564 | 153564 | 22398 | DSF0001008770
23 | KBAC | LOVE IN ACTION DAY CARE | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 4/9/2021 | 7/9/2021 | 8/4/2021 | 19107 | 16161 | 16161 | DSF0001008771
23 | KBAC | LOVE IN ACTION DAY CARE | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Design | Complete | 1/4/2022 | 5/4/2022 | 10/22/2024 | 85983 | 17936 | 17936 | DSF0001008771
23 | KBAC | LOVE IN ACTION DAY CARE | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Construction | PNS | PNS | PNS | PNS | 1108232 | 1108232 | 79454 | DSF0001008771
23 | KBAC | LOVE IN ACTION DAY CARE | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | CM,F&E | PNS | PNS | PNS | PNS | 205405 | 205405 | 18344 | DSF0001008771
23 | KBAC | K000 - BROOKLYN | SCA CIP | PATH OF TRAVEL ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 5/15/2024 | 8/16/2024 | 10/22/2024 | 821 | 0 | 0 | DSF0001112184
23 | KBAC | K000 - BROOKLYN | SCA CIP | PATH OF TRAVEL ACS EARLY LEARN LEASE RENEWAL | Design | Complete | 10/23/2024 | 1/16/2025 | 10/23/2024 | 3694 | 0 | 0 | DSF0001112184
23 | KBAC | K000 - BROOKLYN | SCA CIP | PATH OF TRAVEL ACS EARLY LEARN LEASE RENEWAL | Construction | PNS | PNS | PNS | PNS | 47617 | 47617 | 0 | DSF0001112184
23 | KBAC | K000 - BROOKLYN | SCA CIP | PATH OF TRAVEL ACS EARLY LEARN LEASE RENEWAL | CM,F&E | PNS | PNS | PNS | PNS | 8826 | 8826 | 3209 | DSF0001112184
23 | KBDD | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 4/9/2021 | 7/9/2021 | 8/3/2021 | 13540 | 17412 | 17412 | DSF0001008773
23 | KBDD | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | Complete | 10/26/2022 | 3/29/2023 | 5/12/2023 | 60930 | 3995 | 3995 | DSF0001008773
23 | KBDD | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Construction | In-Progress | 1/8/2024 | 12/2/2024 |  | 785320 | 737713 | 307823 | DSF0001008773
23 | KBDD | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | CM,F&E | In-Progress | 1/8/2024 | 12/2/2024 |  | 145555 | 125784 | 32406 | DSF0001008773
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | Scope | Complete | 6/12/2014 | 9/11/2014 | 11/5/2014 | 70650 | 61506 | 61506 | DSF0000800040, DSF0000800039
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | Design | Complete | 11/13/2014 | 4/17/2015 | 8/21/2015 | 282600 | 797734 | 698090 | DSF0000800040, DSF0000800039
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | Construction | In-Progress | 1/19/2016 | 1/17/2017 |  | 5298750 | 6320949 | 4823138 | DSF0000800040, DSF0000800039
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | CM,F&E | In-Progress | 1/19/2016 | 1/17/2017 |  | 329700 | 641154 | 576165 | DSF0000800040, DSF0000800039
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | SMOKE PURGE SYSTEM | Scope | Complete | 3/14/2019 | 6/12/2019 | 11/27/2019 | 3872 | 18842 | 18842 | DSF0000912288
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | SMOKE PURGE SYSTEM | Design | Complete | 1/6/2020 | 2/6/2020 | 1/15/2020 | 17426 | 88325 | 88325 | DSF0000912288
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | SMOKE PURGE SYSTEM | Construction | PNS | PNS | PNS | PNS | 224597 | 224597 | 183 | DSF0000912288
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | SMOKE PURGE SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 41628 | 41628 | 11470 | DSF0000912288
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 8/12/2024 | 12/30/2024 | 12/16/2024 | 78611 | 93619 | 51396 | DSF0001071294
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | ROOFS | Design | PNS | PNS | PNS | PNS | 393053 | 393053 | 173242 | DSF0001071294
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 8843687 | 8843687 | 554 | DSF0001071294
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 550274 | 550274 | 31023 | DSF0001071294
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/15/2023 | 5/16/2023 | 4/28/2023 | 0 | 53735 | 52916 | DSF0001035791
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 5/1/2023 | 9/15/2023 | 9/22/2023 | 30000 | 59421 | 11509 | DSF0001035791
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 8/26/2024 | 6/21/2025 |  | 440000 | 380590 | 590 | DSF0001035791
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 8/26/2024 | 6/21/2025 |  | 30000 | 40205 | 9811 | DSF0001035791
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 846 | 846 | DSF0001112925
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 39000 | 38154 | 3385 | DSF0001112925
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 572000 | 572000 | 0 | DSF0001112925
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 39000 | 39000 | 0 | DSF0001112925
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113623
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113623
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113623
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113623
24 | Q005 | Q009 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/2/2024 | DIIR |  | DIIR | 113000 | 0 | DSF0001086342
24 | Q005 | I.S. 5 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112924
24 | Q005 | I.S. 5 - QUEENS | DOE - RESOA | FY20 RESO A MULTIMEDIA CENTER | Construction | Complete | 3/17/2023 | DOER | 6/10/2024 | DOER | 166495 | 34539 | DSF0000913357
24 | Q005 | I.S. 5 - QUEENS | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 193236 | 0 | DSF0000913358
24 | Q005 | I.S. 5 - QUEENS | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 63000 | 0 | DSF0001086340
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/29/2021 | 2/2/2022 | 7/15/2022 | 27650 | 41829 | 41829 | DSF0001034184
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 7/18/2022 | 12/2/2022 | 4/12/2023 | 138250 | 99532 | 92101 | DSF0001034184
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 10/10/2023 | 10/8/2024 |  | 3110625 | 2811163 | 798828 | DSF0001034184
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 10/10/2023 | 10/8/2024 |  | 193550 | 111757 | 67180 | DSF0001034184
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/1/2023 | 11/30/2023 | 11/15/2023 | 140732 | 154140 | 141482 | DSF0001071320, DSF0001111840, DSF0001111839, DSF0001111838
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 12/20/2023 | 5/22/2024 | 4/4/2024 | 703660 | 236107 | 236107 | DSF0001071320, DSF0001111840, DSF0001111839, DSF0001111838
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | PNS | PNS | PNS | PNS | 15832351 | 15832351 | 901 | DSF0001071320, DSF0001111840, DSF0001111839, DSF0001111838
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 985124 | 985124 | 21057 | DSF0001071320, DSF0001111840, DSF0001111839, DSF0001111838
24 | Q007 | P.S. 7 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 7/20/2022 | FTK |  | FTK | 263659 | 81540 | DSF0000961176
24 | Q007 | P.S. 7 - QUEENS | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001035228
24 | Q007 | P.S. 7 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 325000 | 0 | DSF0001112926
24 | Q007 | P.S. 7 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/3/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084261
24 | Q009 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | Scope | Complete | 12/17/2018 | 5/7/2021 | 5/20/2021 | 196818 | 226281 | 226281 | DSF0000911890, DSF0000900586, DSF0000994882
24 | Q009 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | Design | Complete | 5/21/2021 | 11/30/2021 | 1/31/2022 | 974931 | 797057 | 714741 | DSF0000911890, DSF0000900586, DSF0000994882
24 | Q009 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | Construction | In-Progress | 7/28/2023 | 10/19/2024 |  | 21143803 | 19122780 | 3029766 | DSF0000911890, DSF0000900586, DSF0000994882
24 | Q009 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | CM,F&E | In-Progress | 7/28/2023 | 10/19/2024 |  | 1446408 | 402650 | 317079 | DSF0000911890, DSF0000900586, DSF0000994882
24 | Q009 | Q009 SPED - QUEENS | Fast Track Projects | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 4/24/2023 | FTK |  | FTK | 77513 | 77490 | DSF0000867345
24 | Q009 | Q009 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112929
24 | Q009 | Q009 SPED - QUEENS | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/12/2024 | DOER |  | DOER | 231660 | 0 | DSF0000913184
24 | Q009 | Q009 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832 | 9274 | DSF0001084988
24 | Q012 | P.S. 12 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/9/2024 | 8/8/2024 | 5/8/2024 | 4329 | 4355 | 4355 | DSF0001087489
24 | Q012 | P.S. 12 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/8/2024 | 11/4/2024 | 10/30/2024 | 19479 | 17419 | 17419 | DSF0001087489
24 | Q012 | P.S. 12 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 251067 | 251067 | 1621 | DSF0001087489
24 | Q012 | P.S. 12 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 50798 | 50798 | 9130 | DSF0001087489
24 | Q012 | P.S. 12 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112933
24 | Q012 | P.S. 12 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 40000 | 0 | DSF0000488299
24 | Q012 | P.S. 12 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112189
24 | Q012 | P.S. 12 - QUEENS | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 6/24/2020 | DOES |  | DOES | 118453 | 0 | DSF0000865744
24 | Q013 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 6/24/2019 | 12/20/2019 | 11/19/2019 | 142812 | 291995 | 290127 | DSF0000900624, DSF0000900626, DSF0000900627, DSF0000960710, DSF0000946117
24 | Q013 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 12/2/2019 | 6/15/2020 | 5/4/2020 | 708443 | 534436 | 528325 | DSF0000900624, DSF0000900626, DSF0000900627, DSF0000960710, DSF0000946117
24 | Q013 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | In-Progress | 5/17/2021 | 11/2/2023 |  | 15453582 | 14210349 | 13708439 | DSF0000900624, DSF0000900626, DSF0000900627, DSF0000960710, DSF0000946117
24 | Q013 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | In-Progress | 5/17/2021 | 11/2/2023 |  | 1041860 | 1166157 | 1158818 | DSF0000900624, DSF0000900626, DSF0000900627, DSF0000960710, DSF0000946117
24 | Q013 | P.S. 13 - QUEENS | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Scope | Complete | 4/18/2024 | 7/19/2024 | 6/12/2024 | 0 | 16058 | 16058 | DSF0001086346
24 | Q013 | P.S. 13 - QUEENS | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Design | Complete | 6/24/2024 | 12/27/2024 | 9/13/2024 | 30000 | 34445 | 8231 | DSF0001086346
24 | Q013 | P.S. 13 - QUEENS | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 12/23/2024 | 9/18/2025 |  | 440000 | 187832 | 14527 | DSF0001086346
24 | Q013 | P.S. 13 - QUEENS | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | CM,F&E | In-Progress | 12/23/2024 | 9/18/2025 |  | 30000 | 17781 | 4768 | DSF0001086346
24 | Q013 | P.S. 13 - QUEENS | DOE - Skilled Trades | WATER MAIN LEAK REPAIR | Construction | In-Progress | 3/13/2024 | DOES |  | DOES | 88000 | 0 | DSF0001112083
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SOCCER PITCH / FY20 RESO A SOCCER PITCH | Scope | Complete | 3/4/2021 | 3/25/2022 | 3/14/2022 | 0 | 23842 | 23842 | DSF0000913361, DSF0000913362
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SOCCER PITCH / FY20 RESO A SOCCER PITCH | Design | Complete | 3/15/2022 | 5/11/2022 | 5/4/2022 | 41879 | 59903 | 55565 | DSF0000913361, DSF0000913362
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SOCCER PITCH / FY20 RESO A SOCCER PITCH | Construction | In-Progress | 10/9/2023 | 11/11/2024 |  | 614232 | 558681 | 283083 | DSF0000913361, DSF0000913362
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SOCCER PITCH / FY20 RESO A SOCCER PITCH | CM,F&E | In-Progress | 10/9/2023 | 11/11/2024 |  | 41879 | 71986 | 70808 | DSF0000913361, DSF0000913362
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/2/2021 | 6/30/2021 | 6/13/2023 | 0 | 34692 | 18055 | DSF0000913360, DSF0000913363
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 6/13/2023 | 10/13/2023 | 8/8/2023 | 33120 | 66064 | 54056 | DSF0000913360, DSF0000913363
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/22/2024 | 4/21/2025 |  | 485757 | 443842 | 123596 | DSF0000913360, DSF0000913363
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 4/22/2024 | 4/21/2025 |  | 33120 | 58188 | 29505 | DSF0000913360, DSF0000913363
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 2/1/2023 | 11/22/2023 | 1/11/2024 | 0 | 12249 | 12249 | DSF0001035798, DSF0001035799
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 1/12/2024 | 5/15/2024 | 2/16/2024 | 30000 | 36419 | 31116 | DSF0001035798, DSF0001035799
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | In-Progress | 7/15/2024 | 5/10/2025 |  | 440000 | 413116 | 20700 | DSF0001035798, DSF0001035799
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | In-Progress | 7/15/2024 | 5/10/2025 |  | 30000 | 62493 | 32960 | DSF0001035798, DSF0001035799
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 12/11/2023 | 7/10/2024 | 6/17/2024 | 0 | 8587 | 8587 | DSF0001086347, DSF0001087050
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 6/26/2024 | 11/12/2024 | 11/5/2024 | 31591 | 32630 | 11290 | DSF0001086347, DSF0001087050
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 463340 | 463340 | 1186 | DSF0001086347, DSF0001087050
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 31591 | 31591 | 9844 | DSF0001086347, DSF0001087050
24 | Q014 | P.S. 14 - QUEENS | SCA IEH | PO18-TEST CLOSET CEILINGS IN ROOMS 4417C & 4452 FOR ACM LOOSE PARTICLES ARE FALLING DOWN, HOLES EXPO | Construction | Complete | 8/1/2024 | IEH | 8/23/2024 | IEH | 0 | 0 | SCA0000073223
24 | Q014 | P.S. 14 - QUEENS | SCA IEH | PO18-TEST WALLS & CEILING FOR ACM IN RM 302 IF WALLS ARE POSITIVE, ABATE AND REPAIR DAMAGE AREA ABOV | Construction | Complete | 10/25/2024 | IEH | 10/27/2024 | IEH | 0 | 0 | SCA0000073546
24 | Q014 | P.S. 14 - QUEENS | SCA IEH | PO18-77/24Q014/DRILL HOLES IN ACM PLASTER FOR SPEAKERS & TO RUN WIRES 3 AREAS 250 PRINCIPALS OFFICE, | Construction | Complete | 11/6/2024 | IEH | 11/9/2024 | IEH | 0 | 0 | SCA0000073584
24 | Q014 | P.S. 14 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 2/21/2022 | FTK |  | FTK | 307586 | 189656 | DSF0000961030
24 | Q014 | P.S. 14 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500000 | 0 | DSF0001112934
24 | Q014 | P.S. 14 - QUEENS | DOE - RESOA | FY08 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0000544915
24 | Q014 | P.S. 14 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/19/2023 | DOER |  | DOER | 279947 | 0 | DSF0001009325
24 | Q014 | P.S. 14 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/8/2024 | DOES | 9/12/2024 | DOES | 65832 | 12504 | DSF0001084264
24 | Q019 | P.S. 19 - QUEENS | SCA CIP | PARAPETS / ROOFS / WINDOWS | Scope | Complete | 7/13/2023 | 11/29/2023 | 11/15/2023 | 98632 | 85284 | 84781 | DSF0001071528, DSF0001111843, DSF0001111842
24 | Q019 | P.S. 19 - QUEENS | SCA CIP | PARAPETS / ROOFS / WINDOWS | Design | Complete | 11/20/2023 | 4/23/2024 | 4/24/2024 | 488781 | 445368 | 335560 | DSF0001071528, DSF0001111843, DSF0001111842
24 | Q019 | P.S. 19 - QUEENS | SCA CIP | PARAPETS / ROOFS / WINDOWS | Construction | In-Progress | 11/4/2024 | 5/5/2026 |  | 10618464 | 9721643 | 76123 | DSF0001071528, DSF0001111843, DSF0001111842
24 | Q019 | P.S. 19 - QUEENS | SCA CIP | PARAPETS / ROOFS / WINDOWS | CM,F&E | In-Progress | 11/4/2024 | 5/5/2026 |  | 723297 | 57134 | 57134 | DSF0001071528, DSF0001111843, DSF0001111842
24 | Q019 | P.S. 19 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/8/2021 | 12/6/2021 | 11/17/2021 | 0 | 38780 | 38780 | DSF0000913104, DSF0000913105
24 | Q019 | P.S. 19 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 11/17/2021 | 3/18/2022 | 4/18/2022 | 115996 | 163648 | 155353 | DSF0000913104, DSF0000913105
24 | Q019 | P.S. 19 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 7/14/2022 | 7/13/2023 | 9/26/2024 | 1701274 | 1698734 | 1634388 | DSF0000913104, DSF0000913105
24 | Q019 | P.S. 19 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 7/14/2022 | 7/13/2023 | 9/26/2024 | 115996 | 105371 | 105102 | DSF0000913104, DSF0000913105
24 | Q019 | P.S. 19 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086350
24 | Q019 | P.S. 19 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/27/2022 | DOES |  | DOES | 120743 | 0 | DSF0001008970
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / REPLACEMENT OF RTUS / ROOFS | Scope | Complete | 5/21/2020 | 11/18/2020 | 10/8/2020 | 72015 | 140063 | 121498 | DSF0000956380, DSF0000956381, DSF0001008584, DSF0001005521
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / REPLACEMENT OF RTUS / ROOFS | Design | Complete | 10/20/2020 | 6/15/2021 | 4/14/2021 | 354828 | 312749 | 312749 | DSF0000956380, DSF0000956381, DSF0001008584, DSF0001005521
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / REPLACEMENT OF RTUS / ROOFS | Construction | PNS | PNS | PNS | PNS | 7529981 | 7529981 | 1266 | DSF0000956380, DSF0000956381, DSF0001008584, DSF0001005521
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / REPLACEMENT OF RTUS / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 543436 | 543436 | 14543 | DSF0000956380, DSF0000956381, DSF0001008584, DSF0001005521
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/30/2021 | 3/3/2022 | 2/28/2022 | 21300 | 29430 | 29430 | DSF0001034185
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 3/16/2022 | 7/29/2022 | 9/14/2022 | 106500 | 164288 | 156115 | DSF0001034185
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 5/15/2023 | 5/13/2024 |  | 2396250 | 2203581 | 2179427 | DSF0001034185
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 5/15/2023 | 5/13/2024 |  | 149100 | 193939 | 176412 | DSF0001034185
24 | Q028 | P.S. 28 - QUEENS | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 770 | 770 | DSF0000913367
24 | Q028 | P.S. 28 - QUEENS | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 3082 | 3082 | DSF0000913367
24 | Q028 | P.S. 28 - QUEENS | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913367
24 | Q028 | P.S. 28 - QUEENS | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913367
24 | Q028 | P.S. 28 - QUEENS | Fast Track Projects | LSP- SEWAGE EJECTOR PUMP | Construction | In-Progress | 10/23/2023 | FTK |  | FTK | 138549 | 133220 | DSF0000961038
24 | Q028 | P.S. 28 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035810
24 | Q028 | P.S. 28 - QUEENS | DOE - RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 465784 | 0 | DSF0001112255
24 | Q028 | P.S. 28 - QUEENS | DOE - RESOA | RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 73971 | 0 | DSF0001112254
24 | Q028 | P.S. 28 - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112253
24 | Q028 | P.S. 28 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112944
24 | Q028 | P.S. 28 - QUEENS | DOE - Skilled Trades | ACE BMS UPGRADE | Construction | In-Progress | 1/11/2023 | DOES |  | DOES | 958412 | 0 | DSF0001071659
24 | Q049 | P.S. 49 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/10/2024 | 10/25/2024 | 9/18/2024 | 142511 | 124936 | 124534 | DSF0001099755, DSF0001099758, DSF0001099757, DSF0001099759
24 | Q049 | P.S. 49 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | Design | In-Progress | 10/1/2024 | 3/7/2025 |  | 664049 | 664775 | 194478 | DSF0001099755, DSF0001099758, DSF0001099757, DSF0001099759
24 | Q049 | P.S. 49 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 10520978 | 10520978 | 13567 | DSF0001099755, DSF0001099758, DSF0001099757, DSF0001099759
24 | Q049 | P.S. 49 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1056267 | 1056267 | 51518 | DSF0001099755, DSF0001099758, DSF0001099757, DSF0001099759
24 | Q049 | P.S. 49 - QUEENS | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 50000 | 50000 | 0 | DSF0001112962
24 | Q049 | P.S. 49 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086364
24 | Q049 | P.S. 49 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 220000 | 0 | DSF0001033752
24 | Q049 | P.S. 49 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001034918
24 | Q049 | P.S. 49 - QUEENS | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 5/12/2023 | DOER | 7/26/2023 | DOER | 62453 |  | DSF0001035825
24 | Q049 | P.S. 49 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 155000 | 0 | DSF0001112961
24 | Q049 | P.S. 49 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/21/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084654
24 | Q058 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | Scope | Complete | 7/11/2019 | 11/26/2019 | 11/26/2019 | 58926 | 84236 | 54436 | DSF0000910388, DSF0000910389
24 | Q058 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | Design | Complete | 11/26/2019 | 4/29/2020 | 6/30/2020 | 286603 | 355464 | 348592 | DSF0000910388, DSF0000910389
24 | Q058 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | Construction | In-Progress | 6/25/2021 | 3/16/2023 |  | 5754009 | 5135286 | 4765245 | DSF0000910388, DSF0000910389
24 | Q058 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | CM,F&E | In-Progress | 6/25/2021 | 3/16/2023 |  | 472707 | 513913 | 510155 | DSF0000910388, DSF0000910389
24 | Q058 | Q009 SPED - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 35000 | 0 | DSF0000890239
24 | Q058 | P.S. 58 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0001008177
24 | Q058 | P.S. 58 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001033260
24 | Q058 | P.S. 58 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112966
24 | Q058 | P.S. 58 - QUEENS | DOE - RESOA | FY24 RESO A PLAYGROUND | Construction | PNS | PNS | PNS | PNS | DOER | 375000 | 0 | DSF0001086370
24 | Q058 | P.S. 58 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 255000 | 0 | DSF0001112965
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112970
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001112970
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001112970
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001112970
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113632
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113632
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113632
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113632
24 | Q061 | I.S. 61 - QUEENS | DIIT - RESOA | FY10 RESO A- DESKTOP COMPUTERS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500 | 0 | DSF0000690218
24 | Q061 | I.S. 61 - QUEENS | DOE - RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001035834
24 | Q061 | I.S. 61 - QUEENS | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 2/17/2021 | DOES | 3/3/2021 | DOES | 17638 | 43563 | DSF0000888987
24 | Q061 | I.S. 61 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/21/2023 | DOES | 3/15/2024 | DOES | 541029 | 528250 | DSF0001035101
24 | Q061 | I.S. 61 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/5/2024 | DOES | 8/14/2024 | DOES | 65832 | 9964 | DSF0001084801
24 | Q068 | P.S. 68 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/2/2024 | DIIR | 50000 | 50000 | DSF0001086377
24 | Q068 | P.S. 68 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112975
24 | Q068 | P.S. 68 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001033763
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Scope | Complete | 1/28/2021 | 12/30/2021 | 2/1/2022 | 92135 | 162811 | 162811 | DSF0000890866, DSF0000995873, DSF0001021643
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Design | Complete | 2/8/2022 | 7/8/2022 | 5/12/2023 | 436890 | 438626 | 360547 | DSF0000890866, DSF0000995873, DSF0001021643
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Construction | In-Progress | 9/14/2023 | 12/1/2025 |  | 8984548 | 8997837 | 3904315 | DSF0000890866, DSF0000995873, DSF0001021643
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 9/14/2023 | 12/1/2025 |  | 657395 | 333454 | 323420 | DSF0000890866, DSF0000995873, DSF0001021643
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/2/2024 | 9/3/2024 | 5/8/2024 | 7080 | 3387 | 3387 | DSF0001087504
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/8/2024 | 11/4/2024 | 10/30/2024 | 31860 | 13548 | 13548 | DSF0001087504
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 410641 | 410641 | 4200 | DSF0001087504
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 80374 | 80374 | 8106 | DSF0001087504
24 | Q071 | P.S. 71 - QUEENS | Fast Track Projects | LSP HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 11/20/2024 | FTK |  | FTK | 313096 | 40994 | DSF0001087251
24 | Q071 | P.S. 71 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 8/16/2024 | FTK |  | FTK | 603741 | 21035 | DSF0001112052
24 | Q071 | P.S. 71 - QUEENS | DIIT - Project Connect | DATA/VOICE & WIRELESS NETWORK CABLE WIRING, NETWORK SERVER EQUIPMENT, DATA/VOICE & WIRELESS NETWORK | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 298607 | 0 | DSF0000800165
24 | Q071 | P.S. 71 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086380
24 | Q071 | P.S. 71 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112978
24 | Q071 | P.S. 71 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 12/29/2023 | DOER | 8/22/2024 | DOER | 303014 | 272990 | DSF0001035335
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | Scope | Complete | 10/11/2011 | 1/12/2012 | 12/6/2011 | 27750 | 18465 | 18465 | DSF0000721890
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | Design | Complete | 12/15/2011 | 6/19/2012 | 4/24/2012 | 83250 | 94716 | 88277 | DSF0000721890
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | Construction | In-Progress | 11/28/2012 | 2/20/2014 |  | 1059125 | 1027565 | 846190 | DSF0000721890
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 11/28/2012 | 2/20/2014 |  | 212750 | 193004 | 186565 | DSF0000721890
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 10/3/2018 | 3/11/2019 | 12/5/2018 | 117150 | 147660 | 147660 | DSF0000885445, DSF0000890603
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/7/2018 | 5/10/2019 | 5/7/2019 | 468600 | 658499 | 636355 | DSF0000885445, DSF0000890603
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 7/22/2019 | 7/20/2021 |  | 8786250 | 7890345 | 6298476 | DSF0000885445, DSF0000890603
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 7/22/2019 | 7/20/2021 |  | 546700 | 996558 | 988228 | DSF0000885445, DSF0000890603
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 7/3/2019 | 10/2/2019 | 6/17/2021 | 18661 | 38050 | 38050 | DSF0000912583
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 6/29/2021 | 1/4/2022 | 1/21/2022 | 83973 | 65598 | 64429 | DSF0000912583
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 1082318 | 1082318 | 4696 | DSF0000912583
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 200602 | 200602 | 10754 | DSF0000912583
24 | Q073 | I.S. 73 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/8/2021 | 7/7/2021 | 6/11/2021 | 0 | 15659 | 15659 | DSF0000913185
24 | Q073 | I.S. 73 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 6/14/2021 | 11/15/2021 | 11/1/2021 | 45000 | 61620 | 61620 | DSF0000913185
24 | Q073 | I.S. 73 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 4/4/2022 | 12/29/2022 | 10/16/2024 | 660000 | 409058 | 332548 | DSF0000913185
24 | Q073 | I.S. 73 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 4/4/2022 | 12/29/2022 | 10/16/2024 | 45000 | 49261 | 46314 | DSF0000913185
24 | Q073 | I.S. 73 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE DAMAGED WOOD FLOOR IN ROOM 414 WITH VCT TILES | Construction | Complete | 10/25/2024 | IEH | 11/10/2024 | IEH | 0 | 0 | SCA0000073547
24 | Q073 | I.S. 73 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 538760 | 0 | DSF0000960108
24 | Q073 | I.S. 73 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112982
24 | Q073 | I.S. 73 - QUEENS | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 86377 | 0 | DSF0001033767
24 | Q073 | I.S. 73 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/13/2024 | DOES | 8/22/2024 | DOES | 65832 | 14313 | DSF0001084804
24 | Q073 | I.S. 73 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/16/2024 | DOES |  | DOES | 463341 | 0 | DSF0001085750
24 | Q073 | I.S. 73 - QUEENS | DOE - Skilled Trades | MASONRY REPAIRS | Construction | In-Progress | 1/9/2024 | DOES |  | DOES | 93507 | 74041 | DSF0001100196
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 10/15/2018 | 3/5/2019 | 1/31/2019 | 87983 | 354962 | 349513 | DSF0000878706, DSF0000878707, DSF0000878708, DSF0000878709, DSF0000912291
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/31/2019 | 7/2/2019 | 5/11/2022 | 439202 | 1115855 | 571960 | DSF0000878706, DSF0000878707, DSF0000878708, DSF0000878709, DSF0000912291
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 8/22/2022 | 5/12/2024 |  | 9820913 | 10102632 | 9489114 | DSF0000878706, DSF0000878707, DSF0000878708, DSF0000878709, DSF0000912291
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 8/22/2022 | 5/12/2024 |  | 621175 | 456112 | 452525 | DSF0000878706, DSF0000878707, DSF0000878708, DSF0000878709, DSF0000912291
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/18/2022 | 3/23/2023 | 12/9/2022 | 3311 | 7162 | 7162 | DSF0001034558
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/9/2022 | 6/7/2023 | 4/4/2023 | 14900 | 28648 | 28648 | DSF0001034558
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 8/7/2023 | 6/1/2024 | 10/10/2024 | 192038 | 174441 | 148654 | DSF0001034558
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 8/7/2023 | 6/1/2024 | 10/10/2024 | 127459 | 129692 | 89780 | DSF0001034558
24 | Q075 | Q075 SPED - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 5/21/2021 | 2/23/2022 | 2/24/2023 | 0 | 19024 | 0 | DSF0000913386
24 | Q075 | Q075 SPED - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 2/27/2023 | 6/30/2023 | 3/10/2023 | 0 | 0 | 0 | DSF0000913386
24 | Q075 | Q075 SPED - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913386
24 | Q075 | Q075 SPED - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 631 | 631 | DSF0000913386
24 | Q075 | Q075 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 6/4/2024 | DIIR | 232000 | 232000 | DSF0001035230
24 | Q075 | Q075 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 287000 | 0 | DSF0001112984
24 | Q075 | Q075 SPED - QUEENS | DOE - RESOA | FY20 RESO AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 630976 | 0 | DSF0000913387
24 | Q075 | Q075 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/14/2024 | DOES | 8/20/2024 | DOES | 65832 | 14928 | DSF0001084657
24 | Q081 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | Scope | Complete | 8/17/2023 | 1/5/2024 | 12/8/2023 | 97939 | 240644 | 209644 | DSF0001072566, DSF0001072567, DSF0001100313, DSF0001111883, DSF0001100316
24 | Q081 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | Design | Complete | 12/14/2023 | 5/16/2024 | 5/3/2024 | 489696 | 549368 | 533688 | DSF0001072566, DSF0001072567, DSF0001100313, DSF0001111883, DSF0001100316
24 | Q081 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | Construction | In-Progress | 8/12/2024 | 5/3/2026 |  | 11018171 | 10160598 | 237506 | DSF0001072566, DSF0001072567, DSF0001100313, DSF0001111883, DSF0001100316
24 | Q081 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | CM,F&E | In-Progress | 8/12/2024 | 5/3/2026 |  | 685576 | 170439 | 164756 | DSF0001072566, DSF0001072567, DSF0001100313, DSF0001111883, DSF0001100316
24 | Q081 | P.S. 81 - QUEENS | SCA IEH | PO18-CHOP OUT FLOOR APRROX 18' X 18' AROUND DRAIN PIPE PENETRATING FLOOR LOCATED , TEACHERS CAFETERI | Construction | Complete | 7/26/2024 | IEH | 10/19/2024 | IEH | 0 | 0 | SCA0000073182
24 | Q081 | P.S. 81 - QUEENS | DOE - RESOA | FY23 RESO A FLOORING | Construction | In-Progress | 7/5/2024 | DOER |  | DOER | 484599 | 0 | DSF0001035854
24 | Q081 | P.S. 81 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 5/19/2021 | DOES |  | DOES | 112416 | 0 | DSF0000891070
24 | Q081 | P.S. 81 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 6/1/2022 | DOES |  | DOES | 98766 | 0 | DSF0001008971
24 | Q081 | P.S. 81 - QUEENS | DOE - Skilled Trades | WATER MAIN VALVE REPLACEMENT | Construction | In-Progress | 1/19/2024 | DOES |  | DOES | 115607 | 0 | DSF0001112062
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/22/2021 | 2/28/2022 | 6/15/2022 | 8471 | 11985 | 11985 | SCA0000070746, DSF0001036320
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 9/21/2022 | 2/9/2023 | 3/3/2023 | 38121 | 31392 | 27731 | SCA0000070746, DSF0001036320
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 491337 | 491337 | 53 | SCA0000070746, DSF0001036320
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 91067 | 91067 | 15447 | SCA0000070746, DSF0001036320
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 6/21/2023 | 11/6/2023 | 11/1/2023 | 81356 | 137447 | 121550 | DSF0001072671, DSF0001111781
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | Complete | 11/17/2023 | 4/22/2024 | 5/1/2024 | 406777 | 240537 | 233395 | DSF0001072671, DSF0001111781
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Construction | PNS | PNS | PNS | PNS | 9152496 | 9152496 | 39417 | DSF0001072671, DSF0001111781
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 569488 | 569488 | 35615 | DSF0001072671, DSF0001111781
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY19 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Scope | Complete | 12/6/2018 | 4/10/2019 | 6/10/2019 | 0 | 36143 | 36143 | DSF0000890687
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY19 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Design | Complete | 7/25/2019 | 12/11/2019 | 6/23/2020 | 186000 | 222451 | 220476 | DSF0000890687
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY19 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Construction | In-Progress | 8/3/2022 | 9/1/2023 |  | 2728000 | 1391210 | 1285516 | DSF0000890687
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY19 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | CM,F&E | In-Progress | 8/3/2022 | 9/1/2023 |  | 186000 | 124561 | 124561 | DSF0000890687
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Scope | Complete | 2/8/2023 | 6/8/2023 | 6/28/2023 | 0 | 19029 | 19029 | DSF0001035857
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Design | In-Progress | 7/12/2023 | 1/12/2024 |  | 90000 | 70971 | 6767 | DSF0001035857
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 12446 | DSF0001035857
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 23698 | DSF0001035857
24 | Q087 | P.S. 87 - QUEENS | DIIT - RESOA | FY09 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 264187 | 0 | DSF0000623130
24 | Q087 | P.S. 87 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112989
24 | Q087 | P.S. 87 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/20/2023 | DOER |  | DOER | 93592 | 0 | DSF0001033780
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2/6/2018 | 5/7/2018 | 3/23/2018 | 26304 | 23219 | 23219 | DSF0000878883
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 4/25/2018 | 10/26/2018 | 8/27/2018 | 96448 | 104511 | 76899 | DSF0000878883
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 4/3/2019 | 4/1/2020 |  | 1021472 | 1006444 | 752824 | DSF0000878883
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 4/3/2019 | 4/1/2020 |  | 236736 | 308551 | 303456 | DSF0000878883
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/19/2019 | 2/21/2020 | 4/21/2021 | 17468 | 67116 | 67116 | DSF0000914315
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | Design | Complete | 4/27/2021 | 9/10/2021 | 5/11/2022 | 87340 | 111596 | 111596 | DSF0000914315
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 12/16/2022 | 12/15/2023 |  | 1965150 | 1836973 | 1610534 | DSF0000914315
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 12/16/2022 | 12/15/2023 |  | 122276 | 175836 | 162097 | DSF0000914315
24 | Q088 | P.S. 88 - QUEENS | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/5/2024 | FTK |  | FTK | 503101 | 419489 | DSF0001035050
24 | Q088 | P.S. 88 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112990
24 | Q088 | P.S. 88 - QUEENS | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 6/30/2022 | DOER |  | DOER | 451053 | 0 | DSF0001033269
24 | Q088 | P.S. 88 - QUEENS | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | Complete | 7/22/2022 | DOER | 10/17/2022 | DOER | 151796 | 149753 | DSF0001034493
24 | Q088 | P.S. 88 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/29/2022 | DOER |  | DOER | 176787 | 0 | DSF0001034914
24 | Q088 | P.S. 88 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/19/2021 | DOES |  | DOES | 80839 | 0 | DSF0000866128
24 | Q088 | P.S. 88 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 5/23/2022 | DOES |  | DOES | 55978 | 0 | DSF0001034250
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT / VENTILATION | Scope | Complete | 3/14/2019 | 7/15/2019 | 1/21/2020 | 65275 | 141000 | 133051 | DSF0001035183, DSF0001021954
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT / VENTILATION | Design | Complete | 1/21/2020 | 6/19/2020 | 9/30/2022 | 326375 | 294096 | 268998 | DSF0001035183, DSF0001021954
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT / VENTILATION | Construction | PNS | PNS | PNS | PNS | 7343426 | 7343426 | 30000 | DSF0001035183, DSF0001021954
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT / VENTILATION | CM,F&E | PNS | PNS | PNS | PNS | 456924 | 456924 | 31277 | DSF0001035183, DSF0001021954
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | ROOFS / WINDOWS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 6/20/2023 | 11/3/2023 | 11/7/2023 | 115182 | 181552 | 181552 | DSF0001072709, DSF0001111822, DSF0001111821, DSF0001111820
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | ROOFS / WINDOWS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 11/13/2023 | 4/16/2024 | 4/30/2024 | 568834 | 319390 | 303878 | DSF0001072709, DSF0001111822, DSF0001111821, DSF0001111820
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | ROOFS / WINDOWS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 12186966 | 12186966 | 30932 | DSF0001072709, DSF0001111822, DSF0001111821, DSF0001111820
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | ROOFS / WINDOWS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 859318 | 859318 | 45626 | DSF0001072709, DSF0001111822, DSF0001111821, DSF0001111820
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | AIR HANDLING UNITS | Scope | Complete | 11/14/2023 | 11/14/2023 | 11/14/2023 | 10646 | 10341 | 10341 | DSF0001111800
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | AIR HANDLING UNITS | Design | Complete | 11/14/2023 | 5/15/2024 | 5/15/2024 | 53230 | 73086 | 66520 | DSF0001111800
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | AIR HANDLING UNITS | Construction | PNS | PNS | PNS | PNS | 1197674 | 1197674 | 2644 | DSF0001111800
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | AIR HANDLING UNITS | CM,F&E | PNS | PNS | PNS | PNS | 74522 | 74522 | 9531 | DSF0001111800
24 | Q089 | P.S. 89 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN 1ST FLOOR HALLWAY APPROX. 396SF | Construction | In-Progress | 5/28/2024 | IEH |  | IEH | 0 | 0 | SCA0000073028
24 | Q089 | P.S. 89 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 10/23/2023 | FTK |  | FTK | 534986 | 269273 | DSF0000947299
24 | Q089 | P.S. 89 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 51000 | 0 | DSF0001035336
24 | Q089 | P.S. 89 - QUEENS | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/31/2023 | DOER |  | DOER | 443333 | 0 | DSF0000867271
24 | Q089 | P.S. 89 - QUEENS | DOE - RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 315128 | 0 | DSF0001035860
24 | Q089 | P.S. 89 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086394
24 | Q089 | P.S. 89 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/7/2020 | DOES |  | DOES | 192500 | 0 | DSF0001021941
24 | Q089 | P.S. 89 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/21/2024 | DOES | 9/12/2024 | DOES | 65832 |  | DSF0001084312
24 | Q091 | P.S. 91 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR PIPE/ JOINT INSULATION, CEILING PLASTER, WALL PLASTER, WALL BOARD MASTIC, FIRE | Construction | In-Progress | 12/21/2022 | IEH |  | IEH | 0 | 0 | SCA0000071645
24 | Q091 | P.S. 91 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112995
24 | Q091 | P.S. 91 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/12/2024 | DOER |  | DOER | 199080 | 0 | DSF0001033785
24 | Q091 | P.S. 91 - QUEENS | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 4/30/2021 | DOES |  | DOES | 185484 | 0 | DSF0000865745
24 | Q091 | P.S. 91 - QUEENS | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 5/7/2024 | DOES |  | DOES | 74916 | 0 | DSF0001100506
24 | Q093 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 8/27/2014 | 4/13/2015 | 3/9/2015 | 309057 | 263846 | 263846 | DSF0000800329, DSF0000812371, DSF0000789064, DSF0000789066, DSF0000812370
24 | Q093 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 5/1/2015 | 11/16/2017 | 4/19/2018 | 1227451 | 1721899 | 1423742 | DSF0000800329, DSF0000812371, DSF0000789064, DSF0000789066, DSF0000812370
24 | Q093 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 7/20/2018 | 8/7/2020 |  | 22226862 | 23990186 | 13297092 | DSF0000800329, DSF0000812371, DSF0000789064, DSF0000789066, DSF0000812370
24 | Q093 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 7/20/2018 | 8/7/2020 |  | 1556381 | 1796327 | 1620640 | DSF0000800329, DSF0000812371, DSF0000789064, DSF0000789066, DSF0000812370
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112996
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 41040 | 41040 | 0 | DSF0001112996
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 601920 | 601920 | 0 | DSF0001112996
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 41040 | 41040 | 0 | DSF0001112996
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113636
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113636
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113636
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113636
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 7/3/2024 | 11/4/2024 | 10/3/2024 | 0 | 31682 | 31682 | DSF0001086395
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 10/4/2024 | 3/12/2025 |  | 45000 | 45000 | 77728 | DSF0001086395
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001086395
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 18916 | DSF0001086395
24 | Q093 | I.S. 93 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033787
24 | Q093 | I.S. 93 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035864
24 | Q093 | I.S. 93 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112997
24 | Q093 | I.S. 93 - QUEENS | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 3/22/2024 | DOEL |  | DOEL | 68461 | 68461
24 | Q093 | Q075 SPED - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 159856 | 0 | DSF0001008708
24 | Q093 | I.S. 93 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/7/2024 | DOES | 8/14/2024 | DOES | 65832 | 19006 | DSF0001084806
24 | Q102 | P.S. 102 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033794
24 | Q102 | P.S. 102 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033794
24 | Q102 | P.S. 102 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033794
24 | Q102 | P.S. 102 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033794
24 | Q102 | P.S. 102 - QUEENS | SCA IEH | PO18-TEST ROOM 338 & IF POSITIVE ABATE & REPLACE TEST ALL LAYERS OF FLOOR PLEASE NOTIFY ALL COPIED O | Construction | Complete | 7/17/2024 | IEH | 9/1/2024 | IEH | 0 | 0 | SCA0000073146
24 | Q102 | P.S. 102 - QUEENS | SCA IEH | PO18-77/24Q102/ ACM TESTING OF CEILING CLASSROOM 321 PLASTER AND PAINT HAS FALLEN FROM THE CEILING R | Construction | Complete | 9/17/2024 | IEH | 9/21/2024 | IEH | 0 | 0 | SCA0000073387
24 | Q102 | P.S. 102 - QUEENS | SCA IEH | PO18-ABATE & OPEN UP APPROXIMATELY 15 SQ. FT OF FLOOR AT 2ND FLOOR - AUDITORIUM STAGE | Construction | In-Progress | 12/11/2024 | IEH |  | IEH | 0 | 0 | SCA0000073695
24 | Q102 | P.S. 102 - QUEENS | Fast Track Projects | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 12/20/2018 | FTK |  | FTK | 100215 | 83625 | DSF0000890874
24 | Q102 | P.S. 102 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/29/2023 | DIIR | 6/17/2024 | DIIR | 199296 | 199296 | DSF0001033270
24 | Q102 | P.S. 102 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001035871
24 | Q102 | P.S. 102 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/28/2024 | DIIR | 11/4/2024 | DIIR | 49822 | 49822 | DSF0001086400
24 | Q102 | P.S. 102 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113005
24 | Q102 | P.S. 102 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 240000 | 0 | DSF0001113004
24 | Q102 | P.S. 102 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/30/2024 | DOES | 11/11/2024 | DOES | 65832 |  | DSF0001084660
24 | Q113 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 7/5/2022 | 11/18/2022 | 11/2/2023 | 44636 | 137102 | 87003 | DSF0001022372, DSF0001111773
24 | Q113 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | Complete | 11/8/2023 | 4/12/2024 | 5/15/2024 | 214997 | 168062 | 122830 | DSF0001022372, DSF0001111773
24 | Q113 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 9/9/2024 | 3/2/2026 |  | 4129279 | 3725057 | 274473 | DSF0001022372, DSF0001111773
24 | Q113 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 9/9/2024 | 3/2/2026 |  | 373856 | 110426 | 106022 | DSF0001022372, DSF0001111773
24 | Q113 | P.S. 113 - QUEENS | Fast Track Projects | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 9/7/2023 | FTK |  | FTK | 422400 | 370091 | DSF0001035876
24 | Q113 | P.S. 113 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/24/2023 | DIIR |  | DIIR | 50000 | 0 | DSF0001035875
24 | Q113 | P.S. 113 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113011
24 | Q113 | P.S. 113 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2/1/2023 | DOER | 12/12/2023 | DOER | 94087 | 26359 | DSF0001008162
24 | Q113 | P.S. 113 - QUEENS | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/3/2023 | DOER |  | DOER | 68331 | 0 | DSF0001033799
24 | Q113 | P.S. 113 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113010
24 | Q113 | P.S. 113 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/16/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084663
24 | Q119 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | Scope | Complete | 6/24/2019 | 12/20/2019 | 11/18/2019 | 207142 | 390013 | 390013 | DSF0000902236, DSF0000902234, DSF0000902237, DSF0000902238, DSF0000902239, DSF0000902233, DSF0000960625, DSF0000947795
24 | Q119 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | Design | Complete | 12/2/2019 | 6/15/2020 | 5/12/2020 | 1021278 | 706158 | 687663 | DSF0000902236, DSF0000902234, DSF0000902237, DSF0000902238, DSF0000902239, DSF0000902233, DSF0000960625, DSF0000947795
24 | Q119 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | Construction | In-Progress | 3/2/2022 | 2/29/2024 |  | 21730387 | 20275875 | 18606538 | DSF0000902236, DSF0000902234, DSF0000902237, DSF0000902238, DSF0000902239, DSF0000902233, DSF0000960625, DSF0000947795
24 | Q119 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | CM,F&E | In-Progress | 3/2/2022 | 2/29/2024 |  | 1558231 | 785088 | 757005 | DSF0000902236, DSF0000902234, DSF0000902237, DSF0000902238, DSF0000902239, DSF0000902233, DSF0000960625, DSF0000947795
24 | Q119 | I.S. 119 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Scope | Complete | 3/2/2023 | 7/3/2023 | 8/23/2023 | 0 | 18419 | 18419 | DSF0001035883
24 | Q119 | I.S. 119 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Design | Complete | 9/5/2023 | 2/8/2024 | 5/24/2024 | 27234 | 64929 | 30021 | DSF0001035883
24 | Q119 | I.S. 119 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Construction | In-Progress | 11/4/2024 | 8/30/2025 |  | 399430 | 334481 | 3393 | DSF0001035883
24 | Q119 | I.S. 119 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE | CM,F&E | In-Progress | 11/4/2024 | 8/30/2025 |  | 27234 | 39830 | 15428 | DSF0001035883
24 | Q119 | I.S. 119 - QUEENS | Fast Track Projects | LSP REPLACEMENT OF GAS FIRED WATER HEATER | Construction | In-Progress | 9/8/2020 | FTK |  | FTK | 170828 | 106350 | DSF0000914283
24 | Q119 | I.S. 119 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 7/2/2024 | DIIR | 50000 | 23819 | DSF0001086412
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY09 RESO A- AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 35369 | 0 | DSF0000709496
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY18 RESO A ROOM CONVERSION/PARTITIONING | Construction | In-Progress | 9/10/2018 | DOER |  | DOER | 63596 | 0 | DSF0000867263
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/30/2023 | DOER |  | DOER | 286036 | 0 | DSF0001008159
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 14318 | 0 | DSF0001033804
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 135000 | 0 | DSF0001113015
24 | Q119 | I.S. 119 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/15/2024 | DOES | 8/22/2024 | DOES | 65832 | 22173 | DSF0001084666
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | Scope | Complete | 9/19/2019 | 2/25/2020 | 7/19/2021 | 26700 | 41343 | 41343 | DSF0000912584
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | Design | Complete | 11/8/2021 | 3/29/2022 | 3/16/2022 | 133500 | 130839 | 125914 | DSF0000912584
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | Construction | In-Progress | 3/6/2023 | 3/4/2025 |  | 3003750 | 2968057 | 2250460 | DSF0000912584
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | CM,F&E | In-Progress | 3/6/2023 | 3/4/2025 |  | 186900 | 150446 | 135834 | DSF0000912584
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 1/19/2023 | 6/5/2023 | 11/8/2023 | 12366 | 62157 | 62157 | DSF0001073391
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 11/20/2023 | 4/23/2024 | 8/2/2024 | 61828 | 83294 | 81418 | DSF0001073391
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 1391129 | 1391129 | 15845 | DSF0001073391
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 86559 | 86559 | 28079 | DSF0001073391
24 | Q125 | I.S. 125 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 81000 | 0 | DSF0001086416
24 | Q125 | I.S. 125 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113020
24 | Q125 | I.S. 125 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/24/2022 | DOER |  | DOER | 65723 | 0 | DSF0001008108
24 | Q125 | I.S. 125 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 6/1/2020 | DOES |  | DOES | 60341 | 0 | DSF0000866129
24 | Q125 | I.S. 125 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/21/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084808
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | PHASE 3-PLAYGROUND REDEVELOPMENT FOR JOP | Scope | Complete | 12/12/2018 | 4/16/2019 | 7/15/2019 | 27774 | 69137 | 55972 | DSF0000798195
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | PHASE 3-PLAYGROUND REDEVELOPMENT FOR JOP | Design | Complete | 7/17/2019 | 12/3/2019 | 5/11/2022 | 138868 | 286773 | 185561 | DSF0000798195
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | PHASE 3-PLAYGROUND REDEVELOPMENT FOR JOP | Construction | PNS | PNS | PNS | PNS | 3124536 | 3124536 | 9666 | DSF0000798195
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | PHASE 3-PLAYGROUND REDEVELOPMENT FOR JOP | CM,F&E | PNS | PNS | PNS | PNS | 194416 | 194416 | 20422 | DSF0000798195
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | Scope | Complete | 6/25/2019 | 12/28/2020 | 11/5/2020 | 329900 | 348857 | 341857 | DSF0000902669, DSF0000902670, DSF0000902671, DSF0000960662, DSF0000948236, DSF0000948250, DSF0000948238, DSF0001007720
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | Design | Complete | 11/5/2020 | 4/12/2021 | 4/28/2021 | 1649501 | 958834 | 867413 | DSF0000902669, DSF0000902670, DSF0000902671, DSF0000960662, DSF0000948236, DSF0000948250, DSF0000948238, DSF0001007720
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | Construction | In-Progress | 10/24/2022 | 4/10/2025 |  | 37113749 | 34277929 | 11984332 | DSF0000902669, DSF0000902670, DSF0000902671, DSF0000960662, DSF0000948236, DSF0000948250, DSF0000948238, DSF0001007720
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | CM,F&E | In-Progress | 10/24/2022 | 4/10/2025 |  | 2328816 | 1365150 | 1339921 | DSF0000902669, DSF0000902670, DSF0000902671, DSF0000960662, DSF0000948236, DSF0000948250, DSF0000948238, DSF0001007720
24 | Q143 | P.S. 143 - QUEENS | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 7/24/2024 |  | 9/23/2024 | 75000 | 75000 | 74606 | DSF0001035236
24 | Q143 | P.S. 143 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033275
24 | Q143 | P.S. 143 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 175000 | 174342 | DSF0001086432
24 | Q143 | P.S. 143 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/30/2024 | DOER |  | DOER | 49567 | 0 | DSF0001035909
24 | Q143 | P.S. 143 - QUEENS | DOE - RESOA | FY24 RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 123000 | 0 | DSF0001086433
24 | Q143 | P.S. 143 - QUEENS | DOE - RESOA | FY25 RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001113039
24 | Q143 | P.S. 143 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/11/2017 | DOES |  | DOES | 174753 | 0 | DSF0000866036
24 | Q143 | P.S. 143 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/26/2024 | DOES | 8/1/2024 | DOES | 65832 |  | DSF0001084343
24 | Q153 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 7/22/2019 | 10/21/2019 | 9/25/2019 | 19800 | 15800 | 15800 | DSF0000902868
24 | Q153 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 12/18/2019 | 5/20/2020 | 5/8/2020 | 89100 | 63315 | 63315 | DSF0000902868
24 | Q153 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Construction | In-Progress | 7/26/2021 | 5/21/2022 |  | 1148399 | 1023642 | 996402 | DSF0000902868
24 | Q153 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 7/26/2021 | 5/21/2022 |  | 212850 | 250870 | 247921 | DSF0000902868
24 | Q153 | P.S. 153 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033824
24 | Q153 | P.S. 153 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113049
24 | Q153 | P.S. 153 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | Complete | 11/22/2023 | DOER | 12/7/2023 | DOER | 507487 | 25765 | DSF0001008158
24 | Q153 | P.S. 153 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0 | DSF0001033823
24 | Q153 | P.S. 153 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 110000 | 0 | DSF0001085190
24 | Q153 | P.S. 153 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 110000 | 0 | DSF0001086442
24 | Q199 | P.S. 199 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001036088
24 | Q199 | P.S. 199 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113084
24 | Q199 | P.S. 199 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001035968
24 | Q199 | P.S. 199 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/9/2024 | DOER |  | DOER | 303202 | 0 | DSF0001111875
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | Scope | Complete | 3/12/2018 | 6/8/2018 | 5/14/2019 | 25050 | 41920 | 41920 | DSF0000881069
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | Design | Complete | 5/14/2019 | 10/15/2019 | 5/16/2019 | 91850 | 99064 | 88531 | DSF0000881069
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | Construction | In-Progress | 7/15/2019 | 7/13/2020 |  | 972775 | 1039080 | 817618 | DSF0000881069
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 7/15/2019 | 7/13/2020 |  | 225450 | 107285 | 101880 | DSF0000881069
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 12/19/2018 | 7/26/2019 | 3/28/2019 | 19950 | 6024 | 6024 | DSF0000868233, DSF0000912427
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 3/28/2019 | 8/27/2019 | 5/10/2019 | 73150 | 24225 | 24225 | DSF0000868233, DSF0000912427
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/22/2019 | 4/16/2020 |  | 774725 | 932275 | 931334 | DSF0000868233, DSF0000912427
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 7/22/2019 | 4/16/2020 |  | 179550 | 109597 | 109597 | DSF0000868233, DSF0000912427
24 | Q229 | P.S. 229 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033873
24 | Q229 | P.S. 229 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033873
24 | Q229 | P.S. 229 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033873
24 | Q229 | P.S. 229 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033873
24 | Q229 | P.S. 229 - QUEENS | SCA IEH | PO18-PLEASE REPLACE FLOOR 9X9 TILE APPROX 1000 SQ FT AND REMOVE BOOKSHELVES CONTAINS POSS ACM LOCATI | Construction | Complete | 5/17/2023 | IEH | 11/10/2024 | IEH | 0 | 0 | SCA0000071985
24 | Q229 | P.S. 229 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113109
24 | Q229 | P.S. 229 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/22/2021 | DOER |  | DOER | 116689 | 0 | DSF0001008167
24 | Q229 | P.S. 229 - QUEENS | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 79141 | 0 | DSF0001033874
24 | Q229 | P.S. 229 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 9/18/2023 | DOER | 8/22/2024 | DOER | 754633 |  | DSF0001036000
24 | Q229 | P.S. 229 - QUEENS | DOE - Skilled Trades | BOILER REPAIR | Construction | In-Progress | 2/5/2020 | DOES |  | DOES | 1351480 | 0 | DSF0000960697
24 | Q229 | P.S. 229 - QUEENS | Trust For Public Land | FY22 RESO A PLAYGROUND UPGRADE | Construction | Complete | 1/2/2024 | TPL | 10/1/2024 | TPL | 2700000 | 2442826 | DSF0001033298
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 8/12/2019 | 12/13/2019 | 3/25/2021 | 77600 | 111569 | 111569 | DSF0000910517, DSF0001024628, DSF0001024629
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 10/28/2021 | 4/25/2022 | 9/19/2022 | 388000 | 567782 | 302191 | DSF0000910517, DSF0001024628, DSF0001024629
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 3/21/2024 | 3/20/2026 |  | 8730000 | 7837809 | 227957 | DSF0000910517, DSF0001024628, DSF0001024629
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 3/21/2024 | 3/20/2026 |  | 543200 | 43497 | 43387 | DSF0000910517, DSF0001024628, DSF0001024629
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/30/2022 | 11/16/2022 | 3/27/2023 | 17175 | 55231 | 53469 | DSF0001024634
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | EXTERIOR MASONRY | Design | Complete | 4/4/2023 | 9/5/2023 | 9/6/2023 | 85875 | 70796 | 56609 | DSF0001024634
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 1932192 | 1932192 | 962 | DSF0001024634
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 120225 | 120225 | 6118 | DSF0001024634
24 | Q239 | P.S. 239 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/16/2023 | 5/17/2023 | 6/15/2023 | 0 | 33769 | 33769 | DSF0001036007
24 | Q239 | P.S. 239 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 6/27/2023 | 11/13/2023 | 1/26/2024 | 38275 | 48501 | 47470 | DSF0001036007
24 | Q239 | P.S. 239 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 561363 | 561363 | 145 | DSF0001036007
24 | Q239 | P.S. 239 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 38275 | 38275 | 5058 | DSF0001036007
24 | Q239 | P.S. 239 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 3/31/2022 | FTK |  | FTK | 226636 | 98712 | DSF0000960899
24 | Q239 | P.S. 239 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/20/2021 | DOER |  | DOER | 258791 | 0 | DSF0001008427
24 | Q239 | P.S. 239 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/12/2024 | DOER |  | DOER | 72633 | 0 | DSF0001086490
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | DCAS ROOFS / DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | Complete | 12/4/2023 | 5/3/2024 | 4/18/2024 | 128180 | 163769 | 163769 | DSF0001075462, DSF0001087155
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | DCAS ROOFS / DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | Complete | 4/18/2024 | 11/13/2024 | 9/25/2024 | 598174 | 329283 | 26451 | DSF0001075462, DSF0001087155
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | DCAS ROOFS / DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS | Construction | PNS | PNS | PNS | PNS | 9485339 | 9485339 | 187 | DSF0001075462, DSF0001087155
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | DCAS ROOFS / DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 939989 | 939989 | 61457 | DSF0001075462, DSF0001087155
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/24/2022 | 7/22/2022 | 4/11/2022 | 3050 | 4095 | 4095 | DSF0001034372
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/11/2022 | 10/4/2022 | 8/17/2022 | 13725 | 16381 | 16381 | DSF0001034372
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | Complete | 2/21/2023 | 12/17/2023 | 12/8/2023 | 176900 | 153265 | 130914 | DSF0001034372
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | Complete | 2/21/2023 | 12/17/2023 | 12/8/2023 | 114181 | 125808 | 90465 | DSF0001034372
24 | Q245 | P.S. 305 - QUEENS | Fast Track Projects | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/12/2023 | FTK |  | FTK | 54708 | 52080 | DSF0001033899
24 | Q245 | P.S. 305 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 165000 | 0 | DSF0001113119
24 | Q245 | P.S. 305 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 9/25/2023 | DOER |  | DOER | 150000 | 0 | DSF0001086495
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 349 | 349 | DSF0001033809
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | Design | PNS | PNS | PNS | PNS | 42493 | 42144 | 1395 | DSF0001033809
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | 623227 | 704000 | 0 | DSF0001033809
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 42493 | 48000 | 0 | DSF0001033809
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/28/2023 | 4/1/2024 | 3/5/2024 | 0 | 33903 | 33903 | DSF0001086496, DSF0001086497
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / FY24 RESO A PLAYGROUND UPGRADE | Design | Complete | 3/20/2024 | 8/20/2024 | 9/9/2024 | 153000 | 102925 | 98513 | DSF0001086496, DSF0001086497
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 2244000 | 2244000 | 735 | DSF0001086496, DSF0001086497
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 153000 | 153000 | 25458 | DSF0001086496, DSF0001086497
24 | Q247 | P.S. 128 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113120
24 | Q247 | P.S. 128 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/28/2023 | DOER |  | DOER | 156649 | 0 | DSF0001008163
24 | Q247 | P.S. 128 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 10/5/2019 | DOES |  | DOES | 114157 | 0 | DSF0000865865
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/26/2023 | 11/9/2023 | 12/11/2023 | 20641 | 150741 | 118116 | DSF0001075522, DSF0001075524
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 12/11/2023 | 5/13/2024 | 6/18/2024 | 99129 | 88971 | 84804 | DSF0001075522, DSF0001075524
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 1877817 | 1877817 | 145 | DSF0001075522, DSF0001075524
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 175058 | 175058 | 24986 | DSF0001075522, DSF0001075524
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | IPDVS | Scope | Complete | 3/22/2022 | 7/20/2022 | 3/30/2022 | 3330 | 4267 | 4267 | DSF0001034373
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | IPDVS | Design | Complete | 3/30/2022 | 9/22/2022 | 8/17/2022 | 14985 | 17067 | 17067 | DSF0001034373
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | IPDVS | Construction | Complete | 2/21/2023 | 12/17/2023 | 12/8/2023 | 193140 | 171302 | 144451 | DSF0001034373
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | IPDVS | CM,F&E | Complete | 2/21/2023 | 12/17/2023 | 12/8/2023 | 185672 | 190160 | 147722 | DSF0001034373
24 | Q260 | P.S. 307 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001033901
24 | Q260 | P.S. 307 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001036013
24 | Q269 | P.S. 143 - QUEENS | SCA CIP | PARAPETS / FLOOD ELIMINATION / ROOFS / WINDOWS / EXTERIOR MASONRY | Scope | In-Progress | 3/11/2021 | 7/26/2021 |  | 71811 | 97310 | 81074 | DSF0000957777, DSF0000957775, DSF0000957776, DSF0000957778, DSF0000957779
24 | Q269 | P.S. 143 - QUEENS | SCA CIP | PARAPETS / FLOOD ELIMINATION / ROOFS / WINDOWS / EXTERIOR MASONRY | Design | PNS | PNS | PNS | PNS | 345562 | 345562 | 1145 | DSF0000957777, DSF0000957775, DSF0000957776, DSF0000957778, DSF0000957779
24 | Q269 | P.S. 143 - QUEENS | SCA CIP | PARAPETS / FLOOD ELIMINATION / ROOFS / WINDOWS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 6608042 | 6608042 | 51786 | DSF0000957777, DSF0000957775, DSF0000957776, DSF0000957778, DSF0000957779
24 | Q269 | P.S. 143 - QUEENS | SCA CIP | PARAPETS / FLOOD ELIMINATION / ROOFS / WINDOWS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 603869 | 603869 | 44367 | DSF0000957777, DSF0000957775, DSF0000957776, DSF0000957778, DSF0000957779
24 | Q269 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY16 RESO A LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000822917
24 | Q269 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY16 RESO A LOW-VOLTAGE ELECTRICAL SYSTEM | Design | PNS | PNS | PNS | PNS | 13500 | 13500 | 0 | DSF0000822917
24 | Q269 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY16 RESO A LOW-VOLTAGE ELECTRICAL SYSTEM | Construction | PNS | PNS | PNS | PNS | 198000 | 198000 | 0 | DSF0000822917
24 | Q269 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY16 RESO A LOW-VOLTAGE ELECTRICAL SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 13500 | 13500 | 0 | DSF0000822917
24 | Q269 | Q721 SPED - QUEENS | SCA IEH | PO18-ABATE & REMOVE WINDOWS IN TEACHER'S LOUNGE WINDOW CAULKING IS ACM | Construction | Complete | 8/19/2024 | IEH | 10/2/2024 | IEH | 0 | 0 | SCA0000073298
24 | Q269 | Q721 SPED - QUEENS | SCA IEH | PO18-1 EA - 1-1/2' THRU WALL PENETRATION FROM THE VESTIBULE (ADJACENT TO STAIR 'D' OUT TO THE EXTERI | Construction | Complete | 6/29/2024 | IEH | 10/3/2024 | IEH | 0 | 0 | SCA0000073467
24 | Q269 | ELM TREE ELEMENTARY SCHOOL | DOE - RESOA | FY16 RESO A PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0000822918
24 | Q287 | P.S. 330 - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 42180 | 0 | DSF0001036020
24 | Q287 | P.S. 330 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086503
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113125
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113125
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001113125
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113125
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113658
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113658
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113658
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113658
24 | Q290 | P.S. 290 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086504
24 | Q290 | P.S. 290 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113124
24 | Q290 | P.S. 290 - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/29/2023 | DOER |  | DOER | 395152 | 0 | DSF0001033892
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033863
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033863
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033863
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033863
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/10/2022 | 6/8/2022 | 8/19/2022 | 0 | 7636 | 7636 | DSF0001033864
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/31/2022 | 1/20/2023 | 3/22/2023 | 18150 | 27459 | 27459 | DSF0001033864
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 11/13/2023 | 8/8/2024 |  | 266200 | 168770 | 3032 | DSF0001033864
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 11/13/2023 | 8/8/2024 |  | 18150 | 36615 | 15892 | DSF0001033864
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 12/13/2023 | 4/15/2024 | 6/17/2024 | 0 | 7971 | 7971 | DSF0001086505
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | Complete | 6/17/2024 | 11/19/2024 | 12/17/2024 | 30000 | 24603 | 13882 | DSF0001086505
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 198 | DSF0001086505
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 23418 | DSF0001086505
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 135000 | 135000 | 134183 | DSF0001086506
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 10/18/2024 | DIIR | 350000 | 350000 | DSF0001008012
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113923
24 | Q311 | CORONA ARTS AND SCIENCES ACADEMY | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/21/2023 | DIIR | 5/24/2024 | DIIR | 300000 | 300000 | DSF0001033311
24 | Q311 | CORONA ARTS AND SCIENCES ACADEMY | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0 | DSF0001036025
24 | Q311 | CORONA ARTS AND SCIENCES ACADEMY | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113127
24 | Q313 | THE CHILDREN'S LAB SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 10/1/2024 | DIIR | 74734 | 74734 | DSF0001086509
24 | Q313 | THE CHILDREN'S LAB SCHOOL | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 12/1/2021 | DOER |  | DOER | 109130 | 0 | DSF0001008115
24 | Q313 | THE CHILDREN'S LAB SCHOOL | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 151256 | 0 | DSF0001111928
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | RESO A ROOM CONVERSION | Scope | Complete | 9/14/2022 | 1/13/2023 | 1/20/2023 | 0 | 15661 | 15661 | DSF0001034189
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | RESO A ROOM CONVERSION | Design | Complete | 1/25/2023 | 6/27/2023 | 5/11/2023 | 39635 | 54159 | 20231 | DSF0001034189
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | RESO A ROOM CONVERSION | Construction | Complete | 11/13/2023 | 9/7/2024 | 8/28/2024 | 581316 | 315580 | 266354 | DSF0001034189
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | RESO A ROOM CONVERSION | CM,F&E | Complete | 11/13/2023 | 9/7/2024 | 8/28/2024 | 40273 | 55561 | 52019 | DSF0001034189
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | In-Progress | 12/18/2024 | 4/21/2025 |  | 0 | 132 | 132 | DSF0001113130
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 6000 | 5868 | 529 | DSF0001113130
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001113130
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001113130
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113659
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113659
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113659
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113659
24 | Q315 | P.S. 110 - QUEENS | Fast Track Projects | RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 1/3/2024 | FTK |  | FTK | 162427 | 127274 | DSF0001034188
24 | Q315 | P.S. 110 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 238000 | 0 | DSF0001036028
24 | Q315 | P.S. 110 - QUEENS | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113128
24 | Q315 | P.S. 110 - QUEENS | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113129
24 | Q320 | P.S. 305 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 8/21/2024 | DOER |  | DOER | 390344 | 0 | DSF0001035342
24 | Q321 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/24/2024 | DOES | 8/8/2024 | DOES | 65832 | 9257 | DSF0001085497
24 | Q322 | THE RIVERVIEW SCHOOL - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING LOCATIONS ROOMS: 102, 107, 107A, 107B, 107D, 107 | Construction | Complete | 6/14/2023 | IEH | 8/30/2024 | IEH | 0 | 0 | SCA0000072066
24 | Q331 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | Scope | Complete | 2/8/2022 | 4/14/2022 | 4/25/2022 | 171608 | 180713 | 173507 | DSF0001034354
24 | Q331 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | Design | Complete | 4/26/2022 | 6/14/2022 | 1/6/2023 | 772234 | 692051 | 597187 | DSF0001034354
24 | Q331 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | Construction | Complete | 1/20/2023 | 9/3/2023 | 7/24/2024 | 9738729 | 10042041 | 9772864 | DSF0001034354
24 | Q331 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | CM,F&E | Complete | 1/20/2023 | 9/3/2023 | 7/24/2024 | 1460449 | 454760 | 1425803 | DSF0001034354
24 | Q340 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 1/17/2019 | 7/2/2019 | 7/16/2019 | 627900 | 619744 | 528620 | DSF0000890641
24 | Q340 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 7/17/2019 | 1/16/2020 | 8/13/2020 | 2825550 | 2726672 | 1646887 | DSF0000890641
24 | Q340 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 7/8/2024 | 9/3/2026 |  | 35633325 | 32952996 | 3138322 | DSF0000890641
24 | Q340 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 7/8/2024 | 9/3/2026 |  | 5023200 | 2555356 | 768999 | DSF0000890641
24 | Q348 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/12/2024 | DOES | 7/29/2024 | DOES | 65832 |  | DSF0001085503
24 | Q368 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/17/2024 | DOES | 10/17/2024 | DOES | 50832 |  | DSF0001085507
24 | Q373 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/23/2024 | DOES | 7/26/2024 | DOES | 50832 | 7900 | DSF0001084416
24 | Q392 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085513
24 | Q399 | Q000 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 11/1/2024 | IEH | 11/20/2024 | IEH | 0 | 0 | SCA0000073559
24 | Q399 | Q000 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/3/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085515
24 | Q414 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/27/2023 | DOES | 11/18/2024 | DOES | 50832 |  | DSF0001085518
24 | Q419 | NEW 2021 D.24 MS IN BUILDING Q419 | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113155
24 | Q419 | NEW 2021 D.24 MS IN BUILDING Q419 | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/19/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084831
24 | Q422 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/27/2023 | DOES | 11/1/2024 | DOES | 50832 |  | DSF0001085519
24 | Q437 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/17/2024 | DOES | 9/18/2024 | DOES | 65832 | 7612 | DSF0001085520
24 | Q437 | PRE-K CENTER @ 98-22 55 AVENUE - QUEENS | DOE Managed PRE-K | LEASE | Construction | In-Progress | 9/7/2017 | DOEP |  | DOEP | 662334 | 0 | DSF0000865849
24 | Q444 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | Scope | Complete | 11/1/2021 | 12/21/2021 | 2/3/2022 | 179859 | 172744 | 172744 | DSF0001034158
24 | Q444 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | Design | Complete | 2/4/2022 | 2/18/2022 | 10/19/2023 | 809367 | 605736 | 505723 | DSF0001034158
24 | Q444 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | Construction | In-Progress | 12/5/2023 | 9/3/2024 |  | 10207014 | 9643634 | 8989284 | DSF0001034158
24 | Q444 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | CM,F&E | In-Progress | 12/5/2023 | 9/3/2024 |  | 1501678 | 476627 | 1344931 | DSF0001034158
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 3/29/2018 | 5/23/2019 | 1/29/2019 | 18776 | 27406 | 27406 | DSF0000868294, DSF0000912221
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 1/29/2019 | 6/28/2019 | 5/16/2019 | 74387 | 79414 | 79414 | DSF0000868294, DSF0000912221
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/22/2019 | 4/16/2020 |  | 1330370 | 1250229 | 1116392 | DSF0000868294, DSF0000912221
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 7/22/2019 | 4/16/2020 |  | 96949 | 215096 | 215096 | DSF0000868294, DSF0000912221
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Scope | Complete | 8/16/2018 | 1/8/2019 | 10/3/2022 | 409223 | 406346 | 406346 | DSF0000889656, DSF0001085152, DSF0000912471, DSF0000949980, DSF0000998945, DSF0001025390, DSF0001076197
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Design | Complete | 12/2/2022 | 5/5/2023 | 5/12/2023 | 2046114 | 1741267 | 1410919 | DSF0000889656, DSF0001085152, DSF0000912471, DSF0000949980, DSF0000998945, DSF0001025390, DSF0001076197
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Construction | In-Progress | 8/21/2023 | 2/5/2026 |  | 46037588 | 41938052 | 7725834 | DSF0000889656, DSF0001085152, DSF0000912471, DSF0000949980, DSF0000998945, DSF0001025390, DSF0001076197
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/21/2023 | 2/5/2026 |  | 2865150 | 930489 | 807658 | DSF0000889656, DSF0001085152, DSF0000912471, DSF0000949980, DSF0000998945, DSF0001025390, DSF0001076197
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP RESOA | FY22 RESO A CAFETERIA UPGRADE | Scope | Complete | 4/14/2022 | 8/15/2022 | 7/6/2023 | 0 | 35395 | 35395 | DSF0001033927
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP RESOA | FY22 RESO A CAFETERIA UPGRADE | Design | Complete | 7/10/2023 | 11/24/2023 | 10/24/2023 | 30000 | 91807 | 46663 | DSF0001033927
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2/26/2024 | 12/21/2024 |  | 440000 | 264395 | 128745 | DSF0001033927
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP RESOA | FY22 RESO A CAFETERIA UPGRADE | CM,F&E | In-Progress | 2/26/2024 | 12/21/2024 |  | 30000 | 54308 | 49309 | DSF0001033927
24 | Q455 | NEWTOWN HS - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 4/23/2021 | EMER |  | EMER | 352792 | 309797 | SCA0000053345
24 | Q455 | NEWTOWN HS - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001036051
24 | Q455 | NEWTOWN HS - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 6/1/2020 | DOES |  | DOES | 61426 | 0 | DSF0000866132
24 | Q455 | NEWTOWN HS - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 8/2/2023 | DOES |  | DOES | 722572 | 0 | DSF0001083755
24 | Q455 | NEWTOWN HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/16/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085008
24 | Q455 | INTERNATIONAL HIGH SCHOOL FOR HEALTH SCIENCES | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/8/2024 | DOES |  | DOES | 676227 | 0 | DSF0001085761
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 1/10/2020 | 5/27/2020 | 6/18/2021 | 116705 | 3048 | 3048 | DSF0001036314
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 3/29/2023 | 8/29/2023 | 4/30/2024 | 583526 | 628674 | 543636 | DSF0001036314
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 13129338 | 13129338 | 48928 | DSF0001036314
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 816937 | 816937 | 39588 | DSF0001036314
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | FY23 RESO A ROOFTOP PLAYGROUND | Scope | In-Progress | 3/29/2023 | 8/14/2023 |  | 0 | 21807 | 9950 | DSF0001036052
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | FY23 RESO A ROOFTOP PLAYGROUND | Design | PNS | PNS | PNS | PNS | 55510 | 33703 | 0 | DSF0001036052
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | FY23 RESO A ROOFTOP PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 814150 | 880000 | 516 | DSF0001036052
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | FY23 RESO A ROOFTOP PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 55510 | 60000 | 235 | DSF0001036052
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP PLAYGROUND | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036053
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP PLAYGROUND | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036053
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036053
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036053
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2/6/2023 | DOER | 10/22/2024 | DOER | 143326 | 60923 | DSF0000961425
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/27/2024 | DOES | 10/4/2024 | DOES | 65832 | 7556 | DSF0001085009
24 | Q457 | NEWTOWN HS - QUEENS | SCA IEH | PO18-ABATE 10 LINEAR FEET OF ACM IN ON STEAM PIPE IN BASEMENT CRAWL SPACE UNDER UNDER 1ST FLOOR BOYS | Construction | Complete | 10/15/2024 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000073503
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | Scope | Complete | 3/11/2021 | 7/26/2021 | 12/8/2021 | 23094 | 39059 | 39059 | DSF0000950134
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | Design | Complete | 1/5/2022 | 7/8/2022 | 5/11/2022 | 115470 | 150444 | 137996 | DSF0000950134
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | Construction | In-Progress | 7/11/2022 | 7/10/2023 |  | 2598075 | 2512535 | 2390336 | DSF0000950134
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 7/11/2022 | 7/10/2023 |  | 289644 | 574744 | 547637 | DSF0000950134
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | Scope | Complete | 6/16/2021 | 11/1/2021 | 1/6/2022 | 31515 | 44784 | 42098 | DSF0000999104, DSF0001025589
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | Design | Complete | 1/25/2022 | 6/24/2022 | 5/11/2022 | 155850 | 121571 | 121571 | DSF0000999104, DSF0001025589
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | Construction | In-Progress | 9/19/2022 | 3/11/2024 |  | 3357412 | 3093348 | 2794921 | DSF0000999104, DSF0001025589
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | CM,F&E | In-Progress | 9/19/2022 | 3/11/2024 |  | 233540 | 467087 | 446976 | DSF0000999104, DSF0001025589
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/30/2021 | EMER |  | EMER |  | 0 | SCA0000070092
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA IEH | PO18-ASSIGNED TO SCA AS AN EMERGENCY ON 6/27/24 | Construction | Complete | 6/28/2024 | IEH | 7/3/2024 | IEH | 0 | 0 | SCA0000073100
24 | Q485 | GROVER CLEVELAND HS - QUEENS | Fast Track Projects | LSP RESO A CAFETERIA UPGRADE - LIGHTING | Construction | PNS | FTK | FTK | FTK | FTK | 316913 | 0 | DSF0001112224
24 | Q485 | GROVER CLEVELAND HS - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 9/20/2022 | FTK |  | FTK | 260778 | 113664 | DSF0000960900
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/5/2024 | DIIR | 12/5/2024 | DIIR | 75000 | 75000 | DSF0001033935
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/18/2024 | DIIR | 12/5/2024 | DIIR | 49558 | 49558 | DSF0001036063
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113172
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 125874 | 0 | DSF0000961439
24 | Q485 | THE RIVERVIEW SCHOOL - QUEENS | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001009270
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/12/2024 | DOER |  | DOER | 635177 | 0 | DSF0001033934
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001086551
24 | Q485 | THE RIVERVIEW SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113173
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 11/18/2018 | DOES |  | DOES | 346062 | 0 | DSF0000865867
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 12/30/2022 | DOES | 3/21/2023 | DOES | 671001 | 663810 | DSF0000960864
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/22/2024 | DOES | 12/3/2024 | DOES | 65832 |  | DSF0001085015
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | Scope | Complete | 5/8/2019 | 9/23/2019 | 2/11/2020 | 18899 | 50203 | 50203 | DSF0000912330
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | Design | Complete | 2/11/2020 | 7/13/2020 | 6/30/2020 | 85045 | 97902 | 97902 | DSF0000912330
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | Construction | In-Progress | 4/12/2022 | 7/5/2023 |  | 1096136 | 985846 | 961013 | DSF0000912330
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | CM,F&E | In-Progress | 4/12/2022 | 7/5/2023 |  | 203163 | 273070 | 265403 | DSF0000912330
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | MECHANICAL PIPING | Scope | Complete | 8/1/2024 | 11/20/2024 | 12/31/2024 | 18355 | 14357 | 178 | DSF0001112281
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | MECHANICAL PIPING | Design | PNS | PNS | PNS | PNS | 73422 | 73422 | 712 | DSF0001112281
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | MECHANICAL PIPING | Construction | PNS | PNS | PNS | PNS | 1055440 | 1055440 | 0 | DSF0001112281
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | MECHANICAL PIPING | CM,F&E | PNS | PNS | PNS | PNS | 270743 | 270743 | 10204 | DSF0001112281
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/25/2022 | DOES |  | DOES | 308282 | 0 | DSF0001034260
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 9/13/2024 | DOES | 65832 | 9385 | DSF0001085019
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113180
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 41040 | 41040 | 0 | DSF0001113180
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 601920 | 601920 | 0 | DSF0001113180
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 41040 | 41040 | 0 | DSF0001113180
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113669
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113669
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113669
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113669
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0001008165
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001036070
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113181
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 60000 | 0 | DSF0001033945
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 10/7/2022 | DOER |  | DOER | 430056 | 0 | DSF0001034347
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086568
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 68658 | 0 | DSF0001112109
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 4/7/2023 | DOES |  | DOES | 60422 | 0 | DSF0000889365
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/16/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085022
24 | Q600 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | Scope | Complete | 4/20/2021 | 1/22/2022 | 2/4/2022 | 38155 | 46217 | 46217 | DSF0000950241, DSF0001009290
24 | Q600 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | Design | Complete | 2/4/2022 | 4/28/2022 | 7/28/2022 | 190152 | 183375 | 183375 | DSF0000950241, DSF0001009290
24 | Q600 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | Construction | In-Progress | 4/13/2023 | 4/11/2024 |  | 4224206 | 3892105 | 3191451 | DSF0000950241, DSF0001009290
24 | Q600 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | CM,F&E | In-Progress | 4/13/2023 | 4/11/2024 |  | 329617 | 315679 | 314057 | DSF0000950241, DSF0001009290
24 | Q600 | QUEENS TECH HS - Q | SCA CIP RESOA | FY18 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 9/4/2019 | 1/7/2020 | 10/2/2019 | 0 | 7037 | 7037 | DSF0000867964
24 | Q600 | QUEENS TECH HS - Q | SCA CIP RESOA | FY18 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 4/29/2020 | 10/23/2020 | 5/14/2020 | 28700 | 28147 | 28147 | DSF0000867964
24 | Q600 | QUEENS TECH HS - Q | SCA CIP RESOA | FY18 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/9/2022 | 3/4/2023 |  | 420929 | 209609 | 188333 | DSF0000867964
24 | Q600 | QUEENS TECH HS - Q | SCA CIP RESOA | FY18 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/9/2022 | 3/4/2023 |  | 225553 | 223888 | 204362 | DSF0000867964
24 | Q600 | QUEENS TECH HS - Q | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | Complete | 9/20/2022 | FTK | 11/15/2024 | FTK | 98653 | 73959 | DSF0000950237
24 | Q600 | QUEENS TECH HS - Q | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008120
24 | Q600 | QUEENS TECH HS - Q | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/5/2022 | DOER |  | DOER | 19881 | 0 | DSF0001033947
24 | Q600 | QUEENS TECH HS - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/19/2024 | DOES | 10/11/2024 | DOES | 65832 | 9805 | DSF0001085024
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/17/2021 | 6/15/2021 | 6/17/2021 | 12500 | 21530 | 21530 | DSF0000950245
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 6/22/2021 | 12/27/2021 | 12/14/2021 | 62500 | 123574 | 107783 | DSF0000950245
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 4/8/2024 | 4/7/2025 |  | 1406250 | 1303786 | 310040 | DSF0000950245
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 4/8/2024 | 4/7/2025 |  | 87500 | 39506 | 39506 | DSF0000950245
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES | Scope | Complete | 12/3/2021 | 10/14/2022 | 1/9/2023 | 161101 | 105301 | 105301 | DSF0001085827, DSF0001035197, DSF0001035198, DSF0001035199
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES | Design | Complete | 1/12/2023 | 6/14/2023 | 8/24/2023 | 783464 | 319813 | 303861 | DSF0001085827, DSF0001035197, DSF0001035198, DSF0001035199
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 15721394 | 15721394 | 123217 | DSF0001085827, DSF0001035197, DSF0001035198, DSF0001035199
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 1293015 | 1293015 | 30548 | DSF0001085827, DSF0001035197, DSF0001035198, DSF0001035199
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113184
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113184
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001113184
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113184
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113670
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113670
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113670
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113670
24 | Q610 | AVIATION HS - QUEENS | SCA Emergency Response | IDA TEMPORARY BOILER- RED DOT | Construction | In-Progress | 8/5/2022 | EMER |  | EMER | 1670134 | 1538470 | SCA0000071354
24 | Q610 | AVIATION HS - QUEENS | Fast Track Projects | TEMPORARY FILTER WORK | Construction | In-Progress | 3/9/2020 | FTK |  | FTK | 597617 | 587785 | SCA0000062931
24 | Q610 | AVIATION VOCATIONAL H.S. | DOE - RESOA | FY08 RESO A PLAYGROUND REDEVELOPMEN | Construction | PNS | PNS | PNS | PNS | DOER | 288309 | 0 | DSF0000544958
24 | Q610 | AVIATION HS - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 119235 | 0 | DSF0001036073
24 | Q610 | AVIATION HS - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 11/16/2018 | DOES |  | DOES | 159718 | 0 | DSF0000889366
24 | Q610 | AVIATION HS - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/9/2023 | DOES | 12/1/2023 | DOES | 554166 | 431932 | DSF0001035105
24 | Q610 | AVIATION HS - QUEENS | DOE - Skilled Trades | ESCALATOR UPGRADES | Construction | In-Progress | 1/29/2024 | DOES |  | DOES | 398000 | 0 | DSF0001104568
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/29/2021 | 2/2/2022 | 7/15/2022 | 18980 | 38165 | 38165 | DSF0001034186
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 7/18/2022 | 12/2/2022 | 4/18/2023 | 94900 | 103024 | 103024 | DSF0001034186
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 12/4/2023 | 12/2/2024 |  | 2135250 | 1951624 | 1746471 | DSF0001034186
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 12/4/2023 | 12/2/2024 |  | 132860 | 175564 | 127184 | DSF0001034186
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/1/2024 | 5/31/2024 | 3/27/2024 | 6731 | 3105 | 3105 | DSF0001087544
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/27/2024 | 9/20/2024 | 6/14/2024 | 30291 | 12418 | 12418 | DSF0001087544
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/30/2024 | 10/25/2025 |  | 390413 | 287635 | 41355 | DSF0001087544
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/30/2024 | 10/25/2025 |  | 76625 | 35631 | 8912 | DSF0001087544
24 | Q721 | P.S. 16 - QUEENS | SCA IEH | PO18-1 EA - 1-1/2' THRU WALL PENETRATION FROM THE VESTIBULE (ADJACENT TO STAIR 'D' OUT TO THE EXTERI | Construction | Complete | 7/10/2024 | IEH | 10/3/2024 | IEH | 0 | 0 | SCA0000073128
24 | Q721 | P.S. 16 - QUEENS | Fast Track Projects | LSP WATER HEATER | Construction | In-Progress | 1/7/2019 | FTK |  | FTK | 256639 | 247664 | DSF0000881784
24 | Q721 | P.S. 16 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 88000 | 0 | DSF0000890850
24 | Q721 | P.S. 16 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/10/2024 | DIIR | 11/7/2024 | DIIR | 50000 | 50000 | DSF0001033253
24 | Q721 | P.S. 16 - QUEENS | DOE - RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001036084
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113673
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113673
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113673
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113673
24 | Q722 | Q721 SPED - QUEENS | Fast Track Projects | FY22 RESO A CAFETERIA UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 82713 | 34447 | DSF0001033952
24 | Q722 | Q721 SPED - QUEENS | DOE - RESOA | FY23 RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001036085
24 | Q722 | Q721 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0 | DSF0001086579
24 | Q722 | Q721 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 700000 | 0 | DSF0001113195
24 | Q722 | Q721 SPED - QUEENS | DOE - Skilled Trades | DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 2/2/2023 | DOES |  | DOES | 83809 | 0 | DSF0000960681
24 | Q722 | Q721 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/28/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085032
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/1/2024 | 5/31/2024 | 3/27/2024 | 7755 | 3683 | 3683 | DSF0001087545
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/27/2024 | 9/20/2024 | 6/14/2024 | 34896 | 14731 | 14731 | DSF0001087545
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/30/2024 | 10/25/2025 |  | 449769 | 340493 | 14773 | DSF0001087545
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/30/2024 | 10/25/2025 |  | 87626 | 43819 | 8521 | DSF0001087545
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP RESOA | FY18 RESO CLASSROOM CONVERSION | Scope | Complete | 11/27/2018 | 3/15/2019 | 3/13/2019 | 0 | 27178 | 16866 | DSF0000866561
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP RESOA | FY18 RESO CLASSROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 2701 | 2701 | DSF0000866561
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP RESOA | FY18 RESO CLASSROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 8393 | 8393 | DSF0000866561
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP RESOA | FY18 RESO CLASSROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 3734 | 3734 | DSF0000866561
24 | Q735 | HS OF APPLIED COMMUNICATION-Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 6/11/2024 | DOER |  | DOER | 42022 | 0 | DSF0001086581
24 | Q744 | PAN AMERICAN INTERNATIONAL HS - QUEENS | DOE - RESOA | FY16 RESO A CAFETERIA/MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0000822754
24 | Q777 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086582
24 | Q777 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/13/2023 | DOES |  | DOES | 65832 | 0 | DSF0001085537
24 | Q841 | PS 23 @ HILLSIDE PSYCH - Q | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 9/13/2024 | IEH | 9/26/2024 | IEH | 0 | 0 | SCA0000073372
24 | Q848 | P.S. 81 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE / FY21 RESO A CAFETERIA UPGRADE | Scope | Complete | 7/13/2021 | 3/15/2022 | 5/6/2022 | 0 | 7929 | 7929 | DSF0001007773, DSF0001008422
24 | Q848 | P.S. 81 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE / FY21 RESO A CAFETERIA UPGRADE | Design | Complete | 5/6/2022 | 6/13/2022 | 5/11/2022 | 22999 | 30552 | 30552 | DSF0001007773, DSF0001008422
24 | Q848 | P.S. 81 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE / FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/10/2023 | 1/4/2024 |  | 337306 | 275492 | 253234 | DSF0001007773, DSF0001008422
24 | Q848 | P.S. 81 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE / FY21 RESO A CAFETERIA UPGRADE | CM,F&E | In-Progress | 4/10/2023 | 1/4/2024 |  | 22999 | 44884 | 44362 | DSF0001007773, DSF0001008422
24 | Q848 | P.S. 81 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 11/22/2024 | IEH | 11/30/2024 | IEH | 0 | 0 | SCA0000073634
24 | Q849 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | Scope | Complete | 6/2/2022 | 11/28/2022 | 10/6/2022 | 243079 | 233136 | 216503 | DSF0001026294, DSF0001026293, DSF0001026292, DSF0001036322, DSF0001026290
24 | Q849 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | Design | Complete | 10/18/2022 | 6/5/2023 | 4/17/2023 | 1206317 | 562911 | 562911 | DSF0001026294, DSF0001026293, DSF0001026292, DSF0001036322, DSF0001026290
24 | Q849 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | Construction | In-Progress | 10/3/2023 | 10/1/2025 |  | 26356778 | 23926788 | 5666627 | DSF0001026294, DSF0001026293, DSF0001026292, DSF0001036322, DSF0001026290
24 | Q849 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | CM,F&E | In-Progress | 10/3/2023 | 10/1/2025 |  | 1769648 | 376291 | 263276 | DSF0001026294, DSF0001026293, DSF0001026292, DSF0001036322, DSF0001026290
24 | Q849 | I.S. 77 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/12/2024 | DIIR | 8/21/2024 | DIIR | 56000 |  | DSF0001036089
24 | Q849 | BUSHWICK LEADERS - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 185000 | 0 | DSF0001113202
24 | Q849 | I.S. 77 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0 | DSF0001113200
24 | Q849 | I.S. 77 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113201
24 | Q849 | I.S. 77 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/4/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084832
24 | Q849 | I.S. 77 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/8/2024 | DOES |  | DOES | 645132 | 0 | DSF0001085763
24 | Q877 | P.S. 7 - QUEENS | Fast Track Projects | LSP FLOORING REPLACEMENT | Construction | In-Progress | 5/6/2024 | FTK |  | FTK | 347789 | 285043 | DSF0001111892
24 | Q908 | Q255 SPED - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 12/17/2024 | IEH | 12/26/2024 | IEH | 0 | 0 | SCA0000073722
24 | Q908 | P.S. 143 - QUEENS | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/15/2020 | FTK |  | FTK | 126063 | 126063 | DSF0000961170
24 | QASU | BETTER CCOMMUNITY LIFE DAY CARE CENTER SITE | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | Scope | Complete | 8/21/2023 | 1/17/2024 | 12/17/2024 | 67297 | 8376 | 2611 | DSF0001085335
24 | QASU | BETTER CCOMMUNITY LIFE DAY CARE CENTER SITE | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | Design | PNS | PNS | PNS | PNS | 336487 | 336487 | 10441 | DSF0001085335
24 | QASU | BETTER CCOMMUNITY LIFE DAY CARE CENTER SITE | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | Construction | PNS | PNS | PNS | PNS | 7570946 | 7570946 | 13638 | DSF0001085335
24 | QASU | BETTER CCOMMUNITY LIFE DAY CARE CENTER SITE | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | CM,F&E | PNS | PNS | PNS | PNS | 471081 | 471081 | 18480 | DSF0001085335
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 12/18/2017 | 5/4/2018 | 3/21/2018 | 103128 | 89232 | 89232 | DSF0000877872, DSF0000877874, DSF0000889087, DSF0000877873
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 3/21/2018 | 8/20/2018 | 5/18/2018 | 407457 | 573749 | 525828 | DSF0000877872, DSF0000877874, DSF0000889087, DSF0000877873
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 7/23/2018 | 1/13/2020 |  | 7186455 | 7548188 | 6320772 | DSF0000877872, DSF0000877874, DSF0000889087, DSF0000877873
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 7/23/2018 | 1/13/2020 |  | 546930 | 974144 | 926223 | DSF0000877872, DSF0000877874, DSF0000889087, DSF0000877873
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | Scope | Complete | 7/23/2013 | 12/18/2017 | 12/18/2017 | 141166 | 70035 | 70035 | DSF0000765327, DSF0000787947, DSF0000867109
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | Design | Complete | 4/20/2018 | 10/22/2018 | 5/16/2019 | 564660 | 565719 | 531234 | DSF0000765327, DSF0000787947, DSF0000867109
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | Construction | In-Progress | 7/29/2019 | 7/17/2021 |  | 10587375 | 9952110 | 9003450 | DSF0000765327, DSF0000787947, DSF0000867109
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | CM,F&E | In-Progress | 7/29/2019 | 7/17/2021 |  | 658769 | 158127 | 153752 | DSF0000765327, DSF0000787947, DSF0000867109
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112937
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112937
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001112937
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112937
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113625
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113625
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113625
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113625
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/16/2023 | 1/22/2024 | 12/13/2023 | 0 | 6989 | 6989 | DSF0001086351
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 12/13/2023 | 6/10/2024 | 3/6/2024 | 30000 | 27955 | 27955 | DSF0001086351
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 7/29/2024 | 5/24/2025 |  | 440000 | 284941 | 108088 | DSF0001086351
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 7/29/2024 | 5/24/2025 |  | 109484 | 126434 | 110205 | DSF0001086351
25 | Q020 | P.S. 20 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 3/7/2022 | FTK |  | FTK | 319188 | 129157 | DSF0000960834
25 | Q020 | P.S. 20 - QUEENS | Fast Track Projects | GYM FLOOR REPLACEMENT | Construction | In-Progress | 8/8/2023 | FTK |  | FTK | 707439 | 643384 | SCA0000071073
25 | Q020 | P.S. 20 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112938
25 | Q020 | P.S. 20 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001035803
25 | Q020 | P.S. 20 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/8/2023 | DOER |  | DOER | 294023 | 0 | DSF0001035804
25 | Q020 | P.S. 20 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 3/30/2019 | DOES |  | DOES | 72176 | 0 | DSF0000865899
25 | Q021 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/27/2019 | 11/29/2019 | 9/18/2019 | 58253 | 74958 | 74958 | DSF0000912543, DSF0000912544
25 | Q021 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/25/2019 | 3/2/2020 | 1/23/2020 | 291265 | 379119 | 345509 | DSF0000912543, DSF0000912544
25 | Q021 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/6/2021 | 7/5/2023 |  | 6553445 | 6044734 | 5414051 | DSF0000912543, DSF0000912544
25 | Q021 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/6/2021 | 7/5/2023 |  | 407770 | 357311 | 345218 | DSF0000912543, DSF0000912544
25 | Q021 | P.S. 21 - QUEENS | SCA IEH | PO18-ABATE 12 LINEAR FEET ACM LOCATION BASEMENT HALLWAY CEILING OUTSIDE B8 3 RISER VALVES | Construction | In-Progress | 9/19/2024 | IEH |  | IEH | 0 | 0 | SCA0000073401
25 | Q021 | P.S. 21 - QUEENS | SCA IEH | PO18-BOILER FEED LINE ROTTED & LEAKING STEADY DRIP TEST BOILER FEED LINE &IF POSITIVE ABATE 10 ACM | Construction | In-Progress | 12/24/2024 | IEH |  | IEH | 0 | 0 | SCA0000073740
25 | Q021 | P.S. 21 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 402191 | 0 | DSF0000960072
25 | Q021 | P.S. 21 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112939
25 | Q021 | P.S. 21 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 280299 | 0 | DSF0001035805
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 8/27/2018 | 11/28/2018 | 12/10/2018 | 12200 | 27434 | 27434 | DSF0000888913
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 1/3/2019 | 5/20/2019 | 2/28/2020 | 60999 | 123317 | 117200 | DSF0000888913
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 8/16/2021 | 8/15/2022 |  | 1372472 | 1670190 | 1317965 | DSF0000888913
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 8/16/2021 | 8/15/2022 |  | 85398 | 162039 | 155922 | DSF0000888913
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/14/2024 | 10/31/2024 | 10/28/2024 | 189621 | 182363 | 130363 | DSF0001099296, DSF0001099298, DSF0001099299, DSF0001099300, DSF0001113851
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | In-Progress | 11/29/2024 | 5/2/2025 |  | 876491 | 876491 | 258812 | DSF0001099296, DSF0001099298, DSF0001099299, DSF0001099300, DSF0001113851
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | PNS | PNS | PNS | PNS | 13823877 | 13823877 | 0 | DSF0001099296, DSF0001099298, DSF0001099299, DSF0001099300, DSF0001113851
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1484072 | 1484072 | 24739 | DSF0001099296, DSF0001099298, DSF0001099299, DSF0001099300, DSF0001113851
25 | Q022 | P.S. 22 - QUEENS | DIIT - RESOA | FY21 RESO A (MA) TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 250000 | 0 | DSF0001008623
25 | Q022 | P.S. 22 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 360000 | 0 | DSF0001112941
25 | Q022 | P.S. 22 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112940
25 | Q022 | P.S. 22 - QUEENS | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 5/9/2016 | DOES |  | DOES | 194136 | 0 | DSF0000787973
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | SCA IEH | PO18-ABATE & REMOVE FLOOR TILES ROOM - 106 ; 151 | Construction | Complete | 6/25/2024 | IEH | 7/12/2024 | IEH | 0 | 0 | SCA0000073083
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | Fast Track Projects | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 10/23/2023 | FTK |  | FTK | 103686 | 103642 | DSF0001008004
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/11/2023 | DOER |  | DOER | 52593 | 0 | DSF0000913365
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | DOE - RESOA | FY25 RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001112942
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/9/2024 | DOES | 9/16/2024 | DOES | 65832 |  | DSF0001084989
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/1/2023 | 4/4/2024 | 2/22/2024 | 0 | 15672 | 15672 | DSF0001086353
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 2/26/2024 | 7/26/2024 | 5/6/2024 | 34620 | 47837 | 46656 | DSF0001086353
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 507760 | 507760 | 14214 | DSF0001086353
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 34620 | 34620 | 13746 | DSF0001086353
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | In-Progress | 12/18/2024 | 4/21/2025 |  | 0 | 0 | 0 | DSF0001112943
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 9000 | 9000 | 0 | DSF0001112943
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 132000 | 132000 | 0 | DSF0001112943
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 9000 | 9000 | 0 | DSF0001112943
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113626
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113626
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113626
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113626
25 | Q024 | P.S. 24 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR CEILING AND PLASTER IN THE AUDITORIUM CE JERRY GIAMMATTEO | Construction | Complete | 5/28/2024 | IEH | 11/14/2024 | IEH | 0 | 0 | SCA0000073027
25 | Q024 | P.S. 24 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 522016 | 0 | DSF0000960074
25 | Q024 | P.S. 24 - QUEENS | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 9/29/2023 | DOER |  | DOER | 290060 | 0 | DSF0001008003
25 | Q024 | P.S. 24 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 76112 | 0 | DSF0001112216
25 | Q024 | P.S. 24 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/26/2024 | DOES | 12/4/2024 | DOES | 65832 | 16197 | DSF0001084272
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/25/2019 | 11/26/2019 | 9/25/2019 | 79750 | 116065 | 116065 | DSF0000912542, DSF0000900805
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/27/2019 | 3/4/2020 | 1/23/2020 | 398750 | 580981 | 501912 | DSF0000912542, DSF0000900805
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 4/12/2021 | 4/11/2023 |  | 8971875 | 9801613 | 8276141 | DSF0000912542, DSF0000900805
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 4/12/2021 | 4/11/2023 |  | 558250 | 1227515 | 1165313 | DSF0000912542, DSF0000900805
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/14/2023 | 10/31/2023 | 11/6/2023 | 33761 | 59730 | 59730 | DSF0001071629
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | EXTERIOR MASONRY | Design | Complete | 11/15/2023 | 4/18/2024 | 5/6/2024 | 168805 | 119234 | 113189 | DSF0001071629
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 3798115 | 3798115 | 41065 | DSF0001071629
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 236327 | 236327 | 38561 | DSF0001071629
25 | Q025 | Q233 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086354
25 | Q025 | J.H.S. 25 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084799
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 12/18/2017 | 5/4/2018 | 4/3/2018 | 85230 | 56741 | 56741 | DSF0000877975
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 4/3/2018 | 8/31/2018 | 2/24/2023 | 426150 | 481151 | 420301 | DSF0000877975
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 7/10/2023 | 9/6/2025 |  | 9588375 | 9145976 | 7245940 | DSF0000877975
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 7/10/2023 | 9/6/2025 |  | 596610 | 565801 | 474826 | DSF0000877975
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/7/2024 | 10/24/2024 | 10/22/2024 | 290062 | 122924 | 122924 | DSF0001099403, DSF0001099404, DSF0001099405, DSF0001127202
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | In-Progress | 11/8/2024 | 4/15/2025 |  | 1353620 | 1353620 | 259482 | DSF0001099403, DSF0001099404, DSF0001099405, DSF0001127202
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 21464549 | 21464549 | 0 | DSF0001099403, DSF0001099404, DSF0001099405, DSF0001127202
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 2127117 | 2127117 | 31684 | DSF0001099403, DSF0001099404, DSF0001099405, DSF0001127202
25 | Q029 | P.S. 29 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 357192 | 0 | DSF0000960080
25 | Q029 | P.S. 29 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | Complete | 1/19/2024 | DOER | 2/21/2024 | DOER | 70128 |  | DSF0001035811
25 | Q029 | P.S. 29 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/28/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084274
25 | Q032 | P.S. 32 - QUEENS | SCA CIP | EXISTING BUILDING WORK | Scope | Complete | 3/25/2021 | 7/23/2021 | 7/26/2021 | 70576 | 162389 | 80195 | DSF0000911835
25 | Q032 | P.S. 32 - QUEENS | SCA CIP | EXISTING BUILDING WORK | Design | Complete | 7/26/2021 | 1/18/2022 | 2/6/2023 | 352881 | 583697 | 367569 | DSF0000911835
25 | Q032 | P.S. 32 - QUEENS | SCA CIP | EXISTING BUILDING WORK | Construction | PNS | PNS | PNS | PNS | 7939823 | 7939823 | 80893 | DSF0000911835
25 | Q032 | P.S. 32 - QUEENS | SCA CIP | EXISTING BUILDING WORK | CM,F&E | PNS | PNS | PNS | PNS | 494033 | 494033 | 57088 | DSF0000911835
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113627
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113627
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113627
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113627
25 | Q032 | P.S. 32 - QUEENS | Fast Track Projects | LSP FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 7/10/2023 | FTK |  | FTK | 290182 | 275719 | DSF0001035814
25 | Q032 | P.S. 32 - QUEENS | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112947
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/19/2021 | 9/17/2021 | 7/20/2021 | 78720 | 76195 | 76195 | DSF0000995979, DSF0001008803
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 7/22/2021 | 1/21/2022 | 3/30/2022 | 393600 | 329912 | 285767 | DSF0000995979, DSF0001008803
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 6/22/2022 | 2/11/2024 |  | 8856000 | 8355253 | 4660127 | DSF0000995979, DSF0001008803
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 6/22/2022 | 2/11/2024 |  | 551040 | 253978 | 252860 | DSF0000995979, DSF0001008803
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | HVAC PIPING REPLACEMENT | Scope | Complete | 12/29/2021 | 6/1/2022 | 1/4/2022 | 19000 | 3695 | 3695 | DSF0001021771
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | HVAC PIPING REPLACEMENT | Design | Complete | 1/4/2022 | 6/6/2022 | 2/24/2022 | 85502 | 14780 | 14780 | DSF0001021771
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | HVAC PIPING REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 1102021 | 1102021 | 0 | DSF0001021771
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | HVAC PIPING REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 204254 | 204254 | 42372 | DSF0001021771
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/9/2024 | 8/8/2024 | 5/7/2024 | 6285 | 2050 | 2050 | DSF0001087505
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/7/2024 | 11/1/2024 | 10/30/2024 | 28281 | 8198 | 8198 | DSF0001087505
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 364511 | 364511 | 17821 | DSF0001087505
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 71824 | 71824 | 8777 | DSF0001087505
25 | Q079 | P.S. 79 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Scope | Complete | 2/14/2023 | 5/15/2023 | 5/22/2023 | 0 | 31693 | 27933 | DSF0001035850
25 | Q079 | P.S. 79 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Design | Complete | 5/23/2023 | 10/10/2023 | 11/28/2023 | 61425 | 52913 | 41583 | DSF0001035850
25 | Q079 | P.S. 79 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Construction | In-Progress | 11/15/2024 | 10/10/2025 |  | 900900 | 857909 | 24719 | DSF0001035850
25 | Q079 | P.S. 79 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | CM,F&E | In-Progress | 11/15/2024 | 10/10/2025 |  | 61425 | 79173 | 16110 | DSF0001035850
25 | Q079 | P.S. 79 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112986
25 | Q079 | P.S. 79 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150643 | 0 | DSF0001033775
25 | Q079 | P.S. 79 - QUEENS | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/6/2023 | DOES |  | DOES | 472009 | 339486 | DSF0001072523
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | RTU REPLACEMENT | Scope | Complete | 4/14/2023 | 4/14/2023 | 4/14/2023 | 5809 | 692 | 692 | DSF0001073046
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | RTU REPLACEMENT | Design | Complete | 4/14/2023 | 6/7/2023 | 6/7/2023 | 26140 | 2768 | 2768 | DSF0001073046
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | RTU REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 336912 | 336912 | 0 | DSF0001073046
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | RTU REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 62445 | 62445 | 245 | DSF0001073046
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS WINDOWS / DCAS ELECTRICAL SERVICE UPGRADE / DCAS FIRE ALARM / DCAS LIGHTING UPGRADE | Scope | Complete | 8/23/2023 | 1/22/2024 | 12/22/2023 | 350647 | 317911 | 314800 | DSF0001085599, DSF0001111905, DSF0001100794, DSF0001100785, DSF0001113734
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS WINDOWS / DCAS ELECTRICAL SERVICE UPGRADE / DCAS FIRE ALARM / DCAS LIGHTING UPGRADE | Design | In-Progress | 1/3/2024 | 8/9/2024 |  | 1706373 | 1706373 | 442367 | DSF0001085599, DSF0001111905, DSF0001100794, DSF0001100785, DSF0001113734
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS WINDOWS / DCAS ELECTRICAL SERVICE UPGRADE / DCAS FIRE ALARM / DCAS LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | 34035543 | 34035543 | 285789 | DSF0001085599, DSF0001111905, DSF0001100794, DSF0001100785, DSF0001113734
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS WINDOWS / DCAS ELECTRICAL SERVICE UPGRADE / DCAS FIRE ALARM / DCAS LIGHTING UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 2501382 | 2501382 | 166602 | DSF0001085599, DSF0001111905, DSF0001100794, DSF0001100785, DSF0001113734
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/20/2023 | 10/19/2023 | 6/26/2023 | 4934 | 3703 | 3703 | DSF0001035051
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/26/2023 | 12/21/2023 | 11/1/2023 | 22203 | 14813 | 14813 | DSF0001035051
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/9/2024 | 1/3/2025 |  | 286175 | 259021 | 165200 | DSF0001035051
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/9/2024 | 1/3/2025 |  | 147760 | 197187 | 138752 | DSF0001035051
25 | Q107 | P.S. 107 - QUEENS | SCA CIP RESOA | FY16 RESO A MEDIA CENTER UPGRADE | Scope | Complete | 8/27/2019 | 12/31/2019 | 4/23/2021 | 0 | 11902 | 11902 | DSF0000912553
25 | Q107 | P.S. 107 - QUEENS | SCA CIP RESOA | FY16 RESO A MEDIA CENTER UPGRADE | Design | Complete | 5/3/2021 | 9/16/2021 | 1/27/2022 | 42000 | 95618 | 95618 | DSF0000912553
25 | Q107 | P.S. 107 - QUEENS | SCA CIP RESOA | FY16 RESO A MEDIA CENTER UPGRADE | Construction | In-Progress | 6/9/2022 | 3/5/2023 |  | 616000 | 353226 | 276765 | DSF0000912553
25 | Q107 | P.S. 107 - QUEENS | SCA CIP RESOA | FY16 RESO A MEDIA CENTER UPGRADE | CM,F&E | In-Progress | 6/9/2022 | 3/5/2023 |  | 264544 | 278952 | 264986 | DSF0000912553
25 | Q107 | P.S. 107 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING LOCATIONS: 1ST FLOOR STAIRWELL #8(NOW STAIRWELL | Construction | Complete | 10/10/2023 | IEH | 11/26/2024 | IEH | 0 | 0 | SCA0000072382
25 | Q107 | P.S. 107 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 104000 | 0 | DSF0001035232
25 | Q107 | P.S. 107 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/9/2024 | DOES | 7/18/2024 | DOES | 65832 | 22925 | DSF0001084324
25 | Q120 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | Scope | Complete | 5/27/2020 | 11/17/2021 | 9/15/2021 | 239846 | 289098 | 289098 | DSF0000947804, DSF0000947806, DSF0000947807, DSF0000947808, DSF0001008590, DSF0001009320, DSF0001022518
25 | Q120 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | Design | Complete | 10/19/2021 | 6/30/2022 | 4/27/2022 | 1197635 | 591575 | 572862 | DSF0000947804, DSF0000947806, DSF0000947807, DSF0000947808, DSF0001008590, DSF0001009320, DSF0001022518
25 | Q120 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | Construction | Complete | 9/6/2022 | 9/4/2024 | 9/3/2024 | 26808715 | 24438832 | 21980742 | DSF0000947804, DSF0000947806, DSF0000947807, DSF0000947808, DSF0001008590, DSF0001009320, DSF0001022518
25 | Q120 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | CM,F&E | Complete | 9/6/2022 | 9/4/2024 | 9/3/2024 | 1690897 | 488551 | 464973 | DSF0000947804, DSF0000947806, DSF0000947807, DSF0000947808, DSF0001008590, DSF0001009320, DSF0001022518
25 | Q120 | P.S. 120 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | Complete | 5/26/2021 | EMER | 10/10/2024 | EMER | 322765 | 172469 | SCA0000069669
25 | Q120 | P.S. 120 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/10/2021 | DOER |  | DOER | 479311 | 0 | DSF0001007994
25 | Q120 | P.S. 120 - QUEENS | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 11/23/2020 | DOES | 2/9/2021 | DOES | 5339 | 21483 | DSF0000961533
25 | Q129 | P.S. 129 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 6/13/2024 | 10/30/2024 | 9/13/2024 | 244389 | 91729 | 78237 | DSF0001101208, DSF0001113759, DSF0001101207
25 | Q129 | P.S. 129 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | In-Progress | 9/23/2024 | 2/27/2025 |  | 1140482 | 1140482 | 157295 | DSF0001101208, DSF0001113759, DSF0001101207
25 | Q129 | P.S. 129 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | PNS | PNS | PNS | PNS | 18084802 | 18084802 | 33156 | DSF0001101208, DSF0001113759, DSF0001101207
25 | Q129 | P.S. 129 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 1792188 | 1792188 | 63816 | DSF0001101208, DSF0001113759, DSF0001101207
25 | Q129 | P.S. 129 - QUEENS | Fast Track Projects | LSP DOMESTIC HOT WATER HEATER | Construction | Complete | 9/20/2022 | FTK | 11/15/2024 | FTK | 98213 | 64926 | DSF0000947971
25 | Q129 | P.S. 129 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113024
25 | Q129 | P.S. 129 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086418
25 | Q154 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/14/2022 | 4/17/2023 | 12/21/2022 | 4269 | 5757 | 5757 | DSF0001034587
25 | Q154 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/21/2022 | 6/20/2023 | 4/4/2023 | 19211 | 23027 | 23027 | DSF0001034587
25 | Q154 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 8/7/2023 | 6/1/2024 | 10/10/2024 | 247602 | 239866 | 188058 | DSF0001034587
25 | Q154 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 8/7/2023 | 6/1/2024 | 10/10/2024 | 152797 | 153621 | 102122 | DSF0001034587
25 | Q154 | P.S. 154 - QUEENS | SCA IEH | PO18-TEST 5 INCH STEAM LINE &IF POSITIVE ABATE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | Complete | 12/4/2024 | IEH | 12/8/2024 | IEH | 0 | 0 | SCA0000073664
25 | Q154 | Q255 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001086444
25 | Q154 | P.S. 154 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/8/2024 | DIIR | 10/30/2024 | DIIR | 300000 | 300000 | DSF0001086445
25 | Q154 | P.S. 154 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113050
25 | Q154 | Q255 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 100000 | 0 | DSF0001086446
25 | Q163 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 4/28/2021 | 9/13/2021 | 11/8/2021 | 13340 | 16918 | 16918 | DSF0000997530
25 | Q163 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 11/19/2021 | 4/25/2022 | 5/17/2022 | 60030 | 54487 | 54487 | DSF0000997530
25 | Q163 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 10/24/2022 | 2/15/2024 |  | 773720 | 761783 | 611788 | DSF0000997530
25 | Q163 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 10/24/2022 | 2/15/2024 |  | 143405 | 143849 | 127310 | DSF0000997530
25 | Q163 | P.S. 163 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 350467 | 0 | DSF0000960148
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/19/2024 | DOER |  | DOER | 42091 | 0 | DSF0001007997
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | Complete | 4/8/2022 | DOER | 10/20/2023 | DOER | 233811 |  | DSF0001033833
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001035935
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001086451
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113056
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/31/2022 | 11/23/2022 | 9/9/2022 | 155491 | 154059 | 147512 | DSF0001023398, DSF0001023399, DSF0001023400, DSF0001035208
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 9/23/2022 | 6/12/2023 | 4/14/2023 | 777450 | 443758 | 443758 | DSF0001023398, DSF0001023399, DSF0001023400, DSF0001035208
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 7/17/2023 | 10/3/2025 |  | 17492626 | 15884931 | 5942586 | DSF0001023398, DSF0001023399, DSF0001023400, DSF0001035208
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 7/17/2023 | 10/3/2025 |  | 1088430 | 686340 | 559051 | DSF0001023398, DSF0001023399, DSF0001023400, DSF0001035208
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/23/2022 | 9/21/2022 | 6/15/2022 | 5787 | 4606 | 4606 | DSF0001034600
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 26043 | 18420 | 18420 | DSF0001034600
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 5/22/2023 | 3/16/2024 | 7/12/2024 | 335670 | 300083 | 275211 | DSF0001034600
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 5/22/2023 | 3/16/2024 | 7/12/2024 | 180245 | 163833 | 94960 | DSF0001034600
25 | Q164 | P.S. 164 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | Complete | 3/6/2023 | FTK | 8/19/2024 | FTK | 483011 | 384643 | DSF0000948628
25 | Q164 | P.S. 164 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/21/2023 | DIIR | 2/28/2024 | DIIR | 100000 | 100000 | DSF0001033834
25 | Q164 | P.S. 164 - QUEENS | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 11/17/2021 | DOER |  | DOER | 83173 | 0 | DSF0000914023
25 | Q165 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/16/2023 | 10/18/2023 | 6/21/2023 | 4985 | 2066 | 2066 | DSF0001035052
25 | Q165 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/21/2023 | 12/18/2023 | 11/1/2023 | 22433 | 8264 | 8264 | DSF0001035052
25 | Q165 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/9/2024 | 1/3/2025 |  | 289135 | 264882 | 176800 | DSF0001035052
25 | Q165 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/9/2024 | 1/3/2025 |  | 131451 | 182070 | 107984 | DSF0001035052
25 | Q165 | P.S. 165 - QUEENS | DOE - RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 7/31/2019 | DOER |  | DOER | 490623 | 0 | DSF0000800363
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 7/22/2021 | 10/21/2021 | 10/20/2021 | 14360 | 8505 | 8505 | DSF0000997602
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 10/27/2021 | 4/1/2022 | 1/19/2022 | 64620 | 34019 | 34019 | DSF0000997602
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | Construction | Complete | 4/11/2022 | 1/5/2023 | 6/28/2024 | 832880 | 750944 | 669840 | DSF0000997602
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | CM,F&E | Complete | 4/11/2022 | 1/5/2023 | 6/28/2024 | 154370 | 98814 | 97369 | DSF0000997602
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113058
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 72660 | 72660 | 0 | DSF0001113058
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1065680 | 1065680 | 0 | DSF0001113058
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 72660 | 72660 | 0 | DSF0001113058
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113649
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113649
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113649
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113649
25 | Q168 | Q255 SPED - QUEENS | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 35000 | 35000 | 0 | DSF0000914026
25 | Q168 | I.S. 250 - QUEENS | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/1/2024 | DOER |  | DOER | 296731 | 0 | DSF0000890912
25 | Q168 | Q255 SPED - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 8/16/2024 | DOER |  | DOER | 178540 | 0 | DSF0001035937
25 | Q169 | P.S. 169 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL UPGRADE / WINDOWS / ROOFS / LIGHTING UPGRADE | Scope | In-Progress | 11/15/2024 | 4/18/2025 |  | 365595 | 365595 | 170621 | DSF0001083818, DSF0001086888, DSF0001086887, DSF0001074268, DSF0001113742
25 | Q169 | P.S. 169 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL UPGRADE / WINDOWS / ROOFS / LIGHTING UPGRADE | Design | PNS | PNS | PNS | PNS | 1699749 | 1699749 | 760158 | DSF0001083818, DSF0001086888, DSF0001086887, DSF0001074268, DSF0001113742
25 | Q169 | P.S. 169 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL UPGRADE / WINDOWS / ROOFS / LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | 26896614 | 26896614 | 243921 | DSF0001083818, DSF0001086888, DSF0001086887, DSF0001074268, DSF0001113742
25 | Q169 | P.S. 169 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL UPGRADE / WINDOWS / ROOFS / LIGHTING UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 2751794 | 2751794 | 277409 | DSF0001083818, DSF0001086888, DSF0001086887, DSF0001074268, DSF0001113742
25 | Q169 | I.S. 294 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Scope | Complete | 8/12/2021 | 12/15/2021 | 12/29/2021 | 0 | 9970 | 9970 | DSF0000961435
25 | Q169 | I.S. 294 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 1/4/2022 | 6/6/2022 | 5/2/2022 | 47400 | 31797 | 31070 | DSF0000961435
25 | Q169 | I.S. 294 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 695200 | 695200 | 2710 | DSF0000961435
25 | Q169 | I.S. 294 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 47400 | 47400 | 4949 | DSF0000961435
25 | Q169 | I.S. 294 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033895
25 | Q169 | I.S. 294 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/3/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001035938
25 | Q169 | I.S. 294 - QUEENS | DOE - RESOA | RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/22/2023 | DOER |  | DOER | 59485 | 0 | DSF0001085810
25 | Q169 | I.S. 294 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 395000 | 0 | DSF0001086454
25 | Q169 | P.S. 169 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113059
25 | Q184 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/21/2022 | 12/7/2022 | 8/10/2023 | 30349 | 129891 | 126795 | DSF0001023720, DSF0001023721, DSF0001023722
25 | Q184 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/6/2023 | 2/9/2024 | 4/18/2024 | 149646 | 272388 | 168711 | DSF0001023720, DSF0001023721, DSF0001023722
25 | Q184 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 9/23/2024 | 9/12/2026 |  | 3185472 | 2921539 | 69494 | DSF0001023720, DSF0001023721, DSF0001023722
25 | Q184 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/23/2024 | 9/12/2026 |  | 228186 | 348399 | 344443 | DSF0001023720, DSF0001023721, DSF0001023722
25 | Q184 | P.S. 184 - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/29/2022 | 7/29/2022 | 7/28/2022 | 0 | 105253 | 97014 | DSF0000961433
25 | Q184 | P.S. 184 - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/9/2022 | 12/27/2022 | 3/13/2023 | 77136 | 88001 | 66230 | DSF0000961433
25 | Q184 | P.S. 184 - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 11/27/2023 | 10/20/2024 |  | 1131331 | 782333 | 485100 | DSF0000961433
25 | Q184 | P.S. 184 - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 11/27/2023 | 10/20/2024 |  | 77136 | 95589 | 71966 | DSF0000961433
25 | Q184 | P.S. 184 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113075
25 | Q185 | J.H.S. 185 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033847
25 | Q185 | J.H.S. 185 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001035950
25 | Q185 | J.H.S. 185 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 66000 | 0 | DSF0001086465
25 | Q185 | J.H.S. 185 - QUEENS | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001007967
25 | Q185 | J.H.S. 185 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/2/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084815
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 7/24/2019 | 10/23/2019 | 9/25/2019 | 18000 | 10267 | 10267 | DSF0000903365
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 10/22/2019 | 3/26/2020 | 3/26/2020 | 81000 | 41113 | 41113 | DSF0000903365
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 6/9/2021 | 4/4/2022 |  | 1044000 | 928549 | 896292 | DSF0000903365
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 6/9/2021 | 4/4/2022 |  | 193500 | 107663 | 107663 | DSF0000903365
25 | Q189 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 5/20/2022 | 10/5/2022 | 12/27/2022 | 157000 | 231875 | 230295 | DSF0001023794, DSF0001023792, DSF0001023793, DSF0001074577
25 | Q189 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Design | Complete | 1/18/2023 | 6/20/2023 | 5/9/2023 | 785001 | 680915 | 614940 | DSF0001023794, DSF0001023792, DSF0001023793, DSF0001074577
25 | Q189 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Construction | In-Progress | 7/7/2023 | 10/3/2025 |  | 17662500 | 16270217 | 10715641 | DSF0001023794, DSF0001023792, DSF0001023793, DSF0001074577
25 | Q189 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | CM,F&E | In-Progress | 7/7/2023 | 10/3/2025 |  | 1099001 | 785760 | 654398 | DSF0001023794, DSF0001023792, DSF0001023793, DSF0001074577
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/22/2024 | 5/21/2024 | 6/26/2024 | 0 | 17984 | 769 | DSF0001086466
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 7/8/2024 | 12/9/2024 |  | 42300 | 24316 | 3075 | DSF0001086466
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 620400 | 620400 | 0 | DSF0001086466
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 42300 | 42300 | 9822 | DSF0001086466
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/6/2024 | 8/7/2024 | 8/1/2024 | 0 | 0 | 0 | DSF0001087070
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | In-Progress | 8/12/2024 | 12/16/2024 |  | 12686 | 12686 | 0 | DSF0001087070
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 186063 | 186063 | 0 | DSF0001087070
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 12686 | 12686 | 0 | DSF0001087070
25 | Q189 | J.H.S. 189 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 100000 | 0 | DSF0000890902
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY10 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 60705 | 0 | DSF0000690195
25 | Q189 | THE FLUSHING INTERNATIONAL HS - Q | DOE - RESOA | FY16 RESO A ELECTRICAL SYSTEMS | Construction | In-Progress | 4/16/2018 | DOER |  | DOER | 143060 | 0 | DSF0000822773
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1630098 | 0 | DSF0000913421
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 9/21/2022 | DOER |  | DOER | 392230 | 0 | DSF0000961436
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY23 RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035954
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 9/13/2023 | DOER |  | DOER | 30677 | 0 | DSF0001035955
25 | Q189 | THE FLUSHING INTERNATIONAL HS - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/5/2024 | DOES | 8/12/2024 | DOES | 65832 |  | DSF0001084816
25 | Q189 | J.H.S. 189 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/26/2024 | DOES |  | DOES | 727467 | 0 | DSF0001085754
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/13/2023 | 11/29/2023 | 1/9/2024 | 31416 | 70670 | 70670 | DSF0001023870, DSF0001023871
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/19/2024 | 6/20/2024 | 5/14/2024 | 152811 | 78239 | 74353 | DSF0001023870, DSF0001023871
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 3069303 | 3069303 | 32514 | DSF0001023870, DSF0001023871
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 251896 | 267949 | 184358 | DSF0001023870, DSF0001023871
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | Scope | Complete | 9/22/2016 | 6/5/2018 | 3/22/2018 | 145334 | 227539 | 227539 | DSF0000843951, DSF0000880580, DSF0000888785, DSF0000960584
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | Design | Complete | 4/4/2018 | 9/4/2018 | 10/5/2018 | 582551 | 892149 | 846091 | DSF0000843951, DSF0000880580, DSF0000888785, DSF0000960584
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 7/15/2019 | 7/13/2021 |  | 10858766 | 10446616 | 9702960 | DSF0000843951, DSF0000880580, DSF0000888785, DSF0000960584
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 7/15/2019 | 7/13/2021 |  | 693003 | 1329678 | 1325824 | DSF0000843951, DSF0000880580, DSF0000888785, DSF0000960584
25 | Q193 | P.S. 193 - QUEENS | SCA IEH | PO18-TEST AUDITORIUM CEILING FOR ACM. PLASTER BUBBLING | Construction | Complete | 7/25/2024 | IEH | 8/31/2024 | IEH | 0 | 0 | SCA0000073179
25 | Q193 | P.S. 193 - QUEENS | SCA IEH | PO18-ABATE & REPAIR CEILING PLASTER AT 1ST FLOOR HALLWAY BY GYM & EXIT #4. | Construction | In-Progress | 12/3/2024 | IEH |  | IEH | 0 | 0 | SCA0000073659
25 | Q193 | P.S. 193 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/20/2024 | DIIR | 10/29/2024 | DIIR | 254258 | 254258 | DSF0001035963
25 | Q193 | P.S. 193 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | Complete | 11/22/2022 | DOER | 7/25/2023 | DOER | 130521 | 103715 | DSF0001033852
25 | Q193 | P.S. 193 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112398
25 | Q193 | P.S. 193 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113079
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 6/9/2021 | 11/24/2021 | 11/5/2021 | 42780 | 46302 | 46302 | DSF0000998024
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | Design | Complete | 11/19/2021 | 4/25/2022 | 5/11/2022 | 213900 | 118968 | 118968 | DSF0000998024
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | Construction | In-Progress | 7/15/2022 | 1/5/2024 |  | 4812750 | 4596727 | 4470606 | DSF0000998024
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | CM,F&E | In-Progress | 7/15/2022 | 1/5/2024 |  | 299460 | 154919 | 154919 | DSF0000998024
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/25/2022 | 9/23/2022 | 6/15/2022 | 7070 | 3868 | 3868 | DSF0001034657
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 31815 | 15472 | 15472 | DSF0001034657
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 5/22/2023 | 3/16/2024 | 7/12/2024 | 410058 | 364679 | 336553 | DSF0001034657
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 5/22/2023 | 3/16/2024 | 7/12/2024 | 213587 | 190202 | 117452 | DSF0001034657
25 | Q194 | J.H.S. 194 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113080
25 | Q194 | J.H.S. 194 - QUEENS | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 8/2/2021 | DOER |  | DOER | 152773 | 0 | DSF0000961420
25 | Q194 | J.H.S. 194 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001083855
25 | Q194 | J.H.S. 194 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/15/2024 | DOES | 8/23/2024 | DOES | 65832 | 4454 | DSF0001084818
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 9/1/2023 | 1/23/2024 | 12/29/2023 | 82831 | 142817 | 137733 | DSF0001074775, DSF0001102546, DSF0001102547
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/3/2024 | 6/4/2024 | 4/22/2024 | 406321 | 369036 | 369036 | DSF0001074775, DSF0001102546, DSF0001102547
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 9/16/2024 | 1/13/2027 |  | 8464905 | 7732194 | 85009 | DSF0001074775, DSF0001102546, DSF0001102547
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/16/2024 | 1/13/2027 |  | 638536 | 84680 | 83941 | DSF0001074775, DSF0001102546, DSF0001102547
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/23/2023 | 5/22/2023 | 2/3/2023 | 4170 | 3052 | 3052 | DSF0001034576
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/3/2023 | 8/1/2023 | 5/2/2023 | 18765 | 12208 | 12208 | DSF0001034576
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/11/2023 | 10/5/2024 |  | 241860 | 220685 | 199718 | DSF0001034576
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/11/2023 | 10/5/2024 |  | 94240 | 90568 | 82867 | DSF0001034576
25 | Q200 | P.S. 200 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113651
25 | Q200 | P.S. 200 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113651
25 | Q200 | P.S. 200 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113651
25 | Q200 | P.S. 200 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113651
25 | Q200 | P.S. 200 - QUEENS | SCA IEH | PO18-77/25Q200/ABATE APPROX 10 FT OF ACM INSULATION SPRAYED RED. ACTIVE LEAK UNABLE TO ISOLATE 2 RIS | Construction | In-Progress | 12/11/2024 | IEH |  | IEH | 0 | 0 | SCA0000073694
25 | Q200 | P.S. 200 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 150000 | 131984 | DSF0001086470
25 | Q200 | P.S. 200 - QUEENS | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 270875 | 0 | DSF0001035969
25 | Q200 | P.S. 200 - QUEENS | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0 | DSF0001113085
25 | Q200 | P.S. 200 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/14/2024 | DOES | 8/21/2024 | DOES | 65832 | 25318 | DSF0001084681
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/9/2024 | 8/8/2024 | 4/23/2024 | 5134 | 930 | 930 | DSF0001087533
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/23/2024 | 10/18/2024 | 9/25/2024 | 23102 | 3718 | 3718 | DSF0001087533
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 297763 | 297763 | 2685 | DSF0001087533
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 59453 | 59453 | 7678 | DSF0001087533
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/27/2018 | 6/19/2019 | 2/21/2019 | 17660 | 9410 | 9410 | DSF0000890984, DSF0000912323
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2/21/2019 | 7/23/2019 | 5/16/2019 | 70249 | 37574 | 37574 | DSF0000890984, DSF0000912323
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/22/2019 | 5/16/2020 |  | 1281825 | 1193206 | 1183599 | DSF0000890984, DSF0000912323
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 7/22/2019 | 5/16/2020 |  | 87535 | 321442 | 321442 | DSF0000890984, DSF0000912323
25 | Q201 | P.S. 201 - QUEENS | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113086
25 | Q209 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | Scope | Complete | 9/30/2022 | 1/24/2024 | 12/22/2023 | 158001 | 268260 | 259014 | DSF0001024148, DSF0001024149, DSF0001024150, DSF0001024151, DSF0001086898
25 | Q209 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | Design | Complete | 1/3/2024 | 5/17/2024 | 5/2/2024 | 790000 | 648262 | 648262 | DSF0001024148, DSF0001024149, DSF0001024150, DSF0001024151, DSF0001086898
25 | Q209 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | Construction | In-Progress | 9/23/2024 | 1/20/2027 |  | 17775001 | 16112559 | 253029 | DSF0001024148, DSF0001024149, DSF0001024150, DSF0001024151, DSF0001086898
25 | Q209 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | CM,F&E | In-Progress | 9/23/2024 | 1/20/2027 |  | 1105999 | 102257 | 94321 | DSF0001024148, DSF0001024149, DSF0001024150, DSF0001024151, DSF0001086898
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/4/2022 | 6/7/2022 | 4/14/2022 | 0 | 4070 | 4070 | DSF0001033862
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 4/18/2022 | 9/16/2022 | 7/13/2022 | 23400 | 16384 | 16384 | DSF0001033862
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2/20/2023 | 11/16/2023 | 9/8/2023 | 343200 | 296562 | 271876 | DSF0001033862
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 2/20/2023 | 11/16/2023 | 9/8/2023 | 23400 | 49594 | 49034 | DSF0001033862
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033861
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033861
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033861
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 160 | 160 | DSF0001033861
25 | Q209 | P.S. 209 - QUEENS | SCA IEH | PO18-REMOVE ACM SPRAYED RED APPROX 15FT IN BOILER ROOM CRAWL SPACE , WEST CRAWL SPACE CUSTODIAN SPAC | Construction | Complete | 7/25/2024 | IEH | 8/24/2024 | IEH | 0 | 0 | SCA0000073176
25 | Q209 | Q177 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001086477
25 | Q209 | P.S. 209 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001035982
25 | Q209 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113094
25 | Q209 | P.S. 209 - QUEENS | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001113095
25 | Q214 | P.S. 214 - QUEENS | SCA IEH | PO18-BOILER ROOM, ABATE 5 L.F. PIPE INSULATION BASEMENT STAIRWAY TO AUDITORIUM, ABATE 6 L.F. PIPE IN | Construction | Complete | 6/28/2024 | IEH | 9/16/2024 | IEH | 0 | 0 | SCA0000073098
25 | Q214 | P.S. 214 - QUEENS | Fast Track Projects | LSP RESO A PLAYGROUND UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 248280 | 5241 | DSF0001087152
25 | Q214 | P.S. 214 - QUEENS | Fast Track Projects | LSP FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 7/10/2023 | FTK |  | FTK | 109013 | 1111 | DSF0001035987
25 | Q214 | P.S. 214 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0001008000
25 | Q214 | P.S. 214 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0 | DSF0001033294
25 | Q214 | P.S. 214 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0 | DSF0001113102
25 | Q214 | P.S. 214 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | Complete | 10/30/2023 | DOER | 2/13/2024 | DOER | 104867 |  | DSF0001033867
25 | Q214 | P.S. 214 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2/7/2024 | DOER | 10/23/2024 | DOER | 255388 |  | DSF0001086480
25 | Q214 | P.S. 214 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113100
25 | Q214 | P.S. 214 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 140000 | 0 | DSF0001113101
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/1/2023 | 6/1/2023 | 2/6/2023 | 4340 | 4736 | 4736 | DSF0001034636
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/6/2023 | 8/2/2023 | 5/2/2023 | 19530 | 18945 | 18945 | DSF0001034636
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 12/11/2023 | 10/5/2024 |  | 251720 | 230603 | 204589 | DSF0001034636
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 12/11/2023 | 10/5/2024 |  | 143853 | 141288 | 96434 | DSF0001034636
25 | Q219 | P.S. 219 - QUEENS | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 171706 | 0 | DSF0000791153
25 | Q219 | P.S. 219 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084684
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | Scope | Complete | 2/27/2018 | 5/25/2018 | 7/31/2018 | 142290 | 127209 | 121490 | DSF0000881116
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | Design | Complete | 8/28/2018 | 1/16/2019 | 4/16/2019 | 569160 | 761112 | 701458 | DSF0000881116
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | Construction | In-Progress | 7/29/2019 | 7/17/2021 |  | 10671750 | 10097115 | 9293190 | DSF0000881116
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | CM,F&E | In-Progress | 7/29/2019 | 7/17/2021 |  | 664020 | 503082 | 486383 | DSF0000881116
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Scope | Complete | 3/12/2020 | 7/13/2020 | 3/17/2021 | 0 | 19221 | 19221 | DSF0000913442
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Design | Complete | 9/23/2021 | 2/24/2022 | 2/7/2022 | 105240 | 137427 | 137427 | DSF0000913442
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 6/17/2022 | 3/13/2023 |  | 1543520 | 803496 | 133803 | DSF0000913442
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | CM,F&E | In-Progress | 6/17/2022 | 3/13/2023 |  | 105240 | 105736 | 103071 | DSF0000913442
25 | Q237 | EAST-WEST SCHOOL OF INTL STUDIES-Q | DOE - RESOA | RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001034683
25 | Q237 | J.H.S. 237 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | Complete | 4/7/2023 | DOER | 4/25/2023 | DOER | 34134 |  | DSF0001036004
25 | Q237 | EAST-WEST SCHOOL OF INTL STUDIES-Q | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001036005
25 | Q237 | J.H.S. 237 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 90000 | 0 | DSF0001113113
25 | Q237 | J.H.S. 237 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 260000 | 0 | DSF0001113114
25 | Q237 | J.H.S. 237 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/1/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001084827
25 | Q242 | P.S. 242 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001036010
25 | Q242 | P.S. 242 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 60000 | 59772 | DSF0001086491
25 | Q242 | P.S. 242 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113116
25 | Q242 | P.S. 242 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 110926 | 0 | DSF0000488318
25 | Q242 | P.S. 242 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 38711 | 0 | DSF0001036009
25 | Q242 | P.S. 242 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0 | DSF0001086492
25 | Q244 | P.S. 244 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Scope | Complete | 10/10/2023 | 3/8/2024 | 3/25/2024 | 56562 | 153308 | 153308 | DSF0001087154, DSF0001111916
25 | Q244 | P.S. 244 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Design | Complete | 3/25/2024 | 8/23/2024 | 5/15/2024 | 282809 | 335601 | 43696 | DSF0001087154, DSF0001111916
25 | Q244 | P.S. 244 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Construction | PNS | PNS | PNS | PNS | 6363184 | 6363184 | 530 | DSF0001087154, DSF0001111916
25 | Q244 | P.S. 244 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 395932 | 395932 | 85417 | DSF0001087154, DSF0001111916
25 | Q244 | P.S. 244 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113118
25 | Q244 | P.S. 244 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086493
25 | Q244 | P.S. 244 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001113117
25 | Q244 | P.S. 244 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/11/2023 | DOES | 10/14/2024 | DOES | 50832 |  | DSF0001084393
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY25 RESO A CLASSROOM UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113135
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY25 RESO A CLASSROOM UPGRADES | Design | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001113135
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY25 RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | 220000 | 220000 | 0 | DSF0001113135
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY25 RESO A CLASSROOM UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001113135
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CLASSROOM UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113660
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CLASSROOM UPGRADES | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113660
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113660
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CLASSROOM UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113660
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE / RESO A EXTERIOR DOOR | Scope | Complete | 5/3/2022 | 10/25/2023 | 10/18/2023 | 0 | 72925 | 66902 | DSF0001033320, DSF0001085154
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE / RESO A EXTERIOR DOOR | Design | Complete | 10/25/2023 | 3/25/2024 | 2/5/2024 | 54359 | 89660 | 58690 | DSF0001033320, DSF0001085154
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE / RESO A EXTERIOR DOOR | Construction | In-Progress | 6/10/2024 | 5/5/2025 |  | 797263 | 638151 | 50036 | DSF0001033320, DSF0001085154
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE / RESO A EXTERIOR DOOR | CM,F&E | In-Progress | 6/10/2024 | 5/5/2025 |  | 54359 | 67806 | 23218 | DSF0001033320, DSF0001085154
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 130000 | 0 | DSF0001007968
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 180547 | 0 | DSF0001085166
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/25/2022 | 9/2/2022 | 10/12/2022 | 1787500 | 1451079 | 1363078 | DSF0000911866
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 10/13/2022 | 4/7/2023 | 5/12/2023 | 8043750 | 2575995 | 1680869 | DSF0000911866
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 4/22/2024 | 9/3/2026 |  | 101440625 | 90636514 | 4838747 | DSF0000911866
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 4/22/2024 | 9/3/2026 |  | 14300000 | 5576825 | 519692 | DSF0000911866
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 9/8/2022 | 9/8/2022 | 9/8/2022 | 65500 | 49599 | 49599 | DSF0000911866
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 9/8/2022 | 12/8/2022 | 4/18/2023 | 327500 | 129120 | 121162 | DSF0000911866
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 7/3/2023 | 3/28/2024 |  | 7368750 | 6652418 | 338433 | DSF0000911866
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 7/3/2023 | 3/28/2024 |  | 458500 | 169165 | 154209 | DSF0000911866
25 | Q409 | DISTRICT 25 PRE-K CENTER | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 9/28/2022 | 12/30/2022 | 12/20/2022 | 17580 | 27210 | 27210 | DSF0001034348
25 | Q409 | DISTRICT 25 PRE-K CENTER | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/21/2022 | 6/27/2023 | 5/1/2023 | 87901 | 81857 | 79440 | DSF0001034348
25 | Q409 | DISTRICT 25 PRE-K CENTER | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 1977765 | 1977765 | 550463 | DSF0001034348
25 | Q409 | DISTRICT 25 PRE-K CENTER | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 123061 | 149041 | 100575 | DSF0001034348
25 | Q409 | DISTRICT 25 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/5/2024 | DOES | 10/25/2024 | DOES | 65832 | 8906 | DSF0001085516
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/14/2021 | 2/17/2022 | 3/30/2022 | 96080 | 128549 | 128549 | DSF0001103872, DSF0001083947
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 4/14/2023 | 8/30/2023 | 4/16/2024 | 472411 | 312420 | 268384 | DSF0001103872, DSF0001083947
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 9937911 | 9937911 | 39263 | DSF0001103872, DSF0001083947
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 732505 | 732505 | 60638 | DSF0001103872, DSF0001083947
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA GYM FLOOR REPLACEMENT | Scope | Complete | 1/13/2023 | 4/17/2023 | 2/15/2023 | 2739 | 15811 | 398 | DSF0001034898
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA GYM FLOOR REPLACEMENT | Design | Complete | 4/13/2023 | 8/14/2023 | 4/16/2024 | 12325 | 26780 | 1319 | DSF0001034898
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA GYM FLOOR REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 158859 | 158859 | 3160 | DSF0001034898
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA GYM FLOOR REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 29444 | 29444 | 3921 | DSF0001034898
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Scope | Complete | 8/9/2023 | 12/12/2023 | 8/24/2023 | 2093 | 20350 | 336 | DSF0001085326
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Design | Complete | 8/25/2023 | 1/17/2024 | 4/16/2024 | 9419 | 21342 | 1344 | DSF0001085326
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 121397 | 121397 | 1659 | DSF0001085326
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 22500 | 22500 | 7695 | DSF0001085326
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA IEH | PO18-64 SQUARE FEET OF CONCEALED SPLINE CEILING ON VERGE OF COLLAPSE IN MAIN (JV) ENTRANCE VESTIBUL | Construction | Complete | 8/16/2024 | IEH | 8/18/2024 | IEH | 0 | 0 | SCA0000073299
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA IEH | PO18-TEST CEILING IN LOBBY/ MAIN ENTRANCE 1ST. FLOOR FOR ACM CEILING TILE MASTIC IS ACM ABATEMENT DR | Construction | Complete | 9/3/2024 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000073344
25 | Q425 | JOHN BOWNE HS - QUEENS | Fast Track Projects | IDA GYM FLOOR REPLACEMENT | Construction | In-Progress | 6/6/2022 | FTK |  | FTK | 1418087 | 1252887 | SCA0000070494
25 | Q425 | JOHN BOWNE HS - QUEENS | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001033922
25 | Q425 | JOHN BOWNE HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/13/2024 | DOES | 9/5/2024 | DOES | 65832 | 15416 | DSF0001085001
25 | Q425 | JOHN BOWNE HS - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/23/2024 | DOES |  | DOES | 589937 | 0 | DSF0001085759
25 | Q426 | JOHN BOWNE HS - QUEENS | SCA CIP RESOA | FY24 RESO A FARM BUILDING | Scope | In-Progress | 9/14/2023 | 12/15/2023 |  | 0 | 52946 | 25213 | DSF0001085823
25 | Q426 | JOHN BOWNE HS - QUEENS | SCA CIP RESOA | FY24 RESO A FARM BUILDING | Design | PNS | PNS | PNS | PNS | 420000 | 367054 | 44421 | DSF0001085823
25 | Q426 | JOHN BOWNE HS - QUEENS | SCA CIP RESOA | FY24 RESO A FARM BUILDING | Construction | PNS | PNS | PNS | PNS | 6160000 | 6160000 | 5471 | DSF0001085823
25 | Q426 | JOHN BOWNE HS - QUEENS | SCA CIP RESOA | FY24 RESO A FARM BUILDING | CM,F&E | PNS | PNS | PNS | PNS | 420000 | 420000 | 100576 | DSF0001085823
25 | Q426 | JOHN BOWNE HS - QUEENS | DOE - RESOA | FY24 RESO A PAVED AREA- BLACKTOP | Construction | Complete | 8/14/2023 | DOER | 1/23/2024 | DOER | 374366 |  | DSF0001085114
25 | Q443 | Q000 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 11/21/2024 | IEH | 11/26/2024 | IEH | 0 | 0 | SCA0000073629
25 | Q443 | Q000 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/9/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085523
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | In-Progress | 9/6/2024 | 1/27/2025 |  | 10000 | 14568 | 389 | DSF0001104148
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | PNS | PNS | PNS | PNS | 40000 | 40000 | 1557 | DSF0001104148
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 575000 | 575000 | 0 | DSF0001104148
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 147500 | 147500 | 7479 | DSF0001104148
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 4/2/2024 | 8/2/2024 | 11/8/2024 | 0 | 19402 | 1834 | DSF0001086542
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 11/8/2024 | 3/31/2025 |  | 90000 | 70598 | 7338 | DSF0001086542
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001086542
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 6705 | DSF0001086542
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 4/2/2024 | 7/3/2024 | 12/30/2024 | 0 | 0 | 0 | DSF0001087085
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | In-Progress | 12/30/2024 | 5/2/2025 |  | 14833 | 14833 | 0 | DSF0001087085
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 217555 | 217555 | 0 | DSF0001087085
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 14833 | 14833 | 733 | DSF0001087085
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/15/2023 | 6/16/2023 | 11/9/2023 | 0 | 19986 | 19986 | DSF0001036057, DSF0001036058
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 11/13/2023 | 4/1/2024 | 8/21/2024 | 45000 | 63824 | 59653 | DSF0001036057, DSF0001036058
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 22359 | DSF0001036057, DSF0001036058
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 58569 | 25330 | DSF0001036057, DSF0001036058
25 | Q460 | FLUSHING HS - QUEENS | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/11/2023 | FTK |  | FTK | 145416 | 137341 | DSF0000867241
25 | Q460 | FLUSHING HS - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 100000 | 0 | DSF0000890927
25 | Q460 | QUEENS HIGH SCHOOL FOR LANGUAGE STUDIES | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 12/17/2024 | DIIR | 99645 | 99645 | DSF0001033878
25 | Q460 | QUEENS HIGH SCHOOL FOR LANGUAGE STUDIES | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 9/25/2024 | DIIR |  | DIIR | 100000 | 0 | DSF0001036056
25 | Q460 | VERITAS ACADEMY | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 10/25/2024 | DIIR | 100000 | 100000 | DSF0001086530
25 | Q460 | VERITAS ACADEMY | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 169000 | 0 | DSF0001113166
25 | Q460 | FLUSHING HS - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113167
25 | Q460 | FLUSHING HS - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | Complete | 2/13/2023 | DOER | 7/25/2023 | DOER | 52837 | 1131 | DSF0001033928
25 | Q460 | FLUSHING HS - QUEENS | DOE - RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 125000 | 1187 | DSF0001086541
25 | Q460 | FLUSHING HS - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 430000 | 0 | DSF0001113164
25 | Q460 | VERITAS ACADEMY | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113165
25 | Q460 | FLUSHING HS - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 12/9/2022 | DOES | 12/20/2023 | DOES | 427265 | 420234 | DSF0000960863
25 | Q460 | FLUSHING HS - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 10/16/2023 | DOES |  | DOES | 778289 | 0 | DSF0001076243
25 | Q460 | FLUSHING HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/9/2024 | DOES | 8/16/2024 | DOES | 65832 |  | DSF0001085010
25 | Q460 | FLUSHING HS - QUEENS | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 3/11/2024 | DOES |  | DOES | 571711 | 49245 | DSF0001104146
25 | Q462 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 2/24/2020 | 7/8/2020 | 11/29/2021 | 10073 | 18873 | 18873 | DSF0000960682
25 | Q462 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | Design | Complete | 12/8/2021 | 5/11/2022 | 12/2/2022 | 45329 | 90862 | 72646 | DSF0000960682
25 | Q462 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | Construction | In-Progress | 12/18/2023 | 12/16/2024 |  | 584240 | 634917 | 157447 | DSF0000960682
25 | Q462 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | CM,F&E | In-Progress | 12/18/2023 | 12/16/2024 |  | 108286 | 108229 | 76433 | DSF0000960682
25 | Q463 | FLUSHING HS - QUEENS | SCA CIP RESOA | FY23 RESO A ATHLETIC FIELD UPGRADE | Scope | Complete | 1/20/2023 | 5/19/2023 | 7/20/2023 | 0 | 218564 | 217585 | DSF0001036054
25 | Q463 | FLUSHING HS - QUEENS | SCA CIP RESOA | FY23 RESO A ATHLETIC FIELD UPGRADE | Design | Complete | 7/25/2023 | 1/25/2024 | 5/14/2024 | 77472 | 319795 | 290581 | DSF0001036054
25 | Q463 | FLUSHING HS - QUEENS | SCA CIP RESOA | FY23 RESO A ATHLETIC FIELD UPGRADE | Construction | PNS | PNS | PNS | PNS | 1136256 | 1136256 | 58646 | DSF0001036054
25 | Q463 | FLUSHING HS - QUEENS | SCA CIP RESOA | FY23 RESO A ATHLETIC FIELD UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 77472 | 77472 | 41229 | DSF0001036054
25 | Q499 | P.S./I.S. 499 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 8/25/2020 | FTK |  | FTK | 155255 | 81174 | DSF0000914245
25 | Q499 | Q993 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001036066
25 | Q499 | Q993 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001086561
25 | Q499 | P.S./I.S. 499 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084693
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/13/2023 | 8/17/2023 | 9/18/2023 | 1195340 | 1230719 | 1220840 | DSF0000911856
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 9/19/2023 | 4/12/2024 | 5/9/2024 | 5379030 | 2136310 | 1449281 | DSF0000911856
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 9/16/2024 | 9/3/2027 |  | 67835545 | 61071768 | 349272 | DSF0000911856
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 9/16/2024 | 9/3/2027 |  | 9562720 | 3840683 | 440984 | DSF0000911856
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 5/11/2023 | 5/11/2023 | 5/11/2023 | 39545 | 1764 | 1764 | DSF0000911856
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 5/12/2023 | 8/31/2023 | 1/16/2024 | 197723 | 106007 | 105819 | DSF0000911856
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 5/20/2024 | 12/15/2024 |  | 4448759 | 4715518 | 1659289 | DSF0000911856
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 5/20/2024 | 12/15/2024 |  | 276812 | 226268 | 220192 | DSF0000911856
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/20/2023 | 8/24/2023 | 8/17/2023 | 952120 | 728475 | 713487 | DSF0001034679
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 8/18/2023 | 3/28/2024 | 5/9/2024 | 4284540 | 1051653 | 958933 | DSF0001034679
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 11/18/2024 | 9/3/2027 |  | 54032810 | 47775463 | 154876 | DSF0001034679
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 11/18/2024 | 9/3/2027 |  | 7616960 | 3042049 | 329613 | DSF0001034679
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 6/2/2023 | 7/7/2023 | 6/2/2023 | 15889 | 19883 | 19796 | DSF0001034679
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 6/5/2023 | 10/27/2023 | 11/17/2023 | 71501 | 98428 | 83055 | DSF0001034679
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 7/8/2024 | 5/3/2025 |  | 921563 | 856309 | 233414 | DSF0001034679
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 7/8/2024 | 5/3/2025 |  | 170807 | 143836 | 139188 | DSF0001034679
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/22/2024 | 9/17/2024 | 9/17/2024 | 2082900 | 668073 | 565657 | DSF0000911839
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | In-Progress | 9/18/2024 | 4/21/2025 |  | 8331599 | 8331599 | 1944058 | DSF0000911839
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 115080208 | 115080208 | 176407 | DSF0000911839
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 15101023 | 15101023 | 311603 | DSF0000911839
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 4/23/2024 | 4/23/2024 | 4/23/2024 | 40251 | 10820 | 10820 | DSF0000911839
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 4/24/2024 | 8/23/2024 | 11/6/2024 | 187838 | 79277 | 79084 | DSF0000911839
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 2978577 | 2978577 | 69760 | DSF0000911839
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 295174 | 295174 | 23781 | DSF0000911839
25 | Q515 | TOWNSEND HARRIS HS - Q | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY / COOLING TOWER REPLACEMENT | Scope | Complete | 7/11/2024 | 11/26/2024 | 11/26/2024 | 572362 | 195721 | 134288 | DSF0001076500, DSF0001113882, DSF0001132164, DSF0001132165, DSF0001132168
25 | Q515 | TOWNSEND HARRIS HS - Q | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY / COOLING TOWER REPLACEMENT | Design | In-Progress | 12/16/2024 | 5/19/2025 |  | 2739330 | 2739330 | 246360 | DSF0001076500, DSF0001113882, DSF0001132164, DSF0001132165, DSF0001132168
25 | Q515 | TOWNSEND HARRIS HS - Q | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY / COOLING TOWER REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 50602377 | 50602377 | 31310 | DSF0001076500, DSF0001113882, DSF0001132164, DSF0001132165, DSF0001132168
25 | Q515 | TOWNSEND HARRIS HS - Q | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY / COOLING TOWER REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 4168976 | 4168976 | 31205 | DSF0001076500, DSF0001113882, DSF0001132164, DSF0001132165, DSF0001132168
25 | Q515 | TOWNSEND HARRIS HS - Q | Fast Track Projects | LSP- WATER BOOSTER PUMP SYSTEM | Construction | In-Progress | 1/7/2019 | FTK |  | FTK | 365305 | 318809 | DSF0000891043
25 | Q515 | TOWNSEND HARRIS HS - Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001086565
25 | Q515 | TOWNSEND HARRIS HS - Q | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 70467 | 0 | DSF0001086564
25 | Q515 | TOWNSEND HARRIS HS - Q | DOE - Skilled Trades | HVAC COOLING TOWER REPLACEMENT | Construction | In-Progress | 12/6/2022 | DOES |  | DOES | 2401394 | 0 | DSF0000904556
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/15/2024 | DIIR | 7/30/2024 | DIIR | 150000 | 150000 | DSF0001086578
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | DOE - RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 10/17/2019 | DOER |  | DOER | 192361 | 0 | DSF0000867381
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 69565 | 0 | DSF0001008086
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0001033950
25 | Q792 | NORTH QUEENS COMMUNITY HS - Q | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 105000 | 0 | DSF0000889946
25 | Q792 | NORTH QUEENS COMMUNITY HS - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/29/2024 | DOES | 9/6/2024 | DOES | 65832 |  | DSF0001085538
25 | Q859 | REG OPERATION CENTER C- QUEENS | DOE - Skilled Trades | COOLING TOWER | Construction | In-Progress | 6/2/2016 | DOES |  | DOES | 316593 | 0 | DSF0000844132
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 1/21/2020 | 6/19/2020 | 5/27/2020 | 64200 | 78482 | 78482 | DSF0000960646, DSF0000960647
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/27/2020 | 10/27/2020 | 8/19/2020 | 321000 | 357891 | 303058 | DSF0000960646, DSF0000960647
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 5/10/2022 | 5/8/2024 |  | 7222500 | 6550917 | 6246562 | DSF0000960646, DSF0000960647
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 5/10/2022 | 5/8/2024 |  | 449400 | 603723 | 598658 | DSF0000960646, DSF0000960647
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 8/15/2024 | 1/3/2025 | 10/9/2024 | 131955 | 140169 | 113598 | DSF0001071510, DSF0001127020, DSF0001127021
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 10/23/2024 | 3/28/2025 |  | 640177 | 640177 | 307611 | DSF0001071510, DSF0001127020, DSF0001127021
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 12581745 | 12581745 | 79 | DSF0001071510, DSF0001127020, DSF0001127021
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 943275 | 943275 | 29808 | DSF0001071510, DSF0001127020, DSF0001127021
26 | Q018 | P.S. 18 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/12/2022 | DOER |  | DOER | 82800 | 0 | DSF0001008048
26 | Q018 | P.S. 18 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 85000 | 0 | DSF0001035802
26 | Q018 | P.S. 18 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 254581 | 0 | DSF0001086349
26 | Q026 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | Scope | Complete | 10/25/2019 | 9/21/2021 | 9/21/2021 | 1198860 | 864486 | 824159 | DSF0000911853, DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | Design | Complete | 9/21/2021 | 5/11/2022 | 5/9/2022 | 5394870 | 2775499 | 2066490 | DSF0000911853, DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | Construction | Complete | 8/8/2022 | 9/3/2025 | 12/16/2024 | 68035305 | 61912510 | 58349945 | DSF0000911853, DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | CM,Art,F&E | Complete | 8/8/2022 | 9/3/2025 | 12/16/2024 | 9590880 | 6110567 | 3037542 | DSF0000911853, DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 1/19/2018 | 6/20/2018 | 4/9/2018 | 108255 | 71227 | 71227 | DSF0000798312, DSF0000798314
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/2/2018 | 11/29/2018 | 8/21/2018 | 433020 | 239026 | 226111 | DSF0000798312, DSF0000798314
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 1/14/2019 | 1/12/2021 |  | 8119125 | 7776967 | 7269329 | DSF0000798312, DSF0000798314
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 1/14/2019 | 1/12/2021 |  | 505190 | 708381 | 695482 | DSF0000798312, DSF0000798314
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING RENOVATIONS | Scope | Complete | 8/5/2021 | 10/18/2021 | 12/6/2021 | 79322 | 73383 | 73383 | DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING RENOVATIONS | Design | Complete | 12/15/2021 | 6/10/2022 | 7/19/2023 | 396611 | 230794 | 224668 | DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING RENOVATIONS | Construction | PNS | PNS | PNS | PNS | 8923743 | 8923743 | 105559 | DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING RENOVATIONS | CM,F&E | PNS | PNS | PNS | PNS | 555255 | 555255 | 37654 | DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING-GYMNASIUM / EXISTING BUILDING-AUDITORIUM | Scope | Complete | 2/10/2022 | 6/27/2022 | 7/27/2022 | 11184 | 9080 | 3315 | DSF0000911853, DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING-GYMNASIUM / EXISTING BUILDING-AUDITORIUM | Design | Complete | 8/9/2022 | 1/30/2023 | 5/11/2023 | 50326 | 14256 | 14256 | DSF0000911853, DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING-GYMNASIUM / EXISTING BUILDING-AUDITORIUM | Construction | PNS | PNS | PNS | PNS | 648640 | 648640 | 21854 | DSF0000911853, DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING-GYMNASIUM / EXISTING BUILDING-AUDITORIUM | CM,F&E | PNS | PNS | PNS | PNS | 120221 | 120221 | 14717 | DSF0000911853, DSF0000911853
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 12/1/2021 | 6/24/2022 | 7/8/2022 | 23546 | 22672 | 22672 | SCA0000070743, DSF0001035066
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 7/11/2022 | 12/12/2022 | 5/22/2023 | 105958 | 68745 | 65309 | SCA0000070743, DSF0001035066
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 1365680 | 1365680 | 4558 | SCA0000070743, DSF0001035066
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 253122 | 253122 | 18443 | SCA0000070743, DSF0001035066
26 | Q026 | P.S. 26 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 50000 | 0 | DSF0000890854
26 | Q026 | P.S. 26 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 10/15/2024 | DIIR | 69750 | 69750 | DSF0001033740
26 | Q026 | P.S. 26 - QUEENS | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001033739
26 | Q031 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 9/17/2014 | 2/5/2015 | 3/16/2015 | 226470 | 129723 | 129723 | DSF0000800273, DSF0000833500, DSF0000843954, DSF0000833494, DSF0000843955, DSF0000833495, DSF0000833496
26 | Q031 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 2/12/2016 | 7/14/2016 | 10/12/2016 | 898205 | 1019021 | 931008 | DSF0000800273, DSF0000833500, DSF0000843954, DSF0000833494, DSF0000843955, DSF0000833495, DSF0000833496
26 | Q031 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | Construction | In-Progress | 5/8/2017 | 4/7/2019 |  | 16151973 | 32525076 | 26095955 | DSF0000800273, DSF0000833500, DSF0000843954, DSF0000833494, DSF0000843955, DSF0000833495, DSF0000833496
26 | Q031 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | CM,F&E | In-Progress | 5/8/2017 | 4/7/2019 |  | 1156717 | 1950723 | 1904264 | DSF0000800273, DSF0000833500, DSF0000843954, DSF0000833494, DSF0000843955, DSF0000833495, DSF0000833496
26 | Q031 | P.S. 31 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086358
26 | Q031 | P.S. 31 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 6/29/2022 | DOES | 12/11/2023 | DOES | 223562 | 6201 | DSF0001008703
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 11/16/2018 | 4/5/2019 | 6/19/2019 | 69195 | 174599 | 174599 | DSF0000878186, DSF0000878187, DSF0000878188
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 7/10/2024 | 12/11/2024 |  | 276782 | 276782 | 8736 | DSF0000878186, DSF0000878187, DSF0000878188
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 5189659 | 5189659 | 5417 | DSF0000878186, DSF0000878187, DSF0000878188
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 322912 | 322912 | 21815 | DSF0000878186, DSF0000878187, DSF0000878188
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | SSBA - WORK IN EXISTING BUILDING | Scope | Complete | 6/8/2021 | 10/20/2021 | 2/8/2022 | 20400 | 66933 | 66933 | DSF0000889663
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | SSBA - WORK IN EXISTING BUILDING | Design | Complete | 2/17/2022 | 7/20/2022 | 1/4/2023 | 101998 | 229984 | 215939 | DSF0000889663
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | SSBA - WORK IN EXISTING BUILDING | Construction | PNS | PNS | PNS | PNS | 2294962 | 2294962 | 24964 | DSF0000889663
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | SSBA - WORK IN EXISTING BUILDING | CM,F&E | PNS | PNS | PNS | PNS | 142798 | 142798 | 33180 | DSF0000889663
26 | Q041 | P.S. 41 - QUEENS | SCA Emergency Response | STONE CRACKS | Construction | In-Progress | 2/4/2022 | EMER |  | EMER |  | 0 | SCA0000070849
26 | Q041 | Q993 SPED - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 35000 | 0 | DSF0000913960
26 | Q041 | P.S. 41 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112954
26 | Q041 | Q993 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112955
26 | Q041 | Q993 SPED - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112195
26 | Q041 | P.S. 41 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/15/2023 | DOES |  | DOES | 205645 | 0 | DSF0001034423
26 | Q046 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | Scope | Complete | 10/28/2019 | 12/19/2019 | 2/28/2020 | 67959 | 130695 | 130695 | DSF0000798204
26 | Q046 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | Design | Complete | 3/11/2020 | 10/13/2020 | 12/22/2021 | 339795 | 390083 | 213678 | DSF0000798204
26 | Q046 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | Construction | In-Progress | 7/10/2024 | 3/1/2026 |  | 7645388 | 6930634 | 17151 | DSF0000798204
26 | Q046 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | CM,F&E | In-Progress | 7/10/2024 | 3/1/2026 |  | 480465 | 560797 | 552304 | DSF0000798204
26 | Q046 | P.S. 46 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 3/28/2024 | DOER |  | DOER | 274552 | 0 | DSF0001086363
26 | Q046 | P.S. 46 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084287
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA GYM PARTITION & BLEACHERS | Scope | Complete | 11/5/2021 | 3/28/2022 | 12/4/2023 | 84779 | 323695 | 320858 | SCA0000070744, DSF0001111865, DSF0001111864
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA GYM PARTITION & BLEACHERS | Design | In-Progress | 12/5/2023 | 9/27/2024 |  | 415109 | 415109 | 171338 | SCA0000070744, DSF0001111865, DSF0001111864
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA GYM PARTITION & BLEACHERS | Construction | PNS | PNS | PNS | PNS | 8580091 | 8580091 | 354199 | SCA0000070744, DSF0001111865, DSF0001111864
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA GYM PARTITION & BLEACHERS | CM,F&E | PNS | PNS | PNS | PNS | 659332 | 659332 | 87381 | SCA0000070744, DSF0001111865, DSF0001111864
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/21/2022 | 12/7/2022 | 3/31/2023 | 97063 | 132275 | 132170 | DSF0001021572, DSF0001021573, DSF0001021574
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 4/21/2023 | 9/22/2023 | 10/10/2023 | 485315 | 458655 | 379712 | DSF0001021572, DSF0001021573, DSF0001021574
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 5/6/2024 | 5/5/2026 |  | 10919587 | 10026143 | 2319250 | DSF0001021572, DSF0001021573, DSF0001021574
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 5/6/2024 | 5/5/2026 |  | 680443 | 337718 | 308511 | DSF0001021572, DSF0001021573, DSF0001021574
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113633
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113633
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113633
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113633
26 | Q067 | J.H.S. 67 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001112974
26 | Q067 | J.H.S. 67 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 12/15/2023 | DOER |  | DOER | 112704 | 0 | DSF0001035839
26 | Q067 | J.H.S. 67 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/15/2024 | DOES | 11/13/2024 | DOES | 65832 |  | DSF0001084802
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA DOMESTIC PIPING / IDA ELECTRICAL SYSTEMS / IDA CLIMATE CONTROL | Scope | Complete | 10/8/2021 | 2/14/2022 | 2/3/2022 | 65530 | 85203 | 85203 | SCA0000070745, DSF0001083685, DSF0001083684, DSF0001072469, DSF0001072461
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA DOMESTIC PIPING / IDA ELECTRICAL SYSTEMS / IDA CLIMATE CONTROL | Design | Complete | 9/21/2022 | 2/9/2023 | 2/16/2023 | 316124 | 250740 | 238687 | SCA0000070745, DSF0001083685, DSF0001083684, DSF0001072469, DSF0001072461
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA DOMESTIC PIPING / IDA ELECTRICAL SYSTEMS / IDA CLIMATE CONTROL | Construction | PNS | PNS | PNS | PNS | 6115639 | 6115639 | 16063 | SCA0000070745, DSF0001083685, DSF0001083684, DSF0001072469, DSF0001072461
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA DOMESTIC PIPING / IDA ELECTRICAL SYSTEMS / IDA CLIMATE CONTROL | CM,F&E | PNS | PNS | PNS | PNS | 545169 | 545169 | 97314 | SCA0000070745, DSF0001083685, DSF0001083684, DSF0001072469, DSF0001072461
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS / FLOOD ELIMINATION / FENCING | Scope | Complete | 7/2/2024 | 11/18/2024 | 11/19/2024 | 663568 | 170652 | 138184 | DSF0001100216, DSF0001100217, DSF0001113891, DSF0001127989, DSF0001113890, DSF0001128002
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS / FLOOD ELIMINATION / FENCING | Design | In-Progress | 12/6/2024 | 5/9/2025 |  | 3096655 | 3096655 | 184890 | DSF0001100216, DSF0001100217, DSF0001113891, DSF0001127989, DSF0001113890, DSF0001128002
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS / FLOOD ELIMINATION / FENCING | Construction | PNS | PNS | PNS | PNS | 49104085 | 49104085 | 4388 | DSF0001100216, DSF0001100217, DSF0001113891, DSF0001127989, DSF0001113890, DSF0001128002
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS / FLOOD ELIMINATION / FENCING | CM,F&E | PNS | PNS | PNS | PNS | 4866170 | 4866170 | 42278 | DSF0001100216, DSF0001100217, DSF0001113891, DSF0001127989, DSF0001113890, DSF0001128002
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/1/2022 | 11/1/2022 | 7/22/2022 | 4534 | 4623 | 4623 | DSF0001034654
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/22/2022 | 1/20/2023 | 1/18/2023 | 20403 | 18493 | 18493 | DSF0001034654
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 6/12/2023 | 4/6/2024 | 4/6/2024 | 262972 | 232369 | 205176 | DSF0001034654
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 6/12/2023 | 4/6/2024 | 4/6/2024 | 163606 | 178777 | 124169 | DSF0001034654
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112983
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 36000 | 36000 | 0 | DSF0001112983
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 528000 | 528000 | 0 | DSF0001112983
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 36000 | 36000 | 0 | DSF0001112983
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113634
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113634
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113634
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113634
26 | Q074 | I.S. 74 - QUEENS | SCA IEH | PO18-77/26Q074/ROOM IS CLOSED 9X9 TILES COMING UP ROOM 328 THESE WAS A STEAM LEAK THAT HAS BEEN REPA | Construction | Complete | 11/19/2024 | IEH | 12/8/2024 | IEH | 0 | 0 | SCA0000073619
26 | Q074 | I.S. 74 - QUEENS | Fast Track Projects | IDA GYM FLOOR REPLACEMENT @ Q074 | Construction | In-Progress | 5/25/2022 | FTK |  | FTK | 628603 | 537631 | SCA0000070482
26 | Q074 | I.S. 74 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/29/2024 | DIIR | 7/24/2024 | DIIR | 175000 | 175000 | DSF0001033769
26 | Q074 | I.S. 74 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/3/2024 | DOER |  | DOER | 160864 | 0 | DSF0001035848
26 | Q074 | I.S. 74 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/15/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084805
26 | Q094 | P.S. 94 - QUEENS | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LAB | F&E | Complete | 6/6/2024 |  | 8/14/2024 | 100000 | 100000 | 100000 | DSF0001086397
26 | Q094 | P.S. 94 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0 | DSF0001112998
26 | Q094 | P.S. 94 - QUEENS | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/13/2016 | DOER |  | DOER | 224547 | 0 | DSF0000822859
26 | Q094 | P.S. 94 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/8/2024 | DOER |  | DOER | 97118 | 0 | DSF0001035865
26 | Q094 | P.S. 94 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 8/23/2023 | DOES |  | DOES | 116027 | 0 | DSF0001034425
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | Scope | Complete | 3/14/2018 | 7/27/2018 | 8/22/2018 | 59355 | 20865 | 20865 | DSF0000901929
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | Design | Complete | 9/19/2018 | 2/25/2019 | 5/13/2019 | 237420 | 168443 | 153111 | DSF0000901929
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | Construction | Complete | 7/29/2019 | 10/20/2020 | 4/22/2022 | 4451625 | 4522066 | 4086181 | DSF0000901929
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | CM,F&E | Complete | 7/29/2019 | 10/20/2020 | 4/22/2022 | 276990 | 187994 | 172662 | DSF0000901929
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 4/28/2022 | 9/13/2022 | 8/9/2022 | 10940 | 26008 | 15031 | DSF0001022117
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 8/12/2022 | 1/18/2023 | 12/22/2022 | 49230 | 59433 | 59433 | DSF0001022117
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 4/17/2023 | 2/10/2024 |  | 634520 | 564106 | 40325 | DSF0001022117
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 4/17/2023 | 2/10/2024 |  | 117605 | 92684 | 91577 | DSF0001022117
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Scope | Complete | 2/26/2021 | 6/25/2021 | 5/28/2021 | 0 | 11130 | 11130 | DSF0000913394
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Design | Complete | 6/8/2021 | 11/29/2021 | 2/11/2022 | 48700 | 91668 | 15804 | DSF0000913394
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 6/6/2022 | 3/2/2023 |  | 714265 | 420909 | 326351 | DSF0000913394
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | CM,F&E | In-Progress | 6/6/2022 | 3/2/2023 |  | 48700 | 50883 | 49961 | DSF0000913394
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/9/2023 | 3/14/2024 | 11/28/2023 | 0 | 6538 | 6538 | DSF0001086399
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | In-Progress | 10/18/2024 | 4/17/2025 |  | 34743 | 28205 | 26152 | DSF0001086399
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 509557 | 509557 | 3683 | DSF0001086399
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 34743 | 34743 | 4898 | DSF0001086399
26 | Q098 | P.S. 98 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 10/27/2023 | DIIR | 7/25/2024 | DIIR | 100000 | 100000 | DSF0001035868
26 | Q098 | P.S. 98 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/11/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001086398
26 | Q098 | P.S. 98 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113003
26 | Q098 | P.S. 98 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/15/2024 | DOES |  | DOES | 83268 | 0 | DSF0001034426
26 | Q115 | P.S. 115 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113013
26 | Q115 | P.S. 115 - QUEENS | DOE - RESOA | FY 21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/29/2023 | DOER |  | DOER | 227449 | 0 | DSF0001008042
26 | Q130 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/20/2021 | 9/20/2021 | 7/23/2021 | 80154 | 69634 | 69634 | DSF0000960808, DSF0000996879, DSF0001008804
26 | Q130 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 7/27/2021 | 1/27/2022 | 12/15/2021 | 400084 | 380136 | 318585 | DSF0000960808, DSF0000996879, DSF0001008804
26 | Q130 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 8/3/2022 | 8/1/2024 |  | 8942768 | 8253717 | 7796538 | DSF0000960808, DSF0000996879, DSF0001008804
26 | Q130 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 8/3/2022 | 8/1/2024 |  | 566200 | 350124 | 347453 | DSF0000960808, DSF0000996879, DSF0001008804
26 | Q130 | Q993 SPED - QUEENS | Fast Track Projects | LSP FY23 RESO A ROOM CONVERSION | Construction | PNS | FTK | FTK | FTK | FTK | 106400 | 0 | DSF0001035898
26 | Q130 | P.S. 130 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 7/8/2024 | DIIR | 50000 | 50000 | DSF0001086420
26 | Q130 | P.S. 130 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113025
26 | Q130 | Q993 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113026
26 | Q133 | P.S. 133 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/30/2023 | 11/16/2023 | 11/22/2023 | 89511 | 205850 | 205850 | DSF0001073534, DSF0001101271, DSF0001101276, DSF0001101275
26 | Q133 | P.S. 133 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Design | Complete | 12/13/2023 | 5/15/2024 | 4/30/2024 | 446924 | 590910 | 426548 | DSF0001073534, DSF0001101271, DSF0001101276, DSF0001101275
26 | Q133 | P.S. 133 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 11/4/2024 | 3/3/2027 |  | 10001209 | 9071063 | 106609 | DSF0001073534, DSF0001101271, DSF0001101276, DSF0001101275
26 | Q133 | P.S. 133 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 11/4/2024 | 3/3/2027 |  | 631311 | 71456 | 71456 | DSF0001073534, DSF0001101271, DSF0001101276, DSF0001101275
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/20/2023 | 4/20/2023 | 3/29/2023 | 0 | 25420 | 25420 | DSF0001035901
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 21000 | 1630 | 1630 | DSF0001035901
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 308000 | 862106 | 1550 | DSF0001035901
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 21000 | 58780 | 2931 | DSF0001035901
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 2/24/2023 | 5/25/2023 |  | 0 | 64 | 64 | DSF0001035902
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 257 | 257 | DSF0001035902
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035902
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035902
26 | Q133 | P.S. 133 - QUEENS | SCA IEH | PO18-IN BASEMENT FAN ROOM AREA MARKED IN RED AREA FOR THE AUDITORIUM BLOWER AND AUDITORIUM EXHAUST | Construction | Complete | 8/13/2024 | IEH | 10/5/2024 | IEH | 0 | 0 | SCA0000073281
26 | Q133 | P.S. 133 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 290000 | 0 | DSF0001113028
26 | Q133 | P.S. 133 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/30/2022 | DOES |  | DOES | 128865 | 0 | DSF0001034254
26 | Q133 | P.S. 133 - QUEENS | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 5/13/2024 | DOES |  | DOES | 75386 | 0 | DSF0001112219
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 11/13/2023 | 4/1/2024 | 6/4/2024 | 195440 | 172822 | 172822 | DSF0001074065, DSF0001101821, DSF0001101823, DSF0001101824
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Design | Complete | 6/6/2024 | 11/7/2024 | 12/5/2024 | 896473 | 386018 | 202529 | DSF0001074065, DSF0001101821, DSF0001101823, DSF0001101824
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 14076915 | 14076915 | 166722 | DSF0001074065, DSF0001101821, DSF0001101823, DSF0001101824
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1606590 | 1606590 | 62293 | DSF0001074065, DSF0001101821, DSF0001101823, DSF0001101824
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | GYM CEILING | Scope | Complete | 7/6/2023 | 11/6/2023 | 1/10/2024 | 17864 | 26297 | 26297 | DSF0001085201
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | GYM CEILING | Design | Complete | 1/22/2024 | 6/5/2024 | 11/19/2024 | 83366 | 58653 | 32705 | DSF0001085201
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | GYM CEILING | Construction | PNS | PNS | PNS | PNS | 1321953 | 1321953 | 18552 | DSF0001085201
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | GYM CEILING | CM,F&E | PNS | PNS | PNS | PNS | 131004 | 131004 | 20204 | DSF0001085201
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 9/13/2018 | 6/19/2019 | 2/20/2019 | 39159 | 29507 | 29507 | DSF0000868321, DSF0000880102, DSF0000912319
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2/20/2019 | 7/22/2019 | 5/16/2019 | 151190 | 120443 | 120006 | DSF0000868321, DSF0000880102, DSF0000912319
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/22/2019 | 5/16/2020 |  | 2346034 | 2266189 | 2031298 | DSF0000868321, DSF0000880102, DSF0000912319
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 7/22/2019 | 5/16/2020 |  | 253539 | 152327 | 151890 | DSF0000868321, DSF0000880102, DSF0000912319
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 10/30/2023 | 3/4/2024 | 11/28/2023 | 0 | 6276 | 6276 | DSF0001035927
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 12/1/2023 | 5/29/2024 | 3/6/2024 | 66300 | 25109 | 25109 | DSF0001035927
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 7/29/2024 | 5/24/2025 |  | 972400 | 165686 | 0 | DSF0001035927
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 7/29/2024 | 5/24/2025 |  | 70040 | 24786 | 13723 | DSF0001035927
26 | Q158 | J.H.S. 158 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0 | DSF0001033829
26 | Q158 | J.H.S. 158 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/7/2024 | DOES | 11/18/2024 | DOES | 65832 |  | DSF0001084813
26 | Q159 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/27/2022 | 11/10/2022 | 1/13/2023 | 145740 | 285671 | 275584 | DSF0001023304, DSF0001023305, DSF0001023306, DSF0001083852
26 | Q159 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/18/2023 | 6/20/2023 | 5/5/2023 | 728699 | 701681 | 627860 | DSF0001023304, DSF0001023305, DSF0001023306, DSF0001083852
26 | Q159 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 7/10/2023 | 10/6/2025 |  | 16395751 | 15022619 | 10392849 | DSF0001023304, DSF0001023305, DSF0001023306, DSF0001083852
26 | Q159 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 7/10/2023 | 10/6/2025 |  | 1020180 | 673487 | 548845 | DSF0001023304, DSF0001023305, DSF0001023306, DSF0001083852
26 | Q159 | P.S. 159 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225335 | 0 | DSF0001035928
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 5/15/2024 | 10/1/2024 | 9/17/2024 | 32273 | 67081 | 36518 | DSF0001101909
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | In-Progress | 9/24/2024 | 2/28/2025 |  | 150606 | 150606 | 12742 | DSF0001101909
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 2388188 | 2388188 | 67145 | DSF0001101909
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 236667 | 236667 | 31918 | DSF0001101909
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/1/2023 | 1/26/2024 | 12/20/2023 | 14541 | 64075 | 51417 | DSF0001008849, DSF0001008854
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Design | Complete | 1/23/2024 | 5/23/2024 | 5/10/2024 | 71092 | 169702 | 148400 | DSF0001008849, DSF0001008854
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 1460127 | 1460127 | 22020 | DSF0001008849, DSF0001008854
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 113877 | 113877 | 62903 | DSF0001008849, DSF0001008854
26 | Q162 | P.S. 162 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR ACOUSTICAL CEILING PLASTER IN AUDITORIUM HALLWAY | Construction | In-Progress | 1/3/2024 | IEH |  | IEH | 0 | 0 | SCA0000072609
26 | Q162 | P.S. 162 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 158000 | 157407 | DSF0001086450
26 | Q162 | P.S. 162 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113055
26 | Q162 | P.S. 162 - QUEENS | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/13/2018 | DOER |  | DOER | 89107 | 0 | DSF0000867284
26 | Q162 | P.S. 162 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113054
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/11/2019 | 10/25/2019 | 10/25/2019 | 151880 | 222197 | 222197 | DSF0000903136, DSF0000903137, DSF0000903138, DSF0000960585
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/13/2019 | 6/15/2020 | 4/14/2020 | 759401 | 600433 | 587958 | DSF0000903136, DSF0000903137, DSF0000903138, DSF0000960585
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 8/16/2021 | 8/15/2023 |  | 17086500 | 17815017 | 16159094 | DSF0000903136, DSF0000903137, DSF0000903138, DSF0000960585
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 8/16/2021 | 8/15/2023 |  | 1063161 | 950425 | 928758 | DSF0000903136, DSF0000903137, DSF0000903138, DSF0000960585
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/16/2022 | 9/14/2022 | 6/15/2022 | 5258 | 4682 | 4682 | DSF0001034659
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 23661 | 18727 | 18727 | DSF0001034659
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 6/12/2023 | 4/6/2024 | 4/6/2024 | 304964 | 279476 | 239861 | DSF0001034659
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 6/12/2023 | 4/6/2024 | 4/6/2024 | 176647 | 166991 | 112800 | DSF0001034659
26 | Q172 | J.H.S. 172 - QUEENS | SCA IEH | PO18-PLEASE ABATE APPROXIMATELY 12 LINEAR FEET OF PIPE ACM UNDER EXIT A, STAIRWELL 1 IN BOILER ROOM. | Construction | Complete | 3/28/2024 | IEH | 8/24/2024 | IEH | 0 | 0 | SCA0000072881
26 | Q172 | J.H.S. 172 - QUEENS | SCA Furniture & Equipment | RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 100000 | 100000 | 0 | DSF0001083945
26 | Q172 | J.H.S. 172 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001035940
26 | Q172 | J.H.S. 172 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001113061
26 | Q172 | J.H.S. 172 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/2/2016 | DOES |  | DOES | 56232 | 0 | DSF0000813679
26 | Q172 | J.H.S. 172 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/18/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084814
26 | Q172 | J.H.S. 172 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/2/2024 | DOES |  | DOES | 741164 | 0 | DSF0001085752
26 | Q173 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/16/2021 | 12/15/2021 | 11/4/2021 | 63240 | 152321 | 152321 | DSF0000997675, DSF0001023540, DSF0001023542
26 | Q173 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/18/2021 | 6/30/2022 | 4/18/2022 | 316200 | 308953 | 308953 | DSF0000997675, DSF0001023540, DSF0001023542
26 | Q173 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 7/15/2022 | 4/4/2024 |  | 7114500 | 6481598 | 5289561 | DSF0000997675, DSF0001023540, DSF0001023542
26 | Q173 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/15/2022 | 4/4/2024 |  | 443909 | 376085 | 369188 | DSF0000997675, DSF0001023540, DSF0001023542
26 | Q173 | P.S. 173 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/3/2024 | DIIR | 7/12/2024 | DIIR | 50000 | 49619 | DSF0001086456
26 | Q173 | P.S. 173 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0 | DSF0001113063
26 | Q173 | P.S. 173 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/1/2022 | DOER |  | DOER | 96296 | 0 | DSF0001008076
26 | Q173 | P.S. 173 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 197000 | 0 | DSF0001074329
26 | Q173 | P.S. 173 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001113062
26 | Q173 | P.S. 173 - QUEENS | DOE - Skilled Trades | BROKEN WATER MAIN | Construction | In-Progress | 3/22/2019 | DOES |  | DOES | 99248 | 0 | DSF0000912546
26 | Q173 | P.S. 173 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832 | 29103 | DSF0001084361
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 10/15/2015 | 3/21/2016 | 12/31/2015 | 122396 | 132963 | 132962 | DSF0000798293, DSF0000790486
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/6/2016 | 6/7/2016 | 6/24/2016 | 480196 | 554257 | 549191 | DSF0000798293, DSF0000790486
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 10/17/2016 | 4/9/2018 |  | 8161174 | 8116966 | 7876023 | DSF0000798293, DSF0000790486
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 10/17/2016 | 4/9/2018 |  | 693216 | 812392 | 807326 | DSF0000798293, DSF0000790486
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA WASTE SYSTEMS / IDA INTERIOR SPACES / IDA FIRE ALARM SYSTEM / IDA MECHANICAL PIPING | Scope | Complete | 1/20/2022 | 5/23/2022 | 8/5/2022 | 102642 | 118328 | 21020 | SCA0000070747, DSF0001129908, DSF0001113833, DSF0001113834, DSF0001129907
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA WASTE SYSTEMS / IDA INTERIOR SPACES / IDA FIRE ALARM SYSTEM / IDA MECHANICAL PIPING | Design | In-Progress | 11/20/2024 | 5/27/2025 |  | 466201 | 466201 | 15548 | SCA0000070747, DSF0001129908, DSF0001113833, DSF0001113834, DSF0001129907
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA WASTE SYSTEMS / IDA INTERIOR SPACES / IDA FIRE ALARM SYSTEM / IDA MECHANICAL PIPING | Construction | PNS | PNS | PNS | PNS | 8130247 | 8130247 | 10199 | SCA0000070747, DSF0001129908, DSF0001113833, DSF0001113834, DSF0001129907
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA WASTE SYSTEMS / IDA INTERIOR SPACES / IDA FIRE ALARM SYSTEM / IDA MECHANICAL PIPING | CM,F&E | PNS | PNS | PNS | PNS | 989952 | 989952 | 5606 | SCA0000070747, DSF0001129908, DSF0001113833, DSF0001113834, DSF0001129907
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 9/20/2017 | 4/10/2019 | 3/26/2019 | 251255 | 197918 | 197715 | DSF0000867084, DSF0000880356, DSF0000880357, DSF0000880358, DSF0000880359, DSF0000912509
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 3/26/2019 | 8/23/2019 | 5/17/2019 | 994516 | 568294 | 551666 | DSF0000867084, DSF0000880356, DSF0000880357, DSF0000880358, DSF0000880359, DSF0000912509
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 10/21/2019 | 8/10/2021 |  | 17704514 | 17384903 | 17290328 | DSF0000867084, DSF0000880356, DSF0000880357, DSF0000880358, DSF0000880359, DSF0000912509
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 10/21/2019 | 8/10/2021 |  | 1309066 | 533388 | 528659 | DSF0000867084, DSF0000880356, DSF0000880357, DSF0000880358, DSF0000880359, DSF0000912509
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/26/2022 | 9/26/2022 | 6/15/2022 | 3814 | 5070 | 5070 | DSF0001034568
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 17165 | 20281 | 20281 | DSF0001034568
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 11/27/2023 | 9/21/2024 | 11/20/2024 | 221235 | 203652 | 159457 | DSF0001034568
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 11/27/2023 | 9/21/2024 | 11/20/2024 | 106219 | 96831 | 91173 | DSF0001034568
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113650
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113650
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113650
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113650
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 1/30/2023 | 5/31/2023 | 7/1/2024 | 0 | 26026 | 26026 | DSF0001035945
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | In-Progress | 7/8/2024 | 11/21/2024 |  | 88366 | 72669 | 43381 | DSF0001035945
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 1296041 | 1296041 | 0 | DSF0001035945
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 88366 | 88366 | 46651 | DSF0001035945
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | In-Progress | 6/13/2024 | 9/16/2024 |  | 0 | 0 | 0 | DSF0001035946
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035946
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035946
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035946
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/15/2024 | 5/15/2024 | 10/30/2024 | 0 | 16322 | 1766 | DSF0001086899
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 11/12/2024 | 4/1/2025 |  | 45000 | 28678 | 7062 | DSF0001086899
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001086899
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 5178 | DSF0001086899
26 | Q177 | Q177 SPED - QUEENS | SCA Emergency Response | EMR PROTECTIVE MEASURES - IDA | Construction | In-Progress | 9/3/2021 | EMER |  | EMER | 4382595 | 4085230 | SCA0000070463
26 | Q177 | Q177 SPED - QUEENS | DIIT - RESOA | FY09 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500 | 0 | DSF0000622617
26 | Q177 | Q177 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001035238
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/3/2024 | DOER |  | DOER | 532370 | 0 | DSF0000890899
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112250
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0 | DSF0001113069
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113070
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0 | DSF0001113071
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001113814
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113815
26 | Q177 | Q177 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084993
26 | Q178 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/29/2022 | 10/28/2022 | 9/28/2022 | 3560 | 4949 | 4949 | DSF0001034567
26 | Q178 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/28/2022 | 3/29/2023 | 3/29/2023 | 16020 | 19795 | 19795 | DSF0001034567
26 | Q178 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 11/27/2023 | 9/21/2024 | 11/20/2024 | 206480 | 186223 | 137732 | DSF0001034567
26 | Q178 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 11/27/2023 | 9/21/2024 | 11/20/2024 | 84906 | 74312 | 52369 | DSF0001034567
26 | Q178 | P.S. 178 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033841
26 | Q178 | P.S. 178 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113072
26 | Q178 | P.S. 178 - QUEENS | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0000913420
26 | Q178 | P.S. 178 - QUEENS | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035947
26 | Q178 | P.S. 178 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/11/2022 | DOES |  | DOES | 105621 | 0 | DSF0001009185
26 | Q178 | P.S. 178 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/31/2024 | DOES | 8/12/2024 | DOES | 65832 |  | DSF0001084676
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | ROOFS | Scope | Complete | 6/18/2024 | 11/4/2024 | 10/4/2024 | 51253 | 68400 | 52900 | DSF0001074430
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | ROOFS | Design | In-Progress | 10/16/2024 | 3/21/2025 |  | 256263 | 256263 | 211589 | DSF0001074430
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 5765914 | 5765914 | 24765 | DSF0001074430
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 358768 | 358768 | 12450 | DSF0001074430
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/14/2022 | 4/17/2023 | 1/3/2023 | 4078 | 4895 | 4895 | DSF0001034566
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/3/2023 | 6/29/2023 | 3/29/2023 | 18349 | 19580 | 19580 | DSF0001034566
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | Complete | 11/27/2023 | 9/21/2024 | 11/20/2024 | 236501 | 214229 | 159876 | DSF0001034566
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | Complete | 11/27/2023 | 9/21/2024 | 11/20/2024 | 106867 | 98005 | 76091 | DSF0001034566
26 | Q179 | Q004 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/7/2024 | DIIR |  | DIIR | 63000 | 0 | DSF0001086460
26 | Q179 | Q004 SPED - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 281961 | 0 | DSF0001111925
26 | Q179 | Q004 SPED - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112323
26 | Q179 | Q004 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113073
26 | Q179 | Q004 SPED - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113724
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | Scope | Complete | 1/14/2020 | 5/29/2020 | 5/3/2021 | 123354 | 174463 | 174449 | DSF0000948958, DSF0000997895, DSF0000997896, DSF0000997902, DSF0001008921
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | Design | Complete | 5/24/2021 | 10/25/2021 | 2/2/2022 | 615417 | 576544 | 548540 | DSF0000948958, DSF0000997895, DSF0000997896, DSF0000997902, DSF0001008921
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | Construction | In-Progress | 9/6/2022 | 9/4/2024 |  | 13729741 | 13032458 | 11971002 | DSF0000948958, DSF0000997895, DSF0000997896, DSF0000997902, DSF0001008921
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | CM,F&E | In-Progress | 9/6/2022 | 9/4/2024 |  | 873635 | 757985 | 737883 | DSF0000948958, DSF0000997895, DSF0000997896, DSF0000997902, DSF0001008921
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Scope | In-Progress | 11/15/2024 | 4/18/2025 |  | 241939 | 241939 | 117493 | DSF0001034486, DSF0001036331
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Design | PNS | PNS | PNS | PNS | 1129052 | 1129052 | 486442 | DSF0001034486, DSF0001036331
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Construction | PNS | PNS | PNS | PNS | 17903539 | 17903539 | 72889 | DSF0001034486, DSF0001036331
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 1774225 | 1774225 | 129733 | DSF0001034486, DSF0001036331
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/17/2023 | 7/18/2023 | 3/28/2023 | 4640 | 3246 | 3246 | DSF0001034593
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/28/2023 | 9/21/2023 | 5/3/2023 | 20880 | 12983 | 12983 | DSF0001034593
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/30/2023 | 8/24/2024 |  | 269120 | 240463 | 135144 | DSF0001034593
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/30/2023 | 8/24/2024 |  | 209601 | 193468 | 152897 | DSF0001034593
26 | Q186 | Q224 SPED - QUEENS | Fast Track Projects | CTF ROOM CONVERSION / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 11/5/2021 | FTK |  | FTK | 1707875 | 1571192 | DSF0000960712, DSF0000960906
26 | Q186 | P.S. 186 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 110000 | 107283 | DSF0001033848
26 | Q186 | Q224 SPED - QUEENS | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001008045
26 | Q186 | P.S. 186 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/5/2024 | DOER |  | DOER | 47308 | 0 | DSF0001035951
26 | Q186 | Q224 SPED - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001035952
26 | Q186 | P.S. 186 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/30/2022 | DOES |  | DOES | 118707 | 0 | DSF0001034255
26 | Q186 | P.S. 186 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/12/2024 | DOES | 8/21/2024 | DOES | 65832 |  | DSF0001084679
26 | Q188 | P.S. 188 - QUEENS | SCA IEH | PO18-TEST/ABATE AND REPLACE 9 X 9 FLOOR TILES IN RMS 107,116,204,114, TILES ARE CRACKING AND LIFTING | Construction | Complete | 7/26/2024 | IEH | 10/9/2024 | IEH | 0 | 0 | SCA0000073185
26 | Q188 | P.S. 188 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113076
26 | Q188 | P.S. 188 - QUEENS | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/29/2023 | DOER |  | DOER | 816004 | 0 | DSF0001035953
26 | Q188 | P.S. 188 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 42948 | 0 | DSF0001111894
26 | Q191 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/10/2023 | 7/11/2023 | 3/29/2023 | 4800 | 1952 | 1952 | DSF0001034570
26 | Q191 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/29/2023 | 9/22/2023 | 5/3/2023 | 21600 | 7806 | 7806 | DSF0001034570
26 | Q191 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/30/2023 | 8/24/2024 |  | 278400 | 251858 | 202321 | DSF0001034570
26 | Q191 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/30/2023 | 8/24/2024 |  | 76455 | 57078 | 50344 | DSF0001034570
26 | Q191 | P.S. 191 - QUEENS | DIIT - Project Connect | DATA/VOICE & WIRELESS NETWORK CABLE WIRING, NETWORK SERVER EQUIPMENT, DATA/VOICE & WIRELESS NETWORK | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 261220 | 0 | DSF0000800170
26 | Q191 | Q993 SPED - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000914040
26 | Q191 | Q993 SPED - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008057
26 | Q191 | Q993 SPED - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001033955
26 | Q191 | Q993 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 113000 | 0 | DSF0001086467
26 | Q191 | P.S. 191 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113077
26 | Q191 | P.S. 191 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 210000 | 0 | DSF0001035960
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | Scope | Complete | 12/22/2017 | 5/10/2018 | 3/2/2018 | 58200 | 78502 | 78502 | DSF0000880739
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | Design | Complete | 3/14/2018 | 8/13/2018 | 5/14/2018 | 232800 | 324298 | 282592 | DSF0000880739
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | Construction | In-Progress | 7/23/2018 | 10/15/2019 |  | 4365000 | 5100702 | 3766392 | DSF0000880739
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | CM,F&E | In-Progress | 7/23/2018 | 10/15/2019 |  | 271600 | 713470 | 669497 | DSF0000880739
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/27/2019 | 11/29/2019 | 8/23/2019 | 65750 | 61857 | 61857 | DSF0000912539, DSF0000897780
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/10/2019 | 2/13/2020 | 12/20/2019 | 328750 | 314324 | 292424 | DSF0000912539, DSF0000897780
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 10/10/2022 | 10/8/2024 |  | 7396875 | 6712503 | 3936708 | DSF0000912539, DSF0000897780
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 10/10/2022 | 10/8/2024 |  | 461282 | 445050 | 410437 | DSF0000912539, DSF0000897780
26 | Q203 | P.S. 203 - QUEENS | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/3/2020 | DOER |  | DOER | 263679 | 0 | DSF0000913426
26 | Q203 | P.S. 203 - QUEENS | DOE - RESOA | FY21 RESO A EXTERIOR DOORS | Construction | Complete | 12/23/2022 | DOER | 5/4/2024 | DOER | 170861 | 146814 | DSF0001008860
26 | Q203 | P.S. 203 - QUEENS | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001113089
26 | Q203 | P.S. 203 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 6/28/2022 | DOES | 11/15/2022 | DOES | 155986 | 5368 | DSF0001008714
26 | Q205 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2023 | 6/29/2023 | 3/3/2023 | 3700 | 7106 | 7106 | DSF0001034588
26 | Q205 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/3/2023 | 8/28/2023 | 5/3/2023 | 16650 | 28425 | 28425 | DSF0001034588
26 | Q205 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/2/2023 | 7/27/2024 |  | 214600 | 197168 | 109725 | DSF0001034588
26 | Q205 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/2/2023 | 7/27/2024 |  | 114173 | 105224 | 84775 | DSF0001034588
26 | Q205 | P.S. 205 - QUEENS | SCA IEH | PO18-ABATEMENT OF TAR RADIATOR COVERS AND WHITE AIRCELL PIPE INSULATION IN ROOM 218 | Construction | In-Progress | 2/12/2024 | IEH |  | IEH | 0 | 0 | SCA0000072726
26 | Q205 | P.S. 205 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS 1ST FLOOR ROOM #107JA AND 107JB 1ST HALLWAY OUTSIDE ROOM | Construction | Complete | 2/27/2024 | IEH | 7/13/2024 | IEH | 0 | 0 | SCA0000072765
26 | Q205 | P.S. 205 - QUEENS | SCA IEH | PO18-77/26Q205/TEST ABATE IF POSITIVE PIPE INSULATION HOT AND COLD RISER VALVES AND LINES IN BASEMEN | Construction | Complete | 9/26/2024 | IEH | 10/19/2024 | IEH | 0 | 0 | SCA0000073441
26 | Q205 | P.S. 205 - QUEENS | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 372000 | 372000 | 0 | DSF0001035339
26 | Q205 | Q224 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 6/5/2024 | DIIR |  | DIIR | 112000 | 0 | DSF0001086472
26 | Q205 | P.S. 205 - QUEENS | DOE - RESOA | FY19 RESO A MULTIMEDIA CENTER | Construction | Complete | 11/5/2021 | DOER | 11/1/2023 | DOER | 103136 | 98317 | DSF0000890353
26 | Q205 | P.S. 205 - QUEENS | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001033858
26 | Q205 | Q224 SPED - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 105991 | 0 | DSF0001033872
26 | Q208 | P.S./I.S. 208 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/11/2024 | 9/11/2024 | 10/18/2024 | 22940 | 82046 | 64046 | DSF0001112242
26 | Q208 | P.S./I.S. 208 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | In-Progress | 10/21/2024 | 3/11/2025 |  | 107054 | 137918 | 34515 | DSF0001112242
26 | Q208 | P.S./I.S. 208 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 1697567 | 1697567 | 94346 | DSF0001112242
26 | Q208 | P.S./I.S. 208 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 168227 | 168227 | 5542 | DSF0001112242
26 | Q208 | P.S./I.S. 208 - QUEENS | SCA CIP | PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Scope | In-Progress | 12/4/2024 | 3/7/2025 |  | 647 | 647 | 322 | DSF0001113871
26 | Q208 | P.S./I.S. 208 - QUEENS | SCA CIP | PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Design | PNS | PNS | PNS | PNS | 2589 | 2589 | 1287 | DSF0001113871
26 | Q208 | P.S./I.S. 208 - QUEENS | SCA CIP | PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 37216 | 37216 | 0 | DSF0001113871
26 | Q208 | P.S./I.S. 208 - QUEENS | SCA CIP | PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 9547 | 9547 | 0 | DSF0001113871
26 | Q208 | Q993 SPED - QUEENS | DIIT - RESOA | RESO A- FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000960996
26 | Q208 | P.S./I.S. 208 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001035980
26 | Q208 | P.S./I.S. 208 - QUEENS | DOE - RESOA | FY17 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 185000 | 0 | DSF0000844799
26 | Q208 | P.S./I.S. 208 - QUEENS | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 144686 | 0 | DSF0001033293
26 | Q208 | Q993 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 350000 | 0 | DSF0001086476
26 | Q208 | P.S./I.S. 208 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113093
26 | Q208 | P.S./I.S. 208 - QUEENS | DOE - Skilled Trades | GAS LEAK | Construction | In-Progress | 5/15/2019 | DOES |  | DOES | 18145 | 0 | DSF0000912507
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | Complete | 6/3/2019 | 10/17/2019 | 12/23/2019 | 219544 | 234050 | 234050 | DSF0000912408, DSF0000998298, DSF0001034159, DSF0000998299, DSF0001083773, DSF0001083772
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | Complete | 10/6/2021 | 4/13/2022 | 1/5/2023 | 1080292 | 961491 | 836277 | DSF0000912408, DSF0000998298, DSF0001034159, DSF0000998299, DSF0001083773, DSF0001083772
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | Construction | In-Progress | 4/17/2023 | 10/2/2025 |  | 22799480 | 20492955 | 12898625 | DSF0000912408, DSF0000998298, DSF0001034159, DSF0000998299, DSF0001083773, DSF0001083772
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | CM,F&E | In-Progress | 4/17/2023 | 10/2/2025 |  | 1667470 | 398354 | 382606 | DSF0000912408, DSF0000998298, DSF0001034159, DSF0000998299, DSF0001083773, DSF0001083772
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 10/14/2022 | 3/6/2023 | 2/22/2023 | 156066 | 159181 | 155284 | DSF0000998304, DSF0001024213, DSF0001024214
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 4/4/2023 | 9/5/2023 | 9/7/2023 | 780330 | 337599 | 337599 | DSF0000998304, DSF0001024213, DSF0001024214
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS | Construction | PNS | PNS | PNS | PNS | 17557429 | 17557429 | 99882 | DSF0000998304, DSF0001024213, DSF0001024214
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1092463 | 1092463 | 83985 | DSF0000998304, DSF0001024213, DSF0001024214
26 | Q213 | P.S. 213 - QUEENS | DOE - RESOA | FY13 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 42261 | 0 | DSF0000754645
26 | Q213 | P.S. 213 - QUEENS | DOE - RESOA | FY17 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 422356 | 0 | DSF0000844798
26 | Q213 | P.S. 213 - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/23/2024 | DOER |  | DOER | 96963 | 0 | DSF0001033866
26 | Q213 | P.S. 213 - QUEENS | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113099
26 | Q216 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | Scope | Complete | 5/16/2022 | 2/28/2023 | 2/28/2023 | 1281380 | 794698 | 758284 | DSF0000914322, DSF0000914322, DSF0000914322
26 | Q216 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | Design | Complete | 2/28/2023 | 6/12/2023 | 5/12/2023 | 5766210 | 2416522 | 1507932 | DSF0000914322, DSF0000914322, DSF0000914322
26 | Q216 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | Construction | In-Progress | 9/25/2023 | 9/3/2026 |  | 72718315 | 65410012 | 8563410 | DSF0000914322, DSF0000914322, DSF0000914322
26 | Q216 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | CM,Art,F&E | In-Progress | 9/25/2023 | 9/3/2026 |  | 10251040 | 4420784 | 916457 | DSF0000914322, DSF0000914322, DSF0000914322
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 12/16/2014 | 5/19/2015 | 4/10/2015 | 90011 | 97593 | 97593 | DSF0000798301, DSF0000791100
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 4/17/2015 | 9/17/2015 | 9/22/2015 | 360045 | 307942 | 291845 | DSF0000798301, DSF0000791100
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 4/17/2017 | 7/17/2018 |  | 6750856 | 7062870 | 6716597 | DSF0000798301, DSF0000791100
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 4/17/2017 | 7/17/2018 |  | 420054 | 1068611 | 1061412 | DSF0000798301, DSF0000791100
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 10/29/2018 | 3/19/2019 | 3/21/2019 | 257999 | 136796 | 136796 | DSF0000880910, DSF0000880911, DSF0000880912, DSF0000903778
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 3/21/2019 | 8/9/2019 | 5/17/2019 | 1032001 | 656358 | 651217 | DSF0000880910, DSF0000880911, DSF0000880912, DSF0000903778
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 7/22/2019 | 4/11/2021 |  | 19350000 | 18488617 | 18258753 | DSF0000880910, DSF0000880911, DSF0000880912, DSF0000903778
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 7/22/2019 | 4/11/2021 |  | 1204000 | 483125 | 477437 | DSF0000880910, DSF0000880911, DSF0000880912, DSF0000903778
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA WASTE SYSTEMS / IDA MECHANICAL PIPING / IDA INTERIOR SPACES | Scope | Complete | 6/16/2022 | 11/1/2022 | 9/18/2024 | 294820 | 263824 | 263824 | SCA0000070748, DSF0001113751, DSF0001102844, DSF0001102843, DSF0001113750
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA WASTE SYSTEMS / IDA MECHANICAL PIPING / IDA INTERIOR SPACES | Design | In-Progress | 9/18/2024 | 2/24/2025 |  | 1411719 | 1411719 | 16209 | SCA0000070748, DSF0001113751, DSF0001102844, DSF0001102843, DSF0001113750
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA WASTE SYSTEMS / IDA MECHANICAL PIPING / IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 26577922 | 26577922 | 460 | SCA0000070748, DSF0001113751, DSF0001102844, DSF0001102843, DSF0001113750
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA WASTE SYSTEMS / IDA MECHANICAL PIPING / IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 2194790 | 2194790 | 4755 | SCA0000070748, DSF0001113751, DSF0001102844, DSF0001102843, DSF0001113750
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | Scope | Complete | 6/6/2022 | 11/29/2022 | 11/29/2022 | 28900 | 32947 | 32947 | DSF0001024263, DSF0000914322
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | Design | Complete | 11/29/2022 | 3/16/2023 | 3/21/2023 | 144499 | 124706 | 117421 | DSF0001024263, DSF0000914322
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | Construction | In-Progress | 6/26/2023 | 6/24/2024 |  | 3251222 | 3076361 | 2759085 | DSF0001024263, DSF0000914322
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | CM,F&E | In-Progress | 6/26/2023 | 6/24/2024 |  | 202299 | 352789 | 335338 | DSF0001024263, DSF0000914322
26 | Q216 | J.H.S. 216 - QUEENS | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/21/2022 | DOER |  | DOER | 283306 | 0 | DSF0000913432
26 | Q216 | J.H.S. 216 - QUEENS | DOE - RESOA | FY21 RESO A LOCKER ROOM UPGRADE | Construction | Complete | 1/6/2022 | DOER | 1/28/2022 | DOER | 179311 | 176899 | DSF0001008080
26 | Q216 | J.H.S. 216 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 1/14/2022 | DOES | 6/20/2022 | DOES | 192136 | 97770 | DSF0001008715
26 | Q216 | J.H.S. 216 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/9/2024 | DOES | 9/16/2024 | DOES | 65832 | 9253 | DSF0001084822
26 | Q221 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 8/31/2022 | 3/1/2023 | 12/9/2022 | 96409 | 192991 | 192740 | DSF0001024344, DSF0001024345, DSF0001024346, DSF0001024347
26 | Q221 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 12/9/2022 | 6/7/2023 | 4/21/2023 | 478159 | 481210 | 481136 | DSF0001024344, DSF0001024345, DSF0001024346, DSF0001024347
26 | Q221 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 7/17/2023 | 10/13/2025 |  | 10422440 | 9676514 | 8961538 | DSF0001024344, DSF0001024345, DSF0001024346, DSF0001024347
26 | Q221 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/17/2023 | 10/13/2025 |  | 705506 | 665807 | 542707 | DSF0001024344, DSF0001024345, DSF0001024346, DSF0001024347
26 | Q221 | P.S. 221 - QUEENS | SCA IEH | PO18-ROOM 1005 - ABATE PIPE INSULATION PAINTED IN RED - 10 LF ROOM 3136C - ABATE & REPLACE FLOOR TIL | Construction | In-Progress | 7/25/2024 | IEH |  | IEH | 0 | 0 | SCA0000073177
26 | Q221 | P.S. 221 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113104
26 | Q221 | P.S. 221 - QUEENS | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/31/2018 | DOER |  | DOER | 111500 | 0 | DSF0000822864
26 | Q266 | P.S./I.S. 266 - QUEENS | Fast Track Projects | LSP HOT WATER HEATER | Construction | In-Progress | 1/15/2020 | FTK |  | FTK | 254155 | 217157 | DSF0000912581
26 | Q266 | P.S./I.S. 266 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/3/2024 | DIIR | 7/12/2024 | DIIR | 113000 | 109513 | DSF0001086499
26 | Q266 | P.S./I.S. 266 - QUEENS | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 12/26/2023 | DOER |  | DOER | 135246 | 0 | DSF0001033306
26 | Q332 | P.S. 376 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 55000 | 0 | DSF0001113133
26 | Q361 | THE CIVIC SCHOOL OF BAYSIDE HILLS - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033918
26 | Q361 | THE CIVIC SCHOOL OF BAYSIDE HILLS - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001113139
26 | Q361 | THE CIVIC SCHOOL OF BAYSIDE HILLS - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001008051
26 | Q361 | THE CIVIC SCHOOL OF BAYSIDE HILLS - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001036034
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY19 RESO A ROOM CONVERSION | Scope | Complete | 8/13/2019 | 12/10/2019 | 3/10/2021 | 0 | 15779 | 15779 | DSF0000912605
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY19 RESO A ROOM CONVERSION | Design | Complete | 4/21/2021 | 9/10/2021 | 3/9/2022 | 74876 | 89536 | 87842 | DSF0000912605
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY19 RESO A ROOM CONVERSION | Construction | In-Progress | 2/12/2024 | 12/7/2024 |  | 1098186 | 1028984 | 474453 | DSF0000912605
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY19 RESO A ROOM CONVERSION | CM,F&E | In-Progress | 2/12/2024 | 12/7/2024 |  | 91207 | 119485 | 52884 | DSF0000912605
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A GREENHOUSE | Scope | Complete | 2/5/2020 | 5/20/2020 | 7/14/2021 | 0 | 129227 | 122476 | DSF0000913449
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A GREENHOUSE | Design | In-Progress | 9/22/2022 | 3/30/2023 |  | 279059 | 177870 | 119433 | DSF0000913449
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A GREENHOUSE | Construction | PNS | PNS | PNS | PNS | 4092872 | 4092872 | 35334 | DSF0000913449
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A GREENHOUSE | CM,F&E | PNS | PNS | PNS | PNS | 279059 | 279059 | 101341 | DSF0000913449
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GREENHOUSE | Scope | In-Progress | 3/1/2024 | 5/31/2024 |  | 0 | 0 | 0 | DSF0000913448
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GREENHOUSE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913448
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GREENHOUSE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913448
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GREENHOUSE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 1455 | 1455 | DSF0000913448
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | In-Progress | 11/21/2024 | 3/26/2025 |  | 0 | 2453 | 2453 | DSF0001113149
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 24000 | 21547 | 9810 | DSF0001113149
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 352000 | 352000 | 0 | DSF0001113149
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 24000 | 24000 | 0 | DSF0001113149
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113664
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113664
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113664
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113664
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA IEH | PO18-DETERMINE IF SOFT CONCRETE FILLER FLOORING MATERIAL WILL BE DISTRUBED DURING FLOOR REPAIR IN RO | Construction | In-Progress | 1/3/2023 | IEH |  | IEH | 0 | 0 | SCA0000071657
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA IEH | PO18-77/26Q405/ TEST ABATE IF POSITIVE PIPE INSULATI0N ROOM 111 REMOVE ALL INSULATIN BEHIND METAL CO | Construction | In-Progress | 1/11/2024 | IEH |  | IEH | 0 | 0 | SCA0000072638
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0001007965
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/3/2024 | DOER |  | DOER | 188309 | 0 | DSF0001112037
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 1350000 | 0 | DSF0001113148
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | WATER MAIN REPAIRS | Construction | In-Progress | 1/11/2021 | DOES |  | DOES | 518370 | 0 | DSF0001008634
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/21/2023 | DOES |  | DOES | 362799 | 0 | DSF0001034432
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 9/25/2023 | DOES |  | DOES | 744456 | 0 | DSF0001083754
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/19/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084997
26 | Q406 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - RESOA | RESO A ATHLETIC FIELDS | Construction | In-Progress | 8/10/2024 | DOER |  | DOER | 50000 | 0 | DSF0001112402
26 | Q406 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 2150000 | 0 | DSF0001113150
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | RPZ VALVES | Scope | Complete | 10/23/2018 | 4/23/2019 | 9/12/2019 | 10924 | 43370 | 43370 | DSF0000891081
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | RPZ VALVES | Design | Complete | 9/6/2022 | 3/7/2023 | 3/2/2023 | 54621 | 143369 | 143369 | DSF0000891081
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | RPZ VALVES | Construction | PNS | PNS | PNS | PNS | 1228964 | 1228964 | 25205 | DSF0000891081
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | RPZ VALVES | CM,F&E | PNS | PNS | PNS | PNS | 76469 | 76469 | 43488 | DSF0000891081
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | Scope | Complete | 3/4/2021 | 7/2/2021 | 7/22/2021 | 24450 | 20729 | 20729 | DSF0000960657
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | Design | Complete | 7/28/2021 | 12/30/2021 | 12/29/2021 | 122250 | 79175 | 79175 | DSF0000960657
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | Construction | Complete | 4/10/2023 | 4/8/2024 | 8/30/2024 | 2750625 | 2681524 | 2354892 | DSF0000960657
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | CM,F&E | Complete | 4/10/2023 | 4/8/2024 | 8/30/2024 | 171150 | 141454 | 140696 | DSF0000960657
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 8/5/2020 | 1/8/2021 | 12/23/2020 | 116640 | 159179 | 159179 | DSF0000948984, DSF0000960978
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/28/2020 | 7/30/2021 | 7/1/2021 | 583200 | 702829 | 662054 | DSF0000948984, DSF0000960978
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 1/3/2022 | 1/2/2024 |  | 13122000 | 13027412 | 11687565 | DSF0000948984, DSF0000960978
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 1/3/2022 | 1/2/2024 |  | 816480 | 585747 | 545742 | DSF0000948984, DSF0000960978
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 3/5/2020 | 7/6/2020 | 3/6/2020 | 13420 | 7170 | 9542 | DSF0000868292, DSF0000960830
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 3/6/2020 | 8/5/2020 | 5/12/2020 | 49540 | 28880 | 38169 | DSF0000868292, DSF0000960830
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | Complete | 1/11/2021 | 10/7/2021 | 10/7/2021 | 528810 | 528810 | 1022299 | DSF0000868292, DSF0000960830
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | Complete | 1/11/2021 | 10/7/2021 | 10/7/2021 | 121480 | 100347 | 102898 | DSF0000868292, DSF0000960830
26 | Q415 | Q993 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 112000 | 0 | DSF0001086525
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | Complete | 3/22/2021 | DOER | 12/22/2021 | DOER | 41965 | 4517 | DSF0000913454
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 9/8/2023 | DOER |  | DOER | 47114 | 0 | DSF0001008038
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 61000 | 0 | DSF0001036043
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 56000 | 0 | DSF0001086526
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 6/30/2022 | DOES | 3/8/2023 | DOES | 141386 | 7245 | DSF0001034259
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 1/27/2023 | DOES |  | DOES | 2056793 | 0 | SCA0000070998
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/11/2024 | DOES | 9/19/2024 | DOES | 65832 | 9200 | DSF0001084999
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/6/2024 | DOES |  | DOES | 686311 | 0 | DSF0001085758
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / NON-IDA REINFORCE SUPPORT ELEMENTS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES | Scope | Complete | 9/29/2022 | 2/17/2023 | 2/21/2023 | 114924 | 183970 | 180693 | DSF0001085603, DSF0001083918, DSF0001076010, DSF0001083916
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / NON-IDA REINFORCE SUPPORT ELEMENTS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES | Design | Complete | 2/21/2023 | 7/24/2023 | 7/26/2023 | 568324 | 432709 | 394634 | DSF0001085603, DSF0001083918, DSF0001076010, DSF0001083916
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / NON-IDA REINFORCE SUPPORT ELEMENTS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 12243148 | 12243148 | 41670 | DSF0001085603, DSF0001083918, DSF0001076010, DSF0001083916
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / NON-IDA REINFORCE SUPPORT ELEMENTS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 851642 | 851642 | 34130 | DSF0001085603, DSF0001083918, DSF0001076010, DSF0001083916
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | Scope | Complete | 3/19/2018 | 5/24/2019 | 7/30/2019 | 30972 | 46993 | 46993 | DSF0000889026, DSF0000904175
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | Design | Complete | 9/12/2019 | 3/19/2020 | 6/10/2020 | 148068 | 207239 | 207049 | DSF0000889026, DSF0000904175
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | Construction | In-Progress | 7/6/2022 | 7/5/2023 |  | 2744023 | 2667888 | 2518782 | DSF0000889026, DSF0000904175
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | CM,F&E | In-Progress | 7/6/2022 | 7/5/2023 |  | 267746 | 501454 | 495113 | DSF0000889026, DSF0000904175
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 3/21/2022 | 4/4/2022 | 4/4/2022 | 11376 | 28137 | 28137 | DSF0000821799
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 4/5/2022 | 8/12/2022 | 4/12/2023 | 56882 | 66010 | 55315 | DSF0000821799
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 8/7/2023 | 11/3/2025 |  | 1279836 | 1144446 | 1023346 | DSF0000821799
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 8/7/2023 | 11/3/2025 |  | 79634 | 36653 | 36653 | DSF0000821799
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA IEH | PO18-ABATE & REPLACE FLOOR TILES IN ROOM 330 | Construction | In-Progress | 12/12/2024 | IEH |  | IEH | 0 | 0 | SCA0000073703
26 | Q430 | FRANCIS LEWIS HS - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 105000 | 0 | DSF0000889928
26 | Q430 | FRANCIS LEWIS HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/31/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085002
26 | Q431 | FRANCIS LEWIS HS - QUEENS | SCA CIP RESOA | FY20 RESO A ATHLETIC FIELD UPGRADE | Scope | Complete | 2/27/2020 | 6/26/2020 | 3/21/2022 | 0 | 167361 | 167361 | DSF0000913455
26 | Q431 | FRANCIS LEWIS HS - QUEENS | SCA CIP RESOA | FY20 RESO A ATHLETIC FIELD UPGRADE | Design | Complete | 3/21/2022 | 8/18/2022 | 4/12/2023 | 746531 | 524096 | 441771 | DSF0000913455
26 | Q431 | FRANCIS LEWIS HS - QUEENS | SCA CIP RESOA | FY20 RESO A ATHLETIC FIELD UPGRADE | Construction | In-Progress | 8/7/2023 | 11/3/2025 |  | 10949121 | 10641605 | 2196229 | DSF0000913455
26 | Q431 | FRANCIS LEWIS HS - QUEENS | SCA CIP RESOA | FY20 RESO A ATHLETIC FIELD UPGRADE | CM,F&E | In-Progress | 8/7/2023 | 11/3/2025 |  | 747121 | 401421 | 391085 | DSF0000913455
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 6/30/2022 | 11/16/2022 | 6/15/2023 | 107878 | 163002 | 163002 | DSF0001034985, DSF0001083856
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | In-Progress | 7/11/2023 | 1/16/2024 |  | 539391 | 539391 | 176620 | DSF0001034985, DSF0001083856
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 12136318 | 12136318 | 92105 | DSF0001034985, DSF0001083856
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 755148 | 755148 | 141813 | DSF0001034985, DSF0001083856
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/14/2023 | 6/28/2023 | 5/23/2023 | 0 | 16923 | 16923 | DSF0001036045
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 28994 | 12071 | 2740 | DSF0001036045
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 425249 | 957712 | 3939 | DSF0001036045
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 28994 | 65299 | 1252 | DSF0001036045
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 2/21/2023 | FTK |  | FTK | 430947 | 250888 | DSF0000961032
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0 | DSF0001008041
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/15/2023 | DOER |  | DOER | 94580 | 0 | DSF0001033906
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | Complete | 7/14/2023 | DOER | 10/22/2024 | DOER | 611001 |  | DSF0001033923
26 | Q435 | Q177 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 124128 | 3039 | DSF0001086535
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 56000 | 0 | DSF0001086536
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001113157
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 7/19/2023 | DOES | 12/20/2023 | DOES | 999430 | 2197 | DSF0000960860
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/11/2024 | DOES | 11/25/2024 | DOES | 65832 | 15500 | DSF0001085003
26 | Q461 | Q000 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/8/2024 | IEH | 8/20/2024 | IEH | 0 | 0 | SCA0000073266
26 | Q461 | Q000 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/30/2024 | DOES | 9/10/2024 | DOES | 65832 |  | DSF0001085525
26 | Q469 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/6/2023 | 2/8/2024 | 2/7/2024 | 5171 | 27237 | 27237 | DSF0000888760
26 | Q469 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2/7/2024 | 6/24/2024 | 4/18/2024 | 23271 | 108943 | 108943 | DSF0000888760
26 | Q469 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 299937 | 299937 | 22264 | DSF0000888760
26 | Q469 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 55592 | 55592 | 19776 | DSF0000888760
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Scope | Complete | 6/26/2023 | 12/22/2023 | 10/3/2023 | 148504 | 146764 | 134342 | DSF0001076533, DSF0001076534, DSF0001087220, DSF0001087219
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Design | Complete | 10/10/2023 | 6/10/2024 | 4/2/2024 | 735127 | 329714 | 329714 | DSF0001076533, DSF0001076534, DSF0001087220, DSF0001087219
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Construction | In-Progress | 9/23/2024 | 1/20/2027 |  | 15900755 | 14252146 | 36 | DSF0001076533, DSF0001076534, DSF0001087220, DSF0001087219
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/23/2024 | 1/20/2027 |  | 1094986 | 70640 | 68980 | DSF0001076533, DSF0001076534, DSF0001087220, DSF0001087219
26 | Q566 | GLEN OAKS CAMPUS | SCA Emergency Response | SIDE WALK BRIDGING | Construction | In-Progress | 1/9/2012 | EMER |  | EMER |  | 0 | SCA0000019914
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | DIIT - RESOA | FY15 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 72495 | 0 | DSF0000821794
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | DIIT - RESOA | FY 15 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 39000 | 0 | DSF0000821795
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 123000 | 0 | DSF0001033329
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 56000 | 0 | DSF0001086566
26 | Q809 | Q224 SPED - QUEENS | Fast Track Projects | LOCKER ROOM & BATHROOM UPGRADE | Construction | In-Progress | 9/22/2022 | FTK |  | FTK | 1773939 | 1738554 | DSF0000960552
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 9/25/2015 | 1/25/2016 | 12/18/2015 | 83700 | 137034 | 132700 | DSF0000798374, DSF0000792110
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/7/2016 | 2/10/2017 | 5/5/2017 | 334800 | 681743 | 666243 | DSF0000798374, DSF0000792110
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 8/22/2017 | 11/19/2018 |  | 6277500 | 7751386 | 7012560 | DSF0000798374, DSF0000792110
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 8/22/2017 | 11/19/2018 |  | 390600 | 943203 | 932599 | DSF0000798374, DSF0000792110
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/15/2023 | 7/14/2023 | 3/20/2023 | 3900 | 2494 | 2494 | DSF0001034569
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/20/2023 | 9/13/2023 | 5/3/2023 | 17550 | 9976 | 9976 | DSF0001034569
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 10/2/2023 | 7/27/2024 |  | 226200 | 205588 | 133647 | DSF0001034569
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 10/2/2023 | 7/27/2024 |  | 123029 | 105446 | 95040 | DSF0001034569
26 | Q811 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000013154
26 | Q811 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 0 | 0 | 0 | DSF0000013154
26 | Q811 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 5/22/2006 | 5/31/2007 |  | 0 | 0 | 0 | DSF0000013154
26 | Q811 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 5/22/2006 | 5/31/2007 |  | 0 | 0 | 0 | DSF0000013154
26 | Q811 | Q811 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 10/29/2024 | DIIR | 161432 | 161432 | DSF0001086585
26 | Q811 | Q811 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/7/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085033
26 | QAPM | PS 23 @ HILLSIDE PSYCH - Q | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008062
26 | QAPM | PS 23 @ HILLSIDE PSYCH - Q | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001033737
26 | QAPM | PS 23 @ HILLSIDE PSYCH - Q | DOE - RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001036096
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | Scope | Complete | 2/7/2014 | 7/10/2014 | 4/8/2014 | 251956 | 218821 | 218821 | DSF0000788302, DSF0000788296, DSF0000788293, DSF0000799428, DSF0000799439, DSF0000799438, DSF0000799608, DSF0000799919
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | Design | Complete | 4/8/2014 | 9/8/2014 | 9/11/2014 | 991112 | 1582139 | 1451475 | DSF0000788302, DSF0000788296, DSF0000788293, DSF0000799428, DSF0000799439, DSF0000799438, DSF0000799608, DSF0000799919
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | Construction | In-Progress | 1/6/2015 | 3/15/2017 |  | 17083341 | 17440209 | 16168197 | DSF0000788302, DSF0000788296, DSF0000788293, DSF0000799428, DSF0000799439, DSF0000799438, DSF0000799608, DSF0000799919
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | CM,F&E | In-Progress | 1/6/2015 | 3/15/2017 |  | 1393945 | 4478103 | 4437172 | DSF0000788302, DSF0000788296, DSF0000788293, DSF0000799428, DSF0000799439, DSF0000799438, DSF0000799608, DSF0000799919
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 3/12/2021 | 7/27/2021 | 9/1/2021 | 166231 | 167764 | 167764 | DSF0000960811, DSF0001034154, DSF0001034153
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 9/17/2021 | 2/23/2022 | 3/10/2022 | 824628 | 552104 | 552104 | DSF0000960811, DSF0001034154, DSF0001034153
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Construction | In-Progress | 8/5/2022 | 8/3/2024 |  | 17989111 | 16316947 | 5331034 | DSF0000960811, DSF0001034154, DSF0001034153
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | CM,F&E | In-Progress | 8/5/2022 | 8/3/2024 |  | 1212610 | 469005 | 453991 | DSF0000960811, DSF0001034154, DSF0001034153
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112956
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 51000 | 51000 | 0 | DSF0001112956
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 748000 | 748000 | 0 | DSF0001112956
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 51000 | 51000 | 0 | DSF0001112956
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113629
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113629
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113629
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113629
27 | Q042 | P.S. 42 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/14/2021 | EMER |  | EMER | 39945 | 17907 | SCA0000070728
27 | Q042 | P.S. 42 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 9/25/2024 | DIIR | 12/16/2024 | DIIR | 250000 | 250000 | DSF0001033258
27 | Q042 | P.S. 42 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0 | DSF0001035331
27 | Q042 | Q233 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001112957
27 | Q042 | P.S. 42 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084651
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 7/31/2018 | 10/30/2018 | 12/12/2018 | 17685 | 39477 | 39477 | DSF0000888907
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 1/7/2019 | 5/29/2019 | 5/17/2019 | 70740 | 143998 | 143070 | DSF0000888907
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 12/18/2019 | 12/16/2020 |  | 1326375 | 1613648 | 831310 | DSF0000888907
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 12/18/2019 | 12/16/2020 |  | 82530 | 475442 | 471065 | DSF0000888907
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | Scope | Complete | 8/30/2019 | 1/21/2020 | 10/27/2021 | 140840 | 194120 | 194120 | DSF0000912916, DSF0000912917, DSF0000995406, DSF0001021181
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | Design | Complete | 11/5/2021 | 4/12/2022 | 5/5/2022 | 704200 | 540164 | 488293 | DSF0000912916, DSF0000912917, DSF0000995406, DSF0001021181
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | Construction | In-Progress | 8/15/2022 | 5/5/2024 |  | 15844499 | 14366040 | 12714850 | DSF0000912916, DSF0000912917, DSF0000995406, DSF0001021181
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/15/2022 | 5/5/2024 |  | 987109 | 378966 | 343954 | DSF0000912916, DSF0000912917, DSF0000995406, DSF0001021181
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033749
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033749
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033749
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033749
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 3354 | 2936 | DSF0001033750
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 41646 | 855 | DSF0001033750
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001033750
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001033750
27 | Q043 | P.S. 43 - QUEENS | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 350000 | 350000 | 0 | DSF0001112959
27 | Q043 | P.S. 43 - QUEENS | Fast Track Projects | EMERGENCY PROTECTIVE MEASURES - HURRICANE SANDY | Construction | In-Progress | 10/31/2012 | FTK |  | FTK | 1882053 | 1882052 | SCA0000023487
27 | Q043 | Q256 SPED - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 345295 | 0 | DSF0000960088
27 | Q043 | Q256 SPED - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033303
27 | Q043 | Q256 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 6/10/2024 | DIIR |  | DIIR | 229193 | 0 | DSF0001035822
27 | Q043 | P.S. 43 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 334000 | 0 | DSF0001112958
27 | Q043 | P.S. 43 - QUEENS | DOE - Skilled Trades | ELEVATOR PISTON REPLACEMENT | Construction | In-Progress | 8/18/2023 | DOES |  | DOES | 266915 | 123691 | DSF0001071947
27 | Q045 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/17/2018 | 3/7/2019 | 2/20/2019 | 182490 | 114694 | 114694 | DSF0000878240, DSF0000878242, DSF0000878243, DSF0000878244
27 | Q045 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/20/2019 | 7/22/2019 | 5/10/2019 | 729960 | 678895 | 627183 | DSF0000878240, DSF0000878242, DSF0000878243, DSF0000878244
27 | Q045 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 8/5/2019 | 8/3/2021 |  | 13686750 | 13628478 | 10968242 | DSF0000878240, DSF0000878242, DSF0000878243, DSF0000878244
27 | Q045 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/5/2019 | 8/3/2021 |  | 851621 | 1627559 | 1603982 | DSF0000878240, DSF0000878242, DSF0000878243, DSF0000878244
27 | Q045 | P.S. 45 - QUEENS | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0000961431
27 | Q045 | P.S. 45 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112960
27 | Q047 | P.S. 47 - QUEENS | Fast Track Projects | FIRE ALARM REPLACEMENT | Construction | In-Progress | 6/24/2019 | FTK |  | FTK | 2868508 | 2589036 | SCA0000054628
27 | Q047 | P.S. 47 - QUEENS | DOE - Skilled Trades | GYM PARTITION | Construction | In-Progress | 3/11/2019 | DOES |  | DOES | 43302 | 0 | DSF0000911942
27 | Q051 | P.S. 51 - QUEENS | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 36287 | 0 | DSF0001086365
27 | Q051 | P.S. 51 - QUEENS | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 7/11/2024 | DOES |  | DOES | 75560 | 0 | DSF0001099784
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 10/3/2018 | 3/11/2019 | 1/14/2019 | 141298 | 142799 | 142799 | DSF0000890601, DSF0000878359
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/30/2019 | 7/1/2019 | 5/15/2019 | 608905 | 668678 | 650956 | DSF0000890601, DSF0000878359
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/15/2019 | 7/13/2021 |  | 12236625 | 11133351 | 10424104 | DSF0000890601, DSF0000878359
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/15/2019 | 7/13/2021 |  | 761390 | 1299233 | 1296340 | DSF0000890601, DSF0000878359
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | WALK-IN REFRIGERTAORS AND FREEZERS | Scope | Complete | 6/23/2023 | 10/23/2023 | 9/25/2023 | 11659 | 15501 | 15501 | DSF0001083810
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | WALK-IN REFRIGERTAORS AND FREEZERS | Design | Complete | 10/2/2023 | 3/1/2024 | 2/7/2024 | 52464 | 58629 | 43297 | DSF0001083810
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | WALK-IN REFRIGERTAORS AND FREEZERS | Construction | In-Progress | 8/12/2024 | 6/7/2025 |  | 676198 | 603973 | 8670 | DSF0001083810
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | WALK-IN REFRIGERTAORS AND FREEZERS | CM,F&E | In-Progress | 8/12/2024 | 6/7/2025 |  | 125330 | 86461 | 23396 | DSF0001083810
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | Scope | Complete | 6/24/2021 | 1/12/2022 | 1/20/2022 | 15933 | 21074 | 21074 | DSF0000995568, DSF0001009311
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | Design | Complete | 1/21/2022 | 5/23/2022 | 4/11/2022 | 79562 | 74079 | 74079 | DSF0000995568, DSF0001009311
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | Construction | Complete | 7/20/2023 | 7/18/2024 | 8/2/2024 | 1781235 | 1631145 | 1507808 | DSF0000995568, DSF0001009311
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | CM,F&E | Complete | 7/20/2023 | 7/18/2024 | 8/2/2024 | 112302 | 129597 | 109839 | DSF0000995568, DSF0001009311
27 | Q053 | I.S. 319 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033907
27 | Q053 | I.S. 319 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033907
27 | Q053 | I.S. 319 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033907
27 | Q053 | I.S. 319 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033907
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112964
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 72000 | 72000 | 0 | DSF0001112964
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1056000 | 1056000 | 0 | DSF0001112964
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 72000 | 72000 | 0 | DSF0001112964
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113631
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113631
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113631
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113631
27 | Q053 | I.S. 53 - QUEENS | SCA IEH | PO18-77/27Q053 /TEST KITCHEN FAN EXH #1 HOUSING INSULATION IF POSITIVE ABATE INSULATION ON FAN | Construction | Complete | 11/12/2024 | IEH | 11/14/2024 | IEH | 0 | 0 | SCA0000073595
27 | Q053 | I.S. 53 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 209455 | 0 | DSF0000960092
27 | Q053 | I.S. 319 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | In-Progress | 3/22/2024 | DOER |  | DOER | 55278 | 0 | DSF0001033755
27 | Q053 | I.S. 319 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0 | DSF0001033908
27 | Q053 | I.S. 53 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/10/2023 | DOER |  | DOER | 231115 | 0 | DSF0001035334
27 | Q053 | I.S. 53 - QUEENS | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0 | DSF0001086368
27 | Q053 | I.S. 53 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/1/2024 | DOES | 8/8/2024 | DOES | 65832 | 13588 | DSF0001084655
27 | Q053 | I.S. 53 - QUEENS | DOE - Skilled Trades | GYM FLOOR REPLACEMENT | Construction | In-Progress | 2/9/2024 | DOES |  | DOES | 294982 | 216301 | DSF0001111939
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/31/2019 | 3/15/2019 | 3/27/2019 | 18375 | 39943 | 39943 | DSF0000912167
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 3/27/2019 | 5/17/2019 | 5/17/2019 | 73500 | 110402 | 98555 | DSF0000912167
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 8/7/2019 | 8/5/2020 |  | 1378125 | 1494486 | 1166228 | DSF0000912167
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 8/7/2019 | 8/5/2020 |  | 85750 | 243618 | 231771 | DSF0000912167
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/8/2019 | 1/10/2020 | 1/31/2020 | 17800 | 28033 | 28033 | DSF0000901262
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2/19/2020 | 7/20/2020 | 10/6/2021 | 80100 | 117322 | 108913 | DSF0000901262
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 2/5/2024 | 2/3/2025 |  | 1032400 | 919907 | 27263 | DSF0000901262
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 2/5/2024 | 2/3/2025 |  | 191350 | 70608 | 68737 | DSF0000901262
27 | Q056 | P.S. 56 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 10/28/2021 | 3/3/2022 | 1/6/2022 | 0 | 2626 | 2626 | DSF0001008204
27 | Q056 | P.S. 56 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 1/6/2022 | 7/1/2022 | 3/2/2022 | 24000 | 10503 | 10503 | DSF0001008204
27 | Q056 | P.S. 56 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/20/2022 | 3/15/2023 |  | 352000 | 237403 | 203148 | DSF0001008204
27 | Q056 | P.S. 56 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/20/2022 | 3/15/2023 |  | 143856 | 157733 | 155688 | DSF0001008204
27 | Q056 | P.S. 56 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/16/2021 | DOES |  | DOES | 172134 | 0 | DSF0000912989
27 | Q056 | P.S. 56 - QUEENS | DOE - Skilled Trades | DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 1/23/2020 | DOES |  | DOES | 64037 | 0 | DSF0000960686
27 | Q056 | P.S. 56 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 5/31/2023 | DOES |  | DOES | 242864 | 0 | DSF0001034249
27 | Q060 | P.S. 60 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/6/2024 | 10/23/2024 | 10/3/2024 | 31943 | 5308 | 5245 | DSF0001127717
27 | Q060 | P.S. 60 - QUEENS | SCA CIP | EXTERIOR MASONRY | Design | In-Progress | 10/4/2024 | 3/12/2025 |  | 149066 | 149066 | 47428 | DSF0001127717
27 | Q060 | P.S. 60 - QUEENS | SCA CIP | EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 2363759 | 2363759 | 1028 | DSF0001127717
27 | Q060 | P.S. 60 - QUEENS | SCA CIP | EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 234246 | 234246 | 38921 | DSF0001127717
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/14/2023 | 4/17/2024 | 4/15/2024 | 0 | 19361 | 19361 | DSF0001086372
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 4/16/2024 | 8/30/2024 |  | 29979 | 62965 | 38927 | DSF0001086372
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 439687 | 439687 | 4493 | DSF0001086372
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 29979 | 29979 | 18299 | DSF0001086372
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 12/14/2023 | 3/18/2024 | 9/18/2024 | 0 | 0 | 1218 | DSF0001087055
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | In-Progress | 9/19/2024 | 1/27/2025 |  | 21 | 21 | 4874 | DSF0001087055
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 314 | 314 | 0 | DSF0001087055
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 21 | 21 | 3079 | DSF0001087055
27 | Q060 | P.S. 60 - QUEENS | SCA IEH | PO18-REMOVE ACM SPRAYED RED ON PIPING APPROX 5FT PIPING IS LOCATED IN BASEMENT BY STAIRWELL CUSTODIA | Construction | Complete | 10/15/2024 | IEH | 10/19/2024 | IEH | 0 | 0 | SCA0000073505
27 | Q060 | P.S. 60 - QUEENS | SCA IEH | PO18-REMOVE ACM ON WATER PIPING LOCATED IN BOILER ROOM SPRAYED YELLOW APPROX 20FT 4 INCH WATER LINE | Construction | Complete | 12/4/2024 | IEH | 12/14/2024 | IEH | 0 | 0 | SCA0000073667
27 | Q060 | P.S. 60 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112969
27 | Q060 | P.S. 60 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 650000 | 0 | DSF0001111909
27 | Q062 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/22/2023 | 11/7/2023 | 11/3/2023 | 110505 | 192998 | 192770 | DSF0001021490, DSF0001021491, DSF0001021492, DSF0001111825
27 | Q062 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/15/2023 | 4/18/2024 | 5/7/2024 | 547485 | 398724 | 308653 | DSF0001021490, DSF0001021491, DSF0001021492, DSF0001111825
27 | Q062 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 9/12/2024 | 9/1/2026 |  | 11882344 | 10899390 | 156586 | DSF0001021490, DSF0001021491, DSF0001021492, DSF0001111825
27 | Q062 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 9/12/2024 | 9/1/2026 |  | 811344 | 52200 | 51931 | DSF0001021490, DSF0001021491, DSF0001021492, DSF0001111825
27 | Q062 | P.S. 62 - QUEENS | SCA CIP RESOA | FY20 RESO A COMPUTER LAB | Scope | Complete | 5/26/2021 | 10/8/2021 | 2/1/2022 | 0 | 17207 | 17207 | DSF0000913970
27 | Q062 | P.S. 62 - QUEENS | SCA CIP RESOA | FY20 RESO A COMPUTER LAB | Design | Complete | 2/10/2022 | 8/1/2022 | 8/10/2022 | 72000 | 82332 | 58807 | DSF0000913970
27 | Q062 | P.S. 62 - QUEENS | SCA CIP RESOA | FY20 RESO A COMPUTER LAB | Construction | In-Progress | 3/13/2023 | 1/6/2024 |  | 1056000 | 504125 | 435300 | DSF0000913970
27 | Q062 | P.S. 62 - QUEENS | SCA CIP RESOA | FY20 RESO A COMPUTER LAB | CM,F&E | In-Progress | 3/13/2023 | 1/6/2024 |  | 172178 | 177531 | 137748 | DSF0000913970
27 | Q062 | P.S. 62 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 227048 | 199320 | DSF0000960677
27 | Q062 | P.S. 62 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001035835
27 | Q062 | P.S. 62 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/6/2024 | DOER |  | DOER | 382581 | 0 | DSF0001086374
27 | Q062 | P.S. 62 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001112971
27 | Q062 | P.S. 62 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/8/2024 | DOES | 11/15/2024 | DOES | 65832 | 20013 | DSF0001084295
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | Scope | Complete | 8/22/2019 | 1/28/2020 | 2/24/2020 | 19870 | 60049 | 60049 | DSF0000901374
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | Design | Complete | 2/16/2021 | 7/16/2021 | 2/22/2022 | 99350 | 355083 | 309466 | DSF0000901374
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | Construction | In-Progress | 8/5/2022 | 8/4/2023 |  | 2235375 | 2031460 | 1814145 | DSF0000901374
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | CM,F&E | In-Progress | 8/5/2022 | 8/4/2023 |  | 139090 | 207369 | 195044 | DSF0000901374
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/10/2024 | 10/25/2024 | 10/11/2024 | 380072 | 233894 | 172902 | DSF0001100012, DSF0001100015, DSF0001113826, DSF0001127785, DSF0001127786
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 10/30/2024 | 4/4/2025 |  | 1768026 | 1771158 | 239627 | DSF0001100012, DSF0001100015, DSF0001113826, DSF0001127785, DSF0001127786
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 27985670 | 27985670 | 21539 | DSF0001100012, DSF0001100015, DSF0001113826, DSF0001127785, DSF0001127786
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 2849983 | 2849983 | 31550 | DSF0001100012, DSF0001100015, DSF0001113826, DSF0001127785, DSF0001127786
27 | Q063 | P.S. 63 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 11/29/2021 | FTK |  | FTK | 268334 | 176979 | DSF0000960688
27 | Q063 | P.S. 63 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112972
27 | Q063 | P.S. 63 - QUEENS | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 10/8/2021 | DOER |  | DOER | 108899 | 0 | DSF0001008189
27 | Q063 | P.S. 63 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 221263 | 0 | DSF0001035836
27 | Q064 | P.S. 64 - QUEENS | Fast Track Projects | TEMPORARY BOILER | Construction | Complete | 8/3/2016 | FTK | 4/27/2022 | FTK | 772108 | 772108 | DSF0000834021
27 | Q064 | P.S. 64 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035837
27 | Q064 | P.S. 64 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112973
27 | Q064 | P.S. 64 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 56000 | 0 | DSF0001086376
27 | Q066 | P.S. 66 - QUEENS | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | Complete | 11/13/2023 | DOER | 11/20/2023 | DOER | 13238 | 49820 | DSF0001035838
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | Scope | Complete | 6/13/2017 | 10/13/2017 | 9/25/2017 | 27870 | 25449 | 25449 | DSF0000743438
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | Design | Complete | 2/21/2018 | 7/23/2018 | 5/18/2018 | 102190 | 146069 | 145944 | DSF0000743438
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | Construction | In-Progress | 7/23/2018 | 7/22/2019 |  | 1082285 | 951320 | 890731 | DSF0000743438
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | CM,F&E | In-Progress | 7/23/2018 | 7/22/2019 |  | 250830 | 142643 | 142518 | DSF0000743438
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Scope | Complete | 1/13/2020 | 4/13/2020 | 9/24/2021 | 83050 | 91872 | 91872 | DSF0000947313, DSF0000996192
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Design | Complete | 9/29/2021 | 4/6/2022 | 5/10/2023 | 415250 | 441219 | 410139 | DSF0000947313, DSF0000996192
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Construction | In-Progress | 9/12/2023 | 12/4/2024 |  | 9343125 | 9223127 | 6320434 | DSF0000947313, DSF0000996192
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | CM,F&E | In-Progress | 9/12/2023 | 12/4/2024 |  | 581350 | 333023 | 236770 | DSF0000947313, DSF0000996192
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 6/21/2024 | 11/6/2024 | 10/15/2024 | 332754 | 166231 | 160863 | DSF0001100478, DSF0001100482, DSF0001100483, DSF0001113827, DSF0001128260
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | In-Progress | 11/14/2024 | 4/18/2025 |  | 1541012 | 1541012 | 199728 | DSF0001100478, DSF0001100482, DSF0001100483, DSF0001113827, DSF0001128260
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | PNS | PNS | PNS | PNS | 24330748 | 24330748 | 46346 | DSF0001100478, DSF0001100482, DSF0001100483, DSF0001113827, DSF0001128260
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 2571915 | 2571915 | 40542 | DSF0001100478, DSF0001100482, DSF0001100483, DSF0001113827, DSF0001128260
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112994
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112994
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001112994
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112994
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113635
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113635
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113635
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113635
27 | Q090 | P.S. 90 - QUEENS | SCA IEH | PO18-TEST FLOOR & SUBLAYERS FOR ACM IN RMS 208,110,212,409B ABATE AND REPLACE IF POSITIVE. DAMAGED F | Construction | Complete | 7/25/2024 | IEH | 8/27/2024 | IEH | 0 | 0 | SCA0000073175
27 | Q090 | P.S. 90 - QUEENS | SCA IEH | PO18-TEST BOILER ROOM PIPE INSULATION &IF POSITIVE ABATE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | Complete | 9/19/2024 | IEH | 10/4/2024 | IEH | 0 | 0 | SCA0000073400
27 | Q090 | P.S. 90 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112993
27 | Q090 | P.S. 90 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112991
27 | Q090 | P.S. 90 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112992
27 | Q090 | P.S. 90 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/2/2024 | DOES |  | DOES | 238033 | 0 | DSF0001008707
27 | Q090 | P.S. 90 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/24/2024 | DOES | 9/13/2024 | DOES | 65832 | 12602 | DSF0001084313
27 | Q096 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | Scope | Complete | 1/27/2020 | 3/1/2021 | 3/9/2021 | 1142001 | 681356 | 681356 | DSF0000912660, DSF0000912660, DSF0000912660, DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | Design | Complete | 3/10/2021 | 8/26/2021 | 5/11/2022 | 5138999 | 2563466 | 2233552 | DSF0000912660, DSF0000912660, DSF0000912660, DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | Construction | Complete | 7/25/2022 | 9/3/2024 | 9/5/2024 | 64808500 | 74231985 | 51796337 | DSF0000912660, DSF0000912660, DSF0000912660, DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | CM,Art,F&E | Complete | 7/25/2022 | 9/3/2024 | 9/5/2024 | 9136001 | 8154850 | 6273402 | DSF0000912660, DSF0000912660, DSF0000912660, DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 10/27/2020 | 10/27/2020 | 10/27/2020 | 15255 | 19724 | 19724 | DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 12/18/2020 | 5/28/2021 | 1/20/2022 | 68649 | 33131 | 33131 | DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 884809 | 884809 | 9808 | DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 163995 | 163995 | 6093 | DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 10/27/2020 | 10/27/2020 | 10/27/2020 | 29810 | 65191 | 65191 | DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 10/28/2020 | 2/1/2021 | 2/2/2021 | 149050 | 356566 | 352367 | DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 5/24/2021 | 10/20/2021 |  | 3353625 | 3316300 | 2875856 | DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 5/24/2021 | 10/20/2021 |  | 208670 | 212175 | 207230 | DSF0000912660
27 | Q096 | P.S. 96 - QUEENS | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/1/2023 | DOER |  | DOER | 359759 | 0 | DSF0001033790
27 | Q096 | P.S. 96 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/27/2023 | DOER |  | DOER | 60784 | 0 | DSF0001035866
27 | Q097 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | Scope | Complete | 1/29/2020 | 6/12/2020 | 11/19/2021 | 94746 | 147626 | 130257 | DSF0000947436, DSF0001022095, DSF0001022098, DSF0001022102
27 | Q097 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | Design | Complete | 12/1/2021 | 5/4/2022 | 5/13/2022 | 464365 | 445836 | 415393 | DSF0000947436, DSF0001022095, DSF0001022098, DSF0001022102
27 | Q097 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | Construction | In-Progress | 7/12/2022 | 4/1/2024 |  | 9638032 | 8731493 | 7754907 | DSF0000947436, DSF0001022095, DSF0001022098, DSF0001022102
27 | Q097 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | CM,F&E | In-Progress | 7/12/2022 | 4/1/2024 |  | 734207 | 941797 | 920110 | DSF0000947436, DSF0001022095, DSF0001022098, DSF0001022102
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113001
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001113001
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001113001
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001113001
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113637
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113637
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113637
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113637
27 | Q097 | P.S. 97 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 7/3/2024 | DIIR | 50000 | 50000 | DSF0001035867
27 | Q097 | P.S. 97 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113002
27 | Q097 | P.S. 97 - QUEENS | DOE - RESOA | FY14 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 118435 | 0 | DSF0000798722
27 | Q097 | P.S. 97 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/19/2022 | DOES |  | DOES | 106527 | 0 | DSF0001009074
27 | Q100 | P.S. 100 - QUEENS | SCA CIP | ROOFS / EMERGENCY GENERATOR / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/6/2023 | 162840 | 273865 | 247728 | DSF0001072917, DSF0001087227, DSF0001087225, DSF0001087224, DSF0001087223
27 | Q100 | P.S. 100 - QUEENS | SCA CIP | ROOFS / EMERGENCY GENERATOR / EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 11/3/2023 | 6/28/2024 | 4/19/2024 | 804579 | 477599 | 466578 | DSF0001072917, DSF0001087227, DSF0001087225, DSF0001087224, DSF0001087223
27 | Q100 | P.S. 100 - QUEENS | SCA CIP | ROOFS / EMERGENCY GENERATOR / EXTERIOR MASONRY / WINDOWS / PARAPETS | Construction | PNS | PNS | PNS | PNS | 17271198 | 17271198 | 158374 | DSF0001072917, DSF0001087227, DSF0001087225, DSF0001087224, DSF0001087223
27 | Q100 | P.S. 100 - QUEENS | SCA CIP | ROOFS / EMERGENCY GENERATOR / EXTERIOR MASONRY / WINDOWS / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 1211997 | 1211997 | 52295 | DSF0001072917, DSF0001087227, DSF0001087225, DSF0001087224, DSF0001087223
27 | Q104 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | Scope | Complete | 5/22/2019 | 8/21/2019 | 8/13/2019 | 13950 | 31091 | 31091 | DSF0000911829
27 | Q104 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | Design | Complete | 8/27/2019 | 1/15/2020 | 3/31/2020 | 62775 | 81374 | 74898 | DSF0000911829
27 | Q104 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | Construction | In-Progress | 6/9/2021 | 6/8/2022 |  | 809100 | 842946 | 668138 | DSF0000911829
27 | Q104 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | CM,F&E | In-Progress | 6/9/2021 | 6/8/2022 |  | 149963 | 79547 | 72797 | DSF0000911829
27 | Q104 | P.S. 104 - QUEENS | SCA IEH | PO18-BASEMENT PIPE DUCT SPACE ABATE UNRAVELING PIPE INSULATION | Construction | Complete | 9/5/2024 | IEH | 11/23/2024 | IEH | 0 | 0 | SCA0000073352
27 | Q104 | P.S. 104 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 700000 | 0 | DSF0001086401
27 | Q104 | P.S. 104 - QUEENS | DOE - Skilled Trades | WATER MAIN LEAK REPAIR | Construction | In-Progress | 3/16/2024 | DOES |  | DOES | 100000 | 0 | DSF0001112183
27 | Q105 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 4/11/2023 | 44850 | 147758 | 32851 | DSF0001022233, DSF0001022235
27 | Q105 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 12/1/2023 | 5/3/2024 | 5/8/2024 | 224250 | 328382 | 288862 | DSF0001022233, DSF0001022235
27 | Q105 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 7/29/2024 | 4/19/2026 |  | 5045625 | 4617402 | 28141 | DSF0001022233, DSF0001022235
27 | Q105 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/29/2024 | 4/19/2026 |  | 313950 | 131969 | 129909 | DSF0001022233, DSF0001022235
27 | Q105 | P.S. 105 - QUEENS | SCA IEH | PO18-77/27Q105/NURSES OFFICE CLOSED 9X9 FL TILES LIFTING | Construction | Complete | 11/22/2024 | IEH | 11/24/2024 | IEH | 0 | 0 | SCA0000073640
27 | Q105 | P.S. 105 - QUEENS | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086402
27 | Q105 | P.S. 105 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/28/2024 | DOES | 7/8/2024 | DOES | 65832 | 17278 | DSF0001084661
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001008181
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 10140 | 10140 | 0 | DSF0001008181
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 148720 | 148720 | 0 | DSF0001008181
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 10140 | 10140 | 0 | DSF0001008181
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113006
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 72000 | 72000 | 0 | DSF0001113006
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 1056000 | 1056000 | 0 | DSF0001113006
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 72000 | 72000 | 0 | DSF0001113006
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113638
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113638
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113638
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113638
27 | Q108 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 6/10/2022 | 9/9/2022 | 9/14/2022 | 14880 | 3551 | 3551 | DSF0001022292
27 | Q108 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 9/14/2022 | 2/17/2023 | 2/15/2023 | 66960 | 14206 | 14206 | DSF0001022292
27 | Q108 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Construction | In-Progress | 9/18/2023 | 8/12/2024 |  | 863034 | 766133 | 481817 | DSF0001022292
27 | Q108 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 9/18/2023 | 8/12/2024 |  | 159959 | 112194 | 54404 | DSF0001022292
27 | Q108 | P.S. 108 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 528023 | 0 | DSF0000960116
27 | Q108 | P.S. 108 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/24/2023 | DOER |  | DOER | 861763 | 0 | DSF0001035872
27 | Q108 | P.S. 108 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/18/2023 | DOES |  | DOES | 149934 | 0 | DSF0001034251
27 | Q114 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/7/2022 | 1/10/2023 | 11/15/2022 | 4575 | 5632 | 5632 | DSF0001034572
27 | Q114 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 11/15/2022 | 5/12/2023 | 3/8/2023 | 20588 | 22625 | 22527 | DSF0001034572
27 | Q114 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/10/2023 | 5/4/2024 |  | 265350 | 236740 | 208914 | DSF0001034572
27 | Q114 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/10/2023 | 5/4/2024 |  | 156764 | 163972 | 118661 | DSF0001034572
27 | Q114 | P.S. 114 - QUEENS | SCA IEH | PO18-GYMNASIUM REPAIR LIFTING SECTION OF THE WOOD FLOORING - ROOM 206 REPAIR DAMAGED AREAS OF FLOOR | Construction | In-Progress | 5/15/2024 | IEH |  | IEH | 0 | 0 | SCA0000073005
27 | Q114 | P.S. 114 - QUEENS | Fast Track Projects | LSP- PLAY YARD RENOVATION | Construction | In-Progress | 9/2/2021 | FTK |  | FTK | 139900 | 139816 | DSF0000996592
27 | Q114 | Q256 SPED - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 345295 | 0 | DSF0000960121
27 | Q114 | P.S. 114 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001033800
27 | Q114 | P.S. 114 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 50000 | 47684 | DSF0001086408
27 | Q114 | P.S. 114 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113012
27 | Q114 | P.S. 114 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 325000 | 0 | DSF0001035877
27 | Q114 | P.S. 114 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 56000 | 0 | DSF0001086409
27 | Q114 | P.S. 114 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/6/2022 | DOES |  | DOES | 103809 | 0 | DSF0001009193
27 | Q114 | P.S. 114 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 8/16/2022 | DOES |  | DOES | 166573 | 0 | DSF0001034252
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | Scope | Complete | 7/20/2015 | 1/21/2016 | 10/21/2015 | 16230 | 58517 | 58517 | DSF0000821930
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | Design | Complete | 11/10/2015 | 5/13/2016 | 5/10/2016 | 64920 | 171005 | 169001 | DSF0000821930
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 11/18/2016 | 11/17/2017 |  | 1217250 | 1165402 | 1054042 | DSF0000821930
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 11/18/2016 | 11/17/2017 |  | 75740 | 419426 | 417422 | DSF0000821930
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/3/2021 | 12/2/2021 | 10/28/2021 | 239100 | 206515 | 206515 | DSF0000996762, DSF0000996764, DSF0000996765, DSF0000996766, DSF0001034298
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/24/2021 | 6/30/2022 | 4/25/2022 | 1195500 | 379120 | 379120 | DSF0000996762, DSF0000996764, DSF0000996765, DSF0000996766, DSF0001034298
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 2/22/2024 | 2/20/2026 |  | 26898750 | 24337707 | 1840580 | DSF0000996762, DSF0000996764, DSF0000996765, DSF0000996766, DSF0001034298
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 2/22/2024 | 2/20/2026 |  | 1673700 | 88109 | 69164 | DSF0000996762, DSF0000996764, DSF0000996765, DSF0000996766, DSF0001034298
27 | Q123 | P.S. 123 - QUEENS | SCA CIP RESOA | FY19 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 10/22/2018 | 8/19/2019 | 11/19/2019 | 0 | 22268 | 22268 | DSF0000890880, DSF0000912264
27 | Q123 | P.S. 123 - QUEENS | SCA CIP RESOA | FY19 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 12/3/2019 | 4/3/2020 | 4/2/2021 | 37599 | 97569 | 97569 | DSF0000890880, DSF0000912264
27 | Q123 | P.S. 123 - QUEENS | SCA CIP RESOA | FY19 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | Complete | 6/16/2021 | 3/12/2022 | 6/14/2022 | 551452 | 434977 | 387452 | DSF0000890880, DSF0000912264
27 | Q123 | P.S. 123 - QUEENS | SCA CIP RESOA | FY19 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | Complete | 6/16/2021 | 3/12/2022 | 6/14/2022 | 91275 | 108211 | 83693 | DSF0000890880, DSF0000912264
27 | Q123 | P.S. 123 - QUEENS | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 154000 | 154000 | 0 | DSF0001113018
27 | Q123 | P.S. 123 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 225689 | 189693 | DSF0000960807
27 | Q123 | P.S. 123 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 190000 | 0 | DSF0001008128
27 | Q123 | P.S. 123 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | Complete | 12/26/2023 | DOER | 3/22/2024 | DOER | 78613 |  | DSF0001035888
27 | Q123 | P.S. 123 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113017
27 | Q123 | P.S. 123 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/22/2022 | DOES |  | DOES | 68928 | 0 | DSF0001009187
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 10/17/2016 | 3/22/2017 | 11/22/2016 | 81210 | 127054 | 127054 | DSF0000798317, DSF0000789560
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 12/7/2016 | 5/10/2017 | 5/11/2017 | 324840 | 717433 | 667884 | DSF0000798317, DSF0000789560
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 5/21/2018 | 8/13/2019 |  | 6090750 | 6793839 | 5723169 | DSF0000798317, DSF0000789560
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 5/21/2018 | 8/13/2019 |  | 378980 | 1083445 | 1039913 | DSF0000798317, DSF0000789560
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Scope | Complete | 5/28/2019 | 9/30/2019 | 11/21/2019 | 82346 | 49788 | 49788 | DSF0000902352, DSF0001022584, DSF0001034498
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Design | Complete | 1/8/2020 | 6/15/2020 | 9/30/2022 | 403783 | 336338 | 285971 | DSF0000902352, DSF0001022584, DSF0001034498
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Construction | In-Progress | 8/14/2023 | 2/3/2025 |  | 8397811 | 7800980 | 2086192 | DSF0000902352, DSF0001022584, DSF0001034498
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | CM,F&E | In-Progress | 8/14/2023 | 2/3/2025 |  | 636015 | 242208 | 169310 | DSF0000902352, DSF0001022584, DSF0001034498
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 3/11/2022 | 7/11/2022 | 3/11/2022 | 3800 | 5517 | 5517 | DSF0001034364
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | Design | Complete | 3/16/2022 | 9/8/2022 | 7/18/2022 | 17100 | 22067 | 22067 | DSF0001034364
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | Construction | In-Progress | 2/27/2023 | 12/23/2023 |  | 220400 | 203642 | 130103 | DSF0001034364
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | CM,F&E | In-Progress | 2/27/2023 | 12/23/2023 |  | 167436 | 163276 | 105061 | DSF0001034364
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113019
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 37500 | 37500 | 0 | DSF0001113019
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 550000 | 550000 | 0 | DSF0001113019
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 37500 | 37500 | 0 | DSF0001113019
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113640
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113640
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113640
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113640
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY21 RESO A ATHLETIC FIELDS | Scope | Complete | 9/2/2021 | 1/4/2022 | 3/3/2022 | 0 | 37321 | 37321 | DSF0001008122
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY21 RESO A ATHLETIC FIELDS | Design | Complete | 3/16/2022 | 9/6/2022 | 3/31/2023 | 184726 | 81034 | 77702 | DSF0001008122
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY21 RESO A ATHLETIC FIELDS | Construction | In-Progress | 10/23/2023 | 1/14/2025 |  | 2709321 | 2561719 | 2119829 | DSF0001008122
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY21 RESO A ATHLETIC FIELDS | CM,F&E | In-Progress | 10/23/2023 | 1/14/2025 |  | 184726 | 163823 | 112844 | DSF0001008122
27 | Q124 | P.S. 124 - QUEENS | SCA IEH | PO18-TEST WOOD FLOORS &IF POSITIVE ABATE & REPLACE PLEASE NOTIFY ALL COPIED OF RESULTS WOOD FLOORS B | Construction | Complete | 7/31/2024 | IEH | 8/31/2024 | IEH | 0 | 0 | SCA0000073219
27 | Q124 | P.S. 124 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 371929 | 0 | DSF0000960127
27 | Q124 | P.S. 124 - QUEENS | DIIT - RESOA | RESO A- TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 74250 | 0 | DSF0000775816
27 | Q124 | P.S. 124 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001035889
27 | Q124 | P.S. 124 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/25/2022 | DOES |  | DOES | 69675 | 0 | DSF0001008968
27 | Q124 | P.S. 124 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 9/26/2022 | DOES |  | DOES | 187170 | 0 | DSF0001034253
27 | Q124 | P.S. 124 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/26/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084668
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113033
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001113033
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1760000 | 1760000 | 0 | DSF0001113033
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 120000 | 120000 | 0 | DSF0001113033
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113643
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113643
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113643
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113643
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/16/2022 | 7/1/2022 | 8/15/2022 | 0 | 9969 | 9969 | DSF0000913189
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A GYMNASIUM UPGRADE | Design | Complete | 9/6/2022 | 1/25/2023 | 3/8/2023 | 32076 | 41455 | 40844 | DSF0000913189
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 9/5/2023 | 6/30/2024 |  | 470455 | 432544 | 319085 | DSF0000913189
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A GYMNASIUM UPGRADE | CM,F&E | In-Progress | 9/5/2023 | 6/30/2024 |  | 32076 | 54065 | 33616 | DSF0000913189
27 | Q137 | M.S. 137 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 247452 | 166974 | DSF0000960810
27 | Q137 | M.S. 137 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033815
27 | Q137 | M.S. 137 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001035906
27 | Q137 | M.S. 137 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 350000 | 0 | DSF0001113034
27 | Q137 | M.S. 137 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 50000 | 0 | DSF0001086426
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 10/4/2023 | 2/23/2024 | 9/5/2024 | 17815 | 83204 | 57389 | DSF0001073807, DSF0001101565
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | In-Progress | 10/10/2024 | 3/18/2025 |  | 84318 | 84414 | 8399 | DSF0001073807, DSF0001101565
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Construction | PNS | PNS | PNS | PNS | 1742592 | 1742592 | 29325 | DSF0001073807, DSF0001101565
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 161562 | 161562 | 56460 | DSF0001073807, DSF0001101565
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/22/2022 | 3/27/2023 | 1/6/2023 | 4425 | 1726 | 1726 | DSF0001034571
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/6/2023 | 7/5/2023 | 3/8/2023 | 19913 | 7199 | 7101 | DSF0001034571
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/10/2023 | 5/4/2024 |  | 256650 | 236229 | 210496 | DSF0001034571
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/10/2023 | 5/4/2024 |  | 175570 | 175487 | 129076 | DSF0001034571
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/4/2023 | 3/6/2024 | 7/25/2024 | 0 | 29114 | 28656 | DSF0001086435
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 8/6/2024 | 12/23/2024 |  | 41974 | 51649 | 14010 | DSF0001086435
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 615617 | 615617 | 2268 | DSF0001086435
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 41974 | 41974 | 21634 | DSF0001086435
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/5/2024 | 6/5/2024 | 6/27/2024 | 0 | 0 | 1043 | DSF0001087063
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 7/9/2024 | 11/8/2024 |  | 26 | 26 | 4171 | DSF0001087063
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 383 | 383 | 0 | DSF0001087063
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 26 | 26 | 3411 | DSF0001087063
27 | Q146 | P.S. 146 - QUEENS | SCA Emergency Response | EMERGENCY INVESTIGATION CRACKS FALLING DEBRIS Q146 | Construction | In-Progress | 6/6/2023 | EMER |  | EMER | 193134 | 130241 | SCA0000072058
27 | Q146 | P.S. 146 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 182000 | 0 | DSF0001113042
27 | Q146 | P.S. 146 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/17/2023 | DOER |  | DOER | 445417 | 0 | DSF0000960623
27 | Q146 | P.S. 146 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 63000 | 0 | DSF0001113040
27 | Q146 | P.S. 146 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/3/2022 | DOES |  | DOES | 63046 | 0 | DSF0001009081
27 | Q155 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 10/30/2018 | 3/20/2019 | 4/1/2019 | 144558 | 109736 | 109206 | DSF0000880044, DSF0000880046, DSF0000880047, DSF0000880048, DSF0000880049
27 | Q155 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 4/1/2019 | 8/29/2019 | 5/17/2019 | 576841 | 606067 | 570984 | DSF0000880044, DSF0000880046, DSF0000880047, DSF0000880048, DSF0000880049
27 | Q155 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 6/14/2021 | 12/5/2022 |  | 10690817 | 10045460 | 9134519 | DSF0000880044, DSF0000880046, DSF0000880047, DSF0000880048, DSF0000880049
27 | Q155 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 6/14/2021 | 12/5/2022 |  | 692703 | 611526 | 604862 | DSF0000880044, DSF0000880046, DSF0000880047, DSF0000880048, DSF0000880049
27 | Q155 | P.S. 155 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/12/2023 | 4/19/2024 | 4/18/2024 | 0 | 28130 | 28130 | DSF0001086447, DSF0001087065
27 | Q155 | P.S. 155 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 5/3/2024 | 9/19/2024 | 11/15/2024 | 45000 | 50605 | 28236 | DSF0001086447, DSF0001087065
27 | Q155 | P.S. 155 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660005 | 18731 | DSF0001086447, DSF0001087065
27 | Q155 | P.S. 155 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 49770 | 31778 | DSF0001086447, DSF0001087065
27 | Q155 | P.S. 155 - QUEENS | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 7/18/2024 |  | 9/20/2024 | 80000 | 80000 | 79837 | DSF0001035924
27 | Q155 | P.S. 155 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/29/2024 | DOER |  | DOER | 334796 | 0 | DSF0001035923
27 | Q155 | P.S. 155 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 150000 | 0 | DSF0001086448
27 | Q155 | P.S. 155 - QUEENS | DOE - RESOA | RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 239000 | 0 | DSF0001113877
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/10/2021 | 9/23/2021 | 1/21/2022 | 70940 | 88332 | 88332 | DSF0000912442, DSF0001034478, DSF0001023665
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/26/2022 | 6/27/2022 | 9/13/2022 | 354701 | 405380 | 387146 | DSF0000912442, DSF0001034478, DSF0001023665
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 7/17/2023 | 4/6/2025 |  | 7980750 | 7340101 | 1804777 | DSF0000912442, DSF0001034478, DSF0001023665
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/17/2023 | 4/6/2025 |  | 496580 | 349484 | 275194 | DSF0000912442, DSF0001034478, DSF0001023665
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | Fast Track Projects | CONDENSATION RESOLUTION | Construction | In-Progress | 7/12/2018 | FTK |  | FTK | 13120502 | 12277451 | DSF0000865949
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086462
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - RESOA | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/7/2023 | DOER |  | DOER | 539862 | 0 | DSF0000866345
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - RESOA | RESO A HYDROPONICS LAB | Construction | In-Progress | 6/30/2023 | DOER |  | DOER | 276707 | 0 | DSF0001034530
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 151485 | 0 | DSF0001035343
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113074
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/29/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084994
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/20/2024 | DOES |  | DOES | 482665 | 0 | DSF0001085753
27 | Q183 | P.S. 183 - QUEENS | SCA CIP RESOA | FY19 RESO A PLAYGROUND / PATH OF TRAVEL RESO A PLAYGROUND | Scope | Complete | 10/17/2018 | 7/29/2019 | 7/12/2019 | 0 | 46371 | 46371 | DSF0000890900, DSF0000912550
27 | Q183 | P.S. 183 - QUEENS | SCA CIP RESOA | FY19 RESO A PLAYGROUND / PATH OF TRAVEL RESO A PLAYGROUND | Design | Complete | 9/18/2019 | 11/15/2019 | 9/20/2019 | 82593 | 136571 | 102737 | DSF0000890900, DSF0000912550
27 | Q183 | P.S. 183 - QUEENS | SCA CIP RESOA | FY19 RESO A PLAYGROUND / PATH OF TRAVEL RESO A PLAYGROUND | Construction | In-Progress | 5/17/2021 | 5/16/2022 |  | 1211358 | 1279511 | 941852 | DSF0000890900, DSF0000912550
27 | Q183 | P.S. 183 - QUEENS | SCA CIP RESOA | FY19 RESO A PLAYGROUND / PATH OF TRAVEL RESO A PLAYGROUND | CM,F&E | In-Progress | 5/17/2021 | 5/16/2022 |  | 82593 | 274892 | 266021 | DSF0000890900, DSF0000912550
27 | Q183 | P.S. 183 - QUEENS | SCA IEH | PO18-TGG/ABATE PIPE INSULATION IN CRAWL SPACE.APPROX 30 LINEAR FEET SPRAYED IN RED | Construction | Complete | 9/18/2024 | IEH | 9/19/2024 | IEH | 0 | 0 | SCA0000073394
27 | Q183 | P.S. 183 - QUEENS | SCA IEH | PO18-77/27Q183/ABATE 9X9 TILE ROOM 247 THEY HAVE BECOME FRIABLE ROOM HAS BEEN CLOSED | Construction | Complete | 9/27/2024 | IEH | 10/5/2024 | IEH | 0 | 0 | SCA0000073436
27 | Q183 | P.S. 183 - QUEENS | SCA IEH | PO18-77/27Q183/9X9 FLOOR TILE LIFTING RM 339 ROOM HAS BEEN CLOSED ABATE AND REPLACE JOSEPH GARGIULI | Construction | Complete | 11/25/2024 | IEH | 12/1/2024 | IEH | 0 | 0 | SCA0000073642
27 | Q183 | P.S. 183 - QUEENS | SCA IEH | PO18-ABATE PIPE INSULATION IN CRAWL SPACE. APPROX 30 LINEAR FEET SPRAYED IN RED. | Construction | Complete | 11/26/2024 | IEH | 12/27/2024 | IEH | 0 | 0 | SCA0000073647
27 | Q183 | P.S. 183 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | Complete | 2/14/2023 | DOER | 8/21/2023 | DOER | 94953 |  | DSF0001033843
27 | Q183 | P.S. 183 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001035338
27 | Q183 | P.S. 183 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 228536 | 0 | DSF0001086464
27 | Q183 | P.S. 183 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/28/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084678
27 | Q197 | P.S. 197 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE / FY21 RESO A PLAYGROUND UPGRADE / RETAINING WALL | Scope | Complete | 7/22/2021 | 8/22/2023 | 2/4/2022 | 0 | 68865 | 55975 | DSF0001007755, DSF0001008179, DSF0001074727
27 | Q197 | P.S. 197 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE / FY21 RESO A PLAYGROUND UPGRADE / RETAINING WALL | Design | Complete | 2/7/2022 | 6/7/2022 | 4/14/2022 | 44818 | 53678 | 42517 | DSF0001007755, DSF0001008179, DSF0001074727
27 | Q197 | P.S. 197 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE / FY21 RESO A PLAYGROUND UPGRADE / RETAINING WALL | Construction | In-Progress | 6/20/2022 | 3/16/2023 |  | 657333 | 497381 | 439315 | DSF0001007755, DSF0001008179, DSF0001074727
27 | Q197 | P.S. 197 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE / FY21 RESO A PLAYGROUND UPGRADE / RETAINING WALL | CM,F&E | In-Progress | 6/20/2022 | 3/16/2023 |  | 44818 | 77076 | 75497 | DSF0001007755, DSF0001008179, DSF0001074727
27 | Q197 | P.S. 197 - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/26/2024 | DOER |  | DOER | 241770 | 0 | DSF0001033291
27 | Q197 | P.S. 197 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/22/2024 | DOES | 8/9/2024 | DOES | 65832 |  | DSF0001084372
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 7/3/2019 | 11/19/2019 | 1/13/2020 | 85659 | 126752 | 126752 | DSF0000903523, DSF0000903525, DSF0000949147
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 1/13/2020 | 6/12/2020 | 4/23/2021 | 425946 | 501088 | 406482 | DSF0000903523, DSF0000903525, DSF0000949147
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 7/22/2021 | 4/12/2023 |  | 9380598 | 9693486 | 3162496 | DSF0000903523, DSF0000903525, DSF0000949147
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 7/22/2021 | 4/12/2023 |  | 617231 | 1185826 | 1176030 | DSF0000903523, DSF0000903525, DSF0000949147
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/1/2022 | 4/4/2023 | 1/4/2023 | 4080 | 1412 | 1412 | DSF0001034651
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/4/2023 | 6/30/2023 | 3/15/2023 | 18360 | 5647 | 5647 | DSF0001034651
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/10/2023 | 5/4/2024 |  | 236640 | 210378 | 123040 | DSF0001034651
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/10/2023 | 5/4/2024 |  | 168996 | 164262 | 115707 | DSF0001034651
27 | Q198 | P.S. 333 - QUEENS | SCA IEH | PO18-ABATE/REPLACE APPROX 378 SQ FT OF 9'X9' FLOOR TILE IN ROOM 207 AND APPROX 360 SQ FT OF 9'X9' FL | Construction | Complete | 10/15/2024 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000073502
27 | Q198 | P.S. 333 - QUEENS | Fast Track Projects | SANDY NEW A/C CHILLERS | Construction | In-Progress | 7/1/2013 | FTK |  | FTK | 1608557 | 1608557 | DSF0000775970
27 | Q198 | P.S. 333 - QUEENS | Fast Track Projects | EMERGENCY PROTECTIVE MEASURES - HURRICANE SANDY | Construction | In-Progress | 10/31/2012 | FTK |  | FTK | 3429874 | 3192874 | SCA0000023483
27 | Q198 | P.S. 333 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 429000 | 0 | DSF0001113083
27 | Q198 | P.S. 333 - QUEENS | DOE - RESOA | FY21 RESO A MEDIA CENTER | Construction | In-Progress | 5/25/2022 | DOER |  | DOER | 80109 | 0 | DSF0001008186
27 | Q198 | P.S. 333 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001035344
27 | Q198 | P.S. 333 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/6/2024 | DOES | 9/13/2024 | DOES | 65832 | 12863 | DSF0001084680
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY / SIDEWALK REPAIR / WINDOWS | Scope | Complete | 3/15/2022 | 9/13/2022 | 7/22/2022 | 213666 | 204602 | 201812 | DSF0000949223, DSF0000949226, DSF0000949225, DSF0000949227, DSF0001024041, DSF0001035196
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY / SIDEWALK REPAIR / WINDOWS | Design | Complete | 7/28/2022 | 1/26/2023 | 1/12/2023 | 1057363 | 374354 | 373792 | DSF0000949223, DSF0000949226, DSF0000949225, DSF0000949227, DSF0001024041, DSF0001035196
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY / SIDEWALK REPAIR / WINDOWS | Construction | PNS | PNS | PNS | PNS | 22842132 | 22842132 | 100192 | DSF0000949223, DSF0000949226, DSF0000949225, DSF0000949227, DSF0001024041, DSF0001035196
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY / SIDEWALK REPAIR / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1577908 | 1577908 | 70085 | DSF0000949223, DSF0000949226, DSF0000949225, DSF0000949227, DSF0001024041, DSF0001035196
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 8/13/2020 | 1/19/2021 | 12/28/2020 | 82125 | 73674 | 73674 | DSF0000948952, DSF0000798328
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/31/2020 | 7/30/2021 | 7/6/2021 | 410625 | 305490 | 280572 | DSF0000948952, DSF0000798328
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 6/22/2022 | 6/20/2024 |  | 9239062 | 8543275 | 6532551 | DSF0000948952, DSF0000798328
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 6/22/2022 | 6/20/2024 |  | 574875 | 391041 | 374906 | DSF0000948952, DSF0000798328
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/23/2023 | 10/23/2023 | 9/25/2023 | 14789 | 15957 | 15957 | DSF0001083890
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/2/2023 | 3/1/2024 | 2/7/2024 | 66551 | 69738 | 53489 | DSF0001083890
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 7/22/2024 | 5/16/2025 |  | 857762 | 770210 | 7850 | DSF0001083890
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 7/22/2024 | 5/16/2025 |  | 158982 | 94997 | 15136 | DSF0001083890
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 1/30/2023 | 5/31/2023 | 5/10/2023 | 0 | 13495 | 13495 | DSF0001035972
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | In-Progress | 7/31/2024 | 12/17/2024 |  | 89986 | 76491 | 31714 | DSF0001035972
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 1319791 | 1319791 | 3367 | DSF0001035972
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 89986 | 89986 | 38648 | DSF0001035972
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035973
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 14 | 14 | 0 | DSF0001035973
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 209 | 209 | 0 | DSF0001035973
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 14 | 14 | 1119 | DSF0001035973
27 | Q202 | I.S. 202 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113087
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113088
27 | Q202 | I.S. 202 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/10/2023 | DOER |  | DOER | 347087 | 0 | DSF0001008193
27 | Q202 | I.S. 202 - QUEENS | DOE - RESOA | FY23 RESO A PHONE UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 249975 | 0 | DSF0001035971
27 | Q202 | I.S. 202 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/6/2024 | DOES | 8/13/2024 | DOES | 65832 | 16909 | DSF0001084819
27 | Q202 | I.S. 202 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/5/2024 | DOES |  | DOES | 592862 | 0 | DSF0001085756
27 | Q207 | P.S. 207 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/11/2023 | 11/27/2023 | 11/8/2023 | 37896 | 81690 | 81690 | DSF0001074898, DSF0001111817
27 | Q207 | P.S. 207 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 11/15/2023 | 4/18/2024 | 5/14/2024 | 188387 | 257175 | 175977 | DSF0001074898, DSF0001111817
27 | Q207 | P.S. 207 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 11/20/2024 | 8/11/2026 |  | 4143838 | 3784826 | 68026 | DSF0001074898, DSF0001111817
27 | Q207 | P.S. 207 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 11/20/2024 | 8/11/2026 |  | 273502 | 39105 | 39105 | DSF0001074898, DSF0001111817
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113653
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113653
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113653
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113653
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/1/2023 | 9/8/2023 | 6/28/2023 | 0 | 17477 | 17477 | DSF0001035978, DSF0001035979
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 7/5/2023 | 11/6/2023 | 9/26/2023 | 43819 | 62721 | 61686 | DSF0001035978, DSF0001035979
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 2/20/2024 | 12/15/2024 |  | 642676 | 520533 | 408651 | DSF0001035978, DSF0001035979
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 2/20/2024 | 12/15/2024 |  | 78964 | 97229 | 67576 | DSF0001035978, DSF0001035979
27 | Q207 | P.S. 207 - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | Complete | 9/15/2023 | DOER | 12/12/2023 | DOER | 126416 | 19702 | DSF0001034934
27 | Q207 | P.S. 207 - QUEENS | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | In-Progress | 8/23/2024 | DOER |  | DOER | 27605 | 0 | DSF0001034935
27 | Q207 | P.S. 207 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 234043 | 0 | DSF0001086474
27 | Q207 | P.S. 207 - QUEENS | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0 | DSF0001113092
27 | Q207 | P.S. 207 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/7/2024 | DOES | 10/18/2024 | DOES | 65832 | 14750 | DSF0001084682
27 | Q210 | I.S. 210 - QUEENS | DIIT - RESOA | FY15 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 5978 | 0 | DSF0000800369
27 | Q210 | I.S. 210 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 203539 | 0 | DSF0000488315
27 | Q210 | I.S. 210 - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 626196 | 0 | DSF0001035983
27 | Q210 | I.S. 210 - QUEENS | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001113096
27 | Q210 | I.S. 210 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/21/2024 | DOES | 11/1/2024 | DOES | 65832 | 10933 | DSF0001084821
27 | Q210 | I.S. 210 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/10/2024 | DOES |  | DOES | 755506 | 0 | DSF0001111854
27 | Q215 | P.S. 362 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/10/2024 | 11/7/2024 | 7/16/2024 | 4615 | 777 | 777 | DSF0001087538
27 | Q215 | P.S. 362 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/16/2024 | 1/13/2025 |  | 20768 | 20768 | 3109 | DSF0001087538
27 | Q215 | P.S. 362 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 267678 | 267678 | 1028 | DSF0001087538
27 | Q215 | P.S. 362 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 53877 | 53877 | 7248 | DSF0001087538
27 | Q223 | P.S. 223 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | Complete | 3/16/2022 | FTK | 12/23/2022 | FTK | 791269 | 737294 | DSF0001034168
27 | Q223 | P.S. 223 - QUEENS | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER | Construction | In-Progress | 3/25/2024 | FTK |  | FTK | 324975 | 69469 | DSF0001024382
27 | Q223 | Q075 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 6/4/2024 | DIIR | 80000 | 80000 | DSF0001035990
27 | Q223 | P.S. 223 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/6/2024 | DIIR | 11/4/2024 | DIIR | 300000 | 300000 | DSF0001035991
27 | Q223 | P.S. 223 - QUEENS | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 2/3/2023 | DOER | 6/24/2023 | DOER | 109982 | 33495 | DSF0001033295
27 | Q225 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 7/8/2022 | 11/23/2022 | 12/4/2023 | 113791 | 253408 | 253398 | DSF0001024398, DSF0001024399, DSF0001024400, DSF0001111872
27 | Q225 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 12/8/2023 | 5/10/2024 | 4/29/2024 | 568955 | 522684 | 397640 | DSF0001024398, DSF0001024399, DSF0001024400, DSF0001111872
27 | Q225 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | In-Progress | 9/30/2024 | 9/19/2026 |  | 12801488 | 11597740 | 56360 | DSF0001024398, DSF0001024399, DSF0001024400, DSF0001111872
27 | Q225 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | In-Progress | 9/30/2024 | 9/19/2026 |  | 796538 | 60095 | 60095 | DSF0001024398, DSF0001024399, DSF0001024400, DSF0001111872
27 | Q225 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/24/2023 | 9/25/2023 | 5/25/2023 | 3454 | 251 | 251 | DSF0001035040
27 | Q225 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 5/25/2023 | 11/22/2023 | 9/20/2023 | 15543 | 1006 | 1006 | DSF0001035040
27 | Q225 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 1/8/2024 | 11/2/2024 |  | 200331 | 182006 | 148436 | DSF0001035040
27 | Q225 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 1/8/2024 | 11/2/2024 |  | 144083 | 140502 | 101377 | DSF0001035040
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113655
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113655
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113655
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113655
27 | Q225 | I.S. 318 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION / CTF ROOM CONVERSION | Construction | In-Progress | 7/11/2024 | FTK |  | FTK | 644349 | 83149 | DSF0001083932, DSF0001083931
27 | Q225 | I.S. 318 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086482
27 | Q225 | I.S. 318 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113106
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0 | DSF0001113105
27 | Q225 | P.S. 317 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/17/2022 | DOES | 8/29/2023 | DOES | 217115 | 175397 | DSF0001034256
27 | Q225 | P.S. 317 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/29/2024 | DOES | 8/22/2024 | DOES | 65832 | 7426 | DSF0001084387
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | Scope | Complete | 2/14/2019 | 5/31/2019 | 3/14/2022 | 36801 | 43438 | 43438 | DSF0000912235
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | Design | Complete | 3/14/2022 | 9/13/2022 | 5/11/2022 | 184005 | 190368 | 176694 | DSF0000912235
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | Construction | Complete | 8/10/2022 | 11/2/2023 | 11/2/2023 | 4140113 | 4065791 | 3899840 | DSF0000912235
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | CM,F&E | Complete | 8/10/2022 | 11/2/2023 | 11/2/2023 | 492290 | 763711 | 740941 | DSF0000912235
27 | Q226 | I.S. 226 - QUEENS | SCA CIP | RTU REPLACEMENT / ROOFS | Scope | Complete | 9/22/2021 | 1/31/2022 | 5/10/2022 | 72216 | 55503 | 55503 | DSF0000998503, DSF0001024419
27 | Q226 | I.S. 226 - QUEENS | SCA CIP | RTU REPLACEMENT / ROOFS | Design | Complete | 6/27/2022 | 11/29/2022 | 4/13/2023 | 357504 | 271894 | 192383 | DSF0000998503, DSF0001024419
27 | Q226 | I.S. 226 - QUEENS | SCA CIP | RTU REPLACEMENT / ROOFS | Construction | In-Progress | 11/15/2024 | 2/7/2026 |  | 7734516 | 6903836 | 39836 | DSF0000998503, DSF0001024419
27 | Q226 | I.S. 226 - QUEENS | SCA CIP | RTU REPLACEMENT / ROOFS | CM,F&E | In-Progress | 11/15/2024 | 2/7/2026 |  | 532334 | 108690 | 107866 | DSF0000998503, DSF0001024419
27 | Q226 | I.S. 226 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING ROOMS: ROOMS:304A, 304E, 312A, 312E, 342A, 342E, | Construction | Complete | 6/5/2023 | IEH | 8/20/2024 | IEH | 0 | 0 | SCA0000072040
27 | Q226 | I.S. 226 - QUEENS | Fast Track Projects | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 8/30/2024 | FTK |  | FTK | 4368 | 4368 | DSF0001035995
27 | Q226 | Q233 SPED - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 242422 | 0 | DSF0000960166
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | DOE - RESOA | FY21 RESO A FITNESS ROOM UPGRADE | Construction | In-Progress | 4/5/2022 | DOER |  | DOER | 100677 | 0 | DSF0001008124
27 | Q226 | I.S. 226 - QUEENS | DOE - RESOA | RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2/5/2024 | DOER |  | DOER | 47283 | 0 | DSF0001008934
27 | Q226 | I.S. 226 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 200000 | 10616 | DSF0001086483
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113107
27 | Q226 | I.S. 226 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113108
27 | Q226 | I.S. 226 - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 12/9/2022 | DOES | 9/11/2023 | DOES | 719828 | 633217 | DSF0000960859
27 | Q226 | I.S. 226 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/31/2024 | DOES | 11/13/2024 | DOES | 65832 |  | DSF0001084824
27 | Q232 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | Scope | Complete | 4/10/2018 | 8/23/2018 | 8/21/2018 | 243681 | 220497 | 216686 | DSF0000881103, DSF0000888970, DSF0000881100, DSF0000881101, DSF0000891023
27 | Q232 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | Design | Complete | 9/19/2018 | 2/25/2019 | 5/7/2019 | 967549 | 758802 | 658727 | DSF0000881103, DSF0000888970, DSF0000881100, DSF0000881101, DSF0000891023
27 | Q232 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | Construction | In-Progress | 8/5/2019 | 8/3/2021 |  | 17497696 | 16681111 | 15426803 | DSF0000881103, DSF0000888970, DSF0000881100, DSF0000881101, DSF0000891023
27 | Q232 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/5/2019 | 8/3/2021 |  | 1230438 | 2085122 | 2061961 | DSF0000881103, DSF0000888970, DSF0000881100, DSF0000881101, DSF0000891023
27 | Q232 | P.S. 232 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 10/23/2024 | DIIR | 49821 | 49821 | DSF0001036002
27 | Q232 | P.S. 232 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/12/2024 | DIIR | 10/23/2024 | DIIR | 49817 | 49817 | DSF0001086485
27 | Q232 | P.S. 232 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001113111
27 | Q232 | P.S. 232 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/17/2024 | DOES | 11/13/2024 | DOES | 65832 |  | DSF0001084686
27 | Q253 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/21/2022 | 4/24/2023 | 1/6/2023 | 5000 | 986 | 986 | DSF0001034581
27 | Q253 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/6/2023 | 7/5/2023 | 3/15/2023 | 22500 | 3946 | 3946 | DSF0001034581
27 | Q253 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/10/2023 | 5/4/2024 |  | 290000 | 252346 | 141044 | DSF0001034581
27 | Q253 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/10/2023 | 5/4/2024 |  | 186668 | 168284 | 119608 | DSF0001034581
27 | Q253 | P.S. 253 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/5/2022 | DOES |  | DOES | 134504 | 0 | DSF0001009192
27 | Q254 | P.S. 254 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/5/2024 | 11/4/2024 | 7/16/2024 | 4124 | 575 | 575 | DSF0001087543
27 | Q254 | P.S. 254 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 7/16/2024 | 1/13/2025 |  | 18559 | 18559 | 2301 | DSF0001087543
27 | Q254 | P.S. 254 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 239205 | 239205 | 198 | DSF0001087543
27 | Q254 | P.S. 254 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 48599 | 48599 | 5322 | DSF0001087543
27 | Q254 | P.S. 254 - QUEENS | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 959775 | 0 | DSF0001008192
27 | Q254 | P.S. 254 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113121
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS ROOFS / DCAS FIRE ALARM PANEL | Scope | Complete | 10/12/2023 | 3/12/2024 | 3/1/2024 | 128835 | 183697 | 183333 | DSF0001087156, DSF0001111920, DSF0001112092
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS ROOFS / DCAS FIRE ALARM PANEL | Design | Complete | 3/1/2024 | 10/1/2024 | 5/7/2024 | 638381 | 871469 | 437752 | DSF0001087156, DSF0001111920, DSF0001112092
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS ROOFS / DCAS FIRE ALARM PANEL | Construction | In-Progress | 10/2/2024 | 10/1/2026 |  | 13862284 | 12304558 | 558 | DSF0001087156, DSF0001111920, DSF0001112092
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS ROOFS / DCAS FIRE ALARM PANEL | CM,F&E | In-Progress | 10/2/2024 | 10/1/2026 |  | 945310 | 70744 | 70744 | DSF0001087156, DSF0001111920, DSF0001112092
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 4/1/2022 | 8/1/2022 | 5/3/2022 | 2480 | 1463 | 1463 | DSF0001034374
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 5/3/2022 | 10/27/2022 | 7/18/2022 | 11160 | 5852 | 5852 | DSF0001034374
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | In-Progress | 2/27/2023 | 12/23/2023 |  | 143840 | 141076 | 2868 | DSF0001034374
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | In-Progress | 2/27/2023 | 12/23/2023 |  | 128778 | 128294 | 94052 | DSF0001034374
27 | Q273 | P.S. 273 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | Complete | 10/18/2023 | 3/18/2024 | 3/4/2024 | 64756 | 142966 | 142966 | DSF0001087153
27 | Q273 | P.S. 273 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | Complete | 3/4/2024 | 8/2/2024 | 5/14/2024 | 323780 | 721505 | 374541 | DSF0001087153
27 | Q273 | P.S. 273 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Construction | In-Progress | 10/7/2024 | 9/26/2026 |  | 7285050 | 6540356 | 0 | DSF0001087153
27 | Q273 | P.S. 273 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | CM,F&E | In-Progress | 10/7/2024 | 9/26/2026 |  | 453292 | 94130 | 90775 | DSF0001087153
27 | Q273 | P.S. 273 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 11/30/2021 | FTK |  | FTK | 196272 | 183049 | DSF0000960691
27 | Q316 | QUEENS EXPLORERS ELEMENTARY SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/29/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001086511
27 | Q316 | QUEENS EXPLORERS ELEMENTARY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113131
27 | Q335 | P.S. 377 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/29/2024 | DIIR |  | DIIR | 202000 | 202000 | DSF0001086512
27 | Q335 | P.S. 377 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113134
27 | Q343 | P.S. 47 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113138
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113141
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001113141
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001113141
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001113141
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113663
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113663
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113663
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113663
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086515
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086515
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086515
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086515
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087078
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087078
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087078
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087078
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087079
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087079
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087079
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087079
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 0 | DSF0001008123
27 | Q400 | VOYAGES PREP - SOUTH QUEENS | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 0 | DSF0001113143
27 | Q400 | NEW VISIONS CHARTER HIGH SCHOOL FOR ADVANCED MATH AND SCIENCE IV | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 0 | DSF0001113144
27 | Q400 | AUGUST MARTIN HS - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001033326
27 | Q400 | ALTERNATE LEARNING CENTER - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 115000 | 0 | DSF0001113142
27 | Q400 | VOYAGES PREP - SOUTH QUEENS | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 5/5/2023 | DOER |  | DOER | 95143 | 0 | DSF0001008134
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/25/2024 | DOER |  | DOER | 123334 | 0 | DSF0001036035
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1776919 | 0 | DSF0001085611
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0 | DSF0001086516
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 310979 | 0 | DSF0001111929
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - RESOA | FY25 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 238000 | 0 | DSF0001113146
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - Skilled Trades | SEWAGE EJECTOR PUMP REPLACEMENT | Construction | In-Progress | 3/4/2021 | DOES |  | DOES | 77011 | 0 | DSF0000998663
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/3/2024 | DOES | 10/11/2024 | DOES | 65832 | 9494 | DSF0001084996
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 8/8/2023 | DOES |  | DOES | 311101 | 0 | DSF0001085816
27 | Q401 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | Scope | Complete | 5/22/2020 | 11/14/2022 | 11/9/2022 | 439294 | 1089709 | 1089400 | DSF0000949713, DSF0001007719, DSF0001008845
27 | Q401 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | Design | Complete | 11/18/2022 | 5/18/2023 | 4/25/2023 | 2193674 | 2807526 | 2590078 | DSF0000949713, DSF0001007719, DSF0001008845
27 | Q401 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | Construction | In-Progress | 2/5/2024 | 1/19/2027 |  | 49116028 | 44363013 | 9764494 | DSF0000949713, DSF0001007719, DSF0001008845
27 | Q401 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | CM,F&E | In-Progress | 2/5/2024 | 1/19/2027 |  | 3096007 | 526292 | 517485 | DSF0000949713, DSF0001007719, DSF0001008845
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | SEA WALL / BULKHEAD REPAIR | Scope | Complete | 4/16/2019 | 7/16/2019 | 10/10/2019 | 166282 | 176449 | 174871 | DSF0000904102
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | SEA WALL / BULKHEAD REPAIR | Design | In-Progress | 11/20/2019 | 4/8/2020 |  | 775983 | 917312 | 458539 | DSF0000904102
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | SEA WALL / BULKHEAD REPAIR | Construction | PNS | PNS | PNS | PNS | 12304878 | 12304878 | 39988 | DSF0000904102
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | SEA WALL / BULKHEAD REPAIR | CM,F&E | PNS | PNS | PNS | PNS | 1219402 | 1219402 | 50069 | DSF0000904102
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 4/11/2022 | 8/24/2022 | 3/15/2023 | 39968 | 96792 | 77384 | DSF0001025080, DSF0001075884
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 3/16/2023 | 8/16/2023 | 5/12/2023 | 199839 | 227987 | 216686 | DSF0001025080, DSF0001075884
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 8/7/2023 | 1/17/2025 |  | 4496384 | 4107021 | 1066596 | DSF0001025080, DSF0001075884
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 8/7/2023 | 1/17/2025 |  | 279775 | 207094 | 148549 | DSF0001025080, DSF0001075884
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP RESOA | FY20 RESO A WEIGHT ROOM | Scope | Complete | 5/7/2021 | 9/8/2021 | 9/18/2023 | 0 | 77442 | 77442 | DSF0000913450
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP RESOA | FY20 RESO A WEIGHT ROOM | Design | Complete | 9/19/2023 | 2/7/2024 | 4/9/2024 | 156382 | 115806 | 94800 | DSF0000913450
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP RESOA | FY20 RESO A WEIGHT ROOM | Construction | In-Progress | 11/6/2024 | 10/1/2025 |  | 2293603 | 1986427 | 18887 | DSF0000913450
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP RESOA | FY20 RESO A WEIGHT ROOM | CM,F&E | In-Progress | 11/6/2024 | 10/1/2025 |  | 156382 | 72563 | 70503 | DSF0000913450
27 | Q410 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000012009
27 | Q410 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 0 | 0 | 0 | DSF0000012009
27 | Q410 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 9/7/2006 | 4/15/2007 |  | 0 | 0 | 0 | DSF0000012009
27 | Q410 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 9/7/2006 | 4/15/2007 |  | 0 | 0 | 0 | DSF0000012009
27 | Q410 | ROCKAWAY PARK HS FOR ENVIRONMENTAL SUST - Q | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LAB | F&E | Complete | 4/30/2024 |  | 5/28/2024 | 50000 | 50000 | 46965 | DSF0001033313
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/18/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001033883
27 | Q410 | ROCKAWAY PARK HS FOR ENVIRONMENTAL SUST - Q | DIIT - RESOA | FY23 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001036041
27 | Q410 | Q256 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001086520
27 | Q410 | ROCKAWAY COLLEGIATE HIGH SCHOOL - Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 50000 | 46388 | DSF0001086522
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/18/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001086523
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113151
27 | Q410 | ROCKAWAY PARK HS FOR ENVIRONMENTAL SUST - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113153
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/9/2017 | DOER |  | DOER | 44426 | 0 | DSF0000843948
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 3/14/2022 | DOER |  | DOER | 667207 | 0 | DSF0000913452
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 5/5/2022 | DOER |  | DOER | 615131 | 0 | DSF0000913453
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 200000 | 0 | DSF0001086524
27 | Q410 | ROCKAWAY PARK HS FOR ENVIRONMENTAL SUST - Q | DOE - RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 49612 | 0 | DSF0001086521
27 | Q410 | ROCKAWAY COLLEGIATE HIGH SCHOOL - Q | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113154
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/2/2024 | DOES |  | DOES | 635674 | 0 | DSF0000960861
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/26/2024 | DOES | 7/5/2024 | DOES | 65832 | 19182 | DSF0001084998
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - Skilled Trades | ELEVATOR PISTON REPLACEMENT | Construction | In-Progress | 3/20/2024 | DOES |  | DOES | 163853 | 0 | DSF0001103786
27 | Q411 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | Scope | Complete | 6/18/2019 | 10/18/2019 | 9/13/2019 | 43620 | 82381 | 82381 | DSF0000912277
27 | Q411 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | Design | Complete | 11/4/2019 | 4/8/2020 | 11/4/2021 | 218100 | 551757 | 501004 | DSF0000912277
27 | Q411 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | Construction | In-Progress | 2/28/2022 | 8/21/2023 |  | 4907250 | 5053226 | 4730553 | DSF0000912277
27 | Q411 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | CM,F&E | In-Progress | 2/28/2022 | 8/21/2023 |  | 305340 | 983892 | 982881 | DSF0000912277
27 | Q438 | Q256 SPED - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/18/2024 | IEH | 7/19/2024 | IEH | 0 | 0 | SCA0000073076
27 | Q438 | Q256 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113158
27 | Q439 | CURIOUS YOUNG LEARNERS PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/26/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085521
27 | Q464 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/7/2024 | IEH | 8/13/2024 | IEH | 0 | 0 | SCA0000073255
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | Scope | Complete | 5/21/2021 | 8/20/2021 | 7/20/2021 | 25550 | 127205 | 107592 | DSF0000961034
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | Design | Complete | 8/4/2021 | 12/21/2021 | 11/22/2021 | 127750 | 208983 | 193296 | DSF0000961034
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | Construction | In-Progress | 7/29/2022 | 1/19/2024 |  | 2874375 | 3082872 | 2944267 | DSF0000961034
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | CM,F&E | In-Progress | 7/29/2022 | 1/19/2024 |  | 178850 | 174945 | 174945 | DSF0000961034
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | SWIMMING POOL / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/5/2021 | 4/11/2024 | 5/8/2024 | 113498 | 103590 | 103590 | DSF0000960879, DSF0001104185
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | SWIMMING POOL / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 5/8/2024 | 10/9/2024 | 5/15/2024 | 567490 | 310943 | 288488 | DSF0000960879, DSF0001104185
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | SWIMMING POOL / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 12768530 | 12768530 | 123237 | DSF0000960879, DSF0001104185
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | SWIMMING POOL / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 794486 | 794486 | 80645 | DSF0000960879, DSF0001104185
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113168
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001113168
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 220000 | 220000 | 0 | DSF0001113168
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001113168
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113170
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 450000 | 450000 | 0 | DSF0001113170
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 6600000 | 6600000 | 0 | DSF0001113170
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 450000 | 450000 | 0 | DSF0001113170
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113665
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113665
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113665
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113665
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113666
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113666
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113666
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113666
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Scope | Complete | 8/1/2023 | 12/4/2023 | 11/7/2023 | 0 | 4291 | 4291 | DSF0001036061
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Design | Complete | 11/7/2023 | 4/11/2024 | 4/24/2024 | 30000 | 17164 | 17164 | DSF0001036061
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 11121 | DSF0001036061
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 6303 | DSF0001036061
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | RESO A RECORDING STUDIO | Scope | In-Progress | 6/29/2023 | 10/30/2023 |  | 0 | 0 | 17122 | DSF0001083966
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | RESO A RECORDING STUDIO | Design | PNS | PNS | PNS | PNS | 13263 | 12801 | 12801 | DSF0001083966
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | RESO A RECORDING STUDIO | Construction | PNS | PNS | PNS | PNS | 194525 | 194525 | 30545 | DSF0001083966
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | RESO A RECORDING STUDIO | CM,F&E | PNS | PNS | PNS | PNS | 13263 | 13263 | 7575 | DSF0001083966
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/4/2023 | 4/5/2024 | 8/21/2024 | 0 | 15321 | 15321 | DSF0001086543
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 8/23/2024 | 1/29/2025 |  | 44397 | 52607 | 19788 | DSF0001086543
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 651160 | 651160 | 10681 | DSF0001086543
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 44397 | 44397 | 30604 | DSF0001086543
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 7/16/2024 | 10/15/2024 | 8/23/2024 | 0 | 0 | 0 | DSF0001087086
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | In-Progress | 8/30/2024 | 12/30/2024 |  | 603 | 603 | 0 | DSF0001087086
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 8840 | 8840 | 1605 | DSF0001087086
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 603 | 603 | 5956 | DSF0001087086
27 | Q465 | M.S. 282 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM CONVERSION / FY20 RESO A ROBOTICS LAB | Scope | Complete | 12/13/2019 | 3/15/2022 | 3/16/2022 | 0 | 51696 | 51696 | DSF0000913457, DSF0000913458
27 | Q465 | M.S. 282 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM CONVERSION / FY20 RESO A ROBOTICS LAB | Design | Complete | 3/16/2022 | 8/15/2022 | 4/4/2023 | 187997 | 141199 | 130862 | DSF0000913457, DSF0000913458
27 | Q465 | M.S. 282 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM CONVERSION / FY20 RESO A ROBOTICS LAB | Construction | In-Progress | 11/24/2023 | 10/18/2024 |  | 2757282 | 2889751 | 1121125 | DSF0000913457, DSF0000913458
27 | Q465 | M.S. 282 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM CONVERSION / FY20 RESO A ROBOTICS LAB | CM,F&E | In-Progress | 11/24/2023 | 10/18/2024 |  | 204959 | 179721 | 122481 | DSF0000913457, DSF0000913458
27 | Q465 | M.S. 282 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 3/21/2022 | FTK |  | FTK | 209979 | 114874 | DSF0000961139
27 | Q465 | M.S. 282 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/14/2024 | DIIR | 8/23/2024 | DIIR | 250000 | 93400 | DSF0001033308
27 | Q465 | M.S. 282 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 9/17/2024 | DIIR |  | DIIR | 254000 | 0 | DSF0001036060
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 180000 | 0 | DSF0001113169
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 9/20/2019 | DOER |  | DOER | 274193 | 0 | DSF0000912666
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | Complete | 8/14/2021 | DOER | 3/28/2022 | DOER | 81607 | 80509 | DSF0001008183
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001033309
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/5/2023 | DOER |  | DOER | 1075538 | 0 | DSF0001033882
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | Complete | 8/17/2023 | DOER | 6/19/2024 | DOER | 163886 |  | DSF0001036059
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0 | DSF0001087163
27 | Q465 | M.S. 282 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 3/31/2023 | DOES |  | DOES | 62936 | 0 | DSF0000866133
27 | Q465 | M.S. 282 - QUEENS | DOE - Skilled Trades | OUTDOOR CLASSROOM | Construction | In-Progress | 5/3/2024 | DOES |  | DOES | 269024 | 0 | DSF0001034902
27 | Q465 | M.S. 282 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/26/2024 | DOES | 7/5/2024 | DOES | 65832 | 9102 | DSF0001085011
27 | Q468 | CURIOUS YOUNG LEARNERS PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/9/2023 | DOES | 8/15/2024 | DOES | 65832 |  | DSF0001085526
27 | Q473 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 7/17/2024 | IEH |  | IEH | 0 | 0 | SCA0000073143
27 | Q474 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 9/13/2024 | IEH | 9/27/2024 | IEH | 0 | 0 | SCA0000073369
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | Scope | Complete | 11/1/2019 | 4/26/2022 | 4/26/2022 | 244246 | 224826 | 224018 | DSF0000914309, DSF0000950068, DSF0001008647, DSF0000999054, DSF0001025518
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | Design | Complete | 4/27/2022 | 7/27/2022 | 5/6/2022 | 1216979 | 1422478 | 1303185 | DSF0000914309, DSF0000950068, DSF0001008647, DSF0000999054, DSF0001025518
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | Construction | In-Progress | 7/11/2022 | 7/9/2024 |  | 27014556 | 24887055 | 16596276 | DSF0000914309, DSF0000950068, DSF0001008647, DSF0000999054, DSF0001025518
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | CM,F&E | In-Progress | 7/11/2022 | 7/9/2024 |  | 1741576 | 1039854 | 1027331 | DSF0000914309, DSF0000950068, DSF0001008647, DSF0000999054, DSF0001025518
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913039
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 9449 | 9449 | 0 | DSF0000913039
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 138589 | 138589 | 0 | DSF0000913039
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 9449 | 9449 | 0 | DSF0000913039
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A CULINARY KITCHEN | Scope | Complete | 12/7/2023 | 4/24/2024 | 11/6/2024 | 0 | 7474 | 1709 | DSF0001111753
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A CULINARY KITCHEN | Design | In-Progress | 11/13/2024 | 5/19/2025 |  | 351396 | 343922 | 6837 | DSF0001111753
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 5153815 | 5153815 | 0 | DSF0001111753
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 351396 | 351396 | 5314 | DSF0001111753
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A SCIENCE LAB UPGRADE | Scope | Complete | 12/7/2023 | 3/26/2024 | 11/4/2024 | 0 | 13706 | 990 | DSF0001111752
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 11/13/2024 | 4/17/2025 |  | 35604 | 69390 | 3961 | DSF0001111752
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 522185 | 522185 | 0 | DSF0001111752
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 35604 | 35604 | 4157 | DSF0001111752
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 12/7/2023 | 4/4/2024 | 11/5/2024 | 0 | 15321 | 765 | DSF0001086548
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 11/13/2024 | 4/17/2025 |  | 44697 | 60539 | 3059 | DSF0001086548
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 655557 | 655557 | 0 | DSF0001086548
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 44697 | 44697 | 6222 | DSF0001086548
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | In-Progress | 4/29/2024 | 7/31/2024 |  | 0 | 0 | 0 | DSF0001087088
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 303 | 303 | 0 | DSF0001087088
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 4443 | 4443 | 0 | DSF0001087088
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 303 | 303 | 253 | DSF0001087088
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | In-Progress | 12/11/2024 | 3/14/2025 |  | 0 | 0 | 0 | DSF0001113823
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113823
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113823
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113823
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Scope | In-Progress | 12/11/2024 | 3/14/2025 |  | 0 | 0 | 0 | DSF0001113822
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113822
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113822
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113822
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Scope | Complete | 3/28/2022 | 12/8/2022 | 11/14/2022 | 0 | 20659 | 15689 | DSF0001033930, DSF0001033931
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Design | Complete | 11/18/2022 | 3/23/2023 | 1/13/2023 | 55492 | 156730 | 91707 | DSF0001033930, DSF0001033931
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/10/2023 | 5/4/2024 |  | 813882 | 627848 | 214801 | DSF0001033930, DSF0001033931
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 7/10/2023 | 5/4/2024 |  | 142520 | 181345 | 96287 | DSF0001033930, DSF0001033931
27 | Q475 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000011862
27 | Q475 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 0 | 0 | 0 | DSF0000011862
27 | Q475 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 8/12/2005 | 10/10/2006 |  | 0 | 0 | 0 | DSF0000011862
27 | Q475 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 8/12/2005 | 10/10/2006 |  | 0 | 0 | 0 | DSF0000011862
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA IEH | PO18-77/27Q475/TEST WALL PLASTER ROOM 502 IF POSITIVE ABATE AND REPAIR | Construction | In-Progress | 5/22/2024 | IEH |  | IEH | 0 | 0 | SCA0000073023
27 | Q475 | RICHMOND HILL HS - QUEENS | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | Complete | 1/30/2023 | DOER | 12/18/2023 | DOER | 265042 | 72057 | DSF0001033323
27 | Q475 | RICHMOND HILL HS - QUEENS | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/3/2023 | DOER |  | DOER | 407527 | 0 | DSF0001033929
27 | Q475 | RICHMOND HILL HS - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 419283 | 0 | DSF0001111751
27 | Q475 | RICHMOND HILL HS - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 306649 | 0 | DSF0001111750
27 | Q475 | RICHMOND HILL HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/24/2024 | DOES | 10/7/2024 | DOES | 65832 | 16725 | DSF0001085013
27 | Q477 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 3/3/2021 | 6/2/2021 | 6/3/2021 | 8740 | 18719 | 18719 | DSF0000960731
27 | Q477 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | Complete | 6/14/2021 | 10/28/2021 | 12/2/2021 | 39330 | 73278 | 61977 | DSF0000960731
27 | Q477 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | Construction | Complete | 4/11/2022 | 1/5/2023 | 12/28/2023 | 506920 | 467657 | 390918 | DSF0000960731
27 | Q477 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | CM,F&E | Complete | 4/11/2022 | 1/5/2023 | 12/28/2023 | 93955 | 84960 | 83912 | DSF0000960731
27 | Q477 | CURIOUS YOUNG LEARNERS PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/29/2024 | DOES | 6/18/2024 | DOES | 50832 |  | DSF0001085527
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033932
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033932
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033932
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033932
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087090
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087090
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087090
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087090
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Scope | Complete | 11/27/2023 | 3/29/2024 | 10/16/2024 | 0 | 40109 | 40109 | DSF0001086550
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 19891 | 5830 | DSF0001086550
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 3844783 | 0 | DSF0001086550
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 262144 | 5152 | DSF0001086550
27 | Q480 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000012011
27 | Q480 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 0 | 0 | 0 | DSF0000012011
27 | Q480 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 7/15/2007 | 5/30/2008 |  | 0 | 0 | 0 | DSF0000012011
27 | Q480 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 7/15/2007 | 5/30/2008 |  | 0 | 0 | 0 | DSF0000012011
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - RESOA | FY18 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0000866436
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | Complete | 4/30/2024 | DOER | 5/21/2024 | DOER | 484515 | 9233 | DSF0001033933
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 274354 | 0 | DSF0001035244
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035245
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - Skilled Trades | REPLACE SWIMMING POOL RAW WATER TANK | Construction | In-Progress | 8/27/2019 | DOES |  | DOES | 96475 | 0 | DSF0000904449
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/16/2024 | DOES | 8/15/2024 | DOES | 65832 | 8740 | DSF0001085014
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087089
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087089
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087089
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087089
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Scope | In-Progress | 11/27/2023 | 2/28/2024 |  | 0 | 7272 | 1507 | DSF0001086549
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 6000 | 2810 | 2810 | DSF0001086549
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 903 | DSF0001086549
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6221 | 6221 | DSF0001086549
27 | Q486 | CURIOUS YOUNG LEARNERS PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/8/2024 | DOES | 11/1/2024 | DOES | 50832 | 189 | DSF0001085529
27 | Q509 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | Scope | Complete | 6/9/2022 | 10/19/2022 | 10/19/2022 | 234660 | 227129 | 227129 | DSF0000889273, DSF0000889273
27 | Q509 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | Design | Complete | 10/19/2022 | 3/23/2023 | 4/10/2023 | 1055970 | 594384 | 439006 | DSF0000889273, DSF0000889273
27 | Q509 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | Construction | In-Progress | 7/12/2023 | 9/3/2025 |  | 13316955 | 12188450 | 7977696 | DSF0000889273, DSF0000889273
27 | Q509 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | CM,F&E | In-Progress | 7/12/2023 | 9/3/2025 |  | 1877280 | 1122375 | 232155 | DSF0000889273, DSF0000889273
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 1/23/2024 | 6/26/2024 | 6/26/2024 | 2025546 | 1463448 | 1431613 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | In-Progress | 6/27/2024 | 2/24/2025 |  | 8102185 | 8102185 | 990192 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 111911426 | 111911426 | 699337 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 14685210 | 14685210 | 735853 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 3/26/2024 | 3/26/2024 | 3/26/2024 | 68971 | 8098 | 8098 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 3/27/2024 | 6/26/2024 | 12/2/2024 | 321867 | 266408 | 226064 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 5103887 | 5103887 | 402827 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 505791 | 505791 | 150675 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 5/16/2024 | 5/16/2024 | 5/16/2024 | 43889 | 3721 | 3721 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Design | In-Progress | 5/17/2024 | 8/30/2024 |  | 204817 | 204817 | 14883 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 3247819 | 3247819 | 31054 | DSF0000798206
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 321856 | 321856 | 44248 | DSF0000798206
27 | Q593 | P.S. 47 - QUEENS | SCA CIP | PATH OF TRAVEL | Scope | Complete | 1/3/2024 | 4/4/2024 | 3/20/2024 | 2918 | 20992 | 840 | DSF0000911857
27 | Q593 | P.S. 47 - QUEENS | SCA CIP | PATH OF TRAVEL | Design | PNS | PNS | PNS | PNS | 13132 | 13132 | 3360 | DSF0000911857
27 | Q593 | P.S. 47 - QUEENS | SCA CIP | PATH OF TRAVEL | Construction | PNS | PNS | PNS | PNS | 169261 | 169261 | 0 | DSF0000911857
27 | Q593 | P.S. 47 - QUEENS | SCA CIP | PATH OF TRAVEL | CM,F&E | PNS | PNS | PNS | PNS | 31372 | 31372 | 1984 | DSF0000911857
27 | Q593 | P.S. 317 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113182
27 | Q593 | P.S. 47 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND YARD RENOVATION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001035992
27 | Q593 | P.S. 47 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/17/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085530
27 | Q593 | P.S. @ 140 BEACH 112 STREET - QUEENS | DOE Managed PRE-K | PHASE I SWING SPACE WORK | Construction | In-Progress | 5/8/2020 | DOEP |  | DOEP | 3000000 | 0 | DSF0000911857
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP | ROOFS / WINDOWS / PARAPETS | Scope | Complete | 12/21/2023 | 5/8/2024 | 9/3/2024 | 55627 | 75065 | 75002 | DSF0001076701, DSF0001113758, DSF0001113757
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP | ROOFS / WINDOWS / PARAPETS | Design | In-Progress | 9/17/2024 | 2/21/2025 |  | 259937 | 259937 | 92772 | DSF0001076701, DSF0001113758, DSF0001113757
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP | ROOFS / WINDOWS / PARAPETS | Construction | PNS | PNS | PNS | PNS | 5257119 | 5257119 | 280 | DSF0001076701, DSF0001113758, DSF0001113757
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP | ROOFS / WINDOWS / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 530428 | 530428 | 14375 | DSF0001076701, DSF0001113758, DSF0001113757
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/27/2019 | 6/27/2019 | 5/31/2019 | 0 | 14912 | 14912 | DSF0000890934
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 6/6/2019 | 11/6/2019 | 5/15/2020 | 41805 | 79233 | 79233 | DSF0000890934
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2/8/2022 | 11/4/2022 | 10/31/2023 | 613140 | 479480 | 421400 | DSF0000890934
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 2/8/2022 | 11/4/2022 | 10/31/2023 | 41805 | 59009 | 57474 | DSF0000890934
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | Complete | 7/31/2023 | DOER | 9/18/2023 | DOER | 179136 |  | DSF0001008136
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/19/2024 | DOES |  | DOES | 469072 | 0 | DSF0001085762
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/24/2020 | 10/23/2020 | 9/23/2020 | 2400 | 3822 | 3822 | DSF0000960777
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/23/2020 | 3/19/2021 | 5/5/2021 | 10800 | 15287 | 15287 | DSF0000960777
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/20/2022 | 3/15/2023 |  | 139200 | 127893 | 111757 | DSF0000960777
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/20/2022 | 3/15/2023 |  | 177728 | 183085 | 116442 | DSF0000960777
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/8/2024 | IEH | 8/16/2024 | IEH | 0 | 0 | SCA0000073264
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1135968 | 0 | DSF0001008139
27 | Q816 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | Scope | Complete | 5/8/2018 | 8/7/2018 | 5/8/2018 | 109140 | 2097 | 2097 | DSF0000843866
27 | Q816 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | Design | Complete | 5/9/2018 | 9/24/2018 | 5/9/2018 | 436558 | 89885 | 69557 | DSF0000843866
27 | Q816 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | Construction | Complete | 8/16/2021 | 2/6/2023 | 6/18/2024 | 8185466 | 7484285 | 7008020 | DSF0000843866
27 | Q816 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | CM,F&E | Complete | 8/16/2021 | 2/6/2023 | 6/18/2024 | 509318 | 221747 | 216332 | DSF0000843866
27 | Q816 | Q256 SPED - QUEENS | Fast Track Projects | EMERGENCY PROTECTIVE MEASURES - HURRICANE SANDY | Construction | In-Progress | 10/31/2012 | FTK |  | FTK | 3425235 | 3425235 | SCA0000023477
27 | Q884 | P.S. 65 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001033262
27 | Q884 | P.S. 65 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001036090
27 | Q884 | P.S. 65 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001086587
27 | Q884 | P.S. 65 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113203
27 | Q907 | P.S. 43 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/7/2024 | IEH | 8/14/2024 | IEH | 0 | 0 | SCA0000073253
27 | QAAT | CHALLENGE PREP CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADES | Purch & Install | In-Progress | 9/1/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0001008178
27 | QAAT | CHALLENGE PREP CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 500000 | 261208 | DSF0001086590
27 | QAAT | CHALLENGE PREP CHARTER SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001113205
27 | QAAT | CHALLENGE PREP CHARTER SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113206
27 | QMAD | PENINSULA PREPARATORY ACADEMY CHARTER SCHOOL - QUEENS | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001033837
27 | QMAD | PENINSULA PREPARATORY ACADEMY CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0 | DSF0001033838
28 | Q003 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2/14/2020 | 6/30/2020 | 3/9/2021 | 50630 | 80441 | 80441 | DSF0000945992, DSF0000994798, DSF0000994799
28 | Q003 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Design | Complete | 4/6/2021 | 9/3/2021 | 10/21/2021 | 253151 | 498494 | 498494 | DSF0000945992, DSF0000994798, DSF0000994799
28 | Q003 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 4/14/2022 | 10/5/2023 |  | 5695875 | 5105504 | 4989642 | DSF0000945992, DSF0000994798, DSF0000994799
28 | Q003 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 4/14/2022 | 10/5/2023 |  | 354411 | 775628 | 773088 | DSF0000945992, DSF0000994798, DSF0000994799
28 | Q003 | P.S. 303 - QUEENS | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 336000 | 336000 | 0 | DSF0001112923
28 | Q003 | P.S. 303 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 351039 | 0 | DSF0001033898
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/22/2023 | 11/7/2023 | 12/5/2023 | 186518 | 240803 | 240428 | DSF0001071341, DSF0001099048, DSF0001099052, DSF0001099053
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/2/2024 | 6/3/2024 | 10/31/2024 | 870415 | 414670 | 385869 | DSF0001071341, DSF0001099048, DSF0001099052, DSF0001099053
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 13802293 | 13802293 | 13484 | DSF0001071341, DSF0001099048, DSF0001099052, DSF0001099053
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1367795 | 1367795 | 61650 | DSF0001071341, DSF0001099048, DSF0001099052, DSF0001099053
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS FIRE ALARM / DCAS ELECTRICAL UPGRADE / DCAS LIGHTING UPGRADE | Scope | Complete | 10/5/2023 | 3/5/2024 | 4/8/2024 | 399157 | 223263 | 223263 | DSF0001086893, DSF0001099046, DSF0001112238, DSF0001113917
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS FIRE ALARM / DCAS ELECTRICAL UPGRADE / DCAS LIGHTING UPGRADE | Design | In-Progress | 5/23/2024 | 12/19/2024 |  | 1952546 | 1952546 | 385197 | DSF0001086893, DSF0001099046, DSF0001112238, DSF0001113917
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS FIRE ALARM / DCAS ELECTRICAL UPGRADE / DCAS LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | 39910861 | 39910861 | 2176 | DSF0001086893, DSF0001099046, DSF0001112238, DSF0001113917
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS FIRE ALARM / DCAS ELECTRICAL UPGRADE / DCAS LIGHTING UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 2837344 | 2837344 | 102341 | DSF0001086893, DSF0001099046, DSF0001112238, DSF0001113917
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112928
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001112928
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001112928
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001112928
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113624
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113624
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113624
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113624
28 | Q008 | THE EMERSON SCHOOL - QUEENS | Fast Track Projects | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 4/11/2024 | FTK |  | FTK | 199957 | 70338 | DSF0001086343
28 | Q008 | YORK EARLY COLLEGE ACADEMY - Q | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 105000 | 0 | DSF0000889915
28 | Q008 | J.H.S. 8 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 10/10/2024 | DIIR | 12/9/2024 | DIIR | 224206 | 224206 | DSF0001035794
28 | Q008 | J.H.S. 8 - QUEENS | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1044293 | 0 | DSF0000890847
28 | Q008 | J.H.S. 8 - QUEENS | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 205000 | 0 | DSF0001035793
28 | Q008 | J.H.S. 8 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0 | DSF0001112927
28 | Q008 | J.H.S. 8 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/7/2023 | DOES | 6/14/2023 | DOES | 544611 | 537285 | DSF0001035106
28 | Q008 | J.H.S. 8 - QUEENS | DOE - Skilled Trades | DEWATERING SYSTEM PUMP REPAIRS | Construction | In-Progress | 3/19/2024 | DOES |  | DOES | 226743 | 0 | DSF0001071340
28 | Q008 | J.H.S. 8 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/24/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084797
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 7/9/2024 | 11/7/2024 | 10/2/2024 | 0 | 30617 | 30617 | DSF0001086356
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 10/2/2024 | 2/21/2025 |  | 44519 | 44519 | 40909 | DSF0001086356
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 652938 | 652938 | 0 | DSF0001086356
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 44519 | 44519 | 14829 | DSF0001086356
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 12/8/2023 | 4/9/2024 | 6/24/2024 | 0 | 13449 | 13449 | DSF0001086357
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 7/8/2024 | 12/9/2024 |  | 30000 | 40045 | 24876 | DSF0001086357
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001086357
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 39960 | 39960 | DSF0001086357
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | In-Progress | 9/11/2024 | 12/12/2024 |  | 0 | 0 | 470 | DSF0001087052
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 482 | 482 | 1881 | DSF0001087052
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 7062 | 7062 | 0 | DSF0001087052
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 482 | 482 | 1179 | DSF0001087052
28 | Q030 | P.S. 354 - QUEENS | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 10/31/2024 | FTK |  | FTK | 18455 | 11745 | DSF0001087492
28 | Q030 | P.S. 354 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001112946
28 | Q030 | P.S. 30 - QUEENS | DOE - RESOA | FY07 RESO A AIR CONDITIONING RETROF | Construction | PNS | PNS | PNS | PNS | DOER | 228583 | 0 | DSF0000488301
28 | Q030 | P.S. 354 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001112945
28 | Q030 | P.S. 354 - QUEENS | DOE - RESOA | RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001113878
28 | Q030 | P.S. 354 - QUEENS | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 7/14/2023 | DOES |  | DOES | 154801 | 0 | DSF0000811388
28 | Q030 | P.S. 354 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/24/2024 | DOES | 9/13/2024 | DOES | 65832 | 189 | DSF0001084275
28 | Q040 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | Scope | Complete | 6/22/2022 | 11/7/2022 | 2/2/2023 | 136780 | 127822 | 127822 | DSF0001021119, DSF0001112190
28 | Q040 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | Design | Complete | 2/8/2023 | 7/12/2023 | 5/4/2023 | 683900 | 425078 | 359655 | DSF0001021119, DSF0001112190
28 | Q040 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | Construction | In-Progress | 8/26/2024 | 8/25/2026 |  | 15387750 | 14325592 | 1037611 | DSF0001021119, DSF0001112190
28 | Q040 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | CM,F&E | In-Progress | 8/26/2024 | 8/25/2026 |  | 957460 | 68349 | 68349 | DSF0001021119, DSF0001112190
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112952
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 51000 | 51000 | 0 | DSF0001112952
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 748000 | 748000 | 0 | DSF0001112952
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 51000 | 51000 | 0 | DSF0001112952
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113628
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113628
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113628
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113628
28 | Q040 | P.S. 40 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0001008133
28 | Q040 | P.S. 40 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/13/2024 | DIIR |  | DIIR | 55000 | 0 | DSF0001086362
28 | Q040 | P.S. 40 - QUEENS | DOE - RESOA | FY17 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 291274 | 0 | DSF0000844971
28 | Q040 | P.S. 40 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/2/2021 | DOER |  | DOER | 140238 | 0 | DSF0000913371
28 | Q040 | P.S. 40 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112951
28 | Q040 | P.S. 40 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112953
28 | Q048 | Q075 SPED - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 223355 | 196278 | DSF0000946648
28 | Q048 | Q075 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/13/2024 | DOES | 8/20/2024 | DOES | 65832 | 3725 | DSF0001084653
28 | Q054 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | Scope | Complete | 8/7/2020 | 12/7/2020 | 3/22/2021 | 19800 | 46153 | 46153 | DSF0000961135
28 | Q054 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | Design | Complete | 3/31/2021 | 9/7/2021 | 12/22/2021 | 99000 | 287970 | 287970 | DSF0000961135
28 | Q054 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | Construction | In-Progress | 7/25/2022 | 1/15/2024 |  | 2227500 | 2997130 | 2638852 | DSF0000961135
28 | Q054 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | CM,F&E | In-Progress | 7/25/2022 | 1/15/2024 |  | 138600 | 625649 | 625649 | DSF0000961135
28 | Q054 | P.S. 54 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 152300 | 0 | DSF0001033756
28 | Q054 | P.S. 54 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/24/2023 | DOER |  | DOER | 569725 | 0 | DSF0001035827
28 | Q055 | P.S. 55 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 2/25/2021 | DOER |  | DOER | 160750 | 0 | DSF0000913375
28 | Q055 | P.S. 55 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086369
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/29/2023 | 4/2/2024 | 4/16/2024 | 0 | 21698 | 21698 | DSF0001086381
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | In-Progress | 4/23/2024 | 9/24/2024 |  | 88250 | 67437 | 39580 | DSF0001086381
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1294334 | 1294334 | 1918 | DSF0001086381
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 88250 | 88250 | 23519 | DSF0001086381
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 11/29/2023 | 4/2/2024 | 4/16/2024 | 0 | 14475 | 14475 | DSF0001086383
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | In-Progress | 4/23/2024 | 9/24/2024 |  | 29156 | 45164 | 27150 | DSF0001086383
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 427622 | 427622 | 0 | DSF0001086383
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 29156 | 29156 | 15386 | DSF0001086383
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/28/2024 | 8/28/2024 | 8/20/2024 | 0 | 0 | 14702 | DSF0001087056
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | In-Progress | 8/22/2024 | 12/27/2024 |  | 1750 | 1750 | 2543 | DSF0001087056
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 25666 | 25666 | 0 | DSF0001087056
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 1750 | 1750 | 4620 | DSF0001087056
28 | Q072 | J.H.S. 72 - QUEENS | SCA IEH | PO18-ABATE APPROX 30 FEET OF PIPE INSULATION LOCATED IN BOILER ROOM INSULATION MARKED WITH RED SPRAY | Construction | Complete | 11/25/2024 | IEH | 11/30/2024 | IEH | 0 | 0 | SCA0000073643
28 | Q072 | J.H.S. 72 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 2/14/2022 | FTK |  | FTK | 234587 | 176131 | DSF0000960901
28 | Q072 | J.H.S. 72 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001112980
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 6/1/2021 | DOER |  | DOER | 318213 | 0 | DSF0000800469
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/25/2024 | DOER |  | DOER | 347450 | 0 | DSF0001035845
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001035846
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 2900000 | 0 | DSF0001085179
28 | Q072 | REDWOOD MIDDLE SCHOOL | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 400000 | 0 | DSF0001086382
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001086384
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112979
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001112981
28 | Q072 | J.H.S. 72 - QUEENS | DOE - Skilled Trades | WASTE LINE REPAIR | Construction | In-Progress | 2/12/2020 | DOES |  | DOES | 475946 | 450366 | DSF0000960622
28 | Q072 | J.H.S. 72 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/23/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084803
28 | Q072 | J.H.S. 72 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/2/2024 | DOES |  | DOES | 573972 | 0 | DSF0001085749
28 | Q080 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | Scope | Complete | 5/23/2019 | 8/13/2020 | 12/16/2021 | 101108 | 159908 | 159908 | DSF0000901623, DSF0000947140, DSF0000960673, DSF0001021781
28 | Q080 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | Design | Complete | 12/20/2021 | 5/23/2022 | 5/9/2022 | 487192 | 557295 | 506473 | DSF0000901623, DSF0000947140, DSF0000960673, DSF0001021781
28 | Q080 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | Construction | In-Progress | 8/15/2022 | 8/13/2024 |  | 9374718 | 8654170 | 7890979 | DSF0000901623, DSF0000947140, DSF0000960673, DSF0001021781
28 | Q080 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 8/15/2022 | 8/13/2024 |  | 845365 | 618149 | 607701 | DSF0000901623, DSF0000947140, DSF0000960673, DSF0001021781
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 5/6/2022 | 12/8/2022 | 11/1/2022 | 0 | 26248 | 23465 | DSF0001033776, DSF0001033777
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 11/2/2022 | 3/2/2023 | 3/21/2023 | 76114 | 104339 | 92400 | DSF0001033776, DSF0001033777
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/25/2023 | 8/19/2024 |  | 1116340 | 592091 | 381116 | DSF0001033776, DSF0001033777
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 9/25/2023 | 8/19/2024 |  | 201895 | 226424 | 155435 | DSF0001033776, DSF0001033777
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Scope | Complete | 1/30/2023 | 11/9/2023 | 2/9/2024 | 0 | 17063 | 14046 | DSF0001035852, DSF0001035853
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Design | Complete | 2/9/2024 | 6/12/2024 | 4/18/2024 | 49696 | 70879 | 42306 | DSF0001035852, DSF0001035853
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Construction | In-Progress | 11/22/2024 | 9/17/2025 |  | 728882 | 571762 | 8017 | DSF0001035852, DSF0001035853
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | CM,F&E | In-Progress | 11/22/2024 | 9/17/2025 |  | 49696 | 58954 | 17374 | DSF0001035852, DSF0001035853
28 | Q080 | P.S. 80 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 55000 | 53881 | DSF0001086388
28 | Q080 | P.S. 80 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001112987
28 | Q082 | P.S. 82 - QUEENS | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 190000 | 0 | DSF0001008081
28 | Q082 | P.S. 82 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 5039 | 0 | DSF0001086389
28 | Q086 | P.S. 86 - QUEENS | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 11/21/2024 | FTK |  | FTK | 17589 | 13489 | DSF0001087509
28 | Q086 | P.S. 86 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/4/2024 | DIIR |  | DIIR | 125000 | 0 | DSF0001086390
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | Complete | 1/25/2021 | DOER | 1/26/2021 | DOER | 66173 |  | DSF0000913391
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001033267
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001033268
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112244
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001112988
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086391
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 9/13/2021 | 12/14/2021 | 12/13/2021 | 13460 | 49715 | 49715 | DSF0001009284
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | Design | Complete | 12/14/2021 | 5/2/2022 | 5/11/2022 | 60570 | 80232 | 78714 | DSF0001009284
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | Construction | In-Progress | 1/3/2023 | 1/2/2024 |  | 780680 | 714248 | 616498 | DSF0001009284
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | CM,F&E | In-Progress | 1/3/2023 | 1/2/2024 |  | 144695 | 110536 | 109170 | DSF0001009284
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | Scope | Complete | 9/22/2021 | 3/2/2023 | 3/15/2023 | 30769 | 88326 | 78485 | DSF0000996357, DSF0001009285, DSF0001083698
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | Design | Complete | 3/16/2023 | 7/19/2023 | 3/16/2023 | 143615 | 173990 | 164283 | DSF0000996357, DSF0001009285, DSF0001083698
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | Construction | Complete | 6/12/2023 | 9/3/2024 | 9/3/2024 | 2346552 | 2286300 | 2182671 | DSF0000996357, DSF0001009285, DSF0001083698
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | CM,F&E | Complete | 6/12/2023 | 9/3/2024 | 9/3/2024 | 292100 | 219840 | 199090 | DSF0000996357, DSF0001009285, DSF0001083698
28 | Q099 | P.S. 99 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 328204 | 0 | DSF0000960114
28 | Q099 | P.S. 99 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001035869
28 | Q099 | P.S. 99 - QUEENS | DOE - RESOA | FY18 RESO A TOILETS-STUDENTS | Construction | In-Progress | 12/1/2017 | DOER |  | DOER | 126296 | 0 | DSF0000867397
28 | Q099 | P.S. 99 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/15/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084659
28 | Q101 | P.S. 101 - QUEENS | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113884
28 | Q101 | P.S. 101 - QUEENS | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001113884
28 | Q101 | P.S. 101 - QUEENS | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001113884
28 | Q101 | P.S. 101 - QUEENS | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001113884
28 | Q101 | P.S. 101 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 1/31/2022 | FTK |  | FTK | 216811 | 182800 | DSF0000961015
28 | Q101 | P.S. 101 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/16/2021 | DOER |  | DOER | 231196 | 0 | DSF0000913397
28 | Q101 | P.S. 101 - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 209359 | 0 | DSF0001035069
28 | Q101 | P.S. 101 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0 | DSF0001035870
28 | Q101 | P.S. 101 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/15/2024 | DOES |  | DOES | 128236 | 0 | DSF0001034427
28 | Q117 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 3/11/2021 | 7/26/2021 | 11/22/2021 | 45500 | 68016 | 67058 | DSF0000996637
28 | Q117 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | Design | Complete | 12/1/2021 | 5/4/2022 | 4/27/2022 | 227500 | 217171 | 217171 | DSF0000996637
28 | Q117 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | Construction | In-Progress | 8/22/2022 | 2/12/2024 |  | 5118751 | 4673412 | 4391410 | DSF0000996637
28 | Q117 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | CM,F&E | In-Progress | 8/22/2022 | 2/12/2024 |  | 318500 | 337692 | 337274 | DSF0000996637
28 | Q117 | P.S. 117 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 7/7/2021 | 1/3/2022 | 12/20/2021 | 0 | 37980 | 29180 | DSF0000961422, DSF0001007728
28 | Q117 | P.S. 117 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 12/22/2021 | 3/14/2022 | 4/12/2022 | 72000 | 118283 | 111947 | DSF0000961422, DSF0001007728
28 | Q117 | P.S. 117 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | Complete | 6/20/2022 | 6/19/2023 | 2/1/2024 | 1056000 | 838203 | 727625 | DSF0000961422, DSF0001007728
28 | Q117 | P.S. 117 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 6/20/2022 | 6/19/2023 | 2/1/2024 | 72000 | 134785 | 132373 | DSF0000961422, DSF0001007728
28 | Q117 | P.S. 117 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 1/7/2019 | FTK |  | FTK | 404455 | 205669 | DSF0000879330
28 | Q117 | P.S. 117 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 116178 | 0 | DSF0000488305
28 | Q117 | P.S. 117 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 48564 | 0 | DSF0001111887
28 | Q121 | P.S. 121 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 11/16/2018 | EMER |  | EMER | 84374 | 79867 | SCA0000055010
28 | Q121 | P.S. 121 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 1950000 | 799435 | DSF0001086414
28 | Q121 | P.S. 121 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 630385 | 0 | DSF0001113764
28 | Q121 | P.S. 121 - QUEENS | DOE - Skilled Trades | BOOSTER PUMP REPLACEMENT | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 76229 | 0 | DSF0001112097
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | IPDVS | Scope | Complete | 1/6/2022 | 5/6/2022 | 1/20/2022 | 6000 | 7371 | 7371 | DSF0001009287
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | IPDVS | Design | Complete | 1/21/2022 | 7/18/2022 | 7/18/2022 | 27000 | 29485 | 29485 | DSF0001009287
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | IPDVS | Construction | In-Progress | 2/27/2023 | 12/23/2023 |  | 348000 | 254457 | 180659 | DSF0001009287
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | IPDVS | CM,F&E | In-Progress | 2/27/2023 | 12/23/2023 |  | 140877 | 163816 | 162941 | DSF0001009287
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | Scope | Complete | 3/30/2021 | 4/12/2022 | 8/8/2022 | 64360 | 122151 | 122151 | DSF0000948161, DSF0001085108
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | Design | Complete | 9/22/2022 | 2/28/2023 | 4/27/2023 | 321800 | 409279 | 318832 | DSF0000948161, DSF0001085108
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | Construction | In-Progress | 10/3/2023 | 4/1/2025 |  | 7240500 | 6613578 | 1479545 | DSF0000948161, DSF0001085108
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | CM,F&E | In-Progress | 10/3/2023 | 4/1/2025 |  | 450520 | 288131 | 215453 | DSF0000948161, DSF0001085108
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113036
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 108000 | 108000 | 0 | DSF0001113036
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 1584000 | 1584000 | 0 | DSF0001113036
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 108000 | 108000 | 0 | DSF0001113036
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113644
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113644
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113644
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113644
28 | Q139 | P.S. 139 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113035
28 | Q139 | P.S. 139 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/15/2021 | DOES |  | DOES | 140638 | 0 | DSF0001008945
28 | Q140 | P.S. 140 - QUEENS | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER | Construction | In-Progress | 4/1/2024 | FTK |  | FTK | 351100 | 89183 | DSF0001022905
28 | Q140 | P.S. 140 - QUEENS | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 10/31/2024 | FTK |  | FTK | 17163 | 7463 | DSF0001087523
28 | Q140 | P.S. 140 - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 37000 | 0 | DSF0000914008
28 | Q140 | P.S. 140 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0 | DSF0001033817
28 | Q140 | P.S. 140 - QUEENS | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001033282
28 | Q140 | P.S. 140 - QUEENS | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 114422 | 0 | DSF0001035907
28 | Q140 | P.S. 140 - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0 | DSF0001035908
28 | Q140 | P.S. 140 - QUEENS | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | Complete | 7/22/2024 | DOER | 9/24/2024 | DOER | 54612 |  | DSF0001086430
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 5/21/2021 | 10/6/2021 | 1/21/2022 | 52876 | 103998 | 103998 | DSF0000997112, DSF0001022950, DSF0001022949, DSF0001022948
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 1/21/2022 | 6/22/2022 | 5/11/2022 | 261507 | 418845 | 413995 | DSF0000997112, DSF0001022950, DSF0001022949, DSF0001022948
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | Complete | 9/12/2022 | 6/2/2024 | 6/2/2024 | 5635639 | 5354913 | 4921640 | DSF0000997112, DSF0001022950, DSF0001022949, DSF0001022948
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | Complete | 9/12/2022 | 6/2/2024 | 6/2/2024 | 392417 | 157154 | 157154 | DSF0000997112, DSF0001022950, DSF0001022949, DSF0001022948
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/29/2020 | 9/28/2020 | 7/21/2020 | 3616 | 9403 | 9403 | DSF0000960770
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/21/2020 | 1/15/2021 | 6/2/2021 | 16272 | 37612 | 37612 | DSF0000960770
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/20/2022 | 3/15/2023 |  | 209728 | 193811 | 165741 | DSF0000960770
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/20/2022 | 3/15/2023 |  | 202120 | 217142 | 215248 | DSF0000960770
28 | Q142 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000011991
28 | Q142 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 0 | 0 | 0 | DSF0000011991
28 | Q142 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 9/6/2006 | 10/10/2006 |  | 0 | 0 | 0 | DSF0000011991
28 | Q142 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 9/6/2006 | 10/10/2006 |  | 0 | 0 | 0 | DSF0000011991
28 | Q142 | Q752 SPED - QUEENS | SCA IEH | PO18-COMPLETE ABATEMENT DRILLING AT CAFETERIA CEILING 1/2' DIAMENTE & 2' DEEP. TOTAL 3 HOLES. | Construction | In-Progress | 11/26/2024 | IEH |  | IEH | 0 | 0 | SCA0000073651
28 | Q142 | Q752 SPED - QUEENS | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 11/12/2020 | DOES | 12/16/2020 | DOES | 3893 | 18861 | DSF0000866926
28 | Q142 | Q752 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/9/2024 | DOES | 8/20/2024 | DOES | 65832 |  | DSF0001084990
28 | Q144 | P.S. 144 - QUEENS | SCA IEH | PO18-W/J=NEED 4 LINEAR FEET OF 2' STEAM SUPPLY PIPE & 4 LINEAR FEET OF 1 1/4' RETURN PIPE ABATED IN | Construction | Complete | 12/4/2024 | IEH | 12/7/2024 | IEH | 0 | 0 | SCA0000073666
28 | Q144 | P.S. 144 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | Complete | 11/13/2023 | DOER | 6/27/2024 | DOER | 179168 | 1034 | DSF0001035911
28 | Q144 | P.S. 144 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 12/15/2023 | DOER |  | DOER | 179577 | 0 | DSF0001035912
28 | Q144 | P.S. 144 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 150000 | 0 | DSF0001086434
28 | Q144 | P.S. 144 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/29/2021 | DOES |  | DOES | 61178 | 0 | DSF0000866130
28 | Q144 | P.S. 144 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/26/2022 | DOES |  | DOES | 84686 | 0 | DSF0001009071
28 | Q157 | J.H.S. 157 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/18/2024 | DIIR | 7/10/2024 | DIIR | 80000 | 80000 | DSF0001086449
28 | Q157 | J.H.S. 157 - QUEENS | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 12/10/2021 | DOER |  | DOER | 50000 | 0 | DSF0000913412
28 | Q157 | J.H.S. 157 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/22/2024 | DOES | 8/2/2024 | DOES | 65832 | 10240 | DSF0001084991
28 | Q160 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | Scope | Complete | 1/12/2021 | 1/28/2022 | 3/21/2022 | 1154320 | 829021 | 821685 | DSF0000911859, DSF0000911859, DSF0000911859
28 | Q160 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | Design | Complete | 3/21/2022 | 8/18/2022 | 4/29/2022 | 5194440 | 3447775 | 2623319 | DSF0000911859, DSF0000911859, DSF0000911859
28 | Q160 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | Construction | In-Progress | 7/25/2022 | 9/3/2025 |  | 65507660 | 60869749 | 55123222 | DSF0000911859, DSF0000911859, DSF0000911859
28 | Q160 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | CM,Art,F&E | In-Progress | 7/25/2022 | 9/3/2025 |  | 9234560 | 8580911 | 5525410 | DSF0000911859, DSF0000911859, DSF0000911859
28 | Q160 | P.S. 160 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA / EXISTING BUILDING-GYMNASIUM | Scope | Complete | 6/14/2022 | 10/28/2022 | 12/18/2023 | 47871 | 50991 | 9495 | DSF0000911859, DSF0000911859, DSF0000911859, DSF0000911859
28 | Q160 | P.S. 160 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA / EXISTING BUILDING-GYMNASIUM | Design | In-Progress | 1/2/2024 | 6/18/2024 |  | 224983 | 224983 | 38003 | DSF0000911859, DSF0000911859, DSF0000911859, DSF0000911859
28 | Q160 | P.S. 160 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA / EXISTING BUILDING-GYMNASIUM | Construction | PNS | PNS | PNS | PNS | 3818776 | 3818776 | 976 | DSF0000911859, DSF0000911859, DSF0000911859, DSF0000911859
28 | Q160 | P.S. 160 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA / EXISTING BUILDING-GYMNASIUM | CM,F&E | PNS | PNS | PNS | PNS | 442899 | 442899 | 40605 | DSF0000911859, DSF0000911859, DSF0000911859, DSF0000911859
28 | Q160 | P.S. 160 - QUEENS | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | Scope | Complete | 2/17/2023 | 5/18/2023 | 6/7/2023 | 0 | 23687 | 23687 | DSF0001035932
28 | Q160 | P.S. 160 - QUEENS | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | Design | In-Progress | 6/15/2023 | 11/1/2023 |  | 108511 | 84824 | 32893 | DSF0001035932
28 | Q160 | P.S. 160 - QUEENS | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | Construction | PNS | PNS | PNS | PNS | 1591499 | 1591499 | 8915 | DSF0001035932
28 | Q160 | P.S. 160 - QUEENS | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 108511 | 108511 | 11352 | DSF0001035932
28 | Q160 | P.S. 160 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113053
28 | Q160 | P.S. 160 - QUEENS | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 65000 | 0
28 | Q160 | P.S. 160 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/13/2023 | DOER |  | DOER | 490143 | 0 | DSF0001035929
28 | Q161 | P.S. 161 - QUEENS | SCA CIP | WINDOWS / PARAPETS | Scope | Complete | 4/26/2023 | 9/12/2023 | 9/20/2023 | 56238 | 81492 | 81492 | DSF0001083952, DSF0001087208
28 | Q161 | P.S. 161 - QUEENS | SCA CIP | WINDOWS / PARAPETS | Design | Complete | 10/4/2023 | 3/11/2024 | 4/24/2024 | 279049 | 221355 | 214866 | DSF0001083952, DSF0001087208
28 | Q161 | P.S. 161 - QUEENS | SCA CIP | WINDOWS / PARAPETS | Construction | PNS | PNS | PNS | PNS | 6093334 | 6093334 | 145 | DSF0001083952, DSF0001087208
28 | Q161 | P.S. 161 - QUEENS | SCA CIP | WINDOWS / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 409731 | 409731 | 27985 | DSF0001083952, DSF0001087208
28 | Q161 | P.S. 161 - QUEENS | Fast Track Projects | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/8/2024 | FTK |  | FTK | 338592 | 258969 | DSF0001035933
28 | Q161 | P.S. 161 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 6/10/2022 | DOES |  | DOES | 153331 | 0 | DSF0001009186
28 | Q174 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | Scope | Complete | 9/30/2020 | 3/4/2022 | 4/6/2022 | 994026 | 779258 | 749600 | DSF0000911860, DSF0000911860
28 | Q174 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | Design | Complete | 4/6/2022 | 5/16/2022 | 4/25/2022 | 4473117 | 2762675 | 2180419 | DSF0000911860, DSF0000911860
28 | Q174 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | Construction | Complete | 7/11/2022 | 9/3/2024 | 8/15/2024 | 56410974 | 56292196 | 52935161 | DSF0000911860, DSF0000911860
28 | Q174 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | CM,Art,F&E | Complete | 7/11/2022 | 9/3/2024 | 8/15/2024 | 7952208 | 7142302 | 6018178 | DSF0000911860, DSF0000911860
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | EXISTING BUILDING-PA/CLOCK SYSTEMS / EXISTING BUILDING-FIRE ALARM SYSTEM / EXISTING BUILDING- INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-GYMNASIUM | Scope | Complete | 10/28/2021 | 3/4/2022 | 6/3/2022 | 46084 | 61440 | 61440 | DSF0000911860, DSF0000911860, DSF0000911860, DSF0000911860, DSF0000911860
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | EXISTING BUILDING-PA/CLOCK SYSTEMS / EXISTING BUILDING-FIRE ALARM SYSTEM / EXISTING BUILDING- INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-GYMNASIUM | Design | Complete | 6/22/2022 | 12/9/2022 | 7/17/2023 | 220019 | 205641 | 201060 | DSF0000911860, DSF0000911860, DSF0000911860, DSF0000911860, DSF0000911860
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | EXISTING BUILDING-PA/CLOCK SYSTEMS / EXISTING BUILDING-FIRE ALARM SYSTEM / EXISTING BUILDING- INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-GYMNASIUM | Construction | PNS | PNS | PNS | PNS | 4050643 | 4050643 | 3247 | DSF0000911860, DSF0000911860, DSF0000911860, DSF0000911860, DSF0000911860
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | EXISTING BUILDING-PA/CLOCK SYSTEMS / EXISTING BUILDING-FIRE ALARM SYSTEM / EXISTING BUILDING- INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-GYMNASIUM | CM,F&E | PNS | PNS | PNS | PNS | 400606 | 400606 | 40610 | DSF0000911860, DSF0000911860, DSF0000911860, DSF0000911860, DSF0000911860
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | ELECTRICAL SERVICE UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS / PARAPETS / ROOFS / LIGHTING UPGRADE | Scope | Complete | 9/20/2024 | 2/21/2025 | 11/12/2024 | 285595 | 85822 | 54355 | DSF0001112392, DSF0001112391, DSF0001102100, DSF0001102099, DSF0001129851
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | ELECTRICAL SERVICE UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS / PARAPETS / ROOFS / LIGHTING UPGRADE | Design | In-Progress | 12/11/2024 | 6/12/2025 |  | 1321029 | 1321029 | 217411 | DSF0001112392, DSF0001112391, DSF0001102100, DSF0001102099, DSF0001129851
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | ELECTRICAL SERVICE UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS / PARAPETS / ROOFS / LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | 20843256 | 20843256 | 0 | DSF0001112392, DSF0001112391, DSF0001102100, DSF0001102099, DSF0001129851
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | ELECTRICAL SERVICE UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS / PARAPETS / ROOFS / LIGHTING UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 2225062 | 2225062 | 16375 | DSF0001112392, DSF0001112391, DSF0001102100, DSF0001102099, DSF0001129851
28 | Q174 | P.S. 174 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 290000 | 0 | DSF0001033288
28 | Q174 | P.S. 174 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086458
28 | Q174 | P.S. 174 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113066
28 | Q174 | P.S. 174 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 450000 | 8500 | DSF0001086457
28 | Q174 | P.S. 174 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113064
28 | Q174 | P.S. 174 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001113065
28 | Q175 | P.S. 175 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/21/2022 | DOER |  | DOER | 197313 | 0 | DSF0000913418
28 | Q175 | P.S. 175 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113067
28 | Q175 | P.S. 175 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/2/2024 | DOES | 7/18/2024 | DOES | 65832 | 22069 | DSF0001084363
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 1/27/2020 | 6/25/2020 | 4/10/2020 | 79690 | 74347 | 74347 | DSF0000903387, DSF0000914329
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 4/15/2020 | 9/15/2020 | 7/29/2020 | 398450 | 378959 | 318444 | DSF0000903387, DSF0000914329
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 6/6/2022 | 6/4/2024 |  | 8965125 | 8224679 | 7712686 | DSF0000903387, DSF0000914329
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 6/6/2022 | 6/4/2024 |  | 557830 | 834323 | 829311 | DSF0000903387, DSF0000914329
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Scope | Complete | 3/14/2023 | 6/12/2023 | 8/2/2023 | 0 | 39738 | 39738 | DSF0001035956
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Design | Complete | 8/24/2023 | 1/12/2024 | 5/30/2024 | 60000 | 65348 | 59243 | DSF0001035956
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 5790 | DSF0001035956
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 11636 | DSF0001035956
28 | Q190 | J.H.S. 190 - QUEENS | Fast Track Projects | TEMPORARY OIL TANK @Q190 | Construction | In-Progress | 10/30/2019 | FTK |  | FTK | 442486 | 403928 | SCA0000061787
28 | Q190 | J.H.S. 190 - QUEENS | DOE - RESOA | FY22 RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 204721 | 0 | DSF0001033850
28 | Q190 | J.H.S. 190 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/8/2024 | DOER |  | DOER | 70387 | 0 | DSF0001085322
28 | Q190 | J.H.S. 190 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/4/2024 | DOES | 12/16/2024 | DOES | 65832 |  | DSF0001084817
28 | Q190 | J.H.S. 190 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/24/2024 | DOES |  | DOES | 602824 | 0 | DSF0001085755
28 | Q196 | P.S. 196 - QUEENS | SCA IEH | PO18-OIL TANK ROOM ABATE 70 L.F. PIPE INSULATION, 25 L.F. JOINT INSULATION | Construction | In-Progress | 6/29/2023 | IEH |  | IEH | 0 | 0 | SCA0000072088
28 | Q196 | P.S. 196 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113082
28 | Q196 | P.S. 196 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 6/28/2024 | DOER | 10/23/2024 | DOER | 90959 | 995 | DSF0001036095
28 | Q196 | P.S. 196 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 254372 | 0 | DSF0001035966
28 | Q196 | P.S. 196 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/25/2024 | DOES | 11/25/2024 | DOES | 65832 | 8695 | DSF0001084371
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - EXISTING SCHOOL RENOVATION WORK | Scope | Complete | 2/19/2020 | 7/17/2020 | 7/27/2021 | 35448 | 48613 | 48613 | DSF0000888762
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - EXISTING SCHOOL RENOVATION WORK | Design | Complete | 8/10/2021 | 1/4/2022 | 7/24/2023 | 177239 | 235231 | 228075 | DSF0000888762
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - EXISTING SCHOOL RENOVATION WORK | Construction | PNS | PNS | PNS | PNS | 3987872 | 3987872 | 25631 | DSF0000888762
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - EXISTING SCHOOL RENOVATION WORK | CM,F&E | PNS | PNS | PNS | PNS | 248134 | 248134 | 30104 | DSF0000888762
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/13/2022 | 11/29/2022 | 7/25/2023 | 78905 | 179151 | 177682 | DSF0001024094, DSF0001024095, DSF0001024096
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 8/25/2023 | 1/31/2024 | 4/25/2024 | 394527 | 302546 | 294463 | DSF0001024094, DSF0001024095, DSF0001024096
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 8876845 | 8876845 | 83266 | DSF0001024094, DSF0001024095, DSF0001024096
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 552337 | 552337 | 80924 | DSF0001024094, DSF0001024095, DSF0001024096
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - DEMOLITION OF TCU UNIT AND PLAYGROUND DEVELOPMENT | Scope | Complete | 12/6/2022 | 3/9/2023 | 5/15/2023 | 27156 | 46738 | 46738 | DSF0000888762
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - DEMOLITION OF TCU UNIT AND PLAYGROUND DEVELOPMENT | Design | Complete | 5/16/2023 | 10/2/2023 | 4/25/2024 | 108623 | 139793 | 69424 | DSF0000888762
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - DEMOLITION OF TCU UNIT AND PLAYGROUND DEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 2036681 | 2036681 | 87619 | DSF0000888762
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - DEMOLITION OF TCU UNIT AND PLAYGROUND DEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 126727 | 126727 | 29710 | DSF0000888762
28 | Q206 | P.S. 206 - QUEENS | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/21/2022 | DOER |  | DOER | 67809 | 0 | DSF0000913428
28 | Q206 | P.S. 206 - QUEENS | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 7/11/2022 | DOER |  | DOER | 176332 | 0 | DSF0001008149
28 | Q206 | P.S. 206 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/2/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084377
28 | Q217 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 9/12/2022 | 3/10/2023 | 12/22/2022 | 98970 | 158771 | 158771 | DSF0001024285, DSF0001024286, DSF0001024287
28 | Q217 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/5/2023 | 7/3/2023 | 4/25/2023 | 494851 | 342859 | 342859 | DSF0001024285, DSF0001024286, DSF0001024287
28 | Q217 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 7/13/2023 | 7/1/2025 |  | 11134126 | 10556463 | 6357916 | DSF0001024285, DSF0001024286, DSF0001024287
28 | Q217 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/13/2023 | 7/1/2025 |  | 692790 | 591711 | 470360 | DSF0001024285, DSF0001024286, DSF0001024287
28 | Q217 | I.S. 217 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113103
28 | Q217 | I.S. 217 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001033869
28 | Q217 | I.S. 217 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 1/27/2023 | DOES |  | DOES | 490212 | 0 | DSF0000911911
28 | Q217 | I.S. 217 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/27/2023 | DOES | 11/14/2023 | DOES | 405571 |  | DSF0001035107
28 | Q217 | I.S. 217 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/10/2024 | DOES | 10/17/2024 | DOES | 65832 |  | DSF0001084823
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2/5/2020 | 7/7/2020 | 5/7/2020 | 69332 | 72000 | 72000 | DSF0000914331, DSF0000798420, DSF0000903833
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/11/2020 | 12/31/2020 | 8/19/2020 | 338529 | 343453 | 282241 | DSF0000914331, DSF0000798420, DSF0000903833
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 4/4/2022 | 4/2/2024 |  | 6913462 | 6329034 | 5832350 | DSF0000914331, DSF0000798420, DSF0000903833
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 4/4/2022 | 4/2/2024 |  | 546318 | 707021 | 707021 | DSF0000914331, DSF0000798420, DSF0000903833
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 1/10/2022 | 5/10/2022 | 5/2/2022 | 54983 | 87685 | 87685 | DSF0001034285, DSF0001024330, DSF0001024321
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 7/11/2022 | 1/12/2023 | 2/10/2023 | 269594 | 431865 | 343766 | DSF0001034285, DSF0001024330, DSF0001024321
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 10/4/2023 | 1/1/2025 |  | 5605382 | 5177569 | 4156993 | DSF0001034285, DSF0001024330, DSF0001024321
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 10/4/2023 | 1/1/2025 |  | 424812 | 178558 | 120963 | DSF0001034285, DSF0001024330, DSF0001024321
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 12/21/2023 | 5/8/2024 | 8/2/2024 | 21028 | 70021 | 69899 | DSF0001075115
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | EXTERIOR MASONRY | Design | In-Progress | 8/7/2024 | 1/10/2025 |  | 98131 | 98131 | 13793 | DSF0001075115
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 1556081 | 1556081 | 40 | DSF0001075115
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 154206 | 154206 | 30524 | DSF0001075115
28 | Q220 | P.S. 220 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 56000 | 0 | DSF0001086481
28 | Q220 | P.S. 220 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/11/2017 | DOES |  | DOES | 234437 | 0 | DSF0000866046
28 | Q276 | P.S. 48 - QUEENS | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 150000 | 150000 | 150000 | DSF0001086501
28 | Q276 | P.S. 48 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 450000 | 0 | DSF0001033259
28 | Q276 | Q075 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 6/4/2024 | DIIR | 80000 | 80000 | DSF0001036018
28 | Q276 | P.S. 48 - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 192000 | 0 | DSF0001113879
28 | Q276 | P.S. 48 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/15/2024 | DOES | 11/19/2024 | DOES | 50832 | 9961 | DSF0001084401
28 | Q277 | P.S. 182 - QUEENS | SCA CIP | EXTERIOR WALLS | Scope | Complete | 9/18/2024 | 1/8/2025 | 12/20/2024 | 2440 | 1768 | 1768 | SCA0000071095
28 | Q277 | P.S. 182 - QUEENS | SCA CIP | EXTERIOR WALLS | Design | PNS | PNS | PNS | PNS | 10979 | 10979 | 7071 | SCA0000071095
28 | Q277 | P.S. 182 - QUEENS | SCA CIP | EXTERIOR WALLS | Construction | PNS | PNS | PNS | PNS | 141505 | 141505 | 2502 | SCA0000071095
28 | Q277 | P.S. 182 - QUEENS | SCA CIP | EXTERIOR WALLS | CM,F&E | PNS | PNS | PNS | PNS | 26227 | 26227 | 7902 | SCA0000071095
28 | Q277 | Q009 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/2/2024 | DIIR |  | DIIR | 100000 | 0 | DSF0001086502
28 | Q277 | Q009 SPED - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 192000 | 0 | DSF0001036019
28 | Q277 | P.S. 182 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 10/6/2023 | DOES |  | DOES | 60794 | 0 | DSF0000911909
28 | Q278 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | Scope | Complete | 1/21/2022 | 3/18/2022 | 3/22/2022 | 88660 | 147222 | 147222 | DSF0000911862
28 | Q278 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | Design | Complete | 3/23/2022 | 9/9/2022 | 11/16/2022 | 398970 | 602770 | 194166 | DSF0000911862
28 | Q278 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | Construction | In-Progress | 8/7/2023 | 9/3/2025 |  | 5031455 | 4555388 | 1809472 | DSF0000911862
28 | Q278 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | CM,F&E | In-Progress | 8/7/2023 | 9/3/2025 |  | 709280 | 578915 | 226858 | DSF0000911862
28 | Q278 | P.S. 182 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500000 | 0 | DSF0001033842
28 | Q314 | THE QUEENS SCHOOL FOR LEADERSHIP AND EXCELLENCE | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/21/2023 | DOES | 11/16/2023 | DOES | 527850 | 516349 | DSF0001035109
28 | Q314 | THE QUEENS SCHOOL FOR LEADERSHIP AND EXCELLENCE | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/20/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084408
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | Scope | Complete | 5/20/2021 | 8/13/2021 | 6/28/2021 | 18770 | 34072 | 34072 | DSF0000998863
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | Design | Complete | 8/25/2021 | 1/31/2022 | 2/16/2022 | 93850 | 149354 | 119117 | DSF0000998863
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | Construction | In-Progress | 8/8/2022 | 11/5/2023 |  | 2111625 | 1931892 | 1795730 | DSF0000998863
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | CM,F&E | In-Progress | 8/8/2022 | 11/5/2023 |  | 131390 | 40331 | 40331 | DSF0000998863
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | Scope | Complete | 6/16/2021 | 11/1/2021 | 11/3/2021 | 13700 | 39304 | 39304 | DSF0001008903
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | Design | Complete | 12/13/2021 | 5/16/2022 | 4/13/2022 | 61650 | 51130 | 51130 | DSF0001008903
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | Construction | In-Progress | 6/20/2022 | 4/15/2023 |  | 794600 | 729745 | 430713 | DSF0001008903
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | CM,F&E | In-Progress | 6/20/2022 | 4/15/2023 |  | 147275 | 94611 | 93130 | DSF0001008903
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/5/2023 | 5/31/2023 | 11/3/2023 | 157000 | 171979 | 171979 | DSF0001103972, DSF0001036047
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 11/13/2023 | 4/16/2024 | 5/14/2024 | 785000 | 705076 | 536838 | DSF0001103972, DSF0001036047
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/20/2024 | 9/19/2026 |  | 17662500 | 15889374 | 268644 | DSF0001103972, DSF0001036047
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 9/20/2024 | 9/19/2026 |  | 1099000 | 52367 | 52367 | DSF0001103972, DSF0001036047
28 | Q440 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000011843
28 | Q440 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 0 | 0 | 0 | DSF0000011843
28 | Q440 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 5/16/2006 | 5/31/2007 |  | 0 | 0 | 0 | DSF0000011843
28 | Q440 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 5/16/2006 | 5/31/2007 |  | 0 | 0 | 0 | DSF0000011843
28 | Q440 | FOREST HILLS HS - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION- FALLING SLATE | Construction | In-Progress | 9/1/2022 | EMER |  | EMER | 531511 | 445910 | SCA0000071338
28 | Q440 | FOREST HILLS HS - QUEENS | SCA IEH | PO18-ACM CEILING PLASTER PEELING FALLING OFF ABATE AND REPAIR CEILING PLASTER AT AUDITORIUM | Construction | Complete | 11/7/2024 | IEH | 11/11/2024 | IEH | 0 | 0 | SCA0000073591
28 | Q440 | FOREST HILLS HS - QUEENS | SCA IEH | PO18-ABATE & REMOVE ACM IN BOILER ROOM WATER LINE NEXT TO CHEMICAL FEED TANK SPRAYED ORANGE APPROX 8 | Construction | Complete | 12/17/2024 | IEH | 12/28/2024 | IEH | 0 | 0 | SCA0000073723
28 | Q440 | FOREST HILLS HS - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001033321
28 | Q440 | FOREST HILLS HS - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001113159
28 | Q440 | FOREST HILLS HS - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001033924
28 | Q440 | FOREST HILLS HS - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 11/2/2018 | DOES |  | DOES | 233035 | 0 | DSF0000814835
28 | Q440 | FOREST HILLS HS - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 1/13/2023 | DOES | 10/31/2023 | DOES | 955614 | 141239 | DSF0001034911
28 | Q440 | FOREST HILLS HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/18/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085004
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | FY24 RESO A TENNIS COURT UPGRADE | Scope | Complete | 12/13/2023 | 3/22/2024 | 3/7/2024 | 0 | 36035 | 36035 | DSF0001086537
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | FY24 RESO A TENNIS COURT UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 2770 | 2770 | DSF0001086537
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | FY24 RESO A TENNIS COURT UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086537
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | FY24 RESO A TENNIS COURT UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 1112 | 1112 | DSF0001086537
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A TENNIS COURT UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087083
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A TENNIS COURT UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087083
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A TENNIS COURT UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087083
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A TENNIS COURT UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087083
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 7/26/2023 | 12/12/2023 | 2/8/2024 | 25127 | 82951 | 69624 | DSF0001076297
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 3/1/2024 | 8/1/2024 | 7/18/2024 | 117260 | 56121 | 52717 | DSF0001076297
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 1859415 | 1859415 | 30572 | DSF0001076297
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 184266 | 184266 | 35082 | DSF0001076297
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | Scope | Complete | 2/9/2022 | 11/9/2022 | 9/19/2022 | 35940 | 4997 | 4997 | DSF0001034314, DSF0001025494
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | Design | Complete | 9/20/2022 | 1/20/2023 | 1/5/2023 | 161730 | 179559 | 166637 | DSF0001034314, DSF0001025494
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | Construction | In-Progress | 5/9/2024 | 8/1/2025 |  | 2084520 | 2138479 | 499089 | DSF0001034314, DSF0001025494
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | CM,F&E | In-Progress | 5/9/2024 | 8/1/2025 |  | 386355 | 105509 | 75772 | DSF0001034314, DSF0001025494
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087087
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087087
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087087
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087087
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113171
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | Design | PNS | PNS | PNS | PNS | 240000 | 240000 | 0 | DSF0001113171
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 3520000 | 3520000 | 0 | DSF0001113171
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 240000 | 240000 | 0 | DSF0001113171
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113667
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113667
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113667
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113667
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 1/11/2024 | 5/13/2024 |  | 0 | 32553 | 412 | DSF0001086544
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 180000 | 147447 | 1649 | DSF0001086544
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 2640000 | 2640000 | 0 | DSF0001086544
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 180000 | 180000 | 0 | DSF0001086544
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA IEH | PO18-ABATE 35 FEET OF ACM ON WASTE LINE IN ROOMS B35 & PAINT LOCKER ROOM ACM IS COMBINED WITH THE HO | Construction | Complete | 8/1/2024 | IEH | 8/10/2024 | IEH | 0 | 0 | SCA0000073224
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | Fast Track Projects | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/15/2022 | FTK |  | FTK | 473479 | 473470 | DSF0000913459
28 | Q470 | HILLSIDE ACADEMY FOR ARTS AND LETTERS - Q | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 12/20/2021 | FTK |  | FTK | 220706 | 130770 | DSF0000960917
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | Fast Track Projects | LSP- LIGHTING UPGRADE | Construction | Complete | 5/29/2023 | FTK | 8/16/2024 | FTK | 678624 | 568115 | DSF0001025473
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | Fast Track Projects | LSP- LIBRARY UPGRADE | Construction | Complete | 4/17/2023 | FTK | 8/14/2024 | FTK | 473975 | 439199 | DSF0001034313
28 | Q470 | JAMAICA GATEWAY TO THE SCIENCES - Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0 | DSF0001086545
28 | Q470 | HILLSIDE ACADEMY FOR ARTS AND LETTERS - Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0 | DSF0001086546
28 | Q470 | JAMAICA GATEWAY TO THE SCIENCES - Q | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 163978 | 0 | DSF0001086547
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | DOE - Skilled Trades | FLOORING REPLACEMENT | Construction | In-Progress | 3/9/2022 | DOES |  | DOES | 1000000 | 0 | DSF0001034311
28 | Q471 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | RESO A ATHLETIC FIELDS | Scope | In-Progress | 10/10/2024 | 2/3/2025 |  | 0 | 7096 | 1331 | DSF0001113711
28 | Q471 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 6000 | 6000 | 5323 | DSF0001113711
28 | Q471 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001113711
28 | Q471 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 279 | DSF0001113711
28 | Q497 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/5/2021 | 8/31/2021 | 8/31/2021 | 2215100 | 1380103 | 1353691 | DSF0000911858
28 | Q497 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 9/1/2021 | 4/5/2022 | 4/28/2022 | 9967950 | 4558649 | 4138227 | DSF0000911858
28 | Q497 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 10/1/2022 | 9/3/2026 |  | 125706925 | 112447214 | 26997460 | DSF0000911858
28 | Q497 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 10/1/2022 | 9/3/2026 |  | 17720800 | 7787280 | 1274523 | DSF0000911858
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | Scope | Complete | 11/5/2018 | 2/7/2019 | 2/4/2020 | 20970 | 28283 | 28283 | DSF0000881640
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | Design | Complete | 2/4/2020 | 8/5/2020 | 4/19/2021 | 104850 | 153209 | 134661 | DSF0000881640
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | Construction | In-Progress | 6/5/2023 | 6/3/2024 |  | 2359125 | 2155123 | 8633 | DSF0000881640
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | CM,F&E | In-Progress | 6/5/2023 | 6/3/2024 |  | 146790 | 90311 | 75556 | DSF0000881640
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | Scope | Complete | 2/25/2020 | 5/22/2020 | 11/24/2021 | 30525 | 52597 | 52597 | DSF0000950171, DSF0001034321
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | Design | Complete | 11/29/2021 | 4/15/2022 | 8/25/2022 | 146797 | 92495 | 92495 | DSF0000950171, DSF0001034321
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | Construction | In-Progress | 2/1/2023 | 3/1/2024 |  | 2799135 | 2627476 | 2298560 | DSF0000950171, DSF0001034321
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | CM,F&E | In-Progress | 2/1/2023 | 3/1/2024 |  | 257352 | 286359 | 274784 | DSF0000950171, DSF0001034321
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 1/25/2023 | 5/25/2023 | 4/11/2023 | 17500 | 18548 | 18548 | DSF0001083787
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 4/18/2023 | 10/18/2023 | 8/14/2023 | 78750 | 63027 | 60371 | DSF0001083787
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 2/26/2024 | 1/25/2025 |  | 1015000 | 901558 | 326309 | DSF0001083787
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 2/26/2024 | 1/25/2025 |  | 188125 | 120510 | 77107 | DSF0001083787
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033327
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033327
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033327
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033327
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113177
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | Design | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001113177
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001113177
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 0 | DSF0001113177
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113668
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113668
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113668
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113668
28 | Q505 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000011995
28 | Q505 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 0 | 0 | 0 | DSF0000011995
28 | Q505 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 6/14/2006 | 5/31/2007 |  | 0 | 0 | 0 | DSF0000011995
28 | Q505 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 6/14/2006 | 5/31/2007 |  | 0 | 0 | 0 | DSF0000011995
28 | Q505 | HILLCREST HS - QUEENS | SCA IEH | PO18-TEST AND ABATE PIPE INSULATION IF POSITIVE 3RD FLOOR KITCHEN DRAINPIPE (SPACE ID: 4341) PIPE LO | Construction | Complete | 9/5/2024 | IEH | 11/14/2024 | IEH | 0 | 0 | SCA0000073354
28 | Q505 | HILLCREST HS - QUEENS | SCA IEH | PO18-ABATE PIPE INSULATION AROUND 3 VALVES LOCATED IN THE CLOSET OF ROOM 158 | Construction | Complete | 10/2/2024 | IEH | 10/12/2024 | IEH | 0 | 0 | SCA0000073463
28 | Q505 | HILLCREST HS - QUEENS | SCA IEH | PO18-TEST FOR ACM/ABATE IF POSITIVE SPACE ID 4341E & 4341G BATHROOM FLOOR TILE AREAS MARKED WITH SPR | Construction | Complete | 10/21/2024 | IEH | 12/18/2024 | IEH | 0 | 0 | SCA0000073521
28 | Q505 | HILLCREST HS - QUEENS | Fast Track Projects | CTF-LYFE CENTER | Construction | In-Progress | 3/23/2017 | FTK |  | FTK | 143916 | 130352 | DSF0000843728
28 | Q505 | HILLCREST HS - QUEENS | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/21/2022 | DOER |  | DOER | 532548 | 0 | DSF0001033328
28 | Q505 | HILLCREST HS - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/27/2023 | DOER |  | DOER | 623121 | 0 | DSF0001036067
28 | Q505 | HILLCREST HS - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 9/7/2022 | DOES |  | DOES | 884052 | 0 | DSF0000912216
28 | Q505 | HILLCREST HS - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/5/2021 | DOES |  | DOES | 183590 | 0 | DSF0000913003
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Scope | Complete | 1/9/2024 | 4/4/2024 | 7/23/2024 | 0 | 0 | 120390 | DSF0001086563
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Design | In-Progress | 7/31/2024 | 1/3/2025 |  | 92767 | 92767 | 111924 | DSF0001086563
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 1360586 | 1360586 | 152 | DSF0001086563
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 92767 | 92767 | 16373 | DSF0001086563
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Scope | Complete | 4/15/2024 | 7/17/2024 | 9/19/2024 | 0 | 284 | 284 | DSF0001087095
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Design | In-Progress | 9/20/2024 | 1/28/2025 |  | 233 | 233 | 1137 | DSF0001087095
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 3414 | 3414 | 750 | DSF0001087095
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 233 | 233 | 6203 | DSF0001087095
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | Scope | Complete | 6/27/2022 | 11/10/2022 | 12/20/2022 | 149285 | 257811 | 247210 | DSF0000800312, DSF0001025748, DSF0001025749, DSF0001025750, DSF0001083880, DSF0001076588
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | Design | Complete | 1/24/2023 | 6/26/2023 | 5/10/2023 | 742837 | 754681 | 679238 | DSF0000800312, DSF0001025748, DSF0001025749, DSF0001025750, DSF0001083880, DSF0001076588
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | Construction | In-Progress | 7/17/2023 | 1/1/2026 |  | 16403796 | 14950496 | 7397710 | DSF0000800312, DSF0001025748, DSF0001025749, DSF0001025750, DSF0001083880, DSF0001076588
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | CM,F&E | In-Progress | 7/17/2023 | 1/1/2026 |  | 1071872 | 603508 | 442745 | DSF0000800312, DSF0001025748, DSF0001025749, DSF0001025750, DSF0001083880, DSF0001076588
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/16/2023 | 7/17/2023 | 3/21/2023 | 3581 | 826 | 826 | DSF0001034559
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/3/2023 | 16116 | 3304 | 3304 | DSF0001034559
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/20/2023 | 11/18/2024 |  | 207714 | 196070 | 103740 | DSF0001034559
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/20/2023 | 11/18/2024 |  | 99770 | 107983 | 80618 | DSF0001034559
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA IEH | PO18-77/28Q595/ABATE ACM PIPE INSULATION APPROX 40 FT CLASSROOM 205 CEILING CANNOT BE SPRAYED DO TO | Construction | Complete | 10/11/2024 | IEH | 10/12/2024 | IEH | 0 | 0 | SCA0000073500
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA IEH | PO18-ABATE SPACE ID: 2151. APPROX 12FT OF INSULATION. LEAK FROM 1ST FLOOR MENS STAFF BATHROOM. LINE | Construction | Complete | 11/7/2024 | IEH | 11/8/2024 | IEH | 0 | 0 | SCA0000073593
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA IEH | PO18-PLEASE ABATE AND REPAIR DAMAGED ACM WALL PLASTER ON WINDOW WALL #3 SIDE COVERED WITH PLASTIC SH | Construction | Complete | 12/13/2024 | IEH | 12/15/2024 | IEH | 0 | 0 | SCA0000073730
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113183
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/5/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085023
28 | Q608 | EZRA JACK KEATS PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/15/2024 | DOES | 7/24/2024 | DOES | 50832 | 7366 | DSF0001085531
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | Scope | Complete | 12/17/2019 | 4/21/2020 | 3/25/2020 | 12420 | 60529 | 60529 | DSF0000961191
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | Design | Complete | 3/25/2020 | 8/14/2020 | 6/30/2020 | 55890 | 225092 | 134977 | DSF0000961191
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | Construction | In-Progress | 2/25/2022 | 11/21/2022 |  | 720360 | 860691 | 544556 | DSF0000961191
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | CM,F&E | In-Progress | 2/25/2022 | 11/21/2022 |  | 133515 | 172620 | 158576 | DSF0000961191
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113671
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113671
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113671
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113671
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 7/28/2021 | 9/11/2023 | 9/21/2023 | 0 | 20650 | 20650 | DSF0000961423, DSF0001007742
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 9/22/2023 | 2/22/2024 | 4/23/2024 | 74118 | 69009 | 62994 | DSF0000961423, DSF0001007742
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 1087063 | 1087063 | 35277 | DSF0000961423, DSF0001007742
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 74118 | 80311 | 44262 | DSF0000961423, DSF0001007742
28 | Q620 | THOMAS A. EDISON HS - Q | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 50000 | 0 | DSF0000890420
28 | Q620 | THOMAS A. EDISON HS - Q | DOE - RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 8/27/2021 | DOER |  | DOER | 209223 | 0 | DSF0000890933
28 | Q620 | THOMAS A. EDISON HS - Q | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 12803 | 0 | DSF0001033330
28 | Q620 | THOMAS A. EDISON HS - Q | DOE - RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113185
28 | Q620 | THOMAS A. EDISON HS - Q | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/6/2023 | DOES |  | DOES | 754116 | 0 | DSF0000960866
28 | Q620 | THOMAS A. EDISON HS - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/8/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085026
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | Scope | Complete | 6/3/2021 | 11/3/2023 | 1/8/2024 | 128800 | 158171 | 155048 | DSF0000999284, DSF0001025878, DSF0001076715, DSF0001104663
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | Design | Complete | 1/19/2024 | 7/23/2024 | 5/15/2024 | 644000 | 704713 | 540026 | DSF0000999284, DSF0001025878, DSF0001076715, DSF0001104663
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | Construction | In-Progress | 8/26/2024 | 8/25/2026 |  | 14490000 | 13381345 | 179327 | DSF0000999284, DSF0001025878, DSF0001076715, DSF0001104663
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | CM,F&E | In-Progress | 8/26/2024 | 8/25/2026 |  | 901600 | 67788 | 67788 | DSF0000999284, DSF0001025878, DSF0001076715, DSF0001104663
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/1/2021 | EMER |  | EMER | 193599 | 44953 | SCA0000069409
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | Fast Track Projects | LSP - FY19 RESO A SCIENCE LAB UPGRADES | Construction | PNS | FTK | FTK | FTK | FTK | 13766 | 0 | DSF0000890938
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0000913462
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001008087
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/8/2024 | DOES | 7/12/2024 | DOES | 65832 | 9123 | DSF0001085028
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP | TENNIS COURT REMEDIATION | Scope | Complete | 4/30/2024 | 8/30/2024 | 11/1/2024 | 10333 | 55813 | 45137 | DSF0001085107
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP | TENNIS COURT REMEDIATION | Design | In-Progress | 11/19/2024 | 5/15/2025 |  | 51663 | 100560 | 14773 | DSF0001085107
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP | TENNIS COURT REMEDIATION | Construction | PNS | PNS | PNS | PNS | 1162413 | 1162413 | 21345 | DSF0001085107
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP | TENNIS COURT REMEDIATION | CM,F&E | PNS | PNS | PNS | PNS | 72328 | 72328 | 10227 | DSF0001085107
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/17/2023 | 6/21/2023 | 6/20/2023 | 0 | 12127 | 12127 | DSF0001036081
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 6/29/2023 | 11/15/2023 | 4/18/2024 | 48000 | 55784 | 4895 | DSF0001036081
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | In-Progress | 12/2/2024 | 9/27/2025 |  | 704000 | 459990 | 0 | DSF0001036081
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | CM,F&E | In-Progress | 12/2/2024 | 9/27/2025 |  | 48000 | 42422 | 7003 | DSF0001036081
28 | Q686 | I.S./H.S. 167 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Scope | Complete | 2/9/2023 | 5/10/2023 | 9/6/2023 | 0 | 77798 | 77798 | DSF0001036077
28 | Q686 | I.S./H.S. 167 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Design | PNS | PNS | PNS | PNS | 29562 | 4559 | 4559 | DSF0001036077
28 | Q686 | I.S./H.S. 167 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Construction | PNS | PNS | PNS | PNS | 433569 | 5246621 | 0 | DSF0001036077
28 | Q686 | I.S./H.S. 167 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | CM,F&E | PNS | PNS | PNS | PNS | 29562 | 357724 | 1594 | DSF0001036077
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 27000 | 0 | DSF0000889903
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 50000 | 0 | DSF0000890337
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 225000 | 0 | DSF0001033285
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 54175 | 0 | DSF0001036080
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001086572
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086573
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113189
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | DOE - RESOA | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/2/2021 | DOER |  | DOER | 163514 | 0 | DSF0000867308
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 200000 | 0 | DSF0001086574
28 | Q686 | I.S./H.S. 167 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113188
28 | Q686 | Q233 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113190
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0 | DSF0001113191
28 | Q690 | HS FOR LAW ENFORCEMENT - QUEENS | SCA CIP RESOA | FY24 RESO A ROOFTOP PLAYGROUND | Scope | Complete | 12/8/2023 | 4/25/2024 | 6/13/2024 | 0 | 34571 | 34388 | DSF0001086575
28 | Q690 | HS FOR LAW ENFORCEMENT - QUEENS | SCA CIP RESOA | FY24 RESO A ROOFTOP PLAYGROUND | Design | In-Progress | 6/25/2024 | 11/26/2024 |  | 90000 | 61462 | 18989 | DSF0001086575
28 | Q690 | HS FOR LAW ENFORCEMENT - QUEENS | SCA CIP RESOA | FY24 RESO A ROOFTOP PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 1320000 | 1320000 | 0 | DSF0001086575
28 | Q690 | HS FOR LAW ENFORCEMENT - QUEENS | SCA CIP RESOA | FY24 RESO A ROOFTOP PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 90000 | 90000 | 17014 | DSF0001086575
28 | Q690 | HS FOR LAW ENFORCEMENT - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/28/2024 | DOES | 9/16/2024 | DOES | 50832 |  | DSF0001085030
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113192
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 9000 | 9000 | 0 | DSF0001113192
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 132000 | 132000 | 0 | DSF0001113192
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 9000 | 9000 | 0 | DSF0001113192
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113672
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113672
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113672
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113672
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 400000 | 0 | DSF0001086577
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/18/2024 | DOES | 10/11/2024 | DOES | 50832 |  | DSF0001085031
28 | Q774 | QUEENS HS FOR THE SCIENCES - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 115000 | 0 | DSF0001033331
28 | Q814 | P.S. 82 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 10/23/2024 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000073530
28 | Q883 | ALTERNATE LEARNING CENTER - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/8/2024 | IEH | 8/15/2024 | IEH | 0 | 0 | SCA0000073265
28 | Q994 | I.S. 217 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 12/5/2024 | IEH | 12/22/2024 | IEH | 0 | 0 | SCA0000073669
29 | Q015 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/15/2023 | 12/15/2023 | 9/5/2023 | 3871 | 2333 | 2333 | DSF0001085323
29 | Q015 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/5/2023 | 3/5/2024 | 11/1/2023 | 17419 | 9331 | 9331 | DSF0001085323
29 | Q015 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/9/2024 | 1/3/2025 |  | 224510 | 207745 | 126784 | DSF0001085323
29 | Q015 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 2/9/2024 | 1/3/2025 |  | 69114 | 93669 | 91801 | DSF0001085323
29 | Q015 | P.S. 15 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/14/2024 | DIIR | 10/30/2024 | DIIR | 49074 | 49074 | DSF0001086348
29 | Q015 | P.S. 15 - QUEENS | DOE - RESOA | FY17 RESO A LIBRARY UPGRADES | Construction | In-Progress | 7/15/2022 | DOER |  | DOER | 180667 | 0 | DSF0000844891
29 | Q015 | P.S. 15 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 4/23/2024 | DOER | 9/26/2024 | DOER | 158260 |  | DSF0001035800
29 | Q015 | P.S. 15 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112935
29 | Q015 | P.S. 15 - QUEENS | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 2/28/2023 | DOES |  | DOES | 960706 | 0 | SCA0000070996
29 | Q015 | P.S. 15 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 2/21/2024 | DOES |  | DOES | 893504 | 1402 | DSF0001112132
29 | Q033 | P.S. 33 - QUEENS | Fast Track Projects | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 12/20/2018 | FTK |  | FTK | 132750 | 120118 | DSF0000890856
29 | Q033 | P.S. 33 - QUEENS | Fast Track Projects | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/16/2021 | FTK |  | FTK | 143407 | 142017 | DSF0000913368
29 | Q033 | P.S. 33 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 75000 | 12355 | DSF0001086359
29 | Q034 | P.S. 34 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 7/30/2021 | 12/16/2021 | 4/1/2022 | 6269 | 1297 | 6 | DSF0000995252
29 | Q034 | P.S. 34 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 4/1/2022 | 6/1/2022 | 4/1/2022 | 28213 | 20240 | 23 | DSF0000995252
29 | Q034 | P.S. 34 - QUEENS | SCA CIP | FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 363629 | 363629 | 51 | DSF0000995252
29 | Q034 | P.S. 34 - QUEENS | SCA CIP | FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 67397 | 67397 | 1216 | DSF0000995252
29 | Q034 | P.S. 34 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/2/2021 | 2/7/2022 | 2/3/2022 | 0 | 47263 | 47263 | DSF0000913369, DSF0000913370
29 | Q034 | P.S. 34 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 2/4/2022 | 6/6/2022 | 2/22/2022 | 73224 | 93228 | 50900 | DSF0000913369, DSF0000913370
29 | Q034 | P.S. 34 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 1073964 | 1014387 | 42694 | DSF0000913369, DSF0000913370
29 | Q034 | P.S. 34 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 73224 | 69163 | 31319 | DSF0000913369, DSF0000913370
29 | Q035 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 6/30/2022 | 12/27/2022 | 10/4/2022 | 109490 | 172195 | 156468 | DSF0000995279, DSF0001021034, DSF0001021035, DSF0001036330
29 | Q035 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Design | Complete | 10/14/2022 | 6/12/2023 | 4/26/2023 | 547449 | 542939 | 536661 | DSF0000995279, DSF0001021034, DSF0001021035, DSF0001036330
29 | Q035 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Construction | In-Progress | 7/12/2023 | 1/1/2025 |  | 12317625 | 11373863 | 6871163 | DSF0000995279, DSF0001021034, DSF0001021035, DSF0001036330
29 | Q035 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | CM,F&E | In-Progress | 7/12/2023 | 1/1/2025 |  | 767710 | 777425 | 658682 | DSF0000995279, DSF0001021034, DSF0001021035, DSF0001036330
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086360
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 18000 | 18000 | 0 | DSF0001086360
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 264000 | 264000 | 0 | DSF0001086360
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 18000 | 18000 | 0 | DSF0001086360
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087054
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087054
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087054
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087054
29 | Q035 | P.S. 35 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 8/22/2024 | FTK |  | FTK | 390307 | 59828 | DSF0001112051
29 | Q035 | P.S. 35 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/2/2023 | DIIR | 11/4/2024 | DIIR | 101634 | 101634 | DSF0001035816
29 | Q035 | P.S. 35 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 9/9/2024 | DIIR | 12/16/2024 | DIIR | 113000 | 113000 | DSF0001086361
29 | Q035 | P.S. 35 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112948
29 | Q035 | P.S. 35 - QUEENS | DOE - Skilled Trades | REPLACEMENT OF (5) ROOF TOPS UNITS | Construction | In-Progress | 6/4/2021 | DOES |  | DOES | 977340 | 0 | DSF0000900952
29 | Q036 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 3/1/2021 | 7/16/2021 | 10/26/2021 | 64814 | 138353 | 133111 | DSF0000946456, DSF0000946457, DSF0001021051
29 | Q036 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 11/3/2021 | 4/8/2022 | 3/24/2022 | 314425 | 388521 | 285594 | DSF0000946456, DSF0000946457, DSF0001021051
29 | Q036 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 7/18/2022 | 9/14/2024 |  | 6240379 | 6135100 | 2740545 | DSF0000946456, DSF0000946457, DSF0001021051
29 | Q036 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 7/18/2022 | 9/14/2024 |  | 526761 | 435546 | 420934 | DSF0000946456, DSF0000946457, DSF0001021051
29 | Q036 | P.S. 36 - QUEENS | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | In-Progress | 5/18/2023 |  |  | 100000 | 100000 | 100000 | DSF0001035229
29 | Q036 | P.S. 36 - QUEENS | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 2/13/2024 | DOEL |  | DOEL | 71647 | 71647
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 5/9/2017 | 10/10/2017 | 7/7/2017 | 154256 | 149205 | 149205 | DSF0000798349, DSF0000788217
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/14/2017 | 12/15/2017 | 11/6/2017 | 617025 | 584541 | 572580 | DSF0000798349, DSF0000788217
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 6/18/2018 | 12/9/2019 |  | 11569214 | 6811737 | 6575643 | DSF0000798349, DSF0000788217
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 6/18/2018 | 12/9/2019 |  | 719862 | 528275 | 518731 | DSF0000798349, DSF0000788217
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 8/15/2013 | 5/11/2015 | 11/3/2015 | 245222 | 260613 | 260613 | DSF0000777242, DSF0000788218, DSF0000844042, DSF0000811529, DSF0000833628, DSF0000833629
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | Design | Complete | 4/5/2016 | 9/2/2016 | 2/14/2017 | 967305 | 1045135 | 885375 | DSF0000777242, DSF0000788218, DSF0000844042, DSF0000811529, DSF0000833628, DSF0000833629
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | Construction | In-Progress | 7/18/2017 | 4/8/2019 |  | 16918073 | 15571860 | 14777595 | DSF0000777242, DSF0000788218, DSF0000844042, DSF0000811529, DSF0000833628, DSF0000833629
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | CM,F&E | In-Progress | 7/18/2017 | 4/8/2019 |  | 1320918 | 2060048 | 2052640 | DSF0000777242, DSF0000788218, DSF0000844042, DSF0000811529, DSF0000833628, DSF0000833629
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/30/2019 | 1/13/2020 | 9/10/2019 | 4431 | 2717 | 2717 | DSF0000912705, DSF0000914265
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 9/10/2019 | 2/13/2020 | 2/5/2020 | 19939 | 10936 | 10936 | DSF0000912705, DSF0000914265
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 10/15/2020 | 7/11/2021 |  | 256987 | 314455 | 299454 | DSF0000912705, DSF0000914265
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 10/15/2020 | 7/11/2021 |  | 47631 | 27127 | 27127 | DSF0000912705, DSF0000914265
29 | Q037 | P.S. 37 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 8/20/2024 | FTK |  | FTK | 150066 | 25288 | DSF0001112050
29 | Q037 | P.S. 37 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0 | DSF0001033747
29 | Q037 | P.S. 37 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001112949
29 | Q037 | P.S. 37 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/28/2021 | DOES |  | DOES | 200833 | 0 | DSF0001008704
29 | Q037 | P.S. 37 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/27/2024 | DOES |  | DOES | 1852154 | 0 | DSF0001112144
29 | Q038 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | Scope | Complete | 5/11/2021 | 9/24/2021 | 12/7/2021 | 152878 | 141155 | 141155 | DSF0000995332, DSF0000995334, DSF0000995335, DSF0000995336, DSF0001021100, DSF0001034685
29 | Q038 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | Design | Complete | 12/10/2021 | 5/13/2022 | 10/6/2022 | 754443 | 710096 | 643081 | DSF0000995332, DSF0000995334, DSF0000995335, DSF0000995336, DSF0001021100, DSF0001034685
29 | Q038 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | Construction | In-Progress | 2/6/2023 | 3/26/2025 |  | 16114442 | 14570221 | 10113804 | DSF0000995332, DSF0000995334, DSF0000995335, DSF0000995336, DSF0001021100, DSF0001034685
29 | Q038 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | CM,F&E | In-Progress | 2/6/2023 | 3/26/2025 |  | 1144755 | 241698 | 187459 | DSF0000995332, DSF0000995334, DSF0000995335, DSF0000995336, DSF0001021100, DSF0001034685
29 | Q038 | P.S. 38 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112950
29 | Q038 | P.S. 38 - QUEENS | DOE - Skilled Trades | BOILER BLOWBACK | Construction | In-Progress | 11/16/2018 | DOES |  | DOES | 1090118 | 0 | SCA0000055065
29 | Q038 | P.S. 38 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/29/2021 | DOES |  | DOES | 196755 | 0 | DSF0001008705
29 | Q038 | P.S. 38 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/16/2023 | DOES |  | DOES | 228083 | 0 | DSF0001034422
29 | Q052 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 8/30/2019 | 1/6/2020 | 9/9/2019 | 2279 | 1963 | 1963 | DSF0000912706
29 | Q052 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 9/9/2019 | 2/12/2020 | 2/5/2020 | 10256 | 7937 | 7937 | DSF0000912706
29 | Q052 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 10/15/2020 | 7/11/2021 |  | 132185 | 191081 | 182175 | DSF0000912706
29 | Q052 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 10/15/2020 | 7/11/2021 |  | 24500 | 18795 | 18795 | DSF0000912706
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112963
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112963
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001112963
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112963
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113630
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113630
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113630
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113630
29 | Q052 | P.S. 52 - QUEENS | SCA IEH | PO18-AHERA BOOK IS FROM 2014 TEST ALL LAYERS IF POSITIVE ABATE AND REPLACE PLEASE ABATE 12X12 FLOOR | Construction | Complete | 10/2/2024 | IEH | 12/8/2024 | IEH | 0 | 0 | SCA0000073466
29 | Q052 | P.S. 52 - QUEENS | DIIT - Project Connect | DATA/VOICE & WIRELESS NETWORK CABLE WIRING, NETWORK SERVER EQUIPMENT, DATA/VOICE & WIRELESS NETWORK | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 276115 | 0 | DSF0000800163
29 | Q052 | P.S. 52 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 336680 | 0 | DSF0000960091
29 | Q052 | P.S. 52 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0 | DSF0001035333
29 | Q052 | P.S. 52 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 194290 | 0 | DSF0001086366
29 | Q052 | P.S. 52 - QUEENS | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100733 | 0 | DSF0001086367
29 | Q052 | P.S. 52 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/1/2022 | DOES |  | DOES | 58041 | 0 | DSF0001009190
29 | Q059 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 5/4/2023 | 96428 | 146906 | 146906 | DSF0001021426, DSF0001021427, DSF0001021428
29 | Q059 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 5/22/2023 | 10/24/2023 | 10/23/2023 | 482141 | 457002 | 371902 | DSF0001021426, DSF0001021427, DSF0001021428
29 | Q059 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 6/15/2024 | 3/6/2026 |  | 10848150 | 10000069 | 989200 | DSF0001021426, DSF0001021427, DSF0001021428
29 | Q059 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 6/15/2024 | 3/6/2026 |  | 674996 | 92608 | 90826 | DSF0001021426, DSF0001021427, DSF0001021428
29 | Q059 | I.S. 59 - QUEENS | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE | Scope | Complete | 2/22/2021 | 6/22/2021 | 7/20/2021 | 0 | 18081 | 18081 | DSF0000913378
29 | Q059 | I.S. 59 - QUEENS | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE | Design | Complete | 1/4/2022 | 5/19/2022 | 7/13/2022 | 54182 | 65570 | 65570 | DSF0000913378
29 | Q059 | I.S. 59 - QUEENS | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | Complete | 2/27/2023 | 11/23/2023 | 9/7/2023 | 794666 | 628242 | 578069 | DSF0000913378
29 | Q059 | I.S. 59 - QUEENS | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE | CM,F&E | Complete | 2/27/2023 | 11/23/2023 | 9/7/2023 | 195277 | 229064 | 180283 | DSF0000913378
29 | Q059 | I.S. 59 - QUEENS | SCA IEH | PO18-ABATE AND REMOVE PIPE INSULATION ROOM B21 MECH/FAN RM AUDI & GYM UNIT - 11 VALVE FOR PIPES, 8 S | Construction | Complete | 7/2/2024 | IEH | 9/22/2024 | IEH | 0 | 0 | SCA0000073115
29 | Q059 | I.S. 59 - QUEENS | SCA IEH | PO18-77/29Q059/LOOSE 9X9 FLOOR TILE G.O. ROOM 328 ROOM IS CLOSED DUE TO THE LOOSE TILE THIS IS THE M | Construction | Complete | 11/12/2024 | IEH | 12/26/2024 | IEH | 0 | 0 | SCA0000073601
29 | Q059 | I.S. 59 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 359533 | 0 | DSF0000960096
29 | Q059 | I.S. 59 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/5/2024 | DIIR | 10/26/2024 | DIIR | 65000 | 65000 | DSF0001033759
29 | Q059 | I.S. 59 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/7/2024 | DIIR | 10/26/2024 | DIIR | 197000 | 197000 | DSF0001035832
29 | Q059 | EAGLE ACADEMY III - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001112967
29 | Q059 | I.S. 59 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 410195 | 0 | DSF0001086371
29 | Q059 | I.S. 59 - QUEENS | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001112968
29 | Q059 | I.S. 59 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 1/24/2023 | DOES |  | DOES | 60651 | 0 | DSF0000866127
29 | Q059 | I.S. 59 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/11/2024 | DOES | 10/21/2024 | DOES | 65832 | 17077 | DSF0001084800
29 | Q059 | I.S. 59 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/17/2024 | DOES |  | DOES | 595602 | 0 | DSF0001111853
29 | Q095 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | Scope | Complete | 4/28/2022 | 11/29/2022 | 11/14/2022 | 1076660 | 1033965 | 801418 | DSF0001034477, DSF0001034477, DSF0001034477, DSF0001034477, DSF0001034477
29 | Q095 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | Design | Complete | 11/14/2022 | 5/18/2023 | 4/28/2023 | 4844970 | 2366961 | 1541757 | DSF0001034477, DSF0001034477, DSF0001034477, DSF0001034477, DSF0001034477
29 | Q095 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | Construction | In-Progress | 9/18/2023 | 9/3/2026 |  | 61100455 | 55668153 | 6651862 | DSF0001034477, DSF0001034477, DSF0001034477, DSF0001034477, DSF0001034477
29 | Q095 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | CM,Art,F&E | In-Progress | 9/18/2023 | 9/3/2026 |  | 8613281 | 4310863 | 1454480 | DSF0001034477, DSF0001034477, DSF0001034477, DSF0001034477, DSF0001034477
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Scope | Complete | 8/26/2022 | 12/30/2022 | 11/14/2022 | 31548 | 70967 | 66622 | DSF0001034477
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Design | Complete | 5/4/2023 | 11/20/2023 | 4/1/2024 | 157740 | 198665 | 102553 | DSF0001034477
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Construction | PNS | PNS | PNS | PNS | 3549139 | 3549139 | 4154 | DSF0001034477
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | CM,F&E | PNS | PNS | PNS | PNS | 220835 | 220835 | 47632 | DSF0001034477
29 | Q095 | P.S. 95 - QUEENS | SCA IEH | PO18-ABATE & REMOVE PIPE INSULATION IN RM 213 CEILING FOR ACM | Construction | Complete | 11/5/2024 | IEH | 11/26/2024 | IEH | 0 | 0 | SCA0000073572
29 | Q095 | P.S. 95 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 11/30/2021 | FTK |  | FTK | 251562 | 228576 | DSF0000960586
29 | Q095 | P.S. 95 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 6/24/2024 | DIIR |  | DIIR | 64480 | 0 | DSF0001033789
29 | Q095 | P.S. 95 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113000
29 | Q095 | P.S. 95 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001112999
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | Scope | Complete | 3/16/2021 | 7/29/2021 | 12/7/2021 | 124001 | 208925 | 208925 | DSF0000947631, DSF0000947627, DSF0000947629, DSF0001034351
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | Design | Complete | 12/8/2021 | 5/11/2022 | 5/10/2022 | 620000 | 409334 | 409334 | DSF0000947631, DSF0000947627, DSF0000947629, DSF0001034351
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | Construction | In-Progress | 11/28/2022 | 11/16/2024 |  | 13950000 | 12718482 | 11774657 | DSF0000947631, DSF0000947627, DSF0000947629, DSF0001034351
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | CM,F&E | In-Progress | 11/28/2022 | 11/16/2024 |  | 868000 | 257060 | 157952 | DSF0000947631, DSF0000947627, DSF0000947629, DSF0001034351
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2/14/2022 | 5/13/2022 | 4/18/2022 | 16059 | 12451 | 12451 | DSF0001022311
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 4/19/2022 | 9/19/2022 | 9/21/2022 | 80295 | 49800 | 49800 | DSF0001022311
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | PNS | PNS | PNS | PNS | 1806635 | 1806635 | 7867 | DSF0001022311
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 112413 | 112413 | 20137 | DSF0001022311
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/6/2019 | 3/25/2020 | 11/21/2019 | 5030 | 6265 | 6265 | DSF0000912712, DSF0000960471
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 11/21/2019 | 4/24/2020 | 2/5/2020 | 22635 | 25126 | 25126 | DSF0000912712, DSF0000960471
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 10/15/2020 | 7/11/2021 |  | 291749 | 394917 | 376138 | DSF0000912712, DSF0000960471
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 10/15/2020 | 7/11/2021 |  | 54074 | 32442 | 32442 | DSF0000912712, DSF0000960471
29 | Q109 | I.S. 109 - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 133000 | 0 | DSF0000913399
29 | Q109 | I.S. 109 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 8/27/2024 | DIIR | 113000 | 113000 | DSF0001086403
29 | Q109 | I.S. 109 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113007
29 | Q109 | I.S. 109 - QUEENS | DOE - RESOA | FY16 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 1/31/2018 | DOER |  | DOER | 124328 | 0 | DSF0000822868
29 | Q109 | I.S. 109 - QUEENS | DOE - RESOA | FY22 RESO A LOCKER ROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 328116 | 0 | DSF0001033797
29 | Q109 | I.S. 109 - QUEENS | DOE - RESOA | FY23 RESO A LOCKER ROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001035233
29 | Q109 | I.S. 109 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/7/2024 | DOES | 8/30/2024 | DOES | 65832 |  | DSF0001084807
29 | Q109 | I.S. 109 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/30/2024 | DOES |  | DOES | 592515 | 0 | DSF0001100855
29 | Q116 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | Scope | Complete | 5/10/2022 | 4/17/2023 | 2/17/2023 | 1296661 | 829815 | 824513 | DSF0000911863, DSF0000911863, DSF0000911863, DSF0000911863, DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | Design | Complete | 2/21/2023 | 8/23/2023 | 4/20/2023 | 5834970 | 2302551 | 1520844 | DSF0000911863, DSF0000911863, DSF0000911863, DSF0000911863, DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | Construction | In-Progress | 12/15/2023 | 9/3/2026 |  | 73585455 | 65331739 | 16748911 | DSF0000911863, DSF0000911863, DSF0000911863, DSF0000911863, DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | CM,Art,F&E | In-Progress | 12/15/2023 | 9/3/2026 |  | 10373281 | 4372225 | 1006539 | DSF0000911863, DSF0000911863, DSF0000911863, DSF0000911863, DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION/PROGRAM ACCESSIBILITY | Scope | Complete | 5/26/2023 | 10/26/2023 | 10/2/2023 | 46664 | 45252 | 45252 | DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION/PROGRAM ACCESSIBILITY | Design | Complete | 10/10/2023 | 3/14/2024 | 8/26/2024 | 233321 | 160551 | 88577 | DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION/PROGRAM ACCESSIBILITY | Construction | PNS | PNS | PNS | PNS | 5249718 | 5249718 | 379727 | DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION/PROGRAM ACCESSIBILITY | CM,F&E | PNS | PNS | PNS | PNS | 326649 | 326649 | 45595 | DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 7/5/2022 | 7/5/2022 | 7/5/2022 | 46456 | 2807 | 2807 | DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 7/6/2022 | 9/16/2022 | 10/25/2022 | 232280 | 327612 | 309730 | DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 4/10/2023 | 7/2/2024 |  | 5226300 | 5250025 | 3256786 | DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 4/10/2023 | 7/2/2024 |  | 325192 | 517295 | 513133 | DSF0000911863
29 | Q116 | P.S. 116 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 385395 | 0 | DSF0000960123
29 | Q116 | P.S. 116 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086410
29 | Q116 | P.S. 116 - QUEENS | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001113014
29 | Q116 | P.S. 116 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/3/2024 | DOES | 10/16/2024 | DOES | 65832 | 11279 | DSF0001084665
29 | Q118 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/21/2021 | 11/4/2021 | 1/26/2022 | 156001 | 231097 | 231091 | DSF0000947762, DSF0000947763, DSF0000947764, DSF0000947765
29 | Q118 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/27/2022 | 6/28/2022 | 5/11/2022 | 780000 | 554099 | 546598 | DSF0000947762, DSF0000947763, DSF0000947764, DSF0000947765
29 | Q118 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 8/15/2022 | 5/5/2024 |  | 17550000 | 16619998 | 13034303 | DSF0000947762, DSF0000947763, DSF0000947764, DSF0000947765
29 | Q118 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/15/2022 | 5/5/2024 |  | 1093229 | 784438 | 764022 | DSF0000947762, DSF0000947763, DSF0000947764, DSF0000947765
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/30/2023 | 3/4/2024 | 5/31/2024 | 0 | 87277 | 59427 | DSF0001086411
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 9/11/2024 | 1/30/2025 |  | 59654 | 12421 | 12421 | DSF0001086411
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 874927 | 874927 | 0 | DSF0001086411
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 59654 | 59654 | 13790 | DSF0001086411
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/2/2024 | 7/2/2024 | 6/10/2024 | 0 | 0 | 616 | DSF0001087060
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | In-Progress | 10/11/2024 | 2/11/2025 |  | 346 | 346 | 2464 | DSF0001087060
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 5073 | 5073 | 0 | DSF0001087060
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 346 | 346 | 836 | DSF0001087060
29 | Q118 | P.S. 118 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 273148 | 140238 | DSF0000960806
29 | Q118 | P.S. 118 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 165000 | 0 | DSF0001033274
29 | Q118 | P.S. 118 - QUEENS | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 41943 | 0 | DSF0001033276
29 | Q118 | P.S. 118 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 8/14/2023 | DOER | 10/23/2024 | DOER | 189056 |  | DSF0001035880
29 | Q118 | P.S. 118 - QUEENS | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035881
29 | Q118 | P.S. 118 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 200000 | 0 | DSF0001022466
29 | Q131 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | Scope | Complete | 12/19/2017 | 5/31/2023 | 8/4/2023 | 146611 | 302796 | 296189 | DSF0000843904, DSF0000960540, DSF0000996903, DSF0000996901, DSF0001073502
29 | Q131 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | Design | Complete | 8/4/2023 | 12/21/2023 | 4/30/2024 | 733051 | 646606 | 553179 | DSF0000843904, DSF0000960540, DSF0000996903, DSF0000996901, DSF0001073502
29 | Q131 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | Construction | In-Progress | 8/19/2024 | 5/10/2026 |  | 16493625 | 15255520 | 86480 | DSF0000843904, DSF0000960540, DSF0000996903, DSF0000996901, DSF0001073502
29 | Q131 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | CM,F&E | In-Progress | 8/19/2024 | 5/10/2026 |  | 1026270 | 279655 | 275194 | DSF0000843904, DSF0000960540, DSF0000996903, DSF0000996901, DSF0001073502
29 | Q131 | P.S. 131 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | Complete | 12/13/2021 | FTK | 8/13/2024 | FTK | 285896 | 243446 | DSF0000960809
29 | Q131 | P.S. 131 - QUEENS | Fast Track Projects | LSP- VACUUM PUMP REPLACEMENT | Construction | In-Progress | 9/11/2023 | FTK |  | FTK | 98339 | 86042 | DSF0001022705
29 | Q131 | P.S. 131 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 64000 | 0 | DSF0001113027
29 | Q131 | P.S. 131 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | Complete | 12/1/2022 | DOER | 12/20/2023 | DOER | 135304 | 54442 | DSF0001008074
29 | Q131 | P.S. 131 - QUEENS | DOE - Skilled Trades | BROKEN SEWER LINE REPLACEMENT | Construction | In-Progress | 12/20/2024 | DOES |  | DOES | 110000 | 0 | DSF0001113914
29 | Q132 | P.S. 132 - QUEENS | SCA CIP RESOA | FY18 RESO A KITCHEN AREAS | Scope | Complete | 2/1/2018 | 4/5/2018 | 5/2/2018 | 0 | 29628 | 29628 | DSF0000867322
29 | Q132 | P.S. 132 - QUEENS | SCA CIP RESOA | FY18 RESO A KITCHEN AREAS | Design | Complete | 5/15/2018 | 10/16/2018 | 5/6/2019 | 259352 | 330417 | 290629 | DSF0000867322
29 | Q132 | P.S. 132 - QUEENS | SCA CIP RESOA | FY18 RESO A KITCHEN AREAS | Construction | In-Progress | 7/12/2021 | 1/12/2023 |  | 3803824 | 3563570 | 3256496 | DSF0000867322
29 | Q132 | P.S. 132 - QUEENS | SCA CIP RESOA | FY18 RESO A KITCHEN AREAS | CM,F&E | In-Progress | 7/12/2021 | 1/12/2023 |  | 259352 | 484338 | 472230 | DSF0000867322
29 | Q132 | P.S. 132 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001033811
29 | Q132 | P.S. 132 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/29/2023 | DOER |  | DOER | 313447 | 0 | DSF0001035899
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | Scope | Complete | 2/15/2019 | 9/15/2021 | 11/23/2021 | 254504 | 171519 | 171519 | DSF0000879647, DSF0000948069, DSF0000961140, DSF0000996968
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | Design | Complete | 12/3/2021 | 5/23/2022 | 3/1/2023 | 1266898 | 829120 | 740158 | DSF0000879647, DSF0000948069, DSF0000961140, DSF0000996968
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | Construction | In-Progress | 7/13/2023 | 7/1/2025 |  | 28018687 | 26925078 | 17807815 | DSF0000879647, DSF0000948069, DSF0000961140, DSF0000996968
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | CM,F&E | In-Progress | 7/13/2023 | 7/1/2025 |  | 1823719 | 439302 | 330224 | DSF0000879647, DSF0000948069, DSF0000961140, DSF0000996968
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/19/2022 | 4/20/2023 | 1/3/2023 | 4051 | 3715 | 3715 | DSF0001034577
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/3/2023 | 6/29/2023 | 5/3/2023 | 18230 | 14860 | 14860 | DSF0001034577
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/20/2023 | 11/18/2024 |  | 234963 | 216369 | 123148 | DSF0001034577
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/20/2023 | 11/18/2024 |  | 117597 | 119198 | 111015 | DSF0001034577
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113029
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113029
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001113029
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113029
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113641
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113641
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113641
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113641
29 | Q134 | P.S. 134 - QUEENS | SCA IEH | PO18-TEST LEAKING PIPE RM 217 &IF POSITIVE ABATE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | Complete | 11/6/2024 | IEH | 12/24/2024 | IEH | 0 | 0 | SCA0000073581
29 | Q134 | P.S. 134 - QUEENS | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER | Construction | In-Progress | 5/15/2023 | FTK |  | FTK | 348895 | 65686 | DSF0001022774
29 | Q134 | Q233 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001086422
29 | Q134 | P.S. 134 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113030
29 | Q134 | P.S. 134 - QUEENS | DOE - RESOA | FY09 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 17503 | 0 | DSF0000623136
29 | Q134 | P.S. 134 - QUEENS | DOE - RESOA | FY23 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001035903
29 | Q134 | P.S. 134 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/26/2024 | DOER |  | DOER | 180584 | 0 | DSF0001035904
29 | Q135 | P.S. 135 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/15/2024 | 12/17/2024 | 8/21/2024 | 5572 | 945 | 945 | DSF0001087521
29 | Q135 | P.S. 135 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 8/21/2024 | 2/20/2025 |  | 25076 | 25076 | 3780 | DSF0001087521
29 | Q135 | P.S. 135 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 323197 | 323197 | 0 | DSF0001087521
29 | Q135 | P.S. 135 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 64167 | 64167 | 8293 | DSF0001087521
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113031
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113031
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001113031
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113031
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113642
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113642
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113642
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113642
29 | Q135 | P.S. 135 - QUEENS | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 6/3/2021 | FTK | 4/11/2024 | FTK | 304848 | 297165 | DSF0000961558
29 | Q135 | P.S. 135 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113032
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 5/17/2019 | 10/2/2019 | 9/5/2019 | 126420 | 155631 | 153078 | DSF0000912356, DSF0000914286
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 9/25/2019 | 3/17/2020 | 7/1/2020 | 632103 | 691976 | 670526 | DSF0000912356, DSF0000914286
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | In-Progress | 6/30/2022 | 2/13/2025 |  | 14222328 | 12888717 | 7151244 | DSF0000912356, DSF0000914286
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | In-Progress | 6/30/2022 | 2/13/2025 |  | 884945 | 169629 | 168994 | DSF0000912356, DSF0000914286
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/16/2024 | 12/18/2024 | 8/22/2024 | 5090 | 1172 | 1172 | DSF0001087522
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | In-Progress | 8/22/2024 | 2/21/2025 |  | 22903 | 22903 | 4690 | DSF0001087522
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | PNS | PNS | PNS | PNS | 295192 | 295192 | 0 | DSF0001087522
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | PNS | PNS | PNS | PNS | 58976 | 58976 | 7056 | DSF0001087522
29 | Q136 | P.S. 136 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 1/29/2024 | 5/29/2024 | 7/9/2024 | 0 | 21661 | 21599 | DSF0001086425
29 | Q136 | P.S. 136 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 7/15/2024 | 11/29/2024 |  | 60000 | 54465 | 13333 | DSF0001086425
29 | Q136 | P.S. 136 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 1684 | DSF0001086425
29 | Q136 | P.S. 136 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 11842 | DSF0001086425
29 | Q136 | P.S. 136 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 12/20/2024 | DIIR | 350000 | 350000 | DSF0001086424
29 | Q138 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 6/9/2022 | 12/5/2022 | 10/11/2022 | 249042 | 291895 | 273291 | DSF0001022860, DSF0001022859, DSF0001022858, DSF0001022857, DSF0001022855
29 | Q138 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 10/14/2022 | 6/12/2023 | 4/18/2023 | 1238169 | 593429 | 593429 | DSF0001022860, DSF0001022859, DSF0001022858, DSF0001022857, DSF0001022855
29 | Q138 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Construction | In-Progress | 7/21/2023 | 7/19/2026 |  | 27249649 | 24641888 | 12749106 | DSF0001022860, DSF0001022859, DSF0001022858, DSF0001022857, DSF0001022855
29 | Q138 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | CM,F&E | In-Progress | 7/21/2023 | 7/19/2026 |  | 1796112 | 439587 | 311152 | DSF0001022860, DSF0001022859, DSF0001022858, DSF0001022857, DSF0001022855
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/15/2023 | 4/18/2024 | 4/10/2024 | 0 | 19033 | 19033 | DSF0001086428
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 4/22/2024 | 9/6/2024 |  | 76616 | 57583 | 19791 | DSF0001086428
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 1123708 | 1123708 | 7365 | DSF0001086428
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 76616 | 76616 | 9130 | DSF0001086428
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 4/3/2024 | 7/5/2024 | 7/23/2024 | 0 | 0 | 1013 | DSF0001087062
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | In-Progress | 7/23/2024 | 11/25/2024 |  | 1384 | 1384 | 4052 | DSF0001087062
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 20292 | 20292 | 0 | DSF0001087062
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 1384 | 1384 | 2002 | DSF0001087062
29 | Q138 | P.S. 138 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 78000 | 0 | DSF0001086427
29 | Q138 | P.S. 138 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/5/2024 | DOES | 9/13/2024 | DOES | 65832 |  | DSF0001084670
29 | Q147 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/19/2022 | 12/5/2022 | 6/12/2023 | 56463 | 135257 | 132820 | DSF0001023043, DSF0001023044, DSF0001023045
29 | Q147 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 7/5/2023 | 12/6/2023 | 12/8/2023 | 282314 | 322959 | 252585 | DSF0001023043, DSF0001023044, DSF0001023045
29 | Q147 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 4/29/2024 | 10/20/2025 |  | 6352043 | 5917942 | 510552 | DSF0001023043, DSF0001023044, DSF0001023045
29 | Q147 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 4/29/2024 | 10/20/2025 |  | 395238 | 177481 | 169266 | DSF0001023043, DSF0001023044, DSF0001023045
29 | Q147 | P.S. 147 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION- SPALLED CONCRETE @ Q147 | Construction | In-Progress | 9/6/2022 | EMER |  | EMER | 202102 | 137224 | SCA0000071435
29 | Q147 | P.S. 147 - QUEENS | SCA IEH | PO18-ABATE VALVE AND PIPE INSULATION LOCATED IN BASEMENT BOILER ROOM 4FT OF INSULATION (MARKED WITH | Construction | Complete | 8/28/2024 | IEH | 9/28/2024 | IEH | 0 | 0 | SCA0000073330
29 | Q147 | P.S. 147 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 100000 | 0 | DSF0001033821
29 | Q147 | P.S. 147 - QUEENS | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 287000 | 0 | DSF0001035916
29 | Q147 | P.S. 147 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 150000 | 0 | DSF0001086436
29 | Q147 | P.S. 147 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 222000 | 0 | DSF0001087167
29 | Q147 | P.S. 147 - QUEENS | DOE - RESOA | RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001111818
29 | Q147 | P.S. 147 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/13/2024 | DOES | 9/13/2024 | DOES | 65832 | 20407 | DSF0001084672
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE / PATH OF TRAVEL RESO A COMPUTER LAB UPGRADE | Scope | Complete | 2/6/2023 | 6/6/2023 | 5/23/2023 | 0 | 26969 | 26969 | DSF0001035925, DSF0001035926
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE / PATH OF TRAVEL RESO A COMPUTER LAB UPGRADE | Design | Complete | 5/30/2023 | 10/30/2023 | 11/15/2023 | 45913 | 87822 | 69165 | DSF0001035925, DSF0001035926
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE / PATH OF TRAVEL RESO A COMPUTER LAB UPGRADE | Construction | In-Progress | 6/21/2024 | 4/16/2025 |  | 673393 | 491843 | 14248 | DSF0001035925, DSF0001035926
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE / PATH OF TRAVEL RESO A COMPUTER LAB UPGRADE | CM,F&E | In-Progress | 6/21/2024 | 4/16/2025 |  | 45913 | 51558 | 15754 | DSF0001035925, DSF0001035926
29 | Q156 | P.S. 156 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 95000 | 0 | DSF0001113051
29 | Q156 | QUEENS UNITED MIDDLE SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113052
29 | Q156 | QUEENS UNITED MIDDLE SCHOOL | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 10/4/2023 | DOER |  | DOER | 396055 | 0 | DSF0001034939
29 | Q156 | QUEENS UNITED MIDDLE SCHOOL | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/11/2024 | DOER |  | DOER | 216517 | 0 | DSF0001034938
29 | Q156 | QUEENS UNITED MIDDLE SCHOOL | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/7/2024 | DOER |  | DOER | 357837 | 0 | DSF0001034936
29 | Q156 | P.S. 156 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 11/22/2021 | DOES |  | DOES | 94118 | 0 | DSF0001009189
29 | Q156 | P.S. 156 - QUEENS | DOE - Skilled Trades | CAFETERIA CEILING TILE REPLACEMENT | Construction | In-Progress | 12/12/2023 | DOES |  | DOES | 133327 | 0 | DSF0001111877
29 | Q176 | P.S. 176 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/26/2013 | 2/28/2014 | 2/28/2014 | 52357 | 97432 | 97432 | DSF0000777287
29 | Q176 | P.S. 176 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | Complete | 3/26/2014 | 8/8/2014 | 9/26/2014 | 261784 | 283707 | 283707 | DSF0000777287
29 | Q176 | P.S. 176 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 5890146 | 5890146 | 6152 | DSF0000777287
29 | Q176 | P.S. 176 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 366498 | 366498 | 41139 | DSF0000777287
29 | Q176 | P.S. 176 - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/18/2023 | DIIR | 12/18/2024 | DIIR | 250000 | 250000 | DSF0001111931
29 | Q176 | P.S. 176 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001113068
29 | Q176 | P.S. 176 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 84383 | 0 | DSF0001086459
29 | Q181 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/14/2020 | 5/29/2020 | 6/21/2021 | 99024 | 93270 | 93270 | DSF0000948892, DSF0000997818, DSF0001009253, DSF0000997826
29 | Q181 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | Design | Complete | 7/26/2021 | 12/28/2021 | 2/28/2022 | 486988 | 337674 | 337674 | DSF0000948892, DSF0000997818, DSF0001009253, DSF0000997826
29 | Q181 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 7/13/2022 | 4/2/2024 |  | 10253598 | 9297308 | 8609919 | DSF0000948892, DSF0000997818, DSF0001009253, DSF0000997826
29 | Q181 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 7/13/2022 | 4/2/2024 |  | 754182 | 856777 | 844824 | DSF0000948892, DSF0000997818, DSF0001009253, DSF0000997826
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 6/24/2024 | 10/24/2024 | 10/3/2024 | 0 | 20810 | 13007 | DSF0001086463
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | In-Progress | 10/3/2024 | 2/24/2025 |  | 21000 | 21000 | 42414 | DSF0001086463
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 308000 | 308000 | 0 | DSF0001086463
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 21000 | 21000 | 12203 | DSF0001086463
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | In-Progress | 9/26/2024 | 12/30/2024 |  | 0 | 940 | 940 | DSF0001087069
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 3762 | 3762 | DSF0001087069
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087069
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 3240 | 3240 | DSF0001087069
29 | Q181 | P.S. 181 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | Complete | 3/6/2023 | FTK | 11/15/2024 | FTK | 102153 | 79461 | DSF0000997819
29 | Q181 | P.S. 181 - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 265000 | 0 | DSF0001113885
29 | Q181 | P.S. 181 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/19/2022 | DOES |  | DOES | 140433 | 0 | DSF0001009191
29 | Q192 | I.S. 192 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 11/15/2024 | FTK |  | FTK | 32524 | 1979 | DSF0001112053
29 | Q192 | I.S. 192 - QUEENS | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 45107 | 0 | DSF0001035961
29 | Q192 | I.S. 192 - QUEENS | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035240
29 | Q192 | PATHWAYS COLL. PREP SCHOOL - Q | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035242
29 | Q192 | I.S. 192 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 453246 | 0 | DSF0001086468
29 | Q192 | PATHWAYS COLL. PREP SCHOOL - Q | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113078
29 | Q192 | I.S. 192 - QUEENS | DOE - Skilled Trades | DOMESTIC HOT WATER HOLDING TANK | Construction | In-Progress | 9/11/2020 | DOES |  | DOES | 21964 | 0 | DSF0000960973
29 | Q192 | I.S. 192 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/26/2023 | DOES | 11/14/2023 | DOES | 637315 | 555258 | DSF0001035088
29 | Q192 | I.S. 192 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/22/2024 | DOES | 8/14/2024 | DOES | 65832 |  | DSF0001084995
29 | Q192 | I.S. 192 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 4/2/2024 | DOES |  | DOES | 187294 | 1433 | DSF0001112165
29 | Q195 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | Scope | Complete | 8/2/2019 | 12/19/2019 | 5/24/2021 | 80105 | 68480 | 61924 | DSF0000903482, DSF0000998042, DSF0001023907
29 | Q195 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | Design | Complete | 5/26/2021 | 10/27/2021 | 5/12/2022 | 400526 | 377821 | 377821 | DSF0000903482, DSF0000998042, DSF0001023907
29 | Q195 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | Construction | In-Progress | 7/27/2022 | 1/17/2024 |  | 9011847 | 8245300 | 6269225 | DSF0000903482, DSF0000998042, DSF0001023907
29 | Q195 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | CM,F&E | In-Progress | 7/27/2022 | 1/17/2024 |  | 561944 | 733451 | 725423 | DSF0000903482, DSF0000998042, DSF0001023907
29 | Q195 | P.S. 195 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 200000 | 198791 | DSF0001035965
29 | Q195 | P.S. 195 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 255000 | 0 | DSF0001113081
29 | Q195 | P.S. 195 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 1/31/2024 | DOES |  | DOES | 90594 | 8615 | DSF0001112166
29 | Q231 | I.S. 231 - QUEENS | DIIT - RESOA | FY10 RESO A- DESKTOP COMPUTERS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500 | 0 | DSF0000709474
29 | Q231 | COLLABORATIVE ARTS MIDDLE SCHOOL - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0 | DSF0001113110
29 | Q231 | COMMUNITY VOICES MIDDLE SCHOOL - QUEENS | DOE - RESOA | FY16 RESO A MULTI-MEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 73649 | 0 | DSF0000889290
29 | Q231 | COMMUNITY VOICES MIDDLE SCHOOL - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 70941 | 0 | DSF0001112220
29 | Q231 | COLLABORATIVE ARTS MIDDLE SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/17/2024 | DOES | 11/22/2024 | DOES | 65832 | 13781 | DSF0001084826
29 | Q231 | COLLABORATIVE ARTS MIDDLE SCHOOL - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/2/2024 | DOES |  | DOES | 705476 | 0 | DSF0001085757
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/8/2018 | 3/26/2019 | 3/1/2019 | 208401 | 139787 | 124981 | DSF0000881133, DSF0000881134, DSF0000960543, DSF0000960831
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | Design | Complete | 3/1/2019 | 7/31/2019 | 5/10/2022 | 1042001 | 690888 | 690888 | DSF0000881133, DSF0000881134, DSF0000960543, DSF0000960831
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 8/15/2022 | 10/2/2024 |  | 23445015 | 21404955 | 15648975 | DSF0000881133, DSF0000881134, DSF0000960543, DSF0000960831
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 8/15/2022 | 10/2/2024 |  | 1458801 | 267056 | 258292 | DSF0000881133, DSF0000881134, DSF0000960543, DSF0000960831
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 9/6/2024 | 9/6/2024 | 9/6/2024 | 82656 | 62596 | 0 | DSF0001103193
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | ROOFS | Design | In-Progress | 9/6/2024 | 11/15/2024 |  | 385726 | 385726 | 0 | DSF0001103193
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 6116507 | 6116507 | 0 | DSF0001103193
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 606140 | 606140 | 0 | DSF0001103193
29 | Q238 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000011999
29 | Q238 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 0 | 0 | 0 | DSF0000011999
29 | Q238 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 12/1/2005 | 6/25/2006 |  | 0 | 0 | 0 | DSF0000011999
29 | Q238 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 12/1/2005 | 6/25/2006 |  | 0 | 0 | 0 | DSF0000011999
29 | Q238 | Q009 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/2/2024 | DIIR |  | DIIR | 160000 | 0 | DSF0001086488
29 | Q238 | Q009 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113115
29 | Q238 | I.S. 238 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 423808 | 0 | DSF0001033876
29 | Q238 | I.S. 238 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001036006
29 | Q238 | I.S. 238 - QUEENS | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0 | DSF0001086489
29 | Q238 | I.S. 238 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 8/20/2021 | DOES |  | DOES | 371658 | 0 | DSF0000865864
29 | Q263 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | Scope | Complete | 1/17/2020 | 6/3/2020 | 6/28/2021 | 116100 | 125708 | 125708 | DSF0000960553, DSF0001006679, DSF0001006678, DSF0001024758
29 | Q263 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | Design | Complete | 8/26/2021 | 2/1/2022 | 2/23/2022 | 572361 | 436832 | 413369 | DSF0000960553, DSF0001006679, DSF0001006678, DSF0001024758
29 | Q263 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | Construction | In-Progress | 7/18/2022 | 11/13/2024 |  | 12173990 | 6588343 | 1736347 | DSF0000960553, DSF0001006679, DSF0001006678, DSF0001024758
29 | Q263 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | CM,F&E | In-Progress | 7/18/2022 | 11/13/2024 |  | 882155 | 381148 | 380806 | DSF0000960553, DSF0001006679, DSF0001006678, DSF0001024758
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/17/2023 | 5/18/2023 | 4/3/2023 | 0 | 20656 | 20656 | DSF0001036014
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 24600 | 7961 | 7961 | DSF0001036014
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 360800 | 1159737 | 0 | DSF0001036014
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 24600 | 79073 | 0 | DSF0001036014
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036015
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036015
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036015
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036015
29 | Q263 | P.S. /I.S 295 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/16/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084688
29 | Q263 | P.S. /I.S 295 - QUEENS | DOE - Skilled Trades | RTU REPAIRS | Construction | In-Progress | 10/19/2023 | DOES |  | DOES | 181200 | 75000 | DSF0001087245
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 8/24/2023 | 26008 | 94516 | 91877 | DSF0001024787, DSF0001024789
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 9/21/2023 | 2/27/2024 | 4/25/2024 | 117036 | 117483 | 109872 | DSF0001024787, DSF0001024789
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 1508468 | 1508468 | 0 | DSF0001024787, DSF0001024789
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 279586 | 279586 | 43589 | DSF0001024787, DSF0001024789
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/13/2022 | 4/14/2023 | 1/3/2023 | 3168 | 3876 | 3876 | DSF0001034619
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/3/2023 | 6/29/2023 | 5/3/2023 | 14254 | 15506 | 15506 | DSF0001034619
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 11/20/2023 | 11/18/2024 |  | 183723 | 169849 | 90500 | DSF0001034619
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 11/20/2023 | 11/18/2024 |  | 112068 | 121340 | 113402 | DSF0001034619
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001033886
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | Design | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0001033886
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | Construction | PNS | PNS | PNS | PNS | 44000 | 44000 | 0 | DSF0001033886
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0001033886
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036016
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Design | PNS | PNS | PNS | PNS | 24000 | 24000 | 0 | DSF0001036016
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Construction | PNS | PNS | PNS | PNS | 352000 | 352000 | 0 | DSF0001036016
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | CM,F&E | PNS | PNS | PNS | PNS | 24000 | 24000 | 0 | DSF0001036016
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY18 RESO A ROOFTOP PLAYGROUND | Scope | Complete | 1/17/2018 | 4/17/2018 | 6/13/2018 | 0 | 13627 | 13627 | DSF0000867340
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY18 RESO A ROOFTOP PLAYGROUND | Design | Complete | 1/16/2019 | 6/3/2019 | 5/18/2020 | 46500 | 95184 | 95184 | DSF0000867340
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY18 RESO A ROOFTOP PLAYGROUND | Construction | In-Progress | 5/14/2021 | 2/7/2022 |  | 682000 | 579826 | 540989 | DSF0000867340
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY18 RESO A ROOFTOP PLAYGROUND | CM,F&E | In-Progress | 5/14/2021 | 2/7/2022 |  | 46500 | 58544 | 57441 | DSF0000867340
29 | Q268 | P.S. 268 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/3/2024 | DOES | 10/8/2024 | DOES | 50832 |  | DSF0001084690
29 | Q268 | P.S. 268 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 4/15/2024 | DOES |  | DOES | 74680 | 0 | DSF0001112169
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | Scope | Complete | 4/20/2021 | 2/11/2022 | 1/19/2022 | 36710 | 52647 | 46882 | DSF0000960878, DSF0001005828, DSF0001034164, DSF0001024810
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | Design | Complete | 1/20/2022 | 3/9/2022 | 3/2/2022 | 170636 | 178225 | 133324 | DSF0000960878, DSF0001005828, DSF0001034164, DSF0001024810
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | Construction | In-Progress | 7/24/2023 | 10/20/2024 |  | 2722682 | 2403984 | 2182720 | DSF0000960878, DSF0001005828, DSF0001034164, DSF0001024810
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/24/2023 | 10/20/2024 |  | 353782 | 689335 | 669797 | DSF0000960878, DSF0001005828, DSF0001034164, DSF0001024810
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/21/2023 | 4/24/2024 | 4/1/2024 | 0 | 15441 | 15441 | DSF0001086500
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | In-Progress | 4/2/2024 | 8/16/2024 |  | 33205 | 19183 | 19183 | DSF0001086500
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 487003 | 487399 | 0 | DSF0001086500
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 33205 | 33232 | 7023 | DSF0001086500
29 | Q270 | P.S. / I.S. 270 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 215648 | 197257 | DSF0000960589
29 | Q270 | P.S. / I.S. 270 - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/18/2024 | DIIR |  | DIIR | 80000 | 0 | DSF0001087172
29 | Q270 | Q004 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113123
29 | Q270 | P.S. / I.S. 270 - QUEENS | DOE - RESOA | FY20 RESO A ROOM UPGRADE | Construction | In-Progress | 3/7/2024 | DOER |  | DOER | 299638 | 0 | DSF0000913445
29 | Q270 | P.S. / I.S. 270 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113122
29 | Q270 | P.S. / I.S. 270 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/3/2022 | DOES |  | DOES | 150770 | 0 | DSF0001009188
29 | Q363 | DISTRICT 29 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/17/2024 | DOES | 12/4/2024 | DOES | 65832 |  | DSF0001085505
29 | Q374 | SUCCESS ACADEMY CHARTER SCHOOL - ROSEDALE - NEW YORK 5 | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/7/2024 | IEH | 8/14/2024 | IEH | 0 | 0 | SCA0000073254
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 8/6/2020 | 10/28/2021 | 6/17/2022 | 76540 | 130325 | 126330 | DSF0000961092, DSF0000961429, DSF0001025130
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 8/31/2022 | 2/28/2023 | 3/10/2023 | 382701 | 423447 | 334472 | DSF0000961092, DSF0000961429, DSF0001025130
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | Construction | In-Progress | 5/20/2024 | 11/10/2025 |  | 8610750 | 8048177 | 289146 | DSF0000961092, DSF0000961429, DSF0001025130
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | CM,F&E | In-Progress | 5/20/2024 | 11/10/2025 |  | 535780 | 137630 | 135062 | DSF0000961092, DSF0000961429, DSF0001025130
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 12/13/2023 | 4/1/2024 | 6/18/2024 | 0 | 20153 | 20153 | DSF0001086533
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 7/3/2024 | 12/5/2024 |  | 35968 | 65216 | 13801 | DSF0001086533
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 527533 | 527533 | 0 | DSF0001086533
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 35968 | 35968 | 32405 | DSF0001086533
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 7/3/2024 | 10/3/2024 | 8/8/2024 | 0 | 0 | 148 | DSF0001087081
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | In-Progress | 8/8/2024 | 12/9/2024 |  | 32 | 32 | 593 | DSF0001087081
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 468 | 468 | 0 | DSF0001087081
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 32 | 32 | 6643 | DSF0001087081
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION / FY20 RESO A PATH OF TRAVEL ROOM CONVERSION | Scope | Complete | 6/1/2021 | 2/17/2023 | 1/19/2023 | 0 | 33094 | 23553 | DSF0000913191, DSF0000913192
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION / FY20 RESO A PATH OF TRAVEL ROOM CONVERSION | Design | Complete | 1/19/2023 | 5/5/2023 | 4/28/2023 | 115311 | 96981 | 90774 | DSF0000913191, DSF0000913192
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION / FY20 RESO A PATH OF TRAVEL ROOM CONVERSION | Construction | Complete | 11/21/2023 | 5/13/2025 | 9/10/2024 | 1691219 | 1497906 | 1474027 | DSF0000913191, DSF0000913192
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION / FY20 RESO A PATH OF TRAVEL ROOM CONVERSION | CM,F&E | Complete | 11/21/2023 | 5/13/2025 | 9/10/2024 | 226244 | 227496 | 157816 | DSF0000913191, DSF0000913192
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 1/25/2024 | 10/8/2024 | 8/8/2024 | 0 | 21616 | 21616 | DSF0001086531, DSF0001087080
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 8/8/2024 | 12/9/2024 | 11/18/2024 | 55130 | 66093 | 17026 | DSF0001086531, DSF0001087080
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 808569 | 808569 | 0 | DSF0001086531, DSF0001087080
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 55130 | 56002 | 28760 | DSF0001086531, DSF0001087080
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA IEH | PO18-TEST FOR ACM, IF POSITIVE ABATE PIPE INSULATION ON WASTELINE BASEMENT CRAWLSPACE (SPACE ID: 120 | Construction | Complete | 9/4/2024 | IEH | 9/26/2024 | IEH | 0 | 0 | SCA0000073348
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001086528
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/28/2021 | DOER |  | DOER | 467653 | 0 | DSF0000890914
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | Complete | 7/31/2023 | DOER | 12/12/2023 | DOER | 87840 | 1145 | DSF0001033307
29 | Q420 | PREPARATORY ACADEMY FOR WRITERS-Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 100000 | 0 | DSF0001086532
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113156
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DOE - Skilled Trades | LEAKING CURB VALVE | Construction | In-Progress | 6/26/2020 | DOES |  | DOES | 186590 | 130465 | DSF0000961138
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/17/2023 | DOES | 10/2/2023 | DOES | 519555 |  | DSF0001035110
29 | Q442 | Q000 - QUEENS | SCA IEH | PO18-NEED ACM ABATEMENT OF ENTIRE CRAWL SPACE | Construction | Complete | 5/13/2024 | IEH | 6/9/2024 | IEH | 0 | 0 | SCA0000072998
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | Scope | Complete | 11/30/2021 | 3/18/2022 | 2/9/2022 | 22260 | 38010 | 38010 | DSF0000999139
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | Design | Complete | 2/16/2022 | 7/19/2022 | 5/9/2022 | 111300 | 195146 | 192273 | DSF0000999139
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | Construction | In-Progress | 8/8/2022 | 8/7/2023 |  | 2504250 | 2279111 | 2037222 | DSF0000999139
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 8/8/2022 | 8/7/2023 |  | 155820 | 219474 | 207376 | DSF0000999139
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY20 RESO A LOW VOLTAGE | Scope | Complete | 12/17/2019 | 3/19/2020 | 3/11/2020 | 0 | 6086 | 6086 | DSF0000913193
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY20 RESO A LOW VOLTAGE | Design | Complete | 5/26/2021 | 10/27/2021 | 9/28/2021 | 96813 | 24428 | 24428 | DSF0000913193
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY20 RESO A LOW VOLTAGE | Construction | In-Progress | 1/24/2022 | 11/19/2022 |  | 1419922 | 1192898 | 1040837 | DSF0000913193
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY20 RESO A LOW VOLTAGE | CM,F&E | In-Progress | 1/24/2022 | 11/19/2022 |  | 96813 | 31761 | 31761 | DSF0000913193
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 12/14/2023 | 4/2/2024 | 4/8/2024 | 0 | 15702 | 15639 | DSF0001086558
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Design | Complete | 4/8/2024 | 9/9/2024 | 8/16/2024 | 29775 | 44193 | 43446 | DSF0001086558
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 436700 | 436700 | 500 | DSF0001086558
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 29775 | 29775 | 28401 | DSF0001086558
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/4/2023 | 4/5/2024 | 4/25/2024 | 0 | 15065 | 15065 | DSF0001086553
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | Complete | 5/6/2024 | 9/20/2024 | 10/1/2024 | 59749 | 63989 | 4661 | DSF0001086553
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 876317 | 876317 | 7365 | DSF0001086553
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 59749 | 59749 | 9719 | DSF0001086553
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Scope | In-Progress | 12/4/2023 | 4/5/2024 |  | 0 | 33424 | 1283 | DSF0001086552
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 180000 | 146576 | 5130 | DSF0001086552
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 2640000 | 2640000 | 0 | DSF0001086552
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 180000 | 180000 | 999 | DSF0001086552
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/15/2024 | 6/14/2024 | 4/8/2024 | 0 | 0 | 0 | DSF0001087093
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 4/8/2024 | 8/6/2024 | 8/16/2024 | 225 | 225 | 0 | DSF0001087093
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 3300 | 3300 | 0 | DSF0001087093
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 225 | 225 | 4825 | DSF0001087093
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | In-Progress | 3/15/2024 | 6/14/2024 |  | 0 | 153 | 153 | DSF0001087091
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 610 | 610 | DSF0001087091
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087091
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 451 | 451 | DSF0001087091
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/15/2024 | 6/14/2024 | 5/23/2024 | 0 | 267 | 267 | DSF0001087092
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 6/4/2024 | 10/7/2024 | 10/1/2024 | 251 | 251 | 1068 | DSF0001087092
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 3683 | 3683 | 2587 | DSF0001087092
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 251 | 251 | 2831 | DSF0001087092
29 | Q490 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 0 | 0 | 0 | DSF0000012002
29 | Q490 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 0 | 0 | 0 | DSF0000012002
29 | Q490 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Construction | In-Progress | 10/18/2005 | 6/18/2006 |  | 0 | 0 | 0 | DSF0000012002
29 | Q490 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | CM | In-Progress | 10/18/2005 | 6/18/2006 |  | 0 | 0 | 0 | DSF0000012002
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA IEH | PO18-ACM TEST & ABATE PIPE INSULATION 30 FT 1 1/4 PIPE UNDER MAIN ENTRANCE STAIRS. SPRAYED IN GREEN | Construction | Complete | 11/29/2024 | IEH | 12/30/2024 | IEH | 0 | 0 | SCA0000073654
29 | Q490 | BENJAMIN FRANKLIN HS FOR FINANCE AND INFORMATION TECH | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 125000 | DSF0001086559
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 7/21/2016 | FTK |  | FTK | 1513253 | 1320484 | DSF0000843982
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113174
29 | Q490 | BENJAMIN FRANKLIN HS FOR FINANCE AND INFORMATION TECH | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 95000 | 0 | DSF0001113175
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0001113176
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | Complete | 11/12/2021 | DOER | 4/6/2022 | DOER | 129281 | 190067 | DSF0000890930
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 183459 | 0 | DSF0001033324
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001033325
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001033937
29 | Q490 | BENJAMIN FRANKLIN HS FOR FINANCE AND INFORMATION TECH | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | Complete | 5/19/2023 | DOER | 10/6/2023 | DOER | 96428 | 148744 | DSF0001036027
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 75000 | 0 | DSF0001086554
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0 | DSF0001086555
29 | Q490 | BENJAMIN FRANKLIN HS FOR FINANCE AND INFORMATION TECH | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 148000 | 0 | DSF0001086557
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 3/8/2023 | DOES |  | DOES | 62936 | 0 | DSF0000866134
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 12/5/2022 | DOES | 9/19/2023 | DOES | 813527 | 801597 | DSF0000960865
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/14/2024 | DOES | 10/24/2024 | DOES | 65832 |  | DSF0001085016
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 5/7/2024 | DOES |  | DOES | 74768 | 0 | DSF0001104354
29 | Q491 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001008540
29 | Q633 | EAGLE ACADEMY III - QUEENS | SCA CIP RESOA | FY24 RESO A WEIGHT ROOM | Scope | Complete | 3/21/2024 | 7/23/2024 | 7/3/2024 | 0 | 13735 | 13735 | DSF0001086570
29 | Q633 | EAGLE ACADEMY III - QUEENS | SCA CIP RESOA | FY24 RESO A WEIGHT ROOM | Design | Complete | 7/3/2024 | 11/19/2024 | 12/4/2024 | 30000 | 42279 | 40084 | DSF0001086570
29 | Q633 | EAGLE ACADEMY III - QUEENS | SCA CIP RESOA | FY24 RESO A WEIGHT ROOM | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001086570
29 | Q633 | EAGLE ACADEMY III - QUEENS | SCA CIP RESOA | FY24 RESO A WEIGHT ROOM | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 20124 | DSF0001086570
29 | Q633 | EAGLE ACADEMY III - QUEENS | Fast Track Projects | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 5731 | 5731 | DSF0001086569
29 | Q633 | EAGLE ACADEMY III - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/3/2024 | DIIR | 11/12/2024 | DIIR | 49823 | 49823 | DSF0001086571
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 108569 | 0 | DSF0001033314
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | Complete | 2/12/2024 | DOER | 4/23/2024 | DOER | 225007 |  | DSF0001036074
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001035243
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0 | DSF0001113186
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/6/2024 | DOES | 10/25/2024 | DOES | 65832 | 8138 | DSF0001085532
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - Skilled Trades | SEWAGE EJECTOR PUMP | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 67359 | 0 | DSF0001111914
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/17/2024 | DOES |  | DOES | 321694 | 0 | DSF0001111941
29 | Q799 | CAMBRIA HEIGHTS ACADEMY - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113199
29 | Q799 | CAMBRIA HEIGHTS ACADEMY - QUEENS | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001033909
29 | Q799 | CAMBRIA HEIGHTS ACADEMY - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/10/2023 | DOES | 10/31/2023 | DOES | 212493 |  | DSF0001035090
29 | Q822 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 5/17/2019 | 10/2/2019 | 9/5/2019 | 11789 | 6386 | 6386 | DSF0000914287
29 | Q822 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 9/25/2019 | 3/17/2020 | 7/1/2020 | 58947 | 34687 | 33672 | DSF0000914287
29 | Q822 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | In-Progress | 6/30/2022 | 2/13/2025 |  | 1326297 | 1359549 | 1227490 | DSF0000914287
29 | Q822 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | In-Progress | 6/30/2022 | 2/13/2025 |  | 82525 | 19440 | 19346 | DSF0000914287
29 | Q836 | P.S. 36 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/15/2022 | DOES | 12/19/2022 | DOES | 102977 | 93774 | DSF0001034261
29 | Q851 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 7/5/2023 | 7/5/2023 | 7/5/2023 | 17023 | 15144 | 15144 | DSF0001085304
29 | Q851 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | Design | Complete | 7/5/2023 | 12/6/2023 | 12/8/2023 | 76605 | 67890 | 48796 | DSF0001085304
29 | Q851 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | Construction | In-Progress | 4/29/2024 | 10/20/2025 |  | 987349 | 896503 | 138755 | DSF0001085304
29 | Q851 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | CM,F&E | In-Progress | 4/29/2024 | 10/20/2025 |  | 183000 | 13076 | 13076 | DSF0001085304
29 | Q892 | P.S. 360 - QUEENS | Fast Track Projects | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | FTK | FTK | FTK | FTK | 184682 | 173690 | DSF0001086589
29 | Q892 | P.S. 360 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/29/2023 | DIIR | 5/10/2024 | DIIR | 144000 | 144000 | DSF0001033319
29 | Q892 | P.S. 360 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/7/2024 | DIIR | 12/3/2024 | DIIR | 249120 | 249120 | DSF0001036092
29 | Q892 | P.S. 360 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 3/1/2024 | DOER | 5/23/2024 | DOER | 8994 |  | DSF0001036093
29 | Q892 | P.S. 360 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001086588
29 | Q892 | P.S. 360 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113204
29 | QAFE | RIVERTON STREET CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 9/1/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000914115
29 | QMAC | MERRICK ACADEMY CHARTER SCHOOL - QUEENS | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LABS | F&E | Complete | 7/17/2024 |  | 7/26/2024 | 350000 | 350000 | 349935 | DSF0001036097
29 | QMAC | MERRICK ACADEMY CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0001086591
30 | Q002 | P.S. 2 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/12/2024 | 10/29/2024 | 9/27/2024 | 169715 | 148379 | 109303 | DSF0001098979, DSF0001098981, DSF0001113799, DSF0001126782
30 | Q002 | P.S. 2 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | Design | In-Progress | 12/10/2024 | 5/13/2025 |  | 788554 | 788554 | 276732 | DSF0001098979, DSF0001098981, DSF0001113799, DSF0001126782
30 | Q002 | P.S. 2 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 12473559 | 12473559 | 26748 | DSF0001098979, DSF0001098981, DSF0001113799, DSF0001126782
30 | Q002 | P.S. 2 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1282942 | 1282942 | 24208 | DSF0001098979, DSF0001098981, DSF0001113799, DSF0001126782
30 | Q002 | P.S. 2 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/4/2024 | DIIR |  | DIIR | 103000 | 0 | DSF0001086339
30 | Q002 | P.S. 2 - QUEENS | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/13/2023 | DOER |  | DOER | 377681 | 0 | DSF0000913103
30 | Q002 | P.S. 2 - QUEENS | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 6/1/2022 | DOER | 12/19/2022 | DOER | 85639 | 84487 | DSF0000913353
30 | Q002 | P.S. 2 - QUEENS | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1085000 | 0 | DSF0000913356
30 | Q002 | P.S. 2 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/5/2022 | DOES |  | DOES | 92607 | 0 | DSF0001009064
30 | Q010 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | Scope | Complete | 8/22/2019 | 1/10/2020 | 2/21/2020 | 15433 | 37993 | 37993 | DSF0000900589
30 | Q010 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | Design | Complete | 6/1/2021 | 11/1/2021 | 4/11/2022 | 77163 | 79814 | 79814 | DSF0000900589
30 | Q010 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | Construction | In-Progress | 6/21/2022 | 9/13/2023 |  | 1736156 | 1620785 | 1593173 | DSF0000900589
30 | Q010 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | CM,F&E | In-Progress | 6/21/2022 | 9/13/2023 |  | 108028 | 191968 | 191968 | DSF0000900589
30 | Q010 | I.S. 10 - QUEENS | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 10/1/2021 | DOER | 12/21/2021 | DOER | 118028 | 118520 | DSF0000913359
30 | Q010 | I.S. 10 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 140749 | 0 | DSF0001035796
30 | Q010 | I.S. 10 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/13/2022 | DOES |  | DOES | 75953 | 0 | DSF0001008961
30 | Q010 | I.S. 10 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/4/2024 | DOES | 9/11/2024 | DOES | 65832 | 24887 | DSF0001084798
30 | Q010 | I.S. 10 - QUEENS | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/3/2023 | DOES |  | DOES | 582463 | 0 | DSF0001071381
30 | Q011 | P.S. 11 - QUEENS | SCA CIP | ROOFS / PARAPETS | Scope | Complete | 5/13/2024 | 9/27/2024 | 11/8/2024 | 83654 | 53211 | 35268 | DSF0001099110, DSF0001126908
30 | Q011 | P.S. 11 - QUEENS | SCA CIP | ROOFS / PARAPETS | Design | In-Progress | 12/18/2024 | 5/21/2025 |  | 399805 | 399805 | 14507 | DSF0001099110, DSF0001126908
30 | Q011 | P.S. 11 - QUEENS | SCA CIP | ROOFS / PARAPETS | Construction | PNS | PNS | PNS | PNS | 7278693 | 7278693 | 0 | DSF0001099110, DSF0001126908
30 | Q011 | P.S. 11 - QUEENS | SCA CIP | ROOFS / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 604036 | 604036 | 14725 | DSF0001099110, DSF0001126908
30 | Q011 | P.S. 11 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/12/2024 | DIIR | 10/31/2024 | DIIR | 49810 | 49810 | DSF0001086344
30 | Q011 | P.S. 11 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112932
30 | Q011 | Q255 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 175000 | 0 | DSF0001086345
30 | Q011 | Q255 SPED - QUEENS | DOE - RESOA | RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001111874
30 | Q011 | P.S. 11 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113733
30 | Q011 | P.S. 11 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001112930
30 | Q011 | P.S. 11 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 800000 | 0 | DSF0001112931
30 | Q011 | P.S. 11 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/23/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084650
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/20/2023 | 143584 | 122394 | 121218 | DSF0001071488, DSF0001111755, DSF0001111756, DSF0001111757
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 11/9/2023 | 6/28/2024 | 4/11/2024 | 708217 | 237638 | 237607 | DSF0001071488, DSF0001111755, DSF0001111756, DSF0001111757
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Construction | PNS | PNS | PNS | PNS | 15095780 | 15095780 | 105926 | DSF0001071488, DSF0001111755, DSF0001111756, DSF0001111757
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1077841 | 1077841 | 29456 | DSF0001071488, DSF0001111755, DSF0001111756, DSF0001111757
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/14/2023 | 10/16/2023 | 6/29/2023 | 4106 | 1608 | 1608 | DSF0001035037
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/29/2023 | 12/27/2023 | 9/20/2023 | 18477 | 6433 | 6433 | DSF0001035037
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 1/8/2024 | 11/2/2024 |  | 238149 | 213699 | 175722 | DSF0001035037
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 1/8/2024 | 11/2/2024 |  | 113648 | 106666 | 98100 | DSF0001035037
30 | Q017 | P.S. 17 - QUEENS | DOE - RESOA | FY10 RESO A OUTSIDE BULLETIN BOARD | Construction | PNS | PNS | PNS | PNS | DOER | 43465 | 0 | DSF0000690130
30 | Q017 | P.S. 17 - QUEENS | DOE - RESOA | FY12 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 44017 | 0 | DSF0000731663
30 | Q017 | THE 30TH AVENUE SCHOOL | DOE - RESOA | FY18 RESO A HYDROPONICS LAB | Construction | Complete | 7/16/2019 | DOER | 12/28/2021 | DOER | 233414 | 233414 | DSF0000912357
30 | Q017 | P.S. 17 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | Complete | 7/1/2024 | DOER | 8/23/2024 | DOER | 243143 |  | DSF0001035801
30 | Q017 | THE 30TH AVENUE SCHOOL | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 465000 | 0 | DSF0001112936
30 | Q017 | THE 30TH AVENUE SCHOOL | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/5/2022 | DOES |  | DOES | 138601 | 0 | DSF0001009179
30 | Q069 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | Scope | Complete | 1/23/2019 | 4/5/2019 | 5/3/2019 | 32890 | 58247 | 58247 | DSF0000878619
30 | Q069 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | Design | Complete | 5/8/2019 | 11/8/2019 | 10/11/2019 | 164450 | 388070 | 367060 | DSF0000878619
30 | Q069 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | Construction | In-Progress | 1/21/2020 | 1/19/2021 |  | 3700125 | 3411609 | 3121358 | DSF0000878619
30 | Q069 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | CM,F&E | In-Progress | 1/21/2020 | 1/19/2021 |  | 230230 | 267694 | 263078 | DSF0000878619
30 | Q069 | P.S. 69 - QUEENS | Fast Track Projects | FIRE ALARM REPLACEMENT | Construction | In-Progress | 3/8/2019 | FTK |  | FTK | 5028859 | 4712390 | SCA0000053506
30 | Q069 | P.S. 69 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 2/28/2022 | FTK |  | FTK | 569643 | 71995 | DSF0000946974
30 | Q069 | P.S. 69 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/11/2023 | DIIR |  | DIIR | 50000 | 0 | DSF0001033264
30 | Q069 | P.S. 69 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001035842
30 | Q069 | P.S. 69 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001112976
30 | Q069 | P.S. 69 - QUEENS | DOE - RESOA | FY10 RESO A STEEL FENCE | Construction | PNS | PNS | PNS | PNS | DOER | 55141 | 0 | DSF0000690095
30 | Q069 | P.S. 69 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 104478 | 0 | DSF0001035841
30 | Q069 | P.S. 69 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 197812 | 0 | DSF0001086378
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 6/22/2021 | 11/5/2021 | 11/1/2021 | 7118 | 14759 | 14759 | DSF0000995850
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 11/8/2021 | 4/13/2022 | 4/6/2022 | 32033 | 39848 | 33227 | DSF0000995850
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | Construction | In-Progress | 9/6/2022 | 6/2/2023 |  | 412868 | 413377 | 353763 | DSF0000995850
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | CM,F&E | In-Progress | 9/6/2022 | 6/2/2023 |  | 76523 | 70246 | 69131 | DSF0000995850
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 5/6/2019 | 9/5/2019 | 5/21/2019 | 2391 | 2391 | 2510 | DSF0000912094
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 5/21/2019 | 10/22/2019 | 10/30/2019 | 10760 | 10109 | 10109 | DSF0000912094
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/16/2020 | 6/12/2021 |  | 138683 | 138683 | 291019 | DSF0000912094
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 9/16/2020 | 6/12/2021 |  | 25704 | 25704 | 44136 | DSF0000912094
30 | Q070 | P.S. 70 - QUEENS | SCA CIP RESOA | FY20 RESO LIBRARY UPGRADE | Scope | Complete | 5/27/2022 | 9/28/2022 | 8/25/2022 | 0 | 10666 | 10666 | DSF0000913381
30 | Q070 | P.S. 70 - QUEENS | SCA CIP RESOA | FY20 RESO LIBRARY UPGRADE | Design | Complete | 8/30/2022 | 1/19/2023 | 1/31/2023 | 35850 | 44532 | 44532 | DSF0000913381
30 | Q070 | P.S. 70 - QUEENS | SCA CIP RESOA | FY20 RESO LIBRARY UPGRADE | Construction | In-Progress | 5/22/2023 | 4/15/2024 |  | 525802 | 389648 | 213029 | DSF0000913381
30 | Q070 | P.S. 70 - QUEENS | SCA CIP RESOA | FY20 RESO LIBRARY UPGRADE | CM,F&E | In-Progress | 5/22/2023 | 4/15/2024 |  | 168383 | 180561 | 122585 | DSF0000913381
30 | Q070 | Q004 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112977
30 | Q070 | P.S. 70 - QUEENS | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/29/2022 | DOER |  | DOER | 292486 | 0 | DSF0000913108
30 | Q070 | P.S. 70 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 300000 | 1242 | DSF0001086379
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | RETAINING WALL | Scope | Complete | 5/24/2024 | 10/10/2024 | 10/7/2024 | 12933 | 20665 | 20665 | DSF0001100257
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | RETAINING WALL | Design | In-Progress | 10/17/2024 | 3/24/2025 |  | 58200 | 58200 | 3236 | DSF0001100257
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | RETAINING WALL | Construction | PNS | PNS | PNS | PNS | 750131 | 750131 | 564 | DSF0001100257
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | RETAINING WALL | CM,F&E | PNS | PNS | PNS | PNS | 139033 | 139033 | 16094 | DSF0001100257
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/16/2022 | 3/21/2023 | 12/5/2022 | 5100 | 6921 | 6921 | DSF0001034625
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/5/2022 | 6/1/2023 | 3/8/2023 | 22950 | 27683 | 27683 | DSF0001034625
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/10/2023 | 5/4/2024 |  | 295800 | 261602 | 239731 | DSF0001034625
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/10/2023 | 5/4/2024 |  | 178563 | 169182 | 104958 | DSF0001034625
30 | Q076 | P.S. 76 - QUEENS | SCA IEH | PO18-RM 118 ABATE ALL ACM ON PIPES AND SLEAVE GOING THROUGH THE WALL | Construction | Complete | 3/12/2024 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000072809
30 | Q076 | P.S. 76 - QUEENS | SCA IEH | PO18-ABATE & REPLACE FLOOR TILES ON 3RD FLOOR HALLWAY NEAR 304. DAMAGE APPROXIMATELY 10 SF | Construction | In-Progress | 10/25/2024 | IEH |  | IEH | 0 | 0 | SCA0000073539
30 | Q076 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001086386
30 | Q076 | P.S. 76 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 77000 | 0 | DSF0001086387
30 | Q076 | P.S. 76 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001112985
30 | Q076 | THE RIVERVIEW SCHOOL - QUEENS | DOE - RESOA | FY21 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 34754 | 0 | DSF0001008100
30 | Q076 | P.S. 76 - QUEENS | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 5/6/2024 | DOES |  | DOES | 71371 | 0 | DSF0001100259
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / FIRE ALARM SYSTEM REPLACEMENT / HVAC UPGRADES / WINDOWS | Scope | Complete | 7/12/2022 | 11/28/2022 | 5/15/2023 | 138000 | 223587 | 213016 | DSF0001021851, DSF0001021852, DSF0001085196, DSF0001072602, DSF0001072613, DSF0001085195
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / FIRE ALARM SYSTEM REPLACEMENT / HVAC UPGRADES / WINDOWS | Design | Complete | 6/13/2023 | 12/18/2023 | 2/9/2024 | 658175 | 401241 | 382557 | DSF0001021851, DSF0001021852, DSF0001085196, DSF0001072602, DSF0001072613, DSF0001085195
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / FIRE ALARM SYSTEM REPLACEMENT / HVAC UPGRADES / WINDOWS | Construction | PNS | PNS | PNS | PNS | 12056445 | 12056445 | 262689 | DSF0001021851, DSF0001021852, DSF0001085196, DSF0001072602, DSF0001072613, DSF0001085195
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / FIRE ALARM SYSTEM REPLACEMENT / HVAC UPGRADES / WINDOWS | CM,F&E | PNS | PNS | PNS | PNS | 1204649 | 1204649 | 63457 | DSF0001021851, DSF0001021852, DSF0001085196, DSF0001072602, DSF0001072613, DSF0001085195
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | STRUCTURAL REPAIRS | Scope | Complete | 9/18/2024 | 2/6/2025 | 12/13/2024 | 105122 | 107130 | 40497 | DSF0001034335
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | STRUCTURAL REPAIRS | Design | In-Progress | 12/16/2024 | 5/19/2025 |  | 525610 | 525610 | 59110 | DSF0001034335
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | STRUCTURAL REPAIRS | Construction | PNS | PNS | PNS | PNS | 11826233 | 11826233 | 74771 | DSF0001034335
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | STRUCTURAL REPAIRS | CM,F&E | PNS | PNS | PNS | PNS | 735854 | 735854 | 54806 | DSF0001034335
30 | Q084 | P.S. 84 - QUEENS | SCA IEH | PO18-ABATE REPLACE & REPLASTER BOYS CAFE CEILING CEILING TILE DROPPED PLASTER UNDERNEATH IS CRUMBLIN | Construction | Complete | 7/17/2024 | IEH | 8/23/2024 | IEH | 0 | 0 | SCA0000073148
30 | Q085 | P.S. 85 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 6/24/2024 | 11/7/2024 | 9/27/2024 | 193939 | 84142 | 57847 | DSF0001072629, DSF0001072631, DSF0001113798, DSF0001128158
30 | Q085 | P.S. 85 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | In-Progress | 11/19/2024 | 4/23/2025 |  | 923978 | 923978 | 173962 | DSF0001072629, DSF0001072631, DSF0001113798, DSF0001128158
30 | Q085 | P.S. 85 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS | Construction | PNS | PNS | PNS | PNS | 16538068 | 16538068 | 27232 | DSF0001072629, DSF0001072631, DSF0001113798, DSF0001128158
30 | Q085 | P.S. 85 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 1403284 | 1403284 | 19571 | DSF0001072629, DSF0001072631, DSF0001113798, DSF0001128158
30 | Q085 | P.S. 85 - QUEENS | SCA CIP RESOA | FY21 RESO A CAFETERIA UPGRADE / PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | Complete | 7/21/2021 | 4/4/2022 | 3/4/2022 | 0 | 10288 | 10288 | DSF0001008033, DSF0001008078
30 | Q085 | P.S. 85 - QUEENS | SCA CIP RESOA | FY21 RESO A CAFETERIA UPGRADE / PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | Complete | 3/4/2022 | 5/20/2022 | 5/13/2022 | 64425 | 56988 | 52729 | DSF0001008033, DSF0001008078
30 | Q085 | P.S. 85 - QUEENS | SCA CIP RESOA | FY21 RESO A CAFETERIA UPGRADE / PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/7/2023 | 9/29/2024 |  | 944900 | 679866 | 495482 | DSF0001008033, DSF0001008078
30 | Q085 | P.S. 85 - QUEENS | SCA CIP RESOA | FY21 RESO A CAFETERIA UPGRADE / PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | In-Progress | 8/7/2023 | 9/29/2024 |  | 129433 | 143085 | 62241 | DSF0001008033, DSF0001008078
30 | Q085 | P.S. 85 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER, CEILING PLASTER AND FLOOR TILES IN THE FOLLOWING LOCATIONS: STAI | Construction | In-Progress | 7/31/2023 | IEH |  | IEH | 0 | 0 | SCA0000072181
30 | Q085 | P.S. 85 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | Complete | 1/31/2022 | FTK | 7/10/2024 | FTK | 213682 | 189823 | DSF0000960679
30 | Q085 | P.S. 85 - QUEENS | DOE - Skilled Trades | EXTERIOR STAIRS | Construction | In-Progress | 12/15/2023 | DOES |  | DOES | 63374 | 20500 | DSF0001111908
30 | Q111 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Scope | Complete | 8/26/2019 | 1/15/2020 | 11/17/2021 | 75080 | 131524 | 130813 | DSF0000902113, DSF0001022342, DSF0001022339
30 | Q111 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Design | Complete | 12/8/2021 | 5/11/2022 | 5/5/2022 | 375404 | 339374 | 339374 | DSF0000902113, DSF0001022342, DSF0001022339
30 | Q111 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 8/15/2022 | 2/5/2024 |  | 8446568 | 7895039 | 6660251 | DSF0000902113, DSF0001022342, DSF0001022339
30 | Q111 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 8/15/2022 | 2/5/2024 |  | 528886 | 1030536 | 1018098 | DSF0000902113, DSF0001022342, DSF0001022339
30 | Q111 | P.S. 111 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113008
30 | Q111 | P.S. 111 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 162881 | 0 | DSF0001035337
30 | Q111 | P.S. 111 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/11/2024 | DOER |  | DOER | 296023 | 0 | DSF0001086404
30 | Q111 | P.S. 111 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/19/2022 | DOES |  | DOES | 83683 | 0 | DSF0001009177
30 | Q111 | P.S. 111 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/10/2024 | DOES | 7/24/2024 | DOES | 65832 | 11556 | DSF0001084662
30 | Q112 | P.S. 112 - QUEENS | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Scope | Complete | 12/1/2016 | 3/6/2017 | 3/8/2017 | 0 | 60553 | 60553 | DSF0000844957
30 | Q112 | P.S. 112 - QUEENS | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Design | Complete | 3/24/2017 | 8/8/2017 | 5/17/2017 | 84646 | 104618 | 104618 | DSF0000844957
30 | Q112 | P.S. 112 - QUEENS | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 8/22/2017 | 5/18/2018 |  | 1241473 | 1227090 | 1103155 | DSF0000844957
30 | Q112 | P.S. 112 - QUEENS | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | CM,F&E | In-Progress | 8/22/2017 | 5/18/2018 |  | 84646 | 421684 | 420123 | DSF0000844957
30 | Q112 | P.S. 112 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001035234
30 | Q112 | P.S. 112 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001086406
30 | Q112 | P.S. 112 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113009
30 | Q112 | P.S. 112 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | Complete | 11/21/2023 | DOER | 5/21/2024 | DOER | 183968 |  | DSF0001035874
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 5/27/2021 | 8/26/2021 | 10/8/2021 | 11000 | 42301 | 42301 | DSF0000996735
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 12/28/2021 | 6/30/2022 | 9/23/2022 | 55000 | 170415 | 133329 | DSF0000996735
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Construction | In-Progress | 10/6/2023 | 7/1/2024 |  | 1237500 | 1309720 | 1230865 | DSF0000996735
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | CM,F&E | In-Progress | 10/6/2023 | 7/1/2024 |  | 77000 | 182428 | 146717 | DSF0000996735
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 7/14/2022 | 11/30/2022 | 6/12/2023 | 117730 | 174246 | 151233 | DSF0001022541, DSF0001022542, DSF0001022543, DSF0001073321
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 7/5/2023 | 12/6/2023 | 3/29/2024 | 588650 | 461253 | 367601 | DSF0001022541, DSF0001022542, DSF0001022543, DSF0001073321
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 7/5/2024 | 6/19/2027 |  | 13244625 | 12127544 | 1198243 | DSF0001022541, DSF0001022542, DSF0001022543, DSF0001073321
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 7/5/2024 | 6/19/2027 |  | 824110 | 178338 | 175467 | DSF0001022541, DSF0001022542, DSF0001022543, DSF0001073321
30 | Q122 | P.S. 122 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ Q122 | Construction | In-Progress | 4/4/2023 | EMER |  | EMER | 59986 | 52907 | SCA0000071865
30 | Q122 | P.S. 122 - QUEENS | SCA IEH | PO18-TEST WOOD FLOOR &IF POSITIVE ABATE & REPLACE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | Complete | 9/18/2024 | IEH | 9/29/2024 | IEH | 0 | 0 | SCA0000073392
30 | Q122 | P.S. 122 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 1/31/2022 | FTK |  | FTK | 226659 | 190832 | DSF0000960587
30 | Q122 | P.S. 122 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113016
30 | Q122 | P.S. 122 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/30/2024 | DOES | 10/11/2024 | DOES | 65832 | 9526 | DSF0001084667
30 | Q126 | I.S. 126 - QUEENS | SCA CIP RESOA | FY23 RESO A SCIENCE LAB / PATH OF TRAVEL RESO A SCIENCE LAB | Scope | Complete | 3/2/2023 | 7/3/2023 | 10/31/2023 | 0 | 0 | 28749 | DSF0001035893, DSF0001035894
30 | Q126 | I.S. 126 - QUEENS | SCA CIP RESOA | FY23 RESO A SCIENCE LAB / PATH OF TRAVEL RESO A SCIENCE LAB | Design | Complete | 10/31/2023 | 4/4/2024 | 10/17/2024 | 42000 | 42000 | 36642 | DSF0001035893, DSF0001035894
30 | Q126 | I.S. 126 - QUEENS | SCA CIP RESOA | FY23 RESO A SCIENCE LAB / PATH OF TRAVEL RESO A SCIENCE LAB | Construction | PNS | PNS | PNS | PNS | 616000 | 616000 | 12605 | DSF0001035893, DSF0001035894
30 | Q126 | I.S. 126 - QUEENS | SCA CIP RESOA | FY23 RESO A SCIENCE LAB / PATH OF TRAVEL RESO A SCIENCE LAB | CM,F&E | PNS | PNS | PNS | PNS | 42000 | 42000 | 27800 | DSF0001035893, DSF0001035894
30 | Q126 | I.S. 126 - QUEENS | SCA IEH | PO18-TEST BROKEN 2' RISER VALVE IN BASEMENT &IF POSITIVE ABATE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | Complete | 9/13/2024 | IEH | 9/14/2024 | IEH | 0 | 0 | SCA0000073379
30 | Q126 | I.S. 126 - QUEENS | SCA IEH | PO18-77/30Q126/TEST 3 INCH FLOOR DRAIN PIPE INSULATION IN OIL TANK ROOM IF POSITIVE ABATE APPROX 20 | Construction | Complete | 9/24/2024 | IEH | 10/5/2024 | IEH | 0 | 0 | SCA0000073414
30 | Q126 | I.S. 126 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 91140 | 0 | DSF0000488307
30 | Q126 | I.S. 126 - QUEENS | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 139566 | 0 | DSF0001035892
30 | Q126 | I.S. 126 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/7/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084809
30 | Q126 | I.S. 126 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/3/2024 | DOES |  | DOES | 912072 | 0 | DSF0001085751
30 | Q127 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/28/2022 | 3/30/2023 | 12/5/2022 | 4600 | 3750 | 3750 | DSF0001034629
30 | Q127 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/5/2022 | 6/1/2023 | 3/8/2023 | 20700 | 15000 | 15000 | DSF0001034629
30 | Q127 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/10/2023 | 5/4/2024 |  | 266800 | 251007 | 214788 | DSF0001034629
30 | Q127 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/10/2023 | 5/4/2024 |  | 163854 | 158201 | 113692 | DSF0001034629
30 | Q127 | P.S. 127 - QUEENS | SCA IEH | PO18-TEST 3RD FL STAIRWELL DRAIN LINE &IF POSITIVE ABATE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | In-Progress | 9/23/2024 | IEH |  | IEH | 0 | 0 | SCA0000073408
30 | Q127 | P.S. 127 - QUEENS | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER | Construction | In-Progress | 3/14/2022 | FTK |  | FTK | 287190 | 161636 | DSF0000996845
30 | Q127 | P.S. 127 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113023
30 | Q127 | P.S. 127 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 32902 | 0 | DSF0001035895
30 | Q127 | P.S. 127 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086417
30 | Q127 | P.S. 127 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113021
30 | Q127 | P.S. 127 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113022
30 | Q127 | P.S. 127 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/28/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084669
30 | Q141 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/22/2019 | 2/10/2020 | 10/7/2019 | 3256 | 2960 | 4741 | DSF0000912722, DSF0000914324
30 | Q141 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 10/7/2019 | 3/12/2020 | 1/29/2020 | 14655 | 13181 | 19089 | DSF0000912722, DSF0000914324
30 | Q141 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 2/5/2021 | 11/1/2021 |  | 188885 | 188885 | 359810 | DSF0000912722, DSF0000914324
30 | Q141 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | CM,F&E | In-Progress | 2/5/2021 | 11/1/2021 |  | 35009 | 35009 | 56430 | DSF0000912722, DSF0000914324
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113038
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113038
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001113038
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113038
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113646
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113646
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113646
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113646
30 | Q141 | I.S. 141 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 2/28/2022 | FTK |  | FTK | 350789 | 207514 | DSF0000960837
30 | Q141 | I.S. 141 - QUEENS | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 82172 | 0 | DSF0000799343
30 | Q141 | I.S. 141 - QUEENS | DOE - RESOA | FY21 RESO A STEM LAB | Construction | Complete | 7/5/2022 | DOER | 4/11/2023 | DOER | 161335 | 162281 | DSF0001008019
30 | Q141 | I.S. 141 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 72000 | 0 | DSF0001086431
30 | Q141 | I.S. 141 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/21/2024 | DOES | 12/3/2024 | DOES | 65832 |  | DSF0001084811
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 12/12/2014 | 5/15/2015 | 2/26/2015 | 127455 | 107788 | 107788 | DSF0000798276, DSF0000789941
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 4/1/2015 | 8/31/2015 | 8/26/2015 | 509820 | 345117 | 338554 | DSF0000798276, DSF0000789941
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 1/9/2017 | 12/9/2018 |  | 9559125 | 8546608 | 8146057 | DSF0000798276, DSF0000789941
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 1/9/2017 | 12/9/2018 |  | 594790 | 701761 | 701761 | DSF0000798276, DSF0000789941
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / EMERGENCY GENERATOR | Scope | Complete | 6/21/2023 | 11/6/2023 | 12/15/2023 | 119002 | 227110 | 205720 | DSF0001073783, DSF0001112095, DSF0001112094, DSF0001101543, DSF0001101544
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / EMERGENCY GENERATOR | Design | In-Progress | 12/27/2023 | 5/29/2024 |  | 584024 | 584024 | 203315 | DSF0001073783, DSF0001112095, DSF0001112094, DSF0001101543, DSF0001101544
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / EMERGENCY GENERATOR | Construction | PNS | PNS | PNS | PNS | 12190420 | 12190420 | 295731 | DSF0001073783, DSF0001112095, DSF0001112094, DSF0001101543, DSF0001101544
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / EMERGENCY GENERATOR | CM,F&E | PNS | PNS | PNS | PNS | 915393 | 915393 | 62495 | DSF0001073783, DSF0001112095, DSF0001112094, DSF0001101543, DSF0001101544
30 | Q145 | I.S. 145 - QUEENS | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 8/29/2023 | DOEL |  | DOEL | 69103 | 4103
30 | Q145 | I.S. 145 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/21/2023 | DOER |  | DOER | 265441 | 0 | DSF0001008092
30 | Q145 | I.S. 145 - QUEENS | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 6/30/2023 | DOER |  | DOER | 235127 | 0 | DSF0001033820
30 | Q145 | I.S. 145 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 8/20/2021 | DOES |  | DOES | 295329 | 0 | DSF0000911912
30 | Q145 | I.S. 145 - QUEENS | Trust For Public Land | FY23 RESO A PLAYGROUND UPGRADE | Construction | Complete | 1/2/2024 | TPL | 9/16/2024 | TPL | 3005000 | 1808090 | DSF0001035913
30 | Q148 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 3/25/2019 | 7/24/2019 | 6/19/2019 | 3729 | 3729 | 6008 | DSF0000912104
30 | Q148 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 6/19/2019 | 11/20/2019 | 11/7/2019 | 16778 | 16778 | 24132 | DSF0000912104
30 | Q148 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/16/2020 | 6/12/2021 |  | 216254 | 216254 | 273993 | DSF0000912104
30 | Q148 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 9/16/2020 | 6/12/2021 |  | 40082 | 40082 | 42449 | DSF0000912104
30 | Q148 | P.S. 148 - QUEENS | DIIT - Project Connect | DATA/VOICE & WIRELESS NETWORK CABLE WIRING, NETWORK SERVER EQUIPMENT, DATA/VOICE & WIRELESS NETWORK | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 294095 | 0 | DSF0000800169
30 | Q148 | P.S. 148 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 316357 | 0 | DSF0001086437
30 | Q148 | P.S. 148 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113043
30 | Q148 | P.S. 148 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 3/19/2021 | DOES |  | DOES | 61927 | 0 | DSF0000866131
30 | Q149 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | Scope | Complete | 6/9/2023 | 12/8/2023 | 11/1/2023 | 233536 | 330304 | 314397 | DSF0001023093, DSF0001023092, DSF0001023091, DSF0001111769, DSF0001111770, DSF0001111768
30 | Q149 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | Design | Complete | 12/18/2023 | 5/20/2024 | 4/22/2024 | 1163035 | 392502 | 392502 | DSF0001023093, DSF0001023092, DSF0001023091, DSF0001111769, DSF0001111770, DSF0001111768
30 | Q149 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | Construction | In-Progress | 9/18/2024 | 9/2/2027 |  | 25766388 | 23362150 | 378885 | DSF0001023093, DSF0001023092, DSF0001023091, DSF0001111769, DSF0001111770, DSF0001111768
30 | Q149 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | CM,F&E | In-Progress | 9/18/2024 | 9/2/2027 |  | 1669604 | 115663 | 114942 | DSF0001023093, DSF0001023092, DSF0001023091, DSF0001111769, DSF0001111770, DSF0001111768
30 | Q149 | P.S. 149 - QUEENS | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0000799344
30 | Q149 | P.S. 149 - QUEENS | DOE - RESOA | FY17 RESO A CAFETERIA UPGRADE | Construction | Complete | 8/3/2018 | DOER | 8/18/2021 | DOER | 283339 | 267622 | DSF0000844782
30 | Q149 | P.S. 149 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 275617 | 0 | DSF0001035917
30 | Q149 | P.S. 149 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 450000 | 374285 | DSF0001086438
30 | Q149 | P.S. 149 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 90000 | 0 | DSF0001113044
30 | Q150 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/28/2019 | 11/14/2019 | 11/6/2019 | 88879 | 169770 | 166917 | DSF0000902814, DSF0000902816, DSF0000902817, DSF0000902818
30 | Q150 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/13/2019 | 4/16/2020 | 6/26/2020 | 444401 | 888107 | 804824 | DSF0000902814, DSF0000902816, DSF0000902817, DSF0000902818
30 | Q150 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 6/8/2021 | 6/7/2023 |  | 9998999 | 17273255 | 12177014 | DSF0000902814, DSF0000902816, DSF0000902817, DSF0000902818
30 | Q150 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 6/8/2021 | 6/7/2023 |  | 622161 | 2179475 | 2167310 | DSF0000902814, DSF0000902816, DSF0000902817, DSF0000902818
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113045
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113045
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001113045
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113045
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113648
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113648
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113648
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113648
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/1/2023 | 6/2/2023 | 10/16/2023 | 0 | 13663 | 13663 | DSF0001035918
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 11/28/2023 | 4/30/2024 | 3/21/2024 | 85107 | 74669 | 59259 | DSF0001035918
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/7/2024 | 9/1/2025 |  | 1248234 | 475010 | 0 | DSF0001035918
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 10/7/2024 | 9/1/2025 |  | 85107 | 48990 | 12800 | DSF0001035918
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/27/2024 | 9/26/2024 | 11/22/2024 | 0 | 18507 | 938 | DSF0001086439
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 3752 | 3752 | DSF0001086439
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086439
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001086439
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/16/2024 | 10/15/2024 | 11/22/2024 | 0 | 0 | 0 | DSF0001087064
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087064
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087064
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087064
30 | Q150 | P.S. 150 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 7/10/2023 | FTK |  | FTK | 329862 | 69387 | DSF0000960588
30 | Q150 | P.S. 150 - QUEENS | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 9/27/2024 | FTK |  | FTK | 27973 | 4825 | DSF0001087524
30 | Q150 | P.S. 150 - QUEENS | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 75000 | 0 | DSF0000867969
30 | Q150 | P.S. 150 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033822
30 | Q150 | P.S. 150 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113046
30 | Q150 | P.S. 150 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001111674
30 | Q150 | P.S. 150 - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113732
30 | Q150 | P.S. 150 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/24/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001084673
30 | Q151 | P.S. 151 - QUEENS | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 1/15/2020 | FTK |  | FTK | 53886 | 53874 | DSF0000912608
30 | Q151 | P.S. 151 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 3/21/2022 | FTK |  | FTK | 207017 | 112509 | DSF0000960680
30 | Q151 | P.S. 151 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113047
30 | Q151 | P.S. 151 - QUEENS | DOE - RESOA | FY08 RESO A PAVED AREAS - CONCRETE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0000544900
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / GYM WINDOWS / RTU REPLACEMENT / FIRE ALARM REPLACEMENT | Scope | Complete | 6/2/2021 | 10/18/2021 | 10/28/2021 | 136645 | 144485 | 144485 | DSF0000997323, DSF0001023153, DSF0001023154, DSF0001034309, DSF0001023158, DSF0001023146
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / GYM WINDOWS / RTU REPLACEMENT / FIRE ALARM REPLACEMENT | Design | Complete | 11/19/2021 | 4/25/2022 | 10/20/2022 | 658969 | 396100 | 381871 | DSF0000997323, DSF0001023153, DSF0001023154, DSF0001034309, DSF0001023158, DSF0001023146
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / GYM WINDOWS / RTU REPLACEMENT / FIRE ALARM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 12728523 | 12728523 | 244118 | DSF0000997323, DSF0001023153, DSF0001023154, DSF0001034309, DSF0001023158, DSF0001023146
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / GYM WINDOWS / RTU REPLACEMENT / FIRE ALARM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 1138450 | 1138450 | 40567 | DSF0000997323, DSF0001023153, DSF0001023154, DSF0001034309, DSF0001023158, DSF0001023146
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 5/28/2019 | 9/26/2019 | 7/2/2019 | 5660 | 3310 | 3310 | DSF0000912105
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 7/2/2019 | 12/4/2019 | 11/6/2019 | 25472 | 13298 | 13298 | DSF0000912105
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/16/2020 | 6/12/2021 |  | 328303 | 328303 | 452673 | DSF0000912105
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | CM,F&E | In-Progress | 9/16/2020 | 6/12/2021 |  | 60849 | 56444 | 56444 | DSF0000912105
30 | Q152 | P.S. 152 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/22/2024 | DIIR |  | DIIR | 150000 | 0 | DSF0001033283
30 | Q152 | P.S. 152 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001086440
30 | Q152 | P.S. 152 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113048
30 | Q166 | P.S. 166 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/5/2023 | 12/4/2023 | 10/26/2023 | 131122 | 166505 | 166505 | DSF0001074229, DSF0001074230, DSF0001111788
30 | Q166 | P.S. 166 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/7/2023 | 6/28/2024 | 4/22/2024 | 655614 | 329066 | 329066 | DSF0001074229, DSF0001074230, DSF0001111788
30 | Q166 | P.S. 166 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 14751305 | 14751305 | 211771 | DSF0001074229, DSF0001074230, DSF0001111788
30 | Q166 | P.S. 166 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 917858 | 917858 | 29261 | DSF0001074229, DSF0001074230, DSF0001111788
30 | Q166 | P.S. 166 - QUEENS | SCA IEH | PO18-TEST FLOOR TILES IN RM 452,436.IF POSITIVE ABATE & REPLACE FLOORS ARE BUCKLING DUE TO WATER DAM | Construction | Complete | 9/23/2024 | IEH | 10/9/2024 | IEH | 0 | 0 | SCA0000073410
30 | Q166 | P.S. 166 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 223941 | 185371 | DSF0000961031
30 | Q166 | P.S. 166 - QUEENS | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 10/31/2024 | FTK |  | FTK | 25880 | 4825 | DSF0001087528
30 | Q166 | P.S. 166 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113057
30 | Q166 | P.S. 166 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 308864 | 0 | DSF0001086453
30 | Q166 | P.S. 166 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001086452
30 | Q166 | P.S. 166 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001112086
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 3/6/2020 | 6/22/2020 | 7/9/2021 | 36021 | 71967 | 71967 | DSF0001023504, DSF0000997642
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | Complete | 7/27/2021 | 12/29/2021 | 1/19/2022 | 175581 | 238814 | 215157 | DSF0001023504, DSF0000997642
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Construction | In-Progress | 7/27/2022 | 1/17/2024 |  | 3559571 | 6728695 | 6221381 | DSF0001023504, DSF0000997642
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | CM,F&E | In-Progress | 7/27/2022 | 1/17/2024 |  | 286043 | 1027507 | 1022411 | DSF0001023504, DSF0000997642
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS FIRE ALARM UPGRADE / DCAS ELECTRICAL SERVICE UPGRADE | Scope | Complete | 8/25/2023 | 1/22/2024 | 5/21/2024 | 170996 | 133675 | 113237 | DSF0001085600, DSF0001112321, DSF0001112320
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS FIRE ALARM UPGRADE / DCAS ELECTRICAL SERVICE UPGRADE | Design | In-Progress | 6/19/2024 | 1/16/2025 |  | 832113 | 832113 | 213187 | DSF0001085600, DSF0001112321, DSF0001112320
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS FIRE ALARM UPGRADE / DCAS ELECTRICAL SERVICE UPGRADE | Construction | PNS | PNS | PNS | PNS | 17485200 | 17485200 | 140411 | DSF0001085600, DSF0001112321, DSF0001112320
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | DCAS ELECTRIFICATION/HEAT PUMP SYSTEMS / DCAS FIRE ALARM UPGRADE / DCAS ELECTRICAL SERVICE UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 1319040 | 1319040 | 71002 | DSF0001085600, DSF0001112321, DSF0001112320
30 | Q171 | P.S. 171 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/20/2020 | EMER |  | EMER |  | 0 | SCA0000063767
30 | Q171 | P.S. 171 - QUEENS | SCA IEH | PO18-TEST INSULATION FOR ACM ON ON GATE VALVE IN ROOM 130. ABATE IF POSTIVE VALVE LOCATED IN CRAWL S | Construction | Complete | 9/11/2024 | IEH | 9/14/2024 | IEH | 0 | 0 | SCA0000073367
30 | Q171 | P.S. 171 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 159000 | 0 | DSF0001113060
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY19 RESO A SOLAR PANEL INSTALLATION | Construction | In-Progress | 1/3/2019 | DOER |  | DOER | 1037313 | 0 | DSF0000890895
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/8/2021 | DOER |  | DOER | 38177 | 0 | DSF0000913416
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/15/2022 | DOER |  | DOER | 228155 | 0 | DSF0001034961
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 63081 | 0 | DSF0001086455
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/22/2024 | DOER |  | DOER | 102696 | 0 | DSF0001087207
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 3/23/2024 | DOER |  | DOER | 100000 | 3500 | DSF0001087204
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 6/28/2024 | DOER |  | DOER | 75282 | 0 | DSF0001087205
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/16/2023 | DOER |  | DOER | 180000 | 1424 | DSF0001111824
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | RESO A FLOORING | Construction | PNS | PNS | PNS | PNS | DOER | 49327 | 0 | DSF0001112208
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112209
30 | Q171 | P.S. 171 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/19/2021 | DOES |  | DOES | 135591 | 0 | DSF0001008712
30 | Q204 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/14/2020 | 11/10/2020 | 9/9/2020 | 138890 | 203783 | 203783 | DSF0000949262, DSF0000949263, DSF0000961568
30 | Q204 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 9/21/2020 | 7/1/2021 | 5/7/2021 | 694451 | 595767 | 591869 | DSF0000949262, DSF0000949263, DSF0000961568
30 | Q204 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | Construction | Complete | 7/15/2021 | 10/2/2023 | 9/12/2024 | 15625125 | 14379374 | 13538144 | DSF0000949262, DSF0000949263, DSF0000961568
30 | Q204 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | CM,F&E | Complete | 7/15/2021 | 10/2/2023 | 9/12/2024 | 972230 | 830125 | 821369 | DSF0000949262, DSF0000949263, DSF0000961568
30 | Q204 | I.S. 204 - QUEENS | Fast Track Projects | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/10/2023 | FTK |  | FTK | 92849 | 74748 | DSF0001033857
30 | Q204 | ENERGY TECH HIGH SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 9/25/2024 | DIIR | 12/17/2024 | DIIR | 49821 | 49821 | DSF0001033881
30 | Q204 | I.S. 204 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001035976
30 | Q204 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/30/2024 | DIIR | 11/6/2024 | DIIR | 75000 | 75000 | DSF0001035977
30 | Q204 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086471
30 | Q204 | I.S. 204 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113091
30 | Q204 | I.S. 204 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0 | DSF0001113090
30 | Q204 | I.S. 204 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/9/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084820
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113098
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113098
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001113098
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113098
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113654
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113654
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113654
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113654
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035985
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER | Design | PNS | PNS | PNS | PNS | 21000 | 21000 | 0 | DSF0001035985
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | 308000 | 308000 | 0 | DSF0001035985
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER | CM,F&E | PNS | PNS | PNS | PNS | 21000 | 21000 | 0 | DSF0001035985
30 | Q212 | P.S. 212 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 98000 | 0 | DSF0001113097
30 | Q212 | P.S. 212 - QUEENS | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0 | DSF0001086479
30 | Q212 | P.S. 212 - QUEENS | DOE - Skilled Trades | ACE BMS UPGRADE | Construction | In-Progress | 2/23/2023 | DOES |  | DOES | 980644 | 0 | DSF0001074980
30 | Q222 | P.S. 222 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 1/8/2024 | 5/22/2024 | 9/4/2024 | 17676 | 34424 | 11605 | DSF0001075153
30 | Q222 | P.S. 222 - QUEENS | SCA CIP | ROOFS | Design | In-Progress | 10/9/2024 | 3/17/2025 |  | 88382 | 88382 | 17650 | DSF0001075153
30 | Q222 | P.S. 222 - QUEENS | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 1988597 | 1988597 | 0 | DSF0001075153
30 | Q222 | P.S. 222 - QUEENS | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 123735 | 123735 | 775 | DSF0001075153
30 | Q222 | P.S. 222 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 3/21/2022 | FTK |  | FTK | 258575 | 141171 | DSF0000960903
30 | Q222 | P.S. 222 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/11/2023 | DOES | 9/18/2024 | DOES | 50832 |  | DSF0001084385
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 8/26/2019 | 11/26/2019 | 3/9/2020 | 13800 | 52618 | 52618 | DSF0000903926
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 3/11/2020 | 8/10/2020 | 12/9/2021 | 69000 | 141513 | 139356 | DSF0000903926
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Construction | In-Progress | 6/13/2022 | 6/12/2023 |  | 1552500 | 1390189 | 1303939 | DSF0000903926
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 6/13/2022 | 6/12/2023 |  | 96600 | 66668 | 66127 | DSF0000903926
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/11/2022 | 12/13/2022 | 8/25/2022 | 6010 | 2479 | 2479 | DSF0001034669
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/25/2022 | 3/31/2023 | 3/8/2023 | 27045 | 9914 | 9914 | DSF0001034669
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/24/2023 | 5/18/2024 |  | 348580 | 312355 | 219639 | DSF0001034669
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/24/2023 | 5/18/2024 |  | 177491 | 162166 | 106463 | DSF0001034669
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001035998
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Design | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001035998
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001035998
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 3808 | DSF0001035998
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/15/2018 | 3/21/2019 | 3/29/2019 | 0 | 14771 | 14771 | DSF0000890910
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 4/2/2021 | 9/1/2021 | 9/29/2022 | 126000 | 90612 | 89571 | DSF0000890910
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/20/2023 | 4/14/2024 |  | 1848000 | 1718900 | 917750 | DSF0000890910
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | CM,F&E | In-Progress | 7/20/2023 | 4/14/2024 |  | 126000 | 141825 | 104433 | DSF0000890910
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 5/12/2021 | 8/26/2021 | 1/12/2022 | 0 | 37130 | 37130 | DSF0000913436
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Design | Complete | 1/18/2022 | 6/17/2022 | 5/11/2022 | 148007 | 140827 | 138235 | DSF0000913436
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 3/20/2023 | 3/18/2024 |  | 2170772 | 2171793 | 1832948 | DSF0000913436
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 3/20/2023 | 3/18/2024 |  | 257782 | 253166 | 239736 | DSF0000913436
30 | Q227 | I.S. 227 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 150000 | 0 | DSF0001086484
30 | Q227 | I.S. 227 - QUEENS | DOE - Skilled Trades | HVAC SYSTEM REPLACEMENT | Construction | In-Progress | 10/15/2022 | DOES |  | DOES | 1000000 | 1654985 | DSF0000903942
30 | Q227 | I.S. 227 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/19/2023 | DOES | 11/12/2024 | DOES | 522304 | 432816 | DSF0001035104
30 | Q227 | I.S. 227 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/24/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084685
30 | Q228 | P.S. 228 - QUEENS | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 5/20/2020 | 11/17/2020 | 10/30/2020 | 49706 | 204303 | 204273 | DSF0000956474, DSF0000956473, DSF0001008581
30 | Q228 | P.S. 228 - QUEENS | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 5/27/2021 | 11/23/2021 | 11/22/2021 | 242850 | 412263 | 412263 | DSF0000956474, DSF0000956473, DSF0001008581
30 | Q228 | P.S. 228 - QUEENS | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 4972825 | 4972825 | 7438 | DSF0000956474, DSF0000956473, DSF0001008581
30 | Q228 | P.S. 228 - QUEENS | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 390543 | 390543 | 27361 | DSF0000956474, DSF0000956473, DSF0001008581
30 | Q230 | I.S. 230 - QUEENS | SCA CIP | FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE | Scope | Complete | 11/7/2019 | 3/27/2020 | 12/7/2021 | 117767 | 167689 | 164537 | DSF0000914308, DSF0001024500, DSF0001024508
30 | Q230 | I.S. 230 - QUEENS | SCA CIP | FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE | Design | In-Progress | 1/26/2022 | 6/27/2022 |  | 588832 | 588832 | 211724 | DSF0000914308, DSF0001024500, DSF0001024508
30 | Q230 | I.S. 230 - QUEENS | SCA CIP | FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | 13248721 | 13248721 | 107 | DSF0000914308, DSF0001024500, DSF0001024508
30 | Q230 | I.S. 230 - QUEENS | SCA CIP | FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 824365 | 824365 | 18523 | DSF0000914308, DSF0001024500, DSF0001024508
30 | Q230 | I.S. 230 - QUEENS | SCA CIP | ROOFS | Scope | In-Progress | 8/22/2024 | 1/10/2025 |  | 10391 | 71966 | 47530 | DSF0001075681
30 | Q230 | I.S. 230 - QUEENS | SCA CIP | ROOFS | Design | PNS | PNS | PNS | PNS | 51955 | 51955 | 32000 | DSF0001075681
30 | Q230 | I.S. 230 - QUEENS | SCA CIP | ROOFS | Construction | PNS | PNS | PNS | PNS | 1168997 | 1168997 | 152 | DSF0001075681
30 | Q230 | I.S. 230 - QUEENS | SCA CIP | ROOFS | CM,F&E | PNS | PNS | PNS | PNS | 72738 | 72738 | 12439 | DSF0001075681
30 | Q230 | I.S. 230 - QUEENS | DIIT - RESOA | FY10 RESO A- DESKTOP COMPUTERS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500 | 0 | DSF0000690219
30 | Q230 | I.S. 230 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/11/2022 | DOES |  | DOES | 113272 | 0 | DSF0001009065
30 | Q230 | I.S. 230 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084825
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/27/2019 | 11/13/2019 | 12/13/2019 | 37229 | 49125 | 49125 | DSF0000910496, DSF0000910497, DSF0000960825
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 12/13/2019 | 5/15/2020 | 7/16/2020 | 175017 | 231178 | 224443 | DSF0000910496, DSF0000910497, DSF0000960825
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | Complete | 6/27/2022 | 12/18/2023 | 10/9/2024 | 2975201 | 2662998 | 2462953 | DSF0000910496, DSF0000910497, DSF0000960825
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | Complete | 6/27/2022 | 12/18/2023 | 10/9/2024 | 344072 | 252814 | 235338 | DSF0000910496, DSF0000910497, DSF0000960825
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/21/2021 | 2/25/2022 | 7/11/2022 | 19517 | 45913 | 25116 | SCA0000070749, DSF0001113767
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | In-Progress | 10/9/2024 | 3/17/2025 |  | 88558 | 111106 | 23441 | SCA0000070749, DSF0001113767
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 1699096 | 1699096 | 0 | SCA0000070749, DSF0001113767
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 206599 | 206599 | 1866 | SCA0000070749, DSF0001113767
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/21/2024 | 11/6/2024 | 10/30/2024 | 139333 | 85963 | 85963 | DSF0001103152, DSF0001113838
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | In-Progress | 12/18/2024 | 5/21/2025 |  | 647845 | 647845 | 250593 | DSF0001103152, DSF0001113838
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 10251849 | 10251849 | 0 | DSF0001103152, DSF0001113838
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 1048193 | 1048193 | 19838 | DSF0001103152, DSF0001113838
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113112
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113112
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001113112
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001113112
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113656
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113656
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113656
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113656
30 | Q234 | P.S. 234 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 50000 | 47624 | DSF0001033299
30 | Q234 | I.S. 235 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0 | DSF0001086486
30 | Q234 | P.S. 234 - QUEENS | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 3/22/2022 | DOER |  | DOER | 36221 | 0 | DSF0000913441
30 | Q234 | I.S. 235 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 428000 | 0 | DSF0001086487
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 10/29/2019 | 4/28/2020 | 2/20/2020 | 3740 | 19250 | 19250 | DSF0000890589
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2/25/2020 | 8/18/2020 | 4/28/2020 | 16830 | 76997 | 76997 | DSF0000890589
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | In-Progress | 6/23/2021 | 3/19/2022 |  | 216920 | 214510 | 131850 | DSF0000890589
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | In-Progress | 6/23/2021 | 3/19/2022 |  | 40205 | 37675 | 37280 | DSF0000890589
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 6/8/2021 | 10/22/2021 | 12/30/2021 | 39437 | 47852 | 47852 | DSF0000998634
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | ROOFS | Design | Complete | 1/25/2022 | 6/24/2022 | 5/5/2022 | 197184 | 162430 | 162430 | DSF0000998634
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | ROOFS | Construction | Complete | 8/18/2022 | 2/8/2024 | 12/14/2023 | 4436634 | 3949354 | 3705248 | DSF0000998634
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | ROOFS | CM,F&E | Complete | 8/18/2022 | 2/8/2024 | 12/14/2023 | 276057 | 137274 | 116921 | DSF0000998634
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 2/8/2023 | 3/13/2024 | 2/12/2024 | 17052 | 45168 | 45168 | DSF0001034346, DSF0001111866
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 2/21/2024 | 6/24/2024 | 3/27/2024 | 76736 | 75887 | 68789 | DSF0001034346, DSF0001111866
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 989037 | 989037 | 2442 | DSF0001034346, DSF0001111866
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 183313 | 183313 | 23737 | DSF0001034346, DSF0001111866
30 | Q292 | P.S. 92 - QUEENS | Fast Track Projects | LSP BOOSTER SYSTEM REPLACEMENT | Construction | In-Progress | 1/29/2024 | FTK |  | FTK | 127500 | 110280 | DSF0001085830
30 | Q292 | P.S. 92 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | Complete | 10/3/2024 | DOER | 11/17/2024 | DOER | 108891 |  | DSF0001036022
30 | Q292 | P.S. 92 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 290915 | 0 | DSF0001036023
30 | Q292 | P.S. 92 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113126
30 | Q292 | P.S. 92 - QUEENS | DOE - Skilled Trades | FIRE STOPPING | Construction | In-Progress | 7/15/2019 | DOES |  | DOES | 2224704 | 0 | DSF0000866321
30 | Q292 | P.S. 92 - QUEENS | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 12/20/2023 | DOES |  | DOES | 256035 | 0 | DSF0001111891
30 | Q297 | I.S. 230 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 10/11/2024 | IEH | 10/30/2024 | IEH | 0 | 0 | SCA0000073496
30 | Q312 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/30/2024 | DIIR | 11/6/2024 | DIIR | 75000 | 75000 | DSF0001036026
30 | Q312 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086507
30 | Q312 | P.S. 78 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 11/15/2024 | DIIR | 74387 | 74387 | DSF0001086508
30 | Q312 | P.S. 78 - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001112256
30 | Q312 | P.S. 78 - QUEENS | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 4/22/2024 | DOER |  | DOER | 90943 | 0 | DSF0000914072
30 | Q329 | EAST ELMHURST COMMUNITY SCHOOL - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033315
30 | Q329 | EAST ELMHURST COMMUNITY SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001113132
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/14/2023 | 3/18/2024 | 7/1/2024 | 0 | 18721 | 18721 | DSF0001086513
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | In-Progress | 7/9/2024 | 11/22/2024 |  | 60000 | 51657 | 27332 | DSF0001086513
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001086513
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 23423 | DSF0001086513
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | In-Progress | 12/18/2024 | 4/21/2025 |  | 0 | 0 | 0 | DSF0001113137
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001113137
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 88000 | 88000 | 0 | DSF0001113137
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 6000 | 6000 | 0 | DSF0001113137
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113661
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113661
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113661
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113661
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113136
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 12/21/2016 | 6/28/2017 | 6/28/2017 | 1494500 | 1339068 | 1338951 | DSF0000843659
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 6/29/2017 | 1/9/2018 | 5/12/2023 | 6725250 | 3229962 | 2737683 | DSF0000843659
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 9/30/2024 | 9/3/2027 |  | 84812875 | 75640875 | 888129 | DSF0000843659
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 9/30/2024 | 9/3/2027 |  | 11956000 | 4806890 | 572327 | DSF0000843659
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 11/14/2022 | 11/14/2022 | 11/14/2022 | 187000 | 4423 | 4423 | DSF0000843659
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 11/15/2022 | 1/11/2023 | 4/27/2023 | 935000 | 296662 | 216777 | DSF0000843659
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | Construction | In-Progress | 7/23/2024 | 1/18/2025 |  | 21037500 | 18910867 | 81980 | DSF0000843659
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 7/23/2024 | 1/18/2025 |  | 1309000 | 306027 | 291268 | DSF0000843659
30 | Q346 | Q000 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/15/2024 | IEH | 7/27/2024 | IEH | 0 | 0 | SCA0000073134
30 | Q346 | Q000 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/12/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085502
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113140
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001113140
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001113140
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001113140
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113662
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113662
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113662
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113662
30 | Q397 | DISTRICT 30 PRE-K CENTER | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | Complete | 12/23/2021 | DOER | 4/11/2023 | DOER | 110205 | 136443 | DSF0000913447
30 | Q398 | P.S. 398 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/8/2024 | DOES | 10/3/2024 | DOES | 50832 |  | DSF0001084418
30 | Q404 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/30/2024 | DIIR | 11/6/2024 | DIIR | 75000 | 75000 | DSF0001036037
30 | Q404 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 6/3/2024 | DIIR |  | DIIR | 75000 | 0 | DSF0001086519
30 | Q404 | HUNTERS POINT COMMUNITY MIDDLE SCHOOL -Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113147
30 | Q404 | ACAD FOR CAREERS IN TV AND FILM -Q | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | Complete | 1/9/2023 | DOER | 4/21/2023 | DOER | 19229 | 23614 | DSF0001008102
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/15/2021 | 10/1/2021 | 10/7/2021 | 0 | 34720 | 34720 | DSF0000913110, DSF0000913111
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Design | Complete | 10/13/2021 | 12/17/2021 | 12/1/2021 | 73318 | 181318 | 167836 | DSF0000913110, DSF0000913111
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/11/2022 | 1/5/2023 |  | 1075337 | 945797 | 886243 | DSF0000913110, DSF0000913111
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | CM,F&E | In-Progress | 4/11/2022 | 1/5/2023 |  | 73318 | 118610 | 116895 | DSF0000913110, DSF0000913111
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 681551 | 0 | DSF0000960206
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 5/20/2024 | DIIR | 125648 | 125648 | DSF0001036049
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 295166 | 0 | DSF0001033322
30 | Q447 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | Scope | Complete | 8/3/2021 | 8/24/2021 | 8/24/2021 | 239760 | 228541 | 228541 | DSF0001009246
30 | Q447 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | Design | Complete | 8/25/2021 | 11/22/2021 | 3/8/2022 | 1078920 | 1199369 | 1116831 | DSF0001009246
30 | Q447 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | Construction | In-Progress | 7/13/2022 | 9/3/2023 |  | 13606380 | 12428258 | 12130003 | DSF0001009246
30 | Q447 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | CM,F&E | In-Progress | 7/13/2022 | 9/3/2023 |  | 1940169 | 635364 | 1102568 | DSF0001009246
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | Scope | Complete | 9/27/2016 | 9/28/2016 | 9/28/2016 | 11670 | 16446 | 16446 | DSF0000845578
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | Design | Complete | 9/28/2016 | 3/28/2017 | 4/24/2017 | 42790 | 66783 | 66658 | DSF0000845578
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | Construction | In-Progress | 6/27/2017 | 12/23/2017 |  | 453185 | 464089 | 430158 | DSF0000845578
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | CM,F&E | In-Progress | 6/27/2017 | 12/23/2017 |  | 105030 | 65451 | 64526 | DSF0000845578
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/4/2022 | 12/6/2022 | 9/28/2022 | 5550 | 4288 | 4288 | DSF0001034660
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/28/2022 | 3/29/2023 | 3/8/2023 | 24975 | 17152 | 17152 | DSF0001034660
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 7/24/2023 | 5/18/2024 |  | 321900 | 292144 | 195524 | DSF0001034660
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 7/24/2023 | 5/18/2024 |  | 164768 | 152412 | 95154 | DSF0001034660
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | Scope | Complete | 8/10/2020 | 5/25/2023 | 2/22/2023 | 91056 | 113444 | 105971 | DSF0000961087, DSF0001034485, DSF0001025337, DSF0001083696
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | Design | Complete | 2/22/2023 | 6/26/2023 | 5/11/2023 | 449880 | 702272 | 663615 | DSF0000961087, DSF0001034485, DSF0001025337, DSF0001083696
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | Construction | In-Progress | 8/11/2023 | 5/1/2025 |  | 9654766 | 9017108 | 1003751 | DSF0000961087, DSF0001034485, DSF0001025337, DSF0001083696
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | CM,F&E | In-Progress | 8/11/2023 | 5/1/2025 |  | 685653 | 1605019 | 1520450 | DSF0000961087, DSF0001034485, DSF0001025337, DSF0001083696
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA IEH | PO18-TEST ROOM 004 WALL PLASTER &IF POSITIVE ABATE & REPLASTER | Construction | Complete | 7/26/2024 | IEH | 9/1/2024 | IEH | 0 | 0 | SCA0000073180
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA IEH | PO18-(2)-4' OSY AND (1) 3'OS&Y VALVE DOMESTIC WATER APPPROX 15LFT OF REMOVAL, BASEMENT - BOILER ROOM | Construction | Complete | 12/3/2024 | IEH | 12/18/2024 | IEH | 0 | 0 | SCA0000073661
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA IEH | PO18-77/30Q450/ OPEN CEILING IN ROOM 107 ABATE ANY ACM PIPE INSULATION ON LEAKING PIPE AND ANY ABOV | Construction | Complete | 12/11/2024 | IEH | 12/15/2024 | IEH | 0 | 0 | SCA0000073692
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 3/1/2023 | FTK |  | FTK | 2257299 | 1799225 | DSF0001034538
30 | Q450 | GOTHAM TECH HIGH SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113160
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113161
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0 | DSF0001086539
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DOE - Skilled Trades | ENVIRONMENTAL BENEFIT PROJECT | Construction | In-Progress | 5/12/2018 | DOES |  | DOES | 2779989 | 0 | SCA0000051025
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 2/24/2023 | DOES | 9/8/2023 | DOES | 611969 | 602643 | DSF0001035096
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/19/2024 | DOES | 8/26/2024 | DOES | 65832 | 17981 | DSF0001085006
30 | Q451 | ACADEMY OF AMERICAN STUDIES - Q | DOE - Skilled Trades | INSTALLATION AND RELOCATION OF SPLIT DUCTLESS UNIT | Construction | In-Progress | 6/22/2018 | DOES |  | DOES | 62700 | 0 | DSF0000889348
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Scope | Complete | 5/5/2014 | 9/18/2014 | 12/22/2014 | 325500 | 207420 | 207420 | DSF0000791664, DSF0000814902, DSF0000814906, DSF0000814904
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Design | Complete | 3/10/2015 | 8/7/2015 | 12/23/2015 | 1302001 | 1477754 | 1304544 | DSF0000791664, DSF0000814902, DSF0000814906, DSF0000814904
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 8/5/2019 | 8/3/2021 |  | 24412499 | 28232987 | 16639316 | DSF0000791664, DSF0000814902, DSF0000814906, DSF0000814904
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 8/5/2019 | 8/3/2021 |  | 1519000 | 2267142 | 2126856 | DSF0000791664, DSF0000814902, DSF0000814906, DSF0000814904
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | Scope | Complete | 8/24/2015 | 12/24/2015 | 12/12/2016 | 32700 | 47542 | 47542 | DSF0000822192
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | Design | Complete | 12/14/2016 | 5/8/2017 | 12/29/2017 | 130800 | 218157 | 209038 | DSF0000822192
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | Construction | In-Progress | 4/16/2018 | 4/15/2019 |  | 2452500 | 2740433 | 2551048 | DSF0000822192
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | CM,F&E | In-Progress | 4/16/2018 | 4/15/2019 |  | 177728 | 508051 | 487717 | DSF0000822192
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | PUBLIC ADDRESS SYSTEM REPLACEMENT | Scope | Complete | 6/7/2023 | 9/7/2023 | 9/8/2023 | 13456 | 4658 | 4658 | DSF0001076153
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | PUBLIC ADDRESS SYSTEM REPLACEMENT | Design | Complete | 9/20/2023 | 2/26/2024 | 2/23/2024 | 67278 | 18632 | 18632 | DSF0001076153
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | PUBLIC ADDRESS SYSTEM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 1513765 | 1513765 | 0 | DSF0001076153
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | PUBLIC ADDRESS SYSTEM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 94190 | 94190 | 8412 | DSF0001076153
30 | Q452 | LONG ISLAND CITY H.S. | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Scope | Complete | 1/9/2024 | 4/9/2024 | 8/1/2024 | 0 | 5481 | 5481 | DSF0001086540
30 | Q452 | LONG ISLAND CITY H.S. | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Design | In-Progress | 8/8/2024 | 1/13/2025 |  | 45000 | 39519 | 21927 | DSF0001086540
30 | Q452 | LONG ISLAND CITY H.S. | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001086540
30 | Q452 | LONG ISLAND CITY H.S. | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 7261 | DSF0001086540
30 | Q452 | LONG ISLAND CITY HS - Q | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000867819
30 | Q452 | LONG ISLAND CITY HS - Q | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 105000 | 0 | DSF0000867456
30 | Q452 | Q993 SPED - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000914091
30 | Q452 | LONG ISLAND CITY HS - Q | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008022
30 | Q452 | Q993 SPED - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008028
30 | Q452 | Q993 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113162
30 | Q452 | LONG ISLAND CITY HS - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085007
30 | Q452 | LONG ISLAND CITY HS - Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/5/2024 | DOES |  | DOES | 675423 | 0 | DSF0001085760
30 | Q472 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 6/11/2018 | 1/4/2019 | 1/4/2019 | 3577000 | 2492366 | 2414219 | DSF0000866092
30 | Q472 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 1/7/2019 | 12/11/2019 | 5/5/2021 | 16096500 | 10142390 | 9812119 | DSF0000866092
30 | Q472 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 9/15/2021 | 9/3/2025 |  | 202994750 | 198735673 | 191920074 | DSF0000866092
30 | Q472 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 9/15/2021 | 9/3/2025 |  | 28616000 | 17733740 | 9193612 | DSF0000866092
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/6/2023 | 9/25/2023 | 10/26/2023 | 1627873 | 1032514 | 1025766 | DSF0000889670
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 10/27/2023 | 4/15/2024 | 5/14/2024 | 6511491 | 1678914 | 1277178 | DSF0000889670
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 89939971 | 89939971 | 562426 | DSF0000889670
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 11802078 | 11802078 | 510565 | DSF0000889670
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 4/14/2023 | 4/14/2023 | 4/14/2023 | 90859 | 6861 | 6861 | DSF0000889670
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 4/17/2023 | 10/6/2023 | 11/29/2023 | 454294 | 372276 | 372276 | DSF0000889670
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 10221614 | 10221614 | 402897 | DSF0000889670
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 636012 | 636012 | 64882 | DSF0000889670
30 | Q570 | FRANK SINATRA SCL OF THE ARTS HS - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 35000 | 0 | DSF0000890411
30 | Q570 | Q993 SPED - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008119
30 | Q570 | Q993 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001036069
30 | Q570 | FRANK SINATRA SCL OF THE ARTS HS - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/12/2024 | DIIR |  | DIIR | 100000 | 0 | DSF0001086567
30 | Q570 | FRANK SINATRA SCL OF THE ARTS HS - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001113178
30 | Q570 | FRANK SINATRA SCL OF THE ARTS HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/11/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085021
30 | Q575 | ACADEMY OF AMERICAN STUDIES - Q | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113179
30 | Q667 | Q004 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001036076
30 | Q667 | Q004 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113187
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 6/24/2023 | FTK |  | FTK | 1083629 | 964912 | DSF0001034949
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001113196
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0 | DSF0001086580
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/18/2023 | DOES | 6/5/2023 | DOES | 325412 | 321034 | DSF0001035108
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | DOE - Skilled Trades | BMS UPGRADE | Construction | In-Progress | 5/20/2024 | DOES |  | DOES | 1512831 | 0 | DSF0001104781
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | Scope | Complete | 7/17/2018 | 10/16/2018 | 9/24/2018 | 42642 | 48620 | 48620 | DSF0000889660
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | Design | Complete | 12/6/2018 | 6/7/2019 | 5/16/2019 | 170568 | 190842 | 190842 | DSF0000889660
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | Construction | In-Progress | 8/12/2019 | 7/11/2020 |  | 3198151 | 3252357 | 3167407 | DSF0000889660
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | CM,F&E | In-Progress | 8/12/2019 | 7/11/2020 |  | 200191 | 293924 | 292824 | DSF0000889660
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/28/2022 | 3/3/2023 | 12/6/2022 | 2169 | 1647 | 1647 | DSF0001034562
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/6/2022 | 6/2/2023 | 4/11/2023 | 9759 | 6586 | 6586 | DSF0001034562
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/5/2023 | 9/3/2024 |  | 125783 | 119096 | 107379 | DSF0001034562
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/5/2023 | 9/3/2024 |  | 119137 | 118418 | 72851 | DSF0001034562
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP RESOA | FY21 RESO A ROBOTICS LAB | Scope | Complete | 8/19/2021 | 12/22/2021 | 1/6/2023 | 0 | 23863 | 23863 | DSF0000961437
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP RESOA | FY21 RESO A ROBOTICS LAB | Design | Complete | 3/10/2023 | 8/10/2023 | 8/11/2023 | 42000 | 83966 | 82380 | DSF0000961437
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP RESOA | FY21 RESO A ROBOTICS LAB | Construction | PNS | PNS | PNS | PNS | 616000 | 616000 | 2360 | DSF0000961437
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP RESOA | FY21 RESO A ROBOTICS LAB | CM,F&E | PNS | PNS | PNS | PNS | 42000 | 42000 | 10642 | DSF0000961437
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | DOE - RESOA | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 8/5/2022 | DOER |  | DOER | 112044 | 0 | DSF0000866379
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113197
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/5/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085535
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/9/2022 | 3/15/2023 | 1/18/2023 | 2046 | 3712 | 3712 | DSF0001034555
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/18/2023 | 7/14/2023 | 4/11/2023 | 9205 | 15142 | 14849 | DSF0001034555
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/5/2023 | 9/3/2024 |  | 118639 | 115189 | 100017 | DSF0001034555
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/5/2023 | 9/3/2024 |  | 122985 | 121721 | 76153 | DSF0001034555
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087099
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087099
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087099
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087099
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 3/13/2023 | FTK |  | FTK | 307007 | 90293 | DSF0001026082
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001111754
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113198
30 | Q800 | DIV OF SCHOOL FACILITIES - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 7/23/2018 | EMER |  | EMER | 700467 | 520487 | SCA0000052805
30 | Q800 | CITIBANK - QUEENS | SCA IEH | PO18-ACM TEST/ABATE/REPLACE AS NECESSARY FLOORS IN THE FOLLOWING AREAS: 1) 6TH FLOOR SERVICE AREA, P | Construction | In-Progress | 3/17/2023 | IEH |  | IEH | 0 | 0 | SCA0000071832
30 | Q800 | D.O.T. - QUEENS | DOE - Skilled Trades | ELEVATOR MOTOR & GENERATOR | Construction | In-Progress | 2/13/2024 | DOES |  | DOES | 229179 | 69586 | DSF0001104902
30 | Q801 | SCHOOL FOOD SERVICE - QUEENS | SCA IEH | IEH PO18-DOCK & WAREHOUSE PIPE INSULATION | Construction | In-Progress | 5/25/2021 | IEH |  | IEH | 0 | 0 | SCA0000069629
30 | Q801 | SCHOOL FOOD SERVICE - QUEENS | SCA IEH | PO18-CAGE ADJACENT TO ROOM 516A ABATE 15 L.F. PIPE INSULATION ASSIGNED TO SCA AS EMERGENCY AS PER SC | Construction | Complete | 11/1/2024 | IEH | 11/2/2024 | IEH | 0 | 0 | SCA0000073582
30 | Q801 | BUREAU OF SUPPLIES - QUEENS | Fast Track Projects | EMERGENCY PROTECTIVE MEASURES - HURRICANE SANDY | Construction | In-Progress | 10/31/2012 | FTK |  | FTK | 3053683 | 2731376 | DSF0000777713
30 | Q801 | BUREAU OF SUPPLIES - QUEENS | DOE - Skilled Trades | ROOM CONVERSION- CONVERT TO TRAINING ROOM | Construction | In-Progress | 6/9/2016 | DOES |  | DOES | 8943 | 0 | DSF0000801052
30 | Q801 | BUREAU OF SUPPLIES - QUEENS | DOE - Skilled Trades | FIRE PUMP REPLACEMENT | Construction | In-Progress | 9/30/2020 | DOES |  | DOES | 240179 | 0 | DSF0000961535
30 | Q801 | QUEENS AREA OFFICE - QUEENS | DOE - Skilled Trades | MASONRY REPAIRS | Construction | In-Progress | 1/18/2024 | DOES |  | DOES | 102123 | 0 | DSF0001104928
30 | Q868 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/25/2023 | 5/24/2023 | 2/21/2023 | 2168 | 2199 | 2199 | DSF0001034550
30 | Q868 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/21/2023 | 8/16/2023 | 4/11/2023 | 9756 | 8794 | 8794 | DSF0001034550
30 | Q868 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/5/2023 | 9/3/2024 |  | 125746 | 120843 | 33978 | DSF0001034550
30 | Q868 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/5/2023 | 9/3/2024 |  | 113154 | 111185 | 65353 | DSF0001034550
30 | Q868 | P.S. 78 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/25/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085541
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP | RTU REPLACEMENT / BMS SYSTEM UPGRADE / FIRE ALARM REPLACEMENT | Scope | Complete | 3/2/2021 | 7/15/2021 | 7/15/2021 | 74411 | 72813 | 72813 | DSF0000950630, DSF0001009333, DSF0000999634
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP | RTU REPLACEMENT / BMS SYSTEM UPGRADE / FIRE ALARM REPLACEMENT | Design | Complete | 9/8/2021 | 3/16/2022 | 9/13/2022 | 372050 | 294846 | 280325 | DSF0000950630, DSF0001009333, DSF0000999634
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP | RTU REPLACEMENT / BMS SYSTEM UPGRADE / FIRE ALARM REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 8371134 | 8371134 | 7079 | DSF0000950630, DSF0001009333, DSF0000999634
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP | RTU REPLACEMENT / BMS SYSTEM UPGRADE / FIRE ALARM REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 520870 | 520870 | 18291 | DSF0000950630, DSF0001009333, DSF0000999634
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001036091
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0001036091
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 44000 | 44000 | 0 | DSF0001036091
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 3000 | 3000 | 0 | DSF0001036091
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 175000 | 0 | DSF0001008099
31 | R001 | P.S. 1 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A BREEZEWAY | Scope | Complete | 1/28/2022 | 5/27/2022 | 6/23/2022 | 0 | 38726 | 38726 | DSF0001033957
31 | R001 | P.S. 1 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A BREEZEWAY | Design | Complete | 7/5/2022 | 12/6/2022 | 1/25/2023 | 37040 | 49693 | 49693 | DSF0001033957
31 | R001 | P.S. 1 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A BREEZEWAY | Construction | In-Progress | 11/10/2023 | 9/4/2024 |  | 543255 | 482722 | 290668 | DSF0001033957
31 | R001 | P.S. 1 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A BREEZEWAY | CM,F&E | In-Progress | 11/10/2023 | 9/4/2024 |  | 37040 | 67629 | 31150 | DSF0001033957
31 | R001 | P.S. 1 - STATEN ISLAND | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 124000 | 124000 | 0 | DSF0001113208
31 | R001 | P.S. 1 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/5/2024 | DIIR | 10/11/2024 | DIIR | 99613 | 99613 | DSF0001086592
31 | R001 | P.S. 1 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113207
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - RESOA | FY20 RESO A FLOORING | Construction | In-Progress | 8/13/2021 | DOER |  | DOER | 92982 | 0 | DSF0000913463
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/6/2022 | DOER |  | DOER | 264162 | 0 | DSF0000961473
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 193570 | 0 | DSF0001036098
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/11/2022 | DOES |  | DOES | 176560 | 0 | DSF0001034262
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/18/2024 | DOES | 10/1/2024 | DOES | 65832 | 21025 | DSF0001084421
31 | R002 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 11/21/2019 | 4/9/2020 | 12/29/2021 | 11580 | 31774 | 31774 | DSF0000950686
31 | R002 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Design | Complete | 1/7/2022 | 6/9/2022 | 5/4/2022 | 52110 | 31814 | 31814 | DSF0000950686
31 | R002 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Construction | Complete | 5/8/2023 | 4/1/2024 | 8/23/2024 | 671640 | 596011 | 486841 | DSF0000950686
31 | R002 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | CM,F&E | Complete | 5/8/2023 | 4/1/2024 | 8/23/2024 | 124485 | 113961 | 110686 | DSF0000950686
31 | R002 | I.S. 2 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 275000 | 0 | DSF0001113209
31 | R002 | I.S. 2 - STATEN ISLAND | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 9/10/2019 | DOER |  | DOER | 333324 | 0 | DSF0000867207
31 | R002 | I.S. 2 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/29/2024 | DOER |  | DOER | 177123 | 0 | DSF0000961443
31 | R002 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ACCESSIBILITY | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001008387
31 | R002 | I.S. 2 - STATEN ISLAND | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 427936 | 0 | DSF0001036099
31 | R002 | I.S. 2 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/17/2024 | DOES | 10/24/2024 | DOES | 65832 |  | DSF0001084833
31 | R002 | I.S. 2 - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/13/2024 | DOES |  | DOES | 527282 | 0 | DSF0001085764
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Scope | Complete | 3/6/2018 | 7/6/2018 | 8/15/2018 | 24980 | 24433 | 24433 | DSF0000888889
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Design | Complete | 12/6/2018 | 6/7/2019 | 5/17/2019 | 124900 | 95200 | 78137 | DSF0000888889
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Construction | PNS | PNS | PNS | PNS | 2810250 | 2810250 | 10734 | DSF0000888889
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | CM,F&E | PNS | PNS | PNS | PNS | 174860 | 174860 | 104704 | DSF0000888889
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/18/2019 | 11/19/2019 | 10/4/2019 | 69300 | 104671 | 104671 | DSF0000798310, DSF0000904972
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 10/8/2019 | 3/13/2020 | 1/23/2020 | 346500 | 407777 | 393622 | DSF0000798310, DSF0000904972
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 6/14/2021 | 6/13/2023 |  | 7796250 | 7346525 | 7105079 | DSF0000798310, DSF0000904972
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 6/14/2021 | 6/13/2023 |  | 485100 | 1032963 | 1029192 | DSF0000798310, DSF0000904972
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113210
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113210
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 0 | DSF0001113210
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 0 | DSF0001113210
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113675
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113675
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113675
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113675
31 | R003 | P.S. 3 - STATEN ISLAND | SCA IEH | PO18-ABATE ACM IN THE FAN ROOM B-6 , SPACE ID #1006 APPROX. 10 LINEAR FEET OF PIPE INSULATION ABOVE | Construction | Complete | 10/9/2024 | IEH | 10/12/2024 | IEH | 0 | 0 | SCA0000073483
31 | R003 | P.S. 3 - STATEN ISLAND | SCA IEH | PO18-ABATE ACM IN 1ST FLOOR BOY'S BATHROOM , SPACE ID #2154 CUT OUT APPROX. 3X3 FOOT SECTION OF FLOO | Construction | In-Progress | 10/28/2024 | IEH |  | IEH | 0 | 0 | SCA0000073548
31 | R003 | P.S. 3 - STATEN ISLAND | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 8/7/2024 | DIIR | 9/25/2024 | DIIR | 140000 | 140000 | DSF0001112217
31 | R003 | P.S. 3 - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 206003 | 0 | DSF0001086594
31 | R003 | P.S. 3 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/6/2022 | DOES |  | DOES | 142021 | 0 | DSF0001008716
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/20/2019 | 11/21/2019 | 8/27/2019 | 68770 | 130062 | 130062 | DSF0000912534, DSF0000904988
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/10/2019 | 2/13/2020 | 2/19/2020 | 343850 | 487348 | 455401 | DSF0000912534, DSF0000904988
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 6/22/2021 | 6/21/2023 |  | 7736625 | 8044234 | 5389944 | DSF0000912534, DSF0000904988
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 6/22/2021 | 6/21/2023 |  | 481390 | 1571892 | 1555259 | DSF0000912534, DSF0000904988
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | Scope | Complete | 11/6/2020 | 1/15/2021 | 1/26/2021 | 39300 | 29386 | 29386 | DSF0000961578
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | Design | Complete | 2/2/2021 | 7/2/2021 | 11/16/2021 | 196500 | 186059 | 156170 | DSF0000961578
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | Construction | In-Progress | 7/29/2022 | 1/19/2024 |  | 4421250 | 3979379 | 2734464 | DSF0000961578
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | CM,F&E | In-Progress | 7/29/2022 | 1/19/2024 |  | 275100 | 285965 | 281796 | DSF0000961578
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Scope | Complete | 1/21/2022 | 4/21/2022 | 8/10/2022 | 0 | 14415 | 14415 | DSF0001032975
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Design | Complete | 8/12/2022 | 12/30/2022 | 1/24/2023 | 28800 | 46573 | 43854 | DSF0001032975
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 422400 | 985909 | 15495 | DSF0001032975
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 28800 | 67221 | 17112 | DSF0001032975
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Scope | Complete | 10/6/2023 | 2/9/2024 | 10/17/2023 | 0 | 4907 | 4907 | DSF0001035246
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Design | Complete | 10/17/2023 | 4/15/2024 | 1/31/2024 | 28500 | 19629 | 19629 | DSF0001035246
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Construction | In-Progress | 7/25/2024 | 6/19/2025 |  | 418000 | 250772 | 666 | DSF0001035246
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | CM,F&E | In-Progress | 7/25/2024 | 6/19/2025 |  | 32764 | 13240 | 12259 | DSF0001035246
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913115
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913115
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913115
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0000913115
31 | R004 | P.S. 4 - STATEN ISLAND | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS 306 AND 307 | Construction | Complete | 8/5/2022 | IEH | 10/22/2024 | IEH | 0 | 0 | SCA0000071359
31 | R004 | P.S. 4 - STATEN ISLAND | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/8/2020 | FTK |  | FTK | 420129 | 412299 | DSF0000961068
31 | R004 | P.S. 4 - STATEN ISLAND | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/16/2020 | FTK |  | FTK | 49042 | 48484 | DSF0000866946
31 | R004 | P.S. 4 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113211
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 364715 | 0 | DSF0000913116
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001008399
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001036101
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086595
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2018 | DOES |  | DOES | 75200 | 0 | DSF0000792298
31 | R005 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | Scope | Complete | 1/21/2020 | 7/14/2020 | 1/19/2021 | 1277800 | 732401 | 726384 | DSF0000889303
31 | R005 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | Design | Complete | 1/20/2021 | 1/13/2021 | 5/11/2022 | 5750100 | 4272387 | 3287195 | DSF0000889303
31 | R005 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | Construction | In-Progress | 7/18/2022 | 9/3/2025 |  | 72515150 | 72160563 | 46819448 | DSF0000889303
31 | R005 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | CM,Art,F&E | In-Progress | 7/18/2022 | 9/3/2025 |  | 10222400 | 8145031 | 4358603 | DSF0000889303
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP | EXISTING BUILDING WORK / EXISTING BUILDING-AUD/GYM | Scope | Complete | 3/8/2021 | 5/14/2021 | 4/28/2021 | 20684 | 72680 | 72680 | DSF0000889303, DSF0000889303
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP | EXISTING BUILDING WORK / EXISTING BUILDING-AUD/GYM | Design | Complete | 4/29/2021 | 9/20/2021 | 1/20/2022 | 102919 | 446883 | 181926 | DSF0000889303, DSF0000889303
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP | EXISTING BUILDING WORK / EXISTING BUILDING-AUD/GYM | Construction | PNS | PNS | PNS | PNS | 2272423 | 2272423 | 13792 | DSF0000889303, DSF0000889303
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP | EXISTING BUILDING WORK / EXISTING BUILDING-AUD/GYM | CM,F&E | PNS | PNS | PNS | PNS | 148536 | 148536 | 34064 | DSF0000889303, DSF0000889303
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP RESOA | FY17 RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 4/9/2018 | 8/8/2018 |  | 0 | 44678 | 44676 | DSF0000844241
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP RESOA | FY17 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 33000 | 33000 | 56 | DSF0000844241
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP RESOA | FY17 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 484000 | 484000 | 5547 | DSF0000844241
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP RESOA | FY17 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 33000 | 33000 | 4079 | DSF0000844241
31 | R005 | P.S. 5 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/4/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001086596
31 | R005 | P.S. 5 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113212
31 | R005 | P.S. 5 - STATEN ISLAND | DOE - RESOA | FY19 RESO A TOILETS - STUDENTS | Construction | In-Progress | 12/18/2021 | DOER |  | DOER | 336877 | 0 | DSF0000890695
31 | R005 | P.S. 5 - STATEN ISLAND | DOE - RESOA | FY22 RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001033961
31 | R005 | P.S. 5 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FENCING UPGRADE | Construction | In-Progress | 6/6/2023 | DOER |  | DOER | 12832 | 0 | DSF0001035247
31 | R005 | P.S. 5 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/15/2022 | DOES |  | DOES | 62104 | 0 | DSF0001034435
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | Scope | Complete | 2/15/2019 | 7/18/2019 | 3/31/2020 | 134750 | 133307 | 131982 | DSF0001083949, DSF0001026699
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | Design | Complete | 7/26/2021 | 12/28/2021 | 3/31/2023 | 673750 | 705349 | 450063 | DSF0001083949, DSF0001026699
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | Construction | In-Progress | 8/1/2023 | 7/20/2025 |  | 15159375 | 13606788 | 1690419 | DSF0001083949, DSF0001026699
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | CM,F&E | In-Progress | 8/1/2023 | 7/20/2025 |  | 943250 | 391128 | 386987 | DSF0001083949, DSF0001026699
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/18/2019 | 11/1/2019 | 7/6/2021 | 24551 | 62639 | 60262 | DSF0000910674
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | Design | Complete | 7/6/2021 | 12/7/2021 | 5/16/2022 | 122753 | 96596 | 79770 | DSF0000910674
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | Construction | In-Progress | 3/10/2023 | 6/1/2024 |  | 2761938 | 2481157 | 2145696 | DSF0000910674
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | CM,F&E | In-Progress | 3/10/2023 | 6/1/2024 |  | 173384 | 574940 | 572841 | DSF0000910674
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/7/2023 | 4/10/2024 | 3/20/2024 | 0 | 11209 | 11209 | DSF0001086597
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | Complete | 3/25/2024 | 8/8/2024 | 8/16/2024 | 48000 | 34490 | 33306 | DSF0001086597
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 704000 | 704000 | 122 | DSF0001086597
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 48000 | 48000 | 9161 | DSF0001086597
31 | R006 | P.S. 6 - STATEN ISLAND | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 144000 | 144000 | 0 | DSF0001113213
31 | R006 | P.S. 6 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 210000 | 189522 | DSF0001036103
31 | R006 | P.S. 6 - STATEN ISLAND | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 5/25/2023 | DOER |  | DOER | 370037 | 0 | DSF0000913118
31 | R006 | P.S. 6 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/11/2022 | DOER |  | DOER | 339749 | 0 | DSF0000961476
31 | R007 | I.S. 7 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 10/23/2023 | 2/26/2024 | 11/7/2023 | 0 | 5236 | 5236 | DSF0001036104
31 | R007 | I.S. 7 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/7/2023 | 5/6/2024 | 1/31/2024 | 30000 | 20945 | 20945 | DSF0001036104
31 | R007 | I.S. 7 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 7/25/2024 | 6/19/2025 |  | 440000 | 280506 | 8778 | DSF0001036104
31 | R007 | I.S. 7 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 7/25/2024 | 6/19/2025 |  | 34264 | 15124 | 14142 | DSF0001036104
31 | R007 | I.S. 7 - STATEN ISLAND | SCA IEH | PO18-ABATE APPROX. 30 LF PIPE INSULATION MARKED IN RED, 25FT LOCATED IN ROOM #B19 SPACE ID #1019, AP | Construction | Complete | 9/12/2024 | IEH | 9/21/2024 | IEH | 0 | 0 | SCA0000073373
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 312916 | 0 | DSF0001008391
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 4/4/2024 | DOER |  | DOER | 235255 | 0 | DSF0001033963
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035248
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 97734 | 0 | DSF0001086598
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0 | DSF0001113214
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/14/2023 | DOES |  | DOES | 222760 | 0 | DSF0001034263
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/14/2022 | DOES |  | DOES | 225309 | 0 | DSF0001034436
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - Skilled Trades | PUMP ROOM VENTILATION | Construction | In-Progress | 3/20/2024 | DOES |  | DOES | 188894 | 0 | DSF0001105450
31 | R008 | P.S. 8 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS / PATH OF TRAVEL RESO A PLAYGROUNDS | Scope | Complete | 7/11/2018 | 6/15/2020 | 3/25/2021 | 0 | 78881 | 78881 | DSF0000867330, DSF0000912268
31 | R008 | P.S. 8 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS / PATH OF TRAVEL RESO A PLAYGROUNDS | Design | Complete | 3/26/2021 | 6/4/2021 | 5/14/2021 | 255558 | 297743 | 273026 | DSF0000867330, DSF0000912268
31 | R008 | P.S. 8 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS / PATH OF TRAVEL RESO A PLAYGROUNDS | Construction | In-Progress | 8/3/2023 | 8/1/2024 |  | 3748190 | 3628429 | 1183697 | DSF0000867330, DSF0000912268
31 | R008 | P.S. 8 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS / PATH OF TRAVEL RESO A PLAYGROUNDS | CM,F&E | In-Progress | 8/3/2023 | 8/1/2024 |  | 255558 | 260757 | 249436 | DSF0000867330, DSF0000912268
31 | R008 | P.S. 8 - STATEN ISLAND | SCA IEH | PO18-ABATE & REPLACE FLOORS IN THE FOLLOWING ROOMS: 208, 209, 211, 213, B23 - TOTAL APPROX. 4000 SQ. | Construction | Complete | 9/20/2024 | IEH | 10/17/2024 | IEH | 0 | 0 | SCA0000073405
31 | R008 | P.S. 8 - STATEN ISLAND | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 98000 | 98000 | 0 | DSF0000961485
31 | R008 | P.S. 8 - STATEN ISLAND | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 148000 | 148000 | 147609 | DSF0001086600
31 | R008 | P.S. 8 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/30/2024 | DIIR | 10/22/2024 | DIIR | 99648 | 99648 | DSF0001086599
31 | R008 | P.S. 8 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113215
31 | R008 | P.S. 8 - STATEN ISLAND | DOE - RESOA | FY20 RESO A FLOORING | Construction | In-Progress | 8/6/2021 | DOER |  | DOER | 28970 | 0 | DSF0000913121
31 | R008 | P.S. 8 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/18/2022 | DOES |  | DOES | 111417 | 0 | DSF0001034437
31 | R010 | P.S. 80 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/23/2024 | DIIR | 10/25/2024 | DIIR | 74716 | 74716 | DSF0001086601
31 | R010 | P.S. 80 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113216
31 | R010 | P.S. 80 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0000961466
31 | R010 | P.S. 80 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION: MEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113217
31 | R011 | P.S. 11 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033965
31 | R011 | P.S. 11 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113218
31 | R011 | P.S. 11 - STATEN ISLAND | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 4/24/2023 | DOER |  | DOER | 53693 | 0 | DSF0000913464
31 | R011 | P.S. 11 - STATEN ISLAND | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2/29/2024 | DOER |  | DOER | 8107 | 0 | DSF0001086602
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | Scope | Complete | 10/26/2018 | 3/18/2019 | 3/12/2019 | 178169 | 139959 | 92974 | DSF0000882218, DSF0000882219, DSF0000882220, DSF0000882221, DSF0000882222, DSF0001105502
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | Design | Complete | 3/12/2019 | 8/9/2019 | 5/17/2019 | 703945 | 727405 | 526401 | DSF0000882218, DSF0000882219, DSF0000882220, DSF0000882221, DSF0000882222, DSF0001105502
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | Construction | In-Progress | 7/19/2021 | 4/9/2023 |  | 12414816 | 13079719 | 9865493 | DSF0000882218, DSF0000882219, DSF0000882220, DSF0000882221, DSF0000882222, DSF0001105502
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | CM,F&E | In-Progress | 7/19/2021 | 4/9/2023 |  | 945039 | 733534 | 648877 | DSF0000882218, DSF0000882219, DSF0000882220, DSF0000882221, DSF0000882222, DSF0001105502
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 10/29/2024 | 3/4/2025 | 11/6/2024 | 0 | 3768 | 3768 | DSF0000913465
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | In-Progress | 11/6/2024 | 5/6/2025 |  | 33000 | 29232 | 15072 | DSF0000913465
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 484000 | 484000 | 0 | DSF0000913465
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 33000 | 33000 | 2300 | DSF0000913465
31 | R013 | P.S. 13 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0 | DSF0001033966
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/31/2019 | DOER |  | DOER | 75850 | 0 | DSF0000866333
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/5/2023 | DOER |  | DOER | 261565 | 0 | DSF0000913122
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 10/7/2022 | DOER |  | DOER | 305000 | 29800 | DSF0000961478
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY22 RESO A SUPPLEMETAL COOLING | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 259028 | 0 | DSF0001032968
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113219
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - Skilled Trades | CHILLER REPAIR | Construction | In-Progress | 5/25/2023 | DOES |  | DOES | 78336 | 17302 | DSF0001112387
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Scope | Complete | 3/6/2018 | 7/6/2018 | 8/15/2018 | 12340 | 11809 | 11809 | DSF0000888890
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Design | Complete | 12/6/2018 | 6/7/2019 | 5/17/2019 | 55530 | 107944 | 72115 | DSF0000888890
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Construction | In-Progress | 3/4/2024 | 1/27/2025 |  | 715720 | 638923 | 307243 | DSF0000888890
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | CM,F&E | In-Progress | 3/4/2024 | 1/27/2025 |  | 132655 | 95354 | 55562 | DSF0000888890
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/11/2021 | 2/15/2022 | 3/11/2022 | 0 | 44162 | 38397 | DSF0000961448, DSF0001007726
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 3/14/2022 | 7/12/2022 | 8/2/2022 | 49054 | 76655 | 47622 | DSF0000961448, DSF0001007726
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | Complete | 11/3/2023 | 9/27/2024 | 10/23/2024 | 719457 | 667329 | 550647 | DSF0000961448, DSF0001007726
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 11/3/2023 | 9/27/2024 | 10/23/2024 | 49054 | 71788 | 45611 | DSF0000961448, DSF0001007726
31 | R014 | P.S. 078 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001034008
31 | R014 | P.S. 078 - STATEN ISLAND | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001086603
31 | R014 | P.S. 078 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113220
31 | R014 | P.S. 078 - STATEN ISLAND | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/7/2022 | DOES |  | DOES | 89306 | 0 | DSF0001009194
31 | R014 | P.S. 078 - STATEN ISLAND | DOE - Skilled Trades | RTU REPLACEMENT | Construction | In-Progress | 10/26/2023 | DOES |  | DOES | 200125 | 0 | DSF0001111812
31 | R016 | P.S. 16 - STATEN ISLAND | SCA Furniture & Equipment | FY20 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 70000 | 70000 | 0 | DSF0000914124
31 | R016 | FORT HILL COLLABORATIVE ELEMENTARY SCHOOL - R | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | Complete | 11/13/2024 |  | 12/20/2024 | 194000 | 194000 | 190301 | DSF0001035249
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/6/2023 | DOER |  | DOER | 280197 | 0 | DSF0001034995
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001086604
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001086605
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 584000 | 0 | DSF0001113221
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/14/2022 | DOES |  | DOES | 193747 | 0 | DSF0001034438
31 | R018 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 6/13/2019 | 10/29/2019 | 7/6/2021 | 36449 | 137674 | 129759 | DSF0000905128, DSF0000999893, DSF0000999896
31 | R018 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 8/25/2021 | 1/31/2022 | 2/3/2022 | 180225 | 296909 | 271103 | DSF0000905128, DSF0000999893, DSF0000999896
31 | R018 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | Complete | 7/18/2022 | 1/8/2024 | 8/14/2024 | 3879953 | 3661941 | 3657911 | DSF0000905128, DSF0000999893, DSF0000999896
31 | R018 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | Complete | 7/18/2022 | 1/8/2024 | 8/14/2024 | 270330 | 678475 | 671263 | DSF0000905128, DSF0000999893, DSF0000999896
31 | R018 | P.S. 18 - STATEN ISLAND | SCA IEH | PO18-ASSIST STEAMFITTERS: IN THE VESTIBULE OF EXIT 3, REMOVE ACMON THE BACK OF THE HEAT SHIELD AND S | Construction | Complete | 11/12/2024 | IEH | 12/10/2024 | IEH | 0 | 0 | SCA0000073600
31 | R018 | P.S. 18 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113223
31 | R018 | P.S. 18 - STATEN ISLAND | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | Complete | 7/5/2023 | DOER | 8/14/2023 | DOER | 63494 |  | DSF0001035346
31 | R018 | P.S. 18 - STATEN ISLAND | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113222
31 | R019 | P.S. 19 - STATEN ISLAND | SCA Capacity | ADDITION | Scope | Complete | 11/20/2023 | 6/10/2024 | 5/6/2024 | 1219599 | 931402 | 849556 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA Capacity | ADDITION | Design | In-Progress | 5/7/2024 | 11/20/2024 |  | 4878398 | 4878398 | 745274 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA Capacity | ADDITION | Construction | PNS | PNS | PNS | PNS | 67382868 | 67382868 | 341403 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA Capacity | ADDITION | CM,Art,F&E | PNS | PNS | PNS | PNS | 8842096 | 8842096 | 685416 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING - ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING - IPDVS UPGRADE / EXISTING BUILDING - FIRE ALARM UPGRADE | Scope | Complete | 2/13/2024 | 6/13/2024 | 5/15/2024 | 20301 | 5067 | 0 | DSF0000911850, DSF0000911850, DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING - ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING - IPDVS UPGRADE / EXISTING BUILDING - FIRE ALARM UPGRADE | Design | In-Progress | 5/15/2024 | 11/19/2024 |  | 91357 | 91357 | 0 | DSF0000911850, DSF0000911850, DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING - ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING - IPDVS UPGRADE / EXISTING BUILDING - FIRE ALARM UPGRADE | Construction | PNS | PNS | PNS | PNS | 1177487 | 1177487 | 5791 | DSF0000911850, DSF0000911850, DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING - ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING - IPDVS UPGRADE / EXISTING BUILDING - FIRE ALARM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 218241 | 218241 | 8881 | DSF0000911850, DSF0000911850, DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Scope | In-Progress | 12/30/2024 | 4/30/2025 |  | 21636 | 21636 | 0 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Design | PNS | PNS | PNS | PNS | 100966 | 100966 | 0 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Construction | PNS | PNS | PNS | PNS | 1601028 | 1601028 | 0 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | CM,F&E | PNS | PNS | PNS | PNS | 158660 | 158660 | 0 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 11/30/2023 | 11/30/2023 | 11/30/2023 | 31031 | 2830 | 2830 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 12/1/2023 | 3/22/2024 | 4/15/2024 | 144813 | 234239 | 94531 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | Construction | In-Progress | 8/27/2024 | 8/26/2025 |  | 2296313 | 2169283 | 149186 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 8/27/2024 | 8/26/2025 |  | 227563 | 252387 | 240236 | DSF0000911850
31 | R019 | P.S. 19 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 195000 | 0 | DSF0001113224
31 | R019 | P.S. 19 - STATEN ISLAND | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 9/16/2024 | DOER |  | DOER | 115563 | 0 | DSF0001035250
31 | R019 | P.S. 19 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/22/2022 | DOES |  | DOES | 133457 | 0 | DSF0001034265
31 | R020 | P.S. 20 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 1/26/2024 | 6/11/2024 | 7/3/2024 | 60520 | 67896 | 66079 | DSF0001077627, DSF0001105588, DSF0001105587
31 | R020 | P.S. 20 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | In-Progress | 7/9/2024 | 12/10/2024 |  | 282428 | 282428 | 18843 | DSF0001077627, DSF0001105588, DSF0001105587
31 | R020 | P.S. 20 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | PNS | PNS | PNS | PNS | 4478500 | 4478500 | 17413 | DSF0001077627, DSF0001105588, DSF0001105587
31 | R020 | P.S. 20 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 443815 | 443815 | 86194 | DSF0001077627, DSF0001105588, DSF0001105587
31 | R020 | P.S. 20 - STATEN ISLAND | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 383000 | 383000 | 0 | DSF0001113225
31 | R020 | P.S. 20 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 193000 | 0 | DSF0001086606
31 | R020 | P.S. 20 - STATEN ISLAND | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | Complete | 7/18/2023 | DOER | 8/28/2023 | DOER | 256052 | 22320 | DSF0001035251
31 | R020 | P.S. 20 - STATEN ISLAND | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/25/2021 | DOES |  | DOES | 67976 | 0 | DSF0001009086
31 | R020 | P.S. 20 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/13/2022 | DOES |  | DOES | 56455 | 0 | DSF0001034439
31 | R021 | P.S. 21 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 1/26/2024 | 6/11/2024 | 11/13/2024 | 138180 | 132612 | 23269 | DSF0001077646, DSF0001133318, DSF0001133317
31 | R021 | P.S. 21 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | PNS | PNS | PNS | PNS | 646089 | 646089 | 8359 | DSF0001077646, DSF0001133318, DSF0001133317
31 | R021 | P.S. 21 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | PNS | PNS | PNS | PNS | 11521289 | 11521289 | 23951 | DSF0001077646, DSF0001133318, DSF0001133317
31 | R021 | P.S. 21 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | PNS | PNS | PNS | PNS | 1140561 | 1140561 | 19973 | DSF0001077646, DSF0001133318, DSF0001133317
31 | R021 | P.S. 21 - STATEN ISLAND | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 11/1/2021 | DOER |  | DOER | 128355 | 0 | DSF0000890700
31 | R021 | P.S. 21 - STATEN ISLAND | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1150000 | 0 | DSF0001086607
31 | R021 | P.S. 21 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/16/2024 | DOES | 8/20/2024 | DOES | 65832 | 11210 | DSF0001084433
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 8/8/2019 | 12/26/2019 | 3/13/2020 | 100062 | 287191 | 260685 | DSF0000905200, DSF0000905202, DSF0000905203, DSF0000905204
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 3/13/2020 | 8/12/2020 | 6/30/2020 | 499671 | 689473 | 559681 | DSF0000905200, DSF0000905202, DSF0000905203, DSF0000905204
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 8/23/2021 | 5/14/2023 |  | 11186958 | 13472876 | 8095560 | DSF0000905200, DSF0000905202, DSF0000905203, DSF0000905204
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/23/2021 | 5/14/2023 |  | 705791 | 1166932 | 1092373 | DSF0000905200, DSF0000905202, DSF0000905203, DSF0000905204
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/17/2023 | 2/14/2024 | 1/31/2024 | 0 | 28374 | 28374 | DSF0001036109, DSF0001036112
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2/1/2024 | 6/4/2024 | 4/25/2024 | 60000 | 56755 | 43151 | DSF0001036109, DSF0001036112
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 880000 | 880000 | 4152 | DSF0001036109, DSF0001036112
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 60000 | 60000 | 18924 | DSF0001036109, DSF0001036112
31 | R022 | P.S. 22 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/3/2024 | DIIR | 10/22/2024 | DIIR | 80000 | 80000 | DSF0001035253
31 | R022 | P.S. 22 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001036110
31 | R022 | P.S. 22 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 29745 | 0 | DSF0001036111
31 | R022 | P.S. 22 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 135451 | 0 | DSF0001034440
31 | R023 | P.S. 23 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 1/26/2023 | 11/30/2023 | 10/19/2023 | 0 | 32869 | 32806 | DSF0001036113, DSF0001036114
31 | R023 | P.S. 23 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 10/20/2023 | 2/23/2024 | 4/18/2024 | 31025 | 70936 | 51912 | DSF0001036113, DSF0001036114
31 | R023 | P.S. 23 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 455034 | 455034 | 8724 | DSF0001036113, DSF0001036114
31 | R023 | P.S. 23 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 31025 | 44529 | 13113 | DSF0001036113, DSF0001036114
31 | R023 | P.S. 23 - STATEN ISLAND | Fast Track Projects | LSP SIDEWALK REPLACEMENT | Construction | In-Progress | 4/12/2024 | FTK |  | FTK | 184105 | 174650 | DSF0001105651
31 | R023 | P.S. 23 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/2/2024 | DIIR | 7/11/2024 | DIIR | 75000 | 71490 | DSF0001086609
31 | R023 | P.S. 23 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113226
31 | R023 | P.S. 23 - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/5/2021 | DOER |  | DOER | 261228 | 0 | DSF0000961481
31 | R023 | P.S. 23 - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 57101 | 0 | DSF0001008373
31 | R023 | P.S. 23 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086608
31 | R023 | P.S. 23 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/6/2024 | DOES | 7/18/2024 | DOES | 65832 | 28764 | DSF0001084435
31 | R024 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | Scope | Complete | 4/20/2021 | 9/2/2021 | 12/15/2021 | 30364 | 30549 | 30549 | DSF0000950974, DSF0001026961
31 | R024 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | Design | Complete | 12/27/2021 | 5/27/2022 | 11/1/2022 | 146362 | 180237 | 135277 | DSF0000950974, DSF0001026961
31 | R024 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | Construction | In-Progress | 7/24/2023 | 10/15/2024 |  | 2820920 | 2596856 | 1849080 | DSF0000950974, DSF0001026961
31 | R024 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | CM,F&E | In-Progress | 7/24/2023 | 10/15/2024 |  | 253493 | 225407 | 223018 | DSF0000950974, DSF0001026961
31 | R024 | I.S. 24 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113227
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 3/16/2021 | DOER |  | DOER | 8238 | 0 | DSF0000913127
31 | R024 | R721 SPED - STATEN ISLAND | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 10/14/2022 | DOER | 5/25/2023 | DOER | 80351 |  | DSF0000913128
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/13/2023 | DOER |  | DOER | 403334 | 0 | DSF0001033970
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001036115
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 485000 | 0 | DSF0001086611
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113228
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/23/2024 | DOES | 10/7/2024 | DOES | 65832 |  | DSF0001084835
31 | R025 | R025 SPED - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 1/26/2024 | 6/11/2024 | 9/25/2024 | 46652 | 38969 | 18453 | DSF0001077727, DSF0001105681, DSF0001105684, DSF0001105685
31 | R025 | R025 SPED - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Design | In-Progress | 10/10/2024 | 3/18/2025 |  | 206200 | 206200 | 7610 | DSF0001077727, DSF0001105681, DSF0001105684, DSF0001105685
31 | R025 | R025 SPED - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 2999080 | 2999080 | 7427 | DSF0001077727, DSF0001105681, DSF0001105684, DSF0001105685
31 | R025 | R025 SPED - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 492304 | 492304 | 14231 | DSF0001077727, DSF0001105681, DSF0001105684, DSF0001105685
31 | R026 | P.S. 26 - STATEN ISLAND | SCA IEH | PO18-REPAIR / ENCAPSULATE AND PAINT DAMAGED ACM PLASTER AREAS ON WALL #2(APPROXIMATELY 1SF) AND WALL | Construction | Complete | 9/6/2024 | IEH | 9/7/2024 | IEH | 0 | 0 | SCA0000073356
31 | R026 | P.S. 26 - STATEN ISLAND | SCA IEH | PO18-ABATE CEILING FOR EXTERMINATOR TO ELIMINATE TERMITES PLAY AREA, SPACE ID #1008, APPROX. 40 SQ. | Construction | Complete | 10/31/2024 | IEH | 11/1/2024 | IEH | 0 | 0 | SCA0000073568
31 | R026 | P.S. 26 - STATEN ISLAND | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 6/18/2021 | FTK |  | FTK | 46884 | 41598 | DSF0000961560
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY20 RESO A FLOORING | Construction | In-Progress | 7/28/2022 | DOER |  | DOER | 210771 | 0 | DSF0000913129
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/6/2022 | DOER |  | DOER | 315898 | 0 | DSF0000961482
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FLOORING UPGRADE | Construction | In-Progress | 6/9/2023 | DOER |  | DOER | 27713 | 0 | DSF0001035254
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY24 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001086612
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001113229
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001113230
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - Skilled Trades | HEATING PLANT UPGRADE | Construction | In-Progress | 4/22/2024 | DOES |  | DOES | 109794 | 0 | DSF0001105705
31 | R027 | I.S. 27 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113231
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | Complete | 7/13/2023 | DOER | 9/27/2023 | DOER | 118865 | 21268 | DSF0000961452
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 390000 | 0 | DSF0001036117
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 3438 | 0 | DSF0001086613
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113232
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/22/2023 | DOES | 11/6/2023 | DOES | 631900 | 589190 | DSF0001035112
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/28/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084836
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | Scope | Complete | 2/14/2019 | 7/1/2019 | 7/7/2021 | 30869 | 176124 | 173810 | DSF0000905308, DSF0001000091
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | Design | Complete | 8/5/2021 | 1/10/2022 | 5/9/2022 | 154346 | 179247 | 179247 | DSF0000905308, DSF0001000091
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | Construction | In-Progress | 7/18/2022 | 7/17/2023 |  | 3472784 | 4267155 | 3956809 | DSF0000905308, DSF0001000091
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | CM,F&E | In-Progress | 7/18/2022 | 7/17/2023 |  | 216084 | 757039 | 752136 | DSF0000905308, DSF0001000091
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PLAYGROUNDS | Scope | Complete | 5/20/2022 | 8/22/2022 | 8/23/2022 | 1473 | 1473 | 7607 | DSF0001034916
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PLAYGROUNDS | Design | Complete | 9/1/2022 | 1/5/2023 | 1/27/2023 | 6627 | 6627 | 22928 | DSF0001034916
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PLAYGROUNDS | Construction | PNS | PNS | PNS | PNS | 85417 | 85417 | 5070 | DSF0001034916
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PLAYGROUNDS | CM,F&E | PNS | PNS | PNS | PNS | 15832 | 15832 | 7539 | DSF0001034916
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 9/22/2022 | 2/10/2023 | 4/28/2023 | 56287 | 128468 | 126033 | DSF0001085822, DSF0001085123, DSF0001077783
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 5/2/2023 | 10/3/2023 | 10/25/2023 | 274324 | 317096 | 301843 | DSF0001085822, DSF0001085123, DSF0001077783
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Construction | In-Progress | 12/20/2024 | 9/10/2026 |  | 5557189 | 4954060 | 33770 | DSF0001085822, DSF0001085123, DSF0001077783
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | CM,F&E | In-Progress | 12/20/2024 | 9/10/2026 |  | 447340 | 35847 | 35847 | DSF0001085822, DSF0001085123, DSF0001077783
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/25/2020 | 10/26/2020 | 7/7/2020 | 2247 | 3593 | 3593 | DSF0000960779
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/7/2020 | 1/1/2021 | 1/6/2021 | 10112 | 14370 | 14370 | DSF0000960779
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/12/2022 | 3/7/2023 |  | 130339 | 120986 | 102391 | DSF0000960779
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/12/2022 | 3/7/2023 |  | 161422 | 210544 | 210544 | DSF0000960779
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113234
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001113234
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 220000 | 220000 | 0 | DSF0001113234
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001113234
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113676
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113676
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113676
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113676
31 | R029 | P.S. 29 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/28/2022 | EMER |  | EMER | 12571 | 11755 | SCA0000071254
31 | R029 | P.S. 29 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0 | DSF0001008383
31 | R029 | P.S. 29 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001036118
31 | R029 | P.S. 29 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001086615
31 | R029 | P.S. 29 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113233
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 5/20/2019 | DOER |  | DOER | 147391 | 0 | DSF0000844863
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY19 RESO A PLAYGROUND | Construction | In-Progress | 8/3/2021 | DOER |  | DOER | 209238 | 0 | DSF0000890940
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 10/17/2022 | DOER |  | DOER | 39314 | 0 | DSF0000961487
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001032971
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 7/8/2023 | DOER |  | DOER | 167381 | 0 | DSF0001035348
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 451000 | 0 | DSF0001086614
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP | FIRE ALARM SYSTEM | Scope | Complete | 6/26/2024 | 9/25/2024 | 11/22/2024 | 12082 | 14671 | 14671 | DSF0001105750
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP | FIRE ALARM SYSTEM | Design | In-Progress | 12/5/2024 | 6/10/2025 |  | 48326 | 58684 | 58684 | DSF0001105750
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP | FIRE ALARM SYSTEM | Construction | PNS | PNS | PNS | PNS | 694689 | 694689 | 119 | DSF0001105750
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP | FIRE ALARM SYSTEM | CM,F&E | PNS | PNS | PNS | PNS | 178203 | 178203 | 11879 | DSF0001105750
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/17/2022 | 11/1/2023 | 1/4/2024 | 0 | 37107 | 37107 | DSF0001032972, DSF0001034929
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 1/16/2024 | 5/16/2024 | 4/25/2024 | 44625 | 70846 | 57772 | DSF0001032972, DSF0001034929
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 654501 | 654501 | 36105 | DSF0001032972, DSF0001034929
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 44625 | 44625 | 20684 | DSF0001032972, DSF0001034929
31 | R030 | P.S. 30 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/21/2024 | DIIR | 10/24/2024 | DIIR | 74736 | 74736 | DSF0001086616
31 | R030 | P.S. 30 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113235
31 | R030 | P.S. 30 - STATEN ISLAND | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/19/2022 | DOER |  | DOER | 418843 | 0 | DSF0000890705
31 | R030 | P.S. 30 - STATEN ISLAND | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 5/17/2024 | DOER |  | DOER | 375050 | 0 | DSF0001035256
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/16/2021 | 9/16/2021 | 7/28/2021 | 83700 | 209921 | 195421 | DSF0001000113, DSF0001008805
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 7/30/2021 | 1/31/2022 | 4/13/2022 | 418501 | 857049 | 819342 | DSF0001000113, DSF0001008805
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 8/8/2022 | 8/6/2024 |  | 9416250 | 8887068 | 8343138 | DSF0001000113, DSF0001008805
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 8/8/2022 | 8/6/2024 |  | 585900 | 680515 | 676235 | DSF0001000113, DSF0001008805
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/14/2022 | 11/30/2022 | 3/17/2023 | 69170 | 203722 | 193952 | DSF0001027066, DSF0001027067, DSF0001027068
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 4/27/2023 | 9/28/2023 | 5/13/2024 | 338283 | 408093 | 289515 | DSF0001027066, DSF0001027067, DSF0001027068
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 8/15/2024 | 8/14/2026 |  | 6956497 | 6378220 | 184959 | DSF0001027066, DSF0001027067, DSF0001027068
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 8/15/2024 | 8/14/2026 |  | 540974 | 79012 | 78903 | DSF0001027066, DSF0001027067, DSF0001027068
31 | R031 | P.S. 31 - STATEN ISLAND | SCA Furniture & Equipment | RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 125000 | 125000 | 0 | DSF0001035173
31 | R031 | P.S. 31 - STATEN ISLAND | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 68000 | 0 | DSF0000890442
31 | R031 | P.S. 31 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 400000 | 0 | DSF0001033336
31 | R031 | P.S. 31 - STATEN ISLAND | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 127577 | 0 | DSF0000961492
31 | R031 | P.S. 31 - STATEN ISLAND | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADES | Construction | In-Progress | 1/17/2024 | DOER |  | DOER | 519916 | 1828 | DSF0001035257
31 | R031 | P.S. 31 - STATEN ISLAND | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113236
31 | R032 | P.S. 32 - STATEN ISLAND | SCA CIP | FACADE RESTORATION | Scope | Complete | 8/1/2023 | 12/18/2023 | 12/19/2023 | 20473 | 38260 | 38260 | DSF0001085302
31 | R032 | P.S. 32 - STATEN ISLAND | SCA CIP | FACADE RESTORATION | Design | Complete | 1/8/2024 | 6/7/2024 | 5/14/2024 | 102363 | 100754 | 90072 | DSF0001085302
31 | R032 | P.S. 32 - STATEN ISLAND | SCA CIP | FACADE RESTORATION | Construction | PNS | PNS | PNS | PNS | 2303172 | 2303172 | 11289 | DSF0001085302
31 | R032 | P.S. 32 - STATEN ISLAND | SCA CIP | FACADE RESTORATION | CM,F&E | PNS | PNS | PNS | PNS | 143308 | 143308 | 35951 | DSF0001085302
31 | R032 | P.S. 32 - STATEN ISLAND | SCA IEH | PO18-ABATE PIPE INSULATION : APPROX. 15 LINEAR FEET IN TOTAL PIPING MARKED IN RED, LOCATED IN (2) AR | Construction | Complete | 8/31/2024 | IEH | 8/31/2024 | IEH | 0 | 0 | SCA0000073357
31 | R032 | P.S. 32 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0 | DSF0001083823
31 | R032 | P.S. 32 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113238
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 696667 | 0 | DSF0001033979
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001036120
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086617
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113237
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 111644 | 0 | DSF0001034441
31 | R034 | I.S. 34 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / CLIMATE CONTROL | Scope | Complete | 6/19/2019 | 11/20/2019 | 8/14/2019 | 134088 | 73091 | 73091 | DSF0000798376, DSF0000792707
31 | R034 | I.S. 34 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / CLIMATE CONTROL | Design | Complete | 9/12/2019 | 2/18/2020 | 2/26/2020 | 625745 | 279007 | 278186 | DSF0000798376, DSF0000792707
31 | R034 | I.S. 34 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / CLIMATE CONTROL | Construction | PNS | PNS | PNS | PNS | 9922525 | 9922525 | 43351 | DSF0000798376, DSF0000792707
31 | R034 | I.S. 34 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / CLIMATE CONTROL | CM,F&E | PNS | PNS | PNS | PNS | 983313 | 983313 | 121489 | DSF0000798376, DSF0000792707
31 | R034 | I.S. 34 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/25/2021 | EMER |  | EMER | 1959211 | 1941961 | SCA0000069649
31 | R034 | I.S. 34 - STATEN ISLAND | SCA IEH | PO18-BASEMENT STAIRWELL A, 1 L.F. PIPE INSULATION FAN ROOM, 11 L.F. PIPE INSULATION KITCHEN, 7 L.F. | Construction | Complete | 7/17/2024 | IEH | 9/8/2024 | IEH | 0 | 0 | SCA0000073147
31 | R034 | I.S. 34 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 100000 | 92243 | DSF0001086619
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 8/6/2021 | DOER |  | DOER | 167541 | 0 | DSF0000913468
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 11/8/2021 | DOER |  | DOER | 221000 | 0 | DSF0000961465
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) CAFETERIA UPGRADE | Construction | In-Progress | 4/3/2023 | DOER |  | DOER | 176117 | 0 | DSF0001032961
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001033980
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001035258
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/17/2024 | DOER |  | DOER | 38464 | 0 | DSF0001086618
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001113239
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/16/2024 | DOES | 9/23/2024 | DOES | 65832 |  | DSF0001084837
31 | R035 | P.S. 35 - STATEN ISLAND | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/2/2020 | FTK |  | FTK | 262190 | 255934 | DSF0000961048
31 | R035 | P.S. 35 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001086620
31 | R036 | P.S. 36 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/2/2021 | 8/31/2021 | 12/22/2021 | 0 | 38511 | 38511 | DSF0000961483
31 | R036 | P.S. 36 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 1/4/2022 | 5/19/2022 | 7/15/2022 | 59379 | 64822 | 64822 | DSF0000961483
31 | R036 | P.S. 36 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | Complete | 6/28/2023 | 5/22/2024 | 5/22/2024 | 870892 | 662520 | 647200 | DSF0000961483
31 | R036 | P.S. 36 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 6/28/2023 | 5/22/2024 | 5/22/2024 | 59379 | 64997 | 63694 | DSF0000961483
31 | R036 | P.S. 36 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/23/2023 | DIIR |  | DIIR | 200000 | 0 | DSF0001036122
31 | R036 | P.S. 36 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001086622
31 | R036 | P.S. 36 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113240
31 | R036 | P.S. 36 - STATEN ISLAND | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/21/2022 | DOER |  | DOER | 31319 | 0 | DSF0000913133
31 | R036 | P.S. 36 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086621
31 | R038 | P.S. 38 - STATEN ISLAND | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 237524 | 0 | DSF0000960247
31 | R038 | P.S. 38 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 75000 | 75000 | DSF0001086623
31 | R038 | P.S. 38 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113241
31 | R038 | P.S. 38 - STATEN ISLAND | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/29/2022 | DOER |  | DOER | 928366 | 0 | DSF0000890708
31 | R039 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 4/8/2021 | 8/23/2021 | 11/17/2021 | 43730 | 103649 | 103649 | DSF0000951165, DSF0000951167, DSF0000951169
31 | R039 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 11/29/2021 | 5/2/2022 | 4/22/2022 | 208391 | 251292 | 251292 | DSF0000951165, DSF0000951167, DSF0000951169
31 | R039 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 9/26/2022 | 3/18/2024 |  | 3801630 | 4630699 | 2934962 | DSF0000951165, DSF0000951167, DSF0000951169
31 | R039 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 9/26/2022 | 3/18/2024 |  | 383027 | 664411 | 659597 | DSF0000951165, DSF0000951167, DSF0000951169
31 | R039 | P.S. 39 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ R039 | Construction | In-Progress | 8/24/2022 | EMER |  | EMER | 17342 | 11881 | SCA0000071400
31 | R039 | P.S. 39 - STATEN ISLAND | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0000799345
31 | R039 | P.S. 39 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113243
31 | R039 | P.S. 39 - STATEN ISLAND | DOE - RESOA | FY20 RESO A MAKERSPACE | Construction | In-Progress | 7/11/2022 | DOER |  | DOER | 353431 | 0 | DSF0000914131
31 | R039 | P.S. 39 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FLOORING | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001036124
31 | R039 | P.S. 39 - STATEN ISLAND | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113242
31 | R039 | P.S. 39 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/23/2024 | DOES | 7/30/2024 | DOES | 65832 | 18519 | DSF0001084444
31 | R040 | R373 SPED - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/18/2024 | DIIR |  | DIIR | 80000 | 0 | DSF0001086625
31 | R040 | R373 SPED - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0 | DSF0001113244
31 | R040 | R373 SPED - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 2/18/2022 | DOER |  | DOER | 223255 | 0 | DSF0000961447
31 | R040 | R373 SPED - STATEN ISLAND | DOE - RESOA | FY24 RESO A DIGITAL SIGN | Construction | In-Progress | 6/1/2024 | DOER |  | DOER | 67341 | 0 | DSF0001086626
31 | R040 | R373 SPED - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/10/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084694
31 | R041 | P.S. 41 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/6/2021 | 11/23/2022 | 2/14/2023 | 202251 | 384435 | 382352 | DSF0001009202, DSF0001027209, DSF0001027210, DSF0001027211
31 | R041 | P.S. 41 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 6/16/2023 | 12/14/2023 | 5/13/2024 | 1011250 | 966507 | 412493 | DSF0001009202, DSF0001027209, DSF0001027210, DSF0001027211
31 | R041 | P.S. 41 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 11/21/2024 | 11/20/2026 |  | 22753126 | 21095206 | 405762 | DSF0001009202, DSF0001027209, DSF0001027210, DSF0001027211
31 | R041 | P.S. 41 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 11/21/2024 | 11/20/2026 |  | 1415751 | 176632 | 174852 | DSF0001009202, DSF0001027209, DSF0001027210, DSF0001027211
31 | R041 | P.S. 41 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/26/2021 | EMER |  | EMER | 1393854 | 1190104 | SCA0000069670
31 | R041 | P.S. 41 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION-EMERGENCY STABILIZATION THIRD FLOOR FACADE CRACKING | Construction | In-Progress | 8/2/2022 | EMER |  | EMER | 9472 | 8286 | SCA0000071344
31 | R041 | P.S. 41 - STATEN ISLAND | SCA IEH | PO18-PATCH AND REPAIR PIPE INSULATION WORKSHOP, 1 L.F. FAN ROOM, 2 L.F. STORAGE ROOM, 2 L.F. BOILER | Construction | Complete | 7/17/2024 | IEH | 7/25/2024 | IEH | 0 | 0 | SCA0000073142
31 | R041 | P.S. 41 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113245
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 12/18/2023 | 5/3/2024 | 7/16/2024 | 78794 | 60717 | 60717 | DSF0001077980, DSF0001113722, DSF0001105929
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | In-Progress | 8/13/2024 | 1/16/2025 |  | 370570 | 370570 | 11296 | DSF0001077980, DSF0001113722, DSF0001105929
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 7052981 | 7052981 | 125936 | DSF0001077980, DSF0001113722, DSF0001105929
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 674407 | 674407 | 38957 | DSF0001077980, DSF0001113722, DSF0001105929
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Scope | Complete | 1/23/2018 | 4/23/2018 | 2/28/2018 | 0 | 26689 | 26689 | DSF0000866371
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Design | Complete | 2/28/2018 | 7/13/2018 | 12/14/2018 | 58860 | 67336 | 67336 | DSF0000866371
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Construction | PNS | PNS | PNS | PNS | 863280 | 863280 | 39238 | DSF0000866371
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | CM,F&E | PNS | PNS | PNS | PNS | 58860 | 58860 | 16058 | DSF0000866371
31 | R042 | P.S. 42 - STATEN ISLAND | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 260000 | 260000 | 260000 | DSF0001086629
31 | R042 | P.S. 42 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/4/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001086628
31 | R042 | P.S. 42 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113246
31 | R042 | P.S. 42 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 8/4/2022 | DOES |  | DOES | 153800 | 0 | DSF0001034442
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | Scope | Complete | 3/14/2022 | 7/12/2022 | 4/13/2022 | 4003 | 3108 | 3108 | DSF0001034376
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | Design | Complete | 4/13/2022 | 10/6/2022 | 7/20/2022 | 18015 | 12429 | 12429 | DSF0001034376
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | Construction | Complete | 3/24/2023 | 2/16/2024 | 9/19/2024 | 232195 | 202316 | 173444 | DSF0001034376
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | CM,F&E | Complete | 3/24/2023 | 2/16/2024 | 9/19/2024 | 278662 | 269574 | 209492 | DSF0001034376
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113247
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 21000 | 21000 | 0 | DSF0001113247
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 308000 | 308000 | 0 | DSF0001113247
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 21000 | 21000 | 0 | DSF0001113247
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113677
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113677
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113677
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113677
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY18 RESO A ATHLETIC FIELDS | Scope | Complete | 1/12/2018 | 2/13/2018 | 3/8/2018 | 0 | 20847 | 20847 | DSF0000867209
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY18 RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 87983 | 67136 | 333 | DSF0000867209
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY18 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 1290412 | 8987350 | 3182 | DSF0000867209
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY18 RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 87983 | 612774 | 1342 | DSF0000867209
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE / FY21 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 3/1/2021 | 10/19/2021 | 2/14/2022 | 0 | 43504 | 36968 | DSF0000913136, DSF0000961460
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE / FY21 RESO A SCIENCE LAB UPGRADES | Design | Complete | 2/14/2022 | 8/5/2022 | 3/21/2023 | 139501 | 107172 | 76272 | DSF0000913136, DSF0000961460
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE / FY21 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 5/2/2024 | 5/1/2026 |  | 2046000 | 1494932 | 221112 | DSF0000913136, DSF0000961460
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE / FY21 RESO A SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 5/2/2024 | 5/1/2026 |  | 144737 | 230057 | 220611 | DSF0000913136, DSF0000961460
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA Furniture & Equipment | FY22 RESO A MOBILE SCIENCE CARTS | F&E | Complete | 5/29/2024 |  | 7/1/2024 | 175000 | 175000 | 175000 | DSF0001034003
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0001008363
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 125000 | 0 | DSF0001008388
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | DIIT - RESOA | FY22 RESO A (MA) TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 11/13/2024 | DIIR | 150000 | 150000 | DSF0001032960
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/3/2024 | DIIR |  | DIIR | 50000 | 0 | DSF0001086630
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 7/5/2024 | DIIR | 100000 | 99620 | DSF0001086631
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/15/2024 | DIIR | 10/30/2024 | DIIR | 99620 | 99620 | DSF0001086632
31 | R043 | R721 SPED - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/23/2024 | DIIR | 8/1/2024 | DIIR | 160000 | 159235 | DSF0001086633
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113249
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0 | DSF0001113250
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113251
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 9/1/2023 | DOER | 9/25/2023 | DOER | 87989 | 78914 | DSF0001036129
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 3/22/2024 | DOER |  | DOER | 300000 | 0 | DSF0001086634
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113248
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/9/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085034
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | DOE - Skilled Trades | RTU COMPRESSOR REPLACEMENT | Construction | In-Progress | 6/8/2023 | DOES |  | DOES | 95581 | 22868 | DSF0001085198
31 | R044 | P.S. 44 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 7/2/2024 | DIIR | 80000 | 80000 | DSF0001086636
31 | R044 | P.S. 44 - STATEN ISLAND | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 7/19/2022 | DOER |  | DOER | 54780 | 0 | DSF0000913137
31 | R044 | P.S. 44 - STATEN ISLAND | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | Complete | 5/17/2023 | DOER | 11/22/2023 | DOER | 86747 |  | DSF0001035350
31 | R044 | P.S. 44 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 127900 | 0 | DSF0001086635
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 64450 | 0
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - RESOA | FY14 RESO A FENCING | Construction | In-Progress | 8/28/2014 | DOER |  | DOER | 109262 | 0 | DSF0000798696
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FENCING UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035261
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - RESOA | RESO A ROOM CONVERSION | Construction | In-Progress | 1/22/2024 | DOER |  | DOER | 180000 | 1229 | DSF0001112048
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113252
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 6/14/2021 | DOES |  | DOES | 60921 | 0 | DSF0000866135
31 | R046 | P.S. 46 - STATEN ISLAND | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 75000 | 75000 | 0 | DSF0001036132
31 | R046 | P.S. 46 - STATEN ISLAND | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 96000 | 96000 | 0 | DSF0001113254
31 | R046 | P.S. 46 - STATEN ISLAND | Fast Track Projects | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 5/18/2021 | FTK |  | FTK | 2585878 | 2550342 | DSF0000866381
31 | R046 | P.S. 46 - STATEN ISLAND | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0 | DSF0000799346
31 | R046 | P.S. 46 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113253
31 | R046 | P.S. 46 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 695017 | 0 | DSF0001086638
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | Scope | Complete | 9/13/2017 | 2/1/2019 | 2/19/2019 | 170358 | 247535 | 247535 | DSF0000860113, DSF0000905572, DSF0000798346, DSF0000792908, DSF0000905571, DSF0000905573
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | Design | Complete | 2/19/2019 | 7/19/2019 | 5/16/2019 | 757717 | 986645 | 853601 | DSF0000860113, DSF0000905572, DSF0000798346, DSF0000792908, DSF0000905571, DSF0000905573
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | Construction | In-Progress | 2/10/2020 | 2/8/2022 |  | 15637502 | 15476995 | 14626458 | DSF0000860113, DSF0000905572, DSF0000798346, DSF0000792908, DSF0000905571, DSF0000905573
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | CM,F&E | In-Progress | 2/10/2020 | 2/8/2022 |  | 973000 | 1442873 | 1390835 | DSF0000860113, DSF0000905572, DSF0000798346, DSF0000792908, DSF0000905571, DSF0000905573
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113255
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 8/13/2021 | DOER |  | DOER | 272116 | 0 | DSF0000866372
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY21 RESO A FLOORING | Construction | In-Progress | 6/28/2024 | DOER |  | DOER | 88958 | 0 | DSF0000961477
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001083871
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001086639
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY24 RESO A OUTDOOR CLASSROOM | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001086640
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0001113256
31 | R049 | I.S. 49 - STATEN ISLAND | SCA IEH | PO18-TEST FOR ACM, LOOSE PLASTER CEILING IN STAIRWELL 'A' , 1ST FLOOR APPROX. 2 SQ. FT. SECTION CAME | Construction | In-Progress | 12/22/2023 | IEH |  | IEH | 0 | 0 | SCA0000072589
31 | R049 | I.S. 49 - STATEN ISLAND | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/2/2020 | FTK |  | FTK | 370338 | 361418 | DSF0000961049
31 | R049 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113258
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - RESOA | FY19 RESO A CAFETERIA UPGRADE | Construction | Complete | 7/26/2022 | DOER | 9/21/2022 | DOER | 33275 | 70960 | DSF0000912361
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - RESOA | FY 19 RESO A AUDITORIUM UPGRADE | Construction | Complete | 7/27/2022 | DOER | 9/21/2022 | DOER | 60461 | 74959 | DSF0000912362
31 | R049 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0000961454
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) SCIENCE LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001032962
31 | R049 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035347
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 255000 | 0 | DSF0001113257
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/22/2024 | DOES | 8/2/2024 | DOES | 65832 | 10031 | DSF0001084838
31 | R049 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/1/2024 | DOES |  | DOES | 563042 | 0 | DSF0001085765
31 | R050 | P.S. 50 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 7/5/2024 | DIIR | 75000 | 74718 | DSF0001086641
31 | R050 | P.S. 50 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113260
31 | R050 | P.S. 50 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) ROOM CONVERSION | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 500247 | 0 | DSF0001032978
31 | R050 | P.S. 50 - STATEN ISLAND | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113259
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113261
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001113261
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 220000 | 220000 | 0 | DSF0001113261
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 15000 | 15000 | 0 | DSF0001113261
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113678
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113678
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113678
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113678
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/1/2019 | 2/5/2020 | 6/23/2021 | 0 | 49831 | 49831 | DSF0000958383
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | Complete | 6/30/2021 | 11/16/2021 | 2/2/2023 | 517935 | 92468 | 90349 | DSF0000958383
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 7596381 | 7596381 | 44168 | DSF0000958383
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 517935 | 517935 | 30877 | DSF0000958383
31 | R051 | I.S. 51 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/10/2023 | DIIR |  | DIIR | 75000 | 0 | DSF0001033993
31 | R051 | I.S. 51 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001086642
31 | R051 | I.S. 51 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113262
31 | R051 | I.S. 51 - STATEN ISLAND | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/27/2019 | DOER |  | DOER | 3710 | 0 | DSF0000913470
31 | R051 | I.S. 51 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) AUDITORIUM UPGRADE | Construction | In-Progress | 11/10/2022 | DOER |  | DOER | 260234 | 0 | DSF0001032963
31 | R051 | I.S. 51 - STATEN ISLAND | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 8/6/2021 | DOES |  | DOES | 397298 | 0 | DSF0000912213
31 | R051 | I.S. 51 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/29/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084839
31 | R051 | I.S. 51 - STATEN ISLAND | DOE - Skilled Trades | EARTHQUAKE REMEDIATION WORK- DISPLACED STONES | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 62561 | 0 | DSF0001106079
31 | R052 | P.S. 52 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / PAVED AREA- BLACKTOP | Scope | Complete | 5/22/2024 | 10/8/2024 | 10/25/2024 | 105825 | 86022 | 86022 | DSF0001078144, DSF0001106097, DSF0001113783, DSF0001133813
31 | R052 | P.S. 52 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / PAVED AREA- BLACKTOP | Design | In-Progress | 10/25/2024 | 4/1/2025 |  | 492572 | 492572 | 10377 | DSF0001078144, DSF0001106097, DSF0001113783, DSF0001133813
31 | R052 | P.S. 52 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / PAVED AREA- BLACKTOP | Construction | PNS | PNS | PNS | PNS | 9894821 | 9894821 | 1502 | DSF0001078144, DSF0001106097, DSF0001113783, DSF0001133813
31 | R052 | P.S. 52 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / PAVED AREA- BLACKTOP | CM,F&E | PNS | PNS | PNS | PNS | 1024085 | 1024085 | 27594 | DSF0001078144, DSF0001106097, DSF0001113783, DSF0001133813
31 | R052 | P.S. 52 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 165000 | 122712 | DSF0001086643
31 | R052 | P.S. 52 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113263
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 63190 | 0 | DSF0000844866
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY18 RESO A TOILETS-STUDENTS | Construction | In-Progress | 3/11/2019 | DOER |  | DOER | 328622 | 0 | DSF0000866360
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/20/2021 | DOER |  | DOER | 176003 | 0 | DSF0000913471
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) AUDITORIUM UPGRADE | Construction | In-Progress | 8/26/2023 | DOER |  | DOER | 152598 | 0 | DSF0001032979
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/18/2023 | DOER |  | DOER | 139492 | 0 | DSF0001035264
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/23/2020 | DOES |  | DOES | 134930 | 0 | DSF0000913008
31 | R053 | P.S. 53 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 9/2/2022 | 1/24/2023 | 3/28/2023 | 22400 | 93388 | 93388 | DSF0001111861
31 | R053 | P.S. 53 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Design | Complete | 4/18/2023 | 9/19/2023 | 12/14/2023 | 112000 | 97307 | 70003 | DSF0001111861
31 | R053 | P.S. 53 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 11/12/2024 | 11/11/2025 |  | 2520000 | 2290968 | 25130 | DSF0001111861
31 | R053 | P.S. 53 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 11/12/2024 | 11/11/2025 |  | 156800 | 48931 | 48931 | DSF0001111861
31 | R053 | P.S. 53 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0 | DSF0001113264
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/18/2022 | DOER |  | DOER | 458000 | 0 | DSF0000961472
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 2/17/2023 | DOER |  | DOER | 90326 | 0 | DSF0001008402
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001035062
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001036138
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 3/7/2024 | DOER |  | DOER | 400000 | 0 | DSF0001086644
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 3/9/2016 | DOES |  | DOES | 75200 | 0 | DSF0000793004
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - Skilled Trades | WATER MAIN REPAIR | Construction | In-Progress | 3/13/2018 | DOES |  | DOES | 62279 | 0 | DSF0000888996
31 | R054 | P.S. 54 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 10/31/2024 | DIIR | 74736 | 74736 | DSF0001086645
31 | R054 | P.S. 54 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113265
31 | R054 | P.S. 54 - STATEN ISLAND | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75200 | 0 | DSF0000793020
31 | R054 | P.S. 54 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/25/2022 | DOES |  | DOES | 156825 | 0 | DSF0001034443
31 | R055 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 4/15/2021 | 9/15/2021 | 7/2/2021 | 84190 | 113953 | 113953 | DSF0001008806, DSF0001000455
31 | R055 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/8/2021 | 12/9/2021 | 3/31/2022 | 420950 | 595564 | 512985 | DSF0001008806, DSF0001000455
31 | R055 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/5/2022 | 7/3/2024 |  | 9471375 | 8753779 | 8141973 | DSF0001008806, DSF0001000455
31 | R055 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/5/2022 | 7/3/2024 |  | 589330 | 808040 | 803626 | DSF0001008806, DSF0001000455
31 | R055 | P.S. 55 - STATEN ISLAND | SCA IEH | PO18-TEST AND REMOVE A 6' X 2' SECTION OF LATHE AND PLASTER CEILING SPRAYED RED LOCATED IN THE BASEM | Construction | Complete | 9/11/2024 | IEH | 9/15/2024 | IEH | 0 | 0 | SCA0000073368
31 | R055 | P.S. 55 - STATEN ISLAND | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 131000 | 131000 | 0 | DSF0001113267
31 | R055 | P.S. 55 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001036140
31 | R055 | P.S. 55 - STATEN ISLAND | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001113266
31 | R055 | P.S. 55 - STATEN ISLAND | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | Complete | 2/8/2022 | DOES | 8/31/2022 | DOES | 83508 | 82385 | DSF0001009088
31 | R056 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/30/2022 | 11/16/2022 | 10/26/2022 | 84240 | 122437 | 122370 | DSF0001027476, DSF0001027477, DSF0001027478
31 | R056 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/9/2022 | 4/14/2023 | 4/4/2023 | 421199 | 439765 | 418453 | DSF0001027476, DSF0001027477, DSF0001027478
31 | R056 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | In-Progress | 7/7/2023 | 1/6/2025 |  | 9477000 | 8649667 | 7957301 | DSF0001027476, DSF0001027477, DSF0001027478
31 | R056 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/7/2023 | 1/6/2025 |  | 589679 | 607236 | 597934 | DSF0001027476, DSF0001027477, DSF0001027478
31 | R056 | P.S. 56 - STATEN ISLAND | SCA Furniture & Equipment | FY23 RESO A MOBILE STEM CARTS | F&E | Complete | 6/22/2024 |  | 10/15/2024 | 349502 | 349502 | 349461 | DSF0001036141
31 | R056 | P.S. 56 - STATEN ISLAND | DIIT - RESOA | FY09 RESO A SECURITY CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 154077 | 0 | DSF0000623174
31 | R056 | P.S. 56 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/7/2023 | DIIR | 7/31/2024 | DIIR | 224812 | 224812 | DSF0001033338
31 | R056 | P.S. 56 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001086648
31 | R056 | P.S. 56 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113269
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 12/16/2019 | DOER |  | DOER | 65784 | 0 | DSF0000890712
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | RESO A ROOM CONVERSION | Construction | In-Progress | 7/9/2021 | DOER |  | DOER | 56090 | 0 | DSF0000960890
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | RESO A GREENROOF | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001083768
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 98404 | 0 | DSF0001086647
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/21/2024 | DOER |  | DOER | 99072 | 0 | DSF0001111871
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001113268
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2/11/2022 | 6/28/2022 | 10/17/2022 | 142100 | 164681 | 161049 | DSF0001034390, DSF0001078236
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 11/4/2022 | 4/26/2023 | 5/10/2023 | 710500 | 528310 | 483802 | DSF0001034390, DSF0001078236
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | Construction | In-Progress | 7/10/2023 | 7/8/2025 |  | 15986250 | 14537315 | 4048218 | DSF0001034390, DSF0001078236
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | In-Progress | 7/10/2023 | 7/8/2025 |  | 995437 | 769696 | 724737 | DSF0001034390, DSF0001078236
31 | R057 | P.S. 57 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/8/2024 | DIIR | 7/25/2024 | DIIR | 60000 | 60000 | DSF0001033998
31 | R057 | P.S. 57 - STATEN ISLAND | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 306034 | 0 | DSF0000890713
31 | R057 | P.S. 57 - STATEN ISLAND | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/21/2022 | DOER |  | DOER | 153693 | 0 | DSF0001008842
31 | R057 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 315000 | 0 | DSF0001113270
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113271
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 31800 | 31800 | 0 | DSF0001113271
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 466400 | 466400 | 0 | DSF0001113271
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 31800 | 31800 | 0 | DSF0001113271
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113679
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113679
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113679
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113679
31 | R058 | P.S. 58 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001036142
31 | R058 | P.S. 58 - STATEN ISLAND | DOE - RESOA | FY14 RESO A ROOM CONVERSIONS / PART | Construction | In-Progress | 8/25/2014 | DOER |  | DOER | 80295 | 0 | DSF0000798835
31 | R058 | P.S. 58 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/13/2023 | DOES | 11/22/2024 | DOES | 50832 |  | DSF0001084458
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Scope | Complete | 7/14/2022 | 10/13/2022 | 1/3/2023 | 0 | 9924 | 9924 | DSF0001032980
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Design | Complete | 1/11/2023 | 5/26/2023 | 5/11/2023 | 20200 | 20200 | 36123 | DSF0001032980
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Construction | Complete | 12/8/2023 | 11/1/2024 | 8/1/2024 | 296272 | 285001 | 261673 | DSF0001032980
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | CM,F&E | Complete | 12/8/2023 | 11/1/2024 | 8/1/2024 | 20200 | 20200 | 40955 | DSF0001032980
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Scope | Complete | 11/20/2023 | 1/22/2024 | 11/30/2023 | 0 | 3774 | 3774 | DSF0001035351
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Design | Complete | 11/30/2023 | 5/28/2024 | 1/31/2024 | 27000 | 15097 | 15097 | DSF0001035351
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Construction | In-Progress | 7/25/2024 | 6/19/2025 |  | 396000 | 187096 | 910 | DSF0001035351
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | CM,F&E | In-Progress | 7/25/2024 | 6/19/2025 |  | 31264 | 13386 | 12404 | DSF0001035351
31 | R059 | THE HARBOR VIEW SCHOOL - R | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 3/16/2023 | DOER | 9/28/2024 | DOER | 139271 | 75247 | DSF0000913143
31 | R059 | THE HARBOR VIEW SCHOOL - R | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086650
31 | R059 | THE HARBOR VIEW SCHOOL - R | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113272
31 | R059 | THE HARBOR VIEW SCHOOL - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/9/2024 | DOES | 9/25/2024 | DOES | 65832 |  | DSF0001085542
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 3/5/2024 | 7/19/2024 | 8/13/2024 | 8536 | 37553 | 37490 | DSF0001106248, DSF0001106252
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | Design | In-Progress | 8/28/2024 | 2/3/2025 |  | 37244 | 37412 | 8225 | DSF0001106248, DSF0001106252
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 493941 | 493941 | 2175 | DSF0001106248, DSF0001106252
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 101122 | 101122 | 36459 | DSF0001106248, DSF0001106252
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/2/2021 | 1/20/2022 | 1/20/2022 | 0 | 25752 | 25752 | DSF0000961455, DSF0001007749
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 1/20/2022 | 4/22/2022 | 3/28/2022 | 37261 | 43452 | 43452 | DSF0000961455, DSF0001007749
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | Complete | 7/5/2022 | 5/30/2023 | 9/6/2023 | 546502 | 520211 | 466400 | DSF0000961455, DSF0001007749
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 7/5/2022 | 5/30/2023 | 9/6/2023 | 37261 | 71981 | 70603 | DSF0000961455, DSF0001007749
31 | R060 | P.S. 60 - STATEN ISLAND | SCA IEH | PO18-ACM TESTING ON SCHOOL SIGN IN FRONT OF THE SCHOOL | Construction | In-Progress | 1/5/2024 | IEH |  | IEH | 0 | 0 | SCA0000072614
31 | R060 | P.S. 60 - STATEN ISLAND | Fast Track Projects | LSP REPLACE UNIVENTS | Construction | In-Progress | 1/12/2023 | FTK |  | FTK | 788671 | 280304 | DSF0000960692
31 | R060 | P.S. 60 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/5/2024 | DIIR | 10/22/2024 | DIIR | 74433 | 74433 | DSF0001086653
31 | R060 | P.S. 60 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113273
31 | R060 | P.S. 60 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001086652
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/29/2023 | 10/30/2023 | 10/3/2023 | 11748 | 15871 | 15871 | DSF0001083807
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/11/2023 | 3/12/2024 | 2/13/2024 | 52864 | 57168 | 43751 | DSF0001083807
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 7/26/2024 | 8/29/2025 |  | 681356 | 616287 | 8466 | DSF0001083807
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 7/26/2024 | 8/29/2025 |  | 126286 | 81647 | 18210 | DSF0001083807
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | PAVED AREA- BLACKTOP | Scope | Complete | 3/26/2024 | 6/25/2024 | 8/12/2024 | 11567 | 50028 | 37840 | DSF0001112054
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | PAVED AREA- BLACKTOP | Design | In-Progress | 8/19/2024 | 1/7/2025 |  | 52051 | 57182 | 16210 | DSF0001112054
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | PAVED AREA- BLACKTOP | Construction | PNS | PNS | PNS | PNS | 670883 | 670883 | 33692 | DSF0001112054
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | PAVED AREA- BLACKTOP | CM,F&E | PNS | PNS | PNS | PNS | 124345 | 124345 | 13643 | DSF0001112054
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PAVED AREA- BLACKTOP | Scope | Complete | 9/23/2024 | 12/23/2024 | 10/29/2024 | 2966 | 6341 | 0 | DSF0001113753
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PAVED AREA- BLACKTOP | Design | In-Progress | 11/5/2024 | 3/5/2025 |  | 11862 | 11862 | 0 | DSF0001113753
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PAVED AREA- BLACKTOP | Construction | PNS | PNS | PNS | PNS | 170520 | 170520 | 0 | DSF0001113753
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PAVED AREA- BLACKTOP | CM,F&E | PNS | PNS | PNS | PNS | 43742 | 43742 | 2055 | DSF0001113753
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/29/2021 | 11/30/2021 | 8/18/2021 | 4477 | 6223 | 6223 | DSF0000960782
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/18/2021 | 2/16/2022 | 12/29/2021 | 20148 | 24890 | 24890 | DSF0000960782
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/12/2022 | 3/7/2023 |  | 259685 | 236074 | 209120 | DSF0000960782
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/12/2022 | 3/7/2023 |  | 194121 | 196239 | 196079 | DSF0000960782
31 | R061 | I.S. 61 - STATEN ISLAND | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 100000 | 0 | DSF0000866588
31 | R061 | I.S. 61 - STATEN ISLAND | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/15/2022 | DOER |  | DOER | 564532 | 0 | DSF0001035352
31 | R061 | I.S. 61 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 12/4/2023 | DOER |  | DOER | 2140840 | 61379 | DSF0001086654
31 | R061 | I.S. 61 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/29/2024 | DOES | 8/5/2024 | DOES | 65832 |  | DSF0001084840
31 | R062 | THE KATHLEEN GRIMM SCHOOL FOR LEADERSHIP AND SUSTAINABILITY | SCA Furniture & Equipment | FY24 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 148000 | 148000 | 148000 | DSF0001086656
31 | R062 | THE KATHLEEN GRIMM SCHOOL FOR LEADERSHIP AND SUSTAINABILITY | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 195000 | 0 | DSF0001113274
31 | R062 | THE KATHLEEN GRIMM SCHOOL FOR LEADERSHIP AND SUSTAINABILITY | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 1/27/2020 | DOER |  | DOER | 145255 | 0 | DSF0000913144
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113275
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 16500 | 16500 | 0 | DSF0001113275
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 242000 | 242000 | 0 | DSF0001113275
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 16500 | 16500 | 1236 | DSF0001113275
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113680
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113680
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113680
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113680
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001033340
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0000913145
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001036146
31 | R068 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/27/2024 | DOES | 12/10/2024 | DOES | 50832 |  | DSF0001085544
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2/16/2023 | 7/5/2023 | 11/15/2023 | 31000 | 161790 | 161790 | DSF0001078345
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Design | Complete | 12/5/2023 | 5/7/2024 | 4/17/2024 | 155000 | 312172 | 247103 | DSF0001078345
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Construction | In-Progress | 9/27/2024 | 6/18/2026 |  | 3487500 | 3205986 | 144969 | DSF0001078345
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | CM,F&E | In-Progress | 9/27/2024 | 6/18/2026 |  | 217000 | 71197 | 68803 | DSF0001078345
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Scope | Complete | 1/3/2024 | 4/3/2024 | 3/20/2024 | 0 | 2050 | 2050 | DSF0001086657
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Design | Complete | 5/9/2024 | 10/10/2024 | 10/9/2024 | 30000 | 8200 | 8200 | DSF0001086657
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 7677 | DSF0001086657
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 11166 | DSF0001086657
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 346 | 346 | DSF0001086658
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 30000 | 29654 | 1383 | DSF0001086658
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 440000 | 440000 | 0 | DSF0001086658
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 30000 | 30000 | 0 | DSF0001086658
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087109
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087109
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087109
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001087109
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 370579 | 0 | DSF0000799347
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY20 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0 | DSF0000960711
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 1/12/2024 | DIIR | 50000 | 50000 | DSF0001008371
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 1/12/2024 | DIIR | 100000 | 100000 | DSF0001008406
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113276
31 | R070 | THE WAVERLY ACADEMY OF EMPOWERED LEARNERS | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 100000 | 100000 | 0 | DSF0001113279
31 | R070 | THE YOUNG WOMEN¿S LEADERSHIP SCHOOL OF STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 7/8/2024 | DIIR | 70000 | 70000 | DSF0001086659
31 | R070 | THE WAVERLY ACADEMY OF EMPOWERED LEARNERS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/14/2024 | DIIR |  | DIIR | 75000 | 0 | DSF0001086660
31 | R070 | THE WAVERLY ACADEMY OF EMPOWERED LEARNERS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0 | DSF0001113277
31 | R070 | THE YOUNG WOMEN¿S LEADERSHIP SCHOOL OF STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0 | DSF0001113278
31 | R070 | THE WAVERLY ACADEMY OF EMPOWERED LEARNERS | DOE - RESOA | RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0 | DSF0001113756
31 | R071 | P.S. 48 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 10/16/2024 | DIIR | 155000 | 155000 | DSF0001086661
31 | R071 | P.S. 48 - STATEN ISLAND | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0 | DSF0001035263
31 | R071 | P.S. 48 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0 | DSF0001113280
31 | R071 | P.S. 48 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/19/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084695
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 10/9/2018 | 3/14/2019 | 12/21/2018 | 119640 | 119314 | 119314 | DSF0000890598, DSF0000877738
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/9/2019 | 6/11/2019 | 5/7/2019 | 478560 | 526517 | 494027 | DSF0000890598, DSF0000877738
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 7/22/2019 | 7/20/2021 |  | 8973000 | 9558566 | 8470682 | DSF0000890598, DSF0000877738
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 7/22/2019 | 7/20/2021 |  | 558320 | 1577639 | 1546149 | DSF0000890598, DSF0000877738
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | Scope | Complete | 2/13/2019 | 7/15/2019 | 2/12/2020 | 92360 | 110250 | 110250 | DSF0000911803, DSF0001000610
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | Design | Complete | 9/9/2021 | 2/14/2022 | 4/15/2022 | 461800 | 330405 | 309449 | DSF0000911803, DSF0001000610
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | Construction | In-Progress | 8/8/2022 | 8/6/2024 |  | 10390500 | 9430022 | 6301772 | DSF0000911803, DSF0001000610
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | CM,F&E | In-Progress | 8/8/2022 | 8/6/2024 |  | 646520 | 782140 | 771316 | DSF0000911803, DSF0001000610
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 5/24/2024 | 8/26/2024 | 8/28/2024 | 66586 | 107725 | 90287 | DSF0001112187
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLAYGROUND UPGRADE | Design | In-Progress | 10/15/2024 | 3/5/2025 |  | 310735 | 310735 | 13170 | DSF0001112187
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 4927367 | 4927367 | 58534 | DSF0001112187
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 488298 | 488298 | 22903 | DSF0001112187
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | Scope | Complete | 1/28/2022 | 9/23/2022 | 1/20/2023 | 168263 | 245310 | 237883 | DSF0001083778, DSF0001086897, DSF0001083779, DSF0001078375, DSF0001078373
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | Design | Complete | 1/31/2023 | 7/3/2023 | 9/20/2023 | 836921 | 761380 | 519647 | DSF0001083778, DSF0001086897, DSF0001083779, DSF0001078375, DSF0001078373
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 8/19/2024 | 8/18/2026 |  | 18450750 | 18901659 | 2196045 | DSF0001083778, DSF0001086897, DSF0001083779, DSF0001078375, DSF0001078373
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 8/19/2024 | 8/18/2026 |  | 1210786 | 452645 | 379148 | DSF0001083778, DSF0001086897, DSF0001083779, DSF0001078375, DSF0001078373
31 | R072 | I.S. 72 - STATEN ISLAND | DIIT - RESOA | FY11 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 109492 | 0 | DSF0000710887
31 | R072 | I.S. 72 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001034005
31 | R072 | I.S. 72 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 125000 | 114021 | DSF0001086662
31 | R072 | I.S. 72 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001113281
31 | R072 | I.S. 72 - STATEN ISLAND | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0 | DSF0001034006
31 | R072 | I.S. 72 - STATEN ISLAND | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | Complete | 7/14/2023 | DOER | 10/21/2024 | DOER | 227647 |  | DSF0001036151
31 | R072 | I.S. 72 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113282
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 11/29/2021 | 5/2/2022 | 2/23/2022 | 104190 | 59819 | 59819 | DSF0001008808, DSF0001008807
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2/25/2022 | 7/27/2022 | 5/12/2022 | 520950 | 316345 | 263042 | DSF0001008808, DSF0001008807
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 7/12/2023 | 1/1/2025 |  | 11721375 | 10617956 | 8624925 | DSF0001008808, DSF0001008807
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 7/12/2023 | 1/1/2025 |  | 729330 | 551958 | 538568 | DSF0001008808, DSF0001008807
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 5/24/2017 | 6/9/2020 | 5/26/2021 | 214034 | 454525 | 446500 | DSF0000845593, DSF0000882956, DSF0000882958, DSF0000882959, DSF0000882960, DSF0000905848, DSF0000912593, DSF0000913147
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 6/2/2021 | 10/18/2021 | 2/15/2022 | 1025603 | 1079978 | 936679 | DSF0000845593, DSF0000882956, DSF0000882958, DSF0000882959, DSF0000882960, DSF0000905848, DSF0000912593, DSF0000913147
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 8/3/2022 | 8/1/2024 |  | 21352656 | 19288817 | 6359753 | DSF0000845593, DSF0000882956, DSF0000882958, DSF0000882959, DSF0000882960, DSF0000905848, DSF0000912593, DSF0000913147
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | CM,F&E | In-Progress | 8/3/2022 | 8/1/2024 |  | 1567818 | 1279836 | 1247810 | DSF0000845593, DSF0000882956, DSF0000882958, DSF0000882959, DSF0000882960, DSF0000905848, DSF0000912593, DSF0000913147
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY23 RESO A MEDIA UPGRADE | Construction | Complete | 5/24/2023 | DOER | 6/16/2023 | DOER | 19814 |  | DSF0001036153
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FLOORING UPGRADE | Construction | In-Progress | 7/31/2023 | DOER |  | DOER | 130041 | 0 | DSF0001035268
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 493172 | 0 | DSF0001086663
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 180000 | 0 | DSF0001113283
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113284
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/1/2024 | DOES | 8/7/2024 | DOES | 50832 |  | DSF0001084842
31 | R077 | THE RICHMOND PRE-K CENTER | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/23/2024 | DIIR | 9/6/2024 | DIIR | 158000 | 157404 | DSF0001086667
31 | R077 | THE RICHMOND PRE-K CENTER | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 9/15/2023 | DOER |  | DOER | 159428 | 0 | DSF0001036155
31 | R077 | THE RICHMOND PRE-K CENTER | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 111663 | 0 | DSF0001086664
31 | R077 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 11/25/2024 | DOES | 50832 | 189 | DSF0001085545
31 | R080 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/12/2019 | DOES |  | DOES | 831928 | 0 | DSF0000912203
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | SCA CIP | STEAM PIPE REPLACEMENT | Scope | Complete | 2/23/2024 | 7/25/2024 | 7/25/2024 | 14207 | 17078 | 17078 | SCA0000072714
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | SCA CIP | STEAM PIPE REPLACEMENT | Design | In-Progress | 8/6/2024 | 1/9/2025 |  | 63932 | 63932 | 30555 | SCA0000072714
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | SCA CIP | STEAM PIPE REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 824016 | 824016 | 1266 | SCA0000072714
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | SCA CIP | STEAM PIPE REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 152727 | 152727 | 31777 | SCA0000072714
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 180000 | 0 | DSF0001086665
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113285
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/17/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085546
31 | R086 | R721 SPED - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0 | DSF0001113286
31 | R086 | R721 SPED - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 7/5/2024 | DOES | 50832 |  | DSF0001085035
31 | R089 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/9/2024 | DOES | 11/19/2024 | DOES | 50832 |  | DSF0001085036
31 | R090 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/15/2024 | DOES | 11/26/2024 | DOES | 50832 | 9135 | DSF0001085547
31 | R091 | THE RICHMOND PRE-K CENTER | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086666
31 | R094 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/10/2024 | DOES | 7/25/2024 | DOES | 50832 | 8438 | DSF0001085550
31 | R100 | THE RICHMOND PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113681
31 | R100 | THE RICHMOND PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113681
31 | R100 | THE RICHMOND PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113681
31 | R100 | THE RICHMOND PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113681
31 | R100 | THE RICHMOND PRE-K CENTER | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113287
31 | R100 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/25/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085552
31 | R101 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/20/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085553
31 | R110 | THE RICHMOND PRE-K CENTER | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / PATH OF TRAVEL IDA INTERIOR SPACES | Scope | Complete | 4/8/2022 | 11/16/2023 | 9/14/2023 | 27675 | 68903 | 39939 | DSF0001111844, DSF0001083883, DSF0001085610
31 | R110 | THE RICHMOND PRE-K CENTER | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / PATH OF TRAVEL IDA INTERIOR SPACES | Design | Complete | 9/27/2023 | 2/2/2024 | 12/15/2023 | 124535 | 104470 | 102036 | DSF0001111844, DSF0001083883, DSF0001085610
31 | R110 | THE RICHMOND PRE-K CENTER | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / PATH OF TRAVEL IDA INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 1605121 | 1605121 | 8638 | DSF0001111844, DSF0001083883, DSF0001085610
31 | R110 | THE RICHMOND PRE-K CENTER | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / PATH OF TRAVEL IDA INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 297501 | 297501 | 36571 | DSF0001111844, DSF0001083883, DSF0001085610
31 | R110 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/12/2024 | DOES | 9/4/2024 | DOES | 50832 | 9342 | DSF0001085554
31 | R112 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/23/2024 | DOES | 9/25/2024 | DOES | 65832 | 11084 | DSF0001085555
31 | R113 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/6/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085556
31 | R113 | 3K CENTER @ 841 FATHER CAPODANNO BOULEVARD - STATEN ISLAND | DOE Managed PRE-K | LEASE | Construction | In-Progress | 9/11/2019 | DOEP |  | DOEP | 34454 | 0 | DSF0000912545
31 | R119 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | Scope | Complete | 4/28/2021 | 1/18/2022 | 4/20/2022 | 26871 | 54728 | 53747 | DSF0000961035, DSF0001034155
31 | R119 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | Design | Complete | 4/20/2022 | 9/1/2022 | 3/6/2023 | 133620 | 213845 | 173892 | DSF0000961035, DSF0001034155
31 | R119 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | Construction | In-Progress | 10/16/2023 | 4/15/2025 |  | 2942927 | 2749566 | 2298722 | DSF0000961035, DSF0001034155
31 | R119 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | CM,F&E | In-Progress | 10/16/2023 | 4/15/2025 |  | 211487 | 74388 | 54839 | DSF0000961035, DSF0001034155
31 | R119 | R025 SPED - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/17/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085557
31 | R121 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/25/2021 | 8/12/2021 | 8/27/2021 | 1537800 | 991092 | 984958 | DSF0000889060
31 | R121 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Design | Complete | 8/30/2021 | 4/25/2022 | 9/2/2022 | 6920100 | 3396017 | 2356673 | DSF0000889060
31 | R121 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 3/27/2023 | 9/3/2025 |  | 87270150 | 79289491 | 69558241 | DSF0000889060
31 | R121 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 3/27/2023 | 9/3/2025 |  | 12302400 | 7638436 | 3673664 | DSF0000889060
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/28/2023 | 9/5/2023 | 9/5/2023 | 1337500 | 930414 | 927113 | DSF0000911852
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Design | Complete | 9/6/2023 | 3/29/2024 | 5/6/2024 | 6018750 | 2160740 | 1218727 | DSF0000911852
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Construction | In-Progress | 8/15/2024 | 9/3/2027 |  | 75903125 | 68723055 | 1096325 | DSF0000911852
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | CM,Art,F&E | In-Progress | 8/15/2024 | 9/3/2027 |  | 10700000 | 4468746 | 639590 | DSF0000911852
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 3/28/2023 | 3/28/2023 | 3/28/2023 | 23890 | 36871 | 36871 | DSF0000911852
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 3/28/2023 | 9/15/2023 | 9/22/2023 | 119450 | 271637 | 210493 | DSF0000911852
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | Construction | In-Progress | 4/15/2024 | 4/14/2025 |  | 2687625 | 3117431 | 581507 | DSF0000911852
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 4/15/2024 | 4/14/2025 |  | 167230 | 330181 | 320226 | DSF0000911852
31 | R123 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/19/2024 | 10/10/2024 | 10/8/2024 | 3314412 | 1914308 | 1902752 | DSF0000890637
31 | R123 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Design | In-Progress | 10/9/2024 | 4/17/2025 |  | 13257648 | 13257648 | 43187 | DSF0000890637
31 | R123 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 183121265 | 183121265 | 142314 | DSF0000890637
31 | R123 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 24029487 | 24029487 | 206311 | DSF0000890637
31 | R123 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 3/19/2024 | 8/1/2024 | 7/25/2024 | 1275959 | 1475885 | 1474627 | DSF0000890637
31 | R123 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Design | In-Progress | 7/26/2024 | 2/6/2025 |  | 5954475 | 5954475 | 801342 | DSF0000890637
31 | R123 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Construction | PNS | PNS | PNS | PNS | 94420966 | 94420966 | 802298 | DSF0000890637
31 | R123 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | CM,F&E | PNS | PNS | PNS | PNS | 9357033 | 9357033 | 371381 | DSF0000890637
31 | R125 | P.S./I.S. @ 27 LANDIS AVENUE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/19/2024 | 10/3/2024 | 9/26/2024 | 1805919 | 1112766 | 1092434 | DSF0000798213
31 | R125 | P.S./I.S. @ 27 LANDIS AVENUE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Design | In-Progress | 9/27/2024 | 4/17/2025 |  | 7223675 | 7223675 | 87513 | DSF0000798213
31 | R125 | P.S./I.S. @ 27 LANDIS AVENUE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Construction | PNS | PNS | PNS | PNS | 99777015 | 99777015 | 1028 | DSF0000798213
31 | R125 | P.S./I.S. @ 27 LANDIS AVENUE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | CM,Art,F&E | PNS | PNS | PNS | PNS | 13092911 | 13092911 | 203304 | DSF0000798213
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | CHAPEL RENOVATION @ 57 CLEVELAND PLACE | Scope | Complete | 3/19/2024 | 10/29/2024 | 10/29/2024 | 509937 | 409362 | 373728 | DSF0001112087
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | CHAPEL RENOVATION @ 57 CLEVELAND PLACE | Design | In-Progress | 10/30/2024 | 4/17/2025 |  | 2039747 | 2039747 | 53514 | DSF0001112087
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | CHAPEL RENOVATION @ 57 CLEVELAND PLACE | Construction | PNS | PNS | PNS | PNS | 28174009 | 28174009 | 1819 | DSF0001112087
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | CHAPEL RENOVATION @ 57 CLEVELAND PLACE | CM,Art,F&E | PNS | PNS | PNS | PNS | 3697042 | 3697042 | 232794 | DSF0001112087
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 7/21/2023 | 7/21/2023 | 7/21/2023 | 94980 | 120326 | 119312 | DSF0000890637
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 7/21/2023 | 12/15/2023 | 5/13/2024 | 474900 | 1012692 | 700490 | DSF0000890637
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Construction | In-Progress | 7/22/2024 | 7/21/2025 |  | 10685250 | 20187325 | 4772520 | DSF0000890637
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 7/22/2024 | 7/21/2025 |  | 674596 | 1101051 | 938190 | DSF0000890637
31 | R127 | MAINTENANCE BUILDING @ 12 HASTINGS STREET - STATEN ISLAND | SCA Capacity | NEW MAINTENANCE BUILDING | Scope | Complete | 3/19/2024 | 10/10/2024 | 10/8/2024 | 153554 | 142819 | 138256 | DSF0001112088
31 | R127 | MAINTENANCE BUILDING @ 12 HASTINGS STREET - STATEN ISLAND | SCA Capacity | NEW MAINTENANCE BUILDING | Design | In-Progress | 10/9/2024 | 4/17/2025 |  | 614217 | 614217 | 6187 | DSF0001112088
31 | R127 | MAINTENANCE BUILDING @ 12 HASTINGS STREET - STATEN ISLAND | SCA Capacity | NEW MAINTENANCE BUILDING | Construction | PNS | PNS | PNS | PNS | 8483870 | 8483870 | 24619 | DSF0001112088
31 | R127 | MAINTENANCE BUILDING @ 12 HASTINGS STREET - STATEN ISLAND | SCA Capacity | NEW MAINTENANCE BUILDING | CM,Art,F&E | PNS | PNS | PNS | PNS | 1113268 | 1113268 | 83475 | DSF0001112088
31 | R128 | ATHLETIC FIELD @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | ATHLETIC FIELD & FINAL SITEWORK @ 57 CLEVELAND PLACE | Scope | Complete | 3/19/2024 | 8/1/2024 | 7/25/2024 | 549642 | 646813 | 646813 | DSF0001112089
31 | R128 | ATHLETIC FIELD @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | ATHLETIC FIELD & FINAL SITEWORK @ 57 CLEVELAND PLACE | Design | In-Progress | 7/26/2024 | 4/17/2025 |  | 2198567 | 2198567 | 492493 | DSF0001112089
31 | R128 | ATHLETIC FIELD @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | ATHLETIC FIELD & FINAL SITEWORK @ 57 CLEVELAND PLACE | Construction | PNS | PNS | PNS | PNS | 30367704 | 30367704 | 0 | DSF0001112089
31 | R128 | ATHLETIC FIELD @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | ATHLETIC FIELD & FINAL SITEWORK @ 57 CLEVELAND PLACE | CM,Art,F&E | PNS | PNS | PNS | PNS | 3984902 | 3984902 | 109760 | DSF0001112089
31 | R131 | P.S. @ 15 LISBON PLACE - STATEN ISLAND | SCA Lease Site Improvement | LEASE | Scope | In-Progress | 9/30/2024 | 1/15/2025 |  | 500000 | 500000 | 86265 | DSF0000911848
31 | R131 | P.S. @ 15 LISBON PLACE - STATEN ISLAND | SCA Lease Site Improvement | LEASE | Design | PNS | PNS | PNS | PNS | 2000000 | 2000000 | 33408 | DSF0000911848
31 | R131 | P.S. @ 15 LISBON PLACE - STATEN ISLAND | SCA Lease Site Improvement | LEASE | Construction | PNS | PNS | PNS | PNS | 27625000 | 27625000 | 22831 | DSF0000911848
31 | R131 | P.S. @ 15 LISBON PLACE - STATEN ISLAND | SCA Lease Site Improvement | LEASE | CM,F&E | PNS | PNS | PNS | PNS | 3625000 | 3625000 | 93634 | DSF0000911848
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 7/19/2019 | 12/5/2019 | 12/23/2019 | 294742 | 400910 | 400910 | DSF0000905874, DSF0000905875, DSF0000951581
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 1/8/2020 | 6/9/2020 | 6/25/2020 | 1473705 | 1325229 | 1294447 | DSF0000905874, DSF0000905875, DSF0000951581
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | In-Progress | 7/6/2021 | 6/19/2024 |  | 33158366 | 31166988 | 28433205 | DSF0000905874, DSF0000905875, DSF0000951581
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | In-Progress | 7/6/2021 | 6/19/2024 |  | 2063187 | 1412877 | 1371952 | DSF0000905874, DSF0000905875, DSF0000951581
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | Scope | Complete | 10/7/2021 | 2/28/2022 | 1/24/2022 | 26467 | 40301 | 40301 | DSF0001000667
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | Design | Complete | 2/2/2022 | 8/4/2022 | 10/5/2022 | 132335 | 144821 | 129147 | DSF0001000667
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | Construction | In-Progress | 5/15/2023 | 5/13/2024 |  | 2977547 | 2946441 | 2836916 | DSF0001000667
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | CM,F&E | In-Progress | 5/15/2023 | 5/13/2024 |  | 228706 | 319060 | 311436 | DSF0001000667
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | Scope | Complete | 1/11/2019 | 12/4/2020 | 6/4/2021 | 110078 | 107604 | 104122 | DSF0000951585, DSF0000960626, DSF0000961097, DSF0001000648
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | Design | Complete | 6/15/2021 | 11/15/2021 | 2/3/2022 | 543998 | 455218 | 405324 | DSF0000951585, DSF0000960626, DSF0000961097, DSF0001000648
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | Construction | In-Progress | 8/8/2022 | 8/6/2024 |  | 11687077 | 10960273 | 9717375 | DSF0000951585, DSF0000960626, DSF0000961097, DSF0001000648
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | CM,F&E | In-Progress | 8/8/2022 | 8/6/2024 |  | 818478 | 593402 | 573115 | DSF0000951585, DSF0000960626, DSF0000961097, DSF0001000648
31 | R435 | NEW DORP HS - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/20/2023 | DIIR |  | DIIR | 175000 | 0 | DSF0001036157
31 | R435 | NEW DORP HS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | Complete | 8/9/2021 | DOER | 8/24/2021 | DOER | 59263 | 58466 | DSF0001008364
31 | R435 | NEW DORP HS - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 408079 | 0 | DSF0001086668
31 | R435 | NEW DORP HS - STATEN ISLAND | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0 | DSF0001113288
31 | R435 | NEW DORP HS - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 8/29/2024 | DOES |  | DOES | 50832 | 0 | DSF0001085037
31 | R436 | NEW DORP HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Scope | Complete | 3/5/2021 | 7/29/2021 | 1/4/2023 | 0 | 322032 | 234308 | DSF0000913150
31 | R436 | NEW DORP HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Design | In-Progress | 1/4/2023 | 6/30/2023 |  | 832200 | 510168 | 251429 | DSF0000913150
31 | R436 | NEW DORP HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Construction | PNS | PNS | PNS | PNS | 12205600 | 12205600 | 144016 | DSF0000913150
31 | R436 | NEW DORP HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 832200 | 832200 | 54357 | DSF0000913150
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 9/28/2023 | 2/16/2024 | 12/22/2023 | 17700 | 26784 | 26321 | DSF0001078512
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 1/8/2024 | 6/7/2024 | 4/25/2024 | 88500 | 59246 | 58094 | DSF0001078512
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | REINFORCING SUPPORT ELEMENTS | Construction | PNS | PNS | PNS | PNS | 1991250 | 1991250 | 10277 | DSF0001078512
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | REINFORCING SUPPORT ELEMENTS | CM,F&E | PNS | PNS | PNS | PNS | 123900 | 123900 | 41148 | DSF0001078512
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/12/2022 | 9/12/2022 | 5/31/2022 | 6400 | 5631 | 5631 | DSF0001034666
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/31/2022 | 11/25/2022 | 8/31/2022 | 28800 | 22522 | 22522 | DSF0001034666
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 5/31/2023 | 4/24/2024 |  | 371200 | 324728 | 293091 | DSF0001034666
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 5/31/2023 | 4/24/2024 |  | 190188 | 167653 | 102568 | DSF0001034666
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA IEH | PO18-BASEMENT HALLWAY, 1964 BUILDING ABATE 233 SQ. FT. CEILING TILES - FIRST FLOOR HALLWAY, 1964 BUI | Construction | Complete | 9/9/2024 | IEH | 9/22/2024 | IEH | 0 | 0 | SCA0000073360
31 | R440 | STATEN ISLAND TECHNICAL HS - R | Fast Track Projects | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 10/19/2023 | FTK |  | FTK | 145508 | 130574 | DSF0001008380
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001034013
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001036158
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001086670
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0000961462
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001113290
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/24/2023 | DOES |  | DOES | 84136 | 0 | DSF0000866136
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 151197 | 0 | DSF0001034266
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/17/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085038
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - Skilled Trades | HEATING PLANT UPGRADE | Construction | In-Progress | 12/13/2023 | DOES |  | DOES | 263819 | 117327 | DSF0001111881
31 | R445 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Scope | Complete | 8/5/2020 | 12/4/2020 | 3/1/2021 | 85860 | 41043 | 41043 | DSF0000961096, DSF0001000700
31 | R445 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Design | Complete | 3/3/2021 | 8/13/2021 | 1/24/2022 | 429300 | 379907 | 309012 | DSF0000961096, DSF0001000700
31 | R445 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Construction | In-Progress | 6/29/2022 | 12/20/2023 |  | 9659250 | 9372907 | 8707711 | DSF0000961096, DSF0001000700
31 | R445 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | CM,F&E | In-Progress | 6/29/2022 | 12/20/2023 |  | 601020 | 433688 | 426169 | DSF0000961096, DSF0001000700
31 | R445 | PORT RICHMOND HS - R | DOE - RESOA | FY22 RESO A (MA) AUDITORIUM UPGRADE | Construction | In-Progress | 9/26/2022 | DOER |  | DOER | 197249 | 0 | DSF0001032966
31 | R445 | PORT RICHMOND HS - R | DOE - RESOA | FY22 RESO A (MA) SCIENCE LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001032967
31 | R445 | PORT RICHMOND HS - R | DOE - Skilled Trades | ELEVATOR UPGRADE | Construction | In-Progress | 2/17/2017 | DOES |  | DOES | 15242 | 0 | DSF0000800120
31 | R445 | PORT RICHMOND HS - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 7/10/2024 | DOES | 65832 |  | DSF0001085039
31 | R445 | PORT RICHMOND HS - R | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/31/2024 | DOES |  | DOES | 743382 | 0 | DSF0001085716
31 | R445 | PORT RICHMOND HS - R | DOE - Skilled Trades | COLLAPSED ROOF DRAIN | Construction | In-Progress | 3/18/2024 | DOES |  | DOES | 157837 | 0 | DSF0001106498
31 | R446 | PORT RICHMOND HS - R | Fast Track Projects | LSP REPLACE BOILER | Construction | In-Progress | 7/23/2019 | FTK |  | FTK | 731742 | 663632 | DSF0000889649
31 | R450 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | Scope | Complete | 8/26/2020 | 12/24/2020 | 4/27/2021 | 36280 | 108372 | 108372 | DSF0000961127
31 | R450 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | Design | Complete | 5/25/2021 | 10/19/2021 | 11/8/2021 | 181400 | 366555 | 332201 | DSF0000961127
31 | R450 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | Construction | In-Progress | 4/12/2022 | 8/9/2023 |  | 4081500 | 4340727 | 3714726 | DSF0000961127
31 | R450 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | CM,F&E | In-Progress | 4/12/2022 | 8/9/2023 |  | 253960 | 786924 | 779431 | DSF0000961127
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSIONS | Construction | In-Progress | 6/1/2022 | DOER |  | DOER | 326302 | 0 | DSF0000961470
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 4/22/2024 | DOER |  | DOER | 75231 | 0 | DSF0001035353
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - RESOA | RESO A- FY24 RESO A PAVED AREA - BLACKTOP | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001085592
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - Skilled Trades | STAGE RIGGING & DRAPERY | Construction | In-Progress | 6/7/2017 | DOES |  | DOES | 29494 | 0 | DSF0000816488
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/7/2017 | DOES |  | DOES | 152778 | 0 | DSF0000866056
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/12/2023 | DOES | 11/6/2023 | DOES | 489606 | 441490 | DSF0001035113
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/30/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085040
31 | R451 | CURTIS HS - STATEN ISLAND | DOE - RESOA | RESO A ATHLETIC FIELDS | Construction | In-Progress | 12/27/2021 | DOER |  | DOER | 2636300 | 8207 | DSF0000951660
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/2/2022 | 7/15/2022 | 1/3/2023 | 117350 | 135638 | 135638 | DSF0001034391, DSF0001078574
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | In-Progress | 1/6/2023 | 6/26/2023 |  | 586752 | 586752 | 217700 | DSF0001034391, DSF0001078574
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | 13201932 | 13201932 | 87274 | DSF0001034391, DSF0001078574
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | CM,F&E | PNS | PNS | PNS | PNS | 821454 | 821454 | 55209 | DSF0001034391, DSF0001078574
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY - PERM FIX FOR RED DOT 131992 / EXTERIOR DOORS | Scope | Complete | 10/20/2022 | 3/10/2023 | 12/1/2023 | 152908 | 153961 | 153961 | DSF0001134229, DSF0001106553
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY - PERM FIX FOR RED DOT 131992 / EXTERIOR DOORS | Design | In-Progress | 12/12/2023 | 5/14/2024 |  | 709531 | 709531 | 153743 | DSF0001134229, DSF0001106553
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY - PERM FIX FOR RED DOT 131992 / EXTERIOR DOORS | Construction | PNS | PNS | PNS | PNS | 11215228 | 11215228 | 32225 | DSF0001134229, DSF0001106553
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY - PERM FIX FOR RED DOT 131992 / EXTERIOR DOORS | CM,F&E | PNS | PNS | PNS | PNS | 1166245 | 1166245 | 24138 | DSF0001134229, DSF0001106553
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EMERGENCY GENERATOR | Scope | Complete | 3/27/2024 | 7/29/2024 | 3/27/2024 | 47368 | 40864 | 18955 | DSF0001106539
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EMERGENCY GENERATOR | Design | In-Progress | 3/27/2024 | 8/27/2024 |  | 221052 | 221052 | 6217 | DSF0001106539
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EMERGENCY GENERATOR | Construction | PNS | PNS | PNS | PNS | 3505250 | 3505250 | 12718 | DSF0001106539
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EMERGENCY GENERATOR | CM,F&E | PNS | PNS | PNS | PNS | 347367 | 347367 | 22541 | DSF0001106539
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2/27/2018 | 1/6/2020 | 1/3/2020 | 135212 | 242418 | 242418 | DSF0000883080, DSF0000912617, DSF0000912616
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 1/8/2020 | 6/9/2020 | 6/30/2020 | 667839 | 1495295 | 904154 | DSF0000883080, DSF0000912617, DSF0000912616
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Construction | In-Progress | 6/14/2021 | 6/13/2023 |  | 14315154 | 13780041 | 12624722 | DSF0000883080, DSF0000912617, DSF0000912616
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | CM,F&E | In-Progress | 6/14/2021 | 6/13/2023 |  | 1008151 | 1028231 | 1011806 | DSF0000883080, DSF0000912617, DSF0000912616
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA Emergency Response | SIDEWALK BRIDGING | Construction | In-Progress | 4/6/2011 | EMER |  | EMER |  | 0 | SCA0000016521
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION- SPALLED CRACKED CONCRETE | Construction | In-Progress | 9/7/2022 | EMER |  | EMER | 3526500 | 1988751 | SCA0000071443
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA IEH | PO18-REMOVE APPROX 5 FT OF ACM PIPE COVERING ON 8 INCH PIPE LOCATED IN ROOM D010 STORAGE ROOM. PIPE | Construction | Complete | 8/10/2024 | IEH | 8/11/2024 | IEH | 0 | 0 | SCA0000073276
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/8/2024 | DIIR |  | DIIR | 75000 | 0 | DSF0001034011
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 50000 | 49812 | DSF0001086671
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001036159
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001086672
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0 | DSF0001113291
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 9/23/2024 | DOES |  | DOES | 212371 | 0 | DSF0001034267
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/19/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085041
31 | R455 | R721 SPED - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/31/2024 | DOES |  | DOES | 820398 | 0 | DSF0001085766
31 | R456 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | NEW FIELDHOUSE BUILDING | Scope | Complete | 3/2/2022 | 6/30/2022 | 1/3/2023 | 243495 | 213388 | 192185 | DSF0001027839
31 | R456 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | NEW FIELDHOUSE BUILDING | Design | Complete | 1/10/2023 | 6/12/2023 | 5/14/2024 | 1217475 | 489892 | 443677 | DSF0001027839
31 | R456 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | NEW FIELDHOUSE BUILDING | Construction | PNS | PNS | PNS | PNS | 27393188 | 27393188 | 408572 | DSF0001027839
31 | R456 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | NEW FIELDHOUSE BUILDING | CM,F&E | PNS | PNS | PNS | PNS | 1704465 | 1704465 | 283585 | DSF0001027839
31 | R456 | TOTTENVILLE HS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ATHLETIC FIELDS | Construction | In-Progress | 8/31/2022 | DOER |  | DOER | 760164 | 0 | DSF0000961459
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 10/26/2023 | 2/26/2024 | 1/31/2024 | 0 | 28759 | 28759 | DSF0001086673
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 53806 | 25047 | 3119 | DSF0001086673
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 789154 | 1961037 | 3247 | DSF0001086673
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 53806 | 133707 | 9451 | DSF0001086673
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 11/7/2023 | 3/8/2024 | 1/31/2024 | 0 | 95 | 95 | DSF0001087260
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 494 | 399 | 382 | DSF0001087260
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 7246 | 58777 | 0 | DSF0001087260
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 494 | 4008 | 1119 | DSF0001087260
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | Fast Track Projects | PATH OF TRAVEL LSP ROOM CONVERSION | Construction | In-Progress | 1/14/2022 | FTK |  | FTK | 157776 | 134763 | DSF0000912260
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0000961461
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 202093 | 0 | DSF0001032985
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0 | DSF0001036160
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | Complete | 1/31/2024 | DOER | 9/24/2024 | DOER | 152389 |  | DSF0001086675
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/7/2017 | DOES |  | DOES | 277650 | 0 | DSF0000866067
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - Skilled Trades | ACE FAN SYSTEM UPGRADE | Construction | In-Progress | 2/3/2020 | DOES |  | DOES | 39427 | 182184 | DSF0000905995
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/14/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001085042
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/20/2024 | DOES |  | DOES | 857963 | 0 | DSF0001085767
31 | R461 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Scope | Complete | 3/3/2021 | 4/1/2021 | 10/19/2021 | 0 | 74623 | 74623 | DSF0000913158
31 | R461 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Design | Complete | 1/14/2022 | 6/16/2022 | 5/13/2022 | 280864 | 185436 | 185436 | DSF0000913158
31 | R461 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Construction | Complete | 7/10/2023 | 7/8/2024 | 7/8/2024 | 4119341 | 3821370 | 3525551 | DSF0000913158
31 | R461 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | CM,F&E | Complete | 7/10/2023 | 7/8/2024 | 7/8/2024 | 280864 | 102685 | 102592 | DSF0000913158
31 | R461 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0 | DSF0001113292
31 | R462 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/5/2024 | IEH | 8/16/2024 | IEH | 0 | 0 | SCA0000073231
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/21/2024 | 3/26/2025 | 11/25/2024 | 0 | 1785 | 1785 | DSF0001113293
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Design | In-Progress | 11/25/2024 | 5/22/2025 |  | 24000 | 22215 | 7139 | DSF0001113293
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 352000 | 352000 | 0 | DSF0001113293
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 24000 | 24000 | 81 | DSF0001113293
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY22 RESO A (MA) CULINARY KITCHEN / PATH OF TRAVEL RESO A (MA) CULINARY KITCHEN | Scope | Complete | 3/10/2022 | 2/24/2023 | 1/30/2023 | 0 | 35209 | 35209 | DSF0001032957, DSF0001083680
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY22 RESO A (MA) CULINARY KITCHEN / PATH OF TRAVEL RESO A (MA) CULINARY KITCHEN | Design | Complete | 1/31/2023 | 5/31/2023 | 2/13/2023 | 240001 | 124968 | 124968 | DSF0001032957, DSF0001083680
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY22 RESO A (MA) CULINARY KITCHEN / PATH OF TRAVEL RESO A (MA) CULINARY KITCHEN | Construction | In-Progress | 8/7/2023 | 8/5/2024 |  | 3520001 | 2699046 | 1411439 | DSF0001032957, DSF0001083680
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY22 RESO A (MA) CULINARY KITCHEN / PATH OF TRAVEL RESO A (MA) CULINARY KITCHEN | CM,F&E | In-Progress | 8/7/2023 | 8/5/2024 |  | 240001 | 453235 | 442612 | DSF0001032957, DSF0001083680
31 | R470 | CONCORD HS - R | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113682
31 | R470 | CONCORD HS - R | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113682
31 | R470 | CONCORD HS - R | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113682
31 | R470 | CONCORD HS - R | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113682
31 | R470 | CONCORD HS - R | Fast Track Projects | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 104281 | 7244 | DSF0001035354
31 | R470 | CONCORD HS - R | DOE - RESOA | FY19 RESO A ROOM CONVERSION | Construction | In-Progress | 7/30/2021 | DOER |  | DOER | 59574 | 0 | DSF0000890472
31 | R470 | CONCORD HS - R | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/26/2019 | DOES |  | DOES | 199770 | 0 | DSF0000889639
31 | R470 | CONCORD HS - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/23/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085043
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/14/2021 | 11/12/2021 | 7/30/2021 | 3795 | 7500 | 7500 | DSF0000960785
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/30/2021 | 1/28/2022 | 12/29/2021 | 17080 | 30001 | 30001 | DSF0000960785
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 5/12/2022 | 3/7/2023 |  | 220137 | 207993 | 183248 | DSF0000960785
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 5/12/2022 | 3/7/2023 |  | 223893 | 263234 | 263234 | DSF0000960785
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/20/2017 | EMER |  | EMER | 35275 | 35275 | SCA0000047395
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA IEH | PO18-CAFETERIA ABATE APPROX 831 SQ. FT. CEILING TILES - ROOM 406A, NURSE'S OFFICE ABATE APPROX 6 SQ. | Construction | Complete | 7/30/2024 | IEH | 9/10/2024 | IEH | 0 | 0 | SCA0000073203
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 7/18/2022 | FTK |  | FTK | 3616008 | 3072300 | DSF0001034172
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | Fast Track Projects | LSP VENTILATION/DUST COLLECTION SYSTEM | Construction | In-Progress | 8/31/2018 | FTK |  | FTK | 258754 | 239924 | DSF0000838607
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 490000 | 471989 | DSF0001086676
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DOE - RESOA | RESO A ROOM CONVERSION | Construction | In-Progress | 8/21/2023 | DOER |  | DOER | 32287 | 0 | DSF0000844924
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DOE - RESOA | FY20 RESO A ROOFTOP PLAYGROUND | Construction | In-Progress | 1/12/2024 | DOER |  | DOER | 250000 | 0 | DSF0000913159
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 4911 | 0 | DSF0000961458
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/26/2018 | DOES |  | DOES | 324637 | 0 | DSF0000889370
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/28/2024 | DOES |  | DOES | 65832 | 0 | DSF0001085044
31 | R722 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 4/7/2022 | 4/7/2022 | 4/7/2022 | 95738 | 109156 | 105022 | DSF0000961149
31 | R722 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 5/13/2022 | 11/15/2022 | 11/14/2022 | 478689 | 233390 | 198828 | DSF0000961149
31 | R722 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | Construction | In-Progress | 11/15/2023 | 11/13/2024 |  | 10770495 | 11071399 | 9425713 | DSF0000961149
31 | R722 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | CM,F&E | In-Progress | 11/15/2023 | 11/13/2024 |  | 670164 | 539171 | 517508 | DSF0000961149
31 | R722 | R721 SPED - STATEN ISLAND | SCA Emergency Response | TEMPORARY BOILER | Construction | In-Progress | 4/10/2017 | EMER |  | EMER |  | 0 | DSF0000866179
31 | R722 | R721 SPED - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 9/6/2022 | EMER |  | EMER | 721259 | 686801 | SCA0000071246
31 | R722 | R721 SPED - STATEN ISLAND | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 308330 | 0 | DSF0000960276
31 | R801 | PATHWAYS TO GRADUATION - CITYWIDE | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/3/2024 | DOES | 9/4/2024 | DOES | 65832 | 189 | DSF0001085558
31 | R825 | R025 SPED - STATEN ISLAND | SCA IEH | PO18-ASSIST PLUMBERS: TEST CONCRETE FLOOR APPXOX. 3 IN X 3 IN AREA MARKED WITH A RED X. IF POSITIVE, | Construction | Complete | 6/28/2024 | IEH | 7/27/2024 | IEH | 0 | 0 | SCA0000073101
31 | R825 | R025 SPED - STATEN ISLAND | SCA IEH | PO18-ABATE PIPE INSULATION IN THE SENSORY ROOM, SPACE ID #1006 C.E. | Construction | Complete | 9/8/2024 | IEH | 9/8/2024 | IEH | 0 | 0 | SCA0000073361
31 | R825 | R025 SPED - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0 | DSF0001033973
31 | R825 | R025 SPED - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/23/2024 | DIIR | 4/18/2024 | DIIR | 279019 | 279019 | DSF0001036162
31 | R825 | R025 SPED - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 190000 | 0 | DSF0001086677
31 | R825 | R025 SPED - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0 | DSF0001032984
31 | R826 | R025 SPED - STATEN ISLAND | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/8/2024 | IEH | 8/23/2024 | IEH | 0 | 0 | SCA0000073260
31 | R826 | P.S. 3 - STATEN ISLAND | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 10/25/2017 | DOES | 4/8/2019 | DOES | 10726 |  | DSF0000866962
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | Scope | Complete | 10/2/2023 | 2/13/2024 | 11/9/2023 | 15600 | 20462 | 3702 | DSF0001106667
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | Design | Complete | 11/15/2023 | 4/18/2024 | 3/7/2024 | 70200 | 62718 | 14807 | DSF0001106667
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | Construction | In-Progress | 7/19/2024 | 7/18/2025 |  | 904800 | 1098499 | 68301 | DSF0001106667
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | CM,F&E | In-Progress | 7/19/2024 | 7/18/2025 |  | 167700 | 101610 | 87186 | DSF0001106667
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/29/2022 | 7/27/2022 | 4/13/2022 | 1600 | 3727 | 3727 | DSF0001034377
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/13/2022 | 10/6/2022 | 7/20/2022 | 7200 | 14908 | 14908 | DSF0001034377
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | Complete | 3/24/2023 | 2/16/2024 | 9/19/2024 | 92800 | 83953 | 70366 | DSF0001034377
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | Complete | 3/24/2023 | 2/16/2024 | 9/19/2024 | 122798 | 126821 | 69607 | DSF0001034377
31 | R829 | P.S. 65 - STATEN ISLAND | SCA Emergency Response | EMERGENCY- CLOCK TOWER @ R829 | Construction | In-Progress | 8/9/2023 | EMER |  | EMER |  | 0 | SCA0000072210
31 | R829 | P.S. 65 - STATEN ISLAND | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001086678
31 | R829 | P.S. 65 - STATEN ISLAND | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113295
31 | R829 | P.S. 65 - STATEN ISLAND | DOE - Skilled Trades | RTU UPGRADE | Construction | In-Progress | 8/14/2023 | DOES |  | DOES | 293466 | 0 | DSF0001085795
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | Scope | Complete | 7/22/2019 | 12/6/2019 | 11/26/2019 | 58970 | 80396 | 80396 | DSF0000906107, DSF0000960661
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | Design | Complete | 11/26/2019 | 4/29/2020 | 6/30/2020 | 294850 | 297132 | 277317 | DSF0000906107, DSF0000960661
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | Construction | In-Progress | 9/13/2023 | 6/3/2025 |  | 6634125 | 6999583 | 5713770 | DSF0000906107, DSF0000960661
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | CM,F&E | In-Progress | 9/13/2023 | 6/3/2025 |  | 413675 | 594802 | 573707 | DSF0000906107, DSF0000960661
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | Scope | Complete | 12/22/2014 | 3/25/2015 | 4/15/2015 | 0 | 25380 | 25380 | DSF0000800366
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | Design | Complete | 5/11/2016 | 9/26/2016 | 9/2/2016 | 0 | 52114 | 52114 | DSF0000800366
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | Construction | Complete | 4/7/2017 | 1/1/2018 | 10/24/2024 | 0 | 197682 | 197626 | DSF0000800366
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | CM,F&E | Complete | 4/7/2017 | 1/1/2018 | 10/24/2024 | 0 | 59224 | 59224 | DSF0000800366
31 | R831 | P.S. 74 - STATEN ISLAND | SCA Furniture & Equipment | FY25 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 96000 | 96000 | 0 | DSF0001113297
31 | R831 | P.S. 74 - STATEN ISLAND | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0 | DSF0000799350
31 | R831 | P.S. 74 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001113296
31 | R831 | P.S. 74 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/21/2024 | DOES | 10/16/2024 | DOES | 65832 | 5685 | DSF0001084464
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 3/10/2023 | 6/8/2023 | 7/5/2023 | 16559 | 31734 | 31734 | DSF0001083895
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | In-Progress | 7/14/2023 | 11/30/2023 |  | 82794 | 82794 | 34051 | DSF0001083895
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | 1862861 | 1862861 | 70063 | DSF0001083895
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | CM,F&E | PNS | PNS | PNS | PNS | 115911 | 115911 | 81787 | DSF0001083895
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/11/2022 | 9/9/2022 | 6/7/2022 | 3340 | 4977 | 4977 | DSF0001034565
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/7/2022 | 12/2/2022 | 8/31/2022 | 15030 | 19908 | 19908 | DSF0001034565
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 5/31/2023 | 4/24/2024 |  | 193720 | 175595 | 158924 | DSF0001034565
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 5/31/2023 | 4/24/2024 |  | 149421 | 140200 | 90445 | DSF0001034565
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | Fast Track Projects | LSP FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/17/2023 | FTK |  | FTK | 72441 | 66632 | DSF0001036123
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033982
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 11/30/2023 | DOER |  | DOER | 100415 | 0 | DSF0000913114
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 63898 | 0 | DSF0001086680
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 4/26/2019 | DOES |  | DOES | 212656 | 0 | DSF0000889638
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - Skilled Trades | INTERIOR SPACES | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 291404 | 0 | DSF0001112188
31 | R861 | P.S. 861 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/30/2021 | 10/29/2021 | 2/17/2022 | 0 | 12540 | 12540 | DSF0000961446
31 | R861 | P.S. 861 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2/17/2022 | 7/5/2022 | 5/11/2022 | 21000 | 34494 | 34494 | DSF0000961446
31 | R861 | P.S. 861 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | Complete | 12/1/2023 | 9/25/2024 | 4/30/2024 | 308000 | 251015 | 210050 | DSF0000961446
31 | R861 | P.S. 861 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 12/1/2023 | 9/25/2024 | 4/30/2024 | 21000 | 25353 | 24870 | DSF0000961446
31 | R861 | P.S. 861 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/8/2024 | DIIR |  | DIIR | 129000 | 0 | DSF0001086681
31 | R861 | P.S. 861 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001113298
31 | R861 | P.S. 861 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/7/2024 | DOES |  | DOES | 50832 | 0 | DSF0001084696
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | Scope | Complete | 1/31/2019 | 6/3/2019 | 10/12/2022 | 271750 | 231999 | 231999 | DSF0000866758, DSF0000912289, DSF0001078791, DSF0001078779
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | Design | Complete | 10/19/2022 | 3/24/2023 | 9/11/2023 | 1358750 | 1149164 | 673620 | DSF0000866758, DSF0000912289, DSF0001078791, DSF0001078779
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | Construction | In-Progress | 7/2/2024 | 7/1/2026 |  | 30571876 | 28896286 | 2245112 | DSF0000866758, DSF0000912289, DSF0001078791, DSF0001078779
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | CM,F&E | In-Progress | 7/2/2024 | 7/1/2026 |  | 1902250 | 468965 | 423275 | DSF0000866758, DSF0000912289, DSF0001078791, DSF0001078779
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/29/2023 | 10/30/2023 | 10/10/2023 | 18500 | 16068 | 16068 | DSF0001083791
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/11/2023 | 3/12/2024 | 2/15/2024 | 83250 | 89794 | 62038 | DSF0001083791
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Construction | In-Progress | 8/14/2024 | 9/17/2025 |  | 1073000 | 1011295 | 51185 | DSF0001083791
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | CM,F&E | In-Progress | 8/14/2024 | 9/17/2025 |  | 198875 | 125544 | 25644 | DSF0001083791
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 7/18/2023 | 12/4/2023 | 11/14/2023 | 22450 | 33462 | 33462 | DSF0001078785
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 11/24/2023 | 4/26/2024 | 4/30/2024 | 112250 | 81245 | 71982 | DSF0001078785
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | REINFORCING SUPPORT ELEMENTS | Construction | PNS | PNS | PNS | PNS | 2525625 | 2525625 | 43667 | DSF0001078785
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | REINFORCING SUPPORT ELEMENTS | CM,F&E | PNS | PNS | PNS | PNS | 157150 | 157150 | 51433 | DSF0001078785
31 | R880 | P.S. 80 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/12/2020 | EMER |  | EMER | 2838547 | 2838547 | SCA0000062467
31 | R880 | P.S. 80 - STATEN ISLAND | SCA IEH | PO18-ASSIST ELECTRICICANS: TEST VCT FLOOR AND ADHESIVES FOR ACM. ELECTRICIANS NEED TO DRILL FLOOR MO | Construction | Complete | 7/31/2024 | IEH | 8/10/2024 | IEH | 0 | 0 | SCA0000073211
31 | R880 | P.S. 80 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0 | DSF0001086682
31 | R880 | P.S. 80 - STATEN ISLAND | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 7/19/2018 | DOES |  | DOES | 436958 | 0 | DSF0000889371
31 | R880 | P.S. 80 - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 4/11/2023 | DOES | 11/6/2023 | DOES | 710012 | 668345 | DSF0001034907
31 | R880 | P.S. 80 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/10/2024 | DOES | 9/25/2024 | DOES | 65832 | 15393 | DSF0001084465
31 | R883 | P.S. 80 - STATEN ISLAND | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 12/13/2024 | IEH | 12/31/2024 | IEH | 0 | 0 | SCA0000073671
31 | R883 | P.S. 80 - STATEN ISLAND | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 12/16/2024 | IEH | 12/26/2024 | IEH | 0 | 0 | SCA0000073714
31 | R884 | R373 SPED - STATEN ISLAND | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 3/5/2021 | 7/20/2021 | 7/27/2021 | 43048 | 70663 | 70663 | DSF0000951921, DSF0000951922, DSF0000951923
31 | R884 | R373 SPED - STATEN ISLAND | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Design | PNS | PNS | PNS | PNS | 208668 | 208668 | 2148 | DSF0000951921, DSF0000951922, DSF0000951923
31 | R884 | R373 SPED - STATEN ISLAND | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 4126553 | 4126553 | 262 | DSF0000951921, DSF0000951922, DSF0000951923
31 | R884 | R373 SPED - STATEN ISLAND | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 350626 | 350626 | 15736 | DSF0000951921, DSF0000951922, DSF0000951923
31 | R886 | P.S. 80 - STATEN ISLAND | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 10/2/2019 | FTK |  | FTK | 1308670 | 1298589 | DSF0000912530
31 | R973 | R373 SPED - STATEN ISLAND | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/9/2024 | IEH | 8/27/2024 | IEH | 0 | 0 | SCA0000073271
31 | RALZ | RICHMOND PREPARATORY CHARTER SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0 | DSF0001086683
31 | RALZ | RICHMOND PREPARATORY CHARTER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113299
31 | RAMT | STATEN ISLAND HEBREW PUBLIC CHARTER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0 | DSF0001113300
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 4/8/2021 | 8/23/2021 | 10/18/2021 | 139471 | 155339 | 155339 | DSF0000961141
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 10/26/2021 | 4/15/2022 | 8/4/2023 | 697357 | 449947 | 391464 | DSF0000961141
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Construction | PNS | PNS | PNS | PNS | 15690539 | 15690539 | 46009 | DSF0000961141
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | CM,F&E | PNS | PNS | PNS | PNS | 976300 | 976300 | 100463 | DSF0000961141
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 4/9/2021 | 9/9/2021 | 7/1/2021 | 78996 | 85436 | 85436 | DSF0001008797, DSF0000985437
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/14/2021 | 12/15/2021 | 11/18/2021 | 394980 | 462169 | 388792 | DSF0001008797, DSF0000985437
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | In-Progress | 11/7/2022 | 11/5/2024 |  | 8887050 | 8952258 | 7325302 | DSF0001008797, DSF0000985437
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | In-Progress | 11/7/2022 | 11/5/2024 |  | 554494 | 415960 | 374455 | DSF0001008797, DSF0000985437
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / ROOFTOP EXHAUST FAN REPLACEMENT | Scope | Complete | 5/18/2021 | 10/1/2021 | 8/3/2022 | 136225 | 211772 | 199403 | DSF0000985441, DSF0000985442, DSF0001060834
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / ROOFTOP EXHAUST FAN REPLACEMENT | Design | Complete | 9/13/2022 | 2/16/2023 | 3/30/2023 | 681124 | 663189 | 393176 | DSF0000985441, DSF0000985442, DSF0001060834
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / ROOFTOP EXHAUST FAN REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 15325294 | 15325294 | 201095 | DSF0000985441, DSF0000985442, DSF0001060834
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / ROOFTOP EXHAUST FAN REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 953573 | 953573 | 50600 | DSF0000985441, DSF0000985442, DSF0001060834
32 | K045 | P.S. 45 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 10 LINEAR FEET OF ACM FROM PIPE IN ROOM# 3221B | Construction | Complete | 9/1/2024 | IEH | 9/4/2024 | IEH | 0 | 0 | SCA0000073341
32 | K045 | P.S. 45 - BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/12/2024 | DOER |  | DOER | 50000 | 0 | DSF0001085954
32 | K045 | P.S. 45 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/13/2024 | DOES | 11/25/2024 | DOES | 65832 |  | DSF0001084586
32 | K075 | P.S. 75 - BROOKLYN | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADE | Construction | Complete | 3/8/2021 | DOER | 12/28/2021 | DOER | 153231 | 152320 | DSF0000913179
32 | K075 | P.S. 75 - BROOKLYN | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 189867 | 0 | DSF0001035404
32 | K075 | P.S. 75 - BROOKLYN | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 120000 | 0 | DSF0001112554
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 7/1/2022 | 11/17/2022 | 2/28/2023 | 67168 | 149264 | 147061 | DSF0001010692, DSF0001010693, DSF0001061379
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 3/9/2023 | 8/9/2023 | 8/25/2023 | 324573 | 389412 | 286874 | DSF0001010692, DSF0001010693, DSF0001061379
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | In-Progress | 10/15/2024 | 4/2/2027 |  | 6328101 | 5853089 | 150169 | DSF0001010692, DSF0001010693, DSF0001061379
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | In-Progress | 10/15/2024 | 4/2/2027 |  | 554698 | 125083 | 118803 | DSF0001010692, DSF0001010693, DSF0001061379
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | Scope | Complete | 7/20/2021 | 2/23/2022 | 3/2/2023 | 0 | 11742 | 11742 | DSF0001007764, DSF0001008244
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | Design | Complete | 3/3/2023 | 7/6/2023 | 3/20/2023 | 39000 | 63447 | 44423 | DSF0001007764, DSF0001008244
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | Construction | Complete | 7/21/2023 | 6/14/2024 | 9/19/2024 | 572000 | 478092 | 386211 | DSF0001007764, DSF0001008244
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | CM,F&E | Complete | 7/21/2023 | 6/14/2024 | 9/19/2024 | 39000 | 58084 | 52885 | DSF0001007764, DSF0001008244
32 | K086 | P.S. 86 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION & REPAIRS- FALLING MASONRY @ K086 | Construction | In-Progress | 9/5/2023 | EMER |  | EMER | 477080 | 0 | SCA0000072273
32 | K086 | P.S. 86 - BROOKLYN | SCA IEH | PO18-TEST ALL FLOOR LAYERS FOR ACM APPROXIMATELY 30SQ FT OF LOOSE FLOOR TILES IN CAFETERIA NEED R/R | Construction | Complete | 1/9/2024 | IEH | 12/30/2024 | IEH | 0 | 0 | SCA0000072632
32 | K086 | P.S. 86 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE ACM MATERIALS IN ROOM 300 AND 302 1. WALL PLASTER -- 560SF 2. FLOOR, UPTO CONC | Construction | Complete | 11/20/2024 | IEH | 12/16/2024 | IEH | 0 | 0 | SCA0000073627
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Scope | Complete | 6/12/2023 | 10/27/2023 | 11/24/2023 | 123700 | 281317 | 260579 | DSF0001061687, DSF0001089420, DSF0001089423
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Design | Complete | 12/6/2023 | 5/8/2024 | 5/3/2024 | 618501 | 512890 | 404215 | DSF0001061687, DSF0001089420, DSF0001089423
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Construction | In-Progress | 9/3/2024 | 9/2/2026 |  | 13916250 | 12618322 | 299770 | DSF0001061687, DSF0001089420, DSF0001089423
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | CM,F&E | In-Progress | 9/3/2024 | 9/2/2026 |  | 865899 | 93367 | 92361 | DSF0001061687, DSF0001089420, DSF0001089423
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112566
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 39000 | 39000 | 0 | DSF0001112566
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 572000 | 572000 | 0 | DSF0001112566
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 39000 | 39000 | 0 | DSF0001112566
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113565
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113565
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113565
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113565
32 | K106 | P.S. 106 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR WALL AND CEILING LOC: NURSE'S OFFICE, RM 117 METAL CEILING TILES COLLAPSED | Construction | Complete | 10/1/2024 | IEH | 10/5/2024 | IEH | 0 | 0 | SCA0000073462
32 | K106 | P.S. 106 - BROOKLYN | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 11/11/2021 | FTK |  | FTK | 293531 | 186065 | DSF0000937823
32 | K106 | P.S. 106 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/1/2022 | DOES |  | DOES | 60530 | 0 | DSF0000866103
32 | K111 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 7/11/2023 | 11/27/2023 | 11/14/2023 | 82281 | 86309 | 86308 | DSF0001061765, DSF0001111836, DSF0001111835
32 | K111 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 11/15/2023 | 4/18/2024 | 4/26/2024 | 408683 | 430909 | 317537 | DSF0001061765, DSF0001111836, DSF0001111835
32 | K111 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Construction | In-Progress | 7/17/2024 | 1/2/2027 |  | 8960023 | 8196083 | 138124 | DSF0001061765, DSF0001111836, DSF0001111835
32 | K111 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | CM,F&E | In-Progress | 7/17/2024 | 1/2/2027 |  | 596373 | 115905 | 115528 | DSF0001061765, DSF0001111836, DSF0001111835
32 | K111 | I.S. 347 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113566
32 | K111 | I.S. 347 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113566
32 | K111 | I.S. 347 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113566
32 | K111 | I.S. 347 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113566
32 | K111 | I.S. 347 - BROOKLYN | DIIT - RESOA | FY15 RESO A SECURITY CAMERA UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 210150 | 0 | DSF0000822010
32 | K111 | I.S. 347 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 10/18/2024 | DIIR | 100000 | 100000 | DSF0000913750
32 | K111 | I.S. 349 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0 | DSF0001033551
32 | K111 | I.S. 349 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001035423
32 | K111 | I.S. 347 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 185079 | 0 | DSF0001085976
32 | K111 | I.S. 347 - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0 | DSF0001112570
32 | K111 | I.S. 349 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/13/2024 | DOES | 8/22/2024 | DOES | 65832 |  | DSF0001084735
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 5/16/2024 | 10/2/2024 | 11/1/2024 | 95463 | 147113 | 125342 | DSF0001089615, DSF0001089618
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | Design | In-Progress | 11/20/2024 | 4/24/2025 |  | 445495 | 445495 | 15097 | DSF0001089615, DSF0001089618
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | Construction | PNS | PNS | PNS | PNS | 7064269 | 7064269 | 24425 | DSF0001089615, DSF0001089618
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | CM,F&E | PNS | PNS | PNS | PNS | 700062 | 700062 | 26249 | DSF0001089615, DSF0001089618
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001112572
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112572
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 660000 | 660000 | 0 | DSF0001112572
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 45000 | 45000 | 0 | DSF0001112572
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113568
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113568
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113568
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001113568
32 | K116 | P.S. 116 - BROOKLYN | SCA IEH | PO18-ABATE AND COMPLETELY REMOVE BOILER #1 INSULATION ALL INSULATION IS ACM PARTS ARE OBSOLETE. ACM | Construction | Complete | 4/15/2024 | IEH | 9/30/2024 | IEH | 0 | 0 | SCA0000072932
32 | K116 | P.S. 116 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REPAIR CEILING IN 3RD FLOOR SLOP SINK (SPACE ID 4314) APPROX 50 SQ FT | Construction | In-Progress | 11/19/2024 | IEH |  | IEH | 0 | 0 | SCA0000073620
32 | K116 | P.S. 116 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING. APPROX 40 SQ FT LOCATION: STORAGE ROOM IN CLASSROOM (SPACE ID 5408A) | Construction | Complete | 12/5/2024 | IEH | 12/6/2024 | IEH | 0 | 0 | SCA0000073676
32 | K123 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | Scope | Complete | 3/26/2021 | 8/10/2021 | 11/2/2021 | 175410 | 173105 | 173105 | DSF0001008654, DSF0001011282
32 | K123 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | Design | Complete | 11/3/2021 | 4/25/2022 | 10/5/2022 | 877050 | 603901 | 485358 | DSF0001008654, DSF0001011282
32 | K123 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | Construction | In-Progress | 9/15/2023 | 3/2/2026 |  | 19733625 | 18424410 | 3075419 | DSF0001008654, DSF0001011282
32 | K123 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | CM,F&E | In-Progress | 9/15/2023 | 3/2/2026 |  | 1229197 | 678024 | 673960 | DSF0001008654, DSF0001011282
32 | K123 | P.S. 123 - BROOKLYN | SCA Furniture & Equipment | FY21 RESO A MOBILE SCIENCE LABS | F&E | PNS | PNS | PNS | PNS | 240000 | 240000 | 0 | DSF0000961220
32 | K123 | P.S. 123 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | Complete | 7/20/2023 | DOER | 5/23/2024 | DOER | 206078 |  | DSF0001033478
32 | K123 | P.S. 123 - BROOKLYN | DOE - RESOA | FY24 RESO A LEARNING GARDEN | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0 | DSF0001085982
32 | K123 | P.S. 123 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112573
32 | K123 | P.S. 123 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/8/2022 | DOES |  | DOES | 64265 | 0 | DSF0000866104
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | Scope | Complete | 4/7/2021 | 8/6/2021 | 10/26/2021 | 11796 | 20792 | 20792 | DSF0000938330
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | Design | Complete | 11/1/2021 | 3/22/2022 | 3/4/2022 | 58979 | 114041 | 108689 | DSF0000938330
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | Construction | Complete | 5/15/2023 | 5/3/2025 | 10/18/2024 | 1327022 | 1402330 | 1369272 | DSF0000938330
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | CM,F&E | Complete | 5/15/2023 | 5/3/2025 | 10/18/2024 | 82570 | 272402 | 269387 | DSF0000938330
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/7/2023 | 12/7/2023 | 9/18/2023 | 5000 | 6134 | 6134 | DSF0001035007
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/18/2023 | 3/18/2024 | 11/15/2023 | 22500 | 24538 | 24538 | DSF0001035007
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 4/26/2024 | 3/21/2025 |  | 290000 | 261013 | 2413 | DSF0001035007
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 4/26/2024 | 3/21/2025 |  | 53750 | 31797 | 4797 | DSF0001035007
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Scope | Complete | 1/24/2024 | 4/23/2024 | 6/6/2024 | 0 | 2831 | 2831 | DSF0001085993
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Design | Complete | 6/18/2024 | 11/20/2024 | 10/16/2024 | 15000 | 11325 | 11325 | DSF0001085993
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | 220000 | 220000 | 162654 | DSF0001085993
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 15000 | 18683 | 18683 | DSF0001085993
32 | K145 | P.S. 145 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR COLLAPSED WALL IN CLASSROOM 401. WALL COLLAPSED EXPOSING BRICK WALL, AND CRACK | Construction | Complete | 7/18/2024 | IEH | 8/11/2024 | IEH | 0 | 0 | SCA0000073153
32 | K145 | P.S. 145 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION IN THE SPRINKLER ROOM PIPES HAVE BEEN MAKED | Construction | Complete | 8/30/2024 | IEH | 8/31/2024 | IEH | 0 | 0 | SCA0000073340
32 | K145 | P.S. 145 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOORING ON ALL THE REQUESTED DAMAGED LOCATION REPORT ATTACHED WITHIN THE EMA | Construction | Complete | 9/16/2024 | IEH | 9/30/2024 | IEH | 0 | 0 | SCA0000073377
32 | K145 | P.S. 145 - BROOKLYN | SCA IEH | PO18-ABATE AND DRILL HOLES IN KITCHEN AND ELECTRICAL ROOM 1/2' DIA 2' DEEP HOLES - 23 (BY MISTAKE ON | Construction | Complete | 10/18/2024 | IEH | 11/16/2024 | IEH | 0 | 0 | SCA0000073518
32 | K145 | P.S. 145 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR PIPE INSUALATION AND DUCT INSULATION IN CAFETERIA | Construction | Complete | 10/31/2024 | IEH | 11/5/2024 | IEH | 0 | 0 | SCA0000073564
32 | K145 | P.S. 145 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN ROOM 208 APPROX. 4LF ************* ASSIGNED TO SCA ON 11/22 | Construction | Complete | 11/22/2024 | IEH | 11/24/2024 | IEH | 0 | 0 | SCA0000073641
32 | K145 | P.S. 145 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001112583
32 | K145 | P.S. 145 - BROOKLYN | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0 | DSF0001112584
32 | K145 | P.S. 145 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 1/21/2022 | DOES |  | DOES | 68837 | 0 | DSF0000866105
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | Scope | Complete | 11/18/2019 | 4/6/2020 | 3/10/2020 | 164682 | 231070 | 230893 | DSF0000893128, DSF0000938418, DSF0000960896, DSF0000938410, DSF0000960897
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | Design | Complete | 3/10/2020 | 8/7/2020 | 5/28/2020 | 814277 | 630911 | 630848 | DSF0000893128, DSF0000938418, DSF0000960896, DSF0000938410, DSF0000960897
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | Construction | Complete | 7/19/2021 | 1/4/2024 | 8/29/2024 | 17531338 | 16754141 | 16328497 | DSF0000893128, DSF0000938418, DSF0000960896, DSF0000938410, DSF0000960897
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | CM,F&E | Complete | 7/19/2021 | 1/4/2024 | 8/29/2024 | 1221262 | 1054267 | 999694 | DSF0000893128, DSF0000938418, DSF0000960896, DSF0000938410, DSF0000960897
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/20/2023 | 11/20/2023 | 8/2/2023 | 4700 | 6348 | 6348 | DSF0001035008
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/15/2023 | 21150 | 25398 | 25398 | DSF0001035008
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 4/26/2024 | 3/21/2025 |  | 272600 | 306123 | 62523 | DSF0001035008
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 4/26/2024 | 3/21/2025 |  | 75044 | 60560 | 35180 | DSF0001035008
32 | K151 | P.S. 151 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING PLASTER AND PIPE INSULATION ROOMS #103, 104, 107, 110, 202, 205, 206/2 | Construction | Complete | 7/24/2024 | IEH | 9/12/2024 | IEH | 0 | 0 | SCA0000073172
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/3/2020 | 10/1/2020 | 7/2/2020 | 3266 | 5625 | 5625 | DSF0000960738
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/2/2020 | 12/30/2020 | 5/19/2021 | 14697 | 22500 | 22500 | DSF0000960738
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 7/15/2022 | 5/10/2023 |  | 189428 | 168881 | 135802 | DSF0000960738
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | In-Progress | 7/15/2022 | 5/10/2023 |  | 174542 | 176957 | 89428 | DSF0000960738
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 1/24/2023 | 11/30/2023 | 12/27/2023 | 368600 | 363927 | 363761 | DSF0001083706, DSF0001083814, DSF0001111903, DSF0001090256
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 1/12/2024 | 10/3/2024 | 5/14/2024 | 1843001 | 1489203 | 1141476 | DSF0001083706, DSF0001083814, DSF0001111903, DSF0001090256
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Construction | In-Progress | 8/5/2024 | 8/3/2028 |  | 41467501 | 37906474 | 1153800 | DSF0001083706, DSF0001083814, DSF0001111903, DSF0001090256
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | CM,F&E | In-Progress | 8/5/2024 | 8/3/2028 |  | 2580201 | 500299 | 258736 | DSF0001083706, DSF0001083814, DSF0001111903, DSF0001090256
32 | K162 | I.S. 162 - BROOKLYN | SCA IEH | PO18-ROOM 407A, ABATE FLOOR TILES | Construction | Complete | 7/1/2024 | IEH | 9/12/2024 | IEH | 0 | 0 | SCA0000073109
32 | K162 | I.S. 162 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 100000 | 96631 | DSF0001033025
32 | K162 | I.S. 162 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/10/2021 | DOER |  | DOER | 1042466 | 0 | DSF0000913228
32 | K162 | I.S. 162 - BROOKLYN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/11/2022 | DOER |  | DOER | 216296 | 0 | DSF0001033492
32 | K162 | I.S. 162 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/30/2022 | DOES |  | DOES | 430227 | 0 | DSF0001008672
32 | K162 | I.S. 162 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/5/2022 | DOES |  | DOES | 68769 | 0 | DSF0001008963
32 | K162 | I.S. 162 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/21/2024 | DOES | 8/28/2024 | DOES | 65832 |  | DSF0001084738
32 | K162 | I.S. 162 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/1/2024 | DOES |  | DOES | 423370 | 0 | DSF0001085718
32 | K274 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | Scope | Complete | 1/22/2020 | 1/7/2022 | 12/15/2021 | 16909 | 65666 | 65586 | DSF0000940561, DSF0000960887
32 | K274 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | Design | Complete | 12/16/2021 | 4/19/2022 | 3/18/2022 | 76093 | 125092 | 106898 | DSF0000940561, DSF0000960887
32 | K274 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | Construction | In-Progress | 7/5/2022 | 7/4/2023 |  | 980757 | 2707043 | 2304344 | DSF0000940561, DSF0000960887
32 | K274 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | CM,F&E | In-Progress | 7/5/2022 | 7/4/2023 |  | 181778 | 407983 | 404689 | DSF0000940561, DSF0000960887
32 | K274 | P.S. 274 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONIC LAB | Construction | Complete | 7/1/2019 | DOER | 1/15/2021 | DOER | 290302 | 42631 | DSF0000890773
32 | K274 | P.S. 274 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 3/21/2024 | DOER |  | DOER | 250000 | 0 | DSF0001086062
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/8/2021 | 11/10/2022 | 1/25/2023 | 72818 | 112986 | 104954 | DSF0001014182, DSF0001035059, DSF0001036332
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 1/26/2023 | 5/25/2023 | 6/9/2023 | 362617 | 380610 | 317575 | DSF0001014182, DSF0001035059, DSF0001036332
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Construction | In-Progress | 7/8/2024 | 7/7/2026 |  | 8031738 | 7459727 | 143407 | DSF0001014182, DSF0001035059, DSF0001036332
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | CM,F&E | In-Progress | 7/8/2024 | 7/7/2026 |  | 520744 | 98790 | 98306 | DSF0001014182, DSF0001035059, DSF0001036332
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001008243
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 23994 | 23994 | 0 | DSF0001008243
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 351910 | 352000 | 0 | DSF0001008243
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 23994 | 24000 | 0 | DSF0001008243
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0 | DSF0001007763
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 6 | 6 | 0 | DSF0001007763
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 90 | 102 | 102 | DSF0001007763
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 6 | 383 | 383 | DSF0001007763
32 | K291 | I.S. 291 - BROOKLYN | Fast Track Projects | IDA GYM FLOOR REPLACEMENT | Construction | In-Progress | 6/3/2022 | FTK |  | FTK | 715971 | 702300 | SCA0000070541
32 | K291 | I.S. 291 - BROOKLYN | DIIT - RESOA | FY13 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 180000 | 0 | DSF0000821730
32 | K291 | I.S. 291 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/7/2024 | DIIR | 8/23/2024 | DIIR | 110000 | 110000 | DSF0001033056
32 | K291 | I.S. 291 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/22/2023 | DOES | 9/6/2023 | DOES | 504187 | 439800 | DSF0001035114
32 | K291 | I.S. 291 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/21/2024 | DOES | 12/3/2024 | DOES | 65832 |  | DSF0001084761
32 | K296 | I.S. 562 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0 | DSF0001033107
32 | K296 | K053 SPED - BROOKLYN | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | Complete | 7/20/2023 | DOER | 4/26/2024 | DOER | 171594 |  | DSF0000911805
32 | K296 | I.S. 562 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/3/2023 | DOER |  | DOER | 1668178 | 0 | DSF0001033585
32 | K296 | I.S. 562 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/15/2023 | DOES | 9/27/2023 | DOES | 475918 |  | DSF0001035115
32 | K296 | I.S. 562 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 10/30/2024 | DOES | 11/14/2024 | DOES | 65832 |  | DSF0001084763
32 | K299 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Scope | Complete | 4/5/2021 | 8/18/2021 | 8/13/2021 | 133519 | 131885 | 131885 | DSF0001008566, DSF0001034349
32 | K299 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Design | Complete | 9/15/2021 | 3/8/2022 | 9/8/2022 | 661849 | 560042 | 452732 | DSF0001008566, DSF0001034349
32 | K299 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Construction | In-Progress | 2/21/2024 | 8/8/2026 |  | 14394248 | 13082871 | 1337014 | DSF0001008566, DSF0001034349
32 | K299 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | CM,F&E | In-Progress | 2/21/2024 | 8/8/2026 |  | 979343 | 233740 | 231979 | DSF0001008566, DSF0001034349
32 | K299 | P.S. 299 - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0 | DSF0001008424
32 | K299 | P.S. 299 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/18/2022 | DOES |  | DOES | 104245 | 0 | DSF0001009051
32 | K299 | P.S. 299 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/15/2024 | DOES | 7/25/2024 | DOES | 65832 | 8938 | DSF0001084141
32 | K376 | P.S. 376 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0 | DSF0001033080
32 | K376 | P.S. 376 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/21/2024 | DIIR | 10/25/2024 | DIIR | 100000 | 100000 | DSF0001086103
32 | K376 | P.S. 376 - BROOKLYN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | In-Progress | 5/13/2024 | DOER |  | DOER | 100000 | 0 | DSF0001086104
32 | K376 | P.S. 376 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 10/8/2019 | DOES |  | DOES | 85121 | 0 | DSF0000865892
32 | K376 | P.S. 376 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/21/2022 | DOES |  | DOES | 117805 | 0 | DSF0001009159
32 | K377 | P.S. 377 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/22/2024 | DOES | 7/25/2024 | DOES | 65832 | 11149 | DSF0001084164
32 | K377 | P.S. 377 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/15/2024 | DOES |  | DOES | 646666 | 0 | DSF0001085717
32 | K383 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/3/2022 | 10/3/2022 | 9/1/2022 | 3560 | 2888 | 2888 | DSF0001034668
32 | K383 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/1/2022 | 3/3/2023 | 3/2/2023 | 16020 | 11550 | 11550 | DSF0001034668
32 | K383 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/27/2023 | 8/21/2024 |  | 206480 | 191034 | 109939 | DSF0001034668
32 | K383 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/27/2023 | 8/21/2024 |  | 153125 | 148116 | 88235 | DSF0001034668
32 | K383 | I.S. 383 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 8/17/2022 | DOES |  | DOES | 1318071 | 0 | DSF0000912219
32 | K383 | I.S. 383 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 8/28/2024 | DOES | 9/6/2024 | DOES | 65832 |  | DSF0001084618
32 | K383 | I.S. 383 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/26/2024 | DOES |  | DOES | 705124 | 0 | DSF0001085712
32 | K384 | P.S. 384 - BROOKLYN | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 3/5/2019 | 7/5/2019 | 1/26/2022 | 43328 | 4054 | 4054 | DSF0001014986
32 | K384 | P.S. 384 - BROOKLYN | SCA CIP | ROOF REPLACEMENT | Design | Complete | 12/29/2022 | 7/5/2023 | 12/13/2023 | 216640 | 381201 | 291323 | DSF0001014986
32 | K384 | P.S. 384 - BROOKLYN | SCA CIP | ROOF REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 4874398 | 4874398 | 3611 | DSF0001014986
32 | K384 | P.S. 384 - BROOKLYN | SCA CIP | ROOF REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 303296 | 303296 | 15303 | DSF0001014986
32 | K384 | P.S. 384 - BROOKLYN | SCA IEH | PO18-ABATE AND PERFORM FULL FLOOR PENETRATION ON AREA MARKED IN BLUE. LOCATION: KITCHEN. PENETRATE ( | Construction | Complete | 10/8/2024 | IEH | 10/12/2024 | IEH | 0 | 0 | SCA0000073475
32 | K384 | P.S. 384 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 10/29/2021 | DOES |  | DOES | 59415 | 345652 | DSF0000990082
32 | K384 | P.S. 384 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 272254 | 0 | DSF0001034231
32 | K384 | P.S. 384 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 9/10/2024 | DOES | 9/16/2024 | DOES | 65832 | 5897 | DSF0001084619
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | SCA CIP | WATER HEATER REPLACEMENT | Scope | Complete | 6/20/2023 | 9/20/2023 | 8/29/2023 | 18993 | 20178 | 382 | DSF0001066264
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | SCA CIP | WATER HEATER REPLACEMENT | Design | In-Progress | 12/9/2024 | 5/12/2025 |  | 94963 | 94963 | 1529 | DSF0001066264
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | SCA CIP | WATER HEATER REPLACEMENT | Construction | PNS | PNS | PNS | PNS | 2136666 | 2136666 | 7213 | DSF0001066264
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | SCA CIP | WATER HEATER REPLACEMENT | CM,F&E | PNS | PNS | PNS | PNS | 132948 | 132948 | 3144 | DSF0001066264
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | SCA IEH | PO18-ABATE AND REPLACE 9X9 ACM FLOOR TILES GREY TILES ARE POPPING UP, ACM PER AHERA LOC: KITCHEN WOM | Construction | Complete | 11/6/2024 | IEH | 12/30/2024 | IEH | 0 | 0 | SCA0000073576
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | Fast Track Projects | RNWL SBHC | Construction | In-Progress | 7/2/2016 | FTK |  | FTK | 1586499 | 1584473 | DSF0000822683
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 80000 | 0 | DSF0000913547
32 | K480 | THE ACADEMY OF URBAN PLANNING AND ENGINEERING - K | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 6/30/2023 | DOER |  | DOER | 178767 | 0 | DSF0001033104
32 | K480 | THE ACADEMY OF URBAN PLANNING AND ENGINEERING - K | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0 | DSF0001086131
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 3/9/2023 | DOES |  | DOES | 1414342 | 0 | DSF0001066263
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/10/2024 | DOES |  | DOES | 65832 | 0 | DSF0001084911
32 | K554 | I.S. 554 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/17/2024 | IEH | 7/17/2024 | IEH | 0 | 0 | SCA0000073074
32 | K677 | SUCCESS ACADEMY CHARTER SCHOOL - BUSHWICK | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/5/2024 | IEH | 8/9/2024 | IEH | 0 | 0 | SCA0000073230
32 | K799 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | Scope | Complete | 8/10/2015 | 12/28/2015 | 3/28/2016 | 103442 | 91741 | 91741 | DSF0000822169, DSF0000843223, DSF0000843222, DSF0000843221
32 | K799 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | Design | Complete | 6/24/2016 | 11/28/2016 | 2/7/2017 | 404279 | 646366 | 616941 | DSF0000822169, DSF0000843223, DSF0000843222, DSF0000843221
32 | K799 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | Construction | In-Progress | 5/21/2018 | 11/11/2019 |  | 6728865 | 7127771 | 6676004 | DSF0000822169, DSF0000843223, DSF0000843222, DSF0000843221
32 | K799 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | CM,F&E | In-Progress | 5/21/2018 | 11/11/2019 |  | 606049 | 1440182 | 1434696 | DSF0000822169, DSF0000843223, DSF0000843222, DSF0000843221
32 | K799 | ALC - BROOKLYN CHOICES | SCA Emergency Response | EMERGENCY STABILZATION | Construction | In-Progress | 2/2/2015 | EMER |  | EMER | 288080 | 288080 | SCA0000033752
32 | K799 | ALC - BROOKLYN CHOICES | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 12/12/2024 | IEH | 12/27/2024 | IEH | 0 | 0 | SCA0000073704
32 | K799 | ALC - BROOKLYN CHOICES | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0 | DSF0001112739
32 | K842 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 5/21/2024 | 10/7/2024 | 10/28/2024 | 30718 | 57749 | 40165 | DSF0001094982, DSF0001094984, DSF0001113846
32 | K842 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | In-Progress | 11/12/2024 | 4/16/2025 |  | 136969 | 136969 | 14336 | DSF0001094982, DSF0001094984, DSF0001113846
32 | K842 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Construction | PNS | PNS | PNS | PNS | 2115186 | 2115186 | 2681 | DSF0001094982, DSF0001094984, DSF0001113846
32 | K842 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | CM,F&E | PNS | PNS | PNS | PNS | 296269 | 296269 | 17646 | DSF0001094982, DSF0001094984, DSF0001113846
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | Scope | Complete | 6/18/2013 | 12/2/2013 | 11/18/2013 | 130880 | 130246 | 130246 | DSF0000776207, DSF0000874482
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | Design | Complete | 11/19/2013 | 5/22/2014 | 5/14/2020 | 654400 | 1869941 | 1622539 | DSF0000776207, DSF0000874482
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | Construction | Complete | 7/11/2022 | 7/9/2024 | 6/17/2024 | 14724000 | 18525054 | 17649245 | DSF0000776207, DSF0000874482
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | CM,F&E | Complete | 7/11/2022 | 7/9/2024 | 6/17/2024 | 1055099 | 1580447 | 1544596 | DSF0000776207, DSF0000874482
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | ROOM CONVERSION | Scope | Complete | 4/11/2022 | 8/10/2022 | 4/11/2022 | 10612 | 317 | 317 | DSF0001034892
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | ROOM CONVERSION | Design | Complete | 4/11/2022 | 12/30/2022 | 3/7/2023 | 53059 | 1269 | 1269 | DSF0001034892
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 1193824 | 1193824 | 0 | DSF0001034892
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 74282 | 74282 | 5027 | DSF0001034892
32 | K865 | COMMUNITY BASED ORGANIZATION - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 12/9/2024 | IEH |  | IEH | 0 | 0 | SCA0000073686
32 | K865 | BUSHWICK LEADERS - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 8/30/2024 | DIIR |  | DIIR | 197000 | 0 | DSF0001033105
32 | K865 | BUSHWICK LEADERS - K | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/26/2021 | DOER |  | DOER | 209486 | 0 | DSF0000890798
32 | K865 | BUSHWICK LEADERS - K | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/17/2022 | DOES |  | DOES | 53562 | 0 | DSF0001009049
32 | K865 | DOE ADMINISTRATIVE OFFICE - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 12/10/2022 | DOES |  | DOES | 1195241 | 870486 | DSF0001067420
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/10/2023 | 7/25/2023 | 3/15/2023 | 4720 | 2062 | 2062 | DSF0001034573
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/15/2023 | 9/8/2023 | 5/2/2023 | 21240 | 8247 | 8247 | DSF0001034573
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | Construction | In-Progress | 9/27/2023 | 8/21/2024 |  | 273760 | 246203 | 155334 | DSF0001034573
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | CM,F&E | In-Progress | 9/27/2023 | 8/21/2024 |  | 113730 | 94453 | 90342 | DSF0001034573
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | DOE - RESOA | FY18 RESO A HYDROPONICS LAB | Construction | Complete | 5/17/2019 | DOER | 12/30/2020 | DOER | 133435 |  | DSF0000866466
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/16/2023 | DOES | 7/21/2023 | DOES | 266576 |  | DSF0001035117
32 | KBRV | BETHESDA DAY CARE CENTER OF BROOKLYN | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 4/8/2021 | 8/9/2021 | 7/19/2021 | 2522 | 13929 | 13929 | DSF0001008776
32 | KBRV | BETHESDA DAY CARE CENTER OF BROOKLYN | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | In-Progress | 5/3/2022 | 10/3/2022 |  | 11349 | 19225 | 1108 | DSF0001008776
32 | KBRV | BETHESDA DAY CARE CENTER OF BROOKLYN | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Construction | PNS | PNS | PNS | PNS | 146275 | 146275 | 8204 | DSF0001008776
32 | KBRV | BETHESDA DAY CARE CENTER OF BROOKLYN | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | CM,F&E | PNS | PNS | PNS | PNS | 27111 | 27111 | 19232 | DSF0001008776
32 | KBSG | 200 CENTRAL AVENUE DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 4/12/2021 | 8/11/2021 | 7/19/2021 | 4950 | 15471 | 15471 | DSF0001008778
32 | KBSG | 200 CENTRAL AVENUE DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Design | Complete | 1/3/2022 | 5/3/2022 | 1/6/2023 | 22277 | 29044 | 29044 | DSF0001008778
32 | KBSG | 200 CENTRAL AVENUE DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Construction | PNS | PNS | PNS | PNS | 287121 | 287121 | 26649 | DSF0001008778
32 | KBSG | 200 CENTRAL AVENUE DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | CM,F&E | PNS | PNS | PNS | PNS | 53216 | 53216 | 7173 | DSF0001008778