## Sheet1
Project Geographic District | Project Building Identifier | Project School Name | Project Type | Project Description | Project Phase Name | Project Status Name | Project Phase Actual Start Date | Project Phase Planned End Date | Project Phase Actual End Date | Project Budget Amount | Final Estimate of Actual Costs Through End of Phase Amount | Total Phase Actual Spending Amount
1 | M015 | P.S. 15 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE THE FLOOR IN THE FOLLOWING ROOMS: 202, 208, 210, 212, 315, 402, 406, 408, 50 | Construction | In-Progress | 7/19/2024 | IEH |  | IEH | 816 | 241
1 | M015 | P.S. 15 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 6/28/2024 | DOER |  | DOER | 195734 | 0
1 | M015 | P.S. 15 - MANHATTAN | DOE - Skilled Trades | SCHOOLYARD RESURFACING | Construction | In-Progress | 2/19/2024 | DOES |  | DOES | 407270 | 0
1 | M019 | P.S. 19 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 141466 | 0
1 | M019 | P.S. 315 - MANHATTAN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0
1 | M019 | P.S. 315 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/27/2024 | DOES | 4/3/2024 | DOES | 65832 | 2197
1 | M020 | P.S. 20 - MANHATTAN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 3/22/2019 | DOER |  | DOER | 162518 | 0
1 | M020 | P.S. 20 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/7/2021 | DOES |  | DOES | 195021 | 0
1 | M020 | P.S. 20 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/2/2024 | DOES | 4/9/2024 | DOES | 65832 | 189
1 | M022 | NEW EXPLORATIONS - M | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 3/5/2024 | 6/3/2024 |  | 0 | 7108 | 1343
1 | M022 | NEW EXPLORATIONS - M | Fast Track Projects | LSP- VACUUM PUMPS REPLACEMENTS | Construction | In-Progress | 2/8/2024 | FTK |  | FTK | 186188 | 37000
1 | M022 | NEW EXPLORATIONS - M | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0
1 | M022 | NEW EXPLORATIONS - M | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/6/2021 | DOER |  | DOER | 80736 | 0
1 | M022 | NEW EXPLORATIONS - M | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/16/2022 | DOER |  | DOER | 189971 | 0
1 | M022 | NEW EXPLORATIONS - M | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
1 | M022 | NEW EXPLORATIONS - M | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 265000 | 0
1 | M022 | NEW EXPLORATIONS - M | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/20/2024 | DOES | 6/28/2024 | DOES | 265619
1 | M025 | I.S. 378 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/1/2019 | EMER |  | EMER | 523752 | 519082
1 | M025 | I.S. 378 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/22/2024 | DOES |  | DOES | 587152 | 0
1 | M034 | P.S. 34 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
1 | M034 | P.S. 34 - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 12/1/2022 | DOER |  | DOER | 34574 | 0
1 | M034 | P.S. 34 - MANHATTAN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 3/15/2024 | DOER |  | DOER | 103169 | 0
1 | M034 | P.S. 34 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/25/2022 | DOES |  | DOES | 92365 | 0
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 51 | 51
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
1 | M056 | I.S. 332 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
1 | M056 | J.H.S. 292 - MANHATTAN | SCA IEH | PO18-WE ARE GOING TO NEED AN ABATEMENT AT M056. THE LOCATIONS ARE RMS. 313 AND 213 AND IT'S APPROXIM | Construction | In-Progress | 4/12/2024 | IEH |  | IEH | 1666 | 1091
1 | M056 | J.H.S. 292 - MANHATTAN | SCA IEH | PO18-HAVE THE GYM FLOOR CORE DRILLED AND TEST FOR ASBESTOS PRINCIPAL WOULD LIKE 2 HOLES MADE TO SUPP | Construction | Complete | 7/29/2024 | IEH | 9/4/2024 | IEH | 33236 | 2560
1 | M056 | J.H.S. 292 - MANHATTAN | SCA IEH | PO18-IN BASEMENT MECHANICAL ROOM CELLAR: FAN ROOM# C25 (1025) - AUDITORIUM BLOWER CELLAR: FAN ROOM ( | Construction | Complete | 8/23/2024 | IEH | 8/25/2024 | IEH | 205 | 205
1 | M056 | J.H.S. 292 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0
1 | M056 | J.H.S. 292 - MANHATTAN | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 120291 | 0
1 | M056 | J.H.S. 292 - MANHATTAN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 8669 | 0
1 | M056 | I.S. 332 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/8/2024 | DOES |  | DOES | 571709 | 0
1 | M056 | MANHATTAN CHARTER SCHOOL II | Trust For Public Land | TPL- EXTREME WEATHER PLAYGROUND UPGRADE | Construction | In-Progress | 2/10/2024 | TPL |  | TPL | 2757910 | 2385830
1 | M060 | EAST SIDE COMMUNITY SCHOOL | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 11/3/2020 | FTK |  | FTK | 194813 | 190289
1 | M060 | EAST SIDE COMMUNITY SCHOOL | Fast Track Projects | ROOF | Construction | In-Progress | 5/16/2019 | FTK |  | FTK | 1719207 | 1630567
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/18/2024 | DIIR | 53000 | 53000
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/31/2022 | DOER |  | DOER | 38764 | 0
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 2575903 | 0
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 174000 | 0
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 6/5/2023 | DOES |  | DOES | 60921 | 0
1 | M060 | EAST SIDE COMMUNITY SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/1/2024 | DOES |  | DOES | 438872 | 0
1 | M061 | P.S. 361 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION OVER THE AUDITORIUM ENTRY DOORS LOCATED IN THE 1ST FLOOR THE INS | Construction | In-Progress | 7/24/2024 | IEH |  | IEH | 635 | 60
1 | M061 | P.S. 361 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
1 | M061 | P.S. 361 - MANHATTAN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/29/2022 | DOER |  | DOER | 219727 | 0
1 | M061 | P.S. 315 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/31/2022 | DOES |  | DOES | 72044 | 0
1 | M061 | P.S. 361 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/5/2024 | DOES | 4/12/2024 | DOES | 65832 | 25380
1 | M063 | P.S. 363 - MANHATTAN | Fast Track Projects | LSP FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/29/2023 | FTK |  | FTK | 108253 | 70175
1 | M063 | P.S. 63 - MANHATTAN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 10/25/2023 | DOEL | 3/26/2024 | DOEL | 95707 | 95707
1 | M063 | P.S. 63 - MANHATTAN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/7/2022 | DOER |  | DOER | 202779 | 0
1 | M063 | P.S. 363 - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/15/2024 | DOER |  | DOER | 201403 | 0
1 | M063 | P.S. 63 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
1 | M063 | P.S. 363 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 7/27/2022 | DOES |  | DOES | 94774 | 0
1 | M063 | P.S. 63 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/24/2023 | DOES |  | DOES | 65832 | 0
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/2/2019 | 3/4/2020 | 2/11/2020 | 0 | 27695 | 27695
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 3/18/2020 | 6/17/2020 | 12/4/2020 | 0 | 18840 | 18840
1 | M064 | I.S. 839 - MANHATTAN | SCA IEH | PO18-REMOVE AND REPLACE 9X9 ACM TILES IN 1ST AND 2ND FLOORS SQFT FOR 1ST FLOOR IS 510 2ND FLOOR | Construction | Complete | 5/29/2024 | IEH | 7/2/2024 | IEH | 28783 | 4219
1 | M064 | I.S. 839 - MANHATTAN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | In-Progress | 3/8/2024 | DOER |  | DOER | 128641 | 0
1 | M064 | I.S. 839 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
1 | M064 | P.S. 64 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 6/5/2023 | DOES |  | DOES | 62522 | 0
1 | M064 | I.S. 839 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/25/2024 | DOES |  | DOES | 65832 | 0
1 | M064 | P.S. 64 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/3/2024 | DOES | 6/24/2024 | DOES | 255112
1 | M097 | BARD COLLEGE HS - MANHATTAN | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/10/2019 | FTK |  | FTK | 54508 | 54508
1 | M097 | BARD COLLEGE HS - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 223957 | 0
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - Skilled Trades | DOMESTIC WATER HEATER | Construction | In-Progress | 3/1/2022 | DOES |  | DOES | 90361 | 376
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - Skilled Trades | SCHOOLYARD RESURFACING | Construction | In-Progress | 8/14/2023 | DOES |  | DOES | 567979 | 0
1 | M097 | BARD COLLEGE HS - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/26/2024 | DOES |  | DOES | 197896 | 0
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 8/15/2023 | 11/15/2023 | 4/15/2024 | 0 | 26741 | 26741
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
1 | M110 | P.S. 110 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/18/2021 | EMER |  | EMER | 928675 | 707109
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR CEILING PLASTER IN ROOM #504 | Construction | Complete | 5/8/2023 | IEH | 5/3/2024 | IEH | 355 | 355
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-ACM TEST FOR WALL TO INSTALL BOTTLE FILLERS 2 LOCATIONS GYMNASIUM / BUBBLER / M11001GM000GYM.1B | Construction | Complete | 4/12/2024 | IEH | 7/13/2024 | IEH | 19272 | 3016
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER LOCATED IN THE 2ND FLOOR AND 3RD FLOOR STAIRSCASE F THAT IS FALL | Construction | Complete | 5/13/2024 | IEH | 6/1/2024 | IEH | 20895 | 20800
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-2 AREAS IN GYMNASIUM NEEDS TO BE ABATED ONE AREA IS THE GYMNASIUM PHONE THAT FELL FROM THE WALL | Construction | In-Progress | 7/30/2024 | IEH |  | IEH | 1541 | 966
1 | M110 | P.S. 110 - MANHATTAN | SCA IEH | PO18-CORE DRILLING HOLES FOR ELECTRICAL CONDUITS IN THE GYM | Construction | Complete | 8/23/2024 | IEH | 8/30/2024 | IEH | 22140 | 649
1 | M134 | P.S. 134 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
1 | M134 | P.S. 134 - MANHATTAN | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
1 | M134 | P.S. 134 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
1 | M134 | P.S. 134 - MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 1/18/2022 | DOES |  | DOES | 391092 | 0
1 | M134 | P.S. 134 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/19/2022 | DOES |  | DOES | 77253 | 0
1 | M134 | P.S. 134 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/13/2024 | DOES | 5/23/2024 | DOES | 65832 | 10156
1 | M137 | P.S. 184 - MANHATTAN | DOE - RESOA | FY15 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
1 | M137 | P.S. 184 - MANHATTAN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/6/2022 | DOER |  | DOER | 97723 | 0
1 | M137 | P.S. 184 - MANHATTAN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 128263 | 0
1 | M140 | P.S. 140 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
1 | M140 | P.S. 140 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/22/2022 | DOES |  | DOES | 81461 | 0
1 | M142 | P.S. 142 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/11/2024 | DOER |  | DOER | 112434 | 0
1 | M142 | P.S. 142 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 249419 | 0
1 | M142 | P.S. 142 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
1 | M142 | P.S. 142 - MANHATTAN | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 7/30/2022 | DOES |  | DOES |  | 0
1 | M142 | P.S. 142 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/30/2024 | DOES | 5/3/2024 | DOES | 65832 | 189
1 | M188 | P.S. 188 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR IN ROOM 501A, AHERA BOOK SHOWS IT AS HOT. | Construction | Complete | 4/15/2024 | IEH | 8/4/2024 | IEH | 19537 | 1332
1 | M188 | P.S. 188 - MANHATTAN | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 9/5/2019 | FTK |  | FTK | 76709 | 76709
1 | M188 | M094 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 60000
1 | M188 | P.S. 188 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 6/4/2024 | DIIR | 60000 | 60000
1 | M188 | P.S. 188 - MANHATTAN | DOE - RESOA | FY11 RESO A PLAYGROUND REDEVELOPMEN | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
1 | M188 | P.S. 188 - MANHATTAN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
1 | M188 | P.S. 188 - MANHATTAN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 135000 | 0
1 | M188 | P.S. 188 - MANHATTAN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
1 | M188 | M094 SPED - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/3/2022 | DOES |  | DOES | 313034 | 0
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | SCA IEH | PO18-ABATE CEILING ABOVE STAIRCASE E , BATHROOM ON 5TH FL BOYS BATHROOM AND 5TH FLOOR NEAR THE ELEV | Construction | In-Progress | 7/10/2024 | IEH |  | IEH | 871 | 121
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | Fast Track Projects | FY18 RESO A SAFETY SYSTEMS | Construction | In-Progress | 11/13/2018 | FTK |  | FTK | 15012 | 12702
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | DOE - RESOA | FY18 RESO A MEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 235237 | 0
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 2/26/2021 | DOER |  | DOER | 53288 | 0
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | DOE - Skilled Trades | REPAIRS TO FIRE DAMAGE | Construction | In-Progress | 11/12/2019 | DOES |  | DOES | 266861 | 0
1 | M510 | SATELLITE AT FORSYTHE | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/6/2023 | DOER |  | DOER | 151912 | 0
1 | M510 | CASCADES CTR FOR TCHING & LNG - M | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 5/13/2024 | DOER |  | DOER | 47394 | 0
1 | M510 | SATELLITE AT FORSYTHE | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
1 | M510 | CASCADES CTR FOR TCHING & LNG - M | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 8/21/2023 | DOES |  | DOES | 62190 | 0
1 | M751 | M751 SPED - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ M751 | Construction | In-Progress | 9/30/2024 | EMER |  | EMER |  | 0
1 | M751 | M751 SPED - MANHATTAN | SCA IEH | PO18-COLLAPSED AND ACM CEILING MATERIAL IN ROOM 505 TEACHERS' S LOUNGE ROOM HAS BEEN CLOSED OFF . | Construction | Complete | 7/8/2024 | IEH | 7/21/2024 | IEH | 31504 | 1322
1 | M751 | M751 SPED - MANHATTAN | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 4/6/2023 | DOER |  | DOER | 318711 | 0
1 | M751 | M751 SPED - MANHATTAN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/6/2023 | DOER |  | DOER | 290515 | 0
1 | M751 | M751 SPED - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 12/26/2018 | DOES |  | DOES | 236177 | 0
2 | M001 | P.S. 1 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 199373 | 0
2 | M001 | P.S. 1 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 12/27/2021 | DOES |  | DOES | 307767 | 0
2 | M001 | P.S. 1 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/17/2024 | DOES | 5/9/2024 | DOES | 65832 | 189
2 | M002 | P.S. 2 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/13/2019 | EMER |  | EMER | 11153 | 11153
2 | M002 | P.S. 2 - MANHATTAN | Fast Track Projects | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/14/2021 | FTK |  | FTK | 37701 | 34965
2 | M002 | P.S. 2 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 117999 | 0
2 | M002 | P.S. 2 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/1/2022 | DOES |  | DOES | 494086 | 0
2 | M003 | P.S. 3 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/26/2024 | DIIR | 125000 | 125000
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/22/2022 | DOER |  | DOER | 35857 | 0
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY24 RESO A (MA) CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 3109 | 0
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 69000 | 0
2 | M003 | P.S. 3 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
2 | M003 | P.S. 3 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/13/2024 | DOES |  | DOES | 65832 | 0
2 | M006 | P.S. 6 - MANHATTAN | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 6/14/2021 | 3/25/2022 | 1/31/2022 | 0 | 22402 | 22402
2 | M006 | P.S. 6 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
2 | M006 | P.S. 6 - MANHATTAN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
2 | M006 | P.S. 6 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/25/2024 | DOES | 4/2/2024 | DOES | 65832 | 10117
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 2/3/2021 | DOER |  | DOER | 274039 | 0
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 459087 | 0
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/6/2022 | DOER |  | DOER | 32577 | 0
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 135418 | 0
2 | M011 | P.S. 11 - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
2 | M011 | P.S. 11 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/24/2022 | DOES |  | DOES | 95590 | 0
2 | M011 | P.S. 11 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/5/2024 | DOES | 4/19/2024 | DOES | 65832 | 11654
2 | M017 | P.S. 212 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 40000 | 0
2 | M017 | P.S. 212 - MANHATTAN | DOE - RESOA | FY16 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 6/8/2024 | DOER |  | DOER | 270785 | 0
2 | M017 | P.S. 212 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/17/2022 | DOER |  | DOER | 39884 | 0
2 | M017 | P.P.A.S. - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
2 | M017 | P.S. 212 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
2 | M017 | P.S. 212 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 11/1/2021 | DOES |  | DOES | 57782 | 0
2 | M017 | P.P.A.S. - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/17/2024 | DOES |  | DOES | 65832 | 0
2 | M033 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M033 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M033 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M033 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M033 | P.S. 33 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 120000 | 0
2 | M033 | M138 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M033 | P.S. 33 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/5/2022 | DOER |  | DOER | 20668 | 0
2 | M033 | P.S. 33 - MANHATTAN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 6/27/2022 | DOER |  | DOER | 93353 | 0
2 | M033 | P.S. 33 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 162651 | 0
2 | M033 | P.S. 33 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/26/2023 | DOER |  | DOER | 225000 | 9700
2 | M033 | M138 SPED - MANHATTAN | DOE - RESOA | FY24 RESO A (MA) ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 235250 | 0
2 | M033 | M138 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
2 | M033 | P.S. 33 - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 2/26/2024 | DOES |  | DOES | 544403 | 1908
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Scope | Complete | 3/12/2020 | 7/27/2020 | 6/8/2021 | 0 | 33452 | 33452
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY21 RESO A (MA) SCIENCE LAB UPGRADE | Scope | Complete | 3/3/2021 | 6/16/2021 | 9/1/2021 | 0 | 35876 | 35876
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Scope | Complete | 4/25/2022 | 12/8/2022 | 11/1/2022 | 0 | 23281 | 23281
2 | M040 | P.S. 40 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- INVESTIGATION @ M040 | Construction | In-Progress | 6/9/2023 | EMER |  | EMER | 103375 | 103375
2 | M040 | P.S. 40 - MANHATTAN | SCA IEH | PO18-ACM CORE DRILLING NEEDED IN THE KITCHEN (2) 1.25' HOLES DRILLED THRU THE WALL (12) 1/2' HOLES D | Construction | In-Progress | 7/18/2024 | IEH |  | IEH | 635 | 60
2 | M040 | I.S. 255 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 55000
2 | M040 | I.S. 255 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M040 | P.S. 40 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M040 | P.S. 40 - MANHATTAN | DOE - RESOA | FY 15 RESO A CAFETERIA FLOORING UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 43622 | 0
2 | M040 | P.S. 40 - MANHATTAN | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/25/2019 | DOER |  | DOER | 505108 | 0
2 | M040 | I.S. 255 - MANHATTAN | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 3199 | 0
2 | M040 | P.S. 40 - MANHATTAN | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 103977 | 0
2 | M040 | I.S. 255 - MANHATTAN | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 6/21/2024 | DOER |  | DOER | 90171 | 0
2 | M040 | I.S. 255 - MANHATTAN | DOE - RESOA | FY25 RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
2 | M040 | I.S. 255 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/13/2024 | DOES |  | DOES | 398140 | 0
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/14/2023 | 5/15/2023 | 6/27/2023 | 0 | 11562 | 11562
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 142 | 142
2 | M041 | P.S. 41 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
2 | M041 | P.S. 41 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/24/2021 | DOER |  | DOER | 61043 | 0
2 | M041 | P.S. 41 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/8/2023 | DOER |  | DOER | 150000 | 9653
2 | M041 | P.S. 41 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
2 | M041 | P.S. 41 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 11/12/2021 | DOES |  | DOES | 83081 | 0
2 | M041 | P.S. 41 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | RESO A- SOLAR ROOF INSTALL | Construction | PNS | PNS | PNS | PNS | DOER | 111545 | 0
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 3/24/2022 | DOER |  | DOER | 32804 | 0
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/18/2023 | DOER |  | DOER | 85430 | 0
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 113550 | 0
2 | M042 | P.S. 42 - MANHATTAN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
2 | M042 | P.S. 42 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/1/2022 | DOES |  | DOES | 91622 | 0
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 3/22/2022 | EMER |  | EMER | 33094 | 20565
2 | M047 | P.S. 347 - MANHATTAN | DOE - RESOA | FY16 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 44000 | 0
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/19/2024 | DOER |  | DOER | 303779 | 0
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 253558 | 0
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100307 | 0
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/10/2022 | DOES |  | DOES | 125997 | 0
2 | M066 | P.S. 151 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ M066 | Construction | In-Progress | 3/7/2024 | EMER |  | EMER | 49029 | 4750
2 | M066 | P.S. 151 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M066 | P.S. 151 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M066 | P.S. 151 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/11/2024 | DOER |  | DOER | 323500 | 0
2 | M066 | P.S. 151 - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 12/20/2023 | DOER |  | DOER | 59343 | 0
2 | M066 | P.S. 151 - MANHATTAN | DOE - RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 207929 | 0
2 | M066 | P.S. 151 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/2/2022 | DOES |  | DOES | 78332 | 0
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | RESO A LOCKER ROOM UPGRADE | Scope | Complete | 7/19/2022 | 11/18/2022 | 1/9/2024 | 0 | 39660 | 39660
2 | M070 | MUSEUM SCHOOL - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 5/23/2024 | DIIR | 75000 | 75000
2 | M070 | MUSEUM SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/1/2024 | DIIR | 7/10/2024 | DIIR | 65000
2 | M070 | NYC LAB HS - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 6/14/2024 | DIIR |  | DIIR | 65000 | 0
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M070 | NYC LAB HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 7/8/2021 | DOER |  | DOER | 84686 | 0
2 | M070 | MUSEUM SCHOOL - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/13/2023 | DOER |  | DOER | 153775 | 0
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 5/13/2016 | DOES |  | DOES | 205854 | 0
2 | M070 | NYC LAB HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/18/2024 | DOES | 6/27/2024 | DOES | 65832
2 | M089 | P.S. 89 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
2 | M089 | P.S. 89 - MANHATTAN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 64000 | 0
2 | M089 | P.S. 89 - MANHATTAN | DOE - Skilled Trades | GYMNASIUM FLOOR | Construction | In-Progress | 5/26/2016 | DOES |  | DOES | 210102 | 0
2 | M089 | P.S. 89 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/3/2024 | DOES | 6/14/2024 | DOES | 50832
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY 21 RESO A (MA) FITNESS ROOM / PATH OF TRAVEL RESO A FITNESS ROOM | Scope | Complete | 4/6/2021 | 12/20/2021 | 11/3/2021 | 0 | 25066 | 25066
2 | M104 | I.S. 104 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/12/2024 | DIIR | 6/12/2024 | DIIR | 100000 | 100000
2 | M104 | I.S. 104 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/19/2021 | DOER |  | DOER | 161767 | 0
2 | M104 | I.S. 104 - MANHATTAN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/12/2023 | DOER |  | DOER | 257073 | 0
2 | M104 | I.S. 104 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/11/2024 | DOER |  | DOER | 168590 | 0
2 | M104 | I.S. 104 - MANHATTAN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 6/1/2016 | DOES |  | DOES | 270403 | 0
2 | M111 | P.S. 111 - MANHATTAN | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | Complete | 4/14/2023 | DIIR | 6/7/2024 | DIIR | 69000 | 69000
2 | M111 | P.S. 111 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/5/2023 | DIIR | 6/7/2024 | DIIR | 100000 | 100000
2 | M111 | P.S. 111 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/10/2022 | DOER |  | DOER | 25152 | 0
2 | M111 | P.S. 111 - MANHATTAN | DOE - RESOA | FY21 RESO A INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
2 | M111 | P.S. 111 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 333911 | 0
2 | M111 | P.S. 111 - MANHATTAN | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
2 | M111 | P.S. 111 - MANHATTAN | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
2 | M111 | P.S. 111 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/26/2022 | DOES |  | DOES | 110754 | 0
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY25 RESO A INTERIOR SPACES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A INTERIOR SPACES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A INTERIOR SPACES | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A INTERIOR SPACES | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY16 RESO A GREEN ROOF | Scope | Complete | 1/26/2016 | 6/9/2016 | 3/8/2016 | 0 | 29585 | 29585
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | RESO A- DANCE STUDIO | Scope | Complete | 4/9/2021 | 7/12/2021 | 7/28/2021 | 0 | 18380 | 18380
2 | M114 | M138 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 54000 | 0
2 | M114 | M138 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M114 | I.S. 114 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 5/23/2024 | DIIR | 110000 | 110000
2 | M114 | M138 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M114 | I.S. 114 - MANHATTAN | DOE - RESOA | RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/7/2023 | DOER |  | DOER | 551514 | 0
2 | M114 | I.S. 114 - MANHATTAN | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 12/18/2023 | DOER |  | DOER | 237435 | 0
2 | M114 | I.S. 114 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/24/2024 | DOES | 5/2/2024 | DOES | 50832
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/24/2022 | 6/22/2022 | 11/3/2022 | 0 | 52382 | 52280
2 | M116 | P.S. 116 - MANHATTAN | SCA CIP RESOA | RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 4/17/2024 | 7/18/2024 | 8/19/2024 | 0 | 936 | 936
2 | M116 | P.S. 116 - MANHATTAN | SCA IEH | PO18-ROOM 506 ABATE 624 SQ. FT. DAMAGED WOODEN FLOORING ASSIGNED TO SCA ON 06/27/2024 | Construction | In-Progress | 6/28/2024 | IEH |  | IEH | 1627 | 302
2 | M116 | P.S. 116 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 49000 | 0
2 | M116 | P.S. 116 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 180000 | 0
2 | M116 | P.S. 116 - MANHATTAN | DOE - RESOA | FY17 RESO A KITCHEN AREAS | Construction | PNS | PNS | PNS | PNS | DOER | 103801 | 0
2 | M116 | P.S. 116 - MANHATTAN | DOE - RESOA | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/10/2023 | DOER |  | DOER | 307625 | 0
2 | M116 | P.S. 116 - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 8/30/2021 | DOER |  | DOER | 324251 | 0
2 | M116 | P.S. 116 - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
2 | M116 | P.S. 116 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/8/2024 | DOES | 5/28/2024 | DOES | 65832 | 9826
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/25/2022 | 4/25/2022 | 8/11/2022 | 0 | 51696 | 49376
2 | M124 | P.S. 124 - MANHATTAN | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 7/12/2022 | DOER |  | DOER | 93124 | 0
2 | M124 | P.S. 124 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/25/2022 | DOER |  | DOER | 316643 | 0
2 | M124 | P.S. 124 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 310000 | 0
2 | M124 | P.S. 124 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/20/2022 | DOES |  | DOES | 123403 | 0
2 | M126 | P.S. 126 - MANHATTAN | SCA IEH | PO18-ABATEMENT IN PIPE SPACE APPROXIMATELY 8', PAINTED BLACK | Construction | Complete | 7/30/2024 | IEH | 8/22/2024 | IEH | 13057 | 1147
2 | M126 | P.S. 126 - MANHATTAN | Fast Track Projects | FY20 RESO A ROOM CONVERSION | Construction | PNS | FTK | FTK | FTK | FTK | 52000 | 0
2 | M126 | P.S. 126 - MANHATTAN | DOE - RESOA | FY17 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 1/15/2019 | DOER |  | DOER | 225277 | 0
2 | M126 | P.S. 126 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/26/2022 | 4/26/2022 | 8/11/2022 | 0 | 13240 | 13240
2 | M130 | P.S. 130 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/14/2024 | DIIR | 6/30/2024 | DIIR | 100000 | 99639
2 | M130 | P.S. 130 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/13/2024 | DIIR | 100000 | 100000
2 | M130 | P.S. 130 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/12/2024 | DIIR | 6/21/2024 | DIIR | 100000
2 | M130 | P.S. 130 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/6/2022 | DOER |  | DOER | 91489 | 0
2 | M130 | P.S. 130 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/9/2024 | DOES |  | DOES | 65832 | 0
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M131 | I.S. 131 - MANHATTAN | Fast Track Projects | LSP DANCE FLOOR REPLACEMENT | Construction | In-Progress | 12/22/2020 | FTK |  | FTK | 215114 | 171412
2 | M131 | EMMA LAZARUS HIGH SCHOOL | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
2 | M131 | PACE HIGH SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 6/25/2024 | DIIR | 150000 | 150000
2 | M131 | I.S. 131 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/14/2022 | DOER |  | DOER | 102028 | 0
2 | M131 | I.S. 131 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/5/2023 | DOES | 10/30/2023 | DOES | 635998
2 | M158 | P.S. 158 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: RM: 313 APPROX. 700SF RM: 314 APPROX. 700SF RM: 315 APP | Construction | Complete | 3/11/2024 | IEH | 7/25/2024 | IEH | 574145 | 552476
2 | M158 | YORKVILLE EAST MIDDLE SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 5/30/2024 | DIIR | 50000 | 50000
2 | M158 | P.S. 158 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/23/2024 | DIIR | 5/7/2024 | DIIR | 150000 | 150000
2 | M158 | YORKVILLE EAST MIDDLE SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
2 | M158 | P.S. 158 - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/16/2023 | DOER |  | DOER | 223413 | 0
2 | M158 | P.S. 158 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
2 | M158 | P.S. 158 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 7/5/2023 | DOES |  | DOES | 69818 | 0
2 | M158 | P.S. 158 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/21/2024 | DOES |  | DOES | 65832 | 0
2 | M167 | I.S. 167 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/28/2023 | 6/29/2023 | 10/11/2023 | 0 | 15704 | 15704
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - Skilled Trades | HEATING PLANT UPGRADE | Construction | In-Progress | 4/22/2024 | DOES |  | DOES | 109794 | 0
2 | M167 | I.S. 167 - MANHATTAN | Fast Track Projects | LSP ASPHALT PAVEMENT AT PLAYGROUND | Construction | In-Progress | 4/24/2024 | FTK |  | FTK | 55125 | 0
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY12 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 162502 | 0
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
2 | M167 | I.S. 167 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 223000 | 0
2 | M167 | I.S. 167 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
2 | M167 | I.S. 167 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
2 | M167 | I.S. 167 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/6/2017 | DOES |  | DOES | 170000 | 0
2 | M169 | M169 SPED - MANHATTAN | Fast Track Projects | FY20 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 11/17/2022 | FTK |  | FTK | 107283 | 103296
2 | M169 | M169 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/20/2023 | DIIR | 5/3/2024 | DIIR | 250000 | 250000
2 | M169 | M169 SPED - MANHATTAN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 10852 | 0
2 | M169 | M169 SPED - MANHATTAN | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
2 | M169 | M169 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 296000 | 0
2 | M169 | M169 SPED - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/17/2024 | DOES | 6/25/2024 | DOES | 65832
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Scope | Complete | 10/10/2018 | 12/10/2018 | 12/3/2018 | 0 | 16165 | 16165
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | NYS IPDVS NEW INSTALLATION | Scope | Complete | 5/11/2023 | 9/12/2023 | 5/26/2023 | 0 | 709 | 709
2 | M183 | P.S. 183 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/21/2024 | DIIR | 5/30/2024 | DIIR | 50000
2 | M183 | P.S. 183 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M183 | P.S. 183 - MANHATTAN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/14/2022 | DOER |  | DOER | 22009 | 0
2 | M183 | P.S. 183 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/4/2024 | DOES | 7/5/2024 | DOES | 65832
31 | R027 | I.S. 27 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP RESOA | RESO A ROOFTOP PLAYGROUND | Scope | Complete | 10/26/2022 | 3/16/2023 | 1/30/2023 | 0 | 142533 | 89137
2 | M190 | P.S. 290 - MANHATTAN | DIIT - RESOA | FY 14 RESO A SECURITY CAMERAS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 42078 | 0
2 | M190 | P.S. 290 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/29/2024 | DIIR | 5/21/2024 | DIIR | 50000 | 50000
2 | M190 | P.S. 290 - MANHATTAN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 325000 | 0
2 | M190 | P.S. 290 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/20/2024 | DOES | 5/30/2024 | DOES | 65832
2 | M198 | P.S. 77 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/9/2023 | 3/14/2024 | 11/14/2023 | 0 | 4941 | 4941
2 | M198 | P.S. 198 - MANHATTAN | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/28/2023 | FTK |  | FTK | 141188 | 0
2 | M198 | P.S. 198 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 5/1/2024 | DIIR | 50000 | 50000
2 | M198 | P.S. 198 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/21/2023 | DIIR | 5/1/2024 | DIIR | 50000 | 50000
2 | M198 | P.S. 77 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 314000 | 0
2 | M198 | P.S. 198 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/9/2024 | DIIR | 6/18/2024 | DIIR | 50000
2 | M198 | P.S. 77 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M198 | P.S. 198 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M198 | P.S. 198 - MANHATTAN | DOE - RESOA | FY18 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 130410 | 0
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 194507 | 0
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 58813 | 0
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
2 | M198 | P.S. 77 - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
2 | M234 | P.S. 234 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/13/2017 | EMER |  | EMER | 366821 | 326322
2 | M234 | P.S. 234 - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
2 | M234 | P.S. 234 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/28/2022 | DOES |  | DOES | 106148 | 0
2 | M267 | P.S. 267 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/13/2024 | DIIR | 7/22/2024 | DIIR | 126000
2 | M267 | P.S. 267 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
2 | M267 | P.S. 267 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/21/2022 | DOER |  | DOER | 79328 | 0
2 | M267 | P.S. 267 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
2 | M267 | P.S. 267 - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 88037 | 0
2 | M271 | P.S./I.S. 217 - MANHATTAN | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 35000 | 0
2 | M271 | P.S./I.S. 217 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 7/10/2020 | DIIR |  | DIIR | 35000 | 0
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/24/2022 | DOER |  | DOER | 95603 | 0
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/12/2022 | DOER |  | DOER | 145990 | 0
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 300000 | 9025
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
2 | M271 | P.S./I.S. 217 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/11/2024 | DOES |  | DOES | 50832 | 0
2 | M276 | M094 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
2 | M276 | P.S./I.S. 276 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
2 | M276 | P.S./I.S. 276 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
2 | M276 | P.S./I.S. 276 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/3/2024 | DOES |  | DOES | 50832 | 0
2 | M281 | PS 281 - THE RIVER SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 7/1/2024 | DIIR | 100000 | 100000
2 | M281 | M094 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 50000
2 | M281 | M094 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 54000 | 0
2 | M281 | PS 281 - THE RIVER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M281 | PS 281 - THE RIVER SCHOOL | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 85000 | 0
2 | M281 | PS 281 - THE RIVER SCHOOL | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 209309 | 0
2 | M282 | I.S. 896 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/1/2023 | 11/2/2023 | 9/28/2023 | 0 | 15829 | 15766
2 | M282 | RICHARD R. GREEN HS OF TEACHING - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
2 | M282 | RICHARD R. GREEN HS OF TEACHING - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M282 | I.S. 896 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
2 | M282 | URBAN ASSEMBLY SCHOOL - MANHATTAN | DOE - Skilled Trades | AHU CHILLED WATER COIL REPLACEMENT | Construction | In-Progress | 1/3/2024 | DOES |  | DOES | 49412 | 0
2 | M323 | M.S. 297 | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/7/2023 | 3/11/2024 | 6/18/2024 | 0 | 7472 | 7410
2 | M323 | M751 SPED - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 149532 | 0
2 | M323 | M.S. 297 | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/16/2024 | DOES | 5/23/2024 | DOES | 65832
2 | M338 | P.S. 51 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Scope | Complete | 4/30/2021 | 8/2/2021 | 9/29/2021 | 0 | 7806 | 7806
2 | M338 | M094 SPED - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
2 | M338 | P.S. 51 - MANHATTAN | DOE - RESOA | FY20 RESO A ROOFTOP PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 52384 | 0
2 | M338 | P.S. 51 - MANHATTAN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
2 | M338 | P.S. 51 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 50832 | 0
2 | M340 | M094 SPED - MANHATTAN | Fast Track Projects | FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 5/17/2022 | FTK |  | FTK | 131361 | 121636
2 | M340 | M094 SPED - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 50000
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M340 | M094 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 233693 | 0
2 | M340 | SIXTH AVENUE ELEMENTARY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/22/2024 | DOES |  | DOES | 50832 | 0
2 | M343 | P.S. 343 - MANHATTAN | SCA CIP RESOA | FY23 RESO A ROOFING | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M343 | P.S. 343 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/10/2024 | DOES |  | DOES | 50832 | 0
2 | M391 | DISTRICT 2 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M391 | DISTRICT 2 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M391 | DISTRICT 2 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M391 | DISTRICT 2 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M391 | DISTRICT 2 PRE-K CENTER | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0
2 | M391 | DISTRICT 2 PRE-K CENTER | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 213000 | 0
2 | M391 | DISTRICT 2 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/6/2024 | DOES | 5/10/2024 | DOES | 65832
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 7/12/2018 | EMER |  | EMER | 132662 | 117493
2 | M440 | LANDMARK HS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/6/2024 | DIIR | 6/12/2024 | DIIR | 75000 | 75000
2 | M440 | QUEST TO LEARN - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M440 | MANHATTAN BUSINESS ACADEMY | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/29/2023 | DIIR | 5/1/2024 | DIIR | 50000 | 50000
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 6/5/2024 | DIIR | 50000 | 50000
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M440 | QUEST TO LEARN - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
2 | M440 | LANDMARK HS - MANHATTAN | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 4/8/2016 | DOER |  | DOER | 84401 | 0
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - RESOA | FY19 RESO A AUDITORIUM SUPPLEMENTAL COOLING | Construction | In-Progress | 5/24/2019 | DOER |  | DOER | 900052 | 0
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 3/7/2022 | DOER |  | DOER | 37177 | 0
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 3/5/2024 | DOER |  | DOER | 665711 | 0
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 8/21/2023 | DOES |  | DOES | 70047 | 0
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/15/2022 | DOES |  | DOES | 181274 | 0
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/10/2024 | DOES | 65832
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | DOE - Skilled Trades | CONDENSATE PUMP REPLACEMENT | Construction | In-Progress | 8/18/2023 | DOES |  | DOES | 395156 | 0
2 | M440 | QUEST TO LEARN - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/6/2024 | DOES |  | DOES | 606170 | 0
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | FY25 RESO A SOLAR PANEL INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A SOLAR PANEL INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A SOLAR PANEL INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A SOLAR PANEL INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A SOLAR PANEL INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M445 | LOWER MANHATTAN ARTS - MANHATTAN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/17/2021 | 4/22/2022 | 7/5/2022 | 0 | 19448 | 19448
2 | M445 | NEW DESIGN HS - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 6/12/2024 | DIIR | 50000 | 50000
2 | M445 | DUAL LANGUAGE HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 9/30/2023 | DOER |  | DOER | 121089 | 0
2 | M445 | ESSEX STREET ACADEMY - MANHATTAN | DOE - RESOA | RESO A SWIMMING POOL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 135662 | 0
2 | M447 | ESSEX STREET ACADEMY - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
2 | M451 | LIBERTY HS ACADEMY FOR NEWCOMERS-M | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
2 | M451 | LIBERTY HS ACADEMY FOR NEWCOMERS-M | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
2 | M453 | DISTRICT 2 PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/8/2024 | IEH | 8606 | 8606
2 | M460 | ACADEMY FOR SOFTWARE ENGINEERING - MANHATTAN | SCA CIP RESOA | FY24 RESO A MOBILE SCIENCE LABS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Scope | In-Progress | 12/12/2023 | 4/12/2024 |  | 0 | 59195 | 984
2 | M460 | ACADEMY FOR SOFTWARE ENGINEERING - MANHATTAN | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 11/5/2021 | FTK |  | FTK | 486852 | 415870
2 | M460 | INT'L HS AT UNION SQUARE - MANHATTAN | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 8/25/2021 | FTK |  | FTK | 1854318 | 1584461
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 160000 | 0
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M460 | INT'L HS AT UNION SQUARE - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DOE - RESOA | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/5/2024 | DOER |  | DOER | 271791 | 0
2 | M460 | INT'L HS AT UNION SQUARE - MANHATTAN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 3/9/2023 | DOER |  | DOER | 578508 | 0
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 5/19/2023 | DOER |  | DOER | 208379 | 0
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
2 | M460 | GRAMERCY ARTS HS - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
2 | M460 | UNION SQUARE ACADEMY FOR HEALTH SCIENCES - MANHATTAN | DOE - RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
2 | M460 | WASHINGTON IRVING HS - MANHATTAN | DOE - Skilled Trades | WATER MAIN LEAK REPAIR | Construction | In-Progress | 5/17/2024 | DOES |  | DOES | 65000 | 0
2 | M471 | DISTRICT 2 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/29/2024 | DOES |  | DOES | 65832 | 0
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | Fast Track Projects | PATH OF TRAVEL LSP CTF ROOM CONVERSION | Construction | In-Progress | 12/6/2021 | FTK |  | FTK | 208057 | 163553
2 | M475 | INSTITUTE FOR COLLABORATIVE ED - M | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 4/1/2020 | DIIR |  | DIIR | 35000 | 0
2 | M475 | INSTITUTE FOR COLLABORATIVE ED - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 60000
2 | M475 | M226 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M475 | INSTITUTE FOR COLLABORATIVE ED - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/22/2023 | DOES | 8/21/2023 | DOES | 564515 | 452635
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/31/2018 | DOER |  | DOER | 69832 | 0
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY17 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 2/28/2017 | DOER |  | DOER | 512808 | 0
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 7/20/2022 | DOER |  | DOER | 852255 | 0
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY22 RESO A RECORDING STUDIO | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 666277 | 0
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
2 | M477 | STUYVESANT HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/30/2024 | DOES | 6/5/2024 | DOES | 50832 | 95
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Scope | Complete | 6/15/2022 | 9/14/2022 | 12/5/2022 | 0 | 21339 | 21339
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 4/5/2024 | 7/9/2024 | 6/28/2024 | 0 | 254 | 254
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 2/1/2023 | 6/2/2023 | 6/15/2023 | 0 | 22910 | 22891
2 | M480 | P.S. 225 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/31/2018 | EMER |  | EMER | 86719 | 86719
2 | M480 | VANGUARD HS - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
2 | M480 | M226 SPED - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 50000 | 0
2 | M480 | VANGUARD HS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 50000 | 0
2 | M480 | M226 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/9/2024 | DIIR | 7/18/2024 | DIIR | 50000 | 50000
2 | M480 | URBAN ACADEMY LABORATORY HS - M | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M480 | VANGUARD HS - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M480 | MANHATTAN INTERNATIONAL HS - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/12/2024 | DIIR | 7/10/2024 | DIIR | 50000 | 50000
2 | M480 | URBAN ACADEMY LABORATORY HS - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 50000
2 | M480 | P.S. 225 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 50000
2 | M480 | M226 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M480 | P.S. 225 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M480 | M226 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M480 | VANGUARD HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M480 | MANHATTAN INTERNATIONAL HS - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M480 | TALENT UNLIMITED HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M480 | URBAN ACADEMY LABORATORY HS - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M480 | TALENT UNLIMITED HS - MANHATTAN | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/24/2018 | DOER |  | DOER | 241208 | 0
2 | M480 | TALENT UNLIMITED HS - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/3/2023 | DOER |  | DOER | 315391 | 0
2 | M480 | P.S. 225 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 6/27/2019 | DOES | 7/1/2020 | DOES | 223851 | 9503
2 | M480 | P.S. 225 - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 10/12/2023 | DOES |  | DOES | 694736 | 325233
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | Fast Track Projects | LSP - FY22 RESO A ELECTRICAL UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 174860 | 0
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/12/2022 | DOES |  | DOES | 73822 | 540468
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY20 RESO A GREENROOF | Scope | Complete | 10/30/2019 | 4/3/2020 | 3/10/2020 | 0 | 28662 | 28662
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/12/2023 | 3/14/2024 | 9/19/2024 | 0 | 6153 | 388
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 7/8/2024 | 10/7/2024 |  | 0 | 44 | 44
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 178 | 178
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 168 | 168
2 | M488 | P.S. 59 - MANHATTAN | SCA Emergency Response | EMERGENCY- FACADE INVESTIGATION @ M488 | Construction | In-Progress | 6/5/2023 | EMER |  | EMER | 582115 | 385920
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 100000 | 0
2 | M488 | P.S. 59 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 6/5/2024 | DIIR | 100000 | 100000
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
2 | M488 | P.S. 59 - MANHATTAN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/23/2020 | DOER |  | DOER | 123066 | 0
2 | M488 | P.S. 59 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 60000 | 0
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 68527 | 0
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 9/27/2023 | DOER |  | DOER | 254242 | 0
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 130000 | 0
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - Skilled Trades | IP DIGITAL VIDEO SURVEILLANCE SYSTE | Construction | In-Progress | 5/23/2014 | DOES |  | DOES | 83000 | 0
2 | M488 | ART & DESIGN VOC HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/29/2024 | DOES | 5/21/2024 | DOES | 50832 | 7456
2 | M491 | DISTRICT 2 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/10/2024 | DOES |  | DOES | 50832 | 0
2 | M520 | BERGTRAUM HS - MANHATTAN | Fast Track Projects | LSP- LIGHTING UPGRADE | Construction | In-Progress | 2/21/2023 | FTK |  | FTK | 281494 | 201531
2 | M520 | BERGTRAUM HS - MANHATTAN | Fast Track Projects | LSP- CEILING AND LIGHTING UPGRADE | Construction | In-Progress | 2/21/2023 | FTK |  | FTK | 438361 | 342524
2 | M520 | BERGTRAUM HS - MANHATTAN | Fast Track Projects | LSP- GYMNASIUM UPGRADE | Construction | In-Progress | 5/1/2023 | FTK |  | FTK | 424087 | 383916
2 | M520 | BERGTRAUM HS - MANHATTAN | Fast Track Projects | LSP- AUDITORIUM UPGRADE | Construction | In-Progress | 1/23/2023 | FTK |  | FTK | 572039 | 471865
2 | M520 | THE URBAN ASSEMBLY EARLY COLLEGE HIGH SCHOOL OF EMERGENCY MEDICINE | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 6/10/2024 | DIIR | 50000
2 | M520 | URBAN ASSEMBLY MAKER ACADEMY | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M520 | URBAN ASSEMBLY MAKER ACADEMY | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
2 | M520 | THE URBAN ASSEMBLY EARLY COLLEGE HIGH SCHOOL OF EMERGENCY MEDICINE | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 195709 | 0
2 | M520 | THE URBAN ASSEMBLY EARLY COLLEGE HIGH SCHOOL OF EMERGENCY MEDICINE | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
2 | M520 | BERGTRAUM HS - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 7/23/2019 | DOES |  | DOES | 846987 | 97181
2 | M520 | BERGTRAUM HS - MANHATTAN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 3/10/2023 | DOES | 10/25/2023 | DOES | 509391 | 495994
2 | M535 | FOOD AND FINANCE HS - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
2 | M535 | HOSPITALITY MANAGEMENT HS - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 5/17/2024 | DIIR | 50000 | 50000
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 650000 | 0
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 7/3/2019 | DOES |  | DOES | 5555 | 139963
2 | M600 | FASHION INDUSTRIES VOC HS - M | SCA IEH | PO18-WE WILL NEED APPROXIMATELY 5 TO 6 FEET OF PIPING ABATED IN THE CEILING OF ROOM 702. AREAS ARE M | Construction | Complete | 7/23/2024 | IEH | 8/16/2024 | IEH | 14342 | 652
2 | M600 | FASHION INDUSTRIES VOC HS - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - RESOA | FY17 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/29/2018 | DOER |  | DOER | 74401 | 0
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 218175 | 0
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/9/2021 | DOER |  | DOER | 224140 | 0
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | Complete | 11/14/2023 | DOER | 3/10/2024 | DOER | 150000 | 7000
2 | M600 | FASHION INDUSTRIES VOC HS - M | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/5/2023 | DOER |  | DOER | 78745 | 0
2 | M600 | M751 SPED - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/14/2023 | DOES |  | DOES | 681064 | 0
2 | M615 | CHELSEA VOC HS - MANHATTAN | SCA IEH | PO18-ROOM 405A ABATE APPROX 10 SQ. FT. LOOSE AND BROKEN FLOOR TILES, ENCAPSULATE FLOOR | Construction | In-Progress | 6/27/2024 | IEH |  | IEH | 816 | 241
2 | M615 | CHELSEA VOCATIONAL H.S. | DOE - RESOA | FY09 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 78577 | 0
2 | M615 | NYC ISCHOOL - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/19/2024 | DOER |  | DOER | 150000 | 9025
2 | M615 | CHELSEA VOC HS - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 8/21/2023 | DOES |  | DOES | 62070 | 0
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP RESOA | FY22 RESO ESCALATOR UPGRADE | Scope | Complete | 5/31/2022 | 8/29/2022 | 12/22/2022 | 0 | 40189 | 40189
2 | M620 | MANHATTAN ACADEMY OF ARTS AND LANGUAGE - MANHATTAN | Fast Track Projects | CTF- ROOM CONVERSION | Construction | In-Progress | 10/31/2014 | FTK |  | FTK | 445969 | 420198
2 | M620 | UNITY HS - MANHATTAN | Fast Track Projects | CTF- ROOM CONVERSION | Construction | In-Progress | 11/4/2014 | FTK |  | FTK | 501369 | 447160
2 | M620 | MURRAY HILL ACADEMY HS - M | Fast Track Projects | TEMPORARY EMERGENCY GENERATOR | Construction | In-Progress | 7/10/2017 | FTK |  | FTK | 718461 | 658779
2 | M620 | MURRAY HILL ACADEMY HS - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/12/2024 | DIIR | 6/3/2024 | DIIR | 100000 | 100000
2 | M620 | UNITY HS - MANHATTAN | DOE - Skilled Trades | CHILLER REPLACEMENT | Construction | In-Progress | 7/2/2019 | DOES |  | DOES | 3668432 | 0
2 | M620 | MURRAY HILL ACADEMY HS - M | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMP | Construction | In-Progress | 7/13/2018 | DOES |  | DOES | 203473 | 0
2 | M620 | MANHATTAN ACADEMY OF ARTS AND LANGUAGE - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/20/2024 | DOES |  | DOES | 668913 | 0
2 | M625 | THE BUSINESS OF SPORTS SCHOOL | SCA IEH | PO18-ACM CORE DRILLING REQUEST 2 HOLES THAT NEED TO BE DRILLED IN THE FLOOR DUE TO ASSUMED ACM WE NE | Construction | In-Progress | 7/5/2024 | IEH |  | IEH | 931 | 181
2 | M625 | THE BUSINESS OF SPORTS SCHOOL | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION IN THE 7TH FLOOR HALLWAY CEILING ACCESS PANEL. WE ARE GOING TO N | Construction | In-Progress | 8/23/2024 | IEH |  | IEH | 121 | 121
2 | M625 | URBAN ASSEMBLY GATEWAY SCHOOL FOR TECHNOLOGY - M | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 75000 | 0
2 | M625 | STEPHEN T. MATHER BUILDING ARTS & CRAFTSMANSHIP HS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA IEH | PO18-ABATE PIPE AND WALLS IN BATHROOM 2 LOCATIONS ON THE 4TH FLOOR WALL OPENINGS 420 AND 520 -5TH FL | Construction | Complete | 3/28/2024 | IEH | 4/6/2024 | IEH | 21543 | 21543
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA IEH | PO18-ROOM B20, ABATE 30 SQ. FT. BROKEN AND MISSING FLOOR TILES ROOM 310, ABATE 4 SQ. FT. BROKEN AND | Construction | In-Progress | 5/9/2024 | IEH |  | IEH | 1276 | 526
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
2 | M641 | M721 SPED - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/8/2024 | DIIR | 5/15/2024 | DIIR | 100000 | 100000
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 5/19/2024 | DIIR | 105000 | 2112
2 | M641 | M721 SPED - MANHATTAN | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/14/2023 | DOER |  | DOER | 135106 | 0
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DOE - RESOA | FY21 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 74000 | 0
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 6/20/2024 | DOER |  | DOER | 24870 | 0
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/5/2021 | DOES |  | DOES | 149409 | 0
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | Fast Track Projects | LSP HOT WATER HEATER | Construction | In-Progress | 12/26/2018 | FTK |  | FTK | 238445 | 231046
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 5/14/2024 | DIIR | 50000 | 50000
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 6/3/2024 | DIIR | 50000 | 50000
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/19/2022 | DOES |  | DOES | 76580 | 0
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Scope | Complete | 12/6/2023 | 4/9/2024 | 5/17/2024 | 0 | 13854 | 2926
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 2/26/2024 | 5/28/2024 | 5/17/2024 | 0 | 0 | 0
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA Emergency Response | EMERGENCY SIDEWALK BRIDGING | Construction | In-Progress | 4/15/2022 | EMER |  | EMER |  | 0
2 | M660 | M226 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832
2 | M661 | MNHT COMPR. NIGHT & DAY HS - M | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/10/2023 | DOES |  | DOES | 195635 | 0
2 | M777 | M000 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M777 | M000 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M777 | M000 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M777 | M000 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M777 | M000 - MANHATTAN | DOE - RESOA | FY23 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 70000 | 0
2 | M807 | HARVEY MILK SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M816 | P.S. 527 - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/12/2024 | IEH | 9868 | 9868
2 | M816 | P.S. 527 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
2 | M816 | P.S. 527 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
2 | M816 | P.S. 527 - MANHATTAN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 176702 | 0
2 | M816 | P.S. 527 - MANHATTAN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/25/2023 | DOER |  | DOER | 259030 | 0
2 | M816 | P.S. 527 - MANHATTAN | DOE - Skilled Trades | BOILER REPLACEMENT | Construction | In-Progress | 4/24/2019 | DOES |  | DOES | 1429795 | 0
2 | M816 | P.S. 527 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 12/26/2022 | DOES |  | DOES | 194652 | 0
2 | M824 | MILLENNIUM HS - MANHATTAN | Fast Track Projects | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/1/2019 | FTK |  | FTK | 154172 | 133756
2 | M824 | MILLENNIUM HS - MANHATTAN | DOE - RESOA | FY18 RESO A LIBRARY UPGRADES | Construction | In-Progress | 1/16/2018 | DOER |  | DOER | 479756 | 0
2 | M824 | MILLENNIUM HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/11/2024 | DOES |  | DOES | 65832 | 0
2 | M833 | HS FOR ECONOMICS & FINANCE - M | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/3/2024 | IEH | 6/4/2024 | IEH | 9499 | 9310
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | FY24 RESO A CULINARY KITCHEN | Scope | Complete | 12/6/2023 | 3/25/2024 | 7/19/2024 | 0 | 23423 | 9419
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | In-Progress | 7/9/2024 | 10/8/2024 |  | 0 | 0 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M834 | INDEPENDENCE HS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/30/2023 | DIIR |  | DIIR | 50000 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | DOE - RESOA | FY25 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 10/16/2021 | DOES |  | DOES | 403053 | 417316
2 | M844 | M721 SPED - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ M844 | Construction | In-Progress | 3/8/2024 | EMER |  | EMER | 24515 | 4020
2 | M844 | M721 SPED - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/1/2024 | IEH | 8/11/2024 | IEH | 9423 | 272
2 | M844 | M721 SPED - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/15/2021 | DOES |  | DOES | 140265 | 0
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 7/2/2024 | DIIR | 50000
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 260000 | 0
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/3/2024 | DOES |  | DOES | 65832 | 0
2 | M855 | ELEANOR ROOSEVELT HS - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 882948 | 0
2 | M868 | I.S. 260 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 4/1/2021 | EMER |  | EMER | 18233 | 18233
2 | M868 | I.S. 260 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
2 | M868 | I.S. 260 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
2 | M868 | I.S. 260 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/26/2024 | DOES | 5/8/2024 | DOES | 50832
2 | M871 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/7/2024 | IEH | 8/19/2024 | IEH | 9690 | 0
2 | M874 | BARUCH COLLEGE CAMPUS HS - M | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/6/2024 | IEH | 5/19/2024 | IEH | 8515 | 8515
2 | M874 | BARUCH COLLEGE CAMPUS HS - M | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 160000 | 0
2 | M874 | BARUCH COLLEGE CAMPUS HS - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 4/15/2024 | DIIR | 50000 | 50000
2 | M874 | BARUCH COLLEGE CAMPUS HS - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
2 | M874 | BARUCH COLLEGE CAMPUS HS - M | DOE - RESOA | FY15 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 205255 | 0
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 2/8/2023 | 5/9/2023 |  | 0 | 23778 | 378
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 8/2/2024 | 11/4/2024 |  | 0 | 0 | 0
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | DOE - RESOA | FY13 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 289814 | 0
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
2 | M877 | NEW YORK HARBOR SCHOOL - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/22/2024 | DOES |  | DOES | 65832 | 0
2 | M883 | HARVEST COLLEGIATE HIGH SCHOOL - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/20/2024 | IEH | 9/10/2024 | IEH | 0 | 0
2 | M883 | HARVEST COLLEGIATE HIGH SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 50000
2 | M883 | HARVEST COLLEGIATE HIGH SCHOOL - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/1/2024 | IEH | 6/1/2024 | IEH | 16464 | 91
2 | M894 | A SCHOOL WITHOUT WALLS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | DOE - RESOA | FY18 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 6/27/2024 | DOER |  | DOER | 82150 | 0
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | DOE - Skilled Trades | COOLING TOWER | Construction | In-Progress | 7/22/2019 | DOES |  | DOES | 1239004 | 0
2 | M896 | NYC PUBLIC SCHOOL REPERTORY CO - M | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/2/2024 | IEH | 6/7/2024 | IEH | 12113 | 11924
2 | M896 | NYC PUBLIC SCHOOL REPERTORY CO - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/15/2024 | DIIR | 5/24/2024 | DIIR | 50000 | 37386
2 | M896 | NYC PUBLIC SCHOOL REPERTORY CO - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M912 | BEACON HS - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB FACADE @ M912 | Construction | In-Progress | 5/9/2023 | EMER |  | EMER | 319702 | 20600
2 | M912 | M035 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
2 | M912 | BEACON HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
2 | M912 | BEACON HS - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 180000 | 0
2 | M912 | BEACON HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 5/7/2024 | DOES | 50832
2 | M971 | THE SPRUCE STREET EDUCATIONAL CAMPUS - M | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
2 | M971 | THE SPRUCE STREET EDUCATIONAL CAMPUS - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 50832 | 0
2 | MBDF | BROOME STREET ACADEMY CHARTER SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 100000 | 0
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M009 | P.S. 9 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT | Construction | Complete | 5/22/2023 | IEH | 5/7/2024 | IEH | 62653 | 1056
3 | M009 | P.S. 9 - MANHATTAN | DIIT - RESOA | FY17 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35255 | 0
3 | M009 | P.S. 9 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 175000
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/18/2018 | DOER |  | DOER | 474166 | 0
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/8/2022 | DOER |  | DOER | 402261 | 0
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 280000 | 0
3 | M009 | I.S. 243 - MANHATTAN | DOE - RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0
3 | M009 | I.S. 243 - MANHATTAN | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
3 | M009 | P.S. 9 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
3 | M009 | P.S. 9 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/14/2022 | DOES |  | DOES | 141282 | 0
3 | M044 | P.S. 334 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT | Construction | Complete | 5/22/2023 | IEH | 5/7/2024 | IEH | 92667 | 1173
3 | M044 | I.S. 245 - MANHATTAN | DIIT - RESOA | FY 14 RESO A SECURITY CAMERAS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 98129 | 0
3 | M044 | I.S. 245 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
3 | M044 | I.S. 245 - MANHATTAN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 24511 | 0
3 | M044 | I.S. 245 - MANHATTAN | DOE - RESOA | RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 32774 | 0
3 | M044 | P.S. 334 - MANHATTAN | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
3 | M044 | I.S. 245 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 155275 | 0
3 | M044 | P.S. 334 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0
3 | M044 | I.S. 245 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 521275 | 0
3 | M054 | I.S. 54 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
3 | M054 | I.S. 54 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 200000 | 0
3 | M054 | I.S. 54 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/30/2023 | DOER |  | DOER | 334092 | 0
3 | M054 | I.S. 54 - MANHATTAN | DOE - RESOA | FY21 RESO A ROOM UPGRADE | Construction | In-Progress | 11/11/2022 | DOER |  | DOER | 1031251 | 0
3 | M054 | I.S. 54 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
3 | M054 | I.S. 54 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/13/2023 | DOES | 9/26/2023 | DOES | 288086 | 52897
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY19 RESO A PLAYGROUND | Construction | In-Progress | 12/23/2019 | DOER |  | DOER | 462752 | 0
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 360000 | 0
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
3 | M075 | P.S. 75 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
3 | M075 | P.S. 75 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/7/2023 | DOES | 10/18/2023 | DOES | 275863
3 | M075 | P.S. 75 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/13/2024 | DOES | 6/21/2024 | DOES | 65832 | 7763
3 | M076 | P.S. 76 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/9/2022 | DOES |  | DOES | 65729 | 0
3 | M081 | MID-MAN ADULT LEARNING CENTER - M | SCA IEH | PO18-ABATE AND REPAIRS ARE NEEDED IN VARIOUS LACTIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT | Construction | In-Progress | 5/22/2023 | IEH |  | IEH | 750 | 0
3 | M081 | MID-MAN ADULT LEARNING CENTER - M | SCA IEH | PO18-PATCH AND REPAIR PIPE INSULATION: CUSTODIAN WORKSHOP, BASEMENT STAIRCASE G&H, 2ND FLOOR HALLWAY | Construction | In-Progress | 8/20/2024 | IEH |  | IEH | 0 | 0
3 | M081 | MID-MAN ADULT LEARNING CENTER - M | DOE - Skilled Trades | PA SYSTEM REPLACEMENT | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 195731 | 45000
3 | M084 | P.S. 84 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/2/2018 | 10/1/2018 | 10/12/2018 | 0 | 30736 | 30736
3 | M084 | P.S. 84 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIRS AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT | Construction | In-Progress | 5/22/2023 | IEH |  | IEH | 18241 | 166
3 | M084 | P.S. 84 - MANHATTAN | SCA IEH | PO18-REMOVE FLOOR TILES/REPLACE THE ROOMS ARE 338.330,326,319,304,212,210,217,224, 226 | Construction | Complete | 11/13/2023 | IEH | 6/25/2024 | IEH | 248349 | 3041
3 | M084 | P.S. 84 - MANHATTAN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADE | Construction | In-Progress | 8/2/2023 | DOER |  | DOER | 38124 | 0
3 | M084 | P.S. 84 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/6/2023 | DOER |  | DOER | 308409 | 0
3 | M087 | P.S. 87 - MANHATTAN | DOE - RESOA | FY17 RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 48000 | 0
3 | M087 | P.S. 87 - MANHATTAN | DOE - RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 238196 | 0
3 | M087 | P.S. 87 - MANHATTAN | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
3 | M088 | J.H.S. 860 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M088 | J.H.S. 860 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M088 | J.H.S. 860 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M088 | J.H.S. 860 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M088 | J.H.S. 860 - MANHATTAN | SCA Emergency Response | STABILIZATION- SWB @ M088 | Construction | In-Progress | 2/29/2024 | EMER |  | EMER | 24515 | 4961
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | DOE - RESOA | FY13 RESO A AUDITORIUM BLACKBOX THE | Construction | In-Progress | 7/20/2022 | DOER |  | DOER | 110440 | 0
3 | M088 | J.H.S. 860 - MANHATTAN | DOE - RESOA | FY25 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
3 | M088 | SUCCESS ACADEMY CHARTER SCHOOL - HARLEM 1 | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 7/31/2017 | DOES |  | DOES | 121244 | 0
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 1375724 | 0
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/20/2023 | DOES | 10/31/2023 | DOES | 465819
3 | M113 | P.S. 241 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 4/2/2021 | EMER |  | EMER | 33094 | 21596
3 | M113 | P.S. 241 - MANHATTAN | SCA IEH | PO18-SEVEN FEET OF ACM PIPE INSULATION NEEDS TO BE REMOVED FROM AUDITORIUM BLOWER. STEAMFITTERS NEED | Construction | Complete | 5/5/2023 | IEH | 5/3/2024 | IEH | 0 | 0
3 | M113 | P.S. 241 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIRS ARE NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT | Construction | Complete | 5/16/2023 | IEH | 9/8/2024 | IEH | 192736 | 3177
3 | M113 | P.S. 241 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/27/2023 | DIIR | 4/9/2024 | DIIR | 75000 | 74516
3 | M113 | P.S. 241 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/21/2023 | DOES | 9/26/2023 | DOES | 299180
3 | M113 | P.S. 241 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/21/2024 | DOES | 4/3/2024 | DOES | 65832 | 10085
3 | M118 | I.S. 258 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 51 | 51
3 | M118 | LAFAYETTE ACADEMY - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/24/2024 | DIIR | 130000
3 | M118 | P.S. 333 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 440335 | 0
3 | M118 | I.S. 258 - MANHATTAN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/17/2022 | DOER |  | DOER | 117218 | 0
3 | M118 | P.S. 333 - MANHATTAN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/17/2023 | DOER |  | DOER | 249282 | 0
3 | M118 | I.S. 258 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
3 | M118 | P.S. 333 - MANHATTAN | DOE - RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 4/5/2024 | DOER |  | DOER | 9912 | 0
3 | M118 | P.S. 333 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/30/2023 | DOES | 6/25/2023 | DOES | 320915 | 316598
3 | M118 | P.S. 333 - MANHATTAN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 10/5/2016 | DOES |  | DOES | 1504948 | 0
3 | M144 | P.S. 242 - MANHATTAN | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/5/2023 | DOER |  | DOER | 57479 | 0
3 | M144 | P.S. 242 - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 196000 | 0
3 | M144 | P.S. 242 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 12/17/2021 | DOES |  | DOES | 181418 | 0
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT P | Construction | In-Progress | 5/22/2023 | IEH |  | IEH | 632 | 57
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA IEH | PO18-ABATE SINK UNDERCOATING RM 105 (AS PER AHERA RM 106) | Construction | Complete | 7/29/2024 | IEH | 8/14/2024 | IEH | 1722 | 1147
3 | M145 | WEST PREP ACADEMY - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 7/2/2024 | DIIR | 50000
3 | M145 | P.S. 145 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 12/23/2021 | DOER |  | DOER | 376754 | 0
3 | M145 | P.S. 145 - MANHATTAN | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
3 | M145 | P.S. 145 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/19/2024 | DOER |  | DOER | 350000 | 7000
3 | M145 | P.S. 145 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/22/2022 | DOES |  | DOES | 169313 | 0
3 | M145 | WEST PREP ACADEMY - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/1/2022 | DOES |  | DOES | 64366 | 0
3 | M145 | WEST PREP ACADEMY - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/16/2023 | DOES | 5/23/2023 | DOES | 269762 | 266133
3 | M145 | WEST PREP ACADEMY - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/16/2024 | DOES |  | DOES | 65832 | 0
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M149 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M149 | P.S. 149 - MANHATTAN | DOE - RESOA | FY08 RESO A HALL, STAIR & FLR RENO. | Construction | PNS | PNS | PNS | PNS | DOER | 387821 | 0
3 | M163 | P.S. 163 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR ARE NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVELLANCE REPORT P | Construction | In-Progress | 5/22/2023 | IEH |  | IEH | 122975 | 655
3 | M163 | P.S. 163 - MANHATTAN | SCA IEH | PO18-NURSE OFFICE RM 140 ACM ABATEMENT AND REMOVAL OF FLOOR MOUNTED PARTITION SUPPORTS, ROOM WAS CON | Construction | Complete | 3/25/2024 | IEH | 4/8/2024 | IEH | 5568 | 869
3 | M163 | P.S. 163 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
3 | M163 | P.S. 163 - MANHATTAN | DOE - RESOA | FY16 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/7/2019 | DOER |  | DOER | 205675 | 0
3 | M163 | P.S. 163 - MANHATTAN | DOE - Skilled Trades | VACUUM CONDENSATE PUMPS | Construction | In-Progress | 11/15/2021 | DOES |  | DOES | 61502 | 0
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/13/2023 | 7/13/2023 | 10/11/2023 | 0 | 25716 | 25716
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/13/2023 | 6/12/2023 | 11/7/2023 | 0 | 293 | 293
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/13/2023 | 2/13/2024 | 1/5/2024 | 0 | 20154 | 465
3 | M165 | P.S. 165 - MANHATTAN | Fast Track Projects | LSP GYMNASIUM FLOOR | Construction | In-Progress | 1/8/2021 | FTK |  | FTK | 832651 | 619254
3 | M165 | P.S. 165 - MANHATTAN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 595179 | 0
3 | M165 | P.S. 165 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 5/13/2022 | DOER |  | DOER | 265245 | 0
3 | M165 | I.S. 862 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/22/2023 | DOES |  | DOES | 230678 | 0
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADES | Scope | Complete | 6/5/2019 | 8/12/2019 | 8/23/2019 | 0 | 6655 | 6655
3 | M166 | P.S. 166 - MANHATTAN | SCA IEH | PO18-ACM AND LEAD DUST WIPE CLEARANCE ABATE WALL AND CEILING PLASTER IN ROOMS #210, 502(GYM) | Construction | Complete | 7/23/2024 | IEH | 8/4/2024 | IEH | 29261 | 1244
3 | M166 | P.S. 166 - MANHATTAN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
3 | M166 | P.S. 166 - MANHATTAN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 4/5/2024 | DOER |  | DOER | 40790 | 0
3 | M166 | P.S. 166 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
3 | M166 | P.S. 166 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
3 | M166 | P.S. 166 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/16/2021 | DOES |  | DOES | 189953 | 0
3 | M166 | P.S. 166 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/8/2022 | DOES |  | DOES | 206642 | 0
3 | M166 | P.S. 166 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/29/2024 | DOES | 4/9/2024 | DOES | 65832 | 10346
3 | M180 | P.S. 180 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
3 | M180 | P.S. 180 - MANHATTAN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/16/2019 | DOER |  | DOER | 170000 | 0
3 | M180 | P.S. 180 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 10/18/2022 | DOES |  | DOES | 104412 | 0
3 | M185 | P.S. 185 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
3 | M185 | P.S. 185 - MANHATTAN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/15/2022 | DOER |  | DOER | 296996 | 0
3 | M185 | P.S. 185 - MANHATTAN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/15/2022 | DOER |  | DOER | 206073 | 0
3 | M185 | P.S. 185 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP RESOA | FY19 RESO A PLAYGROUND | Scope | Complete | 12/20/2018 | 3/25/2019 | 8/7/2019 | 0 | 27407 | 27407
3 | M191 | P.S. 452 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 6/13/2024 | DIIR | 100000 | 100000
3 | M191 | P.S. 452 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 340000 | 0
3 | M191 | P.S. 452 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 90450 | 0
3 | M191 | P.S. 452 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/11/2024 | DOES |  | DOES | 65832 | 0
3 | M199 | P.S. 199 - MANHATTAN | SCA IEH | PO18-ABATE FOR FLOOR TILES IN STORAGE ROOM B4 TILES ARE 9X9 | Construction | In-Progress | 7/25/2024 | IEH |  | IEH | 635 | 60
3 | M199 | P.S. 199 - MANHATTAN | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 2/26/2021 | DOER |  | DOER | 210783 | 0
3 | M199 | P.S. 199 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 107298 | 0
3 | M199 | P.S. 199 - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
3 | M199 | P.S. 199 - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0
3 | M199 | P.S. 199 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/14/2022 | DOES |  | DOES | 89313 | 0
3 | M199 | P.S. 199 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/25/2024 | DOES | 4/1/2024 | DOES | 65832 | 15527
3 | M199 | P.S. 199 - MANHATTAN | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 9/4/2023 | DOES |  | DOES | 175407 | 0
3 | M207 | P.S. 149 - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
3 | M207 | P.S. 149 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 65832 | 0
3 | M342 | THE RIVERSIDE SCHOOL FOR MAKERS AND ARTISTS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
3 | M342 | THE RIVERSIDE SCHOOL FOR MAKERS AND ARTISTS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
3 | M342 | THE RIVERSIDE SCHOOL FOR MAKERS AND ARTISTS - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
3 | M342 | THE RIVERSIDE SCHOOL FOR MAKERS AND ARTISTS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 50832 | 0
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Scope | Complete | 6/23/2017 | 9/25/2017 | 10/10/2017 | 0 | 12421 | 12421
3 | M470 | FRANK MCCOURT HS- MANHATTAN | SCA Emergency Response | EMERGENCY TEMPORARY FUEL TANK @ M470 | Construction | In-Progress | 10/2/2023 | EMER |  | EMER | 461206 | 353738
3 | M470 | FRANK MCCOURT HS- MANHATTAN | Fast Track Projects | PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 9/6/2023 | FTK |  | FTK | 268474 | 85419
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 11/10/2022 | DOER |  | DOER | 288329 | 0
3 | M470 | INNOVATION DIPLOMA PLUS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | FY15 RESO A TECHNICAL THEATER SHOP | Scope | Complete | 5/14/2015 | 9/14/2015 | 12/23/2015 | 0 | 216895 | 147658
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 825000 | 0
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - Skilled Trades | AIR HANDLING UNIT REPLACEMENT | Construction | Complete | 9/7/2022 | DOES | 4/2/2024 | DOES | 254071 | 563318
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/27/2024 | DOES |  | DOES | 814967 | 0
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - Skilled Trades | HOT WATER HEATER SYSTEM REPLACEMENT | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 94271 | 0
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | DOE - Skilled Trades | COOLING TOWER FILL REPLACEMENT | Construction | In-Progress | 5/16/2024 | DOES |  | DOES | 121500 | 0
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
3 | M490 | THE MAXINE GREEN HIGH SCHOOL FOR IMAGINATIVE INQUIRY - M | Fast Track Projects | FY20 RESO A INTERIOR SPACES | Construction | In-Progress | 7/7/2022 | FTK |  | FTK | 190034 | 182606
3 | M490 | P.S. 859 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 116665 | 0
3 | M490 | HUNTER SCIENCE HS - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 193000
3 | M490 | HUNTER SCIENCE HS - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
3 | M490 | P.S. 859 - MANHATTAN | DOE - RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 88818 | 0
3 | M490 | P.S. 859 - MANHATTAN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/15/2024 | DOER |  | DOER | 389752 | 0
3 | M490 | P.S. 859 - MANHATTAN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 312863 | 0
3 | M490 | SCHOOL SAFETY - MANHATTAN | DOE - Skilled Trades | INTERIOR SPACES | Construction | In-Progress | 11/1/2020 | DOES |  | DOES | 663032 | 0
3 | M490 | SCHOOL SAFETY - MANHATTAN | DOE - Skilled Trades | LIGHTING UPGRADE | Construction | In-Progress | 3/12/2021 | DOES |  | DOES | 145591 | 0
3 | M490 | SCHOOL SAFETY - MANHATTAN | DOE - Skilled Trades | INTERIOR SPACES | Construction | In-Progress | 3/29/2021 | DOES |  | DOES | 302521 | 0
3 | M490 | SCHOOL BASED HEALTH CENTER - MANHATTAN | DOE - Skilled Trades | STUDENT BATHROOM UPGRADE | Construction | In-Progress | 7/2/2021 | DOES |  | DOES | 620614 | 0
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/10/2024 | DOES |  | DOES | 65832 | 0
3 | M506 | EDWARD A. REYNOLDS WEST SIDE HS-M | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/15/2021 | DOES |  | DOES | 278403 | 0
3 | M506 | EDWARD A. REYNOLDS WEST SIDE HS-M | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/6/2022 | DOES |  | DOES | 85598 | 0
3 | M506 | EDWARD A. REYNOLDS WEST SIDE HS-M | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/21/2023 | DOES | 10/25/2023 | DOES | 326168 | 301442
3 | M506 | EDWARD A. REYNOLDS WEST SIDE HS-M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/22/2024 | DOES |  | DOES | 50832 | 0
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY18 RESO A MEDIA CENTER UPGRADE | Scope | Complete | 4/24/2018 | 8/23/2018 | 8/20/2018 | 0 | 11728 | 11728
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 2/1/2023 | 6/1/2023 | 2/6/2023 | 0 | 2602 | 2602
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 50000 | 0
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 7/10/2020 | DIIR |  | DIIR | 100000 | 0
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 7/10/2020 | DIIR |  | DIIR | 50000 | 0
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 2/17/2022 | DIIR |  | DIIR | 111666 | 0
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 40000 | 0
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 153995 | 0
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
3 | M841 | M811 SPED - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/8/2021 | EMER |  | EMER | 33094 | 25923
3 | M841 | M811 SPED - MANHATTAN | SCA IEH | PO18-ABATE CEILING IN THE STAIRCASE B AND C STAIRCASE C IS ABOUT 4 FEET BY 4 FEET AND STAIRCASES B 1 | Construction | Complete | 6/3/2024 | IEH | 6/9/2024 | IEH | 36679 | 27929
3 | M841 | M811 SPED - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 3/21/2022 | DOES |  | DOES | 72385 | 374843
3 | M841 | M811 SPED - MANHATTAN | DOE - Skilled Trades | CHILLED WATER COIL REPLACEMENT | Construction | In-Progress | 2/23/2024 | DOES |  | DOES | 67305 | 0
3 | M932 | P.S. 859 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
3 | MQAE | HARLEM HEBREW LANGUAGE CHARTER SCHOOL | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
3 | MQAE | HARLEM HEBREW LANGUAGE CHARTER SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 99648 | 0
4 | M007 | P.S. 7 - MANHATTAN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 10/23/2020 | FTK |  | FTK | 207020 | 161939
4 | M013 | P.S. 497 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR CAFETERIA CEILING | Construction | Complete | 5/28/2024 | IEH | 6/2/2024 | IEH | 39023 | 31054
4 | M013 | P.S. 497 - MANHATTAN | DOE - RESOA | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/16/2018 | DOER |  | DOER | 127861 | 0
4 | M013 | EAST HARLEM SCHOLARS ACADEMY CHARTER SCHOOL II - M | DOE - RESOA | FY19 RESO A TOILET STUDENTS | Construction | In-Progress | 6/21/2019 | DOER |  | DOER | 79836 | 0
4 | M013 | P.S. 497 - MANHATTAN | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/15/2023 | DOER |  | DOER | 60436 | 0
4 | M013 | EAST HARLEM SCHOLARS ACADEMY CHARTER SCHOOL II - M | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 5/9/2022 | DOER |  | DOER | 37611 | 0
4 | M013 | CENTRAL PARK EAST HS - MANHATTAN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 3/5/2020 | DOER |  | DOER | 75000 | 0
4 | M013 | P.S. 497 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 260000 | 0
4 | M013 | CENTRAL PARK EAST HS - MANHATTAN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 288000 | 0
4 | M013 | P.S. 497 - MANHATTAN | DOE - Skilled Trades | ACE BOILER BURNER CONVERSIONS | Construction | In-Progress | 4/29/2022 | DOES |  | DOES | 3390158 | 0
4 | M013 | CENTRAL PARK EAST HS - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 3/27/2023 | DOES | 4/17/2023 | DOES | 481214 | 474741
4 | M013 | CENTRAL PARK EAST HS - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/1/2024 | DOES | 5/16/2024 | DOES | 65832 | 378
4 | M013 | CENTRAL PARK EAST HS - MANHATTAN | DOE - Skilled Trades | GYM CEILING | Construction | In-Progress | 5/5/2023 | DOES |  | DOES | 167171 | 0
4 | M045 | P.S. 37 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL FOR PIPE INSULATION ON A STEAM PIPE, 8' LOCATED IN THE STORAGE ROOM THE BASEMENT AR | Construction | Complete | 8/1/2024 | IEH | 9/18/2024 | IEH | 1879 | 1304
4 | M045 | P.S. 37 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
4 | M045 | P.S. 37 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 446089 | 0
4 | M045 | P.S. 37 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/10/2024 | DOES |  | DOES | 65832 | 0
4 | M045 | P.S. 37 - MANHATTAN | DOE - Skilled Trades | SWIMMING POOL | Construction | In-Progress | 5/29/2024 | DOES |  | DOES | 428076 | 0
4 | M050 | P.S. 964 - MANHATTAN | SCA IEH | PO18-ROOM 122, ABATE 10 SQ. FT. CEILING PLASTER, 10 L.F. PIPE INSULATION ROOM 208, ABATE 5 SQ. FT. W | Construction | In-Progress | 5/29/2024 | IEH |  | IEH | 575 | 0
4 | M050 | P.S. 964 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 6/24/2024 | DIIR | 60000 | 60000
4 | M050 | NY CENTER FOR AUTISM CHARTER - M | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/11/2023 | DOER |  | DOER | 189281 | 0
4 | M057 | P.S. 57 - MANHATTAN | SCA IEH | PO18-AUDITORIUM MATERIALS FOR MOLD REMOVAL/REPLACEMENT: REMOVE 12X12 BEIGE & PEACH FLOOR TILES, 100 | Construction | Complete | 5/26/2023 | IEH | 5/3/2024 | IEH | 37626 | 37626
4 | M072 | P.S. 72 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SIDEWALK BRIDGE @ PS72M | Construction | In-Progress | 10/2/2023 | EMER |  | EMER | 199023 | 95377
4 | M072 | P.S. 72 - MANHATTAN | SCA IEH | PO18-ABATE FIBERGLASS INSULATION ABOUT 100 LINEAR FEET NEEDS TO BE REMOVED BASEMENT | Construction | Complete | 9/27/2023 | IEH | 6/25/2024 | IEH | 18101 | 472
4 | M072 | P.S. 72 - MANHATTAN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 7/13/2021 | FTK |  | FTK | 119228 | 111965
4 | M072 | P.S. 72 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
4 | M072 | P.S. 72 - MANHATTAN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
4 | M072 | P.S. 72 - MANHATTAN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 1/23/2024 | DOEL |  | DOEL | 55323 | 50323
4 | M072 | P.S. 72 - MANHATTAN | DOE - RESOA | FY17 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 79400 | 0
4 | M072 | P.S. 72 - MANHATTAN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/1/2022 | DOER |  | DOER | 197247 | 0
4 | M072 | P.S. 72 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 6/22/2022 | DOES |  | DOES | 444648 | 0
4 | M083 | P.S. 83 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN THE GYM 2ND FLOOR APPROXIMATELY 64 SQFT. FLOOR TILES 9X9, CRAC | Construction | In-Progress | 3/28/2024 | IEH |  | IEH | 963 | 388
4 | M083 | P.S. 182 - MANHATTAN | DOE - RESOA | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 11/27/2019 | DOER |  | DOER | 93994 | 0
4 | M083 | P.S. 83 - MANHATTAN | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
4 | M083 | P.S. 83 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
4 | M083 | P.S. 182 - MANHATTAN | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0
4 | M096 | P.S. 96 - MANHATTAN | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 764952 | 0
4 | M096 | P.S. 96 - MANHATTAN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADE | Construction | In-Progress | 4/1/2024 | DOER |  | DOER | 101050 | 0
4 | M096 | P.S. 96 - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
4 | M099 | I.S. 224 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOM 206 APPROX. 672SF | Construction | Complete | 9/27/2023 | IEH | 4/8/2024 | IEH | 49691 | 1876
4 | M099 | I.S. 224 - MANHATTAN | SCA IEH | PO18-M385@M099 SUCCESS ACADEMY #2024-63662 DRILL TO INSTALL A WIRELESS ACCESS POINT ON CEILING | Construction | Complete | 8/1/2024 | IEH | 8/10/2024 | IEH | 71073 | 649
4 | M099 | I.S. 224 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 5/24/2024 | DIIR | 50000 | 50000
4 | M099 | RENNAISSANCE CHARTER HS - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 10/16/2023 | DOES |  | DOES | 62543 | 0
4 | M099 | I.S. 224 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/11/2024 | DOES |  | DOES | 518284 | 0
4 | M101 | PS/IS 375 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 229748 | 0
4 | M102 | P.S. 102 - MANHATTAN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 9/20/2023 | DOEL | 3/26/2024 | DOEL | 97853 | 97853
4 | M102 | M169 SPED - MANHATTAN | DOE - RESOA | FY14 RESO A PLAYGROUND REDEVELOPMEN | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
4 | M102 | P.S. 102 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 95448 | 0
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 8/25/2022 | DOER |  | DOER | 34498 | 0
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 30194 | 0
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/6/2017 | DOES |  | DOES | 252768 | 0
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY17 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/10/2019 | DOER |  | DOER | 212061 | 0
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/1/2018 | DOER |  | DOER | 36612 | 0
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 413660 | 0
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/15/2022 | DOER |  | DOER | 174853 | 0
4 | M108 | P.S. 108 - MANHATTAN | DOE - RESOA | FY23 RESO A STEM LAB | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 100141 | 0
4 | M112 | P.S. 112 - MANHATTAN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 150000 | 0
4 | M112 | P.S. 112 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-R/R STEAM LEAK IN RM EB11 (TEST WALL) | Construction | In-Progress | 12/22/2023 | IEH |  | IEH | 969 | 394
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-ABATEMENT OF COATING OVER FIBERGLASS CEILING TILES IN ROOM 311(MENS LOUNGE ROOM), FLOOR TILES, | Construction | Complete | 2/15/2024 | IEH | 6/7/2024 | IEH | 44883 | 4224
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-ABATE FLOOR IN WEST #322 (CORE DRILLING REQUIRED) THROUGH THE CEILING IN RM #222. NEW FEED IS N | Construction | Complete | 6/28/2024 | IEH | 7/2/2024 | IEH | 6961 | 661
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-ABATED AND REPAIR 9X9 FLOOR TILES ROOM 310. TILES ARE DETERIORATING, CRACKED AND POPPING UP | Construction | Complete | 7/1/2024 | IEH | 7/24/2024 | IEH | 7963 | 588
4 | M117 | I.S. 12 - MANHATTAN | SCA IEH | PO18-TEST FOR ACM IN GYM ALL LAYERS OF FLOORING CORE DRILLING NEEDED TO INSTALL VOLLYBALL POST ASSIG | Construction | In-Progress | 7/29/2024 | IEH |  | IEH | 756 | 181
4 | M117 | M138 SPED - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 55000 | 0
4 | M117 | I.S. 12 - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/2/2024 | DOER |  | DOER | 422002 | 0
4 | M117 | M138 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
4 | M117 | I.S. 12 - MANHATTAN | DOE - Skilled Trades | ACE BOILER BURNER CONVERSIONS | Construction | In-Progress | 5/24/2021 | DOES |  | DOES | 2974717 | 0
4 | M117 | I.S. 12 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/18/2022 | DOES |  | DOES | 173826 | 0
4 | M117 | I.S. 12 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/30/2023 | DOES | 10/25/2023 | DOES | 464694 | 363508
4 | M121 | P.S. 38 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/31/2022 | EMER |  | EMER | 33094 | 15855
4 | M121 | P.S. 38 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
4 | M121 | P.S. 38 - MANHATTAN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 11/13/2023 | DOEL | 2/20/2024 | DOEL | 101247 | 101247
4 | M121 | P.S. 38 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
4 | M121 | P.S. 38 - MANHATTAN | DOE - Skilled Trades | DOMESTIC WATER BOOSTER PUMPS | Construction | In-Progress | 3/3/2021 | DOES |  | DOES | 68672 | 0
4 | M121 | P.S. 38 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 10/20/2022 | DOES |  | DOES | 65999 | 0
4 | M121 | P.S. 38 - MANHATTAN | DOE - Skilled Trades | BOILER FEED & VACUUM PUMP REPLACEMENT | Construction | In-Progress | 3/11/2024 | DOES |  | DOES | 60712 | 0
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/13/2023 | DOER |  | DOER | 118865 | 0
4 | M146 | P.S. 146 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION - CONCRETE/STEEL SPALL | Construction | In-Progress | 8/4/2022 | EMER |  | EMER | 55686 | 23831
4 | M146 | P.S. 146 - MANHATTAN | SCA IEH | PO18-ABATE PIPE INSULATION GYM B/R., LW 136300 8-10' | Construction | Complete | 12/14/2023 | IEH | 4/8/2024 | IEH | 20960 | 588
4 | M146 | P.S. 146 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION IN THE CRAWLSPACE APPROXIMATELY 10 FT OF PIPING ON BOTH LINES IN | Construction | In-Progress | 7/2/2024 | IEH |  | IEH | 635 | 60
4 | M146 | P.S. 146 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/1/2023 | DOER |  | DOER | 500000 | 9025
4 | M146 | P.S. 146 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0
4 | M146 | P.S. 146 - MANHATTAN | DOE - Skilled Trades | STEAM PIPING REPLACEMENT | Construction | Complete | 10/2/2023 | DOES | 4/3/2024 | DOES | 115315 | 113671
4 | M155 | I.S. 377 - MANHATTAN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/23/2022 | DOER |  | DOER | 41643 | 0
4 | M155 | P.S. 155 - MANHATTAN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 5/9/2016 | DOES |  | DOES | 75200 | 0
4 | M155 | P.S. 155 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/14/2023 | DOES |  | DOES | 342806 | 0
4 | M155 | P.S. 155 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 65832 | 0
4 | M171 | P.S. 171 - MANHATTAN | SCA IEH | PO18-REMOVE TWO(2) DAMAGED ACM PIPE INSULATION IN ROOM 214 ON WALL #3, APPROXIMATELY 13 LF EACH | Construction | Complete | 6/24/2024 | IEH | 6/30/2024 | IEH | 20416 | 13072
4 | M171 | P.S. 171 - MANHATTAN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 1/13/2020 | FTK |  | FTK | 228869 | 212458
4 | M171 | P.S. 171 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/22/2024 | DIIR | 6/28/2024 | DIIR | 222000 | 222000
4 | M171 | P.S. 171 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA IEH | PO18-PERFORM ABATEMENT & ONE 4' INCH CORE DRILLING ON THE FLOOR LOCATED IN THE WORK ROOM IN LIBRARY | Construction | In-Progress | 8/23/2024 | IEH |  | IEH | 60 | 60
4 | M435 | I.S. 825 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/10/2024 | DIIR | 5/10/2024 | DIIR | 80000 | 80000
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 170000 | 0
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/20/2023 | DOES |  | DOES | 935298 | 0
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/8/2022 | DOES |  | DOES | 193378 | 0
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 6/28/2024 | DOES | 65832
4 | M495 | PARK EAST HS - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 75000
4 | M495 | PARK EAST HS - MANHATTAN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 3/28/2023 | DOER |  | DOER | 43664 | 0
4 | M495 | PARK EAST HS - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
4 | M495 | PARK EAST HS - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 2/21/2023 | DOES |  | DOES | 178998 | 0
4 | M495 | PARK EAST HS - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/22/2024 | DOES |  | DOES | 299106 | 0
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA Emergency Response | EMERGENCY STABILIZATION- EXTERIOR MASONRY | Construction | In-Progress | 11/28/2022 | EMER |  | EMER | 1020799 | 989462
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 7/30/2021 | FTK |  | FTK | 145232 | 132840
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | DOE - Skilled Trades | ROOFS | Construction | In-Progress | 10/4/2023 | DOES |  | DOES | 460219 | 0
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/7/2024 | DIIR | 50000 | 50000
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | DOE - RESOA | FY25 RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/16/2024 | DOES |  | DOES | 704000 | 0
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 390000 | 0
5 | M030 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M030 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M030 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M030 | M138 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M030 | P.S. 30 - MANHATTAN | SCA IEH | PO18-ACM ABATEMENT, | Construction | Complete | 12/5/2022 | IEH | 1/9/2023 | IEH | 912 | 337
5 | M030 | P.S. 30 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/8/2024 | DIIR | 6/7/2024 | DIIR | 100000 | 100000
5 | M030 | M138 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/23/2024 | DIIR | 4/8/2024 | DIIR | 50000 | 50000
5 | M030 | M138 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
5 | M030 | P.S. 30 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/9/2024 | DOES | 4/19/2024 | DOES | 65832 | 11355
5 | M036 | P.S. 36 - MANHATTAN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 1/10/2018 | 2/9/2018 | 3/26/2018 | 0 | 11151 | 11151
5 | M036 | P.S. 36 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
5 | M036 | P.S. 36 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
5 | M036 | P.S. 36 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 330000
5 | M036 | P.S. 36 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/14/2022 | DOES |  | DOES | 83169 | 0
5 | M036 | P.S. 36 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/25/2024 | DOES | 4/5/2024 | DOES | 65832 | 9586
5 | M043 | URBAN ASSEMBLY SCHOOL FOR THE PERFORMING ARTS | Fast Track Projects | FY18 RESO A LIBRARY UPGRADES | Construction | In-Progress | 10/4/2019 | FTK |  | FTK | 247362 | 191852
5 | M043 | URBAN ASSEMBLY SCHOOL FOR THE PERFORMING ARTS | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/1/2024 | DOER |  | DOER | 129688 | 0
5 | M043 | I.S. 286 - MANHATTAN | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 5/31/2022 | DOER |  | DOER | 442101 | 0
5 | M043 | URBAN ASSEMBLY SCHOOL FOR THE PERFORMING ARTS | DOE - RESOA | FY22 RESO A FLOORING | Construction | In-Progress | 7/17/2023 | DOER |  | DOER | 75918 | 0
5 | M043 | I.S. 367 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 10/30/2023 | DOES |  | DOES | 62190 | 0
5 | M043 | I.S. 286 - MANHATTAN | DOE - Skilled Trades | CHARTER MATCH FLOOR REPLACEMENT | Construction | In-Progress | 8/15/2021 | DOES |  | DOES | 1114304 | 0
5 | M043 | URBAN ASSEMBLY SCHOOL FOR THE PERFORMING ARTS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 65832 | 0
5 | M046 | P.S. 46 - MANHATTAN | SCA IEH | PO18-COLD LINE VALVE # 23 HAS ACM LOCATED IN THE BASEMENT HALLWAY PICTURES ARE ATTACHED | Construction | Complete | 8/19/2024 | IEH | 9/15/2024 | IEH | 21531 | 1739
5 | M046 | P.S. 46 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 153000 | 0
5 | M046 | P.S. 46 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/28/2024 | DIIR | 9/6/2024 | DIIR | 100000
5 | M046 | P.S. 46 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
5 | M046 | P.S. 46 - MANHATTAN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/17/2022 | DOER |  | DOER | 273745 | 0
5 | M079 | M079 SPED - MANHATTAN | Fast Track Projects | IPDVS INSTALLATIONS | Construction | In-Progress | 9/15/2022 | FTK |  | FTK | 530851 | 501883
5 | M079 | M079 SPED - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/5/2022 | DOER |  | DOER | 230949 | 0
5 | M079 | M079 SPED - MANHATTAN | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/3/2023 | DOER |  | DOER | 377957 | 0
5 | M079 | M079 SPED - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 12/20/2021 | DOES |  | DOES | 140016 | 0
5 | M079 | M079 SPED - MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 4/11/2024 | DOES |  | DOES | 578713 | 1408
5 | M092 | P.S. 92 - MANHATTAN | SCA IEH | PO18-ABATE PIPE INSULATION WATER MAIN IN RM B19 (GAS METER RM AHERA SPACE ID 1016) PIPE COVER ITSELF | Construction | Complete | 8/26/2024 | IEH | 9/26/2024 | IEH | 648 | 73
5 | M092 | P.S. 92 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
5 | M092 | P.S. 92 - MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 8/4/2018 | DOES |  | DOES | 103926 | 0
5 | M092 | P.S. 92 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/28/2023 | DOES | 10/24/2023 | DOES | 315603
5 | M092 | P.S. 92 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 1330000 | 0
5 | M092 | P.S. 92 - MANHATTAN | Trust For Public Land | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | TPL | 400000 | 0
5 | M123 | P.S. 123 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 12/20/2023 | DIIR | 65000 | 37284
5 | M123 | P.S. 123 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 174266 | 0
5 | M123 | P.S. 123 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/29/2024 | DOES |  | DOES | 963000 | 0
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Scope | Complete | 10/23/2018 | 1/25/2019 | 8/16/2019 | 0 | 62290 | 62290
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 3/1/2023 | 6/30/2023 | 7/11/2023 | 0 | 13440 | 13439
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A POOL UPGRADE | Scope | Complete | 3/1/2023 | 5/31/2023 | 10/31/2023 | 0 | 135143 | 135143
5 | M125 | P.S. 125 - MANHATTAN | SCA Emergency Response | EMR PROTECTIVE MEASURES- IDA | Construction | In-Progress | 9/21/2021 | EMER |  | EMER | 92837 | 92837
5 | M125 | P.S. 125 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 286000 | 0
5 | M125 | P.S. 125 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
5 | M125 | I.S. 362 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
5 | M125 | I.S. 362 - MANHATTAN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 1/10/2024 | DOEL |  | DOEL | 134526 | 134526
5 | M125 | I.S. 362 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 719000 | 0
5 | M129 | P.S. 129 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: RM :233 APPROX. 200SF RM: 234 APPROX. 675SF RM: 236 APP | Construction | Complete | 3/30/2023 | IEH | 9/10/2024 | IEH | 57 | 57
5 | M129 | P.S. 129 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING ROOMS: RM: 217 APPROX. 510SF RM: 219 APPROX. 645 | Construction | In-Progress | 9/27/2023 | IEH |  | IEH | 773 | 198
5 | M129 | P.S. 129 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION & RISER VALVE NEEDS TO BE ABATED LOCATION: 1ST FL HALLWAY ACROSS | Construction | Complete | 8/20/2024 | IEH | 9/14/2024 | IEH | 9231 | 1310
5 | M129 | P.S. 129 - MANHATTAN | SCA IEH | PO18-OIL TANK ROOM ABATE 10 L.F. PIPE INSULATION, SPRAYED RED - BOILER ROOM ABATE 10 L.F. FROM BURNE | Construction | In-Progress | 9/24/2024 | IEH |  | IEH | 0 | 0
5 | M129 | SCHOOL OF EARTH EXPLORATION AND DISCOVERY HARLEM (SEED HARLEM) | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
5 | M129 | P.S. 129 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
5 | M129 | P.S. 129 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/22/2021 | DOER |  | DOER | 269150 | 0
5 | M133 | P.S. 133 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 9/10/2021 | EMER |  | EMER | 11177 | 11177
5 | M133 | P.S. 133 - MANHATTAN | SCA IEH | PO18-REPAIR LEAKING RADIATORE ON 3RD FLOOR HALLWAY | Construction | In-Progress | 11/1/2023 | IEH |  | IEH | 5067 | 0
5 | M133 | P.S. 133 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 257505 | 0
5 | M133 | P.S. 133 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | Complete | 12/1/2021 | DOER | 3/29/2023 | DOER | 324090 | 259218
5 | M133 | P.S. 133 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/7/2021 | DOES |  | DOES | 173926 | 0
5 | M133 | P.S. 133 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/16/2024 | DOES |  | DOES | 172000 | 0
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M136 | SCHOOL SAFETY - MANHATTAN | SCA IEH | PO18-ABATEMENT NEEDED ON ELECTRICAL WIRE INSULATION WHITE AND RED | Construction | Complete | 1/17/2024 | IEH | 6/27/2024 | IEH | 20215 | 1183
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 11/3/2020 | FTK |  | FTK | 528452 | 509836
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 182118 | 0
5 | M136 | MOTT HALL HS - MANHATTAN | DIIT - RESOA | ENY TECHNOLOGY | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 120163 | 0
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | DIIT - RESOA | ENY TECHNOLOGY | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 119257 | 0
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
5 | M136 | MOTT HALL HS - MANHATTAN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
5 | M136 | MOTT HALL HS - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 312360 | 9700
5 | M136 | MOTT HALL HS - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 145000 | 0
5 | M136 | I.S. 302 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 6/5/2023 | DOES |  | DOES | 62190 | 0
5 | M136 | EAGLE ACADEMY FOR YOUNG MEN OF HARLEM | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 65832 | 0
5 | M154 | P.S. 154 - MANHATTAN | SCA IEH | PO18-APPROX 10 LINEAR FEET OF ABATEMENT IS NEEDED FOR ALL (3) VALVES LOCATIONS ARE 1 - HALLWAY BY EL | Construction | Complete | 3/28/2024 | IEH | 4/21/2024 | IEH | 36984 | 29460
5 | M154 | P.S. 154 - MANHATTAN | SCA IEH | PO18-CUSTODIAN'S LOCKER ROOM PICK UP 2 SQ. FT. FLOOR TILES AND ENCAPSULATE FLOOR | Construction | In-Progress | 7/22/2024 | IEH |  | IEH | 1720 | 145
5 | M154 | P.S. 154 - MANHATTAN | Fast Track Projects | LSP- VACUUM PUMPS REPLACEMENT | Construction | In-Progress | 5/2/2024 | FTK |  | FTK | 100125 | 0
5 | M154 | P.S. 154 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
5 | M154 | P.S. 154 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
5 | M154 | P.S. 154 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/25/2022 | DOES |  | DOES | 116620 | 0
5 | M154 | P.S. 154 - MANHATTAN | DOE - Skilled Trades | HEATING PLANT UPGRADE | Construction | In-Progress | 8/11/2023 | DOES |  | DOES | 72922 | 0
5 | M161 | P.S. 161 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN AUDITORIUM JEREMY FOGARTY JFOGARTY@SCHOOLS.NYC.GOV | Construction | Complete | 8/8/2023 | IEH | 4/20/2024 | IEH | 62189 | 61614
5 | M161 | P.S. 161 - MANHATTAN | SCA IEH | PO18-REMOVE ACM TILE UNDER CABINETS ROOM 117 | Construction | Complete | 9/15/2023 | IEH | 9/10/2024 | IEH | 0 | 0
5 | M161 | P.S. 161 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
5 | M161 | P.S. 161 - MANHATTAN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/13/2023 | DOER |  | DOER | 65741 | 0
5 | M161 | P.S. 161 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/16/2019 | DOES |  | DOES | 205755 | 0
5 | M161 | P.S. 161 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/10/2024 | DOES | 6/20/2024 | DOES | 65832
5 | M161 | P.S. 161 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/6/2024 | DOES |  | DOES | 308022 | 0
5 | M161 | P.S. 161 - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 9/23/2024 | DOES |  | DOES | 666000 | 0
5 | M175 | P.S. 175 HENRY H GARNET - M | SCA IEH | PO18-ABATEMENT ON FUEL LINE PIPES AND VALVES | Construction | Complete | 1/8/2024 | IEH | 6/29/2024 | IEH | 17202 | 1017
5 | M175 | P.S. 175 HENRY H GARNET - M | SCA IEH | PO18-PLEASE REMOVE ASBESTOS AROUND GATE VALVES AND LINE, SO PLUMBERS CAN REPLACE VALVES TO ALLOW WAT | Construction | In-Progress | 9/24/2024 | IEH |  | IEH | 0 | 0
5 | M175 | P.S. 175 HENRY H GARNET - M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
5 | M175 | P.S. 175 HENRY H GARNET - M | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/27/2022 | DOER |  | DOER | 389963 | 0
5 | M175 | P.S. 175 HENRY H GARNET - M | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 3/4/2024 | DOER |  | DOER | 426210 | 0
5 | M175 | P.S. 175 HENRY H GARNET - M | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 3/1/2024 | DOES |  | DOES | 126420 | 0
5 | M175 | P.S. 175 HENRY H GARNET - M | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 507000 | 0
5 | M194 | HARLEM VILLAGE ACADEMIES HIGH CHARTER SCHOOL - MANHATTAN | DIIT - Project Connect | COMPUTERS | Purch & Install | In-Progress | 9/1/2021 | DIIT |  | DIIT | 60000 | 0
5 | M194 | P.S. 194 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 150000
5 | M194 | P.S. 194 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 247000 | 0
5 | M194 | P.S. 194 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/12/2022 | DOES |  | DOES | 67910 | 0
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/12/2024 | DIIR | 6/14/2024 | DIIR | 50000 | 50000
5 | M195 | I.S. 195 - MANHATTAN | DOE - RESOA | FY10 RESO A GYM RENOVATION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 11/21/2022 | DOES |  | DOES | 443438 | 0
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M197 | P.S. 197 - MANHATTAN | SCA IEH | PO18-ROOMS 107,125,221.227,229 NEEDS TESTING AND ABATEMENT 9X9 FLOOR TILES | Construction | Complete | 2/12/2024 | IEH | 5/30/2024 | IEH | 168464 | 2797
5 | M197 | P.S. 197 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 263698 | 0
5 | M197 | P.S. 197 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 55000 | 0
5 | M197 | P.S. 197 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 150000
5 | M197 | P.S. 197 - MANHATTAN | DOE - RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
5 | M200 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M200 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M200 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M200 | M811 SPED - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M200 | P.S. 200 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M200 | P.S. 200 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M200 | P.S. 200 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M200 | P.S. 200 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M200 | P.S. 200 - MANHATTAN | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
5 | M200 | P.S. 200 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 5/27/2024 | DIIR | 75000 | 23310
5 | M200 | M811 SPED - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 145000 | 0
5 | M200 | P.S. 200 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
5 | M200 | P.S. 200 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/29/2024 | DOES | 4/10/2024 | DOES | 65832 | 10177
5 | M223 | I.S. 223 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 3/19/2018 | EMER |  | EMER | 327887 | 230409
5 | M223 | SISULU-WALKER CHARTER SCHOOL OF HARLEM | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 5/25/2024 | IEH | 23473 | 23284
5 | M223 | I.S. 223 - MANHATTAN | DIIT - RESOA | FY12 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
5 | M223 | I.S. 223 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
5 | M223 | I.S. 223 - MANHATTAN | DOE - RESOA | FY15 RESO A SCIENCE LAB CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
5 | M223 | I.S. 223 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
5 | M371 | P.S. 318 - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 5/9/2024 | IEH | 10805 | 10616
5 | M371 | P.S. 318 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/21/2023 | DIIR | 4/15/2024 | DIIR | 60000 | 60000
5 | M371 | P.S. 318 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
5 | M389 | SUCCESS ACADEMY CHARTER SCHOOL - HARLEM 6 | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/1/2024 | IEH | 6/3/2024 | IEH | 11607 | 11418
5 | M484 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/1/2024 | IEH | 8/8/2024 | IEH | 10724 | 0
5 | M484 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
5 | M484 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 3438 | 0
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 11/21/2022 | DOES |  | DOES | 568857 | 0
5 | M911 | HARLEM RENAISSANCE HS - M | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 128087 | 0
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY19 RESO A PLAYGROUND UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/26/2024 | IEH | 4/30/2024 | IEH | 23200 | 23200
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 166851 | 0
5 | M916 | TEACHER'S COLLEGE COMMUNITY SCHOOL- M | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 175000
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/10/2024 | DOES |  | DOES | 65832 | 0
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/11/2024 | DOES |  | DOES | 253000 | 0
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/13/2024 | 9/13/2024 | 9/5/2024 | 0 | 24802 | 14664
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Scope | In-Progress | 9/4/2024 | 12/5/2024 |  | 0 | 0 | 0
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 0 | 233 | 233
6 | M004 | P.S. 4 - MANHATTAN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M004 | P.S. 4 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M004 | P.S. 4 - MANHATTAN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 16562 | 0
6 | M004 | P.S. 4 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 130000 | 0
6 | M004 | P.S. 4 - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
6 | M004 | P.S. 4 - MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMPS | Construction | In-Progress | 6/11/2021 | DOES |  | DOES | 672485 | 0
6 | M005 | P.S. 5 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
6 | M005 | P.S. 5 - MANHATTAN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 12/22/2022 | DOER |  | DOER | 136794 | 0
6 | M005 | P.S. 5 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 650000 | 0
6 | M005 | P.S. 5 - MANHATTAN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M008 | P.S. 8 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 500000 | 0
6 | M008 | P.S. 8 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 10/28/2021 | DOES |  | DOES | 112875 | 0
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ROOM 306B ASBESTOS ABATEMENT AREA TESTED POSITIVE. D75 SCHOOL MOVING IN BMURPHY16@ SCHOOLS.NYC | Construction | In-Progress | 8/28/2023 | IEH |  | IEH | 807 | 57
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ABATE & REPLACE 9X9 FLOOR TILES AND MISS MATCHED FLOOR TILE. 1ST FLOOR 1,284 SQ FT., 3RD FL | Construction | Complete | 3/11/2024 | IEH | 4/30/2024 | IEH | 22286 | 319
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-REMOVAL OF ABESTOS FROM PLUMBING PIPECHSES ROOM 314 INSIDE PIPECHASE HAS WHITE AIRCELL ON PIPE | Construction | Complete | 5/8/2024 | IEH | 6/24/2024 | IEH | 14620 | 13775
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ROOM 212, 7 L.F. WATER DAMAGED PIPE INSULATION ROOM 306A, 9 SQ. FT. BROKEN & MISSING FLOOR TILE | Construction | In-Progress | 7/1/2024 | IEH |  | IEH | 575 | 0
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ACM REMOVAL OF PIPE INSULATION IN THE CRAWL SPACE. 2 LINES PAINTED RED WE WILL NEED APPROXIMATE | Construction | Complete | 8/2/2024 | IEH | 8/29/2024 | IEH | 1034 | 284
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ABATE CEILING TILES IN CLOSET IN CR # B07 THAT ARE FALLEN 1X 1 CEIILING TILES AS PER AHERA BOOK | Construction | Complete | 8/15/2024 | IEH | 8/16/2024 | IEH | 2453 | 1328
6 | M028 | P.S. 28 - MANHATTAN | SCA IEH | PO18-ABATE APPROX. 30LF OF CONDUCTORS ACM WIRING BETWEEN EXISTING CT CABINET AND EXISTING FACILITY M | Construction | In-Progress | 8/16/2024 | IEH |  | IEH | 1480 | 905
6 | M028 | P.S. 28 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
6 | M028 | P.S. 28 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/4/2024 | DOES | 4/15/2024 | DOES | 65832 | 16223
6 | M048 | M138 SPED - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 59000 | 0
6 | M048 | P.S. 48 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
6 | M048 | P.S. 48 - MANHATTAN | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 6/23/2023 | DOER |  | DOER | 191529 | 0
6 | M048 | P.S. 48 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/19/2024 | DOER |  | DOER | 200000 | 9025
6 | M052 | J.H.S. 52 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
6 | M052 | INWOOD EARLY COLLEGE FOR HEALTH AND INFORMATION TECHNOLOGY (PTECH) | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
6 | M052 | J.H.S. 52 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 50000
6 | M052 | J.H.S. 52 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
6 | M052 | INWOOD EARLY COLLEGE FOR HEALTH AND INFORMATION TECHNOLOGY (PTECH) | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
6 | M052 | J.H.S. 52 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
6 | M052 | J.H.S. 52 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/3/2023 | DOES |  | DOES | 483536 | 0
6 | M052 | J.H.S. 52 - MANHATTAN | Trust For Public Land | TPL � EXTREME WEATHER PLAYGROUND UPGRADE | Construction | Complete | 11/16/2023 | TPL | 6/26/2024 | TPL | 2349223 | 2158049
6 | M090 | I.S. 319 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 3/22/2022 | EMER |  | EMER | 11437 | 11437
6 | M090 | I.S. 319 - MANHATTAN | Fast Track Projects | LSP FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 184356 | 0
6 | M090 | I.S. 319 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
6 | M090 | M138 SPED - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 68000 | 0
6 | M090 | I.S. 324 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
6 | M090 | I.S. 319 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
6 | M090 | I.S. 324 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 263000 | 0
6 | M090 | I.S. 324 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
6 | M090 | I.S. 319 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/20/2023 | DOES |  | DOES | 639908 | 0
6 | M090 | I.S. 324 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/29/2024 | DOES |  | DOES | 50832 | 0
6 | M093 | P.S. 210 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 1/25/2024 | DIIR |  | DIIR | 165000 | 0
6 | M093 | P.S. 210 - MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMP | Construction | In-Progress | 8/6/2018 | DOES |  | DOES | 128252 | 0
6 | M093 | P.S. 210 - MANHATTAN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
6 | M093 | P.S. 210 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/30/2024 | DOES |  | DOES | 50832 | 0
6 | M098 | P.S. 98 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 65000 | 0
6 | M098 | P.S. 98 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
6 | M098 | P.S. 98 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
6 | M098 | P.S. 98 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 6/27/2023 | DOES |  | DOES | 352453 | 0
6 | M098 | P.S. 98 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/10/2024 | DOES | 4/19/2024 | DOES | 65832 | 9058
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M115 | P.S. 115 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR CEILING PLASTER IN ROOM 405 . IT IS 2.5 ' X 2' PIECE OF THE CEILING PLASTER F | Construction | Complete | 4/12/2024 | IEH | 5/12/2024 | IEH | 30866 | 145
6 | M115 | P.S. 115 - MANHATTAN | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 9/19/2024 | FTK |  | FTK | 98454 | 3238
6 | M115 | P.S. 115 - MANHATTAN | DOE - RESOA | FY17 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 35000 | 0
6 | M115 | P.S. 115 - MANHATTAN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
6 | M115 | P.S. 115 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/15/2023 | DOER |  | DOER | 274048 | 0
6 | M115 | P.S. 115 - MANHATTAN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 335000 | 0
6 | M115 | KIPP NYC WASHINGTON HEIGHTS ACADEMY I CS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 1/14/2022 | DOES |  | DOES | 165210 | 0
6 | M115 | P.S. 115 - MANHATTAN | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 166413 | 0
6 | M128 | P.S. 128 - MANHATTAN | SCA Emergency Response | TEMPORARY BOILER | Construction | In-Progress | 3/11/2024 | EMER |  | EMER | 958679 | 698198
6 | M128 | P.S. 128 - MANHATTAN | SCA IEH | PO18-PLEASE ASSIST WITH THE REMOVAL OF ASBESTOS TILES AND REPLACE WITH ACM FREE TILES IN THE FOLLOW | Construction | Complete | 12/1/2023 | IEH | 4/12/2024 | IEH | 60377 | 289
6 | M128 | P.S. 128 - MANHATTAN | Fast Track Projects | FY20 RESO A CAFETERIA UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 4137 | 4137
6 | M128 | P.S. 128 - MANHATTAN | Fast Track Projects | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | FTK | FTK | FTK | FTK | 4176 | 4176
6 | M128 | P.S. 513 - MANHATTAN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
6 | M132 | P.S. 132 - MANHATTAN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 12/27/2018 | FTK |  | FTK | 225031 | 209415
6 | M132 | P.S. 132 - MANHATTAN | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 38400 | 0
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 75000
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
6 | M132 | P.S. 132 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 79000 | 0
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DOE - RESOA | FY21 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 8/30/2021 | DOER |  | DOER | 51697 | 0
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY21 RESO A SECURITY LIGHTING | Construction | In-Progress | 7/1/2022 | DOER |  | DOER | 20721 | 0
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/31/2023 | DOER |  | DOER | 151551 | 0
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 241419 | 0
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY23 RESO A EXTERIOR UPGRADES | Construction | In-Progress | 7/26/2024 | DOER |  | DOER | 331159 | 0
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
6 | M132 | DOS PUENTES ELEMENTARY SCHOOL | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0
6 | M132 | P.S. 132 - MANHATTAN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
6 | M132 | P.S. 132 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/4/2024 | DOES |  | DOES | 65832 | 0
6 | M143 | I.S. 143 - MANHATTAN | SCA Emergency Response | EMERGENCY TEMPORARY BOILER @ M143 | Construction | In-Progress | 5/22/2023 | EMER |  | EMER | 1084276 | 874670
6 | M143 | I.S. 143 - MANHATTAN | SCA IEH | PO18-ABATE ACM IN ROOM 211 - 2 SQUARE FEET. RECEIVED ARL, AS PER SCA WORK WAS COMPLETED ON 02/12/202 | Construction | Complete | 2/11/2024 | IEH | 5/24/2024 | IEH | 9861 | 621
6 | M143 | I.S. 143 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOM B-2. MULTIPLE BROKEN 9X9 TILES MEASURING 130 SQ. FT., CON | Construction | Complete | 7/29/2024 | IEH | 8/21/2024 | IEH | 44759 | 1159
6 | M143 | I.S. 143 - MANHATTAN | Fast Track Projects | CTF ROOM CONVERSION | Construction | Complete | 9/6/2023 | FTK | 1/5/2024 | FTK | 623152 | 547329
6 | M143 | I.S. 348 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0
6 | M143 | I.S. 348 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
6 | M143 | I.S. 348 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
6 | M143 | I.S. 348 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M143 | I.S. 143 - MANHATTAN | DOE - RESOA | FY14 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
6 | M143 | I.S. 143 - MANHATTAN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 11/21/2022 | DOES |  | DOES | 631642 | 0
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/2/2023 | 3/7/2024 | 11/17/2023 | 0 | 4501 | 4501
6 | M152 | P.S. 152 - MANHATTAN | SCA IEH | PO18-THIN LAYER OF WATERPROOFING BEHIND THE WALL PLASTER BROWN COAT (BLACK)IS ACM ABATE APPROXIMATEL | Construction | Complete | 2/21/2024 | IEH | 9/22/2024 | IEH | 1555 | 885
6 | M152 | P.S. 152 - MANHATTAN | SCA IEH | PO18-ROOM CLOSER, APPROX 80 SQ ABATEMENT NEEDED - IN WALL AND CEILINGS IN RM 217 DUE TO WATER DAMAGE | Construction | In-Progress | 6/21/2024 | IEH |  | IEH | 145 | 145
6 | M152 | P.S. 152 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/23/2024 | DOES | 5/3/2024 | DOES | 65832 | 11145
6 | M153 | P.S. 153 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 241250 | 0
6 | M153 | P.S. 153 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
6 | M153 | P.S. 368 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M153 | P.S. 153 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
6 | M153 | P.S. 153 - MANHATTAN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/8/2022 | DOER |  | DOER | 285143 | 0
6 | M153 | P.S. 368 - MANHATTAN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 7/14/2021 | DOER |  | DOER | 82950 | 0
6 | M153 | P.S. 368 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 375000 | 0
6 | M153 | P.S. 153 - MANHATTAN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/16/2022 | DOES |  | DOES | 92941 | 0
6 | M164 | I.S. 328 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/3/2022 | EMER |  | EMER | 49068 | 25172
6 | M164 | I.S. 223 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M164 | I.S. 328 - MANHATTAN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/22/2024 | DOER |  | DOER | 383835 | 0
6 | M164 | I.S. 223 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
6 | M164 | I.S. 328 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/9/2024 | DOES |  | DOES | 646666 | 0
6 | M173 | P.S. 173 - MANHATTAN | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/1/2023 | FTK |  | FTK | 530321 | 368229
6 | M173 | I.S. 349 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M173 | P.S. 173 - MANHATTAN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 10/22/2023 | DOES |  | DOES | 62166 | 0
6 | M173 | P.S. 173 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/12/2024 | DOES | 5/31/2024 | DOES | 65832 | 8519
6 | M173 | I.S. 349 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/3/2024 | DOES |  | DOES | 350534 | 0
6 | M176 | P.S. 311 - MANHATTAN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ M176 | Construction | In-Progress | 4/8/2024 | EMER |  | EMER | 20000 | 5464
6 | M176 | P.S. 314 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 68000 | 0
6 | M176 | P.S. 314 - MANHATTAN | DOE - RESOA | FY14 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
6 | M176 | P.S. 311 - MANHATTAN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/15/2022 | DOER |  | DOER | 202574 | 0
6 | M176 | P.S. 314 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
6 | M176 | P.S. 314 - MANHATTAN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 394369 | 0
6 | M176 | P.S. 314 - MANHATTAN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 250000 | 0
6 | M176 | P.S. 311 - MANHATTAN | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
6 | M176 | P.S. 311 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0
6 | M176 | P.S. 314 - MANHATTAN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/22/2022 | DOES |  | DOES | 69546 | 0
6 | M176 | P.S. 311 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/6/2023 | DOES |  | DOES | 50832 | 0
6 | M178 | P.S. 178 - MANHATTAN | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/1/2023 | FTK |  | FTK | 314160 | 240789
6 | M178 | P.S. 178 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 7/5/2024 | DIIR | 150000
6 | M178 | P.S. 178 - MANHATTAN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
6 | M178 | P.S. 178 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/6/2023 | DOES |  | DOES | 50832 | 0
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/20/2023 | 4/21/2023 | 8/8/2023 | 0 | 50024 | 41851
6 | M187 | P.S. 187 - MANHATTAN | SCA IEH | PO18-WE NEED PIPES INSULATION IN THE BATHROOM 358 TO BE ABATED AS SOON AS POSSIBLE HEIGHT IS 13 FEET | Construction | Complete | 1/26/2024 | IEH | 4/19/2024 | IEH | 49345 | 6465
6 | M187 | P.S. 187 - MANHATTAN | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 11/27/2023 | FTK |  | FTK | 137685 | 118960
6 | M187 | P.S. 187 - MANHATTAN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 437848 | 9025
6 | M187 | P.S. 187 - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
6 | M187 | P.S. 187 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/1/2024 | DOES |  | DOES | 284719 | 0
6 | M189 | P.S. 189 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
6 | M189 | P.S. 189 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M189 | P.S. 189 - MANHATTAN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 346778 | 0
6 | M189 | P.S. 189 - MANHATTAN | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0
6 | M189 | P.S. 189 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/26/2024 | DOES | 5/3/2024 | DOES | 65832 | 7921
6 | M192 | HAMILTON GRANGE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/13/2023 | 7/13/2023 | 8/8/2023 | 0 | 12532 | 12532
6 | M192 | P.S. 192 - MANHATTAN | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN 3RS FLOOR HALLWAY APPROX. 2976SF | Construction | In-Progress | 2/2/2024 | IEH |  | IEH | 575 | 0
6 | M192 | P.S. 192 - MANHATTAN | SCA IEH | PO18-ABATE AND REPLACE 9X9 FLOOR TILES IN THE FOLLOWING ROOMS 226A APPROX 408 SQ FT AND ROOM 145 A | Construction | In-Progress | 4/12/2024 | IEH |  | IEH | 668 | 93
6 | M192 | P.S. 192 - MANHATTAN | Fast Track Projects | LSP- LSP HOT WATER HEATER | Construction | In-Progress | 7/15/2022 | FTK |  | FTK | 253602 | 53093
6 | M192 | P.S. 192 - MANHATTAN | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 11/1/2023 | FTK |  | FTK | 448435 | 286272
6 | M192 | P.S. 325 - MANHATTAN | DIIT - RESOA | FY16 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
6 | M192 | P.S. 325 - MANHATTAN | DIIT - RESOA | FY17 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0
6 | M192 | P.S. 192 - MANHATTAN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 140000 | 0
6 | M192 | P.S. 192 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 200000
6 | M192 | HAMILTON GRANGE MIDDLE SCHOOL | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 9/19/2022 | DOER |  | DOER | 347821 | 0
6 | M192 | P.S. 192 - MANHATTAN | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 637558 | 0
6 | M192 | P.S. 192 - MANHATTAN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
6 | M192 | P.S. 192 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/17/2024 | DOES |  | DOES | 65832 | 0
6 | M218 | I.S. 293 - MANHATTAN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 239412 | 0
6 | M218 | I.S. 322 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M218 | I.S. 293 - MANHATTAN | DOE - RESOA | RESO A ATHLETIC FIELD | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
6 | M218 | I.S. 293 - MANHATTAN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/15/2023 | DOES |  | DOES | 415529 | 0
6 | M233 | ALTERNATE LEARNING CENTER - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/5/2024 | IEH | 6/6/2024 | IEH | 23100 | 23100
6 | M263 | P.S. 366 - MANHATTAN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
6 | M263 | P.S. 366 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/4/2024 | DOES |  | DOES | 50832 | 0
6 | M380 | M138 SPED - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 5/25/2024 | IEH | 12731 | 12542
6 | M387 | SUCCESS ACADEMY CHARTER SCHOOL - WASHINGTON HEIGHTS - NEW YORK 1 | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/19/2024 | IEH | 4/27/2024 | IEH | 16700 | 5891
6 | M465 | HS FOR MEDIA & COMM - MANHATTAN | SCA CIP RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M465 | GEORGE WASHINGTON CAMPUS YABC | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 8/2/2018 | EMER |  | EMER | 760956 | 534580
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA IEH | PO18-ABATE AND REMOVE PIPE INSULATION IN ROOM B-39 CURRENTLY PAINTED IN RED IT IS 12 FT ACM | Construction | Complete | 7/10/2024 | IEH | 7/10/2024 | IEH | 16736 | 218
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA IEH | PO18-PATCH UP /REMOVE FRIABLE ACM IN SOUTH BLOWER ROOM BASEMENT LEVEL PIPING IS ABOUT 10 FEET UP IN | Construction | Complete | 8/19/2024 | IEH | 9/8/2024 | IEH | 10143 | 749
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | Fast Track Projects | CAFETERIA CHILLER | Construction | In-Progress | 3/30/2021 | FTK |  | FTK | 8550824 | 8499740
6 | M465 | THE COLLEGE ACADEMY - M | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
6 | M465 | THE COLLEGE ACADEMY - M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 124000 | 0
6 | M465 | HS FOR MEDIA & COMM - MANHATTAN | DIIT - RESOA | FY25 RESO A CLASSROOM CONNECTIVITY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMP | Construction | In-Progress | 8/20/2018 | DOES |  | DOES | 788302 | 0
6 | M465 | THE COLLEGE ACADEMY - M | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 35000 | 0
6 | M465 | THE COLLEGE ACADEMY - M | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175219 | 0
6 | M465 | THE COLLEGE ACADEMY - M | DOE - RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 5/27/2022 | DOER |  | DOER | 669714 | 0
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - RESOA | FY19 RESO A ROOM CONVERSION | Construction | In-Progress | 6/28/2019 | DOER |  | DOER | 177840 | 0
6 | M465 | HS FOR LAW AND PUBLIC SERVICE - M | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 230000 | 0
6 | M465 | HS FOR LAW AND PUBLIC SERVICE - M | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0
6 | M465 | HS FOR MEDIA & COMM - MANHATTAN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
6 | M465 | HS FOR LAW AND PUBLIC SERVICE - M | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 731791 | 0
6 | M466 | HS FOR MEDIA & COMM - MANHATTAN | DOE - Skilled Trades | ATHLETIC FIELD | Construction | In-Progress | 11/29/2023 | DOES |  | DOES | 1386120 | 34691
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Scope | In-Progress | 4/28/2022 | 8/29/2022 |  | 0 | 11407 | 479
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 9/1/2022 | 12/5/2022 | 12/20/2022 | 0 | 25271 | 25271
6 | M528 | I.S. 528 - MANHATTAN | Fast Track Projects | LSP HOT WATER HEATER | Construction | In-Progress | 3/9/2020 | FTK |  | FTK | 320943 | 36720
6 | M528 | I.S. 528 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
6 | M528 | I.S. 528 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 75000
6 | M528 | I.S. 528 - MANHATTAN | DOE - RESOA | FY17 RESO A TOILETS-STUDENTS | Construction | PNS | PNS | PNS | PNS | DOER | 145000 | 0
6 | M528 | I.S. 528 - MANHATTAN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/28/2022 | DOER |  | DOER | 29572 | 0
6 | M528 | I.S. 528 - MANHATTAN | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
6 | M528 | I.S. 528 - MANHATTAN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/26/2024 | DOES |  | DOES | 65832 | 0
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | SCA CIP RESOA | FY19 RESO A WEIGHT ROOM UPGRADE | Scope | Complete | 1/31/2019 | 6/3/2019 | 9/3/2019 | 0 | 6854 | 6854
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 6/17/2024 | DOER |  | DOER | 103793 | 0
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 2/15/2018 | DOES |  | DOES | 434801 | 3174
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | DOE - Skilled Trades | ELEVATOR MODERNIZATIONS | Construction | In-Progress | 5/7/2019 | DOES |  | DOES | 181697 | 24294
6 | M540 | A. PHILIP RANDOLPH HS -MANHATTAN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 1/31/2023 | DOES | 9/26/2023 | DOES | 550731 | 520815
6 | M812 | HS FOR MATH, SCI AND ENGINEERING-M | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M812 | HS FOR MATH, SCI AND ENGINEERING-M | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 100000
6 | M812 | HS FOR MATH, SCI AND ENGINEERING-M | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
6 | M814 | I.S. 346 - MANHATTAN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 9/4/2024 | DIIR | 250000
6 | M814 | I.S. 346 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
6 | M814 | I.S. 346 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M814 | I.S. 346 - MANHATTAN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
6 | M859 | I.S. 348 - MANHATTAN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/1/2024 | IEH | 8/13/2024 | IEH | 10697 | 0
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE | Scope | In-Progress | 7/12/2021 | 10/26/2021 |  | 0 | 9285 | 3244
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP RESOA | FY22 RESO A (MA) MEDIA CENTER | Scope | In-Progress | 6/1/2022 | 10/3/2022 |  | 0 | 96704 | 704
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | Fast Track Projects | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/18/2022 | FTK |  | FTK | 202962 | 169165
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2/20/2024 | DOER |  | DOER | 79775 | 0
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | DOE - Skilled Trades | WATER MAIN REPAIRS | Construction | In-Progress | 9/15/2020 | DOES |  | DOES | 43847 | 489
6 | M898 | P.S. 18 - MANHATTAN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0
6 | M898 | P.S. 18 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 99000 | 0
6 | M918 | P.S./I.S. 278 - MANHATTAN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 280000 | 0
6 | M918 | P.S./I.S. 278 - MANHATTAN | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
6 | M918 | P.S./I.S. 278 - MANHATTAN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/8/2024 | DIIR | 9/16/2024 | DIIR | 75000
6 | M918 | P.S./I.S. 278 - MANHATTAN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
7 | Q535 | NEW RIKERS ISLAND SCHOOL - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
7 | X001 | P.S. 1 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 331345 | 0
7 | X001 | P.S. 1 - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 125000 | 0
7 | X001 | P.S. 1 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/24/2024 | DIIR | 150000
7 | X001 | P.S. 1 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
7 | X001 | P.S. 1 - BRONX | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 189966 | 0
7 | X001 | P.S. 1 - BRONX | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/12/2024 | DOER |  | DOER | 237465 | 0
7 | X001 | P.S. 1 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 238239 | 0
7 | X001 | P.S. 1 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 5/27/2024 | DOES |  | DOES | 232507 | 0
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | FY23 RESO A SBHC | Scope | Complete | 2/3/2023 | 6/5/2023 | 10/25/2023 | 0 | 27152 | 27152
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SBHC | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SBHC | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SBHC | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X005 | P.S. 5 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SBHC | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X005 | P.S. 5 - BRONX | SCA IEH | PO18-ABATE AND REPLACE 9 X 9 ACM TILES IN ROOM 320 APPROX. 450 SQ. FT | Construction | Complete | 9/13/2023 | IEH | 9/10/2024 | IEH | 0 | 0
7 | X005 | P.S. 5 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 220000 | 0
7 | X005 | P.S. 5 - BRONX | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 233598 | 0
7 | X005 | P.S. 5 - BRONX | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
7 | X005 | P.S. 5 - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
7 | X005 | P.S. 5 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 11/17/2015 | DOES |  | DOES | 75200 | 0
7 | X005 | P.S. 5 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 4/18/2022 | DOES |  | DOES | 235510 | 0
7 | X005 | P.S. 5 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 2/27/2024 | DOES |  | DOES | 910908 | 0
7 | X018 | P.S. 18 - BRONX | SCA CIP RESOA | FY17 RESO A ELECTRICAL UPGRADE | Scope | Complete | 9/14/2017 | 11/14/2017 | 10/17/2017 | 0 | 11544 | 11544
7 | X018 | P.S. 18 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/7/2024 | DIIR | 5/16/2024 | DIIR | 100000
7 | X018 | P.S. 18 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 5/27/2024 | DOES |  | DOES | 427462 | 0
7 | X025 | P.S. 25 - BRONX | SCA IEH | PO18-TEST AND ABATE 9' X 9' FLOOR TILES IF POSITIVE IN THE KITCHEN WHERE OLD OVEN USED TO BE. | Construction | Complete | 8/13/2024 | IEH | 9/26/2024 | IEH | 20090 | 1467
7 | X025 | P.S. 25 - BRONX | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 11/14/2022 | DOER |  | DOER | 150652 | 0
7 | X025 | P.S. 25 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 328000 | 0
7 | X025 | P.S. 25 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/1/2019 | DOES |  | DOES | 104860 | 0
7 | X025 | P.S. 25 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/18/2024 | DOES |  | DOES | 65832 | 0
7 | X025 | P.S. 25 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 1/29/2024 | DOES |  | DOES | 885356 | 50380
7 | X027 | P.S. 277 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/29/2021 | FTK |  | FTK | 47958 | 47081
7 | X027 | P.S. 277 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
7 | X027 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/20/2023 | DOER |  | DOER | 129994 | 0
7 | X027 | P.S. 277 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 8/28/2024 | DOES |  | DOES | 161854 | 0
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X029 | P.S. 29 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X029 | P.S. 29 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
7 | X029 | P.S. 29 - BRONX | DOE - Skilled Trades | ACE BOILER BURNER CONVERSION | Construction | In-Progress | 8/8/2022 | DOES |  | DOES | 2261921 | 0
7 | X029 | P.S. 29 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 8/28/2024 | DOES |  | DOES | 341779 | 0
7 | X030 | P.S. 30 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 224159 | 0
7 | X030 | P.S. 30 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/26/2024 | DOES | 7/8/2024 | DOES | 65832
7 | X040 | P.S. 179 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
7 | X040 | YOUNG LEADERS ELEM - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
7 | X040 | YOUNG LEADERS ELEM - BRONX | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/1/2021 | DOER |  | DOER | 19410 | 0
7 | X040 | P.S. 179 - BRONX | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
7 | X040 | P.S. 179 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/4/2022 | DOES |  | DOES | 206922 | 0
7 | X040 | P.S. 179 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 5/27/2024 | DOES |  | DOES | 893681 | 0
31 | R027 | I.S. 27 - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/22/2023 | DOES |  | DOES | 631900 | 0
7 | X043 | P.S. 43 - BRONX | Fast Track Projects | FY20 RESO A LIBRARY UPGRADE | Construction | In-Progress | 8/31/2023 | FTK |  | FTK | 255839 | 127282
7 | X043 | X017 SPED - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 5/9/2024 | DIIR | 100000 | 100000
7 | X043 | X017 SPED - BRONX | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 4/4/2023 | DOER |  | DOER | 190341 | 0
7 | X043 | P.S. 43 - BRONX | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/1/2021 | DOER |  | DOER | 29020 | 0
7 | X043 | X017 SPED - BRONX | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/20/2023 | DOER |  | DOER | 303494 | 0
7 | X049 | P.S. 49 - BRONX | SCA IEH | PO18-REMOVE ASBESTOS CONTAMINATED BASEBOARD AND MASTIC IN ALL BASEBORADS AROUND ROOM # 142.. APPROX | Construction | Complete | 5/31/2024 | IEH | 6/1/2024 | IEH | 9773 | 420
7 | X049 | P.S. 49 - BRONX | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 188000 | 0
7 | X049 | P.S. 49 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 186806 | 0
7 | X049 | P.S. 49 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/28/2024 | DOES | 6/12/2024 | DOES | 65832
7 | X065 | P.S. 65 - BRONX | SCA IEH | PO18-ROOM 118 CUSTODIAN'S OFFICE, ABATE 3 L.F. PIPE INSULATION MARKED BLUE ROOM 251 OFFICE, ABATE 30 | Construction | Complete | 7/1/2024 | IEH | 9/11/2024 | IEH | 865 | 290
7 | X065 | P.S. 65 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 4/2/2024 | DOES |  | DOES | 346372 | 0
7 | X139 | I.S. 224 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/14/2024 | DIIR | 8/23/2024 | DIIR | 288000
7 | X139 | I.S. 343 - BRONX | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/12/2023 | DOER |  | DOER | 235275 | 0
7 | X139 | I.S. 343 - BRONX | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/22/2023 | DOER |  | DOER | 237455 | 0
7 | X139 | I.S. 224 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/11/2024 | DOES |  | DOES | 668496 | 0
7 | X139 | I.S. 224 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 6/14/2024 | DOES |  | DOES | 737143 | 0
7 | X149 | I.S. 221 - BRONX | SCA IEH | PO18-ABATE PIPE INSULATION ROOMS - BASEMENT GIRLS LOCKER ROOM(SPACE ID-1021), TOILET IN 107, 115, 21 | Construction | Complete | 7/25/2024 | IEH | 9/13/2024 | IEH | 1040 | 290
7 | X149 | I.S. 221 - BRONX | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/25/2019 | FTK |  | FTK | 74638 | 73454
7 | X149 | THE LABORATORY SCHOOL OF FINANCE AND TECHNOLOGY: X223 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 95000 | 0
7 | X149 | I.S. 221 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/8/2024 | DOES |  | DOES | 588718 | 0
7 | X149 | I.S. 221 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 2/6/2024 | DOES |  | DOES | 792811 | 0
7 | X151 | P.S. 31 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
7 | X151 | P.S. 31 - BRONX | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 11/9/2022 | DOER |  | DOER | 211775 | 0
7 | X151 | P.S. 31 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/14/2024 | DOES |  | DOES | 503485 | 0
7 | X154 | P.S. 154 - BRONX | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/22/2023 | 6/21/2023 | 7/3/2023 | 0 | 33425 | 17592
7 | X154 | P.S. 154 - BRONX | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 154177 | 0
7 | X155 | P.S. 754 SPED - BRONX | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 3/12/2021 | DOER |  | DOER | 311942 | 0
7 | X155 | P.S. 754 SPED - BRONX | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 3/14/2024 | DOES |  | DOES | 156771 | 0
7 | X155 | P.S. 754 SPED - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/6/2022 | DOES |  | DOES | 206250 | 0
7 | X155 | P.S. 754 SPED - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/25/2023 | DOES |  | DOES | 542190 | 0
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 65832 | 0
7 | X157 | P.S. 157 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 9/7/2017 | DOES | 2/1/2020 | DOES | 125391 | 133223
7 | X161 | P.S. 161 - BRONX | SCA IEH | PO18-ABATE FLOOR IN CAFETERIA | Construction | Complete | 7/26/2024 | IEH | 9/13/2024 | IEH | 12468 | 218
7 | X161 | X017 SPED - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 5/9/2024 | DIIR | 254000 | 254000
7 | X161 | SOUTH BRONX LITERACY ACADEMY | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
7 | X161 | P.S. 161 - BRONX | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
7 | X161 | P.S. 161 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 149129 | 0
7 | X161 | P.S. 161 - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 6/14/2024 | DOES |  | DOES | 567206 | 0
7 | X162 | I.S. 584 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
7 | X162 | I.S. 162 - BRONX | DOE - Skilled Trades | GYMNASIUM UPGRADE | Construction | In-Progress | 7/24/2017 | DOES |  | DOES | 136414 | 0
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 3/30/2023 | DOES |  | DOES | 233473 | 0
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 5/27/2024 | DOES |  | DOES | 808609 | 0
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 377804 | 0
7 | X183 | SUCCESS ACADEMY CHARTER SCHOOL - BRONX 1 | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/24/2023 | DOES |  | DOES | 508513 | 0
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | DOE - Skilled Trades | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 2/20/2024 | DOES |  | DOES | 128769 | 0
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | DOE - Skilled Trades | CHARTER MATCH INTERIOR SPACES | Construction | In-Progress | 11/13/2023 | DOES |  | DOES | 275173 | 0
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA IEH | PO18-ABATEMENT & HOLES DRILLED FOR PLUMBING. ROOM #227 | Construction | Complete | 7/8/2024 | IEH | 9/16/2024 | IEH | 23751 | 501
7 | X184 | I.S. 296 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
7 | X184 | I.S. 298 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 2/21/2024 | DIIR |  | DIIR | 250000 | 0
7 | X184 | I.S. 296 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
7 | X184 | I.S. 296 - BRONX | DOE - RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | Complete | 8/23/2019 | DOER | 3/28/2020 | DOER | 266752 | 281218
7 | X184 | X017 SPED - BRONX | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 10/7/2022 | DOER |  | DOER | 150766 | 0
7 | X184 | I.S. 296 - BRONX | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/22/2023 | DOER |  | DOER | 391883 | 0
7 | X184 | X017 SPED - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 305565 | 0
7 | X184 | I.S. 298 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
7 | X184 | I.S. 296 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 1/4/2021 | DOES |  | DOES | 157393 | 0
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/4/2024 | DOES |  | DOES | 550208 | 0
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 3/8/2024 | DOES |  | DOES | 549675 | 1884
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 6/14/2024 | DOES |  | DOES | 1182773 | 0
7 | X354 | LEARNING THROUGH PLAY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/13/2024 | DOES |  | DOES | 50832 | 0
7 | X356 | LEARNING THROUGH PLAY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/27/2023 | DOES |  | DOES | 50832 | 0
7 | X470 | MOTT HAVEN VILLAGE PREP - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 159376 | 0
7 | X470 | CAREERS IN SPORTS HIGH SCHOOL - BRONX | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 11/21/2022 | DOES |  | DOES | 613615 | 0
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 11/11/2022 | DOES |  | DOES | 128988 | 0
7 | X600 | ALFRED E. SMITH HS - X | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 9/15/2023 | DOER |  | DOER | 285886 | 2796
7 | X600 | BRONX DESIGN AND CONSTRUCTION ACADEMY - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 12/20/2023 | DOER |  | DOER | 100000 | 0
7 | X600 | ALFRED E. SMITH HS - X | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 8/31/2015 | DOES |  | DOES | 75200 | 0
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 9/1/2021 | DIIR |  | DIIR | 110000 | 0
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 112568 | 0
7 | X655 | MOTT HAVEN COMMUNITY HIGH SCHOOL - BRONX | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 1/4/2021 | DOES |  | DOES | 226128 | 0
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | SCA CIP | EXTERIOR FACADE @ X790 | Scope | In-Progress | 4/8/2024 | 8/22/2024 |  | 0 | 10439 | 4269
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | SCA CIP | EXTERIOR FACADE @ X790 | Design | PNS | PNS | PNS | PNS | 0 | 1609 | 1609
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | SCA CIP | EXTERIOR FACADE @ X790 | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | SCA CIP | EXTERIOR FACADE @ X790 | CM,F&E | PNS | PNS | PNS | PNS | 0 | 3630 | 3630
7 | X790 | X188 SPED - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 166000 | 0
7 | X790 | X188 SPED - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
7 | X790 | X188 SPED - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | DOE - Skilled Trades | ACE BMS UPGRADE | Construction | In-Progress | 2/28/2023 | DOES |  | DOES | 1554000 | 1114377
7 | X790 | BRONX LEADERSHIP ACADEMY II HS - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 50832 | 0
7 | X807 | DOE ADMINISTRATIVE OFFICE - BRONX | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 12/1/2023 | DOER |  | DOER | 95568 | 0
7 | X807 | DOE ADMINISTRATIVE OFFICE - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 314000 | 0
7 | X855 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
7 | X884 | HEALTH OPPORTUNITIES (HS LVL) - X | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 5/31/2024 | IEH | 11813 | 522
7 | X884 | COMM HS FOR SOCIAL JUSTICE - X | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
7 | X884 | COMM HS FOR SOCIAL JUSTICE - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
7 | X884 | COMM HS FOR SOCIAL JUSTICE - X | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
7 | X884 | HEALTH OPPORTUNITIES (HS LVL) - X | DOE - RESOA | FY15 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 56818 | 0
7 | X884 | HEALTH OPPORTUNITIES (HS LVL) - X | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/12/2024 | DOER |  | DOER | 139199 | 0
7 | X897 | RESTART - CITYWIDE | SCA IEH | PO18-ABATE AND REPAIR AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVEILLANCE REPORT P | Construction | Complete | 5/22/2023 | IEH | 9/26/2024 | IEH | 690 | 115
7 | XAGV | FAMILY LIFE ACADEMY CHARTER SCHOOL II - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35000 | 0
7 | XAXQ | HEKETI COMMUNITY CHARTER SCHOOL - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35000 | 0
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Scope | In-Progress | 2/16/2023 | 5/17/2023 |  | 0 | 37899 | 15320
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SCHOOLYARD UPGRADE | Scope | In-Progress | 2/14/2023 | 5/16/2023 |  | 0 | 0 | 0
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SCHOOLYARD UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SCHOOLYARD UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X014 | P.S. 14 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SCHOOLYARD UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 62 | 62
8 | X014 | P.S. 14 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/6/2023 | DIIR | 6/10/2024 | DIIR | 100000 | 100000
8 | X014 | P.S. 14 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
8 | X014 | P.S. 14 - BRONX | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 216000 | 0
8 | X014 | P.S. 14 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/31/2022 | DOES |  | DOES | 59477 | 0
8 | X014 | P.S. 14 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/23/2024 | DOES | 5/31/2024 | DOES | 65832
8 | X036 | P.S. 36 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 3/3/2021 | FTK |  | FTK | 10291 | 10291
8 | X036 | P.S. 36 - BRONX | DOE - RESOA | FY14 RESO A TECHNOLOGY | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X039 | HOLCOMBE L. RUCKER SCHOOLOF COMMUNITY RESEARCH - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/25/2016 | 9/26/2016 | 8/25/2016 | 0 | 74597 | 74597
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN ROOMS: RM: 105 APPROX. 610 SF RM: 206 APPROX. 287SF | Construction | Complete | 9/5/2023 | IEH | 8/26/2024 | IEH | 73094 | 2390
8 | X039 | LONGWOOD PREPARATORY ACADEMY | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/17/2024 | DOES |  | DOES | 579250 | 0
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Scope | Complete | 8/2/2022 | 12/5/2022 | 11/15/2022 | 0 | 13107 | 13107
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 1/15/2020 | 5/14/2020 | 1/30/2020 | 0 | 8025 | 8025
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY21 RESO A STEM LAB / PATH OF TRAVEL RESO A STEM LAB | Scope | Complete | 6/9/2022 | 4/25/2023 | 3/22/2023 | 0 | 29351 | 29351
8 | X052 | I.S. 302 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 294752 | 0
8 | X052 | I.S. 302 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/15/2024 | DOES |  | DOES | 613462 | 0
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 1/30/2020 | FTK |  | FTK | 48382 | 48382
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 2/10/2023 | DOER |  | DOER | 163424 | 0
8 | X062 | P.S. 62 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 8/17/2020 | FTK |  | FTK | 246392 | 234274
8 | X062 | P.S. 62 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 75200 | 0
8 | X062 | P.S. 62 - BRONX | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/31/2022 | DOES |  | DOES | 68599 | 0
8 | X062 | P.S. 62 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/27/2024 | DOES | 4/10/2024 | DOES | 65832 | 11145
8 | X069 | P.S. 69 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 4/18/2019 | EMER |  | EMER | 57663 | 57663
8 | X071 | P.S. 71 - BRONX | SCA IEH | PO18-CAFETERIA - ABATE 6' OF ACM PIPE INSULATION - MARKED RED FOR ID. | Construction | Complete | 7/23/2024 | IEH | 7/26/2024 | IEH | 15205 | 350
8 | X071 | P.S. 71 - BRONX | DIIT - RESOA | FY 15 RESO A SECURITY CAMERAS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 244256 | 0
8 | X071 | P.S. 71 - BRONX | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
8 | X071 | P.S. 71 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
8 | X072 | P.S. 72 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/4/2022 | EMER |  | EMER |  | 0
8 | X072 | P.S. 72 - BRONX | SCA IEH | PO18-ROOM 211, REPAIR 1 L.F. PIPE INSULATION ROOM 306, ABATE 2 SQ. FT. DAMAGE FLOOR TILE ROOM 308, A | Construction | In-Progress | 7/1/2024 | IEH |  | IEH | 648 | 73
8 | X072 | P.S. 72 - BRONX | SCA IEH | PO18-ABATE/REPLACE ACM 9X9 FLOOR TILES IN THE FOLLOWING ROOMS: 307,306,351,308,309,310,312,314 APPR | Construction | Complete | 7/30/2024 | IEH | 9/11/2024 | IEH | 117437 | 435
8 | X072 | P.S. 72 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/25/2019 | FTK |  | FTK | 205576 | 194763
8 | X072 | P.S. 72 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 149460 | 0
8 | X072 | P.S. 72 - BRONX | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 8/3/2021 | 11/2/2021 | 1/7/2022 | 0 | 17663 | 17663
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/24/2022 | 4/25/2022 | 3/22/2022 | 0 | 11732 | 11732
8 | X074 | I.S. 424 - BRONX | SCA IEH | PO18-ROOMS 328 & 330 ABATE RADIATOR INSULATION WALL RESET AND RADIATOR COVER TAR | Construction | Complete | 7/15/2024 | IEH | 8/12/2024 | IEH | 895 | 145
8 | X074 | I.S. 424 - BRONX | Fast Track Projects | LSP FY23 RESO A LOCKER ROOM UPGRADES | Construction | PNS | FTK | FTK | FTK | FTK | 104173 | 110
8 | X074 | HYDE LEADERSHIP CHARTER SCHOOL - X | Fast Track Projects | LSP AUDITORIUM STAGE & SPOT LIGHTING | Construction | In-Progress | 9/20/2021 | FTK |  | FTK | 178172 | 165832
8 | X074 | I.S. 424 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
8 | X074 | I.S. 424 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1125751 | 0
8 | X074 | I.S. 424 - BRONX | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 730572 | 0
8 | X074 | I.S. 424 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/7/2023 | DOES |  | DOES | 426789 | 0
8 | X075 | P.S. 75 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/12/2021 | 3/18/2022 | 3/11/2022 | 0 | 47543 | 42999
8 | X075 | X352 SPED - BRONX | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 3/19/2020 | DOER |  | DOER | 278308 | 0
8 | X075 | P.S. 75 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/20/2023 | DOER |  | DOER | 235796 | 0
8 | X093 | P.S. 93 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 37041 | 0
8 | X093 | P.S. 93 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 126000 | 0
8 | X093 | P.S. 93 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
8 | X093 | P.S. 93 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 12/9/2022 | DOES |  | DOES | 69021 | 0
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A MOBILE SCIENCE LAB | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X100 | P.S. 100 - BRONX | SCA CIP RESOA | RESO A MOBILE SCIENCE LABS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X100 | P.S. 100 - BRONX | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN CEILING PLENUM OF ROOM #102 APPROX. 25LF | Construction | Complete | 3/18/2024 | IEH | 4/7/2024 | IEH | 41755 | 33695
8 | X100 | P.S. 100 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 182000 | 0
8 | X100 | P.S. 100 - BRONX | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
8 | X100 | P.S. 100 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/25/2024 | DOES | 5/6/2024 | DOES | 65832 | 19224
8 | X101 | X010 SPED - BRONX | Fast Track Projects | CTF ROOM CONVERSIONS / PARTITIONING / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 5/18/2023 | FTK |  | FTK | 1640835 | 1481928
8 | X101 | X010 SPED - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 100000 | 0
8 | X101 | I.S. 101 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
8 | X101 | P.S. 304 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 225495 | 0
8 | X107 | P.S. 107 - BRONX | SCA Emergency Response | SIDEWALK BRIDGE | Construction | In-Progress | 6/3/2022 | EMER |  | EMER | 86499 | 74168
8 | X107 | P.S. 107 - BRONX | SCA IEH | PO18-ABATE ACM FLOORING IN THE FOLLOWING ROOMS - CLASSROOM 107 - 915 SF CLASSROOM 225 - 672 SF CLASS | Construction | Complete | 7/31/2023 | IEH | 6/17/2024 | IEH | 2474 | 166
8 | X107 | BOYS PREPARATORY CHARTER SCHOOL OF THE BRONX | Fast Track Projects | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/23/2023 | FTK |  | FTK | 139500 | 0
8 | X107 | P.S. 107 - BRONX | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0
8 | X107 | P.S. 107 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 5/2/2024 | DOES | 65832 | 189
8 | X119 | P.S. 119 - BRONX | SCA Emergency Response | EMERGENCY- STRUCTURAL ISSUES/BUILDING FACADES | Construction | In-Progress | 12/27/2022 | EMER |  | EMER | 528966 | 464210
8 | X119 | P.S. 119 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
8 | X120 | I.S. 301 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
8 | X120 | I.S. 301 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
8 | X120 | I.S. 301 - BRONX | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 110053 | 0
8 | X120 | GIRLS PREP CHARTER SCHOOL - X | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
8 | X120 | I.S. 301 - BRONX | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
8 | X120 | X188 SPED - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
8 | X120 | I.S. 301 - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 10/21/2021 | DOES |  | DOES | 388374 | 0
8 | X123 | I.S. 337 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/10/2024 | DIIR | 6/14/2024 | DIIR | 100000
8 | X123 | I.S. 337 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
8 | X123 | I.S. 123 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/6/2023 | DOES | 10/25/2023 | DOES | 449213 | 88492
8 | X125 | I.S. 562 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/7/2023 | 6/8/2023 | 5/9/2023 | 0 | 32429 | 32428
8 | X125 | P.S. 119 - BRONX | SCA IEH | PO18-TEST AND ABATE (IF NEEDED) 4' OF PIPE INSULATION IN ROOM 202 TO REPAIR ROOF DRAIN. | Construction | Complete | 7/23/2024 | IEH | 9/26/2024 | IEH | 793 | 218
8 | X125 | I.S. 562 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 164041 | 0
8 | X125 | P.S. 119 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/22/2023 | DOES |  | DOES | 431009 | 0
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X130 | P.S. 130 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X131 | I.S. 131 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/28/2018 | 4/2/2019 | 3/13/2019 | 0 | 51661 | 17987
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/2/2024 | 6/4/2024 | 6/24/2024 | 0 | 14111 | 618
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/23/2023 | 7/10/2023 | 9/25/2024 | 0 | 16078 | 581
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | In-Progress | 9/18/2024 | 12/20/2024 |  | 0 | 0 | 0
8 | X131 | I.S. 131 - BRONX | SCA IEH | PO18-SPACE ID: 2144 - ROOM 144 - TEST AND ABATE PIPE INSULATION IN ROOM 144, MARKED GREY FOR ID. | Construction | In-Progress | 8/28/2024 | IEH |  | IEH | 865 | 290
8 | X131 | SOUNDVIEW ACADEMY FOR CULTURE AND SCHOLARSHIP - X | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 7/15/2021 | FTK |  | FTK | 1231077 | 1180384
8 | X131 | I.S. 131 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
8 | X131 | SUCCESS ACADEMY CHARTER SCHOOL - BRONX 4 - NEW YORK 2 | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 12/7/2022 | DOER |  | DOER | 909014 | 0
8 | X131 | I.S. 131 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 7/29/2015 | DOES |  | DOES | 188220 | 0
8 | X131 | I.S. 131 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 8/30/2022 | DOES |  | DOES | 216748 | 0
8 | X131 | I.S. 131 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/21/2023 | DOES |  | DOES | 567791 | 0
8 | X138 | P.S. 138 - BRONX | DOE - RESOA | FY21 RESO A COMPUTER LAB | Construction | In-Progress | 10/12/2022 | DOER |  | DOER | 118534 | 0
8 | X138 | P.S. 138 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/12/2024 | DOES |  | DOES | 65832 | 0
8 | X140 | P.S. 140 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 12/7/2023 | 6/14/2024 | 6/7/2024 | 0 | 12872 | 12872
8 | X146 | P.S. 146 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 125000 | 0
8 | X146 | P.S. 146 - BRONX | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/13/2023 | DOER |  | DOER | 259411 | 0
8 | X146 | X186 SPED - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 104000 | 0
8 | X152 | P.S. 152 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ X152 | Construction | In-Progress | 6/21/2023 | EMER |  | EMER | 70292 | 46202
8 | X152 | P.S. 152 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
8 | X174 | WOMEN'S ACADEMY OF EXCELLENCE - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/21/2023 | DIIR | 5/6/2024 | DIIR | 100000 | 100000
8 | X174 | BRONX MATH PREP - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
8 | X174 | WOMEN'S ACADEMY OF EXCELLENCE - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/23/2024 | DIIR | 5/6/2024 | DIIR | 250000 | 250000
8 | X174 | I.S. 174 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 11/22/2023 | DOEL | 2/20/2024 | DOEL | 62957 | 62957
8 | X174 | ARCHIMEDES ACADEMY FOR MATH - BRONX | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 136000 | 0
8 | X174 | ARCHIMEDES ACADEMY FOR MATH - BRONX | DOE - RESOA | FY23 RESO A ROBOTICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 331000 | 0
8 | X174 | WOMEN'S ACADEMY OF EXCELLENCE - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 700000 | 0
8 | X174 | ARCHIMEDES ACADEMY FOR MATH - BRONX | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/16/2022 | DOES |  | DOES | 61230 | 0
8 | X174 | WOMEN'S ACADEMY OF EXCELLENCE - BRONX | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 11/17/2022 | DOES |  | DOES | 1803128 | 0
8 | X182 | P.S. 182 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 10/22/2021 | FTK |  | FTK | 63761 | 63761
8 | X182 | P.S. 182 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
8 | X182 | P.S. 182 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
8 | X192 | MOTT HALL COMMUNITY SCHOOL - BRONX | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 4/1/2020 | DIIR |  | DIIR | 100000 | 0
8 | X192 | I.S. 371 - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 6/21/2024 | DIIR | 100000
8 | X192 | BRONX DELTA SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0
8 | X192 | I.S. 371 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 4/15/2024 | DIIR | 75000
8 | X192 | I.S. 371 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/21/2024 | DIIR | 75000 | 75000
32 | K865 | BUSHWICK LEADERS - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 197000 | 0
8 | X192 | BRONX DELTA SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 75000 | 0
8 | X192 | I.S. 371 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 575000 | 0
8 | X192 | BRONX DELTA SCHOOL | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
8 | X192 | I.S. 366 - X | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 75200 | 0
8 | X192 | I.S. 371 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/15/2024 | DOES | 4/23/2024 | DOES | 65832 | 9315
8 | X317 | P.S. 583 - BRONX | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 6/25/2024 | DOER |  | DOER | 142938 | 0
8 | X392 | M.S./H.S. 269 - BRONX | DOE - RESOA | FY19 RESO A KITCHEN AREAS | Construction | In-Progress | 6/30/2022 | DOER |  | DOER | 78308 | 0
8 | X405 | HERBERT H. LEHMAN HS - X | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN VARIOUS BATHROOMS | Construction | Complete | 1/13/2023 | IEH | 9/10/2024 | IEH | 0 | 0
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 5/24/2016 | FTK |  | FTK | 1013044 | 940960
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | CTF-ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/17/2017 | FTK |  | FTK | 2513122 | 2443733
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 5/2/2022 | FTK |  | FTK | 3298739 | 2980737
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 5/2/2022 | FTK |  | FTK | 3116250 | 2839916
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 8/22/2023 | FTK |  | FTK | 146529 | 133052
8 | X405 | HERBERT H. LEHMAN HS - X | Fast Track Projects | GAS METER ROOM COMPLIANCE PROJECT | Construction | In-Progress | 9/25/2018 | FTK |  | FTK | 371579 | 337804
8 | X405 | WESTCHESTER SQUARE ACADEMY - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 75000
8 | X405 | HERBERT H. LEHMAN HS - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/2/2024 | DIIR | 7/11/2024 | DIIR | 100000
8 | X405 | X721 SPED - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
8 | X405 | BRONX RIVER HIGH SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
8 | X405 | RENAISSANCE HS FOR MUS THEATRE - X | DOE - RESOA | FY20 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75795 | 0
8 | X405 | HERBERT H. LEHMAN HS - X | DOE - Skilled Trades | INTERIOR SPACES | Construction | In-Progress | 6/15/2021 | DOES |  | DOES | 1298930 | 0
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X450 | ALC - STEVENSON CAMPUS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
8 | X450 | MILLENIUM ART ACADEMY - BRONX | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/13/2018 | 10/15/2018 | 8/23/2018 | 0 | 4886 | 4886
8 | X450 | X017 SPED - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 5/9/2024 | DIIR | 55000 | 55000
8 | X450 | GOTHAM COLLABORATIVE HIGH SCHOOL - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 6/6/2024 | DIIR | 100000 | 100000
8 | X450 | BRONX COMPASS HIGH SCHOOL - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/5/2024 | DIIR | 100000
8 | X450 | BRONX COMMUNITY HIGH SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 272000 | 0
8 | X450 | MILLENIUM ART ACADEMY - BRONX | DOE - RESOA | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/15/2019 | DOER |  | DOER | 209669 | 0
8 | X450 | ANTONIA PANTOJA PREP ACADEMY - X | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 11/10/2021 | DOER |  | DOER | 443074 | 0
8 | X450 | X017 SPED - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/1/2023 | DOER |  | DOER | 303149 | 0
8 | X450 | X017 SPED - BRONX | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 215748 | 0
8 | X450 | X017 SPED - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 384704 | 0
8 | X450 | MILLENIUM ART ACADEMY - BRONX | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 12/24/2020 | DOES |  | DOES | 234472 | 0
8 | X450 | MILLENIUM ART ACADEMY - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/3/2022 | DOES |  | DOES | 223320 | 0
8 | X450 | MILLENIUM ART ACADEMY - BRONX | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 11/4/2022 | DOES |  | DOES | 1850964 | 0
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | DOE - RESOA | FY16 RESO A ROOM CONVERSIONS / LEARNING KITCHEN | Construction | PNS | PNS | PNS | PNS | DOER | 989965 | 0
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/28/2019 | DOES |  | DOES | 230617 | 0
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/4/2021 | DOES |  | DOES | 61009 | 0
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 4/10/2023 | DOES | 12/27/2023 | DOES | 489240 | 2196
8 | X650 | NEW VISIONS CHARTER HS FOR ADVANCED MATH AND SCIENCE, II | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 130470 | 80759
8 | X823 | BOYS PREPARATORY CHARTER SCHOOL OF THE BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 35000 | 0
8 | X833 | REGION 2 SUPERINTENDENT - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
8 | X880 | P.S. 69 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/19/2024 | IEH | 5/11/2024 | IEH | 18315 | 18126
8 | X953 | HOSPITAL SCHOOLS - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0
8 | X972 | BRONX ARENA HIGH SCHOOL - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 6/4/2024 | IEH | 12141 | 6577
8 | XOLA | EARL MONROE NEW RENAISSANCE BASKETBALL CHARTER SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA IEH | PO18-ABATE AND REPLACE BROKEN ACM FLOOR TILES IN ROOMS 208 AND 227. | Construction | Complete | 8/27/2024 | IEH | 9/1/2024 | IEH | 71209 | 1757
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 175000
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/6/2023 | DOER |  | DOER | 466645 | 0
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X004 | P.S. 4 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X004 | P.S. 4 - BRONX | SCA Emergency Response | EMERGENCY- SWB @ X004 | Construction | In-Progress | 3/18/2024 | EMER |  | EMER | 49148 | 20671
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY25 RESO A SHBC | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SHBC | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SHBC | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SHBC | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A SHBC | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY21 RESO A (MA) AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/10/2022 | 12/29/2022 | 1/31/2023 | 0 | 72637 | 72419
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-ABATE/REPLACE ACM 9 X 9 FLOOR TILES IN THE NURSE OFFICE APPROX: 623 SQ. FT | Construction | Complete | 1/31/2024 | IEH | 6/1/2024 | IEH | 34266 | 34172
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-ABATE HALLWAY AREA IN FRONT OF DOORS AND FLOOR TILES IN BATHROOMS 230, 330, 316, 322 AND 310. R | Construction | Complete | 5/28/2024 | IEH | 6/30/2024 | IEH | 39700 | 4217
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-X494@X022 SUCCESS ACADEMY CHARTER SCHOOL - BRONX 2 REQUEST #2024-63660 DRILL TO INSTALL A WIREL | Construction | Complete | 6/25/2024 | IEH | 6/29/2024 | IEH | 36180 | 1742
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-ROOM 108, REPLACE 15 MISSING AND BROKEN FLOOR TILES ROOM 233, REPLACE 1 BROKEN FLOOR TILE ROOM | Construction | Complete | 6/28/2024 | IEH | 9/4/2024 | IEH | 68988 | 634
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-SPACE ID: 4338 - CLASSROOM 338 ABATE 12' X 12' FLOOR TILES AND REMOVE OLD LAB SINK NEAR WHITEBO | Construction | In-Progress | 7/31/2024 | IEH |  | IEH | 1124 | 374
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-ABATE ACM FOR CORE DRILLING FOR ELECTRICAL OUTLET INSTALLATIONS, AND THE INSTALLATION OF CONDUI | Construction | Complete | 8/14/2024 | IEH | 8/18/2024 | IEH | 10118 | 809
9 | X022 | I.S. 22 - BRONX | SCA IEH | PO18-ABATE FLOOR ROOM 121B - EXISTING VCT FLOORING AROUND WOODEN BUILT-IN CABINETRY AND LOCKER ROOM | Construction | Complete | 8/23/2024 | IEH | 9/17/2024 | IEH | 129654 | 1498
9 | X022 | I.S. 22 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 6/10/2021 | FTK |  | FTK | 169421 | 163035
9 | X022 | I.S. 22 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 165713 | 0
9 | X022 | I.S. 22 - BRONX | DOE - RESOA | FY21 RESO A (MA) SUPPLEMENTAL COOLING | Construction | In-Progress | 4/6/2023 | DOER |  | DOER | 381416 | 0
9 | X022 | I.S. 22 - BRONX | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/6/2023 | DOER |  | DOER | 811497 | 0
9 | X022 | I.S. 22 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/20/2024 | DOES |  | DOES | 535717 | 0
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X028 | P.S. 28 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X028 | P.S. 28 - BRONX | SCA IEH | PO18-PRINCIPAL'S OFFICE ROOM 205 REMOVE 4' OF ACM PIPE INSULATION MARKED FOR ID. REMOVE 1' OF ACM PI | Construction | In-Progress | 8/30/2024 | IEH |  | IEH | 768 | 193
9 | X042 | P.S. 42 - BRONX | DIIT - RESOA | FY 11 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 247499 | 0
9 | X042 | P.S. 42 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/21/2024 | DIIR | 8/6/2024 | DIIR | 150000 | 150000
9 | X042 | P.S. 42 - BRONX | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/5/2023 | 3/7/2024 | 4/29/2024 | 0 | 41844 | 41844
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 19 | 19
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 76 | 76
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X053 | P.S. 53 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X053 | P.S. 53 - BRONX | SCA IEH | PO18-ABATE APP.14LF OF PIPE INSULATION IN ROOM #407 | Construction | Complete | 7/29/2024 | IEH | 8/6/2024 | IEH | 13124 | 924
9 | X053 | P.S. 53 - BRONX | SCA IEH | PO18-ABATE/REPLACE 9 X 9 ACM FLOOR TILES ROOM 309 APPROX: 607 SQ. FT. | Construction | Complete | 7/31/2024 | IEH | 8/31/2024 | IEH | 34080 | 1606
9 | X053 | P.S. 53 - BRONX | SCA IEH | PO18-ABATE APP.14LF OF PIPE INSULATION IN ROOM #407 | Construction | Complete | 8/5/2024 | IEH | 8/27/2024 | IEH | 91 | 91
9 | X053 | P.S. 53 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 11/21/2023 | DOEL | 1/24/2024 | DOEL | 294115 | 294115
9 | X053 | P.S. 53 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 65300 | 0
9 | X053 | P.S. 53 - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/3/2024 | DOER |  | DOER | 209865 | 0
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 12/12/2023 | 3/14/2024 |  | 0 | 8246 | 556
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X055 | P.S. 55 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X055 | P.S. 55 - BRONX | SCA IEH | PO18-ABATE BROKEN/CRACKED 9' X 9' ACM FLOORING TILES ON THE FOLLOWING FLOORS- 2ND FLOOR - 50' X 90' | Construction | Complete | 4/26/2024 | IEH | 8/18/2024 | IEH | 208758 | 5441
9 | X055 | P.S. 55 - BRONX | DOE - RESOA | FY18 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Construction | In-Progress | 3/5/2018 | DOER |  | DOER | 371013 | 0
9 | X055 | P.S. 55 - BRONX | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 1/29/2024 | DOER |  | DOER | 700000 | 0
9 | X058 | P.S. 58 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 4/26/2024 | DOES | 65832 | 8103
9 | X063 | P.S. 63 - BRONX | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 12/19/2023 | 3/26/2024 | 5/7/2024 | 0 | 17659 | 17659
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X064 | LUCERO ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X064 | THE WALTON AVENUE SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 228000 | 0
9 | X064 | LUCERO ELEMENTARY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
9 | X064 | THE WALTON AVENUE SCHOOL | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 725000 | 0
9 | X064 | THE WALTON AVENUE SCHOOL | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/18/2022 | DOES |  | DOES | 330405 | 0
9 | X070 | P.S. 70 - BRONX | DIIT - RESOA | FY10 RESO A DESKTOP COMPUTERS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 1000 | 0
9 | X073 | P.S. 73 - BRONX | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 2/6/2023 | 6/7/2023 | 9/29/2023 | 0 | 5765 | 5765
9 | X073 | P.S. 73 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 7/1/2021 | EMER |  | EMER | 124404 | 124404
9 | X073 | P.S. 73 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
9 | X073 | P.S. 73 - BRONX | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/5/2021 | DOER |  | DOER | 28941 | 0
9 | X073 | P.S. 73 - BRONX | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 6/30/2022 | DOER |  | DOER | 290644 | 0
9 | X082 | I.S. 303 - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/1/2023 | 6/2/2023 | 5/9/2023 | 0 | 12979 | 12979
9 | X082 | I.S. 232 - BRONX | SCA IEH | PO18-ABATE (6) 4' SECTIONS OF THE GYM FLOOR TO REPAIR SECTIONS THAT ARE BUCKLING. SOFT CONCRETE FILL | Construction | In-Progress | 9/22/2023 | IEH |  | IEH | 1366 | 616
9 | X082 | ACADEMY FOR LANGUAGE & TECH - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 7/25/2023 | FTK |  | FTK | 988090 | 923323
9 | X082 | I.S. 303 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/12/2024 | DIIR | 6/21/2024 | DIIR | 170000
9 | X082 | I.S. 232 - BRONX | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/27/2020 | DOER |  | DOER | 421013 | 0
9 | X082 | I.S. 303 - BRONX | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | In-Progress | 9/27/2023 | DOER |  | DOER | 87515 | 0
9 | X082 | I.S. 303 - BRONX | DOE - RESOA | RESO A ROOM CONVERSION | Construction | In-Progress | 6/5/2023 | DOER |  | DOER | 21715 | 0
9 | X082 | I.S. 303 - BRONX | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/5/2023 | DOER |  | DOER | 380938 | 0
9 | X082 | ACADEMY FOR LANGUAGE & TECH - X | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
9 | X082 | I.S. 232 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/22/2024 | DOES |  | DOES | 323927 | 0
9 | X088 | P.S. 88 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X090 | THE FAMILY SCHOOL - BRONX | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 598003 | 0
9 | X104 | P.S. 199 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 9/6/2022 | EMER |  | EMER | 1869712 | 1855331
9 | X104 | P.S. 199 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 139500 | 0
9 | X104 | P.S. 199 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 1/5/2021 | DOES |  | DOES | 192500 | 0
9 | X109 | P.S. 109 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X109 | P.S. 109 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X109 | P.S. 109 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X109 | P.S. 109 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X109 | P.S. 109 - BRONX | SCA IEH | PO18-CELLAR FAN ROOM, ABATE 30 L.F. PIPE INSULATION PAINTED RED BOILER ROOM, ABATE 14 L.F. PIPE INSU | Construction | In-Progress | 6/26/2024 | IEH |  | IEH | 1366 | 616
9 | X109 | P.S. 109 - BRONX | Fast Track Projects | PAVED AREAS- BLACKTOP | Construction | In-Progress | 10/2/2019 | FTK |  | FTK | 274731 | 273605
9 | X109 | P.S. 109 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 335000 | 0
9 | X109 | P.S. 109 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 106000 | 0
9 | X109 | P.S. 109 - BRONX | DOE - RESOA | FY21 RESO A ACCESSIBILITY | Construction | PNS | PNS | PNS | PNS | DOER | 335667 | 0
9 | X109 | P.S. 109 - BRONX | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 375000 | 0
9 | X109 | P.S. 109 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 185872 | 0
9 | X110 | P.S. 110 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 8/1/2018 | EMER |  | EMER |  | 0
9 | X110 | P.S. 110 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 8/10/2020 | FTK |  | FTK | 363904 | 351579
9 | X110 | P.S. 110 - BRONX | DIIT - RESOA | FY 11 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 79187 | 0
9 | X110 | P.S. 110 - BRONX | DOE - RESOA | FY22 RESO A FENCING | Construction | In-Progress | 10/15/2022 | DOER |  | DOER | 181144 | 0
9 | X110 | M.S. 128 - BRONX | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 397936 | 0
9 | X110 | P.S. 110 - BRONX | DOE - RESOA | RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 6/28/2024 | DOER |  | DOER | 60376 | 0
9 | X110 | P.S. 110 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
9 | X110 | P.S. 110 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/5/2023 | DOES |  | DOES | 452640 | 0
9 | X110 | P.S. 110 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 7/10/2024 | DOES | 65832
9 | X114 | P.S. 114 - BRONX | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOM #113 APPROX. 598SF | Construction | Complete | 8/7/2023 | IEH | 4/16/2024 | IEH | 658 | 658
9 | X114 | P.S. 114 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
9 | X114 | P.S. 114 - BRONX | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | SCA CIP RESOA | FY16 RESO A SCIENCE LAB UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X117 | I.S. 117 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X117 | I.S. 117 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/24/2024 | DIIR | 250000 | 2539
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 6/14/2024 | DIIR | 100000 | 100000
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300620 | 0
9 | X117 | YOUNG WOMEN'S LEADERSHIP SCHOOL OF THE BRONX - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/19/2024 | DOER |  | DOER | 62000 | 0
9 | X126 | P.S. 126 - BRONX | SCA IEH | PO18-ABATE BATHROOM WALL IN ROOM 232 APPROX. 18 1/2 X 30 | Construction | In-Progress | 7/27/2023 | IEH |  | IEH | 1022 | 272
9 | X126 | P.S. 126 - BRONX | DIIT - RESOA | FY 11 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 59397 | 0
9 | X126 | P.S. 126 - BRONX | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 6/1/2023 | DOER |  | DOER | 27535 | 0
9 | X126 | P.S. 126 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 182701 | 0
9 | X126 | P.S. 126 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 188137 | 0
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X132 | P.S. 132 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X132 | P.S. 132 - BRONX | SCA IEH | PO18-ABATE/REPLACE CEILING/WALL TILES KITCHEN VESTIBULE (BY EXIT 6): CERAMIC TILE MASTIC Y* - ASSUME | Construction | Complete | 8/5/2024 | IEH | 8/9/2024 | IEH | 17552 | 272
9 | X132 | P.S. 132 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
9 | X132 | P.S. 132 - BRONX | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 10/13/2023 | DOES |  | DOES | 160168 | 0
9 | X132 | P.S. 132 - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 7/20/2018 | DOES |  | DOES | 351661 | 0
9 | X132 | P.S. 132 - BRONX | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 1/20/2021 | DOES |  | DOES | 85761 | 0
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | SCA IEH | PO18-CHARTER SCHOOL ABATEMENT - REMOVE LEDGES AND REPLACE FLOORING IN ROOMS 402, 403, 404, 405 406 A | Construction | Complete | 5/28/2024 | IEH | 8/29/2024 | IEH | 60924 | 821
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 9/10/2019 | FTK |  | FTK | 142933 | 141396
9 | X145 | M.S. 593 - BRONX | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 2/2/2021 | FTK |  | FTK | 502769 | 368343
9 | X145 | M.S. 594 - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 125000 | 0
9 | X145 | M.S. 593 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 100000
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | DOE - RESOA | FY21 RESO A COURTYARD UPGRADE | Construction | In-Progress | 6/29/2023 | DOER |  | DOER | 315765 | 0
9 | X145 | I.S. 145 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/15/2016 | DOES |  | DOES | 172211 | 0
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 219564 | 0
9 | X145 | NEW MILLENNIUM BRONX ACADEMY OF THE ARTS - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/26/2023 | DOES | 1/2/2024 | DOES | 477629 | 423831
9 | X147 | I.S. 339 - BRONX | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOM 427 APPROX. 430SF | Construction | Complete | 11/1/2023 | IEH | 5/26/2024 | IEH | 41588 | 35638
9 | X147 | I.S. 339 - BRONX | SCA IEH | PO18-REPLACE DAMAGE FLOOR TILE PRINCIPAL OFFICE ACM YES LOCATION ROOM 248 SECOND FLOOR DESCRIPTION F | Construction | Complete | 3/6/2024 | IEH | 7/20/2024 | IEH | 63382 | 52632
9 | X147 | I.S. 339 - BRONX | SCA IEH | PO18-ABATE/REPLACE ACM FLOOR TILES ROOM 429 | Construction | Complete | 7/31/2024 | IEH | 9/22/2024 | IEH | 56008 | 1696
9 | X147 | I.S. 339 - BRONX | SCA IEH | PO18-ABATE/REPLACE ACM FLOOR TILES ROOM 232 | Construction | In-Progress | 8/9/2024 | IEH |  | IEH | 302 | 302
9 | X147 | I.S. 339 - BRONX | SCA IEH | PO18-STAIRCASE D BETWEEN 4TH FLOOR AND 3RD FLOOR LANDING DAMAGE FLOOR TILE (TRIP HAZARD IS PRESENT) | Construction | In-Progress | 8/14/2024 | IEH |  | IEH | 979 | 404
9 | X147 | I.S. 313 - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 233000 | 0
9 | X147 | I.S. 339 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
9 | X147 | I.S. 339 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/30/2023 | DOES |  | DOES | 475126 | 0
9 | X148 | I.S. 219 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 4/30/2021 | 8/31/2021 | 8/6/2021 | 0 | 20000 | 20000
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/22/2023 | 6/21/2023 | 11/9/2023 | 0 | 105364 | 67564
9 | X148 | I.S. 215 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 5/25/2023 | 8/25/2023 | 11/9/2023 | 0 | 545 | 545
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA IEH | PO18-ABATE ACM PIPE INSULATION IN BASMENT PIPE CHASE APPROX: 5 FT EACH | Construction | In-Progress | 9/3/2024 | IEH |  | IEH | 1185 | 435
9 | X148 | I.S. 215 - BRONX | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/27/2023 | DOER |  | DOER | 195522 | 0
9 | X148 | I.S. 215 - BRONX | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/5/2024 | DOER |  | DOER | 123570 | 0
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 7/24/2023 | DOES | 9/27/2023 | DOES | 346130
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | DOE - Skilled Trades | GYMNASIUM FLOOR REPLACEMENT | Construction | Complete | 6/1/2023 | DOES | 5/10/2024 | DOES | 775829
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/23/2019 | 12/1/2021 | 12/3/2021 | 0 | 25990 | 25990
9 | X166 | BRONX EARLY COLLEGE ACADEMY | SCA IEH | PO18-ABATE FLOOR IN ROOM #420 | Construction | Complete | 8/9/2024 | IEH | 8/17/2024 | IEH | 29094 | 1878
9 | X166 | SCIENCE AND TECHNOLOGY ACADEMY: A MOTT HALL SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/30/2024 | DIIR | 7/9/2024 | DIIR | 100000
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/20/2023 | DOER |  | DOER | 1400000 | 0
9 | X166 | SCIENCE AND TECHNOLOGY ACADEMY: A MOTT HALL SCHOOL | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 7/16/2021 | DOES |  | DOES | 183729 | 0
9 | X166 | BRONX EARLY COLLEGE ACADEMY | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 2/10/2021 | DOES |  | DOES | 193120 | 0
9 | X166 | BRONX EARLY COLLEGE ACADEMY | DOE - Skilled Trades | ELEVATOR MODERNIZATIONS | Construction | Complete | 1/31/2022 | DOES | 4/30/2024 | DOES | 440538 | 431579
9 | X166 | BRONX EARLY COLLEGE ACADEMY | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/22/2024 | DOES |  | DOES | 357548 | 0
9 | X170 | P.S. 170 - BRONX | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/26/2023 | DOER |  | DOER | 199056 | 0
9 | X170 | P.S. 170 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/8/2024 | DOER |  | DOER | 17781 | 0
9 | X172 | P.S. 11 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/23/2024 | IEH | 8/28/2024 | IEH | 14919 | 0
9 | X172 | P.S. 11 - BRONX | DOE - RESOA | FY21 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
9 | X229 | THE NEW AMERICAN ACADEMY AT ROBERTO CLEMENT STATE PARK - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
9 | X235 | P.S./I.S. 218 - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/15/2024 | DOER |  | DOER | 223000 | 0
9 | X235 | P.S./I.S. 218 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/29/2024 | DOES | 6/4/2024 | DOES | 50832
9 | X236 | P.S. 163 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/8/2024 | IEH | 7/24/2024 | IEH | 12908 | 121
9 | X240 | I.S. 327 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X240 | I.S. 327 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X240 | I.S. 327 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X240 | I.S. 327 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X240 | I.S. 327 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/14/2024 | DIIR | 6/12/2024 | DIIR | 200000 | 200000
9 | X240 | I.S. 327 - BRONX | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 91538 | 0
9 | X256 | HARRIET TUBMAN CHARTER SCHOOL - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 203732 | 0
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
9 | X285 | THE HIGHBRIDGE GREEN SCHOOL | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
9 | X338 | P.S. 204 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 300000 | 0
9 | X338 | P.S. 204 - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 5/19/2023 | DOER |  | DOER | 49205 | 0
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOOR TILES 2ND FLOOR HALLWAY | Construction | In-Progress | 8/5/2024 | IEH |  | IEH | 1185 | 435
9 | X400 | HS FOR VIOLIN AND DANCE - BRONX | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 8/1/2022 | FTK |  | FTK | 374018 | 359736
9 | X400 | BRONX INTERNATIONAL - BRONX | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 6/6/2022 | FTK |  | FTK | 1202185 | 1151157
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 8/11/2022 | FTK |  | FTK | 353651 | 343277
9 | X400 | BRONX INTERNATIONAL - BRONX | Fast Track Projects | LSP LIGHTING UPGRADE | Construction | In-Progress | 12/27/2022 | FTK |  | FTK | 1825094 | 10904
9 | X400 | HS FOR VIOLIN AND DANCE - BRONX | Fast Track Projects | LSP- INTERIOR SPACES | Construction | In-Progress | 7/22/2022 | FTK |  | FTK | 164788 | 153562
9 | X400 | BRONX INTERNATIONAL - BRONX | Fast Track Projects | LSP- GYM UPGRADE | Construction | In-Progress | 7/12/2022 | FTK |  | FTK | 197850 | 176919
9 | X400 | BRONX INTERNATIONAL - BRONX | Fast Track Projects | LSP- INTERIOR SPACES FOR ROOM 501 | Construction | In-Progress | 7/12/2022 | FTK |  | FTK | 125369 | 91239
9 | X400 | HIGH SCHOOL FOR EXCELLENCE - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 130000 | 0
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
9 | X400 | HS FOR VIOLIN AND DANCE - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
9 | X400 | BRONX INTERNATIONAL - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/27/2019 | DOES |  | DOES | 246546 | 0
9 | X410 | NEW DIRECTIONS SECONDARY SCHOOL | DIIT - RESOA | FY 11 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 49571 | 0
9 | X410 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176099 | 0
9 | X410 | DREAMYARD PREPARATORY SCHOOL | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
9 | X410 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
9 | X410 | P469 - THE BRONX SCHOOL FOR CONTINUOUS LEARNERS - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 8/5/2022 | DOES |  | DOES | 129517 | 0
9 | X410 | HS OF BUSINESS - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/12/2023 | DOES |  | DOES | 852629 | 0
9 | X410 | HS OF BUSINESS - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/19/2024 | DOES |  | DOES | 65832 | 0
9 | X411 | HS OF BUSINESS - BRONX | DOE - RESOA | FY24 RESO A ATHLETIC FIELDS | Construction | In-Progress | 4/1/2024 | DOER |  | DOER | 4135256 | 0
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/6/2023 | 6/7/2023 | 6/27/2023 | 0 | 11044 | 11044
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 598429 | 0
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/8/2023 | DOES |  | DOES | 529323 | 0
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X465 | EAGLE ACADEMY FOR YOUNG MEN - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X582 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
9 | X782 | THE HIGHBRIDGE GREEN SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X782 | THE HIGHBRIDGE GREEN SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X782 | THE HIGHBRIDGE GREEN SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X782 | THE HIGHBRIDGE GREEN SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
9 | X782 | THE HIGHBRIDGE GREEN SCHOOL | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0
9 | X824 | PASSAGES ACADEMY | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/13/2024 | IEH | 5/22/2024 | IEH | 12684 | 7309
9 | X851 | P.S. 53 - BRONX | DOE - RESOA | FY21 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
9 | X876 | BRONX LEADERSHIP ACADEMY - X | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/6/2024 | IEH | 5/16/2024 | IEH | 12265 | 6890
9 | X876 | BRONX LEADERSHIP ACADEMY - X | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
9 | X909 | X723 SPED - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/26/2023 | DOES |  | DOES | 50832 | 0
9 | X927 | X723 SPED - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/23/2024 | IEH | 8/6/2024 | IEH | 15251 | 332
9 | X970 | I.S. 241 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/6/2024 | IEH | 5/15/2024 | IEH | 11720 | 6345
9 | X970 | VALIDUS PREPRATORY ACADEMY -X | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 306000 | 0
9 | X970 | I.S. 241 - BRONX | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/30/2022 | DOER |  | DOER | 646553 | 0
9 | X970 | I.S. 241 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 514810 | 0
9 | XADW | BRONX CHARTER SCHOOL FOR EXCELLENCE 5 | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
10 | X003 | P.S. 3 - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/3/2021 | DOES |  | DOES | 145434 | 0
10 | X003 | P.S. 3 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 5/8/2024 | DOES | 50832
10 | X007 | P.S. 7 - BRONX | SCA CIP | PERM FIX- RETAINING WALL @ X007 | Scope | In-Progress | 7/18/2024 | 12/4/2024 |  | 0 | 462 | 462
10 | X007 | P.S. 7 - BRONX | SCA CIP | PERM FIX- RETAINING WALL @ X007 | Design | PNS | PNS | PNS | PNS | 0 | 1849 | 1849
10 | X007 | P.S. 7 - BRONX | SCA CIP | PERM FIX- RETAINING WALL @ X007 | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X007 | P.S. 7 - BRONX | SCA CIP | PERM FIX- RETAINING WALL @ X007 | CM,F&E | PNS | PNS | PNS | PNS | 0 | 2258 | 2258
10 | X007 | P.S. 7 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
10 | X007 | P.S. 7 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
10 | X007 | P.S. 7 - BRONX | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/31/2022 | DOER |  | DOER | 337640 | 0
10 | X007 | P.S. 7 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 1/24/2023 | DOES |  | DOES | 69054 | 0
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | Scope | In-Progress | 8/7/2024 | 11/6/2024 |  | 0 | 49 | 49
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/6/2023 | 4/9/2024 | 3/4/2024 | 0 | 13794 | 13794
10 | X008 | P.S. 8 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/28/2024 | DOES | 6/5/2024 | DOES | 65832
10 | X009 | P.S. 9 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/8/2023 | 4/11/2024 | 3/22/2024 | 0 | 16041 | 16041
10 | X009 | P.S. 9 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | Complete | 1/2/2018 | EMER | 4/30/2024 | EMER |  | 0
10 | X009 | P.S. 9 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
10 | X009 | P.S. 9 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
10 | X015 | P.S. 15 - BRONX | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 7/25/2023 | 11/27/2023 | 11/8/2023 | 0 | 16035 | 16035
10 | X015 | P.S. 291 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/24/2024 | DIIR | 103000
10 | X015 | P.S. 15 - BRONX | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
10 | X015 | P.S. 15 - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/4/2021 | DOES |  | DOES | 285032 | 0
10 | X015 | P.S. 15 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/18/2024 | DOES |  | DOES | 50832 | 0
10 | X020 | P.S. 20 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/9/2021 | 10/7/2021 | 11/17/2021 | 0 | 71002 | 71002
10 | X020 | X168 SPED - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION / FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/10/2021 | 3/16/2022 | 12/6/2021 | 0 | 5532 | 5532
10 | X020 | P.S. 20 - BRONX | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 5/4/2018 | FTK |  | FTK | 142544 | 121469
10 | X020 | X168 SPED - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/24/2024 | DIIR | 100000
10 | X020 | P.S. 20 - BRONX | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 5/8/2024 | DOER |  | DOER | 72118 | 0
10 | X020 | P.S. 20 - BRONX | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
10 | X020 | P.S. 20 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/29/2024 | DOES |  | DOES | 50832 | 0
10 | X023 | P.S. 23 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 4/1/2019 | DOES |  | DOES | 88910 | 0
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X024 | P.S. 24 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X024 | P.S. 24 - BRONX | SCA IEH | PO18-SPACE ID 1023: ABATE ACM PIPE INSULATION IN COLD CAFETERIA APPROX. 15' SPRAYED RED | Construction | Complete | 7/30/2024 | IEH | 8/8/2024 | IEH | 10363 | 1135
10 | X024 | P.S. 24 - BRONX | SCA IEH | PO18-SPACE ID 1023: ABATE ACM PIPE INSULATION IN COLD CAFETERIA APPROX. 10' SPRAYED RED ALSO ABATE P | Construction | Complete | 9/18/2024 | IEH | 9/29/2024 | IEH | 302 | 302
10 | X024 | P.S. 24 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 3/15/2021 | FTK |  | FTK | 8786 | 8786
10 | X024 | P.S. 24 - BRONX | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/5/2022 | DOER |  | DOER | 118632 | 0
10 | X024 | P.S. 24 - BRONX | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 475306 | 0
10 | X024 | P.S. 24 - BRONX | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 4/9/2024 | DOER |  | DOER | 107911 | 0
10 | X026 | P.S. 396 - BRONX | SCA CIP RESOA | FY21 RESO A PA SYSTEM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X026 | I.S. 390 - BRONX | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Scope | Complete | 1/19/2023 | 6/16/2023 | 8/23/2023 | 0 | 66366 | 66366
10 | X026 | I.S. 390 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X026 | I.S. 390 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X026 | I.S. 390 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X026 | I.S. 390 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X026 | I.S. 390 - BRONX | SCA IEH | PO18-GYMNASIUM ABATE APPROX 3 L.F. EACH FROM TWO CEILING PIPES | Construction | Complete | 6/14/2023 | IEH | 6/17/2024 | IEH | 22619 | 1271
10 | X026 | I.S. 390 - BRONX | SCA IEH | PO18-SPACE ID 4393(RM 315). THE 12X12 IS HOT AND THE SOFT CONCRETE FLOOR FILLER APPROXL 25 SQ. FT. | Construction | Complete | 8/15/2024 | IEH | 9/1/2024 | IEH | 26846 | 1401
10 | X026 | P.S. 396 - BRONX | DOE - RESOA | FY18 RESO A PLAYGROUNDS | Construction | Complete | 9/22/2022 | DOER | 12/16/2022 | DOER | 383292
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY22 RESO A LEARNING GARDEN | Construction | In-Progress | 4/13/2023 | DOER |  | DOER | 54161 | 0
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
10 | X026 | P.S. 396 - BRONX | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 152064 | 0
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 650000 | 0
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
10 | X026 | I.S. 390 - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
10 | X026 | P.S. 396 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
10 | X032 | P.S. 32 - BRONX | SCA IEH | PO18-SPACE ID: 4310 - ROOM 310 - TEST CEILINGS AND WALLS ABATE AND REPAIR CEILING PLASTER | Construction | Complete | 7/23/2024 | IEH | 8/7/2024 | IEH | 19419 | 1050
10 | X032 | P.S. 32 - BRONX | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 8/10/2022 | DOER |  | DOER | 292094 | 0
10 | X032 | P.S. 32 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/4/2023 | DOER |  | DOER | 202596 | 0
10 | X034 | X188 SPED - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
10 | X034 | X188 SPED - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 50832
10 | X037 | P.S. 37 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 3/24/2022 | 7/22/2022 | 4/5/2022 | 0 | 4364 | 4364
10 | X037 | P.S. 37 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
10 | X037 | P.S. 37 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
10 | X037 | P.S. 37 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
10 | X045 | I.S. 45 - BRONX | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/3/2021 | 2/7/2022 | 5/13/2022 | 0 | 152029 | 128556
10 | X045 | I.S. 45 - BRONX | SCA IEH | PO18-ABATE AND REPAIR TROWELLED ON FIREPROOFING IN FAN ROOM APPROX. 25SF VIOLATION 35273285K | Construction | In-Progress | 11/17/2022 | IEH |  | IEH | 2710 | 2135
10 | X045 | I.S. 45 - BRONX | SCA IEH | PO18-TEST WALLS ROOM 407 DRILL WALLS FOR ELECTRIC CONDUITS | Construction | Complete | 7/31/2024 | IEH | 8/23/2024 | IEH | 11812 | 833
10 | X045 | I.S. 45 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
10 | X046 | P.S. 46 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/6/2024 | DIIR | 6/17/2024 | DIIR | 50000 | 50000
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/2/2023 | 5/3/2023 | 9/12/2023 | 0 | 41375 | 41375
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 5/25/2023 | 9/26/2023 | 6/6/2023 | 0 | 943 | 943
10 | X054 | P.S. 54 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/5/2024 | DIIR | 250000
10 | X054 | P.S. 54 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
10 | X054 | P.S. 54 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
10 | X056 | P.S. 56 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 80000 | 0
10 | X056 | P.S. 56 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
10 | X056 | P.S. 56 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
10 | X056 | P.S. 56 - BRONX | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 1/18/2021 | DOES |  | DOES | 439 | 0
10 | X056 | P.S. 56 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/1/2023 | DOES | 5/14/2024 | DOES | 65832
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/1/2023 | 5/2/2023 | 9/20/2023 | 0 | 40517 | 40517
10 | X059 | P.S. 59 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/27/2023 | 5/26/2023 | 11/20/2023 | 0 | 534 | 534
10 | X059 | P.S. 59 - BRONX | SCA IEH | PO18-ABATE/REPLACE 9 X 9 ACM FLOOR TILES ROOM 502 APPROX: 5 X 5 AREA | Construction | Complete | 3/6/2024 | IEH | 4/29/2024 | IEH | 45564 | 1784
10 | X059 | P.S. 59 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 3/2/2020 | FTK |  | FTK | 214362 | 212494
10 | X079 | I.S. 447 - BRONX | SCA CIP RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 8/26/2019 | 12/27/2019 | 9/5/2019 | 0 | 4783 | 4783
10 | X079 | SCHOOL FOR ENVIR CITIZEN - BRONX | SCA CIP RESOA | FY21 RESO A SUPPLEMENTAL COOLING / FY21 RESO A ROOM CONVERSION | Scope | Complete | 9/2/2021 | 1/7/2022 | 1/20/2022 | 0 | 24072 | 24072
10 | X079 | I.S. 447 - BRONX | SCA IEH | PO18-SPACE ID: 2113 - TEST AND ABATE ACM PIPE INSULATION SPRAYED RED FOR ID, SLOP SINK ROOM 113 | Construction | Complete | 7/29/2024 | IEH | 8/29/2024 | IEH | 15814 | 1607
10 | X079 | I.S. 447 - BRONX | DOE - RESOA | FY13 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 148495 | 0
10 | X079 | I.S. 447 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
10 | X079 | SCHOOL FOR ENVIR CITIZEN - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
10 | X079 | I.S. 447 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 10/4/2019 | DOES |  | DOES | 157746 | 0
10 | X080 | I.S. 80 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/6/2023 | 4/19/2024 | 6/18/2024 | 0 | 21701 | 21701
10 | X080 | I.S. 80 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ X080 | Construction | In-Progress | 3/21/2023 | EMER |  | EMER | 21873 | 21873
10 | X080 | P.S. 280 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 405000 | 0
10 | X080 | I.S. 80 - BRONX | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/5/2020 | DOER |  | DOER | 858770 | 2339
10 | X081 | P.S. 81 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 1/6/2020 | 5/5/2020 | 1/29/2020 | 0 | 9666 | 9666
10 | X081 | P.S. 81 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
10 | X081 | P.S. 81 - BRONX | DOE - RESOA | FY10 RESO A FENCING FOR PLAYGROUND | Construction | PNS | PNS | PNS | PNS | DOER | 76000 | 0
10 | X081 | P.S. 81 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/5/2023 | 3/7/2024 | 4/23/2024 | 0 | 10505 | 1272
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/5/2023 | 6/10/2024 | 6/20/2024 | 0 | 21919 | 1031
10 | X085 | P.S. 85 - BRONX | SCA IEH | PO18-ABATE/REPLACE 9X9 ACM FLOOR TILES ROOMS 306,309,310 EACH ROOM APPROX. 632 SQ. FT. | Construction | In-Progress | 9/17/2024 | IEH |  | IEH | 725 | 725
10 | X085 | P.S. 85 - BRONX | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 9/6/2023 | DOER |  | DOER | 385643 | 0
10 | X085 | P.S. 85 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 468545 | 0
10 | X085 | P.S. 85 - BRONX | DOE - Skilled Trades | PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 6/28/2022 | DOES |  | DOES | 305973 | 0
10 | X085 | P.S. 85 - BRONX | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 11/2/2023 | DOES |  | DOES | 319218 | 0
10 | X086 | P.S. 86 - BRONX | SCA IEH | PO18-ABATE ACM PIPE INSULATION HOT WATER LINE ON THE 4TH FLOOR. LINE IS APPROXIMATELY 12' FROM THE G | Construction | Complete | 8/12/2024 | IEH | 9/7/2024 | IEH | 37201 | 900
10 | X086 | P.S. 86 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
10 | X086 | P.S. 86 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 381631 | 0
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/12/2022 | 10/11/2022 | 3/1/2023 | 0 | 84596 | 84596
10 | X091 | P.S. 91 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ X091 | Construction | In-Progress | 9/11/2023 | EMER |  | EMER | 459107 | 243398
10 | X091 | P.S. 91 - BRONX | Fast Track Projects | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/14/2019 | FTK |  | FTK | 75926 | 68645
10 | X091 | P.S. 91 - BRONX | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 194000 | 0
10 | X091 | P.S. 91 - BRONX | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 194000 | 0
10 | X091 | P.S. 91 - BRONX | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/1/2023 | DOER |  | DOER | 357216 | 0
10 | X091 | P.S. 91 - BRONX | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | In-Progress | 3/10/2023 | DOER |  | DOER | 111165 | 0
10 | X091 | P.S. 91 - BRONX | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | Complete | 4/23/2024 | DOER | 4/23/2024 | DOER | 302532
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 12/14/2023 | 3/18/2024 |  | 0 | 11342 | 414
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X094 | P.S. 94 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X094 | P.S. 94 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
10 | X094 | P.S. 94 - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 111424 | 0
10 | X094 | P.S. 94 - BRONX | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0
10 | X095 | P.S. 95 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/5/2019 | FTK |  | FTK | 119534 | 114798
10 | X095 | P.S. 344 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
10 | X095 | P.S. 95 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/30/2024 | DIIR | 7/9/2024 | DIIR | 75000
10 | X095 | P.S. 344 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
10 | X095 | P.S. 344 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
10 | X095 | P.S. 95 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
10 | X095 | P.S. 95 - BRONX | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
10 | X095 | P.S. 95 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/13/2023 | DOES |  | DOES | 65832 | 0
10 | X115 | M.S. 363 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/27/2019 | 6/27/2019 | 10/16/2019 | 0 | 24409 | 22888
10 | X115 | M.S. 363 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 10/26/2021 | EMER |  | EMER | 200977 | 77398
10 | X115 | M.S. 363 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
10 | X115 | M.S. 363 - BRONX | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 755000 | 0
10 | X115 | M.S. 363 - BRONX | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 188000 | 0
10 | X115 | M.S. 363 - BRONX | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
10 | X115 | M.S. 363 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/21/2022 | DOES |  | DOES | 201812 | 0
10 | X118 | I.S. 118 - BRONX | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Scope | Complete | 12/5/2018 | 3/5/2019 | 3/4/2019 | 0 | 36456 | 27239
10 | X118 | I.S. 118 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0
10 | X118 | I.S. 118 - BRONX | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
10 | X118 | I.S. 118 - BRONX | DOE - Skilled Trades | CAFETERIA LIGHTING UPGRADE & CEILING INSTALLATION | Construction | In-Progress | 8/1/2023 | DOES |  | DOES | 145120 | 0
10 | X118 | I.S. 118 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/2/2024 | DOES |  | DOES | 388882 | 0
10 | X122 | P.S. 310 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X122 | P.S. 310 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X122 | P.S. 310 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X122 | P.S. 310 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X122 | P.S. 310 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 4/9/2021 | FTK |  | FTK | 492347 | 485398
10 | X122 | P.S. 310 - BRONX | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
10 | X122 | P.S. 310 - BRONX | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 228000 | 0
10 | X122 | P.S. 310 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A STEM LAB | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A STEM LAB | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A STEM LAB | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY22 RESO A STEM LAB | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Scope | Complete | 6/17/2022 | 11/15/2022 | 7/3/2023 | 0 | 34610 | 18492
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/31/2023 | 5/1/2023 | 6/14/2023 | 0 | 102562 | 102562
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 7/13/2023 | 11/13/2023 | 7/31/2023 | 0 | 2317 | 2317
10 | X137 | I.S. 391 - BRONX | SCA IEH | PO18-ROOM 308 REPLACE 1 BROKEN FLOOR TILE AT SOUTH END OF CLASSROOM - ROOM 312 REPLACE 2 BROKEN FLOO | Construction | In-Progress | 6/28/2024 | IEH |  | IEH | 1293 | 543
10 | X137 | I.S. 391 - BRONX | DIIT - RESOA | FY17 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 76250 | 0
10 | X137 | I.S. 391 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 7/15/2024 | DIIR | 250000 | 250000
10 | X141 | M.S./H.S. 141 - BRONX | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X141 | M.S./H.S. 141 - BRONX | SCA IEH | PO18-ABATE/REPLACE DETERIORATED 9X9 ACM FLOOR TILES, NO SUMMER PROGRAM 304A; 35 SQ.FT., 107; 756 SQ. | Construction | Complete | 8/9/2024 | IEH | 9/26/2024 | IEH | 74333 | 779
10 | X141 | M.S./H.S. 141 - BRONX | SCA IEH | PO18-ABATE AND REPAIR DAMAGED FLOOR TILES ROOM #107 | Construction | Complete | 8/12/2024 | IEH | 8/20/2024 | IEH | 35719 | 1014
10 | X141 | M.S./H.S. 141 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0
10 | X141 | M.S./H.S. 141 - BRONX | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | Complete | 12/30/2019 | DOER | 10/31/2023 | DOER | 761480 | 671739
10 | X141 | M.S./H.S. 141 - BRONX | DOE - RESOA | FY22 RESO A CAFETRIA UPGRADE | Construction | In-Progress | 8/25/2023 | DOER |  | DOER | 167651 | 0
10 | X141 | M.S./H.S. 141 - BRONX | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | Complete | 11/30/2020 | DOES | 11/15/2023 | DOES | 643124 | 317236
10 | X141 | M.S./H.S. 141 - BRONX | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 1/27/2021 | DOES |  | DOES | 154029 | 0
10 | X141 | M.S./H.S. 141 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 11/1/2022 | DOES |  | DOES | 140998 | 0
10 | X143 | I.S. 244 - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/14/2019 | 12/16/2022 | 12/7/2022 | 0 | 14578 | 14578
10 | X143 | I.S. 244 - BRONX | SCA IEH | PO18-REMOVE APPX 8 FEET OF ACM COVERING LOCATED IN 5TH FLOOR PIPE CHASE IN GIRLS BATHROOM SPRAYED RE | Construction | Complete | 7/29/2024 | IEH | 8/18/2024 | IEH | 13345 | 1455
10 | X143 | MARIE CURIE HS FOR NURSING - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/21/2024 | DIIR | 7/18/2024 | DIIR | 50000 | 50000
10 | X143 | I.S. 244 - BRONX | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
10 | X143 | I.S. 244 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
10 | X143 | MARIE CURIE HS FOR NURSING - BRONX | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
10 | X159 | P.S. 159 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/3/2024 | IEH | 13956 | 8581
10 | X177 | BEDFORD PARK ELEMENTARY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
10 | X177 | BEDFORD PARK ELEMENTARY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 50832 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X205 | P.S. 205 - BRONX | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 7/22/2022 | DOER |  | DOER | 261803 | 0
10 | X206 | I.S. 206B - BRONX | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 6/30/2021 | 3/25/2022 | 2/15/2022 | 0 | 21090 | 21090
10 | X206 | I.S. 206B - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
10 | X206 | I.S. 206B - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 28172 | 0
10 | X206 | I.S. 206B - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 2/5/2015 | DOES |  | DOES | 171784 | 0
10 | X254 | I.S. 254 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/24/2023 | DOES |  | DOES | 354611 | 0
10 | X279 | P.S. 279 - BRONX | Fast Track Projects | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 80000 | 0
10 | X279 | P.S. 279 - BRONX | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 435000 | 0
10 | X279 | P.S. 279 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/24/2022 | DOER |  | DOER | 28508 | 0
10 | X279 | P.S. 279 - BRONX | DOE - Skilled Trades | ACE FAN SYSTEM UPGRADE | Construction | In-Progress | 10/2/2019 | DOES |  | DOES | 14946 | 95806
10 | X283 | I.S. 228 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/27/2024 | DOER |  | DOER | 122221 | 0
10 | X283 | I.S. 228 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/20/2023 | DOES |  | DOES | 50832 | 0
10 | X306 | P.S. 306 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 11/29/2023 | 4/2/2024 | 2/28/2024 | 0 | 13189 | 13189
10 | X306 | P.S. 306 - BRONX | SCA Emergency Response | EMERGENCY WORK- FIRE PUMP | Construction | In-Progress | 1/25/2013 | EMER |  | EMER |  | 0
10 | X306 | I.S. 331 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/5/2024 | DIIR | 5/14/2024 | DIIR | 150000
10 | X306 | P.S. 306 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
10 | X306 | X186 SPED - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 110000 | 0
10 | X306 | X186 SPED - BRONX | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 104000 | 0
10 | X306 | P.S. 306 - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMPS | Construction | In-Progress | 6/21/2019 | DOES |  | DOES | 230055 | 0
10 | X306 | P.S. 306 - BRONX | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | Complete | 11/30/2020 | DOES | 2/23/2024 | DOES | 1442458
10 | X306 | P.S. 306 - BRONX | DOE - Skilled Trades | PUBLIC ADDRESS SYSTEM | Construction | In-Progress | 6/8/2021 | DOES |  | DOES | 182479 | 0
10 | X306 | I.S. 331 - BRONX | Trust For Public Land | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 1/20/2024 | TPL |  | TPL | 5099430 | 1398556
10 | X340 | P.S. 340 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
10 | X360 | P.S. 360 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 12/5/2023 | 3/7/2024 |  | 0 | 8411 | 1875
10 | X360 | P.S. 360 - BRONX | Fast Track Projects | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 12/10/2019 | FTK |  | FTK | 78481 | 77364
10 | X360 | P.S. 360 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/23/2023 | DIIR | 4/5/2024 | DIIR | 150000 | 150000
10 | X361 | P.S. 94 - BRONX | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 9/29/2020 | FTK |  | FTK | 153154 | 122661
10 | X368 | X721 SPED - BRONX | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
10 | X368 | M.S./H.S. 368 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
10 | X368 | M.S./H.S. 368 - BRONX | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
10 | X368 | M.S./H.S. 368 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/28/2024 | DOES | 6/6/2024 | DOES | 50832
10 | X373 | ROSE HILL PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 50832 | 0
10 | X430 | DISCOVERY HS - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 130000 | 0
10 | X430 | KINGSBRIDGE INTERNATIONAL HS - X | DOE - RESOA | FY11 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0
10 | X430 | KINGSBRIDGE INTERNATIONAL HS - X | DOE - RESOA | FY14 RESO A ROOM CONVERSIONS / PART | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0
10 | X430 | M.S./H.S. 342 - BRONX | DOE - RESOA | FY18 RESO A LIBRARY UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 724826 | 0
10 | X430 | M.S./H.S. 342 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 12/12/2022 | DOES |  | DOES | 65771 | 0
10 | X430 | KINGSBRIDGE INTERNATIONAL HS - X | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/24/2023 | DOES |  | DOES | 530995 | 0
10 | X430 | M.S./H.S. 342 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 65832 | 0
10 | X431 | M.S./H.S. 342 - BRONX | DOE - RESOA | RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
10 | X432 | ROSE HILL PRE-K CENTER | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 161000 | 0
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP RESOA | RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 11/17/2023 | 3/22/2024 |  | 0 | 18215 | 969
10 | X435 | KAPPA - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 1/25/2024 | DIIR |  | DIIR | 100000 | 0
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
10 | X435 | BELMONT PREPARATORY HS - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/26/2024 | DOER |  | DOER | 171996 | 0
10 | X435 | HS OF LAW & COMMUNITY SERV - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/25/2023 | DOER |  | DOER | 179084 | 0
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 2/17/2023 | DOES |  | DOES | 968456 | 1600
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE | Scope | In-Progress | 6/18/2021 | 10/20/2021 |  | 0 | 19172 | 19172
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X440 | DEWITT CLINTON HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
10 | X440 | DEWITT CLINTON HS - X | SCA IEH | PO18-ABATE ACM PIPE INSULATION ROOM 201 A PIECE OF ACM FELL OFF NO KIDS WERE IN THE ROOM ROOM IS NOW | Construction | In-Progress | 1/26/2024 | IEH |  | IEH | 1228 | 103
10 | X440 | DEWITT CLINTON HS - X | Fast Track Projects | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/28/2022 | FTK |  | FTK | 222773 | 210688
10 | X440 | PATHWAYS TO GRADUATION - CITYWIDE | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
10 | X440 | DEWITT CLINTON HS - X | DOE - Skilled Trades | ACE- STEAM SYSTEM UPGRADE | Construction | In-Progress | 4/9/2019 | DOES |  | DOES | 286139 | 0
10 | X440 | DEWITT CLINTON HS - X | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 2/3/2023 | DOES |  | DOES | 1036316 | 0
10 | X441 | DEWITT CLINTON HS - X | SCA IEH | PO18-ABATE AND REPAIR AS NEEDED IN VARIOUS LOCATIONS DUE TO THE AHERA PERIODIC SURVELLANCE REPORT PL | Construction | In-Progress | 5/22/2023 | IEH |  | IEH | 17671 | 365
10 | X443 | ROSE HILL PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/18/2024 | DOES |  | DOES | 65832 | 0
10 | X444 | ROSE HILL PRE-K CENTER | SCA IEH | PO18-ABATE 7 FT X 9 FT SECTION OF THE WOOD FLOOR IN CLASSROOM 303 SOFT CONCRETE FILLER MATERIAL / FE | Construction | In-Progress | 8/28/2023 | IEH |  | IEH | 2290 | 515
10 | X444 | ROSE HILL PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 5/3/2024 | IEH | 12268 | 6893
10 | X444 | ROSE HILL PRE-K CENTER | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 153000 | 0
10 | X445 | BRONX HS OF SCIENCE - X | SCA CIP RESOA | RESO A CAFETERIA UPGRADE | Scope | In-Progress | 3/22/2022 | 7/21/2022 |  | 0 | 42212 | 23686
10 | X445 | BRONX HS OF SCIENCE - X | SCA IEH | PO18-ABATE PIPE INSULATION SPRAYED IN RED LOCATED IN WATER MAIN ROOM BEHIND KITCHEN APPROX: 45 FT. | Construction | Complete | 3/26/2024 | IEH | 5/12/2024 | IEH | 22170 | 2385
10 | X445 | BRONX HS OF SCIENCE - X | SCA IEH | PO18-TEST CEILING IN HALLWAY NEAR ROOM 45S MEDICAL SUITE | Construction | Complete | 3/27/2024 | IEH | 4/27/2024 | IEH | 17426 | 16851
10 | X445 | BRONX HS OF SCIENCE - X | SCA IEH | PO18-ABATE BASEMENT HALLWAY CEILING ABATE AND REPAIR PIPE INSULATION IN BASEMENT HALLWAY | Construction | Complete | 8/1/2024 | IEH | 8/4/2024 | IEH | 18994 | 1208
10 | X445 | BRONX HS OF SCIENCE - X | SCA IEH | PO18-ABATE MEDICAL SUITE CEILING 049, 049A, 049B, 049C, 049D, 049E | Construction | Complete | 8/7/2024 | IEH | 8/11/2024 | IEH | 48410 | 1358
10 | X445 | BRONX HS OF SCIENCE - X | DOE - RESOA | FY14 RESO A ROOM CONVERSIONS / PART | Construction | PNS | PNS | PNS | PNS | DOER | 16902 | 0
10 | X445 | BRONX HS OF SCIENCE - X | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 10/11/2023 | DOES |  | DOES | 175579 | 0
10 | X445 | BRONX HS OF SCIENCE - X | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 3/8/2021 | DOES |  | DOES | 220921 | 0
10 | X445 | BRONX HS OF SCIENCE - X | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 388699 | 0
10 | X469 | X000 - BRONX | SCA CIP RESOA | FY19 RESO A ROOFTOP PLAYGROUND | Scope | PNS | PNS | PNS | PNS | 0 | 17078 | 39
10 | X475 | BRONX SCHOOL OF LAW & FINANCE - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 151000
10 | X475 | BRONX THEATRE HS - BRONX | DOE - RESOA | FY19 RESO A HYDROPONIC LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
10 | X475 | ELLIS PREPARATORY ACADEMY-X | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 12/26/2022 | DOER |  | DOER | 304739 | 0
10 | X475 | BRONX THEATRE HS - BRONX | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 55000 | 0
10 | X475 | MARBLE HILL INTERNATIONAL HS - X | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/12/2021 | DOES |  | DOES | 200590 | 0
10 | X475 | MARBLE HILL INTERNATIONAL HS - X | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/19/2022 | DOES |  | DOES | 269992 | 0
10 | X475 | BX ENGINEERING & TECH ACADEMY - X | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/2/2024 | DOES |  | DOES | 743245 | 0
10 | X475 | BRONX THEATRE HS - BRONX | DOE - Skilled Trades | EXTERIOR MASONRY REPAIRS | Construction | In-Progress | 11/29/2023 | DOES |  | DOES | 260000 | 0
10 | X475 | BRONX THEATRE HS - BRONX | DOE - Skilled Trades | ELEVATOR CABLE REPLACEMENT | Construction | In-Progress | 3/12/2024 | DOES |  | DOES | 78000 | 0
10 | X476 | X000 - BRONX | DOE - RESOA | RESO A ATHLETIC FIELD UPGRADE | Construction | Complete | 12/22/2022 | DOER | 3/26/2024 | DOER | 5050000 | 5524662
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/3/2023 | 5/4/2023 | 7/19/2023 | 0 | 73400 | 57647
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | SCA IEH | PO18-SPACE ID: 5302 CLASSROOM 302 - DAMAGED 9' X 9' FLOOR TILES ASSUMED UNDER SINK IN CLASSROOM. TES | Construction | In-Progress | 9/19/2024 | IEH |  | IEH | 0 | 0
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 58336 | 0
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/12/2022 | DOES |  | DOES | 68617 | 538855
10 | X660 | HIGH SCHOOL FOR ENERGY AND TECHNOLOGY - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 8/4/2023 | DOES |  | DOES | 549827 | 0
10 | X779 | P.S. 315 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY22 RESO A GYMNASIUM UPGRADE | Scope | Complete | 8/11/2022 | 3/1/2023 | 1/13/2023 | 0 | 20491 | 12876
10 | X779 | P.S. 315 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
10 | X779 | P.S. 315 - BRONX | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
10 | X779 | P.S. 315 - BRONX | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
10 | X779 | P.S. 315 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/3/2024 | DOES |  | DOES | 65832 | 0
10 | X780 | SUCCESS ACADEMY CHARTER SCHOOL - HARLEM 6 | SCA IEH | PO18-ABATE ACM PIPE INSULATION IN CAFETERIA APPROX: 40 FT. | Construction | Complete | 8/30/2024 | IEH | 9/12/2024 | IEH | 20788 | 985
10 | X781 | THE BRONX STEM AND ARTS ACADEMY - BRONX | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 812000 | 0
10 | X819 | P.S. 207 - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/18/2024 | IEH | 12522 | 6958
10 | X819 | P.S. 207 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 437000 | 0
10 | X819 | P.S. 207 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
10 | X819 | P.S. 207 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
10 | X819 | P.S. 207 - BRONX | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 2/11/2022 | DOER |  | DOER | 456732 | 0
10 | X819 | P.S. 207 - BRONX | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 263537 | 0
10 | X826 | P.S. 226 - BRONX | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | In-Progress | 3/22/2024 | DOER |  | DOER | 272491 | 0
10 | X826 | P.S. 226 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/18/2024 | DOES | 5/9/2024 | DOES | 50832 | 8022
10 | X827 | P.S. 226 - BRONX | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | In-Progress | 11/22/2023 | DOER |  | DOER | 98973 | 0
10 | X842 | X168 SPED - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/29/2024 | IEH | 9/26/2024 | IEH | 15040 | 121
10 | X843 | P.S. 246 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
10 | X843 | P.S. 246 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 11/22/2023 | DOEL |  | DOEL | 121996 | 121996
10 | X843 | P.S. 246 - BRONX | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 52000 | 0
10 | X852 | BRONX DANCE ACADEMY - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/17/2024 | IEH | 5/7/2024 | IEH | 12693 | 7318
10 | X852 | BRONX DANCE ACADEMY - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
10 | X852 | BRONX DANCE ACADEMY - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
10 | X852 | BRONX DANCE ACADEMY - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 8/2/2023 | DOER |  | DOER | 16863 | 0
10 | X852 | BRONX DANCE ACADEMY - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
10 | X859 | KIPP FREEDOM CHARTER SCHOOL - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/16/2024 | DOES |  | DOES | 65832 | 0
10 | XAYF | MINIVENTURES OF NY, INC.- SITE #4 - BRONX | Fast Track Projects | LSP - ACS EARLY LEARN LEASE RENEWAL | Construction | In-Progress | 11/30/2023 | FTK |  | FTK | 154843 | 79956
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 10/19/2023 | 2/23/2024 | 2/26/2024 | 0 | 10190 | 2655
11 | X012 | X012 SPED - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 1/10/2024 | 5/24/2024 | 4/24/2024 | 0 | 393 | 393
11 | X012 | X012 SPED - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
11 | X016 | P.S. 16 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
11 | X016 | P.S. 16 - BRONX | DOE - RESOA | FY23 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
11 | X016 | P.S. 16 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
11 | X019 | P.S. 19 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/24/2020 | EMER |  | EMER | 46508 | 31884
11 | X019 | P.S. 19 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
11 | X019 | P.S. 19 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
11 | X021 | P.S. 21 - BRONX | SCA IEH | PO18-ABATEMENT OF WALL PAINT, PIPE FLANGE GASKET ON OIL PUMP AREA PIPE JOINT COMPOUND TO FIBERGLASS | Construction | Complete | 1/24/2024 | IEH | 5/12/2024 | IEH | 28492 | 19647
11 | X021 | P.S. 21 - BRONX | SCA IEH | PO18-BOILER ROOM, REPAIR 6 SQ. FT. DAMAGED BOILER SHELL - REPAIR AND ENCAPSULATE FLOOR: CAFETERIA, 3 | Construction | In-Progress | 7/3/2024 | IEH |  | IEH | 122921 | 869
11 | X021 | P.S. 21 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 8/9/2019 | DOES |  | DOES | 301364 | 0
11 | X021 | P.S. 21 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/14/2024 | DOES | 5/21/2024 | DOES | 65832 | 15193
11 | X041 | P.S. 41 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 1/9/2020 | 5/8/2020 | 1/15/2020 | 0 | 6825 | 6825
11 | X041 | P.S. 41 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/24/2022 | DOER |  | DOER | 372443 | 0
11 | X068 | P.S. 68 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X068 | P.S. 68 - BRONX | Fast Track Projects | FY24 RESO A CTF ROOM CONVERSION | Construction | In-Progress | 5/15/2024 | FTK |  | FTK | 212218 | 115547
11 | X076 | P.S. 76 - BRONX | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 9/29/2020 | FTK |  | FTK | 105863 | 105863
11 | X076 | P.S. 76 - BRONX | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
11 | X076 | P.S. 76 - BRONX | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 344826 | 0
11 | X076 | P.S. 76 - BRONX | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/18/2022 | DOES |  | DOES | 108529 | 0
11 | X078 | P.S. 78 - BRONX | DOE - RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 90000 | 0
11 | X083 | P.S. 83 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/13/2023 | DIIR | 4/2/2024 | DIIR | 100000 | 99988
11 | X083 | P.S. 83 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
11 | X083 | P.S. 83 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
11 | X083 | P.S. 83 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 9/27/2023 | DOEL | 5/9/2024 | DOEL | 55828 | 55828
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X087 | P.S. 87 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X087 | P.S. 87 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
11 | X087 | P.S. 87 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 200000 | 47410
11 | X089 | P.S. 89 - BRONX | SCA IEH | PO18-ABATE AND REPLACE FLOORING ROOMS #204, 407, 413 | Construction | Complete | 7/9/2024 | IEH | 7/20/2024 | IEH | 36931 | 2560
11 | X089 | P.S. 89 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 100000 | 0
11 | X089 | P.S. 89 - BRONX | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 3/9/2020 | DOES |  | DOES | 352561 | 0
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 5/3/2022 | 8/2/2022 | 7/22/2022 | 0 | 30292 | 30292
11 | X096 | P.S. 96 - BRONX | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X097 | P.S. 97 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/24/2022 | 4/22/2022 | 5/20/2022 | 0 | 34654 | 34654
11 | X097 | P.S. 97 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/19/2022 | DOES |  | DOES | 63866 | 0
11 | X097 | P.S. 97 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 9/28/2023 | DOES |  | DOES | 65832 | 0
11 | X103 | P.S. 103 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
11 | X103 | P.S. 103 - BRONX | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 773021 | 0
11 | X103 | P.S. 103 - BRONX | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/11/2022 | DOES |  | DOES | 878758 | 0
11 | X103 | P.S. 103 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/1/2023 | DOES | 6/3/2024 | DOES | 65832 | 9520
11 | X105 | P.S. 105 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION- SIDEWALK BRIDGE INSTALLATION @ X105 | Construction | In-Progress | 1/30/2023 | EMER |  | EMER | 139554 | 129060
11 | X105 | P.S. 105 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
11 | X105 | P.S. 105 - BRONX | Trust For Public Land | FY18 RESO A PLAYGROUNDS | Construction | PNS | PNS | PNS | PNS | TPL | 800000 | 0
11 | X106 | P.S. 106 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/6/2020 | EMER |  | EMER | 94984 | 82405
11 | X106 | P.S. 106 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/24/2024 | DIIR | 150000
11 | X108 | P.S. 108 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 5/30/2024 | DIIR | 180000 | 180000
11 | X108 | P.S. 108 - BRONX | DOE - RESOA | FY19 RESO A TOILETS - STUDENTS | Construction | In-Progress | 3/17/2022 | DOER |  | DOER | 169357 | 0
11 | X108 | P.S. 108 - BRONX | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
11 | X111 | P.S. 111 - BRONX | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
11 | X111 | P.S. 111 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
11 | X112 | P.S. 112 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/26/2023 | 4/26/2023 | 6/21/2023 | 0 | 66549 | 48240
11 | X112 | P.S. 112 - BRONX | Fast Track Projects | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/14/2019 | FTK |  | FTK | 130816 | 128934
11 | X112 | P.S. 112 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 221000 | 0
11 | X112 | P.S. 112 - BRONX | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 170000 | 0
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | FY22 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 10/7/2022 | 5/22/2023 | 4/20/2023 | 0 | 23797 | 23797
11 | X113 | THE YOUNG SCHOLARS ACADEMY - BRONX | DIIT - RESOA | FY16 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 1/28/2020 | DIIR |  | DIIR | 35000 | 0
11 | X113 | NORTH BRONX SCHOOL OF EMPOWERMENT | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
11 | X113 | NORTH BRONX SCHOOL OF EMPOWERMENT | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
11 | X113 | SCHOOL OF DIPLOMACY | DOE - RESOA | RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
11 | X113 | SCHOOL OF DIPLOMACY | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
11 | X113 | SCHOOL OF DIPLOMACY | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/16/2022 | DOES |  | DOES | 196585 | 0
11 | X113 | SCHOOL OF DIPLOMACY | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/7/2023 | DOES |  | DOES | 874246 | 0
11 | X121 | P.S. 121 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
11 | X121 | P.S. 121 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/12/2024 | DOES | 6/19/2024 | DOES | 65832 | 189
11 | X127 | I.S. 127 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
11 | X127 | I.S. 127 - BRONX | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
11 | X127 | I.S. 127 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/28/2022 | DOES |  | DOES | 195345 | 0
11 | X127 | I.S. 127 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/5/2024 | DOES |  | DOES | 681548 | 0
11 | X127 | I.S. 127 - BRONX | DOE - Skilled Trades | WATER MAIN REPAIR | Construction | In-Progress | 1/23/2023 | DOES |  | DOES | 148733 | 0
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP GARDEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP GARDEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP GARDEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X135 | I.S. 556 - BRONX | SCA IEH | PO18-REMOVE ASBESTOS FLOORS AND CLOSETS IN CLASSROOMS PRINCIPAL WOULD LIKE CLOSETS REMOVE FOR MORE S | Construction | In-Progress | 10/7/2022 | IEH |  | IEH | 2673 | 2098
11 | X135 | I.S. 556 - BRONX | SCA IEH | PO18-ABATE LOOSE-CRACKED 9' X 9' ACM FLOOR TILES IN ROOM 315 - 3' X 1.5' | Construction | Complete | 2/1/2024 | IEH | 4/26/2024 | IEH | 38148 | 2211
11 | X135 | I.S. 326 - BRONX | Fast Track Projects | EMERGENCY STABILIZATION- GYM ROOF REPLACEMENT | Construction | In-Progress | 5/8/2019 | FTK |  | FTK | 1378661 | 1238651
11 | X135 | I.S. 326 - BRONX | Fast Track Projects | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 32000 | 0
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 6/28/2023 | DOER |  | DOER | 156559 | 0
11 | X135 | PELHAM ACADEMY OF ACADEMICS AND COMMUNITY ENGAGEMENT | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/27/2023 | DOER |  | DOER | 527115 | 0
11 | X135 | I.S. 326 - BRONX | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 10/13/2023 | DOES |  | DOES | 160630 | 0
11 | X135 | I.S. 556 - BRONX | DOE - Skilled Trades | PLAYGROUND | Construction | In-Progress | 12/13/2019 | DOES |  | DOES | 181595 | 0
11 | X135 | I.S. 326 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/19/2024 | DOES |  | DOES | 607016 | 0
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/5/2023 | 4/8/2024 | 4/15/2024 | 0 | 26876 | 21713
11 | X142 | I.S. 529 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 8/1/2019 | FTK |  | FTK | 158956 | 146234
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/12/2024 | DIIR | 6/30/2024 | DIIR | 130000 | 129534
11 | X142 | I.S. 532 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/5/2024 | DIIR | 50000
11 | X142 | I.S. 529 - BRONX | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/18/2020 | DOER |  | DOER | 267179 | 0
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 1/30/2023 | DOER | 3/29/2023 | DOER | 345539 | 304
11 | X142 | I.S. 532 - BRONX | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 361909 | 0
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/11/2024 | DOER |  | DOER | 400000 | 0
11 | X142 | I.S. 532 - BRONX | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
11 | X142 | I.S. 529 - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 2/2/2023 | DOES |  | DOES | 569355 | 0
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X144 | I.S. 144 - BRONX | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X144 | I.S. 144 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 9/27/2023 | DOER |  | DOER | 140396 | 0
11 | X144 | I.S. 144 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
11 | X153 | P.S. 153 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X153 | P.S. 153 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/10/2024 | DIIR | 4/8/2024 | DIIR | 87000 | 87000
11 | X153 | P.S. 153 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
11 | X160 | P.S. 160 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/4/2021 | 7/2/2021 | 6/15/2021 | 0 | 15215 | 15215
11 | X160 | P.S. 160 - BRONX | SCA IEH | PO18-SPACE ID: 1003 C3 TANK ROOM: ABATE APPROX. 25' OF PIPE INSULATION, MARKED FOR ID. | Construction | Complete | 5/31/2024 | IEH | 6/12/2024 | IEH | 427 | 427
11 | X160 | P.S. 160 - BRONX | SCA IEH | PO18-REPLACE APPROXIMATELY 900 SQ FT OF ACM FLOOR TILES IN CLASSROOM 110 CLASSROOM IS A D75 CLASSROO | Construction | In-Progress | 9/25/2024 | IEH |  | IEH | 0 | 0
11 | X160 | P.S. 160 - BRONX | Fast Track Projects | LSP HOT WATER TANK IN BOILER ROOM | Construction | In-Progress | 7/15/2022 | FTK |  | FTK | 235492 | 63826
11 | X160 | THE EQUALITY CHARTER SCHOOL - X | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 6/18/2022 | DOER |  | DOER | 318856 | 0
11 | X160 | P.S. 160 - BRONX | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 155715 | 0
11 | X160 | P.S. 160 - BRONX | DOE - Skilled Trades | CHARTER MATCH CEILING TILE REPLACEMENT | Construction | In-Progress | 12/22/2023 | DOES |  | DOES | 463919 | 0
11 | X169 | P.S. 169 - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
11 | X175 | P.S. 175 - BRONX | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 7/5/2019 | FTK |  | FTK | 46277 | 46277
11 | X175 | P.S. 175 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
11 | X175 | P.S. 175 - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
11 | X175 | P.S. 175 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75150 | 0
11 | X178 | P.S. 178 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 229000 | 0
11 | X178 | P.S. X596 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
11 | X178 | P.S. 178 - BRONX | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 322828 | 0
11 | X178 | P.S. 178 - BRONX | DOE - RESOA | RESO A MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 84116 | 0
11 | X178 | P.S. 178 - BRONX | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 207276 | 0
11 | X180 | I.S. 180 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/31/2024 | DIIR | 4/10/2024 | DIIR | 150000
11 | X180 | I.S. 180 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 7/26/2024 | DIIR |  | DIIR | 150000 | 0
11 | X180 | I.S. 180 - BRONX | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
11 | X181 | I.S. 181 - BRONX | Fast Track Projects | FY15 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 1/1/2024 | FTK |  | FTK | 2540243 | 160137
11 | X181 | I.S. 181 - BRONX | DIIT - RESOA | FY14 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35000 | 0
11 | X181 | I.S. 181 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 7/8/2024 | DIIR |  | DIIR | 100000 | 0
11 | X181 | I.S. 181 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Scope | Complete | 4/9/2021 | 7/12/2021 | 7/27/2022 | 0 | 12652 | 10900
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 161246 | 0
11 | X194 | P.S./I.S. 194 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 100000 | 0
11 | X194 | P.S./I.S. 194 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/17/2024 | DOES |  | DOES | 50832 | 0
11 | X292 | YOUNG VOICES ACADEMY OF THE BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
11 | X311 | THE STEAM BRIDGE SCHOOL - BRONX | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
11 | X311 | THE STEAM BRIDGE SCHOOL - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/9/2024 | DOES | 5/21/2024 | DOES | 65832
11 | X314 | THE MATILDA AVENUE SCHOOL - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
11 | X314 | THE MATILDA AVENUE SCHOOL - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/6/2024 | DOES |  | DOES | 65832 | 0
11 | X362 | NEW WORLD HS - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
11 | X362 | NEW WORLD HS - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 81000 | 0
11 | X362 | NEW WORLD HS - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
11 | X362 | THE BRONXWOOD PREPARATORY ACADEMY - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
11 | X362 | NEW WORLD HS - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 196000 | 0
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
11 | X415 | BRONXDALE HIGH SCHOOL - BRONX | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE / PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | Complete | 12/1/2023 | 6/6/2024 | 5/1/2024 | 0 | 12757 | 2896
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | SCA IEH | PO18-ABATE/ REPLACE PATCHED LENOLEUM FLOOR WITH NEW VINYLE TILE. LOCATION IS ROOM 211, CLASSROOM IS | Construction | In-Progress | 8/28/2023 | IEH |  | IEH | 1315 | 740
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | SCA IEH | PO18-ABATE AUDITORIUM WALLS FOR INSTALLATION OF AC UNITS | Construction | Complete | 4/19/2024 | IEH | 6/16/2024 | IEH | 15999 | 2893
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 139586 | 0
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
11 | X415 | ASTOR COLLEGIATE HS - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
11 | X415 | PELHAM PREP HS - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/10/2024 | DIIR |  | DIIR | 75000 | 75000
11 | X415 | BRONXDALE HIGH SCHOOL - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
11 | X415 | PELHAM PREP HS - BRONX | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
11 | X415 | CHRISTOPHER COLUMBUS CAMPUS YABC | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 4/2/2019 | DOES |  | DOES | 331927 | 0
11 | X415 | COLLEGIATE INST FOR MATH & SCI - X | DOE - Skilled Trades | ELEVATOR MODERNIZATIONS | Construction | In-Progress | 3/31/2022 | DOES |  | DOES | 103592 | 18828
11 | X415 | CHRISTOPHER COLUMBUS CAMPUS YABC | DOE - Skilled Trades | BCC PLAN REVIEW- ELEVATOR MACHINE ROOM UPGRADE | Construction | In-Progress | 7/8/2023 | DOES |  | DOES |  | 0
11 | X425 | X176 SPED - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 11/1/2021 | EMER |  | EMER | 12028 | 12028
11 | X425 | HS FOR WRITING & COMM ARTS - X | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/17/2021 | EMER |  | EMER | 1621507 | 1621507
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN BASEMENT OIL TANK ROOM AND BASEMENT BOILER ROOM | Construction | In-Progress | 7/17/2023 | IEH |  | IEH | 1320 | 570
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN 1ST FLOOR PLENUM ABOVE GYM #2 ABATE AND REPAIR SOFFIT PLAST | Construction | In-Progress | 2/29/2024 | IEH |  | IEH | 63262 | 1656
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA IEH | PO18-ABATE 400 LF OF PIPE LOCATED LOCATED IN BASEMENT CAFETERIA & KITCHEN 760 GUN HILL ROAD - IMMACU | Construction | In-Progress | 9/18/2024 | IEH |  | IEH | 181 | 181
11 | X425 | BRONX LAB SCHOOL - BRONX | Fast Track Projects | INTERIOR SPACES | Construction | In-Progress | 9/18/2018 | FTK |  | FTK | 157414 | 137414
11 | X425 | HS FOR CONTEMPORARY ARTS - X | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 9/24/2024 | DIIR | 100000
11 | X425 | BRONX AEROSPACE HS - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 326000 | 0
11 | X425 | BRONX ACAD OF HEALTH CAREERS - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
11 | X425 | HS FOR CONTEMPORARY ARTS - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
11 | X425 | COMM HS FOR SOCIAL JUSTICE - X | DOE - RESOA | FY10 RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
11 | X425 | BRONX LAB SCHOOL - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 109334 | 0
11 | X425 | HS OF COMPUTERS & TECHNOLOGY - X | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 520694 | 0
11 | X425 | HS FOR WRITING & COMM ARTS - X | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
11 | X425 | BRONX LAB SCHOOL - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/6/2023 | DOES |  | DOES | 784344 | 0
11 | X425 | BRONX LAB SCHOOL - BRONX | DOE - Skilled Trades | GYMNASIUM UPGRADE | Construction | In-Progress | 1/5/2024 | DOES |  | DOES | 282000 | 0
11 | X426 | HS OF COMPUTERS & TECHNOLOGY - X | DOE - RESOA | FY16 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
11 | X455 | BRONX HEALTH SCIENCES HS - X | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 1/27/2023 | 5/30/2023 | 7/13/2023 | 0 | 12222 | 12222
11 | X455 | X176 SPED - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 100000 | 0
11 | X455 | X176 SPED - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 327946 | 0
11 | X455 | BRONX HEALTH SCIENCES HS - X | DOE - RESOA | RESO A INTERIOR SPACES | Construction | PNS | PNS | PNS | PNS | DOER | 543937 | 0
11 | X455 | BRONX HEALTH SCIENCES HS - X | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
11 | X455 | BRONX HEALTH SCIENCES HS - X | DOE - RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
11 | X455 | X176 SPED - BRONX | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 626000 | 0
11 | X455 | HARRY S. TRUMAN HS - X | DOE - Skilled Trades | COOLING TOWER REPLACEMENT | Construction | In-Progress | 3/2/2017 | DOES |  | DOES | 954161 | 0
11 | X455 | HARRY S. TRUMAN HS - X | DOE - Skilled Trades | GAS LINE REPAIR | Construction | In-Progress | 3/9/2018 | DOES |  | DOES | 32806 | 0
11 | X455 | HARRY S. TRUMAN HS - X | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 5/26/2023 | DOES | 7/24/2023 | DOES | 494510 | 392302
11 | X455 | HARRY S. TRUMAN HS - X | DOE - Skilled Trades | SWIMMING POOL | Construction | In-Progress | 9/25/2023 | DOES |  | DOES | 1847326 | 0
11 | X456 | HARRY S. TRUMAN HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD / FY22 RESO A ATHLETIC FIELD UPGRADE | Scope | Complete | 5/12/2022 | 8/12/2022 | 7/29/2022 | 0 | 128540 | 109474
11 | X498 | P.S. / I.S. 498 - BRONX | Fast Track Projects | FY17 RESO A ROOFTOP PLAYGROUND | Construction | PNS | FTK | FTK | FTK | FTK | 22293 | 11048
11 | X498 | P.S. / I.S. 498 - BRONX | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/19/2019 | FTK |  | FTK | 80494 | 73288
11 | X498 | P.S. / I.S. 498 - BRONX | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
11 | X498 | P.S. / I.S. 498 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 100000 | 0
11 | X498 | P.S. / I.S. 498 - BRONX | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
11 | X498 | P.S. / I.S. 498 - BRONX | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
11 | X498 | P.S. / I.S. 498 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/30/2024 | DOES | 6/19/2024 | DOES | 50832
11 | X701 | X723 SPED - BRONX | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 6/1/2024 | IEH | 12350 | 6786
11 | X701 | X723 SPED - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
11 | X722 | X721 SPED - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
11 | X722 | X721 SPED - BRONX | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 67000 | 0
11 | X722 | X721 SPED - BRONX | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
11 | X722 | X721 SPED - BRONX | DOE - Skilled Trades | CHILLER REPLACEMENT | Construction | In-Progress | 12/1/2021 | DOES |  | DOES | 1237315 | 0
11 | X778 | BRONX HS FOR THE VISUAL ARTS - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
11 | X839 | BRONX HS FOR THE VISUAL ARTS - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
11 | XACO | BRONX CHARTER SCHOOL FOR EXCELLENCE 2 | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
11 | XAEF | BRONX CHARTER SCHOOL FOR EXCELLENCE 3 | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
11 | XAJK | BRONX CHARTER FOR EXCELLENCE - X | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
11 | XATE | SUSAN E. WAGNER DAY SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
12 | X006 | P.S. 6 - BRONX | SCA IEH | PO18-REPAIR OF ACM/ LEAD DAMAGED PLASTER IN ROOM 308 | Construction | Complete | 9/6/2024 | IEH | 9/8/2024 | IEH | 35384 | 2192
12 | X006 | P.S. 6 - BRONX | SCA IEH | PO18-REPAIR, ENCAPSULATE AND PAINT ALL DAMAGED ACM PLASTER AREAS IN ROOM# 213 UPPER WALL #3 UPPER WA | Construction | Complete | 9/17/2024 | IEH | 9/21/2024 | IEH | 978 | 978
12 | X006 | P.S. 6 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 172234 | 0
12 | X006 | P.S. 6 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/10/2023 | DIIR | 1/14/2024 | DIIR | 150000 | 9035
12 | X006 | P.S. 6 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
12 | X006 | P.S. 6 - BRONX | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/5/2022 | DOES |  | DOES | 81867 | 0
12 | X006 | P.S. 6 - BRONX | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/8/2021 | DOES |  | DOES | 192500 | 0
12 | X006 | P.S. 6 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/27/2024 | DOES | 4/5/2024 | DOES | 65832 | 6609
12 | X047 | P.S. 47 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/19/2024 | DOES |  | DOES | 65832 | 0
12 | X050 | P.S. 50 - BRONX | SCA CIP RESOA | FY11 RESO A PLAYGROUND REDEVELOPMEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/16/2024 | DIIR | 9/19/2024 | DIIR | 200000
12 | X050 | X186 SPED - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 237573 | 0
12 | X057 | P.S. 57 - BRONX | SCA IEH | PO18-ABATE AND REPAIR BROWN AIRCELL PIPE/ JOINT INSULATION IN BASEMENT STORAGE ROOM(B4) | Construction | Complete | 3/8/2024 | IEH | 4/14/2024 | IEH | 24310 | 2024
12 | X057 | P.S. 57 - BRONX | Fast Track Projects | LSP FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 1/12/2022 | FTK |  | FTK | 137188 | 65819
12 | X057 | I.S. 273 - BRONX | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50400 | 0
12 | X057 | P.S. 57 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/18/2021 | DOES |  | DOES | 183532 | 0
12 | X057 | I.S. 273 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/13/2024 | DOES |  | DOES | 384859 | 0
12 | X057 | P.S. 57 - BRONX | Trust For Public Land | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | TPL | 1370000 | 0
12 | X061 | P.S. 61 - BRONX | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/17/2024 | DOEL |  | DOEL | 138594 | 0
12 | X061 | P.S. 61 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 8/11/2022 | DOES |  | DOES | 165073 | 0
12 | X066 | P.S. 66 - BRONX | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 3/24/2022 | 12/8/2022 | 11/1/2022 | 0 | 16050 | 16050
12 | X066 | P.S. 66 - BRONX | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | Complete | 11/3/2020 | FTK | 6/6/2024 | FTK | 526289 | 525289
12 | X066 | P.S. 66 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 176406 | 0
12 | X066 | P.S. 66 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 130000 | 0
12 | X066 | P.S. 66 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/3/2024 | DOES |  | DOES | 157171 | 0
12 | X066 | P.S. 66 - BRONX | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 3/20/2023 | DOES |  | DOES | 55318 | 0
12 | X067 | P.S. 67 - BRONX | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/6/2018 | EMER |  | EMER | 41270 | 41270
12 | X067 | P.S. 67 - BRONX | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 627221 | 0
12 | X077 | P.S. 195 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
12 | X077 | P.S. 196 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
12 | X077 | P.S. 195 - BRONX | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
12 | X077 | P.S. 196 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/3/2024 | DOES | 4/10/2024 | DOES | 65832 | 15285
12 | X084 | X811 SPED - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/15/2023 | DOER |  | DOER | 357091 | 0
12 | X084 | X811 SPED - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/8/2022 | DOES |  | DOES | 218551 | 0
12 | X092 | P.S. 595 - BRONX | SCA Emergency Response | EMERGENCY- SWB @ X092 | Construction | In-Progress | 3/18/2024 | EMER |  | EMER | 51652 | 31646
12 | X092 | X352 SPED - BRONX | SCA IEH | PO18-REMOVE 10' OF ACM MARKED RED FOR ID IN CRAWLSPACE UNDER EXIT-10. CRAWL SPACE UNDER AUDITORIUM I | Construction | In-Progress | 9/18/2024 | IEH |  | IEH | 181 | 181
12 | X092 | P.S. 595 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
12 | X092 | P.S. 595 - BRONX | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
12 | X098 | I.S. 98 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 133140 | 0
12 | X098 | EXPLORATIONS ACADEMY - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
12 | X098 | I.S. 98 - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 2/17/2023 | DOES |  | DOES | 452606 | 0
12 | X099 | METROPOLITAN HS - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
12 | X099 | METROPOLITAN HS - BRONX | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0
12 | X099 | METROPOLITAN HS - BRONX | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 5/31/2023 | DOES |  | DOES | 175885 | 0
12 | X099 | METROPOLITAN HS - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/25/2024 | DOES | 5/2/2024 | DOES | 65832
12 | X102 | P.S. 536 - BRONX | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 54150 | 0
12 | X102 | P.S. 536 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/28/2023 | DIIR |  | DIIR | 100000 | 0
12 | X102 | P.S. 536 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
12 | X102 | ARCHER ELEMENTARY SCHOOL - BRONX | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
12 | X102 | ARCHER ELEMENTARY SCHOOL - BRONX | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 544254 | 0
12 | X102 | ARCHER ELEMENTARY SCHOOL - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/30/2022 | DOES |  | DOES | 310500 | 0
12 | X116 | I.S. 217 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/1/2023 | DIIR |  | DIIR | 150000 | 0
12 | X116 | I.S. 217 - BRONX | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
12 | X116 | I.S. 217 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/30/2022 | DOES |  | DOES | 209387 | 0
12 | X116 | I.S. 217 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/14/2023 | DOES |  | DOES | 576486 | 0
12 | X129 | I.S. 129 - BRONX | SCA IEH | PO18-ABATE ACM PIPE INSULATION 1ST FLOOR GIRLS BATHROOM CRAWLSPACE APPROX: 4 FT. | Construction | Complete | 7/31/2024 | IEH | 8/10/2024 | IEH | 10984 | 713
12 | X129 | I.S. 316 - BRONX | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 9/28/2024 | FTK |  | FTK | 85055 | 0
12 | X129 | I.S. 316 - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 5/28/2024 | DIIR | 200000 | 200000
12 | X134 | P.S. 134 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/19/2024 | DOES |  | DOES | 65832 | 0
12 | X136 | X186 SPED - BRONX | SCA Emergency Response | SIDEWALK BRIDGING | Construction | In-Progress | 1/13/2012 | EMER |  | EMER |  | 0
12 | X136 | X186 SPED - BRONX | SCA IEH | PO18-REPLACE 9X9 TILES ON THE FOLLOWING ROOMS: ROOM 101 - TRIPPING HAZZARD 752 SQ. FT + CLOSET 54 SQ | Construction | In-Progress | 9/25/2024 | IEH |  | IEH | 0 | 0
12 | X136 | X186 SPED - BRONX | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 4/9/2021 | 8/10/2021 | 12/7/2021 | 0 | 16639 | 16639
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/25/2022 | 7/25/2022 | 7/20/2022 | 0 | 39117 | 26626
12 | X150 | P.S. 150 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
12 | X150 | P.S. 150 - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
12 | X150 | P.S. 150 - BRONX | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 86992 | 0
12 | X158 | I.S. 267 - BRONX | Fast Track Projects | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 38085 | 8425
12 | X158 | BRONX CAREER AND COLLEGE PREPARATORY HIGH SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0
12 | X158 | DR. IZQUIERDO HEALTH CHARTER SCHL - X | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 60000 | 0
12 | X158 | I.S. 267 - BRONX | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 115000 | 0
12 | X158 | BRONX CAREER AND COLLEGE PREPARATORY HIGH SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/12/2024 | DIIR | 6/21/2024 | DIIR | 170000
12 | X158 | I.S. 267 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
12 | X158 | I.S. 267 - BRONX | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 2/3/2023 | DOER |  | DOER | 159458 | 0
12 | X158 | I.S. 267 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/12/2023 | DOES |  | DOES | 403118 | 0
12 | X158 | I.S. 267 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832
12 | X158 | I.S. 267 - BRONX | Trust For Public Land | FY20 RESO A PLAYGROUND UPGRADE | Construction | Complete | 9/1/2023 | TPL | 6/14/2024 | TPL | 2855014 | 2156631
12 | X167 | I.S. 383 - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/18/2024 | DIIR | 4/10/2024 | DIIR | 150000 | 150000
12 | X167 | P.S. 214 - BRONX | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 11/21/2022 | DOES |  | DOES | 498168 | 0
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 2/17/2023 | DOER |  | DOER | 90326 | 0
12 | X193 | P.S. 211 - BRONX | SCA Furniture & Equipment | FY23 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
12 | X193 | P.S. 211 - BRONX | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 245402 | 0
12 | X193 | P.S. 211 - BRONX | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 530323 | 0
12 | X193 | P.S. 211 - BRONX | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/26/2023 | DOES |  | DOES | 509222 | 0
12 | X193 | I.S. 318 - BRONX | DOE - Skilled Trades | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 11/13/2023 | DOES |  | DOES | 271565 | 0
12 | X193 | P.S. 211 - BRONX | DOE - Skilled Trades | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 11/13/2023 | DOES |  | DOES | 282423 | 0
12 | X198 | P.S. 212 - BRONX | Fast Track Projects | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK |  | 0
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/30/2023 | DIIR |  | DIIR | 100000 | 0
12 | X198 | X188 SPED - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | DOE - Skilled Trades | CHARTER MATCH BATHROOM UPGRADE | Construction | In-Progress | 11/17/2023 | DOES |  | DOES | 288883 | 0
12 | X234 | P.S. 300 - BRONX | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 9/29/2022 | DOES |  | DOES | 155531 | 0
12 | X358 | ALC- PS 6 | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/5/2024 | DOES |  | DOES | 50832 | 0
12 | X401 | BRONX REGIONAL HS - X | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/22/2024 | DOES |  | DOES | 646666 | 0
12 | X420 | THE URBAN ASSEMBLY CHARTER SCHOOL FOR COMPUTER SCIENCE - BRONX | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
12 | X420 | PAN AMERICAN INTER HS- X | DIIT - RESOA | FY24 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
12 | X420 | WORLD CULTURES HS - X | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
12 | X420 | MONROE ACAD FOR VISUAL ARTS - X | DOE - RESOA | FY10 RESO A- HEALTH CLINIC | Construction | PNS | PNS | PNS | PNS | DOER | 83206 | 0
12 | X420 | THE METROPOLITAN SOUNDVIEW HIGH SCHOOL - BRONX | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 239699 | 0
12 | X420 | WORLD CULTURES HS - X | DOE - Skilled Trades | CHARTER MATCH LIGHTING UPGRADE | Construction | In-Progress | 3/2/2020 | DOES |  | DOES | 971334 | 0
12 | X421 | WORLD CULTURES HS - X | DOE - Skilled Trades | ATHLETIC FIELD | Construction | In-Progress | 11/16/2023 | DOES |  | DOES | 2500000 | 1975233
12 | X423 | I.S. 242 - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 305000 | 0
12 | X423 | X721 SPED - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
12 | X423 | THE CINEMA SCHOOL - BRONX | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
12 | X423 | I.S. 242 - BRONX | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/26/2024 | DOES | 5/8/2024 | DOES | 50832
12 | X493 | DISTRICT 12 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/20/2024 | DOES |  | DOES | 65832 | 0
12 | X878 | FANNIE LOU HAMER FREEDOM HS - X | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/3/2024 | IEH | 6/4/2024 | IEH | 11012 | 6112
12 | X879 | WINGS ACADEMY - X | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/15/2024 | IEH | 7/30/2024 | IEH | 15419 | 284
12 | X973 | EAST BRONX ACADEMY FOR THE FUTURE -X | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/19/2024 | IEH | 5/8/2024 | IEH | 12672 | 7297
12 | XA21 | X000 - BRONX | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 70000 | 0
13 | K003 | P.S. 3 - BROOKLYN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | Complete | 5/5/2021 | DOER | 1/26/2023 | DOER | 113562
13 | K008 | P.S. 8 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/14/2023 | 5/15/2023 | 6/2/2023 | 0 | 19756 | 19756
13 | K008 | P.S. 8 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
13 | K008 | P.S. 8 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/4/2024 | DOES | 5/31/2024 | DOES | 65832 | 6896
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA IEH | PO18-ABATE WASTE LINE FOR ACM LOCATION: WASTE LINE ABOVE CEILING TILE IN KITCHEN PREP AREA | Construction | Complete | 9/20/2024 | IEH | 9/22/2024 | IEH | 181 | 181
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOOR TILES LOC: ROOM 108: SPECIAL INSTRUCTION ROOM FOR 3RD GRADE 2 B | Construction | In-Progress | 9/25/2024 | IEH |  | IEH | 0 | 0
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/29/2024 | DIIR | 5/1/2024 | DIIR | 350000 | 350000
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 30109 | 0
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | Complete | 2/10/2023 | DOES | 9/29/2023 | DOES | 328027 | 18238
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/26/2024 | DOES |  | DOES | 65832 | 0
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/2/2022 | DOER |  | DOER | 43690 | 0
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 7/12/2021 | DOER |  | DOER | 1156793 | 0
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 4/3/2024 | DOER |  | DOER | 756212 | 0
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
13 | K011 | P.S. 11 - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
13 | K011 | P.S. 11 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/9/2021 | DOES |  | DOES | 223492 | 0
13 | K011 | P.S. 11 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/9/2024 | DOES | 5/16/2024 | DOES | 65832 | 12415
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GREEN ROOF | Scope | Complete | 9/7/2023 | 1/26/2024 | 2/15/2024 | 0 | 76501 | 76501
13 | K020 | P.S. 20 - BROOKLYN | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | Complete | 11/12/2019 | DOER | 3/13/2020 | DOER | 68562 | 68562
13 | K020 | P.S. 20 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/26/2022 | DOER |  | DOER | 312817 | 0
13 | K044 | P.S. 44 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROX. 7 LINEAR FEET OF STEAM PIPE INSULATION FROM RISER AND HORIZONTAL RUN IN R | Construction | Complete | 4/4/2024 | IEH | 5/18/2024 | IEH | 10737 | 7162
13 | K044 | P.S. 44 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/16/2024 | DOES | 4/18/2024 | DOES | 65832 | 13161
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGED ACM 9X9 TILE FLOOR LOCATION: ROOM 324 ESTIMATED 650SQ FT FLOORING IS | Construction | In-Progress | 9/23/2024 | IEH |  | IEH | 0 | 0
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA IEH | PO18-PERFORM QC SUPPLEMENTAL SAMPLING ON CEILING. AS PER SCHOOL, CEILING TILES ARE FALLING THROUGHOU | Construction | In-Progress | 9/27/2024 | IEH |  | IEH | 0 | 0
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 328978 | 0
13 | K046 | P.S. 46 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/23/2022 | DOES |  | DOES | 82229 | 0
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/6/2024 | DOES | 5/13/2024 | DOES | 65832
13 | K056 | I.S. 351 - BROOKLYN | SCA CIP RESOA | FY18 RESO A COURTYARD GREENHOUSE | Scope | Complete | 1/16/2018 | 5/1/2018 | 10/24/2018 | 0 | 112561 | 59118
13 | K056 | P.S. 56 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 80000
13 | K056 | P.S. 56 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/6/2024 | DOES | 5/13/2024 | DOES | 65832
13 | K067 | P.S. 67 - BROOKLYN | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500255 | 0
13 | K067 | COY L. COX SCHOOL | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 446453 | 0
13 | K085 | K753 SPED - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 11/10/2023 | DOER |  | DOER | 146885 | 0
13 | K085 | K753 SPED - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/29/2023 | DOES |  | DOES | 18752 | 0
13 | K093 | P.S. 93 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROX. 12 FT OF STEAM PIPE INSULATION FROM A 2' LINE RUNNING FROM GIRLS BATHROOM | Construction | In-Progress | 7/2/2024 | IEH |  | IEH | 648 | 73
13 | K093 | P.S. 93 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 145217 | 0
13 | K093 | P.S. 93 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/23/2024 | DOES | 4/26/2024 | DOES | 65832 | 189
13 | K113 | I.S. 113 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 573030 | 0
13 | K113 | I.S. 113 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 2/28/2024 | DOES |  | DOES | 548587 | 11655
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 5/5/2023 | DOER |  | DOER | 48558 | 0
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/21/2023 | DOES |  | DOES | 512395 | 0
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 6/4/2024 | DOES |  | DOES | 742232 | 0
13 | K256 | P.S. 256 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 1/13/2023 | DOER |  | DOER | 217022 | 0
13 | K256 | P.S. 256 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/30/2023 | DOER |  | DOER | 224144 | 0
13 | K256 | P.S. 256 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/10/2024 | DOES | 4/17/2024 | DOES | 65832 | 378
13 | K258 | K140 SPED - BROOKLYN | SCA IEH | PO18-PLEASE TEST AND ABATE ACM IF NEEDED IN THE FOLLOWING AREAS. APPROXIMATELY 4 SQUARE FEET OF CEI | Construction | Complete | 8/12/2024 | IEH | 8/19/2024 | IEH | 4112 | 362
13 | K258 | K140 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR ACM ON PIPES | Construction | Complete | 8/29/2024 | IEH | 8/30/2024 | IEH | 16346 | 254
13 | K258 | ALC - MS 258 | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 55000 | 0
13 | K265 | I.S. 265 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 250000 | 0
13 | K265 | I.S. 265 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/25/2024 | DOES |  | DOES | 539480 | 0
13 | K270 | COMMUNITY PARTNERSHIP CHARTER SCHL - K | SCA CIP RESOA | FY11 RESO A- WIRING UPGRADE AND A/C | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
13 | K270 | P.S. 270 - BROOKLYN | SCA IEH | PO18-ROOM 215 ABATE AND REPLACE FLOORING. TILES ARE MISSING AND BROKEN | Construction | Complete | 6/25/2024 | IEH | 7/7/2024 | IEH | 27612 | 20362
13 | K270 | COMMUNITY PARTNERSHIP CHARTER SCHL - K | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 100000 | 0
13 | K270 | P.S. 270 - BROOKLYN | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0
13 | K270 | P.S. 270 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/3/2024 | DOER |  | DOER | 510033 | 0
13 | K270 | P.S. 270 - BROOKLYN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | In-Progress | 12/28/2023 | DOER |  | DOER | 150000 | 0
13 | K270 | P.S. 270 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 105000 | 0
13 | K270 | P.S. 270 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75150 | 0
13 | K270 | P.S. 270 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/17/2024 | DOES |  | DOES | 65832 | 0
13 | K282 | P.S. 282 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
13 | K282 | P.S. 282 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
13 | K282 | P.S. 282 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/29/2024 | DOES | 4/5/2024 | DOES | 65832 | 378
13 | K287 | P.S. 287 - BROOKLYN | SCA IEH | PO18-ROOM B10, ABATE PIPE INSULATION MARKED IN RED HALLWAY OUTSIDE B15, ABATE PIPE INSULATION MARKED | Construction | In-Progress | 9/26/2024 | IEH |  | IEH | 0 | 0
13 | K287 | P.S. 287 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 226357 | 0
13 | K287 | P.S. 287 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 297584 | 0
13 | K287 | P.S. 287 - BROOKLYN | DOE - RESOA | RESO A- RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
13 | K287 | P.S. 287 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
13 | K287 | P.S. 287 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/28/2024 | DOES | 4/10/2024 | DOES | 65832 | 7525
13 | K305 | I.S. 492- BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING 12'X12' ACCOUSTIC CEILING TILE FELL, 6'X6' BUBBLE ON CEILING LOC: 1ST | Construction | Complete | 7/18/2024 | IEH | 7/20/2024 | IEH | 10780 | 586
13 | K305 | I.S. 492- BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 346954 | 0
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/5/2023 | 3/7/2024 | 6/27/2024 | 0 | 27737 | 13118
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 5/15/2024 | 8/16/2024 | 7/30/2024 | 0 | 335 | 335
13 | K307 | P.S. 307 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/16/2019 | EMER |  | EMER | 269424 | 207586
13 | K307 | P.S. 307 - BROOKLYN | Fast Track Projects | RENOVATION OF CLASSROOM 332 | Construction | In-Progress | 11/20/2013 | FTK |  | FTK | 329772 | 329772
13 | K313 | I.S. 527 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/17/2022 | DOER |  | DOER | 231846 | 0
13 | K313 | I.S. 527 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/8/2024 | DOES |  | DOES | 65832 | 0
13 | K317 | P.S. 133 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
13 | K317 | P.S. 133 - BROOKLYN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 6/6/2024 | DOER |  | DOER | 55294 | 0
13 | K317 | P.S. 133 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY13 RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/19/2013 | 10/21/2013 | 11/8/2013 | 0 | 79122 | 79122
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 1/19/2018 | 5/4/2018 | 11/2/2018 | 0 | 51878 | 51878
13 | K430 | BROOKLYN TECH HS - K | SCA Emergency Response | SIDEWALK BRIDGING | Construction | In-Progress | 5/22/2013 | EMER |  | EMER | 1509825 | 1509825
13 | K430 | BROOKLYN TECH HS - K | SCA IEH | PO18-ABATE AND REPLACE 9X9N TILES THAT ARE CRACKED AND DAMAGED. ACM ACCORDING TO THE AHERA BOOK . T | Construction | Complete | 7/30/2024 | IEH | 8/16/2024 | IEH | 997 | 422
13 | K430 | BROOKLYN TECH HS - K | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES LOCATION: ROOM 4E12 TILES ARE CRACKING AND COMING UP APPROX 20SQF | Construction | Complete | 8/5/2024 | IEH | 8/23/2024 | IEH | 575 | 0
13 | K430 | BROOKLYN TECH HS - K | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 5/6/2024 | DIIR | 35000 | 35000
13 | K430 | BROOKLYN TECH HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/2/2024 | DOES |  | DOES | 65832 | 0
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | Fast Track Projects | EMERGENCY INVESTIGATION | Construction | In-Progress | 7/30/2014 | FTK |  | FTK | 271001 | 166733
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | DOE - Skilled Trades | GAS VENT LINE REROUTING | Construction | In-Progress | 11/6/2019 | DOES |  | DOES | 26795 | 10500
13 | K580 | M.S. 915 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/10/2024 | DIIR | 6/13/2024 | DIIR | 114000 | 114000
13 | K580 | M.S. 915 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | Complete | 4/26/2024 | DOER | 7/30/2024 | DOER | 300000
13 | K580 | GEORGE WESTINGHOUSE VOC. HS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/6/2023 | DOES |  | DOES | 573422 | 0
13 | K611 | THE DOCK STREET SCHOOL FOR STEAM STUDIES - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 327971 | 0
13 | K611 | THE DOCK STREET SCHOOL FOR STEAM STUDIES - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/9/2024 | DOES |  | DOES | 50832 | 0
13 | K777 | BROOKLYN NAVY YARD STEM CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 8/14/2024 | IEH |  | IEH | 15195 | 60
13 | K777 | BROOKLYN NAVY YARD STEM CENTER | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0
13 | K777 | BROOKLYN NAVY YARD STEM CENTER | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0
13 | K805 | BROOKLYN INTERNATIONAL HS - K | Fast Track Projects | LSP VACUUM PUMP SET REPLACEMENT | Construction | In-Progress | 4/20/2021 | FTK |  | FTK | 104458 | 88856
13 | K805 | SCIENCE SKILLS CENTER HS - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
13 | K805 | SCIENCE SKILLS CENTER HS - K | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 144109 | 0
13 | K805 | BROOKLYN INTERNATIONAL HS - K | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
13 | K805 | BROOKLYN INTERNATIONAL HS - K | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 5/3/2021 | DOES |  | DOES | 316427 | 0
13 | K831 | DIV. COMPUTER INFO-DATA CNTR - K | DIIT - Project Connect | NEXT GENERATION NETWORK UPGRADE | Purch & Install | Complete | 3/1/2019 | DIIT | 6/23/2023 | DIIT | 342089
13 | K853 | K000 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/29/2024 | IEH | 8/7/2024 | IEH | 12175 | 0
13 | K874 | I.S. 340 - BROOKLYN | Fast Track Projects | LEAD SERVICE LINE | Construction | In-Progress | 10/17/2016 | FTK |  | FTK | 108067 | 108067
13 | K874 | I.S. 340 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/30/2022 | DOES |  | DOES | 332097 | 0
13 | K902 | K077 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
13 | K902 | K077 SPED - BROOKLYN | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 168527 | 0
13 | K902 | K077 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
13 | K914 | BENJAMIN BANNEKER ACAD. (HS LVL)-K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/19/2024 | DOES |  | DOES | 769842 | 0
13 | K914 | BENJAMIN BANNEKER ACAD. (HS LVL)-K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/10/2024 | DOES |  | DOES | 65832 | 0
13 | K994 | BEDFORD ACADEMY HS - K | DOE - RESOA | FY21 RESO A MEDIA CENTER UPGRADE | Construction | In-Progress | 10/11/2023 | DOER |  | DOER | 74399 | 0
13 | K994 | BEDFORD ACADEMY HS - K | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 7/18/2024 | DOER |  | DOER | 37945 | 0
13 | K994 | BEDFORD ACADEMY HS - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 5/10/2024 | DOES | 65832 | 7509
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K016 | P.S. 16 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 93000 | 0
14 | K016 | P.S. 16 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0
14 | K016 | P.S. 16 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 93000 | 0
14 | K016 | P.S. 16 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/5/2024 | DOES | 4/17/2024 | DOES | 65832 | 17799
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K017 | I.S. 577 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE BUCKLING WOOD FLOORS IN THE FOLLOWING ROOMS ROOMS 407, 413 | Construction | Complete | 1/29/2024 | IEH | 4/16/2024 | IEH | 203029 | 5811
14 | K017 | P.S. 17 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
14 | K017 | P.S. 17 - BROOKLYN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
14 | K017 | P.S. 17 - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0
14 | K017 | I.S. 577 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
14 | K017 | P.S. 17 - BROOKLYN | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
14 | K017 | P.S. 17 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 1/7/2022 | DOES |  | DOES | 60651 | 0
14 | K017 | I.S. 577 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/24/2024 | DOES |  | DOES | 65832 | 0
14 | K018 | P.S. 18 - BROOKLYN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 4/9/2024 | DOER |  | DOER | 50000 | 0
14 | K018 | P.S. 18 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
14 | K018 | P.S. 18 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/22/2022 | DOES |  | DOES | 98632 | 0
14 | K019 | P.S. 414 - BROOKLYN | DIIT - RESOA | FY 07 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 64512 | 0
14 | K019 | P.S. 414 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 521172 | 0
14 | K023 | P.S. 23 - BROOKLYN | SCA Emergency Response | EMERGENCY: EXTERIOR | Construction | In-Progress | 6/17/2022 | EMER |  | EMER | 353822 | 299914
14 | K023 | P.S. 23 - BROOKLYN | DOE - RESOA | FY19 RESO A CAFETERIA SUPPLEMENTAL COOLING | Construction | In-Progress | 6/23/2021 | DOER |  | DOER | 251447 | 0
14 | K023 | P.S. 23 - BROOKLYN | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 8/26/2023 | DOER |  | DOER | 137464 | 0
14 | K023 | P.S. 23 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/1/2023 | DOER |  | DOER | 767000 | 378487
14 | K023 | P.S. 23 - BROOKLYN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 4/9/2024 | DOER | 7/16/2024 | DOER | 92000
14 | K031 | P.S. 31 - BROOKLYN | SCA IEH | PO18-ABATE CRUMBLING CEILING IN WOMENS BATHROOM CEILING IS POSITIVE ACM IN AHERA BOOK BATHROOM HAS B | Construction | Complete | 5/7/2024 | IEH | 6/12/2024 | IEH | 16114 | 580
14 | K031 | P.S. 31 - BROOKLYN | SCA IEH | PO18-ABATE AND DRILL 1ST. FL. CORRIDOR WALLS FOR ACM LOCATION: OUTSIDE OF RM. 102 BY BOTTLE FILLER A | Construction | Complete | 8/28/2024 | IEH | 9/22/2024 | IEH | 9754 | 544
14 | K031 | P.S. 31 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0
14 | K031 | P.S. 31 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
14 | K031 | P.S. 31 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
14 | K031 | P.S. 31 - BROOKLYN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 78000 | 0
14 | K031 | P.S. 31 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
14 | K031 | P.S. 31 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/19/2024 | DOES | 5/28/2024 | DOES | 65832 | 7367
14 | K033 | K368 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Scope | Complete | 6/10/2022 | 10/12/2022 | 10/12/2022 | 0 | 18212 | 18212
14 | K033 | K368 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS RM: B12 APPROX. 572SF RM: B46/ CLOSET APPROX. 400SF | Construction | Complete | 3/6/2024 | IEH | 8/7/2024 | IEH | 1183 | 433
14 | K033 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 5/6/2022 | DOER |  | DOER | 179138 | 0
14 | K034 | P.S. 34 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | Complete | 7/5/2023 | DOER | 9/17/2023 | DOER | 306805 | 182598
14 | K034 | P.S. 34 - BROOKLYN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/1/2024 | DOER |  | DOER | 497676 | 0
14 | K034 | P.S. 34 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 209000 | 0
14 | K034 | P.S. 34 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/17/2024 | DOES |  | DOES | 65832 | 0
14 | K049 | THE WILLIAMSBURG HIGH SCHOOL OF ART AND TECHNOLOGY - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 74000 | 0
14 | K049 | BROOKLYN LATIN HS - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 375000 | 0
14 | K049 | THE WILLIAMSBURG HIGH SCHOOL OF ART AND TECHNOLOGY - K | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 9/29/2022 | DOER |  | DOER | 45878 | 0
14 | K049 | LYONS COMMUNITY SCHOOL - K | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 6/13/2022 | DOER |  | DOER | 323344 | 0
14 | K049 | THE WILLIAMSBURG HIGH SCHOOL OF ART AND TECHNOLOGY - K | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
14 | K049 | BROOKLYN LATIN HS - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1375000 | 0
14 | K049 | LYONS COMMUNITY SCHOOL - K | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
14 | K049 | LYONS COMMUNITY SCHOOL - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 3/9/2023 | DOES |  | DOES | 446581 | 0
14 | K050 | J.H.S. 50 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/14/2020 | EMER |  | EMER | 36190 | 36190
14 | K050 | J.H.S. 50 - BROOKLYN | SCA IEH | PO18-ROOM 101 BY ROGHT SIDE CONVECTOR. PLEASE REMOVE ALL PIPE INSULATION FROM STEAM PIPE DOWN THROUG | Construction | Complete | 3/28/2024 | IEH | 8/10/2024 | IEH | 17545 | 1488
14 | K050 | J.H.S. 50 - BROOKLYN | SCA IEH | PO18-ABATE WALL LAYERS FOR ACM LOCATION: ROOMS 518 AND 522 WATER PENETRATION, WALLS ARE WET / PLASTE | Construction | Complete | 4/8/2024 | IEH | 4/14/2024 | IEH | 68137 | 68137
14 | K050 | J.H.S. 50 - BROOKLYN | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 7/26/2024 | FTK |  | FTK | 535312 | 169516
14 | K050 | J.H.S. 50 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY | Purch & Install | Complete | 4/10/2024 | DIIR | 5/22/2024 | DIIR | 300000 | 300000
14 | K050 | J.H.S. 50 - BROOKLYN | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 10/11/2021 | DOER |  | DOER | 206934 | 0
14 | K050 | J.H.S. 50 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
14 | K059 | P.S. 59 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0
14 | K059 | P.S. 59 - BROOKLYN | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 8/31/2020 | DOES |  | DOES | 4677 | 0
14 | K059 | P.S. 59 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/7/2024 | DOES | 5/17/2024 | DOES | 65832 | 9620
14 | K071 | I.S. 71 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING OUTSIDE OF GYM AND GYM OFFICE CEILING PLASTER SPALLING DUE TO WATER PE | Construction | Complete | 7/9/2024 | IEH | 9/17/2024 | IEH | 1550 | 0
14 | K071 | I.S. 71 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/16/2023 | DOES |  | DOES | 624351 | 0
14 | K084 | P.S. 84 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/12/2019 | EMER |  | EMER | 100440 | 93562
14 | K084 | P.S. 84 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 7/26/2023 | DOER |  | DOER | 198196 | 0
14 | K084 | P.S. 84 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
14 | K084 | P.S. 84 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
14 | K110 | P.S. 110 - BROOKLYN | SCA Emergency Response | STABILIZATION- SWB @ K110 | Construction | In-Progress | 4/19/2023 | EMER |  | EMER | 269122 | 128875
14 | K110 | P.S. 110 - BROOKLYN | SCA IEH | PO18-TEST WALLS IN THE FOLLOWING ROOMS FOR ACM ROOM 307 | Construction | Complete | 3/28/2024 | IEH | 6/18/2024 | IEH | 0 | 0
14 | K110 | P.S. 110 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 226000 | 0
14 | K110 | P.S. 110 - BROOKLYN | DOE - RESOA | ELECTRICAL UPGRADE | Construction | In-Progress | 1/30/2020 | DOER |  | DOER | 35504 | 0
14 | K110 | P.S. 110 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/26/2024 | DOES |  | DOES | 65832 | 0
14 | K120 | P.S. 120 - BROOKLYN | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | Complete | 12/4/2021 | DOER | 3/25/2022 | DOER | 190617 | 191618
14 | K120 | P.S. 120 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
14 | K120 | P.S. 120 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 6/1/2018 | DOES |  | DOES | 185158 | 0
14 | K120 | P.S. 120 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/23/2024 | DOES | 4/26/2024 | DOES | 65832 | 10863
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K126 | J.H.S. 126 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0
14 | K126 | J.H.S. 126 - BROOKLYN | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 2/21/2023 | DOES |  | DOES | 304208 | 0
14 | K126 | J.H.S. 126 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/26/2024 | DOES |  | DOES | 65832 | 0
14 | K132 | P.S. 132 - BROOKLYN | SCA Emergency Response | EMERGENCY- SWB @ K132 | Construction | In-Progress | 3/18/2024 | EMER |  | EMER |  | 0
14 | K132 | P.S. 132 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 153000 | 0
14 | K132 | P.S. 132 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/15/2021 | DOES |  | DOES | 61741 | 0
14 | K132 | P.S. 132 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/3/2023 | DOES | 8/25/2023 | DOES | 160385 | 7234
14 | K132 | P.S. 132 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 65832 | 0
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
14 | K147 | P.S. 147 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES LOCATED IN ROOM 412 CE BRIAN SCHETTINO 718-571-6621 | Construction | In-Progress | 9/17/2024 | IEH |  | IEH | 0 | 0
14 | K147 | P.S. 147 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
14 | K147 | YOUNG WOMEN'S LEADERSHIP SCHOOL - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
14 | K147 | P.S. 147 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
14 | K147 | P.S. 147 - BROOKLYN | DOE - RESOA | FY16 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/19/2017 | DOER |  | DOER | 677657 | 0
14 | K147 | P.S. 147 - BROOKLYN | DOE - RESOA | FY19 RESO A PLAYGROUND | Construction | Complete | 4/3/2020 | DOER | 10/19/2022 | DOER | 936532 | 38373
14 | K147 | P.S. 147 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/14/2023 | DOER |  | DOER | 230667 | 0
14 | K147 | YOUNG WOMEN'S LEADERSHIP SCHOOL - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/2/2024 | DOER |  | DOER | 150000 | 0
14 | K148 | K373 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR DAMAGED PLASTER | Construction | Complete | 8/28/2024 | IEH | 9/17/2024 | IEH | 0 | 0
14 | K148 | K373 SPED - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/9/2019 | DOER |  | DOER | 240201 | 0
14 | K157 | P.S. 157 - BROOKLYN | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON DAMAGED PIPE INSULATION IN ROOM 202 APPROXIMATELY 12 LF OF D | Construction | Complete | 8/16/2024 | IEH | 8/23/2024 | IEH | 14540 | 0
14 | K157 | P.S. 157 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/20/2023 | DOEL |  | DOEL | 104804 | 74804
14 | K196 | I.S. 582 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/8/2023 | 4/11/2024 | 6/6/2024 | 0 | 15442 | 15442
14 | K196 | I.S. 582 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
14 | K196 | P.S. 196 - BROOKLYN | DOE - RESOA | FY12 RESO A- LIGHTING UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
14 | K196 | I.S. 582 - BROOKLYN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/30/2021 | DOER |  | DOER | 353738 | 0
14 | K196 | P.S. 196 - BROOKLYN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 2/24/2022 | DOER |  | DOER | 158062 | 0
14 | K196 | P.S. 196 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 6752 | 0
14 | K196 | P.S. 196 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
14 | K196 | I.S. 582 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/15/2024 | DOES |  | DOES | 506053 | 0
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP RESOA | FY19 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Scope | Complete | 2/26/2019 | 6/2/2021 | 5/17/2021 | 0 | 33121 | 33121
14 | K250 | P.S. 250 - BROOKLYN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
14 | K250 | P.S. 250 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
14 | K257 | P.S. 257 - BROOKLYN | DOE - RESOA | FY15 RESO A SUPPLEMENTAL COOLING | Construction | Complete | 5/24/2017 | DOER | 12/18/2019 | DOER | 453730 | 430479
14 | K257 | P.S. 257 - BROOKLYN | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
14 | K257 | P.S. 257 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/13/2023 | 4/16/2024 | 5/7/2024 | 0 | 20061 | 3769
14 | K297 | P.S. 297 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/2/2019 | DOER |  | DOER | 151045 | 0
14 | K297 | P.S. 297 - BROOKLYN | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
14 | K318 | I.S. 318 - BROOKLYN | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/22/2023 | DOER |  | DOER | 360845 | 0
14 | K318 | I.S. 318 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/15/2016 | DOES |  | DOES | 152595 | 0
14 | K318 | I.S. 318 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/27/2023 | DOES |  | DOES | 642110 | 0
14 | K319 | P.S. 319 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
14 | K319 | P.S. 319 - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 152030 | 0
14 | K319 | P.S. 319 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
14 | K319 | P.S. 319 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/28/2024 | DOES |  | DOES | 65832 | 0
14 | K380 | P.S. 380 - BROOKLYN | SCA IEH | PO18-PERFORM QC SUPPLEMENTAL TESTING ON HALLWAY CEILING LOCATED OUTSIDE OF RM 120 ABATE AND REPAIR A | Construction | In-Progress | 9/23/2024 | IEH |  | IEH | 0 | 0
14 | K380 | P.S. 380 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
14 | K380 | P.S. 380 - BROOKLYN | DOE - RESOA | FY14 RESO A RENOVATE OUTDOOR DIGITAL SIGNAGE | Construction | In-Progress | 8/25/2014 | DOER |  | DOER | 30300 | 0
14 | K380 | P.S. 380 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/2/2019 | DOER |  | DOER | 353999 | 0
14 | K380 | P.S. 380 - BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/17/2024 | DOER |  | DOER | 2320 | 0
14 | K380 | K141 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 240000 | 0
14 | K380 | P.S. 380 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/10/2024 | DOES |  | DOES | 50832 | 0
14 | K450 | PROGRESS HS - K | SCA IEH | PO18-PLEASE DRILL 3/4'HOLE THROUGH FOURTH FLOOR NEXT TO ROOM# 415 | Construction | Complete | 8/27/2024 | IEH | 9/29/2024 | IEH | 11919 | 145
14 | K450 | HS OF ENTERPRISE, BUS. & TECH. - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 7/5/2024 | DIIR | 50000 | 50000
14 | K450 | EAST WILLIAMSBURG SCHOLARS ACADEMY - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/28/2024 | DIIR | 150000 | 150000
14 | K450 | PROGRESS HS - K | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 235000 | 0
14 | K450 | HS OF ENTERPRISE, BUS. & TECH. - K | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 90000 | 0
14 | K450 | PROGRESS HS - K | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
14 | K450 | PROGRESS HS - K | DOE - Skilled Trades | SUPPLEMENTAL COOLING | Construction | Complete | 9/22/2023 | DOES | 5/7/2024 | DOES | 1617376 | 865264
14 | K451 | PROGRESS HS - K | DOE - RESOA | FY18 RESO A ATHLETIC FIELDS | Construction | In-Progress | 2/14/2020 | DOER |  | DOER | 8980772 | 0
14 | K610 | A-TECH HIGH SCHOOL - K | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 5/2/2022 | DOER |  | DOER | 139575 | 0
14 | K610 | A-TECH HIGH SCHOOL - K | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 9/20/2023 | DOES |  | DOES | 245705 | 0
14 | K610 | A-TECH HIGH SCHOOL - K | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/1/2022 | DOES |  | DOES | 279434 | 0
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | SCA IEH | PO18-ABATE FOUR MUDDED FITTINGS ON OIL PIPING AT BOILER ROOM CEILING. PIPING IS MARKED WITH GREEN SP | Construction | Complete | 7/9/2024 | IEH | 9/29/2024 | IEH | 575 | 0
14 | K650 | WILLIAMSBURG HS FOR ARCH & DES-K | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/30/2023 | DOER |  | DOER | 516505 | 0
14 | K650 | WILLIAMSBURG HS FOR ARCH & DES-K | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 512708 | 0
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/13/2023 | DOES |  | DOES | 418781 | 0
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/10/2024 | DOES | 6/17/2024 | DOES | 65832
14 | K778 | EL PUENTE ACADEMY - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 4/19/2024 | IEH |  | IEH | 13537 | 1138
15 | K001 | P.S. 1 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
15 | K001 | P.S. 1 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500000 | 0
15 | K001 | P.S. 1 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/15/2024 | DOES | 4/22/2024 | DOES | 65832 | 378
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K010 | P.S. 10 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
15 | K010 | P.S. 10 - BROOKLYN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/7/2022 | DOER |  | DOER | 80055 | 0
15 | K010 | P.S. 10 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 7/6/2022 | DOER |  | DOER | 101320 | 0
15 | K015 | P.S. 15 - BROOKLYN | Fast Track Projects | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 157188 | 92387
15 | K015 | P.S. 15 - BROOKLYN | Fast Track Projects | GAS LEAK | Construction | In-Progress | 4/15/2019 | FTK |  | FTK | 37984 | 37984
15 | K015 | P.S. 15 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K015 | P.S. 15 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 4/19/2019 | DOER |  | DOER | 224393 | 0
15 | K015 | P.S. 15 - BROOKLYN | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 62427 | 0
15 | K015 | P.S. 15 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 65832 | 0
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 2/3/2023 | 5/4/2023 |  | 0 | 78363 | 78363
15 | K024 | P.S. 24 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 9/1/2021 | DIIR |  | DIIR | 150000 | 0
15 | K024 | P.S. 24 - BROOKLYN | DOE - RESOA | FY08 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 93750 | 0
15 | K024 | P.S. 24 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 6/30/2022 | DOER |  | DOER | 283492 | 0
15 | K024 | P.S. 24 - BROOKLYN | DOE - RESOA | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 275000 | 0
15 | K024 | P.S. 24 - BROOKLYN | DOE - RESOA | FY24 RESO A LEARNING GARDEN | Construction | PNS | PNS | PNS | PNS | DOER | 306047 | 0
15 | K024 | P.S. 24 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 681061 | 0
15 | K024 | P.S. 24 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/9/2024 | DOES |  | DOES | 50832 | 0
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 6/24/2024 | DIIR | 180000 | 180000
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 6/10/2022 | DOER |  | DOER | 260453 | 0
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1521 | 0
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 113676 | 0
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 200057 | 0
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 7/1/2024 | DOER |  | DOER | 70012 | 0
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/15/2022 | DOES |  | DOES | 64929 | 0
15 | K029 | P.S. 29 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS 501 AND 500 AND ABATE AND REPAIR WALL PLASTER IN ROOM 30 | Construction | Complete | 7/17/2023 | IEH | 6/4/2024 | IEH | 1952 | 1952
15 | K029 | P.S. 29 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE THE FOLLOWING FLOORS CAFE LOBBY 201B PLAY AREA 1 2030 PLAY AREA 2 2031 STUDEN | Construction | In-Progress | 9/22/2023 | IEH |  | IEH | 1646 | 1071
15 | K029 | P.S. 29 - BROOKLYN | SCA IEH | PO18-PLEASE FERFORM ACM TESTING ON LOOSE FLOOR TILE IN STAIRCASE H AND I , AND ROOM 500 | Construction | In-Progress | 12/29/2023 | IEH |  | IEH | 3858 | 658
15 | K029 | P.S. 29 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR BY RADIATOR IN 204, 500 SCRAPE SOLID SUBSTRATE ON WALLS IN ROOM 500 | Construction | Complete | 7/17/2024 | IEH | 8/8/2024 | IEH | 25690 | 1247
15 | K029 | P.S. 29 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOOR APP. 8X10 NEAR RADIATOR IN ROOM 500 | Construction | Complete | 8/22/2024 | IEH | 8/23/2024 | IEH | 29950 | 637
15 | K029 | P.S. 29 - BROOKLYN | Fast Track Projects | LSP WATER BOOSTER PUMP SET REPLACEMENT | Construction | In-Progress | 6/9/2023 | FTK |  | FTK | 212419 | 200012
15 | K029 | P.S. 29 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0
15 | K029 | P.S. 29 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/22/2024 | DOER |  | DOER | 750000 | 0
15 | K032 | P.S. 32 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/8/2024 | DIIR | 5/6/2024 | DIIR | 86000 | 86000
15 | K032 | P.S. 32 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
15 | K032 | P.S. 32 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/1/2024 | DOES | 4/11/2024 | DOES | 65832 | 6466
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 3/18/2022 | 3/18/2022 | 3/18/2022 | 0 | 0 | 0
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 3/18/2022 | 4/18/2022 | 3/18/2022 | 0 | 0 | 0
15 | K038 | P.S. 38 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 286097 | 0
15 | K038 | P.S. 38 - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
15 | K038 | P.S. 38 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/11/2024 | DOES | 4/17/2024 | DOES | 65832 | 15454
15 | K039 | P.S. 39 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Scope | Complete | 1/5/2024 | 4/5/2024 | 4/16/2024 | 0 | 1309 | 1309
15 | K039 | P.S. 39 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 9/26/2023 | DOEL | 4/16/2024 | DOEL | 57525 | 57525
15 | K039 | P.S. 39 - BROOKLYN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 8/31/2023 | DOER |  | DOER | 42783 | 0
15 | K039 | P.S. 39 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/20/2024 | DOES | 5/24/2024 | DOES | 65832
15 | K051 | I.S. 51 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 50000
15 | K051 | I.S. 51 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 130921 | 0
15 | K051 | I.S. 51 - BROOKLYN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
15 | K058 | P.S. 58 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/8/2021 | 8/9/2021 | 1/18/2022 | 0 | 35948 | 35948
15 | K058 | P.S. 58 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/13/2021 | DOER |  | DOER | 134331 | 0
15 | K058 | P.S. 58 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2024 | DOES |  | DOES | 223789 | 0
15 | K058 | P.S. 58 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/24/2024 | DOES | 5/2/2024 | DOES | 65832 | 11346
15 | K088 | I.S. 88 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 230673 | 0
15 | K088 | K053 SPED - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 6/24/2024 | DIIR | 93000 | 93000
15 | K088 | I.S. 88 - BROOKLYN | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0
15 | K088 | I.S. 88 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/25/2022 | DOER |  | DOER | 222356 | 0
15 | K088 | I.S. 88 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 110000 | 0
15 | K094 | P.S. 94 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROX. 15 LINEAR FEET OF STEAM PIPE RISER INSULATION PLUS 2 HIORIZONTAL LINEARFE | Construction | Complete | 4/22/2024 | IEH | 4/27/2024 | IEH | 15855 | 15855
15 | K094 | P.S. 94 - BROOKLYN | SCA IEH | PO18-ABATE CEILING LAYERS FOR ACM LOC: ROOM 111 STAFF WILL BE PAINTING FOR CONVERSION TO MED | Construction | In-Progress | 9/20/2024 | IEH |  | IEH | 362 | 362
15 | K094 | P.S. 94 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 5/21/2024 | DIIR | 50000 | 50000
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 11/20/2022 | DOER |  | DOER | 242297 | 0
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/29/2022 | DOER |  | DOER | 700288 | 0
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 108758 | 0
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
15 | K094 | P.S. 94 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0
15 | K094 | P.S. 94 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/29/2024 | DOES |  | DOES | 65832 | 0
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/9/2023 | 5/10/2023 | 5/8/2023 | 0 | 24502 | 24502
15 | K107 | P.S. 107 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K107 | P.S. 107 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/29/2024 | DOES |  | DOES | 65832 | 0
15 | K124 | P.S. 124 - BROOKLYN | Fast Track Projects | FY24 RESO A CTF ROOM CONVERSION | Construction | PNS | FTK | FTK | FTK | FTK | 24293 | 12146
15 | K124 | P.S. 124 - BROOKLYN | Fast Track Projects | PATH OF TRAVEL RESO A CTF ROOM CONVERSION | Construction | PNS | FTK | FTK | FTK | FTK |  | 0
15 | K124 | P.S. 124 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K124 | P.S. 124 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 130000 | 0
15 | K124 | P.S. 124 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/26/2024 | DOES | 4/5/2024 | DOES | 65832 | 10034
15 | K130 | P.S. 130 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM RENOVATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K130 | P.S. 130 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM RENOVATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K130 | P.S. 130 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM RENOVATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K130 | P.S. 130 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM RENOVATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K130 | P.S. 130 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
15 | K130 | P.S. 130 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/10/2024 | DOES |  | DOES | 65832 | 0
15 | K131 | P.S. 131 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR WALL LOC, PRINCIPAL OFFICE, RM 106A SCREWS ARE LIFTING BEHIND WHITEBOARD | Construction | Complete | 3/25/2024 | IEH | 4/5/2024 | IEH | 11533 | 11533
15 | K131 | P.S. 131 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 62500 | 0
15 | K131 | P.S. 131 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 68000
15 | K131 | P.S. 131 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K131 | P.S. 131 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
15 | K131 | P.S. 131 - BROOKLYN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/16/2023 | DOER |  | DOER | 505633 | 0
15 | K131 | P.S. 131 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/9/2023 | DOER |  | DOER | 396032 | 0
15 | K131 | P.S. 131 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/15/2022 | DOES |  | DOES | 99547 | 0
15 | K131 | P.S. 131 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/10/2024 | DOES | 5/17/2024 | DOES | 65832
15 | K136 | I.S. 821 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER IN CORRIDOR ADJACENT TO ROOM #402 | Construction | Complete | 3/27/2024 | IEH | 4/23/2024 | IEH | 642 | 642
15 | K136 | I.S. 821 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE 60SQFT OF DAMAGED FLOOR TILES IN ROOM 103 | Construction | Complete | 7/15/2024 | IEH | 7/19/2024 | IEH | 392 | 392
15 | K136 | I.S. 821 - BROOKLYN | SCA IEH | PO18-ABATE, REPAIR AND REPLACE FLOORS IN ROOM 104 DAMAGE AREA 20SF | Construction | Complete | 7/31/2024 | IEH | 8/18/2024 | IEH | 63781 | 842
15 | K136 | I.S. 821 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 150000 | 0
15 | K136 | I.S. 136 - BROOKLYN | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/28/2021 | DOER |  | DOER | 721296 | 0
15 | K136 | I.S. 821 - BROOKLYN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 2788 | 0
15 | K136 | I.S. 821 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/21/2023 | DOES |  | DOES | 387397 | 0
15 | K136 | I.S. 136 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 8/27/2024 | DOES |  | DOES | 822950 | 0
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: 410/409/404A/416/304A/311/314/313/201/202/203/205/208/2 | Construction | Complete | 9/1/2023 | IEH | 5/5/2024 | IEH | 225162 | 225162
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-ABATE/REMOVE DAMAGED ACM INSULATION IN BOILERROOM STEAM HEADER PIPE INSULATION: 50-60 SQ FT BOI | Construction | Complete | 3/25/2024 | IEH | 4/7/2024 | IEH | 17362 | 12462
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE ALL FLOOR LAYERS FOR ACM SUB FLOORING ACM PER AHEHA / HEAVING, CRUMBLING, AND | Construction | In-Progress | 7/24/2024 | IEH |  | IEH | 195985 | 528
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE ALL FLOOR LAYERS FOR ACM SUB FLOORING ACM PER AHEHA / HEAVING, CRUMBLING, AND | Construction | Complete | 7/24/2024 | IEH | 9/29/2024 | IEH | 224048 | 2882
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-ABATE WALLS AND CEILINGS FOR ACM STAIRWELL 3001 EXIT 1 | Construction | Complete | 8/6/2024 | IEH | 8/30/2024 | IEH | 18353 | 580
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON WALL AND CEILING PLASTER IN LOC: SPACE ID 5424 20/30% DAMAGE | Construction | In-Progress | 8/7/2024 | IEH |  | IEH | 3671 | 296
15 | K142 | I.S. 448 - BROOKLYN | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON WALL AND CEILING PLASTERS IN ROOM 319 60% DAMAGED | Construction | In-Progress | 8/8/2024 | IEH |  | IEH | 3501 | 326
15 | K142 | I.S. 448 - BROOKLYN | Fast Track Projects | LSP FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/19/2023 | FTK |  | FTK | 340331 | 327590
15 | K142 | I.S. 448 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 118000 | 0
15 | K142 | P.S. 146 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K142 | I.S. 448 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K142 | I.S. 448 - BROOKLYN | DOE - RESOA | FY16 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/9/2017 | DOER |  | DOER | 268312 | 0
15 | K142 | I.S. 448 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0
15 | K154 | P.S. 154 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 50000
15 | K154 | P.S. 154 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/18/2024 | DOER |  | DOER | 222480 | 0
15 | K154 | P.S. 154 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/26/2024 | DOES | 4/9/2024 | DOES | 65832 | 9527
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/24/2021 | 6/22/2021 | 8/12/2021 | 0 | 17629 | 17629
15 | K169 | P.S. 169 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 5/22/2024 | DIIR | 150000 | 150000
15 | K169 | P.S. 169 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 5/2/2022 | DOES |  | DOES | 62704 | 0
15 | K169 | P.S. 169 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/15/2024 | DOES | 4/24/2024 | DOES | 65832 | 10355
15 | K172 | P.S. 172 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 1/15/2019 | EMER |  | EMER | 23214 | 23214
15 | K172 | P.S. 172 - BROOKLYN | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/21/2020 | FTK |  | FTK | 1142542 | 1064574
15 | K172 | P.S. 172 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
15 | K172 | P.S. 172 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/28/2023 | DOES |  | DOES | 193011 | 0
15 | K172 | P.S. 172 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/6/2024 | DOES | 6/11/2024 | DOES | 65832 | 189
15 | K230 | P.S. 230 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
15 | K230 | P.S. 230 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 480000 | 0
15 | K230 | P.S. 230 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 11/10/2021 | DOES |  | DOES | 84168 | 0
15 | K230 | P.S. 230 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/5/2023 | DOES |  | DOES | 258266 | 0
15 | K231 | K721 SPED - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/1/2024 | IEH | 8/14/2024 | IEH | 12689 | 0
15 | K231 | K721 SPED - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/17/2024 | DIIR | 9/20/2024 | DIIR | 100000
15 | K231 | K721 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 160962 | 0
15 | K231 | K721 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
15 | K231 | K721 SPED - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/14/2022 | DOES |  | DOES | 134222 | 0
15 | K261 | P.S. 261 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 465000 | 0
15 | K261 | P.S. 261 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 556906 | 0
15 | K261 | P.S. 261 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 129000 | 0
15 | K280 | I.S. 442 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/24/2024 | DIIR | 35000
15 | K280 | I.S. 442 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K280 | I.S. 442 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 55000
15 | K280 | PRE-K CENTER AT BISHOP FORD SCHOOL SITE | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
15 | K293 | THE BOERUM HILL SCHOOL FOR INTERNATIONAL STUDIES - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 60000 | 0
15 | K293 | THE BOERUM HILL SCHOOL FOR INTERNATIONAL STUDIES - K | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 9/22/2022 | DOER |  | DOER | 51442 | 0
15 | K293 | SUCCESS ACADEMY CHARTER SCHOOL - COBBLE HILL | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 6/26/2024 | DOER |  | DOER | 210715 | 0
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/16/2022 | 9/15/2022 | 10/14/2022 | 0 | 38633 | 38633
15 | K321 | P.S. 321 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/10/2024 | DIIR | 8/19/2024 | DIIR | 50000
15 | K321 | P.S. 321 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K321 | P.S. 321 - BROOKLYN | DOE - RESOA | FY09 RESO A ROOM CONVERSIONS / PART | Construction | PNS | PNS | PNS | PNS | DOER | 95899 | 0
15 | K333 | SUNSET PARK AVENUES ELEMENTARY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/29/2024 | DOES |  | DOES | 65832 | 0
15 | K338 | M.S. 890 | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 260000 | 0
15 | K338 | M.S. 890 | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/8/2019 | DOER |  | DOER | 155023 | 0
15 | K338 | P.S. 338 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/6/2023 | DOES | 5/14/2024 | DOES | 50832
15 | K369 | COY L. COX SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 385000 | 0
15 | K369 | COY L. COX SCHOOL | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 7/6/2022 | DOER |  | DOER | 337326 | 0
15 | K369 | COY L. COX SCHOOL | DOE - Skilled Trades | PA- CLOCK SYSTEM | Construction | In-Progress | 11/6/2023 | DOES |  | DOES | 207140 | 0
15 | K371 | K371 SPED - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/10/2024 | DIIR | 5/15/2024 | DIIR | 333721 | 333721
15 | K371 | K371 SPED - BROOKLYN | DOE - RESOA | FY19 RESO A ROOM CONVERSION/PARTITIONING | Construction | In-Progress | 2/29/2020 | DOER |  | DOER | 100712 | 0
15 | K371 | K371 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
15 | K371 | K371 SPED - BROOKLYN | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 166279 | 0
15 | K371 | K371 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
15 | K437 | K053 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K437 | M.S. 839 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 8/14/2024 | DIIR | 100000 | 100000
15 | K437 | M.S. 839 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/25/2024 | DIIR | 4/8/2024 | DIIR | 60000 | 60000
15 | K437 | M.S. 839 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/25/2024 | DIIR | 4/8/2024 | DIIR | 54175 | 54175
15 | K437 | M.S. 839 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 6/20/2024 | DIIR | 50000 | 50000
15 | K437 | K053 SPED - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 6/24/2024 | DIIR | 50000 | 50000
15 | K437 | M.S. 839 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K437 | P.S. 130 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/9/2024 | DOES |  | DOES | 50832 | 0
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K460 | PARK SLOPE COLLEGIATE - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | SCA IEH | PO18-ABATE AND REPLACE FLOORS IN ROOMS 330, 332, 336 | Construction | In-Progress | 6/6/2024 | IEH |  | IEH | 1296 | 721
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | SCA IEH | PO18-ABATE PIPE INSULATION PIPE SPACE UNDER POOL MECHANICAL ROOM, 4TH STREET SIDE OF BUILDING BASEME | Construction | Complete | 7/17/2024 | IEH | 7/19/2024 | IEH | 34654 | 649
15 | K460 | SECONDARY SCHOOL FOR LAW - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 4/12/2024 | DIIR | 50000
15 | K460 | PARK SLOPE COLLEGIATE - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
15 | K460 | SECONDARY SCHOOL FOR LAW - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 6/21/2024 | DIIR | 50000
15 | K460 | PARK SLOPE COLLEGIATE - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K460 | PARK SLOPE COLLEGIATE - K | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/28/2023 | DOER |  | DOER | 100315 | 0
15 | K460 | SECONDARY SCHOOL FOR LAW - K | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 12/1/2022 | DOES |  | DOES | 827633 | 0
15 | K460 | MILLENIUM BROOKLYN HIGH SCHOOL - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/18/2024 | DOES |  | DOES | 65832 | 0
15 | K520 | BROOKLYN FRONTIERS HIGH SCHOOL - K | SCA IEH | PO18-ABATE WALL AND CEILING LAYERS FOR ACM LOCS: ROOMS 111 AND 117 STRESS CRACKS FROM EARTHQUAKE | Construction | Complete | 5/7/2024 | IEH | 6/1/2024 | IEH | 17738 | 11568
15 | K520 | BROOKLYN FRONTIERS HIGH SCHOOL - K | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 6/1/2024 | IEH | 24035 | 7291
15 | K520 | BROOKLYN FRONTIERS HIGH SCHOOL - K | DOE - RESOA | FY17 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 201141 | 0
15 | K520 | BROOKLYN FRONTIERS HIGH SCHOOL - K | DOE - RESOA | FY20 RESO A FABLABS | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
15 | K564 | SUNSET PARK HS - BROOKLYN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/21/2022 | DOER |  | DOER | 102406 | 0
15 | K564 | SUNSET PARK HS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/28/2024 | DOES |  | DOES | 50832 | 0
15 | K655 | BROOKLYN HS OF THE ARTS - BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 2/10/2023 | DOES |  | DOES | 489448 | 0
15 | K661 | THE LITTLE BROOKLYN PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/30/2024 | DOES |  | DOES | 65832 | 0
15 | K671 | P.S. 958 | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
15 | K671 | P.S. 958 | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/2/2024 | DOES | 4/5/2024 | DOES | 50832 | 9016
15 | K682 | P.S. 896 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 101143 | 0
15 | K692 | THE LITTLE BROOKLYN PRE-K CENTER | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K749 | THE LITTLE BROOKLYN PRE-K CENTER | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 8/13/2018 | DOES |  | DOES | 195142 | 0
15 | K749 | THE LITTLE BROOKLYN PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/1/2024 | DOES |  | DOES | 65832 | 0
15 | K751 | P.S. 58 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K751 | P.S. 58 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/1/2024 | DOES |  | DOES | 65832 | 0
15 | K763 | THE MAURICE SENDAK COMMUNITY SCHOOL | SCA IEH | PO18-PERFORM QC SUPPLEMENTAL SAMPLING ON FLOORS IN ROOM 318. SOFT FILLER ASSUMED ACM. DAMAGE IS IN | Construction | In-Progress | 9/24/2024 | IEH |  | IEH | 0 | 0
15 | K763 | THE MAURICE SENDAK COMMUNITY SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 50000
15 | K763 | THE MAURICE SENDAK COMMUNITY SCHOOL | DOE - RESOA | FY18 RESO A HYDROPNICS CLASSROOM | Construction | In-Progress | 6/7/2019 | DOER |  | DOER | 113347 | 0
15 | K763 | THE MAURICE SENDAK COMMUNITY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/18/2024 | DOES | 4/2/2024 | DOES | 65832 | 8966
15 | K781 | WEST BROOKLYN COMMUNITY HS - K | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 6/9/2024 | IEH | 26176 | 5521
15 | K781 | WEST BROOKLYN COMMUNITY HS - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K781 | WEST BROOKLYN COMMUNITY HS - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K781 | WEST BROOKLYN COMMUNITY HS - K | DOE - RESOA | FY18 RESO A LIBRARY UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 59842 | 0
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | SCA IEH | PO18-ABATE 40LF OF METAL TRACK ON FLOOR IN ROOM 922B | Construction | Complete | 4/30/2024 | IEH | 5/2/2024 | IEH | 427 | 427
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | SCA IEH | PO18-PLEASE REMOVE 800SF OF RUG AND FLOOR TILE ACM IN ROOM 907 ON THE 9TH FLOOR. | Construction | In-Progress | 5/2/2024 | IEH |  | IEH | 31741 | 1164
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | SCA IEH | PO18-REMOVAL OF RUG AND FLOOR TILES IN ROOM #703 | Construction | Complete | 5/28/2024 | IEH | 8/4/2024 | IEH | 16414 | 1826
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | Fast Track Projects | ELEVATOR MODERNIZATION | Construction | In-Progress | 9/13/2017 | FTK |  | FTK | 4840929 | 4788106
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | DIIT - Project Connect | NEXT GENERATION NETWORK UPGRADE | Purch & Install | Complete | 3/1/2019 | DIIT | 10/28/2022 | DIIT | 1511500
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | DOE - Skilled Trades | COOLING TOWER REPAIRS | Construction | In-Progress | 1/31/2022 | DOES |  | DOES | 233035 | 99667
15 | K801 | HEADQTRS 65 CNTRL ADMIN. - K | DOE - Skilled Trades | MASONRY REPAIRS | Construction | In-Progress | 1/3/2024 | DOES |  | DOES | 302535 | 0
15 | K802 | VIRTUAL INNOVATORS ACADEMY | SCA IEH | PO18-TEST CELING AND WALLS IN 2003A FOR ACM PLASTER WORK IN NEEDED | Construction | Complete | 12/20/2023 | IEH | 4/9/2024 | IEH | 51 | 51
15 | K802 | VIRTUAL INNOVATORS ACADEMY | SCA IEH | PO18-TEST FOR ACM 6 DIFFERENT ROOMS -4001A, CEILING AND WALL DETERIORATION, 301 -5001B, CEILING AND | Construction | Complete | 12/20/2023 | IEH | 4/9/2024 | IEH | 39 | 39
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA IEH | PO18-ABATE AND REPAIR FLOORING IN SCIENCE LABS # 411 AND 416 | Construction | In-Progress | 7/28/2023 | IEH |  | IEH | 1117 | 542
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K825 | SOUTH BROOKLYN COMM. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A KITCHEN UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
15 | K825 | SOUTH BROOKLYN COMM. HS - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/8/2024 | DIIR | 4/18/2024 | DIIR | 70000
15 | K825 | SOUTH BROOKLYN COMM. HS - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
15 | K834 | K372 SPED - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/12/2021 | 10/8/2021 | 10/5/2021 | 0 | 52340 | 52340
15 | K834 | K372 SPED - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 9/26/2024 | IEH |  | IEH | 0 | 0
15 | K834 | K372 SPED - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/7/2024 | DIIR | 8/5/2024 | DIIR | 150000 | 150000
15 | K834 | K372 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 185659 | 0
15 | K845 | P.S. 295 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB | Construction | In-Progress | 9/6/2022 | EMER |  | EMER | 18216 | 10103
15 | K845 | I.S. 443 - BROOKLYN | Fast Track Projects | LSP VACUUM PUMP REPLACEMENT | Construction | In-Progress | 6/22/2021 | FTK |  | FTK | 561423 | 554612
15 | K845 | I.S. 443 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/19/2024 | DOES | 5/2/2024 | DOES | 65832 | 9374
15 | K871 | PATHWAYS TO GRADUATION - CITYWIDE | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 5/25/2024 | IEH | 9084 | 8895
15 | K908 | P.S. 230 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 6/17/2024 | IEH |  | IEH | 12399 | 0
15 | K917 | BROOKLYN COLLEGE ACADEMY - K | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 4/19/2024 | IEH |  | IEH | 12399 | 0
15 | K917 | BROOKLYN COLLEGE ACADEMY - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | K917 | BROOKLYN COLLEGE ACADEMY - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/29/2024 | DIIR | 5/9/2024 | DIIR | 50000
15 | K917 | BROOKLYN COLLEGE ACADEMY - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/7/2024 | DIIR | 50000
15 | K939 | I.S. 136 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
15 | KAGI | BROOKLYN PROSPECT CHARTER SCHOOL - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
15 | KAGI | BROOKLYN PROSPECT CHARTER SCHOOL - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | KBNU | BROOKLYN URBAN CHARTER SCHOOL | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
15 | KBNU | BROOKLYN URBAN CHARTER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
16 | K005 | P.S. 5 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
16 | K005 | P.S. 5 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K005 | P.S. 5 - BROOKLYN | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | Complete | 3/31/2020 | DOER | 12/22/2021 | DOER | 191755 | 189175
16 | K005 | P.S. 5 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 9/19/2023 | DOER |  | DOER | 220942 | 0
16 | K005 | P.S. 5 - BROOKLYN | DOE - RESOA | FY23 RESO A STEM LAB | Construction | In-Progress | 6/2/2023 | DOER |  | DOER | 279578 | 0
16 | K005 | P.S. 5 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 8/18/2020 | DOES |  | DOES | 574176 | 0
16 | K021 | P.S. 21 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION - SWB @ K021 | Construction | In-Progress | 3/29/2024 | EMER |  | EMER |  | 0
16 | K021 | P.S. 21 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K025 | P.S. 25 - BROOKLYN | Fast Track Projects | PATH OF TRAVEL PLAY YARD | Construction | In-Progress | 7/11/2024 | FTK |  | FTK | 364057 | 43432
16 | K025 | P.S. 25 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K025 | SUCCESS ACADEMY CHARTER SCHOOL - BED STUY 3 | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
16 | K025 | P.S. 25 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 88092 | 0
16 | K025 | P.S. 25 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/2/2024 | DOES | 5/10/2024 | DOES | 65832 | 8599
16 | K026 | I.S. 681 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K026 | P.S. 26 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K026 | P.S. 26 - BROOKLYN | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
16 | K035 | I.S. 35 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING ROOMS: RM: 319A APPROX. 466SF RM: 306 APPROX. 1 | Construction | Complete | 7/27/2023 | IEH | 4/13/2024 | IEH | 62114 | 49039
16 | K035 | I.S. 35 - BROOKLYN | SCA IEH | PO18-SURVEY & ABATE AND REPLACE IF NEEDED FLOOR TILES ROOM #301 REPAIR WORK IS NEEDED AS PER SCA | Construction | Complete | 7/26/2024 | IEH | 8/17/2024 | IEH | 85938 | 3828
16 | K035 | I.S. 35 - BROOKLYN | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 34173 | 28974
16 | K035 | I.S. 35 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K035 | BKLYN BROWNSTONE SCL - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K035 | I.S. 35 - BROOKLYN | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
16 | K035 | I.S. 35 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 1/27/2023 | DOES | 6/28/2023 | DOES | 194837 | 7343
16 | K035 | I.S. 35 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/8/2024 | DOES |  | DOES | 458640 | 0
16 | K035 | I.S. 35 - BROOKLYN | Trust For Public Land | TPL- EXTREME WEATHER PLAYGROUND UPGRADE | Construction | In-Progress | 6/1/2024 | TPL |  | TPL | 1933792 | 244972
16 | K040 | P.S. 40 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K040 | GOTHAM PROFESSIONAL ARTS ACAD - K | DOE - RESOA | FY14 RESO A VENTILATION | Construction | PNS | PNS | PNS | PNS | DOER | 40000 | 0
16 | K040 | P.S. 40 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 137402 | 0
16 | K040 | P.S. 40 - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
16 | K040 | P.S. 40 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
16 | K040 | P.S. 40 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/6/2024 | DOES |  | DOES | 65832 | 0
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | Fast Track Projects | BUILDING DRAIN BACKUP | Construction | In-Progress | 10/12/2017 | FTK |  | FTK | 6606522 | 6233107
16 | K057 | BROOKLYN ACADEMY OF GLOBAL FINANCE - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/1/2024 | DIIR | 5/10/2024 | DIIR | 215000
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K057 | BROOKLYN ACADEMY OF GLOBAL FINANCE - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K057 | BROOKLYN ACADEMY OF GLOBAL FINANCE - K | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/7/2023 | DOER |  | DOER | 95591 | 0
16 | K081 | P.S. 81 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K081 | P.S. 81 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/28/2019 | DOER |  | DOER | 184678 | 0
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
16 | K243 | P.S. 243 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 825000 | 0
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/30/2023 | 4/28/2023 | 4/12/2023 | 0 | 57276 | 57276
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/30/2023 | 5/1/2023 | 12/15/2023 | 0 | 14362 | 14362
16 | K262 | P.S. 262 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE 9X9 ASBESTOS TILES IN KITCHEN LOCKER ROOM TILES ARE DAMAGED.REMOVE TILES FOR NEW L | Construction | Complete | 5/7/2024 | IEH | 9/30/2024 | IEH | 43253 | 1902
16 | K262 | P.S. 262 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K262 | P.S. 262 - BROOKLYN | DOE - RESOA | RESO A- RESO A PLAYGROUND | Construction | PNS | PNS | PNS | PNS | DOER | 223000 | 0
16 | K262 | P.S. 262 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/9/2024 | DOES | 5/16/2024 | DOES | 65832
16 | K304 | K140 SPED - BROOKLYN | SCA Emergency Response | EMERGENCY- CRACKED BRICKS - FACADE @ K304 | Construction | In-Progress | 2/29/2024 | EMER |  | EMER | 139087 | 0
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA IEH | PO18-ABATE AND REPAIR DAMAGED FLOOR IN ROOM 323 TEACHERS BATHROOM | Construction | In-Progress | 2/7/2024 | IEH |  | IEH | 24896 | 848
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/10/2023 | DOER |  | DOER | 171838 | 0
16 | K308 | P.S. 308 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K309 | P.S. 309 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K309 | P.S. 309 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
16 | K309 | P.S. 309 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/13/2024 | DOES | 5/24/2024 | DOES | 65832 | 189
16 | K324 | I.S. 267 - BROOKLYN | SCA IEH | PO18-TEST ALL ROOFTOP LAYERS FOR ACM, INCL TAR PAPER AND GRAVEL LOC: AROUND MAIN STAIRCASE A, 4TH FL | Construction | In-Progress | 1/9/2024 | IEH |  | IEH | 1020 | 720
16 | K324 | I.S. 267 - BROOKLYN | Fast Track Projects | CTF- ROOM CONVERSIONS | Construction | In-Progress | 6/7/2023 | FTK |  | FTK | 2751100 | 1878037
16 | K324 | LA CIMA CHARTER SCL - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0
16 | K324 | I.S. 267 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K324 | I.S. 267 - BROOKLYN | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 11/30/2022 | DOES |  | DOES | 930518 | 0
16 | K324 | I.S. 267 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/23/2023 | DOES | 12/1/2023 | DOES | 448280
16 | K324 | I.S. 267 - BROOKLYN | DOE - Skilled Trades | CHARTER MATCH INTERIOR SPACES | Construction | In-Progress | 7/5/2023 | DOES |  | DOES | 790765 | 690000
16 | K335 | P.S. 335 - BROOKLYN | SCA IEH | PO18-RM 47 - TEST CEILING PLASTER AND CEILING TILE ADHESIVE FOR ACM | Construction | Complete | 12/22/2023 | IEH | 7/23/2024 | IEH | 1709 | 959
16 | K335 | P.S. 335 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE PIPE INSULATION FROM PIPE IN THE CEILING OF ROOM# 29C. PIPE MARKED WITH RED PAINT | Construction | Complete | 6/3/2024 | IEH | 7/10/2024 | IEH | 11147 | 706
16 | K335 | M.S. 898 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K335 | P.S. 335 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
16 | K335 | P.S. 335 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
16 | K335 | P.S. 335 - BROOKLYN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 9/13/2023 | DOER |  | DOER | 87298 | 0
16 | K335 | P.S. 335 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/15/2024 | DOES | 4/24/2024 | DOES | 65832 | 7804
16 | K455 | BOYS & GIRLS HS - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 8/4/2020 | FTK |  | FTK | 478159 | 421416
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 99000 | 0
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DOE - RESOA | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 6/30/2021 | DOER |  | DOER | 160421 | 0
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 3/25/2022 | DOER |  | DOER | 165615 | 0
16 | K455 | NELSON MANDELA SCHOOL FOR SOCIAL JUSTICE | DOE - RESOA | FY21 RESO A FABLAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 3/31/2022 | DOES |  | DOES | 643109 | 0
16 | K455 | BOYS & GIRLS HS - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/1/2023 | DOES |  | DOES | 1266556 | 0
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/7/2022 | DOES |  | DOES | 254093 | 0
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/12/2024 | DOES |  | DOES | 65832 | 0
17 | K002 | I.S. 2 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
17 | K002 | K141 SPED - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 200000
17 | K002 | I.S. 2 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 185000 | 0
17 | K002 | K141 SPED - BROOKLYN | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
17 | K002 | I.S. 2 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 4/28/2023 | DOES | 6/27/2023 | DOES | 534614 | 474679
17 | K002 | I.S. 2 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/28/2024 | DOES |  | DOES | 50832 | 0
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/3/2023 | 6/6/2023 | 6/13/2023 | 0 | 14650 | 14650
17 | K006 | P.S. 6 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/10/2022 | EMER |  | EMER | 101912 | 12528
17 | K006 | P.S. 6 - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
17 | K006 | P.S. 6 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 9/17/2018 | DOES |  | DOES | 90004 | 0
17 | K022 | P.S. 705 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 301292 | 0
17 | K022 | P.S. 705 - BROOKLYN | DOE - RESOA | FY18 RESO A SCIENCE LAB | Construction | In-Progress | 5/14/2019 | DOER |  | DOER | 250000 | 0
17 | K022 | P.S. 705 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | Complete | 2/1/2023 | DOES | 2/14/2024 | DOES | 291757 | 2075
17 | K022 | P.S. 705 - BROOKLYN | DOE - Skilled Trades | DOMESTIC WATER MAIN AND VALVE REPLACEMENTS | Construction | In-Progress | 6/5/2021 | DOES |  | DOES | 115180 | 0
17 | K061 | I.S. 61 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REMOVE APPROXIMATELY 6 SQUARE FEET OF CAFE CEILING MARKED WITH GREY DUCT TAPE | Construction | Complete | 9/6/2024 | IEH | 9/7/2024 | IEH | 19664 | 1343
17 | K061 | I.S. 61 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REMOVE APPROXIMATELY 6 SQUARE FEET OF CAFE CEILING MARKED WITH GREY DUCT TAPE | Construction | Complete | 9/9/2024 | IEH | 9/13/2024 | IEH | 0 | 0
17 | K061 | I.S. 61 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 150000 | 0
17 | K061 | K753 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
17 | K091 | P.S. 91 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 6/1/2023 | DOEL | 10/31/2023 | DOEL | 257248 | 257248
17 | K091 | P.S. 91 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 7/6/2023 | DOEL |  | DOEL | 232182 | 230182
17 | K091 | P.S. 91 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/12/2024 | DOER |  | DOER | 18044 | 0
17 | K091 | P.S. 91 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/20/2021 | DOES |  | DOES | 56204 | 0
17 | K092 | P.S. 92 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
17 | K092 | P.S. 92 - BROOKLYN | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 195000 | 0
17 | K092 | P.S. 92 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/8/2023 | 6/6/2023 | 6/13/2023 | 0 | 20696 | 20696
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 3/8/2023 | 6/7/2023 |  | 0 | 0 | 0
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 94 | 94
17 | K138 | P.S. 138 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 5 LINEAR FEET OF ACM FROM 3' WASTE LINE IN STAIRCASE 'J' TWO FEET M | Construction | Complete | 11/30/2023 | IEH | 4/23/2024 | IEH | 0 | 0
17 | K138 | P.S. 138 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER IN THE AUDITORIUM 2024-63617 | Construction | Complete | 2/27/2024 | IEH | 5/4/2024 | IEH | 13091 | 2869
17 | K138 | P.S. 138 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER IN ROOM 211 BOYS BATHROOM | Construction | Complete | 4/15/2024 | IEH | 4/27/2024 | IEH | 26746 | 26746
17 | K138 | P.S. 138 - BROOKLYN | Fast Track Projects | FIRE SPRINKLER | Construction | In-Progress | 9/12/2019 | FTK |  | FTK | 259025 | 259025
17 | K138 | P.S. 138 - BROOKLYN | Fast Track Projects | RPZ VALVES | Construction | In-Progress | 9/12/2019 | FTK |  | FTK | 1288683 | 1284313
17 | K138 | EXPLORE EMPOWER CHARTER SCHL - K | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 35000 | 0
17 | K138 | P.S. 138 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 12/14/2020 | DOES |  | DOES | 119598 | 0
17 | K138 | P.S. 138 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/30/2024 | DOES |  | DOES | 65832 | 0
17 | K161 | P.S. 161 - BROOKLYN | Fast Track Projects | CTF- CHARTER MATCH PROMETHEAN BOARDS | Construction | In-Progress | 7/29/2019 | FTK |  | FTK | 289087 | 288587
17 | K161 | P.S. 161 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 226000 | 0
17 | K161 | SUCCESS ACADEMY CROWN HEIGHTS (BROOKLYN 7) | DOE - RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 11/2/2021 | DOER |  | DOER | 1008060 | 0
17 | K167 | NEW BRIDGES | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 12/1/2023 | 4/2/2024 | 5/31/2024 | 0 | 17573 | 6645
17 | K167 | NEW BRIDGES | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 3/27/2024 | 6/27/2024 | 7/25/2024 | 0 | 156 | 156
17 | K167 | NEW BRIDGES | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 2/16/2024 | DOER |  | DOER | 76434 | 0
17 | K167 | NEW BRIDGES | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/17/2021 | DOES |  | DOES | 74879 | 0
17 | K181 | P.S. 181 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/23/2024 | DIIR | 4/3/2024 | DIIR | 100000 | 100000
17 | K181 | P.S. 181 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
17 | K181 | P.S. 181 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/23/2021 | DOER |  | DOER | 155722 | 0
17 | K181 | P.S. 181 - BROOKLYN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 4/28/2023 | DOER |  | DOER | 71934 | 0
17 | K181 | P.S. 181 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 2/13/2020 | DOES |  | DOES | 71940 | 0
17 | K189 | P.S. 189 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 12/6/2021 | DOER |  | DOER | 152582 | 0
17 | K189 | P.S. 189 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 707369 | 0
17 | K191 | P.S. 191 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 4/10/2023 | DOES |  | DOES | 1025050 | 0
17 | K191 | P.S. 191 - BROOKLYN | DOE - Skilled Trades | REPLACE LEAKING STEEL HOT WATER STORAGE TANK | Construction | In-Progress | 8/1/2022 | DOES |  | DOES | 201216 | 0
17 | K210 | I.S. 394 - BROOKLYN | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 5/28/2021 | DOER |  | DOER | 137992 | 0
17 | K210 | I.S. 394 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 5/13/2024 | DOES | 5/31/2024 | DOES | 342832
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 12/15/2023 | 4/18/2024 |  | 0 | 8461 | 8461
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 8/12/2024 | 11/13/2024 | 9/17/2024 | 0 | 0 | 0
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K221 | P.S. 221 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION @K221 | Construction | In-Progress | 7/21/2023 | EMER |  | EMER | 54487 | 48600
17 | K221 | P.S. 221 - BROOKLYN | Fast Track Projects | PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 4/5/2019 | FTK |  | FTK | 51767 | 37890
17 | K221 | P.S. 221 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
17 | K221 | P.S. 221 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75150 | 0
17 | K221 | P.S. 221 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/18/2022 | DOES |  | DOES | 31112 | 0
17 | K221 | P.S. 221 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/14/2022 | DOES |  | DOES | 148252 | 0
17 | K241 | P.S. 241 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 40 LINEAR FEET OF PIPE INSULATION FROM COLD WATER MAIN IN BOILER RO | Construction | Complete | 3/7/2024 | IEH | 4/23/2024 | IEH | 103 | 103
17 | K241 | P.S. 241 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 25 LINEAR FEET OF PIPE COVER FROM IN FAN ROOM. PIPE MARKED WITH RED | Construction | Complete | 6/25/2024 | IEH | 6/26/2024 | IEH | 16427 | 12127
17 | K241 | P.S. 241 - BROOKLYN | DOE - Skilled Trades | EMERGENCY HEATING PLANT UPGRADE | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 722916 | 0
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/14/2023 | 6/15/2023 | 5/19/2023 | 0 | 28435 | 28435
17 | K246 | I.S. 246 - BROOKLYN | SCA IEH | PO18- REPLACE 280 SQ FT OF 9X9 FLOOR TILE IN ROOM 123 G.O. AND PRINCIPAL OFFICE | Construction | Complete | 7/17/2023 | IEH | 4/26/2024 | IEH | 839 | 264
17 | K246 | I.S. 246 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMPS | Construction | In-Progress | 4/1/2020 | DOES |  | DOES | 365485 | 0
17 | K246 | I.S. 246 - BROOKLYN | DOE - Skilled Trades | SEWAGE EJECTOR PUMPS | Construction | In-Progress | 12/14/2020 | DOES |  | DOES | 79732 | 0
17 | K246 | I.S. 246 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 10/12/2023 | DOES |  | DOES | 1749678 | 0
17 | K246 | I.S. 246 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/29/2024 | DOES |  | DOES | 635096 | 0
17 | K249 | P.S. 249 - BROOKLYN | DOE - RESOA | RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
17 | K249 | P.S. 249 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMPS | Construction | In-Progress | 6/28/2021 | DOES |  | DOES | 401566 | 0
17 | K249 | P.S. 249 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 1/17/2020 | DOES |  | DOES | 262361 | 0
17 | K289 | P.S. 289 - BROOKLYN | DOE - Skilled Trades | REPLACE TELEDYNE LAARS HOT WATER BOILER | Construction | In-Progress | 7/11/2019 | DOES |  | DOES | 39172 | 0
17 | K289 | P.S. 289 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 11/18/2020 | DOES |  | DOES | 103324 | 0
17 | K289 | P.S. 289 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/4/2024 | DOES |  | DOES | 65832 | 0
17 | K316 | P.S. 316 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/13/2023 | 6/14/2023 | 6/23/2023 | 0 | 22235 | 12051
17 | K316 | P.S. 316 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 7/21/2023 | 10/23/2023 |  | 0 | 0 | 0
17 | K316 | P.S. 316 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K316 | P.S. 316 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K316 | P.S. 316 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K316 | P.S. 316 - BROOKLYN | Fast Track Projects | LSP- CONDENSATE PUMP & STEAM TRAP REPLACEMENT | Construction | In-Progress | 9/6/2023 | FTK |  | FTK | 660763 | 335156
17 | K316 | M.S. 353 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
17 | K316 | P.S. 316 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 10/27/2023 | DOEL |  | DOEL | 75790 | 75790
17 | K316 | P.S. 316 - BROOKLYN | DOE - RESOA | RESO A FENCING | Construction | In-Progress | 5/23/2017 | DOER |  | DOER | 126877 | 0
17 | K316 | P.S. 316 - BROOKLYN | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 5/4/2021 | DOER |  | DOER | 156587 | 0
17 | K316 | P.S. 316 - BROOKLYN | DOE - RESOA | FY22 RESO A CAFETERIA SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 227000 | 0
17 | K316 | P.S. 316 - BROOKLYN | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 170000 | 0
17 | K316 | P.S. 316 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 3/23/2020 | DOES |  | DOES | 86832 | 0
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/29/2023 | 3/1/2024 | 3/22/2024 | 0 | 12946 | 12946
17 | K320 | M.S. 352 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 8/8/2024 | 11/7/2024 | 9/19/2024 | 0 | 0 | 0
17 | K320 | M.S. 352 - BROOKLYN | DIIT - RESOA | RESO A-FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
17 | K320 | P.S. 375 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 5/21/2024 | DIIR | 200000 | 200000
17 | K320 | P.S. 375 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/13/2021 | DOER |  | DOER | 298163 | 0
17 | K320 | M.S. 352 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/18/2024 | DOER |  | DOER | 310349 | 0
17 | K320 | M.S. 352 - BROOKLYN | DOE - RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
17 | K320 | P.S. 375 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
17 | K320 | M.S. 352 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
17 | K320 | P.S. 375 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/29/2022 | DOES |  | DOES | 181789 | 0
17 | K390 | M.S. 354 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0
17 | K390 | M.S. 354 - BROOKLYN | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/12/2021 | DOER |  | DOER | 105553 | 0
17 | K390 | M.S. 354 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 12/28/2020 | DOES |  | DOES | 149318 | 0
17 | K390 | M.S. 354 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/9/2024 | DOES |  | DOES | 573324 | 0
17 | K391 | I.S. 722 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 75200 | 0
17 | K391 | I.S. 722 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/11/2023 | DOES |  | DOES | 657741 | 0
17 | K397 | P.S. 397 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 101563 | 0
17 | K397 | P.S. 397 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 205000 | 0
17 | K397 | P.S. 397 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/12/2019 | DOES |  | DOES | 112463 | 0
17 | K398 | P.S. 398 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
17 | K398 | P.S. 770 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
17 | K398 | P.S. 770 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 2/2/2024 | DOER |  | DOER | 140679 | 0
17 | K398 | P.S. 770 - BROOKLYN | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
17 | K398 | P.S. 770 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
17 | K398 | P.S. 398 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 75200 | 0
17 | K398 | P.S. 398 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/29/2024 | DOES | 6/5/2024 | DOES | 65832
17 | K399 | P.S. 399 - BROOKLYN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/7/2022 | DOER |  | DOER | 189222 | 0
17 | K399 | P.S. 399 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
17 | K399 | P.S. 399 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/18/2021 | DOES |  | DOES | 138082 | 0
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Scope | Complete | 12/7/2023 | 4/10/2024 | 5/16/2024 | 0 | 20096 | 2528
17 | K440 | BROOKLYN HS FOR MUSIC &THEATER - K | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/7/2023 | 4/10/2024 | 5/21/2024 | 0 | 16208 | 2371
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 4/4/2024 | 7/8/2024 | 7/23/2024 | 0 | 0 | 0
17 | K440 | BROOKLYN HS FOR SCI & THE ENVI-K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 4/4/2024 | 7/8/2024 | 7/23/2024 | 0 | 0 | 0
17 | K440 | THE INTERNATIONAL HS - BROOKLYN | Fast Track Projects | LSP STAGE RIGGING / STRUCTURAL STEEL | Construction | In-Progress | 3/31/2022 | FTK |  | FTK | 533607 | 312212
17 | K440 | BROOKLYN HS FOR MUSIC &THEATER - K | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
17 | K440 | THE INTERNATIONAL HS - BROOKLYN | DOE - RESOA | FY23 RESO A LOCKER ROOM UPGRADE | Construction | In-Progress | 5/10/2024 | DOER |  | DOER | 269532 | 0
17 | K440 | HS FOR GLOBAL CITIZENSHIP - K | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 124988 | 0
17 | K440 | BROOKLYN HS FOR SCI & THE ENVI-K | DOE - Skilled Trades | REPLACE/UPGRADE STAGE RIGGING COMPONENTS | Construction | In-Progress | 12/21/2018 | DOES |  | DOES | 447006 | 0
17 | K440 | THE INTERNATIONAL HS - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/29/2023 | DOES |  | DOES | 231648 | 0
17 | K457 | BROOKLYN ACADEMY HS - BROOKLYN | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 766000 | 0
17 | K457 | BROOKLYN ACADEMY HS - BROOKLYN | DOE - Skilled Trades | ATHLETIC FIELD | Construction | In-Progress | 9/7/2023 | DOES |  | DOES | 690893 | 0
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K465 | SCIENCE TECH & RESEARCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
17 | K465 | I.S. 382 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/1/2020 | EMER |  | EMER | 607830 | 594475
17 | K465 | SCIENCE TECH & RESEARCH - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
17 | K465 | ACAD. OF HOSP. & TOURISM - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 1/26/2024 | DIIR |  | DIIR | 100000 | 0
17 | K465 | I.S. 382 - BROOKLYN | DOE - RESOA | FY17 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
17 | K465 | HS FOR YOUTH & COMMUNITY DEV. - K | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 49000 | 0
17 | K465 | ACAD. OF HOSP. & TOURISM - K | DOE - RESOA | FY24 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1275000 | 0
17 | K465 | HS FOR YOUTH & COMMUNITY DEV. - K | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 213000 | 0
17 | K465 | SCIENCE TECH & RESEARCH - K | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 233000 | 0
17 | K465 | I.S. 382 - BROOKLYN | DOE - Skilled Trades | ACE- STEAM SYSTEM UPGRADE | Construction | In-Progress | 3/11/2019 | DOES |  | DOES | 189100 | 0
17 | K470 | H.S. 745 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
17 | K470 | HS FOR PUBLIC SERVICE - K | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
17 | K470 | INTERNATIONAL ARTS BUSINESS HS - K | DOE - Skilled Trades | STAGE RIGGING & DRAPERY | Construction | In-Progress | 1/27/2020 | DOES |  | DOES | 407498 | 0
17 | K470 | H.S. 745 - BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/27/2023 | DOES |  | DOES | 716512 | 0
17 | K470 | H.S. 745 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 10/31/2023 | DOES |  | DOES | 1003703 | 0
17 | K470 | H.S. 745 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/16/2024 | DOES |  | DOES | 65832 | 0
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - RESOA | FY18 RESO A LIBRARY UPGRADES | Construction | In-Progress | 8/14/2023 | DOER |  | DOER | 100000 | 0
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 3/15/2021 | DOER |  | DOER | 85968 | 0
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 105000 | 0
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - RESOA | RESO A LIBRARY UPGRADE | Construction | In-Progress | 9/1/2023 | DOER |  | DOER | 272000 | 0
17 | K590 | MEDGAR EVERS COLLEGE PREPARATORY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/25/2024 | DOES |  | DOES | 50832 | 0
17 | K600 | CLARA BARTON HS - K | SCA IEH | PO18-TEST ALL FLOOR LAYERS FOR ACM LOC: ROOM 203 | Construction | Complete | 3/19/2024 | IEH | 4/2/2024 | IEH | 2706 | 821
17 | K600 | CLARA BARTON HS - K | SCA IEH | PO18-ACM ABATEMENT APPROX 50LF 2'-4' PIPES IN FAN ROOM IN THE BASEMENT | Construction | Complete | 4/30/2024 | IEH | 6/23/2024 | IEH | 47145 | 2025
17 | K600 | CLARA BARTON HS - K | SCA IEH | PO18-ABATE AND REPAIR MUDDED FITTINGS TO BROWN AIRCELL PAPER PIPE INSULATION AND WHITE AIRCELL PAPER | Construction | Complete | 5/10/2024 | IEH | 6/9/2024 | IEH | 31072 | 24228
17 | K600 | CLARA BARTON HS - K | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON SAFE DOOR LINING INSIDE ROOM 418. ROOM AS BEEN SHUT DOWN. AB | Construction | In-Progress | 9/24/2024 | IEH |  | IEH | 0 | 0
17 | K600 | CLARA BARTON HS - K | Fast Track Projects | CTF ROOM CONVERSION / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 6/30/2023 | FTK |  | FTK | 1631683 | 1548704
17 | K600 | CLARA BARTON HS - K | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 5/13/2016 | DOES |  | DOES | 238391 | 0
17 | K600 | CLARA BARTON HS - K | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | Complete | 5/3/2021 | DOES | 6/14/2023 | DOES | 312897 | 359246
17 | K600 | CLARA BARTON HS - K | DOE - Skilled Trades | ACCESSIBILITY | Construction | Complete | 11/16/2023 | DOES | 5/10/2024 | DOES | 1093000
17 | K824 | ASPIRATIONS DIPLOMA HS - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
17 | K867 | ALC- PROSPECT PLACE | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 8/14/2024 | IEH |  | IEH | 15473 | 338
17 | K883 | ALTERNATE LEARNING CENTER - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 11/3/2023 | DOER |  | DOER | 86769 | 0
17 | K907 | BROWNSVILLE ACADEMY HIGH SCHOOL - K | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/15/2024 | IEH | 7/27/2024 | IEH | 11153 | 0
17 | K907 | BROWNSVILLE ACADEMY HIGH SCHOOL - K | DOE - RESOA | FY22 RESO A FITNESS ROOM | Construction | PNS | PNS | PNS | PNS | DOER | 132534 | 0
17 | K909 | K373 SPED - BROOKLYN | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 12/27/2022 | FTK |  | FTK | 5507813 | 4569244
17 | K909 | ACORN COMMUNITY HS - K | DOE - RESOA | FY 14 RESO A MULTI-PURPOSE ROOM | Construction | Complete | 5/25/2021 | DOER | 7/28/2021 | DOER | 113983 | 113983
17 | K909 | GOTHAM PROFESSIONAL ARTS ACAD - K | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 11/17/2023 | DOER |  | DOER | 193778 | 0
17 | KBOG | FRIENDS OF CROWN HEIGHTS #3 | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN VARIOUS LOCATIONS THROUGHTOUT THE BUILDING | Construction | Complete | 7/22/2024 | IEH | 8/9/2024 | IEH | 418622 | 8863
18 | K066 | K771 SPED - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/5/2024 | DIIR | 55000
18 | K066 | P.S. 66 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500000 | 0
18 | K066 | K771 SPED - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
18 | K066 | P.S. 66 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/14/2021 | DOES |  | DOES | 118872 | 0
18 | K066 | P.S. 66 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/24/2024 | DOES | 5/1/2024 | DOES | 50832
18 | K068 | I.S. 68 - BROOKLYN | SCA IEH | PO18-REMOVE APPROXIMATELY 382 LF OF CONTAMINATED MOLD GROWTH ACM PIPE INSULATION LOCATED WITHIN THE | Construction | Complete | 5/15/2024 | IEH | 5/26/2024 | IEH | 136655 | 118805
18 | K068 | I.S. 68 - BROOKLYN | SCA IEH | PO18-ABATE ACM INSULATION FROM LINES SO GATE VALVES CAN BE RESTORED FOR BOTH COLD AND HOT WATER. LOC | Construction | Complete | 5/22/2024 | IEH | 9/4/2024 | IEH | 666 | 666
18 | K068 | I.S. 68 - BROOKLYN | SCA IEH | PO18-ABATE & REPLACE LOOSE/BROKEN/MISSING 9X9 TILE AT EXIT#9 OF THE AUDITORIUM INCLUDING THE STAGE L | Construction | Complete | 9/13/2024 | IEH | 9/27/2024 | IEH | 871 | 121
18 | K068 | I.S. 68 - BROOKLYN | SCA IEH | PO18-ABATE & REPLACE LOOSE/BROKEN 9X9 TILE IN ROOM 233. APPROXIMATELY 728SQFT THANK YOU, JAMES PELLE | Construction | In-Progress | 9/13/2024 | IEH |  | IEH | 961 | 386
18 | K068 | I.S. 68 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K068 | I.S. 68 - BROOKLYN | DOE - RESOA | FY19 RESO A LIBRARY UPGRADE | Construction | In-Progress | 2/21/2024 | DOER |  | DOER | 182730 | 0
18 | K068 | I.S. 68 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/15/2023 | DOER |  | DOER | 139736 | 0
18 | K068 | I.S. 68 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 7/29/2015 | DOES |  | DOES | 198919 | 0
18 | K068 | I.S. 68 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/1/2023 | DOES |  | DOES | 487922 | 0
18 | K114 | P.S. 114 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K114 | P.S. 114 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K114 | P.S. 114 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K114 | P.S. 114 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K114 | P.S. 114 - BROOKLYN | DOE - RESOA | FY16 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
18 | K114 | P.S. 114 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/9/2023 | 6/12/2023 | 9/6/2023 | 0 | 17769 | 17769
18 | K115 | P.S. 115 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/9/2021 | DOER |  | DOER | 163585 | 0
18 | K135 | P.S. 135 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PA SYSTEM UPGRADE | Scope | Complete | 9/19/2023 | 12/20/2023 | 12/21/2023 | 0 | 1813 | 1813
18 | K135 | P.S. 135 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES AND UNDERLAYMENT IN ROOMS 209,309,401,403 | Construction | Complete | 4/19/2024 | IEH | 6/24/2024 | IEH | 240186 | 215186
18 | K135 | P.S. 135 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0
18 | K135 | P.S. 135 - BROOKLYN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/29/2022 | DOER |  | DOER | 199729 | 0
18 | K135 | P.S. 135 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/12/2024 | DOER |  | DOER | 237713 | 0
18 | K135 | P.S. 135 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
18 | K135 | P.S. 135 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
18 | K135 | P.S. 135 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/21/2024 | DOES | 6/28/2024 | DOES | 65832 | 189
18 | K208 | P.S. 208 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K208 | P.S. 208 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 1/25/2024 | DOEL |  | DOEL | 55361 | 0
18 | K208 | P.S. 208 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
18 | K208 | P.S. 208 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/15/2024 | DOER |  | DOER | 500000 | 0
18 | K208 | P.S. 208 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/14/2022 | DOES |  | DOES | 60525 | 0
18 | K211 | I.S. 211 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE ENTIRE 3RD FL CORRIDOR AND RELATED STAIRCASES AND LANDINGS FLOOR TILES. THERE | Construction | Complete | 4/10/2024 | IEH | 4/24/2024 | IEH | 191399 | 191399
18 | K211 | I.S. 211 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K211 | I.S. 211 - BROOKLYN | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
18 | K211 | I.S. 211 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
18 | K211 | I.S. 211 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 8/1/2023 | DOES |  | DOES | 537351 | 0
18 | K211 | I.S. 211 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 7/5/2024 | DOES | 65832
18 | K219 | P.S. 219 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE / FY21 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 12/3/2021 | 2/6/2023 | 2/16/2023 | 0 | 46140 | 36031
18 | K219 | P.S. 219 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: ROOM 215- 400 SQFT ROOM 216- 704 SQFT ROOM 218 | Construction | Complete | 12/15/2022 | IEH | 9/25/2024 | IEH | 14386 | 1811
18 | K219 | P.S. 219 - BROOKLYN | SCA IEH | PO18-ABATE PIPE COVERING IN BASEMENT BOILER ROOM 3/4' COLD WATER LINE | Construction | Complete | 7/23/2024 | IEH | 7/26/2024 | IEH | 13050 | 1274
18 | K219 | LAMAD ACADEMY CHARTER SCHOOL | DIIT - RESOA | RESO A- FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 250000 | 0
18 | K219 | P.S. 219 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/2/2019 | DOER |  | DOER | 142925 | 0
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | SCA IEH | PO18-ABATE CEILING WALL & INSULATION IN ROOM 310 INSULATION & CONCRETE FILLER ASSUMED | Construction | Complete | 3/7/2024 | IEH | 4/9/2024 | IEH | 1799 | 1799
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | Fast Track Projects | PATH OF TRAVEL CTF ROOM CONVERSION / PATH OF TRAVEL CTF CHARTER MATCH ROOM CONVERSION / PATH OF TRAVEL CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 7/16/2024 | FTK |  | FTK | 158647 | 11180
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/1/2021 | DOER |  | DOER | 312274 | 0
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
18 | K232 | MIDDLE SCHL MEDIA, LAW AND FINE ARTS - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/16/2023 | DOES | 12/19/2023 | DOES | 422421
18 | K233 | NEW AMERICAN CHARTER SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
18 | K233 | P.S. 233 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 120000 | 0
18 | K233 | P.S. 233 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/26/2024 | DOES |  | DOES | 65832 | 0
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PA SYSTEM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PA SYSTEM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PA SYSTEM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K235 | P.S. 235 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 3/13/2020 | FTK |  | FTK | 384669 | 384668
18 | K235 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 162000 | 0
18 | K235 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K235 | P.S. 235 - BROOKLYN | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
18 | K235 | P.S. 235 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/10/2022 | DOES |  | DOES | 73047 | 0
18 | K242 | P.S. 235 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/4/2021 | EMER |  | EMER | 34244 | 11285
18 | K242 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K242 | LENOX ACADEMY M. S. 961 | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
18 | K242 | P.S. 235 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/28/2024 | DOES | 7/8/2024 | DOES | 65832
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/8/2023 | 6/9/2023 | 6/1/2023 | 0 | 16183 | 16183
18 | K244 | P.S. 244 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/8/2023 | 6/9/2023 | 5/22/2023 | 0 | 14656 | 14656
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 10/30/2023 | 3/4/2024 | 11/1/2023 | 0 | 2990 | 2990
18 | K244 | P.S. 244 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION ROOM 226, 130 L.F. PIPE INSULATION AND JOINTS IN CEILING/METAL JACKET ROO | Construction | Complete | 4/17/2024 | IEH | 6/8/2024 | IEH | 42258 | 730
18 | K244 | P.S. 244 - BROOKLYN | SCA IEH | PO18-ABATE APPROX. 60 FEET OF ACM PIPE COVER FROM A 2' STEAM CONDENSTE PIPE IN FAN ROOM AT TWO SEPER | Construction | In-Progress | 9/26/2024 | IEH |  | IEH | 0 | 0
18 | K244 | P.S. 244 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 276128 | 0
18 | K244 | P.S. 244 - BROOKLYN | DIIT - RESOA | FY15 RESO A IP SURVEILLANCE CAMERA INSTALLATION | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 271277 | 0
18 | K244 | P.S. 244 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K244 | P.S. 244 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/21/2021 | DOER |  | DOER | 188847 | 0
18 | K244 | P.S. 244 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/13/2024 | DOER |  | DOER | 300000 | 0
18 | K244 | P.S. 244 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 12/8/2021 | DOES |  | DOES | 59232 | 317139
18 | K244 | P.S. 244 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | Complete | 6/2/2023 | DOES | 7/25/2023 | DOES | 563135
18 | K244 | P.S. 244 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/17/2024 | DOES |  | DOES | 65832 | 0
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/14/2024 | DIIR | 8/23/2024 | DIIR | 110000
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/22/2022 | DOER |  | DOER | 316605 | 0
18 | K252 | MIDDLE SCHOOL FOR ART & PHILOS - K | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
18 | K268 | P.S. 268 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE ACM WRAPPING FOR COHORT REMEDIATION SHUT OFF VALVES CAN BE FOUND IN THE CRAWL | Construction | Complete | 6/27/2024 | IEH | 7/25/2024 | IEH | 22689 | 2186
18 | K268 | P.S. 268 - BROOKLYN | SCA IEH | PO18-INSULATION ABATEMENT THE PIPES ARE LOCATED IN THE CRAWL SPACE FOR RISERS THAT ARE FEEDING ROOMS | Construction | Complete | 7/30/2024 | IEH | 9/23/2024 | IEH | 1227 | 477
18 | K268 | P.S. 268 - BROOKLYN | DIIT - RESOA | FY09 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 193893 | 0
18 | K268 | P.S. 268 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 375000 | 0
18 | K268 | P.S. 268 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/11/2022 | DOES |  | DOES | 72429 | 0
18 | K272 | P.S. 272 - BROOKLYN | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Scope | Complete | 2/6/2023 | 6/7/2023 | 5/19/2023 | 0 | 21278 | 21278
18 | K272 | P.S. 272 - BROOKLYN | SCA IEH | PO18-REMOVE APPROX 6' OF ACM PIPE COVERING OFF LEAKING 3' WASTE LINE IN FAN ROOM. WILL BE PAINTED RE | Construction | Complete | 5/3/2024 | IEH | 5/5/2024 | IEH | 17772 | 17772
18 | K272 | P.S. 272 - BROOKLYN | SCA Furniture & Equipment | FY18 RESO A MOBILE SCIENCE LAB | F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K272 | P.S. 272 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K272 | P.S. 272 - BROOKLYN | DOE - RESOA | FY17 RESO A ELECTRICAL SYSTEMS | Construction | In-Progress | 12/22/2017 | DOER |  | DOER | 117988 | 0
18 | K272 | P.S. 272 - BROOKLYN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
18 | K272 | P.S. 272 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 5/3/2024 | DOES | 65832
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) CAFETERIA UPGRADE | Scope | Complete | 1/27/2023 | 5/30/2023 | 5/16/2023 | 0 | 8529 | 8529
18 | K276 | P.S. 276 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K276 | P.S. 276 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/25/2021 | DOER |  | DOER | 249133 | 0
18 | K276 | P.S. 276 - BROOKLYN | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/10/2023 | DOER |  | DOER | 105321 | 0
18 | K276 | P.S. 276 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 5/1/2024 | DOER |  | DOER | 175000 | 0
18 | K276 | P.S. 276 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
18 | K276 | P.S. 276 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/15/2020 | DOES |  | DOES | 117240 | 0
18 | K276 | P.S. 276 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 5/3/2024 | DOES | 65832 | 8732
18 | K279 | P.S. 279 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K279 | P.S. 279 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/27/2021 | DOES |  | DOES | 96964 | 0
18 | K279 | P.S. 279 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/16/2024 | DOES | 4/25/2024 | DOES | 65832 | 47
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 4/6/2021 | 7/21/2021 | 11/5/2021 | 0 | 22749 | 22749
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K285 | I.S. 285 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
18 | K285 | I.S. 285 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/31/2024 | DIIR | 8/9/2024 | DIIR | 100000
18 | K285 | I.S. 285 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/26/2024 | DOER |  | DOER | 211061 | 0
18 | K285 | I.S. 285 - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
18 | K285 | I.S. 285 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/8/2022 | DOES |  | DOES | 76791 | 0
18 | K285 | I.S. 285 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/23/2024 | DOES |  | DOES | 635985 | 0
18 | K366 | THE SCIENCE AND MEDICINE MIDDLE SCHOOL - K | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0
18 | K366 | THE SCIENCE AND MEDICINE MIDDLE SCHOOL - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/6/2024 | DOES | 5/10/2024 | DOES | 50832
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | FY25 RESO A ATHLETIC FIELDS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 1/5/2024 | 5/17/2024 | 5/14/2024 | 0 | 6775 | 6712
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 1/5/2024 | 3/8/2024 | 5/14/2024 | 0 | 12491 | 1500
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | Fast Track Projects | CTF ROOM CONVERSION / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 5/17/2024 | FTK |  | FTK | 1276912 | 558322
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | Fast Track Projects | LSP- GYM UPGRADE | Construction | In-Progress | 8/16/2022 | FTK |  | FTK | 515875 | 515843
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | Fast Track Projects | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/19/2023 | FTK |  | FTK | 26538 | 26509
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 191927 | 0
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 241000 | 0
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/6/2024 | DIIR | 7/17/2024 | DIIR | 50000 | 50000
18 | K415 | CULT ACAD ARTS AND SCI - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/7/2024 | DIIR | 7/17/2024 | DIIR | 54175 | 54175
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 4/13/2023 | DOER |  | DOER | 57318 | 0
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/7/2022 | DOER |  | DOER | 150483 | 0
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DOE - Skilled Trades | AUDITORIUM STAGE RIGGING | Construction | In-Progress | 12/9/2019 | DOES |  | DOES | 27299 | 10219
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | DOE - Skilled Trades | REPLACE (3) GALVANIZED WATER MAINS & CURB VALVES | Construction | In-Progress | 3/31/2022 | DOES |  | DOES | 246870 | 16921
18 | K416 | KURT HAHN EXPED LEARNING SCH - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
18 | K416 | IT TAKES A VILLAGE ACADEMY - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K500 | HS FOR MEDICAL PROFESSIONS - K | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/13/2023 | 10/12/2023 | 8/29/2023 | 0 | 32561 | 28291
18 | K500 | K753 SPED - BROOKLYN | Fast Track Projects | CTF ROOM CONVERSION / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | Complete | 6/3/2019 | FTK | 10/11/2021 | FTK | 761776 | 746720
18 | K500 | HS FOR MEDICAL PROFESSIONS - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/14/2024 | DOER |  | DOER | 1050000 | 0
18 | K501 | HS FOR MEDICAL PROFESSIONS - K | DOE - Skilled Trades | ATHLETIC FIELD | Construction | In-Progress | 10/5/2023 | DOES |  | DOES | 2375498 | 0
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/16/2023 | 3/15/2024 | 1/5/2024 | 0 | 34874 | 34874
18 | K515 | BROOKLYN BRIDGE ACADEMY - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K515 | BROOKLYN BRIDGE ACADEMY - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 150000
18 | K515 | ACAD FOR CONSERV & THE ENVIR - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 7/12/2024 | DIIR | 50000 | 50000
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 6/26/2024 | DIIR | 50000 | 50000
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K515 | ACAD FOR CONSERV & THE ENVIR - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
18 | K515 | VICTORY COLLEGIATE HS - K | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
18 | K515 | BROOKLYN COMMUNITY HIGH SCHOOL FOR EXCELLENCE AND EQUITY - K | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
18 | K515 | BROOKLYN COMMUNITY HIGH SCHOOL FOR EXCELLENCE AND EQUITY - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 2/3/2023 | DOES |  | DOES | 697978 | 0
18 | K515 | BROOKLYN COMMUNITY HIGH SCHOOL FOR EXCELLENCE AND EQUITY - K | DOE - Skilled Trades | BCC PLAN REVIEW FOR DSF WORK @ K515 | Construction | In-Progress | 3/3/2021 | DOES |  | DOES | 9617 | 0
18 | K835 | P.S. 235 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- SIDEWALK SHED @ K835 | Construction | In-Progress | 9/24/2024 | EMER |  | EMER |  | 0
18 | K855 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
18 | K855 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
18 | K855 | P.S. 235 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
18 | K860 | EAST BKLN COMMUNITY HS - K | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 4/26/2024 | IEH |  | IEH | 13588 | 1000
19 | K007 | P.S. 7 - BROOKLYN | SCA CIP RESOA | FY18 RESO A IP SECURITY CAMERAS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K013 | P.S. 13 - BROOKLYN | SCA IEH | PO18-ROOM 128, ABATE 70 SQ. FT. LOOSE, POPPING UP FLOOR TILES ROOM 131, ABATE 70 SQ. FT. LOOSE, POPP | Construction | In-Progress | 5/29/2024 | IEH |  | IEH | 138017 | 1316
19 | K013 | P.S. 13 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 350000 | 0
19 | K013 | P.S. 13 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/3/2024 | DOER |  | DOER | 498205 | 0
19 | K013 | P.S. 13 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 11/14/2022 | DOES |  | DOES | 1150474 | 0
19 | K013 | P.S. 13 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 191366 | 0
19 | K065 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ K065 | Construction | In-Progress | 4/13/2023 | EMER |  | EMER | 56326 | 45876
19 | K065 | P.S. 65 - BROOKLYN | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/19/2020 | FTK |  | FTK | 372163 | 300718
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
19 | K072 | EAST NEW YORK MIDDLE SCHOOL OF EXCELLENCE - K | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 4/8/2022 | DOER |  | DOER | 603731 | 0
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/16/2020 | DOES |  | DOES | 760283 | 0
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 9/1/2021 | DOES |  | DOES | 61744 | 304425
19 | K108 | P.S. 108 - BROOKLYN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/17/2024 | DOER |  | DOER | 175764 | 0
19 | K108 | P.S. 108 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
19 | K149 | P.S. 149 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 12/8/2021 | DOES |  | DOES | 60651 | 0
19 | K158 | P.S. 158 - BROOKLYN | Fast Track Projects | STRUCTURAL DEFECTS | Construction | In-Progress | 5/20/2016 | FTK |  | FTK | 640117 | 638757
19 | K158 | P.S. 158 - BROOKLYN | DOE - RESOA | FY18 RESO A AUDITORIUM SOUND SYSTEM UPGRADE | Construction | In-Progress | 3/19/2024 | DOER |  | DOER | 137950 | 0
19 | K158 | P.S. 158 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 1/30/2020 | DOER |  | DOER | 215711 | 0
19 | K158 | P.S. 158 - BROOKLYN | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/6/2023 | DOER |  | DOER | 70321 | 0
19 | K159 | P.S. 159 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 12/18/2019 | FTK |  | FTK | 359763 | 355958
19 | K159 | P.S. 159 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 9/22/2021 | DOES |  | DOES | 74254 | 0
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA IEH | PO18-SECTION OF CEILING HAS COME DOWN IN BASEMENT HALLWAY THE CEILING IS LISTED AS ACM IN AHERA BOOK | Construction | Complete | 7/17/2023 | IEH | 4/23/2024 | IEH | 334 | 334
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | SCA IEH | PO18-ABATE WALLS, FLOORS, AND CEILING FOR ACM LOCATION: LIBRARY AND ROOM 119A RA24 / /LLW#136169 | Construction | Complete | 4/2/2024 | IEH | 5/10/2024 | IEH | 102396 | 4472
19 | K166 | NEW DISTRICT HS IN BUILDING K166 - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 64000 | 0
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1200000 | 0
19 | K166 | VAN SICLEN COMMUNITY MIDDLE SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/13/2023 | DOES |  | DOES | 651994 | 0
19 | K171 | I.S. 171 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION OF FACADE | Construction | In-Progress | 2/4/2010 | EMER |  | EMER |  | 0
19 | K171 | I.S. 171 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- CRACKED DETERIORATED COPING STONES | Construction | In-Progress | 11/30/2022 | EMER |  | EMER | 288464 | 280427
19 | K171 | I.S. 171 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REMOVE APPROXIMATELY 6 SQUARE FEET OF FLOOR IN KITCHEN# 1 IDENTIFIED WITH RED | Construction | Complete | 9/4/2024 | IEH | 9/23/2024 | IEH | 1197 | 447
19 | K171 | I.S. 171 - BROOKLYN | DIIT - RESOA | FY18 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
19 | K171 | I.S. 171 - BROOKLYN | DOE - RESOA | FY16 RESO A GYMNASIUM | Construction | In-Progress | 7/22/2022 | DOER |  | DOER | 208177 | 0
19 | K171 | I.S. 171 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
19 | K171 | I.S. 171 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 152000 | 0
19 | K174 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 20 LINEAR FEET OF PIPE COVERING ACM FROM TWO STEAM RISERS LOCATED I | Construction | Complete | 8/23/2024 | IEH | 8/28/2024 | IEH | 14727 | 1011
19 | K174 | SCHOOL OF THE FUTURE BROOKLYN | Fast Track Projects | FY20 RESO A LIBRARY UPGRADE | Construction | In-Progress | 5/30/2022 | FTK |  | FTK | 53609 | 51352
19 | K174 | P.S. 174 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 8/8/2023 | DOEL | 3/25/2024 | DOEL | 54608 | 54608
19 | K174 | SCHOOL OF THE FUTURE BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/7/2023 | DOER |  | DOER | 241380 | 0
19 | K190 | P.S. 190 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE ROTTED WOOD FLOORS LOCATIONS: CLASSROOMS 507 (22'X39') AND 511 (24'X30') | Construction | Complete | 7/7/2023 | IEH | 4/23/2024 | IEH | 78 | 78
19 | K190 | P.S. 190 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 3/16/2021 | DOER |  | DOER | 207431 | 0
19 | K190 | P.S. 190 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 236903 | 0
19 | K202 | P.S. 202 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 1/20/2023 | DOER |  | DOER | 230140 | 0
19 | K202 | P.S. 202 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 7/12/2018 | DOES |  | DOES | 244560 | 0
19 | K202 | P.S. 202 - BROOKLYN | DOE - Skilled Trades | BOOSTER PUMP REPLACEMENT | Construction | In-Progress | 5/16/2024 | DOES |  | DOES | 84139 | 0
19 | K213 | P.S. 213 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
19 | K213 | P.S. 213 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/9/2024 | DOES | 5/15/2024 | DOES | 65832 | 7327
19 | K214 | P.S. 214 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE 560 SQ FT FLOOR IN ROOM 411 9X9 TILES DAMAGED DURING FLOOD | Construction | Complete | 6/7/2024 | IEH | 6/17/2024 | IEH | 57343 | 4357
19 | K214 | P.S. 214 - BROOKLYN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 179000 | 0
19 | K214 | P.S. 214 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 69820 | 0
19 | K214 | P.S. 214 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 10/12/2021 | DOES |  | DOES | 60651 | 0
19 | K218 | I.S. 218 - BROOKLYN | SCA Emergency Response | EARTHQUAKE REMEDIATION WORK - SWB @K218 | Construction | In-Progress | 4/8/2024 | EMER |  | EMER | 490110 | 296177
19 | K218 | I.S. 218 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE 9X9 FLOOR TILES IN CLASSROOM AND CLOSET LOCATION: ROOM 208 APPROX 1375 SQFT / | Construction | Complete | 3/18/2024 | IEH | 5/4/2024 | IEH | 52603 | 5181
19 | K218 | I.S. 218 - BROOKLYN | SCA IEH | PO18-ABATE EXPOSED ACM INSULATION APPROX. 10 LINEAR FEET | Construction | Complete | 8/8/2024 | IEH | 8/11/2024 | IEH | 17827 | 2676
19 | K218 | SCHOOL FOR CLASSICS HS - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0
19 | K218 | I.S. 218 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/6/2022 | DOER |  | DOER | 243818 | 0
19 | K218 | I.S. 218 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/27/2024 | DOES | 7/5/2024 | DOES | 65832
19 | K224 | P.S. 224 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 3/28/2019 | EMER |  | EMER | 117818 | 103678
19 | K224 | P.S. 224 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILE APPROX. 12SF LOCATED IN THE CAFETERIA | Construction | Complete | 7/23/2024 | IEH | 8/24/2024 | IEH | 41242 | 1781
19 | K224 | P.S. 224 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
19 | K224 | P.S. 224 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/10/2023 | DOER |  | DOER | 171834 | 0
19 | K224 | P.S. 224 - BROOKLYN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
19 | K224 | P.S. 224 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/3/2024 | DOES | 6/10/2024 | DOES | 65832 | 8568
19 | K260 | THE FRESH CREEK SCHOOL - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/2/2023 | DIIR |  | DIIR | 200000 | 0
19 | K260 | THE FRESH CREEK SCHOOL - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/2/2022 | DOES |  | DOES | 177123 | 0
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K273 | P.S. 273 - BROOKLYN | DIIT - RESOA | RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
19 | K273 | P.S. 273 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 515000 | 0
19 | K273 | P.S. 273 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 146301 | 0
19 | K273 | P.S. 273 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/29/2024 | DOES |  | DOES | 65832 | 0
19 | K290 | P.S. 290 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/16/2024 | DOER |  | DOER | 300000 | 0
19 | K290 | P.S. 290 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 105572 | 0
19 | K292 | I.S. 292 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN 1ST FLOOR CORRIDOR | Construction | Complete | 5/30/2024 | IEH | 6/5/2024 | IEH | 543 | 543
19 | K292 | I.S. 292 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 220000 | 0
19 | K292 | I.S. 292 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 121400 | 0
19 | K292 | I.S. 292 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/26/2023 | DOES |  | DOES | 595936 | 0
19 | K302 | VISTA ACADEMY - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES / FY20 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 2/25/2021 | 11/19/2021 | 10/5/2021 | 0 | 30613 | 30613
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA IEH | PO18-ABATE AND REMOVE PIPE INSULATION MARKED IN RED IN BOILER ROOM AT PUMP SET LESS THAN 10 LF | Construction | Complete | 8/21/2024 | IEH | 9/22/2024 | IEH | 13115 | 1564
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/18/2023 | DIIR | 5/7/2024 | DIIR | 110000 | 110000
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0
19 | K302 | VISTA ACADEMY - BROOKLYN | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 1/17/2022 | DOER |  | DOER | 42199 | 0
19 | K302 | VISTA ACADEMY - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/20/2023 | DOES |  | DOES | 309870 | 0
19 | K306 | P.S. 306 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROX. 10 FEET OF ACM STEAM PIPE INSULATION FROM 1-1/4' PIPE IN BASMENT CRAWL SP | Construction | Complete | 6/3/2024 | IEH | 8/1/2024 | IEH | 17470 | 1599
19 | K306 | P.S. 306 - BROOKLYN | DOE - RESOA | FY22 RESO A STEM LAB | Construction | In-Progress | 8/4/2023 | DOER |  | DOER | 174250 | 0
19 | K306 | P.S. 306 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
19 | K306 | P.S. 306 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75200 | 0
19 | K306 | P.S. 306 - BROOKLYN | DOE - Skilled Trades | ACE BOILER BURNER CONVERSIONS | Construction | In-Progress | 6/30/2021 | DOES |  | DOES | 2393506 | 0
19 | K306 | P.S. 306 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/15/2024 | DOES | 4/25/2024 | DOES | 65832 | 10753
19 | K328 | P.S. 328 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROX. 10 LINEAR FEET OF STEAM PIPE INSULATION FROM HORRIZONTAL 6' PIPES ABOUT 8 | Construction | Complete | 6/10/2024 | IEH | 9/14/2024 | IEH | 18394 | 2250
19 | K328 | P.S. 328 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 15 LINEAER FEET OF PIPE COVERING FROM PIPE AND VALVES# 38, 39 AND 4 | Construction | In-Progress | 9/23/2024 | IEH |  | IEH | 0 | 0
19 | K328 | P.S. 328 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 6/29/2022 | DOES |  | DOES | 333888 | 0
19 | K328 | P.S. 328 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/6/2024 | DOES | 5/16/2024 | DOES | 65832 | 10846
19 | K345 | P.S. 345 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE ACM 9X9 FLOOR TILES LOC: CLASSROOMS 110, 120, 130 EACH ROOM IS 33 X 26 WITH A | Construction | Complete | 3/20/2024 | IEH | 4/28/2024 | IEH | 156677 | 2961
19 | K345 | P.S. 345 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGED ACM TILE FLOOR IN KITCHEN APPROX 2' X 4' OF CRUMBLING TILE TILE AND C | Construction | Complete | 3/20/2024 | IEH | 4/19/2024 | IEH | 5906 | 931
19 | K345 | P.S. 345 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR FLOOR TILES IN AUDITORIUM | Construction | Complete | 6/27/2024 | IEH | 7/17/2024 | IEH | 39611 | 1497
19 | K345 | P.S. 345 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/28/2022 | DOER |  | DOER | 205858 | 0
19 | K345 | P.S. 345 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/12/2024 | DOER |  | DOER | 250000 | 0
19 | K345 | P.S. 345 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 5/3/2024 | DOES | 65832
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K346 | I.S. 452 | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/16/2023 | 10/12/2023 | 9/12/2023 | 0 | 22717 | 22717
19 | K346 | P.S. 346 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 8/6/2020 | FTK |  | FTK | 397822 | 383490
19 | K346 | P.S. 346 - BROOKLYN | DIIT - RESOA | RESO A- FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 105000 | 0
19 | K346 | P.S. 346 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
19 | K346 | I.S. 452 | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
19 | K346 | P.S. 346 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 859000 | 0
19 | K346 | P.S. 346 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 145000 | 0
19 | K346 | P.S. 346 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2017 | DOES |  | DOES | 75200 | 0
19 | K346 | P.S. 346 - BROOKLYN | DOE - Skilled Trades | PARTIAL ACCESSIBILITY - ELEVATORS | Construction | In-Progress | 6/1/2017 | DOES |  | DOES | 486102 | 0
19 | K346 | P.S. 346 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/8/2024 | DOES | 6/7/2024 | DOES | 65832 | 189
19 | K346 | I.S. 452 | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/25/2024 | DOES |  | DOES | 461151 | 0
19 | K420 | MULTICULTURAL HS - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 137113 | 0
19 | K420 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 10/1/2021 | DOER |  | DOER | 139367 | 0
19 | K420 | ACADEMY OF INNOV TECH - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 129000 | 0
19 | K420 | ACADEMY OF INNOV TECH - BROOKLYN | DOE - Skilled Trades | ENY AUDITORIUM UPGRADE | Construction | In-Progress | 10/16/2023 | DOES |  | DOES | 672083 | 0
19 | K420 | CYPRESS HILLS COLLEGIATE - K | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 1323692 | 0
19 | K420 | FRANKLIN K LANE CAMPUS YABC | DOE - Skilled Trades | CHARTER MATCH CAFETERIA SERVING LINE | Construction | In-Progress | 6/29/2019 | DOES |  | DOES | 243721 | 0
19 | K422 | ACAD. FOR YOUNG WRITERS - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 205000 | 0
19 | K422 | K053 SPED - BROOKLYN | DOE - RESOA | FY16 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 1/15/2018 | DOER |  | DOER | 131814 | 0
19 | K422 | ACAD. FOR YOUNG WRITERS - K | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
19 | K422 | SPRING CREEK COMMUNITY SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/5/2024 | DOES |  | DOES | 592370 | 0
19 | K422 | SPRING CREEK COMMUNITY SCHOOL | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/4/2024 | DOES | 6/14/2024 | DOES | 50832
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | Scope | Complete | 2/13/2023 | 5/12/2023 | 1/9/2024 | 0 | 54126 | 54126
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LEARNING GARDEN | Scope | In-Progress | 2/13/2023 | 5/15/2023 |  | 0 | 257 | 257
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LEARNING GARDEN | Design | PNS | PNS | PNS | PNS | 0 | 1029 | 1029
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LEARNING GARDEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LEARNING GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 2664 | 2664
19 | K435 | THOMAS JEFFERSON CAMPUS YABC | SCA Emergency Response | EMERGENCY STABILIZATION- UNSAFE FACADE CONDITIONS @ K435 | Construction | In-Progress | 8/1/2023 | EMER |  | EMER | 1416247 | 1250318
19 | K435 | FDNY - CAPTAIN VERNON A. RICHARDS HIGH SCHOOL FOR FIRE AND LIFE SAFETY-K | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 139930 | 0
19 | K435 | PERFORMING ARTS AND TECH. HS - K | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/11/2022 | DOER |  | DOER | 1138269 | 0
19 | K435 | PERFORMING ARTS AND TECH. HS - K | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 6/14/2021 | DOES |  | DOES | 202376 | 0
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | DOE - Skilled Trades | ATHLETIC FIELD | Construction | In-Progress | 4/30/2023 | DOES |  | DOES | 3494120 | 0
19 | K599 | EAST NY FAMILY ACAD. - K | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/18/2024 | DOES |  | DOES | 50832 | 0
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA IEH | PO18-PLEASE REMOVE PIPE COVERING AND SHIELD FROM PIPE IN CEILING OF ROOM# 109 THROUGH TO BASEMENT RO | Construction | Complete | 5/1/2024 | IEH | 5/14/2024 | IEH | 36672 | 26822
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA IEH | PO18-ROOM B07, ABATE 10 SQ. FT. WALL PLASTER AROUND THE WINDOW ROOM B04, ABATE 25 SQ. FT. WALL PLAST | Construction | Complete | 5/13/2024 | IEH | 6/5/2024 | IEH | 69865 | 2823
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA IEH | PO18-ABATE10-12 FEET OF WRAPPED PIPE INSULATION BASEMENT ROOM 36B CE LUIS CRUZ 718-647-5204 X6158 | Construction | Complete | 9/13/2024 | IEH | 9/15/2024 | IEH | 32559 | 3793
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA IEH | PO18-ADDITIONAL WORK IN THE BOILER ROOM | Construction | Complete | 9/18/2024 | IEH | 9/22/2024 | IEH | 399 | 399
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 3/4/2022 | DOES |  | DOES | 631884 | 0
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 12/1/2022 | DOES |  | DOES | 478803 | 0
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
19 | K660 | WILLIAM MAXWELL VOC HS - K | Fast Track Projects | CTF ROOM CONVERSIONS/PARTITIONING | Construction | Complete | 6/2/2017 | FTK | 9/6/2019 | FTK | 2166601 | 2100220
19 | K660 | WILLIAM MAXWELL VOC HS - K | Fast Track Projects | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/28/2023 | FTK |  | FTK | 101795 | 96015
19 | K660 | WILLIAM MAXWELL VOC HS - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/26/2023 | DOES |  | DOES | 471086 | 0
19 | K660 | WILLIAM MAXWELL VOC HS - K | DOE - Skilled Trades | FIRE PUMP SYSTEM REPLACEMENT | Construction | In-Progress | 1/3/2024 | DOES |  | DOES | 98631 | 703344
19 | K667 | M.S. 935 - BROOKLYN | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 371000 | 0
19 | K667 | P.S. 938 - BROOKLYN | DOE - RESOA | FY25 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
19 | K798 | K004 SPED - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 252708 | 0
19 | K857 | K036 SPED - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/7/2022 | DOES |  | DOES | 173373 | 0
19 | K872 | I.S. 364 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 7/11/2024 | IEH |  | IEH | 12399 | 0
19 | K932 | PASSAGES ACADEMY | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/14/2024 | IEH | 8/21/2024 | IEH | 12689 | 0
19 | KAKM | IMAGINE ME LEADERSHIP CHARTER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 633000 | 0
19 | KAMH | COLLEGIATE ACADEMY FOR MATH AND PERSONAL AWARENESS CHARTER SCHOOL - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 250000 | 0
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K048 | P.S. 48 - BROOKLYN | SCA IEH | PO18-KINDLY ABATE 3 AREAS OF CRACKED STEAM LINE INSULATION AND 30 SQUARE FEET OF FLOORING IN THE CAF | Construction | Complete | 4/4/2024 | IEH | 5/25/2024 | IEH | 21561 | 3500
20 | K048 | P.S. 48 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
20 | K048 | P.S. 48 - BROOKLYN | DOE - Skilled Trades | DOMESTIC WATER HEATER | Construction | In-Progress | 7/6/2020 | DOES |  | DOES | 42566 | 0
20 | K048 | P.S. 48 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/23/2022 | DOES |  | DOES | 51304 | 0
20 | K062 | I.S. 62 - BROOKLYN | SCA IEH | PO18-ABATE EXITING CEILING TILE AND PIPE INSULATION IN 1ST FLOOR GYMNASIUM ADJACENT TO THE MAIN LOBB | Construction | Complete | 3/16/2024 | IEH | 7/9/2024 | IEH | 26670 | 1891
20 | K062 | I.S. 62 - BROOKLYN | SCA IEH | PO18-ABATE & REPAIR FALLING CEILING TILE IN ROOM B-30 ( SPACE ID : 1030A) ROOM WAS SHUT DOWN | Construction | Complete | 6/20/2024 | IEH | 6/22/2024 | IEH | 30804 | 3049
20 | K062 | I.S. 62 - BROOKLYN | SCA IEH | PO18-ABATE ACM ON LISTED AREA PLASTER CEILING IN STUDENT CAFETERIA SPACE ID: 1500 | Construction | Complete | 6/28/2024 | IEH | 6/30/2024 | IEH | 36541 | 1616
20 | K062 | I.S. 62 - BROOKLYN | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 9/11/2023 | DOER |  | DOER | 414117 | 0
20 | K062 | I.S. 62 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 3/20/2023 | DOES |  | DOES | 728007 | 0
20 | K062 | I.S. 62 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/8/2024 | DOES |  | DOES | 628935 | 0
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/28/2022 | 4/28/2022 | 6/28/2022 | 0 | 22927 | 22927
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/6/2023 | 4/9/2024 | 3/26/2024 | 0 | 16185 | 16185
20 | K069 | P.S. 69 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/31/2024 | DIIR | 7/9/2024 | DIIR | 200000 | 200000
20 | K069 | P.S. 69 - BROOKLYN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 4/29/2024 | DOER |  | DOER | 79073 | 0
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/13/2018 | 8/30/2019 | 2/12/2020 | 0 | 46351 | 46351
20 | K102 | P.S. 102 - BROOKLYN | SCA IEH | PO18-DRILLING IS NEEDED FOR NEW ELECTRICAL WORK TO BE DONE IN KITCHEN | Construction | In-Progress | 6/4/2024 | IEH |  | IEH | 1170 | 595
20 | K102 | P.S. 102 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/18/2024 | DIIR | 6/18/2024 | DIIR | 150000 | 150000
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY23 RESO A OUTDOOR STEM CENTER | Scope | Complete | 2/15/2023 | 5/16/2023 | 2/9/2024 | 0 | 57066 | 57066
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A OUTDOOR STEM CENTER | Scope | Complete | 2/22/2023 | 5/23/2023 | 4/3/2024 | 0 | 1125 | 1125
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K104 | P.S. 104 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE AND REPLACE THIRD FLOOR HALLWAY FLOOR TILES APPROX 2100 SQUARE FEET AHERA = YES | Construction | In-Progress | 8/28/2023 | IEH |  | IEH | 742 | 167
20 | K104 | P.S. 104 - BROOKLYN | SCA IEH | PO18-TEST / ABATE WALLS TO INSTALL ANCHORS INTO FOUR LOCATIONS TOTAL : BASEMENT @ DRINKING FOUNTAINS | Construction | Complete | 3/18/2024 | IEH | 4/13/2024 | IEH | 16671 | 16671
20 | K104 | P.S. 104 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE FLOOR TILES AND WALLS IN CLOSETS IN ROOMS 122 AND 124. SCA PREVIOUSLY COMPLETED F | Construction | Complete | 4/15/2024 | IEH | 6/8/2024 | IEH | 21980 | 21980
20 | K104 | P.S. 104 - BROOKLYN | SCA IEH | PO18-ABATE DAMAGED WALL MATERIAL FROM ROOMS 122, 124, AND 126 REMOVE ALL DAMAGED MATERIAL DOWN TO TH | Construction | Complete | 4/22/2024 | IEH | 5/5/2024 | IEH | 47488 | 35738
20 | K104 | P.S. 104 - BROOKLYN | SCA IEH | PO18-ABATE DAMAGED WALL MATERIAL FROM ROOMS 120,228 REMOVE ALL DAMAGED MATERIAL DOWN TO THE BRICK AN | Construction | Complete | 5/15/2024 | IEH | 6/12/2024 | IEH | 42433 | 2323
20 | K104 | P.S. 104 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER AND CEILING PLASTER FOR ROOMS: 328,322,228,111,128,222,316,309, A | Construction | Complete | 6/27/2024 | IEH | 8/15/2024 | IEH | 63099 | 2717
20 | K104 | P.S. 104 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/1/2023 | DOER |  | DOER | 505348 | 0
20 | K104 | P.S. 104 - BROOKLYN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 1/27/2023 | DOER |  | DOER | 500000 | 0
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 4/19/2024 | 7/22/2024 |  | 0 | 18003 | 434
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 4/19/2024 | 7/22/2024 |  | 0 | 0 | 0
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K105 | P.S. 105 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K105 | P.S. 105 - BROOKLYN | Fast Track Projects | LSP - REPLACE DOMESTIC WATER HEATER | Construction | In-Progress | 5/23/2018 | FTK |  | FTK | 149854 | 134334
20 | K105 | P.S. 105 - BROOKLYN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/11/2020 | DOER |  | DOER | 477149 | 0
20 | K105 | P.S. 105 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 274857 | 0
20 | K112 | P.S. 112 - BROOKLYN | DIIT - RESOA | FY21 RESO A (MA) TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K112 | P.S. 112 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/5/2024 | DOES | 4/19/2024 | DOES | 65832 | 12164
20 | K127 | P.S. 127 - BROOKLYN | SCA IEH | PO18-REMOVE DOORS AND FRAMES UNDER ABATEMENT ABATEMENT IS AT ROOMS 110, 110, 200 SEE CUSTODIAN FOR L | Construction | Complete | 6/30/2022 | IEH | 9/24/2024 | IEH | 8754 | 679
20 | K127 | P.S. 127 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
20 | K127 | P.S. 127 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
20 | K127 | P.S. 127 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/6/2022 | DOES |  | DOES | 213538 | 0
20 | K127 | P.S. 127 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/23/2024 | DOES |  | DOES | 65832 | 0
20 | K160 | P.S. 160 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR WALL AND CEILING PLASTER IN BASEMENT-CAFETERIA NEAR EXIT #11 | Construction | Complete | 2/15/2024 | IEH | 6/24/2024 | IEH | 1171 | 596
20 | K160 | P.S. 160 - BROOKLYN | SCA IEH | PO18-TEST AND ABATE WALL, CEILLING AND BRICK MORTAR FOR ACM SPACE ID 1004 SCHOOL KITCHEN AND 1004B S | Construction | In-Progress | 6/4/2024 | IEH |  | IEH | 1692 | 942
20 | K160 | P.S. 160 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 55000 | 0
20 | K160 | P.S. 160 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
20 | K160 | P.S. 160 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K160 | P.S. 160 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/29/2022 | DOES |  | DOES | 77473 | 0
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL GYMANSIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL GYMANSIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL GYMANSIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL GYMANSIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/10/2019 | 3/6/2020 | 5/3/2021 | 0 | 6638 | 6638
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Scope | Complete | 7/14/2023 | 11/15/2023 | 10/13/2023 | 0 | 1369 | 1369
20 | K163 | P.S. 748 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/5/2019 | EMER |  | EMER | 50890 | 50890
20 | K163 | P.S. 748 - BROOKLYN | SCA IEH | PO18-TEST PLASTER FOR ACM @ ROOMS 401 AND ROOM 402 | Construction | Complete | 6/17/2024 | IEH | 6/18/2024 | IEH | 3762 | 3762
20 | K163 | P.S. 748 - BROOKLYN | SCA IEH | PO18-ABATE WALL PLASTER IN ROOMS 401, 402 | Construction | Complete | 6/14/2024 | IEH | 6/16/2024 | IEH | 38022 | 1727
20 | K163 | P.S. 748 - BROOKLYN | Fast Track Projects | LSP GYM FLOOR REPLACEMENT | Construction | In-Progress | 9/11/2023 | FTK |  | FTK | 178945 | 152710
20 | K163 | P.S. 163 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 4/3/2023 | DOEL | 7/25/2023 | DOEL | 76231 | 76231
20 | K163 | P.S. 748 - BROOKLYN | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/8/2020 | DOES |  | DOES | 1243 | 0
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING PLASTER IN AUDITORIUM | Construction | Complete | 3/25/2024 | IEH | 4/7/2024 | IEH | 17685 | 17685
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-REPAIR APPROXIMATELY 23 SF OF DAMAGED/ACM PLASTER IN ROOM# 402 | Construction | Complete | 5/24/2024 | IEH | 5/26/2024 | IEH | 29990 | 3448
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE PLASTER ON WALL AND CEILING AT LISTED LOCATIONS: 101,106,108,110,111,205,309,405A,407,409 | Construction | Complete | 7/10/2024 | IEH | 8/6/2024 | IEH | 70049 | 2064
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE WALL PLASTER AND CEILING PLASTER AT LOCATIONS : 407A, 410 AND 301 | Construction | In-Progress | 7/18/2024 | IEH |  | IEH | 1541 | 791
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE DAMAGED CEILING PLASTER IN AUDITORIUM LOBBY BASEMENT PHOTOS AND LAS ATTACHED. 55X12FT / 6 | Construction | Complete | 8/7/2024 | IEH | 8/10/2024 | IEH | 9741 | 791
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE AND TAKE WALLS DOWN TO THE BRICK IN THE FOLLOWING LOCATIONS: 212, 310 | Construction | Complete | 8/13/2024 | IEH | 8/22/2024 | IEH | 20921 | 272
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DAMAGED FLOORS TILES IN ROOMS 205, 208, 210, 210A, 307 AND 311 | Construction | Complete | 8/15/2024 | IEH | 9/25/2024 | IEH | 986 | 236
20 | K164 | P.S. 164 - BROOKLYN | SCA IEH | PO18-TAKE WALLS DOWN TO THE BRICK IN THE FOLLOWING LOCATIONS: 302, 312, 406A, 406B, 410A, STAIRCASE | Construction | Complete | 8/16/2024 | IEH | 9/23/2024 | IEH | 38568 | 818
20 | K164 | K077 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
20 | K164 | P.S. 164 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K164 | P.S. 164 - BROOKLYN | DOE - RESOA | FY10 RESO A- AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 35000 | 0
20 | K164 | P.S. 164 - BROOKLYN | DOE - RESOA | FY11 RESO A FLOORS | Construction | PNS | PNS | PNS | PNS | DOER | 96830 | 0
20 | K164 | P.S. 164 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/26/2022 | DOES |  | DOES | 59823 | 0
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K170 | P.S. 170 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K170 | P.S. 170 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION ON LEAKING WATER MAIN LOCATED IN BOILER | Construction | In-Progress | 2/2/2024 | IEH |  | IEH | 1433 | 658
20 | K170 | P.S. 170 - BROOKLYN | DIIT - RESOA | FY21 RESO A (MA) TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K176 | P.S. 176 - BROOKLYN | SCA IEH | PO18-REMOVE 70 LINEAR FEET OF ACM PIPE INSULATION IN MAIN CAFETERIA CEILING. PIPE INSULATION IN POO | Construction | Complete | 4/5/2024 | IEH | 6/2/2024 | IEH | 35354 | 27809
20 | K176 | P.S. 176 - BROOKLYN | SCA IEH | PO18-ABATE THE FALLING CEILING PLASTER AROUND THE 4 INCH WASTE LINE IN 4TH FLOOR GIRLS BATHROOM ROOM | Construction | Complete | 7/1/2024 | IEH | 7/24/2024 | IEH | 18949 | 754
20 | K176 | P.S. 176 - BROOKLYN | SCA IEH | PO18-ABATE AND DRILL HALLWAY WALLS BEHIND BUBBLERS BY LISTED ROOMS : 5TH FL WALL BEHIND BUBBLER BY | Construction | Complete | 8/23/2024 | IEH | 9/29/2024 | IEH | 1088 | 338
20 | K176 | P.S. 176 - BROOKLYN | SCA IEH | PO18-77/20K176/ ABATE AND REPAIR ACM PLASTER APPROX: 400 SF PEELING / CHIPPING / PLASTER ON CEILING | Construction | Complete | 8/29/2024 | IEH | 8/31/2024 | IEH | 23055 | 1141
20 | K176 | P.S. 176 - BROOKLYN | DIIT - RESOA | RESO A (MA) TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K176 | P.S. 176 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/12/2019 | DOER |  | DOER | 140583 | 0
20 | K176 | P.S. 176 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 6/28/2024 | 10/30/2024 |  | 0 | 20962 | 1853
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 8/30/2024 | 12/3/2024 |  | 0 | 760 | 760
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 3039 | 3039
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 60 | 60
20 | K179 | P.S. 179 - BROOKLYN | SCA IEH | PO18-TEST WALL, COLUMN, SOFFIT, BEAM AND CEILING PLASTER FOR ABESTOS IN ROOM 104 | Construction | In-Progress | 2/2/2024 | IEH |  | IEH | 6403 | 103
20 | K179 | P.S. 179 - BROOKLYN | SCA IEH | PO18-ABATE & REPAIR DAMAGED ACM PIPE INS IN CAFETERIA BY GIRLS BR (SPACE ID 2001) DAMAGED ACM PIPE I | Construction | Complete | 8/12/2024 | IEH | 8/17/2024 | IEH | 17505 | 833
20 | K179 | P.S. 179 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 8/18/2023 | DOEL | 4/29/2024 | DOEL | 83618 | 83618
20 | K180 | K231 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/1/2023 | DIIR |  | DIIR | 130000 | 0
20 | K180 | K231 SPED - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K180 | P.S. 180 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 950000 | 0
20 | K180 | K231 SPED - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/26/2024 | DOER |  | DOER | 253550 | 0
20 | K180 | P.S. 180 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 7/27/2023 | DOER |  | DOER | 175383 | 0
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K185 | P.S. 185 - BROOKLYN | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/8/2020 | FTK |  | FTK | 3623540 | 3522752
20 | K185 | P.S. 185 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500000 | 0
20 | K186 | P.S. 186 - BROOKLYN | SCA IEH | PO18-TEST / ABATE FALLING PLASTER IN STAIRCASE 6&7 1ST FLOOR APPROX 2SQ FT | Construction | In-Progress | 12/26/2023 | IEH |  | IEH | 2806 | 206
20 | K186 | P.S. 186 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE APPROX 4 SQ FT OF DAMAGED FLOOR TILE IN ROOM 303 DAMAGE WAS CAUSED BY A STEAM | Construction | Complete | 7/18/2024 | IEH | 8/6/2024 | IEH | 956 | 381
20 | K186 | P.S. 186 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
20 | K186 | P.S. 186 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 8/1/2023 | DOEL |  | DOEL | 57206 | 57206
20 | K186 | P.S. 186 - BROOKLYN | DOE - RESOA | FY21 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/8/2024 | DOER |  | DOER | 55621 | 0
20 | K186 | P.S. 186 - BROOKLYN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/26/2023 | DOER |  | DOER | 426105 | 0
20 | K186 | P.S. 186 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
20 | K186 | P.S. 186 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
20 | K192 | P.S. 192 - BROOKLYN | Fast Track Projects | LSP REPLACE LEAKING PVI DOMESTIC WATER HEATER | Construction | In-Progress | 9/23/2020 | FTK |  | FTK | 185119 | 163976
20 | K192 | P.S. 192 - BROOKLYN | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 9/29/2020 | FTK |  | FTK | 1131454 | 1101047
20 | K192 | P.S. 192 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K192 | P.S. 192 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/28/2021 | DOES |  | DOES | 67952 | 0
20 | K192 | P.S. 192 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 4/20/2023 | DOES |  | DOES | 610711 | 0
20 | K200 | P.S. 200 - BROOKLYN | SCA Emergency Response | SIDEWALK BRIDGING | Construction | Complete | 5/16/2013 | EMER | 5/7/2024 | EMER |  | 0
20 | K200 | P.S. 200 - BROOKLYN | SCA Emergency Response | EMERGENCY-DETERIORATED MASONRY | Construction | Complete | 1/6/2017 | EMER | 5/7/2024 | EMER | 422266 | 422266
20 | K200 | P.S. 200 - BROOKLYN | SCA IEH | PO18-ABATE FLOOR TILES IN ROOM 427. LOOSE. ROOM HAS BEEN CLOSED UNTIL FURTHER NOTICE | Construction | Complete | 3/1/2024 | IEH | 6/24/2024 | IEH | 19491 | 4253
20 | K200 | P.S. 200 - BROOKLYN | SCA IEH | PO18-ABATE & REPLACE - 1002 STAIRWELL. 9X9 FLOOR TILES ARE BROKEN 132 SQF -CLASS ROOM 2105. 9X | Construction | Complete | 7/30/2024 | IEH | 8/7/2024 | IEH | 961 | 961
20 | K200 | P.S. 200 - BROOKLYN | DIIT - RESOA | RESO A (MA) TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K200 | P.S. 200 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 5/19/2023 | DOEL | 1/12/2024 | DOEL | 85687 | 85687
20 | K200 | P.S. 200 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 7/19/2023 | DOEL | 6/28/2024 | DOEL | 212709 | 132709
20 | K200 | P.S. 200 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/27/2023 | DOER |  | DOER | 128937 | 0
20 | K200 | P.S. 200 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/11/2024 | DOER |  | DOER | 296545 | 0
20 | K200 | P.S. 200 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
20 | K200 | P.S. 200 - BROOKLYN | DOE - RESOA | FY25 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
20 | K200 | P.S. 200 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 65832 | 0
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP RESOA | FY18 RESO A ROOM CONVERSION | Scope | Complete | 1/16/2018 | 4/16/2018 | 3/1/2018 | 0 | 21766 | 21766
20 | K201 | I.S. 201 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE 9 X 9 FLOOR TILES IN KITCHEN STORAGE ROOM 107 136 SQ FT FLOOR IS DETERIORATED | Construction | Complete | 8/1/2024 | IEH | 8/13/2024 | IEH | 25688 | 957
20 | K201 | I.S. 201 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 200000 | 0
20 | K201 | I.S. 201 - BROOKLYN | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 6/2/2021 | DOES |  | DOES | 115955 | 0
20 | K201 | I.S. 201 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/9/2024 | DOES |  | DOES | 65832 | 0
20 | K204 | P.S. 204 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE 9X9 ASBESTOS TILES IN ROOM 101 THE FLOOR IS CRACKING IN SOME SPOTS CAUSING A TRIP | Construction | Complete | 7/31/2024 | IEH | 8/31/2024 | IEH | 25630 | 867
20 | K204 | P.S. 204 - BROOKLYN | DOE - RESOA | FY25 RESO A PHONE UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
20 | K204 | P.S. 204 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
20 | K204 | P.S. 204 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
20 | K204 | P.S. 204 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/13/2022 | DOES |  | DOES | 73215 | 0
20 | K204 | P.S. 204 - BROOKLYN | Trust For Public Land | FY19 RESO A PLAYGROUND | Construction | Complete | 6/22/2023 | TPL | 6/10/2024 | TPL | 740000 | 2800000
20 | K205 | P.S. 205 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
20 | K205 | P.S. 205 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K205 | P.S. 205 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 55000 | 0
20 | K205 | P.S. 205 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/20/2023 | DOER |  | DOER | 4207 | 0
20 | K205 | P.S. 205 - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
20 | K220 | I.S. 220 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 8/16/2023 | DOES |  | DOES | 342811 | 0
20 | K223 | I.S. 223 - BROOKLYN | SCA IEH | PO18-TEST / ABATE PIPE INSULATION ON 2 IN STEAM LINE IN BASEMENT CAFETERIA NEEDED FOR REPAIR OF LEAK | Construction | Complete | 4/3/2024 | IEH | 4/6/2024 | IEH | 15757 | 15757
20 | K223 | I.S. 223 - BROOKLYN | Fast Track Projects | FY19 RESO A TREE GUARDS | Construction | PNS | FTK | FTK | FTK | FTK | 28000 | 0
20 | K223 | URBAN ASSEMBLY SCHOOL FOR LEADERSHIP AND EMPOWERMENT | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 65000 | 0
20 | K223 | I.S. 223 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
20 | K223 | I.S. 223 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/2/2020 | DOES |  | DOES | 593370 | 0
20 | K223 | I.S. 223 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 8/17/2022 | DOES |  | DOES | 61693 | 0
20 | K223 | I.S. 223 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 619382 | 0
20 | K223 | I.S. 223 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/9/2024 | DOES |  | DOES | 526472 | 0
20 | K227 | I.S. 227 - BROOKLYN | DOE - RESOA | FY17 RESO A ELECTRICAL UPGRADES | Construction | In-Progress | 10/1/2018 | DOER |  | DOER | 171911 | 0
20 | K227 | I.S. 227 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 5/7/2021 | DOES |  | DOES | 525582 | 0
20 | K227 | I.S. 227 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 12/19/2023 | DOES |  | DOES | 582257 | 0
20 | K229 | P.S. 229 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/1/2023 | 6/2/2023 | 5/15/2023 | 0 | 16363 | 16363
20 | K229 | P.S. 229 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 7/11/2024 | DIIR | 82000 | 82000
20 | K229 | P.S. 229 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
20 | K229 | P.S. 229 - BROOKLYN | DOE - RESOA | FY20 RESO A MULTIPURPOSE ROOM UPGRADE | Construction | In-Progress | 3/23/2024 | DOER |  | DOER | 122990 | 0
20 | K247 | P.S. 247 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K247 | P.S. 247 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K247 | P.S. 247 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K247 | P.S. 247 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K247 | P.S. 247 - BROOKLYN | DOE - RESOA | FY09 RESO A ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | DOER | 120000 | 0
20 | K247 | P.S. 247 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
20 | K247 | P.S. 247 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 800000 | 0
20 | K247 | P.S. 247 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 10/31/2023 | DOES |  | DOES | 65832 | 0
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 1/19/2023 | 5/4/2023 | 4/20/2023 | 0 | 16156 | 16156
20 | K259 | I.S. 259 - BROOKLYN | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/9/2021 | DOER |  | DOER | 1338397 | 0
20 | K259 | I.S. 259 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/15/2021 | DOER |  | DOER | 264124 | 0
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/13/2023 | 6/14/2023 | 7/6/2023 | 0 | 8552 | 8552
20 | K264 | P.S. 264 - BROOKLYN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/29/2022 | DOER |  | DOER | 195341 | 0
20 | K310 | P.S. 310 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
20 | K314 | P.S. 503 - BROOKLYN | Fast Track Projects | LSP FY16 RESO A EXTERIOR PLAYGROUND LIGHTING | Construction | In-Progress | 8/5/2021 | FTK |  | FTK | 258948 | 237751
20 | K314 | P.S. 506 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 340000 | 0
20 | K314 | P.S. 503 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 176000 | 0
20 | K314 | P.S. 503 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 4/14/2023 | DOES |  | DOES | 2594445 | 0
20 | K314 | P.S. 503 - BROOKLYN | Trust For Public Land | FY23 RESO A PLAYGROUND UPGRADE | Construction | Complete | 10/12/2023 | TPL | 6/14/2024 | TPL | 3550000 | 2311036
20 | K331 | I.S. 30 - BROOKLYN | SCA CIP RESOA | RESO A LIBRARY UPGRADE | Scope | Complete | 1/31/2023 | 6/1/2023 | 11/15/2023 | 0 | 12426 | 12426
20 | K331 | I.S. 30 - BROOKLYN | DIIT - RESOA | RESO A (MA) TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K331 | I.S. 30 - BROOKLYN | DOE - RESOA | RESO A FENCING | Construction | In-Progress | 10/19/2023 | DOER |  | DOER | 232966 | 0
20 | K331 | I.S. 30 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/30/2024 | DOES | 5/7/2024 | DOES | 50832
20 | K404 | K000 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 9/13/2024 | IEH | 9/25/2024 | IEH | 12235 | 60
20 | K445 | NEW UTRECHT HS - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: RMS: 530, 517, 519, 521, 532 AND 403 MM24 | Construction | Complete | 3/18/2024 | IEH | 6/27/2024 | IEH | 13557 | 2675
20 | K445 | NEW UTRECHT HS - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 9/14/2022 | DOES |  | DOES | 66214 | 0
20 | K453 | DISTRICT 20 PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/9/2024 | IEH | 11220 | 6220
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K485 | TELECOM. ARTS & TECH. HS - K | Fast Track Projects | LSP REPLACE BURNER CONTROLS | Construction | In-Progress | 8/15/2019 | FTK |  | FTK | 107580 | 93129
20 | K485 | TELECOM. ARTS & TECH. HS - K | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 908995 | 0
20 | K485 | TELECOM. ARTS & TECH. HS - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 12/23/2022 | DOES |  | DOES | 460774 | 0
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K486 | I.S. 187 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
20 | K486 | I.S. 187 - BROOKLYN | DOE - RESOA | FY14 RESO A MULTIMEDIA ART STUDIO | Construction | PNS | PNS | PNS | PNS | DOER | 46747 | 0
20 | K486 | I.S. 187 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/11/2019 | DOER |  | DOER | 182222 | 0
20 | K486 | I.S. 187 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/13/2022 | DOES |  | DOES | 282097 | 0
20 | K486 | I.S. 187 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 12/5/2023 | DOES |  | DOES | 681745 | 0
20 | K486 | I.S. 187 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/30/2024 | DOES |  | DOES | 586127 | 0
20 | K490 | FORT HAMILTON HS - K | SCA IEH | PO18-REPAIR STEAM LEAK IN RISERS IN ROOMS 140 AND 255 PIPES ARE IN THE WALL AHERA BOOK IS FROM 20015 | Construction | Complete | 12/13/2023 | IEH | 12/29/2023 | IEH | 4664 | 664
20 | K490 | FORT HAMILTON HS - K | SCA IEH | PO18-ABATE AND REPAIR ACOUSTICAL WALL PLASTER IN AUDITORIUM BALCONY | Construction | Complete | 4/5/2024 | IEH | 5/9/2024 | IEH | 466 | 466
20 | K490 | FORT HAMILTON HS - K | DOE - RESOA | FY24 RESO A ATHLETIC FIELDS | Construction | Complete | 3/5/2024 | DOER | 4/3/2024 | DOER | 96000 | 34493
20 | K490 | FORT HAMILTON HS - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/12/2023 | DOES |  | DOES | 801995 | 0
20 | K491 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 50832 | 0
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA IEH | PO18-PLEASE REPLACE 9X9 ACM FLOOR TILES IN THE FOLLOWING CLASSROOMS 147 -1270 SQ FT , 243-750 SQ FT | Construction | Complete | 1/16/2024 | IEH | 4/25/2024 | IEH | 322754 | 3962
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA IEH | PO18-PLEASE TEST FLOOR FOR ACM / INSTALLING FLOOR DRAIN IN ROOM 325 HYDRPONICS ROOM. SCHOOL WILL FUN | Construction | Complete | 3/5/2024 | IEH | 4/23/2024 | IEH | 1095 | 1095
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA IEH | PO18-ABATE ADDITIONAL PIPE INSULATION IN CEILING OF ROOM 133 NEEDED BY PLUBERS FOR REPAIRS TO BE MAD | Construction | Complete | 4/3/2024 | IEH | 4/7/2024 | IEH | 22244 | 22244
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DIIT - RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/5/2023 | DOER |  | DOER | 228430 | 0
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 12/16/2022 | DOES |  | DOES | 748519 | 0
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DOE - Skilled Trades | BCC PLAN REVIEW FOR DSF WORK @ K505 | Construction | In-Progress | 3/4/2021 | DOES |  | DOES | 24042 | 0
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | DOE - Skilled Trades | CONDENSATE TANK REPLACEMENT | Construction | In-Progress | 8/21/2023 | DOES |  | DOES | 335456 | 0
20 | K521 | P.S. 160 - BROOKLYN | SCA IEH | PO18-REPAIR / REPLACE FALLEN CEILING TILES IN ROOMS 414 AND CO2 HALLWAY 5TH FL TILES HAVE FALLEN | Construction | Complete | 10/2/2023 | IEH | 10/30/2023 | IEH | 989 | 239
20 | K521 | P.S. 160 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K613 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/26/2024 | DOES | 7/3/2024 | DOES | 50832
20 | K664 | DISTRICT 20 PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/4/2024 | IEH | 11615 | 6240
20 | K678 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/21/2023 | DOES |  | DOES | 65832 | 0
20 | K695 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/13/2024 | DOES |  | DOES | 65832 | 0
20 | K746 | SUNSET SCHOOL OF CULTURAL LEARNING - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 5/16/2024 | DIIR | 100000 | 100000
20 | K746 | SUNSET SCHOOL OF CULTURAL LEARNING - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
20 | K746 | MS 936 ARTS OFF 3RD - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/22/2024 | DOES | 6/27/2024 | DOES | 50832
20 | K747 | DISTRICT 20 PRE-K CENTER | SCA IEH | PO18-ABATE CEILING IN 2ND FLOOR HALLWAY AND CEILING IN ROOM 121 DAMAGE TO POPCORN CEILING DUE TO WAT | Construction | Complete | 3/28/2024 | IEH | 4/6/2024 | IEH | 18500 | 13600
20 | K747 | DISTRICT 20 PRE-K CENTER | SCA IEH | PO18-ABATE WALLS AND CEILINGS. ACOUSTAL CEILING PLASTER LISTED AS ASSUMED | Construction | Complete | 6/13/2024 | IEH | 6/15/2024 | IEH | 23140 | 16496
20 | K747 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/20/2024 | DOES |  | DOES | 65832 | 0
20 | K768 | P.S. 112 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/1/2024 | DOES | 4/5/2024 | DOES | 65832 | 6857
20 | K780 | DISTRICT 20 PRE-K CENTER | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 7/3/2024 | DOEL |  | DOEL | 86450 | 0
20 | K780 | DISTRICT 20 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/3/2024 | DOES |  | DOES | 65832 | 0
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Scope | Complete | 5/5/2022 | 9/2/2022 | 8/30/2022 | 0 | 15618 | 15618
20 | K807 | P.S. 163 - BROOKLYN | DIIT - RESOA | FY21 RESO A (MA) TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
20 | K807 | P.S. 163 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/30/2022 | DOER |  | DOER | 481535 | 0
20 | K807 | P.S. 163 - BROOKLYN | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 3/20/2024 | DOER |  | DOER | 232249 | 0
20 | K807 | P.S. 163 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/18/2024 | DOES | 4/25/2024 | DOES | 50832
20 | K940 | I.S. 30 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/17/2024 | IEH | 5/3/2024 | IEH | 12987 | 8518
20 | K971 | P.S. 971 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- FALLING MASONRY | Construction | In-Progress | 11/28/2022 | EMER |  | EMER | 373959 | 344950
20 | K971 | P.S. 971 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 7/5/2024 | DIIR | 300000
20 | K971 | P.S. 971 - BROOKLYN | DOE - RESOA | FY23 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
20 | K971 | P.S. 971 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION | Scope | Complete | 2/7/2023 | 6/7/2023 | 7/17/2024 | 0 | 15206 | 650
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 6/3/2024 | 9/4/2024 | 9/12/2024 | 0 | 297 | 297
21 | K043 | I.S. 98 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 514634 | 0
21 | K043 | I.S. 98 - BROOKLYN | DOE - RESOA | FY12 RESO A GYMNASIUM SUPPLEMENTAL COOLING | Construction | In-Progress | 6/15/2016 | DOER |  | DOER | 3887 | 0
21 | K043 | I.S. 98 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
21 | K043 | I.S. 98 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/27/2023 | DOES |  | DOES | 737629 | 0
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | Scope | Complete | 2/18/2022 | 7/6/2022 | 12/6/2022 | 0 | 179913 | 117778
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | Scope | Complete | 9/5/2023 | 12/7/2023 | 8/27/2024 | 0 | 0 | 0
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K090 | P.S. 90 - BROOKLYN | Fast Track Projects | FY18 RESO A LIBRARY UPGRADES | Construction | In-Progress | 7/3/2018 | FTK |  | FTK | 115400 | 108319
21 | K090 | P.S. 90 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 333323 | 0
21 | K090 | P.S. 90 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/17/2023 | DOER |  | DOER | 890488 | 0
21 | K090 | P.S. 90 - BROOKLYN | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 460000 | 0
21 | K090 | P.S. 90 - BROOKLYN | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL ROOFTOP GARDEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE / FY21 RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/17/2021 | 3/2/2022 | 2/28/2022 | 0 | 32731 | 32731
21 | K095 | P.S. 95 - BROOKLYN | SCA IEH | PO18-ABATE PLASTER CEILING ON SOFFIT IN THE NORTH PLAY YARD CAFETERIA THIS IS TO FACILITATE THE REPA | Construction | Complete | 3/26/2024 | IEH | 4/9/2024 | IEH | 1242 | 1242
21 | K095 | P.S. 95 - BROOKLYN | SCA IEH | PO18-ABATE 3X3 BUBBLING PLASTER IN HALLWAY BY ROOM 234 THIS IS NON ACM ACCORDING TO AHERA BOOK. CAN | Construction | Complete | 4/11/2024 | IEH | 9/4/2024 | IEH | 155 | 155
21 | K095 | P.S. 95 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 443306 | 0
21 | K095 | P.S. 95 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/8/2024 | DIIR | 5/17/2024 | DIIR | 100000
21 | K095 | P.S. 95 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K095 | P.S. 95 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/5/2024 | DOES |  | DOES | 641547 | 0
21 | K096 | SUCCESS ACADEMY CHARTER SCHOOL - BENSONHURST - NEW YORK 3 | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
21 | K096 | SUCCESS ACADEMY CHARTER SCHOOL - BENSONHURST - NEW YORK 3 | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
21 | K096 | SUCCESS ACADEMY CHARTER SCHOOL - BENSONHURST - NEW YORK 3 | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K096 | I.S. 96 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 600000 | 0
21 | K096 | I.S. 96 - BROOKLYN | DOE - RESOA | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 12/15/2018 | DOER |  | DOER | 8367 | 0
21 | K096 | I.S. 96 - BROOKLYN | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/7/2024 | DOER |  | DOER | 114806 | 0
21 | K096 | I.S. 96 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 12/15/2020 | DOES |  | DOES | 112296 | 0
21 | K096 | I.S. 96 - BROOKLYN | DOE - Skilled Trades | CHARTER MATCH FLOOR REPLACEMENT | Construction | In-Progress | 9/1/2024 | DOES |  | DOES | 340000 | 0
21 | K097 | P.S. 97 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE TWO 16 FEET ROWS OF FLOOR OUTLETS AND ONE 2 FEET OF OUTLETS OLD COMPUTER ROOM | Construction | In-Progress | 9/23/2024 | IEH |  | IEH | 0 | 0
21 | K097 | P.S. 97 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 420000 | 0
21 | K097 | P.S. 97 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 8/7/2023 | DOEL | 11/20/2023 | DOEL | 161968 | 161968
21 | K097 | P.S. 97 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
21 | K097 | P.S. 97 - BROOKLYN | DOE - RESOA | RESO A HYDROPONICS LAB | Construction | In-Progress | 4/15/2024 | DOER |  | DOER | 108641 | 0
21 | K097 | P.S. 97 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
21 | K099 | P.S. 99 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE (27) EXISTING BULLETIN BOARDS IN SCHOOL CORRIDORS(3,2 &1) INSTALL (27) NEW BUL | Construction | Complete | 8/28/2023 | IEH | 8/29/2024 | IEH | 42211 | 2199
21 | K099 | P.S. 99 - BROOKLYN | SCA IEH | PO18-PLEASE REPLACE 9X9 ABESTOS TILES FIRST FLOOR CORRIDOR NUMEROUS TILES HAVE BECOME LOOSE DUE TO B | Construction | Complete | 4/8/2024 | IEH | 6/13/2024 | IEH | 1141 | 566
21 | K099 | P.S. 99 - BROOKLYN | SCA IEH | PO18-ABATE PLASTER CEILING AND WALLS IN ROOMS 107, 217, 319, AND THE PRINCIPALS OFFICE AS PER AHAERA | Construction | Complete | 4/25/2024 | IEH | 5/5/2024 | IEH | 98669 | 98669
21 | K099 | P.S. 99 - BROOKLYN | SCA IEH | PO18-TOUCH UP FLACKY PAINT ON ACM PLASTER @ VARIOUS LOCATIONS SCA CONTRACTOR TO ADDRESS | Construction | Complete | 8/28/2024 | IEH | 8/30/2024 | IEH | 65707 | 362
21 | K099 | P.S. 99 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
21 | K099 | P.S. 99 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 128824 | 0
21 | K100 | P.S. 100 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
21 | K100 | P.S. 100 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
21 | K101 | P.S. 101 - BROOKLYN | SCA CIP RESOA | RESO A IPDVS SYSTEM | Scope | Complete | 5/8/2023 | 9/7/2023 | 5/16/2023 | 0 | 909 | 909
21 | K101 | P.S. 101 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE TILES AND SUB FLOORING IN ROOMS 327 (OLD ROOM 312) | Construction | Complete | 3/18/2024 | IEH | 8/13/2024 | IEH | 47290 | 41138
21 | K101 | P.S. 101 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
21 | K101 | P.S. 101 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
21 | K101 | P.S. 101 - BROOKLYN | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/31/2023 | DOER |  | DOER | 371675 | 0
21 | K101 | P.S. 101 - BROOKLYN | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/7/2024 | DOER |  | DOER | 38992 | 0
21 | K101 | P.S. 101 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 5/2/2022 | DOES |  | DOES | 62704 | 0
21 | K121 | P.S. 121 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
21 | K121 | P.S. 121 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
21 | K121 | P.S. 121 - BROOKLYN | DOE - RESOA | FY10 RESO A BALLFIELD | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K128 | P.S. 128 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 4/25/2022 | EMER |  | EMER | 120029 | 82633
21 | K128 | P.S. 128 - BROOKLYN | SCA IEH | PO18-ABATE ROOF BY DRAIN OVER ROOM 408 APPROX 100 SQ FT | Construction | Complete | 2/29/2024 | IEH | 5/7/2024 | IEH | 5331 | 5331
21 | K128 | P.S. 128 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR DAMAGED PLASTER WALLS IN CLASSROOM 307 APPROX 25 SF. DAMAGE FROM WATER PENETRA | Construction | Complete | 4/8/2024 | IEH | 4/10/2024 | IEH | 16796 | 16796
21 | K128 | P.S. 128 - BROOKLYN | SCA IEH | PO18-ABATE ACM DAMAGED PLASTER WALLS IN ROOM 305C IDF ROOM. AROUND WINDOW ASSUMED ACM APPROX 30 SF D | Construction | Complete | 4/22/2024 | IEH | 6/22/2024 | IEH | 32017 | 21672
21 | K128 | P.S. 128 - BROOKLYN | SCA IEH | PO18-ABATE DAMAGED PLASTER LOCATED IN CLASSROOM 106 ID: 2106 APPROX: 10 SF PIECES ARE LOOSE AND READ | Construction | Complete | 8/22/2024 | IEH | 8/24/2024 | IEH | 19854 | 12154
21 | K128 | P.S. 128 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K128 | P.S. 128 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
21 | K128 | P.S. 128 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 7/11/2024 | 11/12/2024 |  | 0 | 22942 | 1325
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 9/11/2024 | 12/12/2024 |  | 0 | 0 | 0
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K153 | P.S. 153 - BROOKLYN | SCA IEH | PO18-REMOVE APPROX. 4 FEET OF ACM PIPE COVER FROM A 3' WATER MAIN VALVE. LOCATED IN BASEMENT ROOM | Construction | Complete | 8/5/2024 | IEH | 8/14/2024 | IEH | 15830 | 9130
21 | K153 | P.S. 153 - BROOKLYN | SCA IEH | PO18-CORE DRILL APPROX 32 HOLES IN KITCHEN AND CAFETERIA CEILING IS CONFIRMED ACM PICTURES AND MARKI | Construction | Complete | 8/14/2024 | IEH | 9/14/2024 | IEH | 32470 | 447
21 | K153 | P.S. 153 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/17/2023 | DOES |  | DOES | 65832 | 0
21 | K177 | P.S. 177 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
21 | K177 | P.S. 177 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 10/20/2023 | DOEL | 4/12/2024 | DOEL | 88969 | 88969
21 | K177 | P.S. 177 - BROOKLYN | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Scope | Complete | 4/7/2021 | 8/6/2021 | 9/28/2021 | 0 | 18907 | 18907
21 | K188 | P.S. 188 - BROOKLYN | Fast Track Projects | EMERGENCY AUDITORIUM FLOOR | Construction | In-Progress | 9/5/2018 | FTK |  | FTK | 23085 | 22680
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/18/2019 | DOER |  | DOER | 305968 | 0
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY20 RESO A MEDIA CENTER | Construction | In-Progress | 7/6/2021 | DOER |  | DOER | 235429 | 0
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 1/15/2020 | DOER |  | DOER | 112280 | 147493
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 8/23/2021 | DOER |  | DOER | 262767 | 0
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 98180 | 0
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 4/23/2024 | DOER |  | DOER | 5637 | 0
21 | K188 | P.S. 188 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 7/20/2023 | DOER |  | DOER | 98395 | 0
21 | K188 | P.S. 188 - BROOKLYN | DOE - Skilled Trades | WASTE LINE REPLACEMENT | Construction | In-Progress | 2/26/2021 | DOES |  | DOES | 84300 | 0
21 | K199 | P.S. 199 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K199 | P.S. 199 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
21 | K199 | P.S. 199 - BROOKLYN | DOE - Skilled Trades | DOMESTIC WATER HEATER | Construction | In-Progress | 10/1/2020 | DOES |  | DOES | 43017 | 0
21 | K212 | P.S. 212 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR/ SUB-FLOOR IN ROOM 257 PRINCIPALS OFFICE PRICIPALS FLOOR TO REMOVE TRIP | Construction | In-Progress | 8/8/2024 | IEH |  | IEH | 13679 | 604
21 | K212 | P.S. 212 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR 6LF OF PIPE INSULATION ON GYM CEILING BEHIND GATE. SPACE ID 4361: GYM. APPROXI | Construction | In-Progress | 9/26/2024 | IEH |  | IEH | 0 | 0
21 | K212 | P.S. 212 - BROOKLYN | Fast Track Projects | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 40000 | 0
21 | K212 | P.S. 212 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/24/2024 | DIIR | 140000 | 1175
21 | K212 | P.S. 212 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/22/2021 | DOER |  | DOER | 130357 | 0
21 | K212 | P.S. 212 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/3/2020 | DOES |  | DOES | 344539 | 0
21 | K215 | P.S. 215 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION IN STUDENT BATHROOMS AND STAIRCASE C AND REINSULATE BOYS BATHROOM 119 AP | Construction | Complete | 7/15/2024 | IEH | 9/14/2024 | IEH | 35578 | 1208
21 | K215 | P.S. 215 - BROOKLYN | Fast Track Projects | LSP REPLACE PVI DOMESTIC WATER HEATER | Construction | In-Progress | 12/23/2019 | FTK |  | FTK | 180512 | 166657
21 | K215 | P.S. 215 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K215 | K231 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/1/2023 | DIIR |  | DIIR | 95000 | 0
21 | K215 | P.S. 215 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K215 | P.S. 215 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 328159 | 0
21 | K215 | P.S. 215 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/14/2022 | DOES |  | DOES | 57392 | 0
21 | K215 | P.S. 215 - BROOKLYN | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 12/16/2022 | DOES |  | DOES | 447218 | 0
21 | K216 | P.S. 216 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 8/8/2023 | DOEL | 1/12/2024 | DOEL | 121239 | 121239
21 | K216 | P.S. 216 - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM RENOVATION | Construction | In-Progress | 7/28/2022 | DOER |  | DOER | 145172 | 0
21 | K216 | P.S. 216 - BROOKLYN | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 4/30/2023 | DOER |  | DOER | 47411 | 0
21 | K216 | P.S. 216 - BROOKLYN | DOE - RESOA | FY23 RESO A KITCHEN UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 152267 | 0
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | Complete | 7/7/2023 | DOER | 9/5/2023 | DOER | 157135 | 7258
21 | K216 | P.S. 216 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/1/2024 | DOES | 4/19/2024 | DOES | 65832 | 21340
21 | K225 | K771 SPED - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 3/22/2024 | DIIR | 250000
21 | K225 | K771 SPED - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 3/22/2024 | DIIR | 145000 | 269
21 | K225 | K771 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
21 | K225 | P.S. 225 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
21 | K225 | P.S. 225 - BROOKLYN | DOE - RESOA | FY05 RESO A TRASH COMPACTOR | Construction | PNS | PNS | PNS | PNS | DOER | 71023 | 0
21 | K225 | K771 SPED - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 4/1/2024 | DOER |  | DOER | 181030 | 0
21 | K225 | P.S. 225 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 900000 | 0
21 | K225 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
21 | K225 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 315000 | 0
21 | K225 | P.S. 225 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/31/2022 | DOES |  | DOES | 273464 | 0
21 | K226 | P.S. 226 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION IN 3RD FLOOR STAIRCASE G HALF LANDING APPROX. 60LF AND ROOM 35 | Construction | Complete | 3/22/2024 | IEH | 5/16/2024 | IEH | 49834 | 746
21 | K226 | P.S. 226 - BROOKLYN | SCA IEH | PO18-ABATE TILES IN ROOM 264/264A TILES ARE LISTED AS ACM IN THE AHERA BOOK CURRENTLY 12 TILES POPPE | Construction | Complete | 7/26/2024 | IEH | 7/28/2024 | IEH | 22330 | 1389
21 | K226 | P.S. 226 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE DETERIORATED 9X9 FLOOR TILE IN ROOM 254, ENTIRE ROOM | Construction | In-Progress | 9/10/2024 | IEH |  | IEH | 968 | 218
21 | K226 | P.S. 226 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 55000 | 0
21 | K228 | I.S. 228 - BROOKLYN | SCA IEH | PO18-TEST / ABATE STUDENT CAFETERIA CEILING AT EXIT 12 | Construction | In-Progress | 12/20/2023 | IEH |  | IEH | 9343 | 1718
21 | K228 | I.S. 228 - BROOKLYN | Fast Track Projects | LSP FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 10/11/2023 | FTK |  | FTK | 135000 | 134953
21 | K228 | I.S. 228 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 95000 | 0
21 | K228 | I.S. 228 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K228 | I.S. 228 - BROOKLYN | DOE - RESOA | FY09 RESO A CONTAINERIZATION | Construction | PNS | PNS | PNS | PNS | DOER | 151175 | 0
21 | K228 | I.S. 228 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/24/2022 | DOES |  | DOES | 222926 | 0
21 | K237 | THE ACADAMY OF TALENTED SCHOLARS - K | DIIT - RESOA | FY15 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
21 | K237 | THE ACADAMY OF TALENTED SCHOLARS - K | DIIT - RESOA | FY16 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K237 | THE ACADAMY OF TALENTED SCHOLARS - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/25/2024 | DIIR | 4/22/2024 | DIIR | 50000 | 50000
21 | K237 | THE ACADAMY OF TALENTED SCHOLARS - K | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
21 | K238 | P.S. 238 - BROOKLYN | SCA IEH | PO18-PERFORM SUPPLEMENTAL QC TESTING ON 9X9 ACM FLOOR TILES IF NEEDED ABATE AND REPLACE THE TILES I | Construction | Complete | 7/18/2024 | IEH | 9/27/2024 | IEH | 841 | 91
21 | K238 | K231 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/1/2023 | DIIR |  | DIIR | 65000 | 0
21 | K238 | K231 SPED - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K238 | P.S. 238 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
21 | K238 | P.S. 238 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 5/24/2023 | DOEL | 7/24/2023 | DOEL | 63500 | 23436
21 | K238 | P.S. 238 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 9/11/2023 | DOEL | 1/15/2024 | DOEL | 58378 | 58378
21 | K238 | P.S. 238 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/13/2022 | DOES |  | DOES | 866375 | 0
21 | K238 | P.S. 238 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 3/4/2024 | DOES |  | DOES | 539217 | 1246
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K239 | I.S. 239 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ K239 | Construction | In-Progress | 6/27/2023 | EMER |  | EMER | 40350 | 36510
21 | K239 | I.S. 239 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
21 | K239 | I.S. 239 - BROOKLYN | DOE - RESOA | FY17 RESO A ROOM CONVERSION | Construction | In-Progress | 12/31/2018 | DOER |  | DOER | 161728 | 0
21 | K239 | I.S. 239 - BROOKLYN | DOE - RESOA | FY17 RESO A HYDROPONICS ROOM | Construction | In-Progress | 7/5/2019 | DOER |  | DOER | 281782 | 0
21 | K239 | I.S. 239 - BROOKLYN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 180038 | 0
21 | K239 | I.S. 239 - BROOKLYN | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/19/2024 | DOER |  | DOER | 96647 | 0
21 | K239 | I.S. 239 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/28/2022 | DOES |  | DOES | 170867 | 0
21 | K253 | P.S. 253 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 12/18/2019 | FTK |  | FTK | 437149 | 437092
21 | K253 | P.S. 253 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 60765 | 0
21 | K253 | P.S. 253 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 12/28/2020 | DOES |  | DOES | 124986 | 0
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/9/2020 | 9/16/2021 | 9/13/2021 | 0 | 14204 | 14204
21 | K281 | I.S. 281 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/20/2024 | DIIR | 5/25/2024 | DIIR | 125000 | 125000
21 | K281 | I.S. 281 - BROOKLYN | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 7/25/2022 | DOER |  | DOER | 86625 | 0
21 | K281 | I.S. 281 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 146273 | 0
21 | K281 | I.S. 281 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
21 | K281 | I.S. 281 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 1/7/2021 | DOES |  | DOES | 103718 | 0
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/25/2022 | 9/26/2022 | 10/5/2022 | 0 | 23190 | 23190
21 | K288 | P.S. 288 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
21 | K288 | P.S. 288 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 750000 | 0
21 | K288 | P.S. 288 - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 7/1/2022 | DOER |  | DOER | 198726 | 0
21 | K288 | P.S. 288 - BROOKLYN | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | In-Progress | 9/16/2021 | DOER |  | DOER | 176351 | 0
21 | K288 | P.S. 288 - BROOKLYN | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
21 | K288 | P.S. 288 - BROOKLYN | DOE - RESOA | RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/24/2024 | DOER |  | DOER | 404822 | 0
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSION | Scope | In-Progress | 4/19/2024 | 8/19/2024 |  | 0 | 12137 | 1419
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | In-Progress | 9/27/2024 | 12/26/2024 |  | 0 | 0 | 0
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/2/2023 | 3/7/2024 | 11/15/2023 | 0 | 2835 | 2835
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSIONS/PARTITIONING / PATH OF TRAVEL RESO A ROOM CONVERSIONS/PARTITIONING | Scope | Complete | 3/23/2023 | 11/30/2023 | 10/19/2023 | 0 | 16576 | 16576
21 | K303 | I.S. 303 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION IN ROOM #110 | Construction | Complete | 7/29/2024 | IEH | 8/2/2024 | IEH | 16880 | 9630
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 400000
21 | K303 | I.S. 303 - BROOKLYN | DOE - RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/12/2021 | DOER |  | DOER | 383887 | 0
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/16/2023 | DOER |  | DOER | 216806 | 0
21 | K303 | I.S. 303 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
21 | K303 | I.S. 303 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/5/2022 | DOER |  | DOER | 175829 | 0
21 | K303 | I.S. 303 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 5/16/2024 | DOER |  | DOER | 250000 | 0
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DOE - RESOA | RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DOE - RESOA | RESO A PHONE SYSTEM & WIRING UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 532185 | 0
21 | K303 | R. CARSON SCL OF COASTAL ST-K | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
21 | K303 | I.S. 303 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/18/2023 | DOES |  | DOES | 449988 | 0
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Scope | Complete | 11/18/2020 | 5/28/2021 | 9/17/2021 | 0 | 18278 | 18278
21 | K329 | P.S. 329 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
21 | K329 | P.S. 329 - BROOKLYN | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
21 | K329 | P.S. 329 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 195000 | 0
21 | K329 | P.S. 329 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/10/2024 | DOES | 6/14/2024 | DOES | 65832
21 | K370 | K370 SPED - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K370 | K370 SPED - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K370 | K370 SPED - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K370 | K370 SPED - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K370 | K370 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/7/2023 | DIIR | 5/16/2024 | DIIR | 175000 | 175000
21 | K370 | K370 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1425000 | 0
21 | K400 | LEADERS HIGH SCHOOL - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY21 RESO A LIBRARY UPGRADE | Scope | Complete | 10/7/2021 | 2/11/2022 | 1/13/2022 | 0 | 28239 | 28239
21 | K400 | LIFE ACADEMY H.S. FILM & MUSIC - K | DIIT - RESOA | FY17 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 40000 | 0
21 | K400 | INTERNATIONAL HIGH SCHOOL - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0
21 | K400 | HIGH SCHOOL OF SPORTS MGMT- K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0
21 | K400 | HIGH SCHOOL OF SPORTS MGMT- K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/12/2024 | DIIR | 4/22/2024 | DIIR | 100000
21 | K400 | LEADERS HIGH SCHOOL - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
21 | K400 | LEADERS HIGH SCHOOL - K | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/5/2022 | DOER |  | DOER | 96930 | 0
21 | K400 | LEADERS HIGH SCHOOL - K | DOE - RESOA | FY21 RESO A ROOM RENOVATION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
21 | K400 | KINGSBOROUGH EARLY COLLEGE SCHOOL | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
21 | K400 | HIGH SCHOOL OF SPORTS MGMT- K | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 43151 | 0
21 | K400 | LIFE ACADEMY H.S. FILM & MUSIC - K | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/14/2024 | DOER |  | DOER | 550281 | 0
21 | K400 | INTERNATIONAL HIGH SCHOOL - K | DOE - Skilled Trades | STAGE RIGGING & DRAPERY MODERNIZATION | Construction | In-Progress | 3/2/2021 | DOES |  | DOES | 180912 | 0
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | RESO A ATHLETIC FIELD | Scope | Complete | 8/1/2023 | 10/31/2023 | 8/7/2024 | 0 | 88113 | 82135
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD | Scope | In-Progress | 7/15/2024 | 10/15/2024 |  | 0 | 44 | 44
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD | Design | PNS | PNS | PNS | PNS | 0 | 178 | 178
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K401 | LIFE ACADEMY H.S. FILM & MUSIC - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD | CM,F&E | PNS | PNS | PNS | PNS | 0 | 1656 | 1656
21 | K401 | LEADERS HIGH SCHOOL - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/18/2024 | DIIR | 6/11/2024 | DIIR | 50000 | 50000
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE / FY20 RESO A CAFETERIA UPGRADE | Scope | Complete | 11/18/2020 | 11/4/2021 | 11/17/2021 | 0 | 34171 | 34171
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 35000 | 0
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 9/19/2022 | DOES |  | DOES | 66214 | 0
21 | K411 | ABRAHAM LINCOLN HS - BROOKLYN | DOE - RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | Construction | In-Progress | 2/1/2023 | DOER |  | DOER | 153043 | 0
21 | K525 | EDWARD R. MURROW HS - K | Fast Track Projects | IDA GYM FLOOR REPLACEMENT @ K525 | Construction | In-Progress | 5/12/2022 | FTK |  | FTK | 1130122 | 956303
21 | K525 | EDWARD R. MURROW HS - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/5/2024 | DIIR | 8/9/2024 | DIIR | 247000
21 | K525 | EDWARD R. MURROW HS - K | DOE - RESOA | FY14 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/25/2014 | DOER |  | DOER | 82000 | 0
21 | K525 | EDWARD R. MURROW HS - K | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 210000 | 0
21 | K525 | EDWARD R. MURROW HS - K | DOE - Skilled Trades | BCC PLAN REVIEW FOR DSF WORK @ K525 | Construction | In-Progress | 3/2/2021 | DOES |  | DOES | 12566 | 0
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/7/2018 | 3/14/2019 | 3/22/2019 | 0 | 94333 | 94333
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA IEH | PO18-ACM 9X9 TILES REMOVAL GROUND FLOOR CORRIDOR APPROX. 8,000 SQFT MUSIC WING FOYER EXIT #7 ACM 9X9 | Construction | Complete | 3/20/2024 | IEH | 6/29/2024 | IEH | 100876 | 100876
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 1/4/2022 | DOER |  | DOER | 54647 | 0
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 6/15/2022 | DOER |  | DOER | 51194 | 0
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/5/2024 | DOER |  | DOER | 850 | 0
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 11/4/2023 | DOER |  | DOER | 50000 | 0
21 | K540 | JOHN DEWEY HS - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/1/2024 | DOES |  | DOES | 772243 | 0
21 | K541 | JOHN DEWEY HS - BROOKLYN | DOE - RESOA | FY21 RESO A ATHLETIC FIELD UPGRADE | Construction | In-Progress | 4/5/2021 | DOER |  | DOER | 2138054 | 0
21 | K620 | WILLIAM E. GRADY VOC HS - K | Fast Track Projects | FY21 RESO A CTF ROOM CONVERSION | Construction | In-Progress | 5/14/2024 | FTK |  | FTK | 50372 | 10322
21 | K620 | WILLIAM E. GRADY VOC HS - K | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
21 | K620 | WILLIAM E. GRADY VOC HS - K | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 3/2/2022 | DOER |  | DOER | 115345 | 0
21 | K620 | WILLIAM E. GRADY VOC HS - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/22/2023 | DOES |  | DOES | 358758 | 0
21 | K662 | BROOKLYN DAILY DISCOVERY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/30/2024 | DOES |  | DOES | 65832 | 0
21 | K687 | BROOKLYN DAILY DISCOVERY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/13/2024 | DOES |  | DOES | 50832 | 0
21 | K721 | BKLYN STUDIO SEC. SCL - BROOKLYN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
21 | K721 | BKLYN STUDIO SEC. SCL - BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
21 | K721 | BKLYN STUDIO SEC. SCL - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
21 | K721 | BKLYN STUDIO SEC. SCL - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
21 | K722 | K721 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A KITCHEN UPGRADE | Scope | Complete | 2/2/2022 | 6/17/2022 | 8/10/2022 | 0 | 30561 | 30561
21 | K722 | K721 SPED - BROOKLYN | Fast Track Projects | LSP- INTERIOR SPACES | Construction | In-Progress | 10/21/2022 | FTK |  | FTK | 200531 | 200529
21 | K722 | K721 SPED - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
21 | K722 | K721 SPED - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 7/27/2024 | DIIR | 9/30/2024 | DIIR | 125000
21 | K722 | K721 SPED - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 4/26/2021 | DOER |  | DOER | 139947 | 0
21 | K722 | K721 SPED - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/3/2024 | DOES |  | DOES | 65832 | 0
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/8/2024 | DIIR | 5/23/2024 | DIIR | 100000 | 100000
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
21 | K728 | LIBERATION DIPLOMA PLUS H.S. - K | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
21 | K787 | BROOKLYN DAILY DISCOVERY PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/6/2023 | DOES |  | DOES | 50832 | 0
22 | K014 | I.S. 14 - BROOKLYN | DOE - RESOA | FY13 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 63000 | 0
22 | K014 | I.S. 14 - BROOKLYN | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 7/16/2021 | DOER |  | DOER | 291871 | 0
22 | K014 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0
22 | K014 | I.S. 14 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
22 | K014 | I.S. 14 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/8/2023 | DOES |  | DOES | 362752 | 0
22 | K014 | I.S. 14 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 2/28/2024 | DOES |  | DOES | 573921 | 7365
22 | K042 | THE JOAN SNOW PRE-K CENTER | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K042 | THE JOAN SNOW PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/17/2024 | DOES |  | DOES | 65832 | 0
22 | K052 | P.S. 52 - BROOKLYN | SCA Emergency Response | SIDEWALK BRIDGING | Construction | In-Progress | 2/25/2013 | EMER |  | EMER | 108886 | 108886
22 | K052 | P.S. 52 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR ACOUSTICAL WALL PLASTER IN AUDITORIUM WINDOW WALLS #2 AND #4 1950 WING WILL BE | Construction | In-Progress | 3/26/2024 | IEH |  | IEH | 11354 | 1729
22 | K052 | P.S. 52 - BROOKLYN | DOE - RESOA | FY13 RESO A ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | DOER | 22102 | 0
22 | K052 | P.S. 52 - BROOKLYN | DOE - RESOA | FY22 RESO A PLAYGROUNDS | Construction | In-Progress | 6/6/2022 | DOER |  | DOER | 50000 | 110340
22 | K052 | P.S. 52 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/18/2022 | DOES |  | DOES | 75026 | 0
22 | K052 | P.S. 52 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/27/2024 | DOES | 4/3/2024 | DOES | 65832 | 17360
22 | K063 | THE JOAN SNOW PRE-K CENTER | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K063 | THE JOAN SNOW PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/7/2024 | DOES | 6/4/2024 | DOES | 65832 | 8812
22 | K078 | I.S. 78 - BROOKLYN | Fast Track Projects | LSP HOT WATER HEATER & VACUUM PUMP | Construction | In-Progress | 9/21/2018 | FTK |  | FTK | 908481 | 903518
22 | K078 | I.S. 78 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
22 | K078 | I.S. 78 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
22 | K078 | I.S. 78 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/2/2024 | DOES |  | DOES | 484712 | 0
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/6/2023 | 3/8/2024 | 3/1/2024 | 0 | 17212 | 17212
22 | K119 | P.S. 119 - BROOKLYN | SCA IEH | PO18-TEST / ABATE 3RD FLOOR HALLWAY APPROX. 3800 SQ FT I AS PER DDF CHARLES FORTE DIRECTION | Construction | Complete | 12/26/2023 | IEH | 1/4/2024 | IEH | 9516 | 941
22 | K119 | P.S. 119 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 6/18/2024 | DIIR | 130000 | 130000
22 | K119 | P.S. 119 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 65832 | 0
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/25/2023 | 5/25/2023 | 6/5/2023 | 0 | 13873 | 13873
22 | K139 | P.S. 139 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/9/2022 | EMER |  | EMER | 148276 | 86734
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/25/2023 | 4/25/2023 | 4/12/2023 | 0 | 30079 | 30079
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/8/2023 | 4/11/2024 | 4/9/2024 | 0 | 15218 | 15155
22 | K152 | P.S. 152 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ K152 | Construction | In-Progress | 7/10/2023 | EMER |  | EMER | 75658 | 72171
22 | K152 | P.S. 315 - BROOKLYN | Fast Track Projects | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 9/14/2023 | FTK |  | FTK | 112509 | 106929
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/7/2020 | DOER |  | DOER | 38382 | 0
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/16/2022 | DOER |  | DOER | 132131 | 0
22 | K152 | P.S. 152 - BROOKLYN | DOE - RESOA | FY20 RESO A DIGITAL SIGN | Construction | In-Progress | 10/11/2021 | DOER |  | DOER | 38760 | 0
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 251000 | 0
22 | K152 | P.S. 315 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
22 | K152 | P.S. 315 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/13/2024 | DOES |  | DOES | 65832 | 0
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K193 | P.S. 193 - BROOKLYN | Fast Track Projects | LSP PVI DOMESTIC WATER HEATER | Construction | In-Progress | 5/7/2019 | FTK |  | FTK | 251347 | 145443
22 | K193 | P.S. 193 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 534000 | 0
22 | K193 | P.S. 193 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K193 | P.S. 193 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 3/23/2022 | DOER |  | DOER | 586788 | 0
22 | K193 | P.S. 193 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/3/2024 | DOES | 6/11/2024 | DOES | 65832 | 189
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K194 | P.S. 194 - BROOKLYN | SCA IEH | PO18-ABATE LOOSE/LIFTING 9'X 9' ACM FLOORING TILE TRIPPING HAZARD. SMALL ROOM 8' X 12' HALF THE ROOM | Construction | Complete | 6/25/2024 | IEH | 6/30/2024 | IEH | 19959 | 19959
22 | K194 | P.S. 194 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 50000
22 | K194 | P.S. 194 - BROOKLYN | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/21/2018 | DOER |  | DOER | 488768 | 0
22 | K194 | P.S. 194 - BROOKLYN | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 269352 | 0
22 | K194 | P.S. 194 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/21/2024 | DOES | 6/28/2024 | DOES | 65832 | 30923
22 | K195 | P.S. 195 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 8/23/2021 | EMER |  | EMER | 15642 | 15642
22 | K195 | P.S. 195 - BROOKLYN | SCA IEH | PO18-ABATE PLASTER AND PAINT CEILING IN CLASSROOM 222. AREA TO BE PLASTERED IS APPROXIMATELY 50SG.FT | Construction | Complete | 4/18/2024 | IEH | 4/24/2024 | IEH | 44140 | 44140
22 | K195 | P.S. 195 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/5/2024 | DIIR | 6/14/2024 | DIIR | 260000 | 1451
22 | K195 | P.S. 195 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
22 | K195 | P.S. 195 - BROOKLYN | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 210000 | 0
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K197 | P.S. 197 - BROOKLYN | SCA IEH | PO18-ABATE FLOORING / ROOM 401/ CONCRETE SUBFLOORING LISTED POSITIVE FOR ACM IN ADHERA BOOK. LOOKING | Construction | Complete | 3/19/2024 | IEH | 8/15/2024 | IEH | 2044 | 2044
22 | K197 | P.S. 197 - BROOKLYN | SCA IEH | PO18-ABATE FLOOR TILES IN ROOMS 111 AND ROOM 263 INCLUDING SUBFLOOR | Construction | Complete | 4/8/2024 | IEH | 7/13/2024 | IEH | 78474 | 1634
22 | K197 | P.S. 197 - BROOKLYN | SCA IEH | PO18-ABATE CONCRETE SUB FLOOR AND FELT PAPER UDER THE FLOORING IN ROOM 314 FOR THE REMOVAL OF THE PO | Construction | Complete | 8/23/2024 | IEH | 8/30/2024 | IEH | 79418 | 61951
22 | K197 | P.S. 197 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
22 | K197 | P.S. 197 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
22 | K197 | P.S. 197 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 4/12/2019 | DOER |  | DOER | 119721 | 0
22 | K197 | P.S. 197 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 9/23/2021 | DOER |  | DOER | 90313 | 0
22 | K197 | P.S. 197 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
22 | K197 | P.S. 197 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 7/1/2022 | DOES |  | DOES | 62704 | 0
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | FY24 RESO A (MA) CAFETERIA UPGRADE | Scope | Complete | 11/21/2023 | 3/26/2024 | 3/29/2024 | 0 | 19171 | 19108
22 | K198 | P.S. 198 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K198 | P.S. 198 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K198 | P.S. 198 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K198 | P.S. 198 - BROOKLYN | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 8/17/2020 | DOES |  | DOES | 979 | 0
22 | K203 | P.S. 203 - BROOKLYN | DIIT - RESOA | FY14 RESO A SECURITY CAMERAS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 180000 | 0
22 | K203 | P.S. 203 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K203 | P.S. 203 - BROOKLYN | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/6/2023 | DOER |  | DOER | 313052 | 0
22 | K203 | P.S. 203 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
22 | K203 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
22 | K203 | P.S. 203 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 12/11/2020 | DOES |  | DOES | 185715 | 0
22 | K203 | P.S. 203 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/25/2024 | DOES | 4/1/2024 | DOES | 65832 | 189
22 | K206 | P.S. 206 - BROOKLYN | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/8/2020 | DOER |  | DOER | 406745 | 0
22 | K206 | P.S. 206 - BROOKLYN | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/30/2023 | DOER |  | DOER | 457374 | 0
22 | K206 | P.S. 206 - BROOKLYN | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 456428 | 0
22 | K206 | P.S. 206 - BROOKLYN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/1/2024 | DOER |  | DOER | 322233 | 0
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/21/2024 | 7/8/2024 | 8/22/2024 | 0 | 19611 | 586
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/21/2024 | 6/21/2024 | 8/22/2024 | 0 | 0 | 0
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/10/2019 | 4/9/2020 | 6/9/2021 | 0 | 19615 | 19615
22 | K207 | P.S. 207 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/9/2020 | FTK |  | FTK | 838668 | 829915
22 | K207 | P.S. 207 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/19/2023 | DIIR | 5/13/2024 | DIIR | 125000 | 125000
22 | K207 | P.S. 207 - BROOKLYN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 1/28/2020 | DOER |  | DOER | 12445 | 0
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/30/2017 | 3/28/2017 | 3/16/2017 | 0 | 17226 | 17226
22 | K217 | P.S. 217 - BROOKLYN | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
22 | K217 | P.S. 217 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/7/2022 | DOER |  | DOER | 172974 | 0
22 | K217 | P.S. 217 - BROOKLYN | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
22 | K217 | P.S. 217 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/11/2022 | DOES |  | DOES | 169282 | 0
22 | K217 | P.S. 217 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/14/2024 | DOES | 5/22/2024 | DOES | 65832 | 189
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 9/2/2021 | 12/6/2021 | 3/2/2022 | 0 | 30431 | 30431
22 | K222 | P.S. 222 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K222 | P.S. 222 - BROOKLYN | DOE - RESOA | FY16 RESO A PLAYGROUND REDEVELOPMENT | Construction | Complete | 5/28/2021 | DOER | 9/20/2022 | DOER | 435599 | 435319
22 | K222 | P.S. 222 - BROOKLYN | DOE - RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 297157 | 0
22 | K222 | P.S. 222 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/4/2022 | DOER |  | DOER | 131034 | 0
22 | K222 | P.S. 222 - BROOKLYN | DOE - Skilled Trades | ACE 6- WIRELESS PNEUMATIC THERMOSTATS | Construction | In-Progress | 12/7/2020 | DOES |  | DOES | 106097 | 0
22 | K222 | P.S. 222 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/16/2024 | DOES | 5/15/2024 | DOES | 65832 | 189
22 | K222 | P.S. 222 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/20/2023 | DOES |  | DOES | 612137 | 421244
22 | K234 | I.S. 234 - BROOKLYN | DOE - RESOA | FY18 RESO A LIBRARY UPGRADE | Construction | In-Progress | 12/27/2021 | DOER |  | DOER | 52410 | 0
22 | K234 | I.S. 234 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 12/3/2021 | DOER |  | DOER | 130678 | 0
22 | K234 | I.S. 234 - BROOKLYN | DOE - RESOA | FY21 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 9/6/2022 | DOER |  | DOER | 423372 | 0
22 | K234 | I.S. 234 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 11/5/2021 | DOES |  | DOES | 154677 | 0
22 | K234 | I.S. 234 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 6/28/2023 | DOES |  | DOES | 508295 | 0
22 | K234 | I.S. 234 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/16/2024 | DOES |  | DOES | 65832 | 0
22 | K236 | P.S. 236 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 10/1/2020 | FTK |  | FTK | 283620 | 273493
22 | K236 | P.S. 236 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
22 | K236 | P.S. 236 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K236 | K771 SPED - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
22 | K236 | P.S. 236 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/1/2022 | DOES |  | DOES | 105242 | 0
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K240 | I.S. 240 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
22 | K240 | I.S. 381 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/10/2024 | DIIR |  | DIIR | 100000 | 100000
22 | K240 | I.S. 240 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K240 | I.S. 381 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K240 | I.S. 381 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
22 | K240 | I.S. 240 - BROOKLYN | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
22 | K240 | I.S. 240 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
22 | K240 | I.S. 240 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0
22 | K240 | I.S. 240 - BROOKLYN | DOE - Skilled Trades | GAS PIPING REPAIR | Construction | In-Progress | 8/28/2019 | DOES |  | DOES | 198996 | 7065
22 | K240 | I.S. 240 - BROOKLYN | DOE - Skilled Trades | WATER MAIN REPLACEMENT | Construction | In-Progress | 3/22/2021 | DOES |  | DOES | 156929 | 0
22 | K240 | I.S. 240 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 65832 | 0
22 | K251 | P.S. 251 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/6/2023 | 6/7/2023 | 5/22/2023 | 0 | 22772 | 22772
22 | K251 | P.S. 251 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 3/13/2020 | FTK |  | FTK | 411180 | 411179
22 | K251 | P.S. 251 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K251 | P.S. 251 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 11/1/2021 | DOER |  | DOER | 94456 | 0
22 | K251 | P.S. 251 - BROOKLYN | DOE - RESOA | FY22 RESO A MEDIA STUDIO | Construction | PNS | PNS | PNS | PNS | DOER | 135000 | 0
22 | K251 | P.S. 251 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
22 | K251 | P.S. 251 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/22/2024 | DOES | 4/5/2024 | DOES | 65832 | 22116
22 | K254 | P.S. 254 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
22 | K254 | P.S. 254 - BROOKLYN | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
22 | K254 | P.S. 254 - BROOKLYN | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
22 | K254 | P.S. 254 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/20/2024 | DOES |  | DOES | 65832 | 0
22 | K255 | P.S. 255 - BROOKLYN | SCA IEH | PO18-REMOVE APPROX. 10 FEET OF ACM PIPE COVER FROM A 3' DRAIN PIPE. | Construction | Complete | 9/19/2024 | IEH | 9/22/2024 | IEH | 761 | 761
22 | K269 | P.S. 361 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K269 | P.S. 361 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K269 | P.S. 361 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K269 | P.S. 361 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 100000
22 | K269 | P.S. 361 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 220000
22 | K269 | P.S. 361 - BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0
22 | K269 | P.S. 361 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
22 | K269 | P.S. 361 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 10/15/2022 | DOES |  | DOES | 201714 | 0
22 | K269 | P.S. 361 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/12/2024 | DOES | 5/20/2024 | DOES | 65832 | 189
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 1/10/2018 | 4/26/2018 | 2/12/2018 | 0 | 11230 | 11229
22 | K277 | P.S. 277 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K277 | P.S. 277 - BROOKLYN | DOE - RESOA | FY16 RESO A CAFETERIA/MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 97548 | 0
22 | K277 | P.S. 277 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/29/2022 | DOER |  | DOER | 142267 | 0
22 | K277 | P.S. 277 - BROOKLYN | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/18/2023 | DOER |  | DOER | 123904 | 0
22 | K277 | P.S. 277 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/13/2024 | DOER |  | DOER | 300000 | 0
22 | K277 | P.S. 277 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 1/17/2020 | DOES |  | DOES | 150692 | 0
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K278 | I.S. 278 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS: RMS: 308A, 208A, 329 APPROX. 252SF EACH ROOM RM: 311 AP | Construction | Complete | 8/29/2023 | IEH | 7/28/2024 | IEH | 133265 | 107596
22 | K278 | I.S. 278 - BROOKLYN | DIIT - RESOA | FY15 RESO A IP SURVEILLANCE CAMERA INSTALLATION | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 130728 | 0
22 | K278 | I.S. 278 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/15/2024 | DIIR |  | DIIR | 50000 | 0
22 | K278 | I.S. 278 - BROOKLYN | DOE - RESOA | FY08 RESO A SCIENCE LAB UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
22 | K278 | I.S. 278 - BROOKLYN | DOE - RESOA | FY10 RESO A- AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
22 | K278 | I.S. 278 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 11/4/2022 | DOER |  | DOER | 233803 | 0
22 | K278 | I.S. 278 - BROOKLYN | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | In-Progress | 3/1/2024 | DOER |  | DOER | 21688 | 0
22 | K278 | I.S. 278 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 1/20/2021 | DOES |  | DOES | 151612 | 0
22 | K278 | I.S. 278 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/28/2024 | DOES |  | DOES | 632616 | 0
22 | K286 | K811 SPED - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOM #134B | Construction | Complete | 9/13/2023 | IEH | 4/9/2024 | IEH | 0 | 0
22 | K286 | K811 SPED - BROOKLYN | Fast Track Projects | ELECTRICAL CODE COMPLIANCE | Construction | In-Progress | 5/8/2019 | FTK |  | FTK | 140992 | 140991
22 | K286 | K811 SPED - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/4/2022 | DOER |  | DOER | 159589 | 0
22 | K286 | K811 SPED - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 118000 | 0
22 | K286 | K811 SPED - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 7/26/2024 | DOER |  | DOER | 234949 | 0
22 | K286 | K811 SPED - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 7/19/2019 | DOES |  | DOES | 152471 | 0
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/6/2023 | 6/7/2023 | 7/14/2023 | 0 | 15652 | 15652
22 | K312 | P.S. 312 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 3/2/2023 | DIIR | 206512 | 196523
22 | K312 | P.S. 312 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/1/2023 | DIIR | 6/5/2023 | DIIR | 150000
22 | K312 | P.S. 312 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0
22 | K312 | P.S. 312 - BROOKLYN | DOE - RESOA | FY10 RESO A- AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
22 | K312 | P.S. 312 - BROOKLYN | DOE - RESOA | FY16 RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 94000 | 0
22 | K312 | P.S. 312 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 7/9/2015 | DOES |  | DOES | 183980 | 0
22 | K342 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY16 RESO A LEARNING GARDEN | Scope | Complete | 9/27/2016 | 12/29/2016 | 1/20/2017 | 0 | 187776 | 186151
22 | K395 | P.S. 109 - BROOKLYN | Fast Track Projects | LSP REPLACE LEAKING PVI DOMESTIC WATER HEATER | Construction | In-Progress | 5/22/2019 | FTK |  | FTK | 200609 | 187684
22 | K395 | P.S. 109 - BROOKLYN | Fast Track Projects | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/31/2023 | FTK |  | FTK | 139545 | 138150
22 | K395 | P.S. 109 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K395 | P.S. 109 - BROOKLYN | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
22 | K395 | P.S. 109 - BROOKLYN | DOE - RESOA | FY24 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
22 | K395 | P.S. 109 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/24/2024 | DOES |  | DOES | 50832 | 0
22 | K402 | K000 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/29/2024 | IEH | 9/5/2024 | IEH | 12175 | 0
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K405 | MIDWOOD HS - BROOKLYN | SCA IEH | PO18-PLEASE DEMO EXISTING FLOOR TILES AND PIPE INSULATION IN ROOM #463 | Construction | Complete | 9/21/2023 | IEH | 4/9/2024 | IEH | 165 | 165
22 | K405 | MIDWOOD HS - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 7/30/2020 | FTK |  | FTK | 326288 | 323937
22 | K405 | MIDWOOD HS - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
22 | K405 | MIDWOOD HS - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/23/2023 | DOER |  | DOER | 319428 | 0
22 | K405 | MIDWOOD HS - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Scope | Complete | 1/20/2022 | 5/23/2022 | 7/14/2022 | 0 | 9911 | 9911
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR PIPE & CAFETERIA CEILING ROOM #'S AS PER AHERA PLAN# 1400 | Construction | Complete | 8/20/2024 | IEH | 8/22/2024 | IEH | 28601 | 1412
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY12 RESO A FLOORING | Construction | PNS | PNS | PNS | PNS | DOER | 264039 | 0
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | RESO A FIELDHOUSE UPGRADE | Construction | In-Progress | 12/20/2019 | DOER |  | DOER | 19630 | 0
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 4/16/2021 | DOER |  | DOER | 673887 | 0
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 290000 | 0
22 | K425 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
22 | K426 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY23 RESO A FIELD UPGRADE | Construction | In-Progress | 12/14/2023 | DOER |  | DOER | 2300000 | 232796
22 | K426 | JAMES MADISON HS - BROOKLYN | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA IEH | PO18-ABATE CEILING TILE AND MASTIC 3RD FLOOR HALLWAY APPROX 8000 SQ FT | Construction | Complete | 5/15/2024 | IEH | 6/13/2024 | IEH | 1980 | 1980
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA IEH | PO18-ABATE AND REPAIR DOOR FRAME CAULKING ON CORRIDOR SIDE THROUGHOUT ENTIRE BUILDING ROOMS: 235, 23 | Construction | Complete | 5/28/2024 | IEH | 7/24/2024 | IEH | 789 | 789
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA IEH | PO18-TEST / ABATE DETERIORATED PIPE INSULATION ON DRAIN LINE ON BLOWER #7 LOCATED IN FAN ROOM 062 | Construction | Complete | 6/3/2024 | IEH | 6/13/2024 | IEH | 44163 | 2451
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | SCA IEH | PO18-ABATE ACM WRAPPING ON PIPING DETERIORATED IN ROOM B20. AHERA BOOK LISTS INSULATION AS CONFIRMED | Construction | Complete | 8/13/2024 | IEH | 8/14/2024 | IEH | 16742 | 1190
22 | K495 | PROFESSIONAL PATHWAYS HIGH SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/6/2023 | DOES |  | DOES | 671019 | 0
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K496 | SHEEPSHEAD BAY HS - BROOKLYN | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 3000000 | 0
22 | K535 | LEON GOLDSTEIN HS - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/17/2024 | DOES | 6/25/2024 | DOES | 50832
22 | K555 | BROOKLYN COLLEGE ACADEMY - K | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K555 | BROOKLYN COLLEGE ACADEMY - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K555 | BROOKLYN COLLEGE ACADEMY - K | DOE - RESOA | FY18 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/27/2022 | DOER |  | DOER | 194395 | 0
22 | K705 | MIDWOOD HS - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/14/2024 | IEH | 8/30/2024 | IEH | 12175 | 0
22 | K729 | P.S. 207 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 6/5/2024 | IEH | 15329 | 194
22 | K735 | P.S. 245 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/13/2024 | IEH | 11917 | 11917
22 | K735 | P.S. 245 - BROOKLYN | DOE - RESOA | FY16 RESO A ELECTRICAL SYSTEMS | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0
22 | K776 | P.S. 152 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/13/2024 | IEH | 6/14/2024 | IEH | 11128 | 5753
22 | K839 | P.S. 134 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
22 | K839 | P.S. 134 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
22 | K839 | P.S. 134 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
22 | K849 | P.S. 134 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K849 | P.S. 134 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K849 | P.S. 134 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K849 | P.S. 134 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K849 | P.S. 134 - BROOKLYN | SCA IEH | PO18-DRILLING THROUGH WALLS FOR ELECTRICAL UPGRADE NEW HYDROPONICS LAB #301 | Construction | Complete | 9/18/2023 | IEH | 4/9/2024 | IEH | 0 | 0
22 | K849 | P.S. 134 - BROOKLYN | DOE - RESOA | FY21 RESO A BREEZEWAY | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
22 | K849 | P.S. 134 - BROOKLYN | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/13/2024 | DOER |  | DOER | 400000 | 0
22 | K849 | P.S. 134 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
22 | K849 | P.S. 134 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/27/2024 | DOES |  | DOES | 65832 | 0
22 | K849 | P.S. 134 - BROOKLYN | DOE - Skilled Trades | ASPHALT REPLACEMENT IN YARD | Construction | In-Progress | 7/5/2023 | DOES |  | DOES | 365686 | 0
22 | K852 | P.S. 326 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
22 | K852 | P.S. 326 - BROOKLYN | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/17/2023 | DIIR | 4/2/2024 | DIIR | 100000 | 99649
22 | K852 | P.S. 326 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
22 | K852 | P.S. 326 - BROOKLYN | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
22 | K852 | P.S. 326 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 65832 | 0
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/25/2024 | IEH | 7/25/2024 | IEH | 15516 | 181
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | Fast Track Projects | PATH OF TRAVEL WATER PENETRATION | Construction | In-Progress | 7/31/2024 | FTK |  | FTK | 238377 | 4226
22 | KBZT | K000 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 35000 | 0
22 | KBZT | K000 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/1/2023 | DIIR |  | DIIR | 150000 | 0
23 | K012 | P.S. 12 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 4/15/2024 | DIIR | 350000 | 350000
23 | K012 | P.S. 12 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/1/2023 | DIIR |  | DIIR | 355000 | 0
23 | K012 | P.S. 12 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/28/2019 | DOER |  | DOER | 147096 | 0
23 | K012 | P.S. 12 - BROOKLYN | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 5/9/2022 | DOER |  | DOER | 41371 | 0
23 | K012 | I.S. 484 - BROOKLYN | DOE - RESOA | FY20 RESO A ROOM RENOVATION | Construction | In-Progress | 6/4/2021 | DOER |  | DOER | 89991 | 0
23 | K012 | P.S. 12 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 215000 | 0
23 | K012 | P.S. 12 - BROOKLYN | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 6/21/2024 | DOER |  | DOER | 38808 | 0
23 | K012 | I.S. 484 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/14/2021 | DOES |  | DOES | 114624 | 0
23 | K012 | I.S. 484 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/9/2024 | DOES |  | DOES | 458324 | 0
23 | K041 | P.S. 41 - BROOKLYN | SCA IEH | PO18-FLOOR UNDER PARTITION POSTS AND COUNTER IN ROOM 144 (GEN. OFFICE) NEEDS TO BE TESTED BEFORE THE | Construction | In-Progress | 5/7/2024 | IEH |  | IEH | 1725 | 975
23 | K041 | P.S. 41 - BROOKLYN | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
23 | K041 | I.S. 522 - BROOKLYN | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 223606 | 0
23 | K041 | P.S. 41 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/31/2024 | DOES |  | DOES | 386136 | 0
23 | K055 | BROOKLYN COLLEGIATE: A COLLEGE BOARD SCHOOL | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/5/2022 | DOES |  | DOES | 141048 | 0
23 | K055 | BROOKLYN COLLEGIATE: A COLLEGE BOARD SCHOOL | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/31/2023 | DOES |  | DOES | 621792 | 0
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA IEH | PO18-ABATE & REPAIR DAMAGED PAINT/PLASTER IN THE FOLLOWING AREAS IN ROOMS: 307A - WALL BEHIND THE RA | Construction | Complete | 8/27/2024 | IEH | 9/1/2024 | IEH | 94779 | 2829
23 | K073 | BROOKLYN ENVIRONMENTAL EXPLORATION SCHOOL (BEES) | Fast Track Projects | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/26/2024 | FTK |  | FTK | 229727 | 72941
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | Fast Track Projects | LSP- AUDITORIUM UPGRADE | Construction | In-Progress | 5/19/2023 | FTK |  | FTK | 230445 | 230411
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/10/2024 | DIIR |  | DIIR | 100000 | 0
23 | K073 | BROOKLYN ENVIRONMENTAL EXPLORATION SCHOOL (BEES) | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/21/2024 | DIIR | 60000 | 60000
23 | K073 | P.S. 73 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 2/12/2024 | DOEL |  | DOEL | 68896 | 68896
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
23 | K073 | BROOKLYN ENVIRONMENTAL EXPLORATION SCHOOL (BEES) | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/12/2024 | DOES |  | DOES | 621832 | 0
23 | K137 | P.S. 137 - BROOKLYN | Fast Track Projects | LSP- HOT WATER HEATER | Construction | In-Progress | 5/10/2019 | FTK |  | FTK | 277408 | 242990
23 | K137 | P.S. 137 - BROOKLYN | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 88000 | 0
23 | K137 | P.S. 137 - BROOKLYN | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/23/2022 | DOES |  | DOES | 87735 | 0
23 | K150 | P.S. 150 - BROOKLYN | SCA IEH | PO18-PLEASE ABATE WALLS AND CEILING IN BASEMENT GYMNASIUM TO ASSIST CARPENTERS IN REPLACING BACKBORD | Construction | Complete | 3/13/2024 | IEH | 4/13/2024 | IEH | 31428 | 23723
23 | K150 | P.S. 150 - BROOKLYN | SCA IEH | PO18-ABATE 5X5 AREA IN BASEMENT GYM REQUIRED TO FACILTATE PROPER FASTENING OF THE BASKETBALL BACKBOA | Construction | Complete | 4/30/2024 | IEH | 5/3/2024 | IEH | 0 | 0
23 | K150 | P.S. 150 - BROOKLYN | Fast Track Projects | LSP GYM UPGRADE | Construction | Complete | 4/13/2023 | FTK | 4/4/2024 | FTK | 274815 | 274296
23 | K155 | P.S. 155 - BROOKLYN | Fast Track Projects | LSP AUDITORIUM UPGRADE | Construction | In-Progress | 5/5/2023 | FTK |  | FTK | 224389 | 210159
23 | K155 | P.S. 155 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 62000 | 0
23 | K155 | P.S. 155 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 8/25/2023 | DOEL | 3/26/2024 | DOEL | 104010 | 104010
23 | K155 | P.S. 155 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/19/2024 | DOEL |  | DOEL | 62212 | 0
23 | K155 | P.S. 155 - BROOKLYN | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 9/15/2023 | DOER |  | DOER | 221694 | 0
23 | K155 | P.S. 155 - BROOKLYN | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
23 | K155 | P.S. 155 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/14/2022 | DOES |  | DOES | 182719 | 0
23 | K155 | P.S. 155 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 65832 | 0
23 | K165 | P.S. 165 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR 1ST FL WALLS AND FLOOR TO HAVE ELECTRIC INSTALLED FOR WATER BOTTLE FILLER. | Construction | In-Progress | 4/19/2024 | IEH |  | IEH | 937 | 362
23 | K165 | P.S. 165 - BROOKLYN | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 344187 | 0
23 | K175 | FREDERICK DOUGLAS ACAD VII HS - K | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 5/3/2021 | DOER |  | DOER | 143100 | 0
23 | K175 | TEACHERS PREP (HS LVL) - K | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/6/2023 | DOER |  | DOER | 238388 | 0
23 | K175 | TEACHERS PREP (HS LVL) - K | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | Complete | 4/23/2021 | DOES | 3/19/2023 | DOES | 281016 | 68716
23 | K175 | FREDERICK DOUGLAS ACAD VII HS - K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/22/2024 | DOES |  | DOES | 203734 | 0
23 | K178 | P.S. 178 - BROOKLYN | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 12/26/2023 | DOEL |  | DOEL | 64735 | 64735
23 | K178 | P.S. 178 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 4/22/2019 | DOES |  | DOES | 262741 | 0
23 | K178 | P.S. 178 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/14/2022 | DOES |  | DOES | 107334 | 0
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/27/2023 | 5/30/2023 | 5/16/2023 | 0 | 15432 | 15432
23 | K183 | P.S. 446 - BROOKLYN | SCA IEH | PO18-REPAIR MATERIAL ON BEAM WHERE BASKETBALL HOOP WAS REMOVED IN 1ST FLOOR PLAY AREA | Construction | Complete | 4/29/2024 | IEH | 6/4/2024 | IEH | 18953 | 3589
23 | K183 | P.S. 446 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOOR IN ROOM 202, APPROX 400 SQ FT SOFT CONCRETE FILLER IS CONFIRMED ACM | Construction | In-Progress | 9/16/2024 | IEH |  | IEH | 6316 | 241
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
23 | K183 | P.S. 446 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/25/2023 | DOES |  | DOES | 331490 | 0
23 | K183 | P.S. 446 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/12/2024 | DOES |  | DOES | 65832 | 0
23 | K184 | P.S. 184 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 25 LINEAR FEET OF ACM FROM PIPE LOCATED ABOVE ELECTRICAL PANEL IN | Construction | In-Progress | 7/26/2023 | IEH |  | IEH | 5976 | 401
23 | K184 | P.S. 184 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE AREA AROUND SINK DRAIN IN ROOM# 211 | Construction | Complete | 7/30/2024 | IEH | 8/29/2024 | IEH | 22508 | 1555
23 | K184 | P.S. 184 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY TEN LINEAR FEET OF ACM FROM PIPE IN ROOM# 502 CRAWL SPACE FOR BOYS | Construction | Complete | 9/4/2024 | IEH | 9/7/2024 | IEH | 16653 | 2467
23 | K184 | P.S. 184 - BROOKLYN | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 2/24/2020 | FTK |  | FTK | 425387 | 414410
23 | K184 | P.S. 184 - BROOKLYN | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
23 | K263 | M.S. 671 - BROOKLYN | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 5486 | 5486
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA IEH | PO18-ABATE AND REMOVE APPROX 12 FT OF PIPE INSULATION FROM PIPE. LOCATION IN BOILER ROOM. PIPES ARE | Construction | In-Progress | 9/26/2024 | IEH |  | IEH | 0 | 0
23 | K263 | P.S./I.S. 323 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 333000 | 0
23 | K263 | P.S./I.S. 323 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/24/2022 | DOER |  | DOER | 58788 | 0
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 3/11/2022 | DOER |  | DOER | 308811 | 0
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
23 | K263 | M.S. 671 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
23 | K263 | M.S. 671 - BROOKLYN | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 7/28/2023 | DOES |  | DOES | 873843 | 0
23 | K263 | P.S./I.S. 323 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 3/23/2020 | DOES | 9/26/2023 | DOES | 438564 | 188725
23 | K271 | EAGLE ACAD YOUNG MEN AT OCEAN - K | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 9/26/2022 | DOER |  | DOER | 101524 | 0
23 | K271 | EAGLE ACAD YOUNG MEN AT OCEAN - K | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
23 | K271 | EAGLE ACAD YOUNG MEN AT OCEAN - K | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/17/2022 | DOES |  | DOES | 545985 | 0
23 | K275 | I.S. 518 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/25/2023 | 5/25/2023 | 7/14/2023 | 0 | 7928 | 7928
23 | K275 | BROOKLYN DEMOCRACY ACADEMY - K | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
23 | K275 | I.S. 518 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 9/2/2016 | DOES |  | DOES | 178610 | 0
23 | K275 | I.S. 518 - BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 4/5/2023 | DOES |  | DOES | 655803 | 0
23 | K275 | I.S. 518 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/2/2024 | DOES |  | DOES | 65832 | 0
23 | K284 | P.S. 284 - BROOKLYN | DOE - RESOA | FY09 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
23 | K284 | P.S. 284 - BROOKLYN | DOE - Skilled Trades | AUDITORIUM STAIRS | Construction | In-Progress | 2/6/2018 | DOES |  | DOES | 351904 | 0
23 | K284 | P.S. 284 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 11/11/2021 | DOES |  | DOES | 60651 | 0
23 | K298 | I.S. 363 - BROOKLYN | DOE - RESOA | FY21 RESO A STEM LAB | Construction | In-Progress | 3/11/2024 | DOER |  | DOER | 162769 | 0
23 | K298 | P.S. 298 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 3/25/2022 | DOES |  | DOES | 64443 | 0
23 | K298 | P.S. 298 - BROOKLYN | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 11/21/2022 | DOES |  | DOES | 265867 | 0
23 | K327 | P.S. 327 - BROOKLYN | SCA IEH | PO18-ADOPT A FLOOR COLOR TILE SCHEME THROUGHOUT THE BUILDING OR TRY TO MATCH CLOSER IN THE SHORT TER | Construction | Complete | 9/27/2023 | IEH | 4/23/2024 | IEH | 412 | 412
23 | K327 | P.S. 327 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/10/2024 | DIIR |  | DIIR | 250000 | 0
23 | K327 | P.S. 327 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 155000 | 0
23 | K327 | P.S. 327 - BROOKLYN | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
23 | K327 | P.S. 327 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75200 | 0
23 | K327 | P.S. 327 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/30/2020 | DOES |  | DOES | 798516 | 0
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 8/2/2018 | EMER |  | EMER | 57369 | 57369
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA Emergency Response | EMERGENCY STABILIZATION- COPING STONES SPALLING BRICK | Construction | In-Progress | 10/26/2022 | EMER |  | EMER | 36351 | 11100
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | DOE - RESOA | FY21 RESO A MAKER LAB UPGRADE | Construction | In-Progress | 9/22/2023 | DOER |  | DOER | 146284 | 0
23 | K332 | P.S. 332 - BROOKLYN | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75200 | 0
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Scope | Complete | 6/28/2022 | 10/28/2022 | 2/8/2023 | 0 | 11565 | 987
23 | K356 | I.S. 392 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/14/2023 | 4/17/2024 | 6/5/2024 | 0 | 6767 | 789
23 | K356 | I.S. 392 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 275000 | 0
23 | K356 | P.S. 156 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
23 | K356 | P.S. 156 - BROOKLYN | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
23 | K356 | I.S. 392 - BROOKLYN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
23 | K356 | P.S. 156 - BROOKLYN | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
23 | K356 | P.S. 156 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/13/2023 | DOES |  | DOES | 495211 | 0
23 | K396 | K396 SPED - BROOKLYN | DOE - RESOA | FY20 RESO A SENSORY GYM | Construction | In-Progress | 11/3/2023 | DOER |  | DOER | 218314 | 0
23 | K396 | K396 SPED - BROOKLYN | DOE - RESOA | FY23 RESO A CAFETERIA/ MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0
23 | K396 | K396 SPED - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/15/2022 | DOES |  | DOES | 223197 | 0
23 | K396 | K396 SPED - BROOKLYN | DOE - Skilled Trades | ACCESSIBILITY | Construction | Complete | 9/25/2023 | DOES | 4/24/2024 | DOES | 870410
23 | KAIX | KEY COLLEGIATE CHARTER SCHOOL - BROOKLYN | SCA CIP RESOA | FY21 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/15/2023 | 5/16/2023 | 4/28/2023 | 0 | 53443 | 52624
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q005 | I.S. 5 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/5/2024 | DIIR | 50000
24 | Q005 | Q009 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/2/2024 | DIIR |  | DIIR | 113000 | 0
24 | Q005 | I.S. 5 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q005 | I.S. 5 - QUEENS | DOE - RESOA | FY20 RESO A MULTIMEDIA CENTER | Construction | In-Progress | 3/17/2023 | DOER |  | DOER | 166495 | 0
24 | Q005 | I.S. 5 - QUEENS | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 193236 | 0
24 | Q005 | I.S. 5 - QUEENS | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 63000 | 0
24 | Q005 | I.S. 5 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/26/2024 | DOES | 5/8/2024 | DOES | 50832
24 | Q007 | P.S. 7 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 7/20/2022 | FTK |  | FTK | 263659 | 71973
24 | Q007 | P.S. 7 - QUEENS | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
24 | Q007 | P.S. 7 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 325000 | 0
24 | Q007 | P.S. 7 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/3/2024 | DOES |  | DOES | 50832 | 0
24 | Q009 | Q009 SPED - QUEENS | Fast Track Projects | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 4/24/2023 | FTK |  | FTK | 77513 | 77490
24 | Q009 | Q009 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q009 | Q009 SPED - QUEENS | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/12/2024 | DOER |  | DOER | 231660 | 0
24 | Q009 | Q009 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832
24 | Q012 | P.S. 12 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q012 | P.S. 12 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 40000 | 0
24 | Q012 | P.S. 12 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
24 | Q012 | P.S. 12 - QUEENS | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 6/24/2020 | DOES |  | DOES | 118453 | 0
24 | Q013 | P.S. 13 - QUEENS | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Scope | Complete | 4/18/2024 | 7/19/2024 | 6/12/2024 | 0 | 15881 | 15784
24 | Q013 | P.S. 13 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/16/2024 | DOES | 5/23/2024 | DOES | 65832 | 7903
24 | Q013 | P.S. 13 - QUEENS | DOE - Skilled Trades | WATER MAIN LEAK REPAIR | Construction | In-Progress | 3/13/2024 | DOES |  | DOES | 88000 | 0
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/11/2023 | 4/12/2024 | 6/17/2024 | 0 | 12414 | 1486
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 4/9/2024 | 7/10/2024 | 6/5/2024 | 0 | 0 | 0
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SOCCER PITCH / FY20 RESO A SOCCER PITCH | Scope | Complete | 3/4/2021 | 3/25/2022 | 3/14/2022 | 0 | 23842 | 23842
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/2/2021 | 6/30/2021 | 6/13/2023 | 0 | 34627 | 17990
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 2/1/2023 | 11/22/2023 | 1/11/2024 | 0 | 12151 | 12151
24 | Q014 | P.S. 14 - QUEENS | SCA IEH | PO18-ASBESTOS ABATEMENT IN ROOM#314 | Construction | Complete | 5/31/2024 | IEH | 6/2/2024 | IEH | 36780 | 30835
24 | Q014 | P.S. 14 - QUEENS | SCA IEH | PO18-TEST CLOSET CEILINGS IN ROOMS 4417C & 4452 FOR ACM LOOSE PARTICLES ARE FALLING DOWN, HOLES EXPO | Construction | Complete | 8/1/2024 | IEH | 8/23/2024 | IEH | 17841 | 1026
24 | Q014 | P.S. 14 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 2/21/2022 | FTK |  | FTK | 307586 | 183392
24 | Q014 | P.S. 14 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500000 | 0
24 | Q014 | P.S. 14 - QUEENS | DOE - RESOA | FY08 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
24 | Q014 | P.S. 14 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/19/2023 | DOER |  | DOER | 279947 | 0
24 | Q014 | P.S. 14 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/8/2024 | DOES |  | DOES | 65832 | 0
24 | Q019 | P.S. 19 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/8/2021 | 12/6/2021 | 11/17/2021 | 0 | 38553 | 38553
24 | Q019 | P.S. 19 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/29/2023 | DIIR | 2/2/2024 | DIIR | 52000
24 | Q019 | P.S. 19 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
24 | Q019 | P.S. 19 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/27/2022 | DOES |  | DOES | 120743 | 0
24 | Q028 | P.S. 28 - QUEENS | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 770 | 770
24 | Q028 | P.S. 28 - QUEENS | Fast Track Projects | LSP- SEWAGE EJECTOR PUMP | Construction | In-Progress | 10/23/2023 | FTK |  | FTK | 133875 | 131394
24 | Q028 | P.S. 28 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
24 | Q028 | P.S. 28 - QUEENS | DOE - RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
24 | Q028 | P.S. 28 - QUEENS | DOE - RESOA | RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
24 | Q028 | P.S. 28 - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
24 | Q028 | P.S. 28 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
24 | Q028 | P.S. 28 - QUEENS | DOE - Skilled Trades | ACE BMS UPGRADE | Construction | In-Progress | 1/11/2023 | DOES |  | DOES | 958412 | 532610
24 | Q049 | P.S. 49 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q049 | P.S. 49 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 220000 | 0
24 | Q049 | P.S. 49 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
24 | Q049 | P.S. 49 - QUEENS | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 5/12/2023 | DOER |  | DOER | 62453 | 0
24 | Q049 | P.S. 49 - QUEENS | DOE - RESOA | FY25 RESO A HEATING PLANT UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 155000 | 0
24 | Q058 | Q009 SPED - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 35000 | 0
24 | Q058 | P.S. 58 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
24 | Q058 | P.S. 58 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
24 | Q058 | P.S. 58 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q058 | P.S. 58 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q058 | P.S. 58 - QUEENS | DOE - RESOA | FY22 RESO A WATER FOUNTAIN UPGRADES | Construction | Complete | 1/10/2024 | DOER | 1/14/2024 | DOER | 59680
24 | Q058 | P.S. 58 - QUEENS | DOE - RESOA | FY25 RESO A HEATING PLANT UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 255000 | 0
24 | Q058 | P.S. 58 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 9/8/2017 | DOES | 12/7/2019 | DOES | 175849 | 176263
24 | Q058 | P.S. 58 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/7/2024 | DOES | 5/14/2024 | DOES | 50832
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q061 | I.S. 61 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q061 | I.S. 61 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN 4TH FLOOR HALLWAY APPROX. 2000SF | Construction | Complete | 5/13/2022 | IEH | 4/19/2024 | IEH | 466 | 466
24 | Q061 | I.S. 61 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER IN ROOM 152(TEACHER'S CAFETERIA | Construction | Complete | 2/26/2024 | IEH | 4/14/2024 | IEH | 13455 | 10155
24 | Q061 | I.S. 61 - QUEENS | DIIT - RESOA | FY10 RESO A- DESKTOP COMPUTERS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500 | 0
24 | Q061 | I.S. 61 - QUEENS | DOE - RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
24 | Q061 | I.S. 61 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | Complete | 10/18/2023 | DOER | 5/6/2024 | DOER | 150000 | 198955
24 | Q061 | I.S. 61 - QUEENS | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 2/17/2021 | DOES |  | DOES | 17638 | 0
24 | Q061 | I.S. 61 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 3/1/2021 | DOES | 3/23/2021 | DOES | 129288 | 137636
24 | Q061 | I.S. 61 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/21/2023 | DOES |  | DOES | 541029 | 0
24 | Q068 | P.S. 68 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/12/2024 | DIIR | 6/21/2024 | DIIR | 50000
24 | Q068 | P.S. 68 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/2/2024 | DIIR | 50000 | 50000
24 | Q068 | P.S. 68 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q068 | P.S. 68 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
24 | Q068 | P.S. 68 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/18/2021 | DOES | 1/23/2022 | DOES | 227560 | 234259
24 | Q068 | P.S. 68 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/25/2024 | DOES | 5/1/2024 | DOES | 65832
24 | Q071 | P.S. 71 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 8/16/2024 | FTK |  | FTK | 257902 | 0
24 | Q071 | P.S. 71 - QUEENS | DIIT - Project Connect | DATA/VOICE & WIRELESS NETWORK CABLE WIRING, NETWORK SERVER EQUIPMENT, DATA/VOICE & WIRELESS NETWORK | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 298607 | 0
24 | Q071 | P.S. 71 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q071 | P.S. 71 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q071 | P.S. 71 - QUEENS | DOE - RESOA | FY18 RESO A TOILETS-STUDENTS | Construction | Complete | 11/30/2017 | DOER | 2/19/2021 | DOER | 263695 | 268222
24 | Q071 | P.S. 71 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/29/2023 | DOER |  | DOER | 303014 | 0
24 | Q073 | I.S. 73 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/8/2021 | 7/7/2021 | 6/11/2021 | 0 | 15659 | 15659
24 | Q073 | I.S. 73 - QUEENS | SCA IEH | PO18-ABATEMENT OF ACM ABATE WALLS IN BASEMENT AND ROOM 118 KITCHEN | Construction | Complete | 5/3/2024 | IEH | 5/4/2024 | IEH | 20506 | 20506
24 | Q073 | I.S. 73 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 538760 | 0
24 | Q073 | I.S. 73 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 5/31/2024 | DIIR | 50000 | 50000
24 | Q073 | I.S. 73 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q073 | I.S. 73 - QUEENS | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 10/2/2023 | DOER |  | DOER | 23607 | 0
24 | Q073 | I.S. 73 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/16/2024 | DOES |  | DOES | 433070 | 0
24 | Q073 | I.S. 73 - QUEENS | DOE - Skilled Trades | MASONRY REPAIRS | Construction | In-Progress | 1/9/2024 | DOES |  | DOES | 93507 | 74041
24 | Q075 | Q075 SPED - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 5/21/2021 | 2/23/2022 | 2/24/2023 | 0 | 0 | 0
24 | Q075 | Q075 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 232000 | 0
24 | Q075 | Q075 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 287000 | 0
24 | Q075 | Q075 SPED - QUEENS | DOE - RESOA | FY20 RESO AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 650000 | 0
24 | Q081 | P.S. 81 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR CEILING PLASTER IN 1ST FLOOR CAFETERIA | Construction | Complete | 2/21/2024 | IEH | 6/12/2024 | IEH | 441 | 441
24 | Q081 | P.S. 81 - QUEENS | SCA IEH | PO18-CHOP OUT FLOOR APRROX 18' X 18' AROUND DRAIN PIPE PENETRATING FLOOR LOCATED , TEACHERS CAFETERI | Construction | In-Progress | 7/26/2024 | IEH |  | IEH | 1052 | 302
24 | Q081 | P.S. 81 - QUEENS | DOE - RESOA | FY23 RESO A FLOORING | Construction | In-Progress | 7/5/2024 | DOER |  | DOER | 484599 | 0
24 | Q081 | P.S. 81 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 5/19/2021 | DOES |  | DOES | 112416 | 0
24 | Q081 | P.S. 81 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 6/1/2022 | DOES |  | DOES | 98766 | 0
24 | Q081 | P.S. 81 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/17/2023 | DOES | 5/3/2024 | DOES | 65832 | 11220
24 | Q081 | P.S. 81 - QUEENS | DOE - Skilled Trades | WATER MAIN VALVE REPLACEMENT | Construction | In-Progress | 1/19/2024 | DOES |  | DOES | 115607 | 0
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY19 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Scope | Complete | 12/6/2018 | 4/10/2019 | 6/10/2019 | 0 | 36095 | 36095
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY23 RESO A KITCHEN UPGRADE | Scope | Complete | 2/8/2023 | 6/8/2023 | 6/28/2023 | 0 | 18884 | 18884
24 | Q087 | P.S. 87 - QUEENS | DIIT - RESOA | FY09 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 264187 | 0
24 | Q087 | P.S. 87 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 4/19/2024 | DIIR | 50000 | 50000
24 | Q087 | P.S. 87 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q087 | P.S. 87 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/20/2023 | DOER |  | DOER | 75204 | 0
24 | Q087 | P.S. 87 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/30/2024 | DOES | 6/7/2024 | DOES | 65832
24 | Q088 | P.S. 88 - QUEENS | Fast Track Projects | IPDVS CAMERA INSTALLATION | Construction | In-Progress | 2/5/2024 | FTK |  | FTK | 486951 | 401987
24 | Q088 | P.S. 88 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 5/10/2024 | DIIR | 50000 | 50000
24 | Q088 | P.S. 88 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q088 | P.S. 88 - QUEENS | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 6/30/2022 | DOER |  | DOER | 451053 | 0
24 | Q088 | P.S. 88 - QUEENS | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/22/2022 | DOER |  | DOER | 151796 | 0
24 | Q088 | P.S. 88 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/29/2022 | DOER |  | DOER | 176787 | 0
24 | Q088 | P.S. 88 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/19/2021 | DOES |  | DOES | 80839 | 0
24 | Q088 | P.S. 88 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 5/23/2022 | DOES |  | DOES | 55978 | 0
24 | Q089 | P.S. 89 - QUEENS | SCA IEH | PO18-SAF ACCESS ABATEMENT | Construction | Complete | 4/26/2024 | IEH | 5/4/2024 | IEH | 24268 | 3108
24 | Q089 | P.S. 89 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN 1ST FLOOR HALLWAY APPROX. 396SF | Construction | In-Progress | 5/28/2024 | IEH |  | IEH | 998 | 423
24 | Q089 | P.S. 89 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 10/23/2023 | FTK |  | FTK | 534985 | 267835
24 | Q089 | P.S. 89 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 51000 | 0
24 | Q089 | P.S. 89 - QUEENS | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/31/2023 | DOER |  | DOER | 443333 | 0
24 | Q089 | P.S. 89 - QUEENS | DOE - RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 315128 | 0
24 | Q089 | P.S. 89 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
24 | Q089 | P.S. 89 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 10/22/2021 | DOES | 2/21/2022 | DOES | 130430 | 82640
24 | Q089 | P.S. 89 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/7/2020 | DOES |  | DOES | 192500 | 0
24 | Q089 | P.S. 89 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/21/2024 | DOES |  | DOES | 65832 | 0
24 | Q091 | P.S. 91 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR PIPE/ JOINT INSULATION, CEILING PLASTER, WALL PLASTER, WALL BOARD MASTIC, FIRE | Construction | In-Progress | 12/21/2022 | IEH |  | IEH | 961 | 386
24 | Q091 | P.S. 91 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q091 | P.S. 91 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/12/2024 | DOER |  | DOER | 179126 | 0
24 | Q091 | P.S. 91 - QUEENS | DOE - Skilled Trades | DEP GREEN INFRASTRUCTURE | Construction | In-Progress | 4/30/2021 | DOES |  | DOES | 185484 | 0
24 | Q091 | P.S. 91 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 4/26/2024 | DOES | 65832 | 189
24 | Q091 | P.S. 91 - QUEENS | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 5/7/2024 | DOES |  | DOES | 74916 | 0
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | In-Progress | 7/3/2024 | 11/4/2024 |  | 0 | 23134 | 13579
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q093 | I.S. 93 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q093 | I.S. 93 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
24 | Q093 | I.S. 93 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q093 | I.S. 93 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q093 | I.S. 93 - QUEENS | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 3/22/2024 | DOEL |  | DOEL | 68461 | 68461
24 | Q093 | Q075 SPED - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 159856 | 0
24 | Q102 | P.S. 102 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q102 | P.S. 102 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q102 | P.S. 102 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q102 | P.S. 102 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q102 | P.S. 102 - QUEENS | SCA IEH | PO18-TEST ROOM 338 & IF POSITIVE ABATE & REPLACE TEST ALL LAYERS OF FLOOR PLEASE NOTIFY ALL COPIED O | Construction | Complete | 7/17/2024 | IEH | 9/1/2024 | IEH | 56770 | 1920
24 | Q102 | P.S. 102 - QUEENS | SCA IEH | PO18-77/24Q102/ ACM TESTING OF CEILING CLASSROOM 321 PLASTER AND PAINT HAS FALLEN FROM THE CEILING R | Construction | Complete | 9/17/2024 | IEH | 9/21/2024 | IEH | 14935 | 724
24 | Q102 | P.S. 102 - QUEENS | Fast Track Projects | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 12/20/2018 | FTK |  | FTK | 100215 | 83625
24 | Q102 | P.S. 102 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/29/2023 | DIIR |  | DIIR | 200000 | 0
24 | Q102 | P.S. 102 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
24 | Q102 | P.S. 102 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q102 | P.S. 102 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q102 | P.S. 102 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 240000 | 0
24 | Q113 | P.S. 113 - QUEENS | Fast Track Projects | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | FTK | FTK | FTK | FTK | 399650 | 361452
24 | Q113 | P.S. 113 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/24/2023 | DIIR |  | DIIR | 50000 | 0
24 | Q113 | P.S. 113 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 5/27/2024 | DIIR | 100000
24 | Q113 | P.S. 113 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
24 | Q113 | P.S. 113 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/1/2023 | DOER |  | DOER | 94087 | 0
24 | Q113 | P.S. 113 - QUEENS | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/3/2023 | DOER |  | DOER | 69307 | 0
24 | Q113 | P.S. 113 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
24 | Q119 | I.S. 119 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Scope | Complete | 3/2/2023 | 7/3/2023 | 8/23/2023 | 0 | 18292 | 18292
24 | Q119 | I.S. 119 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | Complete | 7/18/2019 | EMER | 5/4/2024 | EMER | 61460 | 46490
24 | Q119 | I.S. 119 - QUEENS | Fast Track Projects | LSP REPLACEMENT OF GAS FIRED WATER HEATER | Construction | In-Progress | 9/8/2020 | FTK |  | FTK | 170828 | 106350
24 | Q119 | I.S. 119 - QUEENS | Fast Track Projects | REPLACEMENT OF ROOF TOP AC UNITS | Construction | Complete | 6/13/2022 | FTK | 10/25/2022 | FTK | 3050547 | 2982067
24 | Q119 | I.S. 119 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 7/2/2024 | DIIR | 50000
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY09 RESO A- AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 35369 | 0
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY18 RESO A ROOM CONVERSION/PARTITIONING | Construction | In-Progress | 9/10/2018 | DOER |  | DOER | 63596 | 0
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/30/2023 | DOER |  | DOER | 246908 | 0
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 14318 | 0
24 | Q119 | I.S. 119 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 135000 | 0
24 | Q125 | I.S. 125 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 81000 | 0
24 | Q125 | I.S. 125 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q125 | I.S. 125 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/24/2022 | DOER |  | DOER | 65723 | 0
24 | Q125 | I.S. 125 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 6/1/2020 | DOES |  | DOES | 60341 | 0
24 | Q143 | P.S. 143 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
24 | Q143 | P.S. 143 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 175000
24 | Q143 | P.S. 143 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 47908 | 0
24 | Q143 | P.S. 143 - QUEENS | DOE - RESOA | FY24 RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 123000 | 0
24 | Q143 | P.S. 143 - QUEENS | DOE - RESOA | FY25 RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
24 | Q143 | P.S. 143 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/11/2017 | DOES |  | DOES | 174753 | 0
24 | Q153 | P.S. 153 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
24 | Q153 | P.S. 153 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 5/31/2024 | DIIR | 50000 | 50000
24 | Q153 | P.S. 153 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q153 | P.S. 153 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/22/2023 | DOER |  | DOER | 550000 | 0
24 | Q153 | P.S. 153 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0
24 | Q153 | P.S. 153 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 110000 | 0
24 | Q153 | P.S. 153 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 110000 | 0
24 | Q153 | P.S. 153 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 2/1/2021 | DOES | 5/25/2021 | DOES | 135275 | 137344
24 | Q153 | P.S. 153 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/22/2024 | DOES | 5/31/2024 | DOES | 65832
24 | Q199 | P.S. 199 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
24 | Q199 | P.S. 199 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 6/20/2024 | DIIR | 150000 | 150000
24 | Q199 | P.S. 199 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q199 | P.S. 199 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
24 | Q199 | P.S. 199 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/9/2024 | DOER |  | DOER | 3338 | 0
24 | Q199 | P.S. 199 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 2/7/2020 | DOES | 12/7/2020 | DOES | 196684 | 199919
24 | Q229 | P.S. 229 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q229 | P.S. 229 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q229 | P.S. 229 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q229 | P.S. 229 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q229 | P.S. 229 - QUEENS | SCA IEH | PO18-PLEASE ABATE AND REPLACE APPOX 500 SQ FT OF FLOOR TILE LOCATION - PRINCIPALS OFFICE | Construction | Complete | 5/17/2023 | IEH | 4/19/2024 | IEH | 0 | 0
24 | Q229 | P.S. 229 - QUEENS | SCA IEH | PO18-PLEASE REPLACE FLOOR 9X9 TILE APPROX 1000 SQ FT AND REMOVE BOOKSHELVES CONTAINS POSS ACM LOCATI | Construction | In-Progress | 5/17/2023 | IEH |  | IEH | 13075 | 0
24 | Q229 | P.S. 229 - QUEENS | SCA IEH | PO18-77/24Q229 /ROOM 121 BREAK CINDER BLOCK WALL OPEN AND ABATE ALL INSULATION ON WATER LINES AND CL | Construction | Complete | 5/31/2024 | IEH | 6/1/2024 | IEH | 17837 | 2023
24 | Q229 | P.S. 229 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q229 | P.S. 229 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/22/2021 | DOER |  | DOER | 116689 | 0
24 | Q229 | P.S. 229 - QUEENS | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 11772 | 0
24 | Q229 | P.S. 229 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 9/18/2023 | DOER |  | DOER | 754633 | 0
24 | Q229 | P.S. 229 - QUEENS | DOE - Skilled Trades | BOILER REPAIR | Construction | In-Progress | 2/5/2020 | DOES |  | DOES | 1351480 | 0
24 | Q229 | P.S. 229 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/16/2024 | DOES | 6/14/2024 | DOES | 65832
24 | Q229 | P.S. 229 - QUEENS | Trust For Public Land | FY22 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 1/2/2024 | TPL |  | TPL | 2700000 | 2442826
24 | Q239 | P.S. 239 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/16/2023 | 5/17/2023 | 6/15/2023 | 0 | 33811 | 33769
24 | Q239 | P.S. 239 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 3/31/2022 | FTK |  | FTK | 226636 | 95713
24 | Q239 | P.S. 239 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/20/2021 | DOER |  | DOER | 258791 | 0
24 | Q239 | P.S. 239 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/12/2024 | DOER |  | DOER | 12418 | 0
24 | Q245 | P.S. 305 - QUEENS | Fast Track Projects | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/12/2023 | FTK |  | FTK | 54708 | 52080
24 | Q245 | P.S. 305 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 165000 | 0
24 | Q245 | P.S. 305 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 9/25/2023 | DOER |  | DOER | 150000 | 0
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY22 RESO A PA SYSTEM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 349 | 349
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/28/2023 | 4/1/2024 | 3/5/2024 | 0 | 9240 | 9240
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/28/2023 | 2/29/2024 | 2/28/2024 | 0 | 23935 | 23873
24 | Q247 | P.S. 128 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q247 | P.S. 128 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/28/2023 | DOER |  | DOER | 156649 | 0
24 | Q247 | P.S. 128 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 10/5/2019 | DOES |  | DOES | 114157 | 0
24 | Q247 | P.S. 128 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/17/2024 | DOES | 6/25/2024 | DOES | 50832
24 | Q260 | P.S. 307 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
24 | Q260 | P.S. 307 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
24 | Q269 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY16 RESO A LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q269 | Q721 SPED - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/26/2024 | IEH | 5/25/2024 | IEH | 14372 | 4181
24 | Q269 | Q721 SPED - QUEENS | SCA IEH | PO18-ABATE & REMOVE WINDOWS IN TEACHER'S LOUNGE WINDOW CAULKING IS ACM | Construction | In-Progress | 8/19/2024 | IEH |  | IEH | 374 | 374
24 | Q269 | ELM TREE ELEMENTARY SCHOOL | DOE - RESOA | FY16 RESO A PLAYGROUND REDEVELOPMENT | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
24 | Q287 | P.S. 330 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 4/15/2024 | DIIR | 150000 | 150000
24 | Q287 | P.S. 330 - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 42180 | 0
24 | Q287 | P.S. 330 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q290 | P.S. 290 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q290 | P.S. 290 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q290 | P.S. 290 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q290 | P.S. 290 - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/29/2023 | DOER |  | DOER | 138865 | 0
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/10/2022 | 6/8/2022 | 8/19/2022 | 0 | 7636 | 7636
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 12/13/2023 | 4/15/2024 | 6/17/2024 | 0 | 7549 | 7549
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 350000 | 0
24 | Q311 | CORONA ARTS AND SCIENCES ACADEMY | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 300000 | 0
24 | Q311 | CORONA ARTS AND SCIENCES ACADEMY | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0
24 | Q311 | CORONA ARTS AND SCIENCES ACADEMY | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
24 | Q311 | CORONA ARTS AND SCIENCES ACADEMY | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/10/2024 | DOES | 6/14/2024 | DOES | 50832
24 | Q313 | THE CHILDREN'S LAB SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/23/2024 | DIIR |  | DIIR | 75000 | 0
24 | Q313 | THE CHILDREN'S LAB SCHOOL | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 12/1/2021 | DOER |  | DOER | 109130 | 0
24 | Q313 | THE CHILDREN'S LAB SCHOOL | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 151256 | 0
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | RESO A ROOM CONVERSION | Scope | Complete | 9/14/2022 | 1/13/2023 | 1/20/2023 | 0 | 15661 | 15661
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q315 | P.S. 110 - QUEENS | Fast Track Projects | RESO A IPDVS CAMERA INSTALLATION | Construction | In-Progress | 1/3/2024 | FTK |  | FTK | 149338 | 114787
24 | Q315 | P.S. 110 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/15/2024 | DIIR | 5/24/2024 | DIIR | 100000
24 | Q315 | P.S. 110 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 238000 | 0
24 | Q315 | P.S. 110 - QUEENS | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
24 | Q315 | P.S. 110 - QUEENS | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
24 | Q320 | P.S. 305 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 8/21/2024 | DOER |  | DOER | 365991 | 0
24 | Q322 | THE RIVERVIEW SCHOOL - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING LOCATIONS ROOMS: 102, 107, 107A, 107B, 107D, 107 | Construction | Complete | 6/14/2023 | IEH | 8/30/2024 | IEH | 269026 | 2297
24 | Q322 | THE RIVERVIEW SCHOOL - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/4/2024 | IEH | 6/5/2024 | IEH | 10935 | 10935
24 | Q348 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/12/2024 | DOES |  | DOES | 65832 | 0
24 | Q368 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/17/2024 | DOES |  | DOES | 50832 | 0
24 | Q369 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/10/2024 | DOES | 5/17/2024 | DOES | 50832 | 2230
24 | Q373 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/23/2024 | DOES |  | DOES | 50832 | 0
24 | Q391 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/2/2024 | DOES | 4/11/2024 | DOES | 65832 | 378
24 | Q392 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 65832 | 0
24 | Q414 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/27/2023 | DOES |  | DOES | 50832 | 0
24 | Q419 | NEW 2021 D.24 MS IN BUILDING Q419 | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
24 | Q419 | NEW 2021 D.24 MS IN BUILDING Q419 | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/19/2024 | DOES |  | DOES | 50832 | 0
24 | Q422 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/27/2023 | DOES |  | DOES | 50832 | 0
24 | Q437 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/17/2024 | DOES |  | DOES | 65832 | 0
24 | Q437 | PRE-K CENTER @ 98-22 55 AVENUE - QUEENS | DOE Managed PRE-K | LEASE | Construction | In-Progress | 9/7/2017 | DOEP |  | DOEP | 662334 | 0
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP RESOA | FY22 RESO A CAFETERIA UPGRADE | Scope | Complete | 4/14/2022 | 8/15/2022 | 7/6/2023 | 0 | 35395 | 35395
24 | Q455 | NEWTOWN HS - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 4/23/2021 | EMER |  | EMER | 352792 | 309797
24 | Q455 | NEWTOWN HS - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING LOCATIONS: STAIRCASE 1 APPROX. 65SF VESTIBULE/ E | Construction | Complete | 1/19/2023 | IEH | 4/22/2024 | IEH | 342325 | 4793
24 | Q455 | NEWTOWN HS - QUEENS | DOE - RESOA | FY16 RESO A LIBRARY UPGRADE | Construction | Complete | 7/27/2021 | DOER | 5/15/2023 | DOER | 518296 | 655836
24 | Q455 | NEWTOWN HS - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
24 | Q455 | NEWTOWN HS - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 6/1/2020 | DOES |  | DOES | 61426 | 0
24 | Q455 | NEWTOWN HS - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/1/2022 | DOES | 1/16/2023 | DOES | 236590 | 4000
24 | Q455 | NEWTOWN HS - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 8/2/2023 | DOES |  | DOES | 722572 | 0
24 | Q455 | INTERNATIONAL HIGH SCHOOL FOR HEALTH SCIENCES | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/8/2024 | DOES |  | DOES | 676227 | 0
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | FY23 RESO A ROOFTOP PLAYGROUND | Scope | In-Progress | 3/29/2023 | 8/14/2023 |  | 0 | 21807 | 9950
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP PLAYGROUND | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP PLAYGROUND | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP PLAYGROUND | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOFTOP PLAYGROUND | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/6/2023 | DOER |  | DOER | 143326 | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/30/2021 | EMER |  | EMER |  | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA IEH | PO18-ASSIGNED TO SCA AS AN EMERGENCY ON 6/27/24 | Construction | Complete | 6/28/2024 | IEH | 7/3/2024 | IEH | 10800 | 815
24 | Q485 | GROVER CLEVELAND HS - QUEENS | Fast Track Projects | LSP RESO A CAFETERIA UPGRADE - LIGHTING | Construction | PNS | FTK | FTK | FTK | FTK | 300823 | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 9/20/2022 | FTK |  | FTK | 263277 | 54169
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 125874 | 0
24 | Q485 | THE RIVERVIEW SCHOOL - QUEENS | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/12/2024 | DOER |  | DOER | 580359 | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
24 | Q485 | THE RIVERVIEW SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 11/18/2018 | DOES |  | DOES | 346062 | 0
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 11/29/2019 | DOES | 9/22/2020 | DOES | 440513 | 43028
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | Complete | 11/29/2021 | DOES | 1/31/2023 | DOES | 1075148 | 625424
24 | Q485 | GROVER CLEVELAND HS - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 12/30/2022 | DOES |  | DOES | 671001 | 0
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/25/2022 | DOES |  | DOES | 308282 | 0
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 65832 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 60000 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 10/7/2022 | DOER |  | DOER | 430056 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 68658 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 4/7/2023 | DOES |  | DOES | 60422 | 0
24 | Q585 | MASPETH HIGH SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/16/2024 | DOES |  | DOES | 50832 | 0
24 | Q600 | QUEENS TECH HS - Q | SCA CIP RESOA | FY18 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 9/4/2019 | 1/7/2020 | 10/2/2019 | 0 | 7037 | 7037
24 | Q600 | QUEENS TECH HS - Q | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 9/20/2022 | FTK |  | FTK | 82158 | 70314
24 | Q600 | QUEENS TECH HS - Q | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
24 | Q600 | QUEENS TECH HS - Q | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/5/2022 | DOER |  | DOER | 19881 | 0
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | FY25 RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q610 | AVIATION HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q610 | AVIATION HS - QUEENS | SCA Emergency Response | IDA TEMPORARY BOILER- RED DOT | Construction | In-Progress | 8/5/2022 | EMER |  | EMER | 1670134 | 1461549
24 | Q610 | AVIATION HS - QUEENS | Fast Track Projects | TEMPORARY FILTER WORK | Construction | In-Progress | 3/9/2020 | FTK |  | FTK | 597617 | 587785
24 | Q610 | AVIATION VOCATIONAL H.S. | DOE - RESOA | FY08 RESO A PLAYGROUND REDEVELOPMEN | Construction | PNS | PNS | PNS | PNS | DOER | 288309 | 0
24 | Q610 | AVIATION HS - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 119235 | 0
24 | Q610 | AVIATION HS - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 11/16/2018 | DOES |  | DOES | 159718 | 0
24 | Q610 | AVIATION HS - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/9/2023 | DOES |  | DOES | 554166 | 0
24 | Q610 | AVIATION HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/13/2024 | DOES | 6/24/2024 | DOES | 65832
24 | Q610 | AVIATION HS - QUEENS | DOE - Skilled Trades | ESCALATOR UPGRADES | Construction | In-Progress | 1/29/2024 | DOES |  | DOES | 398000 | 0
24 | Q721 | P.S. 16 - QUEENS | Fast Track Projects | LSP WATER HEATER | Construction | In-Progress | 1/7/2019 | FTK |  | FTK | 256639 | 247664
24 | Q721 | P.S. 16 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 88000 | 0
24 | Q721 | P.S. 16 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/10/2024 | DIIR |  | DIIR | 50000 | 0
24 | Q721 | P.S. 16 - QUEENS | DOE - RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
24 | Q721 | P.S. 16 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/21/2024 | DOES | 5/30/2024 | DOES | 65832
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 8/23/2021 | 11/23/2021 | 2/11/2022 | 0 | 34842 | 34274
24 | Q722 | Q721 SPED - QUEENS | Fast Track Projects | LSP FY22 RESO A CAFETERIA UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 34447 | 34334
24 | Q722 | Q721 SPED - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/30/2023 | DIIR | 5/20/2024 | DIIR | 413000 | 413000
24 | Q722 | Q721 SPED - QUEENS | DOE - RESOA | FY23 RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
24 | Q722 | Q721 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0
24 | Q722 | Q721 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 700000 | 0
24 | Q722 | Q721 SPED - QUEENS | DOE - Skilled Trades | DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 2/2/2023 | DOES |  | DOES | 83809 | 0
24 | Q722 | Q721 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/28/2024 | DOES |  | DOES | 50832 | 0
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP RESOA | FY18 RESO CLASSROOM CONVERSION | Scope | Complete | 11/27/2018 | 3/15/2019 | 3/13/2019 | 0 | 27178 | 16866
24 | Q735 | HS OF APPLIED COMMUNICATION-Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 6/11/2024 | DOER |  | DOER | 41580 | 0
24 | Q744 | PAN AMERICAN INTERNATIONAL HS - QUEENS | DOE - RESOA | FY16 RESO A CAFETERIA/MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
24 | Q744 | VOYAGES PREPARATORY - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/30/2024 | DOES | 5/7/2024 | DOES | 50832
24 | Q777 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
24 | Q777 | MOSAIC PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/13/2023 | DOES |  | DOES | 65832 | 0
24 | Q841 | PS 23 @ HILLSIDE PSYCH - Q | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 9/13/2024 | IEH | 9/26/2024 | IEH | 9666 | 91
24 | Q848 | P.S. 81 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE / FY21 RESO A CAFETERIA UPGRADE | Scope | Complete | 7/13/2021 | 3/15/2022 | 5/6/2022 | 0 | 7771 | 7771
24 | Q849 | I.S. 77 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/12/2024 | DIIR | 8/21/2024 | DIIR | 56000
24 | Q849 | BUSHWICK LEADERS - K | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 185000 | 0
24 | Q849 | I.S. 77 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 80000 | 0
24 | Q849 | I.S. 77 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
24 | Q849 | I.S. 77 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/8/2024 | DOES |  | DOES | 645132 | 0
24 | Q876 | Q075 SPED - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/26/2024 | IEH | 4/30/2024 | IEH | 9120 | 9120
24 | Q877 | P.S. 7 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/3/2024 | IEH | 11190 | 11190
24 | Q877 | P.S. 7 - QUEENS | Fast Track Projects | LSP FLOORING REPLACEMENT | Construction | In-Progress | 5/6/2024 | FTK |  | FTK | 347789 | 7799
24 | Q891 | R. F. WAGNER SEC SCL ARTS & TECH-Q | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/17/2024 | IEH | 6/12/2024 | IEH | 15511 | 388
24 | Q908 | P.S. 143 - QUEENS | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 9/15/2020 | FTK |  | FTK | 126063 | 126063
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/16/2023 | 1/22/2024 | 12/13/2023 | 0 | 5799 | 5799
25 | Q020 | P.S. 20 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 3/7/2022 | FTK |  | FTK | 319188 | 129157
25 | Q020 | P.S. 20 - QUEENS | Fast Track Projects | GYM FLOOR REPLACEMENT | Construction | In-Progress | 8/8/2023 | FTK |  | FTK | 713359 | 639889
25 | Q020 | P.S. 20 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
25 | Q020 | P.S. 20 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE RAMP | Construction | Complete | 9/19/2018 | DOES | 3/27/2020 | DOES | 375036 | 189304
25 | Q020 | P.S. 20 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
25 | Q020 | P.S. 20 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/8/2023 | DOER |  | DOER | 12230 | 0
25 | Q020 | P.S. 20 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 3/30/2019 | DOES |  | DOES | 72176 | 0
25 | Q020 | P.S. 20 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/19/2024 | DOES | 4/2/2024 | DOES | 65832 | 33553
25 | Q021 | P.S. 21 - QUEENS | SCA IEH | PO18-ABATE 12 LINEAR FEET ACM LOCATION BASEMENT HALLWAY CEILING OUTSIDE B8 3 RISER VALVES | Construction | In-Progress | 9/19/2024 | IEH |  | IEH | 91 | 91
25 | Q021 | P.S. 21 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 402191 | 0
25 | Q021 | P.S. 21 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 280299 | 0
25 | Q021 | P.S. 21 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
25 | Q021 | P.S. 21 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/15/2024 | DOES | 4/12/2024 | DOES | 65832 | 378
25 | Q022 | P.S. 22 - QUEENS | DIIT - RESOA | FY21 RESO A (MA) TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 250000 | 0
25 | Q022 | P.S. 22 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/24/2024 | DIIR | 350000
25 | Q022 | P.S. 22 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 360000 | 0
25 | Q022 | P.S. 22 - QUEENS | DOE - RESOA | FY17 RESO A AUDITORIUM UPGRADE | Construction | Complete | 4/15/2021 | DOER | 12/27/2022 | DOER | 163099 | 35447
25 | Q022 | P.S. 22 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
25 | Q022 | P.S. 22 - QUEENS | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 5/9/2016 | DOES |  | DOES | 194136 | 0
25 | Q022 | P.S. 22 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 9/8/2017 | DOES | 12/2/2019 | DOES | 187711 | 189945
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | SCA IEH | PO18-77/25Q023/TEST GYM CEILING PLASTER IF POSITIVE SOUND OUT ENTIRE CEILING AND ABATE AND REPAIR AS | Construction | Complete | 5/4/2024 | IEH | 5/5/2024 | IEH | 16322 | 1722
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | SCA IEH | PO18-TEST FOR ACM. WALLS IN ROOM 101 | Construction | Complete | 6/18/2024 | IEH | 6/22/2024 | IEH | 14527 | 954
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | SCA IEH | PO18-ABATE & REMOVE FLOOR TILES ROOM - 106 ; 151 | Construction | Complete | 6/25/2024 | IEH | 7/12/2024 | IEH | 44391 | 761
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | Fast Track Projects | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 10/23/2023 | FTK |  | FTK | 103686 | 103642
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/10/2024 | DIIR | 5/13/2024 | DIIR | 50000 | 50000
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/11/2023 | DOER |  | DOER | 52593 | 0
25 | Q023 | QUEENS ACADEMY HIGH SCHOOL - Q | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/1/2023 | 4/4/2024 | 2/22/2024 | 0 | 15672 | 15672
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q024 | P.S. 24 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR CEILING AND PLASTER IN THE AUDITORIUM CE JERRY GIAMMATTEO | Construction | In-Progress | 5/28/2024 | IEH |  | IEH | 785 | 210
25 | Q024 | P.S. 24 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 522016 | 0
25 | Q024 | P.S. 24 - QUEENS | DOE - RESOA | FY21 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 9/29/2023 | DOER |  | DOER | 290060 | 0
25 | Q024 | P.S. 24 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
25 | Q024 | P.S. 24 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/26/2024 | DOES |  | DOES | 65832 | 0
25 | Q025 | Q233 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
25 | Q025 | J.H.S. 25 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 5/27/2024 | DIIR | 50000
25 | Q025 | J.H.S. 25 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 9/8/2017 | DOES | 12/2/2019 | DOES | 143766 | 145889
25 | Q029 | P.S. 29 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | Complete | 1/31/2022 | FTK | 11/16/2023 | FTK | 190932 | 187188
25 | Q029 | P.S. 29 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 357192 | 0
25 | Q029 | P.S. 29 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/19/2024 | DOER |  | DOER | 70128 | 0
25 | Q029 | P.S. 29 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/28/2024 | DOES |  | DOES | 65832 | 0
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | FY19 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 1/14/2019 | 9/23/2019 | 10/17/2019 | 0 | 21599 | 21599
25 | Q032 | P.S. 32 - QUEENS | Fast Track Projects | LSP FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 7/10/2023 | FTK |  | FTK | 290182 | 275719
25 | Q032 | P.S. 32 - QUEENS | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
25 | Q032 | P.S. 32 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/3/2024 | DOES | 5/21/2024 | DOES | 65832 | 16703
25 | Q079 | P.S. 79 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Scope | Complete | 2/14/2023 | 5/15/2023 | 5/22/2023 | 0 | 31564 | 27804
25 | Q079 | P.S. 79 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
25 | Q079 | P.S. 79 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
25 | Q079 | P.S. 79 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/15/2024 | DOES | 5/20/2024 | DOES | 65832 | 4112
25 | Q079 | P.S. 79 - QUEENS | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/6/2023 | DOES |  | DOES | 472009 | 334719
25 | Q107 | P.S. 107 - QUEENS | SCA CIP RESOA | FY16 RESO A MEDIA CENTER UPGRADE | Scope | Complete | 8/27/2019 | 12/31/2019 | 4/23/2021 | 0 | 11805 | 11805
25 | Q107 | P.S. 107 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING LOCATIONS: 1ST FLOOR STAIRWELL #8(NOW STAIRWELL | Construction | In-Progress | 10/10/2023 | IEH |  | IEH | 756 | 181
25 | Q107 | P.S. 107 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 104000 | 0
25 | Q120 | P.S. 120 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/26/2021 | EMER |  | EMER | 322765 | 172469
25 | Q120 | P.S. 120 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/21/2024 | DIIR | 88000 | 88000
25 | Q120 | P.S. 120 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/10/2021 | DOER |  | DOER | 479311 | 0
25 | Q120 | P.S. 120 - QUEENS | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 11/23/2020 | DOES |  | DOES | 5339 | 0
25 | Q120 | P.S. 120 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/15/2024 | DOES | 4/22/2024 | DOES | 65832 | 22016
25 | Q129 | P.S. 129 - QUEENS | Fast Track Projects | LSP DOMESTIC HOT WATER HEATER | Construction | In-Progress | 9/20/2022 | FTK |  | FTK | 81040 | 61596
25 | Q129 | P.S. 129 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
25 | Q129 | P.S. 129 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
25 | Q154 | Q255 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
25 | Q154 | P.S. 154 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
25 | Q154 | P.S. 154 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
25 | Q154 | Q255 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 100000 | 0
25 | Q154 | P.S. 154 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/19/2019 | DOES | 3/6/2020 | DOES | 82369 | 85608
25 | Q163 | P.S. 163 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 350467 | 0
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/19/2024 | DOER |  | DOER | 42091 | 0
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/8/2022 | DOER |  | DOER | 233811 | 0
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
25 | Q163 | P.S. 163 - QUEENS | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
25 | Q163 | P.S. 163 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/10/2024 | DOES | 4/18/2024 | DOES | 65832 | 12831
25 | Q164 | P.S. 164 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 3/6/2023 | FTK |  | FTK | 483011 | 375020
25 | Q164 | P.S. 164 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/21/2023 | DIIR |  | DIIR | 100000 | 0
25 | Q164 | P.S. 164 - QUEENS | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 11/17/2021 | DOER |  | DOER | 83173 | 0
25 | Q164 | P.S. 164 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/10/2024 | DOES | 6/17/2024 | DOES | 65832
25 | Q165 | P.S. 165 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN CAFETERIA 134A APPROX. 1760SF | Construction | Complete | 6/1/2023 | IEH | 5/13/2024 | IEH | 792 | 217
25 | Q165 | P.S. 165 - QUEENS | SCA IEH | PO18-ABATE 9X9 TILES ROOM 113 APPROX 8 SQFT PHOTOS OF AREA IN EMAIL. CE KNOWS EXACT LOCATION. | Construction | Complete | 4/19/2024 | IEH | 5/19/2024 | IEH | 19679 | 15279
25 | Q165 | P.S. 165 - QUEENS | DOE - RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 7/31/2019 | DOER |  | DOER | 490623 | 0
25 | Q165 | P.S. 165 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/1/2024 | DOES | 4/10/2024 | DOES | 65832 | 25563
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA IEH | PO18-ABATE AND REPAIR CEILING PLASTER IN 3RD FLOOR HALLWAY | Construction | Complete | 5/7/2024 | IEH | 5/12/2024 | IEH | 15774 | 10974
25 | Q168 | I.S. 250 - QUEENS | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/1/2024 | DOER |  | DOER | 296731 | 0
25 | Q168 | Q255 SPED - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 8/16/2024 | DOER |  | DOER | 178540 | 0
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 5/30/2022 | DOES | 8/26/2022 | DOES | 187932 | 3379
25 | Q169 | I.S. 294 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Scope | Complete | 8/12/2021 | 12/15/2021 | 12/29/2021 | 0 | 9970 | 9970
25 | Q169 | I.S. 294 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
25 | Q169 | I.S. 294 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
25 | Q169 | I.S. 294 - QUEENS | DOE - RESOA | RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/22/2023 | DOER |  | DOER | 59485 | 0
25 | Q169 | I.S. 294 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 395000 | 0
25 | Q169 | P.S. 169 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
25 | Q184 | P.S. 184 - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/29/2022 | 7/29/2022 | 7/28/2022 | 0 | 104799 | 96560
25 | Q184 | P.S. 184 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
25 | Q184 | P.S. 184 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/23/2021 | DOES | 11/1/2022 | DOES | 154977 | 127657
25 | Q184 | P.S. 184 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/4/2024 | DOES | 4/15/2024 | DOES | 65832 | 10133
25 | Q185 | J.H.S. 185 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
25 | Q185 | J.H.S. 185 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
25 | Q185 | J.H.S. 185 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 66000 | 0
25 | Q185 | J.H.S. 185 - QUEENS | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/22/2024 | 5/21/2024 | 6/26/2024 | 0 | 17494 | 279
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/6/2024 | 8/7/2024 | 8/1/2024 | 0 | 0 | 0
25 | Q189 | J.H.S. 189 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 100000 | 0
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY10 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 60705 | 0
25 | Q189 | THE FLUSHING INTERNATIONAL HS - Q | DOE - RESOA | FY16 RESO A ELECTRICAL SYSTEMS | Construction | In-Progress | 4/16/2018 | DOER |  | DOER | 143060 | 0
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1630098 | 0
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 9/21/2022 | DOER |  | DOER | 392230 | 0
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY23 RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
25 | Q189 | J.H.S. 189 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 9/13/2023 | DOER |  | DOER | 30677 | 0
25 | Q189 | J.H.S. 189 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 4/18/2019 | DOES | 8/31/2019 | DOES | 199166 | 200323
25 | Q189 | J.H.S. 189 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/26/2024 | DOES |  | DOES | 727467 | 0
25 | Q193 | P.S. 193 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS 103 APPROX. 552SF 107 APPROX. 294SF | Construction | Complete | 7/3/2023 | IEH | 5/24/2024 | IEH | 632 | 57
25 | Q193 | P.S. 193 - QUEENS | SCA IEH | PO18-TEST AUDITORIUM CEILING FOR ACM. PLASTER BUBBLING | Construction | Complete | 7/25/2024 | IEH | 8/31/2024 | IEH | 8302 | 1063
25 | Q193 | P.S. 193 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 6/20/2024 | DIIR |  | DIIR | 250000 | 0
25 | Q193 | P.S. 193 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/22/2022 | DOER |  | DOER | 130521 | 0
25 | Q193 | P.S. 193 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
25 | Q193 | P.S. 193 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
25 | Q193 | P.S. 193 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/3/2024 | DOES | 5/16/2024 | DOES | 65832
25 | Q194 | J.H.S. 194 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
25 | Q194 | J.H.S. 194 - QUEENS | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 8/2/2021 | DOER |  | DOER | 152773 | 0
25 | Q194 | J.H.S. 194 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
25 | Q200 | P.S. 200 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q200 | P.S. 200 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q200 | P.S. 200 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q200 | P.S. 200 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q200 | P.S. 200 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 150000
25 | Q200 | P.S. 200 - QUEENS | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | Complete | 2/18/2022 | DOER | 4/21/2023 | DOER | 212629 | 31954
25 | Q200 | P.S. 200 - QUEENS | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 56570 | 0
25 | Q200 | P.S. 200 - QUEENS | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0
25 | Q201 | P.S. 201 - QUEENS | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 160 | 160
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/4/2022 | 6/7/2022 | 4/14/2022 | 0 | 4003 | 4003
25 | Q209 | P.S. 209 - QUEENS | SCA IEH | PO18-REMOVE ACM SPRAYED RED APPROX 15FT IN BOILER ROOM CRAWL SPACE , WEST CRAWL SPACE CUSTODIAN SPAC | Construction | Complete | 7/25/2024 | IEH | 8/24/2024 | IEH | 7411 | 858
25 | Q209 | Q177 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
25 | Q209 | P.S. 209 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
25 | Q209 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
25 | Q209 | P.S. 209 - QUEENS | DOE - RESOA | FY25 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
25 | Q209 | P.S. 209 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/8/2024 | DOES | 5/17/2024 | DOES | 65832 | 756
25 | Q214 | P.S. 214 - QUEENS | SCA IEH | PO18-BOILER ROOM, ABATE 5 L.F. PIPE INSULATION BASEMENT STAIRWAY TO AUDITORIUM, ABATE 6 L.F. PIPE IN | Construction | Complete | 6/28/2024 | IEH | 9/16/2024 | IEH | 11539 | 296
25 | Q214 | P.S. 214 - QUEENS | Fast Track Projects | LSP RESO A PLAYGROUND UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 239804 | 5241
25 | Q214 | P.S. 214 - QUEENS | Fast Track Projects | LSP FY23 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 7/10/2023 | FTK |  | FTK | 109013 | 1111
25 | Q214 | P.S. 214 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
25 | Q214 | P.S. 214 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0
25 | Q214 | P.S. 214 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0
25 | Q214 | P.S. 214 - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 10/30/2023 | DOER |  | DOER | 104867 | 0
25 | Q214 | P.S. 214 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/7/2024 | DOER |  | DOER | 255388 | 0
25 | Q214 | P.S. 214 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
25 | Q214 | P.S. 214 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 140000 | 0
25 | Q214 | P.S. 214 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/1/2024 | DOES | 5/8/2024 | DOES | 65832 | 2865
25 | Q219 | P.S. 219 - QUEENS | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 171706 | 0
25 | Q219 | P.S. 219 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 65832 | 0
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Scope | Complete | 3/12/2020 | 7/13/2020 | 3/17/2021 | 0 | 19221 | 19221
25 | Q237 | EAST-WEST SCHOOL OF INTL STUDIES-Q | DOE - RESOA | RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
25 | Q237 | J.H.S. 237 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/7/2023 | DOER |  | DOER | 34134 | 0
25 | Q237 | EAST-WEST SCHOOL OF INTL STUDIES-Q | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
25 | Q237 | J.H.S. 237 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 90000 | 0
25 | Q237 | J.H.S. 237 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 260000 | 0
25 | Q242 | P.S. 242 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
25 | Q242 | P.S. 242 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 60000
25 | Q242 | P.S. 242 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
25 | Q242 | P.S. 242 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 110926 | 0
25 | Q242 | P.S. 242 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
25 | Q242 | P.S. 242 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0
25 | Q244 | P.S. 244 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 6/27/2024 | DIIR | 75000 | 75000
25 | Q244 | P.S. 244 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
25 | Q244 | P.S. 244 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
25 | Q244 | P.S. 244 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
25 | Q244 | P.S. 244 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 50832 | 0
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY25 RESO A CLASSROOM UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CLASSROOM UPGRADES | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CLASSROOM UPGRADES | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CLASSROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CLASSROOM UPGRADES | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE / RESO A EXTERIOR DOOR | Scope | Complete | 5/3/2022 | 10/25/2023 | 10/18/2023 | 0 | 72925 | 66902
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 130000 | 0
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 180547 | 0
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/13/2024 | DOES | 6/21/2024 | DOES | 50832 | 189
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA IEH | PO18-64 SQUARE FEET OF CONCEALED SPLINE CEILING ON VERGE OF COLLAPSE IN MAIN (JV) ENTRANCE VESTIBUL | Construction | Complete | 8/16/2024 | IEH | 8/18/2024 | IEH | 13083 | 601
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA IEH | PO18-TEST CEILING IN LOBBY/ MAIN ENTRANCE 1ST. FLOOR FOR ACM CEILING TILE MASTIC IS ACM ABATEMENT DR | Construction | In-Progress | 9/3/2024 | IEH |  | IEH | 648 | 73
25 | Q425 | JOHN BOWNE HS - QUEENS | Fast Track Projects | IDA GYM FLOOR REPLACEMENT | Construction | In-Progress | 6/6/2022 | FTK |  | FTK | 1413623 | 1188920
25 | Q425 | JOHN BOWNE HS - QUEENS | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
25 | Q425 | JOHN BOWNE HS - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/23/2024 | DOES |  | DOES | 583961 | 0
25 | Q426 | JOHN BOWNE HS - QUEENS | SCA CIP RESOA | FY24 RESO A FARM BUILDING | Scope | In-Progress | 9/14/2023 | 12/15/2023 |  | 0 | 26663 | 4523
25 | Q426 | JOHN BOWNE HS - QUEENS | DOE - RESOA | FY24 RESO A PAVED AREA- BLACKTOP | Construction | In-Progress | 8/14/2023 | DOER |  | DOER | 374366 | 0
25 | Q454 | DISTRICT 25 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/1/2024 | DOES | 5/7/2024 | DOES | 65832 | 189
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | In-Progress | 4/2/2024 | 8/2/2024 |  | 0 | 18405 | 837
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | In-Progress | 4/2/2024 | 7/3/2024 |  | 0 | 0 | 0
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
25 | Q460 | VERITAS ACADEMY | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 256 | 256
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/15/2023 | 6/16/2023 | 11/9/2023 | 0 | 19263 | 19263
25 | Q460 | FLUSHING HS - QUEENS | SCA IEH | PO18-ROOM 235 PARTITION ACOUSTICAL FILLER WALL 14FT X 7FT IS POSITIVE FOR ACM, NEED TO BE REMOVED. C | Construction | Complete | 1/12/2024 | IEH | 4/1/2024 | IEH | 22696 | 21121
25 | Q460 | FLUSHING HS - QUEENS | SCA IEH | PO18-PLEASE TEST CORRIDOR FLOOR ON 3RD FLOOR FOR ACM. TEST ALL LAYERS INCLUDING SOFT FILL AND FELT P | Construction | Complete | 2/9/2024 | IEH | 6/25/2024 | IEH | 2436 | 661
25 | Q460 | FLUSHING HS - QUEENS | Fast Track Projects | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/11/2023 | FTK |  | FTK | 145416 | 129378
25 | Q460 | FLUSHING HS - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 100000 | 0
25 | Q460 | QUEENS HIGH SCHOOL FOR LANGUAGE STUDIES | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
25 | Q460 | QUEENS HIGH SCHOOL FOR LANGUAGE STUDIES | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
25 | Q460 | VERITAS ACADEMY | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
25 | Q460 | VERITAS ACADEMY | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 169000 | 0
25 | Q460 | FLUSHING HS - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
25 | Q460 | FLUSHING HS - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 2/13/2023 | DOER |  | DOER | 52837 | 0
25 | Q460 | FLUSHING HS - QUEENS | DOE - RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 125000 | 1187
25 | Q460 | FLUSHING HS - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 430000 | 0
25 | Q460 | VERITAS ACADEMY | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
25 | Q460 | FLUSHING HS - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 12/9/2022 | DOES |  | DOES | 427265 | 0
25 | Q460 | FLUSHING HS - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 10/16/2023 | DOES |  | DOES | 778289 | 0
25 | Q460 | FLUSHING HS - QUEENS | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 3/11/2024 | DOES |  | DOES | 571711 | 7651
25 | Q463 | FLUSHING HS - QUEENS | SCA CIP RESOA | FY23 RESO A ATHLETIC FIELD UPGRADE | Scope | Complete | 1/20/2023 | 5/19/2023 | 7/20/2023 | 0 | 217554 | 212004
25 | Q499 | P.S./I.S. 499 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 8/25/2020 | FTK |  | FTK | 155255 | 80738
25 | Q499 | Q993 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
25 | Q499 | Q993 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
25 | Q499 | P.S./I.S. 499 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 50832 | 0
25 | Q515 | TOWNSEND HARRIS HS - Q | Fast Track Projects | LSP- WATER BOOSTER PUMP SYSTEM | Construction | In-Progress | 1/7/2019 | FTK |  | FTK | 365305 | 310709
25 | Q515 | TOWNSEND HARRIS HS - Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
25 | Q515 | TOWNSEND HARRIS HS - Q | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
25 | Q515 | TOWNSEND HARRIS HS - Q | DOE - Skilled Trades | HVAC COOLING TOWER REPLACEMENT | Construction | In-Progress | 12/6/2022 | DOES |  | DOES | 2401394 | 0
25 | Q515 | TOWNSEND HARRIS HS - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/13/2024 | DOES | 5/20/2024 | DOES | 50832
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 6/8/2024 | IEH | 12597 | 1674
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/15/2024 | DIIR | 7/30/2024 | DIIR | 150000 | 150000
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | DOE - RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 10/17/2019 | DOER |  | DOER | 192361 | 0
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | Complete | 7/29/2021 | DOER | 9/27/2021 | DOER | 353819 | 100239
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 69565 | 0
25 | Q707 | R. F. KENNEDY COMM. MIDDLE/HS-Q | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
25 | Q792 | NORTH QUEENS COMMUNITY HS - Q | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 105000 | 0
25 | Q859 | REG OPERATION CENTER C- QUEENS | DOE - Skilled Trades | COOLING TOWER | Construction | In-Progress | 6/2/2016 | DOES |  | DOES | 316593 | 0
26 | Q018 | P.S. 18 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/12/2022 | DOER |  | DOER | 82800 | 0
26 | Q018 | P.S. 18 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 85000 | 0
26 | Q018 | P.S. 18 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 3976 | 0
26 | Q018 | P.S. 18 - QUEENS | DOE - Skilled Trades | BATHROOM RENOVATIONS/UPGRADES (TWO ON EACH FLOOR) | Construction | Complete | 12/21/2018 | DOES | 9/3/2019 | DOES | 208475 | 209507
26 | Q026 | P.S. 26 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 50000 | 0
26 | Q026 | P.S. 26 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 70000 | 0
26 | Q026 | P.S. 26 - QUEENS | DOE - RESOA | FY17 RESO A AUDITORIUM UPGRADE | Construction | Complete | 3/22/2021 | DOER | 2/23/2022 | DOER | 203991 | 130497
26 | Q026 | P.S. 26 - QUEENS | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
26 | Q026 | P.S. 26 - QUEENS | DOE - Skilled Trades | BATHROOM RENOVATIONS/UPGRADES (ROOM 320) | Construction | Complete | 7/12/2019 | DOES | 10/4/2019 | DOES | 161064 | 162108
26 | Q026 | P.S. 26 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/16/2024 | DOES | 4/24/2024 | DOES | 65832 | 756
26 | Q031 | P.S. 31 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
26 | Q031 | P.S. 31 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/29/2022 | DOES |  | DOES | 223562 | 0
26 | Q031 | P.S. 31 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/1/2024 | DOES | 4/8/2024 | DOES | 65832 | 378
26 | Q041 | P.S. 41 - QUEENS | SCA Emergency Response | STONE CRACKS | Construction | In-Progress | 2/4/2022 | EMER |  | EMER |  | 0
26 | Q041 | Q993 SPED - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 35000 | 0
26 | Q041 | P.S. 41 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
26 | Q041 | Q993 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
26 | Q041 | Q993 SPED - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
26 | Q041 | P.S. 41 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/15/2023 | DOES |  | DOES | 205645 | 0
26 | Q041 | P.S. 41 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/5/2024 | DOES | 4/12/2024 | DOES | 65832 | 11144
26 | Q046 | P.S. 46 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 3/28/2024 | DOER |  | DOER | 3126 | 0
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q067 | J.H.S. 67 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER IN KITCHEN B38A | Construction | Complete | 2/12/2024 | IEH | 4/13/2024 | IEH | 10524 | 2740
26 | Q067 | J.H.S. 67 - QUEENS | SCA IEH | PO18-ABATE STEAM PIPE IN ROOM SB36 FOR THE BOYS AND GIRLS GYM AREA MARK WITH RED DISCONNECT AND REMO | Construction | Complete | 5/29/2024 | IEH | 6/30/2024 | IEH | 41453 | 2721
26 | Q067 | J.H.S. 67 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/18/2023 | DIIR | 6/5/2024 | DIIR | 50000 | 50000
26 | Q067 | J.H.S. 67 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
26 | Q067 | J.H.S. 67 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 12/15/2023 | DOER |  | DOER | 112704 | 0
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q074 | I.S. 74 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q074 | I.S. 74 - QUEENS | Fast Track Projects | IDA GYM FLOOR REPLACEMENT @ Q074 | Construction | In-Progress | 5/25/2022 | FTK |  | FTK | 628603 | 537631
26 | Q074 | I.S. 74 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/29/2024 | DIIR | 7/24/2024 | DIIR | 175000 | 175000
26 | Q074 | I.S. 74 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 160864 | 0
26 | Q094 | P.S. 94 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR PIPE INSULATION/ PIPE JOINT IN BASEMENT GYMNASIUM | Construction | Complete | 2/27/2024 | IEH | 5/23/2024 | IEH | 831 | 831
26 | Q094 | P.S. 94 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0
26 | Q094 | P.S. 94 - QUEENS | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/13/2016 | DOER |  | DOER | 224547 | 0
26 | Q094 | P.S. 94 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/8/2024 | DOER |  | DOER | 97118 | 0
26 | Q094 | P.S. 94 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 8/23/2023 | DOES |  | DOES | 116027 | 0
26 | Q094 | P.S. 94 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/19/2024 | DOES | 5/21/2024 | DOES | 65832 | 11302
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Scope | Complete | 2/26/2021 | 6/25/2021 | 5/28/2021 | 0 | 11065 | 11065
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 11/9/2023 | 3/14/2024 | 11/28/2023 | 0 | 5037 | 5037
26 | Q098 | P.S. 98 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 10/27/2023 | DIIR | 7/25/2024 | DIIR | 100000 | 100000
26 | Q098 | P.S. 98 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
26 | Q098 | P.S. 98 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
26 | Q098 | P.S. 98 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/15/2024 | DOES |  | DOES | 83268 | 0
26 | Q098 | P.S. 98 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/18/2024 | DOES | 6/27/2024 | DOES | 65832
26 | Q115 | P.S. 115 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/21/2024 | DIIR | 6/13/2024 | DIIR | 80000 | 80000
26 | Q115 | P.S. 115 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
26 | Q115 | P.S. 115 - QUEENS | DOE - RESOA | FY 21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/29/2023 | DOER |  | DOER | 227449 | 0
26 | Q130 | Q993 SPED - QUEENS | Fast Track Projects | LSP FY23 RESO A ROOM CONVERSION | Construction | PNS | FTK | FTK | FTK | FTK | 106400 | 0
26 | Q130 | P.S. 130 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 7/8/2024 | DIIR | 50000 | 50000
26 | Q130 | P.S. 130 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
26 | Q130 | Q993 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
26 | Q130 | P.S. 130 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 5/2/2024 | DOES | 65832
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/20/2023 | 4/20/2023 | 3/29/2023 | 0 | 25584 | 25420
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 2/24/2023 | 5/25/2023 |  | 0 | 64 | 64
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 257 | 257
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q133 | P.S. 133 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q133 | P.S. 133 - QUEENS | SCA IEH | PO18-IN BASEMENT FAN ROOM AREA MARKED IN RED AREA FOR THE AUDITORIUM BLOWER AND AUDITORIUM EXHAUST | Construction | In-Progress | 8/13/2024 | IEH |  | IEH | 13804 | 1256
26 | Q133 | P.S. 133 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 290000 | 0
26 | Q133 | P.S. 133 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/30/2022 | DOES |  | DOES | 128865 | 0
26 | Q133 | P.S. 133 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/3/2024 | DOES | 4/11/2024 | DOES | 65832 | 10996
26 | Q133 | P.S. 133 - QUEENS | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 5/13/2024 | DOES |  | DOES | 75386 | 0
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 10/30/2023 | 3/4/2024 | 11/28/2023 | 0 | 5480 | 5480
26 | Q158 | J.H.S. 158 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 50000 | 0
26 | Q159 | P.S. 159 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225335 | 0
26 | Q159 | P.S. 159 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/15/2022 | DOES | 1/5/2023 | DOES | 217835 | 6757
26 | Q159 | P.S. 159 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/1/2024 | DOES | 5/8/2024 | DOES | 65832
26 | Q162 | P.S. 162 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR ACOUSTICAL CEILING PLASTER IN AUDITORIUM HALLWAY | Construction | In-Progress | 1/3/2024 | IEH |  | IEH | 1079 | 504
26 | Q162 | P.S. 162 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 158000
26 | Q162 | P.S. 162 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
26 | Q162 | P.S. 162 - QUEENS | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 12/13/2018 | DOER |  | DOER | 89107 | 0
26 | Q162 | P.S. 162 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
26 | Q162 | P.S. 162 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 3/11/2021 | DOES | 7/28/2021 | DOES | 230883 | 237937
26 | Q172 | J.H.S. 172 - QUEENS | SCA IEH | PO18-PLEASE ABATE APPROXIMATELY 12 LINEAR FEET OF PIPE ACM UNDER EXIT A, STAIRWELL 1 IN BOILER ROOM. | Construction | Complete | 3/28/2024 | IEH | 8/24/2024 | IEH | 9041 | 496
26 | Q172 | J.H.S. 172 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
26 | Q172 | J.H.S. 172 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
26 | Q172 | J.H.S. 172 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/2/2016 | DOES |  | DOES | 56232 | 0
26 | Q172 | J.H.S. 172 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/2/2024 | DOES |  | DOES | 685926 | 0
26 | Q173 | P.S. 173 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/3/2024 | DIIR | 7/12/2024 | DIIR | 50000
26 | Q173 | P.S. 173 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 400000 | 0
26 | Q173 | P.S. 173 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 2/1/2022 | DOER |  | DOER | 96296 | 0
26 | Q173 | P.S. 173 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 197000 | 0
26 | Q173 | P.S. 173 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
26 | Q173 | P.S. 173 - QUEENS | DOE - Skilled Trades | BROKEN WATER MAIN | Construction | In-Progress | 3/22/2019 | DOES |  | DOES | 99248 | 0
26 | Q173 | P.S. 173 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 7/1/2024 | DOES | 7/9/2024 | DOES | 65832 | 20964
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 1/30/2023 | 5/31/2023 | 7/1/2024 | 0 | 24145 | 24051
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | In-Progress | 6/13/2024 | 9/16/2024 |  | 0 | 0 | 0
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q177 | Q177 SPED - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 2/15/2024 | 5/15/2024 |  | 0 | 15576 | 1020
26 | Q177 | Q177 SPED - QUEENS | SCA Emergency Response | EMR PROTECTIVE MEASURES - IDA | Construction | In-Progress | 9/3/2021 | EMER |  | EMER | 4382595 | 4028421
26 | Q177 | Q177 SPED - QUEENS | DIIT - RESOA | FY09 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500 | 0
26 | Q177 | Q177 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/3/2024 | DOER |  | DOER | 532370 | 0
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1075000 | 0
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
26 | Q177 | Q177 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0
26 | Q178 | P.S. 178 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
26 | Q178 | P.S. 178 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
26 | Q178 | P.S. 178 - QUEENS | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
26 | Q178 | P.S. 178 - QUEENS | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
26 | Q178 | P.S. 178 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 8/20/2021 | DOES | 9/27/2021 | DOES | 186264 | 189960
26 | Q178 | P.S. 178 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/11/2022 | DOES |  | DOES | 105621 | 0
26 | Q179 | Q004 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 113000 | 0
26 | Q179 | Q004 SPED - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 2879 | 0
26 | Q179 | Q004 SPED - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
26 | Q179 | Q004 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
26 | Q179 | Q004 SPED - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
26 | Q179 | Q004 SPED - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/10/2024 | DOES | 6/14/2024 | DOES | 65832
26 | Q186 | Q224 SPED - QUEENS | Fast Track Projects | CTF ROOM CONVERSION / PATH OF TRAVEL CTF ROOM CONVERSION | Construction | In-Progress | 11/5/2021 | FTK |  | FTK | 1703607 | 1565947
26 | Q186 | P.S. 186 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 110000
26 | Q186 | Q224 SPED - QUEENS | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
26 | Q186 | P.S. 186 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/5/2024 | DOER |  | DOER | 47308 | 0
26 | Q186 | Q224 SPED - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
26 | Q186 | P.S. 186 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/30/2022 | DOES |  | DOES | 118707 | 0
26 | Q188 | P.S. 188 - QUEENS | SCA IEH | PO18-77/26Q188/TEST 9X9 TILE IN AUDITORIUM CRACKED AND LOSE IF POSITIVE ABATE AND REPLACE TRIP HAZAR | Construction | Complete | 2/5/2024 | IEH | 5/6/2024 | IEH | 52735 | 1304
26 | Q188 | P.S. 188 - QUEENS | SCA IEH | PO18-TEST/ABATE AND REPLACE 9 X 9 FLOOR TILES IN RMS 107,116,204,114, TILES ARE CRACKING AND LIFTING | Construction | In-Progress | 7/26/2024 | IEH |  | IEH | 889 | 314
26 | Q188 | P.S. 188 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
26 | Q188 | P.S. 188 - QUEENS | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/29/2023 | DOER |  | DOER | 275028 | 0
26 | Q188 | P.S. 188 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 42948 | 0
26 | Q188 | P.S. 188 - QUEENS | DOE - Skilled Trades | BATHROOM RENOVATIONS/UPGRADES/FIRST FLOOR (BOYS AND GIRLS) | Construction | Complete | 3/12/2021 | DOES | 4/28/2021 | DOES | 162343 | 1039
26 | Q188 | P.S. 188 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/10/2024 | DOES | 4/19/2024 | DOES | 65832 | 10473
26 | Q191 | P.S. 191 - QUEENS | DIIT - Project Connect | DATA/VOICE & WIRELESS NETWORK CABLE WIRING, NETWORK SERVER EQUIPMENT, DATA/VOICE & WIRELESS NETWORK | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 261220 | 0
26 | Q191 | Q993 SPED - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
26 | Q191 | Q993 SPED - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
26 | Q191 | Q993 SPED - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
26 | Q191 | Q993 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 113000 | 0
26 | Q191 | P.S. 191 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
26 | Q191 | P.S. 191 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 210000 | 0
26 | Q191 | P.S. 191 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/20/2024 | DOES | 5/30/2024 | DOES | 65832
26 | Q203 | P.S. 203 - QUEENS | SCA IEH | PO18-77/26Q203 TEST PIPE INSULATION IF POSITIVE ABATE 4 INCH WASTE LINE IN BASEMENT OUT SIDE BOILER | Construction | Complete | 5/30/2024 | IEH | 6/2/2024 | IEH | 12555 | 1332
26 | Q203 | P.S. 203 - QUEENS | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/3/2020 | DOER |  | DOER | 263679 | 0
26 | Q203 | P.S. 203 - QUEENS | DOE - RESOA | FY21 RESO A EXTERIOR DOORS | Construction | In-Progress | 12/23/2022 | DOER |  | DOER | 170861 | 0
26 | Q203 | P.S. 203 - QUEENS | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
26 | Q203 | P.S. 203 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/28/2022 | DOES |  | DOES | 155986 | 0
26 | Q203 | P.S. 203 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/23/2024 | DOES | 4/26/2024 | DOES | 65832 | 189
26 | Q205 | P.S. 205 - QUEENS | SCA IEH | PO18-ABATEMENT OF TAR RADIATOR COVERS AND WHITE AIRCELL PIPE INSULATION IN ROOM 218 | Construction | In-Progress | 2/12/2024 | IEH |  | IEH | 668 | 93
26 | Q205 | P.S. 205 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN ROOMS 1ST FLOOR ROOM #107JA AND 107JB 1ST HALLWAY OUTSIDE ROOM | Construction | Complete | 2/27/2024 | IEH | 7/13/2024 | IEH | 43662 | 2942
26 | Q205 | P.S. 205 - QUEENS | SCA IEH | PO18-77/26Q205/TEST ABATE IF POSITIVE PIPE INSULATION HOT AND COLD RISER VALVES AND LINES IN BASEMEN | Construction | In-Progress | 9/26/2024 | IEH |  | IEH | 0 | 0
26 | Q205 | Q224 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 6/5/2024 | DIIR |  | DIIR | 112000 | 0
26 | Q205 | P.S. 205 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 5/19/2024 | DIIR | 113000
26 | Q205 | P.S. 205 - QUEENS | DOE - RESOA | FY19 RESO A MULTIMEDIA CENTER | Construction | In-Progress | 11/5/2021 | DOER |  | DOER | 103136 | 0
26 | Q205 | P.S. 205 - QUEENS | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
26 | Q205 | Q224 SPED - QUEENS | DOE - RESOA | FY22 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 105991 | 0
26 | Q208 | Q993 SPED - QUEENS | DIIT - RESOA | RESO A- FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
26 | Q208 | P.S./I.S. 208 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 5/9/2024 | DIIR | 100000 | 100000
26 | Q208 | P.S./I.S. 208 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 5/9/2024 | DIIR | 80000 | 80000
26 | Q208 | P.S./I.S. 208 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
26 | Q208 | P.S./I.S. 208 - QUEENS | DOE - RESOA | FY17 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 185000 | 0
26 | Q208 | P.S./I.S. 208 - QUEENS | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 144686 | 0
26 | Q208 | Q993 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 350000 | 0
26 | Q208 | P.S./I.S. 208 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
26 | Q208 | P.S./I.S. 208 - QUEENS | DOE - Skilled Trades | GAS LEAK | Construction | In-Progress | 5/15/2019 | DOES |  | DOES | 18145 | 0
26 | Q208 | P.S./I.S. 208 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/25/2024 | DOES | 5/2/2024 | DOES | 50832
26 | Q213 | P.S. 213 - QUEENS | DOE - RESOA | FY13 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 42261 | 0
26 | Q213 | P.S. 213 - QUEENS | DOE - RESOA | FY17 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 422356 | 0
26 | Q213 | P.S. 213 - QUEENS | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
26 | Q213 | P.S. 213 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 7/8/2019 | DOES | 10/1/2019 | DOES | 198646 | 199683
26 | Q216 | J.H.S. 216 - QUEENS | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/21/2022 | DOER |  | DOER | 283306 | 0
26 | Q216 | J.H.S. 216 - QUEENS | DOE - RESOA | FY21 RESO A LOCKER ROOM UPGRADE | Construction | In-Progress | 1/6/2022 | DOER |  | DOER | 179311 | 0
26 | Q216 | J.H.S. 216 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 1/14/2022 | DOES |  | DOES | 192136 | 0
26 | Q221 | P.S. 221 - QUEENS | SCA IEH | PO18-ROOM 1005 - ABATE PIPE INSULATION PAINTED IN RED - 10 LF ROOM 3136C - ABATE & REPLACE FLOOR TIL | Construction | In-Progress | 7/25/2024 | IEH |  | IEH | 14622 | 163
26 | Q221 | P.S. 221 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
26 | Q221 | P.S. 221 - QUEENS | DOE - RESOA | FY16 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/31/2018 | DOER |  | DOER | 111500 | 0
26 | Q221 | P.S. 221 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 1/3/2020 | DOES | 4/11/2020 | DOES | 212303 | 34618
26 | Q221 | P.S. 221 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 5/9/2024 | DOES | 65832 | 14954
26 | Q266 | P.S./I.S. 266 - QUEENS | Fast Track Projects | LSP HOT WATER HEATER | Construction | In-Progress | 1/15/2020 | FTK |  | FTK | 227166 | 192857
26 | Q266 | P.S./I.S. 266 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/3/2024 | DIIR | 7/12/2024 | DIIR | 113000
26 | Q266 | P.S./I.S. 266 - QUEENS | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | In-Progress | 12/26/2023 | DOER |  | DOER | 92704 | 0
26 | Q266 | P.S./I.S. 266 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/8/2024 | DOES | 5/15/2024 | DOES | 50832
26 | Q332 | P.S. 376 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 55000 | 0
26 | Q361 | THE CIVIC SCHOOL OF BAYSIDE HILLS - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
26 | Q361 | THE CIVIC SCHOOL OF BAYSIDE HILLS - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
26 | Q361 | THE CIVIC SCHOOL OF BAYSIDE HILLS - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY19 RESO A ROOM CONVERSION | Scope | Complete | 8/13/2019 | 12/10/2019 | 3/10/2021 | 0 | 15585 | 15585
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A GREENHOUSE | Scope | Complete | 2/5/2020 | 5/20/2020 | 7/14/2021 | 0 | 128319 | 86884
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GREENHOUSE | Scope | In-Progress | 3/1/2024 | 5/31/2024 |  | 0 | 0 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GREENHOUSE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GREENHOUSE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GREENHOUSE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 1056 | 1056
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA IEH | PO18-DETERMINE IF SOFT CONCRETE FILLER FLOORING MATERIAL WILL BE DISTRUBED DURING FLOOR REPAIR IN RO | Construction | In-Progress | 1/3/2023 | IEH |  | IEH | 2305 | 730
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA IEH | PO18-77/26Q405/ TEST ABATE IF POSITIVE PIPE INSULATI0N ROOM 111 REMOVE ALL INSULATIN BEHIND METAL CO | Construction | In-Progress | 1/11/2024 | IEH |  | IEH | 1038 | 463
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/3/2024 | DOER |  | DOER | 188309 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 1350000 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | WATER MAIN REPAIRS | Construction | In-Progress | 1/11/2021 | DOES |  | DOES | 518370 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/21/2023 | DOES |  | DOES | 359078 | 0
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 9/25/2023 | DOES |  | DOES | 744456 | 0
26 | Q406 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - RESOA | RESO A ATHLETIC FIELDS | Construction | In-Progress | 8/10/2024 | DOER |  | DOER | 50000 | 0
26 | Q406 | BAYSIDE HIGH SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 2150000 | 0
26 | Q415 | Q993 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 112000 | 0
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 3/22/2021 | DOER |  | DOER | 41965 | 0
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 9/8/2023 | DOER |  | DOER | 47114 | 0
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 61000 | 0
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 56000 | 0
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 6/30/2022 | DOES |  | DOES | 141386 | 0
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 1/27/2023 | DOES |  | DOES | 2056793 | 0
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/6/2024 | DOES |  | DOES | 630395 | 0
26 | Q430 | FRANCIS LEWIS HS - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 105000 | 0
26 | Q431 | FRANCIS LEWIS HS - QUEENS | SCA CIP RESOA | FY20 RESO A ATHLETIC FIELD UPGRADE | Scope | Complete | 2/27/2020 | 6/26/2020 | 3/21/2022 | 0 | 166226 | 163126
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/14/2023 | 6/28/2023 | 5/23/2023 | 0 | 16923 | 16923
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 2/21/2023 | FTK |  | FTK | 430475 | 246120
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 150000 | 0
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | Complete | 6/10/2021 | DOER | 12/10/2021 | DOER | 99832 | 88640
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/15/2023 | DOER |  | DOER | 94580 | 0
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 7/14/2023 | DOER |  | DOER | 611001 | 0
26 | Q435 | Q177 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 124128 | 3039
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 56000 | 0
26 | Q435 | BUSINESS TECHNOLOGY EARLY COLLEGE HIGH SCHOOL | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 7/19/2023 | DOES |  | DOES | 999430 | 0
26 | Q461 | Q000 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/8/2024 | IEH | 8/20/2024 | IEH | 8239 | 0
26 | Q566 | GLEN OAKS CAMPUS | SCA Emergency Response | SIDE WALK BRIDGING | Construction | In-Progress | 1/9/2012 | EMER |  | EMER |  | 0
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | DIIT - RESOA | FY15 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 72495 | 0
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | DIIT - RESOA | FY 15 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 39000 | 0
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 123000 | 0
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 56000 | 0
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/31/2024 | DOES | 6/7/2024 | DOES | 50832
26 | Q809 | Q224 SPED - QUEENS | Fast Track Projects | LOCKER ROOM & BATHROOM UPGRADE | Construction | In-Progress | 9/22/2022 | FTK |  | FTK | 1770209 | 1733160
26 | Q811 | Q811 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 162000 | 0
26 | Q811 | Q811 SPED - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 3/25/2020 | DOES | 9/24/2020 | DOES | 190933 | 192765
26 | Q858 | P.S. 188 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 6/1/2024 | IEH | 9862 | 716
26 | QAPM | PS 23 @ HILLSIDE PSYCH - Q | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
26 | QAPM | PS 23 @ HILLSIDE PSYCH - Q | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
26 | QAPM | PS 23 @ HILLSIDE PSYCH - Q | DOE - RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q042 | P.S. 42 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q042 | P.S. 42 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 12/14/2021 | EMER |  | EMER | 39945 | 27215
27 | Q042 | P.S. 42 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
27 | Q042 | P.S. 42 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0
27 | Q042 | Q233 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
27 | Q042 | P.S. 42 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/24/2024 | DOES |  | DOES | 65832 | 0
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q043 | P.S. 43 - QUEENS | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 3354 | 214
27 | Q043 | P.S. 43 - QUEENS | Fast Track Projects | EMERGENCY PROTECTIVE MEASURES - HURRICANE SANDY | Construction | In-Progress | 10/31/2012 | FTK |  | FTK | 1882053 | 1882052
27 | Q043 | Q256 SPED - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 345295 | 0
27 | Q043 | Q256 SPED - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q043 | Q256 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 230000 | 0
27 | Q043 | P.S. 43 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 334000 | 0
27 | Q043 | P.S. 43 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/6/2024 | DOES | 5/13/2024 | DOES | 50832
27 | Q043 | P.S. 43 - QUEENS | DOE - Skilled Trades | ELEVATOR PISTON REPLACEMENT | Construction | In-Progress | 8/18/2023 | DOES |  | DOES | 266915 | 123691
27 | Q045 | P.S. 45 - QUEENS | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
27 | Q045 | P.S. 45 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
27 | Q045 | P.S. 45 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/20/2024 | DOES | 5/23/2024 | DOES | 65832 | 6605
27 | Q047 | P.S. 47 - QUEENS | Fast Track Projects | FIRE ALARM REPLACEMENT | Construction | In-Progress | 6/24/2019 | FTK |  | FTK | 2868508 | 2589036
27 | Q047 | P.S. 47 - QUEENS | DOE - Skilled Trades | GYM PARTITION | Construction | In-Progress | 3/11/2019 | DOES |  | DOES | 43302 | 0
27 | Q051 | P.S. 51 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 4/16/2024 | DIIR | 50000 | 50000
27 | Q051 | P.S. 51 - QUEENS | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
27 | Q051 | P.S. 51 - QUEENS | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 7/11/2024 | DOES |  | DOES | 75560 | 0
27 | Q053 | I.S. 319 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q053 | I.S. 319 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q053 | I.S. 319 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q053 | I.S. 319 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q053 | I.S. 53 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q053 | I.S. 53 - QUEENS | SCA IEH | PO18-ACM TESTING - ROOM 106 9X9 FLOOR TILES LVL GRAY (PLEASE TEST UNDER 12X12 TO CONFIRM) FLOOR TILE | Construction | Complete | 6/7/2024 | IEH | 6/8/2024 | IEH | 17484 | 13184
27 | Q053 | I.S. 53 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 209455 | 0
27 | Q053 | I.S. 319 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | In-Progress | 3/22/2024 | DOER |  | DOER | 53244 | 0
27 | Q053 | I.S. 319 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0
27 | Q053 | I.S. 53 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/10/2023 | DOER |  | DOER | 231115 | 0
27 | Q053 | I.S. 53 - QUEENS | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0
27 | Q053 | I.S. 53 - QUEENS | DOE - Skilled Trades | GYM FLOOR REPLACEMENT | Construction | In-Progress | 2/9/2024 | DOES |  | DOES | 294982 | 216301
27 | Q056 | P.S. 56 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 10/28/2021 | 3/3/2022 | 1/6/2022 | 0 | 2626 | 2626
27 | Q056 | P.S. 56 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 5/6/2024 | DIIR | 50000 | 50000
27 | Q056 | P.S. 56 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/16/2021 | DOES |  | DOES | 172134 | 0
27 | Q056 | P.S. 56 - QUEENS | DOE - Skilled Trades | DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 1/23/2020 | DOES |  | DOES | 64037 | 0
27 | Q056 | P.S. 56 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 5/31/2023 | DOES |  | DOES | 242864 | 0
27 | Q056 | P.S. 56 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/28/2024 | DOES | 4/4/2024 | DOES | 65832 | 27322
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/14/2023 | 4/17/2024 | 4/15/2024 | 0 | 18204 | 18141
27 | Q060 | P.S. 60 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 12/14/2023 | 3/18/2024 | 9/18/2024 | 0 | 341 | 341
27 | Q060 | P.S. 60 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q060 | P.S. 60 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 650000 | 0
27 | Q062 | P.S. 62 - QUEENS | SCA CIP RESOA | FY20 RESO A COMPUTER LAB | Scope | Complete | 5/26/2021 | 10/8/2021 | 2/1/2022 | 0 | 17207 | 17207
27 | Q062 | P.S. 62 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 221283 | 191634
27 | Q062 | P.S. 62 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
27 | Q062 | P.S. 62 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 3471 | 0
27 | Q062 | P.S. 62 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
27 | Q062 | P.S. 62 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 2/22/2019 | DOES | 9/3/2019 | DOES | 201605 | 202641
27 | Q062 | P.S. 62 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 65832 | 0
27 | Q063 | P.S. 63 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 11/29/2021 | FTK |  | FTK | 252064 | 171917
27 | Q063 | P.S. 63 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q063 | P.S. 63 - QUEENS | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 10/8/2021 | DOER |  | DOER | 108899 | 0
27 | Q063 | P.S. 63 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 221263 | 0
27 | Q063 | P.S. 63 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | Complete | 10/18/2023 | DOER | 3/9/2024 | DOER | 348364 | 348364
27 | Q064 | P.S. 64 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q064 | P.S. 64 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q064 | P.S. 64 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 56000 | 0
27 | Q064 | P.S. 64 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/12/2024 | DOES | 4/19/2024 | DOES | 65832 | 15242
27 | Q066 | P.S. 66 - QUEENS | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | In-Progress | 11/13/2023 | DOER |  | DOER | 13238 | 0
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q090 | P.S. 90 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q090 | P.S. 90 - QUEENS | SCA IEH | PO18-TEST FLOOR & SUBLAYERS FOR ACM IN RMS 208,110,212,409B ABATE AND REPLACE IF POSITIVE. DAMAGED F | Construction | Complete | 7/25/2024 | IEH | 8/27/2024 | IEH | 190621 | 2747
27 | Q090 | P.S. 90 - QUEENS | SCA IEH | PO18-TEST BOILER ROOM PIPE INSULATION &IF POSITIVE ABATE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | In-Progress | 9/19/2024 | IEH |  | IEH | 241 | 241
27 | Q090 | P.S. 90 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
27 | Q090 | P.S. 90 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
27 | Q090 | P.S. 90 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
27 | Q090 | P.S. 90 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/2/2024 | DOES |  | DOES | 238033 | 0
27 | Q090 | P.S. 90 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/24/2024 | DOES |  | DOES | 65832 | 0
27 | Q096 | P.S. 96 - QUEENS | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/1/2023 | DOER |  | DOER | 359759 | 0
27 | Q096 | P.S. 96 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/27/2023 | DOER |  | DOER | 60784 | 0
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 7/8/2021 | 2/14/2022 | 12/22/2021 | 0 | 21425 | 21425
27 | Q097 | P.S. 97 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/10/2024 | DIIR | 7/3/2024 | DIIR | 50000 | 50000
27 | Q097 | P.S. 97 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q097 | P.S. 97 - QUEENS | DOE - RESOA | FY14 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
27 | Q097 | P.S. 97 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/19/2022 | DOES |  | DOES | 106527 | 0
27 | Q097 | P.S. 97 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/15/2024 | DOES | 4/22/2024 | DOES | 65832 | 12945
27 | Q104 | P.S. 104 - QUEENS | SCA IEH | PO18-BASEMENT PIPE DUCT SPACE ABATE UNRAVELING PIPE INSULATION | Construction | In-Progress | 9/5/2024 | IEH |  | IEH | 1052 | 302
27 | Q104 | P.S. 104 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 700000 | 0
27 | Q104 | P.S. 104 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 2/17/2023 | DOES | 5/24/2023 | DOES | 157967 | 6753
27 | Q104 | P.S. 104 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/24/2024 | DOES | 4/30/2024 | DOES | 65832 | 22146
27 | Q104 | P.S. 104 - QUEENS | DOE - Skilled Trades | WATER MAIN LEAK REPAIR | Construction | In-Progress | 3/16/2024 | DOES |  | DOES | 100000 | 0
27 | Q105 | P.S. 105 - QUEENS | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
27 | Q105 | P.S. 105 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/28/2024 | DOES | 7/8/2024 | DOES | 65832
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | FY25 RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q106 | P.S. 106 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q108 | P.S. 108 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | Complete | 2/7/2022 | FTK | 11/6/2023 | FTK | 223706 | 214409
27 | Q108 | P.S. 108 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 528023 | 0
27 | Q108 | P.S. 108 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/24/2023 | DOER |  | DOER | 861763 | 0
27 | Q108 | P.S. 108 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 2/18/2023 | DOES |  | DOES | 149934 | 0
27 | Q108 | P.S. 108 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/24/2024 | DOES | 4/30/2024 | DOES | 65832 | 19257
27 | Q114 | P.S. 114 - QUEENS | SCA IEH | PO18-GYMNASIUM REPAIR LIFTING SECTION OF THE WOOD FLOORING - ROOM 206 REPAIR DAMAGED AREAS OF FLOOR | Construction | In-Progress | 5/15/2024 | IEH |  | IEH | 1138 | 388
27 | Q114 | P.S. 114 - QUEENS | Fast Track Projects | LSP- PLAY YARD RENOVATION | Construction | In-Progress | 9/2/2021 | FTK |  | FTK | 139900 | 122815
27 | Q114 | Q256 SPED - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 345295 | 0
27 | Q114 | P.S. 114 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
27 | Q114 | P.S. 114 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 50000
27 | Q114 | P.S. 114 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
27 | Q114 | P.S. 114 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 325000 | 0
27 | Q114 | P.S. 114 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 56000 | 0
27 | Q114 | P.S. 114 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/6/2022 | DOES |  | DOES | 103809 | 0
27 | Q114 | P.S. 114 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 8/16/2022 | DOES |  | DOES | 166573 | 0
27 | Q123 | P.S. 123 - QUEENS | SCA CIP RESOA | FY19 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 10/22/2018 | 8/19/2019 | 11/19/2019 | 0 | 22268 | 22268
27 | Q123 | P.S. 123 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 225689 | 172348
27 | Q123 | P.S. 123 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 190000 | 0
27 | Q123 | P.S. 123 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 12/26/2023 | DOER |  | DOER | 78613 | 0
27 | Q123 | P.S. 123 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
27 | Q123 | P.S. 123 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/22/2022 | DOES |  | DOES | 68928 | 0
27 | Q123 | P.S. 123 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/17/2024 | DOES | 4/25/2024 | DOES | 65832
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY21 RESO A ATHLETIC FIELDS | Scope | Complete | 9/2/2021 | 1/4/2022 | 3/3/2022 | 0 | 36931 | 36931
27 | Q124 | P.S. 124 - QUEENS | SCA IEH | PO18-TEST WOOD FLOORS &IF POSITIVE ABATE & REPLACE PLEASE NOTIFY ALL COPIED OF RESULTS WOOD FLOORS B | Construction | Complete | 7/31/2024 | IEH | 8/31/2024 | IEH | 18979 | 1231
27 | Q124 | P.S. 124 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 371929 | 0
27 | Q124 | P.S. 124 - QUEENS | DIIT - RESOA | RESO A- TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 74250 | 0
27 | Q124 | P.S. 124 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 6/11/2024 | DIIR | 55000 | 55000
27 | Q124 | P.S. 124 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
27 | Q124 | P.S. 124 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 3/26/2020 | DOES | 1/12/2021 | DOES | 149874 | 186597
27 | Q124 | P.S. 124 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/25/2022 | DOES |  | DOES | 69675 | 0
27 | Q124 | P.S. 124 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 9/26/2022 | DOES |  | DOES | 187170 | 0
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/16/2019 | 5/1/2020 | 5/1/2020 | 0 | 7016 | 7016
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A GYMNASIUM UPGRADE | Scope | Complete | 2/16/2022 | 7/1/2022 | 8/15/2022 | 0 | 9969 | 9969
27 | Q137 | M.S. 137 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 247462 | 130014
27 | Q137 | M.S. 137 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
27 | Q137 | M.S. 137 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q137 | M.S. 137 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 350000 | 0
27 | Q137 | M.S. 137 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 50000 | 0
27 | Q137 | M.S. 137 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/20/2024 | DOES | 5/29/2024 | DOES | 50832
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/4/2023 | 3/6/2024 | 7/25/2024 | 0 | 27607 | 27129
27 | Q146 | P.S. 146 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/5/2024 | 6/5/2024 | 6/27/2024 | 0 | 589 | 589
27 | Q146 | P.S. 146 - QUEENS | SCA Emergency Response | EMERGENCY INVESTIGATION CRACKS FALLING DEBRIS Q146 | Construction | In-Progress | 6/6/2023 | EMER |  | EMER | 193134 | 38570
27 | Q146 | P.S. 146 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 182000 | 0
27 | Q146 | P.S. 146 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/17/2023 | DOER |  | DOER | 445417 | 0
27 | Q146 | P.S. 146 - QUEENS | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 63000 | 0
27 | Q146 | P.S. 146 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/3/2022 | DOES |  | DOES | 63046 | 0
27 | Q155 | P.S. 155 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/12/2023 | 3/14/2024 | 4/18/2024 | 0 | 27015 | 16115
27 | Q155 | P.S. 155 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/19/2024 | 4/19/2024 | 4/8/2024 | 0 | 196 | 196
27 | Q155 | P.S. 155 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/29/2024 | DOER |  | DOER | 334796 | 0
27 | Q155 | P.S. 155 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 150000 | 0
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | Fast Track Projects | CONDENSATION RESOLUTION | Construction | In-Progress | 7/12/2018 | FTK |  | FTK | 13120502 | 11927830
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - RESOA | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/7/2023 | DOER |  | DOER | 539862 | 0
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - RESOA | RESO A HYDROPONICS LAB | Construction | In-Progress | 6/30/2023 | DOER |  | DOER | 276707 | 0
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 162261 | 0
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 12/18/2020 | DOES | 1/19/2021 | DOES | 211511 | 234554
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/20/2024 | DOES |  | DOES | 477433 | 0
27 | Q183 | P.S. 183 - QUEENS | SCA CIP RESOA | FY19 RESO A PLAYGROUND / PATH OF TRAVEL RESO A PLAYGROUND | Scope | Complete | 10/17/2018 | 7/29/2019 | 7/12/2019 | 0 | 46339 | 46339
27 | Q183 | P.S. 183 - QUEENS | SCA IEH | PO18-TGG/ABATE PIPE INSULATION IN CRAWL SPACE.APPROX 30 LINEAR FEET SPRAYED IN RED | Construction | Complete | 9/18/2024 | IEH | 9/19/2024 | IEH | 0 | 0
27 | Q183 | P.S. 183 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 2/14/2023 | DOER |  | DOER | 94953 | 0
27 | Q183 | P.S. 183 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 121899 | 0
27 | Q183 | P.S. 183 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 228536 | 0
27 | Q197 | P.S. 197 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE / FY21 RESO A PLAYGROUND UPGRADE / RETAINING WALL | Scope | Complete | 7/22/2021 | 8/22/2023 | 2/4/2022 | 0 | 69975 | 55651
27 | Q197 | P.S. 197 - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/26/2024 | DOER |  | DOER | 241770 | 0
27 | Q198 | P.S. 333 - QUEENS | Fast Track Projects | SANDY NEW A/C CHILLERS | Construction | In-Progress | 7/1/2013 | FTK |  | FTK | 1608557 | 1608557
27 | Q198 | P.S. 333 - QUEENS | Fast Track Projects | EMERGENCY PROTECTIVE MEASURES - HURRICANE SANDY | Construction | In-Progress | 10/31/2012 | FTK |  | FTK | 3429874 | 3192874
27 | Q198 | P.S. 333 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 429000 | 0
27 | Q198 | P.S. 333 - QUEENS | DOE - RESOA | FY21 RESO A MEDIA CENTER | Construction | In-Progress | 5/25/2022 | DOER |  | DOER | 80109 | 0
27 | Q198 | P.S. 333 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Scope | Complete | 1/30/2023 | 5/31/2023 | 5/10/2023 | 0 | 13008 | 13008
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q202 | I.S. 202 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q202 | HS OF COMMN. ARTS & TECH - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q202 | I.S. 202 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/10/2023 | DOER |  | DOER | 347087 | 0
27 | Q202 | I.S. 202 - QUEENS | DOE - RESOA | FY23 RESO A PHONE UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 249975 | 0
27 | Q202 | I.S. 202 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/5/2024 | DOES |  | DOES | 585910 | 0
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 2/1/2023 | 9/8/2023 | 6/28/2023 | 0 | 17477 | 17477
27 | Q207 | P.S. 207 - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/15/2023 | DOER |  | DOER | 126416 | 0
27 | Q207 | P.S. 207 - QUEENS | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 27605 | 0
27 | Q207 | P.S. 207 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0
27 | Q207 | P.S. 207 - QUEENS | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0
27 | Q207 | P.S. 207 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 10/4/2018 | DOES | 10/1/2019 | DOES | 158511 | 159444
27 | Q210 | I.S. 210 - QUEENS | DIIT - RESOA | FY15 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
27 | Q210 | I.S. 210 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 5/13/2024 | DIIR | 50000
27 | Q210 | I.S. 210 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 203539 | 0
27 | Q210 | I.S. 210 - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 576926 | 0
27 | Q210 | I.S. 210 - QUEENS | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
27 | Q210 | I.S. 210 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/10/2024 | DOES |  | DOES | 733336 | 0
27 | Q223 | P.S. 223 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 3/16/2022 | FTK |  | FTK | 768598 | 736613
27 | Q223 | P.S. 223 - QUEENS | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER | Construction | In-Progress | 3/25/2024 | FTK |  | FTK | 304828 | 66362
27 | Q223 | Q075 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0
27 | Q223 | P.S. 223 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
27 | Q223 | P.S. 223 - QUEENS | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 2/3/2023 | DOER |  | DOER | 109982 | 0
27 | Q223 | P.S. 223 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 6/6/2019 | DOES | 11/1/2019 | DOES | 131083 | 132122
27 | Q223 | P.S. 223 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/14/2024 | DOES | 5/22/2024 | DOES | 65832
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q225 | I.S. 318 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION / CTF ROOM CONVERSION | Construction | In-Progress | 7/11/2024 | FTK |  | FTK | 483863 | 16968
27 | Q225 | I.S. 318 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q225 | I.S. 318 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q225 | SUCCESS ACADEMY CHARTER SCHOOL - FAR ROCKAWAY | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0
27 | Q225 | P.S. 317 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 12/17/2022 | DOES |  | DOES | 217115 | 0
27 | Q225 | P.S. 317 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/29/2024 | DOES |  | DOES | 65832 | 0
27 | Q225 | I.S. 318 - QUEENS | DOE - Skilled Trades | BROKEN SEWER LINE REPLACEMENT | Construction | Complete | 5/6/2024 | DOES | 5/11/2024 | DOES | 108931
27 | Q226 | I.S. 226 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING ROOMS: ROOMS:304A, 304E, 312A, 312E, 342A, 342E, | Construction | Complete | 6/5/2023 | IEH | 8/20/2024 | IEH | 229575 | 194500
27 | Q226 | I.S. 226 - QUEENS | Fast Track Projects | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | FTK | FTK | FTK | FTK | 4329 | 4329
27 | Q226 | Q233 SPED - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 242422 | 0
27 | Q226 | Q233 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/28/2023 | DIIR | 4/9/2024 | DIIR | 80000 | 80000
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | DOE - RESOA | FY21 RESO A FITNESS ROOM UPGRADE | Construction | In-Progress | 4/5/2022 | DOER |  | DOER | 100677 | 0
27 | Q226 | I.S. 226 - QUEENS | DOE - RESOA | RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2/5/2024 | DOER |  | DOER | 47283 | 0
27 | Q226 | I.S. 226 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 200000 | 0
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
27 | Q226 | I.S. 226 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
27 | Q226 | I.S. 226 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/20/2019 | DOES | 1/19/2021 | DOES | 160560 | 179419
27 | Q226 | I.S. 226 - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 12/9/2022 | DOES |  | DOES | 719828 | 0
27 | Q232 | P.S. 232 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q232 | P.S. 232 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q232 | P.S. 232 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
27 | Q253 | P.S. 253 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/5/2022 | DOES |  | DOES | 134504 | 0
27 | Q254 | P.S. 254 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/18/2024 | DIIR | 5/22/2024 | DIIR | 50000
27 | Q254 | P.S. 254 - QUEENS | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
27 | Q254 | P.S. 254 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
27 | Q273 | P.S. 273 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 11/30/2021 | FTK |  | FTK | 195818 | 155819
27 | Q316 | QUEENS EXPLORERS ELEMENTARY SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q316 | QUEENS EXPLORERS ELEMENTARY SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q335 | P.S. 377 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 202000 | 0
27 | Q335 | P.S. 377 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
27 | Q343 | P.S. 47 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY24 RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY24 RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
27 | Q400 | ALTERNATE LEARNING CENTER - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 115000 | 0
27 | Q400 | VOYAGES PREP - SOUTH QUEENS | DOE - RESOA | FY21 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 5/5/2023 | DOER |  | DOER | 95143 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/25/2024 | DOER |  | DOER | 123334 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 2000000 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 310979 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - RESOA | FY25 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 238000 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - Skilled Trades | SEWAGE EJECTOR PUMP REPLACEMENT | Construction | In-Progress | 3/4/2021 | DOES |  | DOES | 77011 | 0
27 | Q400 | AUGUST MARTIN HS - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 8/8/2023 | DOES |  | DOES | 311101 | 0
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP RESOA | FY20 RESO A WEIGHT ROOM | Scope | Complete | 5/7/2021 | 9/8/2021 | 9/18/2023 | 0 | 77272 | 77272
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 5/13/2024 | DIIR | 66666 | 66666
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q410 | ROCKAWAY PARK HS FOR ENVIRONMENTAL SUST - Q | DIIT - RESOA | FY23 RESO A TECHNOLOGY | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q410 | Q256 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
27 | Q410 | ROCKAWAY COLLEGIATE HIGH SCHOOL - Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 50000
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
27 | Q410 | ROCKAWAY PARK HS FOR ENVIRONMENTAL SUST - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - RESOA | RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/9/2017 | DOER |  | DOER | 44426 | 0
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 3/14/2022 | DOER |  | DOER | 667207 | 0
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 5/5/2022 | DOER |  | DOER | 615131 | 0
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 200000 | 0
27 | Q410 | ROCKAWAY COLLEGIATE HIGH SCHOOL - Q | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/2/2024 | DOES |  | DOES | 607815 | 0
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/26/2024 | DOES | 7/5/2024 | DOES | 65832
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | DOE - Skilled Trades | ELEVATOR PISTON REPLACEMENT | Construction | In-Progress | 3/20/2024 | DOES |  | DOES | 124663 | 0
27 | Q438 | Q256 SPED - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 6/18/2024 | IEH |  | IEH | 14747 | 4149
27 | Q438 | Q256 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
27 | Q439 | CURIOUS YOUNG LEARNERS PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/26/2024 | DOES |  | DOES | 50832 | 0
27 | Q464 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/7/2024 | IEH | 8/13/2024 | IEH | 11642 | 91
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Scope | Complete | 8/1/2023 | 12/4/2023 | 11/7/2023 | 0 | 4193 | 4193
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 12/4/2023 | 4/5/2024 | 8/21/2024 | 0 | 24915 | 2955
27 | Q465 | M.S. 282 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM CONVERSION / FY20 RESO A ROBOTICS LAB | Scope | Complete | 12/13/2019 | 3/15/2022 | 3/16/2022 | 0 | 51696 | 42047
27 | Q465 | M.S. 282 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 3/21/2022 | FTK |  | FTK | 209979 | 109600
27 | Q465 | M.S. 282 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/14/2024 | DIIR | 8/23/2024 | DIIR | 250000
27 | Q465 | M.S. 282 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 254000 | 0
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 180000 | 0
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 9/20/2019 | DOER |  | DOER | 274193 | 0
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DOE - RESOA | FY21 RESO A HYDROPONICS LAB | Construction | In-Progress | 8/14/2021 | DOER |  | DOER | 81607 | 0
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/5/2023 | DOER |  | DOER | 1075538 | 0
27 | Q465 | FREDERICK DOUGLASS ACADEMY VI HS-Q | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 8/17/2023 | DOER |  | DOER | 163886 | 0
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0
27 | Q465 | M.S. 282 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 3/31/2023 | DOES |  | DOES | 62936 | 0
27 | Q465 | M.S. 282 - QUEENS | DOE - Skilled Trades | OUTDOOR CLASSROOM | Construction | In-Progress | 5/3/2024 | DOES |  | DOES | 269024 | 0
27 | Q465 | M.S. 282 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/26/2024 | DOES |  | DOES | 65832 | 0
27 | Q468 | CURIOUS YOUNG LEARNERS PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 11/9/2023 | DOES |  | DOES | 65832 | 0
27 | Q473 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | In-Progress | 7/17/2024 | IEH |  | IEH | 7796 | 362
27 | Q474 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 9/13/2024 | IEH | 9/27/2024 | IEH | 10175 | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A CULINARY KITCHEN | Scope | In-Progress | 12/7/2023 | 4/24/2024 |  | 0 | 6716 | 951
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | RESO A SCIENCE LAB UPGRADE | Scope | In-Progress | 12/7/2023 | 3/26/2024 |  | 0 | 13195 | 479
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | In-Progress | 12/7/2023 | 4/4/2024 |  | 0 | 15002 | 446
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | In-Progress | 4/29/2024 | 7/31/2024 |  | 0 | 0 | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Scope | Complete | 3/28/2022 | 12/8/2022 | 11/14/2022 | 0 | 15689 | 15689
27 | Q475 | RICHMOND HILL H.S. | SCA Emergency Response | SIDEWALK BRIDGE (EXT. MSNRY) | Construction | Complete | 8/21/2009 | EMER | 5/31/2024 | EMER |  | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA IEH | PO18-77/27Q475 /ABATE & REPLACE 9 BY 9 TILES UNDER A 12 BY 12 TILES ROOM 128 CUSTODIAN ENGINEER | Construction | Complete | 3/25/2024 | IEH | 5/19/2024 | IEH | 28830 | 23057
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA IEH | PO18-77/27Q475/TEST WALL PLASTER ROOM 502 IF POSITIVE ABATE AND REPAIR | Construction | In-Progress | 5/22/2024 | IEH |  | IEH | 13681 | 431
27 | Q475 | RICHMOND HILL HS - QUEENS | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | In-Progress | 1/30/2023 | DOER |  | DOER | 265042 | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/3/2023 | DOER |  | DOER | 407527 | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 302230 | 0
27 | Q475 | RICHMOND HILL HS - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 320000 | 0
27 | Q477 | CURIOUS YOUNG LEARNERS PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/29/2024 | DOES |  | DOES | 50832 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Scope | In-Progress | 11/27/2023 | 3/29/2024 |  | 0 | 14320 | 483
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - RESOA | FY18 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 4/30/2024 | DOER |  | DOER | 484515 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
27 | Q480 | JOHN ADAMS HS - QUEENS | DOE - Skilled Trades | REPLACE SWIMMING POOL RAW WATER TANK | Construction | In-Progress | 8/27/2019 | DOES |  | DOES | 96475 | 0
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
27 | Q481 | JOHN ADAMS HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Scope | In-Progress | 11/27/2023 | 2/28/2024 |  | 0 | 7273 | 703
27 | Q486 | CURIOUS YOUNG LEARNERS PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/8/2024 | DOES |  | DOES | 50832 | 0
27 | Q593 | P.S. 317 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q593 | P.S. 47 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND YARD RENOVATION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
27 | Q593 | P.S. @ 140 BEACH 112 STREET - QUEENS | DOE Managed PRE-K | PHASE I SWING SPACE WORK | Construction | In-Progress | 5/8/2020 | DOEP |  | DOEP | 3000000 | 0
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/27/2019 | 6/27/2019 | 5/31/2019 | 0 | 14783 | 14783
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | DOE - RESOA | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/31/2023 | DOER |  | DOER | 179136 | 0
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/19/2024 | DOES |  | DOES | 469072 | 0
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/8/2024 | IEH | 8/16/2024 | IEH | 10748 | 573
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
27 | Q816 | Q256 SPED - QUEENS | Fast Track Projects | EMERGENCY PROTECTIVE MEASURES - HURRICANE SANDY | Construction | In-Progress | 10/31/2012 | FTK |  | FTK | 3425235 | 3425235
27 | Q884 | P.S. 65 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 6/4/2024 | IEH | 11743 | 0
27 | Q884 | P.S. 65 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
27 | Q884 | P.S. 65 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
27 | Q884 | P.S. 65 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
27 | Q884 | P.S. 65 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
27 | Q907 | P.S. 43 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/7/2024 | IEH | 8/14/2024 | IEH | 12523 | 91
27 | QAAT | CHALLENGE PREP CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADES | Purch & Install | In-Progress | 9/1/2021 | DIIR |  | DIIR | 100000 | 0
27 | QAAT | CHALLENGE PREP CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/7/2024 | DIIR | 8/16/2024 | DIIR | 500000
27 | QAAT | CHALLENGE PREP CHARTER SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
27 | QAAT | CHALLENGE PREP CHARTER SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
27 | QMAD | PENINSULA PREPARATORY ACADEMY CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0
28 | Q003 | P.S. 303 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 351039 | 0
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q008 | THE EMERSON SCHOOL - QUEENS | Fast Track Projects | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | FTK | FTK | FTK | FTK | 113107 | 56677
28 | Q008 | YORK EARLY COLLEGE ACADEMY - Q | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 105000 | 0
28 | Q008 | THE EMERSON SCHOOL - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY | Purch & Install | Complete | 3/14/2021 | DIIR | 4/20/2024 | DIIR | 150000
28 | Q008 | YORK EARLY COLLEGE ACADEMY - Q | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/18/2023 | DIIR | 5/9/2024 | DIIR | 65000 | 65000
28 | Q008 | J.H.S. 8 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 225000 | 0
28 | Q008 | YORK EARLY COLLEGE ACADEMY - Q | DOE - RESOA | FY19 RESO A ROOM CONVERSION | Construction | Complete | 5/1/2023 | DOER | 5/25/2023 | DOER | 69636 | 82573
28 | Q008 | J.H.S. 8 - QUEENS | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1044293 | 0
28 | Q008 | J.H.S. 8 - QUEENS | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 205000 | 0
28 | Q008 | J.H.S. 8 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0
28 | Q008 | J.H.S. 8 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/7/2023 | DOES |  | DOES | 544611 | 0
28 | Q008 | J.H.S. 8 - QUEENS | DOE - Skilled Trades | DEWATERING SYSTEM PUMP REPAIRS | Construction | In-Progress | 3/19/2024 | DOES |  | DOES | 226743 | 0
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | In-Progress | 7/9/2024 | 11/7/2024 |  | 0 | 22327 | 12772
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 12/8/2023 | 4/9/2024 | 6/24/2024 | 0 | 12281 | 12281
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | In-Progress | 9/11/2024 | 12/12/2024 |  | 0 | 0 | 0
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 162 | 162
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 4/1/2024 | 7/1/2024 | 9/30/2024 | 0 | 0 | 0
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q030 | P.S. 354 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q030 | P.S. 354 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
28 | Q030 | P.S. 30 - QUEENS | DOE - RESOA | FY07 RESO A AIR CONDITIONING RETROF | Construction | PNS | PNS | PNS | PNS | DOER | 228583 | 0
28 | Q030 | P.S. 354 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
28 | Q030 | P.S. 354 - QUEENS | DOE - Skilled Trades | ACE HOT WATER HEATER | Construction | In-Progress | 7/14/2023 | DOES |  | DOES | 154801 | 0
28 | Q030 | P.S. 354 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/24/2024 | DOES |  | DOES | 65832 | 0
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q040 | JAMAICA CHILDREN'S SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q040 | P.S. 40 - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
28 | Q040 | P.S. 40 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 55000 | 0
28 | Q040 | P.S. 40 - QUEENS | DOE - RESOA | FY17 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 291274 | 0
28 | Q040 | P.S. 40 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/2/2021 | DOER |  | DOER | 140238 | 0
28 | Q040 | P.S. 40 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
28 | Q040 | P.S. 40 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
28 | Q048 | Q075 SPED - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 223355 | 192998
28 | Q048 | Q075 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/8/2024 | DIIR | 5/23/2024 | DIIR | 80000 | 80000
28 | Q054 | P.S. 54 - QUEENS | DOE - RESOA | FY19 RESO A TOILETS - STUDENTS | Construction | Complete | 6/4/2021 | DOER | 12/14/2021 | DOER | 88635 | 98443
28 | Q054 | P.S. 54 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 229973 | 0
28 | Q054 | P.S. 54 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/24/2023 | DOER |  | DOER | 247138 | 0
28 | Q054 | P.S. 54 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 5/3/2024 | DOES | 65832
28 | Q055 | P.S. 55 - QUEENS | DOE - RESOA | FY18 RESO A TOILETS-STUDENTS | Construction | Complete | 12/1/2017 | DOER | 11/19/2021 | DOER | 224762 | 206376
28 | Q055 | P.S. 55 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 2/25/2021 | DOER |  | DOER | 160750 | 0
28 | Q055 | P.S. 55 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
28 | Q055 | P.S. 55 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 2/26/2021 | DOES | 3/23/2021 | DOES | 184017 | 192640
28 | Q055 | P.S. 55 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/16/2024 | DOES | 4/23/2024 | DOES | 65832 | 189
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/29/2023 | 4/2/2024 | 4/16/2024 | 0 | 21017 | 21017
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 11/29/2023 | 4/2/2024 | 4/16/2024 | 0 | 14053 | 14053
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q072 | J.H.S. 72 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 2/14/2022 | FTK |  | FTK | 226644 | 176131
28 | Q072 | J.H.S. 72 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY15 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 6/1/2021 | DOER |  | DOER | 318213 | 0
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/25/2024 | DOER |  | DOER | 347450 | 0
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 2900000 | 0
28 | Q072 | REDWOOD MIDDLE SCHOOL | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 400000 | 0
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
28 | Q072 | J.H.S. 72 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
28 | Q072 | J.H.S. 72 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/18/2019 | DOES | 2/16/2021 | DOES | 230758 | 253273
28 | Q072 | J.H.S. 72 - QUEENS | DOE - Skilled Trades | WASTE LINE REPAIR | Construction | In-Progress | 2/12/2020 | DOES |  | DOES | 475946 | 450366
28 | Q072 | J.H.S. 72 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/2/2024 | DOES |  | DOES | 551472 | 0
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/6/2022 | 9/7/2022 | 8/24/2022 | 0 | 13514 | 13514
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 5/6/2022 | 12/8/2022 | 11/1/2022 | 0 | 23465 | 23465
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Scope | Complete | 1/30/2023 | 11/9/2023 | 2/9/2024 | 0 | 16982 | 13965
28 | Q080 | P.S. 80 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/6/2024 | DIIR | 6/13/2024 | DIIR | 100000 | 100000
28 | Q080 | P.S. 80 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 55000
28 | Q080 | P.S. 80 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
28 | Q080 | P.S. 80 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | Complete | 6/1/2021 | DOER | 10/18/2021 | DOER | 202080 | 178352
28 | Q080 | P.S. 80 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/18/2024 | DOES | 5/22/2024 | DOES | 65832 | 25689
28 | Q082 | P.S. 82 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR CEILING PLASTER IN ROOM 204(OLD WING 1904 BUILDING) | Construction | Complete | 5/14/2024 | IEH | 5/26/2024 | IEH | 15037 | 2124
28 | Q082 | P.S. 82 - QUEENS | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 190000 | 0
28 | Q082 | P.S. 82 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
28 | Q086 | P.S. 86 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 1/25/2021 | DOER |  | DOER | 94869 | 0
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
28 | Q086 | P.S. 86 - QUEENS | DOE - RESOA | RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
28 | Q099 | P.S. 99 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 328204 | 0
28 | Q099 | P.S. 99 - QUEENS | DOE - RESOA | FY18 RESO A TOILETS-STUDENTS | Construction | In-Progress | 12/1/2017 | DOER |  | DOER | 126296 | 0
28 | Q101 | P.S. 101 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 1/31/2022 | FTK |  | FTK | 216811 | 182800
28 | Q101 | P.S. 101 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/16/2021 | DOER |  | DOER | 231196 | 0
28 | Q101 | P.S. 101 - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 209359 | 0
28 | Q101 | P.S. 101 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0
28 | Q101 | P.S. 101 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 2/15/2024 | DOES |  | DOES | 127303 | 0
28 | Q101 | P.S. 101 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/8/2024 | DOES | 5/9/2024 | DOES | 65832 | 6627
28 | Q117 | P.S. 117 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 7/7/2021 | 1/3/2022 | 12/20/2021 | 0 | 34359 | 25559
28 | Q117 | P.S. 117 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 1/7/2019 | FTK |  | FTK | 234580 | 205669
28 | Q117 | P.S. 117 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/10/2024 | DIIR | 250000 | 250000
28 | Q117 | P.S. 117 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 116178 | 0
28 | Q117 | P.S. 117 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
28 | Q117 | P.S. 117 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/2/2024 | DOES | 5/16/2024 | DOES | 65832
28 | Q121 | P.S. 121 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 11/16/2018 | EMER |  | EMER | 84374 | 79867
28 | Q121 | P.S. 121 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 1950000 | 799435
28 | Q121 | P.S. 121 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 630385 | 0
28 | Q121 | P.S. 121 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 8/10/2019 | DOES | 8/12/2020 | DOES | 113070 | 944
28 | Q121 | P.S. 121 - QUEENS | DOE - Skilled Trades | BOOSTER PUMP REPLACEMENT | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 76229 | 0
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q139 | P.S. 139 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q139 | P.S. 139 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 6/14/2024 | DIIR | 50000 | 50000
28 | Q139 | P.S. 139 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
28 | Q139 | P.S. 139 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 5/31/2019 | DOES | 3/2/2020 | DOES | 239062 | 244704
28 | Q139 | P.S. 139 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 12/15/2021 | DOES |  | DOES | 140638 | 0
28 | Q140 | P.S. 140 - QUEENS | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER | Construction | In-Progress | 4/1/2024 | FTK |  | FTK | 351100 | 77853
28 | Q140 | P.S. 140 - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 37000 | 0
28 | Q140 | P.S. 140 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
28 | Q140 | P.S. 140 - QUEENS | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
28 | Q140 | P.S. 140 - QUEENS | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
28 | Q140 | P.S. 140 - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 225000 | 0
28 | Q140 | P.S. 140 - QUEENS | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 7/22/2024 | DOER |  | DOER | 54612 | 0
28 | Q140 | P.S. 140 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 9/11/2017 | DOES | 10/8/2019 | DOES | 146558 | 130811
28 | Q140 | P.S. 140 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 4/26/2024 | DOES | 65832 | 21150
28 | Q142 | Q752 SPED - QUEENS | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 11/12/2020 | DOES |  | DOES | 3893 | 0
28 | Q144 | P.S. 144 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | In-Progress | 11/13/2023 | DOER |  | DOER | 179168 | 0
28 | Q144 | P.S. 144 - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 12/15/2023 | DOER |  | DOER | 179577 | 0
28 | Q144 | P.S. 144 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 150000 | 0
28 | Q144 | P.S. 144 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/29/2021 | DOES |  | DOES | 61178 | 0
28 | Q144 | P.S. 144 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/26/2022 | DOES |  | DOES | 84686 | 0
28 | Q144 | P.S. 144 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/8/2024 | DOES | 4/16/2024 | DOES | 65832 | 9030
28 | Q157 | J.H.S. 157 - QUEENS | SCA IEH | PO18-ACM REMOVAL IN THE FOLLOWING LOCATIONS THEY ARE LOCATED ON THE 3RD FLOOR HALLWAY - BROKEN RISER | Construction | Complete | 11/22/2023 | IEH | 5/20/2024 | IEH | 1235 | 485
28 | Q157 | J.H.S. 157 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/18/2024 | DIIR | 7/10/2024 | DIIR | 80000 | 80000
28 | Q157 | J.H.S. 157 - QUEENS | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 12/10/2021 | DOER |  | DOER | 50000 | 0
28 | Q157 | J.H.S. 157 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/22/2024 | DOES |  | DOES | 65832 | 0
28 | Q160 | P.S. 160 - QUEENS | SCA CIP RESOA | FY23 RESO A LEARNING GARDEN | Scope | Complete | 2/17/2023 | 5/18/2023 | 6/7/2023 | 0 | 23557 | 23557
28 | Q160 | P.S. 160 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
28 | Q160 | P.S. 160 - QUEENS | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 65000 | 0
28 | Q160 | P.S. 160 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/13/2023 | DOER |  | DOER | 490143 | 0
28 | Q160 | P.S. 160 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 1/15/2022 | DOES | 2/22/2022 | DOES | 137945 | 37772
28 | Q160 | P.S. 160 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/24/2024 | DOES | 5/3/2024 | DOES | 65832 | 189
28 | Q161 | P.S. 161 - QUEENS | Fast Track Projects | FY23 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | FTK | FTK | FTK | FTK | 323775 | 167037
28 | Q161 | P.S. 161 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 6/10/2022 | DOES |  | DOES | 153331 | 0
28 | Q174 | P.S. 174 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 290000 | 0
28 | Q174 | P.S. 174 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
28 | Q174 | P.S. 174 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
28 | Q174 | P.S. 174 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | Complete | 3/7/2024 | DOER | 5/22/2024 | DOER | 150961
28 | Q174 | P.S. 174 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 450000 | 8500
28 | Q174 | P.S. 174 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
28 | Q174 | P.S. 174 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
28 | Q174 | P.S. 174 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/7/2024 | DOES | 5/14/2024 | DOES | 65832
28 | Q175 | P.S. 175 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/21/2022 | DOER |  | DOER | 197313 | 0
28 | Q175 | P.S. 175 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
28 | Q175 | P.S. 175 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/2/2024 | DOES |  | DOES | 65832 | 0
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Scope | Complete | 3/14/2023 | 6/12/2023 | 8/2/2023 | 0 | 39788 | 39588
28 | Q190 | J.H.S. 190 - QUEENS | Fast Track Projects | TEMPORARY OIL TANK @Q190 | Construction | In-Progress | 10/30/2019 | FTK |  | FTK | 442486 | 403928
28 | Q190 | J.H.S. 190 - QUEENS | DOE - RESOA | FY22 RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 285721 | 0
28 | Q190 | J.H.S. 190 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/8/2024 | DOER |  | DOER | 65219 | 0
28 | Q190 | J.H.S. 190 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/24/2024 | DOES |  | DOES | 602824 | 0
28 | Q196 | P.S. 196 - QUEENS | SCA IEH | PO18-OIL TANK ROOM ABATE 70 L.F. PIPE INSULATION, 25 L.F. JOINT INSULATION | Construction | In-Progress | 6/29/2023 | IEH |  | IEH | 813 | 238
28 | Q196 | P.S. 196 - QUEENS | SCA IEH | PO18-ACM PLASTER CEILING SPALLING AND FALLING ROOM G-15 ROOM HAS BEEN CLOSED AHERA BOOK IS FROM 2023 | Construction | Complete | 5/14/2024 | IEH | 5/18/2024 | IEH | 24198 | 20204
28 | Q196 | P.S. 196 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
28 | Q196 | P.S. 196 - QUEENS | DOE - RESOA | FY18 RESO A TOILETS-STUDENTS | Construction | Complete | 12/1/2017 | DOER | 9/27/2021 | DOER | 250878 | 28554
28 | Q196 | P.S. 196 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 6/28/2024 | DOER |  | DOER | 90959 | 0
28 | Q196 | P.S. 196 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 254372 | 0
28 | Q196 | P.S. 196 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/25/2024 | DOES |  | DOES | 65832 | 0
28 | Q206 | P.S. 206 - QUEENS | DOE - RESOA | FY18 RESO A TOILETS-STUDENTS | Construction | Complete | 12/1/2017 | DOER | 9/27/2021 | DOER | 78316 | 13623
28 | Q206 | P.S. 206 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | Complete | 1/14/2022 | DOER | 8/26/2022 | DOER | 110574 | 109086
28 | Q206 | P.S. 206 - QUEENS | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 2/21/2022 | DOER |  | DOER | 67809 | 0
28 | Q206 | P.S. 206 - QUEENS | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | In-Progress | 7/11/2022 | DOER |  | DOER | 176332 | 0
28 | Q206 | P.S. 206 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/2/2024 | DOES |  | DOES | 65832 | 0
28 | Q217 | I.S. 217 - QUEENS | SCA IEH | PO18-ASSIGNED TO SCA AS AN EMERGENCY ON 6/27/24 SECOND FLOOR GIRLS BATHROOM AND LOCKER ROOM ABATEMEN | Construction | Complete | 6/28/2024 | IEH | 6/30/2024 | IEH | 56442 | 50242
28 | Q217 | I.S. 217 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
28 | Q217 | I.S. 217 - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
28 | Q217 | I.S. 217 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 1/27/2023 | DOES |  | DOES | 490212 | 0
28 | Q217 | I.S. 217 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/27/2023 | DOES |  | DOES | 405571 | 0
28 | Q220 | P.S. 220 - QUEENS | DOE - RESOA | FY18 RESO A TOILETS-STUDENTS | Construction | Complete | 12/1/2017 | DOER | 9/26/2023 | DOER | 200191
28 | Q220 | P.S. 220 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | Complete | 12/7/2023 | DOER | 2/2/2024 | DOER | 139717 | 1046
28 | Q220 | P.S. 220 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 56000 | 0
28 | Q220 | P.S. 220 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/11/2017 | DOES |  | DOES | 234437 | 0
28 | Q276 | P.S. 48 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 450000 | 0
28 | Q276 | Q075 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0
28 | Q276 | P.S. 48 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/15/2024 | DOES |  | DOES | 50832 | 0
28 | Q277 | P.S. 182 - QUEENS | SCA CIP | EXTERIOR WALLS | Scope | In-Progress | 9/18/2024 | 1/8/2025 |  | 0 | 503 | 503
28 | Q277 | P.S. 182 - QUEENS | SCA CIP | EXTERIOR WALLS | Design | PNS | PNS | PNS | PNS | 0 | 2011 | 2011
28 | Q277 | P.S. 182 - QUEENS | SCA CIP | EXTERIOR WALLS | Construction | PNS | PNS | PNS | PNS | 0 | 4000 | 2502
28 | Q277 | P.S. 182 - QUEENS | SCA CIP | EXTERIOR WALLS | CM,F&E | PNS | PNS | PNS | PNS | 0 | 2306 | 1098
28 | Q277 | Q009 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/2/2024 | DIIR |  | DIIR | 100000 | 0
28 | Q277 | P.S. 182 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 10/6/2023 | DOES |  | DOES | 60794 | 0
28 | Q278 | P.S. 182 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500000 | 0
28 | Q314 | THE QUEENS SCHOOL FOR LEADERSHIP AND EXCELLENCE | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/21/2023 | DOES |  | DOES | 527850 | 0
28 | Q314 | THE QUEENS SCHOOL FOR LEADERSHIP AND EXCELLENCE | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/20/2024 | DOES |  | DOES | 50832 | 0
28 | Q383 | EZRA JACK KEATS PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/17/2024 | IEH | 10595 | 10595
28 | Q440 | FOREST HILLS HS - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION- FALLING SLATE | Construction | In-Progress | 9/1/2022 | EMER |  | EMER | 473774 | 293314
28 | Q440 | FOREST HILLS HS - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
28 | Q440 | FOREST HILLS HS - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
28 | Q440 | FOREST HILLS HS - QUEENS | DOE - RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
28 | Q440 | FOREST HILLS HS - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 11/2/2018 | DOES |  | DOES | 233035 | 0
28 | Q440 | FOREST HILLS HS - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | Complete | 7/25/2019 | DOES | 1/19/2022 | DOES | 563325 | 257833
28 | Q440 | FOREST HILLS HS - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/13/2023 | DOES |  | DOES | 955614 | 0
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | FY24 RESO A TENNIS COURT UPGRADE | Scope | Complete | 12/13/2023 | 3/22/2024 | 3/7/2024 | 0 | 36035 | 35972
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A TENNIS COURT UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A TENNIS COURT UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A TENNIS COURT UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q441 | FOREST HILLS HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A TENNIS COURT UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 1/11/2024 | 5/13/2024 |  | 0 | 412 | 412
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA IEH | PO18-ABATE 35 FEET OF ACM ON WASTE LINE IN ROOMS B35 & PAINT LOCKER ROOM ACM IS COMBINED WITH THE HO | Construction | Complete | 8/1/2024 | IEH | 8/10/2024 | IEH | 33185 | 1322
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | Fast Track Projects | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/15/2022 | FTK |  | FTK | 473479 | 473470
28 | Q470 | HILLSIDE ACADEMY FOR ARTS AND LETTERS - Q | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 12/20/2021 | FTK |  | FTK | 220315 | 52812
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | Fast Track Projects | LSP- LIGHTING UPGRADE | Construction | In-Progress | 5/29/2023 | FTK |  | FTK | 657752 | 557780
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | Fast Track Projects | LSP- LIBRARY UPGRADE | Construction | In-Progress | 4/17/2023 | FTK |  | FTK | 473975 | 278404
28 | Q470 | JAMAICA GATEWAY TO THE SCIENCES - Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0
28 | Q470 | HILLSIDE ACADEMY FOR ARTS AND LETTERS - Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0
28 | Q470 | JAMAICA GATEWAY TO THE SCIENCES - Q | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 163978 | 0
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | DOE - Skilled Trades | FLOORING REPLACEMENT | Construction | In-Progress | 3/9/2022 | DOES |  | DOES | 1000000 | 0
28 | Q471 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP RESOA | RESO A ATHLETIC FIELDS | Scope | PNS | PNS | PNS | PNS | 0 | 163 | 163
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY25 RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CULINARY KITCHEN | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q505 | HILLCREST HS - QUEENS | SCA IEH | PO18-TEST AND ABATE PIPE INSULATION IF POSITIVE 3RD FLOOR KITCHEN DRAINPIPE (SPACE ID: 4341) PIPE LO | Construction | In-Progress | 9/5/2024 | IEH |  | IEH | 61347 | 1171
28 | Q505 | HILLCREST HS - QUEENS | Fast Track Projects | CTF-LYFE CENTER | Construction | In-Progress | 3/23/2017 | FTK |  | FTK | 143916 | 130352
28 | Q505 | HILLCREST HS - QUEENS | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/21/2022 | DOER |  | DOER | 532548 | 0
28 | Q505 | HILLCREST HS - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/27/2023 | DOER |  | DOER | 623121 | 0
28 | Q505 | HILLCREST HS - QUEENS | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 9/7/2022 | DOES |  | DOES | 884052 | 0
28 | Q505 | HILLCREST HS - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 3/5/2021 | DOES |  | DOES | 183590 | 0
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELDS | Scope | Complete | 4/15/2024 | 7/17/2024 | 9/19/2024 | 0 | 155 | 155
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CTE ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 7/28/2021 | 9/11/2023 | 9/21/2023 | 0 | 20196 | 20196
28 | Q620 | THOMAS A. EDISON HS - Q | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 50000 | 0
28 | Q620 | THOMAS A. EDISON HS - Q | DOE - RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 8/27/2021 | DOER |  | DOER | 209223 | 0
28 | Q620 | THOMAS A. EDISON HS - Q | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 32846 | 0
28 | Q620 | THOMAS A. EDISON HS - Q | DOE - RESOA | FY25 RESO A CTE ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
28 | Q620 | THOMAS A. EDISON HS - Q | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 1/6/2023 | DOES |  | DOES | 754116 | 0
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/1/2021 | EMER |  | EMER | 193599 | 37683
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | Fast Track Projects | LSP - FY19 RESO A SCIENCE LAB UPGRADES | Construction | PNS | FTK | FTK | FTK | FTK | 13766 | 0
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | DOE - RESOA | FY16 RESO A GYMNASIUM UPGRADE | Construction | Complete | 12/18/2017 | DOER | 6/30/2018 | DOER | 73604 | 73604
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 65832 | 0
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Scope | Complete | 2/17/2023 | 6/21/2023 | 6/20/2023 | 0 | 12127 | 12127
28 | Q686 | I.S./H.S. 167 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Scope | Complete | 2/9/2023 | 5/10/2023 | 9/6/2023 | 0 | 77921 | 77798
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 27000 | 0
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 50000 | 0
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 225000 | 0
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 54175 | 0
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
28 | Q686 | I.S./H.S. 167 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | DOE - RESOA | FY18 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/2/2021 | DOER |  | DOER | 163514 | 0
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 200000 | 0
28 | Q686 | I.S./H.S. 167 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
28 | Q686 | Q233 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0
28 | Q690 | HS FOR LAW ENFORCEMENT - QUEENS | SCA CIP RESOA | FY24 RESO A ROOFTOP PLAYGROUND | Scope | Complete | 12/8/2023 | 4/25/2024 | 6/13/2024 | 0 | 32819 | 32574
28 | Q690 | HS FOR LAW ENFORCEMENT - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/25/2024 | DIIR | 150000 | 150000
28 | Q690 | HS FOR LAW ENFORCEMENT - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/28/2024 | DOES |  | DOES | 50832 | 0
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 400000 | 0
28 | Q695 | QUEENS GATEWAY TO HEALTH SCIENCES SECONDARY SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/18/2024 | DOES |  | DOES | 50832 | 0
28 | Q774 | QUEENS HS FOR THE SCIENCES - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 115000 | 0
28 | Q866 | P.S. 99 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 4/26/2024 | IEH | 4/30/2024 | IEH | 8733 | 8733
28 | Q882 | Q009 SPED - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 5/29/2024 | IEH | 9194 | 4419
28 | Q883 | ALTERNATE LEARNING CENTER - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/8/2024 | IEH | 8/15/2024 | IEH | 9690 | 0
29 | Q015 | P.S. 15 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 6/14/2024 | DIIR |  | DIIR | 50000 | 0
29 | Q015 | P.S. 15 - QUEENS | DOE - RESOA | FY17 RESO A LIBRARY UPGRADES | Construction | In-Progress | 7/15/2022 | DOER |  | DOER | 180667 | 0
29 | Q015 | P.S. 15 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 4/23/2024 | DOER |  | DOER | 158260 | 0
29 | Q015 | P.S. 15 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
29 | Q015 | P.S. 15 - QUEENS | DOE - Skilled Trades | ACCESSIBILITY | Construction | In-Progress | 2/28/2023 | DOES |  | DOES | 960706 | 0
29 | Q015 | P.S. 15 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 2/21/2024 | DOES |  | DOES | 893504 | 1402
29 | Q033 | P.S. 33 - QUEENS | Fast Track Projects | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 12/20/2018 | FTK |  | FTK | 132750 | 120118
29 | Q033 | P.S. 33 - QUEENS | Fast Track Projects | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/16/2021 | FTK |  | FTK | 143407 | 142017
29 | Q033 | P.S. 33 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 4/12/2024 | DIIR | 75000 | 75000
29 | Q033 | P.S. 33 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 75000
29 | Q034 | P.S. 34 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/2/2021 | 2/7/2022 | 2/3/2022 | 0 | 47137 | 47137
29 | Q034 | P.S. 34 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/29/2024 | DIIR | 5/14/2024 | DIIR | 65000 | 65000
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q035 | P.S. 35 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q035 | P.S. 35 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 8/22/2024 | FTK |  | FTK | 49192 | 9421
29 | Q035 | P.S. 35 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/2/2023 | DIIR |  | DIIR | 102000 | 0
29 | Q035 | P.S. 35 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 113000 | 0
29 | Q035 | P.S. 35 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
29 | Q035 | P.S. 35 - QUEENS | DOE - Skilled Trades | REPLACEMENT OF (5) ROOF TOPS UNITS | Construction | In-Progress | 6/4/2021 | DOES |  | DOES | 977340 | 0
29 | Q036 | P.S. 36 - QUEENS | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 2/13/2024 | DOEL |  | DOEL | 71647 | 71647
29 | Q036 | P.S. 36 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | Complete | 4/25/2024 | DOER | 4/25/2024 | DOER | 103867
29 | Q036 | P.S. 36 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | Complete | 5/15/2024 | DOER | 5/20/2024 | DOER | 41819
29 | Q037 | P.S. 37 - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 8/20/2024 | FTK |  | FTK | 42866 | 13115
29 | Q037 | P.S. 37 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
29 | Q037 | P.S. 37 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
29 | Q037 | P.S. 37 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/28/2021 | DOES |  | DOES | 200833 | 0
29 | Q037 | P.S. 37 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 7/27/2024 | DOES |  | DOES | 1302858 | 0
29 | Q038 | P.S. 38 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/7/2024 | DIIR | 4/17/2024 | DIIR | 50000
29 | Q038 | P.S. 38 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
29 | Q038 | P.S. 38 - QUEENS | DOE - Skilled Trades | BOILER BLOWBACK | Construction | In-Progress | 11/16/2018 | DOES |  | DOES | 1090118 | 0
29 | Q038 | P.S. 38 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 10/29/2021 | DOES |  | DOES | 196755 | 0
29 | Q038 | P.S. 38 - QUEENS | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 3/16/2023 | DOES |  | DOES | 228083 | 0
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q052 | P.S. 52 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 3/7/2024 | DOER |  | DOER | 400000 | 0
29 | Q052 | P.S. 52 - QUEENS | DIIT - Project Connect | DATA/VOICE & WIRELESS NETWORK CABLE WIRING, NETWORK SERVER EQUIPMENT, DATA/VOICE & WIRELESS NETWORK | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 276115 | 0
29 | Q052 | P.S. 52 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 336680 | 0
29 | Q052 | P.S. 52 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0
29 | Q052 | P.S. 52 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 120405 | 0
29 | Q052 | P.S. 52 - QUEENS | DOE - RESOA | FY24 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100733 | 0
29 | Q052 | P.S. 52 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/1/2022 | DOES |  | DOES | 58041 | 0
29 | Q059 | I.S. 59 - QUEENS | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE | Scope | Complete | 2/22/2021 | 6/22/2021 | 7/20/2021 | 0 | 18081 | 18081
29 | Q059 | I.S. 59 - QUEENS | SCA IEH | PO18-ABATE AND REMOVE PIPE INSULATION ROOM B21 MECH/FAN RM AUDI & GYM UNIT - 11 VALVE FOR PIPES, 8 S | Construction | Complete | 7/2/2024 | IEH | 9/22/2024 | IEH | 23927 | 858
29 | Q059 | I.S. 59 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 359533 | 0
29 | Q059 | I.S. 59 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
29 | Q059 | I.S. 59 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 197000 | 0
29 | Q059 | EAGLE ACADEMY III - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
29 | Q059 | I.S. 59 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 410195 | 0
29 | Q059 | I.S. 59 - QUEENS | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
29 | Q059 | I.S. 59 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 1/24/2023 | DOES |  | DOES | 60651 | 0
29 | Q059 | I.S. 59 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/17/2024 | DOES |  | DOES | 567816 | 0
29 | Q095 | P.S. 95 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 11/30/2021 | FTK |  | FTK | 245797 | 219126
29 | Q095 | P.S. 95 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
29 | Q095 | P.S. 95 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
29 | Q095 | P.S. 95 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
29 | Q109 | I.S. 109 - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 133000 | 0
29 | Q109 | I.S. 109 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 8/27/2024 | DIIR | 113000 | 113000
29 | Q109 | I.S. 109 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
29 | Q109 | I.S. 109 - QUEENS | DOE - RESOA | FY16 RESO A ROOM CONVERSIONS / PARTITIONING | Construction | In-Progress | 1/31/2018 | DOER |  | DOER | 124328 | 0
29 | Q109 | I.S. 109 - QUEENS | DOE - RESOA | FY23 RESO A LOCKER ROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
29 | Q109 | I.S. 109 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/30/2024 | DOES |  | DOES | 575333 | 0
29 | Q116 | P.S. 116 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR WHITE AIRCELL PIPE/ JOINT INSULATION IN ROOM #456 GIRLS TOILET | Construction | Complete | 3/25/2024 | IEH | 5/10/2024 | IEH | 13389 | 1645
29 | Q116 | P.S. 116 - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 385395 | 0
29 | Q116 | P.S. 116 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
29 | Q116 | P.S. 116 - QUEENS | DOE - RESOA | FY25 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/30/2023 | 3/4/2024 | 5/31/2024 | 0 | 57976 | 57976
29 | Q118 | P.S. 118 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/2/2024 | 7/2/2024 | 6/10/2024 | 0 | 422 | 422
29 | Q118 | P.S. 118 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 271621 | 107397
29 | Q118 | P.S. 118 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 165000 | 0
29 | Q118 | P.S. 118 - QUEENS | DOE - RESOA | FY22 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
29 | Q118 | P.S. 118 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 8/14/2023 | DOER |  | DOER | 189056 | 0
29 | Q118 | P.S. 118 - QUEENS | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
29 | Q118 | P.S. 118 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 200000 | 0
29 | Q118 | P.S. 118 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/23/2024 | DOES | 4/26/2024 | DOES | 65832 | 26879
29 | Q131 | P.S. 131 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 285896 | 243446
29 | Q131 | P.S. 131 - QUEENS | Fast Track Projects | LSP- VACUUM PUMP REPLACEMENT | Construction | In-Progress | 9/11/2023 | FTK |  | FTK | 98339 | 86042
29 | Q131 | P.S. 131 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 5/31/2024 | DIIR | 54000 | 54000
29 | Q131 | P.S. 131 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 64000 | 0
29 | Q131 | P.S. 131 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/1/2022 | DOER |  | DOER | 135304 | 0
29 | Q132 | P.S. 132 - QUEENS | SCA CIP RESOA | FY18 RESO A KITCHEN AREAS | Scope | Complete | 2/1/2018 | 4/5/2018 | 5/2/2018 | 0 | 29207 | 29207
29 | Q132 | P.S. 132 - QUEENS | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
29 | Q132 | P.S. 132 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 6/29/2023 | DOER |  | DOER | 313447 | 0
29 | Q132 | P.S. 132 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 3/3/2020 | DOES | 4/5/2021 | DOES | 242424 | 24040
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q134 | P.S. 134 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q134 | P.S. 134 - QUEENS | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER | Construction | In-Progress | 5/15/2023 | FTK |  | FTK | 348248 | 65038
29 | Q134 | Q233 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
29 | Q134 | P.S. 134 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
29 | Q134 | P.S. 134 - QUEENS | DOE - RESOA | FY09 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 17503 | 0
29 | Q134 | P.S. 134 - QUEENS | DOE - RESOA | FY23 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
29 | Q134 | P.S. 134 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/26/2024 | DOER |  | DOER | 180584 | 0
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q135 | P.S. 135 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q135 | P.S. 135 - QUEENS | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 6/3/2021 | FTK |  | FTK | 304848 | 297165
29 | Q135 | P.S. 135 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
29 | Q136 | P.S. 136 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 1/29/2024 | 5/29/2024 | 7/9/2024 | 0 | 20660 | 2073
29 | Q136 | P.S. 136 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 5/15/2024 | 8/16/2024 | 7/31/2024 | 0 | 0 | 0
29 | Q136 | P.S. 136 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q136 | P.S. 136 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q136 | P.S. 136 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q136 | P.S. 136 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 350000 | 0
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/15/2023 | 4/18/2024 | 4/10/2024 | 0 | 17716 | 17653
29 | Q138 | P.S. 138 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | Complete | 4/3/2024 | 7/5/2024 | 7/23/2024 | 0 | 295 | 295
29 | Q138 | P.S. 138 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 78000 | 0
29 | Q147 | P.S. 147 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION- SPALLED CONCRETE @ Q147 | Construction | In-Progress | 9/6/2022 | EMER |  | EMER | 169109 | 129222
29 | Q147 | P.S. 147 - QUEENS | SCA IEH | PO18-ABATE VALVE AND PIPE INSULATION LOCATED IN BASEMENT BOILER ROOM 4FT OF INSULATION (MARKED WITH | Construction | Complete | 8/28/2024 | IEH | 9/28/2024 | IEH | 5809 | 489
29 | Q147 | P.S. 147 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 100000 | 0
29 | Q147 | P.S. 147 - QUEENS | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 287000 | 0
29 | Q147 | P.S. 147 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 150000 | 0
29 | Q147 | P.S. 147 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 222000 | 0
29 | Q147 | P.S. 147 - QUEENS | DOE - RESOA | RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY22 RESO A ELECTRICAL UPGRADE | Scope | Complete | 1/12/2022 | 5/13/2022 | 6/6/2022 | 0 | 12805 | 12805
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE / PATH OF TRAVEL RESO A COMPUTER LAB UPGRADE | Scope | Complete | 2/6/2023 | 6/6/2023 | 5/23/2023 | 0 | 26419 | 26419
29 | Q156 | P.S. 156 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 95000 | 0
29 | Q156 | QUEENS UNITED MIDDLE SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
29 | Q156 | QUEENS UNITED MIDDLE SCHOOL | DOE - RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 10/4/2023 | DOER |  | DOER | 76500 | 0
29 | Q156 | QUEENS UNITED MIDDLE SCHOOL | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/11/2024 | DOER |  | DOER | 216517 | 0
29 | Q156 | QUEENS UNITED MIDDLE SCHOOL | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 172479 | 0
29 | Q156 | P.S. 156 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 8/2/2019 | DOES | 10/16/2019 | DOES | 222962 | 223884
29 | Q156 | P.S. 156 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 11/22/2021 | DOES |  | DOES | 94118 | 0
29 | Q156 | P.S. 156 - QUEENS | DOE - Skilled Trades | CAFETERIA CEILING TILE REPLACEMENT | Construction | In-Progress | 12/12/2023 | DOES |  | DOES | 133327 | 0
29 | Q176 | P.S. 176 - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
29 | Q176 | P.S. 176 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
29 | Q176 | P.S. 176 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | In-Progress | 6/24/2024 | 10/24/2024 |  | 0 | 16211 | 6604
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | In-Progress | 9/26/2024 | 12/30/2024 |  | 0 | 0 | 0
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q181 | P.S. 181 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q181 | P.S. 181 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 3/6/2023 | FTK |  | FTK | 93409 | 76154
29 | Q181 | P.S. 181 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/19/2022 | DOES |  | DOES | 140433 | 0
29 | Q192 | PATHWAYS COLL. PREP SCHOOL - Q | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/5/2024 | DIIR | 5/14/2024 | DIIR | 205000
29 | Q192 | I.S. 192 - QUEENS | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 59735 | 0
29 | Q192 | I.S. 192 - QUEENS | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
29 | Q192 | PATHWAYS COLL. PREP SCHOOL - Q | DOE - RESOA | FY23 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
29 | Q192 | I.S. 192 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 480149 | 0
29 | Q192 | PATHWAYS COLL. PREP SCHOOL - Q | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
29 | Q192 | PATHWAYS COLL. PREP SCHOOL - Q | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | Complete | 4/20/2023 | DOER | 8/15/2024 | DOER | 11565
29 | Q192 | I.S. 192 - QUEENS | DOE - Skilled Trades | DOMESTIC HOT WATER HOLDING TANK | Construction | In-Progress | 9/11/2020 | DOES |  | DOES | 21964 | 0
29 | Q192 | I.S. 192 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/26/2023 | DOES |  | DOES | 637315 | 0
29 | Q192 | I.S. 192 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/22/2024 | DOES |  | DOES | 65832 | 0
29 | Q192 | I.S. 192 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 4/2/2024 | DOES |  | DOES | 534843 | 1433
29 | Q195 | P.S. 195 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 200000
29 | Q195 | P.S. 195 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 255000 | 0
29 | Q195 | P.S. 195 - QUEENS | DOE - RESOA | FY14 RESO A PLAYGROUND REDEVELOPMEN | Construction | Complete | 9/30/2014 | DOER | 1/25/2023 | DOER | 1359616 | 840734
29 | Q195 | P.S. 195 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 1/31/2024 | DOES |  | DOES | 90594 | 6180
29 | Q231 | I.S. 231 - QUEENS | DIIT - RESOA | FY10 RESO A- DESKTOP COMPUTERS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500 | 0
29 | Q231 | COMMUNITY VOICES MIDDLE SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/15/2023 | DIIR | 1/24/2024 | DIIR | 50000 | 12789
29 | Q231 | COLLABORATIVE ARTS MIDDLE SCHOOL - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0
29 | Q231 | COMMUNITY VOICES MIDDLE SCHOOL - QUEENS | DOE - RESOA | FY16 RESO A MULTI-MEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 73649 | 0
29 | Q231 | COMMUNITY VOICES MIDDLE SCHOOL - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
29 | Q231 | COLLABORATIVE ARTS MIDDLE SCHOOL - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/18/2020 | DOES | 3/12/2021 | DOES | 183347 | 349287
29 | Q231 | COLLABORATIVE ARTS MIDDLE SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/17/2024 | DOES |  | DOES | 65832 | 0
29 | Q231 | COLLABORATIVE ARTS MIDDLE SCHOOL - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/2/2024 | DOES |  | DOES | 705476 | 0
29 | Q238 | Q009 SPED - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 5/2/2024 | DIIR |  | DIIR | 160000 | 0
29 | Q238 | Q009 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
29 | Q238 | I.S. 238 - QUEENS | DOE - RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 423808 | 0
29 | Q238 | I.S. 238 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
29 | Q238 | I.S. 238 - QUEENS | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0
29 | Q238 | I.S. 238 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 8/20/2021 | DOES |  | DOES | 371658 | 0
29 | Q251 | P.S. 251 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 5/10/2024 | DOES | 65832
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/17/2023 | 5/18/2023 | 4/3/2023 | 0 | 19878 | 19878
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q263 | Q177 SPED - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q263 | P.S. /I.S 295 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/16/2024 | DOES |  | DOES | 50832 | 0
29 | Q263 | P.S. /I.S 295 - QUEENS | DOE - Skilled Trades | RTU REPAIRS | Construction | In-Progress | 10/19/2023 | DOES |  | DOES | 181200 | 0
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY22 RESO A ROOFTOP GARDEN | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY18 RESO A ROOFTOP PLAYGROUND | Scope | Complete | 1/17/2018 | 4/17/2018 | 6/13/2018 | 0 | 13627 | 13627
29 | Q268 | P.S. 268 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/3/2024 | DOES |  | DOES | 50832 | 0
29 | Q268 | P.S. 268 - QUEENS | DOE - Skilled Trades | FACILITY ENHANCEMENT | Construction | In-Progress | 4/15/2024 | DOES |  | DOES | 74680 | 0
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/21/2023 | 4/24/2024 | 4/1/2024 | 0 | 15311 | 15311
29 | Q270 | P.S. / I.S. 270 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 215648 | 190705
29 | Q270 | P.S. / I.S. 270 - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0
29 | Q270 | Q004 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
29 | Q270 | P.S. / I.S. 270 - QUEENS | DOE - RESOA | FY20 RESO A ROOM UPGRADE | Construction | In-Progress | 3/7/2024 | DOER |  | DOER | 233798 | 0
29 | Q270 | P.S. / I.S. 270 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
29 | Q270 | P.S. / I.S. 270 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/3/2022 | DOES |  | DOES | 150770 | 0
29 | Q270 | P.S. / I.S. 270 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/14/2024 | DOES | 5/21/2024 | DOES | 50832
29 | Q363 | DISTRICT 29 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/17/2024 | DOES |  | DOES | 65832 | 0
29 | Q374 | SUCCESS ACADEMY CHARTER SCHOOL - ROSEDALE - NEW YORK 5 | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/7/2024 | IEH | 8/14/2024 | IEH | 10175 | 0
29 | Q387 | DISTRICT 29 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 6/4/2024 | DOES | 65832
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 12/13/2023 | 4/1/2024 | 6/18/2024 | 0 | 18337 | 18274
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 1/25/2024 | 5/10/2024 | 6/26/2024 | 0 | 19053 | 18990
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 7/9/2024 | 10/8/2024 | 8/8/2024 | 0 | 133 | 133
29 | Q420 | EXCELSIOR PREP HIGH SCHOOL - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 7/3/2024 | 10/3/2024 | 8/8/2024 | 0 | 148 | 148
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION / FY20 RESO A PATH OF TRAVEL ROOM CONVERSION | Scope | Complete | 6/1/2021 | 2/17/2023 | 1/19/2023 | 0 | 33094 | 23553
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA IEH | PO18-TEST FOR ACM, IF POSITIVE ABATE PIPE INSULATION ON WASTELINE BASEMENT CRAWLSPACE (SPACE ID: 120 | Construction | Complete | 9/4/2024 | IEH | 9/26/2024 | IEH | 1349 | 399
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/14/2023 | DIIR | 5/20/2024 | DIIR | 600000 | 600000
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
29 | Q420 | PREPARATORY ACADEMY FOR WRITERS-Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/22/2024 | DIIR | 6/13/2024 | DIIR | 100000 | 100000
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/28/2021 | DOER |  | DOER | 467653 | 0
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/31/2023 | DOER |  | DOER | 87840 | 0
29 | Q420 | PREPARATORY ACADEMY FOR WRITERS-Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 100000 | 0
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
29 | Q420 | QUEENS PREPARATORY ACADEMY - Q | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | Complete | 7/28/2021 | DOES | 11/8/2022 | DOES | 406769 | 22257
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DOE - Skilled Trades | LEAKING CURB VALVE | Construction | In-Progress | 6/26/2020 | DOES |  | DOES | 186590 | 130465
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/17/2023 | DOES |  | DOES | 519555 | 0
29 | Q442 | Q000 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR WOOD FLOOR IN 1ST FLOOR GYM/ AUDITORIUM APPROX. 4875SF | Construction | Complete | 4/17/2024 | IEH | 6/11/2024 | IEH | 49542 | 3063
29 | Q442 | Q000 - QUEENS | SCA IEH | PO18-ABATEMENT ONLY OF ENTIRE GYM FLOOR | Construction | Complete | 5/7/2024 | IEH | 6/17/2024 | IEH | 741 | 166
29 | Q442 | Q000 - QUEENS | SCA IEH | PO18-NEED ACM ABATEMENT OF ENTIRE CRAWL SPACE | Construction | In-Progress | 5/13/2024 | IEH |  | IEH | 4639 | 3875
29 | Q442 | DISTRICT 29 PRE-K CENTER | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/13/2024 | DIIR | 6/25/2024 | DIIR | 112000 | 112000
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY20 RESO A LOW VOLTAGE | Scope | Complete | 12/17/2019 | 3/19/2020 | 3/11/2020 | 0 | 6086 | 6086
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/5/2022 | 9/6/2022 | 8/29/2022 | 0 | 16094 | 16094
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Scope | Complete | 12/14/2023 | 4/2/2024 | 4/8/2024 | 0 | 15352 | 15352
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/4/2023 | 4/5/2024 | 4/25/2024 | 0 | 14806 | 14743
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY24 RESO A LOCKER ROOM UPGRADE | Scope | In-Progress | 12/4/2023 | 4/5/2024 |  | 0 | 33424 | 1283
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Scope | Complete | 3/15/2024 | 6/14/2024 | 4/8/2024 | 0 | 0 | 0
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | In-Progress | 3/15/2024 | 6/14/2024 |  | 0 | 153 | 153
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 610 | 610
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 451 | 451
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 7/21/2016 | FTK |  | FTK | 1512667 | 1319897
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
29 | Q490 | BENJAMIN FRANKLIN HS FOR FINANCE AND INFORMATION TECH | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 95000 | 0
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 11/12/2021 | DOER |  | DOER | 129281 | 0
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 50107 | 0
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DOE - RESOA | FY22 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DOE - RESOA | FY22 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
29 | Q490 | BENJAMIN FRANKLIN HS FOR FINANCE AND INFORMATION TECH | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 5/19/2023 | DOER |  | DOER | 96428 | 0
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 75000 | 0
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0
29 | Q490 | BENJAMIN FRANKLIN HS FOR FINANCE AND INFORMATION TECH | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 148000 | 0
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 3/8/2023 | DOES |  | DOES | 62936 | 0
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 12/5/2022 | DOES |  | DOES | 813527 | 0
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 5/7/2024 | DOES |  | DOES | 74768 | 0
29 | Q491 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/1/2024 | DIIR | 5/13/2024 | DIIR | 50000 | 50000
29 | Q491 | MATH, SCI., RESEARCH & TECH. HS-Q | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
29 | Q633 | EAGLE ACADEMY III - QUEENS | SCA CIP RESOA | FY24 RESO A WEIGHT ROOM | Scope | Complete | 3/21/2024 | 7/23/2024 | 7/3/2024 | 0 | 12623 | 12560
29 | Q633 | EAGLE ACADEMY III - QUEENS | Fast Track Projects | FY24 RESO A ELECTRICAL UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 5704 | 2494
29 | Q633 | EAGLE ACADEMY III - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 108569 | 0
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/12/2024 | DOER |  | DOER | 225007 | 0
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/6/2024 | DOES |  | DOES | 65832 | 0
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - Skilled Trades | SEWAGE EJECTOR PUMP | Construction | In-Progress | 12/4/2023 | DOES |  | DOES | 67359 | 0
29 | Q633 | EAGLE ACADEMY III - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/17/2024 | DOES |  | DOES | 302596 | 0
29 | Q799 | CAMBRIA HEIGHTS ACADEMY - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
29 | Q799 | CAMBRIA HEIGHTS ACADEMY - QUEENS | DOE - RESOA | FY22 RESO A DIGITAL SIGN | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
29 | Q799 | CAMBRIA HEIGHTS ACADEMY - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 7/10/2023 | DOES |  | DOES | 212493 | 0
29 | Q799 | CAMBRIA HEIGHTS ACADEMY - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/17/2024 | DOES | 6/21/2024 | DOES | 65832
29 | Q836 | P.S. 36 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/15/2022 | DOES |  | DOES | 102977 | 0
29 | Q892 | P.S. 360 - QUEENS | Fast Track Projects | FY24 RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | FTK | FTK | FTK | FTK | 190556 | 158583
29 | Q892 | P.S. 360 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/29/2023 | DIIR |  | DIIR | 144000 | 0
29 | Q892 | P.S. 360 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
29 | Q892 | P.S. 360 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/1/2024 | DOER |  | DOER | 8994 | 0
29 | Q892 | P.S. 360 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
29 | Q892 | P.S. 360 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
29 | QAFE | RIVERTON STREET CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 9/1/2021 | DIIR |  | DIIR | 100000 | 0
29 | QMAC | MERRICK ACADEMY CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
30 | Q002 | P.S. 2 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 103000 | 0
30 | Q002 | P.S. 2 - QUEENS | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/13/2023 | DOER |  | DOER | 377681 | 0
30 | Q002 | P.S. 2 - QUEENS | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 6/1/2022 | DOER |  | DOER | 85639 | 0
30 | Q002 | P.S. 2 - QUEENS | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1085000 | 0
30 | Q002 | P.S. 2 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 11/5/2021 | DOES | 7/20/2022 | DOES | 130120 | 122327
30 | Q002 | P.S. 2 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/5/2022 | DOES |  | DOES | 92607 | 0
30 | Q010 | I.S. 10 - QUEENS | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 10/1/2021 | DOER |  | DOER | 118028 | 0
30 | Q010 | I.S. 10 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 140749 | 0
30 | Q010 | I.S. 10 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 1/28/2021 | DOES | 6/15/2021 | DOES | 140743 | 147992
30 | Q010 | I.S. 10 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/13/2022 | DOES |  | DOES | 75953 | 0
30 | Q010 | I.S. 10 - QUEENS | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 5/3/2023 | DOES |  | DOES | 582463 | 0
30 | Q011 | P.S. 11 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q011 | P.S. 11 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q011 | Q255 SPED - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 175000 | 0
30 | Q011 | Q255 SPED - QUEENS | DOE - RESOA | RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
30 | Q011 | P.S. 11 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
30 | Q011 | P.S. 11 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
30 | Q011 | P.S. 11 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 800000 | 0
30 | Q017 | P.S. 17 - QUEENS | DOE - RESOA | FY10 RESO A OUTSIDE BULLETIN BOARD | Construction | PNS | PNS | PNS | PNS | DOER | 43465 | 0
30 | Q017 | P.S. 17 - QUEENS | DOE - RESOA | FY12 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 44017 | 0
30 | Q017 | THE 30TH AVENUE SCHOOL | DOE - RESOA | FY18 RESO A HYDROPONICS LAB | Construction | In-Progress | 7/16/2019 | DOER |  | DOER | 233414 | 0
30 | Q017 | P.S. 17 - QUEENS | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/1/2024 | DOER |  | DOER | 243143 | 0
30 | Q017 | THE 30TH AVENUE SCHOOL | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 465000 | 0
30 | Q017 | THE 30TH AVENUE SCHOOL | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/5/2022 | DOES |  | DOES | 138601 | 0
30 | Q017 | P.S. 17 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/6/2024 | DOES | 5/16/2024 | DOES | 65832 | 14280
30 | Q069 | P.S. 69 - QUEENS | Fast Track Projects | FIRE ALARM REPLACEMENT | Construction | In-Progress | 3/8/2019 | FTK |  | FTK | 5028859 | 4684969
30 | Q069 | P.S. 69 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 2/28/2022 | FTK |  | FTK | 563743 | 71646
30 | Q069 | P.S. 69 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 10/11/2023 | DIIR |  | DIIR | 50000 | 0
30 | Q069 | P.S. 69 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
30 | Q069 | P.S. 69 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
30 | Q069 | P.S. 69 - QUEENS | DOE - RESOA | FY10 RESO A STEEL FENCE | Construction | PNS | PNS | PNS | PNS | DOER | 55141 | 0
30 | Q069 | P.S. 69 - QUEENS | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 7/15/2024 | DOER |  | DOER | 104478 | 0
30 | Q069 | P.S. 69 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 207926 | 0
30 | Q070 | P.S. 70 - QUEENS | SCA CIP RESOA | FY20 RESO LIBRARY UPGRADE | Scope | Complete | 5/27/2022 | 9/28/2022 | 8/25/2022 | 0 | 10568 | 10568
30 | Q070 | Q004 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
30 | Q070 | P.S. 70 - QUEENS | DOE - RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 8/29/2022 | DOER |  | DOER | 292486 | 0
30 | Q070 | P.S. 70 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/18/2023 | DOER |  | DOER | 300000 | 1242
30 | Q076 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
30 | Q076 | P.S. 76 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 77000 | 0
30 | Q076 | P.S. 76 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q076 | THE RIVERVIEW SCHOOL - QUEENS | DOE - RESOA | FY21 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
30 | Q076 | P.S. 76 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/25/2024 | DOES | 4/5/2024 | DOES | 65832 | 11599
30 | Q076 | P.S. 76 - QUEENS | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 5/6/2024 | DOES |  | DOES | 71371 | 0
30 | Q084 | P.S. 84 - QUEENS | SCA IEH | PO18-ABATE REPLACE & REPLASTER BOYS CAFE CEILING CEILING TILE DROPPED PLASTER UNDERNEATH IS CRUMBLIN | Construction | Complete | 7/17/2024 | IEH | 8/23/2024 | IEH | 9733 | 972
30 | Q084 | P.S. 84 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/30/2024 | DOES | 5/3/2024 | DOES | 65832
30 | Q085 | P.S. 85 - QUEENS | SCA CIP RESOA | FY21 RESO A CAFETERIA UPGRADE / PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | Complete | 7/21/2021 | 4/4/2022 | 3/4/2022 | 0 | 10208 | 10208
30 | Q085 | P.S. 85 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER, CEILING PLASTER AND FLOOR TILES IN THE FOLLOWING LOCATIONS: STAI | Construction | In-Progress | 7/31/2023 | IEH |  | IEH | 1140 | 390
30 | Q085 | P.S. 85 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | Complete | 1/31/2022 | FTK | 7/10/2024 | FTK | 201792 | 144254
30 | Q085 | P.S. 85 - QUEENS | DOE - Skilled Trades | EXTERIOR STAIRS | Construction | In-Progress | 12/15/2023 | DOES |  | DOES | 63374 | 20500
30 | Q111 | P.S. 111 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q111 | P.S. 111 - QUEENS | DOE - RESOA | FY23 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
30 | Q111 | P.S. 111 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 4/11/2024 | DOER |  | DOER | 3691 | 0
30 | Q111 | P.S. 111 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/19/2022 | DOES |  | DOES | 83683 | 0
30 | Q111 | P.S. 111 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/10/2024 | DOES |  | DOES | 65832 | 0
30 | Q112 | P.S. 112 - QUEENS | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Scope | Complete | 12/1/2016 | 3/6/2017 | 3/8/2017 | 0 | 60433 | 60433
30 | Q112 | P.S. 112 - QUEENS | SCA IEH | PO18-OPEN FLOOR AND ABATE AND REPAIR PIPE AND PIPE SLEEVE PIPE LOCATED BETWEEN FLOOR AND CEILING ROO | Construction | Complete | 3/21/2024 | IEH | 4/7/2024 | IEH | 18671 | 18671
30 | Q112 | P.S. 112 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
30 | Q112 | P.S. 112 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
30 | Q112 | P.S. 112 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q112 | P.S. 112 - QUEENS | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | Complete | 12/30/2021 | DOER | 5/9/2024 | DOER | 174681 | 50808
30 | Q112 | P.S. 112 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/21/2023 | DOER |  | DOER | 183968 | 0
30 | Q112 | P.S. 112 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | Complete | 10/18/2023 | DOER | 4/24/2024 | DOER | 150000 | 165415
30 | Q112 | P.S. 112 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/1/2024 | DOES | 5/8/2024 | DOES | 65832
30 | Q122 | P.S. 122 - QUEENS | SCA CIP RESOA | FY16 RESO A SOLAR PANELS | Scope | Complete | 1/12/2016 | 5/26/2016 | 3/25/2016 | 0 | 41047 | 41047
30 | Q122 | P.S. 122 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ Q122 | Construction | In-Progress | 4/4/2023 | EMER |  | EMER | 59986 | 51514
30 | Q122 | P.S. 122 - QUEENS | SCA IEH | PO18-TEST WOOD FLOOR &IF POSITIVE ABATE & REPLACE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | Complete | 9/18/2024 | IEH | 9/29/2024 | IEH | 0 | 0
30 | Q122 | P.S. 122 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 1/31/2022 | FTK |  | FTK | 215129 | 185067
30 | Q122 | P.S. 122 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
30 | Q126 | I.S. 126 - QUEENS | SCA IEH | PO18-TEST BROKEN 2' RISER VALVE IN BASEMENT &IF POSITIVE ABATE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | Complete | 9/13/2024 | IEH | 9/14/2024 | IEH | 15575 | 845
30 | Q126 | I.S. 126 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/12/2024 | DIIR | 6/21/2024 | DIIR | 60000
30 | Q126 | I.S. 126 - QUEENS | DOE - RESOA | FY07 RESO A SCHOOL SAFETY | Construction | PNS | PNS | PNS | PNS | DOER | 91140 | 0
30 | Q126 | I.S. 126 - QUEENS | DOE - RESOA | FY19 RESO A LIBRARY UPGRADES | Construction | Complete | 10/1/2021 | DOER | 12/11/2021 | DOER | 112195 | 158312
30 | Q126 | I.S. 126 - QUEENS | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | Complete | 1/10/2020 | DOER | 12/28/2021 | DOER | 330034 | 198498
30 | Q126 | I.S. 126 - QUEENS | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 139566 | 0
30 | Q126 | I.S. 126 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/3/2024 | DOES |  | DOES | 849614 | 0
30 | Q127 | P.S. 127 - QUEENS | SCA IEH | PO18-TEST 3RD FL STAIRWELL DRAIN LINE &IF POSITIVE ABATE PLEASE NOTIFY ALL COPIED OF RESULTS | Construction | In-Progress | 9/23/2024 | IEH |  | IEH | 0 | 0
30 | Q127 | P.S. 127 - QUEENS | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER | Construction | In-Progress | 3/14/2022 | FTK |  | FTK | 287190 | 158041
30 | Q127 | P.S. 127 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
30 | Q127 | P.S. 127 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
30 | Q127 | P.S. 127 - QUEENS | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
30 | Q127 | P.S. 127 - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
30 | Q127 | P.S. 127 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q141 | I.S. 141 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q141 | I.S. 141 - QUEENS | SCA IEH | PO18-ABATE AND REPAIR CEILING PLASTER IN MUSIC ROOM #115 | Construction | Complete | 3/25/2024 | IEH | 4/14/2024 | IEH | 20796 | 15221
30 | Q141 | I.S. 141 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 2/28/2022 | FTK |  | FTK | 352929 | 161472
30 | Q141 | I.S. 141 - QUEENS | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 82172 | 0
30 | Q141 | I.S. 141 - QUEENS | DOE - RESOA | FY21 RESO A STEM LAB | Construction | In-Progress | 7/5/2022 | DOER |  | DOER | 161335 | 0
30 | Q141 | I.S. 141 - QUEENS | DOE - RESOA | FY24 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 72000 | 0
30 | Q145 | I.S. 145 - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN BASEMENT NORTHEAST SIDE HALLWAY APPROX. 234SF | Construction | Complete | 2/29/2024 | IEH | 6/15/2024 | IEH | 17551 | 11707
30 | Q145 | I.S. 145 - QUEENS | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 8/29/2023 | DOEL |  | DOEL | 69103 | 4103
30 | Q145 | I.S. 145 - QUEENS | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/21/2023 | DOER |  | DOER | 265441 | 0
30 | Q145 | I.S. 145 - QUEENS | DOE - RESOA | FY22 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 6/30/2023 | DOER |  | DOER | 235127 | 0
30 | Q145 | I.S. 145 - QUEENS | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 8/20/2021 | DOES |  | DOES | 295329 | 0
30 | Q145 | I.S. 145 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/4/2024 | DOES | 6/11/2024 | DOES | 65832
30 | Q145 | I.S. 145 - QUEENS | Trust For Public Land | FY23 RESO A PLAYGROUND UPGRADE | Construction | Complete | 1/2/2024 | TPL | 9/16/2024 | TPL | 3005000 | 1381042
30 | Q148 | P.S. 148 - QUEENS | DIIT - Project Connect | DATA/VOICE & WIRELESS NETWORK CABLE WIRING, NETWORK SERVER EQUIPMENT, DATA/VOICE & WIRELESS NETWORK | Purch & Install | In-Progress | 2/6/2009 | DIIT |  | DIIT | 294095 | 0
30 | Q148 | P.S. 148 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 750000 | 0
30 | Q148 | P.S. 148 - QUEENS | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
30 | Q148 | P.S. 148 - QUEENS | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 3/19/2021 | DOES |  | DOES | 61927 | 0
30 | Q148 | P.S. 148 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/28/2024 | DOES | 6/6/2024 | DOES | 65832
30 | Q149 | P.S. 149 - QUEENS | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
30 | Q149 | P.S. 149 - QUEENS | DOE - RESOA | FY17 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/3/2018 | DOER |  | DOER | 283339 | 0
30 | Q149 | P.S. 149 - QUEENS | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 275617 | 0
30 | Q149 | P.S. 149 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 450000 | 374285
30 | Q149 | P.S. 149 - QUEENS | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 90000 | 0
30 | Q149 | P.S. 149 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/28/2024 | DOES | 6/6/2024 | DOES | 65832
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY25 RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 2/1/2023 | 6/2/2023 | 10/16/2023 | 0 | 13482 | 13482
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 6/27/2024 | 9/26/2024 |  | 0 | 18507 | 938
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | In-Progress | 7/16/2024 | 10/15/2024 |  | 0 | 0 | 0
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q150 | P.S. 150 - QUEENS | SCA IEH | PO18-77/30Q150/RM 430 TEST ALL LAYERS OF FLOOR IF POSITIVE ABATE & REPLACE AHERA BOOK IS FROM 2014 | Construction | Complete | 3/20/2024 | IEH | 4/28/2024 | IEH | 37787 | 37787
30 | Q150 | P.S. 150 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 7/10/2023 | FTK |  | FTK | 329862 | 69387
30 | Q150 | P.S. 150 - QUEENS | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 75000 | 0
30 | Q150 | P.S. 150 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q150 | P.S. 150 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q150 | P.S. 150 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
30 | Q150 | P.S. 150 - QUEENS | DOE - RESOA | RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
30 | Q151 | P.S. 151 - QUEENS | Fast Track Projects | LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Construction | In-Progress | 1/15/2020 | FTK |  | FTK | 53886 | 53874
30 | Q151 | P.S. 151 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER REPLACEMENT | Construction | In-Progress | 3/21/2022 | FTK |  | FTK | 196507 | 106244
30 | Q151 | P.S. 151 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q151 | P.S. 151 - QUEENS | DOE - RESOA | FY08 RESO A PAVED AREAS - CONCRETE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
30 | Q151 | P.S. 151 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/11/2024 | DOES | 4/19/2024 | DOES | 65832 | 13612
30 | Q152 | P.S. 152 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
30 | Q152 | P.S. 152 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
30 | Q152 | P.S. 152 - QUEENS | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
30 | Q166 | P.S. 166 - QUEENS | Fast Track Projects | LSP- DOMESTIC WATER HEATER | Construction | In-Progress | 12/13/2021 | FTK |  | FTK | 223941 | 181959
30 | Q166 | P.S. 166 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q166 | P.S. 166 - QUEENS | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
30 | Q166 | P.S. 166 - QUEENS | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
30 | Q171 | P.S. 171 - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/20/2020 | EMER |  | EMER |  | 0
30 | Q171 | P.S. 171 - QUEENS | SCA IEH | PO18-TEST INSULATION FOR ACM ON ON GATE VALVE IN ROOM 130. ABATE IF POSTIVE VALVE LOCATED IN CRAWL S | Construction | Complete | 9/11/2024 | IEH | 9/14/2024 | IEH | 13520 | 604
30 | Q171 | P.S. 171 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 159000 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY19 RESO A SOLAR PANEL INSTALLATION | Construction | In-Progress | 1/3/2019 | DOER |  | DOER | 1037313 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 11/8/2021 | DOER |  | DOER | 38177 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 8/15/2022 | DOER |  | DOER | 228155 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 63081 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/22/2024 | DOER |  | DOER | 102696 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 3/23/2024 | DOER |  | DOER | 100000 | 3500
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 6/28/2024 | DOER |  | DOER | 75282 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | RESO A BATHROOM UPGRADES | Construction | In-Progress | 12/16/2023 | DOER |  | DOER | 180000 | 1424
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | RESO A FLOORING | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - RESOA | RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/19/2021 | DOES |  | DOES | 135591 | 0
30 | Q171 | P.S. 171 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 3/27/2024 | DOES | 4/4/2024 | DOES | 65832 | 12268
30 | Q204 | I.S. 204 - QUEENS | Fast Track Projects | FY22 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/10/2023 | FTK |  | FTK | 77598 | 74748
30 | Q204 | ENERGY TECH HIGH SCHOOL | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q204 | I.S. 204 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
30 | Q204 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
30 | Q204 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q204 | I.S. 204 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q204 | I.S. 204 - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 550000 | 0
30 | Q204 | I.S. 204 - QUEENS | DOE - Skilled Trades | HOT WATER HEATER REPLACEMENT | Construction | Complete | 3/26/2024 | DOES | 4/11/2024 | DOES | 60934 | 67028
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q212 | P.S. 212 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q212 | P.S. 212 - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 98000 | 0
30 | Q212 | P.S. 212 - QUEENS | DOE - RESOA | FY23 RESO A MULTIMEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
30 | Q212 | P.S. 212 - QUEENS | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0
30 | Q212 | P.S. 212 - QUEENS | DOE - Skilled Trades | ACE BMS UPGRADE | Construction | In-Progress | 2/23/2023 | DOES |  | DOES | 980644 | 548664
30 | Q222 | P.S. 222 - QUEENS | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 3/21/2022 | FTK |  | FTK | 258439 | 140917
30 | Q222 | P.S. 222 - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/29/2023 | DIIR | 2/2/2024 | DIIR | 50000
30 | Q222 | P.S. 222 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/11/2023 | DOES |  | DOES | 50832 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/28/2022 | EMER |  | EMER | 12571 | 11755
31 | R029 | P.S. 29 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 75000 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/11/2024 | DIIR | 4/9/2024 | DIIR | 75000 | 75000
31 | R029 | P.S. 29 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Construction | In-Progress | 5/20/2019 | DOER |  | DOER | 147391 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY19 RESO A PLAYGROUND | Construction | In-Progress | 8/3/2021 | DOER |  | DOER | 209238 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 10/17/2022 | DOER |  | DOER | 39314 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 7/8/2023 | DOER |  | DOER | 167381 | 0
31 | R029 | P.S. 29 - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 451000 | 0
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/17/2022 | 11/1/2023 | 1/4/2024 | 0 | 36782 | 36782
31 | R030 | P.S. 30 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R030 | P.S. 30 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R030 | P.S. 30 - STATEN ISLAND | DOE - RESOA | FY19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/19/2022 | DOER |  | DOER | 418843 | 0
31 | R030 | P.S. 30 - STATEN ISLAND | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 3994 | 0
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY23 RESO A PROJECT TBD | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Scope | Complete | 11/15/2018 | 3/21/2019 | 3/29/2019 | 0 | 14123 | 14123
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 5/12/2021 | 8/26/2021 | 1/12/2022 | 0 | 37130 | 37130
30 | Q227 | I.S. 227 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 150000 | 0
30 | Q227 | I.S. 227 - QUEENS | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 9/28/2019 | DOES | 2/12/2020 | DOES | 183425 | 194109
30 | Q227 | I.S. 227 - QUEENS | DOE - Skilled Trades | HVAC SYSTEM REPLACEMENT | Construction | In-Progress | 10/15/2022 | DOES |  | DOES | 1000000 | 1504532
30 | Q227 | I.S. 227 - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/19/2023 | DOES |  | DOES | 522304 | 0
30 | Q230 | I.S. 230 - QUEENS | DIIT - RESOA | FY10 RESO A- DESKTOP COMPUTERS | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 500 | 0
30 | Q230 | I.S. 230 - QUEENS | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/11/2022 | DOES |  | DOES | 113272 | 0
30 | Q230 | I.S. 230 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/8/2024 | DOES |  | DOES | 50832 | 0
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q234 | P.S. 234 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q234 | P.S. 234 - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 50000
30 | Q234 | I.S. 235 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0
30 | Q234 | P.S. 234 - QUEENS | DOE - RESOA | FY20 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 3/22/2022 | DOER |  | DOER | 36221 | 0
30 | Q234 | I.S. 235 - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 428000 | 0
30 | Q234 | P.S. 234 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 12/28/2023 | DOES | 5/15/2024 | DOES | 50832
30 | Q280 | P.S. 280 - QUEENS | DOE - Skilled Trades | FIRE STOPPING | Construction | Complete | 12/20/2019 | DOES | 9/14/2020 | DOES | 34313 | 34313
30 | Q280 | P.S. 280 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 6/18/2024 | DOES | 65832 | 378
30 | Q292 | P.S. 92 - QUEENS | Fast Track Projects | LSP BOOSTER SYSTEM REPLACEMENT | Construction | In-Progress | 1/29/2024 | FTK |  | FTK | 127500 | 45723
30 | Q292 | P.S. 92 - QUEENS | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 108891 | 0
30 | Q292 | P.S. 92 - QUEENS | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 290915 | 0
30 | Q292 | P.S. 92 - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
30 | Q292 | P.S. 92 - QUEENS | DOE - Skilled Trades | FIRE STOPPING | Construction | In-Progress | 7/15/2019 | DOES |  | DOES | 2224704 | 0
30 | Q292 | P.S. 92 - QUEENS | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 12/20/2023 | DOES |  | DOES | 256035 | 0
30 | Q312 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
30 | Q312 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q312 | P.S. 78 - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
30 | Q312 | P.S. 78 - QUEENS | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
30 | Q312 | P.S. 78 - QUEENS | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 4/22/2024 | DOER |  | DOER | 90943 | 0
30 | Q312 | P.S. 78 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/2/2024 | DOES | 5/9/2024 | DOES | 50832
30 | Q329 | EAST ELMHURST COMMUNITY SCHOOL - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q329 | EAST ELMHURST COMMUNITY SCHOOL - QUEENS | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
30 | Q329 | EAST ELMHURST COMMUNITY SCHOOL - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/21/2024 | DOES | 5/30/2024 | DOES | 65832
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/14/2023 | 3/18/2024 | 7/1/2024 | 0 | 16583 | 954
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/23/2024 | DIIR | 5/3/2024 | DIIR | 75000
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/23/2024 | DIIR | 5/15/2024 | DIIR | 150000 | 150000
30 | Q339 | THE WOODSIDE COMMUNITY SCHOOL - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
30 | Q346 | Q000 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 7/15/2024 | IEH | 7/27/2024 | IEH | 10123 | 0
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q389 | DISTRICT 30 PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 4/12/2024 | IEH | 10179 | 10179
30 | Q397 | DISTRICT 30 PRE-K CENTER | DOE - RESOA | FY20 RESO A HYDROPONICS LAB | Construction | In-Progress | 12/23/2021 | DOER |  | DOER | 110205 | 0
30 | Q397 | DISTRICT 30 PRE-K CENTER | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 8/12/2022 | DOES | 2/22/2023 | DOES | 228716 | 3232
30 | Q397 | DISTRICT 30 PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/12/2024 | DOES | 4/24/2024 | DOES | 65832 | 378
30 | Q404 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
30 | Q404 | HUNTERS POINT COMMUNITY MIDDLE SCHOOL -Q | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/23/2024 | DIIR | 6/4/2024 | DIIR | 75000 | 75000
30 | Q404 | THE RIVERVIEW SCHOOL - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
30 | Q404 | HUNTERS POINT COMMUNITY MIDDLE SCHOOL -Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q404 | ACAD FOR CAREERS IN TV AND FILM -Q | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/9/2023 | DOER |  | DOER | 19229 | 0
30 | Q404 | ACAD FOR CAREERS IN TV AND FILM -Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/17/2024 | DOES | 6/24/2024 | DOES | 50832
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/15/2021 | 10/1/2021 | 10/7/2021 | 0 | 34688 | 34688
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 681551 | 0
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 126000 | 0
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 295166 | 0
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | Complete | 1/13/2023 | DOES | 10/17/2023 | DOES | 833365 | 176676
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/4/2024 | DOES | 6/11/2024 | DOES | 65832
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER IN ROOMS 118 AND 218 ABATE AND REPAIR PIPE INSULATION IN ROOM 317 | Construction | Complete | 3/22/2024 | IEH | 4/7/2024 | IEH | 80941 | 80941
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA IEH | PO18-TEST ROOM 004 WALL PLASTER &IF POSITIVE ABATE & REPLASTER | Construction | Complete | 7/26/2024 | IEH | 9/1/2024 | IEH | 39103 | 785
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 3/1/2023 | FTK |  | FTK | 2021723 | 1374232
30 | Q450 | GOTHAM TECH HIGH SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DOE - RESOA | FY24 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 65000 | 0
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DOE - Skilled Trades | ENVIRONMENTAL BENEFIT PROJECT | Construction | In-Progress | 5/12/2018 | DOES |  | DOES | 2779989 | 0
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | Complete | 12/18/2020 | DOES | 1/19/2021 | DOES | 213166 | 219662
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/24/2023 | DOES |  | DOES | 611969 | 0
30 | Q451 | ACADEMY OF AMERICAN STUDIES - Q | DOE - Skilled Trades | INSTALLATION AND RELOCATION OF SPLIT DUCTLESS UNIT | Construction | In-Progress | 6/22/2018 | DOES |  | DOES | 62700 | 0
30 | Q452 | LONG ISLAND CITY H.S. | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Scope | Complete | 1/9/2024 | 4/9/2024 | 8/1/2024 | 0 | 1757 | 1757
30 | Q452 | LONG ISLAND CITY HS - Q | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 50000 | 0
30 | Q452 | LONG ISLAND CITY HS - Q | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 105000 | 0
30 | Q452 | Q993 SPED - QUEENS | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
30 | Q452 | LONG ISLAND CITY HS - Q | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
30 | Q452 | Q993 SPED - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
30 | Q452 | Q993 SPED - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
30 | Q452 | LONG ISLAND CITY HS - Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/15/2024 | DOES |  | DOES | 50832 | 0
30 | Q452 | LONG ISLAND CITY HS - Q | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/5/2024 | DOES |  | DOES | 620064 | 0
30 | Q570 | FRANK SINATRA SCL OF THE ARTS HS - QUEENS | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 35000 | 0
30 | Q570 | Q993 SPED - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
30 | Q570 | Q993 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
30 | Q570 | FRANK SINATRA SCL OF THE ARTS HS - QUEENS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
30 | Q570 | FRANK SINATRA SCL OF THE ARTS HS - QUEENS | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
30 | Q570 | FRANK SINATRA SCL OF THE ARTS HS - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/11/2024 | DOES |  | DOES | 50832 | 0
30 | Q575 | ACADEMY OF AMERICAN STUDIES - Q | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
30 | Q667 | Q004 SPED - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/1/2024 | IEH | 5/8/2024 | IEH | 10540 | 10351
30 | Q667 | Q004 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
30 | Q667 | Q004 SPED - QUEENS | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 6/24/2023 | FTK |  | FTK | 1061530 | 927535
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 5/17/2024 | DIIR | 50000 | 50000
30 | Q725 | Q721 SPED - QUEENS | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/10/2023 | DIIR | 1/14/2024 | DIIR | 75000 | 22751
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 10/31/2023 | DOER |  | DOER | 250000 | 0
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 4/18/2023 | DOES |  | DOES | 325412 | 0
30 | Q725 | HS FOR INFORMATION TECH - QUEENS | DOE - Skilled Trades | BMS UPGRADE | Construction | In-Progress | 5/20/2024 | DOES |  | DOES | 1512831 | 0
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP RESOA | FY21 RESO A ROBOTICS LAB | Scope | Complete | 8/19/2021 | 12/22/2021 | 1/6/2023 | 0 | 23506 | 23506
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | DOE - RESOA | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 8/5/2022 | DOER |  | DOER | 112044 | 0
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/5/2024 | DOES |  | DOES | 65832 | 0
30 | Q797 | P.S. 150 - QUEENS | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 5/17/2024 | IEH | 6/8/2024 | IEH | 16241 | 1601
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | Fast Track Projects | LSP- DOMESTIC HOT WATER HEATER REPLACEMENT | Construction | In-Progress | 3/13/2023 | FTK |  | FTK | 307007 | 85599
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | DOE - RESOA | FY25 RESO A HYDROPONICS LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
30 | Q800 | DIV OF SCHOOL FACILITIES - QUEENS | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 7/23/2018 | EMER |  | EMER | 666580 | 504225
30 | Q800 | CITIBANK - QUEENS | SCA IEH | PO18-ACM TEST/ABATE/REPLACE AS NECESSARY FLOORS IN THE FOLLOWING AREAS: 1) 6TH FLOOR SERVICE AREA, P | Construction | In-Progress | 3/17/2023 | IEH |  | IEH | 575 | 0
30 | Q800 | D.O.T. - QUEENS | DOE - Skilled Trades | ELEVATOR MOTOR & GENERATOR | Construction | In-Progress | 2/13/2024 | DOES |  | DOES | 229179 | 69586
30 | Q801 | SCHOOL FOOD SERVICE - QUEENS | SCA IEH | IEH PO18-DOCK & WAREHOUSE PIPE INSULATION | Construction | In-Progress | 5/25/2021 | IEH |  | IEH | 2812 | 2312
30 | Q801 | SCHOOL FOOD SERVICE - QUEENS | SCA IEH | PO18-ABATE AND REPLACE FLOOR TILES IN THE FOLLOWING LOCATIONS: RMS: 3, 7, 17, 16, 14, 2ND FL HALLWAY | Construction | Complete | 1/29/2024 | IEH | 5/16/2024 | IEH | 349 | 349
30 | Q801 | BUREAU OF SUPPLIES - QUEENS | Fast Track Projects | EMERGENCY PROTECTIVE MEASURES - HURRICANE SANDY | Construction | In-Progress | 10/31/2012 | FTK |  | FTK | 3053683 | 2542815
30 | Q801 | BUREAU OF SUPPLIES - QUEENS | DOE - Skilled Trades | ROOM CONVERSION- CONVERT TO TRAINING ROOM | Construction | In-Progress | 6/9/2016 | DOES |  | DOES | 8943 | 0
30 | Q801 | BUREAU OF SUPPLIES - QUEENS | DOE - Skilled Trades | FIRE PUMP REPLACEMENT | Construction | In-Progress | 9/30/2020 | DOES |  | DOES | 240179 | 0
30 | Q801 | QUEENS AREA OFFICE - QUEENS | DOE - Skilled Trades | MASONRY REPAIRS | Construction | In-Progress | 1/18/2024 | DOES |  | DOES | 102123 | 0
30 | Q868 | P.S. 78 - QUEENS | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/25/2024 | DOES |  | DOES | 50832 | 0
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 175000 | 0
30 | Q972 | DISTRICT 30 PRE-K CENTER | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 3/26/2024 | IEH | 5/1/2024 | IEH | 8528 | 8528
31 | R001 | P.S. 1 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A BREEZEWAY | Scope | Complete | 1/28/2022 | 5/27/2022 | 6/23/2022 | 0 | 45301 | 29936
31 | R001 | P.S. 1 - STATEN ISLAND | SCA IEH | PO18-REMOVE ACM PIPE COVERING AND METAL SLEEVING ON 1 1/4' STEAM RISER IN ROOMS 215 AND 112. COVERIN | Construction | Complete | 4/12/2024 | IEH | 4/13/2024 | IEH | 22524 | 22524
31 | R001 | P.S. 1 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 7/5/2024 | DIIR |  | DIIR | 100000 | 0
31 | R001 | P.S. 1 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - RESOA | FY20 RESO A FLOORING | Construction | In-Progress | 8/13/2021 | DOER |  | DOER | 92982 | 0
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 7/6/2022 | DOER |  | DOER | 264162 | 0
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 193570 | 0
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/11/2022 | DOES |  | DOES | 176560 | 0
31 | R001 | P.S. 1 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 4/18/2024 | DOES |  | DOES | 65832 | 0
31 | R002 | I.S. 2 - STATEN ISLAND | SCA IEH | PO18-ABATE AND REMOVE 12IN X 12IN ACOUSTIC CEILING TILE AND MASTIC IN LIBRARY RM#204. APPROX 1500 SQ | Construction | Complete | 3/22/2024 | IEH | 4/29/2024 | IEH | 98837 | 83087
31 | R002 | I.S. 2 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 5/9/2024 | DIIR | 75000 | 75000
31 | R002 | I.S. 2 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 275000 | 0
31 | R002 | I.S. 2 - STATEN ISLAND | DOE - RESOA | FY18 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 9/10/2019 | DOER |  | DOER | 333324 | 0
31 | R002 | I.S. 2 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 4/29/2024 | DOER |  | DOER | 177123 | 0
31 | R002 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ACCESSIBILITY | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R002 | I.S. 2 - STATEN ISLAND | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 427936 | 0
31 | R002 | I.S. 2 - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/13/2024 | DOES |  | DOES | 527282 | 0
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R003 | P.S. 3 - STATEN ISLAND | DIIT - RESOA | RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 140000 | 0
31 | R003 | P.S. 3 - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
31 | R003 | P.S. 3 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/6/2022 | DOES |  | DOES | 142021 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Scope | Complete | 1/21/2022 | 4/21/2022 | 8/10/2022 | 0 | 14415 | 14415
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Scope | Complete | 10/6/2023 | 2/9/2024 | 10/17/2023 | 0 | 4618 | 4618
31 | R004 | P.S. 4 - STATEN ISLAND | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/8/2020 | FTK |  | FTK | 421444 | 412299
31 | R004 | P.S. 4 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - RESOA | FY20 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 364715 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - RESOA | FY21 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 1/3/2018 | DOES |  | DOES | 75200 | 0
31 | R004 | P.S. 4 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/30/2024 | DOES | 6/7/2024 | DOES | 50832
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP RESOA | FY17 RESO A AUDITORIUM UPGRADE | Scope | In-Progress | 4/9/2018 | 8/8/2018 |  | 0 | 44678 | 44676
31 | R005 | P.S. 5 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/20/2023 | DIIR | 4/19/2024 | DIIR | 100000 | 100000
31 | R005 | P.S. 5 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
31 | R005 | P.S. 5 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R005 | P.S. 5 - STATEN ISLAND | DOE - RESOA | FY19 RESO A TOILETS - STUDENTS | Construction | In-Progress | 12/18/2021 | DOER |  | DOER | 336877 | 0
31 | R005 | P.S. 5 - STATEN ISLAND | DOE - RESOA | FY22 RESO A FENCING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R005 | P.S. 5 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FENCING UPGRADE | Construction | In-Progress | 6/6/2023 | DOER |  | DOER | 12832 | 0
31 | R005 | P.S. 5 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/15/2022 | DOES |  | DOES | 62104 | 0
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Scope | Complete | 12/7/2023 | 4/10/2024 | 3/20/2024 | 0 | 10185 | 10185
31 | R006 | P.S. 6 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 210000
31 | R006 | P.S. 6 - STATEN ISLAND | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 5/25/2023 | DOER |  | DOER | 360319 | 0
31 | R006 | P.S. 6 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 1/11/2022 | DOER |  | DOER | 339749 | 0
31 | R007 | I.S. 7 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Scope | Complete | 10/23/2023 | 2/26/2024 | 11/7/2023 | 0 | 5147 | 5147
31 | R007 | I.S. 7 - STATEN ISLAND | SCA IEH | PO18-ABATE APPROX. 30 LF PIPE INSULATION MARKED IN RED, 25FT LOCATED IN ROOM #B19 SPACE ID #1019, AP | Construction | Complete | 9/12/2024 | IEH | 9/21/2024 | IEH | 1353 | 1353
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 312916 | 0
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 4/4/2024 | DOER |  | DOER | 235255 | 0
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 97734 | 0
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 450000 | 0
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/14/2023 | DOES |  | DOES | 222760 | 0
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/14/2022 | DOES |  | DOES | 225309 | 0
31 | R007 | I.S. 7 - STATEN ISLAND | DOE - Skilled Trades | PUMP ROOM VENTILATION | Construction | In-Progress | 3/20/2024 | DOES |  | DOES | 188894 | 0
31 | R008 | P.S. 8 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS / PATH OF TRAVEL RESO A PLAYGROUNDS | Scope | Complete | 7/11/2018 | 6/15/2020 | 3/25/2021 | 0 | 78048 | 78048
31 | R008 | P.S. 8 - STATEN ISLAND | SCA IEH | PO18-SLOP SINK RM 118- ACM ABATEMENT FOR THROUGH-THE-FL DRILLING (1) 3'' HOLE NEEDED FOR A PLANNED | Construction | Complete | 6/7/2024 | IEH | 6/8/2024 | IEH | 13279 | 9279
31 | R008 | P.S. 8 - STATEN ISLAND | SCA IEH | PO18-ABATE & REPLACE FLOORS IN THE FOLLOWING ROOMS: 208, 209, 211, 213, B23 - TOTAL APPROX. 4000 SQ. | Construction | In-Progress | 9/20/2024 | IEH |  | IEH | 0 | 0
31 | R008 | P.S. 8 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R008 | P.S. 8 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R008 | P.S. 8 - STATEN ISLAND | DOE - RESOA | FY20 RESO A FLOORING | Construction | In-Progress | 8/6/2021 | DOER |  | DOER | 94108 | 0
31 | R008 | P.S. 8 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/18/2022 | DOES |  | DOES | 111417 | 0
31 | R010 | P.S. 80 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R010 | P.S. 80 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R010 | P.S. 80 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R010 | P.S. 80 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION: MEDIA CENTER | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
31 | R011 | P.S. 11 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R011 | P.S. 11 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R011 | P.S. 11 - STATEN ISLAND | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 4/24/2023 | DOER |  | DOER | 53693 | 0
31 | R011 | P.S. 11 - STATEN ISLAND | DOE - RESOA | RESO A PLAYGROUND | Construction | Complete | 7/10/2023 | DOER | 9/21/2023 | DOER | 147376
31 | R011 | P.S. 11 - STATEN ISLAND | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 2/29/2024 | DOER |  | DOER | 8107 | 0
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R013 | P.S. 13 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 65000 | 0
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY18 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/31/2019 | DOER |  | DOER | 75850 | 0
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY20 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 6/5/2023 | DOER |  | DOER | 240277 | 0
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY21 RESO A LIBRARY UPGRADE | Construction | In-Progress | 10/7/2022 | DOER |  | DOER | 305000 | 0
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY22 RESO A SUPPLEMETAL COOLING | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 259028 | 0
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R013 | P.S. 13 - STATEN ISLAND | DOE - Skilled Trades | CHILLER REPAIR | Construction | In-Progress | 5/25/2023 | DOES |  | DOES | 78336 | 0
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/11/2021 | 2/15/2022 | 3/11/2022 | 0 | 38397 | 38397
31 | R014 | P.S. 078 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
31 | R014 | P.S. 078 - STATEN ISLAND | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
31 | R014 | P.S. 078 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
31 | R014 | P.S. 078 - STATEN ISLAND | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/7/2022 | DOES |  | DOES | 89306 | 0
31 | R014 | P.S. 078 - STATEN ISLAND | DOE - Skilled Trades | RTU REPLACEMENT | Construction | In-Progress | 10/26/2023 | DOES |  | DOES | 200125 | 0
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - RESOA | FY22 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 11/6/2023 | DOER |  | DOER | 280197 | 0
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PA SYSTEM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 584000 | 0
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/14/2022 | DOES |  | DOES | 193747 | 0
31 | R016 | P.S. 16 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/17/2024 | DOES | 5/20/2024 | DOES | 65832 | 189
31 | R018 | P.S. 18 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
31 | R018 | P.S. 18 - STATEN ISLAND | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 7/5/2023 | DOER |  | DOER | 63494 | 0
31 | R018 | P.S. 18 - STATEN ISLAND | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R019 | P.S. 19 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 195000 | 0
31 | R019 | P.S. 19 - STATEN ISLAND | DOE - RESOA | FY23 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 115563 | 0
31 | R019 | P.S. 19 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/22/2022 | DOES |  | DOES | 133457 | 0
31 | R019 | P.S. 19 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/8/2024 | DOES | 4/22/2024 | DOES | 65832 | 189
31 | R020 | P.S. 20 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 193000 | 0
31 | R020 | P.S. 20 - STATEN ISLAND | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/18/2023 | DOER |  | DOER | 256052 | 0
31 | R020 | P.S. 20 - STATEN ISLAND | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 8/25/2021 | DOES |  | DOES | 67976 | 0
31 | R020 | P.S. 20 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/13/2022 | DOES |  | DOES | 56455 | 0
31 | R021 | P.S. 21 - STATEN ISLAND | SCA IEH | PO18-TEST FOR ACM IN PLASTER WALLS SPECIFICALLY WALL#3 WHICH IS THE WINDOW WALL IN ROOM 106. RECENTL | Construction | Complete | 4/30/2024 | IEH | 5/6/2024 | IEH | 0 | 0
31 | R021 | P.S. 21 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/10/2023 | DIIR | 4/3/2024 | DIIR | 170000 | 170000
31 | R021 | P.S. 21 - STATEN ISLAND | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 11/1/2021 | DOER |  | DOER | 128355 | 0
31 | R021 | P.S. 21 - STATEN ISLAND | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 1150000 | 0
31 | R021 | P.S. 21 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/16/2024 | DOES |  | DOES | 65832 | 0
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 3/17/2023 | 2/14/2024 | 1/31/2024 | 0 | 12083 | 12083
31 | R022 | P.S. 22 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 2/3/2024 | DIIR |  | DIIR | 80000 | 0
31 | R022 | P.S. 22 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
31 | R022 | P.S. 22 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
31 | R022 | P.S. 22 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 128094 | 0
31 | R022 | P.S. 22 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/2/2024 | DOES | 4/9/2024 | DOES | 65832 | 14831
31 | R023 | P.S. 23 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 1/26/2023 | 11/30/2023 | 10/19/2023 | 0 | 26414 | 26414
31 | R023 | P.S. 23 - STATEN ISLAND | Fast Track Projects | LSP SIDEWALK REPLACEMENT | Construction | In-Progress | 4/12/2024 | FTK |  | FTK | 183938 | 90300
31 | R023 | P.S. 23 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/2/2024 | DIIR | 7/11/2024 | DIIR | 75000
31 | R023 | P.S. 23 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R023 | P.S. 23 - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/5/2021 | DOER |  | DOER | 261228 | 0
31 | R023 | P.S. 23 - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 57101 | 0
31 | R023 | P.S. 23 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
31 | R023 | P.S. 23 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/6/2024 | DOES |  | DOES | 65832 | 0
31 | R024 | I.S. 24 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 6/5/2024 | DIIR | 100000
31 | R024 | I.S. 24 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY20 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 3/16/2021 | DOER |  | DOER | 8238 | 0
31 | R024 | R721 SPED - STATEN ISLAND | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 10/14/2022 | DOER |  | DOER | 80351 | 0
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/13/2023 | DOER |  | DOER | 403334 | 0
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY23 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 485000 | 0
31 | R024 | I.S. 24 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
31 | R025 | R025 SPED - STATEN ISLAND | SCA IEH | PO18-ABATE AND REPAIR WALL PLASTER IN ROOM 202 1- SPACE ID# RM 3202 RM 202 TEST WALL PLASTER UNDER W | Construction | Complete | 3/27/2024 | IEH | 4/20/2024 | IEH | 15313 | 3002
31 | R026 | P.S. 26 - STATEN ISLAND | SCA IEH | PO18-REPAIR / ENCAPSULATE AND PAINT DAMAGED ACM PLASTER AREAS ON WALL #2(APPROXIMATELY 1SF) AND WALL | Construction | Complete | 9/6/2024 | IEH | 9/7/2024 | IEH | 19506 | 2030
31 | R026 | P.S. 26 - STATEN ISLAND | Fast Track Projects | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 6/18/2021 | FTK |  | FTK | 46884 | 41598
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY20 RESO A FLOORING | Construction | In-Progress | 7/28/2022 | DOER |  | DOER | 210771 | 0
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/6/2022 | DOER |  | DOER | 315898 | 0
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FLOORING UPGRADE | Construction | In-Progress | 6/9/2023 | DOER |  | DOER | 27713 | 0
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
31 | R026 | P.S. 26 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
31 | R031 | P.S. 31 - STATEN ISLAND | DIIT - RESOA | FY19 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/13/2020 | DIIR |  | DIIR | 68000 | 0
31 | R031 | P.S. 31 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/14/2023 | DIIR |  | DIIR | 400000 | 0
31 | R031 | P.S. 31 - STATEN ISLAND | DOE - RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 127577 | 0
31 | R031 | P.S. 31 - STATEN ISLAND | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADES | Construction | In-Progress | 1/17/2024 | DOER |  | DOER | 519916 | 1828
31 | R031 | P.S. 31 - STATEN ISLAND | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
31 | R031 | P.S. 31 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/15/2024 | DOES | 5/22/2024 | DOES | 65832
31 | R032 | P.S. 32 - STATEN ISLAND | SCA IEH | PO18-ABATE PIPE INSULATION : APPROX. 15 LINEAR FEET IN TOTAL PIPING MARKED IN RED, LOCATED IN (2) AR | Construction | Complete | 8/31/2024 | IEH | 8/31/2024 | IEH | 20271 | 1450
31 | R032 | P.S. 32 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0
31 | R032 | P.S. 32 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - RESOA | FY22 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 696667 | 0
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - RESOA | FY24 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
31 | R032 | P.S. 32 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 8/12/2022 | DOES |  | DOES | 111644 | 0
31 | R034 | I.S. 34 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/25/2021 | EMER |  | EMER | 1959211 | 1939305
31 | R034 | I.S. 34 - STATEN ISLAND | SCA IEH | PO18-BASEMENT STAIRWELL A, 1 L.F. PIPE INSULATION FAN ROOM, 11 L.F. PIPE INSULATION KITCHEN, 7 L.F. | Construction | Complete | 7/17/2024 | IEH | 9/8/2024 | IEH | 16113 | 2863
31 | R034 | I.S. 34 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 12/23/2023 | DIIR | 4/4/2024 | DIIR | 150000 | 150000
31 | R034 | I.S. 34 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 100000
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 8/6/2021 | DOER |  | DOER | 167541 | 0
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 11/8/2021 | DOER |  | DOER | 221000 | 0
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) CAFETERIA UPGRADE | Construction | In-Progress | 4/3/2023 | DOER |  | DOER | 176117 | 0
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 4/17/2024 | DOER |  | DOER | 38464 | 0
31 | R034 | I.S. 34 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
31 | R035 | P.S. 35 - STATEN ISLAND | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/2/2020 | FTK |  | FTK | 264959 | 255934
31 | R035 | P.S. 35 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
31 | R036 | P.S. 36 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/2/2021 | 8/31/2021 | 12/22/2021 | 0 | 38433 | 38433
31 | R036 | P.S. 36 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/23/2023 | DIIR |  | DIIR | 200000 | 0
31 | R036 | P.S. 36 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
31 | R036 | P.S. 36 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R036 | P.S. 36 - STATEN ISLAND | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 1/21/2022 | DOER |  | DOER | 31319 | 0
31 | R036 | P.S. 36 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
31 | R038 | P.S. 38 - STATEN ISLAND | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 237524 | 0
31 | R038 | P.S. 38 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/22/2024 | DIIR | 7/1/2024 | DIIR | 75000 | 75000
31 | R038 | P.S. 38 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R038 | P.S. 38 - STATEN ISLAND | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/29/2022 | DOER |  | DOER | 1014616 | 0
31 | R038 | P.S. 38 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/1/2024 | DOES | 5/10/2024 | DOES | 65832 | 10943
31 | R039 | P.S. 39 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION- SWB @ R039 | Construction | In-Progress | 8/24/2022 | EMER |  | EMER | 17342 | 11881
31 | R039 | P.S. 39 - STATEN ISLAND | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
31 | R039 | P.S. 39 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/23/2024 | DIIR | 5/10/2024 | DIIR | 155000 | 155000
31 | R039 | P.S. 39 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R039 | P.S. 39 - STATEN ISLAND | DOE - RESOA | FY20 RESO A MAKERSPACE | Construction | In-Progress | 7/11/2022 | DOER |  | DOER | 353431 | 0
31 | R039 | P.S. 39 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FLOORING | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
31 | R039 | P.S. 39 - STATEN ISLAND | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
31 | R040 | R373 SPED - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 80000 | 0
31 | R040 | R373 SPED - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0
31 | R040 | R373 SPED - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 2/18/2022 | DOER |  | DOER | 223255 | 0
31 | R040 | R373 SPED - STATEN ISLAND | DOE - RESOA | FY24 RESO A DIGITAL SIGN | Construction | In-Progress | 6/1/2024 | DOER |  | DOER | 67341 | 0
31 | R041 | P.S. 41 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 5/26/2021 | EMER |  | EMER | 1393854 | 1163542
31 | R041 | P.S. 41 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION-EMERGENCY STABILIZATION THIRD FLOOR FACADE CRACKING | Construction | In-Progress | 8/2/2022 | EMER |  | EMER | 9472 | 5300
31 | R041 | P.S. 41 - STATEN ISLAND | SCA IEH | PO18-PATCH AND REPAIR PIPE INSULATION WORKSHOP, 1 L.F. FAN ROOM, 2 L.F. STORAGE ROOM, 2 L.F. BOILER | Construction | Complete | 7/17/2024 | IEH | 7/25/2024 | IEH | 9800 | 725
31 | R041 | P.S. 41 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Scope | Complete | 1/23/2018 | 4/23/2018 | 2/28/2018 | 0 | 25068 | 25068
31 | R042 | P.S. 42 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
31 | R042 | P.S. 42 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R042 | P.S. 42 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 8/4/2022 | DOES |  | DOES | 153800 | 0
31 | R042 | P.S. 42 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/16/2024 | DOES | 5/24/2024 | DOES | 65832
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP RESOA | FY18 RESO A ATHLETIC FIELDS | Scope | Complete | 1/12/2018 | 2/13/2018 | 3/8/2018 | 0 | 20847 | 20847
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE / FY21 RESO A SCIENCE LAB UPGRADES | Scope | Complete | 3/1/2021 | 10/19/2021 | 2/14/2022 | 0 | 43504 | 36968
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 125000 | 0
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | DIIT - RESOA | FY22 RESO A (MA) TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 7/5/2024 | DIIR | 100000
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R043 | R721 SPED - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/23/2024 | DIIR | 8/1/2024 | DIIR | 160000
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 125000 | 0
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DOE - RESOA | FY23 RESO A WATER FOUNTAIN UPGRADES | Construction | In-Progress | 9/1/2023 | DOER |  | DOER | 87989 | 0
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 3/22/2024 | DOER |  | DOER | 300000 | 0
31 | R043 | I.S./J.H.S. 63 - STATEN ISLAND | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/9/2024 | DOES |  | DOES | 50832 | 0
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | DOE - Skilled Trades | RTU COMPRESSOR REPLACEMENT | Construction | In-Progress | 6/8/2023 | DOES |  | DOES | 95581 | 98766
31 | R044 | P.S. 44 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 7/2/2024 | DIIR | 80000 | 80000
31 | R044 | P.S. 44 - STATEN ISLAND | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 7/19/2022 | DOER |  | DOER | 54780 | 0
31 | R044 | P.S. 44 - STATEN ISLAND | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 5/17/2023 | DOER |  | DOER | 86747 | 0
31 | R044 | P.S. 44 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 302225 | 0
31 | R044 | P.S. 44 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/10/2024 | DOES | 4/17/2024 | DOES | 65832 | 9421
31 | R045 | P.S. 45 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/4/2024 | DIIR | 5/1/2024 | DIIR | 330000 | 330000
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | In-Progress | 9/10/2024 | DOEL |  | DOEL | 64450 | 0
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - RESOA | FY14 RESO A FENCING | Construction | In-Progress | 8/28/2014 | DOER |  | DOER | 109262 | 0
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FENCING UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - RESOA | RESO A ROOM CONVERSION | Construction | In-Progress | 1/22/2024 | DOER |  | DOER | 180000 | 1229
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 6/14/2021 | DOES |  | DOES | 60921 | 0
31 | R045 | P.S. 45 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/10/2024 | DOES | 5/17/2024 | DOES | 65832 | 13449
31 | R046 | P.S. 46 - STATEN ISLAND | Fast Track Projects | FY18 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 5/18/2021 | FTK |  | FTK | 2585500 | 2527893
31 | R046 | P.S. 46 - STATEN ISLAND | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
31 | R046 | P.S. 46 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/6/2024 | DIIR | 4/5/2024 | DIIR | 75000 | 74992
31 | R046 | P.S. 46 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R046 | P.S. 46 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 700000 | 0
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY18 RESO A PLAYGROUNDS | Construction | In-Progress | 8/13/2021 | DOER |  | DOER | 272116 | 0
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY21 RESO A FLOORING | Construction | In-Progress | 6/28/2024 | DOER |  | DOER | 88958 | 0
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 5/3/2024 | DOES | 65832 | 14713
31 | R049 | I.S. 49 - STATEN ISLAND | SCA IEH | PO18-TEST FOR ACM, LOOSE PLASTER CEILING IN STAIRWELL 'A' , 1ST FLOOR APPROX. 2 SQ. FT. SECTION CAME | Construction | In-Progress | 12/22/2023 | IEH |  | IEH | 4829 | 1729
31 | R049 | I.S. 49 - STATEN ISLAND | Fast Track Projects | COVID VENTILATION | Construction | In-Progress | 10/2/2020 | FTK |  | FTK | 372665 | 361418
31 | R049 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - RESOA | FY19 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 7/26/2022 | DOER |  | DOER | 33275 | 0
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - RESOA | FY 19 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 7/27/2022 | DOER |  | DOER | 60461 | 0
31 | R049 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) SCIENCE LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
31 | R049 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 255000 | 0
31 | R049 | I.S. 49 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/22/2024 | DOES |  | DOES | 65832 | 0
31 | R049 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/1/2024 | DOES |  | DOES | 563042 | 0
31 | R050 | P.S. 50 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/26/2024 | DIIR | 7/5/2024 | DIIR | 75000
31 | R050 | P.S. 50 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R050 | P.S. 50 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) ROOM CONVERSION | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 500247 | 0
31 | R050 | P.S. 50 - STATEN ISLAND | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | Complete | 11/1/2019 | 2/5/2020 | 6/23/2021 | 0 | 48534 | 48534
31 | R051 | I.S. 51 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 11/10/2023 | DIIR |  | DIIR | 75000 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/10/2023 | DIIR | 4/17/2024 | DIIR | 75000 | 75000
31 | R051 | I.S. 51 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 12/27/2019 | DOER |  | DOER | 3710 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) AUDITORIUM UPGRADE | Construction | In-Progress | 11/10/2022 | DOER |  | DOER | 260234 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 8/6/2021 | DOES |  | DOES | 397298 | 0
31 | R051 | I.S. 51 - STATEN ISLAND | DOE - Skilled Trades | EARTHQUAKE REMEDIATION WORK- DISPLACED STONES | Construction | In-Progress | 4/8/2024 | DOES |  | DOES | 62561 | 0
31 | R052 | P.S. 52 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/28/2024 | DIIR | 8/6/2024 | DIIR | 165000
31 | R052 | P.S. 52 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | PNS | PNS | PNS | PNS | DOER | 63190 | 0
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY18 RESO A TOILETS-STUDENTS | Construction | In-Progress | 3/11/2019 | DOER |  | DOER | 328622 | 0
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | In-Progress | 10/20/2021 | DOER |  | DOER | 176003 | 0
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) AUDITORIUM UPGRADE | Construction | In-Progress | 8/26/2023 | DOER |  | DOER | 144177 | 0
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - RESOA | FY23 RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/18/2023 | DOER |  | DOER | 139492 | 0
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/23/2020 | DOES |  | DOES | 134930 | 0
31 | R052 | P.S. 52 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/25/2024 | DOES | 5/30/2024 | DOES | 65832
31 | R053 | P.S. 53 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 150000 | 0
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY20 RESO A BATHROOM UPGRADES | Construction | Complete | 7/19/2021 | DOER | 11/1/2021 | DOER | 292668 | 259776
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - RESOA | FY21 RESO A BATHROOM UPGRADES | Construction | In-Progress | 3/18/2022 | DOER |  | DOER | 458000 | 0
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 3/9/2016 | DOES |  | DOES | 75200 | 0
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - Skilled Trades | WATER MAIN REPAIR | Construction | In-Progress | 3/13/2018 | DOES |  | DOES | 62279 | 0
31 | R053 | P.S. 53 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/28/2024 | DOES | 6/7/2024 | DOES | 65832
31 | R054 | P.S. 54 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R054 | P.S. 54 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R054 | P.S. 54 - STATEN ISLAND | DOE - Skilled Trades | WATER HEATERS | Construction | In-Progress | 4/4/2017 | DOES |  | DOES | 75200 | 0
31 | R054 | P.S. 54 - STATEN ISLAND | DOE - Skilled Trades | ACE STEAM SYSTEM OPTIMIZATION | Construction | In-Progress | 7/25/2022 | DOES |  | DOES | 156825 | 0
31 | R054 | P.S. 54 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/7/2024 | DOES | 5/17/2024 | DOES | 65832 | 9998
31 | R055 | P.S. 55 - STATEN ISLAND | SCA IEH | PO18-TEST AND REMOVE A 6' X 2' SECTION OF LATHE AND PLASTER CEILING SPRAYED RED LOCATED IN THE BASEM | Construction | Complete | 9/11/2024 | IEH | 9/15/2024 | IEH | 870 | 870
31 | R055 | P.S. 55 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/10/2023 | DIIR | 1/14/2024 | DIIR | 75000 | 5727
31 | R055 | P.S. 55 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R055 | P.S. 55 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/12/2024 | DIIR | 4/22/2024 | DIIR | 50000
31 | R055 | P.S. 55 - STATEN ISLAND | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | Complete | 11/1/2022 | DOER | 8/23/2023 | DOER | 203882
31 | R055 | P.S. 55 - STATEN ISLAND | DOE - RESOA | FY25 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
31 | R055 | P.S. 55 - STATEN ISLAND | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 2/8/2022 | DOES |  | DOES | 83508 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DIIT - RESOA | FY09 RESO A SECURITY CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 154077 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 4/23/2024 | DIIR | 250000
31 | R056 | P.S. 56 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/7/2023 | DIIR |  | DIIR | 225000 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | FY19 RESO A SCIENCE LAB UPGRADES | Construction | In-Progress | 12/16/2019 | DOER |  | DOER | 65784 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | RESO A ROOM CONVERSION | Construction | In-Progress | 7/9/2021 | DOER |  | DOER | 56090 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | RESO A GREENROOF | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 98404 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | RESO A CAFETERIA UPGRADE | Construction | In-Progress | 8/21/2024 | DOER |  | DOER | 99072 | 0
31 | R056 | P.S. 56 - STATEN ISLAND | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/29/2021 | 10/28/2021 | 6/29/2022 | 0 | 20798 | 20798
31 | R057 | P.S. 57 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/8/2024 | DIIR | 7/25/2024 | DIIR | 60000 | 60000
31 | R057 | P.S. 57 - STATEN ISLAND | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 11/7/2023 | DOER |  | DOER | 306034 | 0
31 | R057 | P.S. 57 - STATEN ISLAND | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/21/2022 | DOER |  | DOER | 153693 | 0
31 | R057 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 315000 | 0
31 | R057 | P.S. 57 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 5/20/2024 | DOES | 5/24/2024 | DOES | 65832 | 189
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/29/2021 | 10/28/2021 | 3/4/2022 | 0 | 32573 | 32573
31 | R058 | P.S. 58 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R058 | P.S. 58 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/23/2024 | DIIR | 6/18/2024 | DIIR | 50000 | 50000
31 | R058 | P.S. 58 - STATEN ISLAND | DOE - RESOA | FY14 RESO A ROOM CONVERSIONS / PART | Construction | In-Progress | 8/25/2014 | DOER |  | DOER | 80295 | 0
31 | R058 | P.S. 58 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 12/13/2023 | DOES |  | DOES | 50832 | 0
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Scope | Complete | 7/14/2022 | 10/13/2022 | 1/3/2023 | 0 | 9924 | 9924
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Scope | Complete | 11/20/2023 | 1/22/2024 | 11/30/2023 | 0 | 3718 | 3718
31 | R059 | THE HARBOR VIEW SCHOOL - R | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 3/16/2023 | DOER |  | DOER | 139271 | 0
31 | R059 | THE HARBOR VIEW SCHOOL - R | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
31 | R059 | THE HARBOR VIEW SCHOOL - R | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/2/2021 | 1/20/2022 | 1/20/2022 | 0 | 25752 | 25752
31 | R060 | P.S. 60 - STATEN ISLAND | SCA IEH | PO18-ACM TESTING ON SCHOOL SIGN IN FRONT OF THE SCHOOL | Construction | In-Progress | 1/5/2024 | IEH |  | IEH | 3935 | 1235
31 | R060 | P.S. 60 - STATEN ISLAND | SCA IEH | PO18-ABATEMENT OF FLOOR TILES AND CHALKBOARD MASTIC IN ROOMS 210 AND 106 | Construction | Complete | 5/31/2024 | IEH | 6/8/2024 | IEH | 73455 | 57081
31 | R060 | P.S. 60 - STATEN ISLAND | Fast Track Projects | LSP REPLACE UNIVENTS | Construction | In-Progress | 1/12/2023 | FTK |  | FTK | 443115 | 198266
31 | R060 | P.S. 60 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R060 | P.S. 60 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R060 | P.S. 60 - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
31 | R060 | P.S. 60 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/9/2024 | DOES | 4/17/2024 | DOES | 65832 | 9237
31 | R061 | I.S. 61 - STATEN ISLAND | DIIT - RESOA | FY18 RESO A TECHNOLOGY | Purch & Install | In-Progress | 6/30/2021 | DIIR |  | DIIR | 100000 | 0
31 | R061 | I.S. 61 - STATEN ISLAND | DOE - RESOA | FY23 RESO A SUPPLEMENTAL COOLING | Construction | In-Progress | 7/15/2022 | DOER |  | DOER | 564532 | 0
31 | R061 | I.S. 61 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | In-Progress | 12/4/2023 | DOER |  | DOER | 900000 | 61379
31 | R062 | THE KATHLEEN GRIMM SCHOOL FOR LEADERSHIP AND SUSTAINABILITY | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/21/2024 | DIIR | 5/14/2024 | DIIR | 50000 | 50000
31 | R062 | THE KATHLEEN GRIMM SCHOOL FOR LEADERSHIP AND SUSTAINABILITY | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 195000 | 0
31 | R062 | THE KATHLEEN GRIMM SCHOOL FOR LEADERSHIP AND SUSTAINABILITY | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 1/27/2020 | DOER |  | DOER | 145255 | 0
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 5/13/2024 | DIIR | 250000
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 5/13/2024 | DIIR | 50000
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/23/2024 | DIIR | 4/3/2024 | DIIR | 90000 | 90000
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | DOE - RESOA | FY20 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R066 | THE PORT RICHMOND SCHOOL FOR VISIONARY LEARNING | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
31 | R068 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 2/27/2024 | DOES |  | DOES | 50832 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Scope | Complete | 1/3/2024 | 4/3/2024 | 3/20/2024 | 0 | 1496 | 1496
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 216 | 216
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 370579 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY20 RESO A TECHNOLOGY | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 50000 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 4/1/2023 | DIIR |  | DIIR | 225000 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R069 | P.S. 69 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/25/2024 | DOES | 5/3/2024 | DOES | 65832 | 10470
31 | R070 | THE YOUNG WOMEN�S LEADERSHIP SCHOOL OF STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 2/21/2024 | DIIR | 5/20/2024 | DIIR | 65000 | 65000
31 | R070 | THE YOUNG WOMEN�S LEADERSHIP SCHOOL OF STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/27/2024 | DIIR | 7/8/2024 | DIIR | 70000 | 70000
31 | R070 | THE WAVERLY ACADEMY OF EMPOWERED LEARNERS | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 250000 | 0
31 | R070 | THE WAVERLY ACADEMY OF EMPOWERED LEARNERS | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 200000 | 0
31 | R070 | THE YOUNG WOMEN�S LEADERSHIP SCHOOL OF STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 120000 | 0
31 | R070 | THE WAVERLY ACADEMY OF EMPOWERED LEARNERS | DOE - RESOA | RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 175000 | 0
31 | R071 | P.S. 48 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 155000 | 0
31 | R071 | P.S. 48 - STATEN ISLAND | DOE - RESOA | FY23 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 150000 | 0
31 | R071 | P.S. 48 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
31 | R071 | P.S. 48 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/19/2024 | DOES |  | DOES | 50832 | 0
31 | R072 | I.S. 72 - STATEN ISLAND | DIIT - RESOA | FY11 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 109492 | 0
31 | R072 | I.S. 72 - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R072 | I.S. 72 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/16/2024 | DIIR | 7/25/2024 | DIIR | 125000
31 | R072 | I.S. 72 - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R072 | I.S. 72 - STATEN ISLAND | DOE - RESOA | FY22 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
31 | R072 | I.S. 72 - STATEN ISLAND | DOE - RESOA | FY23 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 7/14/2023 | DOER |  | DOER | 227647 | 0
31 | R072 | I.S. 72 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
31 | R075 | I.S. 75 - STATEN ISLAND | SCA IEH | PO18-CAFETERIA TILE FLOOR - ABATE FLOOR & REPLACE WITH NEW VCT FLOORING CAFETERIA IS APPROX. 7000 SQ | Construction | Complete | 3/19/2024 | IEH | 4/27/2024 | IEH | 183269 | 165694
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY23 RESO A MEDIA UPGRADE | Construction | In-Progress | 5/24/2023 | DOER |  | DOER | 19814 | 0
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY23 RESO A FLOORING UPGRADE | Construction | In-Progress | 7/31/2023 | DOER |  | DOER | 130041 | 0
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY24 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 523537 | 0
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 180000 | 0
31 | R075 | I.S. 75 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R077 | THE RICHMOND PRE-K CENTER | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 1/25/2024 | DIIR | 3/30/2024 | DIIR | 50000 | 7035
31 | R077 | THE RICHMOND PRE-K CENTER | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 6/23/2024 | DIIR | 9/6/2024 | DIIR | 158000
31 | R077 | THE RICHMOND PRE-K CENTER | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | In-Progress | 9/15/2023 | DOER |  | DOER | 159428 | 0
31 | R077 | THE RICHMOND PRE-K CENTER | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 75000 | 0
31 | R077 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 50832 | 0
31 | R080 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 11/12/2019 | DOES |  | DOES | 831928 | 0
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 180000 | 0
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/17/2024 | DOES |  | DOES | 65832 | 0
31 | R086 | R721 SPED - STATEN ISLAND | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 52000 | 0
31 | R086 | R721 SPED - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 7/5/2024 | DOES | 50832
31 | R089 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/9/2024 | DOES |  | DOES | 50832 | 0
31 | R090 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/15/2024 | DOES |  | DOES | 50832 | 0
31 | R091 | THE RICHMOND PRE-K CENTER | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R091 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/1/2024 | DOES | 4/12/2024 | DOES | 65832 | 9421
31 | R093 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 2/6/2024 | DOES | 5/3/2024 | DOES | 65832 | 8891
31 | R094 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/10/2024 | DOES |  | DOES | 50832 | 0
31 | R100 | THE RICHMOND PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R100 | THE RICHMOND PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R100 | THE RICHMOND PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R100 | THE RICHMOND PRE-K CENTER | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R100 | THE RICHMOND PRE-K CENTER | DOE - RESOA | FY25 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R101 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/20/2024 | DOES |  | DOES | 50832 | 0
31 | R110 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 3/12/2024 | DOES |  | DOES | 50832 | 0
31 | R112 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/23/2024 | DOES |  | DOES | 65832 | 0
31 | R113 | THE RICHMOND PRE-K CENTER | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/6/2024 | DOES |  | DOES | 50832 | 0
31 | R113 | 3K CENTER @ 841 FATHER CAPODANNO BOULEVARD - STATEN ISLAND | DOE Managed PRE-K | LEASE | Construction | In-Progress | 9/11/2019 | DOEP |  | DOEP | 34454 | 0
31 | R119 | R025 SPED - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 1/17/2024 | DOES |  | DOES | 65832 | 0
31 | R435 | NEW DORP HS - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 12/20/2023 | DIIR |  | DIIR | 175000 | 0
31 | R435 | NEW DORP HS - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 4/15/2024 | DIIR | 6/24/2024 | DIIR | 75000
31 | R435 | NEW DORP HS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | In-Progress | 8/9/2021 | DOER |  | DOER | 59263 | 0
31 | R435 | NEW DORP HS - STATEN ISLAND | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 345824 | 0
31 | R435 | NEW DORP HS - STATEN ISLAND | DOE - RESOA | FY25 RESO A BATHROOM UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0
31 | R436 | NEW DORP HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Scope | Complete | 3/5/2021 | 7/29/2021 | 1/4/2023 | 0 | 321578 | 233854
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA IEH | PO18-ABATE - CEILING TILES ARE LOOSE AND SOME HAVE FALLEN PTA ROOM C54 - SPACE ID #1054 | Construction | Complete | 4/19/2024 | IEH | 4/21/2024 | IEH | 35990 | 35990
31 | R440 | STATEN ISLAND TECHNICAL HS - R | Fast Track Projects | FY21 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 10/19/2023 | FTK |  | FTK | 145508 | 130574
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/24/2023 | DOES |  | DOES | 84136 | 0
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 9/30/2022 | DOES |  | DOES | 151197 | 0
31 | R440 | STATEN ISLAND TECHNICAL HS - R | DOE - Skilled Trades | HEATING PLANT UPGRADE | Construction | In-Progress | 12/13/2023 | DOES |  | DOES | 263819 | 117327
31 | R445 | PORT RICHMOND HS - R | DOE - RESOA | FY22 RESO A (MA) AUDITORIUM UPGRADE | Construction | In-Progress | 9/26/2022 | DOER |  | DOER | 197249 | 0
31 | R445 | PORT RICHMOND HS - R | DOE - RESOA | FY22 RESO A (MA) SCIENCE LAB | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
31 | R445 | PORT RICHMOND HS - R | DOE - Skilled Trades | ELEVATOR UPGRADE | Construction | In-Progress | 2/17/2017 | DOES |  | DOES | 15242 | 0
31 | R445 | PORT RICHMOND HS - R | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 6/24/2024 | DOES | 7/10/2024 | DOES | 65832
31 | R445 | PORT RICHMOND HS - R | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/31/2024 | DOES |  | DOES | 743382 | 0
31 | R445 | PORT RICHMOND HS - R | DOE - Skilled Trades | COLLAPSED ROOF DRAIN | Construction | In-Progress | 3/18/2024 | DOES |  | DOES | 157837 | 0
31 | R446 | PORT RICHMOND HS - R | Fast Track Projects | LSP REPLACE BOILER | Construction | In-Progress | 7/23/2019 | FTK |  | FTK | 730398 | 656101
31 | R450 | CURTIS HS - STATEN ISLAND | SCA IEH | PO18-ABATEMENT OF EXISTING CEILING TILES AND WIRE INSULATION IN ROOM 124 SUITE | Construction | Complete | 5/31/2024 | IEH | 6/1/2024 | IEH | 35841 | 30581
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSIONS | Construction | In-Progress | 6/1/2022 | DOER |  | DOER | 326302 | 0
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - RESOA | FY23 RESO A ELECTRICAL UPGRADE | Construction | In-Progress | 4/22/2024 | DOER |  | DOER | 75231 | 0
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - RESOA | RESO A- FY24 RESO A PAVED AREA - BLACKTOP | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - Skilled Trades | STAGE RIGGING & DRAPERY | Construction | In-Progress | 6/7/2017 | DOES |  | DOES | 29494 | 0
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/7/2017 | DOES |  | DOES | 152778 | 0
31 | R450 | CURTIS HS - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/12/2023 | DOES |  | DOES | 489606 | 0
31 | R451 | CURTIS HS - STATEN ISLAND | DOE - RESOA | RESO A ATHLETIC FIELDS | Construction | In-Progress | 12/27/2021 | DOER |  | DOER | 2636300 | 8207
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA Emergency Response | SIDEWALK BRIDGING | Construction | In-Progress | 4/6/2011 | EMER |  | EMER |  | 0
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION- SPALLED CRACKED CONCRETE | Construction | In-Progress | 9/7/2022 | EMER |  | EMER | 3526500 | 1934607
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA IEH | PO18-ASSIST PLUMBERS: ROOM # A-210, OPEN CEILING AND REMOVE PIPE COVERING PIPE LEAKING IN CEILING CA | Construction | Complete | 6/15/2024 | IEH | 6/16/2024 | IEH | 17109 | 11815
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA IEH | PO18-REMOVE APPROX 5 FT OF ACM PIPE COVERING ON 8 INCH PIPE LOCATED IN ROOM D010 STORAGE ROOM. PIPE | Construction | Complete | 8/10/2024 | IEH | 8/11/2024 | IEH | 3300 | 0
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/8/2024 | DIIR |  | DIIR | 75000 | 0
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/10/2024 | DIIR | 7/19/2024 | DIIR | 50000
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | DOE - RESOA | FY25 RESO A GYMNASIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 600000 | 0
31 | R455 | R721 SPED - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/31/2024 | DOES |  | DOES | 820398 | 0
31 | R456 | TOTTENVILLE HS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ATHLETIC FIELDS | Construction | In-Progress | 8/31/2022 | DOER |  | DOER | 760164 | 0
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A ROOM CONVERSION | Scope | Complete | 10/26/2023 | 2/26/2024 | 1/31/2024 | 0 | 28759 | 28759
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 11/7/2023 | 3/8/2024 | 1/31/2024 | 0 | 95 | 95
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | Fast Track Projects | PATH OF TRAVEL LSP ROOM CONVERSION | Construction | In-Progress | 1/14/2022 | FTK |  | FTK | 152012 | 130684
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 202093 | 0
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY23 RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 500000 | 0
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 1/31/2024 | DOER |  | DOER | 47312 | 0
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADE | Construction | In-Progress | 9/7/2017 | DOES |  | DOES | 277650 | 0
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | Complete | 3/2/2020 | DOES | 9/23/2022 | DOES | 479624 | 570220
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - Skilled Trades | ACE FAN SYSTEM UPGRADE | Construction | In-Progress | 2/3/2020 | DOES |  | DOES | 39427 | 182184
31 | R460 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 2/20/2024 | DOES |  | DOES | 857963 | 0
31 | R461 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Scope | Complete | 3/3/2021 | 4/1/2021 | 10/19/2021 | 0 | 74387 | 74387
31 | R461 | SUSAN E. WAGNER HS - STATEN ISLAND | DOE - RESOA | FY25 RESO A ATHLETIC FIELDS | Construction | PNS | PNS | PNS | PNS | DOER | 400000 | 0
31 | R462 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/5/2024 | IEH | 8/16/2024 | IEH | 10714 | 0
31 | R470 | CONCORD HS - R | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R470 | CONCORD HS - R | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R470 | CONCORD HS - R | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R470 | CONCORD HS - R | SCA CIP RESOA | PATH OF TRAVEL RESO A IPDVS CAMERA INSTALLATION | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY25 RESO A IPDVS CAMERA INSTALLATION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY22 RESO A (MA) CULINARY KITCHEN / PATH OF TRAVEL RESO A (MA) CULINARY KITCHEN | Scope | Complete | 3/10/2022 | 2/24/2023 | 1/30/2023 | 0 | 35169 | 35169
31 | R470 | CONCORD HS - R | Fast Track Projects | FY23 RESO A ELECTRICAL UPGRADE | Construction | PNS | FTK | FTK | FTK | FTK | 7536 | 7086
31 | R470 | CONCORD HS - R | DOE - RESOA | FY19 RESO A ROOM CONVERSION | Construction | In-Progress | 7/30/2021 | DOER |  | DOER | 59574 | 0
31 | R470 | CONCORD HS - R | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/26/2019 | DOES |  | DOES | 199770 | 0
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 6/20/2017 | EMER |  | EMER | 35275 | 35275
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA IEH | PO18-CAFETERIA ABATE APPROX 831 SQ. FT. CEILING TILES - ROOM 406A, NURSE'S OFFICE ABATE APPROX 6 SQ. | Construction | Complete | 7/30/2024 | IEH | 9/10/2024 | IEH | 845 | 845
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | Fast Track Projects | CTF ROOM CONVERSION | Construction | In-Progress | 7/18/2022 | FTK |  | FTK | 3614401 | 2978307
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | Fast Track Projects | LSP VENTILATION/DUST COLLECTION SYSTEM | Construction | In-Progress | 8/31/2018 | FTK |  | FTK | 258754 | 239826
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/6/2024 | DIIR | 7/15/2024 | DIIR | 490000
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DOE - RESOA | RESO A ROOM CONVERSION | Construction | In-Progress | 8/21/2023 | DOER |  | DOER | 32287 | 0
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DOE - RESOA | FY20 RESO A ROOFTOP PLAYGROUND | Construction | In-Progress | 1/12/2024 | DOER |  | DOER | 250000 | 0
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DOE - RESOA | FY21 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 4911 | 0
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 6/26/2018 | DOES |  | DOES | 324637 | 0
31 | R722 | R721 SPED - STATEN ISLAND | SCA Emergency Response | TEMPORARY BOILER | Construction | In-Progress | 4/10/2017 | EMER |  | EMER |  | 0
31 | R722 | R721 SPED - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 9/6/2022 | EMER |  | EMER | 721259 | 674444
31 | R722 | R721 SPED - STATEN ISLAND | DIIT - Project Connect | CLASSROOM CONNECTIVITY | Purch & Install | In-Progress | 11/1/2019 | DIIT |  | DIIT | 308330 | 0
31 | R801 | PATHWAYS TO GRADUATION - CITYWIDE | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 7/3/2024 | DOES |  | DOES | 65832 | 0
31 | R825 | R025 SPED - STATEN ISLAND | SCA IEH | PO18-ASSIST PLUMBERS: TEST CONCRETE FLOOR APPXOX. 3 IN X 3 IN AREA MARKED WITH A RED X. IF POSITIVE, | Construction | Complete | 6/28/2024 | IEH | 7/27/2024 | IEH | 18258 | 761
31 | R825 | R025 SPED - STATEN ISLAND | SCA IEH | PO18-ABATE PIPE INSULATION IN THE SENSORY ROOM, SPACE ID #1006 C.E. | Construction | Complete | 9/8/2024 | IEH | 9/8/2024 | IEH | 2465 | 2465
31 | R825 | R025 SPED - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 75000 | 0
31 | R825 | R025 SPED - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 280000 | 0
31 | R825 | R025 SPED - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 190000 | 0
31 | R825 | R025 SPED - STATEN ISLAND | DOE - RESOA | FY22 RESO A (MA) AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 100000 | 0
31 | R825 | R025 SPED - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/29/2024 | DOES | 5/3/2024 | DOES | 50832 | 189
31 | R826 | R025 SPED - STATEN ISLAND | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/8/2024 | IEH | 8/23/2024 | IEH | 11153 | 0
31 | R826 | P.S. 3 - STATEN ISLAND | DOE - Skilled Trades | ELECTRICAL WORK FOR A/C INITIATIVE | Construction | In-Progress | 10/25/2017 | DOES |  | DOES | 10726 | 0
31 | R829 | P.S. 65 - STATEN ISLAND | SCA Emergency Response | EMERGENCY- CLOCK TOWER @ R829 | Construction | In-Progress | 8/9/2023 | EMER |  | EMER |  | 0
31 | R829 | P.S. 65 - STATEN ISLAND | DIIT - RESOA | FY23 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 11/23/2023 | DIIR | 2/26/2024 | DIIR | 50000 | 50000
31 | R829 | P.S. 65 - STATEN ISLAND | DOE - RESOA | FY24 RESO A CAFETERIA UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
31 | R829 | P.S. 65 - STATEN ISLAND | DOE - RESOA | FY25 RESO A STEM LAB | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R829 | P.S. 65 - STATEN ISLAND | DOE - Skilled Trades | RTU UPGRADE | Construction | In-Progress | 8/14/2023 | DOES |  | DOES | 293466 | 0
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | Scope | Complete | 12/22/2014 | 3/25/2015 | 4/15/2015 | 0 | 25380 | 25380
31 | R831 | P.S. 74 - STATEN ISLAND | DIIT - RESOA | FY14 RESO A IP SURVEILLANCE CAMERA | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 175000 | 0
31 | R831 | P.S. 74 - STATEN ISLAND | DOE - Lead Paint | LEAD PAINT ABATEMENT | Construction | Complete | 11/14/2023 | DOEL | 2/20/2024 | DOEL | 69704 | 69704
31 | R831 | P.S. 74 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | Fast Track Projects | LSP FY23 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 5/17/2023 | FTK |  | FTK | 72347 | 66539
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - RESOA | FY20 RESO A ROOM CONVERSION | Construction | In-Progress | 11/30/2023 | DOER |  | DOER | 97489 | 0
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 125000 | 0
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 4/26/2019 | DOES |  | DOES | 212656 | 0
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | DOE - Skilled Trades | INTERIOR SPACES | Construction | In-Progress | 7/1/2024 | DOES |  | DOES | 291404 | 0
31 | R861 | P.S. 861 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Scope | Complete | 7/30/2021 | 10/29/2021 | 2/17/2022 | 0 | 12540 | 12540
31 | R861 | P.S. 861 - STATEN ISLAND | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 129000 | 0
31 | R861 | P.S. 861 - STATEN ISLAND | DOE - RESOA | FY25 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
31 | R861 | P.S. 861 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/7/2024 | DOES |  | DOES | 50832 | 0
31 | R880 | P.S. 80 - STATEN ISLAND | SCA Emergency Response | EMERGENCY STABILIZATION | Construction | In-Progress | 2/12/2020 | EMER |  | EMER | 2839480 | 2838547
31 | R880 | P.S. 80 - STATEN ISLAND | SCA IEH | PO18-ASSIST ELECTRICICANS: TEST VCT FLOOR AND ADHESIVES FOR ACM. ELECTRICIANS NEED TO DRILL FLOOR MO | Construction | Complete | 7/31/2024 | IEH | 8/10/2024 | IEH | 13000 | 2900
31 | R880 | P.S. 80 - STATEN ISLAND | DOE - RESOA | FY24 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 300000 | 0
31 | R880 | P.S. 80 - STATEN ISLAND | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 7/19/2018 | DOES |  | DOES | 436958 | 0
31 | R880 | P.S. 80 - STATEN ISLAND | DOE - Skilled Trades | CAFETERIA SERVING LINE | Construction | In-Progress | 4/11/2023 | DOES |  | DOES | 710012 | 0
31 | R880 | P.S. 80 - STATEN ISLAND | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 6/10/2024 | DOES |  | DOES | 65832 | 0
31 | R886 | P.S. 80 - STATEN ISLAND | Fast Track Projects | CTF CHARTER MATCH ROOM CONVERSION | Construction | In-Progress | 10/2/2019 | FTK |  | FTK | 1302925 | 1282026
31 | R973 | R373 SPED - STATEN ISLAND | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/9/2024 | IEH | 8/27/2024 | IEH | 10542 | 0
31 | RALZ | RICHMOND PREPARATORY CHARTER SCHOOL | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 60000 | 0
31 | RALZ | RICHMOND PREPARATORY CHARTER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
31 | RAMT | STATEN ISLAND HEBREW PUBLIC CHARTER SCHOOL | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
32 | K045 | P.S. 45 - BROOKLYN | SCA IEH | PO18-PLEASE REMOVE APPROXIMATELY 10 LINEAR FEET OF ACM FROM PIPE IN ROOM# 3221B | Construction | Complete | 9/1/2024 | IEH | 9/4/2024 | IEH | 15680 | 471
32 | K045 | P.S. 45 - BROOKLYN | DOE - RESOA | FY24 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 2/12/2024 | DOER |  | DOER | 50000 | 0
32 | K075 | P.S. 75 - BROOKLYN | DOE - RESOA | FY20 RESO A LIBRARY UPGRADE | Construction | Complete | 7/15/2022 | DOER | 2/12/2024 | DOER | 172368
32 | K075 | P.S. 75 - BROOKLYN | DOE - RESOA | FY20 RESO A SCIENCE LAB UPGRADE | Construction | In-Progress | 3/8/2021 | DOER |  | DOER | 153231 | 0
32 | K075 | P.S. 75 - BROOKLYN | DOE - RESOA | FY23 RESO A PLAYGROUND UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 189867 | 0
32 | K075 | P.S. 75 - BROOKLYN | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 120000 | 0
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | Scope | Complete | 7/20/2021 | 2/23/2022 | 3/2/2023 | 0 | 11742 | 11742
32 | K086 | P.S. 86 - BROOKLYN | SCA Emergency Response | EMERGENCY STABILIZATION & REPAIRS- FALLING MASONRY @ K086 | Construction | In-Progress | 9/5/2023 | EMER |  | EMER | 477080 | 0
32 | K086 | P.S. 86 - BROOKLYN | SCA IEH | PO18-TEST ALL FLOOR LAYERS FOR ACM APPROXIMATELY 30SQ FT OF LOOSE FLOOR TILES IN CAFETERIA NEED R/R | Construction | In-Progress | 1/9/2024 | IEH |  | IEH | 2081 | 1506
32 | K086 | P.S. 86 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 11/2/2023 | DOES | 5/10/2024 | DOES | 65832
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | FY25 RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K106 | P.S. 106 - BROOKLYN | Fast Track Projects | LSP DOMESTIC WATER HEATER | Construction | In-Progress | 11/11/2021 | FTK |  | FTK | 293531 | 183994
32 | K106 | P.S. 106 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/1/2022 | DOES |  | DOES | 60530 | 0
32 | K111 | I.S. 347 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K111 | I.S. 347 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K111 | I.S. 347 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K111 | I.S. 347 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SUPPLEMENTAL COOLING | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K111 | I.S. 347 - BROOKLYN | DIIT - RESOA | FY15 RESO A SECURITY CAMERA UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 210150 | 0
32 | K111 | I.S. 347 - BROOKLYN | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 100000 | 0
32 | K111 | I.S. 349 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 300000 | 0
32 | K111 | I.S. 349 - BROOKLYN | DOE - RESOA | FY23 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
32 | K111 | I.S. 347 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
32 | K111 | I.S. 347 - BROOKLYN | DOE - RESOA | FY25 RESO A SUPPLEMENTAL COOLING | Construction | PNS | PNS | PNS | PNS | DOER | 1000000 | 0
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | FY25 RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K116 | P.S. 116 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K116 | P.S. 116 - BROOKLYN | SCA IEH | PO18-ABATE AND COMPLETELY REMOVE BOILER #1 INSULATION ALL INSULATION IS ACM PARTS ARE OBSOLETE. ACM | Construction | Complete | 4/15/2024 | IEH | 9/30/2024 | IEH | 720 | 145
32 | K116 | P.S. 116 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR WATER DAMAGED CEILING LOCATED IN ROOM 109 | Construction | Complete | 5/7/2024 | IEH | 5/12/2024 | IEH | 21526 | 13101
32 | K123 | P.S. 123 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/20/2023 | DOER |  | DOER | 206078 | 0
32 | K123 | P.S. 123 - BROOKLYN | DOE - RESOA | FY24 RESO A LEARNING GARDEN | Construction | PNS | PNS | PNS | PNS | DOER | 350000 | 0
32 | K123 | P.S. 123 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
32 | K123 | P.S. 123 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 4/8/2022 | DOES |  | DOES | 64265 | 0
32 | K123 | P.S. 123 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 4/22/2024 | DOES | 4/26/2024 | DOES | 65832 | 11572
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PA SYSTEM UPGRADE | Scope | Complete | 1/24/2024 | 4/23/2024 | 6/6/2024 | 0 | 2357 | 2357
32 | K145 | P.S. 145 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR COLLAPSED WALL IN CLASSROOM 401. WALL COLLAPSED EXPOSING BRICK WALL, AND CRACK | Construction | Complete | 7/18/2024 | IEH | 8/11/2024 | IEH | 89094 | 2197
32 | K145 | P.S. 145 - BROOKLYN | SCA IEH | PO18-ABATE PIPE INSULATION IN THE SPRINKLER ROOM PIPES HAVE BEEN MAKED | Construction | In-Progress | 8/30/2024 | IEH |  | IEH | 19182 | 399
32 | K145 | P.S. 145 - BROOKLYN | SCA IEH | PO18-ABATE AND REPLACE FLOORING ON ALL THE REQUESTED DAMAGED LOCATION REPORT ATTACHED WITHIN THE EMA | Construction | Complete | 9/16/2024 | IEH | 9/30/2024 | IEH | 0 | 0
32 | K145 | P.S. 145 - BROOKLYN | DIIT - RESOA | FY21 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 3/14/2021 | DIIR | 6/3/2024 | DIIR | 100000
32 | K145 | P.S. 145 - BROOKLYN | DOE - RESOA | FY25 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
32 | K145 | P.S. 145 - BROOKLYN | DOE - RESOA | FY25 RESO A WATER FOUNTAIN UPGRADES | Construction | PNS | PNS | PNS | PNS | DOER | 50000 | 0
32 | K145 | P.S. 145 - BROOKLYN | DOE - Skilled Trades | ACE BOILER CONTROLS UPGRADE | Construction | In-Progress | 1/21/2022 | DOES |  | DOES | 68837 | 0
32 | K151 | P.S. 151 - BROOKLYN | SCA IEH | PO18-REPLACE DAMAGED GLASS IN STAIRCASE B&C AND F&G. | Construction | Complete | 6/27/2024 | IEH | 6/27/2024 | IEH | 30198 | 628
32 | K151 | P.S. 151 - BROOKLYN | SCA IEH | PO18-ABATE AND REPAIR CEILING PLASTER AND PIPE INSULATION ROOMS #103, 104, 107, 110, 202, 205, 206/2 | Construction | Complete | 7/24/2024 | IEH | 9/12/2024 | IEH | 37314 | 1123
32 | K162 | I.S. 162 - BROOKLYN | SCA IEH | PO18-ROOM 407A, ABATE FLOOR TILES | Construction | Complete | 7/1/2024 | IEH | 9/12/2024 | IEH | 937 | 362
32 | K162 | I.S. 162 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | Complete | 5/24/2024 | DIIR | 8/2/2024 | DIIR | 100000
32 | K162 | I.S. 162 - BROOKLYN | DOE - RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | In-Progress | 9/10/2021 | DOER |  | DOER | 1033705 | 0
32 | K162 | I.S. 162 - BROOKLYN | DOE - RESOA | FY22 RESO A BATHROOM UPGRADES | Construction | In-Progress | 11/11/2022 | DOER |  | DOER | 216296 | 0
32 | K162 | I.S. 162 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 11/30/2022 | DOES |  | DOES | 430227 | 0
32 | K162 | I.S. 162 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 5/5/2022 | DOES |  | DOES | 68769 | 0
32 | K162 | I.S. 162 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 3/1/2024 | DOES |  | DOES | 415936 | 0
32 | K274 | P.S. 274 - BROOKLYN | DOE - RESOA | FY19 RESO A HYDROPONIC LAB | Construction | In-Progress | 7/1/2019 | DOER |  | DOER | 290302 | 0
32 | K274 | P.S. 274 - BROOKLYN | DOE - RESOA | FY24 RESO A ROOM CONVERSION | Construction | In-Progress | 3/21/2024 | DOER |  | DOER | 250000 | 0
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | PNS | PNS | PNS | PNS | 0 | 0 | 0
32 | K291 | I.S. 291 - BROOKLYN | Fast Track Projects | IDA GYM FLOOR REPLACEMENT | Construction | In-Progress | 6/3/2022 | FTK |  | FTK | 710311 | 701512
32 | K291 | I.S. 291 - BROOKLYN | DIIT - RESOA | FY13 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 180000 | 0
32 | K291 | I.S. 291 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
32 | K291 | I.S. 291 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 5/22/2023 | DOES |  | DOES | 504187 | 0
32 | K296 | I.S. 562 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 110000 | 0
32 | K296 | K053 SPED - BROOKLYN | DOE - RESOA | FY19 RESO A ROOM CONVERSIONS/PARTITIONING | Construction | In-Progress | 7/20/2023 | DOER |  | DOER | 171594 | 0
32 | K296 | I.S. 562 - BROOKLYN | DOE - RESOA | FY22 RESO A ROOM CONVERSION | Construction | In-Progress | 7/3/2023 | DOER |  | DOER | 1668178 | 0
32 | K296 | I.S. 562 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/15/2023 | DOES |  | DOES | 475918 | 0
32 | K299 | P.S. 299 - BROOKLYN | DOE - RESOA | FY21 RESO A ROOM CONVERSION | Construction | PNS | PNS | PNS | PNS | DOER | 200000 | 0
32 | K299 | P.S. 299 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 4/18/2022 | DOES |  | DOES | 104245 | 0
32 | K376 | P.S. 376 - BROOKLYN | DIIT - RESOA | FY22 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 50000 | 0
32 | K376 | P.S. 376 - BROOKLYN | DIIT - RESOA | FY24 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 100000 | 0
32 | K376 | P.S. 376 - BROOKLYN | DOE - RESOA | FY24 RESO A LIBRARY UPGRADE | Construction | In-Progress | 5/13/2024 | DOER |  | DOER | 100000 | 0
32 | K376 | P.S. 376 - BROOKLYN | DOE - Skilled Trades | ADA SHELTER COMPLIANCE | Construction | In-Progress | 10/8/2019 | DOES |  | DOES | 85121 | 0
32 | K376 | P.S. 376 - BROOKLYN | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/21/2022 | DOES |  | DOES | 117805 | 0
32 | K376 | P.S. 376 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | Complete | 1/8/2024 | DOES | 5/3/2024 | DOES | 50832 | 189
32 | K377 | P.S. 377 - BROOKLYN | DOE - Skilled Trades | SCHOOL ENTRY LOCKING AND EMERGENCY NOTIFICATION SOLUTION | Construction | In-Progress | 5/22/2024 | DOES |  | DOES | 65832 | 0
32 | K383 | I.S. 383 - BROOKLYN | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 8/17/2022 | DOES |  | DOES | 1017585 | 0
32 | K383 | I.S. 383 - BROOKLYN | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 1/26/2024 | DOES |  | DOES | 705124 | 0
32 | K384 | P.S. 384 - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 10/29/2021 | DOES |  | DOES | 59415 | 345652
32 | K384 | P.S. 384 - BROOKLYN | DOE - Skilled Trades | BATHROOM UPGRADES | Construction | In-Progress | 7/5/2022 | DOES |  | DOES | 272254 | 0
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | Fast Track Projects | RNWL SBHC | Construction | In-Progress | 7/2/2016 | FTK |  | FTK | 1586499 | 1584473
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | DIIT - RESOA | FY20 RESO A TECHNOLOGY UPGRADE | Purch & Install | In-Progress | 3/14/2021 | DIIR |  | DIIR | 80000 | 0
32 | K480 | THE ACADEMY OF URBAN PLANNING AND ENGINEERING - K | DOE - RESOA | FY22 RESO A BATHROOM UPGRADE | Construction | In-Progress | 6/30/2023 | DOER |  | DOER | 178767 | 0
32 | K480 | THE ACADEMY OF URBAN PLANNING AND ENGINEERING - K | DOE - RESOA | FY24 RESO A AUDITORIUM UPGRADE | Construction | PNS | PNS | PNS | PNS | DOER | 250000 | 0
32 | K480 | THE BROOKLYN SCHOOL FOR SOCIAL JUSTICE - K | DOE - Skilled Trades | EMERGENCY POWER FOR QUICK CONNECT PROGRAM | Construction | In-Progress | 3/9/2023 | DOES |  | DOES | 1249692 | 0
32 | K554 | I.S. 554 - BROOKLYN | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 6/17/2024 | IEH | 7/17/2024 | IEH | 11904 | 6529
32 | K677 | SUCCESS ACADEMY CHARTER SCHOOL - BUSHWICK | SCA IEH | PO18-SAFE ACCESS ABATEMENT | Construction | Complete | 8/5/2024 | IEH | 8/9/2024 | IEH | 15523 | 604
32 | K799 | ALC - BROOKLYN CHOICES | SCA Emergency Response | EMERGENCY STABILZATION | Construction | In-Progress | 2/2/2015 | EMER |  | EMER | 288080 | 288080
32 | K799 | ALC - BROOKLYN CHOICES | DIIT - RESOA | FY25 RESO A TECHNOLOGY UPGRADE | Purch & Install | PNS | PNS | PNS | PNS | DIIR | 90000 | 0
32 | K865 | BUSHWICK LEADERS - K | DOE - RESOA | FY19 RESO A GYMNASIUM UPGRADE | Construction | In-Progress | 8/26/2021 | DOER |  | DOER | 209486 | 0
32 | K865 | BUSHWICK LEADERS - K | DOE - Skilled Trades | DEP/DOE WATER CONSERVATION FIXTURE RETROFIT PROGRAM | Construction | In-Progress | 1/17/2022 | DOES |  | DOES | 53562 | 0
32 | K865 | DOE ADMINISTRATIVE OFFICE - BROOKLYN | DOE - Skilled Trades | ELEVATOR MODERNIZATION | Construction | In-Progress | 12/10/2022 | DOES |  | DOES | 1195241 | 867001
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | DOE - RESOA | FY18 RESO A HYDROPONICS LAB | Construction | In-Progress | 5/17/2019 | DOER |  | DOER | 133435 | 0
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | DOE - Skilled Trades | CAFETERIA ENHANCEMENT EXPERIENCE | Construction | In-Progress | 6/16/2023 | DOES |  | DOES | 266576 | 0