## Sheet1
Distrito Geografico | ID Edificio | Nombre Escuela | Tipo de Proyecto | Descripción del Proyecto | Fase del Proyecto | Estado del Proyecto | Fecha de Inicio | Fecha de Fin Proyectada | Fecha de Fin Real | Presupuesto del Proyecto | Presupuesto Final Estimado | Cantidad Real Gastada
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 4/13/2021 | 9/13/2021 | 7/1/2021 | 68660 | 70899 | 70899
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/6/2021 | 12/7/2021 | 11/29/2021 | 343300 | 362786 | 298189
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/22/2023 | 10/23/2023 | 7/6/2023 | 4240 | 1518 | 1518
1 | M019 | P.S. 19 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/6/2023 | 1/3/2024 | 12/13/2023 | 19080 | 6074 | 6074
1 | M020 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 5/26/2021 | 10/12/2021 | 1/21/2022 | 124674 | 160738 | 160738
1 | M020 | P.S. 20 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / SECURITY LIGHTING / EXTERIOR MASONRY / PARAPETS | Design | Complete | 1/21/2022 | 6/22/2022 | 5/10/2022 | 613841 | 521613 | 513485
1 | M022 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 4/22/2021 | 9/7/2021 | 12/21/2021 | 195550 | 193921 | 191326
1 | M022 | NEW EXPLORATIONS - M | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/22/2021 | 6/10/2022 | 9/16/2022 | 977750 | 605106 | 444554
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | Scope | Complete | 10/23/2018 | 3/13/2019 | 1/24/2020 | 118770 | 254063 | 253255
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | Design | Complete | 1/24/2020 | 6/24/2020 | 5/5/2021 | 586080 | 582536 | 525486
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | Construction | Complete | 8/13/2021 | 8/11/2024 | 8/14/2024 | 12514695 | 12763307 | 11212816
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | ROOFS / EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS / PARAPETS | CM,F&E | Complete | 8/13/2021 | 8/11/2024 | 8/14/2024 | 889665 | 1281548 | 1217784
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/25/2020 | 10/26/2020 | 7/21/2020 | 3482 | 4450 | 4450
1 | M025 | LOWER EAST SIDE PREP HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/21/2020 | 1/15/2021 | 3/30/2021 | 15667 | 17800 | 17800
1 | M034 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | Scope | Complete | 10/19/2018 | 12/30/2019 | 3/31/2020 | 294023 | 340316 | 330125
1 | M034 | P.S. 34 - MANHATTAN | SCA CIP | HEATING PLANT / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEM / CLIMATE CONTROL / ELECTRICAL SYSTEMS / WINDOWS / ROOFS / SCHOOLYARD RESURFACING | Design | Complete | 12/7/2020 | 5/10/2021 | 5/18/2021 | 1450039 | 1134398 | 1038316
1 | M056 | J.H.S. 292 - MANHATTAN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 4/30/2021 | 7/30/2021 | 7/22/2021 | 27380 | 42814 | 42814
1 | M056 | J.H.S. 292 - MANHATTAN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 8/2/2021 | 2/7/2022 | 2/1/2022 | 136900 | 171027 | 154403
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 5/16/2022 | 9/16/2022 | 8/2/2022 | 53927 | 78550 | 78550
1 | M060 | EAST SIDE COMMUNITY SCHOOL | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 8/8/2022 | 2/13/2023 | 5/8/2023 | 259893 | 201922 | 184167
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | Scope | Complete | 4/9/2019 | 8/22/2019 | 9/20/2019 | 22622 | 11835 | 11835
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | WATER INFILTRATION IN ELECTRICAL ROOM | Design | Complete | 10/23/2019 | 3/27/2020 | 6/8/2020 | 113110 | 118178 | 114874
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/7/2022 | 11/4/2022 | 7/27/2022 | 3838 | 2363 | 2363
1 | M061 | P.S. 361 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/27/2022 | 1/25/2023 | 9/21/2022 | 17271 | 9450 | 9450
1 | M064 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/20/2019 | 11/5/2019 | 12/23/2019 | 111561 | 221145 | 217082
1 | M064 | I.S. 839 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/8/2020 | 6/9/2020 | 6/30/2020 | 551747 | 733548 | 663725
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 2/11/2020 | 6/25/2020 | 1/2/2024 | 74829 | 139951 | 78818
1 | M064 | P.S. 64 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 12/4/2020 | 5/24/2021 | 1/2/2024 | 2354 | 22197 | 15280
1 | M097 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 1/7/2021 | 5/7/2021 | 6/15/2021 | 39541 | 50839 | 50800
1 | M097 | BARD COLLEGE HS - MANHATTAN | SCA CIP | WASTE SYSTEM / PARAPETS / EXTERIOR MASONRY | Design | Complete | 7/15/2021 | 12/16/2021 | 4/21/2022 | 186049 | 145846 | 106797
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP | FACADE REMEDIATION @M110 / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 8/4/2021 | 12/21/2021 | 2/2/2022 | 73176 | 195932 | 177643
1 | M110 | P.S. 110 - MANHATTAN | SCA CIP | FACADE REMEDIATION @M110 / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 6/1/2022 | 11/22/2022 | 5/12/2023 | 355589 | 310017 | 290581
1 | M134 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 10/23/2018 | 3/13/2019 | 1/18/2019 | 371656 | 171214 | 171214
1 | M134 | P.S. 134 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/22/2019 | 6/21/2019 | 5/17/2019 | 1486620 | 826156 | 771304
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Scope | Complete | 1/24/2018 | 1/20/2021 | 5/19/2021 | 15710 | 29475 | 29475
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | FY18 RESO A ELECTRICAL SYSTEMS / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Design | Complete | 7/7/2021 | 12/10/2021 | 3/3/2022 | 62520 | 98375 | 74465
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/11/2022 | 11/8/2022 | 7/28/2022 | 5326 | 2660 | 2660
1 | M137 | P.S. 184 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/28/2022 | 1/26/2023 | 9/21/2022 | 23966 | 10640 | 10640
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/24/2018 | 3/14/2019 | 1/18/2019 | 504775 | 543899 | 505763
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ANSUL SYSTEMS/FIRE SUPPRESSION / ELECTRICAL UPGRADE / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / HEATING PLANT UPGRADE / FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 1/22/2019 | 6/21/2019 | 9/16/2022 | 2518835 | 2354532 | 1756812
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/6/2022 | 11/3/2022 | 7/22/2022 | 4336 | 4223 | 4223
1 | M140 | P.S. 140 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/22/2022 | 1/20/2023 | 9/21/2022 | 19513 | 17729 | 17729
1 | M142 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/22/2020 | 11/19/2020 | 8/19/2020 | 86400 | 152029 | 152029
1 | M142 | P.S. 142 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/1/2020 | 6/15/2021 | 4/6/2021 | 432000 | 390753 | 347885
1 | M446 | UNIVERSITY NEIGHBORHOOD HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / PARAPETS / ROOFS | Scope | Complete | 6/22/2023 | 11/7/2023 | 3/26/2024 | 154686 | 233284 | 88837
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | Scope | Complete | 10/12/2018 | 3/4/2019 | 1/3/2019 | 373649 | 159135 | 159120
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOF | Design | Complete | 1/3/2019 | 6/5/2019 | 5/14/2019 | 1494600 | 1080167 | 939756
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/22/2024 | 5/20/2024 | 1/22/2024 | 5982 | 1725 | 1725
2 | M001 | P.S. 1 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2024 | 9/16/2024 | 8/13/2024 | 26919 | 6899 | 6899
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | Scope | Complete | 2/14/2019 | 6/17/2019 | 10/29/2019 | 113406 | 3077 | 3077
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | WINDOWS / ROOFS / PARAPETS / SECURITY LIGHTING | Design | Complete | 11/25/2019 | 4/28/2020 | 3/22/2022 | 559432 | 344697 | 333251
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/26/2024 | 6/25/2024 | 3/20/2024 | 3740 | 945 | 945
2 | M002 | P.S. 2 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/20/2024 | 9/13/2024 | 8/13/2024 | 16830 | 3780 | 3780
2 | M003 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/26/2023 | 10/25/2023 | 7/6/2023 | 4065 | 1585 | 1585
2 | M003 | P.S. 3 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/6/2023 | 1/3/2024 | 10/18/2023 | 18290 | 6342 | 6342
2 | M006 | P.S. 6 - MANHATTAN | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 1/31/2022 | 3/28/2022 | 4/4/2022 | 60518 | 89611 | 80611
2 | M017 | P.P.A.S. - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/28/2024 | 7/29/2024 | 4/16/2024 | 5043 | 1294 | 1294
2 | M017 | P.P.A.S. - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/16/2024 | 10/10/2024 | 9/25/2024 | 22694 | 5176 | 5176
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | Scope | Complete | 2/28/2019 | 7/29/2019 | 10/3/2019 | 39007 | 69397 | 69397
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS PLAYGROUND SAFETY SURFACE | Design | Complete | 11/13/2019 | 4/16/2020 | 9/1/2021 | 192928 | 234471 | 226749
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/6/2022 | 10/4/2022 | 9/7/2022 | 6015 | 5355 | 5355
2 | M033 | P.S. 33 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/7/2022 | 3/8/2023 | 3/8/2023 | 27067 | 21421 | 21421
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 3/3/2021 | 7/16/2021 | 1/25/2022 | 319430 | 368295 | 365506
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 1/25/2022 | 6/24/2022 | 5/10/2022 | 1597150 | 1149263 | 974622
2 | M040 | I.S. 255 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Design | Complete | 6/15/2021 | 12/2/2021 | 1/12/2022 | 43862 | 72006 | 70456
2 | M040 | P.S. 40 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Design | Complete | 11/2/2022 | 3/2/2023 | 1/20/2023 | 56890 | 79380 | 70380
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/27/2019 | 11/13/2019 | 2/11/2020 | 172368 | 155663 | 153802
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2/11/2020 | 7/13/2020 | 5/14/2021 | 860032 | 584811 | 513457
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/27/2024 | 7/26/2024 | 4/16/2024 | 4394 | 1614 | 1614
2 | M041 | P.S. 41 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/16/2024 | 10/10/2024 | 9/25/2024 | 19773 | 6457 | 6457
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 7/17/2019 | 12/3/2019 | 1/23/2020 | 129854 | 175514 | 169963
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/23/2020 | 6/23/2020 | 6/30/2020 | 643030 | 611673 | 556378
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/3/2023 | 11/1/2023 | 7/12/2023 | 4335 | 1674 | 1674
2 | M042 | P.S. 42 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/12/2023 | 1/9/2024 | 10/18/2023 | 19510 | 6698 | 6698
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 12/18/2019 | 3/20/2020 | 3/16/2020 | 27730 | 54369 | 54369
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 4/20/2021 | 10/21/2021 | 8/3/2022 | 138650 | 355523 | 224041
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | Scope | Complete | 4/29/2022 | 9/14/2022 | 12/7/2022 | 247331 | 323214 | 323204
2 | M047 | J.H.S. 47 (SCH FOR THE DEAF) - M | SCA CIP | EXTERIOR MASONRY / RTU REPLACEMENT / WINDOWS / PARAPETS / ROOFS | Design | Complete | 12/22/2022 | 5/25/2023 | 4/28/2023 | 1236651 | 935117 | 761396
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 12/12/2023 | 4/29/2024 | 7/19/2024 | 54409 | 139006 | 65071
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/30/2020 | 10/29/2020 | 7/13/2020 | 2081 | 6193 | 6193
2 | M066 | P.S. 151 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/13/2020 | 1/7/2021 | 3/30/2021 | 9363 | 24772 | 24772
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | RESO A LOCKER ROOM UPGRADE | Design | Complete | 1/16/2024 | 5/30/2024 | 5/22/2024 | 195787 | 126845 | 119106
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Scope | Complete | 10/18/2023 | 1/22/2024 | 1/9/2024 | 5615 | 5615 | 130
2 | M070 | NYC LAB MIDDLE SCHOOL - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | Complete | 1/12/2024 | 5/15/2024 | 5/22/2024 | 521 | 521 | 521
2 | M089 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/20/2023 | 11/20/2023 | 8/10/2023 | 4160 | 4833 | 4833
2 | M089 | P.S. 89 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/10/2023 | 2/8/2024 | 12/13/2023 | 18720 | 19334 | 19334
2 | M104 | I.S. 104 - MANHATTAN | SCA CIP RESOA | FY 21 RESO A (MA) FITNESS ROOM / PATH OF TRAVEL RESO A FITNESS ROOM | Design | Complete | 11/4/2021 | 3/10/2022 | 4/14/2022 | 90524 | 94457 | 79543
2 | M111 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/10/2023 | 12/12/2023 | 8/22/2023 | 4480 | 3704 | 3704
2 | M111 | P.S. 111 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/22/2023 | 2/21/2024 | 12/13/2023 | 20160 | 14814 | 14814
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | FY16 RESO A GREEN ROOF | Design | Complete | 5/18/2016 | 10/19/2016 | 5/17/2019 | 39714 | 183531 | 183531
2 | M114 | I.S. 114 - MANHATTAN | SCA CIP RESOA | RESO A- DANCE STUDIO | Design | Complete | 8/9/2021 | 1/12/2022 | 8/8/2022 | 45750 | 111363 | 80911
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 5/15/2020 | 11/12/2020 | 10/23/2020 | 154300 | 247640 | 247640
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 10/29/2020 | 6/15/2021 | 7/1/2021 | 771500 | 449392 | 449392
2 | M124 | P.S. 124 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/7/2023 | 12/22/2023 | 12/26/2023 | 42000 | 53366 | 11831
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 10/23/2018 | 3/13/2019 | 1/10/2019 | 279097 | 290155 | 290155
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/16/2019 | 6/17/2019 | 5/29/2020 | 1385660 | 859901 | 842340
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/17/2023 | 7/18/2023 | 3/24/2023 | 5645 | 2617 | 2617
2 | M126 | P.S. 126 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/24/2023 | 9/19/2023 | 5/8/2023 | 25403 | 10465 | 10465
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/12/2024 | 10/11/2024 | 6/13/2024 | 3380 | 2286 | 2286
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP | ROOFS | Scope | Complete | 9/17/2024 | 9/17/2024 | 9/17/2024 | 3000 | 0 | 0
2 | M130 | P.S. 130 - MANHATTAN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/15/2022 | 1/3/2023 | 12/8/2022 | 36000 | 52960 | 51692
2 | M158 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Scope | Complete | 9/9/2020 | 1/20/2021 | 10/1/2021 | 30137 | 38340 | 38340
2 | M158 | P.S. 158 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Design | Complete | 10/13/2021 | 4/19/2022 | 7/12/2022 | 145516 | 225920 | 189181
2 | M167 | I.S. 167 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 1/8/2024 | 5/31/2024 | 8/20/2024 | 31610 | 51774 | 31855
2 | M169 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | Scope | Complete | 10/12/2018 | 6/12/2020 | 5/26/2020 | 61639 | 88445 | 88445
2 | M169 | M169 SPED - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / WINDOWS / ROOFS / PATH OF TRAVEL ROOF | Design | Complete | 5/26/2020 | 9/18/2020 | 12/30/2020 | 301587 | 179754 | 150125
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Design | Complete | 12/3/2018 | 4/29/2019 | 4/1/2019 | 36000 | 58475 | 49903
2 | M183 | P.S. 183 - MANHATTAN | SCA CIP RESOA | NYS IPDVS NEW INSTALLATION | Design | Complete | 5/26/2023 | 11/24/2023 | 8/30/2023 | 30000 | 2836 | 2836
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 12/2/2015 | 5/4/2018 | 2/21/2018 | 76099 | 83507 | 83507
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/28/2018 | 7/30/2018 | 5/4/2018 | 291517 | 386048 | 366697
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | Complete | 8/8/2022 | 10/5/2024 | 4/30/2024 | 4310303 | 4022455 | 3437934
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 8/8/2022 | 10/5/2024 | 4/30/2024 | 522514 | 533996 | 529604
2 | M190 | P.S. 290 - MANHATTAN | SCA CIP RESOA | RESO A ROOFTOP PLAYGROUND | Design | Complete | 2/6/2023 | 7/10/2023 | 12/26/2023 | 643687 | 234030 | 15990
2 | M198 | P.S. 77 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/14/2023 | 5/10/2024 | 3/5/2024 | 27000 | 19762 | 19762
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 3/12/2018 | 7/25/2018 | 12/16/2019 | 28750 | 95254 | 93861
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 1/8/2020 | 6/9/2020 | 6/26/2020 | 143751 | 187935 | 120611
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/10/2024 | 10/9/2024 | 6/14/2024 | 3954 | 911 | 911
2 | M234 | P.S. 234 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 7/1/2024 | 9/30/2024 | 8/21/2024 | 30637 | 756 | 756
2 | M267 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/21/2022 | 7/19/2022 | 4/12/2022 | 3341 | 5686 | 5686
2 | M267 | P.S. 267 - MANHATTAN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/12/2022 | 10/5/2022 | 7/19/2022 | 15033 | 22743 | 22743
2 | M271 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/23/2023 | 7/24/2023 | 3/28/2023 | 4130 | 2003 | 2003
2 | M271 | P.S./I.S. 217 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/28/2023 | 9/21/2023 | 5/5/2023 | 18586 | 8012 | 8012
2 | M276 | P.S./I.S. 276 - MANHATTAN | SCA CIP | IDA INTERIOR SPACES / IDA FLOOD ELIMINATION | Scope | Complete | 1/19/2022 | 5/19/2022 | 4/6/2023 | 18284 | 40499 | 39644
2 | M276 | P.S./I.S. 276 - MANHATTAN | SCA CIP | IDA INTERIOR SPACES / IDA FLOOD ELIMINATION | Design | Complete | 4/24/2023 | 10/24/2023 | 2/21/2024 | 82275 | 61758 | 55851
2 | M282 | I.S. 896 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 9/28/2023 | 2/5/2024 | 7/22/2024 | 30000 | 43563 | 41415
2 | M338 | P.S. 51 - MANHATTAN | SCA CIP RESOA | FY20 RESO A ACCESSIBILITY | Design | Complete | 10/1/2021 | 3/24/2022 | 7/15/2022 | 15052 | 29640 | 29640
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | DEFECTIVE POOL FOUNDATION WALLS | Scope | Complete | 6/17/2015 | 11/17/2015 | 6/22/2016 | 176680 | 154529 | 154529
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | DEFECTIVE POOL FOUNDATION WALLS | Design | Complete | 4/16/2019 | 10/18/2019 | 6/30/2020 | 883400 | 521017 | 480422
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Scope | Complete | 8/1/2018 | 12/18/2018 | 11/21/2018 | 98775 | 132497 | 132497
2 | M440 | JAMES BALDWIN SCHOOL - MANHATTAN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Design | Complete | 2/6/2019 | 7/9/2019 | 9/18/2019 | 492101 | 415286 | 345032
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/16/2020 | 10/15/2020 | 6/22/2020 | 3418 | 6911 | 6911
2 | M440 | HUDSON HS OF LEARNING TECH - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/22/2020 | 12/17/2020 | 12/23/2020 | 15380 | 27643 | 27643
2 | M445 | LOWER MANHATTAN ARTS - MANHATTAN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 7/5/2022 | 11/2/2022 | 11/2/2022 | 125400 | 121298 | 92493
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 8/20/2020 | 12/18/2020 | 6/18/2021 | 198200 | 239364 | 190528
2 | M460 | THE HIGH SCHOOL FOR LANGUAGE AND DIPLOMACY | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 6/30/2021 | 11/30/2021 | 12/20/2021 | 991001 | 896859 | 616499
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 5/21/2020 | 1/29/2021 | 10/27/2020 | 37305 | 99671 | 99671
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 11/24/2020 | 7/28/2021 | 12/13/2021 | 180483 | 354828 | 354828
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 1/27/2020 | 12/13/2021 | 11/9/2021 | 277969 | 185667 | 185667
2 | M475 | HS FOR HEALTH PROF & HUMAN SERV-M | SCA CIP | AUDITORIUM UPGRADE / ROOFS / PATH OF TRAVEL AUDITORIUM UPGRADE / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/9/2021 | 1/20/2022 | 5/12/2023 | 1388986 | 712795 | 596637
2 | M477 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | Scope | Complete | 6/28/2018 | 8/2/2019 | 3/2/2021 | 111561 | 296841 | 296841
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | ROOM CONVERSION | Scope | Complete | 4/11/2022 | 8/10/2022 | 4/11/2022 | 10612 | 317 | 317
2 | M477 | STUYVESANT HS - MANHATTAN | SCA CIP | COOLING TOWER REPLACEMENT / VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / BMS UPGRADE | Design | Complete | 3/2/2021 | 8/31/2021 | 6/8/2021 | 557801 | 933124 | 627031
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | Scope | Complete | 3/5/2021 | 7/20/2021 | 1/25/2022 | 198437 | 442128 | 421448
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS / WINDOWS | Design | Complete | 1/25/2022 | 6/24/2022 | 5/12/2022 | 982629 | 844302 | 841135
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | Scope | Complete | 9/11/2020 | 1/20/2021 | 12/15/2021 | 32665 | 47985 | 47985
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID BMS UPGRADE | Design | Complete | 12/15/2021 | 5/18/2022 | 9/30/2022 | 159563 | 219339 | 183527
2 | M480 | P.S. 225 - MANHATTAN | SCA CIP RESOA | FY23 RESO A LOCKER ROOM UPGRADE / PATH OF TRAVEL RESO A LOCKER ROOM UPGRADE | Design | Complete | 6/15/2023 | 11/2/2023 | 1/24/2024 | 234785 | 93740 | 89548
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS / WINDOWS | Scope | Complete | 10/15/2018 | 3/5/2019 | 4/12/2019 | 90044 | 180570 | 180570
2 | M486 | J. K. ONASSIS HS FOR INT CAREERS-M | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS / WINDOWS | Design | Complete | 4/12/2019 | 9/12/2019 | 6/30/2020 | 437233 | 342685 | 324197
2 | M488 | P.S. 59 - MANHATTAN | SCA CIP RESOA | FY20 RESO A GREENROOF | Design | Complete | 3/11/2020 | 8/10/2020 | 8/23/2022 | 194775 | 127213 | 111464
2 | M493 | P.S. @ 2 HUDSON SQUARE - MANHATTAN | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/19/2018 | 10/9/2018 | 1/25/2021 | 661838 | 836785 | 834689
2 | M493 | P.S. @ 2 HUDSON SQUARE - MANHATTAN | SCA Capacity | NEW SCHOOL | Design | Complete | 1/26/2021 | 4/10/2019 | 4/4/2023 | 2647352 | 1457207 | 1366481
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | Scope | Complete | 11/18/2020 | 2/16/2021 | 5/7/2021 | 71190 | 119477 | 119477
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | VENTILATION @ M520 / AUDITORIUM CEILING REPLACEMENT | Design | Complete | 5/18/2021 | 10/19/2021 | 12/17/2021 | 355950 | 354107 | 317163
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | GENERATOR REPLACEMENT / NEW GAS METER ROOM | Scope | Complete | 3/5/2021 | 7/6/2021 | 3/5/2021 | 18902 | 2734 | 2734
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | GENERATOR REPLACEMENT / NEW GAS METER ROOM | Design | Complete | 3/5/2021 | 8/4/2021 | 2/23/2023 | 85062 | 10932 | 10932
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | Scope | Complete | 7/6/2021 | 11/19/2021 | 10/25/2021 | 151512 | 92010 | 92010
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | ROOFS / WINDOWS / DOMESTIC PIPING | Design | Complete | 11/24/2021 | 4/28/2022 | 5/11/2022 | 754168 | 431668 | 364624
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | Scope | Complete | 3/9/2022 | 5/13/2022 | 9/12/2022 | 20950 | 7327 | 7327
2 | M520 | BERGTRAUM HS - MANHATTAN | SCA CIP | CAFETERIA UPGRADE | Design | Complete | 9/13/2022 | 1/13/2023 | 1/27/2023 | 104750 | 164762 | 132899
2 | M521 | BERGTRAUM HS - MANHATTAN | SCA CIP | ATHLETIC FIELD UPGRADE | Scope | Complete | 8/15/2019 | 2/3/2020 | 1/24/2020 | 83930 | 143676 | 143676
2 | M523 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | Scope | Complete | 11/1/2021 | 12/21/2021 | 1/31/2022 | 216951 | 326093 | 201529
2 | M523 | 3K CENTER @ 403 EAST 65 STREET - MANHATTAN | 3K | LEASE | Design | Complete | 2/1/2022 | 2/18/2022 | 4/5/2023 | 976282 | 683347 | 541090
2 | M524 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | Scope | Complete | 2/4/2022 | 3/4/2022 | 3/11/2022 | 268658 | 265086 | 247062
2 | M524 | 3K CENTER @ 1010 THIRD AVENUE - MANHATTAN | 3K | LEASE | Design | Complete | 3/14/2022 | 6/10/2022 | 2/6/2023 | 1208963 | 1269243 | 1043987
2 | M533 | HARBOR HIGH SCHOOL ATHLETIC COMPLEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Scope | Complete | 10/4/2022 | 2/1/2023 | 2/1/2023 | 2396800 | 1313333 | 1106310
2 | M533 | HARBOR HIGH SCHOOL ATHLETIC COMPLEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Design | Complete | 2/2/2023 | 10/4/2023 | 5/9/2024 | 10785600 | 4346491 | 4195522
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 11/10/2021 | 3/31/2022 | 1/25/2022 | 160567 | 133507 | 133507
2 | M535 | MANHATTAN BRIDGES - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 2/1/2022 | 7/1/2022 | 5/12/2022 | 793146 | 547862 | 517894
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | ROOM CONVERSION | Design | Complete | 4/11/2022 | 12/30/2022 | 3/7/2023 | 53059 | 1269 | 1269
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 10/2/2015 | 2/23/2016 | 4/25/2016 | 176283 | 197110 | 197110
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS | Design | Complete | 10/10/2018 | 3/15/2019 | 5/2/2019 | 865743 | 507479 | 487077
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | Scope | Complete | 11/23/2016 | 3/29/2017 | 4/20/2017 | 258990 | 138919 | 138919
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | EMERGENCY GENERATOR / LOW-VOLTAGE ELECTRICAL SYSTEM / FIRE SYSTEM SPRINKLERS | Design | Complete | 10/10/2018 | 3/15/2019 | 5/10/2019 | 1035960 | 812704 | 676177
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | Scope | Complete | 9/11/2019 | 1/13/2020 | 12/18/2019 | 8140 | 11138 | 11138
2 | M620 | MURRAY HILL ACADEMY HS - M | SCA CIP | CHARTER MATCH INTERIOR SPACES | Design | Complete | 1/8/2020 | 6/15/2020 | 6/30/2020 | 36630 | 40339 | 36594
2 | M634 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Scope | Complete | 9/16/2014 | 10/31/2014 | 10/27/2014 | 716528 | 902217 | 895328
2 | M634 | NEW YORK HARBOR SCHOOL ANNEX - MANHATTAN | SCA Lease Site Improvement | LEASE | Design | Complete | 10/28/2014 | 4/15/2015 | 4/19/2019 | 3224378 | 3581095 | 3250771
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | Scope | Complete | 6/19/2019 | 11/4/2019 | 1/30/2020 | 266212 | 259278 | 257923
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / AUDITORIUM DUCTWORK / AUDITORIUM UPGRADE / PARAPETS / PATH OF TRAVEL AUDITORIUM UPGRADE / ROOFS | Design | Complete | 2/5/2020 | 7/7/2020 | 10/28/2021 | 1321071 | 909569 | 651083
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/17/2023 | 7/18/2023 | 3/21/2023 | 4200 | 2783 | 2783
2 | M641 | CITY-AS-SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/4/2023 | 18900 | 11134 | 11134
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | Scope | Complete | 5/18/2021 | 8/17/2021 | 6/15/2022 | 75078 | 92585 | 92585
2 | M645 | THE HIGH SCHOOL FOR CLIMATE JUSTICE | SCA CIP | FIRE ALARM SYSTEM / VENTILATION | Design | Complete | 6/16/2022 | 12/20/2022 | 5/5/2023 | 375390 | 367778 | 298012
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 2/24/2021 | 7/9/2021 | 12/7/2021 | 38648 | 135138 | 127579
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Design | Complete | 12/15/2021 | 5/18/2022 | 5/10/2022 | 180499 | 136798 | 111323
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/2/2022 | 1/6/2023 | 10/28/2022 | 6200 | 11767 | 11767
2 | M660 | SCHOOL OF THE FUTURE - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/28/2022 | 4/27/2023 | 3/8/2023 | 27900 | 47071 | 47071
2 | M661 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | Scope | Complete | 3/7/2019 | 7/8/2020 | 6/22/2020 | 61612 | 162213 | 151739
2 | M661 | MNHT COMPR. NIGHT & DAY HS - M | SCA CIP | FACADE REMEDIATION / WINDOWS / PARAPETS / FLOOD ELIMINATION / PATH OF TRAVEL FLOOD ELIMINATION | Design | Complete | 6/22/2020 | 8/3/2020 | 6/30/2020 | 288665 | 254059 | 232118
2 | M824 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | Scope | Complete | 5/20/2019 | 9/23/2019 | 7/18/2019 | 140676 | 220325 | 220325
2 | M824 | MILLENNIUM HS - MANHATTAN | SCA CIP | UPE - INTERIOR CONVERSION / IPDVS CAMERA INSTALLATION | Design | Complete | 7/24/2019 | 12/26/2019 | 12/5/2019 | 696032 | 1264577 | 967967
2 | M833 | HS FOR ECONOMICS & FINANCE - M | SCA CIP | ABSORBER REPLACEMENT | Scope | Complete | 8/12/2019 | 12/13/2019 | 3/30/2020 | 43701 | 48744 | 48744
2 | M833 | HS FOR ECONOMICS & FINANCE - M | SCA CIP | ABSORBER REPLACEMENT | Design | Complete | 3/31/2020 | 7/17/2020 | 6/19/2020 | 218503 | 200082 | 176926
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | Scope | Complete | 1/30/2019 | 6/14/2019 | 1/10/2022 | 25250 | 52209 | 40697
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | ROOF | Design | Complete | 1/13/2022 | 6/15/2022 | 4/22/2022 | 126250 | 327056 | 170965
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | HEATING PLANT UPGRADE | Scope | Complete | 6/24/2021 | 11/26/2021 | 1/19/2022 | 34972 | 60798 | 60798
2 | M834 | HS FOR ENVIRONMENTAL STUDIES - M | SCA CIP | HEATING PLANT UPGRADE | Design | Complete | 1/20/2022 | 6/21/2022 | 10/27/2022 | 174858 | 193384 | 169529
2 | M844 | M721 SPED - MANHATTAN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 12/12/2023 | 4/29/2024 | 7/9/2024 | 45876 | 58647 | 36183
2 | M871 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP | STRUCTURAL ISSUES | Scope | Complete | 2/28/2019 | 7/15/2019 | 9/17/2019 | 61083 | 77115 | 76275
2 | M871 | NEW YORK HARBOR SCHOOL - MANHATTAN | SCA CIP | STRUCTURAL ISSUES | Design | Complete | 10/23/2019 | 3/27/2020 | 4/8/2022 | 305417 | 329104 | 280163
2 | M873 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/24/2023 | 9/25/2023 | 6/15/2023 | 3327 | 359 | 359
2 | M873 | MANHATTAN VILLAGE ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/15/2023 | 12/13/2023 | 8/30/2023 | 14970 | 1437 | 1437
2 | M894 | HS FOR LEADERSHIP & PUBLIC SERV-M | SCA CIP | EMERGENCY GENERATOR REPLACEMENT | Scope | Complete | 7/17/2019 | 11/18/2019 | 3/11/2021 | 5770 | 11587 | 11587
2 | M920 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/13/2022 | 2/15/2023 | 10/28/2022 | 4780 | 6694 | 6694
2 | M920 | SATELLITE ACADEMY - M | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/28/2022 | 4/27/2023 | 3/8/2023 | 21510 | 26777 | 26777
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/26/2019 | 11/27/2019 | 9/17/2019 | 73499 | 83034 | 83034
3 | M009 | P.S. 9 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/26/2019 | 3/3/2020 | 2/11/2020 | 354838 | 361717 | 342794
3 | M044 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/14/2021 | 12/13/2021 | 9/16/2021 | 192000 | 171540 | 162266
3 | M044 | P.S. 334 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 10/20/2021 | 6/30/2022 | 4/25/2022 | 960000 | 347483 | 347483
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 10/5/2018 | 3/13/2019 | 12/3/2018 | 100920 | 89740 | 89740
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/12/2018 | 5/15/2019 | 5/13/2019 | 403680 | 412526 | 396123
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/5/2023 | 12/4/2023 | 10/12/2023 | 142980 | 138134 | 137523
3 | M054 | I.S. 54 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 10/18/2023 | 6/11/2024 | 4/10/2024 | 714900 | 264171 | 259655
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 10/30/2019 | 4/29/2020 | 2/13/2020 | 14136 | 28081 | 28081
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2/25/2020 | 8/18/2020 | 4/8/2020 | 63611 | 129418 | 119755
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | ROOFS / STAIRWELL WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 8/3/2023 | 12/20/2023 | 12/29/2023 | 136647 | 236064 | 202825
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | ROOFS / STAIRWELL WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 1/12/2024 | 6/13/2024 | 5/14/2024 | 672871 | 560119 | 560119
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/19/2023 | 11/17/2023 | 7/26/2023 | 4800 | 2655 | 2655
3 | M075 | P.S. 75 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/26/2023 | 1/24/2024 | 11/1/2023 | 21600 | 10624 | 10624
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 9/30/2022 | 2/21/2023 | 1/11/2023 | 142110 | 146477 | 120467
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/24/2023 | 6/26/2023 | 5/4/2023 | 710551 | 397823 | 397823
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/7/2023 | 7/6/2023 | 3/8/2023 | 4980 | 1868 | 1868
3 | M076 | P.S. 76 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/8/2023 | 8/31/2023 | 5/3/2023 | 22410 | 7474 | 7474
3 | M084 | P.S. 84 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUND UPGRADE | Design | Complete | 10/29/2018 | 3/19/2019 | 5/20/2019 | 51674 | 66374 | 64914
3 | M087 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | Scope | Complete | 6/19/2018 | 3/6/2019 | 11/30/2018 | 387378 | 225299 | 225299
3 | M087 | P.S. 87 - MANHATTAN | SCA CIP | WINDOWS / RPZ BACKFLOW PREVENTION DEVICES / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / PARAPETS / EXTERIOR MASONRY / EXTERIOR DOORS | Design | Complete | 12/5/2018 | 5/16/2019 | 4/18/2019 | 1528452 | 898292 | 866393
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | Scope | Complete | 8/4/2021 | 11/3/2021 | 12/8/2021 | 157660 | 186014 | 186014
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | CHILLER REPLACEMENT / FIRE ALARM REPLACEMENT / BMS UPGRADE | Design | Complete | 12/8/2021 | 6/13/2022 | 5/8/2023 | 788300 | 698937 | 448002
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 1/20/2023 | 6/6/2023 | 8/10/2023 | 29051 | 60363 | 60199
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 8/25/2023 | 1/31/2024 | 2/5/2024 | 145255 | 112205 | 59766
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/21/2023 | 11/6/2023 | 11/1/2023 | 70724 | 90211 | 88954
3 | M088 | WADLEIGH SECONDARY SCHOOL FOR THE PERFORMING & VISUAL ARTS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 11/8/2023 | 4/12/2024 | 4/22/2024 | 353618 | 236120 | 121115
3 | M113 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | Scope | Complete | 6/2/2021 | 10/18/2021 | 11/9/2021 | 68681 | 65581 | 65581
3 | M113 | P.S. 241 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS / PARAPETS | Design | Complete | 11/19/2021 | 4/25/2022 | 5/5/2022 | 335836 | 270171 | 249355
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 9/13/2019 | 3/16/2020 | 10/11/2019 | 26620 | 11580 | 11580
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 11/21/2019 | 5/19/2020 | 2/24/2020 | 119790 | 54816 | 54816
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 8/2/2023 | 12/1/2023 | 11/16/2023 | 10874 | 15970 | 15970
3 | M118 | P.S. 333 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 12/4/2023 | 5/6/2024 | 5/3/2024 | 48933 | 51695 | 40612
3 | M144 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 11/15/2018 | 4/4/2019 | 3/6/2019 | 49435 | 50347 | 50347
3 | M144 | P.S. 242 - MANHATTAN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 3/6/2019 | 8/5/2019 | 11/18/2021 | 197741 | 116925 | 110115
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/15/2023 | 11/1/2023 | 11/20/2023 | 111046 | 121472 | 121472
3 | M145 | WEST PREP ACADEMY - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2/28/2024 | 7/30/2024 | 5/3/2024 | 555232 | 381748 | 16757
3 | M149 | M811 SPED - MANHATTAN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/9/2023 | 12/8/2023 | 9/22/2023 | 104451 | 129366 | 129360
3 | M149 | M811 SPED - MANHATTAN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 10/25/2023 | 6/10/2024 | 4/3/2024 | 522249 | 311801 | 311801
3 | M163 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 6/21/2021 | 12/20/2021 | 10/14/2021 | 203462 | 182193 | 171298
3 | M163 | P.S. 163 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Design | Complete | 10/26/2021 | 6/30/2022 | 4/22/2022 | 1012328 | 386014 | 386014
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/15/2020 | 1/29/2021 | 10/19/2020 | 11777 | 34259 | 34259
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 10/27/2020 | 7/28/2021 | 7/28/2021 | 52996 | 137044 | 137044
3 | M165 | P.S. 165 - MANHATTAN | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 10/17/2023 | 3/6/2024 | 4/22/2024 | 82500 | 87854 | 83946
3 | M165 | I.S. 862 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 11/7/2023 | 3/14/2024 | 4/22/2024 | 9483 | 1171 | 1171
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 9/29/2017 | 2/20/2018 | 3/29/2018 | 195014 | 274856 | 274856
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | MASONRY / ROOFS / PARAPETS / WINDOWS | Design | Complete | 3/4/2019 | 8/1/2019 | 9/13/2019 | 973425 | 678209 | 591300
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | Scope | Complete | 3/1/2019 | 5/30/2019 | 12/13/2019 | 13750 | 70483 | 70483
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP | FIRE ALARM/MECHANICAL SYSTEMS | Design | Complete | 1/15/2020 | 7/17/2020 | 6/29/2020 | 68750 | 159947 | 97702
3 | M166 | P.S. 166 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADES | Design | Complete | 9/3/2019 | 11/5/2019 | 1/31/2020 | 2100 | 1819 | 1819
3 | M185 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 3/16/2022 | 7/14/2022 | 4/12/2022 | 5962 | 3389 | 3389
3 | M185 | P.S. 185 - MANHATTAN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 4/12/2022 | 10/5/2022 | 7/19/2022 | 26831 | 13554 | 13554
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 8/13/2021 | 1/3/2022 | 7/29/2022 | 124270 | 127442 | 127433
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 9/2/2022 | 2/24/2023 | 5/3/2023 | 621350 | 356366 | 292955
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | GYM CEILING RESTORATION- PERMANENT FIX | Scope | Complete | 5/17/2023 | 9/19/2023 | 8/23/2023 | 12427 | 12899 | 12899
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP | GYM CEILING RESTORATION- PERMANENT FIX | Design | Complete | 8/30/2023 | 1/19/2024 | 12/12/2023 | 55919 | 30720 | 26998
3 | M191 | P.S. 452 - MANHATTAN | SCA CIP RESOA | FY19 RESO A PLAYGROUND | Design | Complete | 8/10/2021 | 12/28/2021 | 1/18/2022 | 84113 | 78796 | 78796
3 | M199 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/18/2023 | 11/16/2023 | 7/26/2023 | 4400 | 2480 | 2480
3 | M199 | P.S. 199 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/26/2023 | 1/24/2024 | 11/1/2023 | 19800 | 9922 | 9922
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | Scope | Complete | 5/20/2013 | 9/20/2013 | 11/4/2013 | 49058 | 58427 | 48452
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP | HVAC (BMS) WORK / BACKFLOW PREVENTER & WATER METER | Design | Complete | 11/13/2013 | 5/15/2014 | 10/27/2014 | 189433 | 210497 | 207760
3 | M470 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | Scope | Complete | 2/14/2020 | 5/14/2020 | 9/23/2021 | 112212 | 104405 | 99517
3 | M470 | INNOVATION DIPLOMA PLUS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / VENTILATION / CLIMATE CONTROL | Design | Complete | 10/13/2021 | 4/19/2022 | 7/11/2022 | 561061 | 598978 | 346524
3 | M470 | THE URBAN ASSEMBLY SCHOOL FOR GREEN CAREERS | SCA CIP RESOA | FY17 RESO A ROOM CONVERSIONS/PARTITIONING | Design | Complete | 1/31/2018 | 6/18/2018 | 5/21/2018 | 41220 | 49682 | 39615
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | STAIRWELL WALLS | Scope | Complete | 5/25/2023 | 9/25/2023 | 9/21/2023 | 31036 | 36239 | 36239
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | STAIRWELL WALLS | Design | Complete | 10/2/2023 | 3/7/2024 | 5/10/2024 | 155181 | 114174 | 107469
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | Scope | Complete | 5/18/2020 | 1/29/2021 | 8/11/2020 | 29299 | 57257 | 57257
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FIRE SPRINKLER SYSTEM | Design | Complete | 8/19/2020 | 7/28/2021 | 7/28/2021 | 137177 | 219540 | 219540
3 | M485 | FIORELLO LAGUARDIA HS - MANHATTAN | SCA CIP RESOA | FY15 RESO A TECHNICAL THEATER SHOP | Design | Complete | 7/28/2016 | 3/28/2017 | 9/19/2018 | 285834 | 791554 | 673985
3 | M490 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | Scope | Complete | 5/4/2021 | 9/2/2021 | 11/16/2021 | 89950 | 69953 | 69953
3 | M490 | SCHOOL SAFETY - MANHATTAN | SCA CIP | CAFETERIA UPGRADE / AHU REPLACEMENT | Design | Complete | 12/1/2021 | 4/19/2022 | 10/7/2022 | 449750 | 397948 | 316568
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | Scope | Complete | 6/8/2022 | 9/7/2022 | 8/30/2022 | 14950 | 22221 | 22221
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | AUDITORIUM FIRE SAFETY SYSTEM UPGRADE | Design | Complete | 9/12/2022 | 3/20/2023 | 4/21/2023 | 74750 | 114575 | 12711
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | SWIMMING POOL | Scope | Complete | 6/14/2023 | 12/12/2023 | 12/6/2023 | 73230 | 75789 | 75789
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | SWIMMING POOL | Design | Complete | 12/26/2023 | 7/1/2024 | 8/13/2024 | 341739 | 238794 | 216085
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | PATH OF TRAVEL SWIMMING POOL | Scope | Complete | 12/5/2023 | 3/8/2024 | 3/15/2024 | 698 | 620 | 620
3 | M490 | HS FOR ARTS & TECHNOLOGY - M | SCA CIP | PATH OF TRAVEL SWIMMING POOL | Design | Complete | 4/3/2024 | 8/6/2024 | 8/13/2024 | 3139 | 2478 | 2478
3 | M514 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | Scope | Complete | 7/29/2021 | 9/16/2021 | 9/16/2021 | 331100 | 221828 | 221828
3 | M514 | 3K CENTER @ 1972 BROADWAY - MANHATTAN | 3K | LEASE | Design | Complete | 9/17/2021 | 12/20/2021 | 5/4/2022 | 1489950 | 700147 | 669519
3 | M837 | WEST END SECONDARY SCHOOL - MANHATTAN | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2/6/2023 | 8/2/2023 | 5/3/2023 | 20138 | 10409 | 10409
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | Scope | Complete | 4/27/2021 | 9/10/2021 | 9/8/2021 | 56358 | 68816 | 68816
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | ROOFS | Design | Complete | 9/9/2021 | 2/14/2022 | 5/6/2022 | 281792 | 251114 | 238910
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/9/2023 | 7/10/2023 | 3/21/2023 | 4500 | 1843 | 1843
3 | M841 | M811 SPED - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/3/2023 | 20250 | 7371 | 7371
4 | M007 | P.S. 7 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 12/14/2023 | 5/1/2024 | 5/10/2024 | 96443 | 90594 | 90531
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA ROOFS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES / NON-IDA PLAYGROUND UPGRADE | Scope | Complete | 1/21/2022 | 6/7/2022 | 12/21/2022 | 121867 | 246608 | 111046
4 | M013 | P.S. 497 - MANHATTAN | SCA CIP | PATH OF TRAVEL IDA FLOOD ELIMINATION | Scope | Complete | 1/25/2023 | 4/26/2023 | 3/27/2023 | 9146 | 0 | 0
4 | M045 | P.S. 37 - MANHATTAN | SCA CIP | SIDEWALK REPAIR / ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 1/17/2023 | 2/6/2024 | 12/5/2023 | 173001 | 254581 | 213934
4 | M045 | P.S. 37 - MANHATTAN | SCA CIP | SIDEWALK REPAIR / ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | Complete | 12/21/2023 | 5/23/2024 | 4/26/2024 | 865002 | 456687 | 374582
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 7/27/2018 | 12/13/2018 | 3/21/2019 | 124610 | 153729 | 146079
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/6/2019 | 4/27/2020 | 5/14/2021 | 623050 | 447813 | 426824
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/2/2022 | 9/30/2022 | 6/9/2022 | 3426 | 2739 | 2739
4 | M057 | P.S. 57 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/9/2022 | 12/6/2022 | 10/25/2022 | 15415 | 10955 | 10955
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY | Scope | Complete | 7/13/2023 | 11/29/2023 | 11/7/2023 | 34411 | 55331 | 46977
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY | Design | Complete | 11/17/2023 | 4/22/2024 | 4/24/2024 | 172055 | 127629 | 115147
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/14/2022 | 10/13/2022 | 6/28/2022 | 4689 | 4028 | 4028
4 | M072 | P.S. 72 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/28/2022 | 12/23/2022 | 10/25/2022 | 21099 | 16109 | 16109
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2/4/2020 | 7/6/2020 | 4/2/2020 | 59840 | 84240 | 84240
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 4/3/2020 | 9/2/2020 | 7/16/2020 | 299201 | 433268 | 365062
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 9/29/2023 | 2/20/2024 | 11/9/2023 | 173903 | 127284 | 112639
4 | M083 | P.S. 83 - MANHATTAN | SCA CIP | ROOFS / WINDOWS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/20/2023 | 5/22/2024 | 5/7/2024 | 869516 | 322595 | 322475
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2/18/2020 | 7/17/2020 | 4/27/2020 | 96801 | 170994 | 143896
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 4/28/2020 | 9/28/2020 | 10/29/2020 | 484003 | 597277 | 531987
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/11/2022 | 11/8/2022 | 8/18/2022 | 3986 | 3990 | 3990
4 | M096 | P.S. 96 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/18/2022 | 2/16/2023 | 10/25/2022 | 17936 | 15959 | 15959
4 | M099 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/21/2020 | 1/29/2021 | 9/24/2020 | 14880 | 29636 | 29636
4 | M099 | I.S. 224 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 10/14/2020 | 7/28/2021 | 8/18/2021 | 66960 | 110264 | 110264
4 | M101 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/26/2020 | 2/2/2021 | 10/15/2020 | 15640 | 21103 | 21103
4 | M101 | PS/IS 375 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 11/3/2020 | 7/28/2021 | 7/28/2021 | 70380 | 84453 | 84453
4 | M102 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/9/2021 | 9/9/2021 | 6/14/2021 | 75000 | 102475 | 102475
4 | M102 | P.S. 102 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 6/16/2021 | 11/17/2021 | 11/4/2021 | 375000 | 489081 | 427297
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/11/2023 | 5/11/2023 | 1/24/2023 | 2412 | 2397 | 2397
4 | M107 | THE HERITAGE SCHOOL - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/24/2023 | 7/20/2023 | 4/11/2023 | 10852 | 9588 | 9588
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/29/2023 | 10/30/2023 | 10/13/2023 | 8560 | 15547 | 15547
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/25/2023 | 3/26/2024 | 3/20/2024 | 38520 | 79541 | 40820
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 10/25/2018 | 11/1/2019 | 11/22/2019 | 128458 | 220500 | 217803
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 12/3/2019 | 5/5/2020 | 6/29/2020 | 634424 | 545173 | 512692
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / PARAPETS | Construction | Complete | 8/23/2021 | 10/1/2023 | 5/22/2024 | 13593915 | 12773505 | 11932260
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES / FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / PARAPETS | CM,F&E | Complete | 8/23/2021 | 10/1/2023 | 5/22/2024 | 958221 | 880628 | 871447
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/24/2023 | 5/23/2023 | 2/13/2023 | 4119 | 3376 | 3376
4 | M108 | P.S. 108 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/13/2023 | 8/9/2023 | 4/11/2023 | 18537 | 13506 | 13506
4 | M112 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 7/8/2019 | 11/21/2019 | 10/3/2019 | 173003 | 185064 | 129564
4 | M112 | P.S. 112 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 3/3/2021 | 8/17/2021 | 3/27/2023 | 865016 | 1040023 | 519299
4 | M121 | P.S. 38 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 5/4/2023 | 9/20/2023 | 11/7/2023 | 58698 | 97931 | 93881
4 | M121 | P.S. 38 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | Complete | 11/27/2023 | 4/29/2024 | 4/29/2024 | 285575 | 177823 | 157604
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 11/5/2019 | 5/5/2020 | 12/18/2019 | 16980 | 19525 | 19525
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 1/8/2020 | 7/2/2020 | 3/30/2020 | 76410 | 59341 | 59341
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 7/12/2022 | 11/28/2022 | 1/31/2023 | 211757 | 218337 | 217967
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 2/3/2023 | 7/7/2023 | 11/1/2023 | 1058784 | 571772 | 548330
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/8/2023 | 6/8/2023 | 3/2/2023 | 3369 | 3180 | 3180
4 | M146 | P.S. 146 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/2/2023 | 8/25/2023 | 4/11/2023 | 15160 | 12720 | 12720
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | Scope | Complete | 9/8/2021 | 1/27/2022 | 12/28/2021 | 136319 | 186538 | 185858
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION / FIRE ALARM SYSTEM | Design | Complete | 2/2/2022 | 7/20/2022 | 11/10/2022 | 681596 | 540488 | 479716
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | Scope | Complete | 12/22/2022 | 6/22/2023 | 12/13/2023 | 273180 | 308703 | 300356
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ROOFS / ELECTRICAL UPGRADE | Design | Complete | 12/20/2023 | 9/12/2024 | 5/8/2024 | 1365900 | 1099882 | 1057481
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/22/2023 | 9/21/2023 | 6/13/2023 | 3810 | 947 | 947
4 | M155 | P.S. 155 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/13/2023 | 12/11/2023 | 8/16/2023 | 17145 | 3788 | 3788
4 | M171 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2023 | 6/29/2023 | 3/9/2023 | 5310 | 1200 | 1200
4 | M171 | P.S. 171 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/9/2023 | 9/1/2023 | 5/3/2023 | 23895 | 4799 | 4799
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 7/8/2019 | 11/21/2019 | 10/3/2019 | 136097 | 217460 | 161921
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 3/3/2021 | 8/17/2021 | 3/27/2023 | 680484 | 798161 | 396480
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/3/2023 | 7/3/2023 | 3/9/2023 | 6490 | 2057 | 2057
4 | M206 | P.S. 206 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/9/2023 | 9/1/2023 | 5/3/2023 | 29205 | 8225 | 8225
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/20/2020 | 1/29/2021 | 8/7/2020 | 14940 | 40527 | 40527
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 8/19/2020 | 7/28/2021 | 12/15/2021 | 67230 | 153258 | 153258
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/2/2020 | 9/30/2020 | 6/26/2020 | 4926 | 3868 | 3868
4 | M435 | MANHTN CT FOR MATH & SCI. HS - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/26/2020 | 12/23/2020 | 12/22/2020 | 22168 | 15470 | 15470
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/18/2020 | 1/29/2021 | 9/3/2020 | 10937 | 27807 | 27807
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 10/14/2020 | 7/28/2021 | 7/28/2021 | 49214 | 111226 | 111226
4 | M495 | PARK EAST HS - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 12/18/2023 | 5/3/2024 | 6/26/2024 | 35050 | 66784 | 33792
4 | M495 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 208 | 208
4 | M495 | PARK EAST ALT H. S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 9/15/2003 | 10/30/2003 | 10/30/2003 | 2600 | 19743 | 17929
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | EXTERIOR MASONRY- PERMANENT FIX / PARAPETS | Scope | Complete | 5/31/2023 | 10/17/2023 | 10/25/2023 | 73701 | 83903 | 83903
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/22/2023 | 9/21/2023 | 6/6/2023 | 4010 | 611 | 611
4 | M646 | SCHOOL FOR COOPERATIVE TECHNICAL EDUCATION | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/6/2023 | 12/4/2023 | 8/16/2023 | 18045 | 2446 | 2446
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | ROOF LEAK / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 10/7/2022 | 1/11/2023 | 1/27/2023 | 218792 | 265146 | 257888
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | ROOF LEAK / EXTERIOR MASONRY / WINDOWS | Design | Complete | 2/9/2023 | 7/13/2023 | 11/29/2023 | 1093958 | 507907 | 485684
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/28/2021 | 11/29/2021 | 8/18/2021 | 6205 | 8646 | 8646
5 | M010 | FREDERICK DOUGLAS ACADEMY - M | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/18/2021 | 2/16/2022 | 12/22/2021 | 27922 | 34582 | 34582
5 | M030 | P.S. 30 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 5/10/2023 | 11/7/2023 | 10/25/2023 | 175442 | 162357 | 162357
5 | M030 | P.S. 30 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 11/9/2023 | 6/28/2024 | 5/15/2024 | 877211 | 666392 | 634450
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 3/3/2021 | 7/16/2021 | 9/13/2021 | 119974 | 167634 | 167634
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 9/28/2021 | 3/21/2022 | 1/10/2023 | 599870 | 469968 | 354780
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PAVED AREA-CONCRETE | Scope | Complete | 3/14/2023 | 6/12/2023 | 6/20/2023 | 22522 | 65524 | 65524
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PAVED AREA-CONCRETE | Design | Complete | 7/14/2023 | 11/30/2023 | 5/14/2024 | 112609 | 173291 | 90405
5 | M046 | P.S. 46 - MANHATTAN | SCA CIP | PERMANENT FIX- PIPING REPLACEMENT @ M046 / VENTILATION | Scope | Complete | 3/1/2024 | 6/17/2024 | 7/1/2024 | 51955 | 70119 | 5163
5 | M079 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/20/2021 | 9/20/2021 | 8/3/2021 | 83510 | 171703 | 116303
5 | M079 | M079 SPED - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 8/5/2021 | 1/10/2022 | 4/6/2022 | 417550 | 561718 | 500521
5 | M079 | M079 SPED - MANHATTAN | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Scope | Complete | 6/30/2021 | 9/29/2021 | 1/10/2022 | 17302 | 17302 | 17302
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/22/2020 | 2/1/2021 | 10/27/2020 | 13482 | 29380 | 29380
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 11/16/2020 | 7/28/2021 | 7/28/2021 | 60669 | 117613 | 117613
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/4/2023 | 88046 | 78431 | 78431
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | WINDOWS / EXTERIOR MASONRY | Design | Complete | 10/30/2023 | 6/28/2024 | 4/22/2024 | 431183 | 172559 | 172559
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/21/2022 | 11/21/2022 | 8/10/2022 | 5368 | 3664 | 3664
5 | M123 | P.S. 123 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/10/2022 | 2/8/2023 | 1/18/2023 | 24157 | 14656 | 14656
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2/12/2020 | 7/14/2020 | 4/11/2022 | 217910 | 245305 | 234280
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 4/11/2022 | 10/12/2022 | 3/24/2023 | 1089550 | 844608 | 549229
5 | M125 | I.S. 362 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/8/2024 | 11/5/2024 | 7/12/2024 | 3557 | 1229 | 1229
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Design | Complete | 8/28/2019 | 1/16/2020 | 6/15/2020 | 210000 | 201151 | 197604
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Construction | Complete | 4/20/2022 | 6/13/2023 | 6/13/2023 | 3080000 | 2486645 | 2167343
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | CM,F&E | Complete | 4/20/2022 | 6/13/2023 | 6/13/2023 | 210000 | 427839 | 424558
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | Complete | 7/14/2023 | 11/30/2023 | 2/13/2024 | 32379 | 33860 | 31991
5 | M125 | P.S. 125 - MANHATTAN | SCA CIP RESOA | PATH OF TRAVEL RESO A POOL UPGRADE | Scope | Complete | 3/1/2023 | 5/31/2023 | 10/6/2023 | 504 | 504 | 504
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 10/31/2018 | 3/21/2019 | 1/10/2019 | 297170 | 319630 | 319592
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/16/2019 | 6/17/2019 | 3/30/2021 | 1485850 | 987782 | 865879
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 4/24/2023 | 9/21/2023 | 12/14/2023 | 302501 | 213901 | 198364
5 | M129 | P.S. 129 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/26/2023 | 7/22/2024 | 5/15/2024 | 1512501 | 680747 | 549024
5 | M133 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/25/2021 | 11/23/2021 | 10/14/2021 | 119803 | 137290 | 137290
5 | M133 | P.S. 133 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/10/2021 | 6/30/2022 | 4/20/2022 | 599020 | 583876 | 567157
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 5/18/2020 | 1/29/2021 | 7/9/2020 | 9700 | 25020 | 25020
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 10/27/2020 | 7/28/2021 | 7/28/2021 | 43650 | 92780 | 92780
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Construction | Complete | 7/6/2022 | 7/5/2023 | 4/4/2024 | 562600 | 513460 | 470616
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | CM,F&E | Complete | 7/6/2022 | 7/5/2023 | 4/4/2024 | 104275 | 80959 | 79546
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/27/2020 | 9/24/2020 | 6/19/2020 | 3269 | 4468 | 4468
5 | M136 | MOTT HALL HS - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/19/2020 | 12/16/2020 | 12/16/2020 | 14710 | 17872 | 17872
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 9/13/2022 | 2/1/2023 | 12/19/2022 | 16053 | 11876 | 11876
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/21/2022 | 6/27/2023 | 7/11/2023 | 72239 | 47500 | 47500
5 | M154 | P.S. 154 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/25/2024 | 11/25/2024 | 7/29/2024 | 4105 | 780 | 780
5 | M161 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/6/2022 | 2/9/2023 | 10/20/2022 | 4900 | 3119 | 3119
5 | M161 | P.S. 161 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/20/2022 | 4/19/2023 | 1/18/2023 | 22050 | 12473 | 12473
5 | M175 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Scope | Complete | 3/2/2021 | 11/10/2021 | 11/5/2021 | 23406 | 27334 | 27334
5 | M175 | P.S. 175 HENRY H GARNET - M | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Design | Complete | 11/9/2021 | 4/5/2022 | 5/9/2022 | 116471 | 119350 | 96158
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 1/27/2023 | 5/26/2023 | 4/19/2023 | 8380 | 15725 | 15725
5 | M195 | NEW DESIGN MIDDLE SCHOOL - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 4/24/2023 | 10/24/2023 | 8/28/2023 | 37710 | 48107 | 41712
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 4/29/2021 | 9/14/2021 | 11/17/2021 | 210430 | 165632 | 147935
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 11/17/2021 | 5/6/2022 | 10/21/2022 | 1052150 | 438769 | 384969
5 | M197 | P.S. 197 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/26/2024 | 11/26/2024 | 7/29/2024 | 3126 | 602 | 602
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2/27/2023 | 7/27/2023 | 12/14/2023 | 658414 | 42093 | 29231
5 | M501 | THE URBAN ASSEMBLY SCHOOL FOR GLOBAL COMMERCE | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 1/10/2024 | 8/12/2024 | 8/23/2024 | 3072595 | 1015773 | 38003
5 | M911 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/18/2021 | 10/1/2021 | 1/14/2022 | 80048 | 192462 | 189360
5 | M911 | HARLEM RENAISSANCE HS - M | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/2/2022 | 7/5/2022 | 5/9/2022 | 395977 | 291360 | 253117
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/17/2022 | 2/17/2023 | 11/10/2022 | 3672 | 2315 | 2315
5 | M970 | THURGOOD MARSHALL ACADEMY - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 11/10/2022 | 5/10/2023 | 1/18/2023 | 16523 | 9259 | 9259
6 | M005 | P.S. 5 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/4/2024 | 8/5/2024 | 4/16/2024 | 4635 | 2671 | 2671
6 | M005 | P.S. 5 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/16/2024 | 10/10/2024 | 9/24/2024 | 20855 | 10684 | 10684
6 | M008 | P.S. 8 - MANHATTAN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 1/9/2024 | 5/23/2024 | 6/12/2024 | 18414 | 20374 | 2452
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP | WATER INFILTRATION INTO ELECTRCIAL EQUIPMENT / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 3/7/2023 | 7/21/2023 | 6/26/2023 | 20595 | 14061 | 14061
6 | M028 | P.S. 28 - MANHATTAN | SCA CIP | WATER INFILTRATION INTO ELECTRCIAL EQUIPMENT / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 7/17/2023 | 12/18/2023 | 12/15/2023 | 97886 | 82623 | 80579
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | CERTIFICATE OF OCCUPANCY | Scope | Complete | 9/7/2016 | 12/8/2016 | 10/27/2017 | 18951 | 131283 | 131283
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | CERTIFICATE OF OCCUPANCY | Design | Complete | 11/7/2017 | 5/14/2018 | 5/22/2018 | 75804 | 106822 | 105493
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 1/17/2023 | 5/16/2023 | 9/26/2023 | 457850 | 303629 | 31818
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | FIRE ALARM / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 10/4/2023 | 5/6/2024 | 5/8/2024 | 2289250 | 1277743 | 524211
6 | M048 | P.S. 48 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/17/2024 | 8/16/2024 | 4/30/2024 | 4907 | 3287 | 3287
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/29/2021 | 10/28/2021 | 7/27/2021 | 2596 | 12332 | 12332
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/27/2021 | 1/25/2022 | 12/15/2021 | 11682 | 49340 | 49340
6 | M052 | J.H.S. 52 - MANHATTAN | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 1/20/2023 | 6/6/2023 | 11/1/2023 | 236686 | 237547 | 165367
6 | M090 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 2/16/2023 | 6/16/2023 | 4/25/2023 | 12972 | 19332 | 19332
6 | M090 | I.S. 324 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 4/25/2023 | 10/25/2023 | 8/25/2023 | 58374 | 67674 | 51390
6 | M090 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | Scope | Complete | 8/20/2020 | 11/10/2022 | 9/9/2022 | 338022 | 430382 | 402001
6 | M090 | I.S. 319 - MANHATTAN | SCA CIP | COVID VENTILATION / LOW VOLTAGE ELECTRICAL SYSTEM / COVID CLIMATE CONTROL / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / REINFORCING SUPPORT ELEMENTS | Design | Complete | 9/27/2022 | 6/12/2023 | 5/5/2023 | 1684198 | 1124880 | 881852
6 | M093 | P.S. 210 - MANHATTAN | SCA CIP | ROOFS | Scope | Complete | 3/10/2021 | 7/23/2021 | 11/1/2021 | 22378 | 55044 | 52372
6 | M093 | P.S. 210 - MANHATTAN | SCA CIP | ROOFS | Design | Complete | 11/1/2021 | 4/6/2022 | 3/29/2022 | 111889 | 107390 | 74180
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/25/2023 | 4/25/2023 | 4/20/2023 | 21522 | 84678 | 84596
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Scope | Complete | 3/28/2023 | 6/28/2023 | 7/13/2023 | 3784 | 1335 | 1335
6 | M098 | P.S. 98 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/28/2024 | 10/29/2024 | 7/9/2024 | 3824 | 0 | 0
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL UPGRADE | Scope | Complete | 6/22/2021 | 11/5/2021 | 1/7/2022 | 93227 | 167844 | 151172
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL UPGRADE | Design | Complete | 1/12/2022 | 6/14/2022 | 5/11/2022 | 466141 | 340471 | 313762
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 8/18/2020 | 1/20/2021 | 12/16/2021 | 71574 | 88916 | 88916
6 | M115 | P.S. 115 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/16/2021 | 6/21/2022 | 8/15/2022 | 357872 | 267873 | 238537
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 12/15/2020 | 4/5/2021 | 11/16/2021 | 120420 | 129719 | 129719
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | COVID VENTILATION / COVID ELECTRICAL SYSTEM UPGRADE / COVID FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 11/29/2021 | 5/23/2022 | 8/30/2022 | 595229 | 426281 | 320906
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/3/2024 | 11/1/2024 | 7/9/2024 | 3589 | 28 | 28
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 4/6/2015 | 2/1/2018 | 12/18/2017 | 157058 | 158822 | 158822
6 | M132 | P.S. 132 - MANHATTAN | SCA CIP | DEFECTIVE WROUGHT IRON FENCE & HANDRAILS / FY16 RESO A PLAYGROUND REDEVELOPMENT / WATER INFILTRATION / BOILER REPAIR / RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 1/26/2018 | 6/27/2018 | 5/9/2018 | 635343 | 1229645 | 1100297
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | Scope | Complete | 7/8/2021 | 11/23/2021 | 11/15/2021 | 256450 | 149324 | 149324
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | FACADE REMEDIATION @ M143 / WINDOWS | Design | Complete | 12/1/2021 | 5/19/2022 | 5/11/2022 | 1282250 | 1040643 | 615253
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / LIGHTING UPGRADE | Scope | Complete | 8/31/2023 | 1/30/2024 | 2/26/2024 | 371903 | 251567 | 251567
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/10/2018 | 4/10/2019 | 9/6/2019 | 31096 | 34530 | 34530
6 | M143 | I.S. 143 - MANHATTAN | SCA CIP | WATER MAIN / BACKFLOW PREVENTION / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 9/11/2019 | 5/20/2020 | 4/15/2020 | 147389 | 140228 | 140228
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/25/2018 | 9/24/2018 | 10/9/2018 | 84575 | 79488 | 79488
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Design | Complete | 10/16/2018 | 3/6/2019 | 4/29/2019 | 342970 | 342970 | 318240
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | Scope | Complete | 9/10/2019 | 1/14/2020 | 8/16/2021 | 14579 | 22049 | 22049
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | NYS AUDITORIUM UPGRADE | Design | Complete | 8/31/2021 | 2/4/2022 | 5/11/2022 | 72894 | 85968 | 79267
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Scope | Complete | 8/31/2021 | 12/3/2021 | 3/25/2022 | 18526 | 18526 | 18526
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Design | Complete | 3/25/2022 | 7/25/2022 | 1/3/2024 | 5436 | 5436 | 5436
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | Scope | Complete | 5/30/2023 | 10/16/2023 | 9/25/2023 | 229330 | 246882 | 240247
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / EMERGENCY GENERATOR / FLOOD ELIMINATION | Design | Complete | 10/25/2023 | 6/10/2024 | 4/25/2024 | 1131307 | 404092 | 395914
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/27/2023 | 10/27/2023 | 10/5/2023 | 10634 | 17749 | 17686
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/17/2023 | 3/18/2024 | 4/10/2024 | 47852 | 44868 | 44868
6 | M152 | P.S. 152 - MANHATTAN | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/17/2023 | 5/15/2024 | 4/2/2024 | 27000 | 18005 | 18005
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/20/2022 | 12/6/2022 | 5/4/2023 | 77350 | 143338 | 143338
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 6/14/2023 | 11/16/2023 | 10/27/2023 | 386750 | 346454 | 305705
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Scope | Complete | 10/12/2022 | 7/14/2023 | 9/28/2023 | 15192 | 48889 | 48889
6 | M164 | I.S. 328 - MANHATTAN | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Design | Complete | 10/11/2023 | 2/15/2024 | 4/19/2024 | 74053 | 64103 | 56250
6 | M173 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | Scope | Complete | 12/18/2017 | 5/4/2018 | 3/23/2018 | 165873 | 150089 | 150087
6 | M173 | P.S. 173 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS | Design | Complete | 3/23/2018 | 8/22/2018 | 5/18/2018 | 652179 | 584627 | 529862
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/27/2023 | 10/27/2023 | 10/13/2023 | 10620 | 16346 | 13367
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/16/2023 | 3/15/2024 | 4/10/2024 | 47790 | 64196 | 54116
6 | M176 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | Scope | Complete | 6/27/2019 | 7/13/2021 | 9/23/2021 | 68580 | 95630 | 95630
6 | M176 | P.S. 314 - MANHATTAN | SCA CIP | PARAPETS / FY20 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY | Design | Complete | 1/11/2022 | 5/26/2022 | 7/19/2022 | 326100 | 298937 | 276308
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/28/2022 | 10/27/2022 | 7/6/2022 | 3660 | 5349 | 5349
6 | M176 | P.S. 311 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/6/2022 | 1/3/2023 | 1/4/2023 | 16470 | 21397 | 21397
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 1/16/2020 | 5/24/2021 | 2/15/2022 | 104838 | 104838 | 99073
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY17 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2/16/2022 | 4/18/2022 | 11/1/2022 | 142866 | 142866 | 79738
6 | M187 | P.S. 187 - MANHATTAN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 8/9/2023 | 12/13/2023 | 11/1/2023 | 113541 | 57591 | 52776
6 | M189 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | Scope | Complete | 12/18/2017 | 5/4/2018 | 2/28/2018 | 185319 | 256806 | 256760
6 | M189 | P.S. 189 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND | Design | Complete | 2/28/2018 | 7/30/2018 | 5/17/2018 | 735179 | 1185363 | 933574
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | EXTERIOR STAIRS / PAVED AREAS - CONCRETE / NON-TCU TEMPORARY REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/22/2020 | 5/17/2023 | 6/5/2023 | 37500 | 133176 | 118997
6 | M192 | P.S. 192 - MANHATTAN | SCA CIP | EXTERIOR STAIRS / PAVED AREAS - CONCRETE / NON-TCU TEMPORARY REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 6/6/2023 | 10/23/2023 | 12/29/2023 | 186383 | 289250 | 197228
6 | M192 | HAMILTON GRANGE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 8/8/2023 | 1/11/2024 | 1/5/2024 | 14461 | 54518 | 48571
6 | M218 | I.S. 293 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ELECTRIFICATION/HEAT PUMP SYSTEMS / EXTERIOR MASONRY / PARAPETS / ROOFS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SERVICE UPGRADE / WINDOWS / LIGHTING UPGRADE | Scope | Complete | 7/8/2022 | 11/22/2023 | 3/1/2024 | 673976 | 953582 | 669935
6 | M218 | I.S. 293 - MANHATTAN | SCA CIP | FLOOD ELIMINATION / ELECTRIFICATION/HEAT PUMP SYSTEMS / EXTERIOR MASONRY / PARAPETS / ROOFS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SERVICE UPGRADE / WINDOWS / LIGHTING UPGRADE | Design | Complete | 3/1/2024 | 8/1/2024 | 5/15/2024 | 3365191 | 1695891 | 1679351
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | Scope | Complete | 9/11/2017 | 9/14/2017 | 9/21/2017 | 26700 | 70204 | 70204
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WATER MAIN- BACKFLOW ISSUE | Design | Complete | 9/21/2017 | 6/29/2018 | 8/8/2018 | 97900 | 132798 | 124219
6 | M465 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | Scope | Complete | 4/2/2018 | 7/31/2018 | 8/6/2018 | 27662 | 126860 | 126860
6 | M465 | GEORGE WASHINGTON CAMPUS YABC | SCA CIP | COLLAPSED RETAINING WALL | Design | Complete | 12/1/2021 | 5/4/2022 | 5/12/2023 | 138310 | 310782 | 24743
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 11/15/2018 | 4/4/2019 | 4/4/2019 | 564406 | 471256 | 471256
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | WINDOWS / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 4/5/2019 | 9/5/2019 | 5/16/2019 | 2257620 | 1196023 | 1024916
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | Scope | Complete | 1/3/2020 | 5/19/2020 | 10/14/2021 | 57240 | 124249 | 106234
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SCIENCE LAB | Design | Complete | 10/18/2021 | 4/22/2022 | 9/26/2022 | 286200 | 464066 | 412376
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 9/18/2013 | 10/4/2019 | 10/1/2019 | 216730 | 202664 | 202664
6 | M465 | HS FOR HEALTH CAREER & SCIENCE - M | SCA CIP | SWIMMING POOLS / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 10/1/2019 | 3/6/2020 | 5/12/2021 | 1083650 | 1126786 | 1033140
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | Scope | Complete | 10/26/2020 | 3/23/2021 | 3/23/2021 | 2036860 | 1480120 | 1444512
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA Capacity | NEW SCHOOL | Design | Complete | 3/24/2021 | 10/25/2021 | 11/3/2021 | 9165870 | 5472738 | 5142063
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | Scope | Complete | 1/20/2021 | 1/20/2021 | 1/20/2021 | 17304 | 35264 | 35264
6 | M502 | P.S./I.S. @ 3761 10 AVENUE - MANHATTAN | SCA CIP | DEMOLITION | Design | Complete | 1/20/2021 | 10/25/2021 | 12/1/2021 | 86520 | 141063 | 141063
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/6/2022 | 11/3/2022 | 7/19/2022 | 5800 | 7547 | 7547
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/19/2022 | 1/17/2023 | 1/4/2023 | 26100 | 30192 | 30192
6 | M528 | I.S. 528 - MANHATTAN | SCA CIP RESOA | FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 12/21/2022 | 5/9/2023 | 7/5/2023 | 83526 | 66393 | 65113
6 | M847 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | Scope | Complete | 6/25/2018 | 9/24/2018 | 10/9/2018 | 76528 | 76528 | 76528
6 | M847 | P.S. 152 - MANHATTAN | SCA CIP | DEMOLITION OF MINI BUILDING | Design | Complete | 10/16/2018 | 3/6/2019 | 4/29/2019 | 208701 | 208701 | 208701
6 | M859 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | Scope | Complete | 1/11/2021 | 4/12/2021 | 1/19/2021 | 1584 | 1037 | 1037
6 | M859 | I.S. 348 - MANHATTAN | SCA CIP | PUBLIC ADDRESS SYSTEM | Design | Complete | 1/20/2021 | 6/21/2021 | 4/12/2021 | 7127 | 4772 | 4147
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/28/2022 | 7/26/2022 | 4/14/2022 | 1477 | 2955 | 2955
6 | M876 | GREGORIO LUPERON PREP. SCHOOL - M | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/14/2022 | 10/7/2022 | 7/19/2022 | 6646 | 11817 | 11817
6 | MBEQ | U.F.B.C.O. | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 4/7/2021 | 7/7/2021 | 8/6/2021 | 780 | 35150 | 35150
7 | X005 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 6/26/2019 | 11/12/2019 | 12/3/2019 | 57964 | 82112 | 82112
7 | X005 | P.S. 5 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 12/18/2019 | 5/20/2020 | 2/28/2022 | 285806 | 233037 | 233037
7 | X005 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/28/2022 | 11/29/2022 | 11/15/2022 | 3721 | 9128 | 9128
7 | X005 | P.S. 5 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 11/15/2022 | 5/12/2023 | 2/15/2023 | 16744 | 36511 | 36511
7 | X018 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 9/25/2018 | 8/29/2019 | 5/1/2019 | 25281 | 17964 | 17964
7 | X018 | P.S. 18 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 5/1/2019 | 10/1/2019 | 5/16/2019 | 93087 | 75917 | 71980
7 | X025 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/8/2023 | 12/8/2023 | 8/22/2023 | 4690 | 1648 | 1648
7 | X025 | P.S. 25 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/22/2023 | 2/21/2024 | 11/29/2023 | 21105 | 6593 | 6593
7 | X027 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 11/6/2018 | 3/27/2019 | 2/26/2019 | 115360 | 98171 | 98171
7 | X027 | P.S. 277 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 2/27/2019 | 7/29/2019 | 5/17/2019 | 454495 | 499266 | 408517
7 | X027 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 12/22/2020 | 4/22/2021 | 11/23/2021 | 76950 | 105699 | 105699
7 | X027 | P.S. 277 - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 11/29/2021 | 5/23/2022 | 8/16/2022 | 384750 | 375001 | 310720
7 | X027 | P.S. 277 - BRONX | SCA CIP | RETAINING WALL | Scope | Complete | 2/23/2022 | 5/23/2022 | 3/29/2022 | 8577 | 0 | 0
7 | X027 | P.S. 277 - BRONX | SCA CIP | RETAINING WALL | Design | Complete | 3/29/2022 | 3/29/2022 | 3/29/2022 | 38597 | 0 | 0
7 | X027 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/18/2020 | 12/18/2020 | 8/21/2020 | 5200 | 3620 | 3620
7 | X027 | P.S. 277 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/21/2020 | 2/17/2021 | 5/26/2021 | 23400 | 14481 | 14481
7 | X030 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 6/4/2021 | 10/20/2021 | 12/7/2021 | 96300 | 137083 | 137083
7 | X030 | P.S. 30 - BRONX | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 12/8/2021 | 5/11/2022 | 5/12/2022 | 481500 | 421066 | 421066
7 | X043 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | Scope | Complete | 10/27/2015 | 2/16/2017 | 2/27/2017 | 331508 | 452076 | 452076
7 | X043 | P.S. 43 - BRONX | SCA CIP | WATER PENETRATION / BOILER REPLACEMENT / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / CLIMATE CONTROL / DOMESTIC PIPING | Design | Complete | 4/26/2017 | 9/26/2017 | 4/20/2018 | 1318825 | 1464844 | 1079218
7 | X043 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/29/2022 | 8/29/2022 | 8/25/2022 | 4663 | 7401 | 7401
7 | X043 | P.S. 43 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/25/2022 | 2/24/2023 | 2/15/2023 | 20982 | 29602 | 29602
7 | X043 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | Scope | Complete | 5/29/2019 | 8/19/2021 | 7/12/2021 | 170880 | 149317 | 139319
7 | X043 | P.S. 43 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS | Design | Complete | 10/20/2021 | 4/11/2022 | 3/20/2023 | 854400 | 545180 | 436140
7 | X049 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 3/23/2021 | 8/5/2021 | 1/27/2022 | 161224 | 146826 | 146826
7 | X049 | P.S. 49 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 5/27/2022 | 12/1/2022 | 5/12/2023 | 801894 | 674151 | 596966
7 | X065 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 8/5/2020 | 12/4/2020 | 7/2/2021 | 44200 | 22516 | 20065
7 | X065 | P.S. 65 - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 7/7/2021 | 12/8/2021 | 12/22/2021 | 221000 | 155225 | 56256
7 | X065 | P.S. 65 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/11/2024 | 1/14/2025 | 9/18/2024 | 4093 | 1073 | 1073
7 | X149 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | Scope | Complete | 8/12/2020 | 1/15/2021 | 12/4/2020 | 75640 | 99774 | 99774
7 | X149 | I.S. 221 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL | Design | Complete | 12/7/2020 | 5/10/2021 | 3/17/2021 | 378200 | 402471 | 379743
7 | X151 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/12/2021 | 7/12/2021 | 3/25/2021 | 4700 | 6783 | 6783
7 | X151 | I.S. 151 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/25/2021 | 8/17/2021 | 8/25/2021 | 21150 | 27203 | 27203
7 | X154 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 7/25/2018 | 12/11/2018 | 9/23/2019 | 97962 | 137543 | 137543
7 | X154 | P.S. 154 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 11/6/2019 | 4/27/2020 | 6/30/2020 | 481290 | 475221 | 404814
7 | X154 | P.S. 154 - BRONX | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 7/19/2023 | 12/20/2023 | 1/22/2024 | 56764 | 109929 | 34614
7 | X155 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/15/2023 | 12/14/2023 | 10/25/2023 | 135892 | 95148 | 93939
7 | X155 | P.S. 754 SPED - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 11/6/2023 | 6/28/2024 | 4/4/2024 | 679460 | 224545 | 224545
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/3/2024 | 9/4/2024 | 5/13/2024 | 5477 | 665 | 665
7 | X156 | LEADERS OF EXCELLENCE, ADVOCACY AND DISCOVER | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/13/2024 | 3/12/2025 | 9/17/2024 | 24648 | 2661 | 2661
7 | X157 | P.S. 157 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/19/2024 | 8/20/2024 | 4/23/2024 | 4663 | 386 | 386
7 | X157 | P.S. 157 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/23/2024 | 10/18/2024 | 9/17/2024 | 20982 | 1546 | 1546
7 | X161 | P.S. 161 - BRONX | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 1/12/2023 | 5/30/2023 | 12/6/2023 | 41773 | 173121 | 173082
7 | X161 | P.S. 161 - BRONX | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/8/2023 | 5/10/2024 | 5/14/2024 | 203358 | 193070 | 184110
7 | X161 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/31/2022 | 1/4/2023 | 11/15/2022 | 3596 | 9200 | 9200
7 | X161 | P.S. 161 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 11/15/2022 | 5/12/2023 | 2/15/2023 | 16184 | 36798 | 36798
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/11/2022 | 11/25/2022 | 11/22/2023 | 52640 | 215935 | 209457
7 | X162 | HOSTOS-LINCOLN ACADEMY OF SCIENCE | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/28/2023 | 4/30/2024 | 5/2/2024 | 263200 | 411674 | 312034
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 7/6/2023 | 11/6/2023 | 10/25/2023 | 11900 | 16395 | 16395
7 | X183 | THE URBAN ASSEMBLY BRONX ACADEMY OF LETTERS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/1/2023 | 4/1/2024 | 4/12/2024 | 53550 | 103603 | 48914
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 4/7/2021 | 8/20/2021 | 9/2/2021 | 44214 | 177726 | 174955
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/15/2021 | 2/18/2022 | 5/5/2022 | 216529 | 257503 | 252226
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | SCIENCE LAB UPGRADE | Scope | Complete | 3/5/2024 | 6/18/2024 | 6/3/2024 | 15652 | 20939 | 2039
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | PATH OF TRAVEL SCIENCE LAB UPGRADE | Scope | Complete | 6/4/2024 | 9/5/2024 | 7/2/2024 | 2926 | 267 | 267
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/11/2020 | 7/9/2020 | 6/4/2020 | 3546 | 3557 | 3557
7 | X184 | JILL CHAIFETZ TRANSFER HIGH SCHOOL - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/4/2020 | 12/1/2020 | 12/1/2020 | 15956 | 14226 | 14226
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | Scope | Complete | 11/7/2018 | 9/9/2021 | 12/15/2021 | 89549 | 241244 | 241244
7 | X470 | UNIVERSITY HEIGHTS HS - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / ACCESSIBLE RAMP / ROOFS / EXTERIOR MASONRY | Design | Complete | 12/17/2021 | 5/20/2022 | 2/15/2023 | 409361 | 584037 | 535067
7 | X487 | P.S. @ 639 ST ANN'S AVENUE - BRONX | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/1/2019 | 9/6/2019 | 8/28/2019 | 1335780 | 1405829 | 1385877
7 | X487 | P.S. @ 639 ST ANN'S AVENUE - BRONX | SCA Capacity | NEW SCHOOL | Design | Complete | 8/29/2019 | 4/1/2020 | 4/1/2020 | 6011010 | 4958965 | 4762051
7 | X487 | P.S. @ 639 ST ANN'S AVENUE - BRONX | SCA Capacity | NEW SCHOOL | Construction | Complete | 8/2/2021 | 9/3/2024 | 5/13/2024 | 75805515 | 69156272 | 65374035
7 | X487 | P.S. @ 639 ST ANN'S AVENUE - BRONX | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 8/2/2021 | 9/3/2024 | 5/13/2024 | 10686240 | 8001439 | 6579352
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | STRUCTURAL CONCRETE FAILURE @ X600 | Scope | Complete | 8/5/2022 | 12/22/2022 | 12/14/2022 | 19525 | 12861 | 12861
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | STRUCTURAL CONCRETE FAILURE @ X600 | Design | Complete | 12/23/2022 | 5/26/2023 | 8/2/2023 | 87863 | 37377 | 3524
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/9/2020 | 7/7/2020 | 6/4/2020 | 3806 | 3584 | 3584
7 | X600 | ALFRED E. SMITH HS - X | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/4/2020 | 12/1/2020 | 12/1/2020 | 17128 | 14336 | 14336
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | Scope | Complete | 9/7/2018 | 2/6/2019 | 11/26/2018 | 43770 | 25975 | 25975
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | STH SBHC | Design | Complete | 12/5/2018 | 5/29/2019 | 5/17/2019 | 175080 | 262283 | 122751
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | Scope | Complete | 2/10/2020 | 7/7/2020 | 5/3/2021 | 37750 | 60357 | 60357
7 | X655 | HERO HIGH (HEALTH, EDUCATION, AND RESEARCH OCCUPATIONS HS) | SCA CIP | BATHROOM UPGRADES / GYM UPGRADE | Design | Complete | 5/10/2021 | 10/26/2021 | 5/13/2022 | 188750 | 254143 | 246758
7 | X790 | X188 SPED - BRONX | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/8/2021 | 2/14/2022 | 2/3/2022 | 26831 | 19849 | 19849
7 | X790 | X188 SPED - BRONX | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 12/20/2022 | 5/8/2023 | 6/15/2023 | 129250 | 102038 | 90493
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 9/21/2017 | 2/9/2018 | 12/19/2017 | 23694 | 29336 | 29144
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | FLOOD ELIMINATION | Design | Complete | 8/1/2018 | 1/4/2019 | 4/23/2019 | 94776 | 159173 | 139135
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | COVID VENTILATION | Scope | Complete | 1/5/2021 | 5/5/2021 | 9/15/2021 | 57262 | 107560 | 96635
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | COVID VENTILATION | Design | Complete | 9/24/2021 | 2/24/2022 | 3/1/2022 | 286311 | 188101 | 177977
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 6/21/2022 | 11/17/2022 | 11/23/2022 | 290421 | 290421 | 288724
8 | X039 | LONGWOOD PREPARATORY ACADEMY | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SERVICE UPGRADE | Design | Complete | 11/30/2022 | 5/26/2023 | 5/21/2024 | 1006108 | 1006108 | 970753
8 | X039 | HOLCOMBE L. RUCKER SCHOOLOF COMMUNITY RESEARCH - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE | Design | Complete | 9/15/2016 | 3/9/2017 | 3/8/2017 | 36870 | 299175 | 298514
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 11/29/2022 | 4/17/2023 | 5/3/2023 | 90954 | 41149 | 36085
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2/5/2020 | 7/30/2020 | 5/14/2020 | 27000 | 32440 | 32195
8 | X052 | I.S. 302 - BRONX | SCA CIP RESOA | FY21 RESO A STEM LAB / PATH OF TRAVEL RESO A STEM LAB | Design | Complete | 3/22/2023 | 7/25/2023 | 5/2/2023 | 47934 | 85324 | 68437
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | FLOOD ELIMINATION / ROOFS | Scope | Complete | 1/9/2024 | 5/23/2024 | 8/13/2024 | 26981 | 84061 | 50590
8 | X060 | THE LONGWOOD ACADEMY OF DISCOVERY - X | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/20/2024 | 10/21/2024 | 7/1/2024 | 4906 | 1542 | 1542
8 | X062 | P.S. 62 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/18/2024 | 11/18/2024 | 7/23/2024 | 4708 | 1253 | 1253
8 | X062 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | Scope | Complete | 4/1/2021 | 9/22/2021 | 11/3/2021 | 185950 | 202706 | 202706
8 | X062 | P.S. 62 - BRONX | SCA CIP | WINDOWS / FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/10/2021 | 5/2/2022 | 8/9/2022 | 929750 | 715665 | 678744
8 | X069 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/19/2019 | 11/4/2019 | 11/1/2019 | 59740 | 140291 | 140017
8 | X069 | P.S. 69 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY | Design | Complete | 2/19/2020 | 7/20/2020 | 4/29/2022 | 298700 | 290665 | 289542
8 | X071 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 7/29/2019 | 7/9/2021 | 11/24/2021 | 409144 | 531249 | 515060
8 | X071 | P.S. 71 - BRONX | SCA CIP | KITCHEN EXHAUST REPLACEMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 12/7/2021 | 5/10/2022 | 10/11/2022 | 2032006 | 1817358 | 1448093
8 | X072 | P.S. 72 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 3/17/2022 | 8/1/2022 | 2/7/2023 | 92868 | 174901 | 164656
8 | X072 | P.S. 72 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 5/17/2023 | 10/19/2023 | 5/13/2024 | 460223 | 341490 | 239495
8 | X074 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/19/2018 | 3/11/2019 | 10/3/2019 | 89717 | 163059 | 163058
8 | X074 | I.S. 424 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/4/2019 | 5/6/2020 | 4/13/2021 | 433912 | 903723 | 711292
8 | X074 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 10/16/2020 | 2/19/2021 | 2/12/2021 | 3944 | 3962 | 3962
8 | X074 | I.S. 424 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 2/12/2021 | 8/9/2021 | 7/14/2021 | 17748 | 15849 | 15849
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 1/10/2022 | 5/25/2022 | 5/10/2024 | 97500 | 69355 | 65747
8 | X074 | I.S. 424 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 3/22/2022 | 7/25/2022 | 5/10/2024 | 1960 | 22895 | 8706
8 | X075 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 10/24/2018 | 2/22/2019 | 4/8/2019 | 358164 | 319216 | 319216
8 | X075 | P.S. 75 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | Complete | 8/7/2019 | 1/15/2020 | 6/30/2020 | 1790823 | 1107674 | 1059170
8 | X075 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 8/3/2020 | 12/3/2020 | 6/30/2021 | 34550 | 23504 | 16973
8 | X075 | X352 SPED - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 7/7/2021 | 12/8/2021 | 11/22/2021 | 172750 | 113954 | 96559
8 | X075 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/16/2022 | 3/21/2023 | 12/13/2022 | 4672 | 5811 | 5811
8 | X075 | P.S. 75 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/13/2022 | 6/9/2023 | 2/8/2023 | 21026 | 23245 | 23245
8 | X075 | P.S. 75 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 3/14/2022 | 7/15/2022 | 5/11/2022 | 77520 | 71543 | 53103
8 | X101 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 5/15/2017 | 10/16/2017 | 7/7/2017 | 99450 | 120648 | 120648
8 | X101 | P.S. 304 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/14/2017 | 12/15/2017 | 1/12/2018 | 397800 | 418734 | 408132
8 | X101 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/28/2022 | 3/30/2023 | 12/13/2022 | 5300 | 6356 | 6356
8 | X101 | P.S. 304 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/13/2022 | 6/9/2023 | 2/8/2023 | 23850 | 25424 | 25424
8 | X107 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 6/28/2022 | 11/14/2022 | 10/26/2022 | 71874 | 81842 | 81432
8 | X107 | P.S. 107 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 11/30/2022 | 5/3/2023 | 11/15/2023 | 347396 | 225567 | 157040
8 | X119 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | Scope | Complete | 9/15/2017 | 2/5/2018 | 2/2/2018 | 16049 | 17430 | 17430
8 | X119 | P.S. 119 - BRONX | SCA CIP | FLOOD ELIMINATION / PARAPETS | Design | Complete | 3/16/2018 | 8/15/2018 | 10/17/2018 | 58847 | 63875 | 63875
8 | X119 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | Scope | Complete | 6/5/2023 | 12/4/2023 | 10/30/2023 | 124676 | 142776 | 123868
8 | X119 | P.S. 119 - BRONX | SCA CIP | STRUCTURAL ISSUES/BUILDING FACADES- PERM FIX / ROOFS / WINDOWS / PARAPETS | Design | Complete | 11/14/2023 | 4/17/2024 | 4/16/2024 | 623380 | 325614 | 325614
8 | X120 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 7/9/2020 | 12/10/2020 | 9/15/2020 | 88770 | 68219 | 68219
8 | X120 | I.S. 301 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 9/18/2020 | 2/24/2021 | 1/8/2021 | 443850 | 287980 | 259780
8 | X120 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/17/2023 | 5/16/2023 | 2/2/2023 | 2960 | 2598 | 2598
8 | X120 | I.S. 301 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/2/2023 | 7/31/2023 | 4/12/2023 | 13320 | 10390 | 10390
8 | X123 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 9/1/2017 | 1/23/2018 | 1/30/2018 | 68640 | 120343 | 120343
8 | X123 | I.S. 123 - BRONX | SCA CIP | WATER INFILTRATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/8/2020 | 6/9/2020 | 5/7/2020 | 343200 | 529193 | 495214
8 | X123 | I.S. 123 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 12/11/2023 | 4/26/2024 | 7/31/2024 | 190360 | 175422 | 115751
8 | X125 | P.S. 119 - BRONX | SCA CIP | SEWAGE TANK REPLACEMENT- PERM FIX @ X125 | Scope | Complete | 10/4/2023 | 2/8/2024 | 1/5/2024 | 7019 | 11672 | 11672
8 | X125 | P.S. 119 - BRONX | SCA CIP | SEWAGE TANK REPLACEMENT- PERM FIX @ X125 | Design | Complete | 1/22/2024 | 5/15/2024 | 4/25/2024 | 31586 | 28596 | 27063
8 | X125 | I.S. 562 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 5/18/2023 | 10/20/2023 | 12/18/2023 | 45000 | 49395 | 46894
8 | X130 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/21/2019 | 11/22/2019 | 9/25/2019 | 60358 | 62272 | 62272
8 | X130 | P.S. 130 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 10/4/2019 | 3/11/2020 | 2/11/2020 | 294168 | 282565 | 263071
8 | X131 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | Scope | Complete | 1/15/2020 | 6/3/2022 | 11/15/2022 | 11900 | 31873 | 31873
8 | X131 | I.S. 131 - BRONX | SCA CIP | CHARTER MATCH SCIENCE LAB UPGRADE / PATH OF TRAVEL CHARTER MATCH SCIENCE LAB UPGRADE | Design | Complete | 11/25/2022 | 4/7/2023 | 4/17/2023 | 53550 | 118629 | 49832
8 | X131 | I.S. 131 - BRONX | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 4/3/2019 | 9/3/2019 | 3/25/2022 | 49500 | 63829 | 37502
8 | X138 | P.S. 138 - BRONX | SCA Capacity | ADDITION | Scope | Complete | 9/6/2019 | 3/12/2020 | 10/23/2020 | 1155980 | 733168 | 732146
8 | X138 | P.S. 138 - BRONX | SCA Capacity | ADDITION | Design | Complete | 10/26/2020 | 9/14/2020 | 8/12/2021 | 5201910 | 2946193 | 2434885
8 | X138 | P.S. 138 - BRONX | SCA Capacity | ADDITION | Construction | Complete | 1/19/2022 | 9/3/2024 | 9/1/2024 | 65601865 | 65368873 | 46926835
8 | X138 | P.S. 138 - BRONX | SCA Capacity | ADDITION | CM,Art,F&E | Complete | 1/19/2022 | 9/3/2024 | 9/1/2024 | 9247840 | 8320544 | 5474140
8 | X138 | P.S. 138 - BRONX | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS | Scope | Complete | 2/7/2023 | 6/7/2023 | 12/14/2023 | 14596 | 62015 | 41450
8 | X140 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 5/12/2022 | 9/27/2022 | 8/31/2022 | 46285 | 42360 | 42360
8 | X140 | P.S. 140 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS | Design | Complete | 9/2/2022 | 2/8/2023 | 2/8/2023 | 224497 | 186291 | 169881
8 | X140 | P.S. 140 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 4/5/2023 | 7/6/2023 | 8/2/2023 | 24894 | 61170 | 61170
8 | X140 | P.S. 140 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 8/7/2023 | 12/22/2023 | 4/30/2024 | 124469 | 133611 | 122383
8 | X140 | P.S. 140 - BRONX | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/29/2023 | 10/31/2023 | 10/2/2023 | 7313 | 14418 | 592
8 | X140 | P.S. 140 - BRONX | SCA CIP | PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 10/13/2023 | 2/20/2024 | 4/30/2024 | 32908 | 32716 | 2368
8 | X140 | P.S. 140 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/8/2024 | 9/9/2024 | 5/17/2024 | 5638 | 1955 | 1955
8 | X140 | P.S. 140 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 6/11/2024 | 10/15/2024 | 8/13/2024 | 30000 | 34313 | 32546
8 | X146 | P.S. 146 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 11/19/2018 | 4/8/2019 | 3/6/2019 | 170028 | 184128 | 126385
8 | X146 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 8/1/2019 | 12/18/2019 | 12/3/2019 | 89740 | 113807 | 113807
8 | X146 | P.S. 146 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 1/22/2020 | 7/8/2020 | 1/12/2022 | 448700 | 558155 | 527801
8 | X146 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/21/2022 | 4/24/2023 | 1/26/2023 | 5000 | 3925 | 3925
8 | X146 | P.S. 146 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/26/2023 | 7/24/2023 | 4/12/2023 | 22500 | 15697 | 15697
8 | X152 | P.S. 152 - BRONX | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / CHILLER PLANT UPGRADE / FLOOD ELIMINATION | Scope | Complete | 6/5/2019 | 10/21/2019 | 10/10/2019 | 128000 | 189649 | 166630
8 | X152 | P.S. 152 - BRONX | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / CHILLER PLANT UPGRADE / FLOOD ELIMINATION | Design | Complete | 11/20/2019 | 4/23/2020 | 6/15/2020 | 603485 | 482898 | 437950
8 | X152 | P.S. 152 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/15/2024 | 9/16/2024 | 5/21/2024 | 5079 | 592 | 592
8 | X182 | P.S. 182 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/29/2024 | 9/27/2024 | 6/5/2024 | 4749 | 1804 | 1804
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | Scope | Complete | 11/20/2020 | 2/16/2021 | 12/15/2021 | 164800 | 99880 | 96998
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | VENTILATION @ X405 | Design | Complete | 1/13/2022 | 6/20/2022 | 9/28/2022 | 824000 | 748032 | 409377
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | Scope | Complete | 11/10/2021 | 1/13/2022 | 1/12/2022 | 10500 | 19205 | 19205
8 | X405 | HERBERT H. LEHMAN HS - X | SCA CIP | AUDITORIUM UP0GRADE | Design | Complete | 1/31/2022 | 6/3/2022 | 5/10/2022 | 52500 | 110563 | 36644
8 | X451 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | Scope | Complete | 3/22/2019 | 11/1/2021 | 11/24/2021 | 264990 | 382373 | 382373
8 | X451 | X000 - BRONX | SCA CIP | ATHLETIC FIELD/FIELD HOUSE / DEP GREEN INFRASTRUCTURE | Design | Complete | 11/29/2021 | 4/28/2022 | 9/30/2022 | 1324948 | 1581837 | 1255058
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 9/21/2018 | 12/24/2018 | 1/10/2019 | 59010 | 87548 | 87548
8 | X650 | SCHOOL FOR TOURISM AND HOSPITALITY - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 1/16/2019 | 6/3/2019 | 5/16/2019 | 236040 | 432892 | 422707
8 | X650 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 9/15/2021 | 1/19/2022 | 9/30/2021 | 4600 | 3095 | 3095
8 | X650 | ALC-JANE ADDAMS HS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/30/2021 | 3/31/2022 | 1/11/2022 | 20700 | 12378 | 12378
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/14/2023 | 10/13/2023 | 10/17/2023 | 8800 | 16275 | 16275
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/24/2023 | 3/25/2024 | 3/27/2024 | 39600 | 51616 | 41175
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/25/2023 | 5/24/2023 | 2/24/2023 | 4080 | 4526 | 4526
9 | X002 | BRONX CNTR FOR SCIENCE & MATH - X | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/24/2023 | 8/21/2023 | 5/3/2023 | 18360 | 18106 | 18106
9 | X004 | P.S. 4 - BRONX | SCA CIP | SWIMMING POOLS | Scope | Complete | 11/22/2023 | 5/17/2024 | 7/22/2024 | 89722 | 116490 | 5490
9 | X004 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | Scope | Complete | 2/11/2016 | 9/17/2021 | 10/5/2021 | 62480 | 72320 | 72320
9 | X004 | P.S. 4 - BRONX | SCA CIP | RNWL SBHC / RNWL SBHC- ELECTRICAL UPGRADE / STH SBHC- MENTAL HEALTH SUITE | Design | Complete | 10/6/2021 | 3/3/2022 | 5/11/2022 | 312400 | 422837 | 326544
9 | X011 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | Scope | Complete | 2/24/2021 | 6/8/2021 | 1/18/2022 | 144418 | 486036 | 463729
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | Scope | Complete | 2/14/2019 | 7/1/2019 | 7/7/2021 | 30869 | 173897 | 169991
9 | X011 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | Design | Complete | 1/26/2022 | 6/27/2022 | 5/11/2022 | 705001 | 610416 | 599177
9 | X011 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | Construction | Complete | 7/18/2022 | 7/16/2024 | 7/22/2024 | 14384433 | 13560587 | 12856267
9 | X011 | P.S. 11 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / EXTERIOR DOORS / ROOFS / SECURITY LIGHTING | CM,F&E | Complete | 7/18/2022 | 7/16/2024 | 7/22/2024 | 1168540 | 776803 | 770832
9 | X011 | P.S. 11 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/16/2023 | 10/16/2023 | 10/16/2023 | 9700 | 12384 | 12384
9 | X011 | P.S. 11 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/24/2023 | 3/25/2024 | 4/5/2024 | 43650 | 40969 | 39829
9 | X022 | I.S. 22 - BRONX | SCA CIP | ROOFS / GYMNASIUM FLOORING / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 6/5/2023 | 12/4/2023 | 10/2/2023 | 182777 | 203386 | 203386
9 | X022 | I.S. 22 - BRONX | SCA CIP | ROOFS / GYMNASIUM FLOORING / EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 10/18/2023 | 6/11/2024 | 4/19/2024 | 910109 | 352567 | 352567
9 | X022 | I.S. 22 - BRONX | SCA CIP RESOA | FY21 RESO A (MA) AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2/1/2023 | 6/2/2023 | 10/13/2023 | 90000 | 105109 | 101087
9 | X028 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 9/19/2017 | 11/15/2021 | 3/4/2022 | 383131 | 385894 | 385894
9 | X028 | P.S. 28 - BRONX | SCA CIP | DETERIORATED METAL ARCH CEILING & BEAMS / FULL PROGRAM ACCESSIBILITY / ELECTRICAL SERVICE UPGRADE / EXTERIOR MASONRY / WINDOWS | Design | Complete | 3/4/2022 | 8/3/2022 | 5/16/2022 | 1905372 | 1818432 | 1643053
9 | X028 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/13/2023 | 7/12/2023 | 3/21/2023 | 3320 | 2744 | 2744
9 | X028 | P.S. 28 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/21/2023 | 9/14/2023 | 5/3/2023 | 14940 | 10976 | 10976
9 | X053 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | Scope | Complete | 3/14/2022 | 7/12/2022 | 7/20/2022 | 29950 | 29110 | 29110
9 | X053 | P.S. 53 - BRONX | SCA CIP | STH- SBHC | Design | Complete | 8/4/2022 | 1/19/2023 | 5/11/2023 | 149750 | 130820 | 103916
9 | X055 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Scope | Complete | 8/6/2021 | 6/3/2022 | 11/15/2022 | 22639 | 38939 | 38939
9 | X055 | P.S. 55 - BRONX | SCA CIP | CHARTER MATCH AUDITORIUM UPGRADE / PATH OF TRAVEL CHARTER MATCH AUDITORIUM UPGRADE | Design | Complete | 11/25/2022 | 4/7/2023 | 4/17/2023 | 112861 | 158408 | 121247
9 | X058 | P.S. 58 - BRONX | SCA CIP | SITE DRAINAGE | Scope | Complete | 3/18/2024 | 3/18/2024 | 3/18/2024 | 17000 | 6108 | 343
9 | X058 | P.S. 58 - BRONX | SCA CIP | SITE DRAINAGE | Design | Complete | 3/18/2024 | 6/28/2024 | 6/26/2024 | 76500 | 1371 | 1371
9 | X058 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | Scope | Complete | 11/28/2017 | 12/11/2018 | 12/12/2018 | 283697 | 209902 | 209853
9 | X058 | P.S. 58 - BRONX | SCA CIP | FLOOD ELIMINATION / FULL PROGRAM ACCESSIBILITY / EXTERIOR MASONRY / WINDOWS / ROOFS / PARAPETS | Design | Complete | 1/3/2019 | 6/20/2019 | 5/17/2019 | 1120106 | 579719 | 516897
9 | X063 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 3/11/2021 | 7/26/2021 | 8/23/2021 | 208115 | 236644 | 236644
9 | X063 | P.S. 63 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS / PAVED AREAS CONCRETE / WINDOWS / PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 9/29/2021 | 3/7/2022 | 3/2/2022 | 1035400 | 814709 | 651446
9 | X063 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 10/20/2020 | 2/23/2021 | 10/23/2020 | 5772 | 5570 | 5570
9 | X063 | P.S. 63 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 10/23/2020 | 4/22/2021 | 6/9/2021 | 25974 | 22280 | 22280
9 | X063 | P.S. 63 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 3/18/2024 | 6/17/2024 | 7/12/2024 | 265 | 265 | 265
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 5/18/2020 | 11/13/2020 | 11/3/2020 | 205690 | 351001 | 324001
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PARAPETS / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS | Design | Complete | 11/19/2020 | 6/15/2021 | 7/1/2021 | 1028450 | 676450 | 674513
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 5/24/2023 | 8/24/2023 | 11/16/2023 | 20798 | 34525 | 28690
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 11/27/2023 | 4/12/2024 | 5/17/2024 | 103990 | 119636 | 113945
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PATH OF TRAVEL- TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 3/15/2024 | 6/13/2024 | 5/8/2024 | 4073 | 673 | 673
9 | X064 | THE WALTON AVENUE SCHOOL | SCA CIP | PATH OF TRAVEL- TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 5/13/2024 | 9/16/2024 | 5/17/2024 | 16291 | 2690 | 2690
9 | X070 | P.S. 70 - BRONX | SCA CIP | STH SBHC | Scope | Complete | 3/7/2022 | 7/5/2022 | 8/10/2022 | 32500 | 25290 | 25290
9 | X070 | P.S. 70 - BRONX | SCA CIP | STH SBHC | Design | Complete | 8/12/2022 | 1/26/2023 | 3/17/2023 | 162500 | 115123 | 81721
9 | X070 | P.S. 70 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Scope | Complete | 9/30/2022 | 1/4/2023 | 12/30/2022 | 36545 | 118527 | 111768
9 | X070 | P.S. 70 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL-OTHER TEMP STRUCTURE REMOVAL | Design | Complete | 9/5/2023 | 4/2/2024 | 5/7/2024 | 178968 | 373279 | 367856
9 | X070 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 7/6/2023 | 11/6/2023 | 10/25/2023 | 9680 | 16580 | 16580
9 | X070 | P.S. 70 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/1/2023 | 4/1/2024 | 4/9/2024 | 43560 | 97429 | 43208
9 | X073 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/15/2021 | 7/28/2021 | 11/24/2021 | 157770 | 183993 | 183993
9 | X073 | P.S. 73 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/8/2021 | 5/26/2022 | 8/26/2022 | 788850 | 466404 | 383894
9 | X073 | P.S. 73 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/14/2023 | 9/14/2023 | 11/21/2023 | 29151 | 46114 | 45764
9 | X073 | P.S. 73 - BRONX | SCA CIP RESOA | FY23 RESO A CAFETERIA UPGRADE | Design | Complete | 10/2/2023 | 10/2/2023 | 10/2/2023 | 45000 | 18027 | 0
9 | X082 | I.S. 303 - BRONX | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 5/18/2023 | 10/4/2023 | 10/3/2023 | 31200 | 44007 | 31642
9 | X088 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/16/2021 | 9/16/2021 | 8/5/2021 | 51235 | 85011 | 85011
9 | X088 | P.S. 88 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 8/9/2021 | 1/12/2022 | 1/13/2022 | 252730 | 359260 | 340754
9 | X088 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/6/2019 | 1/6/2020 | 9/3/2019 | 2901 | 2074 | 2074
9 | X088 | P.S. 88 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 9/3/2019 | 2/6/2020 | 1/31/2020 | 13056 | 8340 | 8340
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 7/2/2019 | 11/1/2019 | 7/24/2019 | 2537 | 1166 | 1166
9 | X090 | THE FAMILY SCHOOL - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 7/24/2019 | 12/26/2019 | 12/30/2019 | 11418 | 4719 | 4719
9 | X104 | P.S. 199 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 11/5/2021 | 3/28/2022 | 1/30/2023 | 133261 | 144023 | 142749
9 | X104 | P.S. 199 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 7/12/2022 | 11/28/2022 | 9/20/2023 | 227002 | 351262 | 221575
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS UPGRADE / WINDOWS / ROOFS / PARAPETS | Scope | Complete | 10/5/2023 | 3/5/2024 | 3/13/2024 | 457765 | 439412 | 330692
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 6/3/2019 | 10/2/2019 | 6/24/2019 | 12141 | 4568 | 4568
9 | X109 | P.S. 109 - BRONX | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 6/24/2019 | 11/25/2019 | 12/3/2019 | 54636 | 18313 | 18313
9 | X110 | P.S. 110 - BRONX | SCA CIP | REPAIR RETAINING WALLS | Scope | Complete | 8/2/2018 | 12/19/2018 | 12/3/2018 | 15503 | 148516 | 141215
9 | X110 | P.S. 110 - BRONX | SCA CIP | REPAIR RETAINING WALLS | Design | Complete | 5/3/2022 | 5/12/2023 | 5/10/2023 | 77514 | 76356 | 69847
9 | X110 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/28/2019 | 11/16/2022 | 2/8/2023 | 150499 | 178247 | 175590
9 | X110 | P.S. 110 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/9/2023 | 7/13/2023 | 5/11/2023 | 748896 | 684258 | 510906
9 | X110 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/6/2023 | 11/3/2023 | 7/18/2023 | 5400 | 1081 | 1081
9 | X110 | P.S. 110 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/18/2023 | 1/16/2024 | 10/11/2023 | 24300 | 4324 | 4324
9 | X114 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 9/28/2018 | 3/6/2019 | 11/15/2018 | 99750 | 93285 | 93285
9 | X114 | P.S. 114 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 11/30/2018 | 5/3/2019 | 4/12/2019 | 399000 | 411435 | 399792
9 | X114 | P.S. 114 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/26/2020 | 11/20/2020 | 9/25/2020 | 89701 | 236653 | 227811
9 | X114 | P.S. 114 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 10/8/2020 | 12/15/2021 | 7/1/2021 | 444984 | 510819 | 508320
9 | X114 | P.S. 114 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / WINDOWS | Construction | Complete | 1/24/2022 | 10/15/2023 | 5/15/2024 | 9708168 | 9005894 | 8432953
9 | X114 | P.S. 114 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY / WINDOWS | CM,F&E | Complete | 1/24/2022 | 10/15/2023 | 5/15/2024 | 654256 | 851417 | 831109
9 | X114 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/6/2023 | 11/3/2023 | 7/18/2023 | 4136 | 1061 | 1061
9 | X114 | P.S. 114 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/18/2023 | 1/16/2024 | 10/11/2023 | 18612 | 4243 | 4243
9 | X117 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 8/17/2020 | 1/21/2021 | 1/4/2021 | 74140 | 85591 | 85591
9 | X117 | I.S. 117 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/5/2021 | 7/30/2021 | 7/28/2021 | 370700 | 353261 | 332901
9 | X126 | P.S. 126 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 11/10/2021 | 3/31/2022 | 1/19/2023 | 118408 | 201403 | 186209
9 | X126 | P.S. 126 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 1/20/2023 | 7/10/2023 | 9/12/2024 | 592044 | 395447 | 370144
9 | X126 | P.S. 126 - BRONX | SCA CIP | ROOFS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 12/12/2023 | 4/29/2024 | 9/25/2024 | 27014 | 0 | 0
9 | X147 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/15/2023 | 10/16/2023 | 9/22/2023 | 9899 | 16018 | 12505
9 | X147 | I.S. 339 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/4/2023 | 3/5/2024 | 4/4/2024 | 44546 | 62362 | 47196
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 11/21/2018 | 4/10/2019 | 2/11/2020 | 15826 | 64028 | 46404
9 | X148 | FREDERICK DOUGLASS ACADEMY III SECONDARY SCHOOL | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2/11/2020 | 7/13/2020 | 5/14/2021 | 71215 | 120171 | 89178
9 | X148 | I.S. 219 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 8/17/2021 | 1/21/2022 | 2/10/2022 | 67074 | 73513 | 71958
9 | X166 | GRANT AVENUE ELEMENTARY SCHOOL | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 12/3/2021 | 1/18/2022 | 1/13/2022 | 111956 | 159049 | 142435
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Scope | Complete | 2/1/2019 | 6/18/2019 | 1/21/2022 | 60992 | 67606 | 67606
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Design | Complete | 2/2/2022 | 7/5/2022 | 5/11/2022 | 299610 | 282278 | 274885
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/9/2023 | 6/9/2023 | 3/15/2023 | 4440 | 5165 | 5165
9 | X235 | P.S./I.S. 218 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/15/2023 | 9/8/2023 | 5/3/2023 | 19980 | 20659 | 20659
9 | X236 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | SCA CIP | PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 7/25/2023 | 32629 | 70153 | 39666
9 | X236 | GARDEN OF LEARNING AND DISCOVERY PRE-K CENTER | SCA CIP | PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 9/7/2023 | 2/12/2024 | 4/10/2024 | 146829 | 90327 | 81818
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | Scope | Complete | 9/18/2014 | 2/6/2015 | 2/6/2015 | 586154 | 423577 | 407985
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TOWER TERRA COTTA REPLACEMENT / FLOOD ELIMINATION / ROOFS / WINDOWS / INTERIOR SPACES | Design | Complete | 7/29/2016 | 1/3/2017 | 5/15/2017 | 2327215 | 1999734 | 1700302
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADES | Scope | Complete | 11/24/2021 | 8/15/2023 | 9/8/2023 | 20763 | 41886 | 39819
9 | X400 | MORRIS COLLAB HS TECH & HUMAN - X | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADES | Design | Complete | 9/11/2023 | 1/11/2024 | 12/15/2023 | 102871 | 114973 | 98370
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/29/2021 | 9/6/2022 | 10/11/2022 | 35710 | 198939 | 198939
9 | X400 | BRONX INTERNATIONAL - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 10/12/2022 | 2/13/2023 | 12/22/2023 | 177477 | 383958 | 341852
9 | X410 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 1/23/2023 | 5/23/2023 | 3/28/2023 | 11680 | 16689 | 16689
9 | X410 | HS OF BUSINESS - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 3/31/2023 | 9/29/2023 | 8/2/2023 | 52560 | 51366 | 36984
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/30/2022 | 11/16/2022 | 4/3/2024 | 133228 | 189786 | 84577
9 | X460 | BRONX SCHOOL FOR LAW, GOVERNMENT AND JUSTICE | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 7/5/2023 | 11/20/2023 | 11/21/2023 | 30000 | 34155 | 659
9 | X468 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | Scope | Complete | 8/20/2019 | 1/14/2020 | 1/15/2020 | 1150660 | 840988 | 840574
9 | X468 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | Design | Complete | 1/16/2020 | 8/31/2020 | 5/4/2021 | 5177970 | 3131749 | 2519526
9 | X468 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | Construction | Complete | 12/20/2021 | 9/3/2024 | 7/3/2024 | 65299955 | 61772471 | 59258093
9 | X468 | P.S. @ 1302 EDWARD L GRANT HIGHWAY - BRONX | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 12/20/2021 | 9/3/2024 | 7/3/2024 | 9205280 | 6659106 | 5026105
9 | X486 | 3K CENTER @ 1450 PLIMPTON AVENUE - BRONX | 3K | LEASE | Scope | Complete | 11/15/2018 | 12/3/2018 | 12/3/2018 | 250680 | 214584 | 214584
9 | X486 | 3K CENTER @ 1450 PLIMPTON AVENUE - BRONX | 3K | LEASE | Design | Complete | 12/4/2018 | 3/15/2019 | 3/21/2019 | 1128060 | 1142285 | 962882
9 | X486 | 3K CENTER @ 1450 PLIMPTON AVENUE - BRONX | 3K | LEASE | Construction | Complete | 2/20/2023 | 9/3/2023 | 8/14/2024 | 14226090 | 14046262 | 13493977
9 | X486 | 3K CENTER @ 1450 PLIMPTON AVENUE - BRONX | 3K | LEASE | CM,F&E | Complete | 2/20/2023 | 9/3/2023 | 8/14/2024 | 2005440 | 664302 | 1241621
9 | X496 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | Scope | Complete | 6/13/2019 | 11/29/2019 | 12/5/2019 | 1595980 | 1094470 | 1091253
9 | X496 | P.S. @ 2075 WEBSTER AVENUE - BRONX | SCA Capacity | NEW SCHOOL / DEMOLITION OF EXISTING X163 BUILDING | Design | Complete | 12/6/2019 | 6/15/2020 | 10/28/2021 | 7181910 | 5404130 | 3817046
9 | X970 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 2/24/2020 | 7/8/2020 | 11/29/2021 | 90790 | 81337 | 79684
9 | X970 | I.S. 241 - BRONX | SCA CIP | ROOF REPLACEMENT | Design | Complete | 12/8/2021 | 5/11/2022 | 5/10/2022 | 453950 | 369014 | 334825
9 | X970 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 3/22/2022 | 7/20/2022 | 4/12/2022 | 3732 | 3456 | 3456
9 | X970 | I.S. 241 - BRONX | SCA CIP | IPDVS INSTALLATION | Design | Complete | 4/12/2022 | 10/5/2022 | 7/27/2022 | 16793 | 13824 | 13824
9 | XAIN | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | Scope | Complete | 3/10/2021 | 1/13/2022 | 4/11/2022 | 23164 | 87958 | 57331
9 | XAIN | HIGHBRIDGE ADVISORY COUNCIL - BRONX | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / ACS EARLY LEARN PATH OF TRAVEL | Design | Complete | 4/11/2022 | 8/10/2022 | 5/11/2022 | 114030 | 114612 | 24207
10 | X003 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/6/2022 | 2/9/2023 | 10/18/2022 | 4464 | 8700 | 8700
10 | X003 | P.S. 3 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/18/2022 | 4/17/2023 | 2/15/2023 | 20088 | 34800 | 34800
10 | X008 | P.S. 8 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/7/2024 | 12/9/2024 | 8/15/2024 | 4041 | 514 | 514
10 | X008 | P.S. 8 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 3/4/2024 | 8/2/2024 | 7/16/2024 | 33000 | 37282 | 7213
10 | X009 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | Scope | Complete | 1/12/2018 | 5/30/2018 | 6/5/2018 | 233995 | 175679 | 175679
10 | X009 | P.S. 9 - BRONX | SCA CIP | CRACKED MASONRY / PARAPETS / ROOFS | Design | Complete | 11/28/2018 | 5/1/2019 | 4/30/2019 | 935980 | 777989 | 720706
10 | X009 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | Scope | Complete | 4/12/2022 | 8/10/2022 | 9/12/2022 | 62504 | 66335 | 2315
10 | X009 | P.S. 9 - BRONX | SCA CIP | STH-SBHC ROOM CONVERSION / STH-SBHC ELECTRICAL SYSTEMS / INTRUSION ALARM SYSTEM | Design | Complete | 9/26/2022 | 3/13/2023 | 3/31/2023 | 308752 | 599947 | 277314
10 | X009 | P.S. 9 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 3/25/2024 | 8/23/2024 | 8/19/2024 | 60000 | 49909 | 3606
10 | X015 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 3/11/2021 | 7/26/2021 | 10/4/2021 | 48803 | 53202 | 51935
10 | X015 | P.S. 15 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 11/10/2021 | 4/15/2022 | 5/3/2022 | 237462 | 223739 | 220329
10 | X015 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/6/2022 | 2/9/2023 | 10/18/2022 | 5456 | 9058 | 9058
10 | X015 | P.S. 15 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/18/2022 | 4/17/2023 | 2/15/2023 | 24552 | 36231 | 36231
10 | X015 | P.S. 15 - BRONX | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 11/20/2023 | 4/8/2024 | 3/18/2024 | 58500 | 39441 | 6869
10 | X020 | P.S. 20 - BRONX | SCA CIP | HVAC AND BMS UPGRADE / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 5/26/2022 | 10/27/2022 | 1/3/2023 | 310975 | 154253 | 154210
10 | X020 | P.S. 20 - BRONX | SCA CIP | HVAC AND BMS UPGRADE / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 1/13/2023 | 6/15/2023 | 5/12/2023 | 1554876 | 920945 | 795336
10 | X020 | P.S. 20 - BRONX | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 11/30/2021 | 4/18/2022 | 5/12/2022 | 90000 | 85736 | 79051
10 | X020 | X168 SPED - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION / FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 12/6/2021 | 6/2/2022 | 2/23/2022 | 37500 | 40131 | 22131
10 | X023 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/25/2023 | 9/26/2023 | 6/6/2023 | 3690 | 2125 | 2125
10 | X023 | P.S. 23 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/6/2023 | 12/4/2023 | 10/3/2023 | 16605 | 8500 | 8500
10 | X024 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | Scope | Complete | 4/19/2021 | 9/1/2021 | 11/24/2021 | 43398 | 30858 | 30858
10 | X024 | P.S. 24 - BRONX | SCA CIP | EXTERIOR MASONRY / REINFORCING SUPPORT ELEMENTS | Design | Complete | 11/29/2021 | 5/2/2022 | 12/27/2022 | 216989 | 225406 | 164286
10 | X026 | I.S. 390 - BRONX | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 3/7/2023 | 6/5/2023 | 8/9/2023 | 29787 | 45260 | 45260
10 | X032 | P.S. 32 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT: | Scope | Complete | 9/6/2023 | 12/7/2023 | 11/27/2023 | 39758 | 77317 | 942
10 | X034 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/28/2022 | 2/1/2023 | 10/3/2022 | 5181 | 3391 | 3391
10 | X034 | X188 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/3/2022 | 4/3/2023 | 1/11/2023 | 23314 | 13564 | 13564
10 | X037 | P.S. 37 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 4/5/2022 | 9/28/2022 | 7/19/2022 | 24000 | 17454 | 17454
10 | X045 | I.S. 45 - BRONX | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | Complete | 5/17/2022 | 9/30/2022 | 1/27/2023 | 363000 | 278276 | 278276
10 | X046 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Scope | Complete | 8/4/2014 | 12/19/2014 | 12/19/2014 | 112122 | 240930 | 240930
10 | X046 | P.S. 46 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Design | Complete | 7/13/2015 | 12/14/2015 | 6/28/2016 | 558225 | 645125 | 591822
10 | X054 | P.S. 54 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 7/14/2022 | 11/30/2022 | 7/25/2023 | 37560 | 52316 | 50554
10 | X054 | P.S. 54 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 8/23/2023 | 1/29/2024 | 3/21/2024 | 187049 | 194311 | 186977
10 | X054 | P.S. 54 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 6/6/2023 | 12/4/2023 | 10/3/2023 | 24000 | 3772 | 3772
10 | X079 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | Scope | Complete | 4/30/2021 | 8/30/2021 | 7/28/2021 | 13940 | 44784 | 44784
10 | X079 | P.S. 382 - BRONX | SCA CIP | REINFORCE SUPPORT ELEMENTS | Design | Complete | 8/5/2021 | 2/3/2022 | 11/17/2021 | 62730 | 179139 | 179139
10 | X079 | I.S. 447 - BRONX | SCA CIP RESOA | FY19 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 9/5/2019 | 3/5/2020 | 3/10/2020 | 28617 | 25075 | 19131
10 | X079 | SCHOOL FOR ENVIR CITIZEN - BRONX | SCA CIP RESOA | FY21 RESO A SUPPLEMENTAL COOLING / FY21 RESO A ROOM CONVERSION | Design | Complete | 1/20/2022 | 6/20/2022 | 7/22/2022 | 82267 | 92328 | 87759
10 | X080 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/28/2022 | 11/14/2022 | 2/2/2023 | 88790 | 175531 | 174375
10 | X080 | P.S. 280 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/13/2023 | 7/17/2023 | 5/10/2023 | 443950 | 489367 | 404423
10 | X080 | I.S. 80 - BRONX | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 6/28/2024 | 10/31/2024 | 9/6/2024 | 56339 | 72167 | 46597
10 | X081 | P.S. 81 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 2/5/2020 | 7/30/2020 | 5/14/2020 | 27818 | 38788 | 38788
10 | X085 | P.S. 85 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 3/2/2023 | 5/31/2023 | 8/18/2023 | 51736 | 85619 | 85619
10 | X085 | P.S. 85 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 8/18/2023 | 1/8/2024 | 5/14/2024 | 258680 | 177415 | 150076
10 | X085 | P.S. 85 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDELOPMENT | Scope | Complete | 8/4/2023 | 12/6/2023 | 9/1/2023 | 2915 | 5866 | 5866
10 | X085 | P.S. 85 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDELOPMENT | Design | Complete | 9/6/2023 | 1/5/2024 | 5/14/2024 | 13119 | 17666 | 17666
10 | X085 | P.S. 85 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/28/2024 | 10/29/2024 | 7/8/2024 | 3412 | 1029 | 1029
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | Complete | 5/1/2024 | 9/17/2024 | 9/24/2024 | 23061 | 35670 | 5085
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/12/2024 | 6/11/2024 | 6/20/2024 | 5540 | 5540 | 74
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 6/25/2024 | 10/28/2024 | 9/24/2024 | 10473 | 10473 | 296
10 | X085 | P.S. 85 - BRONX | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 6/25/2024 | 10/28/2024 | 9/17/2024 | 60000 | 64133 | 4126
10 | X086 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | Scope | Complete | 3/17/2022 | 8/1/2022 | 1/13/2023 | 108367 | 167122 | 162169
10 | X086 | P.S. 86 - BRONX | SCA CIP | EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS | Design | Complete | 1/18/2023 | 6/20/2023 | 5/9/2023 | 534877 | 452586 | 381514
10 | X086 | P.S. 86 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/8/2024 | 4/8/2024 | 9/26/2024 | 28422 | 41564 | 8805
10 | X086 | P.S. 86 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/3/2024 | 11/1/2024 | 7/9/2024 | 3526 | 1115 | 1115
10 | X091 | P.S. 91 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/18/2023 | 10/4/2023 | 11/1/2023 | 325236 | 248858 | 247293
10 | X091 | P.S. 91 - BRONX | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/8/2023 | 4/12/2024 | 9/18/2024 | 1517765 | 670278 | 342768
10 | X091 | P.S. 91 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 12/5/2023 | 3/8/2024 | 4/9/2024 | 889 | 889 | 889
10 | X094 | P.S. 94 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/17/2024 | 11/15/2024 | 7/23/2024 | 3536 | 626 | 626
10 | X115 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | Scope | Complete | 7/28/2021 | 8/25/2023 | 8/2/2023 | 78240 | 79916 | 79916
10 | X115 | M.S. 363 - BRONX | SCA CIP | SWIMMING POOL / EXTERIOR MASONRY @ X115 / WINDOWS / GYM FLOOR REPLACEMENT | Design | Complete | 8/8/2023 | 12/26/2023 | 1/31/2024 | 391201 | 336675 | 244504
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PLAYGROUNDS | Design | Complete | 8/5/2021 | 1/10/2022 | 5/9/2022 | 154346 | 178140 | 159024
10 | X118 | I.S. 118 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 8/4/2023 | 11/3/2023 | 10/23/2023 | 27634 | 48234 | 48234
10 | X118 | I.S. 118 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 11/1/2023 | 3/21/2024 | 3/26/2024 | 138170 | 109769 | 96857
10 | X118 | I.S. 118 - BRONX | SCA CIP RESOA | FY19 RESO A SUPPLEMENTAL COOLING | Design | Complete | 12/9/2021 | 5/11/2022 | 7/21/2022 | 122580 | 77550 | 75482
10 | X137 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/14/2019 | 6/12/2019 | 3/10/2020 | 22890 | 114350 | 97173
10 | X137 | I.S. 391 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 3/11/2020 | 9/10/2020 | 6/30/2020 | 114450 | 180609 | 154539
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | FY22 RESO A ROOM CONVERSION | Design | Complete | 7/5/2023 | 12/6/2023 | 4/15/2024 | 154815 | 87611 | 72999
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 6/26/2023 | 11/9/2023 | 5/15/2024 | 380596 | 272198 | 216286
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 2/27/2023 | 5/26/2023 | 11/20/2023 | 2220 | 2220 | 2220
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 11/30/2023 | 4/1/2024 | 5/15/2024 | 8881 | 8881 | 8881
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 8/28/2023 | 11/30/2023 | 10/13/2023 | 8070 | 8070 | 0
10 | X137 | M.S./H.S. 225 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 10/20/2023 | 3/5/2024 | 4/15/2024 | 585 | 585 | 0
10 | X137 | I.S. 391 - BRONX | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 7/31/2023 | 1/29/2024 | 10/18/2023 | 24000 | 9267 | 9267
10 | X143 | I.S. 244 - BRONX | SCA CIP RESOA | FY16 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 12/16/2022 | 4/21/2023 | 5/12/2023 | 98731 | 57501 | 53545
10 | X206 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/19/2022 | 1/23/2023 | 9/27/2022 | 2847 | 3373 | 3373
10 | X206 | I.S. 206B - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/27/2022 | 7/20/2023 | 1/11/2023 | 12812 | 13491 | 13491
10 | X206 | I.S. 206B - BRONX | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 2/15/2022 | 5/13/2022 | 8/16/2022 | 66110 | 70319 | 70319
10 | X206 | I.S. 206B - BRONX | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Construction | Complete | 4/14/2023 | 4/12/2024 | 4/11/2024 | 969601 | 706052 | 577122
10 | X206 | I.S. 206B - BRONX | SCA CIP RESOA | FY21 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | CM,F&E | Complete | 4/14/2023 | 4/12/2024 | 4/11/2024 | 269594 | 304822 | 147279
10 | X209 | P.S. 209 - BRONX | SCA CIP | PLAYGROUND SAFETY SURFACE | Scope | Complete | 4/13/2023 | 7/14/2023 | 4/13/2023 | 3336 | 5765 | 0
10 | X209 | P.S. 209 - BRONX | SCA CIP | PLAYGROUND SAFETY SURFACE | Design | Complete | 4/13/2023 | 8/29/2023 | 5/24/2023 | 15010 | 0 | 0
10 | X279 | P.S. 279 - BRONX | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 12/6/2021 | 4/8/2022 | 9/21/2022 | 72203 | 236793 | 233955
10 | X306 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/17/2018 | 3/7/2019 | 9/3/2019 | 172980 | 232592 | 232592
10 | X306 | P.S. 306 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/4/2019 | 2/7/2020 | 5/14/2021 | 864901 | 944641 | 912029
10 | X306 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/20/2022 | 1/24/2023 | 9/29/2022 | 6272 | 3036 | 3036
10 | X306 | P.S. 306 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/29/2022 | 3/30/2023 | 1/11/2023 | 28224 | 12143 | 12143
10 | X306 | P.S. 306 - BRONX | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | Complete | 2/29/2024 | 7/16/2024 | 5/1/2024 | 30000 | 32039 | 31337
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ASPHALT PAVEMENT AT TIBBETT AVE | Scope | Complete | 3/14/2023 | 6/12/2023 | 2/5/2024 | 108500 | 306093 | 306093
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ASPHALT PAVEMENT AT TIBBETT AVE | Design | Complete | 2/20/2024 | 7/5/2024 | 5/16/2024 | 542500 | 180886 | 20292
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/14/2024 | 10/31/2024 | 9/16/2024 | 130463 | 57698 | 37263
10 | X368 | M.S./H.S. 368 - BRONX | SCA CIP RESOA | FY22 RESO A ATHLETIC FIELD UPGRADE | Scope | Complete | 4/28/2022 | 7/29/2022 | 7/20/2022 | 83824 | 83824 | 83824
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | Scope | Complete | 6/18/2019 | 12/16/2019 | 11/20/2019 | 403971 | 363933 | 360892
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / ELECTRICAL SYSTEMS | Design | Complete | 12/18/2019 | 6/15/2020 | 5/15/2020 | 2007396 | 744547 | 740398
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FIRE SPRINKLER SYSTEM | Scope | Complete | 8/10/2023 | 11/9/2023 | 11/8/2023 | 19190 | 49366 | 49366
10 | X430 | M.S./H.S. 342 - BRONX | SCA CIP | FIRE SPRINKLER SYSTEM | Design | Complete | 11/20/2023 | 5/23/2024 | 8/5/2024 | 76759 | 70547 | 63080
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | Scope | Complete | 2/7/2020 | 7/21/2023 | 8/4/2023 | 223330 | 134168 | 134168
10 | X435 | FORDHAM HS FOR THE ARTS - BRONX | SCA CIP | STRUCTURAL ELEMENTS UNDER POOL / PATH OF TRAVEL STRUCTURAL ELEMENTS UNDER POOL / VENTILATION | Design | Complete | 8/30/2023 | 1/5/2024 | 4/11/2024 | 1116650 | 542016 | 364209
10 | X469 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | Scope | Complete | 9/24/2019 | 3/5/2020 | 3/12/2020 | 1153240 | 899738 | 898881
10 | X469 | X000 - BRONX | SCA Capacity | NEW SCHOOL / PLAYGROUND REDEVELOPMENT | Design | Complete | 3/13/2020 | 9/23/2020 | 5/14/2021 | 5189580 | 3233984 | 2894021
10 | X476 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | Scope | Complete | 4/14/2021 | 8/13/2021 | 1/21/2022 | 36500 | 111873 | 107021
10 | X476 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | Design | Complete | 1/21/2022 | 6/13/2022 | 5/10/2022 | 182499 | 272012 | 203468
10 | X476 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | Construction | Complete | 8/15/2022 | 2/5/2024 | 7/24/2024 | 4106226 | 3774362 | 3665006
10 | X476 | BX ENGINEERING & TECH ACADEMY - X | SCA CIP | TENNIS COURT REMEDIATION | CM,F&E | Complete | 8/15/2022 | 2/5/2024 | 7/24/2024 | 255499 | 327202 | 321131
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA Capacity | NEW SCHOOL | Scope | Complete | 7/19/2022 | 12/30/2022 | 1/20/2023 | 1788220 | 903503 | 876551
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA Capacity | NEW SCHOOL | Design | Complete | 1/23/2023 | 8/18/2023 | 5/14/2024 | 8046990 | 1702364 | 1466967
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | Scope | Complete | 1/26/2023 | 1/26/2023 | 1/26/2023 | 42240 | 3480 | 3480
10 | X515 | P.S. @ 3850 REVIEW PLACE - BRONX | SCA CIP | DEMOLITION | Design | Complete | 1/26/2023 | 5/25/2023 | 12/8/2023 | 211200 | 239940 | 157605
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/16/2023 | 1/4/2024 | 4/9/2024 | 225570 | 106066 | 103164
10 | X660 | CROTONA INTERNATIONAL HIGH SCHOOL - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 4/6/2023 | 7/6/2023 | 11/20/2023 | 1354 | 1354 | 1354
10 | X779 | P.S. 315 - BRONX | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 1/18/2023 | 5/11/2023 | 5/5/2023 | 72000 | 57871 | 9307
10 | X826 | P.S. 226 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/16/2024 | 11/14/2024 | 7/23/2024 | 3305 | 564 | 564
10 | X853 | P.S. 59 - BRONX | SCA CIP | ROOFS | Scope | Complete | 7/19/2019 | 12/5/2019 | 11/6/2019 | 21987 | 21606 | 21606
10 | X853 | P.S. 59 - BRONX | SCA CIP | ROOFS | Design | Complete | 11/13/2019 | 4/16/2020 | 5/12/2021 | 109937 | 111763 | 111696
10 | X886 | GIRLS PREPARATORY CHARTER SCHOOL OF THE BRONX II | SCA CIP | HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 12/15/2023 | 5/17/2024 | 5/24/2024 | 72617 | 123897 | 123835
10 | X930 | P.S. 9 - BRONX | SCA CIP | ROOF | Scope | Complete | 1/12/2018 | 5/30/2018 | 6/5/2018 | 18067 | 33365 | 33365
10 | X930 | P.S. 9 - BRONX | SCA CIP | ROOF | Design | Complete | 11/28/2018 | 5/1/2019 | 4/30/2019 | 90336 | 132795 | 98771
11 | X016 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | Scope | Complete | 1/17/2020 | 6/3/2020 | 10/19/2021 | 58202 | 113247 | 113247
11 | X016 | P.S. 16 - BRONX | SCA CIP | EXTERIOR MASONRY / RPZ BACKFLOW PREVENTION DEVICES / PAVED AREA- CONCRETE / FLOOD ELIMINATION / ROOFS | Design | Complete | 10/22/2021 | 3/29/2022 | 3/9/2022 | 281335 | 345203 | 345203
11 | X019 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 6/14/2023 | 10/31/2023 | 11/9/2023 | 71503 | 115650 | 115588
11 | X019 | P.S. 19 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Design | Complete | 11/20/2023 | 4/23/2024 | 5/15/2024 | 348241 | 320416 | 270250
11 | X041 | P.S. 41 - BRONX | SCA CIP RESOA | FY20 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 1/29/2020 | 7/23/2020 | 5/6/2020 | 30000 | 27384 | 27384
11 | X068 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/25/2023 | 9/26/2023 | 6/7/2023 | 3490 | 1618 | 1618
11 | X068 | P.S. 68 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/7/2023 | 12/5/2023 | 10/18/2023 | 15705 | 6474 | 6474
11 | X076 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 10/17/2022 | 5/26/2023 | 4/19/2023 | 15993 | 40243 | 15730
11 | X076 | P.S. 76 - BRONX | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 4/19/2023 | 8/22/2023 | 5/12/2023 | 71969 | 85738 | 51788
11 | X083 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/12/2022 | 9/12/2022 | 6/13/2022 | 5500 | 5541 | 5541
11 | X083 | P.S. 83 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/13/2022 | 12/8/2022 | 12/7/2022 | 24750 | 22162 | 22162
11 | X083 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 6/17/2022 | 11/2/2022 | 3/9/2023 | 120306 | 125177 | 110918
11 | X083 | P.S. 83 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 3/10/2023 | 8/10/2023 | 5/12/2023 | 601528 | 403203 | 351513
11 | X087 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | Scope | Complete | 4/30/2019 | 9/20/2019 | 9/20/2019 | 1096620 | 847375 | 845153
11 | X087 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | Design | Complete | 9/23/2019 | 3/30/2020 | 6/30/2020 | 4934790 | 3182903 | 2489607
11 | X087 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | Construction | Complete | 8/23/2021 | 9/3/2024 | 7/5/2024 | 62233185 | 57999974 | 53221677
11 | X087 | P.S. 87 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK | CM,Art,F&E | Complete | 8/23/2021 | 9/3/2024 | 7/5/2024 | 8772960 | 7031912 | 5214749
11 | X096 | P.S. 96 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/9/2022 | 12/27/2022 | 12/27/2022 | 21983 | 34555 | 27945
11 | X097 | P.S. 97 - BRONX | SCA CIP | ROOM CONVERSION AND ADA WORK IN EXISTING BUILDING (PHASE 3) | Scope | Complete | 6/1/2018 | 11/2/2018 | 5/2/2022 | 17296 | 4607 | 4607
11 | X097 | P.S. 97 - BRONX | SCA CIP | ROOM CONVERSION AND ADA WORK IN EXISTING BUILDING (PHASE 3) | Design | Complete | 5/2/2022 | 5/2/2022 | 5/2/2022 | 63419 | 18426 | 18426
11 | X105 | P.S. 105 - BRONX | SCA Capacity | ADDITION | Scope | Complete | 10/19/2020 | 4/6/2021 | 4/14/2021 | 1067475 | 717767 | 715502
11 | X105 | P.S. 105 - BRONX | SCA Capacity | ADDITION | Design | Complete | 4/15/2021 | 11/9/2021 | 9/16/2022 | 4803640 | 2731631 | 1729503
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-IPDVS WORK / EXISTING BUILDING-FIRE ALARM WORK / EXISTING BUILDING-ELECTRICAL SYSTEMS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/14/2022 | 1/31/2023 | 10/23/2023 | 149604 | 171157 | 171135
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-GYMNASIUM | Scope | Complete | 10/14/2022 | 1/31/2023 | 3/10/2023 | 18206 | 12613 | 12613
11 | X105 | P.S. 105 - BRONX | SCA CIP | EXISTING BUILDING-GYMNASIUM | Design | Complete | 3/15/2023 | 8/30/2023 | 11/21/2023 | 81926 | 54764 | 52258
11 | X106 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 4/11/2023 | 8/25/2023 | 12/20/2023 | 19293 | 57816 | 57816
11 | X106 | P.S. 106 - BRONX | SCA CIP | EXTERIOR MASONRY | Design | Complete | 1/2/2024 | 6/3/2024 | 5/7/2024 | 96467 | 170017 | 130016
11 | X108 | P.S. 108 - BRONX | SCA Capacity | ADDITION | Scope | Complete | 7/1/2019 | 12/2/2019 | 1/16/2020 | 1237400 | 877808 | 849083
11 | X108 | P.S. 108 - BRONX | SCA Capacity | ADDITION | Design | Complete | 1/17/2020 | 6/16/2020 | 5/14/2021 | 5568300 | 2996965 | 2322579
11 | X111 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2/11/2020 | 7/13/2020 | 3/25/2020 | 59720 | 84751 | 84751
11 | X111 | P.S. 111 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 4/2/2020 | 9/1/2020 | 8/12/2020 | 298600 | 397466 | 337733
11 | X111 | P.S. 111 - BRONX | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Scope | Complete | 4/3/2024 | 8/19/2024 | 9/11/2024 | 114324 | 38122 | 19222
11 | X112 | P.S. 112 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 1/23/2024 | 6/6/2024 | 7/12/2024 | 122210 | 615 | 615
11 | X112 | P.S. 112 - BRONX | SCA CIP | ROOFS | Scope | Complete | 1/23/2024 | 6/6/2024 | 7/12/2024 | 107301 | 107301 | 44173
11 | X112 | P.S. 112 - BRONX | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 1/17/2024 | 5/31/2024 | 5/6/2024 | 45000 | 35343 | 14564
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 5/22/2020 | 11/19/2020 | 10/21/2020 | 273270 | 289029 | 289029
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 10/27/2020 | 6/15/2021 | 7/1/2021 | 1366350 | 638855 | 620118
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | AUDITORIUM UPGRADE | Scope | Complete | 10/17/2022 | 2/21/2023 | 2/9/2023 | 15645 | 52390 | 40709
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | AUDITORIUM UPGRADE | Design | Complete | 3/2/2023 | 8/2/2023 | 12/7/2023 | 78227 | 173574 | 166043
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 3/22/2023 | 6/22/2023 | 6/1/2023 | 7065 | 9821 | 9821
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP | PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 6/1/2023 | 10/4/2023 | 12/7/2023 | 31792 | 36745 | 32051
11 | X113 | SCHOOL OF DIPLOMACY | SCA CIP RESOA | FY22 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 4/20/2023 | 8/21/2023 | 5/12/2023 | 182944 | 113519 | 75473
11 | X121 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/25/2019 | 11/26/2019 | 9/25/2019 | 65450 | 95684 | 95684
11 | X121 | P.S. 121 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 10/2/2019 | 3/9/2020 | 3/6/2020 | 327250 | 467096 | 444956
11 | X127 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 8/18/2020 | 1/22/2021 | 11/16/2020 | 96030 | 111571 | 111571
11 | X127 | I.S. 127 - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 11/18/2020 | 4/22/2021 | 2/3/2021 | 480151 | 462070 | 430842
11 | X135 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/8/2021 | 11/23/2021 | 11/5/2021 | 71743 | 84165 | 84165
11 | X135 | I.S. 556 - BRONX | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/1/2021 | 5/4/2022 | 5/12/2022 | 351722 | 297023 | 297023
11 | X142 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | Scope | Complete | 7/22/2021 | 12/23/2021 | 1/14/2022 | 95580 | 103292 | 103292
11 | X142 | I.S. 529 - BRONX | SCA CIP | HEATING PLANT UPGRADE | Design | Complete | 1/14/2022 | 6/16/2022 | 7/12/2022 | 477900 | 840392 | 448464
11 | X142 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 7/26/2021 | 12/10/2021 | 11/18/2021 | 269000 | 312694 | 312694
11 | X142 | I.S. 529 - BRONX | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 12/1/2021 | 5/4/2022 | 5/10/2022 | 1345001 | 828741 | 756023
11 | X142 | BRONX ALLIANCE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/28/2024 | 6/28/2024 | 9/16/2024 | 419 | 419 | 419
11 | X144 | I.S. 144 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 12/5/2023 | 4/22/2024 | 3/13/2024 | 17928 | 35046 | 19323
11 | X144 | I.S. 144 - BRONX | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 3/15/2024 | 8/15/2024 | 9/6/2024 | 71711 | 57085 | 12058
11 | X153 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 3/8/2021 | 7/21/2021 | 11/12/2021 | 255795 | 281991 | 281991
11 | X153 | P.S. 153 - BRONX | SCA CIP | WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / PARAPETS / RTU REPLACEMENT / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/2/2021 | 5/5/2022 | 9/22/2022 | 1265251 | 953177 | 796032
11 | X153 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/4/2022 | 9/1/2022 | 6/6/2022 | 4200 | 2936 | 2936
11 | X153 | P.S. 153 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/6/2022 | 12/1/2022 | 11/30/2022 | 18900 | 11745 | 11745
11 | X160 | P.S. 160 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 6/15/2021 | 11/16/2021 | 11/1/2021 | 20657 | 60318 | 60318
11 | X175 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/27/2022 | 9/27/2022 | 6/15/2022 | 3950 | 5401 | 5401
11 | X175 | P.S. 175 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 17775 | 21602 | 21602
11 | X175 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/19/2022 | 6/2/2023 | 3/14/2023 | 32289 | 131461 | 127626
11 | X175 | P.S. 175 - BRONX | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 3/15/2023 | 12/4/2023 | 4/26/2023 | 158330 | 165443 | 148157
11 | X178 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 1/24/2022 | 6/8/2022 | 8/12/2022 | 68310 | 63318 | 63318
11 | X178 | P.S. 178 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 8/24/2022 | 2/14/2023 | 5/12/2023 | 341550 | 266248 | 248470
11 | X189 | CORNERSTONE ACADEMY FOR SOCIAL ACTION MIDDLE SCHOOL (CASA) | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION | Design | Complete | 8/17/2022 | 2/2/2023 | 3/31/2023 | 36000 | 48749 | 16432
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/24/2022 | 7/22/2022 | 4/12/2022 | 3008 | 3604 | 3604
11 | X362 | ACADEMY FOR SCHOLARSHIP AND ENTR - BRONX | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/12/2022 | 10/5/2022 | 7/27/2022 | 13537 | 14414 | 14414
11 | X415 | BRONXDALE HIGH SCHOOL - BRONX | SCA CIP RESOA | FY24 RESO A KITCHEN UPGRADE / PATH OF TRAVEL RESO A KITCHEN UPGRADE | Design | Complete | 5/14/2024 | 9/12/2024 | 7/26/2024 | 28157 | 41888 | 11584
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 8/5/2020 | 12/4/2020 | 5/28/2021 | 64200 | 92974 | 84452
11 | X425 | BRONX LAB SCHOOL - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 6/8/2021 | 11/15/2021 | 11/23/2021 | 321000 | 324155 | 318758
11 | X425 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 6/9/2022 | 12/5/2022 | 10/25/2022 | 499900 | 349714 | 349635
11 | X425 | X176 SPED - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS / ROOFS / FLOOD ELIMINATION | Design | Complete | 11/8/2022 | 6/12/2023 | 5/8/2023 | 2499499 | 654625 | 654625
11 | X425 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | FY22 RESO A LOCKER ROOM UPGRADE / REINFORCING SUPPORT ELEMENTS / SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Scope | Complete | 5/27/2022 | 1/25/2024 | 12/5/2023 | 283042 | 257302 | 257302
11 | X425 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | FY22 RESO A LOCKER ROOM UPGRADE / REINFORCING SUPPORT ELEMENTS / SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Design | Complete | 12/20/2023 | 5/1/2024 | 5/13/2024 | 1406413 | 633418 | 576326
11 | X426 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | Scope | Complete | 6/29/2018 | 12/28/2018 | 12/11/2018 | 174630 | 478710 | 478710
11 | X426 | HS OF COMPUTERS & TECHNOLOGY - X | SCA CIP | ATHLETIC FIELD / FIELD HOUSE | Design | Complete | 9/17/2019 | 10/2/2020 | 10/5/2020 | 873151 | 1650225 | 1489280
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | Scope | Complete | 3/18/2021 | 8/2/2021 | 1/14/2022 | 195096 | 180335 | 180335
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | EXTERIOR MASONRY / ROOFS / WINDOWS | Design | Complete | 1/18/2022 | 6/17/2022 | 5/11/2022 | 966382 | 590706 | 554000
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 3/10/2022 | 7/25/2022 | 8/30/2022 | 117480 | 103650 | 103650
11 | X455 | HARRY S. TRUMAN HS - X | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 9/6/2022 | 2/27/2023 | 5/9/2023 | 587400 | 421689 | 371688
11 | X456 | HARRY S. TRUMAN HS - X | SCA CIP RESOA | PATH OF TRAVEL RESO A ATHLETIC FIELD / FY22 RESO A ATHLETIC FIELD UPGRADE | Design | Complete | 8/21/2023 | 2/20/2024 | 5/8/2024 | 732000 | 310302 | 310302
11 | X482 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | STANDALONE GYM ANNEX | Scope | Complete | 11/8/2018 | 3/29/2019 | 4/29/2019 | 218660 | 367784 | 367779
11 | X482 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | STANDALONE GYM ANNEX | Design | Complete | 5/1/2019 | 11/25/2019 | 4/21/2020 | 1093300 | 1663437 | 1270816
11 | X482 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | STANDALONE GYM ANNEX | Construction | Complete | 7/6/2021 | 9/28/2022 | 4/18/2024 | 24599250 | 22546579 | 21265504
11 | X482 | BRONX HS FOR THE VISUAL ARTS - BRONX | SCA CIP | STANDALONE GYM ANNEX | CM,F&E | Complete | 7/6/2021 | 9/28/2022 | 4/18/2024 | 1574072 | 1303654 | 1288710
11 | X498 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 5/3/2021 | 9/16/2021 | 7/20/2021 | 28224 | 36508 | 36508
11 | X498 | P.S. / I.S. 498 - BRONX | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | Complete | 8/4/2021 | 1/7/2022 | 12/20/2021 | 137389 | 165125 | 149780
11 | X722 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 11/13/2012 | 4/2/2013 | 3/25/2013 | 162009 | 150673 | 150673
11 | X722 | X721 SPED - BRONX | SCA CIP | EXTERIOR MASONRY WATER PENETRATION / WINDOWS / ROOFS / FLOOD ELIMINATION / PARAPETS | Design | Complete | 5/6/2013 | 10/4/2013 | 2/28/2014 | 633969 | 698888 | 629096
11 | X722 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/3/2022 | 10/3/2022 | 6/16/2022 | 4490 | 3796 | 3796
11 | X722 | X721 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/16/2022 | 12/13/2022 | 12/7/2022 | 20205 | 15186 | 15186
11 | X981 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | Scope | Complete | 6/8/2021 | 10/22/2021 | 1/25/2022 | 94105 | 37807 | 37807
11 | X981 | P.S. 83 - BRONX | SCA CIP | ROOFS / MECHANICAL EQUIPMENT REPLACEMENT | Design | Complete | 2/2/2022 | 7/5/2022 | 1/27/2023 | 470523 | 403996 | 302132
11 | XAPX | WILLIAMSBRIDGE NAACP EARLY CHILDHOOD EDUCATION CEN - BRONX | SCA CIP | ACS EARLY LEARN-LEASE RENOVATION | Scope | Complete | 11/8/2023 | 3/15/2024 | 6/13/2024 | 712 | 18548 | 18548
12 | X006 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 7/11/2019 | 11/26/2019 | 1/31/2020 | 112064 | 214153 | 208232
12 | X006 | P.S. 6 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2/3/2020 | 7/2/2020 | 3/2/2022 | 551088 | 653391 | 640694
12 | X044 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | Scope | Complete | 9/30/2021 | 2/18/2022 | 1/24/2022 | 15435 | 97452 | 97452
12 | X044 | P.S. 44 - BRONX | SCA CIP | WATER PENETRATION @ X044 | Design | Complete | 2/2/2022 | 6/10/2022 | 5/11/2022 | 77175 | 80076 | 80076
12 | X047 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 4/17/2019 | 8/30/2019 | 8/30/2019 | 127200 | 158392 | 158392
12 | X047 | P.S. 47 - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 10/4/2019 | 3/26/2020 | 6/30/2020 | 636000 | 556622 | 543890
12 | X047 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 1/23/2023 | 5/23/2023 | 3/30/2023 | 7040 | 14844 | 2030
12 | X047 | P.S. 47 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 4/10/2023 | 10/11/2023 | 8/2/2023 | 31680 | 38449 | 32674
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Scope | Complete | 6/14/2022 | 10/28/2022 | 1/9/2023 | 58592 | 162079 | 141548
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION | Design | Complete | 1/18/2023 | 6/20/2023 | 5/12/2023 | 289823 | 220610 | 210313
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/12/2020 | 12/14/2020 | 8/21/2020 | 4730 | 2851 | 2851
12 | X050 | FAIRMONT NEIGHBORHOOD SCHOOL | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/21/2020 | 2/17/2021 | 3/31/2021 | 21284 | 11405 | 11405
12 | X057 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/8/2023 | 12/8/2023 | 8/22/2023 | 4300 | 1863 | 1863
12 | X057 | P.S. 57 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/22/2023 | 2/21/2024 | 11/29/2023 | 19350 | 7453 | 7453
12 | X061 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | Scope | Complete | 1/7/2021 | 5/7/2021 | 12/22/2021 | 41250 | 95843 | 95843
12 | X061 | P.S. 61 - BRONX | SCA CIP | COVID VENTILATION | Design | Complete | 12/23/2021 | 5/26/2022 | 8/24/2022 | 206250 | 314354 | 258150
12 | X066 | P.S. 66 - BRONX | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 11/7/2022 | 3/7/2023 | 12/28/2022 | 41808 | 87166 | 78166
12 | X067 | P.S. 67 - BRONX | SCA CIP | KITCHEN ANSUL SYSTEM | Scope | Complete | 2/3/2020 | 6/11/2020 | 10/8/2021 | 12477 | 24972 | 24972
12 | X067 | P.S. 67 - BRONX | SCA CIP | KITCHEN ANSUL SYSTEM | Design | Complete | 10/26/2021 | 5/13/2022 | 10/25/2022 | 56144 | 66926 | 24284
12 | X067 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | Scope | Complete | 10/10/2018 | 5/13/2019 | 3/28/2019 | 319702 | 240815 | 240815
12 | X067 | P.S. 67 - BRONX | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PAVED AREAS- CONCRETE / CAFETERIA FLOOR REPLACEMENT | Design | Complete | 3/28/2019 | 8/12/2019 | 5/17/2019 | 1275345 | 707807 | 594968
12 | X067 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | Scope | Complete | 2/15/2019 | 3/27/2020 | 3/25/2021 | 13687 | 33188 | 27423
12 | X067 | P.S. 67 - BRONX | SCA CIP | AUDITORIUM SEATING / PATH OF TRAVEL AUDITORIUM SEATING | Design | Complete | 4/5/2021 | 8/24/2021 | 1/7/2022 | 61592 | 113028 | 86722
12 | X077 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | Scope | Complete | 4/25/2019 | 2/5/2020 | 2/5/2020 | 1385261 | 1374109 | 1340771
12 | X077 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | Design | Complete | 2/5/2020 | 5/15/2020 | 8/17/2020 | 6233670 | 4290997 | 3758188
12 | X077 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | Construction | Complete | 8/2/2021 | 9/3/2024 | 7/1/2024 | 78613505 | 72497377 | 65905826
12 | X077 | P.S. 196 - BRONX | SCA Capacity | ADDITION / EXISTING SCHOOL RENOVATION WORK (PHASE I) / DEMOLITION (PHASE II) | CM,Art,F&E | Complete | 8/2/2021 | 9/3/2024 | 7/1/2024 | 11082080 | 9101427 | 7662178
12 | X077 | P.S. 195 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/13/2023 | 4/14/2023 | 5/31/2023 | 21800 | 64050 | 63968
12 | X077 | P.S. 195 - BRONX | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 6/6/2023 | 10/23/2023 | 5/1/2024 | 109001 | 121822 | 118685
12 | X077 | P.S. 195 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/4/2023 | 1/9/2024 | 12/21/2023 | 708 | 1412 | 1412
12 | X077 | P.S. 195 - BRONX | SCA CIP | PATH OF TRAVEL- OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 12/28/2023 | 5/30/2024 | 5/1/2024 | 3187 | 5772 | 5647
12 | X084 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/9/2023 | 7/10/2023 | 3/16/2023 | 7180 | 2108 | 2108
12 | X084 | X811 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/16/2023 | 9/11/2023 | 5/2/2023 | 32310 | 8430 | 8430
12 | X092 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/9/2023 | 7/24/2023 | 3/14/2023 | 4880 | 1791 | 1791
12 | X092 | X352 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/14/2023 | 9/7/2023 | 5/2/2023 | 21960 | 7161 | 7161
12 | X098 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Scope | Complete | 2/13/2019 | 6/28/2019 | 2/19/2020 | 89700 | 256871 | 256825
12 | X098 | I.S. 98 - BRONX | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS | Design | Complete | 4/12/2021 | 9/10/2021 | 2/3/2022 | 442641 | 528430 | 506486
12 | X099 | METROPOLITAN HS - BRONX | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/14/2019 | 10/30/2019 | 11/20/2019 | 35134 | 79410 | 77145
12 | X099 | METROPOLITAN HS - BRONX | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / PARAPETS | Design | Complete | 2/16/2021 | 7/16/2021 | 5/14/2021 | 172766 | 181079 | 137187
12 | X099 | METROPOLITAN HS - BRONX | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / PARAPETS | Construction | Complete | 7/12/2021 | 1/2/2023 | 5/9/2024 | 3636326 | 3371254 | 3184080
12 | X099 | METROPOLITAN HS - BRONX | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / PARAPETS | CM,F&E | Complete | 7/12/2021 | 1/2/2023 | 5/9/2024 | 267692 | 529241 | 522888
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 9/24/2020 | 3/2/2021 | 1/12/2021 | 92200 | 87407 | 87407
12 | X129 | I.S. 129 - BRONX | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 1/14/2021 | 8/2/2021 | 12/7/2021 | 461000 | 338707 | 314286
12 | X134 | P.S. 134 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/7/2024 | 12/9/2024 | 9/5/2024 | 4928 | 271 | 271
12 | X134 | P.S. 134 - BRONX | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 7/23/2024 | 1/22/2025 | 9/26/2024 | 240013 | 45718 | 20219
12 | X136 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | Scope | Complete | 8/30/2016 | 2/3/2017 | 10/13/2016 | 134195 | 141969 | 141969
12 | X136 | X186 SPED - BRONX | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / FLOOD ELIMINATION | Design | Complete | 10/26/2016 | 3/31/2017 | 4/26/2017 | 530645 | 521249 | 499912
12 | X136 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 8/10/2021 | 12/28/2021 | 11/30/2021 | 72720 | 101652 | 101652
12 | X136 | X186 SPED - BRONX | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 12/15/2021 | 6/3/2022 | 7/1/2022 | 363600 | 730337 | 335438
12 | X136 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/20/2022 | 4/21/2023 | 1/25/2023 | 7315 | 4102 | 4102
12 | X136 | X186 SPED - BRONX | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/25/2023 | 7/21/2023 | 4/19/2023 | 32918 | 16407 | 16407
12 | X150 | P.S. 150 - BRONX | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/6/2024 | 1/9/2025 | 9/12/2024 | 4788 | 186 | 186
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 12/7/2021 | 5/10/2022 | 9/14/2022 | 59731 | 69247 | 66617
12 | X150 | P.S. 150 - BRONX | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 7/20/2022 | 12/6/2022 | 2/23/2023 | 56743 | 79569 | 79569
12 | X167 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/12/2023 | 10/12/2023 | 9/22/2023 | 12387 | 15695 | 15695
12 | X167 | P.S. 214 - BRONX | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/4/2023 | 3/5/2024 | 4/4/2024 | 55743 | 58478 | 43333
12 | X167 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/22/2020 | 11/20/2020 | 7/27/2020 | 5317 | 3872 | 3872
12 | X167 | P.S. 214 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/27/2020 | 1/21/2021 | 3/30/2021 | 23925 | 15488 | 15488
12 | X193 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/22/2020 | 11/20/2020 | 7/27/2020 | 5214 | 4128 | 4128
12 | X193 | P.S. 211 - BRONX | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/27/2020 | 1/21/2021 | 5/5/2021 | 23461 | 16512 | 16512
12 | X193 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | Scope | Complete | 6/16/2022 | 5/5/2023 | 5/5/2023 | 31639 | 46774 | 41009
12 | X193 | P.S. 211 - BRONX | SCA CIP | STH- SBHC / PATH OF TRAVEL SCHOOL BASED HEALTH CLINIC | Design | Complete | 5/8/2023 | 9/11/2023 | 5/12/2023 | 157666 | 137428 | 93048
12 | X198 | P.S. 212 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/19/2019 | 12/17/2019 | 11/6/2019 | 184250 | 278645 | 278392
12 | X198 | P.S. 212 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND REDEVELOPMENT | Design | Complete | 11/19/2019 | 6/15/2020 | 4/28/2020 | 921250 | 705351 | 703354
12 | X198 | P.S. 212 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND REDEVELOPMENT | Construction | Complete | 6/3/2021 | 5/17/2024 | 12/11/2023 | 20728125 | 18318296 | 18066843
12 | X198 | P.S. 212 - BRONX | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND REDEVELOPMENT | CM,F&E | Complete | 6/3/2021 | 5/17/2024 | 12/11/2023 | 1289749 | 497834 | 497677
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/17/2023 | 5/16/2023 | 2/2/2023 | 4985 | 2362 | 2362
12 | X198 | URBAN SCHOLARS COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/2/2023 | 7/31/2023 | 4/19/2023 | 22433 | 9447 | 9447
12 | X420 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | Scope | Complete | 3/5/2014 | 7/18/2014 | 2/12/2015 | 247379 | 200847 | 189919
12 | X420 | MONROE ACAD FOR VISUAL ARTS - X | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / PARAPETS / ROOFS / WINDOWS | Design | Complete | 8/15/2016 | 1/19/2017 | 4/21/2017 | 982671 | 818508 | 731310
12 | X420 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Scope | Complete | 4/13/2021 | 9/26/2022 | 7/29/2022 | 101545 | 113778 | 102202
12 | X420 | WORLD CULTURES HS - X | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL | Design | Complete | 8/9/2022 | 12/9/2022 | 10/5/2022 | 507289 | 401533 | 339070
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 12/17/2021 | 5/5/2022 | 2/25/2022 | 104750 | 182119 | 147514
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 2/25/2022 | 7/27/2022 | 5/6/2022 | 523751 | 189255 | 189255
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/5/2024 | 7/3/2024 | 3/25/2024 | 3222 | 1478 | 1478
13 | K003 | P.S. 3 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/25/2024 | 9/18/2024 | 8/13/2024 | 14500 | 5910 | 5910
13 | K008 | P.S. 8 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 6/5/2023 | 10/20/2023 | 1/10/2024 | 60000 | 69798 | 59384
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/31/2024 | 5/30/2024 | 3/25/2024 | 4851 | 1387 | 1387
13 | K009 | PUBLIC SCHOOL 9 THE SARAH SMITH GARNET SCHOOL - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/25/2024 | 9/18/2024 | 8/13/2024 | 21827 | 5550 | 5550
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | PUBLIC ADDRESS SYSTEM | Scope | Complete | 4/9/2021 | 7/9/2021 | 7/19/2021 | 15958 | 17916 | 17916
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | PUBLIC ADDRESS SYSTEM | Design | Complete | 8/10/2021 | 1/13/2022 | 2/11/2022 | 71811 | 92025 | 90065
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | PUBLIC ADDRESS SYSTEM | Construction | Complete | 7/11/2022 | 5/6/2023 | 5/5/2023 | 925564 | 820348 | 813203
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | PUBLIC ADDRESS SYSTEM | CM,F&E | Complete | 7/11/2022 | 5/6/2023 | 5/5/2023 | 171549 | 83332 | 83332
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PLAYGROUND RENOVATION / FIRE ALARM SYSTEM | Scope | Complete | 2/11/2022 | 6/28/2022 | 3/22/2023 | 118587 | 215720 | 202065
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PLAYGROUND RENOVATION / FIRE ALARM SYSTEM | Design | Complete | 4/19/2023 | 10/5/2023 | 7/5/2024 | 580177 | 376642 | 339912
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/1/2022 | 11/17/2022 | 1/20/2023 | 82243 | 122239 | 122239
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/31/2023 | 7/3/2023 | 11/16/2023 | 411214 | 333761 | 292730
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/22/2024 | 12/24/2024 | 9/6/2024 | 3959 | 0 | 0
13 | K020 | P.S. 20 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GREEN ROOF | Design | Complete | 2/16/2024 | 7/19/2024 | 9/18/2024 | 423750 | 248025 | 21782
13 | K044 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Scope | Complete | 5/20/2022 | 10/5/2022 | 11/30/2022 | 136640 | 205561 | 179223
13 | K044 | P.S. 44 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Design | Complete | 12/20/2022 | 6/8/2023 | 5/12/2023 | 683200 | 514104 | 365323
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 6/14/2023 | 10/16/2023 | 6/29/2023 | 4240 | 1319 | 1319
13 | K046 | FORT GREENE PREPARATORY ACADEMY - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 6/29/2023 | 12/27/2023 | 9/27/2023 | 19080 | 5277 | 5277
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 6/12/2019 | 10/28/2019 | 9/24/2021 | 124280 | 132066 | 128688
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 10/5/2021 | 4/12/2022 | 8/31/2023 | 621399 | 343420 | 304285
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 9/9/2019 | 1/28/2020 | 1/23/2020 | 12351 | 16570 | 16570
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Design | Complete | 2/5/2020 | 7/7/2020 | 3/1/2021 | 61755 | 156701 | 105355
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 10/20/2023 | 104833 | 177201 | 176092
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 10/26/2023 | 4/1/2024 | 3/19/2024 | 524168 | 369251 | 351106
13 | K054 | P.S. 54 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/18/2024 | 1/22/2025 | 9/25/2024 | 3926 | 0 | 0
13 | K056 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 6/15/2023 | 10/17/2023 | 6/29/2023 | 4000 | 1700 | 1700
13 | K056 | P.S. 56 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 6/29/2023 | 12/27/2023 | 9/27/2023 | 18000 | 6799 | 6799
13 | K056 | I.S. 351 - BROOKLYN | SCA CIP RESOA | FY18 RESO A COURTYARD GREENHOUSE | Design | Complete | 10/31/2018 | 4/5/2019 | 12/13/2019 | 195000 | 144963 | 141589
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Scope | Complete | 6/3/2022 | 10/19/2022 | 12/6/2022 | 132263 | 208408 | 164274
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Design | Complete | 2/6/2023 | 7/25/2023 | 5/15/2024 | 661316 | 474639 | 60074
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/9/2023 | 6/9/2023 | 2/10/2023 | 4873 | 2099 | 2099
13 | K067 | P.S. 67 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/10/2023 | 8/8/2023 | 4/26/2023 | 21929 | 8397 | 8397
13 | K085 | K753 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS | Scope | Complete | 9/14/2021 | 11/21/2022 | 3/6/2023 | 90069 | 151663 | 151663
13 | K085 | K753 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS | Design | Complete | 3/15/2023 | 8/15/2023 | 9/13/2023 | 450345 | 381235 | 351747
13 | K093 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | Scope | Complete | 6/6/2023 | 10/5/2023 | 6/20/2023 | 4580 | 176 | 176
13 | K093 | P.S. 93 - BROOKLYN | SCA CIP | IPDVS NSTALLATION | Design | Complete | 6/20/2023 | 12/15/2023 | 8/30/2023 | 20610 | 705 | 705
13 | K113 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | Scope | Complete | 6/2/2021 | 12/1/2021 | 10/6/2021 | 194245 | 154364 | 154364
13 | K113 | I.S. 113 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PAVED AREAS CONCRETE / WINDOWS | Design | Complete | 10/18/2021 | 6/30/2022 | 4/27/2022 | 961994 | 526576 | 526576
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 4/8/2022 | 10/4/2022 | 7/25/2022 | 8980 | 12612 | 12612
13 | K117 | BROOKLYN COMMUNITY ARTS & MEDIA HIGH SCHOOL (BCAM) - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 7/26/2022 | 1/24/2023 | 12/21/2022 | 40410 | 50447 | 50447
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 1/24/2023 | 6/8/2023 | 11/6/2023 | 61430 | 167289 | 149608
13 | K256 | P.S. 256 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/13/2024 | 12/13/2024 | 8/13/2024 | 4425 | 0 | 0
13 | K258 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/22/2023 | 11/7/2023 | 12/5/2023 | 95880 | 308735 | 261827
13 | K258 | K140 SPED - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 12/14/2023 | 5/16/2024 | 4/30/2024 | 479400 | 777992 | 297209
13 | K265 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/22/2019 | 12/6/2019 | 12/19/2019 | 103017 | 130059 | 130059
13 | K265 | I.S. 265 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/30/2019 | 6/1/2020 | 6/30/2020 | 515089 | 362086 | 350973
13 | K270 | P.S. 270 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/16/2024 | 12/18/2024 | 8/20/2024 | 4221 | 0 | 0
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 5/29/2019 | 10/29/2019 | 8/1/2019 | 58280 | 81169 | 81169
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 8/1/2019 | 1/6/2020 | 2/3/2020 | 291400 | 445239 | 380435
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/15/2023 | 6/15/2023 | 2/17/2023 | 5007 | 2398 | 2398
13 | K282 | P.S. 282 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/17/2023 | 8/15/2023 | 4/26/2023 | 22532 | 9592 | 9592
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 1/17/2020 | 6/18/2020 | 4/14/2020 | 71170 | 106445 | 106445
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 4/15/2020 | 9/15/2020 | 7/31/2020 | 355850 | 392262 | 382491
13 | K287 | P.S. 287 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/10/2024 | 1/13/2025 | 9/13/2024 | 4287 | 0 | 0
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 9/13/2022 | 3/13/2023 | 1/5/2023 | 116173 | 244880 | 111302
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/11/2023 | 7/10/2023 | 5/2/2023 | 580866 | 798016 | 304183
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/6/2023 | 7/5/2023 | 3/9/2023 | 4660 | 2529 | 2529
13 | K305 | I.S. 492- BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/9/2023 | 9/1/2023 | 5/4/2023 | 20970 | 10116 | 10116
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | NYS AUDITORIUM UPGRADE / PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Scope | Complete | 7/30/2019 | 7/8/2020 | 7/22/2020 | 17780 | 36710 | 24210
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | NYS AUDITORIUM UPGRADE / PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Design | Complete | 7/22/2020 | 11/30/2020 | 5/14/2021 | 80010 | 91769 | 80696
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | NYS AUDITORIUM UPGRADE / PATH OF TRAVEL NYS AUDITORIUM UPGRADE | Construction | Complete | 9/15/2021 | 9/14/2022 | 2/9/2023 | 1031240 | 1023380 | 703664
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | NYS AUDITORIUM UPGRADE / PATH OF TRAVEL NYS AUDITORIUM UPGRADE | CM,F&E | Complete | 9/15/2021 | 9/14/2022 | 2/9/2023 | 191292 | 381477 | 379283
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/2/2023 | 10/3/2023 | 6/12/2023 | 4860 | 176 | 176
13 | K307 | P.S. 307 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/12/2023 | 12/8/2023 | 8/30/2023 | 21870 | 705 | 705
13 | K313 | I.S. 527 - BROOKLYN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/17/2022 | 7/15/2022 | 4/13/2022 | 3363 | 2268 | 2268
13 | K313 | I.S. 527 - BROOKLYN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/13/2022 | 10/6/2022 | 7/19/2022 | 15134 | 9072 | 9072
13 | K313 | I.S. 527 - BROOKLYN | SCA CIP | IPDVS FULL CAMERA UPGRADE | Construction | Complete | 2/24/2023 | 12/20/2023 | 12/18/2023 | 195054 | 169832 | 144828
13 | K313 | I.S. 527 - BROOKLYN | SCA CIP | IPDVS FULL CAMERA UPGRADE | CM,F&E | Complete | 2/24/2023 | 12/20/2023 | 12/18/2023 | 251328 | 252574 | 247772
13 | K313 | I.S. 527 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ELECTRICAL SERVICE UPGRADE / ROOFS / FIRE ALARM | Scope | Complete | 11/17/2023 | 4/17/2024 | 7/18/2024 | 377571 | 121381 | 12661
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | Scope | Complete | 2/28/2013 | 5/29/2013 | 7/24/2013 | 77238 | 68602 | 68602
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM / KITCHEN FIRE SUPRESSION SYSTEM | Design | Complete | 8/21/2013 | 2/27/2014 | 9/4/2014 | 300370 | 738707 | 690963
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | Scope | Complete | 4/13/2016 | 8/26/2016 | 2/23/2017 | 367911 | 214730 | 214730
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS / PAVED AREAS CONCRETE | Design | Complete | 5/22/2017 | 10/23/2017 | 3/15/2018 | 1463972 | 940079 | 824864
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 8/1/2017 | 1/4/2018 | 12/11/2018 | 362895 | 249954 | 249954
13 | K430 | BROOKLYN TECH HS - K | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 12/12/2018 | 5/15/2019 | 5/17/2019 | 1451580 | 916008 | 857513
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY13 RESO A AUDITORIUM UPGRADE | Design | Complete | 5/27/2015 | 10/27/2015 | 9/6/2016 | 89709 | 258009 | 251587
13 | K430 | BROOKLYN TECH HS - K | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Design | Complete | 7/9/2019 | 12/10/2019 | 5/28/2020 | 106865 | 132270 | 125883
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | Scope | Complete | 3/18/2013 | 7/17/2013 | 8/23/2013 | 141546 | 308168 | 308168
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WORK REQUIRED TO OBTAIN A C OF O | Design | Complete | 6/5/2015 | 1/11/2016 | 10/28/2016 | 566184 | 593499 | 561481
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/22/2023 | 10/20/2023 | 10/18/2023 | 11111 | 19084 | 19084
13 | K458 | BROOKLYN ACADEMY HS - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/20/2023 | 3/20/2024 | 4/29/2024 | 49997 | 84130 | 61031
13 | K653 | I.S. 653 - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 5/27/2015 | 12/9/2015 | 6/6/2016 | 836600 | 4265 | 4265
13 | K653 | I.S. 653 - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 6/7/2016 | 7/20/2016 | 5/9/2022 | 3764700 | 1099264 | 868719
13 | K653 | I.S. 653 - BROOKLYN | SCA Capacity | NEW SCHOOL | Construction | Complete | 7/11/2022 | 9/3/2025 | 3/1/2024 | 47477050 | 43585446 | 40663158
13 | K653 | I.S. 653 - BROOKLYN | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 7/11/2022 | 9/3/2025 | 3/1/2024 | 6692800 | 3404805 | 3041661
13 | K694 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | Scope | Complete | 4/11/2016 | 7/7/2016 | 6/28/2016 | 71100 | 219229 | 219229
13 | K694 | STEM CENTER @ CLINTON STREET - BROOKLYN | SCA CIP | ROOM CONVERSION | Design | Complete | 6/29/2016 | 12/30/2016 | 3/6/2017 | 355500 | 1015792 | 475295
13 | K743 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 1/26/2016 | 6/9/2016 | 7/22/2016 | 179797 | 97216 | 97216
13 | K743 | ADULT AND CONTINUING EDUCATION | SCA CIP | EXTERIOR MASONRY / LOW VOLTAGE ELECTRICAL SYSTEMS / VENTILATION / ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION | Design | Complete | 3/13/2017 | 8/10/2017 | 5/18/2018 | 698119 | 963788 | 763567
13 | K813 | ALC - FUNDAMENTAL ACADEMY | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 12/22/2023 | 5/9/2024 | 3/13/2024 | 13130 | 16519 | 16519
13 | K813 | ALC - FUNDAMENTAL ACADEMY | SCA CIP | EXTERIOR MASONRY | Design | Complete | 3/15/2024 | 8/15/2024 | 8/2/2024 | 52522 | 47861 | 44012
13 | K831 | DIV. COMPUTER INFO-DATA CNTR - K | SCA CIP | DATA CENTER | Scope | Complete | 1/20/2015 | 5/19/2015 | 6/3/2015 | 407874 | 362965 | 362965
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 6/5/2019 | 9/4/2019 | 8/15/2019 | 10700 | 20719 | 20719
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/4/2019 | 6/8/2020 | 6/30/2020 | 48150 | 85976 | 67443
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/2/2023 | 6/30/2023 | 3/9/2023 | 3140 | 2447 | 2447
13 | K874 | I.S. 340 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/9/2023 | 9/1/2023 | 5/4/2023 | 14130 | 9789 | 9789
14 | K016 | P.S. 16 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/28/2024 | 9/26/2024 | 5/31/2024 | 4830 | 2374 | 2374
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 4/6/2017 | 11/2/2017 | 12/19/2017 | 183712 | 162802 | 162802
14 | K017 | P.S. 17 - BROOKLYN | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 4/25/2018 | 10/25/2018 | 9/30/2022 | 910025 | 549395 | 485039
14 | K017 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 7/27/2023 | 11/28/2023 | 8/2/2023 | 3886 | 3429 | 3429
14 | K017 | I.S. 577 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 12/20/2023 | 17487 | 13718 | 13718
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND UPGRADE | Scope | Complete | 7/8/2022 | 11/23/2022 | 8/21/2023 | 84605 | 158583 | 135690
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / PLAYGROUND UPGRADE | Design | Complete | 8/31/2023 | 2/6/2024 | 1/30/2024 | 417512 | 273743 | 260177
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 12/13/2023 | 12/13/2023 | 12/13/2023 | 1049 | 8420 | 108
14 | K018 | P.S. 18 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 12/13/2023 | 4/12/2024 | 1/30/2024 | 4722 | 432 | 432
14 | K019 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | Scope | Complete | 6/6/2022 | 11/30/2022 | 10/4/2022 | 284352 | 503815 | 465008
14 | K019 | P.S. 414 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND UPGRADE / FY22 RESO A PLAYGROUND UPGRADE / EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / SITE WORK / FLOOD ELIMINATION | Design | Complete | 10/24/2022 | 6/12/2023 | 4/28/2023 | 1412403 | 809156 | 809156
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 8/18/2020 | 1/22/2021 | 1/6/2021 | 71320 | 107204 | 107204
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/8/2021 | 9/30/2021 | 7/2/2021 | 356600 | 402186 | 391997
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/9/2022 | 12/5/2022 | 10/4/2022 | 64303 | 228049 | 190965
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 10/21/2022 | 6/13/2023 | 4/25/2023 | 316912 | 393636 | 386964
14 | K023 | P.S. 23 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/16/2024 | 9/17/2024 | 5/20/2024 | 5190 | 2924 | 2924
14 | K031 | P.S. 31 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 5/13/2019 | 9/26/2019 | 10/1/2019 | 137336 | 148157 | 148157
14 | K031 | P.S. 31 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 10/30/2019 | 4/20/2020 | 5/12/2023 | 686680 | 363580 | 342826
14 | K033 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/26/2022 | 11/21/2022 | 9/26/2022 | 203999 | 239838 | 206822
14 | K033 | K368 SPED - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 9/28/2022 | 6/12/2023 | 4/13/2023 | 1020000 | 364971 | 364792
14 | K033 | K368 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 10/17/2022 | 3/7/2023 | 3/20/2023 | 44520 | 70446 | 58577
14 | K049 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/14/2020 | 1/11/2021 | 9/17/2020 | 4330 | 4718 | 4718
14 | K049 | LYONS COMMUNITY SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/17/2020 | 3/15/2021 | 3/31/2021 | 19483 | 18873 | 18873
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | Scope | Complete | 2/4/2020 | 6/18/2020 | 6/8/2021 | 5860 | 8707 | 8707
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | STRUCTURAL DEFECTS | Design | Complete | 6/11/2021 | 9/30/2021 | 11/17/2021 | 26370 | 116972 | 90964
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 8/13/2020 | 1/19/2021 | 10/16/2020 | 79400 | 83494 | 83494
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 10/19/2020 | 3/24/2021 | 2/5/2021 | 397000 | 334083 | 317342
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 1/10/2023 | 5/25/2023 | 6/14/2023 | 26018 | 32023 | 32023
14 | K050 | J.H.S. 50 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 6/23/2023 | 11/27/2023 | 12/5/2023 | 130091 | 100824 | 88852
14 | K059 | P.S. 59 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 1/4/2024 | 5/20/2024 | 5/24/2024 | 310813 | 97916 | 96324
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | Scope | Complete | 6/25/2018 | 11/8/2018 | 12/18/2018 | 14990 | 29962 | 29962
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WATER INFILTRATION | Design | Complete | 12/18/2018 | 5/21/2019 | 5/14/2021 | 74950 | 160986 | 147157
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/30/2023 | 10/30/2023 | 10/31/2023 | 18927 | 19535 | 18014
14 | K071 | I.S. 71 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/1/2023 | 4/1/2024 | 5/13/2024 | 85170 | 72207 | 69272
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | Scope | Complete | 6/28/2019 | 11/14/2019 | 12/6/2019 | 50683 | 76515 | 74627
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | WATER PENETRATION ALONG PARAPET WALL / OTHER SITEWORK / ROOFS | Design | Complete | 2/28/2020 | 7/29/2020 | 3/1/2022 | 251250 | 258761 | 258761
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 8/5/2020 | 1/8/2021 | 12/22/2020 | 62300 | 93522 | 93522
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/22/2020 | 5/25/2021 | 7/8/2021 | 311500 | 374669 | 360103
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 3/9/2021 | 7/22/2021 | 11/18/2021 | 76638 | 118049 | 116986
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/29/2021 | 5/17/2022 | 9/30/2022 | 383191 | 290720 | 278115
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/10/2023 | 7/11/2023 | 3/20/2023 | 4966 | 2058 | 2058
14 | K084 | P.S. 84 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/20/2023 | 9/13/2023 | 5/2/2023 | 22347 | 8233 | 8233
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 1/9/2020 | 5/26/2020 | 9/14/2021 | 12428 | 100898 | 100898
14 | K110 | P.S. 110 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 11/17/2021 | 4/21/2022 | 12/7/2022 | 62138 | 169980 | 156340
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/21/2023 | 7/20/2023 | 4/3/2023 | 6424 | 2487 | 2487
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/3/2023 | 12/28/2023 | 5/2/2023 | 28908 | 9947 | 9947
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 3/5/2021 | 11/22/2022 | 8/25/2022 | 192109 | 351045 | 349531
14 | K120 | P.S. 120 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/21/2022 | 6/12/2023 | 11/14/2023 | 960550 | 794303 | 737549
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 6/28/2023 | 11/14/2023 | 12/15/2023 | 54028 | 230630 | 203687
14 | K126 | J.H.S. 126 - BROOKLYN | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 12/19/2023 | 5/21/2024 | 5/9/2024 | 267615 | 297835 | 264965
14 | K132 | P.S. 132 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/30/2024 | 11/29/2024 | 9/4/2024 | 4333 | 992 | 992
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | ELECTRICAL SERVICE ROOM | Scope | Complete | 5/30/2019 | 9/30/2019 | 2/5/2020 | 10500 | 43113 | 43113
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | ELECTRICAL SERVICE ROOM | Design | Complete | 2/6/2020 | 7/8/2020 | 10/27/2021 | 52500 | 92379 | 91179
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | FLOOR REPLACEMENT | Scope | Complete | 4/26/2023 | 9/27/2023 | 1/12/2024 | 7115 | 17453 | 17453
14 | K147 | P.S. 147 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/23/2024 | 11/21/2024 | 7/30/2024 | 4171 | 1388 | 1388
14 | K148 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 2/24/2021 | 7/9/2021 | 7/13/2021 | 150490 | 148286 | 148286
14 | K148 | K373 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 7/22/2021 | 1/11/2022 | 10/12/2022 | 752450 | 702154 | 601028
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS | Scope | Complete | 6/4/2019 | 10/3/2019 | 12/18/2019 | 138929 | 156977 | 156961
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS | Design | Complete | 1/14/2020 | 6/15/2020 | 3/30/2021 | 694646 | 431559 | 420404
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/15/2023 | 10/16/2023 | 10/10/2023 | 10583 | 19075 | 17554
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/12/2023 | 3/12/2024 | 4/29/2024 | 47621 | 133465 | 65698
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/13/2023 | 7/12/2023 | 3/21/2023 | 5508 | 1394 | 1394
14 | K157 | P.S. 157 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/2/2023 | 24786 | 5577 | 5577
14 | K196 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Scope | Complete | 8/12/2020 | 12/11/2020 | 2/18/2021 | 35350 | 27177 | 12431
14 | K196 | P.S. 196 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Design | Complete | 3/1/2021 | 8/6/2021 | 9/10/2021 | 169952 | 162528 | 138852
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP | PARAPETS | Scope | Complete | 12/19/2023 | 5/6/2024 | 4/22/2024 | 3207 | 9797 | 5996
14 | K250 | P.S. 250 - BROOKLYN | SCA CIP RESOA | FY19 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Design | Complete | 5/26/2021 | 10/1/2021 | 11/16/2021 | 35239 | 50698 | 50698
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2/7/2023 | 6/23/2023 | 7/31/2023 | 58066 | 78795 | 67295
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/14/2023 | 12/13/2023 | 10/16/2023 | 79440 | 96543 | 95930
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 10/20/2023 | 6/11/2024 | 4/5/2024 | 397197 | 267755 | 264785
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | ANSUL/FIRE SUPPRESSION SYSTEM | Scope | Complete | 9/5/2024 | 9/5/2024 | 9/5/2024 | 22785 | 0 | 0
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/28/2023 | 12/29/2023 | 8/30/2023 | 4154 | 6008 | 6008
14 | K257 | P.S. 257 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/30/2023 | 2/29/2024 | 12/12/2023 | 18693 | 24032 | 24032
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | Scope | Complete | 6/9/2022 | 12/5/2022 | 9/28/2022 | 155844 | 162964 | 126919
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / SITE WORK / WINDOWS | Design | Complete | 10/19/2022 | 6/12/2023 | 4/4/2023 | 775746 | 314872 | 314792
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 9/27/2023 | 1/31/2024 | 10/10/2023 | 4404 | 1263 | 1263
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 10/10/2023 | 4/8/2024 | 12/12/2023 | 19818 | 5053 | 5053
14 | K297 | P.S. 297 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | Complete | 5/8/2024 | 9/24/2024 | 9/13/2024 | 54000 | 68172 | 15074
14 | K319 | P.S. 319 - BROOKLYN | SCA CIP | ROOFS / WINDOWS | Scope | Complete | 8/9/2019 | 12/27/2019 | 3/13/2020 | 33350 | 33064 | 33064
14 | K319 | P.S. 319 - BROOKLYN | SCA CIP | ROOFS / WINDOWS | Design | Complete | 3/13/2020 | 8/12/2020 | 6/30/2020 | 159981 | 167298 | 140636
14 | K319 | P.S. 319 - BROOKLYN | SCA CIP | ROOFS / WINDOWS | Construction | Complete | 1/17/2022 | 7/10/2023 | 5/16/2024 | 3013946 | 2979086 | 2736309
14 | K319 | P.S. 319 - BROOKLYN | SCA CIP | ROOFS / WINDOWS | CM,F&E | Complete | 1/17/2022 | 7/10/2023 | 5/16/2024 | 284228 | 597541 | 594482
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 6/4/2021 | 10/28/2021 | 1/26/2022 | 113560 | 135065 | 135065
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 3/8/2022 | 8/22/2022 | 5/9/2023 | 567800 | 431486 | 335384
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/14/2023 | 7/13/2023 | 3/21/2023 | 6092 | 1913 | 1913
14 | K380 | P.S. 380 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/2/2023 | 27414 | 7651 | 7651
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | SCA CIP | FIRE ALARM SYSTEM | Scope | Complete | 7/22/2021 | 10/21/2021 | 10/4/2022 | 21607 | 63822 | 63822
14 | K650 | WIILIAMSBURG PREP- BROOKLYN | SCA CIP | FIRE ALARM SYSTEM | Design | Complete | 10/20/2022 | 4/26/2023 | 5/8/2023 | 108034 | 159098 | 155868
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 6/16/2022 | 11/1/2022 | 12/28/2022 | 91123 | 141634 | 125354
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/28/2022 | 6/15/2023 | 6/15/2023 | 455615 | 362699 | 312227
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/30/2022 | 11/16/2022 | 12/28/2022 | 33712 | 48840 | 48840
15 | K001 | P.S. 1 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/29/2022 | 6/1/2023 | 6/15/2023 | 164498 | 162269 | 133118
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 6/3/2022 | 9/15/2022 | 9/15/2022 | 1333540 | 909819 | 907169
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 9/16/2022 | 4/5/2023 | 4/28/2023 | 6000930 | 3506239 | 1855029
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 9/8/2022 | 9/8/2022 | 9/8/2022 | 78880 | 64131 | 64131
15 | K004 | I.S. @ 4002 FORT HAMILTON PARKWAY - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 9/21/2022 | 2/14/2023 | 2/24/2023 | 394400 | 194242 | 181509
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/2/2020 | 11/30/2020 | 10/8/2020 | 166640 | 300149 | 300149
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | WINDOWS / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 10/16/2020 | 6/15/2021 | 4/23/2021 | 833202 | 544558 | 543933
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/12/2024 | 5/13/2024 | 3/22/2024 | 4439 | 179 | 179
15 | K010 | P.S. 10 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/22/2024 | 9/17/2024 | 7/16/2024 | 19977 | 717 | 717
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | Scope | Complete | 11/7/2018 | 11/6/2019 | 11/12/2019 | 179240 | 149682 | 149681
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/13/2019 | 5/1/2020 | 4/2/2021 | 896202 | 736770 | 715975
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/13/2023 | 11/13/2023 | 8/2/2023 | 3120 | 2241 | 2241
15 | K015 | P.S. 15 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/8/2023 | 14040 | 8965 | 8965
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | Scope | Complete | 10/16/2018 | 3/6/2019 | 1/22/2019 | 29395 | 24677 | 24677
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | PARAPETS / DOORS | Design | Complete | 1/30/2019 | 7/1/2019 | 5/6/2020 | 132281 | 188960 | 187999
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/18/2023 | 11/16/2023 | 8/2/2023 | 3880 | 1908 | 1908
15 | K024 | P.S. 24 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/8/2023 | 17460 | 7633 | 7633
15 | K027 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 10/18/2018 | 4/18/2019 | 9/11/2019 | 10680 | 18737 | 18737
15 | K027 | SUMMIT ACADEMY CHARTER SCHOOL - K | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 9/25/2019 | 3/25/2020 | 4/13/2020 | 48060 | 51290 | 51290
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/3/2022 | 11/29/2022 | 9/26/2022 | 150072 | 116083 | 105480
15 | K027 | RED HOOK NEIGHBORHOOD SCHOOL - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 9/30/2022 | 6/12/2023 | 4/14/2023 | 750365 | 362850 | 356893
15 | K029 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 5/12/2022 | 9/27/2022 | 11/14/2022 | 158750 | 195865 | 195865
15 | K029 | P.S. 29 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 12/7/2022 | 5/25/2023 | 5/12/2023 | 793750 | 507101 | 452546
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/15/2024 | 7/16/2024 | 4/1/2024 | 4691 | 502 | 502
15 | K038 | P.S. 38 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/1/2024 | 9/25/2024 | 7/16/2024 | 21109 | 2008 | 2008
15 | K051 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/14/2022 | 1/18/2023 | 12/21/2022 | 4120 | 2795 | 2795
15 | K051 | I.S. 51 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/21/2022 | 6/20/2023 | 2/22/2023 | 18540 | 11183 | 11183
15 | K058 | P.S. 58 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 1/18/2022 | 4/22/2022 | 4/8/2022 | 64281 | 94991 | 94991
15 | K088 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | Scope | Complete | 6/14/2021 | 12/13/2021 | 10/20/2021 | 232199 | 144500 | 144500
15 | K088 | I.S. 88 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE | Design | Complete | 11/3/2021 | 6/30/2022 | 4/22/2022 | 1158195 | 465060 | 465060
15 | K094 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | Scope | Complete | 12/23/2021 | 4/22/2022 | 9/12/2022 | 94564 | 85043 | 79908
15 | K094 | P.S. 94 - BROOKLYN | SCA CIP | VENTILATION / FIRE ALARM SYSTEM REPLACEMENT / BMS UPGRADE | Design | Complete | 10/13/2022 | 4/13/2023 | 4/25/2023 | 466664 | 328756 | 300490
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 9/14/2023 | 2/2/2024 | 5/6/2024 | 29520 | 44266 | 42236
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 9/14/2023 | 12/18/2023 | 2/7/2024 | 465 | 465 | 465
15 | K107 | P.S. 107 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 2/9/2024 | 6/12/2024 | 5/6/2024 | 1983 | 1983 | 1983
15 | K154 | P.S. 154 - BROOKLYN | SCA CIP | ROOFS | Scope | Complete | 12/19/2023 | 5/6/2024 | 6/25/2024 | 17385 | 38950 | 5475
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 7/23/2018 | 12/7/2018 | 11/8/2018 | 87734 | 164529 | 138929
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 2/14/2019 | 7/1/2019 | 8/26/2019 | 147899 | 186940 | 186940
15 | K169 | P.S. 169 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 1/15/2020 | 6/16/2020 | 4/29/2022 | 739501 | 488184 | 478997
15 | K172 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | Scope | Complete | 3/5/2019 | 7/18/2019 | 10/2/2020 | 164813 | 255268 | 255268
15 | K172 | P.S. 172 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / PAVED AREAS CONCRETE / WINDOWS | Design | Complete | 12/10/2020 | 5/13/2021 | 4/21/2022 | 816891 | 633471 | 531136
15 | K230 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 10/11/2018 | 3/1/2019 | 4/19/2019 | 127484 | 136740 | 136740
15 | K230 | P.S. 230 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 4/19/2019 | 9/18/2019 | 5/15/2019 | 637422 | 595541 | 546011
15 | K231 | K721 SPED - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 1/5/2024 | 7/18/2024 | 7/12/2024 | 15037 | 29264 | 5499
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | Scope | Complete | 6/17/2022 | 4/25/2023 | 4/28/2023 | 27880 | 39677 | 33678
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | ROOM CONVERSION / PATH OF TRAVEL ROOM CONVERSION | Design | Complete | 5/5/2023 | 9/8/2023 | 5/12/2023 | 136639 | 102774 | 72249
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / PLAYGROUND REDEVELOPMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 9/18/2018 | 4/25/2023 | 4/28/2023 | 58991 | 111588 | 105723
15 | K261 | P.S. 261 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / PLAYGROUND REDEVELOPMENT / TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 5/1/2023 | 9/1/2023 | 2/7/2024 | 294389 | 456098 | 401969
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | Scope | Complete | 3/16/2016 | 3/16/2016 | 3/16/2016 | 231000 | 718501 | 718501
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA CIP | PHASE II WORK | Design | Complete | 3/17/2016 | 8/29/2016 | 4/19/2017 | 924000 | 2596298 | 2556089
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Scope | Complete | 2/6/2023 | 4/17/2023 | 4/10/2023 | 202000 | 189062 | 189062
15 | K280 | EDUCATIONAL CAMPUS @ 500 19 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Design | Complete | 4/11/2023 | 9/19/2023 | 2/16/2024 | 909000 | 490915 | 249171
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/14/2021 | 12/13/2021 | 10/28/2021 | 122827 | 240025 | 217028
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 12/1/2021 | 6/30/2022 | 4/19/2022 | 614136 | 519175 | 516369
15 | K321 | P.S. 321 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 10/18/2022 | 3/8/2023 | 2/14/2023 | 46341 | 62948 | 59875
15 | K347 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Scope | Complete | 1/21/2021 | 5/13/2021 | 5/11/2021 | 423340 | 393953 | 393953
15 | K347 | P.S. @ 763 PRESIDENT STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Design | Complete | 5/12/2021 | 11/12/2021 | 4/11/2022 | 1905030 | 1249045 | 829867
15 | K369 | COY L. COX SCHOOL | SCA CIP | WINDOWS | Scope | Complete | 5/21/2021 | 10/6/2021 | 8/18/2021 | 37780 | 71336 | 71336
15 | K369 | COY L. COX SCHOOL | SCA CIP | WINDOWS | Design | Complete | 9/15/2021 | 2/18/2022 | 1/12/2022 | 188900 | 285346 | 285346
15 | K369 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/16/2022 | 4/19/2023 | 12/27/2022 | 4140 | 3836 | 3836
15 | K369 | COY L. COX SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/27/2022 | 6/23/2023 | 2/22/2023 | 18630 | 15347 | 15347
15 | K447 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | Scope | Complete | 5/28/2021 | 7/16/2021 | 7/15/2021 | 283140 | 233231 | 233231
15 | K447 | 3K CENTER @ 129 VAN BRUNT STREET - BROOKLYN | 3K | LEASE | Design | Complete | 7/16/2021 | 10/7/2021 | 6/7/2022 | 1274130 | 1495093 | 1179675
15 | K460 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | Scope | Complete | 12/21/2018 | 5/9/2019 | 9/24/2019 | 29978 | 74130 | 74097
15 | K460 | SECONDARY SCHOOL FOR LAW - K | SCA CIP | MASONRY | Design | Complete | 10/28/2019 | 4/1/2020 | 5/18/2020 | 149889 | 229906 | 149710
15 | K655 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 10/23/2020 | 2/26/2021 | 3/3/2021 | 5800 | 5567 | 5567
15 | K655 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/3/2021 | 8/25/2021 | 7/14/2021 | 26100 | 22269 | 22269
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 5/18/2017 | 10/19/2017 | 7/18/2017 | 109022 | 165859 | 165859
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/20/2017 | 12/21/2017 | 1/19/2018 | 426177 | 510233 | 491812
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | Scope | Complete | 1/26/2021 | 7/12/2021 | 11/3/2021 | 129522 | 250049 | 241536
15 | K656 | BROOKLYN HS OF THE ARTS - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / ROOFS / COVID VENTILATION | Design | Complete | 11/10/2021 | 4/15/2022 | 5/11/2022 | 639043 | 512647 | 465474
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 5/6/2021 | 9/30/2021 | 11/16/2021 | 2016007 | 1150696 | 1148923
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 9/13/2022 | 9/13/2022 | 9/13/2022 | 68074 | 60578 | 60264
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 9/13/2022 | 4/18/2023 | 7/14/2023 | 340372 | 152065 | 134641
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 7/1/2022 | 8/29/2022 | 7/1/2022 | 105550 | 60915 | 60915
15 | K680 | I.S. @ 46 VERONA STREET - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 7/1/2022 | 11/30/2022 | 12/19/2022 | 527750 | 119480 | 119480
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/28/2022 | 11/14/2022 | 11/16/2022 | 100490 | 99568 | 99568
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 12/9/2022 | 5/12/2023 | 5/12/2023 | 496499 | 311641 | 284259
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/22/2022 | 7/20/2022 | 3/28/2022 | 4700 | 3389 | 3389
15 | K804 | COBBLE HILL SCHL OF AMER. STUD-K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/28/2022 | 9/20/2022 | 7/19/2022 | 21150 | 13556 | 13556
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/26/2022 | 3/1/2023 | 12/23/2022 | 4140 | 5027 | 5027
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/23/2022 | 6/22/2023 | 2/22/2023 | 18630 | 20109 | 20109
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 3/29/2023 | 4/3/2024 | 2/5/2024 | 13581 | 47434 | 46376
15 | K834 | K372 SPED - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 2/5/2024 | 7/23/2024 | 3/14/2024 | 61114 | 42957 | 41876
15 | K834 | K372 SPED - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 11/15/2021 | 4/4/2022 | 10/31/2022 | 49603 | 73118 | 73118
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 12/17/2020 | 4/16/2021 | 6/29/2021 | 21629 | 53170 | 53170
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 6/30/2021 | 12/1/2021 | 11/5/2021 | 108145 | 101835 | 92097
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 11/27/2023 | 4/12/2024 | 6/5/2024 | 96022 | 109001 | 44664
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | Scope | Complete | 11/28/2012 | 4/23/2014 | 6/23/2014 | 176917 | 289253 | 254282
15 | K845 | P.S. 295 - BROOKLYN | SCA CIP | FY13 RESO A GYM UPG / GYM FLOOR / CAFE / GYM FLOOR SUBSTRATE / FLOOD ELIM / FLOORS / PARAPETS / EXT MASONRY / ROOFS | Design | Complete | 12/10/2014 | 5/13/2015 | 8/24/2015 | 672202 | 1193170 | 1121040
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/22/2023 | 9/21/2023 | 6/7/2023 | 4537 | 587 | 587
15 | K845 | I.S. 443 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/7/2023 | 12/5/2023 | 8/30/2023 | 20417 | 2346 | 2346
15 | KBGZ | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Scope | Complete | 3/2/2021 | 8/3/2022 | 2/22/2023 | 23316 | 43607 | 43607
15 | KBGZ | NEVINS DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Design | Complete | 2/28/2023 | 6/30/2023 | 3/31/2023 | 115467 | 178296 | 115172
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | Scope | Complete | 9/17/2020 | 2/23/2021 | 12/9/2020 | 167950 | 160789 | 146789
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL SYSTEMS | Design | Complete | 12/10/2020 | 8/31/2021 | 8/9/2021 | 839750 | 654065 | 595785
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/14/2022 | 10/13/2022 | 6/21/2022 | 4999 | 6697 | 6697
16 | K005 | P.S. 5 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/21/2022 | 12/16/2022 | 12/7/2022 | 22495 | 26788 | 26788
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 5/22/2019 | 10/7/2019 | 4/20/2021 | 113330 | 123282 | 123282
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 7/21/2021 | 1/10/2022 | 10/31/2022 | 566650 | 294218 | 250833
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 1/31/2020 | 7/1/2020 | 4/30/2020 | 68800 | 100167 | 100167
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/4/2020 | 10/2/2020 | 7/22/2020 | 344000 | 404289 | 376518
16 | K021 | P.S. 21 - BROOKLYN | SCA CIP | EXTERIOR MASONRY PERM FIX @ K021 / PARAPETS / ROOFS | Scope | Complete | 5/22/2024 | 10/8/2024 | 9/20/2024 | 127493 | 16591 | 16591
16 | K025 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/28/2020 | 9/25/2020 | 7/2/2020 | 3070 | 7669 | 7669
16 | K025 | P.S. 25 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/2/2020 | 12/30/2020 | 3/30/2021 | 13817 | 30679 | 30679
16 | K035 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/29/2020 | 9/28/2020 | 7/2/2020 | 5300 | 5549 | 5549
16 | K035 | I.S. 35 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/2/2020 | 12/30/2020 | 3/31/2021 | 23850 | 22197 | 22197
16 | K040 | P.S. 40 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/1/2024 | 10/30/2024 | 7/2/2024 | 4457 | 979 | 979
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PAVED AREAS- CONCRETE | Scope | Complete | 7/6/2022 | 11/21/2022 | 5/26/2023 | 87871 | 128464 | 128464
16 | K057 | WHITELAW REID ACADEMY OF ARTS AND BUSINESS - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PAVED AREAS- CONCRETE | Design | Complete | 7/26/2023 | 12/28/2023 | 2/13/2024 | 428097 | 297610 | 283429
16 | K081 | P.S. 81 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/30/2022 | 11/16/2022 | 8/29/2023 | 52171 | 124908 | 111939
16 | K081 | P.S. 81 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 9/18/2023 | 2/22/2024 | 2/15/2024 | 258625 | 65782 | 35588
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/30/2019 | 12/16/2019 | 11/14/2019 | 57772 | 106673 | 106673
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/2/2019 | 5/4/2020 | 5/11/2021 | 285216 | 440733 | 427828
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | TERRACOTTA PANEL REPLACEMENT | Scope | Complete | 8/29/2023 | 1/18/2024 | 11/3/2023 | 11067 | 17082 | 17082
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | TERRACOTTA PANEL REPLACEMENT | Design | Complete | 11/15/2023 | 4/18/2024 | 3/26/2024 | 55335 | 59284 | 48206
16 | K243 | P.S. 243 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/18/2024 | 10/18/2024 | 6/24/2024 | 4416 | 746 | 746
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 4/6/2021 | 9/3/2021 | 6/21/2021 | 89280 | 115764 | 115764
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 6/22/2021 | 11/23/2021 | 11/10/2021 | 446400 | 535274 | 493194
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 4/21/2023 | 9/7/2023 | 5/21/2024 | 92168 | 74585 | 67647
16 | K262 | P.S. 262 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 12/28/2023 | 5/1/2024 | 5/21/2024 | 952 | 9521 | 9521
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 7/17/2019 | 12/3/2019 | 8/8/2022 | 147804 | 142251 | 142251
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 9/16/2022 | 3/24/2023 | 5/9/2023 | 730453 | 500757 | 434193
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/14/2022 | 10/13/2022 | 6/22/2022 | 4721 | 7425 | 7425
16 | K304 | BRIGHTER CHOICE COMMUN SCHL - K | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/22/2022 | 12/19/2022 | 12/19/2022 | 21245 | 32295 | 32295
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 11/1/2022 | 2/3/2023 | 5/15/2023 | 25491 | 98022 | 97422
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | PLAYGROUND UPGRADE | Design | Complete | 5/30/2023 | 10/16/2023 | 2/5/2024 | 127455 | 257076 | 200644
16 | K308 | P.S. 308 - BROOKLYN | SCA CIP | LOW-VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 1/5/2024 | 4/5/2024 | 6/5/2024 | 36006 | 28486 | 28486
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 1/31/2020 | 7/1/2020 | 4/7/2020 | 69310 | 76960 | 76960
16 | K309 | P.S. 309 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 4/8/2020 | 9/8/2020 | 8/12/2020 | 346550 | 351398 | 324598
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | Scope | Complete | 4/21/2022 | 8/5/2022 | 9/13/2022 | 21510 | 30835 | 30835
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | SCIENCE LAB UPGRADE | Design | Complete | 9/28/2022 | 3/6/2023 | 3/3/2023 | 107550 | 136159 | 112065
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/26/2023 | 10/26/2023 | 10/25/2023 | 12302 | 18742 | 17221
16 | K324 | I.S. 267 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/26/2023 | 3/26/2024 | 4/10/2024 | 55361 | 78276 | 63091
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 2/25/2020 | 7/9/2020 | 9/21/2021 | 28730 | 36041 | 30294
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 11/10/2021 | 4/15/2022 | 5/4/2022 | 143650 | 159924 | 159924
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | GYM UPGRADE | Scope | Complete | 1/25/2023 | 5/25/2023 | 5/24/2023 | 32796 | 39707 | 39707
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | GYM UPGRADE | Design | Complete | 7/10/2023 | 11/24/2023 | 2/13/2024 | 163980 | 125662 | 111302
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM UPGRADE | Scope | Complete | 1/25/2023 | 4/25/2023 | 6/28/2023 | 5668 | 16383 | 658
16 | K455 | BOYS & GIRLS HS - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM UPGRADE | Design | Complete | 7/10/2023 | 11/9/2023 | 2/13/2024 | 25507 | 2632 | 2632
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 3/24/2022 | 7/22/2022 | 4/1/2022 | 3510 | 2560 | 2560
16 | K987 | BROOKLYN HIGH SCHOOL FOR LAW AND TECHNOLOGY - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 4/1/2022 | 9/26/2022 | 7/19/2022 | 15795 | 10239 | 10239
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/16/2018 | 3/6/2019 | 2/20/2019 | 133778 | 215574 | 134593
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / CONDENSING UNITS DX COILS REPLACEMENT / VENTILATION / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2/20/2019 | 7/22/2019 | 6/30/2020 | 660659 | 813498 | 691674
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/27/2020 | 9/24/2020 | 6/19/2020 | 2400 | 3747 | 3747
17 | K002 | I.S. 2 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/19/2020 | 12/16/2020 | 12/1/2020 | 10800 | 14989 | 14989
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | Scope | Complete | 10/12/2022 | 3/2/2023 | 1/20/2023 | 22508 | 72272 | 71809
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP | PARAPETS | Design | Complete | 2/1/2023 | 7/5/2023 | 5/9/2023 | 112539 | 186794 | 165466
17 | K006 | P.S. 6 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 7/7/2023 | 12/8/2023 | 11/9/2023 | 33000 | 56924 | 49172
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | Scope | Complete | 7/18/2019 | 12/4/2019 | 12/24/2019 | 53034 | 41789 | 41789
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | PARAPETS / ROOFS | Design | Complete | 12/24/2019 | 5/27/2020 | 6/30/2020 | 265169 | 228772 | 228733
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/15/2023 | 10/16/2023 | 10/12/2023 | 11100 | 18411 | 18411
17 | K022 | P.S. 705 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/12/2023 | 3/12/2024 | 3/19/2024 | 49950 | 64077 | 46999
17 | K061 | I.S. 61 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / DOORS / SIDEWALK ELEVATOR / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / ELECTRICAL UPGRADE / HOT WATER HEATERS / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 10/19/2018 | 3/11/2019 | 1/31/2019 | 762293 | 289920 | 279682
17 | K061 | I.S. 61 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / DOORS / SIDEWALK ELEVATOR / HVAC UPGRADE FOR CLASSROOMS AND PA SPACES / ELECTRICAL UPGRADE / HOT WATER HEATERS / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 2/6/2019 | 7/9/2019 | 5/8/2024 | 3788468 | 3962337 | 2308102
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 12/1/2021 | 4/5/2022 | 1/19/2023 | 139292 | 212612 | 210026
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | ELECTRICAL SYSTEM UPGRADE / FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 1/20/2023 | 6/22/2023 | 5/12/2023 | 691081 | 504817 | 429334
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/30/2024 | 5/29/2024 | 4/2/2024 | 4403 | 4445 | 4445
17 | K091 | P.S. 91 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/2/2024 | 9/26/2024 | 9/25/2024 | 19814 | 17780 | 17780
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2/10/2021 | 7/20/2021 | 9/30/2022 | 2062074 | 1786728 | 1757479
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 2/8/2021 | 3/5/2021 | 3/5/2021 | 18590 | 69518 | 69518
17 | K134 | MEDGAR EVERS COLLEGE PREP SCHOOL ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 3/8/2021 | 5/21/2021 | 7/21/2022 | 92950 | 561279 | 313379
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 11/29/2018 | 4/17/2019 | 8/26/2019 | 86270 | 119282 | 119232
17 | K138 | P.S. 138 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 8/28/2019 | 2/3/2020 | 4/28/2020 | 422009 | 384671 | 368484
17 | K161 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/10/2021 | 12/9/2021 | 10/22/2021 | 170674 | 208878 | 208878
17 | K161 | P.S. 161 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 11/3/2021 | 6/30/2022 | 4/29/2022 | 848576 | 448265 | 448265
17 | K167 | NEW BRIDGES | SCA CIP | COVID VENTILATION | Scope | Complete | 8/28/2020 | 12/28/2020 | 1/25/2021 | 50600 | 86110 | 86110
17 | K167 | NEW BRIDGES | SCA CIP | COVID VENTILATION | Design | Complete | 2/3/2021 | 7/9/2021 | 12/22/2021 | 253000 | 439906 | 313844
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 3/11/2021 | 7/26/2021 | 11/19/2021 | 84670 | 153567 | 153567
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | WATER INFILTRATION @ K189 / EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 12/22/2021 | 5/25/2022 | 5/11/2022 | 423350 | 484818 | 484818
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/20/2020 | 9/18/2020 | 6/19/2020 | 3720 | 4446 | 4446
17 | K189 | P.S. 189 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/19/2020 | 12/16/2020 | 11/25/2020 | 16740 | 17785 | 17785
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM | Scope | Complete | 5/31/2023 | 11/29/2023 | 11/17/2023 | 291793 | 156000 | 152161
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM | Design | Complete | 11/22/2023 | 6/28/2024 | 5/6/2024 | 1454172 | 570680 | 515301
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/14/2024 | 6/13/2024 | 4/19/2024 | 4068 | 3631 | 3631
17 | K191 | P.S. 191 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/19/2024 | 10/16/2024 | 9/25/2024 | 18305 | 14524 | 14524
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 6/9/2023 | 12/8/2023 | 10/6/2023 | 186305 | 235893 | 235620
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION / PARAPETS | Design | Complete | 10/20/2023 | 6/11/2024 | 4/19/2024 | 919057 | 401967 | 399048
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/5/2022 | 4/6/2023 | 12/9/2022 | 4880 | 6355 | 6355
17 | K210 | I.S. 394 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/9/2022 | 6/7/2023 | 3/8/2023 | 21960 | 25417 | 25417
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 7/6/2022 | 11/21/2022 | 8/18/2023 | 55897 | 131961 | 128164
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 9/12/2023 | 2/15/2024 | 3/7/2024 | 269329 | 187712 | 166234
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/31/2024 | 5/30/2024 | 4/3/2024 | 3931 | 0 | 0
17 | K221 | P.S. 221 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/3/2024 | 9/27/2024 | 9/19/2024 | 17689 | 0 | 0
17 | K241 | P.S. 241 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/31/2024 | 5/30/2024 | 4/3/2024 | 4004 | 164 | 164
17 | K241 | P.S. 241 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/3/2024 | 9/27/2024 | 9/19/2024 | 18019 | 656 | 656
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | Scope | Complete | 6/14/2023 | 10/13/2023 | 1/9/2024 | 149220 | 299877 | 143285
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K246 / FIRE ALARM SYSTEM / BMS UPGRADE | Design | Complete | 1/16/2024 | 7/18/2024 | 5/10/2024 | 746100 | 690298 | 320128
17 | K246 | I.S. 246 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 5/19/2023 | 10/5/2023 | 10/20/2023 | 60000 | 75383 | 62986
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/24/2022 | 11/9/2022 | 12/16/2022 | 93351 | 169409 | 163656
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/10/2023 | 6/12/2023 | 5/10/2023 | 462806 | 389897 | 330488
17 | K249 | P.S. 249 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/25/2024 | 10/24/2024 | 8/8/2024 | 4706 | 867 | 867
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/8/2022 | 4/11/2023 | 12/20/2022 | 5000 | 3930 | 3930
17 | K289 | P.S. 289 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/20/2022 | 6/16/2023 | 3/8/2023 | 22500 | 15718 | 15718
17 | K320 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/15/2023 | 12/14/2023 | 11/2/2023 | 129163 | 140229 | 140229
17 | K320 | P.S. 375 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/20/2023 | 4/23/2024 | 4/18/2024 | 636400 | 328263 | 328263
17 | K390 | M.S. 354 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / SECURITY LIGHTING / EXTERIOR DOORS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 7/13/2023 | 11/29/2023 | 1/11/2024 | 274233 | 379221 | 115061
17 | K391 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | Scope | Complete | 6/15/2023 | 10/16/2023 | 10/2/2023 | 67150 | 45066 | 45066
17 | K391 | I.S. 722 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT @ K391 / FIRE ALARM SYSTEM | Design | Complete | 10/17/2023 | 4/22/2024 | 4/25/2024 | 335750 | 318158 | 264391
17 | K398 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/18/2016 | 4/18/2017 | 2/14/2017 | 26400 | 93873 | 93834
17 | K398 | P.S. 398 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | Complete | 7/11/2019 | 1/14/2020 | 12/31/2019 | 132000 | 219425 | 219425
17 | K399 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | Scope | Complete | 1/27/2022 | 11/15/2022 | 11/16/2022 | 96020 | 109410 | 109410
17 | K399 | P.S. 399 - BROOKLYN | SCA CIP | RTU REPLACEMENT / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / STANDALONE DDC CONTROLS | Design | Complete | 11/30/2022 | 5/3/2023 | 5/8/2023 | 465818 | 460738 | 340887
17 | K465 | I.S. 382 - BROOKLYN | SCA CIP | PARAPET AND SIDE OF BUILDING DAMAGE @ K465 / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 6/25/2021 | 11/24/2021 | 1/25/2022 | 601037 | 414185 | 414185
17 | K465 | I.S. 382 - BROOKLYN | SCA CIP | PARAPET AND SIDE OF BUILDING DAMAGE @ K465 / EXTERIOR MASONRY / ROOFS / FLOOD ELIMINATION / WINDOWS | Design | Complete | 1/26/2022 | 6/27/2022 | 5/11/2022 | 3005178 | 1578416 | 1518762
17 | K470 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 6/3/2021 | 12/2/2021 | 10/27/2021 | 382790 | 341612 | 341612
17 | K470 | H.S. 745 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Design | Complete | 11/10/2021 | 6/30/2022 | 5/9/2022 | 1913951 | 752498 | 752498
17 | K474 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | Scope | Complete | 12/4/2019 | 4/7/2020 | 4/7/2021 | 132420 | 169711 | 168334
17 | K474 | NEW BRIDGES | SCA CIP | STANDALONE GYM ANNEX | Design | Complete | 4/14/2021 | 9/14/2021 | 12/15/2021 | 529680 | 1072099 | 784075
17 | K600 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/13/2020 | 9/11/2020 | 6/19/2020 | 4368 | 4197 | 4197
17 | K600 | CLARA BARTON HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/19/2020 | 12/16/2020 | 12/14/2020 | 19657 | 16789 | 16789
17 | K625 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 10/28/2020 | 3/3/2021 | 3/3/2021 | 3532 | 4279 | 4279
17 | K625 | PATHWAYS IN TECHNOLOGY EARLY COLLEGE HS - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 3/3/2021 | 8/25/2021 | 7/14/2021 | 15893 | 17117 | 17117
17 | K877 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 8/5/2019 | 12/20/2019 | 2/19/2020 | 57509 | 78920 | 76423
17 | K877 | K373 SPED - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Design | Complete | 2/19/2020 | 7/20/2020 | 5/14/2021 | 277627 | 329418 | 298959
17 | KASV | MOSDOTH DAY CARE CENTER, INC. | SCA CIP | ACS EARLY LEARN RENEWAL | Scope | Complete | 1/19/2023 | 4/20/2023 | 8/15/2023 | 5065 | 59087 | 51485
17 | KASV | MOSDOTH DAY CARE CENTER, INC. | SCA CIP | ACS EARLY LEARN RENEWAL | Design | Complete | 8/23/2023 | 2/29/2024 | 5/9/2024 | 22793 | 38846 | 38846
17 | KBOR | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 3/2/2021 | 6/30/2021 | 7/2/2021 | 25326 | 47409 | 47409
17 | KBOR | SAINT JOHN'S DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | Complete | 10/1/2021 | 3/28/2022 | 8/9/2022 | 126629 | 101650 | 20001
17 | KMCA | CUNY @ MEDGAR EVERS HS ANNEX - BROOKLYN | SCA Capacity | NEW BUILDING/CUNY CORE & SHELL | Scope | Complete | 7/15/2022 | 10/7/2022 | 9/30/2022 | 879281 | 59966 | 9287
18 | K066 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/7/2022 | 4/10/2023 | 12/23/2022 | 5000 | 4216 | 4216
18 | K066 | P.S. 66 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/23/2022 | 6/22/2023 | 4/4/2023 | 22500 | 17060 | 17060
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/24/2019 | 12/10/2019 | 1/30/2020 | 69590 | 155296 | 155296
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 1/30/2020 | 6/30/2020 | 6/30/2020 | 338340 | 329767 | 328633
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Construction | Complete | 8/10/2021 | 5/1/2023 | 5/15/2024 | 6781385 | 6066979 | 5708407
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | CM,F&E | Complete | 8/10/2021 | 5/1/2023 | 5/15/2024 | 559205 | 625382 | 623202
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2/12/2020 | 7/14/2020 | 5/19/2020 | 77950 | 142599 | 138089
18 | K068 | I.S. 68 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/19/2020 | 10/20/2020 | 11/5/2020 | 389751 | 486280 | 470869
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 3/8/2021 | 7/21/2021 | 8/11/2021 | 59831 | 71708 | 71708
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 9/7/2021 | 2/10/2022 | 4/25/2022 | 287036 | 298790 | 290451
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/28/2024 | 9/26/2024 | 6/5/2024 | 4077 | 732 | 732
18 | K115 | P.S. 115 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 9/15/2023 | 2/5/2024 | 4/10/2024 | 54000 | 58525 | 55863
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | Scope | Complete | 8/21/2020 | 12/21/2020 | 1/27/2021 | 55460 | 73551 | 76506
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM / COVID CLIMATE CONTROL | Design | Complete | 2/2/2021 | 7/9/2021 | 6/29/2021 | 277301 | 399912 | 311104
18 | K208 | P.S. 208 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/30/2024 | 9/30/2024 | 6/5/2024 | 3791 | 768 | 768
18 | K211 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 6/29/2022 | 11/15/2022 | 3/1/2023 | 108440 | 128569 | 128569
18 | K211 | I.S. 211 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 3/2/2023 | 8/17/2023 | 5/12/2023 | 542200 | 446921 | 374863
18 | K219 | P.S. 219 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE / FY21 RESO A SCIENCE LAB UPGRADE | Design | Complete | 2/17/2023 | 6/22/2023 | 5/12/2023 | 225000 | 155927 | 120349
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/9/2023 | 5/9/2023 | 1/25/2023 | 4200 | 3500 | 3500
18 | K235 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/25/2023 | 7/21/2023 | 4/4/2023 | 18900 | 14003 | 14003
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 3/26/2021 | 8/10/2021 | 9/8/2021 | 48428 | 122843 | 122843
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 9/20/2021 | 2/24/2022 | 5/12/2022 | 228254 | 274389 | 256317
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/30/2023 | 5/30/2023 | 2/13/2023 | 4200 | 2820 | 2820
18 | K242 | P.S. 235 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/13/2023 | 8/9/2023 | 4/4/2023 | 18900 | 11279 | 11279
18 | K244 | BROOKLYN SCIENCE AND ENGINEERING ACADEMY | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/1/2023 | 4/30/2024 | 3/20/2024 | 12000 | 11959 | 11959
18 | K268 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/1/2022 | 11/25/2022 | 8/30/2022 | 145999 | 168528 | 132008
18 | K268 | P.S. 268 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 9/29/2022 | 6/12/2023 | 3/15/2023 | 730000 | 388117 | 388117
18 | K272 | P.S. 272 - BROOKLYN | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Design | Complete | 5/19/2023 | 10/3/2023 | 10/16/2023 | 69000 | 73566 | 58368
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | Scope | Complete | 3/12/2018 | 7/10/2018 | 10/16/2018 | 22500 | 24016 | 24016
18 | K279 | P.S. 279 - BROOKLYN | SCA CIP | BACKFLOW PREVENTION DEVICES | Design | Complete | 11/14/2018 | 5/13/2019 | 5/10/2019 | 82500 | 102544 | 101605
18 | K285 | I.S. 285 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES | Scope | Complete | 8/10/2023 | 11/9/2023 | 10/18/2023 | 1784 | 1784 | 1784
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | Scope | Complete | 6/11/2019 | 12/9/2019 | 11/27/2019 | 235000 | 164153 | 164153
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | SWIMMING POOL | Design | Complete | 3/4/2021 | 7/23/2021 | 5/6/2022 | 1175000 | 825775 | 704084
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | LIGHTING UPGRADE | Scope | Complete | 2/22/2022 | 6/22/2022 | 3/28/2022 | 12270 | 2692 | 2692
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | LIGHTING UPGRADE | Design | Complete | 3/28/2022 | 8/25/2022 | 8/25/2022 | 55215 | 10768 | 10768
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | LIGHTING UPGRADE | Construction | Complete | 2/24/2023 | 12/20/2023 | 10/20/2023 | 711654 | 797070 | 739320
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | LIGHTING UPGRADE | CM,F&E | Complete | 2/24/2023 | 12/20/2023 | 10/20/2023 | 131901 | 99314 | 98071
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | CAFETERIA UPGRADE / PATH OF TRAVEL CAFETERIA UPGRADE | Scope | Complete | 1/5/2022 | 12/15/2022 | 1/19/2023 | 22657 | 69755 | 69755
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | CAFETERIA UPGRADE / PATH OF TRAVEL CAFETERIA UPGRADE | Design | Complete | 1/24/2023 | 5/24/2023 | 3/15/2023 | 112151 | 285454 | 281195
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | RESO A- CULINARY ARTS KITCHEN / PATH OF TRAVEL RESO A KITCHEN UPGRADE / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 11/30/2022 | 11/13/2023 | 11/30/2023 | 61605 | 76021 | 70256
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP | RESO A- CULINARY ARTS KITCHEN / PATH OF TRAVEL RESO A KITCHEN UPGRADE / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 11/30/2023 | 2/15/2024 | 4/23/2024 | 307087 | 296311 | 246516
18 | K415 | IT TAKES A VILLAGE ACADEMY - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 3/20/2024 | 6/20/2024 | 7/1/2024 | 496 | 496 | 496
18 | K415 | KURT HAHN EXPED LEARNING SCH - K | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 3/19/2024 | 6/18/2024 | 7/1/2024 | 229 | 229 | 229
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/1/2022 | 11/25/2022 | 9/15/2022 | 211895 | 145873 | 145841
18 | K500 | HS FOR INNOVATION IN AD - BKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 9/28/2022 | 6/12/2023 | 4/27/2023 | 1059470 | 432824 | 432824
18 | K500 | HS FOR MEDICAL PROFESSIONS - K | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 8/31/2023 | 1/2/2024 | 12/6/2023 | 84000 | 68527 | 14287
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | Scope | Complete | 5/23/2019 | 9/23/2019 | 11/27/2019 | 59160 | 55023 | 55023
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP | C OF O / LOW-VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SYSTEMS | Design | Complete | 1/3/2020 | 7/7/2020 | 9/26/2022 | 295800 | 227454 | 207080
18 | K515 | BROOKLYN THEATRE ARTS H.S. - K | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 1/10/2024 | 5/14/2024 | 7/12/2024 | 90000 | 60930 | 52561
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | ROOFS | Scope | Complete | 7/23/2019 | 12/9/2019 | 10/10/2019 | 12790 | 17110 | 17110
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | ROOFS | Design | Complete | 10/22/2019 | 3/26/2020 | 6/8/2020 | 63950 | 80662 | 80614
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | Scope | Complete | 2/25/2020 | 7/24/2020 | 3/25/2021 | 50050 | 44825 | 44825
18 | K818 | DISTRICT OFFICE #18 - BROOKLYN | SCA CIP | BOILER REPLACEMENT / CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / VENTILATION / INTRUSION ALARM | Design | Complete | 6/7/2021 | 12/9/2021 | 12/7/2021 | 234927 | 231062 | 181775
18 | K835 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | Scope | Complete | 2/4/2019 | 7/5/2019 | 9/10/2019 | 40883 | 24498 | 24498
18 | K835 | P.S. 235 - BROOKLYN | SCA CIP | REPLACE (3) ROOF TOP UNITS / ROOFS | Design | Complete | 3/16/2021 | 8/13/2021 | 12/17/2021 | 199691 | 209857 | 120144
18 | K860 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | Scope | Complete | 8/1/2013 | 1/6/2014 | 12/5/2013 | 48840 | 25752 | 25752
18 | K860 | P.S. 219 - BROOKLYN | SCA CIP | BOILER REPLACEMENT | Design | Complete | 1/8/2014 | 6/10/2014 | 10/22/2014 | 195360 | 281516 | 281516
18 | K860 | EAST BKLN COMMUNITY HS - K | SCA CIP | COVID VENTILATION | Scope | Complete | 12/10/2020 | 4/9/2021 | 6/9/2021 | 10487 | 43705 | 43705
18 | K860 | EAST BKLN COMMUNITY HS - K | SCA CIP | COVID VENTILATION | Design | Complete | 6/14/2021 | 11/15/2021 | 10/27/2021 | 52434 | 68933 | 67801
19 | K007 | K004 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/11/2024 | 5/10/2024 | 1/11/2024 | 4063 | 1555 | 1555
19 | K007 | K004 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/20/2024 | 9/13/2024 | 7/16/2024 | 18284 | 6224 | 6224
19 | K013 | P.S. 13 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/18/2024 | 5/16/2024 | 4/2/2024 | 5365 | 1962 | 1962
19 | K013 | P.S. 13 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/2/2024 | 9/26/2024 | 7/16/2024 | 24144 | 7851 | 7851
19 | K065 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | Scope | Complete | 5/25/2023 | 10/12/2023 | 9/26/2023 | 30980 | 99039 | 54259
19 | K065 | ACHIEVEMENT FIRST EAST NEW YORK CHARTER SCHOOL - K | SCA CIP | PERM FIX- EXTERIOR MASONRY @ K065 | Design | Complete | 10/5/2023 | 3/12/2024 | 3/6/2024 | 154902 | 153482 | 107601
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 8/31/2023 | 1/4/2024 | 11/7/2023 | 5690 | 2202 | 2202
19 | K072 | EAST NEW YORK ELEMENTARY SCHOOL OF EXCELLENCE -K | SCA CIP | IPDVS INSTALLATION | Design | Complete | 11/7/2023 | 5/6/2024 | 1/24/2024 | 25603 | 8811 | 8811
19 | K149 | P.S. 149 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/9/2024 | 5/8/2024 | 3/22/2024 | 4062 | 1226 | 1226
19 | K149 | P.S. 149 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/22/2024 | 9/17/2024 | 8/13/2024 | 18281 | 4908 | 4908
19 | K158 | P.S. 158 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/11/2024 | 5/10/2024 | 1/11/2024 | 3924 | 1082 | 1082
19 | K158 | P.S. 158 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2024 | 9/16/2024 | 8/13/2024 | 17660 | 4329 | 4329
19 | K171 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 7/21/2022 | 12/7/2022 | 12/27/2022 | 37670 | 29394 | 29394
19 | K171 | I.S. 171 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 1/4/2023 | 6/6/2023 | 5/3/2023 | 188350 | 116837 | 101446
19 | K174 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 8/29/2023 | 1/2/2024 | 11/7/2023 | 5170 | 1398 | 1398
19 | K174 | BROOKLYN GARDENS ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Design | Complete | 11/7/2023 | 5/6/2024 | 1/24/2024 | 23267 | 5591 | 5591
19 | K190 | P.S. 190 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 9/26/2023 | 1/30/2024 | 9/27/2023 | 5166 | 1424 | 1424
19 | K190 | P.S. 190 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 9/27/2023 | 3/27/2024 | 3/20/2024 | 23248 | 5696 | 5696
19 | K202 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 6/27/2022 | 12/21/2022 | 10/6/2022 | 257257 | 313904 | 304123
19 | K202 | P.S. 202 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | Complete | 10/19/2022 | 6/26/2023 | 5/3/2023 | 1286286 | 406613 | 406613
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 9/18/2019 | 2/6/2020 | 5/4/2021 | 28328 | 94277 | 74538
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 5/13/2021 | 10/14/2021 | 2/7/2022 | 141640 | 213461 | 193056
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/5/2023 | 5/5/2023 | 1/13/2023 | 4395 | 4630 | 4630
19 | K213 | P.S. 213 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/13/2023 | 7/12/2023 | 4/5/2023 | 19776 | 18521 | 18521
19 | K214 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2/6/2019 | 9/3/2019 | 11/15/2019 | 154000 | 157200 | 157200
19 | K214 | P.S. 214 - BROOKLYN | SCA CIP | AUDITORIUM SEATING / FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 1/23/2020 | 7/9/2020 | 5/10/2022 | 770000 | 721250 | 721070
19 | K218 | I.S. 218 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 8/14/2023 | 1/2/2024 | 10/27/2023 | 12668 | 25452 | 25061
19 | K218 | I.S. 218 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 10/30/2023 | 4/3/2024 | 3/13/2024 | 57008 | 39295 | 36540
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | Scope | Complete | 6/7/2019 | 10/23/2019 | 9/1/2021 | 112240 | 261298 | 260119
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / FLOOD ELIMINATION / ROOFS / AIR CONDENSING UNIT | Design | Complete | 9/29/2021 | 3/7/2022 | 5/9/2024 | 561200 | 686351 | 490688
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/1/2023 | 6/1/2023 | 2/6/2023 | 7639 | 4973 | 4973
19 | K224 | P.S. 224 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/6/2023 | 8/2/2023 | 5/3/2023 | 34375 | 19894 | 19894
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 9/17/2021 | 2/7/2022 | 1/26/2022 | 104244 | 170619 | 170619
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 2/23/2022 | 8/9/2022 | 12/7/2022 | 521220 | 489955 | 395148
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/15/2024 | 8/14/2024 | 4/19/2024 | 4155 | 1430 | 1430
19 | K273 | P.S. 273 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/19/2024 | 10/16/2024 | 9/11/2024 | 18697 | 5719 | 5719
19 | K292 | I.S. 292 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/7/2023 | 11/22/2023 | 11/20/2023 | 54000 | 146024 | 146024
19 | K292 | I.S. 292 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 11/21/2023 | 4/24/2024 | 5/6/2024 | 270000 | 276921 | 271106
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 1/10/2023 | 5/25/2023 | 6/5/2023 | 69582 | 92418 | 85060
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 6/21/2023 | 12/8/2023 | 8/29/2024 | 347914 | 198282 | 102106
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/30/2023 | 10/30/2023 | 11/1/2023 | 11700 | 19375 | 19375
19 | K302 | LIBERTY AVENUE MIDDLE SCHOOL | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/2/2023 | 4/2/2024 | 4/30/2024 | 52650 | 84361 | 68306
19 | K302 | VISTA ACADEMY - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SCIENCE LAB UPGRADES / FY20 RESO A SCIENCE LAB UPGRADES | Design | Complete | 10/13/2021 | 12/30/2021 | 2/11/2022 | 57000 | 89411 | 66471
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | Scope | Complete | 6/2/2022 | 11/28/2022 | 9/23/2022 | 140809 | 214285 | 180017
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / SITE WORK | Design | Complete | 9/27/2022 | 6/12/2023 | 4/19/2023 | 702158 | 474528 | 474528
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/17/2024 | 8/16/2024 | 4/24/2024 | 4992 | 1407 | 1407
19 | K306 | P.S. 306 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/24/2024 | 10/21/2024 | 9/11/2024 | 22464 | 5626 | 5626
19 | K328 | P.S. 328 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/17/2024 | 8/16/2024 | 5/1/2024 | 4249 | 1215 | 1215
19 | K328 | P.S. 328 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/1/2024 | 10/28/2024 | 9/11/2024 | 19122 | 4859 | 4859
19 | K345 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/22/2018 | 9/20/2018 | 10/19/2018 | 84019 | 104874 | 104874
19 | K345 | P.S. 345 - BROOKLYN | SCA CIP | WATER INFILTRATION / EXTERIOR MASONRY / WINDOWS | Design | Complete | 12/18/2018 | 3/11/2019 | 9/10/2019 | 380332 | 278763 | 278763
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 3/2/2021 | 7/15/2021 | 11/8/2021 | 128939 | 108064 | 108064
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/9/2021 | 4/14/2022 | 5/13/2022 | 635011 | 395830 | 395830
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 9/22/2023 | 1/26/2024 | 10/24/2023 | 5074 | 1371 | 1371
19 | K346 | P.S. 346 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 10/24/2023 | 4/22/2024 | 12/20/2023 | 22833 | 5485 | 5485
19 | K346 | I.S. 452 | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 9/12/2023 | 1/18/2024 | 11/29/2023 | 60000 | 71996 | 59451
19 | K420 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | Scope | Complete | 2/22/2022 | 6/21/2022 | 6/24/2022 | 6362 | 30398 | 30398
19 | K420 | BROOKLYN LAB SCHOOL - BROOKLYN | SCA CIP | ENY IPDVS CAMERA INSTALLATION | Design | Complete | 11/3/2022 | 5/3/2023 | 5/3/2023 | 23326 | 17831 | 11739
19 | K420 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | SCA CIP | ACCESSIBLE RAMP / ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 1/27/2023 | 6/23/2023 | 8/29/2023 | 1229210 | 965934 | 940179
19 | K420 | THE URBAN ASSEMBLY SCHOOL FOR COLLABORATIVE HEALTHCARE | SCA CIP | ACCESSIBLE RAMP / ELECTRIFICATION/HEAT PUMP SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEMS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 10/5/2023 | 5/15/2024 | 5/13/2024 | 6146050 | 408567 | 202852
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP | ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ANSUL SYSTEMS / FIRE ALARM SYSTEM | Scope | Complete | 6/20/2023 | 12/18/2023 | 11/2/2023 | 670392 | 389157 | 359636
19 | K435 | PERFORMING ARTS AND TECH. HS - K | SCA CIP | ROOFS / WINDOWS / PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ANSUL SYSTEMS / FIRE ALARM SYSTEM | Design | Complete | 12/27/2023 | 7/1/2024 | 5/13/2024 | 3346390 | 828385 | 828301
19 | K435 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Scope | Complete | 11/19/2021 | 6/30/2022 | 5/12/2022 | 16893 | 338976 | 22217
19 | K435 | WORLD ACAD FOR COMMUNITY HEALTH-K | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB UPGRADE | Design | Complete | 5/13/2022 | 9/26/2022 | 10/7/2022 | 83405 | 117015 | 72988
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | Scope | Complete | 3/9/2023 | 10/6/2023 | 10/25/2023 | 549000 | 703978 | 700626
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | FIELD HOUSE / ATHLETIC FIELD | Design | Complete | 10/30/2023 | 5/15/2024 | 5/15/2024 | 2745000 | 1708694 | 1154133
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | Scope | Complete | 10/25/2023 | 10/25/2023 | 10/25/2023 | 19252 | 21678 | 2626
19 | K436 | HIGH SCHOOL FOR CIVIL RIGHTS - K | SCA CIP | EARLY DEMO PACKAGE | Design | Complete | 10/25/2023 | 2/29/2024 | 4/8/2024 | 96262 | 86865 | 10658
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/27/2020 | 11/23/2020 | 10/22/2020 | 282728 | 351779 | 350973
19 | K615 | E NY VOC HS OF TRANSIT TECH.-K | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/3/2020 | 6/15/2021 | 7/1/2021 | 1405112 | 743393 | 743393
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/23/2023 | 10/23/2023 | 10/18/2023 | 15100 | 21756 | 21756
19 | K660 | WILLIAM MAXWELL VOC HS - K | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 11/14/2023 | 4/15/2024 | 5/15/2024 | 75500 | 81902 | 71393
19 | K848 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/16/2018 | 3/6/2019 | 2/8/2019 | 48184 | 44140 | 44140
19 | K848 | P.S. 149 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/8/2019 | 7/11/2019 | 5/8/2019 | 183794 | 135312 | 135226
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | Scope | Complete | 10/25/2022 | 1/27/2023 | 7/20/2023 | 53682 | 69479 | 69477
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | ELEVATOR MODERNIZATION / FIRE ALARM SYSTEM REPLACEMENT / ELECTRICAL SYSTEMS | Design | Complete | 8/2/2023 | 2/7/2024 | 4/17/2024 | 250136 | 531157 | 171626
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/21/2022 | 3/24/2023 | 12/6/2022 | 3697 | 3217 | 3217
19 | K857 | K036 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/6/2022 | 6/2/2023 | 4/5/2023 | 16638 | 12866 | 12866
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 4/9/2021 | 7/9/2021 | 8/3/2021 | 12644 | 25329 | 17555
19 | KBDA | URBAN STRATEGIES DAY CARE CENTER SITE 1 | SCA CIP | PATH OF TRAVEL | Scope | Complete | 5/26/2023 | 9/25/2023 | 9/1/2023 | 1445 | 0 | 0
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 6/29/2020 | 9/28/2020 | 9/2/2020 | 17354 | 80447 | 80447
20 | K048 | P.S. 48 - BROOKLYN | SCA CIP | PLAYGROUNDS / PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 11/25/2020 | 4/14/2021 | 4/14/2021 | 85416 | 169187 | 163817
20 | K053 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/1/2021 | 10/12/2021 | 10/15/2021 | 1189920 | 907422 | 788469
20 | K053 | P.S. @ 280 SENATOR STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 10/18/2021 | 4/1/2022 | 5/11/2022 | 5354640 | 2539707 | 1638277
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 12/13/2017 | 5/16/2018 | 3/20/2018 | 111330 | 100483 | 100483
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 3/23/2018 | 8/22/2018 | 7/31/2018 | 445320 | 464738 | 460208
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/6/2022 | 11/30/2022 | 9/23/2022 | 218830 | 250669 | 248988
20 | K062 | I.S. 62 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 9/27/2022 | 6/12/2023 | 4/27/2023 | 1094151 | 491760 | 491760
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2024 | 7/1/2024 | 4/4/2024 | 2934 | 2040 | 2040
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/4/2024 | 9/30/2024 | 9/25/2024 | 13205 | 8158 | 8158
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 7/11/2022 | 11/25/2022 | 1/5/2023 | 48384 | 56685 | 45874
20 | K069 | P.S. 69 - BROOKLYN | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 4/10/2024 | 9/11/2024 | 8/23/2024 | 75000 | 34883 | 2337
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 11/1/2022 | 4/14/2023 | 4/13/2023 | 1274220 | 720341 | 720280
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 4/14/2023 | 11/30/2023 | 5/1/2024 | 5733990 | 1074092 | 893559
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 1/26/2023 | 1/26/2023 | 1/26/2023 | 72660 | 615 | 615
20 | K082 | I.S. @ 6315 14 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 1/26/2023 | 7/5/2023 | 10/17/2023 | 363300 | 181747 | 177680
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 10/12/2023 | 3/1/2024 | 4/23/2024 | 31559 | 128346 | 119366
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/28/2024 | 7/29/2024 | 4/19/2024 | 4429 | 3370 | 3370
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/19/2024 | 10/16/2024 | 9/25/2024 | 19929 | 13481 | 13481
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2/12/2020 | 4/10/2020 | 3/26/2020 | 41257 | 239176 | 236141
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Construction | Complete | 6/21/2021 | 3/17/2022 | 6/12/2024 | 605104 | 561212 | 401336
20 | K102 | P.S. 102 - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 6/21/2021 | 3/17/2022 | 6/12/2024 | 41257 | 96186 | 91804
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | Scope | Complete | 9/22/2016 | 7/26/2023 | 4/19/2023 | 239660 | 239958 | 239552
20 | K104 | P.S. 104 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / COVID VENTILATION / COVID LOW VOLTAGE ELECTRICAL SYSTEMS / FLOOD ELIMINATION | Design | Complete | 4/20/2023 | 9/21/2023 | 5/9/2023 | 1198300 | 853628 | 625470
20 | K112 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 6/18/2019 | 11/1/2019 | 12/31/2019 | 105581 | 165197 | 163449
20 | K112 | P.S. 112 - BROOKLYN | SCA CIP | WATER INFILTRATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / ROOFS | Design | Complete | 1/8/2020 | 6/9/2020 | 6/30/2020 | 521856 | 418412 | 384584
20 | K127 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | Scope | Complete | 6/30/2017 | 12/6/2021 | 10/28/2021 | 262426 | 409386 | 409386
20 | K127 | P.S. 127 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / PHASE 3 VOLUNTARY ADA/ROOM CONVERSION WORK / PARAPETS / WINDOWS | Design | Complete | 11/18/2021 | 6/30/2022 | 4/26/2022 | 1293602 | 1484874 | 1266334
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/5/2023 | 10/20/2023 | 10/17/2023 | 48516 | 65151 | 64117
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | Complete | 10/24/2023 | 3/28/2024 | 8/13/2024 | 222536 | 126267 | 119901
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/28/2018 | 11/26/2019 | 11/13/2019 | 29171 | 115406 | 104262
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLANYC PLAYGROUND REDEVELOPMENT | Design | Complete | 12/4/2019 | 5/21/2020 | 5/20/2020 | 118252 | 403105 | 402855
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 5/3/2021 | 7/2/2021 | 5/12/2021 | 4680 | 154 | 154
20 | K163 | P.S. 748 - BROOKLYN | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Design | Complete | 10/16/2023 | 3/20/2024 | 2/28/2024 | 30000 | 5476 | 5476
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Scope | Complete | 1/27/2021 | 5/27/2021 | 12/1/2021 | 67750 | 95933 | 95883
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Design | Complete | 12/2/2021 | 5/2/2022 | 8/31/2022 | 338750 | 354035 | 319053
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/14/2022 | 2/16/2023 | 12/21/2022 | 3769 | 6321 | 6321
20 | K164 | P.S. 164 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/21/2022 | 6/20/2023 | 4/4/2023 | 16961 | 25284 | 25284
20 | K176 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/15/2021 | 12/14/2021 | 10/4/2021 | 204217 | 260162 | 235144
20 | K176 | P.S. 176 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 10/12/2021 | 6/30/2022 | 4/6/2022 | 1017869 | 489339 | 489339
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2/6/2020 | 6/22/2020 | 11/3/2021 | 23126 | 64572 | 64572
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | FLOOD ELIMINATION | Design | Complete | 11/5/2021 | 4/12/2022 | 5/13/2022 | 115630 | 146980 | 133464
20 | K179 | P.S. 179 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/15/2024 | 9/16/2024 | 5/21/2024 | 4979 | 2455 | 2455
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | Scope | Complete | 2/11/2020 | 9/13/2021 | 11/3/2021 | 233776 | 239594 | 231377
20 | K180 | P.S. 180 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / FLOOD ELIMINATION | Design | Complete | 11/8/2021 | 4/28/2022 | 9/30/2022 | 1164456 | 663960 | 575773
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/15/2021 | 12/1/2021 | 2/3/2022 | 61398 | 123584 | 123584
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 2/3/2022 | 7/6/2022 | 5/16/2022 | 297421 | 322620 | 311323
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | CLASSROOM FLOORING / PATH OF TRAVEL CLASSROOM FLOORING | Scope | Complete | 3/21/2023 | 2/27/2024 | 12/12/2023 | 23456 | 28112 | 18868
20 | K185 | P.S. 185 - BROOKLYN | SCA CIP | CLASSROOM FLOORING / PATH OF TRAVEL CLASSROOM FLOORING | Design | Complete | 12/13/2023 | 4/12/2024 | 4/11/2024 | 114871 | 60544 | 32308
20 | K186 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/2/2020 | 9/30/2020 | 7/10/2020 | 2597 | 7310 | 7310
20 | K186 | P.S. 186 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/10/2020 | 1/6/2021 | 5/5/2021 | 11687 | 29243 | 29243
20 | K192 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/2/2022 | 1/6/2023 | 10/4/2022 | 3371 | 10076 | 10076
20 | K192 | P.S. 192 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 10/4/2022 | 4/4/2023 | 4/4/2023 | 15170 | 40306 | 40306
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 2/1/2017 | 6/16/2017 | 9/8/2017 | 119212 | 111733 | 111733
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 10/11/2017 | 3/16/2018 | 1/31/2018 | 476847 | 506066 | 467258
20 | K200 | P.S. 200 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/23/2024 | 9/24/2024 | 5/29/2024 | 4375 | 2509 | 2509
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | GYM FLOOR REPLACEMENT | Scope | Complete | 6/29/2023 | 10/31/2023 | 11/15/2023 | 18216 | 17588 | 2392
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | GYM FLOOR REPLACEMENT | Design | Complete | 12/7/2023 | 4/24/2024 | 5/31/2024 | 85010 | 57160 | 9568
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM FLOOR REPLACEMENT | Scope | Complete | 10/27/2023 | 2/1/2024 | 1/11/2024 | 7615 | 7615 | 15
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP | PATH OF TRAVEL GYM FLOOR REPLACEMENT | Design | Complete | 1/12/2024 | 5/15/2024 | 5/31/2024 | 22709 | 22709 | 59
20 | K201 | I.S. 201 - BROOKLYN | SCA CIP RESOA | FY18 RESO A ROOM CONVERSION | Design | Complete | 11/28/2018 | 4/29/2019 | 8/22/2019 | 113900 | 199923 | 179697
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 1/19/2024 | 4/18/2024 | 3/25/2024 | 22834 | 29001 | 28903
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/24/2023 | 9/25/2023 | 6/16/2023 | 4223 | 630 | 630
20 | K205 | P.S. 205 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/16/2023 | 12/14/2023 | 8/30/2023 | 19003 | 2519 | 2519
20 | K223 | I.S. 223 - BROOKLYN | SCA CIP | DAMAGED STEEL BEAM AT THE MAIN ENTRANCE #1 | Scope | Complete | 5/28/2015 | 9/25/2015 | 10/15/2015 | 8724 | 13816 | 13816
20 | K223 | I.S. 223 - BROOKLYN | SCA CIP | DAMAGED STEEL BEAM AT THE MAIN ENTRANCE #1 | Design | Complete | 2/17/2016 | 5/31/2016 | 10/17/2016 | 31989 | 97809 | 71791
20 | K229 | P.S. 229 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 5/15/2023 | 9/29/2023 | 9/27/2023 | 60000 | 54630 | 42135
20 | K259 | I.S. 259 - BROOKLYN | SCA CIP RESOA | FY23 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 4/27/2023 | 9/27/2023 | 8/25/2023 | 66000 | 91198 | 21036
20 | K264 | P.S. 264 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 7/17/2023 | 12/18/2023 | 2/16/2024 | 30000 | 35395 | 8468
20 | K314 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | Scope | Complete | 1/10/2023 | 6/9/2023 | 4/25/2023 | 102004 | 94780 | 93891
20 | K314 | P.S. 503 - BROOKLYN | SCA CIP | CHILLER REPLACEMENT / AHU REPLACEMENT / BMS UPGRADE | Design | Complete | 5/15/2023 | 10/17/2023 | 11/7/2023 | 501798 | 650002 | 351794
20 | K322 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 1/6/2020 | 6/3/2020 | 6/3/2020 | 1215600 | 1273535 | 1245759
20 | K322 | I.S. @ 650 86 STREET - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 6/4/2020 | 1/7/2021 | 1/7/2021 | 5470200 | 4719461 | 4276995
20 | K331 | I.S. 30 - BROOKLYN | SCA CIP RESOA | RESO A LIBRARY UPGRADE | Design | Complete | 11/21/2023 | 4/9/2024 | 4/5/2024 | 30000 | 34519 | 32626
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 6/6/2023 | 6/6/2023 | 6/6/2023 | 40607 | 114398 | 45021
20 | K337 | P.S. @ 8802 5 AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 6/13/2023 | 9/29/2023 | 11/8/2023 | 203037 | 87519 | 70531
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/16/2024 | 9/10/2024 | 9/10/2024 | 2139680 | 434939 | 373411
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | EARLY DEMO WORK-TANK REMOVAL | Scope | Complete | 4/15/2024 | 4/15/2024 | 4/15/2024 | 7427 | 284 | 284
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA Capacity | EARLY DEMO WORK-TANK REMOVAL | Design | Complete | 4/16/2024 | 5/20/2024 | 5/20/2024 | 29708 | 1135 | 1135
20 | K382 | H.S. @ 425-447 OVINGTON AVENUE - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 4/15/2024 | 4/15/2024 | 4/15/2024 | 127577 | 38225 | 38225
20 | K464 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | Scope | Complete | 9/21/2021 | 4/4/2022 | 4/4/2022 | 235540 | 284437 | 284437
20 | K464 | K000 - BROOKLYN | SCA Lease Site Improvement | LEASE / GYMATORIUM ACCESSIBILITY | Design | Complete | 4/4/2022 | 5/31/2022 | 8/16/2022 | 1059930 | 674759 | 533245
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 5/31/2019 | 10/15/2019 | 12/13/2019 | 54000 | 46070 | 46070
20 | K485 | TELECOM. ARTS & TECH. HS - K | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | Complete | 1/14/2020 | 6/15/2020 | 5/11/2021 | 270000 | 247422 | 247422
20 | K490 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 7/9/2019 | 10/7/2019 | 2/12/2020 | 30510 | 61315 | 61315
20 | K490 | FORT HAMILTON HS - K | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2/12/2020 | 8/13/2020 | 6/3/2021 | 152550 | 273584 | 271097
20 | K490 | FORT HAMILTON HS - K | SCA CIP | REPLACE 6' FIRE DOMESTIC WATER MAIN VALVES | Scope | Complete | 6/4/2019 | 8/5/2019 | 7/12/2019 | 8314 | 2293 | 2293
20 | K490 | FORT HAMILTON HS - K | SCA CIP | REPLACE 6' FIRE DOMESTIC WATER MAIN VALVES | Design | Complete | 7/12/2019 | 11/12/2019 | 8/27/2021 | 37411 | 69871 | 68642
20 | K490 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | Scope | Complete | 6/15/2021 | 10/15/2021 | 10/27/2021 | 37080 | 142242 | 142242
20 | K490 | FORT HAMILTON HS - K | SCA CIP | WASTE SYSTEM | Design | Complete | 12/8/2021 | 5/2/2022 | 5/11/2022 | 185400 | 293166 | 287635
20 | K490 | FORT HAMILTON HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / IDA CLIMATE CONTROL / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES / IDA POOL BOILER / IDA ELECTRICAL SYSTEMS | Scope | Complete | 1/31/2022 | 5/31/2022 | 6/13/2023 | 269669 | 303265 | 298564
20 | K490 | FORT HAMILTON HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / IDA CLIMATE CONTROL / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES / IDA POOL BOILER / IDA ELECTRICAL SYSTEMS | Design | Complete | 6/14/2023 | 11/16/2023 | 4/9/2024 | 1339243 | 655872 | 620027
20 | K490 | FORT HAMILTON HS - K | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Scope | Complete | 12/11/2023 | 3/13/2024 | 3/8/2024 | 10712 | 22492 | 22492
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/30/2022 | 11/16/2022 | 6/1/2023 | 296709 | 316715 | 312909
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 6/12/2023 | 11/14/2023 | 12/12/2023 | 1477044 | 679169 | 651816
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | Scope | Complete | 1/12/2021 | 9/22/2022 | 8/25/2022 | 178605 | 241469 | 227495
20 | K505 | FRANKLIN D. ROOSEVELT HS - K | SCA CIP | COVID VENTILATION / STH SBHC / FIRE ALARM SYSTEM REPLACEMENT / CLIMATE CONTROL / PATH OF TRAVEL STH SBHC | Design | Complete | 8/26/2022 | 12/28/2022 | 4/5/2023 | 892900 | 779201 | 556697
20 | K668 | PRE-K CENTER @ 412 63 STREET - BROOKLYN | PRE-K | LEASE | Scope | Complete | 11/10/2016 | 2/22/2017 | 2/22/2017 | 142794 | 67386 | 67386
20 | K668 | PRE-K CENTER @ 412 63 STREET - BROOKLYN | PRE-K | LEASE | Design | Complete | 8/8/2017 | 11/22/2017 | 8/8/2024 | 642574 | 655057 | 629396
20 | K676 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/19/2020 | 8/11/2020 | 8/11/2020 | 1339880 | 1383637 | 1353330
20 | K676 | P.S. @ 6312 13 AVENUE - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 8/12/2020 | 3/19/2021 | 4/9/2021 | 6029460 | 5418189 | 5074329
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 2/5/2024 | 6/20/2024 | 7/22/2024 | 24271 | 32690 | 23790
20 | K807 | P.S. 163 - BROOKLYN | SCA CIP RESOA | FY22 RESO A GYMNASIUM UPGRADE | Design | Complete | 9/6/2022 | 1/25/2023 | 2/1/2023 | 59301 | 59977 | 58416
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | Scope | Complete | 9/5/2019 | 1/24/2020 | 6/22/2021 | 115935 | 142083 | 139366
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | FACADE / WINDOWS / PARAPETS | Design | Complete | 7/12/2021 | 12/13/2021 | 1/25/2022 | 572050 | 334896 | 334896
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/19/2022 | 11/17/2022 | 8/4/2022 | 5380 | 1486 | 1486
21 | K043 | I.S. 98 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/4/2022 | 2/2/2023 | 1/11/2023 | 24210 | 5941 | 5941
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/20/2021 | 10/5/2021 | 12/16/2022 | 55740 | 118880 | 106378
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/18/2024 | 7/17/2024 | 4/10/2024 | 4495 | 2543 | 2543
21 | K090 | P.S. 90 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/10/2024 | 10/4/2024 | 8/22/2024 | 20228 | 10171 | 10171
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2/3/2020 | 7/2/2020 | 5/19/2020 | 125407 | 120818 | 120818
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ELECTRICAL SYSTEMS / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 5/20/2020 | 10/21/2020 | 8/3/2020 | 609827 | 437473 | 437473
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 3/8/2024 | 7/24/2024 | 7/22/2024 | 27996 | 65259 | 22104
21 | K095 | P.S. 95 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE / FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 3/1/2022 | 6/1/2022 | 10/4/2022 | 196467 | 103816 | 96698
21 | K096 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 5/28/2020 | 11/24/2020 | 10/8/2020 | 198872 | 272439 | 272439
21 | K096 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 10/16/2020 | 6/15/2021 | 4/27/2021 | 986690 | 505708 | 496677
21 | K096 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Construction | Complete | 8/3/2021 | 8/1/2024 | 8/1/2024 | 21536856 | 19755955 | 18380793
21 | K096 | I.S. 96 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | CM,F&E | Complete | 8/3/2021 | 8/1/2024 | 8/1/2024 | 1449656 | 1171266 | 1155469
21 | K097 | P.S. 97 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / EXISTING BUILDING WORK | Scope | Complete | 5/9/2017 | 3/21/2018 | 2/21/2018 | 129190 | 140729 | 140729
21 | K097 | P.S. 97 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / EXISTING BUILDING WORK | Design | Complete | 2/21/2018 | 6/18/2018 | 2/4/2020 | 602780 | 642668 | 620376
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 5/7/2019 | 9/20/2019 | 11/4/2019 | 127710 | 137712 | 132120
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 11/13/2019 | 5/1/2020 | 11/19/2021 | 638550 | 567046 | 566096
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/23/2023 | 5/22/2023 | 1/31/2023 | 4120 | 2728 | 2728
21 | K099 | P.S. 99 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/31/2023 | 7/27/2023 | 4/4/2023 | 18540 | 10914 | 10914
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/14/2020 | 11/16/2020 | 10/16/2020 | 211376 | 379580 | 375299
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 10/29/2020 | 6/15/2021 | 7/1/2021 | 1053403 | 645275 | 626976
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Scope | Complete | 8/4/2020 | 12/4/2020 | 2/10/2021 | 39980 | 52579 | 52579
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM | Design | Complete | 2/17/2021 | 7/16/2021 | 8/31/2021 | 199900 | 199966 | 138973
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/25/2023 | 5/24/2023 | 2/3/2023 | 4000 | 2519 | 2519
21 | K100 | P.S. 100 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/3/2023 | 8/1/2023 | 4/4/2023 | 18000 | 10077 | 10077
21 | K101 | P.S. 101 - BROOKLYN | SCA CIP RESOA | RESO A IPDVS SYSTEM | Design | Complete | 5/16/2023 | 11/13/2023 | 10/18/2023 | 14657 | 3638 | 3638
21 | K121 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/20/2022 | 11/18/2022 | 8/4/2022 | 4260 | 1263 | 1263
21 | K121 | P.S. 121 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/4/2022 | 2/2/2023 | 1/11/2023 | 19170 | 5052 | 5052
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 4/8/2022 | 10/4/2022 | 8/25/2022 | 11980 | 31424 | 31424
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 8/26/2022 | 2/27/2023 | 2/23/2023 | 59900 | 125691 | 125691
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 5/26/2022 | 9/27/2022 | 2/22/2023 | 44224 | 35644 | 35644
21 | K128 | P.S. 128 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 3/3/2023 | 8/3/2023 | 5/11/2023 | 221120 | 125181 | 111956
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | Scope | Complete | 1/26/2021 | 5/26/2021 | 1/5/2022 | 69210 | 63370 | 63370
21 | K153 | P.S. 153 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / COVID ELECTRICAL UPGRADE | Design | Complete | 1/6/2022 | 7/11/2022 | 4/4/2023 | 346050 | 323682 | 253530
21 | K177 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 1/18/2021 | 5/18/2021 | 5/12/2021 | 38000 | 54826 | 54826
21 | K177 | P.S. 177 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 5/18/2021 | 10/19/2021 | 10/7/2021 | 190000 | 104229 | 94101
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 1/29/2021 | 5/28/2021 | 2/9/2022 | 48200 | 130163 | 130163
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 2/9/2022 | 7/8/2022 | 9/7/2022 | 241000 | 241790 | 208542
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2/14/2020 | 11/22/2022 | 10/27/2022 | 199005 | 237655 | 237655
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/2/2022 | 4/7/2023 | 3/10/2023 | 990021 | 1135584 | 715937
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/19/2024 | 8/20/2024 | 4/25/2024 | 5815 | 4145 | 4145
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/25/2024 | 10/22/2024 | 8/22/2024 | 26166 | 16579 | 16579
21 | K188 | P.S. 188 - BROOKLYN | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 10/26/2021 | 3/31/2022 | 7/13/2022 | 86564 | 65511 | 65511
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/14/2023 | 12/13/2023 | 10/6/2023 | 135720 | 107428 | 107428
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/9/2023 | 6/28/2024 | 4/29/2024 | 678600 | 228967 | 228481
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/15/2023 | 10/17/2023 | 7/3/2023 | 3920 | 1790 | 1790
21 | K199 | P.S. 199 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/3/2023 | 12/29/2023 | 10/18/2023 | 17640 | 7162 | 7162
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/15/2021 | 12/14/2021 | 10/28/2021 | 241601 | 317367 | 316455
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 11/17/2021 | 6/30/2022 | 4/29/2022 | 1208001 | 552352 | 552352
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/17/2023 | 4/17/2023 | 4/24/2023 | 21878 | 57514 | 57514
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 4/25/2023 | 9/11/2023 | 10/31/2023 | 109392 | 125351 | 119571
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/13/2022 | 4/14/2023 | 1/6/2023 | 3400 | 4733 | 4733
21 | K209 | P.S. 209 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/6/2023 | 7/5/2023 | 4/4/2023 | 15300 | 18933 | 18933
21 | K216 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | Scope | Complete | 8/4/2020 | 12/4/2020 | 1/29/2021 | 54940 | 85152 | 85152
21 | K216 | P.S. 216 - BROOKLYN | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL / COVID FIRE ALARM SYSTEM | Design | Complete | 2/2/2021 | 7/9/2021 | 7/9/2021 | 274700 | 326223 | 239166
21 | K226 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/19/2022 | 4/20/2023 | 1/10/2023 | 3940 | 5119 | 5119
21 | K226 | P.S. 226 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/10/2023 | 7/7/2023 | 4/4/2023 | 17730 | 20479 | 20479
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Scope | Complete | 6/6/2023 | 12/5/2023 | 10/10/2023 | 240689 | 225611 | 222440
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS | Design | Complete | 10/31/2023 | 6/28/2024 | 4/18/2024 | 1195757 | 345413 | 345413
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/13/2021 | 11/10/2021 | 7/19/2021 | 4160 | 5651 | 5651
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/19/2021 | 1/14/2022 | 12/22/2021 | 18720 | 22606 | 22606
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 5/9/2022 | 2/2/2023 | 4/30/2024 | 241280 | 204322 | 181856
21 | K228 | I.S. 228 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 5/9/2022 | 2/2/2023 | 4/30/2024 | 236304 | 227718 | 152607
21 | K238 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/2/2023 | 6/2/2023 | 2/3/2023 | 4444 | 7306 | 7306
21 | K238 | P.S. 238 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/3/2023 | 8/1/2023 | 5/3/2023 | 19997 | 29225 | 29225
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 5/31/2022 | 11/23/2022 | 9/26/2022 | 270000 | 197865 | 185913
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 9/28/2022 | 6/12/2023 | 4/26/2023 | 1350000 | 386176 | 385788
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/18/2023 | 5/17/2023 | 1/24/2023 | 5467 | 7590 | 7590
21 | K239 | I.S. 239 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/24/2023 | 7/20/2023 | 5/3/2023 | 24599 | 30359 | 30359
21 | K253 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | Scope | Complete | 11/5/2019 | 3/6/2020 | 3/6/2020 | 1078540 | 768510 | 768510
21 | K253 | P.S. 253 - BROOKLYN | SCA Capacity | ADDITION | Design | Complete | 3/9/2020 | 9/1/2020 | 5/11/2021 | 4853430 | 2852384 | 2463512
21 | K253 | P.S. 253 - BROOKLYN | SCA CIP | EXISTING BUILDING RENOVATION WORK | Scope | Complete | 6/3/2021 | 12/13/2021 | 2/9/2022 | 33418 | 65914 | 65914
21 | K253 | P.S. 253 - BROOKLYN | SCA CIP | EXISTING BUILDING RENOVATION WORK | Design | Complete | 2/15/2022 | 8/4/2022 | 3/26/2024 | 167092 | 184442 | 168699
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 7/8/2022 | 11/23/2022 | 8/8/2023 | 148170 | 212313 | 212313
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 8/16/2023 | 1/22/2024 | 4/1/2024 | 740850 | 633306 | 473821
21 | K281 | I.S. 281 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 9/14/2021 | 11/4/2021 | 1/14/2022 | 60605 | 61677 | 60302
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2023 | 6/29/2023 | 3/8/2023 | 3793 | 1915 | 1915
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/8/2023 | 8/31/2023 | 4/26/2023 | 17068 | 7659 | 7659
21 | K288 | P.S. 288 - BROOKLYN | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 10/11/2022 | 3/16/2023 | 3/21/2023 | 97500 | 88374 | 83475
21 | K303 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/22/2022 | 11/7/2022 | 1/5/2023 | 119977 | 249570 | 242172
21 | K303 | I.S. 303 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 1/18/2023 | 6/20/2023 | 5/9/2023 | 589908 | 489475 | 411741
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/15/2023 | 5/13/2024 | 3/20/2024 | 30000 | 11340 | 11340
21 | K303 | R. CARSON SCL OF COASTAL ST-K | SCA CIP RESOA | RESO A ROOM CONVERSIONS/PARTITIONING / PATH OF TRAVEL RESO A ROOM CONVERSIONS/PARTITIONING | Design | Complete | 10/19/2023 | 2/26/2024 | 9/20/2024 | 79218 | 56120 | 36764
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/7/2022 | 11/22/2022 | 6/29/2023 | 73554 | 182895 | 182895
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 7/24/2023 | 12/26/2023 | 12/18/2023 | 363605 | 357639 | 264311
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2023 | 6/29/2023 | 3/8/2023 | 3784 | 1633 | 1633
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/8/2023 | 8/31/2023 | 4/26/2023 | 17028 | 6529 | 6529
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Design | Complete | 9/17/2021 | 11/8/2021 | 11/22/2021 | 62727 | 61457 | 61457
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Construction | Complete | 8/26/2022 | 6/21/2023 | 6/21/2023 | 920004 | 512716 | 442357
21 | K329 | P.S. 329 - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | CM,F&E | Complete | 8/26/2022 | 6/21/2023 | 6/21/2023 | 62727 | 58557 | 57600
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Scope | Complete | 2/28/2022 | 7/18/2022 | 7/18/2022 | 1554220 | 1292430 | 1222007
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA Capacity | NEW SCHOOL | Design | Complete | 7/19/2022 | 3/3/2023 | 3/3/2023 | 6993990 | 4474860 | 4121562
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 5/3/2022 | 5/3/2022 | 5/3/2022 | 21847 | 19313 | 19313
21 | K358 | JOHN DEWEY ANNEX - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 5/4/2022 | 8/12/2022 | 10/18/2022 | 109235 | 56691 | 56691
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 5/28/2019 | 8/26/2019 | 2/18/2020 | 10270 | 37651 | 37651
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2/18/2020 | 8/18/2020 | 7/8/2022 | 51350 | 239766 | 102165
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 7/7/2022 | 11/22/2022 | 3/14/2023 | 19702 | 56015 | 56015
21 | K370 | K370 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 3/23/2023 | 8/23/2023 | 10/18/2023 | 98512 | 133249 | 44141
21 | K400 | INTERNATIONAL HIGH SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 4/8/2021 | 8/6/2021 | 4/26/2021 | 5600 | 6499 | 6499
21 | K400 | INTERNATIONAL HIGH SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 4/26/2021 | 10/20/2021 | 9/29/2021 | 25200 | 25997 | 25997
21 | K400 | INTERNATIONAL HIGH SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | Construction | Complete | 5/9/2022 | 2/2/2023 | 4/30/2024 | 324800 | 307728 | 259689
21 | K400 | INTERNATIONAL HIGH SCHOOL - K | SCA CIP | IPDVS CAMERA INSTALLATION | CM,F&E | Complete | 5/9/2022 | 2/2/2023 | 4/30/2024 | 341579 | 322590 | 215488
21 | K400 | LEADERS HIGH SCHOOL - K | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY21 RESO A LIBRARY UPGRADE | Design | Complete | 2/11/2022 | 6/28/2022 | 5/9/2022 | 104081 | 112966 | 112966
21 | K406 | MIDWOOD HS - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / IDA PAVED AREAS- BLACKTOP / IDA HEATING PLANT UPGRADE | Scope | Complete | 4/6/2022 | 7/6/2022 | 4/21/2023 | 39483 | 81218 | 81218
21 | K406 | MIDWOOD HS - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / IDA PAVED AREAS- BLACKTOP / IDA HEATING PLANT UPGRADE | Design | Complete | 4/24/2023 | 9/25/2023 | 11/1/2023 | 193391 | 208442 | 165022
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Scope | Complete | 9/1/2023 | 3/13/2024 | 2/16/2024 | 162484 | 153330 | 153330
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | SWIMMING POOL / PATH OF TRAVEL SWIMMING POOL / VENTILATION | Design | Complete | 2/28/2024 | 7/1/2024 | 5/1/2024 | 812422 | 441050 | 391368
21 | K410 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL CAFETERIA UPGRADE / FY20 RESO A CAFETERIA UPGRADE | Design | Complete | 11/17/2021 | 3/18/2022 | 10/12/2022 | 60716 | 96000 | 61785
21 | K411 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | ATHLETIC FIELD BLEACHERS C OF O | Scope | Complete | 5/23/2023 | 9/22/2023 | 9/19/2023 | 11722 | 16643 | 16643
21 | K411 | ABRAHAM LINCOLN HS - BROOKLYN | SCA CIP | ATHLETIC FIELD BLEACHERS C OF O | Design | Complete | 9/28/2023 | 4/5/2024 | 3/11/2024 | 52748 | 49376 | 8364
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA GYM PARTITION REPLACEMENT | Scope | Complete | 11/30/2021 | 4/4/2022 | 8/1/2022 | 20049 | 18708 | 18708
21 | K525 | EDWARD R. MURROW HS - K | SCA CIP | IDA FLOOD ELIMINATION / IDA GYM PARTITION REPLACEMENT | Design | Complete | 8/10/2022 | 12/28/2022 | 2/8/2023 | 96465 | 62506 | 59144
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | Scope | Complete | 10/30/2018 | 3/4/2021 | 12/17/2020 | 416999 | 388107 | 385817
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | Design | Complete | 1/14/2021 | 9/14/2021 | 5/6/2021 | 2085001 | 884154 | 873792
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | Construction | Complete | 7/6/2021 | 7/4/2024 | 7/4/2024 | 46912500 | 43886353 | 40557786
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PARAPETS / REPLACE UNDERGROUND COMBINATION FIRE/DOMESTIC WATER MAIN / PAVED AREAS- BLACKTOP | CM,F&E | Complete | 7/6/2021 | 7/4/2024 | 7/4/2024 | 2919000 | 1563297 | 1542847
21 | K540 | JOHN DEWEY HS - BROOKLYN | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 3/27/2019 | 8/26/2019 | 5/15/2021 | 786600 | 873670 | 813811
21 | K597 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Scope | Complete | 7/1/2021 | 10/29/2021 | 11/1/2021 | 544440 | 413438 | 413438
21 | K597 | EDUCATIONAL CAMPUS @ 2202 60 STREET - BROOKLYN | SCA Lease Site Improvement | LEASE | Design | Complete | 11/2/2021 | 4/15/2022 | 5/13/2022 | 2449980 | 771174 | 720912
21 | K620 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | Scope | Complete | 9/10/2018 | 1/10/2019 | 2/4/2020 | 22790 | 25549 | 25549
21 | K620 | WILLIAM E. GRADY VOC HS - K | SCA CIP | ANSUL SYSTEM DUCTWORK | Design | Complete | 2/4/2020 | 6/24/2020 | 8/12/2022 | 113950 | 120218 | 118558
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Scope | Complete | 10/24/2018 | 3/14/2019 | 10/22/2019 | 48970 | 118234 | 113384
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Design | Complete | 10/22/2019 | 3/26/2020 | 5/17/2023 | 238879 | 385645 | 344893
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 11/1/2019 | 2/5/2020 | 3/31/2020 | 22680 | 40107 | 40107
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 3/31/2020 | 9/30/2020 | 6/30/2020 | 113400 | 208080 | 208080
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/17/2023 | 6/20/2023 | 3/2/2023 | 4044 | 1176 | 1176
21 | K722 | K721 SPED - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/2/2023 | 8/25/2023 | 5/3/2023 | 18196 | 4704 | 4704
21 | K722 | K721 SPED - BROOKLYN | SCA CIP RESOA | FY22 RESO A KITCHEN UPGRADE | Design | Complete | 8/11/2022 | 1/17/2023 | 2/2/2023 | 150000 | 96752 | 85945
21 | KBUH | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Scope | Complete | 3/2/2021 | 8/4/2022 | 11/2/2022 | 18945 | 11164 | 4388
21 | KBUH | CONEY ISLAND #1 HEAD START | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT / PATH OF TRAVEL | Design | Complete | 11/2/2022 | 3/1/2023 | 4/26/2023 | 94132 | 76053 | 13991
22 | K014 | I.S. 14 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/6/2023 | 11/21/2023 | 2/23/2024 | 22437 | 57183 | 57183
22 | K014 | I.S. 14 - BROOKLYN | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/26/2024 | 7/26/2024 | 5/15/2024 | 112188 | 147503 | 11395
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 7/24/2019 | 12/3/2019 | 1/10/2020 | 104430 | 136045 | 136045
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / WINDOWS / EXTERIOR MASONRY | Design | Complete | 1/15/2020 | 6/16/2020 | 6/26/2020 | 522150 | 537265 | 520608
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 3/3/2022 | 7/1/2022 | 7/15/2022 | 17405 | 35419 | 132
22 | K052 | P.S. 52 - BROOKLYN | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 7/15/2022 | 7/15/2022 | 7/15/2022 | 78324 | 37813 | 529
22 | K078 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 4/29/2022 | 9/29/2022 | 7/7/2022 | 131097 | 51786 | 51786
22 | K078 | I.S. 78 - BROOKLYN | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 7/11/2022 | 12/12/2022 | 11/17/2022 | 645809 | 293033 | 209995
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/14/2021 | 10/28/2021 | 11/8/2021 | 27291 | 63311 | 45060
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/10/2021 | 4/15/2022 | 4/27/2022 | 134863 | 105391 | 105391
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | Complete | 2/13/2023 | 5/7/2024 | 11/2/2023 | 2896817 | 2747683 | 2713205
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 2/13/2023 | 5/7/2024 | 11/2/2023 | 202967 | 274781 | 274239
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | Complete | 3/5/2024 | 7/19/2024 | 8/13/2024 | 44481 | 45420 | 27896
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Scope | Complete | 3/6/2024 | 6/5/2024 | 4/12/2024 | 1973 | 1973 | 1973
22 | K119 | P.S. 119 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 4/23/2024 | 8/26/2024 | 8/13/2024 | 7892 | 7892 | 7892
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 5/15/2023 | 9/29/2023 | 9/26/2023 | 10606 | 18496 | 18412
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 10/5/2023 | 3/12/2024 | 3/19/2024 | 47728 | 37303 | 36714
22 | K139 | P.S. 139 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 6/5/2023 | 10/19/2023 | 10/17/2023 | 48600 | 58018 | 48457
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/20/2015 | 1/22/2016 | 12/21/2015 | 18645 | 31453 | 31453
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 1/28/2016 | 7/29/2016 | 6/3/2016 | 74580 | 131792 | 123019
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | HVAC UPGRADE / BMS UPGRADE | Scope | Complete | 11/10/2022 | 4/17/2023 | 11/15/2023 | 84809 | 103652 | 103652
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | HVAC UPGRADE / BMS UPGRADE | Design | Complete | 11/28/2023 | 4/30/2024 | 8/26/2024 | 424041 | 331340 | 182954
22 | K152 | P.S. 315 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS / FLOOD ELIMINATION / PAVED AREA- CONCRETE | Scope | Complete | 6/12/2023 | 12/11/2023 | 11/3/2023 | 369898 | 245642 | 244175
22 | K152 | P.S. 152 - BROOKLYN | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 4/21/2023 | 9/7/2023 | 9/1/2023 | 33000 | 47090 | 42898
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 3/26/2021 | 11/22/2022 | 7/19/2023 | 237237 | 395766 | 388860
22 | K193 | P.S. 193 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM / PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 8/21/2023 | 1/25/2024 | 4/4/2024 | 1167416 | 853563 | 355534
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 2/26/2021 | 7/13/2021 | 11/29/2021 | 109900 | 96167 | 96167
22 | K194 | P.S. 194 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 11/29/2021 | 5/17/2022 | 2/8/2023 | 549500 | 370800 | 251508
22 | K195 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/2/2021 | 10/18/2021 | 12/22/2021 | 19147 | 30026 | 30026
22 | K195 | P.S. 195 - BROOKLYN | SCA CIP | EXTERIOR MASONRY | Design | Complete | 12/22/2021 | 5/25/2022 | 5/5/2022 | 95734 | 80669 | 78896
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | Scope | Complete | 11/28/2023 | 4/15/2024 | 2/8/2024 | 13400 | 20747 | 20747
22 | K197 | P.S. 197 - BROOKLYN | SCA CIP | PERM FIX- REINFORCING SUPPORT ELEMENTS @ K197 | Design | Complete | 2/12/2024 | 7/15/2024 | 5/14/2024 | 67000 | 59203 | 59203
22 | K198 | P.S. 198 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A (MA) CAFETERIA UPGRADE | Scope | Complete | 4/9/2024 | 7/11/2024 | 6/10/2024 | 10748 | 10748 | 795
22 | K206 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | Scope | Complete | 5/10/2022 | 8/26/2022 | 8/26/2022 | 1192000 | 857109 | 848375
22 | K206 | P.S. 206 - BROOKLYN | SCA Capacity | ADDITION | Design | Complete | 8/29/2022 | 3/3/2023 | 4/12/2023 | 5364000 | 3101772 | 1422396
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING-EXISTING BUILDING-INTERIOR RENOVATIONS/PROGRAM ACCESSIBILITY | Scope | Complete | 9/21/2022 | 1/26/2023 | 3/13/2023 | 91591 | 97679 | 62772
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING-EXISTING BUILDING-INTERIOR RENOVATIONS/PROGRAM ACCESSIBILITY | Design | Complete | 3/15/2023 | 8/15/2023 | 10/23/2023 | 455057 | 239908 | 215541
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | DEMOLITION | Scope | Complete | 7/22/2022 | 7/22/2022 | 7/22/2022 | 33672 | 83785 | 83785
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | DEMOLITION | Design | Complete | 7/25/2022 | 11/18/2022 | 3/15/2023 | 168359 | 241785 | 241784
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | DEMOLITION | Construction | Complete | 7/6/2023 | 3/1/2024 | 5/1/2024 | 3788071 | 3614108 | 3280418
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | DEMOLITION | CM,F&E | Complete | 7/6/2023 | 3/1/2024 | 5/1/2024 | 235702 | 266463 | 255377
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/14/2023 | 6/14/2023 | 3/2/2023 | 3779 | 1385 | 1385
22 | K206 | P.S. 206 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/2/2023 | 8/25/2023 | 5/3/2023 | 17007 | 5539 | 5539
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/7/2021 | 9/22/2021 | 11/16/2021 | 158000 | 186244 | 176456
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/17/2021 | 4/21/2022 | 5/11/2022 | 790000 | 570040 | 512296
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/15/2023 | 6/15/2023 | 3/13/2023 | 4077 | 696 | 696
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/13/2023 | 9/6/2023 | 5/3/2023 | 18346 | 2785 | 2785
22 | K207 | P.S. 207 - BROOKLYN | SCA CIP RESOA | FY18 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 6/9/2021 | 10/22/2021 | 5/12/2022 | 59276 | 104204 | 75772
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Design | Complete | 1/6/2021 | 5/25/2021 | 5/10/2021 | 81589 | 53830 | 53830
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Construction | Complete | 9/27/2023 | 8/21/2024 | 6/20/2024 | 1196638 | 652845 | 602752
22 | K217 | P.S. 217 - BROOKLYN | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | CM,F&E | Complete | 9/27/2023 | 8/21/2024 | 6/20/2024 | 81589 | 65506 | 63810
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/24/2023 | 11/22/2023 | 8/2/2023 | 4870 | 2135 | 2135
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/1/2023 | 21915 | 8540 | 8540
22 | K222 | P.S. 222 - BROOKLYN | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/4/2023 | 12/21/2023 | 2/12/2024 | 60000 | 71862 | 57162
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | Scope | Complete | 3/24/2021 | 7/23/2021 | 10/14/2021 | 27406 | 50420 | 38631
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | INTERIOR SPACES | Design | Complete | 12/1/2021 | 5/4/2022 | 9/23/2022 | 137029 | 220810 | 208269
22 | K234 | I.S. 234 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 6/18/2024 | 11/4/2024 | 9/19/2024 | 270897 | 72405 | 47805
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 5/30/2019 | 10/15/2019 | 11/1/2019 | 177065 | 113088 | 113088
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 12/18/2019 | 6/5/2020 | 11/4/2021 | 876028 | 631330 | 569062
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Construction | Complete | 6/6/2022 | 6/4/2024 | 8/20/2024 | 18906655 | 17444485 | 14799518
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | CM,F&E | Complete | 6/6/2022 | 6/4/2024 | 8/20/2024 | 1440770 | 1633474 | 1623919
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/7/2023 | 5/24/2023 | 2/15/2023 | 5600 | 3171 | 3171
22 | K236 | P.S. 236 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/15/2023 | 8/11/2023 | 5/2/2023 | 25200 | 12684 | 12684
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/22/2020 | 9/22/2020 | 7/6/2020 | 5931 | 9271 | 9271
22 | K240 | I.S. 240 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/6/2020 | 12/31/2020 | 5/5/2021 | 26688 | 37088 | 37088
22 | K251 | P.S. 251 - BROOKLYN | SCA CIP RESOA | FY23 RESO A (MA) LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 5/30/2023 | 10/5/2023 | 11/7/2023 | 45000 | 66050 | 65925
22 | K254 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | Scope | Complete | 1/30/2019 | 5/1/2019 | 4/3/2019 | 33660 | 69367 | 69367
22 | K254 | P.S. 254 - BROOKLYN | SCA CIP | PHASE III WORK ROOM CONVERSION / LOW VOLTAGE / MINOR ADA WORK | Design | Complete | 4/12/2019 | 10/4/2019 | 7/15/2021 | 168300 | 608851 | 370849
22 | K255 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/25/2023 | 11/24/2023 | 8/2/2023 | 4870 | 1581 | 1581
22 | K255 | P.S. 255 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/1/2023 | 21915 | 6324 | 6324
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 3/12/2021 | 7/27/2021 | 11/29/2021 | 48965 | 99463 | 97856
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/8/2021 | 5/11/2022 | 5/13/2022 | 237607 | 284929 | 272585
22 | K277 | P.S. 277 - BROOKLYN | SCA CIP RESOA | FY18 RESO A SCIENCE LAB UPGRADES | Design | Complete | 7/25/2018 | 12/27/2018 | 3/13/2019 | 32974 | 95244 | 87145
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 5/28/2021 | 10/14/2021 | 12/16/2021 | 20883 | 34164 | 33918
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 12/28/2021 | 5/31/2022 | 5/11/2022 | 102209 | 181721 | 147920
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Construction | Complete | 8/29/2022 | 2/19/2024 | 10/31/2023 | 2109208 | 1912282 | 1830923
22 | K278 | I.S. 278 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | CM,F&E | Complete | 8/29/2022 | 2/19/2024 | 10/31/2023 | 162694 | 236594 | 202793
22 | K286 | K811 SPED - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 8/29/2019 | 1/17/2020 | 6/8/2021 | 126919 | 186068 | 170015
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 3/26/2021 | 8/10/2021 | 11/3/2021 | 153170 | 163233 | 163233
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 11/15/2021 | 5/4/2022 | 9/30/2022 | 765850 | 404866 | 356862
22 | K312 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 7/18/2023 | 12/4/2023 | 1/26/2024 | 102000 | 51399 | 48560
22 | K342 | P.S. 312 - BROOKLYN | SCA CIP RESOA | FY16 RESO A LEARNING GARDEN | Design | Complete | 11/7/2017 | 3/28/2018 | 5/17/2019 | 888362 | 1426370 | 1336139
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 2/26/2021 | 7/13/2021 | 11/5/2021 | 195699 | 111768 | 111268
22 | K405 | MIDWOOD HS - BROOKLYN | SCA CIP | PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/10/2021 | 4/15/2022 | 5/11/2022 | 978501 | 512561 | 330297
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 8/14/2020 | 12/14/2020 | 3/24/2021 | 114450 | 81345 | 78715
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 3/29/2021 | 9/9/2021 | 12/1/2021 | 572250 | 363102 | 54061
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | Scope | Complete | 6/1/2023 | 11/30/2023 | 10/4/2023 | 393500 | 292801 | 288226
22 | K425 | JAMES MADISON HS - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS | Design | Complete | 10/26/2023 | 6/10/2024 | 4/15/2024 | 1967502 | 501163 | 488960
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 9/27/2019 | 2/18/2020 | 11/29/2021 | 138070 | 156676 | 155057
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 11/30/2021 | 5/3/2022 | 5/11/2022 | 690350 | 502488 | 485955
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/29/2020 | 9/28/2020 | 7/27/2020 | 4629 | 6577 | 6577
22 | K864 | SUCCESS ACADEMY CHARTER SCHOOL - BERGEN BEACH - NEW YORK 4 | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/27/2020 | 1/21/2021 | 5/5/2021 | 20832 | 26309 | 26309
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/24/2023 | 144603 | 242179 | 201371
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / FENCING | Design | Complete | 10/30/2023 | 6/10/2024 | 4/26/2024 | 715414 | 605475 | 592594
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/23/2023 | 10/23/2023 | 10/24/2023 | 17834 | 18745 | 18745
23 | K012 | P.S. 12 - BROOKLYN | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/26/2023 | 3/26/2024 | 4/1/2024 | 80254 | 65256 | 53902
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 5/22/2023 | 9/21/2023 | 6/1/2023 | 4800 | 555 | 555
23 | K073 | BROOKLYN LANDMARK ELEMENTARY SCHOOL | SCA CIP | IPDVS INSTALLATION | Design | Complete | 6/1/2023 | 11/29/2023 | 11/8/2023 | 21600 | 2221 | 2221
23 | K137 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 4/6/2021 | 8/19/2021 | 11/2/2021 | 191370 | 298199 | 271472
23 | K137 | P.S. 137 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 11/10/2021 | 5/2/2022 | 5/23/2023 | 956850 | 890093 | 762943
23 | K150 | P.S. 150 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/3/2024 | 9/4/2024 | 5/7/2024 | 4891 | 1808 | 1808
23 | K150 | P.S. 150 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/7/2024 | 11/1/2024 | 8/7/2024 | 22009 | 7230 | 7230
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | Scope | Complete | 11/3/2017 | 10/4/2018 | 11/26/2018 | 314342 | 142162 | 142162
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | WATER INFILTRATION / CRACKED MASONRY / ROOF LEAKS / HEATING PLANT UPGRADE / ELECTRICAL SYSTEMS / DOMESTIC PIPING / WINDOWS | Design | Complete | 1/23/2019 | 6/24/2019 | 5/17/2019 | 1252506 | 973714 | 971462
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/30/2023 | 5/30/2023 | 2/15/2023 | 5400 | 1806 | 1806
23 | K155 | P.S. 155 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/15/2023 | 8/11/2023 | 5/2/2023 | 24300 | 7222 | 7222
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | Scope | Complete | 1/26/2021 | 5/26/2021 | 10/20/2021 | 41950 | 26892 | 26892
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | COVID VENTILATION | Design | Complete | 10/28/2021 | 3/28/2022 | 4/18/2022 | 209750 | 204412 | 151407
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 6/7/2023 | 10/6/2023 | 6/20/2023 | 4694 | 1330 | 1330
23 | K183 | P.S. 446 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 6/20/2023 | 12/15/2023 | 10/4/2023 | 21123 | 5320 | 5320
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 7/19/2023 | 12/20/2023 | 1/31/2024 | 47086 | 55628 | 53071
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/27/2023 | 4/28/2023 | 8/1/2023 | 305 | 305 | 305
23 | K183 | RIVERDALE AVENUE MIDDLE SCHOOL | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 8/2/2023 | 12/6/2023 | 1/31/2024 | 1220 | 1220 | 1220
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND SURFACES | Scope | Complete | 8/21/2019 | 1/9/2020 | 12/20/2019 | 2315 | 16531 | 16531
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | PATH OF TRAVEL PLAYGROUND SURFACES | Design | Complete | 2/18/2020 | 8/3/2020 | 5/7/2020 | 10417 | 66122 | 66122
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/24/2023 | 5/23/2023 | 2/1/2023 | 4964 | 1993 | 1993
23 | K184 | P.S. 184 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/1/2023 | 7/28/2023 | 4/26/2023 | 22338 | 7970 | 7970
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | Scope | Complete | 6/21/2023 | 12/19/2023 | 11/2/2023 | 286001 | 181305 | 172293
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS | Design | Complete | 12/27/2023 | 5/29/2024 | 4/23/2024 | 1430000 | 377750 | 377750
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/19/2023 | 5/18/2023 | 2/1/2023 | 6276 | 982 | 982
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/1/2023 | 7/28/2023 | 4/26/2023 | 28242 | 3926 | 3926
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Scope | Complete | 12/1/2023 | 4/4/2024 | 3/1/2024 | 9413 | 9413 | 3648
23 | K263 | P.S./I.S. 323 - BROOKLYN | SCA CIP RESOA | FY24 RESO A GYMNASIUM UPGRADE | Design | Complete | 3/5/2024 | 7/19/2024 | 7/25/2024 | 14589 | 14589 | 14589
23 | K275 | I.S. 518 - BROOKLYN | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 7/19/2023 | 12/20/2023 | 11/21/2023 | 30000 | 29994 | 5253
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | Scope | Complete | 4/2/2019 | 7/17/2019 | 3/16/2020 | 8440 | 14978 | 14978
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | CHARTER MATCH BATHROOM UPGRADE | Design | Complete | 3/16/2020 | 8/28/2020 | 11/1/2022 | 37980 | 60871 | 57671
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | SWIMMING POOL / FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / EXTERIOR DOORS / FLOOD ELIMINATION / PATH OF TRAVEL SWIMMING POOL | Scope | Complete | 4/18/2017 | 7/20/2023 | 6/6/2023 | 286668 | 393208 | 384173
23 | K284 | P.S. 284 - BROOKLYN | SCA CIP | SWIMMING POOL / FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / EXTERIOR DOORS / FLOOD ELIMINATION / PATH OF TRAVEL SWIMMING POOL | Design | Complete | 6/7/2023 | 10/11/2023 | 4/23/2024 | 1408606 | 753589 | 573275
23 | K298 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 7/6/2023 | 11/3/2023 | 7/7/2023 | 4760 | 1050 | 1050
23 | K298 | P.S. 298 - BROOKLYN | SCA CIP | IPDVS INSTALLATION | Design | Complete | 7/7/2023 | 1/4/2024 | 11/8/2023 | 21420 | 4201 | 4201
23 | K327 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | Scope | Complete | 3/8/2019 | 6/6/2019 | 5/23/2019 | 15539 | 36201 | 36201
23 | K327 | K396 SPED - BROOKLYN | SCA CIP | FIRE ALARM REPLACEMENT | Design | Complete | 6/26/2019 | 12/31/2019 | 11/8/2019 | 77694 | 136216 | 136216
23 | K327 | P.S. 327 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/3/2023 | 11/17/2023 | 10/13/2023 | 120761 | 121975 | 121975
23 | K327 | P.S. 327 - BROOKLYN | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 10/16/2023 | 3/20/2024 | 3/26/2024 | 591584 | 357210 | 339597
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | Scope | Complete | 6/28/2019 | 12/27/2019 | 11/19/2019 | 138348 | 167150 | 160514
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / ROOF TOP UNIT / PAVED AREAS- CONCRETE | Design | Complete | 12/3/2019 | 6/15/2020 | 5/1/2020 | 686840 | 456742 | 456742
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/3/2024 | 9/4/2024 | 5/7/2024 | 3974 | 1182 | 1182
23 | K332 | CHRISTOPHER AVENUE COMMUNITY SCHOOL | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/7/2024 | 11/1/2024 | 8/7/2024 | 17883 | 4727 | 4727
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/18/2023 | 82651 | 151830 | 134427
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 10/30/2023 | 6/28/2024 | 4/8/2024 | 408065 | 248435 | 245668
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/30/2023 | 10/31/2023 | 7/25/2023 | 3684 | 1170 | 1170
23 | K356 | P.S. 156 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/25/2023 | 1/23/2024 | 10/4/2023 | 16578 | 4682 | 4682
23 | KAYT | HOPE FAITH AND CHARITY | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 4/5/2021 | 5/28/2021 | 8/3/2021 | 14285 | 16472 | 16472
23 | KAYT | HOPE FAITH AND CHARITY | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Design | Complete | 1/4/2022 | 5/4/2022 | 5/12/2023 | 64283 | 41240 | 36872
23 | KBAC | LOVE IN ACTION DAY CARE | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 4/9/2021 | 7/9/2021 | 8/4/2021 | 9686 | 14506 | 14506
23 | KBDD | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 4/9/2021 | 7/9/2021 | 8/3/2021 | 13540 | 17412 | 17412
23 | KBDD | SALVATION ARMY SUTTER DAY CARE | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Design | Complete | 10/26/2022 | 3/29/2023 | 5/12/2023 | 60930 | 3995 | 3995
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | Scope | Complete | 6/12/2014 | 9/11/2014 | 11/5/2014 | 70650 | 61506 | 61506
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | PUBLIC ADDRESS SYSTEM / HVAC | Design | Complete | 11/13/2014 | 4/17/2015 | 8/21/2015 | 282600 | 797734 | 698090
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | SMOKE PURGE SYSTEM | Scope | Complete | 3/14/2019 | 6/12/2019 | 11/27/2019 | 3872 | 18842 | 18842
24 | Q005 | I.S. 5 - QUEENS | SCA CIP | SMOKE PURGE SYSTEM | Design | Complete | 1/6/2020 | 2/6/2020 | 1/15/2020 | 17426 | 88325 | 88325
24 | Q005 | I.S. 5 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 5/1/2023 | 9/15/2023 | 9/22/2023 | 30000 | 58253 | 10341
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/29/2021 | 2/2/2022 | 7/15/2022 | 27650 | 41699 | 41699
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 7/18/2022 | 12/2/2022 | 4/12/2023 | 138250 | 99013 | 88357
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/1/2023 | 11/30/2023 | 11/15/2023 | 140732 | 153992 | 135142
24 | Q007 | P.S. 7 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 12/20/2023 | 5/22/2024 | 4/4/2024 | 703660 | 235516 | 235516
24 | Q009 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | Scope | Complete | 12/17/2018 | 5/7/2021 | 5/20/2021 | 196818 | 226086 | 226086
24 | Q009 | Q009 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / CAFETERIA UPGRADE / VENTILATION | Design | Complete | 5/21/2021 | 11/30/2021 | 1/31/2022 | 974931 | 792797 | 689303
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PLAYGROUNDS | Scope | Complete | 5/20/2022 | 8/22/2022 | 8/23/2022 | 7607 | 7607 | 7607
24 | Q012 | P.S. 12 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/9/2024 | 8/8/2024 | 5/8/2024 | 4493 | 3548 | 3548
24 | Q013 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Scope | Complete | 6/24/2019 | 12/20/2019 | 11/19/2019 | 142812 | 291348 | 289480
24 | Q013 | P.S. 13 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / WINDOWS / ROOFS | Design | Complete | 12/2/2019 | 6/15/2020 | 5/4/2020 | 708443 | 530368 | 525734
24 | Q013 | P.S. 13 - QUEENS | SCA CIP RESOA | FY24 RESO A ELECTRICAL UPGRADE | Design | Complete | 6/24/2024 | 12/27/2024 | 9/13/2024 | 30000 | 25022 | 7728
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL SOCCER PITCH / FY20 RESO A SOCCER PITCH | Design | Complete | 3/15/2022 | 5/11/2022 | 5/4/2022 | 42600 | 59903 | 52942
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 6/13/2023 | 10/13/2023 | 8/8/2023 | 32337 | 64713 | 52615
24 | Q014 | P.S. 14 - QUEENS | SCA CIP RESOA | FY23 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 1/12/2024 | 5/15/2024 | 2/16/2024 | 30000 | 28858 | 26555
24 | Q019 | P.S. 19 - QUEENS | SCA CIP | PARAPETS / ROOFS / WINDOWS | Scope | Complete | 7/13/2023 | 11/29/2023 | 11/15/2023 | 98632 | 85284 | 84781
24 | Q019 | P.S. 19 - QUEENS | SCA CIP | PARAPETS / ROOFS / WINDOWS | Design | Complete | 11/20/2023 | 4/23/2024 | 4/24/2024 | 488781 | 342458 | 335560
24 | Q019 | P.S. 19 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE / FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 11/17/2021 | 3/18/2022 | 4/18/2022 | 115996 | 162740 | 144303
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / REPLACEMENT OF RTUS / ROOFS | Scope | Complete | 5/21/2020 | 11/18/2020 | 10/8/2020 | 72015 | 139916 | 121351
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / REPLACEMENT OF RTUS / ROOFS | Design | Complete | 10/20/2020 | 6/15/2021 | 4/14/2021 | 354828 | 312162 | 312162
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/30/2021 | 3/3/2022 | 2/28/2022 | 21300 | 29430 | 29430
24 | Q028 | P.S. 28 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 3/16/2022 | 7/29/2022 | 9/14/2022 | 106500 | 164288 | 145402
24 | Q049 | P.S. 49 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/10/2024 | 10/25/2024 | 9/18/2024 | 143642 | 85401 | 39451
24 | Q058 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | Scope | Complete | 7/11/2019 | 11/26/2019 | 11/26/2019 | 58926 | 38935 | 38935
24 | Q058 | P.S. 58 - QUEENS | SCA CIP | ROOFS / PARAPETS | Design | Complete | 11/26/2019 | 4/29/2020 | 6/30/2020 | 286603 | 311574 | 299887
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/2/2024 | 9/3/2024 | 5/8/2024 | 5171 | 2814 | 2814
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Scope | Complete | 1/28/2021 | 12/30/2021 | 2/1/2022 | 92135 | 162555 | 162555
24 | Q071 | P.S. 71 - QUEENS | SCA CIP | FY19 RESO A PA SYSTEM UPGRADE / COVID VENTILATION / COVID FIRE ALARM REPLACEMENT | Design | Complete | 2/8/2022 | 7/8/2022 | 5/12/2023 | 436890 | 431018 | 335573
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | Scope | Complete | 10/11/2011 | 1/12/2012 | 12/6/2011 | 27750 | 18465 | 18465
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLT ELECTRICAL SYSTEMS | Design | Complete | 12/15/2011 | 6/19/2012 | 4/24/2012 | 83250 | 94716 | 88277
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 10/3/2018 | 3/11/2019 | 12/5/2018 | 117150 | 144929 | 144929
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/7/2018 | 5/10/2019 | 5/7/2019 | 468600 | 646950 | 625431
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 7/3/2019 | 10/2/2019 | 6/17/2021 | 18661 | 37531 | 37531
24 | Q073 | I.S. 73 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 6/29/2021 | 1/4/2022 | 1/21/2022 | 83973 | 63522 | 61263
24 | Q073 | I.S. 73 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 6/14/2021 | 11/15/2021 | 11/1/2021 | 45000 | 61620 | 61620
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 10/15/2018 | 3/5/2019 | 1/31/2019 | 87983 | 354962 | 349513
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/31/2019 | 7/2/2019 | 5/11/2022 | 439202 | 1115855 | 497576
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/18/2022 | 3/23/2023 | 12/9/2022 | 3311 | 6610 | 6610
24 | Q075 | Q075 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/9/2022 | 6/7/2023 | 4/4/2023 | 14900 | 26440 | 26440
24 | Q075 | Q075 SPED - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 2/27/2023 | 6/30/2023 | 3/10/2023 | 2177 | 0 | 0
24 | Q081 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | Scope | Complete | 8/17/2023 | 1/5/2024 | 12/8/2023 | 97939 | 230900 | 186579
24 | Q081 | P.S. 81 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION / WINDOWS / ROOFS | Design | Complete | 12/14/2023 | 5/16/2024 | 5/3/2024 | 489696 | 510400 | 494720
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/22/2021 | 2/28/2022 | 6/15/2022 | 8471 | 11985 | 11985
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 9/21/2022 | 2/9/2023 | 3/3/2023 | 38121 | 31392 | 27731
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 6/21/2023 | 11/6/2023 | 11/1/2023 | 81356 | 139319 | 121550
24 | Q087 | P.S. 87 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | Complete | 11/17/2023 | 4/22/2024 | 5/1/2024 | 406777 | 240537 | 233395
24 | Q087 | P.S. 87 - QUEENS | SCA CIP RESOA | FY19 RESO A CAFETERIA / MULTIPURPOSE ROOM UPGRADE | Design | Complete | 7/25/2019 | 12/11/2019 | 6/23/2020 | 186000 | 222256 | 220281
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2/6/2018 | 5/7/2018 | 3/23/2018 | 26304 | 23155 | 23155
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 4/25/2018 | 10/26/2018 | 8/27/2018 | 96448 | 104251 | 76639
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/19/2019 | 2/21/2020 | 4/21/2021 | 17468 | 67116 | 67116
24 | Q088 | P.S. 88 - QUEENS | SCA CIP | PLANYC PLAYGROUND REDEVELOPMENT | Design | Complete | 4/27/2021 | 9/10/2021 | 5/11/2022 | 87340 | 111596 | 111596
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT / VENTILATION | Scope | Complete | 3/14/2019 | 7/15/2019 | 1/21/2020 | 65275 | 140837 | 132888
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT / VENTILATION | Design | Complete | 1/21/2020 | 6/19/2020 | 9/30/2022 | 326375 | 293448 | 268350
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | ROOFS / WINDOWS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 6/20/2023 | 11/3/2023 | 11/7/2023 | 115182 | 181520 | 181520
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | ROOFS / WINDOWS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 11/13/2023 | 4/16/2024 | 4/30/2024 | 568834 | 319261 | 303749
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | AIR HANDLING UNITS | Scope | Complete | 11/14/2023 | 11/14/2023 | 11/14/2023 | 10646 | 9206 | 4444
24 | Q089 | P.S. 89 - QUEENS | SCA CIP | AIR HANDLING UNITS | Design | Complete | 11/14/2023 | 5/15/2024 | 5/15/2024 | 53230 | 75303 | 17775
24 | Q093 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 8/27/2014 | 4/13/2015 | 3/9/2015 | 309057 | 263726 | 263726
24 | Q093 | I.S. 93 - QUEENS | SCA CIP | ACCESSIBILITY / WINDOWS / ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 5/1/2015 | 11/16/2017 | 4/19/2018 | 1227451 | 1712059 | 1215870
24 | Q113 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Scope | Complete | 7/5/2022 | 11/18/2022 | 11/2/2023 | 44636 | 150098 | 87003
24 | Q113 | P.S. 113 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS | Design | Complete | 11/8/2023 | 4/12/2024 | 5/15/2024 | 214997 | 168062 | 122830
24 | Q119 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | Scope | Complete | 6/24/2019 | 12/20/2019 | 11/18/2019 | 207142 | 384241 | 384241
24 | Q119 | I.S. 119 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / FIRE ALARM / LL26 EXIT SIGNS / EXTERIOR DOORS | Design | Complete | 12/2/2019 | 6/15/2020 | 5/12/2020 | 1021278 | 686816 | 664580
24 | Q119 | I.S. 119 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE | Design | Complete | 9/5/2023 | 2/8/2024 | 5/24/2024 | 30000 | 55696 | 29515
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | Scope | Complete | 9/19/2019 | 2/25/2020 | 7/19/2021 | 26700 | 40776 | 40776
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOORING REPLACEMENT | Design | Complete | 11/8/2021 | 3/29/2022 | 3/16/2022 | 133500 | 128573 | 115830
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 1/19/2023 | 6/5/2023 | 11/8/2023 | 12366 | 47250 | 47250
24 | Q125 | I.S. 125 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 11/20/2023 | 4/23/2024 | 8/2/2024 | 61828 | 78077 | 76202
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | PHASE 3-PLAYGROUND REDEVELOPMENT FOR JOP | Scope | Complete | 12/12/2018 | 4/16/2019 | 7/15/2019 | 27774 | 68898 | 55733
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | PHASE 3-PLAYGROUND REDEVELOPMENT FOR JOP | Design | Complete | 7/17/2019 | 12/3/2019 | 5/11/2022 | 138868 | 293276 | 179085
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | Scope | Complete | 6/25/2019 | 12/28/2020 | 11/5/2020 | 329900 | 336731 | 329731
24 | Q143 | P.S. 143 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / AIR CONDITIONING UNIT (RTU) / HEATING SYSTEM UPGRADE / ROOM CONVERSIONS | Design | Complete | 11/5/2020 | 4/12/2021 | 4/28/2021 | 1649501 | 910338 | 815746
24 | Q153 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 7/22/2019 | 10/21/2019 | 9/25/2019 | 19800 | 15463 | 15463
24 | Q153 | P.S. 153 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 12/18/2019 | 5/20/2020 | 5/8/2020 | 89100 | 61966 | 61966
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | Scope | Complete | 3/12/2018 | 6/8/2018 | 5/14/2019 | 25050 | 41749 | 41749
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | FIRE ALARM REPLACEMENT | Design | Complete | 5/14/2019 | 10/15/2019 | 5/16/2019 | 91850 | 98382 | 87849
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 12/19/2018 | 7/26/2019 | 3/28/2019 | 19950 | 6024 | 6024
24 | Q229 | P.S. 229 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 3/28/2019 | 8/27/2019 | 5/10/2019 | 73150 | 24225 | 24225
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 8/12/2019 | 12/13/2019 | 3/25/2021 | 77600 | 111212 | 111212
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | HVAC COOLING SYSTEM REPLACEMENT / CLIMATE CONTROL / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 10/28/2021 | 4/25/2022 | 9/19/2022 | 388000 | 566355 | 278159
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/30/2022 | 11/16/2022 | 3/27/2023 | 17175 | 55231 | 53469
24 | Q239 | P.S. 239 - QUEENS | SCA CIP | EXTERIOR MASONRY | Design | Complete | 4/4/2023 | 9/5/2023 | 9/6/2023 | 85875 | 70796 | 56609
24 | Q239 | P.S. 239 - QUEENS | SCA CIP RESOA | FY23 RESO A PLAYGROUND UPGRADE | Design | Complete | 6/27/2023 | 11/13/2023 | 1/26/2024 | 38275 | 48501 | 47470
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | ROOFS / ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | Complete | 12/4/2023 | 5/3/2024 | 4/18/2024 | 85454 | 163011 | 163011
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | ROOFS / ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | Complete | 4/18/2024 | 11/13/2024 | 9/25/2024 | 427267 | 199544 | 23008
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/24/2022 | 7/22/2022 | 4/11/2022 | 3050 | 3925 | 3925
24 | Q245 | P.S. 305 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/11/2022 | 10/4/2022 | 8/17/2022 | 13725 | 15699 | 15699
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 3/20/2024 | 8/20/2024 | 9/9/2024 | 57000 | 30524 | 18972
24 | Q247 | P.S. 128 - QUEENS | SCA CIP RESOA | FY24 RESO A PLAYGROUND UPGRADE | Design | Complete | 3/20/2024 | 8/5/2024 | 9/9/2024 | 96000 | 38537 | 22815
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 6/26/2023 | 11/9/2023 | 12/11/2023 | 20641 | 147715 | 115090
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 12/11/2023 | 5/13/2024 | 6/18/2024 | 99129 | 67142 | 50645
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | IPDVS | Scope | Complete | 3/22/2022 | 7/20/2022 | 3/30/2022 | 3330 | 4097 | 4097
24 | Q260 | P.S. 307 - QUEENS | SCA CIP | IPDVS | Design | Complete | 3/30/2022 | 9/22/2022 | 8/17/2022 | 14985 | 16386 | 16386
24 | Q298 | ELM TREE ELEMENTARY SCHOOL | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/31/2022 | 1/20/2023 | 3/22/2023 | 18150 | 27459 | 27459
24 | Q315 | P.S. 110 - QUEENS | SCA CIP RESOA | RESO A ROOM CONVERSION | Design | Complete | 1/25/2023 | 6/27/2023 | 5/11/2023 | 39635 | 54159 | 17829
24 | Q331 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | Scope | Complete | 2/8/2022 | 4/14/2022 | 4/25/2022 | 171608 | 180713 | 173507
24 | Q331 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | Design | Complete | 4/26/2022 | 6/14/2022 | 1/6/2023 | 772234 | 639298 | 501450
24 | Q331 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | Construction | Complete | 1/20/2023 | 9/3/2023 | 7/24/2024 | 9738729 | 9897797 | 9772864
24 | Q331 | 3K CENTER @ 104-72 ROOSEVELT AVENUE - QUEENS | 3K | LEASE | CM,F&E | Complete | 1/20/2023 | 9/3/2023 | 7/24/2024 | 1460449 | 454760 | 1377966
24 | Q340 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 1/17/2019 | 7/2/2019 | 7/16/2019 | 627900 | 618029 | 524158
24 | Q340 | P.S. @ 46-10 70 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 7/17/2019 | 1/16/2020 | 8/13/2020 | 2825550 | 2167652 | 1404878
24 | Q366 | 3K CENTER @ 63-57 FRESH POND ROAD - QUEENS | 3K | LEASE | Scope | Complete | 2/4/2022 | 3/11/2022 | 3/11/2022 | 295191 | 282908 | 273795
24 | Q366 | 3K CENTER @ 63-57 FRESH POND ROAD - QUEENS | 3K | LEASE | Design | Complete | 3/14/2022 | 6/3/2022 | 9/6/2022 | 1328358 | 819109 | 784196
24 | Q366 | 3K CENTER @ 63-57 FRESH POND ROAD - QUEENS | 3K | LEASE | Construction | Complete | 11/3/2022 | 9/3/2023 | 6/26/2024 | 16752069 | 16970635 | 16847805
24 | Q366 | 3K CENTER @ 63-57 FRESH POND ROAD - QUEENS | 3K | LEASE | CM,F&E | Complete | 11/3/2022 | 9/3/2023 | 6/26/2024 | 2472452 | 782255 | 1771670
24 | Q444 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | Scope | Complete | 11/1/2021 | 12/21/2021 | 2/3/2022 | 179859 | 171674 | 171674
24 | Q444 | 3K CENTER @ 48-18 VAN DAM STREET - QUEENS | 3K | LEASE | Design | Complete | 2/4/2022 | 2/18/2022 | 10/19/2023 | 809367 | 591835 | 492020
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 3/29/2018 | 5/23/2019 | 1/29/2019 | 18776 | 27202 | 27202
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LSP LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 1/29/2019 | 6/28/2019 | 5/16/2019 | 74387 | 78595 | 78595
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Scope | Complete | 8/16/2018 | 1/8/2019 | 10/3/2022 | 409223 | 405438 | 405438
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP | CEILING ACOUSTAL TILES REPLACEMENT / ROOF SLATE TILES / WATER PENETRATION IN BOILER, GAS ROOM, OIL TANK ROOM, CELLAR HALLWAY / VENTILATION / ROOFS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Design | Complete | 12/2/2022 | 5/5/2023 | 5/12/2023 | 2046114 | 1756268 | 1372873
24 | Q455 | NEWTOWN HS - QUEENS | SCA CIP RESOA | FY22 RESO A CAFETERIA UPGRADE | Design | Complete | 7/10/2023 | 11/24/2023 | 10/24/2023 | 30000 | 91807 | 46663
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 1/10/2020 | 5/27/2020 | 6/18/2021 | 116705 | 2756 | 2756
24 | Q456 | HS FOR ARTS AND BUSINESS - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 3/29/2023 | 8/29/2023 | 4/30/2024 | 583526 | 627506 | 510361
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | Scope | Complete | 3/11/2021 | 7/26/2021 | 12/8/2021 | 23094 | 39059 | 39059
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | SCIENCE LAB UPGRADES | Design | Complete | 1/5/2022 | 7/8/2022 | 5/11/2022 | 115470 | 150444 | 137996
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | Scope | Complete | 6/16/2021 | 11/1/2021 | 1/6/2022 | 31515 | 44784 | 42098
24 | Q485 | GROVER CLEVELAND HS - QUEENS | SCA CIP | EXTERIOR MASONRY / EXTERIOR DOORS | Design | Complete | 1/25/2022 | 6/24/2022 | 5/11/2022 | 155850 | 121571 | 121571
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | Scope | Complete | 5/8/2019 | 9/23/2019 | 2/11/2020 | 18899 | 50203 | 50203
24 | Q520 | MIDDLE COLLEGE HIGH SCHOOL - QUEENS | SCA CIP | WATER INFILTRATION | Design | Complete | 2/11/2020 | 7/13/2020 | 6/30/2020 | 85045 | 97902 | 97902
24 | Q600 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | Scope | Complete | 4/20/2021 | 1/22/2022 | 2/4/2022 | 38155 | 46217 | 46217
24 | Q600 | QUEENS TECH HS - Q | SCA CIP | SCIENCE LAB UPGRADES / PATH OF TRAVEL SCIENCE LAB | Design | Complete | 2/4/2022 | 4/28/2022 | 7/28/2022 | 190152 | 183845 | 183375
24 | Q600 | QUEENS TECH HS - Q | SCA CIP RESOA | FY18 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 4/29/2020 | 10/23/2020 | 5/14/2020 | 29039 | 28147 | 28147
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/17/2021 | 6/15/2021 | 6/17/2021 | 12500 | 21109 | 21109
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 6/22/2021 | 12/27/2021 | 12/14/2021 | 62500 | 121887 | 100055
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES | Scope | Complete | 12/3/2021 | 10/14/2022 | 1/9/2023 | 103266 | 105301 | 105301
24 | Q610 | AVIATION HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA HEATING PLANT UPGRADE / NON-IDA CLIMATE CONTROL / IDA INTERIOR SPACES | Design | Complete | 1/12/2023 | 6/14/2023 | 8/24/2023 | 502200 | 325733 | 287069
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 10/29/2021 | 2/2/2022 | 7/15/2022 | 18980 | 38100 | 38100
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 7/18/2022 | 12/2/2022 | 4/18/2023 | 94900 | 102765 | 96300
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/1/2024 | 5/31/2024 | 3/27/2024 | 6731 | 3105 | 3105
24 | Q721 | P.S. 16 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/27/2024 | 9/20/2024 | 6/14/2024 | 30291 | 12418 | 12418
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2/15/2022 | 6/30/2022 | 2/2/2023 | 47346 | 47565 | 47565
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | Complete | 5/29/2023 | 4/22/2024 | 5/29/2024 | 694411 | 664174 | 614520
24 | Q722 | Q721 SPED - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 5/29/2023 | 4/22/2024 | 5/29/2024 | 47346 | 66800 | 65564
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/1/2024 | 5/31/2024 | 3/27/2024 | 7755 | 3683 | 3683
24 | Q735 | BARD HS EARLY COLLEGE II - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/27/2024 | 9/20/2024 | 6/14/2024 | 34896 | 14731 | 14731
24 | Q848 | P.S. 81 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A CAFETERIA UPGRADE / FY21 RESO A CAFETERIA UPGRADE | Design | Complete | 5/6/2022 | 6/13/2022 | 5/11/2022 | 22998 | 30917 | 29922
24 | Q849 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | Scope | Complete | 6/2/2022 | 11/28/2022 | 10/6/2022 | 243079 | 221469 | 204836
24 | Q849 | I.S. 77 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / FLOOD ELIMINATION | Design | Complete | 10/18/2022 | 6/5/2023 | 4/17/2023 | 1206317 | 516245 | 516245
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 12/18/2017 | 5/4/2018 | 3/21/2018 | 103128 | 89232 | 89232
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 3/21/2018 | 8/20/2018 | 5/18/2018 | 407457 | 573749 | 525828
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | Scope | Complete | 7/23/2013 | 12/18/2017 | 12/18/2017 | 141166 | 69808 | 69808
25 | Q020 | P.S. 20 - QUEENS | SCA CIP | FIRE ALARM SYSTEM / MECHANICAL SYSTEMS REPAIR / CERTIFICATE OF OCCUPANCY | Design | Complete | 4/20/2018 | 10/22/2018 | 5/16/2019 | 564660 | 564810 | 530325
25 | Q020 | P.S. 20 - QUEENS | SCA CIP RESOA | FY24 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 12/13/2023 | 6/10/2024 | 3/6/2024 | 30000 | 23195 | 23195
25 | Q021 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/27/2019 | 11/29/2019 | 9/18/2019 | 58253 | 73861 | 73861
25 | Q021 | P.S. 21 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/25/2019 | 3/2/2020 | 1/23/2020 | 291265 | 374605 | 341120
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 8/27/2018 | 11/28/2018 | 12/10/2018 | 12200 | 27434 | 27434
25 | Q022 | P.S. 22 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 1/3/2019 | 5/20/2019 | 2/28/2020 | 60999 | 119386 | 98453
25 | Q024 | P.S. 24 - QUEENS | SCA CIP RESOA | FY24 RESO A AUDITORIUM UPGRADE | Design | Complete | 2/26/2024 | 7/26/2024 | 5/6/2024 | 34620 | 47837 | 46593
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/25/2019 | 11/26/2019 | 9/25/2019 | 79750 | 114109 | 114109
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/27/2019 | 3/4/2020 | 1/23/2020 | 398750 | 568412 | 494090
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/14/2023 | 10/31/2023 | 11/6/2023 | 33761 | 60358 | 59633
25 | Q025 | J.H.S. 25 - QUEENS | SCA CIP | EXTERIOR MASONRY | Design | Complete | 11/15/2023 | 4/18/2024 | 5/6/2024 | 168805 | 118845 | 112800
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 12/18/2017 | 5/4/2018 | 4/3/2018 | 85230 | 56741 | 56741
25 | Q029 | P.S. 29 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 4/3/2018 | 8/31/2018 | 2/24/2023 | 426150 | 481151 | 405747
25 | Q032 | P.S. 32 - QUEENS | SCA Capacity | ADDITION | Scope | Complete | 9/10/2019 | 2/24/2020 | 2/21/2020 | 967475 | 638086 | 632442
25 | Q032 | P.S. 32 - QUEENS | SCA Capacity | ADDITION | Design | Complete | 2/24/2020 | 9/9/2020 | 5/13/2021 | 4353640 | 3652099 | 3025045
25 | Q032 | P.S. 32 - QUEENS | SCA Capacity | ADDITION | Construction | Complete | 1/11/2022 | 9/3/2024 | 6/18/2024 | 54904232 | 51381230 | 49073138
25 | Q032 | P.S. 32 - QUEENS | SCA Capacity | ADDITION | CM,Art,F&E | Complete | 1/11/2022 | 9/3/2024 | 6/18/2024 | 7739804 | 7380854 | 5668125
25 | Q032 | P.S. 32 - QUEENS | SCA CIP | EXISTING BUILDING WORK | Scope | Complete | 3/25/2021 | 7/23/2021 | 7/26/2021 | 70576 | 80195 | 80195
25 | Q032 | P.S. 32 - QUEENS | SCA CIP | EXISTING BUILDING WORK | Design | Complete | 7/26/2021 | 1/18/2022 | 2/6/2023 | 352881 | 534412 | 321302
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | FY19 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 10/21/2019 | 1/21/2020 | 2/14/2020 | 67421 | 85412 | 73171
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | FY19 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Construction | Complete | 3/6/2023 | 3/4/2024 | 4/9/2024 | 988849 | 654432 | 453441
25 | Q032 | P.S. 32 - QUEENS | SCA CIP RESOA | FY19 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | CM,F&E | Complete | 3/6/2023 | 3/4/2024 | 4/9/2024 | 73841 | 103454 | 102206
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/19/2021 | 9/17/2021 | 7/20/2021 | 78720 | 75072 | 75072
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 7/22/2021 | 1/21/2022 | 3/30/2022 | 393600 | 325415 | 277681
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | HVAC PIPING REPLACEMENT | Scope | Complete | 12/29/2021 | 6/1/2022 | 1/4/2022 | 19000 | 3695 | 3695
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | HVAC PIPING REPLACEMENT | Design | Complete | 1/4/2022 | 6/6/2022 | 2/24/2022 | 85502 | 14780 | 14780
25 | Q079 | P.S. 79 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/9/2024 | 8/8/2024 | 5/7/2024 | 6454 | 1877 | 1877
25 | Q079 | P.S. 79 - QUEENS | SCA CIP RESOA | FY23 RESO A OUTDOOR CLASSROOM | Design | Complete | 5/23/2023 | 10/10/2023 | 11/28/2023 | 61425 | 42000 | 41064
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | RTU REPLACEMENT | Scope | Complete | 4/14/2023 | 4/14/2023 | 4/14/2023 | 5809 | 692 | 692
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | RTU REPLACEMENT | Design | Complete | 4/14/2023 | 6/7/2023 | 6/7/2023 | 26140 | 2768 | 2768
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE / FIRE ALARM / LIGHTING UPGRADE | Scope | Complete | 8/23/2023 | 1/22/2024 | 12/22/2023 | 314790 | 273867 | 260661
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/20/2023 | 10/19/2023 | 6/26/2023 | 4934 | 3171 | 3171
25 | Q107 | P.S. 107 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/26/2023 | 12/21/2023 | 11/1/2023 | 22203 | 12685 | 12685
25 | Q107 | P.S. 107 - QUEENS | SCA CIP RESOA | FY16 RESO A MEDIA CENTER UPGRADE | Design | Complete | 5/3/2021 | 9/16/2021 | 1/27/2022 | 42000 | 81383 | 58635
25 | Q120 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | Scope | Complete | 5/27/2020 | 11/17/2021 | 9/15/2021 | 239846 | 281135 | 281135
25 | Q120 | P.S. 120 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / RTU REPLACEMENT / EXTERIOR DOORS | Design | Complete | 10/19/2021 | 6/30/2022 | 4/27/2022 | 1197635 | 559727 | 534559
25 | Q129 | P.S. 129 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 6/13/2024 | 10/30/2024 | 9/13/2024 | 244389 | 42900 | 29617
25 | Q154 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/14/2022 | 4/17/2023 | 12/21/2022 | 4269 | 5420 | 5420
25 | Q154 | P.S. 154 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/21/2022 | 6/20/2023 | 4/4/2023 | 19211 | 21680 | 21680
25 | Q163 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 4/28/2021 | 9/13/2021 | 11/8/2021 | 13340 | 16918 | 16918
25 | Q163 | P.S. 163 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 11/19/2021 | 4/25/2022 | 5/17/2022 | 60030 | 54487 | 54487
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/31/2022 | 11/23/2022 | 9/9/2022 | 155491 | 148986 | 142439
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 9/23/2022 | 6/12/2023 | 4/14/2023 | 777450 | 423460 | 423460
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/23/2022 | 9/21/2022 | 6/15/2022 | 5787 | 4435 | 4435
25 | Q164 | P.S. 164 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 26043 | 17739 | 17739
25 | Q165 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/16/2023 | 10/18/2023 | 6/21/2023 | 4985 | 2000 | 2000
25 | Q165 | P.S. 165 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/21/2023 | 12/18/2023 | 11/1/2023 | 22433 | 7998 | 7998
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 7/22/2021 | 10/21/2021 | 10/20/2021 | 14360 | 8505 | 8505
25 | Q168 | THE QUEENS SCHOOL OF INQUIRY-Q | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 10/27/2021 | 4/1/2022 | 1/19/2022 | 64620 | 34019 | 34019
25 | Q169 | I.S. 294 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE | Design | Complete | 1/4/2022 | 6/6/2022 | 5/2/2022 | 47400 | 31797 | 31070
25 | Q184 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/21/2022 | 12/7/2022 | 8/10/2023 | 30349 | 127385 | 126795
25 | Q184 | P.S. 184 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 9/6/2023 | 2/9/2024 | 4/18/2024 | 149646 | 272388 | 168090
25 | Q184 | P.S. 184 - QUEENS | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/9/2022 | 12/27/2022 | 3/13/2023 | 77136 | 86185 | 64414
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 7/24/2019 | 10/23/2019 | 9/25/2019 | 18000 | 10188 | 10188
25 | Q189 | J.H.S. 189 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 10/22/2019 | 3/26/2020 | 3/26/2020 | 81000 | 40798 | 40798
25 | Q189 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 5/20/2022 | 10/5/2022 | 12/27/2022 | 157000 | 231554 | 229974
25 | Q189 | THE FLUSHING INTERNATIONAL HS - Q | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / FLOOD ELIMINATION | Design | Complete | 1/18/2023 | 6/20/2023 | 5/9/2023 | 785001 | 679639 | 589393
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/13/2023 | 11/29/2023 | 1/9/2024 | 21160 | 70670 | 70670
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/19/2024 | 6/20/2024 | 5/14/2024 | 102927 | 42164 | 7466
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | Scope | Complete | 9/22/2016 | 6/5/2018 | 3/22/2018 | 145334 | 225336 | 225336
25 | Q193 | P.S. 193 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PATH OF TRAVEL TCU REMOVAL / PLAYGROUND REDEVELOPMENT | Design | Complete | 4/4/2018 | 9/4/2018 | 10/5/2018 | 582551 | 913169 | 837282
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 6/9/2021 | 11/24/2021 | 11/5/2021 | 42780 | 46302 | 46302
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | ROOFS | Design | Complete | 11/19/2021 | 4/25/2022 | 5/11/2022 | 213900 | 118968 | 118968
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/25/2022 | 9/23/2022 | 6/15/2022 | 7070 | 3868 | 3868
25 | Q194 | J.H.S. 194 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 31815 | 15472 | 15472
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 9/1/2023 | 1/23/2024 | 12/29/2023 | 82831 | 139645 | 134561
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/3/2024 | 6/4/2024 | 4/22/2024 | 406321 | 356348 | 356348
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/23/2023 | 5/22/2023 | 2/3/2023 | 4170 | 2723 | 2723
25 | Q200 | P.S. 200 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/3/2023 | 8/1/2023 | 5/2/2023 | 18765 | 10893 | 10893
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 4/9/2024 | 8/8/2024 | 4/23/2024 | 5134 | 930 | 930
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 4/23/2024 | 10/18/2024 | 9/25/2024 | 23102 | 3718 | 3718
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/27/2018 | 6/19/2019 | 2/21/2019 | 17660 | 9410 | 9410
25 | Q201 | P.S. 201 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2/21/2019 | 7/23/2019 | 5/16/2019 | 70249 | 37574 | 37574
25 | Q209 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | Scope | Complete | 9/30/2022 | 1/24/2024 | 12/22/2023 | 158001 | 267569 | 258241
25 | Q209 | P.S. 209 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / PLAYGROUND | Design | Complete | 1/3/2024 | 5/17/2024 | 5/2/2024 | 790000 | 645168 | 645168
25 | Q209 | P.S. 209 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 4/18/2022 | 9/16/2022 | 7/13/2022 | 23400 | 16118 | 16118
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | RTU / HVAC REPLACEMENT | Scope | Complete | 3/26/2019 | 7/29/2019 | 3/24/2020 | 19660 | 21203 | 21203
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | RTU / HVAC REPLACEMENT | Design | Complete | 3/27/2020 | 8/17/2020 | 4/19/2021 | 98300 | 148275 | 127664
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | RTU / HVAC REPLACEMENT | Construction | Complete | 7/15/2022 | 7/14/2023 | 7/14/2023 | 2211750 | 2017366 | 1985960
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | RTU / HVAC REPLACEMENT | CM,F&E | Complete | 7/15/2022 | 7/14/2023 | 7/14/2023 | 137620 | 210451 | 192308
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 2/1/2023 | 6/1/2023 | 2/6/2023 | 4340 | 4388 | 4388
25 | Q219 | P.S. 219 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/6/2023 | 8/2/2023 | 5/2/2023 | 19530 | 17552 | 17552
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | Scope | Complete | 2/27/2018 | 5/25/2018 | 7/31/2018 | 142290 | 127209 | 121490
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP | ELEVATOR MODERNIZATION | Design | Complete | 8/28/2018 | 1/16/2019 | 4/16/2019 | 569160 | 761112 | 664382
25 | Q237 | J.H.S. 237 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Design | Complete | 9/23/2021 | 2/24/2022 | 2/7/2022 | 105240 | 137427 | 109384
25 | Q244 | P.S. 244 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Scope | Complete | 10/10/2023 | 3/8/2024 | 3/25/2024 | 56562 | 152829 | 150643
25 | Q244 | P.S. 244 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS | Design | Complete | 3/25/2024 | 8/23/2024 | 5/15/2024 | 282809 | 334729 | 33489
25 | Q336 | COLLEGE POINT COLLABORATIVE - QUEENS | SCA CIP RESOA | FY22 RESO A PLAYGROUND UPGRADE / RESO A EXTERIOR DOOR | Design | Complete | 10/25/2023 | 3/25/2024 | 2/5/2024 | 54359 | 89409 | 55140
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/25/2022 | 9/2/2022 | 10/12/2022 | 1787500 | 1467839 | 1298493
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 10/13/2022 | 4/7/2023 | 5/12/2023 | 8043750 | 2560685 | 1606914
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 9/8/2022 | 9/8/2022 | 9/8/2022 | 65500 | 49200 | 49200
25 | Q388 | P.S. @ 23-50 WATERS EDGE DRIVE - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 9/8/2022 | 12/8/2022 | 4/18/2023 | 327500 | 119565 | 119565
25 | Q409 | DISTRICT 25 PRE-K CENTER | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 9/28/2022 | 12/30/2022 | 12/20/2022 | 17580 | 27210 | 27210
25 | Q409 | DISTRICT 25 PRE-K CENTER | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 12/21/2022 | 6/27/2023 | 5/1/2023 | 87901 | 81857 | 79440
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/14/2021 | 2/17/2022 | 3/30/2022 | 96080 | 128486 | 118609
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 4/14/2023 | 8/30/2023 | 4/16/2024 | 472411 | 312168 | 268132
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA GYM FLOOR REPLACEMENT | Scope | Complete | 1/13/2023 | 4/17/2023 | 2/15/2023 | 2739 | 15811 | 398
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA GYM FLOOR REPLACEMENT | Design | Complete | 4/13/2023 | 8/14/2023 | 4/16/2024 | 12325 | 1319 | 1319
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Scope | Complete | 8/9/2023 | 12/12/2023 | 8/24/2023 | 2093 | 20350 | 336
25 | Q425 | JOHN BOWNE HS - QUEENS | SCA CIP | PATH OF TRAVEL IDA INTERIOR SPACES | Design | Complete | 8/25/2023 | 1/17/2024 | 4/16/2024 | 9419 | 21342 | 1344
25 | Q460 | FLUSHING HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE / FY23 RESO A GYMNASIUM UPGRADE | Design | Complete | 11/13/2023 | 4/1/2024 | 8/21/2024 | 45000 | 60633 | 56462
25 | Q462 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 2/24/2020 | 7/8/2020 | 11/29/2021 | 10073 | 18095 | 18095
25 | Q462 | FLUSHING HS - QUEENS | SCA CIP | ROOF REPLACEMENT | Design | Complete | 12/8/2021 | 5/11/2022 | 12/2/2022 | 45329 | 87748 | 69532
25 | Q463 | FLUSHING HS - QUEENS | SCA CIP RESOA | FY23 RESO A ATHLETIC FIELD UPGRADE | Design | Complete | 7/25/2023 | 1/25/2024 | 5/14/2024 | 77472 | 315752 | 286538
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/13/2023 | 8/17/2023 | 9/18/2023 | 1195340 | 1228892 | 1065122
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 9/19/2023 | 4/12/2024 | 5/9/2024 | 5379030 | 1464002 | 1314065
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 5/11/2023 | 5/11/2023 | 5/11/2023 | 39545 | 1077 | 1077
25 | Q510 | H.S. @ 13-20 124 STREET - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 5/12/2023 | 8/31/2023 | 1/16/2024 | 197723 | 103071 | 91219
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/20/2023 | 8/24/2023 | 8/17/2023 | 952120 | 734470 | 671572
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 8/18/2023 | 3/28/2024 | 5/9/2024 | 4284540 | 978389 | 921307
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 6/2/2023 | 7/7/2023 | 6/2/2023 | 15889 | 19866 | 19779
25 | Q511 | JOHN BOWNE HS ANNEX - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 6/5/2023 | 10/27/2023 | 11/17/2023 | 71501 | 98363 | 76401
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/22/2024 | 9/17/2024 | 9/17/2024 | 763046 | 315003 | 253083
25 | Q512 | P.S. @ 137-23 45 AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 4/23/2024 | 4/23/2024 | 4/23/2024 | 32564 | 2772 | 2772
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 1/21/2020 | 6/19/2020 | 5/27/2020 | 64200 | 77135 | 77135
26 | Q018 | P.S. 18 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/27/2020 | 10/27/2020 | 8/19/2020 | 321000 | 352504 | 297671
26 | Q026 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | Scope | Complete | 10/25/2019 | 9/21/2021 | 9/21/2021 | 1198860 | 863967 | 823640
26 | Q026 | P.S. 26 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-FIRE ALARM | Design | Complete | 9/21/2021 | 5/11/2022 | 5/9/2022 | 5394870 | 2750653 | 1972783
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 1/19/2018 | 6/20/2018 | 4/9/2018 | 108255 | 71205 | 71205
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/2/2018 | 11/29/2018 | 8/21/2018 | 433020 | 238935 | 226020
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING RENOVATIONS | Scope | Complete | 8/5/2021 | 10/18/2021 | 12/6/2021 | 79322 | 73318 | 73318
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING RENOVATIONS | Design | Complete | 12/15/2021 | 6/10/2022 | 7/19/2023 | 396611 | 230534 | 210114
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING-GYMNASIUM / EXISTING BUILDING-AUDITORIUM | Scope | Complete | 2/10/2022 | 6/27/2022 | 7/27/2022 | 11184 | 9015 | 3250
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | EXISTING BUILDING-GYMNASIUM / EXISTING BUILDING-AUDITORIUM | Design | Complete | 8/9/2022 | 1/30/2023 | 5/11/2023 | 50326 | 13997 | 13997
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 12/1/2021 | 6/24/2022 | 7/8/2022 | 23546 | 22672 | 22672
26 | Q026 | P.S. 26 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 7/11/2022 | 12/12/2022 | 5/22/2023 | 105958 | 68745 | 65309
26 | Q031 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | Scope | Complete | 9/17/2014 | 2/5/2015 | 3/16/2015 | 226470 | 129723 | 129723
26 | Q031 | P.S. 31 - QUEENS | SCA CIP | CHIMNEY LINER REPLACEMENT / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / ROOFS / PARAPETS | Design | Complete | 2/12/2016 | 7/14/2016 | 10/12/2016 | 898205 | 1019021 | 931008
26 | Q041 | P.S. 41 - QUEENS | SCA Capacity | ADDITION / DEMOLITION | Scope | Complete | 2/25/2019 | 8/2/2019 | 8/2/2019 | 1026305 | 799639 | 792131
26 | Q041 | P.S. 41 - QUEENS | SCA Capacity | ADDITION / DEMOLITION | Design | Complete | 8/5/2019 | 2/28/2020 | 3/30/2020 | 4618376 | 2996399 | 2605326
26 | Q041 | P.S. 41 - QUEENS | SCA Capacity | ADDITION / DEMOLITION | Construction | Complete | 7/19/2021 | 9/3/2024 | 6/25/2024 | 58242856 | 54458150 | 51348568
26 | Q041 | P.S. 41 - QUEENS | SCA Capacity | ADDITION / DEMOLITION | CM,Art,F&E | Complete | 7/19/2021 | 9/3/2024 | 6/25/2024 | 8210447 | 9014722 | 6790028
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 11/16/2018 | 4/5/2019 | 6/19/2019 | 69195 | 175393 | 139968
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | SSBA - WORK IN EXISTING BUILDING | Scope | Complete | 6/8/2021 | 10/20/2021 | 2/8/2022 | 20400 | 66933 | 66933
26 | Q041 | P.S. 41 - QUEENS | SCA CIP | SSBA - WORK IN EXISTING BUILDING | Design | Complete | 2/17/2022 | 7/20/2022 | 1/4/2023 | 101998 | 226249 | 215939
26 | Q046 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | Scope | Complete | 10/28/2019 | 12/19/2019 | 2/28/2020 | 67959 | 130632 | 130632
26 | Q046 | P.S. 46 - QUEENS | SCA CIP | WORK IN EXISTING BUILDING | Design | Complete | 3/11/2020 | 10/13/2020 | 12/22/2021 | 339795 | 364047 | 213489
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA GYM PARTITION & BLEACHERS | Scope | Complete | 11/5/2021 | 3/28/2022 | 12/4/2023 | 84779 | 321120 | 267144
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/21/2022 | 12/7/2022 | 3/31/2023 | 97063 | 132275 | 132170
26 | Q067 | J.H.S. 67 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 4/21/2023 | 9/22/2023 | 10/10/2023 | 485315 | 458655 | 354876
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | PATH OF TRAVEL PLAYGROUNDS | Design | Complete | 9/1/2022 | 1/5/2023 | 1/27/2023 | 25426 | 25426 | 22928
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA DOMESTIC PIPING / IDA ELECTRICAL SYSTEMS / IDA CLIMATE CONTROL | Scope | Complete | 10/8/2021 | 2/14/2022 | 2/3/2022 | 65530 | 85203 | 85203
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / IDA DOMESTIC PIPING / IDA ELECTRICAL SYSTEMS / IDA CLIMATE CONTROL | Design | Complete | 9/21/2022 | 2/9/2023 | 2/16/2023 | 316124 | 250740 | 238687
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/1/2022 | 11/1/2022 | 7/22/2022 | 4534 | 3758 | 3758
26 | Q074 | I.S. 74 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 7/22/2022 | 1/20/2023 | 1/18/2023 | 20403 | 15035 | 15035
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | Scope | Complete | 3/14/2018 | 7/27/2018 | 8/22/2018 | 59355 | 20865 | 20865
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | DETERIORATED MASONRY | Design | Complete | 9/19/2018 | 2/25/2019 | 5/13/2019 | 237420 | 150757 | 135425
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 4/28/2022 | 9/13/2022 | 8/9/2022 | 10940 | 26008 | 15031
26 | Q098 | P.S. 98 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 8/12/2022 | 1/18/2023 | 12/22/2022 | 49230 | 59433 | 58021
26 | Q098 | P.S. 98 - QUEENS | SCA CIP RESOA | FY20 RESO A SUPPLEMENTAL COOLING | Design | Complete | 6/8/2021 | 11/29/2021 | 2/11/2022 | 48700 | 91408 | 15544
26 | Q130 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/20/2021 | 9/20/2021 | 7/23/2021 | 80154 | 66860 | 66860
26 | Q130 | P.S. 130 - QUEENS | SCA CIP | DOMESTIC WATER HEATER REPLACEMENT / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 7/27/2021 | 1/27/2022 | 12/15/2021 | 400084 | 369033 | 301882
26 | Q133 | P.S. 133 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 6/30/2023 | 11/16/2023 | 11/22/2023 | 89511 | 204516 | 204516
26 | Q133 | P.S. 133 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / PARAPETS | Design | Complete | 12/13/2023 | 5/15/2024 | 4/30/2024 | 446924 | 420323 | 337977
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 11/13/2023 | 4/1/2024 | 6/4/2024 | 158932 | 171026 | 171026
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | GYM CEILING | Scope | Complete | 7/6/2023 | 11/6/2023 | 1/10/2024 | 22052 | 22367 | 22367
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 9/13/2018 | 6/19/2019 | 2/20/2019 | 39159 | 28776 | 28776
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LOW VOLTAGE ELECTRICAL / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 2/20/2019 | 7/22/2019 | 5/16/2019 | 151190 | 117519 | 117082
26 | Q158 | J.H.S. 158 - QUEENS | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 12/1/2023 | 5/29/2024 | 3/6/2024 | 66300 | 21925 | 21925
26 | Q159 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/27/2022 | 11/10/2022 | 1/13/2023 | 145740 | 285393 | 275306
26 | Q159 | P.S. 159 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 1/18/2023 | 6/20/2023 | 5/5/2023 | 728699 | 700564 | 602626
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 5/15/2024 | 10/1/2024 | 9/17/2024 | 32273 | 46877 | 4159
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Scope | Complete | 6/1/2023 | 1/26/2024 | 12/20/2023 | 14541 | 64025 | 51367
26 | Q162 | P.S. 162 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL PLAYGROUND REDEVELOPMENT | Design | Complete | 1/23/2024 | 5/23/2024 | 5/10/2024 | 71092 | 152206 | 148198
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/11/2019 | 10/25/2019 | 10/25/2019 | 151880 | 217371 | 217371
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/13/2019 | 6/15/2020 | 4/14/2020 | 759401 | 721358 | 568650
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/16/2022 | 9/14/2022 | 6/15/2022 | 5258 | 4117 | 4117
26 | Q172 | J.H.S. 172 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 23661 | 16466 | 16466
26 | Q173 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/16/2021 | 12/15/2021 | 11/4/2021 | 63240 | 150549 | 150549
26 | Q173 | P.S. 173 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/18/2021 | 6/30/2022 | 4/18/2022 | 316200 | 301863 | 301863
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 10/15/2015 | 3/21/2016 | 12/31/2015 | 122396 | 132963 | 118763
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/6/2016 | 6/7/2016 | 6/24/2016 | 480196 | 555060 | 549191
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IDA FLOOD ELIMINATION | Scope | Complete | 1/20/2022 | 5/23/2022 | 8/5/2022 | 28144 | 49861 | 2671
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 9/20/2017 | 4/10/2019 | 3/26/2019 | 251255 | 197789 | 197586
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | PARTIAL ACCESSIBILITY / FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 3/26/2019 | 8/23/2019 | 5/17/2019 | 994516 | 620741 | 551146
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/26/2022 | 9/26/2022 | 6/15/2022 | 3814 | 4553 | 4553
26 | Q177 | Q177 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/15/2022 | 12/12/2022 | 12/7/2022 | 17165 | 18211 | 18211
26 | Q178 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/29/2022 | 10/28/2022 | 9/28/2022 | 3560 | 4864 | 4864
26 | Q178 | P.S. 178 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/28/2022 | 3/29/2023 | 3/29/2023 | 16020 | 19454 | 19454
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/14/2022 | 4/17/2023 | 1/3/2023 | 4078 | 4810 | 4810
26 | Q179 | Q004 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/3/2023 | 6/29/2023 | 3/29/2023 | 18349 | 19239 | 19239
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | Scope | Complete | 1/14/2020 | 5/29/2020 | 5/3/2021 | 123354 | 174365 | 174351
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / EXTERIOR DOORS / WINDOWS | Design | Complete | 5/24/2021 | 10/25/2021 | 2/2/2022 | 615417 | 576155 | 491421
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/17/2023 | 7/18/2023 | 3/28/2023 | 4640 | 2926 | 2926
26 | Q186 | P.S. 186 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/28/2023 | 9/21/2023 | 5/3/2023 | 20880 | 11704 | 11704
26 | Q191 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/10/2023 | 7/11/2023 | 3/29/2023 | 4800 | 1852 | 1852
26 | Q191 | P.S. 191 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/29/2023 | 9/22/2023 | 5/3/2023 | 21600 | 7407 | 7407
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | Scope | Complete | 12/22/2017 | 5/10/2018 | 3/2/2018 | 58200 | 78279 | 78279
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | WINDOWS | Design | Complete | 3/14/2018 | 8/13/2018 | 5/14/2018 | 232800 | 323404 | 281698
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/27/2019 | 11/29/2019 | 8/23/2019 | 65750 | 58621 | 58621
26 | Q203 | P.S. 203 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/10/2019 | 2/13/2020 | 12/20/2019 | 328750 | 279484 | 279484
26 | Q205 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/1/2023 | 6/29/2023 | 3/3/2023 | 3700 | 7021 | 7021
26 | Q205 | P.S. 205 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/3/2023 | 8/28/2023 | 5/3/2023 | 16650 | 28085 | 28085
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | Complete | 6/3/2019 | 10/17/2019 | 12/23/2019 | 219544 | 246745 | 233661
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | WATER PENETRATION IN BOILER ROOM / CLIMATE CONTROL / HEATING PLANT UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE / ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | Complete | 10/6/2021 | 4/13/2022 | 1/5/2023 | 1080292 | 963036 | 802489
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 10/14/2022 | 3/6/2023 | 2/22/2023 | 156066 | 158212 | 154315
26 | Q213 | P.S. 213 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 4/4/2023 | 9/5/2023 | 9/7/2023 | 780330 | 333723 | 333723
26 | Q216 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | Scope | Complete | 5/16/2022 | 2/28/2023 | 2/28/2023 | 1281380 | 791344 | 754930
26 | Q216 | J.H.S. 216 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK-ELECTRICAL SYSTEMS | Design | Complete | 2/28/2023 | 6/12/2023 | 5/12/2023 | 5766210 | 1788272 | 1223407
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 12/16/2014 | 5/19/2015 | 4/10/2015 | 90011 | 96465 | 96465
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 4/17/2015 | 9/17/2015 | 9/22/2015 | 360045 | 303431 | 287334
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 10/29/2018 | 3/19/2019 | 3/21/2019 | 257999 | 136796 | 136796
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 3/21/2019 | 8/9/2019 | 5/17/2019 | 1032001 | 653717 | 651217
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA ELECTRICAL UPGRADE / IDA WASTE SYSTEMS / IDA MECHANICAL PIPING / IDA INTERIOR SPACES | Scope | Complete | 6/16/2022 | 11/1/2022 | 9/18/2024 | 294820 | 23725 | 23725
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | Scope | Complete | 6/6/2022 | 11/29/2022 | 11/29/2022 | 28900 | 32864 | 32864
26 | Q216 | J.H.S. 216 - QUEENS | SCA CIP | IDA FIRE ALARM SYSTEM REPLACEMENT / EARLY PACKAGE/TEMPORARY EGRESS | Design | Complete | 11/29/2022 | 3/16/2023 | 3/21/2023 | 144499 | 124371 | 115064
26 | Q221 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 8/31/2022 | 3/1/2023 | 12/9/2022 | 96409 | 189852 | 189601
26 | Q221 | P.S. 221 - QUEENS | SCA CIP | ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 12/9/2022 | 6/7/2023 | 4/21/2023 | 478159 | 468655 | 468581
26 | Q405 | BAYSIDE HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY19 RESO A ROOM CONVERSION | Design | Complete | 4/21/2021 | 9/10/2021 | 3/9/2022 | 72738 | 88757 | 81267
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | RPZ VALVES | Scope | Complete | 10/23/2018 | 4/23/2019 | 9/12/2019 | 10924 | 40933 | 40933
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | RPZ VALVES | Design | Complete | 9/6/2022 | 3/7/2023 | 3/2/2023 | 54621 | 133621 | 133621
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | Scope | Complete | 3/4/2021 | 7/2/2021 | 7/22/2021 | 24450 | 20729 | 20729
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | AUDITORIUM CEILING | Design | Complete | 7/28/2021 | 12/30/2021 | 12/29/2021 | 122250 | 79175 | 79175
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 8/5/2020 | 1/8/2021 | 12/23/2020 | 116640 | 154281 | 154281
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/28/2020 | 7/30/2021 | 7/1/2021 | 583200 | 671261 | 642321
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 3/5/2020 | 7/6/2020 | 3/6/2020 | 15792 | 9506 | 9506
26 | Q415 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 3/6/2020 | 8/5/2020 | 5/12/2020 | 58829 | 38027 | 38027
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / NON-IDA REINFORCE SUPPORT ELEMENTS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES | Scope | Complete | 9/29/2022 | 2/17/2023 | 2/21/2023 | 114924 | 181019 | 177742
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / NON-IDA REINFORCE SUPPORT ELEMENTS / IDA HEATING PLANT UPGRADE / IDA INTERIOR SPACES | Design | Complete | 2/21/2023 | 7/24/2023 | 7/26/2023 | 568324 | 420902 | 382827
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | Scope | Complete | 3/19/2018 | 5/24/2019 | 7/30/2019 | 30972 | 46993 | 46993
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | RPZ VALVES / FIRE ALARM | Design | Complete | 9/12/2019 | 3/19/2020 | 6/10/2020 | 148068 | 207365 | 207049
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 3/21/2022 | 4/4/2022 | 4/4/2022 | 11376 | 28137 | 63
26 | Q430 | FRANCIS LEWIS HS - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 4/5/2022 | 8/12/2022 | 4/12/2023 | 56882 | 65759 | 31627
26 | Q431 | FRANCIS LEWIS HS - QUEENS | SCA CIP RESOA | FY20 RESO A ATHLETIC FIELD UPGRADE | Design | Complete | 3/21/2022 | 8/18/2022 | 4/12/2023 | 746531 | 519555 | 426171
26 | Q435 | MARTIN VAN BUREN HS - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 6/30/2022 | 11/16/2022 | 6/15/2023 | 107878 | 162223 | 162223
26 | Q469 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/6/2023 | 2/8/2024 | 2/7/2024 | 5146 | 26758 | 26758
26 | Q469 | BENJAMIN N. CARDOZO HS - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 2/7/2024 | 6/24/2024 | 4/18/2024 | 23159 | 107026 | 107026
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Scope | Complete | 6/26/2023 | 12/22/2023 | 10/3/2023 | 148504 | 144417 | 131995
26 | Q566 | QNS HS OF TEACH., LIB. ARTS&SCI-Q | SCA CIP | ROOFS / PARAPETS / FIRE ALARM SYSTEM / EXTERIOR MASONRY | Design | Complete | 10/10/2023 | 6/10/2024 | 4/2/2024 | 735127 | 320329 | 320329
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 9/25/2015 | 1/25/2016 | 12/18/2015 | 83700 | 136933 | 126733
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/7/2016 | 2/10/2017 | 5/5/2017 | 334800 | 681337 | 665837
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/15/2023 | 7/14/2023 | 3/20/2023 | 3900 | 2239 | 2239
26 | Q811 | Q811 SPED - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/20/2023 | 9/13/2023 | 5/3/2023 | 17550 | 8954 | 8954
26 | Q811 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 515 | 515
26 | Q811 | Q811 SPED - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 2600 | 20145 | 20145
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | Scope | Complete | 2/7/2014 | 7/10/2014 | 4/8/2014 | 251956 | 218691 | 218691
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | SANDY:INTERIOR SPACES / HEATING PLANT / FLOOD ELIM / SANITARY / STORM PIPING / HVAC / ELEC SYS / NON-SANDY: CLIMATE CTRL / ELEC SYS | Design | Complete | 4/8/2014 | 9/8/2014 | 9/11/2014 | 991112 | 1581649 | 1450071
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 3/12/2021 | 7/27/2021 | 9/1/2021 | 166231 | 167700 | 167700
27 | Q042 | P.S. 42 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 9/17/2021 | 2/23/2022 | 3/10/2022 | 824628 | 562834 | 544807
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 7/31/2018 | 10/30/2018 | 12/12/2018 | 17685 | 39477 | 39477
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 1/7/2019 | 5/29/2019 | 5/17/2019 | 70740 | 143998 | 143070
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | Scope | Complete | 8/30/2019 | 1/21/2020 | 10/27/2021 | 140840 | 193990 | 193990
27 | Q043 | P.S. 43 - QUEENS | SCA CIP | AIR CONDITIONING SPLIT SYSTEM / WINDOWS / CLIMATE CONTROL / EXTERIOR MASONRY | Design | Complete | 11/5/2021 | 4/12/2022 | 5/5/2022 | 704200 | 539644 | 475909
27 | Q045 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 10/17/2018 | 3/7/2019 | 2/20/2019 | 182490 | 114694 | 114694
27 | Q045 | P.S. 45 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 2/20/2019 | 7/22/2019 | 5/10/2019 | 729960 | 679654 | 580970
27 | Q051 | P.S. 51 - QUEENS | SCA CIP | C OF O | Scope | Complete | 6/7/2021 | 9/10/2021 | 11/1/2021 | 7920 | 27204 | 27204
27 | Q051 | P.S. 51 - QUEENS | SCA CIP | C OF O | Design | Complete | 12/22/2021 | 6/16/2022 | 10/13/2022 | 35640 | 54321 | 44720
27 | Q051 | P.S. 51 - QUEENS | SCA CIP | C OF O | Construction | Complete | 2/6/2023 | 12/2/2023 | 11/29/2023 | 459360 | 414765 | 355588
27 | Q051 | P.S. 51 - QUEENS | SCA CIP | C OF O | CM,F&E | Complete | 2/6/2023 | 12/2/2023 | 11/29/2023 | 85140 | 64731 | 63914
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 10/3/2018 | 3/11/2019 | 1/14/2019 | 141298 | 141108 | 141108
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/30/2019 | 7/1/2019 | 5/15/2019 | 608905 | 661166 | 644194
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | WALK-IN REFRIGERTAORS AND FREEZERS | Scope | Complete | 6/23/2023 | 10/23/2023 | 9/25/2023 | 11669 | 15501 | 15501
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | WALK-IN REFRIGERTAORS AND FREEZERS | Design | Complete | 10/2/2023 | 3/1/2024 | 2/7/2024 | 52511 | 45806 | 43297
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | Scope | Complete | 6/24/2021 | 1/12/2022 | 1/20/2022 | 15933 | 21058 | 21058
27 | Q053 | I.S. 53 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM SEATING | Design | Complete | 1/21/2022 | 5/23/2022 | 4/11/2022 | 79562 | 74014 | 74014
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/31/2019 | 3/15/2019 | 3/27/2019 | 18375 | 39878 | 39878
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | TCU REMOVAL/PLAYGROUND REDEVELOPMENT | Design | Complete | 3/27/2019 | 5/17/2019 | 5/17/2019 | 73500 | 110142 | 98295
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 10/8/2019 | 1/10/2020 | 1/31/2020 | 17800 | 27547 | 27547
27 | Q056 | P.S. 56 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 2/19/2020 | 7/20/2020 | 10/6/2021 | 80100 | 115376 | 102211
27 | Q056 | P.S. 56 - QUEENS | SCA CIP RESOA | FY21 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 1/6/2022 | 7/1/2022 | 3/2/2022 | 24000 | 10503 | 10503
27 | Q062 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/22/2023 | 11/7/2023 | 11/3/2023 | 110505 | 192691 | 166878
27 | Q062 | P.S. 62 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/15/2023 | 4/18/2024 | 5/7/2024 | 547485 | 397209 | 266525
27 | Q062 | P.S. 62 - QUEENS | SCA CIP RESOA | FY20 RESO A COMPUTER LAB | Design | Complete | 2/10/2022 | 8/1/2022 | 8/10/2022 | 72000 | 74678 | 58807
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | Scope | Complete | 8/22/2019 | 1/28/2020 | 2/24/2020 | 19870 | 59530 | 59530
27 | Q063 | P.S. 63 - QUEENS | SCA CIP | RTU REPLACEMENT | Design | Complete | 2/16/2021 | 7/16/2021 | 2/22/2022 | 99350 | 353007 | 294848
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | Scope | Complete | 6/13/2017 | 10/13/2017 | 9/25/2017 | 27870 | 25449 | 25449
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | AUDITORIUM UPGRADE | Design | Complete | 2/21/2018 | 7/23/2018 | 5/18/2018 | 102190 | 146069 | 145944
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Scope | Complete | 1/13/2020 | 4/13/2020 | 9/24/2021 | 83050 | 91254 | 91254
27 | Q090 | P.S. 90 - QUEENS | SCA CIP | FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Design | Complete | 9/29/2021 | 4/6/2022 | 5/10/2023 | 415250 | 438755 | 349553
27 | Q096 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | Scope | Complete | 1/27/2020 | 3/1/2021 | 3/9/2021 | 1142001 | 765038 | 673538
27 | Q096 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | Design | Complete | 3/10/2021 | 8/26/2021 | 5/11/2022 | 5138999 | 2766588 | 1817462
27 | Q096 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | Construction | Complete | 7/25/2022 | 9/3/2024 | 9/5/2024 | 64808500 | 71805710 | 37099513
27 | Q096 | P.S. 96 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING RENOVATION WORK / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA | CM,Art,F&E | Complete | 7/25/2022 | 9/3/2024 | 9/5/2024 | 9136001 | 7127195 | 4519014
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 10/27/2020 | 10/27/2020 | 10/27/2020 | 15255 | 19371 | 19371
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 12/18/2020 | 5/28/2021 | 1/20/2022 | 68649 | 31719 | 31719
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 10/27/2020 | 10/27/2020 | 10/27/2020 | 29810 | 65191 | 65191
27 | Q096 | P.S. 96 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 10/28/2020 | 2/1/2021 | 2/2/2021 | 149050 | 356566 | 323659
27 | Q097 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | Scope | Complete | 1/29/2020 | 6/12/2020 | 11/19/2021 | 94746 | 147366 | 129997
27 | Q097 | P.S. 97 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY / RTU REPLACEMENT | Design | Complete | 12/1/2021 | 5/4/2022 | 5/13/2022 | 464365 | 444799 | 411971
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Design | Complete | 1/5/2022 | 5/4/2022 | 3/28/2022 | 55500 | 82134 | 80424
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | Construction | Complete | 2/27/2023 | 1/22/2024 | 1/22/2024 | 814000 | 628659 | 568582
27 | Q097 | P.S. 97 - QUEENS | SCA CIP RESOA | FY21 RESO A ROOM CONVERSION / PATH OF TRAVEL RESO A ROOM CONVERSION | CM,F&E | Complete | 2/27/2023 | 1/22/2024 | 1/22/2024 | 172531 | 180144 | 165651
27 | Q100 | P.S. 100 - QUEENS | SCA CIP | ROOFS / EMERGENCY GENERATOR / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/6/2023 | 162840 | 272979 | 246515
27 | Q100 | P.S. 100 - QUEENS | SCA CIP | ROOFS / EMERGENCY GENERATOR / EXTERIOR MASONRY / WINDOWS / PARAPETS | Design | Complete | 11/3/2023 | 6/28/2024 | 4/19/2024 | 804579 | 472745 | 461724
27 | Q104 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | Scope | Complete | 5/22/2019 | 8/21/2019 | 8/13/2019 | 13950 | 31091 | 31091
27 | Q104 | P.S. 104 - QUEENS | SCA CIP | DOWNTOWN FAR ROCKAWAY REZONING PARK UPGRADES | Design | Complete | 8/27/2019 | 1/15/2020 | 3/31/2020 | 62775 | 81374 | 74898
27 | Q105 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 4/11/2023 | 44850 | 69697 | 32433
27 | Q105 | P.S. 105 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 12/1/2023 | 5/3/2024 | 5/8/2024 | 224250 | 326553 | 12055
27 | Q108 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 6/10/2022 | 9/9/2022 | 9/14/2022 | 14880 | 3551 | 3551
27 | Q108 | P.S. 108 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 9/14/2022 | 2/17/2023 | 2/15/2023 | 66960 | 14206 | 14206
27 | Q114 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 9/7/2022 | 1/10/2023 | 11/15/2022 | 4575 | 5553 | 5553
27 | Q114 | P.S. 114 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 11/15/2022 | 5/12/2023 | 3/8/2023 | 20588 | 22212 | 22212
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | Scope | Complete | 7/20/2015 | 1/21/2016 | 10/21/2015 | 16230 | 58517 | 58517
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | TCU REMOVAL & PLAYGROUND REDEVELOPMENT | Design | Complete | 11/10/2015 | 5/13/2016 | 5/10/2016 | 64920 | 171005 | 169001
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 6/3/2021 | 12/2/2021 | 10/28/2021 | 239100 | 197674 | 197674
27 | Q123 | P.S. 123 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 11/24/2021 | 6/30/2022 | 4/25/2022 | 1195500 | 343750 | 343750
27 | Q123 | P.S. 123 - QUEENS | SCA CIP RESOA | FY19 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 12/3/2019 | 4/3/2020 | 4/2/2021 | 37599 | 97472 | 97366
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 10/17/2016 | 3/22/2017 | 11/22/2016 | 81210 | 126281 | 126281
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 12/7/2016 | 5/10/2017 | 5/11/2017 | 324840 | 716031 | 664794
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Scope | Complete | 5/28/2019 | 9/30/2019 | 11/21/2019 | 82346 | 49659 | 49659
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | HVAC CHILLER SYSTEM / FIRE ALARM SYSTEM REPLACEMENT / VENTILATION | Design | Complete | 1/8/2020 | 6/15/2020 | 9/30/2022 | 403783 | 335819 | 272631
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | Scope | Complete | 3/11/2022 | 7/11/2022 | 3/11/2022 | 3800 | 5517 | 5517
27 | Q124 | P.S. 124 - QUEENS | SCA CIP | IPDVS INSTALLATION | Design | Complete | 3/16/2022 | 9/8/2022 | 7/18/2022 | 17100 | 22067 | 22067
27 | Q124 | P.S. 124 - QUEENS | SCA CIP RESOA | FY21 RESO A ATHLETIC FIELDS | Design | Complete | 3/16/2022 | 9/6/2022 | 3/31/2023 | 184726 | 79477 | 71146
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Design | Complete | 5/1/2020 | 1/29/2021 | 12/23/2020 | 22184 | 28065 | 28065
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | Construction | Complete | 5/19/2021 | 2/12/2022 | 12/5/2023 | 325359 | 341938 | 290898
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 5/19/2021 | 2/12/2022 | 12/5/2023 | 22184 | 38586 | 37908
27 | Q137 | M.S. 137 - QUEENS | SCA CIP RESOA | FY20 RESO A GYMNASIUM UPGRADE | Design | Complete | 9/6/2022 | 1/25/2023 | 3/8/2023 | 32076 | 41455 | 40844
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 10/4/2023 | 2/23/2024 | 9/5/2024 | 17815 | 83009 | 57194
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/22/2022 | 3/27/2023 | 1/6/2023 | 4425 | 1533 | 1533
27 | Q146 | P.S. 146 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/6/2023 | 7/5/2023 | 3/8/2023 | 19913 | 6133 | 6133
27 | Q155 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 10/30/2018 | 3/20/2019 | 4/1/2019 | 144558 | 109736 | 109206
27 | Q155 | P.S. 155 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 4/1/2019 | 8/29/2019 | 5/17/2019 | 576841 | 606067 | 553413
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 5/10/2021 | 9/23/2021 | 1/21/2022 | 70940 | 88041 | 88041
27 | Q180 | THE SCHOLARS ACADEMY - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/26/2022 | 6/27/2022 | 9/13/2022 | 354701 | 386145 | 342930
27 | Q183 | P.S. 183 - QUEENS | SCA CIP RESOA | FY19 RESO A PLAYGROUND / PATH OF TRAVEL RESO A PLAYGROUND | Design | Complete | 9/18/2019 | 11/15/2019 | 9/20/2019 | 76620 | 138194 | 102608
27 | Q197 | P.S. 197 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A PLAYGROUND UPGRADE / FY21 RESO A PLAYGROUND UPGRADE / RETAINING WALL | Design | Complete | 2/7/2022 | 6/7/2022 | 4/14/2022 | 44818 | 52381 | 41220
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 7/3/2019 | 11/19/2019 | 1/13/2020 | 85659 | 126169 | 126169
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 1/13/2020 | 6/12/2020 | 4/23/2021 | 425946 | 498752 | 404146
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/1/2022 | 4/4/2023 | 1/4/2023 | 4080 | 1163 | 1163
27 | Q198 | P.S. 333 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/4/2023 | 6/30/2023 | 3/15/2023 | 18360 | 4650 | 4650
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY / SIDEWALK REPAIR / WINDOWS | Scope | Complete | 3/15/2022 | 9/13/2022 | 7/22/2022 | 213666 | 204330 | 201540
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS / ROOFS / EXTERIOR MASONRY / SIDEWALK REPAIR / WINDOWS | Design | Complete | 7/28/2022 | 1/26/2023 | 1/12/2023 | 1057363 | 373260 | 372698
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 8/13/2020 | 1/19/2021 | 12/28/2020 | 82125 | 70485 | 70485
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 12/31/2020 | 7/30/2021 | 7/6/2021 | 410625 | 292732 | 267814
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/23/2023 | 10/23/2023 | 9/25/2023 | 14789 | 15828 | 15828
27 | Q202 | I.S. 202 - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/2/2023 | 3/1/2024 | 2/7/2024 | 66551 | 69219 | 52153
27 | Q207 | P.S. 207 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/11/2023 | 11/27/2023 | 11/8/2023 | 37896 | 81772 | 73194
27 | Q207 | P.S. 207 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 11/15/2023 | 4/18/2024 | 5/14/2024 | 188387 | 198182 | 175977
27 | Q207 | P.S. 207 - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 7/5/2023 | 11/6/2023 | 9/26/2023 | 45000 | 62721 | 56457
27 | Q215 | P.S. 362 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/10/2024 | 11/7/2024 | 7/16/2024 | 4615 | 777 | 777
27 | Q225 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 7/8/2022 | 11/23/2022 | 12/4/2023 | 113791 | 253376 | 248313
27 | Q225 | P.S. 317 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 12/8/2023 | 5/10/2024 | 4/29/2024 | 568955 | 400064 | 355660
27 | Q225 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/24/2023 | 9/25/2023 | 5/25/2023 | 3454 | 251 | 251
27 | Q225 | P.S. 225 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 5/25/2023 | 11/22/2023 | 9/20/2023 | 15543 | 1006 | 1006
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | Scope | Complete | 2/14/2019 | 5/31/2019 | 3/14/2022 | 36801 | 43438 | 43438
27 | Q226 | EPIC HIGH SCHOOL - SOUTH | SCA CIP | SCIENCE LAB | Design | Complete | 3/14/2022 | 9/13/2022 | 5/11/2022 | 184005 | 190368 | 176694
27 | Q226 | I.S. 226 - QUEENS | SCA CIP | RTU REPLACEMENT / ROOFS | Scope | Complete | 9/22/2021 | 1/31/2022 | 5/10/2022 | 72216 | 55373 | 55373
27 | Q226 | I.S. 226 - QUEENS | SCA CIP | RTU REPLACEMENT / ROOFS | Design | Complete | 6/27/2022 | 11/29/2022 | 4/13/2023 | 357504 | 227797 | 187644
27 | Q232 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | Scope | Complete | 4/10/2018 | 8/23/2018 | 8/21/2018 | 243681 | 219947 | 216136
27 | Q232 | P.S. 232 - QUEENS | SCA CIP | WATER INFILTRATION / PLANYC BOILER / PLANYC CLIMATE CONTROL / LOW-VOLTAGE ELECTRICAL SYSTEM / EXTERIOR MASONRY | Design | Complete | 9/19/2018 | 2/25/2019 | 5/7/2019 | 967549 | 755815 | 655486
27 | Q253 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/21/2022 | 4/24/2023 | 1/6/2023 | 5000 | 901 | 901
27 | Q253 | P.S. 253 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/6/2023 | 7/5/2023 | 3/15/2023 | 22500 | 3606 | 3606
27 | Q254 | P.S. 254 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 7/5/2024 | 11/4/2024 | 7/16/2024 | 4124 | 562 | 562
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS / FIRE ALARM PANEL | Scope | Complete | 10/12/2023 | 3/12/2024 | 3/1/2024 | 128835 | 282882 | 14954
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / ROOFS / FIRE ALARM PANEL | Design | Complete | 3/1/2024 | 10/1/2024 | 5/7/2024 | 638381 | 393964 | 39960
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 4/1/2022 | 8/1/2022 | 5/3/2022 | 2480 | 1463 | 1463
27 | Q262 | P.S. 306 - QUEENS | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 5/3/2022 | 10/27/2022 | 7/18/2022 | 11160 | 5852 | 5852
27 | Q273 | P.S. 273 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Scope | Complete | 10/18/2023 | 3/18/2024 | 3/4/2024 | 64756 | 150639 | 119606
27 | Q273 | P.S. 273 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS | Design | Complete | 3/4/2024 | 8/2/2024 | 5/14/2024 | 323780 | 569922 | 36226
27 | Q401 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | Scope | Complete | 5/22/2020 | 11/14/2022 | 11/9/2022 | 439294 | 1046675 | 1030855
27 | Q401 | AUGUST MARTIN HS - QUEENS | SCA CIP | ATHLETIC FIELD UPGRADE / PATH OF TRAVEL ATHLETIC FIELD UPGRADE / FIELD HOUSE | Design | Complete | 11/18/2022 | 5/18/2023 | 4/25/2023 | 2193674 | 2450939 | 2347543
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | SEA WALL / BULKHEAD REPAIR | Scope | Complete | 4/16/2019 | 7/16/2019 | 10/10/2019 | 166282 | 176449 | 174871
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 4/11/2022 | 8/24/2022 | 3/15/2023 | 39968 | 96792 | 77384
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 3/16/2023 | 8/16/2023 | 5/12/2023 | 199839 | 227987 | 208210
27 | Q410 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP RESOA | FY20 RESO A WEIGHT ROOM | Design | Complete | 9/19/2023 | 2/7/2024 | 4/9/2024 | 156382 | 96027 | 92399
27 | Q410 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 210 | 210
27 | Q410 | BEACH CHANNEL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 2600 | 6281 | 6281
27 | Q411 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | Scope | Complete | 6/18/2019 | 10/18/2019 | 9/13/2019 | 43620 | 82381 | 82381
27 | Q411 | CHANNEL VIEW SCL FOR RESEARCH - Q | SCA CIP | TENNIS COURT REMEDIATION | Design | Complete | 11/4/2019 | 4/8/2020 | 11/4/2021 | 218100 | 557678 | 501004
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | Scope | Complete | 5/21/2021 | 8/20/2021 | 7/20/2021 | 25550 | 127063 | 107450
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | PAVED AREAS CONCRETE- SIDEWALKS & COURTYARD | Design | Complete | 8/4/2021 | 12/21/2021 | 11/22/2021 | 127750 | 208414 | 192727
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | SWIMMING POOL / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/5/2021 | 4/11/2024 | 5/8/2024 | 83498 | 99922 | 99922
27 | Q465 | M.S. 282 - QUEENS | SCA CIP | SWIMMING POOL / LOW VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 5/8/2024 | 10/9/2024 | 5/15/2024 | 417490 | 296271 | 273816
27 | Q465 | ACAD. OF MEDICAL TECHNOLOGY - Q | SCA CIP RESOA | FY23 RESO A ELECTRICAL UPGRADE | Design | Complete | 11/7/2023 | 4/11/2024 | 4/24/2024 | 30000 | 16772 | 16772
27 | Q465 | QNS HS FOR INF. RESEARCH & TECH.-Q | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 7/16/2024 | 10/15/2024 | 8/23/2024 | 6341 | 6341 | 0
27 | Q465 | M.S. 282 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL ROOM CONVERSION / FY20 RESO A ROBOTICS LAB | Design | Complete | 3/16/2022 | 8/15/2022 | 4/4/2023 | 187765 | 141899 | 128465
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | Scope | Complete | 11/1/2019 | 4/26/2022 | 4/26/2022 | 244246 | 217526 | 216718
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP | LOCKER ROOM UPGRADE / LOW VOLTAGE ELECTRICAL SYSTEM / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / POOL WATER HEATER & FILTRATION | Design | Complete | 4/27/2022 | 7/27/2022 | 5/6/2022 | 1216979 | 1400629 | 1241122
27 | Q475 | RICHMOND HILL HS - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A LIBRARY UPGRADE / FY22 RESO A LIBRARY UPGRADE | Design | Complete | 11/18/2022 | 3/23/2023 | 1/13/2023 | 54701 | 145811 | 91707
27 | Q475 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 784 | 784
27 | Q475 | RICHMOND HILL H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 2600 | 62101 | 62101
27 | Q477 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 3/3/2021 | 6/2/2021 | 6/3/2021 | 8740 | 18719 | 18719
27 | Q477 | CURIOUS YOUNG LEARNERS PRE-K CENTER | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | Complete | 6/14/2021 | 10/28/2021 | 12/2/2021 | 39330 | 73278 | 61977
27 | Q480 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 205 | 205
27 | Q480 | JOHN ADAMS HS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 2600 | 25502 | 25502
27 | Q509 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | Scope | Complete | 6/9/2022 | 10/19/2022 | 10/19/2022 | 234660 | 227032 | 227032
27 | Q509 | P.S. @ 101-11 104 STREET - QUEENS | SCA Lease Site Improvement | LEASE / LEASED SITE- MULTIPURPOSE ROOM UPGRADE | Design | Complete | 10/19/2022 | 3/23/2023 | 4/10/2023 | 1055970 | 577324 | 429248
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 1/23/2024 | 6/26/2024 | 6/26/2024 | 1824024 | 1436643 | 1308022
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 3/26/2024 | 3/26/2024 | 3/26/2024 | 56496 | 5253 | 5253
27 | Q578 | P.S. @ 120-08 JAMAICA AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 5/16/2024 | 5/16/2024 | 5/16/2024 | 43889 | 1069 | 1069
27 | Q593 | P.S. 47 - QUEENS | SCA CIP | PATH OF TRAVEL | Scope | Complete | 1/3/2024 | 4/4/2024 | 3/20/2024 | 2918 | 20436 | 284
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP | ROOFS / WINDOWS / PARAPETS | Scope | Complete | 12/21/2023 | 5/8/2024 | 9/3/2024 | 55627 | 72264 | 72264
27 | Q650 | HS FOR CONST.TRADES,ENGG.,& ARCH-Q | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 6/6/2019 | 11/6/2019 | 5/15/2020 | 41805 | 78714 | 78714
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/24/2020 | 10/23/2020 | 9/23/2020 | 2400 | 3740 | 3740
27 | Q781 | SUCCESS ACADEMY CHARTER SCHOOL - SOUTH JAMAICA | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/23/2020 | 3/19/2021 | 5/5/2021 | 10800 | 14959 | 14959
27 | Q816 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | Scope | Complete | 5/8/2018 | 8/7/2018 | 5/8/2018 | 109140 | 2097 | 2097
27 | Q816 | Q256 SPED - QUEENS | SCA CIP | PHASE III WORK- DEMO AND PLAYGROUND REDEVELOPMENT | Design | Complete | 5/9/2018 | 9/24/2018 | 5/9/2018 | 436558 | 88718 | 69557
28 | Q003 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 2/14/2020 | 6/30/2020 | 3/9/2021 | 50630 | 79856 | 79856
28 | Q003 | P.S. 303 - QUEENS | SCA CIP | ROOF REPLACEMENT / PARAPETS / EXTERIOR MASONRY | Design | Complete | 4/6/2021 | 9/3/2021 | 10/21/2021 | 253151 | 496159 | 454754
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/22/2023 | 11/7/2023 | 12/5/2023 | 135084 | 235214 | 235214
28 | Q008 | J.H.S. 8 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM / ELECTRICAL UPGRADE | Scope | Complete | 10/5/2023 | 3/5/2024 | 4/8/2024 | 376066 | 12391 | 12391
28 | Q040 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | Scope | Complete | 6/22/2022 | 11/7/2022 | 2/2/2023 | 136780 | 127665 | 127665
28 | Q040 | P.S. 40 - QUEENS | SCA CIP | ROOF REPLACEMENT / WINDOWS | Design | Complete | 2/8/2023 | 7/12/2023 | 5/4/2023 | 683900 | 424448 | 359025
28 | Q054 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | Scope | Complete | 8/7/2020 | 12/7/2020 | 3/22/2021 | 19800 | 46153 | 46153
28 | Q054 | P.S. 54 - QUEENS | SCA CIP | DOMESTIC PIPING | Design | Complete | 3/31/2021 | 9/7/2021 | 12/22/2021 | 99000 | 287970 | 287970
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Scope | Complete | 5/28/2024 | 8/28/2024 | 8/20/2024 | 14475 | 14475 | 14475
28 | Q072 | J.H.S. 72 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION | Scope | Complete | 5/28/2024 | 8/28/2024 | 7/10/2024 | 201 | 201 | 201
28 | Q080 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | Scope | Complete | 5/23/2019 | 8/13/2020 | 12/16/2021 | 101108 | 159737 | 159737
28 | Q080 | P.S. 80 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION / PA SYSTEM REPLACEMENT | Design | Complete | 12/20/2021 | 5/23/2022 | 5/9/2022 | 487192 | 556614 | 480244
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 8/24/2022 | 1/30/2023 | 1/4/2023 | 32983 | 65826 | 55213
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | Complete | 5/15/2023 | 4/8/2024 | 12/14/2023 | 483756 | 449042 | 365306
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 5/15/2023 | 4/8/2024 | 12/14/2023 | 58174 | 87395 | 52276
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY22 RESO A LIBRARY UPGRADE / PATH OF TRAVEL RESO A LIBRARY UPGRADE | Design | Complete | 11/2/2022 | 3/2/2023 | 3/21/2023 | 76748 | 104339 | 92400
28 | Q080 | P.S. 80 - QUEENS | SCA CIP RESOA | FY23 RESO A MULTIMEDIA CENTER / PATH OF TRAVEL RESO A MULTIMEDIA CENTER | Design | Complete | 2/9/2024 | 6/12/2024 | 4/18/2024 | 49697 | 62378 | 40845
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 9/13/2021 | 12/14/2021 | 12/13/2021 | 13460 | 49326 | 49326
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | PLAYGROUND UPGRADE | Design | Complete | 12/14/2021 | 5/2/2022 | 5/11/2022 | 60570 | 78676 | 77158
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | Scope | Complete | 9/22/2021 | 3/2/2023 | 3/15/2023 | 30769 | 88294 | 78453
28 | Q099 | P.S. 99 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / GYM UPGRADE / PATH OF TRAVEL GYMNASIUM/AUDITORIUM UPGRADE | Design | Complete | 3/16/2023 | 7/19/2023 | 3/16/2023 | 143615 | 167054 | 48144
28 | Q117 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 3/11/2021 | 7/26/2021 | 11/22/2021 | 45500 | 67886 | 66928
28 | Q117 | P.S. 117 - QUEENS | SCA CIP | ROOF REPLACEMENT | Design | Complete | 12/1/2021 | 5/4/2022 | 4/27/2022 | 227500 | 194915 | 194915
28 | Q117 | P.S. 117 - QUEENS | SCA CIP RESOA | FY21 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 12/22/2021 | 3/14/2022 | 4/12/2022 | 72000 | 111817 | 111817
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | IPDVS | Scope | Complete | 1/6/2022 | 5/6/2022 | 1/20/2022 | 6000 | 6853 | 6853
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | IPDVS | Design | Complete | 1/21/2022 | 7/18/2022 | 7/18/2022 | 27000 | 27411 | 27411
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | Scope | Complete | 3/30/2021 | 4/12/2022 | 8/8/2022 | 64360 | 121592 | 121592
28 | Q139 | P.S. 139 - QUEENS | SCA CIP | ROOF TOP UNIT REPLACEMENTS / AUDITORIUM WATER INFILTRATION | Design | Complete | 9/22/2022 | 2/28/2023 | 4/27/2023 | 321800 | 407040 | 283924
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 5/21/2021 | 10/6/2021 | 1/21/2022 | 52876 | 103998 | 103998
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS / EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 1/21/2022 | 6/22/2022 | 5/11/2022 | 261507 | 418845 | 409146
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 5/29/2020 | 9/28/2020 | 7/21/2020 | 3616 | 9403 | 9403
28 | Q142 | Q752 SPED - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/21/2020 | 1/15/2021 | 6/2/2021 | 16272 | 37612 | 37612
28 | Q142 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 336 | 336
28 | Q142 | J.H.S. 142 | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 2600 | 29037 | 29037
28 | Q144 | P.S. 144 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/19/2019 | 11/4/2019 | 12/13/2019 | 97441 | 105724 | 105398
28 | Q144 | P.S. 144 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 12/13/2019 | 4/15/2020 | 7/30/2020 | 487200 | 479613 | 417498
28 | Q144 | P.S. 144 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Construction | Complete | 8/16/2021 | 8/15/2023 | 2/12/2024 | 10962001 | 11648984 | 9911160
28 | Q144 | P.S. 144 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | CM,F&E | Complete | 8/16/2021 | 8/15/2023 | 2/12/2024 | 682081 | 879830 | 815765
28 | Q160 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | Scope | Complete | 1/12/2021 | 1/28/2022 | 3/21/2022 | 1154320 | 843797 | 812461
28 | Q160 | P.S. 160 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING WORK-IPDVS / EXISTING BUILDING WORK- ELECTRICAL SYSTEMS | Design | Complete | 3/21/2022 | 8/18/2022 | 4/29/2022 | 5194440 | 3193894 | 2490983
28 | Q160 | P.S. 160 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-CAFETERIA / EXISTING BUILDING-GYMNASIUM | Scope | Complete | 6/14/2022 | 10/28/2022 | 12/18/2023 | 47871 | 48956 | 7460
28 | Q161 | P.S. 161 - QUEENS | SCA CIP | WINDOWS / PARAPETS | Scope | Complete | 4/26/2023 | 9/12/2023 | 9/20/2023 | 56238 | 81492 | 81492
28 | Q161 | P.S. 161 - QUEENS | SCA CIP | WINDOWS / PARAPETS | Design | Complete | 10/4/2023 | 3/11/2024 | 4/24/2024 | 279049 | 221355 | 214866
28 | Q174 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | Scope | Complete | 9/30/2020 | 3/4/2022 | 4/6/2022 | 994026 | 777767 | 748109
28 | Q174 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | Design | Complete | 4/6/2022 | 5/16/2022 | 4/25/2022 | 4473117 | 2688951 | 1996250
28 | Q174 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | Construction | Complete | 7/11/2022 | 9/3/2024 | 8/15/2024 | 56410974 | 56134968 | 51304520
28 | Q174 | P.S. 174 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING-IPDVS | CM,Art,F&E | Complete | 7/11/2022 | 9/3/2024 | 8/15/2024 | 7952208 | 6550712 | 4718993
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | EXISTING BUILDING-PA/CLOCK SYSTEMS / EXISTING BUILDING-FIRE ALARM SYSTEM / EXISTING BUILDING- INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-GYMNASIUM | Scope | Complete | 10/28/2021 | 3/4/2022 | 6/3/2022 | 46084 | 60855 | 60855
28 | Q174 | P.S. 174 - QUEENS | SCA CIP | EXISTING BUILDING-PA/CLOCK SYSTEMS / EXISTING BUILDING-FIRE ALARM SYSTEM / EXISTING BUILDING- INTERIOR RENOVATIONS / EXISTING BUILDING-AUDITORIUM / EXISTING BUILDING-GYMNASIUM | Design | Complete | 6/22/2022 | 12/9/2022 | 7/17/2023 | 220019 | 203306 | 198725
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 1/27/2020 | 6/25/2020 | 4/10/2020 | 79690 | 71062 | 71062
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 4/15/2020 | 9/15/2020 | 7/29/2020 | 398450 | 365819 | 304404
28 | Q190 | J.H.S. 190 - QUEENS | SCA CIP RESOA | FY23 RESO A SCHOOLYARD UPGRADE | Design | Complete | 8/24/2023 | 1/12/2024 | 5/30/2024 | 60000 | 64745 | 58640
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - EXISTING SCHOOL RENOVATION WORK | Scope | Complete | 2/19/2020 | 7/17/2020 | 7/27/2021 | 35448 | 47023 | 47023
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - EXISTING SCHOOL RENOVATION WORK | Design | Complete | 8/10/2021 | 1/4/2022 | 7/24/2023 | 177239 | 228874 | 211840
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/13/2022 | 11/29/2022 | 7/25/2023 | 78905 | 178697 | 177228
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 8/25/2023 | 1/31/2024 | 4/25/2024 | 394527 | 300729 | 291538
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - DEMOLITION OF TCU UNIT AND PLAYGROUND DEVELOPMENT | Scope | Complete | 12/6/2022 | 3/9/2023 | 5/15/2023 | 27156 | 46122 | 46122
28 | Q206 | P.S. 206 - QUEENS | SCA CIP | SSBA - DEMOLITION OF TCU UNIT AND PLAYGROUND DEVELOPMENT | Design | Complete | 5/16/2023 | 10/2/2023 | 4/25/2024 | 108623 | 137328 | 66959
28 | Q217 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 9/12/2022 | 3/10/2023 | 12/22/2022 | 98970 | 156174 | 156174
28 | Q217 | I.S. 217 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/5/2023 | 7/3/2023 | 4/25/2023 | 494851 | 332473 | 332473
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 2/5/2020 | 7/7/2020 | 5/7/2020 | 69332 | 71806 | 71806
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | FLOOD ELIMINATION / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 5/11/2020 | 12/31/2020 | 8/19/2020 | 338529 | 342679 | 281467
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 1/10/2022 | 5/10/2022 | 5/2/2022 | 54983 | 87100 | 87100
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | REPLACMENT OF (4) ROOF TOP UNITS / VENTILATION / FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 7/11/2022 | 1/12/2023 | 2/10/2023 | 269594 | 429530 | 327819
28 | Q220 | P.S. 220 - QUEENS | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 12/21/2023 | 5/8/2024 | 8/2/2024 | 14019 | 69033 | 32687
28 | Q278 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | Scope | Complete | 1/21/2022 | 3/18/2022 | 3/22/2022 | 88660 | 147222 | 147222
28 | Q278 | PS 182 ANNEX - QUEENS | SCA Lease Site Improvement | LEASE | Design | Complete | 3/23/2022 | 9/9/2022 | 11/16/2022 | 398970 | 602770 | 182922
28 | Q365 | 3K CENTER @ 98-05 63 DRIVE - QUEENS | 3K | LEASE | Scope | Complete | 5/3/2021 | 6/22/2021 | 6/24/2021 | 169100 | 239690 | 239690
28 | Q365 | 3K CENTER @ 98-05 63 DRIVE - QUEENS | 3K | LEASE | Design | Complete | 6/25/2021 | 9/22/2021 | 5/19/2022 | 760950 | 1379767 | 457573
28 | Q365 | 3K CENTER @ 98-05 63 DRIVE - QUEENS | 3K | LEASE | Construction | Complete | 6/13/2022 | 9/3/2023 | 8/21/2023 | 9596425 | 11235402 | 10291293
28 | Q365 | 3K CENTER @ 98-05 63 DRIVE - QUEENS | 3K | LEASE | CM,F&E | Complete | 6/13/2022 | 9/3/2023 | 8/21/2023 | 1479529 | 448115 | 1460147
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | Scope | Complete | 5/20/2021 | 8/13/2021 | 6/28/2021 | 18770 | 31485 | 31485
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | HVAC CHILLER COOLING SYSTEM REPLACEMENT | Design | Complete | 8/25/2021 | 1/31/2022 | 2/16/2022 | 93850 | 139005 | 107485
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | Scope | Complete | 6/16/2021 | 11/1/2021 | 11/3/2021 | 13700 | 39304 | 39304
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | WATER INFILTRATION AT CHIMNEY | Design | Complete | 12/13/2021 | 5/16/2022 | 4/13/2022 | 61650 | 51130 | 51130
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | Scope | Complete | 1/5/2023 | 5/31/2023 | 11/3/2023 | 157000 | 171914 | 155579
28 | Q440 | FOREST HILLS HS - QUEENS | SCA CIP | SLATE ROOF TILES / FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 11/13/2023 | 4/16/2024 | 5/14/2024 | 785000 | 711386 | 524343
28 | Q440 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 466 | 466
28 | Q440 | FOREST HILLS H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 2600 | 13288 | 13288
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 7/26/2023 | 12/12/2023 | 2/8/2024 | 25127 | 82761 | 54009
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 3/1/2024 | 8/1/2024 | 7/18/2024 | 117260 | 55516 | 7227
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | Scope | Complete | 2/9/2022 | 11/9/2022 | 9/19/2022 | 35940 | 4997 | 4997
28 | Q470 | QUEENS COLLEGIATE SCHOOL - QUEENS | SCA CIP | SCIENCE DEMO ROOM UPGRADES / SCIENCE LAB UPGRADE | Design | Complete | 9/20/2022 | 1/20/2023 | 1/5/2023 | 161730 | 179562 | 138716
28 | Q497 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/5/2021 | 8/31/2021 | 8/31/2021 | 2215100 | 1293618 | 1245597
28 | Q497 | H.S. @ 165-15 88 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 9/1/2021 | 4/5/2022 | 4/28/2022 | 9967950 | 4214195 | 3788006
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | Scope | Complete | 11/5/2018 | 2/7/2019 | 2/4/2020 | 20970 | 28154 | 28154
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | FIRE PROTECTION PLAN | Design | Complete | 2/4/2020 | 8/5/2020 | 4/19/2021 | 104850 | 152690 | 134142
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | Scope | Complete | 2/25/2020 | 5/22/2020 | 11/24/2021 | 30525 | 52272 | 52272
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | CONCRETE COURTYARD PLAZA & STAIRS / RETAINING WALLS | Design | Complete | 11/29/2021 | 4/15/2022 | 8/25/2022 | 146797 | 91199 | 91199
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 1/25/2023 | 5/25/2023 | 4/11/2023 | 17500 | 18548 | 18548
28 | Q505 | HILLCREST HS - QUEENS | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 4/18/2023 | 10/18/2023 | 8/14/2023 | 78750 | 63027 | 48416
28 | Q505 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 470 | 470
28 | Q505 | HILLCREST H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 2600 | 22405 | 22405
28 | Q506 | HILLCREST HS - QUEENS | SCA CIP RESOA | FY24 RESO A ATHLETIC FIELDS | Scope | Complete | 1/9/2024 | 4/4/2024 | 7/23/2024 | 111193 | 111193 | 26388
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | Scope | Complete | 6/27/2022 | 11/10/2022 | 12/20/2022 | 149285 | 257692 | 247091
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | TCU REMOVAL AND PLAYGROUND REDEVELOPMENT / ROOFS / PARAPETS / EXTERIOR MASONRY / WINDOWS / FLOOD ELIMINATION | Design | Complete | 1/24/2023 | 6/26/2023 | 5/10/2023 | 742837 | 754202 | 655943
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/16/2023 | 7/17/2023 | 3/21/2023 | 3581 | 826 | 826
28 | Q595 | QUEENS SATELLITE HS FOR OPPORTUNITY - Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/21/2023 | 9/14/2023 | 5/3/2023 | 16116 | 3304 | 3304
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | Scope | Complete | 12/17/2019 | 4/21/2020 | 3/25/2020 | 12420 | 60529 | 60529
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP | STRUCTURAL REPAIR OF Q620 GYM | Design | Complete | 3/25/2020 | 8/14/2020 | 6/30/2020 | 55890 | 225092 | 102104
28 | Q620 | THOMAS A. EDISON HS - Q | SCA CIP RESOA | FY21 RESO A SCIENCE LAB UPGRADE / PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 9/22/2023 | 2/22/2024 | 4/23/2024 | 74118 | 67193 | 61178
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | Scope | Complete | 6/3/2021 | 11/3/2023 | 1/8/2024 | 128800 | 158115 | 122714
28 | Q680 | YOUNG WOMENS' LEADERSHIP SCHOOL - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / HVAC/BMS UPGRADE / FIRE ALARM SYSTEM | Design | Complete | 1/19/2024 | 7/23/2024 | 5/15/2024 | 644000 | 596875 | 507467
28 | Q686 | QUEENS METROPOLITAN HIGH SCHOOL - QUEENS | SCA CIP RESOA | FY23 RESO A LIBRARY UPGRADE | Design | Complete | 6/29/2023 | 11/15/2023 | 4/18/2024 | 48000 | 44856 | 4895
29 | Q015 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/15/2023 | 12/15/2023 | 9/5/2023 | 3871 | 2266 | 2266
29 | Q015 | P.S. 15 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/5/2023 | 3/5/2024 | 11/1/2023 | 17419 | 9065 | 9065
29 | Q034 | P.S. 34 - QUEENS | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 7/30/2021 | 12/16/2021 | 4/1/2022 | 6269 | 1297 | 6
29 | Q034 | P.S. 34 - QUEENS | SCA CIP | FLOOD ELIMINATION | Design | Complete | 4/1/2022 | 6/1/2022 | 4/1/2022 | 28213 | 20240 | 23
29 | Q034 | P.S. 34 - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL PLAYGROUND UPGRADE / FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 2/4/2022 | 6/6/2022 | 2/22/2022 | 73224 | 54840 | 50394
29 | Q035 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Scope | Complete | 6/30/2022 | 12/27/2022 | 10/4/2022 | 109490 | 160705 | 144978
29 | Q035 | P.S. 35 - QUEENS | SCA CIP | EXTERIOR MASONRY / ROOFS / PARAPETS / WINDOWS | Design | Complete | 10/14/2022 | 6/12/2023 | 4/26/2023 | 547449 | 496975 | 490697
29 | Q036 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 3/1/2021 | 7/16/2021 | 10/26/2021 | 64814 | 137996 | 132754
29 | Q036 | P.S. 36 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Design | Complete | 11/3/2021 | 4/8/2022 | 3/24/2022 | 314425 | 386503 | 259304
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 5/9/2017 | 10/10/2017 | 7/7/2017 | 154256 | 149205 | 149205
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/14/2017 | 12/15/2017 | 11/6/2017 | 617025 | 584541 | 572580
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | Scope | Complete | 8/15/2013 | 5/11/2015 | 11/3/2015 | 245222 | 260613 | 260613
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | FLOOD ELIMINATION / FIRE ALARM / EXTERIOR MASONRY / ELEVATOR / PARAPETS / FLOOD ELIMINATION | Design | Complete | 4/5/2016 | 9/2/2016 | 2/14/2017 | 967305 | 1051101 | 820479
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/30/2019 | 1/13/2020 | 9/10/2019 | 4431 | 2717 | 2717
29 | Q037 | P.S. 37 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 9/10/2019 | 2/13/2020 | 2/5/2020 | 19939 | 10936 | 10936
29 | Q038 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | Scope | Complete | 5/11/2021 | 9/24/2021 | 12/7/2021 | 152878 | 139829 | 139829
29 | Q038 | P.S. 38 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY / HVAC / CLASSROOM AIR HANDLING UNITS / WINDOWS | Design | Complete | 12/10/2021 | 5/13/2022 | 10/6/2022 | 754443 | 659500 | 576124
29 | Q052 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 8/30/2019 | 1/6/2020 | 9/9/2019 | 2279 | 1963 | 1963
29 | Q052 | P.S. 52 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 9/9/2019 | 2/12/2020 | 2/5/2020 | 10256 | 7937 | 7937
29 | Q059 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 5/4/2023 | 96428 | 148324 | 146906
29 | Q059 | I.S. 59 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 5/22/2023 | 10/24/2023 | 10/23/2023 | 482141 | 457002 | 344999
29 | Q059 | I.S. 59 - QUEENS | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE | Design | Complete | 1/4/2022 | 5/19/2022 | 7/13/2022 | 54182 | 65570 | 65570
29 | Q095 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | Scope | Complete | 4/28/2022 | 11/29/2022 | 11/14/2022 | 1076660 | 1032175 | 799628
29 | Q095 | P.S. 95 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING/IPDVS / EXISTING BUILDING/FIRE ALARM REPLACEMENT / EXISTING BUILDING-KITCHEN RENOVATION | Design | Complete | 11/14/2022 | 5/18/2023 | 4/28/2023 | 4844970 | 2264641 | 1467931
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Scope | Complete | 8/26/2022 | 12/30/2022 | 11/14/2022 | 31548 | 70951 | 66606
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION | Design | Complete | 5/4/2023 | 11/20/2023 | 4/1/2024 | 157740 | 208701 | 102488
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 4/28/2022 | 5/26/2022 | 5/19/2022 | 23090 | 29160 | 29160
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 5/20/2022 | 8/11/2022 | 9/30/2022 | 115450 | 263701 | 234517
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | DEMOLITION | Construction | Complete | 4/13/2023 | 1/7/2024 | 4/11/2024 | 2597625 | 2447998 | 2281541
29 | Q095 | P.S. 95 - QUEENS | SCA CIP | DEMOLITION | CM,F&E | Complete | 4/13/2023 | 1/7/2024 | 4/11/2024 | 161630 | 245287 | 236624
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | Scope | Complete | 3/16/2021 | 7/29/2021 | 12/7/2021 | 124001 | 208763 | 208763
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS / WINDOWS | Design | Complete | 12/8/2021 | 5/11/2022 | 5/10/2022 | 620000 | 408686 | 396556
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 2/14/2022 | 5/13/2022 | 4/18/2022 | 16059 | 12196 | 12196
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 4/19/2022 | 9/19/2022 | 9/21/2022 | 80295 | 48778 | 48778
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/6/2019 | 3/25/2020 | 11/21/2019 | 5030 | 6265 | 6265
29 | Q109 | I.S. 109 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 11/21/2019 | 4/24/2020 | 2/5/2020 | 22635 | 25126 | 25126
29 | Q116 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | Scope | Complete | 5/10/2022 | 4/17/2023 | 2/17/2023 | 1296661 | 829465 | 824163
29 | Q116 | P.S. 116 - QUEENS | SCA Capacity | ADDITION / EXISTING BUILDING/FIRE ALARM UPGRADE / EXISTING BUILDING/IPDVS UPGRADE / EXISTING BUILDING/ELECTRICAL SYSTEMS UPGRADE / TCU REMOVAL/PLAYGROUND REDEVELOPMENT-TCU REMOVAL/PLAYGROUND RENOVATION | Design | Complete | 2/21/2023 | 8/23/2023 | 4/20/2023 | 5834970 | 2301025 | 1439199
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION/PROGRAM ACCESSIBILITY | Scope | Complete | 5/26/2023 | 10/26/2023 | 10/2/2023 | 46664 | 44926 | 44926
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | EXISTING BUILDING-INTERIOR RENOVATION/PROGRAM ACCESSIBILITY | Design | Complete | 10/10/2023 | 3/14/2024 | 8/26/2024 | 233321 | 159248 | 87274
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 7/5/2022 | 7/5/2022 | 7/5/2022 | 46456 | 2807 | 2807
29 | Q116 | P.S. 116 - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 7/6/2022 | 9/16/2022 | 10/25/2022 | 232280 | 316811 | 284671
29 | Q118 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/21/2021 | 11/4/2021 | 1/26/2022 | 156001 | 231097 | 231091
29 | Q118 | P.S. 118 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 1/27/2022 | 6/28/2022 | 5/11/2022 | 780000 | 554099 | 546598
29 | Q131 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | Scope | Complete | 12/19/2017 | 5/31/2023 | 8/4/2023 | 146611 | 294415 | 287808
29 | Q131 | P.S. 131 - QUEENS | SCA CIP | PHASE 4 EXISTING BUILDING WORK / WINDOWS / EXTERIOR MASONRY / FLOOD ELIMINATION / DRAINAGE | Design | Complete | 8/4/2023 | 12/21/2023 | 4/30/2024 | 733051 | 698370 | 492579
29 | Q132 | P.S. 132 - QUEENS | SCA CIP RESOA | FY18 RESO A KITCHEN AREAS | Design | Complete | 5/15/2018 | 10/16/2018 | 5/6/2019 | 264016 | 335134 | 288942
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | Scope | Complete | 2/15/2019 | 9/15/2021 | 11/23/2021 | 254504 | 170773 | 170773
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | WATER PENETRATION / EXTERIOR MASONRY / FULL PROGRAM ACCESSIBILITY / PARAPETS | Design | Complete | 12/3/2021 | 5/23/2022 | 3/1/2023 | 1266898 | 826136 | 706140
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/19/2022 | 4/20/2023 | 1/3/2023 | 4051 | 3630 | 3630
29 | Q134 | P.S. 134 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/3/2023 | 6/29/2023 | 5/3/2023 | 18230 | 14519 | 14519
29 | Q135 | P.S. 135 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/15/2024 | 12/17/2024 | 8/21/2024 | 5572 | 733 | 733
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Scope | Complete | 5/17/2019 | 10/2/2019 | 9/5/2019 | 126420 | 155120 | 152567
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY / FIRE ALARM REPLACEMENT | Design | Complete | 9/25/2019 | 3/17/2020 | 7/1/2020 | 632103 | 689931 | 656702
29 | Q136 | P.S. 136 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/16/2024 | 12/18/2024 | 8/22/2024 | 5090 | 829 | 829
29 | Q138 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Scope | Complete | 6/9/2022 | 12/5/2022 | 10/11/2022 | 249042 | 285868 | 267264
29 | Q138 | P.S. 138 - QUEENS | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS / FLOOD ELIMINATION | Design | Complete | 10/14/2022 | 6/12/2023 | 4/18/2023 | 1238169 | 569320 | 569320
29 | Q147 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/19/2022 | 12/5/2022 | 6/12/2023 | 56463 | 138039 | 132820
29 | Q147 | P.S. 147 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 7/5/2023 | 12/6/2023 | 12/8/2023 | 282314 | 322959 | 230235
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY22 RESO A ELECTRICAL UPGRADE | Design | Complete | 6/10/2022 | 11/10/2022 | 9/28/2022 | 22079 | 65637 | 59887
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY22 RESO A ELECTRICAL UPGRADE | Construction | Complete | 4/3/2023 | 12/28/2023 | 10/16/2023 | 323825 | 283983 | 262601
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY22 RESO A ELECTRICAL UPGRADE | CM,F&E | Complete | 4/3/2023 | 12/28/2023 | 10/16/2023 | 22079 | 34285 | 33681
29 | Q156 | P.S. 156 - QUEENS | SCA CIP RESOA | FY23 RESO A COMPUTER LAB UPGRADE / PATH OF TRAVEL RESO A COMPUTER LAB UPGRADE | Design | Complete | 5/30/2023 | 10/30/2023 | 11/15/2023 | 45913 | 76561 | 63845
29 | Q176 | P.S. 176 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/26/2013 | 2/28/2014 | 2/28/2014 | 52357 | 97205 | 97205
29 | Q176 | P.S. 176 - QUEENS | SCA CIP | PLAYGROUND REDEVELOPMENT | Design | Complete | 3/26/2014 | 8/8/2014 | 9/26/2014 | 261784 | 282799 | 282799
29 | Q181 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | Scope | Complete | 1/14/2020 | 5/29/2020 | 6/21/2021 | 99024 | 93270 | 93270
29 | Q181 | P.S. 181 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS / PLAYGROUND REDEVELOPMENT | Design | Complete | 7/26/2021 | 12/28/2021 | 2/28/2022 | 486988 | 337674 | 337674
29 | Q195 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | Scope | Complete | 8/2/2019 | 12/19/2019 | 5/24/2021 | 80105 | 68383 | 61827
29 | Q195 | P.S. 195 - QUEENS | SCA CIP | WATER PENETRATION / PARAPETS / ROOFS | Design | Complete | 5/26/2021 | 10/27/2021 | 5/12/2022 | 400526 | 350430 | 350430
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | Scope | Complete | 11/8/2018 | 3/26/2019 | 3/1/2019 | 208401 | 139787 | 112537
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS / PLAYGROUND REDEVELOPMENT | Design | Complete | 3/1/2019 | 7/31/2019 | 5/10/2022 | 1042001 | 690811 | 642453
29 | Q238 | I.S. 238 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 9/6/2024 | 9/6/2024 | 9/6/2024 | 82656 | 0 | 0
29 | Q238 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 410 | 410
29 | Q238 | I.S. 238 - QUEENS | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 2600 | 19693 | 19693
29 | Q263 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | Scope | Complete | 1/17/2020 | 6/3/2020 | 6/28/2021 | 116100 | 125708 | 125708
29 | Q263 | P.S. /I.S 295 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / RTU REPLACEMENT | Design | Complete | 8/26/2021 | 2/1/2022 | 2/23/2022 | 572361 | 436832 | 413369
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Scope | Complete | 7/8/2022 | 11/23/2022 | 8/24/2023 | 26008 | 94172 | 91287
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY | Design | Complete | 9/21/2023 | 2/27/2024 | 4/25/2024 | 117036 | 93397 | 71370
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 12/13/2022 | 4/14/2023 | 1/3/2023 | 3168 | 3791 | 3791
29 | Q268 | P.S. 268 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/3/2023 | 6/29/2023 | 5/3/2023 | 14254 | 15165 | 15165
29 | Q268 | P.S. 268 - QUEENS | SCA CIP RESOA | FY18 RESO A ROOFTOP PLAYGROUND | Design | Complete | 1/16/2019 | 6/3/2019 | 5/18/2020 | 46500 | 95184 | 95184
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | Scope | Complete | 4/20/2021 | 2/11/2022 | 1/19/2022 | 36710 | 46720 | 46720
29 | Q270 | P.S. / I.S. 270 - QUEENS | SCA CIP | GYM ROOF / GYM FLOOR REPLACEMENT / PATH OF TRAVEL GYM FLOOR REPLACEMENT / EXTERIOR MASONRY | Design | Complete | 1/20/2022 | 3/9/2022 | 3/2/2022 | 170636 | 134348 | 128348
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | Scope | Complete | 8/6/2020 | 10/28/2021 | 6/17/2022 | 76540 | 130195 | 126200
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP | COVID VENTILATION / FY21 RESO A SUPPLEMENTAL COOLING / COVID FIRE ALARM SYSTEM REPLACEMENT | Design | Complete | 8/31/2022 | 2/28/2023 | 3/10/2023 | 382701 | 414723 | 307028
29 | Q420 | G. WASHINGTON CARVER HS FOR SCI.-Q | SCA CIP RESOA | FY20 RESO A ROOM CONVERSION / FY20 RESO A PATH OF TRAVEL ROOM CONVERSION | Design | Complete | 1/19/2023 | 5/5/2023 | 4/28/2023 | 115311 | 96981 | 85794
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | Scope | Complete | 11/30/2021 | 3/18/2022 | 2/9/2022 | 22260 | 38010 | 38010
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP | SCIENCE LAB UPGRADES | Design | Complete | 2/16/2022 | 7/19/2022 | 5/9/2022 | 111300 | 152043 | 152043
29 | Q490 | MATH, SCI., RESEARCH & TECH. HS-Q | SCA CIP RESOA | FY20 RESO A LOW VOLTAGE | Design | Complete | 5/26/2021 | 10/27/2021 | 9/28/2021 | 96813 | 24428 | 24428
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Design | Complete | 9/9/2022 | 2/14/2023 | 2/17/2023 | 50280 | 60496 | 47880
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | Construction | Complete | 7/17/2023 | 5/11/2024 | 4/11/2024 | 737440 | 659550 | 576938
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY22 RESO A AUDITORIUM UPGRADE | CM,F&E | Complete | 7/17/2023 | 5/11/2024 | 4/11/2024 | 50280 | 96345 | 56472
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | FY24 RESO A SCIENCE LAB UPGRADE | Design | Complete | 4/8/2024 | 9/9/2024 | 8/16/2024 | 29775 | 42590 | 17694
29 | Q490 | HEALTH ARTS ROBOTICS AND TECHNOLOGY HS - Q | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB UPGRADE | Design | Complete | 4/8/2024 | 8/6/2024 | 8/16/2024 | 225 | 225 | 0
29 | Q490 | INSTITUTE FOR HEALTH PROFESSIONS AT CAMBRIA HEIGHTS | SCA CIP RESOA | PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Scope | Complete | 3/15/2024 | 6/14/2024 | 5/23/2024 | 267 | 267 | 267
29 | Q490 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Scope | Complete | 9/12/2003 | 9/12/2003 | 9/12/2003 | 720 | 60 | 60
29 | Q490 | JACKSON H.S. | SCA Emergency Lighting | LL 41/16 COMPLIANCE | Design | Complete | 12/1/2004 | 5/15/2005 | 4/18/2005 | 2600 | 17481 | 17481
29 | Q822 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 5/17/2019 | 10/2/2019 | 9/5/2019 | 11789 | 6339 | 6339
29 | Q822 | Q811 SPED - QUEENS | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 9/25/2019 | 3/17/2020 | 7/1/2020 | 58947 | 34497 | 32924
29 | Q851 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | Scope | Complete | 7/5/2023 | 7/5/2023 | 7/5/2023 | 17023 | 15144 | 15144
29 | Q851 | Q811 SPED - QUEENS | SCA CIP | ROOF REPLACEMENT | Design | Complete | 7/5/2023 | 12/6/2023 | 12/8/2023 | 76605 | 67890 | 44186
30 | Q002 | P.S. 2 - QUEENS | SCA CIP | FLOOD ELIMINATION / PARAPETS | Scope | Complete | 6/12/2024 | 10/29/2024 | 9/27/2024 | 108598 | 101518 | 56292
30 | Q010 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | Scope | Complete | 8/22/2019 | 1/10/2020 | 2/21/2020 | 15433 | 37961 | 37961
30 | Q010 | I.S. 10 - QUEENS | SCA CIP | WATER PENETRATION | Design | Complete | 6/1/2021 | 11/1/2021 | 4/11/2022 | 77163 | 79684 | 79684
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/18/2019 | 11/19/2019 | 10/2/2019 | 66300 | 89840 | 89840
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 10/16/2019 | 3/20/2020 | 4/17/2020 | 331501 | 341070 | 323830
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Construction | Complete | 7/6/2021 | 7/5/2023 | 7/28/2023 | 7458750 | 6860642 | 6442070
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | CM,F&E | Complete | 7/6/2021 | 7/5/2023 | 7/28/2023 | 464100 | 502744 | 497183
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Scope | Complete | 6/7/2023 | 12/6/2023 | 10/20/2023 | 143584 | 122185 | 121009
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS / WINDOWS | Design | Complete | 11/9/2023 | 6/28/2024 | 4/11/2024 | 708217 | 236804 | 236773
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/14/2023 | 10/16/2023 | 6/29/2023 | 4106 | 1608 | 1608
30 | Q017 | P.S. 17 - QUEENS | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 6/29/2023 | 12/27/2023 | 9/20/2023 | 18477 | 6433 | 6433
30 | Q069 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | Scope | Complete | 1/23/2019 | 4/5/2019 | 5/3/2019 | 32890 | 58247 | 58247
30 | Q069 | P.S. 69 - QUEENS | SCA CIP | COOLING TOWER REPLACEMENT | Design | Complete | 5/8/2019 | 11/8/2019 | 10/11/2019 | 164450 | 388292 | 332223
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 6/22/2021 | 11/5/2021 | 11/1/2021 | 7118 | 14499 | 14499
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 11/8/2021 | 4/13/2022 | 4/6/2022 | 32033 | 37080 | 14895
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 5/6/2019 | 9/5/2019 | 5/21/2019 | 2510 | 2510 | 2510
30 | Q070 | P.S. 70 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 5/21/2019 | 10/22/2019 | 10/30/2019 | 10760 | 10109 | 10109
30 | Q070 | P.S. 70 - QUEENS | SCA CIP RESOA | FY20 RESO LIBRARY UPGRADE | Design | Complete | 8/30/2022 | 1/19/2023 | 1/31/2023 | 35850 | 44143 | 44143
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/16/2022 | 3/21/2023 | 12/5/2022 | 5100 | 6836 | 6836
30 | Q076 | P.S. 76 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/5/2022 | 6/1/2023 | 3/8/2023 | 22950 | 27342 | 27342
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / FIRE ALARM SYSTEM REPLACEMENT / HVAC UPGRADES / WINDOWS | Scope | Complete | 7/12/2022 | 11/28/2022 | 5/15/2023 | 138000 | 223068 | 212497
30 | Q084 | P.S. 84 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION / FIRE ALARM SYSTEM REPLACEMENT / HVAC UPGRADES / WINDOWS | Design | Complete | 6/13/2023 | 12/18/2023 | 2/9/2024 | 658175 | 400007 | 374071
30 | Q085 | P.S. 85 - QUEENS | SCA CIP | ROOFS / EXTERIOR MASONRY / WINDOWS / PARAPETS | Scope | Complete | 6/24/2024 | 11/7/2024 | 9/27/2024 | 193939 | 34169 | 18569
30 | Q085 | P.S. 85 - QUEENS | SCA CIP RESOA | FY21 RESO A CAFETERIA UPGRADE / PATH OF TRAVEL RESO A CAFETERIA UPGRADE | Design | Complete | 3/4/2022 | 5/20/2022 | 5/13/2022 | 64425 | 51890 | 47631
30 | Q111 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Scope | Complete | 8/26/2019 | 1/15/2020 | 11/17/2021 | 75080 | 133842 | 130813
30 | Q111 | P.S. 111 - QUEENS | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Design | Complete | 12/8/2021 | 5/11/2022 | 5/5/2022 | 375404 | 339374 | 339374
30 | Q112 | P.S. 112 - QUEENS | SCA CIP RESOA | FY17 RESO A PLAYGROUND REDEVELOPMENT | Design | Complete | 3/24/2017 | 8/8/2017 | 5/17/2017 | 84467 | 104140 | 104140
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Scope | Complete | 5/27/2021 | 8/26/2021 | 10/8/2021 | 11000 | 42301 | 42301
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | LOW VOLTAGE ELECTRICAL SYSTEM | Design | Complete | 12/28/2021 | 6/30/2022 | 9/23/2022 | 55000 | 170415 | 121894
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 7/14/2022 | 11/30/2022 | 6/12/2023 | 117730 | 174183 | 151233
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 7/5/2023 | 12/6/2023 | 3/29/2024 | 588650 | 352213 | 345556
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Scope | Complete | 6/5/2019 | 7/31/2020 | 5/26/2020 | 12853 | 43770 | 41981
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Design | Complete | 5/27/2020 | 7/28/2020 | 6/30/2020 | 63039 | 101837 | 101837
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | Construction | Complete | 5/23/2022 | 8/15/2023 | 1/17/2023 | 1312653 | 1207568 | 1191172
30 | Q122 | P.S. 122 - QUEENS | SCA CIP | AUDITORIUM UPGRADE / PATH OF TRAVEL AUDITORIUM UPGRADE | CM,F&E | Complete | 5/23/2022 | 8/15/2023 | 1/17/2023 | 99134 | 82434 | 82360
30 | Q122 | P.S. 122 - QUEENS | SCA CIP RESOA | FY16 RESO A SOLAR PANELS | Design | Complete | 11/7/2017 | 4/12/2018 | 5/9/2018 | 76563 | 252433 | 218695
30 | Q122 | P.S. 122 - QUEENS | SCA CIP RESOA | FY16 RESO A SOLAR PANELS | Construction | Complete | 10/25/2019 | 8/19/2020 | 11/29/2022 | 1122921 | 999621 | 936920
30 | Q122 | P.S. 122 - QUEENS | SCA CIP RESOA | FY16 RESO A SOLAR PANELS | CM,F&E | Complete | 10/25/2019 | 8/19/2020 | 11/29/2022 | 76563 | 115914 | 115914
30 | Q126 | I.S. 126 - QUEENS | SCA CIP | WATER INFILTRATION | Scope | Complete | 5/17/2019 | 10/2/2019 | 11/12/2019 | 15580 | 33744 | 33736
30 | Q126 | I.S. 126 - QUEENS | SCA CIP | WATER INFILTRATION | Design | Complete | 1/14/2020 | 6/15/2020 | 5/6/2021 | 70110 | 82335 | 71930
30 | Q126 | I.S. 126 - QUEENS | SCA CIP | WATER INFILTRATION | Construction | Complete | 1/19/2022 | 10/15/2022 | 7/28/2023 | 903640 | 843364 | 703293
30 | Q126 | I.S. 126 - QUEENS | SCA CIP | WATER INFILTRATION | CM,F&E | Complete | 1/19/2022 | 10/15/2022 | 7/28/2023 | 167485 | 123679 | 106373
30 | Q126 | I.S. 126 - QUEENS | SCA CIP RESOA | FY23 RESO A SCIENCE LAB | Scope | Complete | 3/2/2023 | 7/3/2023 | 10/27/2023 | 35619 | 35619 | 27619
30 | Q126 | I.S. 126 - QUEENS | SCA CIP RESOA | PATH OF TRAVEL RESO A SCIENCE LAB | Scope | Complete | 3/24/2023 | 7/3/2023 | 10/31/2023 | 6049 | 6049 | 1004
30 | Q127 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/28/2022 | 3/30/2023 | 12/5/2022 | 4600 | 3750 | 3750
30 | Q127 | P.S. 127 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/5/2022 | 6/1/2023 | 3/8/2023 | 20700 | 15000 | 15000
30 | Q141 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Scope | Complete | 8/22/2019 | 2/10/2020 | 10/7/2019 | 4958 | 4583 | 4583
30 | Q141 | I.S. 141 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE / LL26 CODE COMPLIANCE/EXIT SIGN REPLACEMENT | Design | Complete | 10/7/2019 | 3/12/2020 | 1/29/2020 | 20346 | 18459 | 18459
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 12/12/2014 | 5/15/2015 | 2/26/2015 | 127455 | 107761 | 107761
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 4/1/2015 | 8/31/2015 | 8/26/2015 | 509820 | 345008 | 337857
30 | Q145 | I.S. 145 - QUEENS | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / EMERGENCY GENERATOR | Scope | Complete | 6/21/2023 | 11/6/2023 | 12/15/2023 | 119002 | 228082 | 181983
30 | Q148 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 3/25/2019 | 7/24/2019 | 6/19/2019 | 6008 | 6008 | 6008
30 | Q148 | P.S. 148 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 6/19/2019 | 11/20/2019 | 11/7/2019 | 24132 | 24132 | 24132
30 | Q149 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | Scope | Complete | 6/9/2023 | 12/8/2023 | 11/1/2023 | 233536 | 328794 | 311729
30 | Q149 | P.S. 149 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS / WINDOWS / PAVED AREAS- CONCRETE / FLOOD ELIMINATION | Design | Complete | 12/18/2023 | 5/20/2024 | 4/22/2024 | 1163035 | 381834 | 381834
30 | Q150 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/28/2019 | 11/14/2019 | 11/6/2019 | 88879 | 169380 | 166527
30 | Q150 | P.S. 150 - QUEENS | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/13/2019 | 4/16/2020 | 6/26/2020 | 444401 | 1132838 | 761548
30 | Q150 | P.S. 150 - QUEENS | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE | Design | Complete | 11/28/2023 | 4/30/2024 | 3/21/2024 | 90000 | 56555 | 49960
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / GYM WINDOWS / RTU REPLACEMENT / FIRE ALARM REPLACEMENT | Scope | Complete | 6/2/2021 | 10/18/2021 | 10/28/2021 | 136645 | 144485 | 144485
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY / GYM WINDOWS / RTU REPLACEMENT / FIRE ALARM REPLACEMENT | Design | Complete | 11/19/2021 | 4/25/2022 | 10/20/2022 | 658969 | 396100 | 381871
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Scope | Complete | 5/28/2019 | 9/26/2019 | 7/2/2019 | 5660 | 3310 | 3310
30 | Q152 | P.S. 152 - QUEENS | SCA CIP | ELECTRICAL WORK FOR A/C INITIATIVE | Design | Complete | 7/2/2019 | 12/4/2019 | 11/6/2019 | 25472 | 13298 | 13298
30 | Q166 | P.S. 166 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/5/2023 | 12/4/2023 | 10/26/2023 | 131122 | 165348 | 165348
30 | Q166 | P.S. 166 - QUEENS | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/7/2023 | 6/28/2024 | 4/22/2024 | 655614 | 324438 | 324438
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Scope | Complete | 3/6/2020 | 6/22/2020 | 7/9/2021 | 36021 | 71967 | 71967
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | EXTERIOR MASONRY / PARAPETS | Design | Complete | 7/27/2021 | 12/29/2021 | 1/19/2022 | 175581 | 238814 | 215157
30 | Q171 | P.S. 171 - QUEENS | SCA CIP | ELECTRIFICATION/HEAT PUMP SYSTEMS / FIRE ALARM UPGRADE / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 8/25/2023 | 1/22/2024 | 5/21/2024 | 170996 | 132444 | 3349
30 | Q204 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | Scope | Complete | 5/14/2020 | 11/10/2020 | 9/9/2020 | 138890 | 203120 | 203120
30 | Q204 | I.S. 204 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / WINDOWS | Design | Complete | 9/21/2020 | 7/1/2021 | 5/7/2021 | 694451 | 594862 | 589218
30 | Q222 | P.S. 222 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 1/8/2024 | 5/22/2024 | 9/4/2024 | 15458 | 9771 | 9771
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Scope | Complete | 8/26/2019 | 11/26/2019 | 3/9/2020 | 13800 | 52229 | 52229
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | PA SYSTEM REPLACEMENT | Design | Complete | 3/11/2020 | 8/10/2020 | 12/9/2021 | 69000 | 139956 | 137799
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/11/2022 | 12/13/2022 | 8/25/2022 | 6010 | 2367 | 2367
30 | Q227 | I.S. 227 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 8/25/2022 | 3/31/2023 | 3/8/2023 | 27045 | 9468 | 9468
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Scope | Complete | 9/22/2022 | 2/10/2023 | 4/28/2023 | 49176 | 128419 | 125984
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY / PARAPETS / ROOFS | Design | Complete | 5/2/2023 | 10/3/2023 | 10/25/2023 | 245880 | 316901 | 301648
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/25/2020 | 10/26/2020 | 7/7/2020 | 2247 | 3593 | 3593
31 | R029 | P.S. 29 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/7/2020 | 1/1/2021 | 1/6/2021 | 10112 | 14370 | 14370
31 | R030 | P.S. 30 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 1/16/2024 | 5/16/2024 | 4/25/2024 | 42000 | 57644 | 56224
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY19 RESO A AUDITORIUM UPGRADE | Design | Complete | 4/2/2021 | 9/1/2021 | 9/29/2022 | 126000 | 88017 | 86976
30 | Q227 | I.S. 227 - QUEENS | SCA CIP RESOA | FY20 RESO A SCIENCE LAB UPGRADES | Design | Complete | 1/18/2022 | 6/17/2022 | 5/11/2022 | 146763 | 140827 | 138235
30 | Q228 | P.S. 228 - QUEENS | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Scope | Complete | 5/20/2020 | 11/17/2020 | 10/30/2020 | 49706 | 204303 | 204273
30 | Q228 | P.S. 228 - QUEENS | SCA CIP | PARAPETS / ROOFS / EXTERIOR MASONRY | Design | Complete | 5/27/2021 | 11/23/2021 | 11/22/2021 | 242850 | 412263 | 412263
30 | Q230 | I.S. 230 - QUEENS | SCA CIP | FLOOD ELIMINATION / LOW VOLTAGE ELECTRICAL SYSTEM / ELECTRICAL UPGRADE | Scope | Complete | 11/7/2019 | 3/27/2020 | 12/7/2021 | 117767 | 167300 | 164148
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 6/27/2019 | 11/13/2019 | 12/13/2019 | 37229 | 48833 | 48833
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | PARAPETS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 12/13/2019 | 5/15/2020 | 7/16/2020 | 175017 | 230010 | 223275
30 | Q234 | P.S. 234 - QUEENS | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/21/2021 | 2/25/2022 | 7/11/2022 | 19517 | 20389 | 1134
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Scope | Complete | 10/29/2019 | 4/28/2020 | 2/20/2020 | 3740 | 19176 | 19176
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | RPZ BACKFLOW PREVENTION DEVICES | Design | Complete | 2/25/2020 | 8/18/2020 | 4/28/2020 | 16830 | 76701 | 76701
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | ROOFS | Scope | Complete | 6/8/2021 | 10/22/2021 | 12/30/2021 | 39437 | 47852 | 47852
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | ROOFS | Design | Complete | 1/25/2022 | 6/24/2022 | 5/5/2022 | 197184 | 162430 | 162430
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Scope | Complete | 2/8/2023 | 3/13/2024 | 2/12/2024 | 17052 | 44876 | 44876
30 | Q292 | P.S. 92 - QUEENS | SCA CIP | PLAYGROUND UPGRADE / PATH OF TRAVEL PLAYGROUND UPGRADE | Design | Complete | 2/21/2024 | 6/24/2024 | 3/27/2024 | 76736 | 74719 | 67621
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 12/21/2016 | 6/28/2017 | 6/28/2017 | 1494500 | 1342610 | 1337978
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 6/29/2017 | 1/9/2018 | 5/12/2023 | 6725250 | 2879751 | 2718395
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 11/14/2022 | 11/14/2022 | 11/14/2022 | 187000 | 3580 | 3580
30 | Q341 | P.S. @ PARCEL C - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 11/15/2022 | 1/11/2023 | 4/27/2023 | 935000 | 293289 | 213404
30 | Q445 | WILLIAM C. BRYANT HS - QUEENS | SCA CIP RESOA | FY20 RESO A PATH OF TRAVEL GYMNASIUM UPGRADE / FY20 RESO A GYMNASIUM UPGRADE | Design | Complete | 10/13/2021 | 12/17/2021 | 12/1/2021 | 73297 | 181188 | 167706
30 | Q447 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | Scope | Complete | 8/3/2021 | 8/24/2021 | 8/24/2021 | 239760 | 228413 | 228413
30 | Q447 | 3K CENTER @ 36-31 38 STREET - QUEENS | 3K | LEASE | Design | Complete | 8/25/2021 | 11/22/2021 | 3/8/2022 | 1078920 | 1113793 | 1037707
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | Scope | Complete | 9/27/2016 | 9/28/2016 | 9/28/2016 | 11670 | 16187 | 16187
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | RPZ VALVES | Design | Complete | 9/28/2016 | 3/28/2017 | 4/24/2017 | 42790 | 65621 | 65621
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 8/4/2022 | 12/6/2022 | 9/28/2022 | 5550 | 3984 | 3984
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/28/2022 | 3/29/2023 | 3/8/2023 | 24975 | 15935 | 15935
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | Scope | Complete | 8/10/2020 | 5/25/2023 | 2/22/2023 | 91056 | 112762 | 105289
30 | Q450 | NEWCOMERS HIGH SCHOOL - Q | SCA CIP | COVID VENTILATION / COVID FIRE ALARM SYSTEM REPLACEMENT / AUDITORIUM SEAT UPGRADE / PATH OF TRAVEL AUDITORIUM SEAT UPGRADE | Design | Complete | 2/22/2023 | 6/26/2023 | 5/11/2023 | 449880 | 550014 | 499818
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Scope | Complete | 5/5/2014 | 9/18/2014 | 12/22/2014 | 325500 | 206837 | 206837
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CRACKED PARAPETS / FLOOD ELIMINATION / EXTERIOR MASONRY / ROOFS | Design | Complete | 3/10/2015 | 8/7/2015 | 12/23/2015 | 1302001 | 1510513 | 1302207
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | Scope | Complete | 8/24/2015 | 12/24/2015 | 12/12/2016 | 32700 | 47542 | 47542
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | CULINARY ARTS ROOM | Design | Complete | 12/14/2016 | 5/8/2017 | 12/29/2017 | 130800 | 218157 | 209038
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | PUBLIC ADDRESS SYSTEM REPLACEMENT | Scope | Complete | 6/7/2023 | 9/7/2023 | 9/8/2023 | 13456 | 4491 | 4491
30 | Q452 | LONG ISLAND CITY HS - Q | SCA CIP | PUBLIC ADDRESS SYSTEM REPLACEMENT | Design | Complete | 9/20/2023 | 2/26/2024 | 2/23/2024 | 67278 | 17967 | 17967
30 | Q472 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 6/11/2018 | 1/4/2019 | 1/4/2019 | 3577000 | 2420970 | 2288663
30 | Q472 | H.S. @ 53-16 NORTHERN BOULEVARD - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 1/7/2019 | 12/11/2019 | 5/5/2021 | 16096500 | 9658845 | 9331091
30 | Q489 | P.S. 85 ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 6/24/2019 | 12/12/2019 | 12/13/2019 | 1127000 | 812747 | 804672
30 | Q489 | P.S. 85 ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 12/16/2019 | 6/23/2020 | 5/7/2021 | 5071500 | 3434081 | 3021962
30 | Q489 | P.S. 85 ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | Construction | Complete | 10/26/2021 | 9/3/2024 | 6/7/2024 | 63957250 | 59522185 | 57246605
30 | Q489 | P.S. 85 ANNEX - QUEENS | SCA Capacity | NEW SCHOOL | CM,Art,F&E | Complete | 10/26/2021 | 9/3/2024 | 6/7/2024 | 9016000 | 6950145 | 5573279
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Scope | Complete | 4/6/2023 | 9/25/2023 | 10/26/2023 | 1627873 | 1028861 | 1020915
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA Capacity | NEW SCHOOL | Design | Complete | 10/27/2023 | 4/15/2024 | 5/14/2024 | 7325428 | 1562491 | 1247353
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA CIP | DEMOLITION | Scope | Complete | 4/14/2023 | 4/14/2023 | 4/14/2023 | 90859 | 6861 | 6861
30 | Q508 | P.S. @ 23-10 43 AVENUE - QUEENS | SCA CIP | DEMOLITION | Design | Complete | 4/17/2023 | 10/6/2023 | 11/29/2023 | 454294 | 349829 | 349829
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | Scope | Complete | 7/17/2018 | 10/16/2018 | 9/24/2018 | 42642 | 48620 | 48620
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | CHAPEL ROOM CONVERSION | Design | Complete | 12/6/2018 | 6/7/2019 | 5/16/2019 | 170568 | 191513 | 190842
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 10/28/2022 | 3/3/2023 | 12/6/2022 | 2169 | 1647 | 1647
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 12/6/2022 | 6/2/2023 | 4/11/2023 | 9759 | 6586 | 6586
30 | Q739 | YOUNG W. LEADERSHIP SCL ASTORIA- Q | SCA CIP RESOA | FY21 RESO A ROBOTICS LAB | Design | Complete | 3/10/2023 | 8/10/2023 | 8/11/2023 | 42000 | 82539 | 78248
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 11/9/2022 | 3/15/2023 | 1/18/2023 | 2046 | 3391 | 3391
30 | Q798 | BACCALAUREATE SCL FOR GLOBAL ED-Q | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 1/18/2023 | 7/14/2023 | 4/11/2023 | 9205 | 13563 | 13563
30 | Q868 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 1/25/2023 | 5/24/2023 | 2/21/2023 | 2168 | 2113 | 2113
30 | Q868 | P.S. 78 - QUEENS | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 2/21/2023 | 8/16/2023 | 4/11/2023 | 9756 | 8453 | 8453
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP | RTU REPLACEMENT / BMS SYSTEM UPGRADE / FIRE ALARM REPLACEMENT | Scope | Complete | 3/2/2021 | 7/15/2021 | 7/15/2021 | 74411 | 72813 | 72813
30 | Q885 | RENAISSANCE CHARTER SCHOOL - QUEENS | SCA CIP | RTU REPLACEMENT / BMS SYSTEM UPGRADE / FIRE ALARM REPLACEMENT | Design | Complete | 9/8/2021 | 3/16/2022 | 9/13/2022 | 372050 | 294846 | 280325
31 | R001 | P.S. 1 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A BREEZEWAY | Design | Complete | 7/5/2022 | 12/6/2022 | 1/25/2023 | 37040 | 49693 | 47950
31 | R002 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 11/21/2019 | 4/9/2020 | 12/29/2021 | 11580 | 31774 | 31774
31 | R002 | I.S. 2 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Design | Complete | 1/7/2022 | 6/9/2022 | 5/4/2022 | 52110 | 31814 | 31814
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Scope | Complete | 3/6/2018 | 7/6/2018 | 8/15/2018 | 24980 | 22905 | 22905
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Design | Complete | 12/6/2018 | 6/7/2019 | 5/17/2019 | 124900 | 80171 | 72025
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/18/2019 | 11/19/2019 | 10/4/2019 | 69300 | 100890 | 100890
31 | R003 | P.S. 3 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 10/8/2019 | 3/13/2020 | 1/23/2020 | 346500 | 394615 | 377303
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 6/20/2019 | 11/21/2019 | 8/27/2019 | 68770 | 121205 | 121205
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 9/10/2019 | 2/13/2020 | 2/19/2020 | 343850 | 451918 | 419971
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | Scope | Complete | 11/6/2020 | 1/15/2021 | 1/26/2021 | 39300 | 29106 | 29106
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP | CHILLER COMPRESSOR REPLACEMENT | Design | Complete | 2/2/2021 | 7/2/2021 | 11/16/2021 | 196500 | 184941 | 143326
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Design | Complete | 8/12/2022 | 12/30/2022 | 1/24/2023 | 28800 | 46573 | 43728
31 | R004 | P.S. 4 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Design | Complete | 10/17/2023 | 4/15/2024 | 1/31/2024 | 28500 | 18474 | 18474
31 | R005 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | Scope | Complete | 1/21/2020 | 7/14/2020 | 1/19/2021 | 1277800 | 713604 | 707587
31 | R005 | P.S. 5 - STATEN ISLAND | SCA Capacity | ADDITION | Design | Complete | 1/20/2021 | 1/13/2021 | 5/11/2022 | 5750100 | 3932916 | 3007818
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP | EXISTING BUILDING WORK / EXISTING BUILDING-AUD/GYM | Scope | Complete | 3/8/2021 | 5/14/2021 | 4/28/2021 | 20684 | 72680 | 72680
31 | R005 | P.S. 5 - STATEN ISLAND | SCA CIP | EXISTING BUILDING WORK / EXISTING BUILDING-AUD/GYM | Design | Complete | 4/29/2021 | 9/20/2021 | 1/20/2022 | 102919 | 348483 | 181926
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | Scope | Complete | 2/15/2019 | 7/18/2019 | 3/31/2020 | 134750 | 132918 | 131593
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | BMS REPLACEMENT / MECHANICAL UNIT REPLACEMENT | Design | Complete | 7/26/2021 | 12/28/2021 | 3/31/2023 | 673750 | 703793 | 429660
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | Scope | Complete | 6/18/2019 | 11/1/2019 | 7/6/2021 | 24551 | 62315 | 59938
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY | Design | Complete | 7/6/2021 | 12/7/2021 | 5/16/2022 | 122753 | 95298 | 78472
31 | R006 | P.S. 6 - STATEN ISLAND | SCA CIP RESOA | FY24 RESO A LIBRARY UPGRADE | Design | Complete | 3/25/2024 | 8/8/2024 | 8/16/2024 | 48000 | 30198 | 15814
31 | R007 | I.S. 7 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A IPDVS CAMERA INSTALLATION | Design | Complete | 11/7/2023 | 5/6/2024 | 1/31/2024 | 30000 | 20589 | 20589
31 | R008 | P.S. 8 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS / PATH OF TRAVEL RESO A PLAYGROUNDS | Design | Complete | 3/26/2021 | 6/4/2021 | 5/14/2021 | 255558 | 294410 | 269693
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | Scope | Complete | 10/26/2018 | 3/18/2019 | 3/12/2019 | 178169 | 93520 | 92974
31 | R013 | P.S. 13 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / WINDOWS / EXTERIOR MASONRY / CHILLER REPLACEMENT | Design | Complete | 3/12/2019 | 8/9/2019 | 5/17/2019 | 703945 | 497192 | 351349
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Scope | Complete | 3/6/2018 | 7/6/2018 | 8/15/2018 | 12340 | 11679 | 11679
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY | Design | Complete | 12/6/2018 | 6/7/2019 | 5/17/2019 | 55530 | 107425 | 66531
31 | R014 | P.S. 078 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 3/14/2022 | 7/12/2022 | 8/2/2022 | 49054 | 59361 | 47622
31 | R018 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 6/13/2019 | 10/29/2019 | 7/6/2021 | 36449 | 137674 | 129759
31 | R018 | P.S. 18 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Design | Complete | 8/25/2021 | 1/31/2022 | 2/3/2022 | 180225 | 271103 | 268295
31 | R019 | P.S. 19 - STATEN ISLAND | SCA Capacity | ADDITION | Scope | Complete | 11/20/2023 | 6/10/2024 | 5/6/2024 | 1219599 | 925971 | 844085
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | EXISTING BUILDING - ELECTRICAL SYSTEMS UPGRADE / EXISTING BUILDING - IPDVS UPGRADE / EXISTING BUILDING - FIRE ALARM UPGRADE | Scope | Complete | 2/13/2024 | 6/13/2024 | 5/15/2024 | 20301 | 5067 | 0
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 11/30/2023 | 11/30/2023 | 11/30/2023 | 31031 | 1708 | 1708
31 | R019 | P.S. 19 - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 12/1/2023 | 3/22/2024 | 4/15/2024 | 144813 | 229748 | 80055
31 | R020 | P.S. 20 - STATEN ISLAND | SCA CIP | ROOFS / EXTERIOR MASONRY / PARAPETS | Scope | Complete | 1/26/2024 | 6/11/2024 | 7/3/2024 | 53036 | 65543 | 27352
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 8/8/2019 | 12/26/2019 | 3/13/2020 | 100062 | 287191 | 229522
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 3/13/2020 | 8/12/2020 | 6/30/2020 | 499671 | 725060 | 455095
31 | R022 | P.S. 22 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A AUDITORIUM UPGRADE / PATH OF TRAVEL RESO A AUDITORIUM UPGRADE | Design | Complete | 2/1/2024 | 6/4/2024 | 4/25/2024 | 68396 | 52855 | 41749
31 | R023 | P.S. 23 - STATEN ISLAND | SCA CIP RESOA | FY23 RESO A GYMNASIUM UPGRADE / PATH OF TRAVEL RESO A GYMNASIUM UPGRADE | Design | Complete | 10/20/2023 | 2/23/2024 | 4/18/2024 | 27000 | 52280 | 51001
31 | R024 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | Scope | Complete | 4/20/2021 | 9/2/2021 | 12/15/2021 | 30364 | 30419 | 30419
31 | R024 | I.S. 24 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / GYM ROOF | Design | Complete | 12/27/2021 | 5/27/2022 | 11/1/2022 | 146362 | 134759 | 113659
31 | R025 | R025 SPED - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 1/26/2024 | 6/11/2024 | 9/25/2024 | 46652 | 37665 | 17514
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 4/16/2021 | 9/16/2021 | 7/28/2021 | 83700 | 199905 | 185405
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 7/30/2021 | 1/31/2022 | 4/13/2022 | 418501 | 816988 | 773918
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/14/2022 | 11/30/2022 | 3/17/2023 | 69170 | 203722 | 193952
31 | R031 | P.S. 31 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 4/27/2023 | 9/28/2023 | 5/13/2024 | 338283 | 315779 | 278437
31 | R032 | P.S. 32 - STATEN ISLAND | SCA CIP | FACADE RESTORATION | Scope | Complete | 8/1/2023 | 12/18/2023 | 12/19/2023 | 20473 | 37933 | 37933
31 | R032 | P.S. 32 - STATEN ISLAND | SCA CIP | FACADE RESTORATION | Design | Complete | 1/8/2024 | 6/7/2024 | 5/14/2024 | 102363 | 99444 | 56800
31 | R034 | I.S. 34 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / CLIMATE CONTROL | Scope | Complete | 6/19/2019 | 11/20/2019 | 8/14/2019 | 89392 | 61734 | 61734
31 | R034 | I.S. 34 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / CLIMATE CONTROL | Design | Complete | 9/12/2019 | 2/18/2020 | 2/26/2020 | 446960 | 233577 | 227577
31 | R036 | P.S. 36 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 1/4/2022 | 5/19/2022 | 7/15/2022 | 59379 | 64402 | 64402
31 | R039 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Scope | Complete | 4/8/2021 | 8/23/2021 | 11/17/2021 | 43730 | 103421 | 103421
31 | R039 | P.S. 39 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / ROOFS / EXTERIOR MASONRY | Design | Complete | 11/29/2021 | 5/2/2022 | 4/22/2022 | 208391 | 250385 | 241897
31 | R041 | P.S. 41 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 7/6/2021 | 11/23/2022 | 2/14/2023 | 202251 | 382517 | 380434
31 | R041 | P.S. 41 - STATEN ISLAND | SCA CIP | HEATING PLANT UPGRADE / ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 6/16/2023 | 12/14/2023 | 5/13/2024 | 1011250 | 415711 | 376292
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP | ROOFS / FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 12/18/2023 | 5/3/2024 | 7/16/2024 | 78268 | 59683 | 59683
31 | R042 | P.S. 42 - STATEN ISLAND | SCA CIP RESOA | FY18 RESO A PLAYGROUNDS | Design | Complete | 2/28/2018 | 7/13/2018 | 12/14/2018 | 58860 | 60849 | 60849
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | Scope | Complete | 3/14/2022 | 7/12/2022 | 4/13/2022 | 4003 | 2870 | 2870
31 | R043 | CSI HS FOR INTERNATIONAL STUDIES - R | SCA CIP | IPDVS COMPLETE TECH REFRESH | Design | Complete | 4/13/2022 | 10/6/2022 | 7/20/2022 | 18015 | 11477 | 11477
31 | R043 | G MCCOWN EXPEDITIONARY LRNG SCL- R | SCA CIP RESOA | FY20 RESO A LIBRARY UPGRADE / FY21 RESO A SCIENCE LAB UPGRADES | Design | Complete | 2/14/2022 | 8/5/2022 | 3/21/2023 | 139501 | 107172 | 76272
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | Scope | Complete | 9/13/2017 | 2/1/2019 | 2/19/2019 | 170358 | 246758 | 246758
31 | R048 | NAPLES STREET ELEMENTARY SCHOOL - R | SCA CIP | WATER PENETRATION IN BASEMENT / PARAPETS / PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL / ROOFS / EXTERIOR MASONRY | Design | Complete | 2/19/2019 | 7/19/2019 | 5/16/2019 | 757717 | 987101 | 845690
31 | R051 | I.S. 51 - STATEN ISLAND | SCA CIP RESOA | RESO A PLAYGROUND UPGRADE | Design | Complete | 6/30/2021 | 11/16/2021 | 2/2/2023 | 517935 | 87278 | 85159
31 | R053 | P.S. 53 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 9/2/2022 | 1/24/2023 | 3/28/2023 | 22400 | 93108 | 63295
31 | R053 | P.S. 53 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Design | Complete | 4/18/2023 | 9/19/2023 | 12/14/2023 | 112000 | 75186 | 66256
31 | R055 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 4/15/2021 | 9/15/2021 | 7/2/2021 | 84190 | 108145 | 108145
31 | R055 | P.S. 55 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/8/2021 | 12/9/2021 | 3/31/2022 | 420950 | 572335 | 481061
31 | R056 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Scope | Complete | 6/30/2022 | 11/16/2022 | 10/26/2022 | 84240 | 142824 | 122370
31 | R056 | P.S. 56 - STATEN ISLAND | SCA CIP | ROOFS / PARAPETS / EXTERIOR MASONRY | Design | Complete | 11/9/2022 | 4/14/2023 | 4/4/2023 | 421199 | 439772 | 393144
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 2/11/2022 | 6/28/2022 | 10/17/2022 | 142100 | 164681 | 161049
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW-VOLTAGE ELECTRICAL SYSTEMS | Design | Complete | 11/4/2022 | 4/26/2023 | 5/10/2023 | 710500 | 525201 | 458919
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 6/29/2022 | 12/13/2022 | 11/22/2022 | 76804 | 92980 | 82133
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | Complete | 5/31/2023 | 4/24/2024 | 4/24/2024 | 1126464 | 1095817 | 736179
31 | R057 | P.S. 57 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 5/31/2023 | 4/24/2024 | 4/24/2024 | 76804 | 101663 | 100547
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 8/9/2022 | 12/27/2022 | 12/1/2022 | 30138 | 53848 | 52728
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Construction | Complete | 5/8/2023 | 4/1/2024 | 4/1/2024 | 442023 | 393340 | 373762
31 | R058 | P.S. 58 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | CM,F&E | Complete | 5/8/2023 | 4/1/2024 | 4/1/2024 | 30138 | 40554 | 39766
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY22 RESO A (MA) PLAYGROUND UPGRADE | Design | Complete | 1/11/2023 | 5/26/2023 | 5/11/2023 | 20200 | 36123 | 34784
31 | R059 | THE HARBOR VIEW SCHOOL - R | SCA CIP RESOA | FY23 RESO A IPDVS UPGRADE | Design | Complete | 11/30/2023 | 5/28/2024 | 1/31/2024 | 27000 | 14873 | 14873
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / EXTERIOR MASONRY | Scope | Complete | 3/5/2024 | 7/19/2024 | 8/13/2024 | 8536 | 36325 | 21475
31 | R060 | P.S. 60 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE / PATH OF TRAVEL RESO A PLAYGROUND UPGRADE | Design | Complete | 1/20/2022 | 4/22/2022 | 3/28/2022 | 37248 | 43452 | 43452
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/29/2023 | 10/30/2023 | 10/3/2023 | 11748 | 15871 | 15871
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/11/2023 | 3/12/2024 | 2/13/2024 | 52864 | 57168 | 43751
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | PAVED AREA- BLACKTOP | Scope | Complete | 3/26/2024 | 6/25/2024 | 8/12/2024 | 11567 | 49345 | 35926
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/29/2021 | 11/30/2021 | 8/18/2021 | 4477 | 6223 | 6223
31 | R061 | I.S. 61 - STATEN ISLAND | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/18/2021 | 2/16/2022 | 12/29/2021 | 20148 | 24890 | 24890
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Scope | Complete | 2/16/2023 | 7/5/2023 | 11/15/2023 | 31000 | 161758 | 161758
31 | R069 | P.S. 69 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION | Design | Complete | 12/5/2023 | 5/7/2024 | 4/17/2024 | 155000 | 252033 | 218756
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 10/9/2018 | 3/14/2019 | 12/21/2018 | 119640 | 118837 | 118837
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 1/9/2019 | 6/11/2019 | 5/7/2019 | 478560 | 524610 | 491200
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | Scope | Complete | 2/13/2019 | 7/15/2019 | 2/12/2020 | 92360 | 110022 | 110022
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | CERTIFICATE OF OCCUPANCY / CHILLER REPLACEMENT | Design | Complete | 9/9/2021 | 2/14/2022 | 4/15/2022 | 461800 | 329496 | 303084
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | PLAYGROUND UPGRADE | Scope | Complete | 5/24/2024 | 8/26/2024 | 8/28/2024 | 66586 | 58554 | 1930
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | Scope | Complete | 1/28/2022 | 9/23/2022 | 1/20/2023 | 168263 | 245277 | 237850
31 | R072 | I.S. 72 - STATEN ISLAND | SCA CIP | IDA FLOOD ELIMINATION / CONCRETE PARAPET WALL / IDA INTERIOR SPACES / EXTERIOR MASONRY / ROOFS | Design | Complete | 1/31/2023 | 7/3/2023 | 9/20/2023 | 836921 | 755045 | 503888
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 11/29/2021 | 5/2/2022 | 2/23/2022 | 104190 | 54160 | 54160
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 2/25/2022 | 7/27/2022 | 5/12/2022 | 520950 | 293710 | 235333
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | Scope | Complete | 5/24/2017 | 6/9/2020 | 5/26/2021 | 214034 | 453539 | 445514
31 | R075 | I.S. 75 - STATEN ISLAND | SCA CIP | FY17 RESO A GREENHOUSE / FLOOD ELIMINATION / PARAPETS / WINDOWS / EXTERIOR MASONRY / PAVED AREAS- CONCRETE / ROOFS / FY20 RESO A PLAYGROUND UPGRADE | Design | Complete | 6/2/2021 | 10/18/2021 | 2/15/2022 | 1025603 | 1076037 | 888369
31 | R082 | THE EAGLE ACADEMY FOR YOUNG MEN OF STATEN ISLAND - R | SCA CIP | STEAM PIPE REPLACEMENT | Scope | Complete | 2/23/2024 | 7/25/2024 | 7/25/2024 | 14207 | 1229 | 1229
31 | R110 | THE RICHMOND PRE-K CENTER | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / PATH OF TRAVEL IDA INTERIOR SPACES | Scope | Complete | 4/8/2022 | 11/16/2023 | 9/14/2023 | 27675 | 45387 | 14403
31 | R110 | THE RICHMOND PRE-K CENTER | SCA CIP | IDA FLOOD ELIMINATION / IDA INTERIOR SPACES / PATH OF TRAVEL IDA INTERIOR SPACES | Design | Complete | 9/27/2023 | 2/2/2024 | 12/15/2023 | 124535 | 97833 | 84883
31 | R119 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | Scope | Complete | 4/28/2021 | 1/18/2022 | 4/20/2022 | 26871 | 54728 | 50020
31 | R119 | R025 SPED - STATEN ISLAND | SCA CIP | PHASE II RENOVATIONS / PATH OF TRAVEL WORK FOR R119 LEASED SITE | Design | Complete | 4/20/2022 | 9/1/2022 | 3/6/2023 | 133620 | 193189 | 146252
31 | R121 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/25/2021 | 8/12/2021 | 8/27/2021 | 1537800 | 987269 | 951682
31 | R121 | P.S. @ 4074 VICTORY BLVD - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Design | Complete | 8/30/2021 | 4/25/2022 | 9/2/2022 | 6920100 | 3363484 | 2210198
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/28/2023 | 9/5/2023 | 9/5/2023 | 1337500 | 928181 | 922484
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Design | Complete | 9/6/2023 | 3/29/2024 | 5/6/2024 | 6018750 | 1304649 | 1160187
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 3/28/2023 | 3/28/2023 | 3/28/2023 | 23890 | 36871 | 20397
31 | R122 | P.S. 13 ANNEX - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 3/28/2023 | 9/15/2023 | 9/22/2023 | 119450 | 248432 | 196953
31 | R123 | I.S./H.S. @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 3/19/2024 | 8/1/2024 | 7/25/2024 | 778932 | 993162 | 991791
31 | R125 | P.S./I.S. @ 27 LANDIS AVENUE - STATEN ISLAND | SCA Capacity | NEW SCHOOL | Scope | Complete | 3/19/2024 | 10/3/2024 | 9/26/2024 | 1797314 | 1091025 | 546659
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 7/21/2023 | 7/21/2023 | 7/21/2023 | 94980 | 119788 | 118774
31 | R126 | ANNEX @ 57 CLEVELAND PLACE - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 7/21/2023 | 12/15/2023 | 5/13/2024 | 474900 | 910062 | 22295
31 | R128 | ATHLETIC FIELD @ 45 CLEVELAND PLACE - STATEN ISLAND | SCA Capacity | ATHLETIC FIELD & FINAL SITEWORK @ 57 CLEVELAND PLACE | Scope | Complete | 3/19/2024 | 8/1/2024 | 7/25/2024 | 361935 | 645706 | 645706
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 7/19/2019 | 12/5/2019 | 12/23/2019 | 294742 | 400910 | 400910
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 1/8/2020 | 6/9/2020 | 6/25/2020 | 1473705 | 1334586 | 1294447
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | Scope | Complete | 10/7/2021 | 2/28/2022 | 1/24/2022 | 26467 | 40301 | 40301
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | SCIENCE LAB UPGRADES | Design | Complete | 2/2/2022 | 8/4/2022 | 10/5/2022 | 132335 | 129147 | 129147
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | Scope | Complete | 1/11/2019 | 12/4/2020 | 6/4/2021 | 110078 | 107608 | 104122
31 | R435 | NEW DORP HS - STATEN ISLAND | SCA CIP | HOT WATER HEATER REPLACEMENT / AIR CONDITIONING / COVID VENTILATION / COVID BMS REPLACEMENT | Design | Complete | 6/15/2021 | 11/15/2021 | 2/3/2022 | 543998 | 455218 | 397345
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 9/28/2023 | 2/16/2024 | 12/22/2023 | 16458 | 26659 | 26195
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 1/8/2024 | 6/7/2024 | 4/25/2024 | 82291 | 50393 | 16407
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/12/2022 | 9/12/2022 | 5/31/2022 | 6400 | 5308 | 5308
31 | R440 | STATEN ISLAND TECHNICAL HS - R | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 5/31/2022 | 11/25/2022 | 8/31/2022 | 28800 | 21229 | 21229
31 | R445 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Scope | Complete | 8/5/2020 | 12/4/2020 | 3/1/2021 | 85860 | 40881 | 40881
31 | R445 | PORT RICHMOND HS - R | SCA CIP | COVID VENTILATION / COVID CLIMATE CONTROL | Design | Complete | 3/3/2021 | 8/13/2021 | 1/24/2022 | 429300 | 379259 | 304385
31 | R450 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | Scope | Complete | 8/26/2020 | 12/24/2020 | 4/27/2021 | 36280 | 108372 | 108372
31 | R450 | CURTIS HS - STATEN ISLAND | SCA CIP | COVID VENTILATION | Design | Complete | 5/25/2021 | 10/19/2021 | 11/8/2021 | 181400 | 351083 | 308323
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | FULL PROGRAM ACCESSIBILITY / LOW VOLTAGE ELECTRICAL SYSTEMS | Scope | Complete | 3/2/2022 | 7/15/2022 | 1/3/2023 | 117350 | 134324 | 134324
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EXTERIOR MASONRY - PERM FIX FOR RED DOT 131992 / EXTERIOR DOORS | Scope | Complete | 10/20/2022 | 3/10/2023 | 12/1/2023 | 103957 | 153669 | 153669
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | EMERGENCY GENERATOR | Scope | Complete | 3/27/2024 | 7/29/2024 | 3/27/2024 | 47368 | 26166 | 1035
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Scope | Complete | 2/27/2018 | 1/6/2020 | 1/3/2020 | 135212 | 242224 | 242224
31 | R455 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | WATER INFILTRATION IN OIL TANK ROOM / PLANYC CLIMATE CONTROL / PLANYC BOILER CONVERSION | Design | Complete | 1/8/2020 | 6/9/2020 | 6/30/2020 | 667839 | 1490380 | 903375
31 | R456 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | NEW FIELDHOUSE BUILDING | Scope | Complete | 3/2/2022 | 6/30/2022 | 1/3/2023 | 243495 | 210956 | 189753
31 | R456 | TOTTENVILLE HS - STATEN ISLAND | SCA CIP | NEW FIELDHOUSE BUILDING | Design | Complete | 1/10/2023 | 6/12/2023 | 5/14/2024 | 1217475 | 480161 | 431882
31 | R461 | SUSAN E. WAGNER HS - STATEN ISLAND | SCA CIP RESOA | FY20 RESO A FIELD UPGRADE | Design | Complete | 1/14/2022 | 6/16/2022 | 5/13/2022 | 280864 | 184490 | 184490
31 | R470 | CONCORD HS - R | SCA CIP RESOA | FY22 RESO A (MA) CULINARY KITCHEN / PATH OF TRAVEL RESO A (MA) CULINARY KITCHEN | Design | Complete | 1/31/2023 | 5/31/2023 | 2/13/2023 | 240001 | 124809 | 121800
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/14/2021 | 11/12/2021 | 7/30/2021 | 3795 | 7388 | 7388
31 | R600 | RALPH R. MCKEE CAREER AND TECHNICAL EDUCATION HS - R | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/30/2021 | 1/28/2022 | 12/29/2021 | 17080 | 29552 | 29552
31 | R722 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | Scope | Complete | 4/7/2022 | 4/7/2022 | 4/7/2022 | 95738 | 105970 | 101836
31 | R722 | P.S. 722 (OTC) - STATEN ISLAND | SCA CIP | DEMOLITION | Design | Complete | 5/13/2022 | 11/15/2022 | 11/14/2022 | 478689 | 220646 | 186084
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | Scope | Complete | 10/2/2023 | 2/13/2024 | 11/9/2023 | 15600 | 20462 | 3702
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | CLOCK TOWER REPAIR @ R829 PERMANENT FIX | Design | Complete | 11/15/2023 | 4/18/2024 | 3/7/2024 | 70200 | 62718 | 14807
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | Scope | Complete | 3/29/2022 | 7/27/2022 | 4/13/2022 | 1600 | 3556 | 3556
31 | R829 | P.S. 65 - STATEN ISLAND | SCA CIP | IPDVS FULL CAMERA UPGRADE | Design | Complete | 4/13/2022 | 10/6/2022 | 7/20/2022 | 7200 | 14221 | 14221
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | Scope | Complete | 7/22/2019 | 12/6/2019 | 11/26/2019 | 58970 | 80118 | 80118
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP | WINDOWS / ROOFS | Design | Complete | 11/26/2019 | 4/29/2020 | 6/30/2020 | 294850 | 296017 | 258451
31 | R831 | P.S. 74 - STATEN ISLAND | SCA CIP RESOA | FY15 RESO A PLAYGROUND REDEVELOPMENT | Design | Complete | 5/11/2016 | 9/26/2016 | 9/2/2016 | 32198 | 52114 | 52114
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | OTHER TEMP STRUCTURE REMOVAL/PLAYGROUND REDEVELOPMENT | Scope | Complete | 3/10/2023 | 6/8/2023 | 7/5/2023 | 16559 | 31734 | 31734
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 5/11/2022 | 9/9/2022 | 6/7/2022 | 3340 | 4537 | 4537
31 | R840 | THE DAVID MARQUIS SCHOOL OF THE ARTS - STATEN ISLAND | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 6/7/2022 | 12/2/2022 | 8/31/2022 | 15030 | 18145 | 18145
31 | R844 | P.S. 36 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Scope | Complete | 3/9/2021 | 7/22/2021 | 11/22/2021 | 53051 | 151396 | 151197
31 | R844 | P.S. 36 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Design | Complete | 11/23/2021 | 4/27/2022 | 4/27/2022 | 249126 | 212957 | 212957
31 | R844 | P.S. 36 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | Construction | Complete | 7/20/2022 | 7/18/2024 | 6/7/2024 | 4210286 | 4495871 | 4266184
31 | R844 | P.S. 36 - STATEN ISLAND | SCA CIP | FLOOD ELIMINATION / PARAPETS / EXTERIOR MASONRY / ROOFS | CM,F&E | Complete | 7/20/2022 | 7/18/2024 | 6/7/2024 | 492316 | 399692 | 389299
31 | R861 | P.S. 861 - STATEN ISLAND | SCA CIP RESOA | FY21 RESO A PLAYGROUND UPGRADE | Design | Complete | 2/17/2022 | 7/5/2022 | 5/11/2022 | 21000 | 34494 | 29458
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | Scope | Complete | 1/31/2019 | 6/3/2019 | 10/12/2022 | 271750 | 232023 | 231873
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | HVAC UPGRADES / EMERGENCY GENERATOR REPLACEMENT / VENTILATION / BMS UPGRADE | Design | Complete | 10/19/2022 | 3/24/2023 | 9/11/2023 | 1358750 | 1148533 | 658463
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Scope | Complete | 6/29/2023 | 10/30/2023 | 10/10/2023 | 18500 | 15840 | 15840
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | WALK-IN REFRIGERATORS AND FREEZERS | Design | Complete | 10/11/2023 | 3/12/2024 | 2/15/2024 | 83250 | 88601 | 60971
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | REINFORCING SUPPORT ELEMENTS | Scope | Complete | 7/18/2023 | 12/4/2023 | 11/14/2023 | 20629 | 33462 | 33462
31 | R880 | P.S. 80 - STATEN ISLAND | SCA CIP | REINFORCING SUPPORT ELEMENTS | Design | Complete | 11/24/2023 | 4/26/2024 | 4/30/2024 | 103147 | 81245 | 71982
31 | R884 | R373 SPED - STATEN ISLAND | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 3/5/2021 | 7/20/2021 | 7/27/2021 | 43048 | 70663 | 70663
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Scope | Complete | 4/8/2021 | 8/23/2021 | 10/18/2021 | 139471 | 153301 | 150726
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY | Design | Complete | 10/26/2021 | 4/15/2022 | 8/4/2023 | 697357 | 441136 | 377275
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Scope | Complete | 4/9/2021 | 9/9/2021 | 7/1/2021 | 78996 | 81029 | 81029
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | PLANYC BOILER CONVERSION / PLANYC CLIMATE CONTROL | Design | Complete | 7/14/2021 | 12/15/2021 | 11/18/2021 | 394980 | 444548 | 361946
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / ROOFTOP EXHAUST FAN REPLACEMENT | Scope | Complete | 5/18/2021 | 10/1/2021 | 8/3/2022 | 136225 | 211448 | 199079
32 | K045 | P.S. 45 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / ROOFTOP EXHAUST FAN REPLACEMENT | Design | Complete | 9/13/2022 | 2/16/2023 | 3/30/2023 | 681124 | 661893 | 391880
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Scope | Complete | 7/1/2022 | 11/17/2022 | 2/28/2023 | 59136 | 149264 | 147061
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP | ROOFS / EXTERIOR MASONRY / FLOOD ELIMINATION | Design | Complete | 3/9/2023 | 8/9/2023 | 8/25/2023 | 292443 | 295387 | 275658
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | Design | Complete | 3/3/2023 | 7/6/2023 | 3/20/2023 | 39000 | 44423 | 40052
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | Construction | Complete | 7/21/2023 | 6/14/2024 | 9/19/2024 | 572000 | 478092 | 297196
32 | K086 | P.S. 86 - BROOKLYN | SCA CIP RESOA | PATH OF TRAVEL RESO A ROOM CONVERSION / FY21 RESO A ROOM CONVERSION | CM,F&E | Complete | 7/21/2023 | 6/14/2024 | 9/19/2024 | 39000 | 52806 | 41000
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Scope | Complete | 6/12/2023 | 10/27/2023 | 11/24/2023 | 123700 | 258084 | 237346
32 | K106 | P.S. 106 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / FLOOD ELIMINATION / ROOFS | Design | Complete | 12/6/2023 | 5/8/2024 | 5/3/2024 | 618501 | 512748 | 389287
32 | K111 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Scope | Complete | 7/11/2023 | 11/27/2023 | 11/14/2023 | 82281 | 86148 | 86147
32 | K111 | I.S. 349 - BROOKLYN | SCA CIP | ROOFS / WINDOWS / EXTERIOR MASONRY | Design | Complete | 11/15/2023 | 4/18/2024 | 4/26/2024 | 408683 | 430144 | 288605
32 | K123 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | Scope | Complete | 3/26/2021 | 8/10/2021 | 11/2/2021 | 175410 | 167551 | 167551
32 | K123 | P.S. 123 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / MECHANICAL VENTILATION | Design | Complete | 11/3/2021 | 4/25/2022 | 10/5/2022 | 877050 | 574878 | 463137
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | Scope | Complete | 4/7/2021 | 8/6/2021 | 10/26/2021 | 11796 | 20663 | 20663
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | CAFETERIA FLOOR | Design | Complete | 11/1/2021 | 3/22/2022 | 3/4/2022 | 58979 | 103360 | 94185
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 8/7/2023 | 12/7/2023 | 9/18/2023 | 5000 | 5995 | 5995
32 | K145 | P.S. 145 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 9/18/2023 | 3/18/2024 | 11/15/2023 | 22500 | 23982 | 23982
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | Scope | Complete | 11/18/2019 | 4/6/2020 | 3/10/2020 | 164682 | 231070 | 230893
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | EXTERIOR MASONRY / PAVED AREA- CONCRETE / PARAPETS / ROOFS / WINDOWS | Design | Complete | 3/10/2020 | 8/7/2020 | 5/28/2020 | 814277 | 610416 | 606434
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 7/20/2023 | 11/20/2023 | 8/2/2023 | 4700 | 5881 | 5881
32 | K151 | P.S. 151 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 8/2/2023 | 1/31/2024 | 11/15/2023 | 21150 | 23528 | 23528
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Scope | Complete | 6/3/2020 | 10/1/2020 | 7/2/2020 | 3266 | 5566 | 5566
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | IPDVS CAMERA INSTALLATION | Design | Complete | 7/2/2020 | 12/30/2020 | 5/19/2021 | 14697 | 22267 | 22267
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Scope | Complete | 1/24/2023 | 11/30/2023 | 12/27/2023 | 368600 | 340338 | 339013
32 | K162 | I.S. 162 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / ELECTRIFICATION/HEAT PUMP SYSTEMS / WINDOWS / ELECTRICAL SERVICE UPGRADE | Design | Complete | 1/12/2024 | 10/3/2024 | 5/14/2024 | 1843001 | 1162576 | 1047120
32 | K274 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | Scope | Complete | 1/22/2020 | 1/7/2022 | 12/15/2021 | 16909 | 65260 | 65180
32 | K274 | P.S. 274 - BROOKLYN | SCA CIP | PLAYGROUND REDEVELOPMENT / PATH OF TRAVEL BASKETBALL PLAY YARD RENOVATION | Design | Complete | 12/16/2021 | 4/19/2022 | 3/18/2022 | 76093 | 121835 | 93219
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Scope | Complete | 10/8/2021 | 11/10/2022 | 1/25/2023 | 72818 | 112986 | 112986
32 | K291 | I.S. 291 - BROOKLYN | SCA CIP | IDA FLOOD ELIMINATION / PATH OF TRAVEL NON-IDA FLOOD ELIMINATION / IDA INTERIOR SPACES | Design | Complete | 1/26/2023 | 5/25/2023 | 6/9/2023 | 362617 | 379859 | 297204
32 | K299 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Scope | Complete | 4/5/2021 | 8/18/2021 | 8/13/2021 | 133519 | 131528 | 131528
32 | K299 | P.S. 299 - BROOKLYN | SCA CIP | FULL PROGRAM ACCESSIBILITY / PA SYSTEM REPLACEMENT | Design | Complete | 9/15/2021 | 3/8/2022 | 9/8/2022 | 661849 | 558615 | 433530
32 | K383 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 6/3/2022 | 10/3/2022 | 9/1/2022 | 3560 | 2717 | 2717
32 | K383 | I.S. 383 - BROOKLYN | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 9/1/2022 | 3/3/2023 | 3/2/2023 | 16020 | 10869 | 10869
32 | K384 | P.S. 384 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / FLOOD ELIMINATION / PARAPETS | Scope | Complete | 3/5/2019 | 7/5/2019 | 1/26/2022 | 118641 | 2659 | 2659
32 | K384 | P.S. 384 - BROOKLYN | SCA CIP | ROOF REPLACEMENT / FLOOD ELIMINATION / PARAPETS | Design | Complete | 12/29/2022 | 7/5/2023 | 12/13/2023 | 568100 | 165095 | 99747
32 | K799 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | Scope | Complete | 8/10/2015 | 12/28/2015 | 3/28/2016 | 103442 | 91741 | 91741
32 | K799 | ALC - BROOKLYN CHOICES | SCA CIP | EXTERIOR MASONRY / WINDOWS / PARAPETS / ROOFS | Design | Complete | 6/24/2016 | 11/28/2016 | 2/7/2017 | 404279 | 645179 | 616941
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | Scope | Complete | 6/18/2013 | 12/2/2013 | 11/18/2013 | 130880 | 130183 | 130183
32 | K865 | BUSHWICK LEADERS - K | SCA CIP | CERTIFICATE OF OCCUPANCY / FIRE SPRINKLER SYSTEM | Design | Complete | 11/19/2013 | 5/22/2014 | 5/14/2020 | 654400 | 1869689 | 1622287
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | Scope | Complete | 3/10/2023 | 7/25/2023 | 3/15/2023 | 4720 | 2062 | 2062
32 | K913 | EBC HS FOR PUB. SERV. - BUSHWICK-K | SCA CIP | IPDVS INSTALLATIONS | Design | Complete | 3/15/2023 | 9/8/2023 | 5/2/2023 | 21240 | 8247 | 8247
32 | KBRV | BETHESDA DAY CARE CENTER OF BROOKLYN | SCA CIP | ACS EARLY LEARN LEASE IMPROVEMENT | Scope | Complete | 4/8/2021 | 8/9/2021 | 7/19/2021 | 2522 | 13929 | 13929
32 | KBSG | 200 CENTRAL AVENUE DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Scope | Complete | 4/12/2021 | 8/11/2021 | 7/19/2021 | 4950 | 15471 | 15471
32 | KBSG | 200 CENTRAL AVENUE DAY CARE CENTER | SCA CIP | ACS EARLY LEARN LEASE RENEWAL | Design | Complete | 1/3/2022 | 5/3/2022 | 1/6/2023 | 22277 | 29044 | 7574